P119856 | Kazakhstan Dvelopment Policy Loan | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory |  | Satisfactory | Modest | http://documents.worldbank.org/curated/en/691961474664201955/text/000020051-20140625154923.txt | http://documents.worldbank.org/curated/en/691961474664201955/pdf/000020051-20140625154923.pdf | Experience with the DPL suggests that a single tranche DPL can yield significant benefits, in the context of a quick response to a crisis and obvious short-term issues, as the ICR states. Such benefits will depend on the government and the Bank having a sound, long-term relationship and the governmentâ€™s willingness to undertake significant actions. The DPL also illustrates that support of the Bank can be helpful in international markets and address domestic political concerns as noted in the ICR. At the same time, the experience with the DPL suggests it is less appropriate to deal with longer-term policies and the associated changes in behavior that are needed to make them effective. Programmatic DPLs may help, but they make take too long to prepare and reach agreement with the Government, relative to the demands imposed by a crisis.
P119872 | Nigeria Statistics Development Program (NSDP) | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | RETF | IPF | 2011 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/202721468190450334/text/ICRR14745-P119872-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/202721468190450334/pdf/ICRR14745-P119872-Box393191B-PUBLIC.pdf | The ICR (pp. 20-21) identifies 21 lessons, mostly related to project design, arrangement, coordination, implementation, and sustainability. Among these lessons, IEG adapts here three salient lessons and also provides one lesson of its own.For a multi-agency project, clarity of the functions and budget of an oversight committee is important to provide guidance and resources for managing the project. This project identified principal members of a Technical Committee, including senior officials at the Ministry of Finance, NBS and NPoPC, but there is little evidence that this committee provided effective guidance for project implementation. The operating cost to organize this committee, including field visits, was unclear, and this might have partly undermined the activities of this committee. Monitoring reports, which were supposed to be the basis of decisions at the Technical Committee, also did not provide a solid foundation for drawing specific guidance.Sustainability of a project requires its strategy to be supported by government funding. In this case, government support for the NSDS did not materialize as planned. Donor support needs to be considered as a supplementary investment, rather than as a substitute for government budget, and failure to do so can lead to serious consequences in the long-term.In-country Bank experts can strengthen project implementation when a project requires highly technical knowledge for supervision, coordination among multiple agencies, and/or strong support for an implementing agency that is not familiar with Bank procedures. This project's ICR emphasizes that the well-qualified statistician based in the Bank country office facilitated project implementation. The in-country financial management specialist and procurement specialist were also helpful when the implementing agencies, particularly NPoPC, which had no experience with Bank-funded projects, experienced challenges with disbursement and procurement.Clear definitions and scope of project development objectives critically affect evaluability. This project's objective was straightforward, but the definition of key terms, such as â€œreliable statistics,â€ was unclear. The ICR also provides information that project developed capacity for the six participating states to produce reliable statistics, but capacity development and actual production of reliable statistics are different, and the statement of objectives requires careful consideration of existing capacity, budget, and duration of the project.
P119892 | Gambia Emergency Agriculture Production Project | Western and Central Africa | Gambia, The | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/477111474571574403/text/000020051-20140625230738.txt | http://documents.worldbank.org/curated/en/477111474571574403/pdf/000020051-20140625230738.pdf | The ICR highlights several lessons learned, among others (ICR p. 20-21, Â§Â§ 65-71):Involving NGOs in the distribution of inputs was vital to ensure transparency under the Project. Adequate implementation capacity is crucial for timely implementation of emergency projects with short implementation periods. Clearly defined roles for the Bank and the EU delegation, especially at country level, improves collaboration between the partners in these types of EU funded TF arrangements. The administrative agreement should clearly define the reporting chain and the responsibilities of the Bank. Other lessons would be:Involvement of local government and organizational structures such as regional and village chiefs, village-level councils, and village storage management committees, facilitated broad-based participation both during the project and in the governance of project investments (i.e. the storage facilities).
P119917 | BF-Reproductive Health Project (FY12) | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2018 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/357861580233474581/text/Burkina-Faso-BF-Reproductive-Health-Project-FY12.txt | http://documents.worldbank.org/curated/en/357861580233474581/pdf/Burkina-Faso-BF-Reproductive-Health-Project-FY12.pdf | Although the lessons in the ICR are well-grounded in the project experience, rather than select from them, this review offers adifferent lesson that reflects on the difficulty in evaluation posed by a discontinuity in the performance of a reformprogram.If a change in policy undermines implementation of an RBF pilot before it is completed, the evaluationplan may need to be reconsidered. The RBF pilot in Burkina Faso showed promising results in its initial years, when theMOH was strongly committed to the approach, the competent RBF technical unit was well placed in the ministry to influencedecisions, and there was adequate funding. The change in these circumstances in 2016 undermined implementation of the RBF andaffected the trajectory of the results of the project. The Impact Evaluation took place a year later, in 2017. The final level ofachievements were the result of both the promising initial years of the program when it functioned as designed, and thedisruptions. It would have been useful if the design of the evaluation could have tried to disentangle the two.
P119939 | Talimarjan Transmission Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/886971498746793731/text/ICRR-Disclosable-P119939-06-29-2017-1498746774512.txt | http://documents.worldbank.org/curated/en/886971498746793731/pdf/ICRR-Disclosable-P119939-06-29-2017-1498746774512.pdf | Two lessons are derived from the ICR by IEG. Advance procurement could help ensure the efficiency ofproject implementation when project effectiveness is delayed due to government procedures. Under this project, thegovernment of Uzbekistan and World Bank signed a Memorandum of Understanding (MOU) to expedite the internal preparation proceduresand advance procurement processes. When loan became effective in November 2011, four main supply contracts out ofseven and two consultancy packages had already been signed. This contributed to the completion of major project investmentactivitiesahead of schedule. It is critical for the Bank to aim at embedding developmentoutcomes and impact in the project objective and ME design, in particular in countries with good data availability andcapacity. This projects objectiveto improve thereliability of electricityin South-WesternUzbekistandid not capture the development outcomes on residential and business consumersas the targetgroup. The ME of this project was designed to monitor the output-level data whichhad already beenroutinely and easily collected by the utility.
P120005 | Gas and Oil Capacity Building Project | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/195561552665445123/text/Ghana-GH-Gas-and-Oil-Capacity-Building-Project.txt | http://documents.worldbank.org/curated/en/195561552665445123/pdf/Ghana-GH-Gas-and-Oil-Capacity-Building-Project.pdf | IEG derives the following lessons, drawn from the ICR:- The design of technicalassistance projects calls for adequate attention to be paid to the question of institutional managerial capacity and competence.Shortcomings in this respect at both the individual institutions and at the supervising institution (COTVET in this project), ledto problems and delays in the implementation of the vocational component.- Equipment specifications: Inadequatespecification of the major equipment purchases canresult in major implementation challenges down the line, as occurred in thecurrent project. It is important for project design to pay specific attention to this aspect.
P120014 | KE Electricity Modernization Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061824113022861/text/P120014-121a12f3-2483-4a25-9a89-f71731e6df5f.txt | https://documents.worldbank.org/curated/en/099061824113022861/pdf/P120014-121a12f3-2483-4a25-9a89-f71731e6df5f.pdf | This review has drawn three lessons based on the information in the ICR.In a project with the objective toimprove the reliability and efficiency of electricity supply, the use of the system-wide indicators can prevent the accuratemeasurement of the projects impact on service delivery. The results framework included SAIDI and commercial lossindicators to measure the reductions in the average duration of supply interruptions and the improvement in the bill collection(resulting in a reduction in commercial losses). Although the project delivered all outputs related to the achievement of theseoutcomes, the achievement of the indicators showed a worsening both in reliability and commercial losses. Because these twoindicators measured system-wide interruptions and commercial losses (the latter estimated as a percentage of total losses), theywere irrelevant and insufficient to measure the projects impact. This shortcoming made it difficult to assess theachievement of the project objectives.In a complex political-economy environment, a standalone investment projectcan be less effective in achieving sector-wide governance reforms. The project aimed at improving the financial situationof KPLC through the implementation of advanced metering technologies to decrease commercial losses and the issuance of a US$200million IDA guarantee to refinance the costly and short-tenure debt of KPLC. The project successfully delivered all related outputs(except installing meters to high consumers which were replaced by SMEs). However, being an entity, the majority of which isowned by the state, the KPLC is affected by political decisions and interference. The political decisions to delay tariffadjustment and increase the allocation to low consumption households resulted in lower revenues for the KPLC. Thegovernments aggressive goal of achieving universal access by 2026 also stretched the finances of the utility. Theorganizational instability caused by frequent changes of the senior management of the KPLC adversely affected the implementation ofproject activities and later the sustainability of the outcomes.Compensating rural communities in-kind(i.e., as infrastructure investments) can be critical in successful implementation of the project activities in remotelocations. The implementation of mini-grid projects in rural areas required the acquisition of unregistered communityland. The related safeguard policy required monetary compensation, but the communities requested in-kind compensation in the formof infrastructure investment. As the ICR (p.28) notes, there is much ambiguity in the applicable legislation on what kind ofcompensations are required for a particular compensation. The project team worked out a plan that resulted in the payment ofin-kind compensation to rural communities. After that, the project implementation improved in rural areas but because ofinsufficient capacity of the implementing agency, poor contractor performance, and insufficient supervision because of the remotelocation of the project sites, the project closed with four mini-grids completed and three ongoing.
P120026 | GH:Sustainable Rural Water & Sanit Serv | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/233801624624008142/text/Ghana-GH-Sustainable-Rural-Water-Sanit-Serv.txt | http://documents.worldbank.org/curated/en/233801624624008142/pdf/Ghana-GH-Sustainable-Rural-Water-Sanit-Serv.pdf | The ICR draws the following lessons from the experience of implementing this project with some adaptation oflanguage.1. Projects need to be prepared with due diligence to avoid implementation delays. In thisproject, the costs of water supply systems were underestimated due to technical considerations,and there was less thananticipated demand for sanitation services during the initial years. These issues were eventually resolved through the AF for theproject. The lesson is that rigorous project preparation and pre-project due diligence is required for avoiding implementationdelays.2. Technology improvements and innovative methods could help enhance access to affordable and sustainablewater supply and sanitation systems. Small town piped systems in Ghana had used electrical systems. For a typical smalltown power system, the cost of power supply could represent 50 percent of the operational cost. To address this issue, the projectintroduced solar panels (instead of the grid powered systems) forimproving the operational efficiency of the water systems.Likewise, for sanitation issues, the project pioneered plastic latrine slabs to assist low income communities in the constructionof household toilets.3. An effective fee collection system for full cost recovery is essential for thelong-term sustainability of the water systems. The beneficiary assessment in this project noted that in some areas thedefault rate of water users was significantly higher for water systems that used a monthly rate for water tariffs when comparedwith a Pay-As-You-Fetch modality. These difficulties were addressed in this project through installing pre-paid smart meters forstandpipes.4. Behavior change communication strategies delivered by relevant stakeholders, coupled with materialsupport, can help in achieving open defecation free status. In this project, there wasdemand for household toilets.The limited results were due to inadequate consultants and targeted communities. This issue was resolved in this project through amore intensive outreach by the District Assemblies and the targeted communities and providing direct material support to the ruralhouseholds.
P120028 | Community Agricultural Resource Management and Competitiveness Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2017 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/377591498659778559/text/ICRR-Disclosable-P120028-06-28-2017-1498659762601.txt | http://documents.worldbank.org/curated/en/377591498659778559/pdf/ICRR-Disclosable-P120028-06-28-2017-1498659762601.pdf | 1. Theestablishment and empowerment oflocal communitiescan succeedin improvingcommunalmanagement even in the often challengingcase ofextensive pasture/livestock production systems. In the caseofCARMAC, thePasture User Associations (PUAs) were an important institutional innovation for stimulating collectivemanagement of communal pastures in mountainous regions. The PUAs were established as cooperatives and were mandated tocollect pasture use fees and allocate them for various important uses including: (i) to pay pasture rental income to the communitycouncil; (ii) toinvest in pasture and livestock production infrastructure; and, (iii) to maintain investments in pastureimprovements.2. Whenlocal communities are able to regulate grazing land use andare empowered to overcome incentive problems that often lead totragedy of the commons issues, recoveryofcommon propertynatural resourcescan be achieved within the lifetime of a single project. The quite rapidsuccess factors in the case of CARMAC seem to be related to: (i) identifying the pasture governance arrangements that were broadlyacceptable to rural communities; (ii) inclusive and participatory planning and decision-making to ensure equitable access toproject benefits (including women and youth); (iii) sound project design based on careful assessment of local conditions andinstitutional studies and experiences from relevant projects in Armenia, Central Asia region and others; (iv) existence ofopportunities for reducing grazing pressure on traditional communal pastures without reducing stock numbers through newinfrastructure to enable access to remote pastures (not always available); (v) effective project management; (vi) high level ofcommitment and policy support from the Government of Armenia.3. Well-targeted solutionsincommunity natural resource management that addresslimitingconstraints inacomplexproductionsystem(including service delivery, marketing andincome diversificationopportunities)can enable communities torealize higher economicgains andhence strengthenincentivesfor communalmanagement.In the case ofCARMAC, the targeted interventionsaddressing both pasture management and animalhealthwereable tobring quiterapid improvements in livelihoods.4. Delays inproject implementation can be reduced or avoided in community-based natural resource management projectsif aflexibleapproach is used inproject design where learning and adjustmentto local conditions is oftenrequired. In the CARMAC case, while theinitial design required communities to provide 50% co-financing foragricultural equipment and machinery (which was not well-received by communities and difficult to meet), delays wereavoidedmainlybecause anNGO(Heifer International) was able tobridge thegaps.5. Along term phased approach may be needed in a community-based natural resourcemanagement projectto consolidatepromising initial gains andto build a sustainablemodel for a viablepasture/livestock livelihood systems.In the caseof CARMAC,sustainability will depend on:(i)efficient, transparent and participatory governance of PUAs as institutions for collective action andfor continued ability tosustain and institutionalize local approaches for regulating grazing pressure and preventing free-riding and open-access; (ii)institutional and technical capacity of PUAs for the development of commercially-oriented and sustainable livestock productionsystems; (iii) financial sustainability of the cooperative pasture management model which was built on fee-based community servicesand new income resources; and (iv) market access and adequate producer prices of milk and meat.The follow-on CARMAC 2project, whichbuilds on the success of CARMAC,will need to consider theselessons to sustain thegains madeduring the first phase.
P120052 | Emergency Support to Enhance Food Security (ESEFS) | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2012 | 2014 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/688391475083981837/text/000020051-20140625194743.txt | http://documents.worldbank.org/curated/en/688391475083981837/pdf/000020051-20140625194743.pdf | The following lessons are taken from the ICR with some adaptation of language:Obstructive and cumbersome procurement policies and procedures at the central level will likely cancel out the best efforts to introduce greater efficiency and celerity at project level. Such policies and procedures are best tackled as part of a Government-wide reform effort since they affect all externally-financed projects.The involvement of local communities, backed by an appropriate administrative structure, will support the sustainability of project-financed facilities.In this case, local committees of representatives of farmer organizations and municipalities played an important role in the management and maintenance of storage facilities, drying areas and irrigation infrastructure.The limited involvement of women in some of the projectâ€™s activities was, at least in part, the result of a lack of effective and visible gender mainstreaming in project design.Input subsidies are easy to initiate but difficult to end. They are, however, likely to be unsustainable because of budgetary constraints. A sound market-based system needs to be pursued as soon as possible.
P120110 | Cholera Emergency Response Project | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/272281474940756997/text/000012394-20150312111515.txt | http://documents.worldbank.org/curated/en/272281474940756997/pdf/000012394-20150312111515.pdf | The ICR (p. 20) identifies several valuable lessons, including:In the case of an emergency situation and weak local government capacity, it is important to find a way to respond quickly to urgent needs but also to involve the local government. At the beginning of this project, NGOs were hired for project implementation, and the MSPP felt it was not adequately consulted, which may have diminished its stewardship role. The ICR does not indicate whether local government is appropriately integrated in the follow-on operation.If emergency situations such as cholera outbreaks are linked to a seasonal cycle, it is important to be proactive and train health workers before potential outbreaks might occur in order to raise awareness within communities.M&E is critical for gaining control of epidemics, tracking progress, and making informed decisions. If not existent, it is critical that a strong information system is developed at the beginning of project implementation and counterparts trained in a common methodology, data collection and analysis.
P120125 | Strengthening Auditor General's Ofice | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2011 | 2016 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/702151506351176313/text/ICRR-Disclosable-P120125-09-25-2017-1506351165832.txt | http://documents.worldbank.org/curated/en/702151506351176313/pdf/ICRR-Disclosable-P120125-09-25-2017-1506351165832.pdf | The following lessons are taken from the ICR, with some revisions to the wording (ICR, p. 20-21):The ICRoffers useful lessons for Bank teams involved in institutional and capacity development of supreme audit institutions (SAIs). Theyare asfollows: The WBG would need to use all instruments at its disposal to make sure necessary reforms are achieved. For example, apolicy lending operation in combination with this TA could have helped to push a key reform, i.e. passage of the new Audit Bill; When an implementing agency has limited capacity and knowledge of Bank requirements (in procurement, in thiscase), training and hands-on support needs to be provided at project start-up and in the first year of implementation. Addedsupervision and implementation support must be built into the project supervision budget. Agreed procurement methodswouldneedtake into consideration the implementing agencys capacity. Deliverable-based contracts versus time-based contractsprovide better incentive to deliver. A well thought out and clearly defined results framework with measurableoutputs, outcomes, and key indicators under control of the project can be important to successful project implementation andmeasurement of achievements. However, in multi-faceted PFM reform programs, where different bodies must play a role, implementingagencies need the freedom to innovate and improvise as unexpected challenges emerge. Only a realistic numberof priority activities should be selected to focus the project teams attention and help direct efforts into completing theplanned objectives within the original time-frame. For example, selecting the most prioritized audit types to be part of the pilot,such as compliance and financial audit would have probably helped to achieve the objectives within the original projectduration. Twinning with a suitably-selected peer institution that combines training with TA, and allows forflexibility on both sides is a good approach for transferring knowledge and expertise. The twinning arrangement with SAI, Indiafollowed the process for a beneficial twinning arrangement and helped the project to proceed with pilot audits and develop along-term relationship between the twoinstitutions.IEG adds an additional lesson:Reforming audit aspart of overall PFM improvements requires continuous support over the long term from the Bank and other development partners tosustain and deepen achievements.
P120125 | Strengthening Auditor General's Ofice | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2011 | 2016 | 2020 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/843621582910259268/text/Bangladesh-Strengthening-Public-Expenditure-Management-Program-Strengthening-Auditor-General-s-Office.txt | http://documents.worldbank.org/curated/en/843621582910259268/pdf/Bangladesh-Strengthening-Public-Expenditure-Management-Program-Strengthening-Auditor-General-s-Office.pdf | 3. Lessons 3.1 The project offers the following lessons\. â€¢ Inadequate assessment of political economy risks to key reforms contributed to unrealistically ambitious project design and targets, leading to shortcomings in implementation. The World Bank did not adequately articulate the political economy risks to enactment of the audit bill. These risks were well known during project design, given past resistance from vested interests and experience with previous budget support operations in Bangladesh. Although there was initial support from the MOF for the proposed audit bill, the World Bank did not clearly flag the significant possibility that passage of the bill would be blocked by vested interests (in this case, in the wake of changes in government leadership and in Parliament). A clearer articulation of the degree and nature of risk would have pointed, ex ante, to the need to articulate either an effective mitigation strategy to reduce the risk that the bill would not be approved or would have suggested the need for a different approach or contingency plan. Without such mitigating measures or contingency plans in place, the project's implementation was delayed, which led to its restructuring and a less-thansatisfactory outcome. â€¢ The project sought to implement a politically sensitive policy reform through the use of technical assistance. The objective could have been more effectively pursued through a different instrument, possibly a development policy operation. The project was designed as a Technical Assistance Loan suitable for capacity building and policy implementation rather than a policy reform. Although capacity building was needed to build OCAG's capacity to undertake 11 quality audits of adequate scope, it was not an effective way of achieving the related policy reform (that is, passage of the new audit bill) necessary to sustainably enhance OCAG's ability meet the project's accountability objective. â€¢ The ability for a pilot to effectively demonstrate the potential of a new way of doing business requires commitment to a systematic assessment of the pilot experience and the dissemination of lessons learned. In the case of this project, pilot audits were undertaken to test, in the absence of a new audit law, the viability of expanding the scope of OCAG's audits (beyond compliance audit) using ISSAI-compliant methodology and improving the uptake of the audit's recommendations by the executive branch. However, no upfront commitment or mechanism was in place to monitor and assess what worked and did not work with the pilots. The absence of a mechanism to learn from the pilots diminished their potential to inform future support for OCAG.
P120134 | MX DPL Adaptation to Climate Change in the Water Sector | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Water | IBRD | DPF | 2010 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/615601474501267172/text/000020051-20140626115730.txt | http://documents.worldbank.org/curated/en/615601474501267172/pdf/000020051-20140626115730.pdf | The ICR presents ten â€œlessons,â€ which tend to be presented as recommendations rather than lessons. Four are selected and presented below, with modification in order to put them in the form of lessons.1. A thematic DPL is more likely to be successfully implemented when its policy content and prior actions reflect broad public consultation as well as the Borrowerâ€™s own program and priorities. This process should include public consultation with sector-specific stakeholders at local and national levels, which was carried out reasonably well in this program.2. Sustained Bank engagement with a Borrower over the years with a range of instruments is important for the effective support of thematic reform processes over the medium and long term. Such instruments can include DPLs, investment lending, credit enhancement, GEF grants and other grants, including from Trust Funds. More specialized instruments in the climate change area include Clean Technology Fund concessional financing, catastrophe risk management and advisory services. 3. The economy-wide institutional weaknesses that limit a lead implementing agencyâ€™s effectiveness in managing sector resources also limit its effectiveness in managing a climate change adaptation agenda. An example is protracted legal review procedures, which can limit the impact of an implementing agency's regulatory functions and jeopardize efficacy. This implies that the parties (e.g. the Bank and the Borrower) should thoroughly assess before or at program or project preparation any administrative and legislative clearance stages required and agree on a realistic time frame for implementation. 4. Bank policies regarding Technical Assistance Programs associated with DPLs can affect the effectiveness of reform implementation. This is especially true in countries where DPL-generated resources for complementary advice, analysis and training do not augment implementing agency budgets. Given the lower priority given in general by donors to aid for middle-income countries, the ability of Bank teams to secure grant resources for associated TA can be onerous and time-consuming. The complementary advice, analysis and training supported by grant funded TA can strengthen the case for DPL-associated policy reforms and provide a positive incentive for implementing agencies to actively participate.
P120139 | Pernambuco Rural Economic Inclusion | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2012 | 2020 | 2022 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099235005052225920/text/P12013904645ff01f095d902213faeeed6b.txt | http://documents.worldbank.org/curated/en/099235005052225920/pdf/P12013904645ff01f095d902213faeeed6b.pdf | The ICR (para 90-96) provided seven lessons. Some of them are summarized below by integrating the key factors duringimplementation (ICR, para 47-68) because they may provide lessons of interests for other rural developmentprojects.The Governments institutional reform at appraisal can critically affect its commitment andcompliance with the World Banks procedures. The State Program for Assistance to Small-Scale Producers (ProRural),which included the Project Management Unit (UGP), was transferred from the State Secretariat of Planning to the State Secretariatof Agriculture and Agrarian Reform (SARA) in 2012. SARA was culturally more connected to the States ruralparty-political system within which the Projects operational agenda and development objectives lost focus. The newProRuralleaderships low commitment in the project led to lax standards and questionable governance, which started toinfluence procurement and financial management decisions and overall progress starting around 2014.Repeatedtransitions of project leadership at the central level can critically affect the efficiency in project management. Theposition of ProRural Director was turned over 12 times from 2012 to 2020. The frequent, high level transitions delayed theprocurement and confirmation of managerial and technical staff. The already over-burdened ProRural team lacked leadership andqualified specialists. Excessive delays and bureaucracy in the UGP hindered the Territorial Management Units (UGTs) to receivetimely responses from the UGP on regional requests and eroded the autonomy of UGTs. This negatively affected progress monitoringbetween the RPOs, the UGTs, and the UGP. The Banks continuous efforts to exploit leadership transitions to energize progressacross multiple fronts saw modest upswings followed by further decline, contributing to the non-approval of further extension ofthe closing date beyond June 2020.The lack of support at the central level to strengthen local capacity to utilizeBusiness Plans (BPs) in the Local Productive Alliance model can result in inadequate institutionalization of the function.ProRural under-valued the importance of the BP as a decision-making and market development tool to support small ruralenterprises, resulting in the lack of the training and specialists to master and institutionalize this function. As a result, thecapacity gap in the local service providers to develop BPs and sub-projects that were linked to territorial strategies was notadequately filled. If inappropriate approach is used to reach out to Indigenous People (IP), then it may lead to their limited engagements with project activities. Under the project, of the rural households benefitingdirectly from project interventions, just 1 percent belonged to Indigenous People or Quilombola, not meeting the target of 5percent (ICR, page 37). This was due to the insufficiency in the qualified technicians to work with IP. Both the National IndianFoundation and the Pernambuco Agronomic Institute fell short in addressing IP demands for multi-disciplinary technical assistanceand training to prepare and implement sub-projects. The Borrowers Completion Report (2021) concludes that the productiveinclusion model was unsuitable for IP and Quilombolas in organizational, cultural, and technical terms, i.e., the overall approachto their participation in similar projects needs re-consideration (ICR, para 44).
P120161 | Second Integrated Sanitation and Sewerage Project - EG | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=100 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/907601574347297646/text/Egypt-Arab-Republic-of-EG-Integrated-Sanitation-Sew-Infra-2.txt | http://documents.worldbank.org/curated/en/907601574347297646/pdf/Egypt-Arab-Republic-of-EG-Integrated-Sanitation-Sew-Infra-2.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1)Lessons from prior experience need to be appropriately reflected in project design.Lessons from prior projects had highlighted the need for strong implementation arrangements. The implementation arrangements ofthis project (with two centralized implementing agencies) were clearly inappropriate,as demonstrated by the experience of theprior Bank financed project. This contributed to delays during implementation.(2)The projectscopeshould be based on a careful assessment of macroeconomic conditions at appraisal. The estimates ofcounterpartfunding for this project were clearly unrealistic, given that economic growth had stalled in the wake ofthe2007-2008 global financial crisis and economic growth was further expected to decline, in the wake of the unrest,following the January 2011 revolution. This risk could have been compartmentalized, by ensuring that the project could be scaleddown, if the Governments contribution was not realized.(3)Infrastructure investments aimed atimproving service delivery need to be complemented with activities aimed at strengthening the capacity of implementing agencies atappraisal. This project focused mainly on financing and building infrastructure, without a clear focus onstrengthening the capacity of water sanitation companies or sector reforms at the outset. Technical training, which aided inimproving project performance during the final years,was provided only during the latter years of implementation.
P120170 | Strengthening Social Resilience to Climate Change | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2012 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/458441468190186005/text/ICRR14637-P120170-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/458441468190186005/pdf/ICRR14637-P120170-Box393183B-PUBLIC.pdf | The ICR identified ten lessons, a number of which were framed in program-specific terms. IEG has selected five lessons of applicability to similar future operations and modified language that was specific to this DPL.(1) Sustained engagement on the part of the Bank is critical to effectively engage in reform processes over the medium and long term, particularly in such areas as environment and climate change. This engagement often requires the deployment by the Bank of a range of available financial instruments, including investment lending, Development Policy Loans as well as Clean Technology Fund (CTF) concessional financing, GEF and other grants. The Bankâ€™s program of financial and knowledge services can also include credit enhancement, hedging swaps, catastrophe risk management and advisory services. (2) Since virtually every socio-economic sector is affected by climate change and can affect climate change policies, the analytical framework will need to encompass a sufficiently wide range of sectors. For example, aside from environment, agriculture, forestry, urban, territorial and social development, the role of education in creating curricula that address climate change adaptation should be analyzed and appropriately modified.(3) The creation of stakeholder forums at national and subnational levels presents an opportunity to share information and generate feedback on adaptation measures. State, municipal and local community level consultative forums, both general and sector-specific, with significant civil society participation, can serve as mechanisms for generating feedback on the quality and sustainability of climate change adaptation tools and measures, providing a participatory feedback mechanism. (4) Prior actions should be limited to a few key policy and institutional reforms. Without such a focus, implementation by the Borrower and supervision by the Bank risk losing sight of the operationâ€™s priorities and its intended outcomes. (5) Given the innovative nature of the actions agreed, a Development Policy Loan may be an appropriate financing instrument. An objective like enhancing social resilience is based to a significant degree on innovative arrangements for policy actions and subsequent implementation. Because of this innovative characteristic, a stand-alone DPL (as opposed to a programmatic series DPL) may be a more appropriate approach, allowing for a greater degree of flexibility in policy experimentation.
P120198 | Norte Grande Road Infrastructure | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/869521600197659427/text/Argentina-AR-Norte-Grande-Road-Infrastructure.txt | http://documents.worldbank.org/curated/en/869521600197659427/pdf/Argentina-AR-Norte-Grande-Road-Infrastructure.pdf | Lessons drawn from the ICR, adapted by IEG: Project implementation units in projects that supportdecentralized levels of government need to include an institutional coordination mechanism to ensure active participation.The implementation of institutional activities suffered during project implementation.A coordinating mechanism (which wouldensure regular collaboration with the provincial governments), with a formal role in the implementation structure, could have beena platform for technical discussions and initiatives on institutional strengthening and contributed to a quicker absorption ofinstitutional strengthening resources. Civil works contracts in local currency need to includemechanisms to protect the public interest and contractors in periods of high inflation or currency devaluation. Thecurrency devaluationsaffected the retention funds maintained by the investor and were a disincentive for contractors torepair deficiencies during the guarantee period. Similar risk arose regarding the performance guarantees provided by contractorswhich lose their value in periods of devaluation (averaging a 30% devaluation throughout the loans period; theguarantees value in local currency fell around 70% in a 2 year contract). Rural roads projectscan significantly contribute to improving womens empowerment and access to economic opportunities by promoting theirparticipation in income generating activities, strengthening their leadership and life skills.The project experienceshows that by promoting womens active participation in the design andimplementation of infrastructure projects, theseprojects can be instrumental in broadening womens networks through their participation in community and women associationsand strengthening their agency.
P120211 | Norte Grande Water Infrastructure | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2019 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/697941607353299146/text/Argentina-Norte-Grande-Water-Infrastructure.txt | http://documents.worldbank.org/curated/en/697941607353299146/pdf/Argentina-Norte-Grande-Water-Infrastructure.pdf | The following main lessons were provided by the ICR (pages 30-31) and are presented here with some adaptation byIEG:Project design and preparation needs to explore partnership options with local NGOs and be guided byopportunities to involve the local community in a participative process. The effectiveness of the projectsinterventions was enhanced by active engagement with project beneficiaries and NGO partnerships. The implementation of theIndigenous Peoples Plan (IPP) underlined the importance of early engagement with project beneficiaries. For example, citizenconsultations at the time of modifying sub-project technical designs resulted in (i) a higher number of final beneficiaries and(ii) the implementation of practical, on-site solutions (such as rainwater harvesting systems) that may not have been consideredotherwise. Partnering with the local NGO Fundacin Gran Chaco was an important factor in the IPPs implementationsuccess. The NGO had thorough knowledge and engagement with the indigenous communities in the project area, which were key forguiding and building SAMEEPs capacity in managing social processes.Improving the sustainability of waterservices involves a long process that requires patient interventions at the levels of both the service provider and the overallenabling environment. While the projects main investments were for infrastructure development, the Bank teamincluded an institutional strengthening program during project design, which set the basis for a more comprehensive approach forutility improvement in the subsequent Plan Belgrano Project. Focusing on the water service provider is important but improvementsin the enabling environment also need to be introduced in order to achieve sustainability of services. Improved coordination amongthe national, federal and local level stakeholders needs to be established to ensure more efficient allocation of resources.Finally, the preparation and implementation of Management and Results Plans canalsoserve as a useful instrument forfacilitating commitment among these different levels.For framework projects to be efficient, the eligibilitycriteria and methodology of intervention needs to be clear and the list of potential investments need to be sufficientlyready. Although going forward with a framework project made sense at the time, the lack of a sufficiently ready list ofpotential investments led to significant delays and risks during project implementation. Technical studies were lacking, andtechnical capacity was low at the provincial level to address contract amendments, thus causing implementation bottlenecks.Inthe future, the Bank could utilize funds from other related projects or from trust funds to finance sufficiently ready andtechnically adequate pre-investment designs. Alternatively, contracts could be undertaken under the design and build modality,rather than on the usual works contract.
P120219 | RUSSIA CULTURAL HERITAGE 2 | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IBRD | IPF | 2011 | 2022 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099103024184514098/text/P120219-4530faeb-2f4f-4f1d-83a4-74d8597ec99d.txt | https://documents.worldbank.org/curated/en/099103024184514098/pdf/P120219-4530faeb-2f4f-4f1d-83a4-74d8597ec99d.pdf | The following lessons are considered the most relevant, extracted from the ICR andrephrased:Small-scale investments can bring big value added might be a suitable mechanism when there islimited financial capacity. They can reach a wide range of communities, some underserved, and promote learning and socialcohesion. CH projects can reach out to vulnerable youth, elderly populations, people with disabilities and marginalizedcommunities, sharing values and history through the experience of women, Indigenous peoples, ethnic minorities etc. Introducingspecific selection criteria could foster these investments.When the engagement of stakeholders is ensured (CI,public authorities at regional and municipal level, local communities, CH professionals, civil society and private sector),subproject design is more adapted and overall project sustainability is fostered. In this project, when restoring popularlandmarks, special attention needs to be given to public communications and structured engagement with the surrounding community.Strong inter-sectoral coordination is also essential for expediting numerous title, zoning, engineers, and environmental clearancesrequired for complex works such as those in CH restoration.
P120234 | Shandong Confucius and Mencius Cultural Heritage Conservation Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/125781523628115222/text/China-CN-Shandong-Confucius-Mencius-Culture.txt | http://documents.worldbank.org/curated/en/125781523628115222/pdf/China-CN-Shandong-Confucius-Mencius-Culture.pdf | The ICR (33-34) includes several lessons learned which were adapted by IEG: Designing a robust Results Framework with a clearly defined PDO and indicators measuring the progress towards achievingthe projects objective and ensuring sufficient capacity to perform ME activities is critical for a successful projectimplementation: Before the project restructuring in April 2016, this projects PDO was not clearly defined andthe Results Framework lacked indicators to measure all aspects of the PDO. In addition, the PIU lacked capacity to performits ME activities sufficiently resulting in theshortcomings (as noted in Section 9 of this Review) in monitoringimplementation progress at the start of the project. Cooperating with UNESCO and national culturalheritage authorities is critical for achieving high quality heritage conservation and management. This projectcooperated with UNESCO and experts from the State Administration of Cultural Heritage (SACH) to ensure compliance with relevantrequirements and laws as well as to obtain technical guidance and insights from local experts and global best practices - as notedin Section 10 of this Review..
P120265 | Urban Governance and Development Program: Emerging Towns Project | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/439541508870587661/text/ICRR-Disclosable-P120265-10-24-2017-1508870568034.txt | http://documents.worldbank.org/curated/en/439541508870587661/pdf/ICRR-Disclosable-P120265-10-24-2017-1508870568034.pdf | The ICR draws the following main lessons from implementing this project, with some adaptation of language.(1)The Banks support to local governments in a fragile political environment and weak governance structure would benefit from arealistic and simple project design and clear implementation arrangements. This project was the first Bank urban operationsince the late 1980s and the project agencies and municipalities did not have prior experience of working with the Bank and this inconjunction with a complex and ambitious design, contributed toimplementation delays in the initial years and eventualreduction in the scope of project activities during implementation.(2) Government strengtheningandinstitutional development may require time to show results,especially in a fragileenvironment. In the case of this project, the project required close support and follow up with municipalities, a strongsocialization process and institutional support. This however contributed to the outcome of improved sustainability of urbandevelopment.(3) An effective urban governance program may require institutional building at both nationaland local levels. This project strengthened institutions both at the national level and at the level ofmunicipalities.
P120313 | Indonesia Climate Change Development Policy Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2010 | 2011 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/623021474941326315/text/000020051-20150312115129.txt | http://documents.worldbank.org/curated/en/623021474941326315/pdf/000020051-20150312115129.pdf | The ICR identifies four lessons, all of which are generically relevant for DPLs. They can be briefly stated as follows: 1. Champions are needed, but institutional engagement too. In short, all involved institutions need to fully buy in to the reform agenda supported by the DPL, which is often not the case, thereby having a negative impact on results and the likelihood of achieving program objectives. The ICR (pg. 24) clearly suggests that this was the case with the present operation. 2. Clear and open communication is needed for strong partnership, and climate finance is a political issue. In the present case, communication with the line ministries responsible for delivering many of the programmatic results was apparently problematic, thereby weakening the needed "partnership" among them. This may have been further hindered by the apparent competition among some of the participating agencies to gain access to climate finance. 3. Government leadership is needed on the policy program. but also the monitoring program. Stronger attention by key central agencies to program results monitoring could have provided stronger signals to the line ministries and better feedback to higher government authorities, while also improving the ability to direct the policy process. 4. Policy based operations provide an important convening instrument. However, in the present case, the number of agencies and actions involved also created communication challenges regarding the program's rationale, use of funds, and links to specific policy actions, while the time and resource commitments needed to do this with success appear to have been underestimated. These lessons are important and suggestive, but as presented in the ICR, quite vague, and other lessons regarding why the Government decided not to go ahead with the DPL series and the Bank apparently acceded to this decision, and/or what the Bank might have done to have countered this situation, could also have been drawn. It likewise points to the inherent "tension" between the financial and substantive objectives of specific DPLs, especially in cases such as the present one in which the Government has easy access to alternative sources of budget support, including other Bank DPLs, which allows countries to "switch DPL horses in the middle of the race" with no risk of losing access to the volume of budget support funding which it needs.
P120313 | Indonesia Climate Change Development Policy Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2010 | 2011 | 2016 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/987781468186883131/text/103063-PPAR-P120313-SecM2016-0046-OUO-9.txt | http://documents.worldbank.org/curated/en/987781468186883131/pdf/103063-PPAR-P120313-SecM2016-0046-OUO-9.pdf | 6. Lessons 6.1 Two of the lessons identified by the ICR are particularly important and with which this assessment fully agrees. In addition, the present evaluation yields a number of other lessons, some of which also are of particular relevance for DPLs with environmental, including climate change, objectives.The first lesson drawn by the ICR was that champions are needed, but institutional engagement too. 6.2 The CC DPL experience clearly illustrates the importance of having both a strong champion and what can happen when, for whatever reasons, that person departs the scene and other leaders with less understanding of and/or commitment to the program's policy objectives take command of key ministries or agencies. It also reveals the importance of obtaining strong and consistent institutional buy-in from the other ministries and agencies involved. The persisting nature of this challenge in Indonesia was stressed by government officials as securing the proactive commitment and participation of line ministries in the implementation of policy reforms included in DPLs continues to be a constraint. Also relevant was the persisting difficulty of bringing other key government entities on board in terms of climate change versus economic growth priorities more specifically. In short, both strong leadership and cross-the-board commitment to implementation of the specific actions contained in DPLs is essential for them to be fully successful in terms of their policy objectives, and this proved not to be the case in the present instance. 6.3 A related lesson, which is particularly relevant for DPLs with environmental, including climate change, objectives which are inherently multior cross-sectoral in nature is that obtaining sufficient institutional buy-in becomes even more difficult when more than one sector is involved. This is especially the case when there are limited incentives for this to occur within the line ministries involved, as in most cases they receive no additional budgetary resources in order to carry out their assigned policy implementation tasks and where the tasks involved may not be very high, if present at all, among their own institutional or sectoral priorities. 6.4 The more general lesson that can be derived from the observation immediately above is the need to be fully aware of the incentives (or lack thereof) for policy action implementation among the various government agencies and levels of government involved in a DPL. In a country like Indonesia where subnational governments have considerable autonomy and often go against specific central government policies and regulations with which they disagree by failing to implement or enforce them, this is a potentially significant constraint on the effectiveness of DPLs that require concrete actions, such as those associated with improved forest management and governance or prohibiting the use of fire for land clearing purposes, on the ground. 6.5 It also leads to another related lesson, the need to fully understand the political economy, as well as the institutional constraints, that are likely to affect the incentives perceived by different ministries and levels of government. Again, the present experience illustrates the importance of this lesson both with respect to the underlying political and economic factors that are driving deforestation, peatland clearance, and the use of GHGemitting fires in large parts of Indonesia (particularly Kalimantan and Sumatra), as well as the reluctance â€“ and associated delays â€“ in the reduction of energy subsidies, despite its considerable potential benefits both in fiscal and environmental terms. The impediments experienced to date in terms of effectively getting REDD+ off the ground in Indonesia despite the attractive prospect of obtaining access to US$ 1 billion in grants from the Norwegian Government for this purpose illustrates the difficulty of overcoming these constraints and also affected implementation of the REDD-related actions of the CC DPL.121 6.6 Understanding the political economy and institutional constraints is particularly important in order to determine how realistically implementable proposed DPL triggers and other indicative actions are likely to be. This implies the need for comprehensive country knowledge and a broad and thorough risk analysis during appraisal. In the present case, some of the risks were recognized but, in practice, underestimated, while others (e.g., some of the broader political economy ones mentioned above and the change in key program supporters on the government side) were not identified in the Program Document. While not all risks can be anticipated, those associated with traditional institutional coordination and ownership problems, decentralization, and policy implementation constraints on the ground due to political and/or economic interests that are likely to oppose and effectively block such measures, can â€“ and should â€“ be identified and assessed as realistically as possible as part of the appraisal process. Failure to do so can result in overly optimistic or ambitious triggers and policy actions as was clearly the case with the CC DPL series. 6.7 In short, another key lesson from this experience is that the Bank needs to be realistic in defining its policy objectives and targets for Climate Change (and other) DPLs. The Bank was initially reluctant to financially support the JICA-ADF-led policy based operation for climate change in Indonesia, but decided to come in after the Government agreed to stronger policy measures regarding energy subsidies and forest governance. However, these measures subsequently proved difficult to implement within the time frame expected to allow the operation to proceed beyond the first loan, and, thus, in practice, were too ambitious in light of the institutional and political economy constraints mentioned above. Similarly, the assessment of program performance revealed that actions taken in some policy subareas were considerably more successful than others. Progress across sectors was uneven, but was generally better in those areas such as renewable (i.e., geothermal) energy, water resource management, and disaster risk management in which the Bank was already providing support through other instruments and which were less politically contentious. In other areas, such as energy pricing, forest governance, and the provision of a financial mechanism/incentives to induce better performance on the part of local governments, it was much weaker, again due 121 Similarly, Indonesia's strong continued reliance on fossil fuels, both for domestic energy consumption and, in the case of coal, for export purposes, means that the likelihood that it can and will significantly shift to renewables, including geothermal energy, in the foreseeable future remains very limited. Energy efficiency improvements notwithstanding, the implications of all of the above elements in terms of generating a substantial decline in GHG emissions in Indonesia are not favorable. In fact, together with deforestation, urbanization, and domestic fossil fuel consumption, such emissions appear to have increased since 2010 and are likely to continue to do so in the years ahead despite GOI efforts including with World Bank and other development partner support to reduce them. to the contextual impediments experienced and which the Bank appears to have underestimated. 6.8 A second and more positive lesson emphasized by the ICR that also merits further elaboration is that policy based operations provide an important convening instrument. DPLs â€“ particularly programmatic ones â€“ indeed have considerable potential value as a convening instrument, and this is especially the case when key Finance and/or Planning Ministries take the lead in this regard (although this strong commitment to the operation needs to continue throughout the anticipated implementation period). As in the present case, they can also play a key role in helping to better coordinate and/or harmonize support from different development partners around a set of common objectives and agreed policy actions. Bank staff affirmed that the joint government-development partner monitoring and planning meetings were particularly useful and this was also observed in the ADF/JICA joint evaluation. However, once the series was suspended, donor coordination appears to have broken down and contacts among them have been less frequent and systematic since that time, at least as concerns helping the country to address climate change, even though this objective remains an institutional priority for most, if not all, of them in their current assistance to Indonesia. 6.9 This loss of convening power and associated policy dialogue both with key government ministries and other development partners points to yet another lesson that can be drawn from the CC DPL experience\. the need for DPLs to be part of a broader engagement strategy with respect to a particular policy reform area involving multiple Bank instruments, including investment loans and technical assistance. Bank staff stressed the importance of twinning DPLs with investment loans to ensure greater likelihood of their effectiveness. In this context, the existence or prospect of Bank investment loans may serve as a positive incentive for ministries or agencies charged with implementing parts of a DPL. This appears to have been the case in the renewable energy (i.e., geothermal energy) and disaster risk management areas of the CC DPL, which recorded some of the more successful policy actions in this DPL and are areas in which the Bank was providing or expected to provide (geothermal) financing for investment projects at the time the series was initiated. In contrast, the Bank had a more checkered past history in terms of lending in the forest sector and with the Forest Ministry even though it had undertaken considerable past analytical work on forest sustainability-related issues, both individually and with other development partners, including ADB, DFID, CIFOR, and ICRAF. The powerful competing economic and political interests in the forest sector, as opposed to the relative absence of them in the renewable energy sector, explain much of the differences in performance in this regard. 6.10 A multi-instrument Bank engagement strategy around a specific emerging development challenge, such as helping a government to address climate change, also needs to have both a longer-term engagement and support institutional capacity building, neither of which can be effectively incorporated in DPLs, even programmatic ones, whose financial objectives are inherently short term. Bank staff stressed the importance of establishing longterm relationships with the bureaucracy and the need for capacity building as critical requirements for the effectiveness of Bank-supported development interventions generally, pointing out that DPLs are not the right instrument to achieve such objectives and should not be expected to do so, especially in the case of Indonesia with which he was very familiar. In short, the limitations as well as the advantages â€“ primarily in financial terms (i.e. fastdisbursing general budget support, particularly in times of economic and/or fiscal crisis) but also secondarily on the policy front â€“ of development policy finance operations need to be clearly understood and the instrument used appropriately and accordingly. 6.11 An additional lesson that can be drawn from the CC DPL experience is that multiyear programmatic DPLs are subject to many of the same risks and uncertainties as investment loans, even though they may have shorter implementation periods, as delays in carrying out policy actions can occur and government commitment can change dramatically over time. In the present case, numerous policy actions, including one of the key triggers for the second loan were delayed, and some still have not been implemented. In short, while programmatic DPLs, if implemented, have several clear advantages including a continuing seat at the table for the Bank in terms of policy dialogue in a particular area and the prospect of helping and/or inducing governments to move forward on a policy agenda of interest to the Bank, they are also subject to some of the same kinds of implementation problems, including unexpected external shocks, as other types of financing instruments. 6.12 Finally, even in cases, such as the present one, in which a DPL is unsuccessful (for whatever reason or combination of reasons) in terms of its specific policy objectives, it can nevertheless play a positive and strategically important role in terms of establishing, continuing, and/or advancing the Bank's policy dialogue with and assistance to a Borrower in a given area, such as climate change, that can be manifested in the increasing use of other Bank instruments, including investment loans and TA, over time. Various past and present Bank managers and operational staff who have worked, or are working on, Indonesia have highlighted the importance of the CC DPL in particular in terms of strengthening the Bank's dialogue with the Ministry of Finance, BAPPENAS, and several line ministries in relation to climate change, which has led to numerous other engagements in this area both on the mitigation and adaptation sides over the past five years. Those interviewed during the evaluation mission in the Ministry of Finance and BAPPENAS, as well as former high officials of the Ministry of Forestry and the Secretariat for the National Council on Climate Change, made essentially the same point when asked to identify the principal benefit of the CC DPL for the country. Thus, while the CC DPL operation is rated Moderately Unsatisfactory, the Bank's collaboration with the GOI in numerous areas related to climate change has blossomed in recent years and may be even more promising in the future. In good measure, this is an outcome of the relationships and policy dialogue established in association with this incomplete programmatic DPL series.
P120321 | Capital Markets Modernization Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2011 | 2017 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/627031494425468542/text/ICRR-Disclosable-P120321-05-10-2017-1494425457299.txt | http://documents.worldbank.org/curated/en/627031494425468542/pdf/ICRR-Disclosable-P120321-05-10-2017-1494425457299.pdf | The lessons learned put forward in the ICR are commonand reflect the experience of the project design and implementation.Key lessons underscore: (i) the need to factor in the project design macroeconomic risks for economies relying on on a particularcommodity or sector, (ii) the importance of having a PIU with an internal capacity to manageall aspects of the project, (iii)the determining factor of a committed Government for a successful project, and (iv) the difficult task of measuring the reformssupported by a TA project that take longer to be completed. This review is inagreement with the above lessons, and adds alsothat attribution of outcomes remains a major challengewhen many other donors were supporting the same category ofreforms.
P120338 | Financial Education and Financial Literacy | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2011 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099125511292110082/text/Russian0Federa0n0Financial0Literacy.txt | http://documents.worldbank.org/curated/en/099125511292110082/pdf/Russian0Federa0n0Financial0Literacy.pdf | The ICR identified a set of recommendations and lessons (p.54-56), and most of them are commonly found in IBRD countries.A selection of the lessons is summarized below. Lessonsspecific to this operation are notincluded. Borrower commitment and leadershipare the key ingredients to achieving stated objectivesandsocial impact. The RussianGovernment provided sustained funding, along with strong leadership andcoordination of partners, which fostered cooperation and built institutional and human capacities. The strong leadershipand inclusive approach allowed the design and implementation of the National FL Strategy,facilitatedhorizontal andvertical institutional linkages among the key stakeholders, and promotedcross-sectoral dialogues and collaboration, as wellasan institutional and public support. The lesson from this project is that because of strong oversight, the projectengaged local government administrations, educational institutions, and other non-government organizations, and financialinstitutions in the development and implementation of a comprehensive financial literacy program which resulted in a sharedownership and contribution to the achievement of positive development outcomes. The stability ofimplementing teamscontributes to the ease with which implementation obstacles areaddressed:Stabilityof the Government,the PIU staff and the WB team facilitated smoothimplementation of project activities and the achievement of project development objectives. Throughoutthe project lifetime,the Government and PIU team remained stable, and highly engaged in addressing all obstacleson the project implementationpath.The Bank team was similarly stable.The lesson from this project is that the stability of the teams assisted inensuring mutual understanding of the project objectives and consistency of purpose when crafting solutions toprojectimplementation obstacles. Embeddingproject implementation within existingcountryinstitutions helps to build capacity, to pilot and testprogramsandthenfostersustainability. A phased implementation approachwas the model adopted to deliver this complex andmulti-sectoral operations, which went through strategic sequencing of activities, testing new ideas and methodologies, evaluatingthem and adjusting as needed. The project teamsworked very closely with the key ministries and other institutions involved oninstitutionalizing project activities to ensure sustainability.In addition, piloting activities provedto be a usefulapproach prior to a nation-wide scale up. The government accepted new ideas and was willing to test them out in pilot programs,evaluate them and adjust prior to a full scale-up, before expanding them to nationwide coverage.Sustainability of projectinterventions critically depends on establishing or strengthening the appropriate institutional framework.The lessonfrom this project is that strategic use of existing institutions and infrastructure like schools, centers, libraries, workplaces,community centers, and unemployment centers provide unique opportunities to deliver a program to large and often diverse segmentsof the population in a cost-effective approach. This project exemplified how limited seed money fromthe World Bank Group can generate results and impact in IBRD countries.Funding of this project was 12 percent fromIBRD, and 88 percent from the Borrower. The seed money from the Bank (US$25 million) mobilized up to ten times an amount ofresources from the Borrower, and supported a large program implemented over ten years with a high level of ownership and potentialfor sustainability.
P120370 | Southern Africa Trade and Transport Facilitation Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Infrastructure | Transport | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099200005232242249/text/P12037001ae40e0800bbbb06710a5395ddc.txt | http://documents.worldbank.org/curated/en/099200005232242249/pdf/P12037001ae40e0800bbbb06710a5395ddc.pdf | The ICR (p. 38-40) included several useful lessons learned, which were adapted by IEG: Regional projectsrequiring international agreements for a successful implementation benefit from a plan B in case no agreement is beingreached. In this project, even though the partner countries on the NSC had reached an initial agreement on establishing alevy on transit along the corridor to ensure the funding of the DCC, no official agreement had been signed when the project wasapproved. Implementing the project with a stop gap funding mechanism put the project at high risk and ended up negatively impactingproject implementation. Ensuring sufficient capacity at the implementing agency, especially when the same agencyimplements multiple Bank projects, is critical. In this project, TANROADS was able to increase its capacity throughoutimplementation. However, with multiple Bank projects being implemented at the same time, TONROADs capacity remainedstretched. A corridor project with multi-sectoral components can have a large impact. However, projectimplementation can be complex and requires adequate capacity at the implementing agency and intense Bank supervision. Thisproject went far beyond a typical roads project including health aspects as a key aspect in its design and raising road safety tothe PDO level. Due to the complexity of the project, several stakeholders and the implementing agency lacking experience inhealth-related projects, implementation faced several challenges.
P120397 | Afghanistan Agricultural Inputs Project (AAIP) | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2019 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/855591603371069038/text/Afghanistan-AF-Agricultural-Inputs-Project.txt | http://documents.worldbank.org/curated/en/855591603371069038/pdf/Afghanistan-AF-Agricultural-Inputs-Project.pdf | The lessons identified by the ICR with some reformulation are as follows:In an FCV country, it is appropriateto tie-up complex procurement to pre-selected institutions/firms at preparation stage and helpful to initiate and complete designof complex civil works in the preparation phase. Most activities of the project were dependent on complex procurement ofgoods/civil works and the engagement of international or national consultants which brought implementation delays. If a preselectedinstitution was hired to oversee and coordinate these procurement activities, capacity and governance issues would not have createddelays.Land resettlement should be triggered for all projects that utilize land. In-depth analysis andconsultations with communities should be conducted in advance to avoid land disputes. There were land disputesduring the project which were not envisaged at the project preparation stage because of the involvement of public institutions.Selection of sites free from disputes and consultation with communities by the project authority should be the prime considerationfor expeditious project implementation. Furthermore, improving land tenure governance by providing guidance and information oninternationally accepted practices for systems that deal with the rights to use, manage and control land iscritical.An appropriate structure to facilitate inter-ministerial coordination is necessary when multipleministries/agencies are involved. Inter-ministerial coordination was a major issue for the project. There weredelays because of lack of agreement among directorates. The bureaucracy did not allow any authority below the level of Minister tohave a coordinating role. The issue of coordination should be taken seriously in future projects.The Bank could bemore flexible in support of extensions for project duration and embrace projects with more than five years of implementation,particularly in an FCV context. Procurement delays that resulted due to capacity, governance and lack of bids were partlydue to the FCV situation in the country. Should the request of the government for a second extension have been granted, some keyactivities could have been completed. The Bank management needs to consider additional challenges and delays in a FCV context andact flexibly in these situations.In fragile and conflict environments, efforts could be made to engender trust andownership of beneficiary communities so that regular ME data can be supplied by community members. In most projectareas where land development was made and local infrastructure were constructed, the project basically utilized information fromcommunity and CDC members as part of record on implementation progress and validation of contractors record. This made datacollection efforts more accurate and reliable.
P120398 | AF On-Farm Water Management (OFWM) | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2011 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/149571603371196834/text/Afghanistan-AF-ARTF-On-Farm-Water-Management-OFWM.txt | http://documents.worldbank.org/curated/en/149571603371196834/pdf/Afghanistan-AF-ARTF-On-Farm-Water-Management-OFWM.pdf | The ICR included seven lessons. The following three are emphasized with some adaptation of language: Toensure achieving maximum benefits to farmers, projects involving irrigation scheme rehabilitation need to be complimented withon-farm technical support and investments.The project experience showed that integrating complementarynon-rehabilitation interventions will help ensure that the benefits of scheme rehabilitation are maximized, sustained, anddistributed more equitably within communities. ME design needs to beoriented towards measuring andevaluating outcomes to provide a comprehensive assessment of the project achievements.The projects MEsystem was heavily focused on outputs tracking, whichintroduced unnecessary complexities. For example, the project faceddifficulties in measuring complex variables such as water productivity and income changes from cropconversion. Coordination between public institutions needs adequate incentives to ensure smooth cooperation inprojects that involveirrigation and agriculture components. The project experience showed that the public sectorcoordination on irrigation and agriculture was problematic. There were efforts to encourage inter-ministry coordination across theMinistry of Agriculture, Irrigation, and Livestock, Ministry of Energy and Water and Ministry of Rural Rehabilitation andDevelopment (via engagement on policy development and reform) as well as intra-ministry coordination between the IrrigationDirectorate and Directorate General of Agriculture Extension and Development. However, these efforts were futile orfleeting.
P120399 | Second Public Expenditure Development Policy Loan | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/829331473934079095/text/ICRR14947-P108759-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/829331473934079095/pdf/ICRR14947-P108759-Box396299B-PUBLIC.pdf | The ICR draws some important lessons (1 through 3), which IEG re-interpreted and summarized as follows. Lessons no. 4-5 have been added by IEG.1. Reforms lacking the support of effective champions may fail to show progress. In the education sector where there was no effective champion little progress was made.2. Mixing short-term fiscal objectives with medium-term structural reforms of public expenditures can lead to contradictions and obstacles to the achievement of one or the other of these objectives. And linking them can lead to the entire program (and the associated external financing prospects) going astray, on account of shortcomings in only one dimension of the program.3. Indicators and targets that consider alternative possible scenarios may improve the usefulness of M&E, especially when achievements of outcomes can be strongly affected by unforeseen external macro-economic developments (e.g. as in the case of the wage and pension bills defined as shares of GDP), and of future data availability (e.g., as in the case of PEFA indicators). 4. In crisis situations, the Bankâ€™s exposure limits may reduce its role in shaping a DPL program. If the World Bank could have lifted, at least temporarily, its exposure limits to allow an even larger financial assistance package, it would have provided the Bank a stronger role in shaping the overall fiscal consolidation program, which instead was driven almost solely by the IMF, and more leverage over the scope and pace of the structural reforms it supported.Crisis situations, when it is necessary to minimize cuts in social spending, may be good opportunities to make social assistance programs more effective (e.g. improving their targeting) This was indeed the case for Serbia in 2009-2011.
P120427 | Public Financial Management Reform II | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/920701547669580505/text/Afghanistan-AF-ARTF-Public-Fin-Mgmt-Reform-II.txt | http://documents.worldbank.org/curated/en/920701547669580505/pdf/Afghanistan-AF-ARTF-Public-Fin-Mgmt-Reform-II.pdf | The ICR (pp. 26-27) offered several useful and insightful lessons, including:Reducing aiddependency requires a long-term transition plan. In this case, transition of consultants to the civil service isthreatened by the governments inability to afford the higher rates of pay required for technical staff. Human resourcesissues are a major focus ofthe follow-on project.Building a sound public financial managementsystem is one of the first priorities of a recovering, fragile state. In this case, building government capacity inprocurement, treasury, and audit has contributed to increased confidence in the use of on-budget systems, including among donorspreviously reluctant to use government systems.Especially in low-capacity environments, flexibilityis needed in the Banks responseto emerging circumstances and priorities. In this case, the Bank teamneeded to be willing to go beyond its usual supervision responsibilities and provide regular mentoring and training in procurementand other areas.
P120435 | Kyrgyz Health Results Based Financing | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/400201582912569316/text/Kyrgyz-Republic-RESULTS-BASED-HEALTH.txt | http://documents.worldbank.org/curated/en/400201582912569316/pdf/Kyrgyz-Republic-RESULTS-BASED-HEALTH.pdf | The ICR (pp. 22-24) contained several insightful lessons, some of which are highlighted here:Reforms toincentivize improved performance at the facility level, typically seen in higher-income settings, can work in lower- andmiddle-income health systems when the necessary groundwork is laid. In this case, the country had a set of prerequisites-- an experienced single payer, a culture of strong monitoring and evaluation, and strong support from key champions of reform--that facilitated piloting and scaleup of new processes.Potentially controversial reforms may work bestwhen they complement rather than disrupt existing institutional and financial frameworks. In this case, theperformance-based payments were layered on top of broader,previously-implemented reforms of provider reimbursementmechanisms, facilitating clear assessment of their impact and increasing the likelihood of support amongstakeholders.Thinking early in a project cycle about provisions for mainstreaming a pilot can increase theprobabilityof sustaining outcomes. In this case, the project could have incorporated more deliberate and focusedtransition support.
P120464 | Southern Sudan Umbrella Program for Health System development | Eastern and Southern Africa | South Sudan | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2010 | 2013 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/795141474564464818/text/000020051-20140626114053.txt | http://documents.worldbank.org/curated/en/795141474564464818/pdf/000020051-20140626114053.pdf | Lessons drawn from the ICR (pages 33-34), adapted by IEG:A strong focus on M&E can produce data that can be used for immediate decision-making, even in a post-conflict setting. In the case of this project, specific health surveys were prioritized, alongside longer-term strengthening of the health information management system, which helped to identify areas of immediate need.Immediate strengthening of the health system (via significant donor funding and technical support) should be undertaken with a view to longer-term health systems development. In the case of this project, capacity building efforts included establishing policy and institutional frameworks in the Ministry of Health, although local capacity remains a significant risk to sustainability.
P120470 | Third Financial Sector Development Policy Loan | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/612871474501653186/text/000020051-20140625225418.txt | http://documents.worldbank.org/curated/en/612871474501653186/pdf/000020051-20140625225418.pdf | The most important lesson emerging from this operation relates to the importance of sustaining a critical policy dialogue during a period of political, social and economic instability. Critical elements contributing to the positive outcome include a champion on the government side and a responsive demand-driven approach on the Bank side, including mobilizing sufficient resources to fund a specialized implementation team and undertake analytical work, and stability of the task team leader. 2. The quality of the overall reform program depends not only on how prior actions are fulfilled but also on whether and how other reforms included in the program are implemented. It is therefore important for the Bank to engage in a broad sectoral dialogue, going beyond narrow prior actions. 3. Supporting a focused, financial sector reform program through a series of related but self-standing DPLs, instead of implementing a programmatic approach that could have covered more sectors, may provide additional flexibility to deepen reforms as opportunities arise, and avoid the difficulties associated with sustaining a multi-sector policy dialogue.4. The presence of a senior task team leader in the country, including during turbulent times, ensures continuity in the sector dialogue and alleviates the risk of policy reversal. However, under-funding of project supervision may undermine the quality of implementation support. This may be addressed by funding implementation support through Trust Funds and cross-subsidizing from other activities. In order to capture full costing of projects, the expected use of the Trust Funds such as FIRST should be incorporated into project design and reported in the ICR. Funding from other parts of the Bank Budget should be similarly reported.5. Care should be taken when designing an M&E system so as not to set targets that may not be readily attributable to the operation or appropriate in the short- to medium-term. With respect to the latter, indices normalized with respect to GDP may prove problematic and should be avoided, especially when measuring change over relatively short time periods.
P120517 | Local Government Support, COVID-19 and Resilience Response Project | Western and Central Africa | Burkina Faso | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099835009192238560/text/P12051707d74ba0e0086cc0c61dc96c6b11.txt | http://documents.worldbank.org/curated/en/099835009192238560/pdf/P12051707d74ba0e0086cc0c61dc96c6b11.pdf | Successful decentralization in fragile environments requires long-term and sustained engagement. Two keyenablers, allowing the Bank to stay the course, were a strong and consistent client dialogue and ownership across severalgovernments, and stable Project Implementation Unit (PIU)and Bank teamsthat provided institutional memory andconsistencyand demonstrated proactivity and adaptability, helping to operationally mitigate and navigate external volatility.The PIU remained unchanged throughout the project, even as ministers frequently turned over, while the Bank TTL remained in placefor five years, leading the project from preparation throughtriggering of its second phase(AF and restructuring). Thisexperience can provide an example for the Bank as it considers its operational response to recent socio-political and securitycrises.Increasing citizen participation in operations, especially in an FCV setting, can represent an acuteME challenge. There is no consensus around methods and tools for measuring the success and failure of citizenparticipation efforts. It can be tempting for projects to focus their measurement on process-oriented and quantitative aspectsthatare considered easier to measure. This was the case for this project,which opted for an evaluation of processes,measuring outputs through intermediate results indicators, with a PDO indicator that did not capture the expected outcome. Thisleaves doubt about whether participation was meaningful.Robust ME in FCV environments requires adaptingME tools and developing national ME capacity. The projects ME was not well adapted to the specificconstraints of volatile FCV environments, such as capacity limitations, low levels of technology,or project siteaccessrestrictions. Theproject also did not use itsME framework to respond to changing conditions on the ground andlacked indicators capturing potential conflict-related outcomes. In parallel, the project made only a limited investment innational ME capacity beyond SUPERMUN. Together, adapting ME tools and more robust investment in national ME capacitycouldhave helped mitigate the ME challenges the project faced.Decentralization and fiscal transfers involatile FCV environments should only be undertaken with extreme caution. In Burkina Faso, existing tensions betweenethnic groups risk making newly decentralized responsibilities and transfers and infrastructure investments a new source ofconflict. Newly opened local decision-making spaces can devolve into new stages of contestation. This made the project asignificant conflict risk, for which the project did not include sufficient mitigation measures, as the projects GRM wasunlikely to be adequate. The project lacked ME to capture inclusion or grievances. The fact that no such incidents arereported in the ICR could be due not to their absence but to insufficient monitoring mechanisms. To identify these challenges, theproject could have benefitted from additional conflict analysis at the project design stage.
P120534 | Economic Management and Governance Reform Grant III | Western and Central Africa | Central African Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/881231474483090132/text/000020051-20140625233710.txt | http://documents.worldbank.org/curated/en/881231474483090132/pdf/000020051-20140625233710.pdf | IEG agrees with the lessons highlighted in the ICR, including the usefulness of a two-tranche budget support operation in fragile countries and the importance of TA for program implementation. In addition, this operation highlights once again the challenges that the Bank is facing in implementing budget support operations in fragile countries, and the need for comprehensive analysis of the political and security situation to fully take the risks of engagement into consideration.
P120536 | Tanzania Poverty Reduction Support Credit 11 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR brings the following lessons, with which the IEG review agrees. A series ofdevelopment policy operations that focuses on a limited, well-researched, jointly designed and monitored reform agenda, is likelytohave more traction than those with broad and dispersed focus. The PRSC 9-11 series focused on two pillars and fivepolicy areas, in contrast to the two preceding it, which encompassed four pillars and a wide range of reform areas. A smaller andsharper focus made it easier to implement and monitor the program and adjust it in a timely manner as the circumstances demandedit, which was instrumental in achieving the outcomes. The move from broad business environment reforms to streamlining processes inselected areas has yielded better outcomes. Narrowing the focus facilitatedconcentrating efforts in fewer areas, but made the program prone to unreachable targets during the duration of the program.The outcome indicator should be achievable both because of the program and as a measure of realism. While theoutcome indicators of the PRSC 9-11 program were clear and well-defined, some of the program targets were set too high (share ofMKUKUTA to reach 100%), or number of signed PPP project at 4). A key reason for over-ambition was drawing the targets from thegovernments long-term development plans and strategies to align them with the governments objectives, but thesetargets were somewhat inappropriate for a short-term program more oriented to the budget cycle.IEGadds the following lesson:The experience of the program shows that inadequate indicators andoutcome targets can affect the assessment of a programs actual development outcome. This suggests that closemonitoring of program results during implementation is as important for program success as monitoring the implementation of theprograms prior actions and triggers.
P120541 | Second Education Development Policy Loan | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2013 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/552071467998764458/text/ICRR14694-P120541-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/552071467998764458/pdf/ICRR14694-P120541-Box393183B-PUBLIC.pdf | The ICR (pp. 21-22) presents several well-founded lessons that can be derived from the experience of the operation. In particular, it notes: Policy operations are less effective when done as a one-year program as compared to a multi-year series of operations. This reflects the need to implement a long-term reform process that incorporates complicated changes and the participation of stakeholders. A bottom-up (or organic) process of decentralization may be more effective in introducing reforms at the local level. The ICR reports that, in this case, decentralization was developed at the center and not always understood at the local level. Having a strong student assessment system is important in any program that aims to introduce reform at the local level. Improving education quality is one of the two central goals of the government program (along with increasing enrollment). Without a system to measure changes in learning, it is not possible to measure the program's impact. Likewise, having an assessment system would have helped to improve the Bank's program's contribution to quality.
P120561 | Tunisia: Ecotourism and Conservation of Desert Biodiversity | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/964911585690292385/text/Tunisia-Tunisia-Ecotourism-and-B-Conservation.txt | http://documents.worldbank.org/curated/en/964911585690292385/pdf/Tunisia-Tunisia-Ecotourism-and-B-Conservation.pdf | The ICR (p. 20 to 22) included several lessons learned which were adapted by IEG: Stressing the linkbetween socioeconomic development and environmental protection of biodiversity is important for taking advantage of potentialsynergies. This project combined activities that generated income, improved local conditions, and supported alternativelivelihoods while at the same time protecting fragile natural resources and biodiversity. Careful planning andimplementing responsible ecotourism can have a positive impact on the value of natural assets and ensure the ecologicalsustainability and the economic profitability in the long-run.
P120565 | Afghanistan - Support to Basic Package of Health Services (Strengthening Health Activity for Rural Poor | South Asia | Afghanistan | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/991611467246542584/text/ICRR-Disclosable-P120565-06-29-2016-1467246524293.txt | http://documents.worldbank.org/curated/en/991611467246542584/pdf/ICRR-Disclosable-P120565-06-29-2016-1467246524293.pdf | Contracting out services to NGOs instead of providing health services through the government might provide flexibilityand agility necessary for project implementation in a challenging environment. In this project, the NGOs operating in ruralsettings were much more successful than the SM-KPPHD management structure in the Kabul pilot. While the government is responsiblefor oversight, stewardship and coordination, NGOs might have better abilities to operate in thefield. Providing a low-cost package of health services, contracting out services to NGOs, andcollaborating closely with the government and development partners while gradually strengthening the governments stewardshipand service provision role is a good approach for health system strengthening in fragile and post-conflictcountries. It is critical for the assessment of a project to include indicators relevant toall of the projects objectives, and to collect data on those outcome indicators specific to the projects geographicalareas.
P120566 | Morocco First Skills and Employment DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2012 | 2013 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/693821495645558967/text/ICRR-Disclosable-P120566-05-24-2017-1495645550309.txt | http://documents.worldbank.org/curated/en/693821495645558967/pdf/ICRR-Disclosable-P120566-05-24-2017-1495645550309.pdf | Lessons learned are derived from the ICR:While preparing Prior Actions and developingtargets, the institutional capacity of relevant ministries to implement reforms needs to be well assessed to the extentpossible. In particular, a number of PDO indicators formulated during project design were too optimistic whereby they did nottake into account unanticipated macroeconomic changes. This was particularly relevant for setting target results for programs thatinvolve the participation and take-up of the private sector.Collaboration with other developmentagencies can be a positive enabler for the success of labor market reforms. For SEDPL2, for instance, the financial andtechnical assistance of the French Development Agency (Agence Franaise de Dveloppement) and the German DevelopmentAgency/German Society for International Cooperation (Deutsche Gesellschaft fr Internationale Zusammenarbeit) helped toaccelerate the implementation of some reforms that would otherwise have taken longer toimplement.A more active involvement of the private sector (federations,training providers, and NGOs) is a promising model to increase the quality and relevance of programs as well as to reach vulnerablesegments of the population, especially at the local level.
P120594 | Samoa Post Tsunami Reconstruction | East Asia and Pacific | Samoa | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/210941472562969300/text/ICRR-Disclosable-P120594-08-30-2016-1472562955244.txt | http://documents.worldbank.org/curated/en/210941472562969300/pdf/ICRR-Disclosable-P120594-08-30-2016-1472562955244.pdf | The ICR (pp. 29-30) has identified a number of lessons, of which the most important are listed below with someadaptation:In a country so much at risk to natural hazards as Samoa, where a significant anddestructive cyclone occurs every five years, sound engineering principles call for reconstruction design standards that are able towithstand future hazards. The project, through design inputs from specialist drainage engineers and from hydrologists toassess flood risks and flood management options, aimed to safeguard the new road infrastructure, and to ensure the incorporation oflonger term climate risks.In small countries with correspondingly sized implementing agencies andconstruction sectors, proven and familiar technologies for designs and procedures for bidding works can advantageously be used toencourage the participation of local companies, thereby helping to ensure competition and containing construction costs, as well asenhancing the efficiency and sustainability of investments. Project design solutions were not overly complex and made useof proven local technical approaches and available materials.The participation of domestic contractors and consultants forworks and services was strong and this, coupled with solid contract management by LTA, ensured that construction costs, even duringperiods of peak reconstruction activity, were contained.There is a need for effective communityconsultations and ongoing engagement at the preparation stage and during works in order to minimize disruptions anddelays. The project made use of existing institutional arrangements for implementation and sought early, and thereafterperiodic, formal consultations with local communities through traditional and local government leadership to establish priorityroutes for upgrading roads and to resolve complex customary land tenure authorizationsWhile the rapidconstruction of strategically located transport routes based on community priorities can increase local community willingness tovoluntarily relocation to less hazardous locations, it is also important to ensure that the new locations are adequately served bybasic utilities. If this does not occur, the return of an important percentage of communities to the hazardous areas islikely.IEG adds a fifth lesson:In order to tap fully the Banks knowledge and experience in policy,regulatory and institutional reforms, Bank involvement in emergency post-disaster relief projects would normally include activitiessupporting the strengthening of institutions and establishment of more robust procedures that can help governments and localcommunities address future disasters. It seems that this was intended in the project under review, since the objectivesrefer to assisting local communities to address future natural disasters. However, few if any activities were incorporated in thedesign to meet this aim, which was, moreover, only partial in that nothing was contemplated at central government level.
P120595 | Tonga Post Tsunami Reconstruction | East Asia and Pacific | Tonga | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/875861475117757777/text/000020051-20150113010913.txt | http://documents.worldbank.org/curated/en/875861475117757777/pdf/000020051-20150113010913.pdf | The ICR highlights the following lessons (with some adjustments by IEG): The time required for satisfactory land acquisition arrangements to be devised should not be underestimated. Project implementation periods should provide for adequate time to negotiate land issues, and, even then, allow for possible additional delays. In this project, even though land acquisition arrangements seemed relatively straightforward at the appraisal stage, unforeseen local political issues stalled implementation of physical investments. For some regular investment projects it may be appropriate to make the completion of land negotiations a condition of effectiveness. For emergency operations, however, such a decision should be made on a case-by-case basis since it could hold up implementation of other urgent recovery activities.For remote and inaccessible locations, a project's estimated implementation period should incorporate a realistic assessment of the logistical challenges posed of reconstruction in a remote location. In this project, existing transport impediments, worsened by the 2009 tsunami itself, made it difficult for essential work teams, equipment and other materials to arrive at the project site, and disrupted schedules for project supervision by the Government and the Bank. When a project's financing plan includes unallocated amounts, of US$0.3 million in the case of this operation, it is important that the formulation of the PDO not be so specific and narrow as to preclude additional activities that might be financed by this amount. For this project, the original PDO specified that investment should be in housing and ancillary water supply and sanitation. Since this did not cover work on an access road later found to be urgent, it required a full restructuring of the project and revision of the objective to make the new investment eligible under the Grant. In hindsight, the revised PDO covering ancillary infrastructure would have been a better formulation from the outset. It would have dispensed with the need for restructuring with Board approval altogether.Direct links among all project activities are especially important in an emergency operation. Under this operation, capacity building activities, for instance, were only loosely connected to the operation's reconstruction and recovery activities, which were given priority. Furthermore, the two sets were implemented by different ministries. If different priorities and timelines are given separately to different activities, then important matters can be left behind, as capacity building was in this project.From IEG: An economic analysis is required, and is generally feasible, for emergency projects at completion. In the case of this project and in many others, the project team misunderstood that an emergency project was also exempt at completion from an economic analysis. The completion exercise is not constrained by the same urgency of preparing an emergency response to a disaster, when a prolonged economic analysis might delay the delivery of Bank assistance to the victims.
P120613 | Additional Financing to the Public Financial Management Reform Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2014 | 2016 | PPAR |  | Satisfactory | Highly Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/678051469685075659/text/Vietnam-Public-Financial-Management-Reform-Project.txt | http://documents.worldbank.org/curated/en/678051469685075659/pdf/Vietnam-Public-Financial-Management-Reform-Project.pdf | 10. Lessons General 10.1 An evolving project level M&E may be a good substitute for a formal one that is pre-set at appraisal. This can be the case when the iterative, demand-driven nature of the activities does not allow clear measurable objectives to be set from the outset. Also approaches, such as use of social media, may be informative and cost-effective. Finally, standalone studies and assessment provide important complements to results-based M&E. 10.2 Outcomes for PFM operations are difficult to measure at closing. The Vietnamese cases show how ongoing policy actions take time to mature as do systems. In this instance, project outcomes became fully apparent in early 2016. In cases elsewhere, a number of factors including poor governance may undermine the initial results. Even though periodic PEFA assessments are not suitable as M&E for operations because of lags in indicators, they can provide useful information on PFM program progress over time. 10.3 PFM reforms need decades to complete. Vietnam is well into its second decade of reform. Both the government strategy and actions needed to reach the higher level objective of good governance show the need for this effort to be sustained into the 2020s. In this context, continued effective provision of financial and, more importantly, knowledge by development partners, will be needed. Strong donor harmonization and coordination have been enabling factors so far. Coordination has become more important now that some partners are no longer participating in the follow-up to the MDTF under preparation, providing separate support instead. 10.4 The funding of operations may not be commensurate with their impact. Significant results were attained under MDTF II even though the grant amount was small. The supervision resources devoted to the project were large compared to disbursements because they underpinned an important policy and institutional dialogue. The World Bank correctly continued to support project implementation, even at a time were difficulties were experienced. On the government side, capacity built was sustained and, together with substantial ownership, resulted in actions being continued beyond the timeframe of the project. 10.5 TA operations that are initially focused on a single ministry may have a greater chance of success. Clarity in ownership and leadership of the activities by the MOF, which is the leading institution in PFM, was essential and avoided overcomplicated coordination mechanisms in the case of MDTF II. However, future PFM reforms will inevitably have to cover multiple entities and would need to ensure activities are well sequenced and coordinated. FMIS 10.6 Strong and sustained government and MOF commitment is essential. Since these projects can take 7â€“10 years or longer for completion, it is necessary to maintain this commitment over a long period, which can extend beyond an election cycle. This commitment can be achieved better if projects are framed as public expenditure management systems reform, rather than just accounting systems reform. In Vietnam, government support was particularly important to address project-staffing issues, resolve business processes issues, and tackle interorganization issues. 10.7 Comprehensive FMIS implementation as in Vietnam takes about 10 years to complete. These projects are characterized by slow disbursement rates over the initial years, which are spent in systems design, testing and piloting. The disbursement profile needs to be adjusted accordingly. 10.8 Continuity in the project team contributes to success. There was stability on both government and Bank side, and key members of the team that designed the project remaining engaged in its implementation for the first few years ensured an effective transfer of knowhow to field-based and other Staff. 10.9 Systems sequencing is key. The TABMIS implementation in Vietnam illustrates how project implementation for similar systems needs to be phased44 to achieve significant outcomes such as good budgetary control and cash management early in the Project. It is necessary to first implement modules to cater to core budget execution processes and processing of payments and receipts transactions, across government, before going on to other noncore elements, such as fixed assets/inventory management, human resource or fleet management. 10.10 Systems deployment strategies should make sure that a large part of the budget is covered from the outset. A major part of the budgetary resources should be subjected to ex-ante budget and cash control so that meaningful fiscal control and cash management is possible at an early stage in the deployment. A deployment across treasury offices through which these transactions are routed, may be sufficient for this purpose. 10.11 Spending unit access is a challenge in the use of treasury centric systems. The lack of spending unit access inhibits ownership at the line ministry and end-user level. This often leads to line ministries developing independent financial systems for their own management use, as in the case of Vietnam. Avoiding this outcome requires that once the basic treasury system has been implemented and is operating in stable mode, the large spending units be empowered and made responsible for the bulk of transactions. 10.12 Availability of specialized IT expertise within the Bank project team is critically important to assure the quality of design and supervision of the projects that support development of complex IT systems. The Bank team needs to have experienced specialists on board or available to advise the client on important technical issues during the design and implementation phases. These specialists also need to be familiar with procurement practices and procedures for IT related procurements and the World Bank rules under which they will need to be applied. 10.13 Staff in the implementing agencies should recognize the inevitability of change. Resistance often comes from staff responsible for operating the legacy systems as well as those who are used to doing their regular work in a given way and are reluctant to change. MOF management has a major role to play. 10.14 The design of the main consultancy package has proven to be a significant bottleneck for TABMIS implementation. The consultancy package should be designed to ensure that appropriate consulting help is available throughout the various stages of the project. 10.15 Not all needs may be foreseen during the project's preparation and original design. The number of system users of TABMIS increased threefold between design and full rollout and had to be accommodated.
P120629 | Second Sustainable and Participatory Energy Management (PROGEDE II) | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2018 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/414611577727294105/text/Senegal-SN-Second-Sust-Part-En-Mngt-SIL.txt | http://documents.worldbank.org/curated/en/414611577727294105/pdf/Senegal-SN-Second-Sust-Part-En-Mngt-SIL.pdf | The following lessons are adapted from the ICR: An institutional arrangement that involvesboththeenvironment and theenergy sectors needs to enablethe development ofa consistentoverarchingapproach. For example, introduction of biogas systems using bio-slurry can helpto increaseagricultural production and reduce deforestation. Such anarrangement can also facilitatethe working relationshipbetween forestry and energy staff and havea positive impact on interactions toenhanceforestry taxation,whilethe adoption of improved stoves can helpto reduce the costs of energy for households. Whenprojectsconsistently and significantly overperformon a similar set of targets, it maybe necessary to reconsiderthe approachto designing the results framework. If there is to be a follow-upoperation the stakeholdersshould bepersuadedto acceptmore ambitious targets. In designing forest managementsystems, consideration maybe given to anincrease in the geographical scope to help ensure the sustainability ofresults.Unregulated producers of charcoal are able to supply cheaper products to the markets and canundercutthe more expensive sustainable wood fuels. If suchproduction isallowed to continue, it cancompromisethe sustainable management systems that have been set up.Asillegal loggers are pushed out to the edges of the projectareas, the need to increase the size of the project area and even make the project regionalbecomesmoreurgent. It is important to consider that absorption capacity may remaina challenge forfinancial interventions at the local level. Even though funding for local households to receive biogas systems wasavailable, a considerable share of the target group could not provide its own financial contribution tobackup thefinancing provided by the World Bank and was therefore deprived of such anopportunity. The projectat the same timecould not achievethe initially envisaged levels of cookstovedistribution. In the next operation, it may be worthconsidering either lowering production/distribution targets andintroducing financial solutions enabling wider engagement fromthe local households/producers/artisans, including possibility of in-kind contributions from beneficiariesascounterpart sub-project funding.
P120631 | Comoros - Emergency Crises Response Project | Eastern and Southern Africa | Comoros | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/134161468028729646/text/ICRR-Disclosable-P120631-06-09-2016-1465498456764.txt | http://documents.worldbank.org/curated/en/134161468028729646/pdf/ICRR-Disclosable-P120631-06-09-2016-1465498456764.pdf | The ICR (pages 28-29) draws the following main lessons from the experience of implementing this project.(1)Modified Cash-for-Work activities can beconsideredeven in nonemergency situations, fordisadvantagedcommunitieswithin countries that are poorly served by social and economic infrastructure.Given the challengesassociated with reaching the poorest households in such communities, suchprograms mayhelp inlong termdevelopment,if a technically robust roster of public works activities selected by communitiesisimplementedthrough closesupervision byintermediaries (engineering consultants and contractors) asdone in the case of thisproject. Building a savings component into the program couldalso be considered for further enhancingdevelopmentbenefits.(2) Creatingassets through community managed development can be a viable option in countrieswhere the government does not assume responsibility for providing basicinfrastructure inpoorcommunities.The experience of this project demonstrates that community-managed developmentisusefulforcreating assets that are of high priority to communities.(3) Includingindicators related togender can be useful for targeting women as beneficiaries. In the case of this project, specific inclusion ofindicators relating to womenhelped to ensure that the weakest and most vulnerable households were included and benefited fromthe project.(4). An implementing agency that is experienced in handling emergency projects is a good resourceincountries prone to external and internal shocks.While in the case of this project,thesemi-autonomous status of the implementing agency helped,some kind of representation of beneficiary communities onthe Board of the implementing agency may be helpful,especially in difficult economic and political circumstances.
P120636 | Land Administration Project - 2 | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/460521609406326577/text/Ghana-GH-Land-Administration-2.txt | http://documents.worldbank.org/curated/en/460521609406326577/pdf/Ghana-GH-Land-Administration-2.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1.Establishing sound management through steering committees can helpproject management andcomponent ownership. In this project, the project established a steering committee to ensure that that five ministriescould work together.Each ministry took responsibility for their mandate and made sure that their activities succeeded.Furthermore, the Human resources strategy and training plan were developed at an early stage, and this plan included arrangementsforpost-graduate training for twenty staff. Each staff member was given specific roles and associatedtasksupontrainingcompletion. This method proved to be effective.2. It is necessary toconsider lessons fromprevious projects, prior to finalizing the next phase. Although this was a follow-up project, the draft of theImplementation Completion Report (ICR) did not include any lessons from the project. And thisproject ended up repeating thesame mistakes as the prior project, especially regarding complexity and overstating what was achievable.3.Implementation and completion of major Information Technology ( IT) systems was not realistic within a five year projectcycle. The IT system for this project was not completed on time and this impacted the overall achievement of the keyproject indicators. The design and feasibility analysis of IT systems need to be concluded prior to appraisal and be fullyoperational within a three year period. The ICR recommends that if the IT system is not contracted within the first year of theproject, then the project should rethink and take appropriate actions to either simplify or downsizeexpectations.4. Although land projects can be highly beneficial if they are successfully completed, they canbecomplex, expensive and time consuming.Teams need to seriously consider such projects from a practicalimplementation perspective, and include experienced land administration and land management specialists both at preparation andduring implementation.Professional expertise is especially needed at theteam leader level.IEGdraws the following lesson.1. Lack of attention to monitoring and evaluation systems can impede the ability of theproject to measure and document its achievements. The ICR highlights as key areas of achievement of theprogram,human resources planning and training.However, the project failed to collect supplementarydata todemonstrate success at the outcome level. This failure to pay attention to the monitoring and evaluation system led to inadequateindicators that could fully capture the project story and document its achievements.
P120660 | LIBERIA Electricity System Enhancement Project (LESEP) | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2017 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/875031538691596361/text/Liberia-LR-Electricity-System-Enhancement-FY11.txt | http://documents.worldbank.org/curated/en/875031538691596361/pdf/Liberia-LR-Electricity-System-Enhancement-FY11.pdf | Following are lessons learned are largely drawn from the ICR, with some modification of languages.1 . Potentialperverse incentives from pre-grant-financing an output-based grant can be mitigated through use of positive and negative financialincentives. The management contractor normally does not undertake financial and commercial risks. Hence, performance risksby the Management Contractor in this project was addressed by the non-compliance penalties set by the Management Contract if theagreed results are not achieved. Failing to reach the GPOBA target would expose the Management Contractor to the risk of forgoingsuccess fees and incurring significant non-compliance penalties. As a result, the Contractor had met the GPOBA target. Thisillustrates the need for a clear and enforceable contract clause to ensure performance.2 . Low-incomecustomers need to be connected strategically to optimize the benefits. IDA financed the extension of the backbonemedium voltage network to the GPOBA targeted communities. This allowed LEC to connect the more affluent customers within thecatchment area, who provided a revenue base and incentives for LEC to roll-out low-income customer connections under the GPOBAprogram. This highlights the importance ofa holistic electrification strategy.3 . Tight andtimely coordination and cooperation among development partners and within the Bank are critical in the power sector in fragilecontexts. IDA and other development partners were well-coordinated to support the energy sector reconstruction. Theproject did not achieve the reliability target (interruption rate) in Monrovia partly due to the network nature of the electricitysystem requiring very tight coordination among the segments of the system. The project covered only part of the distribution andpower generation segments of the system. The transmission network was outside the projects scope and did not keep up withthe projects expansion of distribution network and generation capacity. On the other hand, the Bank energy team timelycollaborated with the Bank macroeconomic team to resolve the LECs HFO licensing and competitive HFO procurement throughpolicy operations (PRSDPO-III).
P120664 | Urumqi District Heating Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/163591483123580143/text/ICRR-Disclosable-P120664-12-30-2016-1483123566678.txt | http://documents.worldbank.org/curated/en/163591483123580143/pdf/ICRR-Disclosable-P120664-12-30-2016-1483123566678.pdf | The first three of the following lessons are taken from the ICR with some adaptation of language. The fourth is drawn byIEG.1. Careful planning and a well-developed communication strategy can help to avoid the risk of over-investingin under-utilized assets and to optimize resource use while being consistent with environmental objectives. Prior analysiscan help to reveal the sensitivity of least-cost options to different scenarios and thereby inform policy dialogueand investment decisions. Ultimately government leadership is essential to navigate any conflict of objectives, such as betweenaffordable and clean heating.2. Local political leadership and policydirections may change during implementation. Design needs to be sufficiently flexible to take this intoaccount.3. Infrastructure and technical assistance projects can help create favorable conditions for sectorreforms. The project expanded metering, building-level substations, variable flow operation across a vast network,integrated billing and accounting, and installed systems to manage energy and information. This can provide a strong basis forcity-wide heating system reforms.4. Careful and thorough consultation and analysis at the preparation stage canassist in the identification of risks of exogenous factors that would have a major impact on the project. In this case, anew policy concerning conversion from coal to gas-fired heating began to be implemented less than a year after Board approval. Thisrisk was not taken into account based on the municipal Governments rejection of the widespread use of gas during appraisal.Wider and more in-depth consultation with National and Regional Authorities and other interested parties may have enabled a moreaccurate assessment of the likelihood of the policy change and the design of appropriate mitigating measures.
P120707 | PNG - Small and Medium Enterprise Access to Finance Project | East Asia and Pacific | Papua New Guinea | Blend | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2021 | 2022 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/781491636066347607/text/Papua-New-Guinea-PNG-SME-Access-to-Finance-Project.txt | http://documents.worldbank.org/curated/en/781491636066347607/pdf/Papua-New-Guinea-PNG-SME-Access-to-Finance-Project.pdf | The ICR contains the following lessons which IEG presents with some modificationChanges in projectindicators need to be made formally to be credible. While project indicators may change over time because of changesin circumstances, these require full documentation so that the logic of why the changes occurred can be analyzed. In the case ofthis project, inadequate discussion and documentation of the changes in the ISRs made the rationale for changes impossible tofollow.Institutions required to provide data deserve feedback. If implementing institutions arerequired to provide data on their operations, it is important that they receive feedback from the analysis of the data theyprovide. In the case of this project, failure to provide BSP with a meaningful feedback on the data submitted was at least partlyresponsible for its withdrawal from the RSF and possibly limited what it might have learned from theproject.Transfer of knowledge from consultants to local staff enhances capacity building. Fordecades it has been agreed that using highly qualified consultants to initially staff PIUs in low-capacity environments iswarranted, but over time local capacity requires strengthening for benefits to be sustainable. In the case of this project, littleknowledge transfer occurred so that when BSP withdrew from the RSF, the consultants departed, and the project essentially came to ahalt because of lack of an understanding of the project on the part of PNG counterparts.When designing a creditguarantee program that also provides training, implementing the training program after SMEs have qualified for loan guaranteesreduces the possibility that participants in the training program will not be part of the lending program. In PNG, theopposite sequencing occurred. As a result, only six percent of training beneficiaries managed to access loans.
P120788 | Central Asia Hydrometeorology Modernization Project | Europe and Central Asia | Central Asia |  |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099031324121020046/text/P1207881aba7b50c818181128709ba785f5.txt | http://documents.worldbank.org/curated/en/099031324121020046/pdf/P1207881aba7b50c818181128709ba785f5.pdf | The ICR (p. 21-22) provided several lessons learned which were adapted by IEG: If capacity building doesnot go hand-in-hand with modernization efforts, this may jeopardize the sustainability of project outcomes. This projectcreated an enabling environment for modernization in the Republic of Tajikistan and Kyrgyz Republic by ensuring that the agencieshad the capacity to absorb and operate the new tools and equipment. The project developed Development Business Plans, increased theoperating budget, and trained the staff of the entities to build institutional, technical, and managementcapacity. User satisfaction surveys can be useful tools to understand the user needs and drive servicedevelopment but has limitations. In this project, a user satisfaction survey was conducted to assess the quality ofweather forecasts. The data collected provided deeper insights into user requirements and preferences and will allow to improveservices accordingly. However, user satisfaction surveys can only provide information about the users perception and is notsufficient to measure the actual quality of services (like the quality of the weather forecasts). Independent/unbiased indicatorswould be needed to allow to measure the actual quality. Combining local knowledge with international expertisefrom development partners and host government leadership allows for the achievement of sustainable project outcomes. Inthis project, a wide range of development partners including the World Bank, the World Meteorological Organization (WMO) and theGlobal Facility for Disaster Reduction and Recovery (GFDRR) provided specialized knowledge that complemented the hydroment agenciesunderstanding of the local context.
P120798 | Nigeria States Health Investment Project | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/234561635166579086/text/Nigeria-NG-States-Health-Prog-Invest-FY12.txt | http://documents.worldbank.org/curated/en/234561635166579086/pdf/Nigeria-NG-States-Health-Prog-Invest-FY12.pdf | The ICR (pp. 50-51) offered several lessons and recommendations, including the following lessons restated byIEG:Effective service provision can be tailored to fragile and conflict areas to support access toquality health care. In the context of the insurgency in the North East, the project adjusted by providing mobile clinics,direct facility financing that guaranteed regular funding to facilities, andthe introduction ofpsychosocial support inroutine health care delivery. While the impact of such approaches was not evaluated, the number of persons reached in insecureenvironments in the states of Adamawa, Yobe, and Borno continued to increase in spite of fragility, conflict, andviolence.Rigorous counter-verification mechanisms are facilitated by enhanced separation ofinstitutional functions. Under the initial parent project, quantitative verification was undertaken by the State PrimaryHealth Care Development Agency, and qualitative verification was carried out by Primary Health Care Departments and LocalGovernment Areas, complemented by community-based ex-post verification. This arrangement showed weaknesses under the originalproject. Hence, the Additional Financing of 2016 introduced independent non-state actors consisting of Independent VerificationAgents and Contract Management and Verification Agencies.An early transition plan for financing mayfacilitate PBF financial sustainability. At project closing, there were concerns and challenges regarding the sustenanceof PBF-related incentives. By contrast, the outlook at entry was favorable, as external contributions from donors represented asmall proportion of total health financing in Nigeria, and a National Health Bill was expected to generate an additional US$3.14per capita to the US$8 per capita public spending on health at that time. However, macroeconomic challenges that emerged during thedecade revealed the need for concrete and realistic long-term financing options.
P120825 | MW: Mining Governance and Growth Support Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/156551564930868431/text/Malawi-MW-Mining-Technical-Assistance-Project.txt | http://documents.worldbank.org/curated/en/156551564930868431/pdf/Malawi-MW-Mining-Technical-Assistance-Project.pdf | The design of extractive sector projects needs to take commodity price projections into consideration.Commodity prices being typically cyclical in nature, the viability of an operation cannot be based only on the prevailing level ofprices at appraisal, should they be at a peak, but needs to take into account the real possibility of a decline over the short tomedium term. To the extent that the operation can focus on the basics, such as enhancing geological knowledge, streamliningadministrative processes, improving sector governance, etc., exposure and hence vulnerability to exogenous factors such ascommodity price fluctuations can be reduced. Project preparation needs to include detailed analysis to ensure theaccuracy of baselines upon which results indicators are based. Equally, target values need to strike a balance between ambition andreality. In the project, for instance,the Efficiency indicator of number of days for issuance of mineral rights wouldhave been more convincing if the target number of days was shown to have been based upon global or regional benchmarks for similarapproval processes and the baseline to have been correctly estimated at appraisal.
P120830 | Rio Grande do Sul SWAp | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/187541588904435475/text/Brazil-BR-Rio-Grande-do-Sul-SWAp-SIL.txt | http://documents.worldbank.org/curated/en/187541588904435475/pdf/Brazil-BR-Rio-Grande-do-Sul-SWAp-SIL.pdf | This review concurred with thekey lessons identified in the ICR, which are summarized and rephrasedbelow: To maximize implementation readiness and results,Bank project teams need to be providedadequate time, and appropriate technical and financial resources.Project implementation is facilitated or hinderedby the quality at entry.The identification ofproject components andunderlyingsub-components need to betheprimary focus of both the design and implementation phases ofa project.Stringent deadlines for project approval,limited staff, and lack of sufficient mechanisms to offset thelimits in capacity, are likely to compromise the project design and implementation. In the case ofcomplex or innovativeprojects, additional time, financial and technical resources should be provided to the task team at preparation to ensure qualityat entry that will determine smooth implementation.Implementation shortfallsin this project resulted from a task teamwith limited experience tasked to meet an unrealistic deadline for delivery. AssociatingTAactivitieswith investments can helpachieve sustainable outcome across all result areas.The provision ofTA activitiesto the agencies engaged in carrying out the Eligible ExpenditurePrograminvestmentssignificantlycontributed to theprogress toward the PDO targets. The TA activities alsohelped enhance the sustainability of achieved outcome by institutionalizing the underlying changes in public sectormanagementand incorporatinglegal and technological tools. An effective resultsframework needs to link activities to PDOs and effectively measure theTA performance .Identification of indicators and their measurement methodologies need to be participatory usingadequateexpertise and experience to fully reflectpriorities of key stakeholdersand avoid indicators with limited measurability.All indicators should be clearlyassociatedwith the PDO to make sure that links between the project activitiesand outcomes are clearly drawn.The Results Framework for the program partially failed to account for and measure someimportant results and outcomes, especially those accomplished within the TA component. Incorporating TA-linked outcomes and outputsinto the Results Framework would have enabled a clearer evaluation and better communication of importantproject achievements.In the future, incorporating more indicators to measure theperformance of TA would enhance the design and achievementof the outcome sustainability. While staffturnover in the World Bank team and intheBorroweragencies is unavoidable, implementation arrangements are needed to ensure the continuity of action towardthe project outcome.On the government side, key ingredients underpinning project performance included: (i)sustained government ownership and commitment; (b) strong leadership for project oversight and management; and (c)afunctionally dedicated Project Management Unit, whether composed of government staff or consultants, with an explicit mandate towork on the project. Leadership changes associated with four different task team leaders over the seven-year life of the projectalso contributed to some difficulties in implementation. Both the WB and the Borrower needs to integrate mechanisms to ensure thatrotation of staff doesnt affect the progress of project implementation. The impact of aprogramor a project lies in large part in the way it incorporates activitiessupporting long-termsustainability.A less ambitious project design that incorporated sustainability mechanisms such as continuedfunding schemes could produce more meaningful and long-lasting results and stronger impact. For instance,requiring acopayment could have produced a more sustainableproject result, or focusing on larger scale technological changes could havemade a stronger impact. Impact evaluation activities should be given a more central focus and included during the design stage.Design of an appropriate ME system for the project as a whole along with each specific area could amplify the projectssuccess, especially in the long term. Impact evaluations within each sector should be encouraged, while technical staff shouldreceive training on how to better design and implement such evaluations. Additionally, a more rigorous independent midtermevaluation should be carried out within and across the different project areas. This would help ensure thattheprojectproperly identifies appropriate adjustments when activities are not achieving the desired results andimpact.
P120836 | Maharashtra Agricultural Competitiveness Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/234261570478468306/text/India-IN-Maharashtra-Agric-Competitiveness.txt | http://documents.worldbank.org/curated/en/234261570478468306/pdf/India-IN-Maharashtra-Agric-Competitiveness.pdf | The ICR included four lessons. The following two are emphasized with some adaptation oflanguage: Market-led crop diversificationthat ispartnered with the private sectorensures sustainability beyond the project. At closing, a majority of the contract arrangements that were initiated withthe project facilitation remained operational. According to the private sector entities, successful partnership between the privatesector and Farmer Producer Organizations is more likely to be sustained beyond the project when partnerships are based on mutualtrust, financial incentives, and when maturity of the participating organizations areestablished. To ensure effective implementation, a tailored and flexible implementation timeframeneeds tobe considered for projects that are designed for implementation of reform-linked interventions.As the project experience showed, such projects need additional time for testing and learning processes and may facedifficulties with availability of qualified Service Providers. Along these lines, the project experience also showed that thepiecemeal approach to extension does not support effective planning and implementation.
P120843 | BD Private Sector Development | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040106252211962/text/P12084309567af06d091ff07f1a971c5a00.txt | http://documents.worldbank.org/curated/en/099040106252211962/pdf/P12084309567af06d091ff07f1a971c5a00.pdf | Anumber of lessons and recommendations were discussed in theparagraphs 74-81of the ICR, which are rathergeneric for this kind of special economic zones projects. This review concurs with five lessons which are summarized and rephrasedbelow:(i) Building institutional capacity to oversee complex special economic zones (SEZ) projects takestime.The key lesson from this project is that it takes time toestablish well-functioning institutionsandentities that can overseethemanagement and implementation of a project supporting an EPZ. These projects may take timeto mature and evolve towardrealistic targets. During project implementation,the rate of disbursements isgenerallynon-linear, because oversight agencies and managersare first involvedin institution building, withdisbursement achievements that arelow in early years and accelerating as institutional capacity firms up.Institutionalarrangements should strive to strike a balance between ensuring sufficient the local requirements and international standards,whileavoiding overly burdening the process with bureaucratic procedures.(ii) Agencies overseeing the SEZprojectsneed to rely ona diversified and competent expertise. Entities and agencies managing EPZ need tohavethe diversified expertise required to handle all stages of the SEZ projecttransaction cycle, including preparation,procurement, and implementation. Particularly, investments in hard infrastructure and skills-upgrading in SEZprojectshaveto mitigate social and environmental risks,make work environments more inclusive, andadheretosocialregulations and environmental standards. To avoid adverse outcomes, the agencies need to acquirethe specificexpertise tailored to local contexts and be aware ofgood international practices through hiring and sustainedtraining.(iii) Government commitment and coordination are central in the oversight of multiple entities involvedinimplementing SEZprojects. SEZprogramsand projects entail a multitude ofactivities across public and private sectors, including regulatory authorities, line ministries,and private actors andinvestors.This interaction of these different actors can be a source ofbottlenecks from limited capacity of certainagencies, and can undermine clarity for potential investors, and create unneeded competition between stakeholders.Thisproject mitigated many of these risks bycapitalizing on the comparative advantage of respective zone authoritiesbyreducingtheir overlap. In the context of this project, one entity (BEZA) had a strong capacity for investmentpromotion and facilitation, includingland and infrastructure development, and it took the lead insupporting industrialdevelopment and manufacturing. On the other side, the BHTPA supportedSMEs with skills programs, coaching and training, andsupporting quality accreditation. All this arose from the Government presence, commitment and coordination throughout theperiod of project implementation.(iv) Flexibility, and proactiveness are principles that can help inaddressing theimplementation challenges inSEZ projects.The project underwent multiple restructuringsboth to scale down its scope to factor in implementation challenges, and to raise targets whenthey proved too modest. Thesechangesmay not have been possible without a committedproject team and country management, and thededication fromthe leadership of implementing agencies.Where a projects success is contingent on key individuals in implementingagencies to act as champions, proactive Bank teams should look for or create such champions.The need for this change wasviewed as critical by the Banks team and arose from a productive dialogue between the WB and Governmentteams,including the embeddedexperts that provided the requiredtechnical capacity.(v) The success ofzone programs in Bangladesh has brought lessons on policy interventions that have resulted in significantinvestment, employment-generation, and social and environmental practices. A last lesson from this project isthatSEZs can bea lab for experimenting with regulatory innovations and soft policies that can enable governments tofind out what works best in a relatively low-cost way that can then be generalized for the entire country. For example, (i)the Child Care Guidelines adopted in the EZs are already being expanded outside of zones, and (ii) the Economic Zone EnterpriseSurvey from 2021 in Bangladesh found that tenant firms were motivated to move into zones by the quality of infrastructure andservices, proximity to transport infrastructure, ease of administrative procedures, and access to land.
P120860 | Catastrophe Development Policy Loan DDO | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2011 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/262751624028803088/text/Peru-PERU-CAT-DDO.txt | http://documents.worldbank.org/curated/en/262751624028803088/pdf/Peru-PERU-CAT-DDO.pdf | The ICR draws the following main lessonfrom the experience of implementing this operation, with some adaptation oflanguage. When prior actions and indicators are selected appropriately, a cat DDO can provide significant assistancein influencing important disaster-related policy reforms. In this operation, annual budgetary allocation for DRM was clearly anappropriate quantitative indicator for driving sector reforms, aimed to promote disaster risk management in prioritysectors.The IEG draws the following lesson from this operation. For a Cat DDO that is renewedmultiple times, revisions and updates of indicators and targets around each renewal are important for monitoring and providingevidence on downstream operationalization of reform trajectories. Where indicators are updated, this provides an opportunity tocontinue to influence sectoral reforms even without new prior actions. Where indicators are not updated, it becomes more difficultto know whether reform trajectories are being sufficiently sustained or are lagging.
P120867 | Vietnam: Global Partnership for Education - Vietnam Escuela Nueva Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2013 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/286131496157233598/text/ICRR-Disclosable-P120867-05-30-2017-1496157220590.txt | http://documents.worldbank.org/curated/en/286131496157233598/pdf/ICRR-Disclosable-P120867-05-30-2017-1496157220590.pdf | The ICR (pp. 25-26)draws interesting lessons on the nature of the intervention. Inaddition to these, a numberof other lessons are listed below:Lesson 1: (from IEG) Scale-up generally succeeds due to multiplecomplementary factors. In this case, scale-up of the VNEN model can be explained by strong government buy-in stemming fromthe pilot program tested in a prior Bank-supported intervention, a track-record of efficacy in the education sector, a plannednation-wide reform of the curriculum that provided a goal-post for the project, an effective training cascading model, and aproactive communication campaign that enabled demonstration effects.Lesson 2: (from IEG)Capacity-building activitiesare critical elementsin the implementation of impact evaluations.In this case,suchskill transfer not only served the project and the timely implementation of data collection and analysis, but alsoprepared the ground for continued impact evaluation research on the project, and more generally in thesector.Lesson 3: (from IEG)Leveragingthe wealth of information that stems from impactevaluations to complement evidence emanating from monitoring frameworks is important. It allows capturing outcomes further down theresults chain even for a project with a short time span. The key isto time data collection and analysisof the impactevaluation well so thatthey can feed into formal reporting processes.Lesson 4: (from the ICR)Teacher training with fewer cascade layers as well as the distribution of training materials prior to training can be beneficialfor trainees. In the VNEN project, developers of the pedagogical materials gave trainings directly to teachers at thedistrict level, thereby eliminating two layers from the cascade-style training traditionally used in Vietnam. An additional benefitto using VNEN teachers as trainers was that they could provide follow-up training at the school level and continuous professionalsupport for teachers. Moreover, the training materials were sent to teachers two weeks prior to training for self-study, so thatteacherscould come prepared with questions, enablinga more productive participatory training activity.
P120867 | Vietnam: Global Partnership for Education - Vietnam Escuela Nueva Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2013 | 2016 | 2019 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/254991560184295154/text/Vietnam-Education-Projects-School-Readiness-and-Escuela-Nueva.txt | http://documents.worldbank.org/curated/en/254991560184295154/pdf/Vietnam-Education-Projects-School-Readiness-and-Escuela-Nueva.pdf | 5. Lessons 5.1 IEG identifies the following lessons from its evaluation of the two operations\. â€¢ In addition to lending, the World Bank can add value through the transmission of knowledge from experiences and lessons that help shape reforms. This included World Bank economic and sector work, study visits, the introduction of international experts, and the introduction of lessons gleaned from an experienced team that built on the long-standing relationship of mutual trust between MOET and the World Bank. The World Bank's knowledge capability was a useful complement to the implementation capacity of the education system in Vietnam. For SRPP, the World Bank advocated and helped support the rollout of a systemwide approach through preschool accreditation to improve quality. Since closure, the government has moved to universalize enrollment beyond kindergarten and has further refined the school selfassessment process. VNEN introduced a new pedagogic philosophy into the primary education system. Many teachers have expanded their pedagogical skills and the model laid part of the foundation for the current curriculum reform and associated teacher training. â€¢ When significant pedagogical changes are required of teachers, incentives, support, and long-term commitment are needed (probably more than education systems realize). The changes envisioned in both of these operations were neither simple nor easy. Studies show the importance of follow-up support to facilitate the application of in-service training. Within the education system, existing mechanisms provide follow-up support to teachers such as school visits, principal feedback, and peer-to-peer learning at school cluster meetings. Some of these mechanisms were applied under both projects, but VNEN employed them more extensively. For example, during the school year, two to four technical support team meetings and training sessions were conducted for VNEN schools. These meetings and sessions involved classroom observations, interviews with teachers and school management, review of logbooks, and exchange of experiences with principals and teachers. E-learning was used under SRPP for follow-up knowledge. Although it may serve to bridge at least some of the existing gaps in follow-up support, e-learning is unlikely to represent a panacea. Constraints in the implementation of SRPP e-learning modules suggest the need to address these issues. This emphasizes the need for long-term commitment and to leverage existing mechanisms more fully to bring about the kind of quality teaching envisioned. â€¢ When scaling up or adopting a systemwide approach, it is important to understand and design this approach in accordance with the decentralized context and challenges faced at the various levels of administration. SRPP required provincial and district officials to provide follow-up support after faceto-face cascade training and to provide technical knowledge to the preschool accreditation and school self-assessment process. Follow-up support to teachers in SRPP and VNEN was implemented more effectively in some provinces than in others. An analysis was conducted (by SRPP) to understand how the decentralized systems operated and to detect capacity constraints. Yet design and implementation did not differentiate resources or technical support to provinces and districts to address differences in capacity. As a result, disadvantaged provinces had much lower percentages of accredited schools. The DLIs set an appropriate incentive for the central level but not for provincial and district levels. â€¢ Targeting disadvantaged areas does not translate into targeted efforts for specific vulnerable groups. The self-selection process under VNEN was used to encourage a demonstration effect in locations where ethnic minority and other 27 disadvantaged populations were present. The school selection process under VNEN favored the best schools (for demonstration effect) in locations where ethnic minority and other disadvantaged populations were present but not necessarily schools in which such children were concentrated. The targeting strategy was implemented to generate the momentum needed to support the further adoption of the model in all provinces (this resulted in greater voluntary adoption in the wealthiest provinces). Although this approach is sensible, it may have missed opportunities to target even more ethnic minority children. SRPP provided lunch subsidies to disadvantaged families, but all other aspects of the project were applied systemwide. A social assessment detected multiple enrollment barriers for ethnic minorities, such as distance from school or parental knowledge, that were not addressed. The baseline survey substantiated the higher level of vulnerability among ethnic minority children (compared with those who speak Vietnamese). Considering the critical juncture for language development during the early years, targeted action was needed to support learning in the first language and introduction to Vietnamese. â€¢ When scaling up, the importance of consultation and communication cannot be underestimated. The literature suggests that scaling up programs requires those promoting the innovation to convince stakeholders of the effectiveness of the intervention. Both of these operations had broad political support. Despite the attention to communicating with stakeholders, particularly during the early stages of VNEN implementation, the scaling up of the model proved challenging. The communication challenge was associated with substantial changes for teachers and divergence from what parents traditionally experienced in school and, more particularly, the expansion of the model to nonproject voluntary schools that did not benefit from the same concentration of support as their project-based counterpart schools. Education is a heavily debated topic in Vietnamese society, suggesting the critical role for sustained and sophisticated communication regarding planned change.
P120895 | Infrastructure & Institutions Emergency Recovery | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/336591560264247596/text/Haiti-HT-MST-Infra-Instit-Emerg-Recov-j.txt | http://documents.worldbank.org/curated/en/336591560264247596/pdf/Haiti-HT-MST-Infra-Instit-Emerg-Recov-j.pdf | The ICR identified a number of lessons, the three most important are presented here with some modification oflanguage: Effective coordination among donors, key stakeholders, and NGOs led by theGovernment is essential for efficient disaster response. The project experience shows that coordination was importanttodefine achievable and solid milestones and indicators, develop a cohesive reform framework, and address issues of capacitybuilding. Setting baseline and target values in an emergency context is a challenge.Therefore, at project appraisal the design of the ME and financial management frameworks could be simple. The project caninclude components to build the capacity of institutions and once the capacity is built, the frameworks can be refined to carry outeffective monitoring. The project demonstrated successfully how a new dual type of emergencyproject i.e. mixing humanitarian activities with sustainable reconstruction planning can effectively support acountrys disaster recovery effort.
P120909 | Lao PDR Upland Food Security Improvement Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/545531468178189618/text/ICRR14842-P120909-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/545531468178189618/pdf/ICRR14842-P120909-Box394823B-PUBLIC.pdf | The following two lesson are emphasized with some adaptation of language:Emergency projects should primarily focus on the immediate emergency needs. An emergency project can be helpful to kick start associated longer-term programs, however, care should be taken to avoid including activities which require significantly more time to design adequately and achieve their development objectives, and which may be negatively affected by broader structural institutional and policy issues.Demand-side assessments among potential beneficiary farming households at the project design stage are an important tool to better understand the acceptability of proposed agricultural technologies, particularly seeds and fertilizer. This would be particularly important in situations where there is limited household cash to purchase inputs, options to rotate cropping to new land (slash and burn), and likely strong food preferences. In this case, there was limited knowledge of what farmers or households in the proposed beneficiary areas had expressed a need for in terms of technologies or subsistence commodities.
P120910 | Guinea-Bissau: Emergency Electricity and Water Rehabilitation Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2015 | 2019 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/564601548364899672/text/Guinea-Bissau-GW-Emergency-Electricity-Water-Rehab.txt | http://documents.worldbank.org/curated/en/564601548364899672/pdf/Guinea-Bissau-GW-Emergency-Electricity-Water-Rehab.pdf | Four lessons are dawn by IEG based on the information in the ICR and that provided by the projectteam.A full analysis of the obstacles to the securing of fuel to operate generators and the fundingof maintenance and repair of equipment is necessary to avoid jeopardizing the achievement and sustainability of developmentoutcomes. Although the proposed use of HFO to operate the generators was the least cost solution and also less vulnerableto theft and embezzlement, Guinea Bissau was unable to secure areliable source ofsupply, and storage facilities werealso lacking. Due to the weak financial viability of the EAGB, a long-term HFO purchase agreement could not be concluded with thesuppliers. Similarly, EAGB could not draw up a plan or obtain funding to repair the project-financedgenerators.Because of the poor state of the electricity and water distribution networks in fragilecountries, restoration of power supply aloneis likely to be insufficient to attain the desired development outcomes.Both the electricity and the water distribution networks in Bissau were in poor condition. Even though power supply wastemporarily improved after the installation of the generators financed under the project, provision of service to consumersremained intermittent, with voltage variations and a high risk of water contamination from worn-out and leakingpipes.Close supervision of the project by the Bank team and the presence of an adequately staffedproject implementation unit can facilitate the completion of project activities and the achievement of project outputs and outcomesin fragile countries even during political instability. The project was intensively supervised with at least threemissions per year to the country to supervise project implementation and provide assistance to the borrower. As a result,theproject was able to resume its activities nine months after the military coupand achieved intended outputs before theextended closing date.Although the presence of an experienced and adequately staffed projectimplementation unit was instrumental in the smooth implementation of the project, the exclusion of the main projectbeneficiarys stafffrom project implementationcan weaken the ownership of the project by thatbeneficiary and pose a threat to the sustainability of development outcomes. As the electricity and water utility, EAGBwas the main recipient and beneficiary of the project outputs. However, the project implementing unit existed under the Ministry ofEconomy had an exclusive authority in the implementation of Bank projects, and did not include any staff members fromEAGB.For example, the project implementing unit did not consult the utility during the procurement of generators. This createdresentment on the EAGB side and weakened the utilitys ownership of the project.
P120913 | Strengthening the Effectiveness of the Social Safety Net Results-Based Financing Specific Investment Loan | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/674971551378796270/text/Moldova-Strengthen-SSN-Results.txt | http://documents.worldbank.org/curated/en/674971551378796270/pdf/Moldova-Strengthen-SSN-Results.pdf | The ICR (p. 26) provided three lessonson the project and reiterated (in an annex) anumber ofimportant technical lessons from the evaluation of theAjutor Social program. This ICR reviewpartially concurs with twoof those lessons and takes them one step further. .Results -based financing allows flexibilitytomaintain implementationof social safety netreformsin the period of political change, but it cannot serveas a safeguard against major policyreversals that canalterthe overall reform trajectory. Thesustainability of investment inmanagement information systemsrequires high levels of capacitybuilding.Better coordination and synergies between World Bank projects andimplementing agenciescan improvethe likelihood of achieving and sustaining results.
P120932 | China Technology Needs Assessment (TNA) | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/957421498054306442/text/ICRR-Disclosable-P120932-06-21-2017-1498054298852.txt | http://documents.worldbank.org/curated/en/957421498054306442/pdf/ICRR-Disclosable-P120932-06-21-2017-1498054298852.pdf | The first three lessons are taken from the ICR, with some adaptation of language, and the other two are drawn byIEG:(i) Climate technology transfer requires close collaboration between all stakeholders, primarily the public andprivate sectors, with an important role to be played by public sector entities, in guiding climate technologies that provide apublic good. The public sector resources are necessary to act as a catalyst in leveraging private sector resources to be investedin climate change technology.(ii) There is a need for a good balance between technical depth and implementationpracticality in the design of the project. Both aspects are indispensable, and there has to be awareness that a technically soundproject that is difficult or impossible to implement is not a good project. This project was technically sound, but practicalimplementation concerns could have been thought through more thoroughly. (iii) Getting the procurement process rightis critical for smooth implementation. Procurement of goods and services is the process that makes or breaks projectimplementation. In this case, the multiplicity of small contracts was a major obstacle to rapid projectimplementation.(iv) Attention to project design and development of an adequate results framework are importantunderpinnings of smooth implementation and of achievement of results. The shortcomings in the design and its resultsframework of this project led to difficulties in both implementation and performance assessment.(v) It is still possibleto generate results even with limited resources, as illustrated by the results achieved with a small Trust Fund amount. Despite thedesign weaknesses, a wide range of outputs was achieved with a limited amount.
P120946 | VN-Public Investment Reform 2 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2011 | 2012 | 2013 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/472941474628773814/text/000020051-20140625225553.txt | http://documents.worldbank.org/curated/en/472941474628773814/pdf/000020051-20140625225553.pdf | IEG identified the following lessons from the ICR itself and from the review of the project overall:A crisis response program should have an explicit macro-economic focus, clearly reflected in both Program Development Objective and in the Policy Framework. This is even more critical when the Borrower does not wish to have a program with IMF. Coordination and dialogue between the Fund and the Bank are critical.The need for explicit actions on macro-fiscal management in DPL series depends in part on the quality and credibility of the Bank-country dialogue. In some cases, specific actions can serve as important commitment mechanisms for Governments. At the same time, a robust dialogue can also lead to early action by Borrowers (for example, on macroeconomic issues prior to PIR2).The combination of a relatively short-term contingency lending program with long-standing institutional reforms may be incongruent, unless the program motivates high impact stroke of the pen reforms. In such circumstances, it may be better to front-loading these reforms at the launch of a DPL series, and support institutional reforms through an intensive program of technical assistance and capacity building.Complex institutional reforms should be supported only after a rigorous analysis of political incentives, stakeholder interests, and potential sources of opposition.
P120946 | VN-Public Investment Reform 2 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2011 | 2012 | 2015 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P120947 | Development Policy Loan 2 | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2011 | 2012 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/700651474490033476/text/000020051-20140625072448.txt | http://documents.worldbank.org/curated/en/700651474490033476/pdf/000020051-20140625072448.pdf | There are two important lessons: (i) selective focus of policy areas based on knowledge and consultation in designing a reform program increase the likelihood of its success; and (ii) an effective outreach strategy is vital to build public support for reform.
P120960 | Burkina Faso Donsin Transport Infrastructure Project | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/479811592410672972/text/Burkina-Faso-BF-Donsin-Transport-Infrastructure-Proj.txt | http://documents.worldbank.org/curated/en/479811592410672972/pdf/Burkina-Faso-BF-Donsin-Transport-Infrastructure-Proj.pdf | The following lessons and a recommendation were adapted from the ICR:A better formulation of the PDO would haveallowed a more realisticassessment of what the project was expected to achieve vis-a-vis the governments vision (thenew international airport outside Ouagadougou).The Bank recognized the risks of the airport development beingdelayed or cancelled and helped formulatea PDO that emphasized the road connectivity and accessibility as a standaloneproject that could be justified on its merits. The technical assistance provided support to the Government to improve its capacityregarding PPPs.Strong due diligence to identify potential risks and close supervision of the procurementcycle areessential to avoid contract management challenges and project delays. This lesson is consistent with manysimilar cases experienced by IEG.It is recommended that the Government of Burkina Fasotransfersthe newroad from MOAD (the Donsin Airport Project Management Entity) to the Ministry of Infrastructure as soon as possible to ensure itreceives appropriate life cycle maintenance. In the event that the construction of the new airport is delayed orcancelled, this road should still be able to function effectively. The Bank has experienced in the past many similar situations inSub-Saharan Africa where, after rehabilitating or constructing new roads, the maintenance has been neglected and the infrastructuredeteriorated quickly.
P120985 | KAZSTAT: Strengthening the National Statistical System of Kazakhstan | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/848981530047462996/text/Kazakhstan-KAZSTAT.txt | http://documents.worldbank.org/curated/en/848981530047462996/pdf/Kazakhstan-KAZSTAT.pdf | (Lessons 1 is derived by IEG; lessons 2 and 3 are taken (revised) from the ICR.)In developingstatistical capacity, it is crucial to adopt a systemic approach to calibratea project to country needs, ensure ownership,and strengthen sustainability. Statistics are essential to monitor country conditions and for policy decision-making.Statistical capacity building projects need therefore to consider existing needs, capacity, and constraints and to build on theseelements in order to succeed and be sustainable. KAZSTAT set ambitious goals, but not unrealistic ones, based on country prioritiesand the governments willingness and capacity already in place. Moreover, the project cleverly used and developedinstitutional elements to ensure that the financed activities could become part of the regular operations of the StatisticalOffice. It decided to assign implementation to a Project Implementation Team that was fully embedded in the ARKS, rather thancreating a separate entity. It supported a twinning partnership with statistical offices facing similar challenges and conditionsto exchange experiences and expertise, rather than resorting to external consultants. It strengthened statistical and technicalcapacity, but also financial and procurement expertise, and supported hardware and software upgrades. All these elements modernizedARKS, and changed processes and methods beyond the life of the project itself.Building onexisting experience and lessons from similar statistical capacity building projects is essential for the World Bank to maximizeresults and minimize risks. KAZSTAT benefited from very strong Bank experience in implementing statistical capacitybuilding projects. The Bank could bring to the table the right technical expertise, and succeeded in identifying those aspectscritical to smooth implementation and, eventually, achieving results based on previous experience in the region. Forexample, focusing on institutional reform (ICR, p. 4), frontloading training and education of staff in the earlier phase of theproject (ICR, p. 22), and ensuring a coordinated and systemic approach were all lessons taken from previous projects that provedinstrumental to this projects success.Consideration of the borrowers nationalconditions that can influence a projects implementation at the onset is essential for success. The ICR (p. 22)stresses that ARKS weakness in financial management could have adversely impacted implementation. However, promptidentification of those weaknesses and adequate mitigating measures (hiring of financial management specialists, and training inBank financial management and disbursement procedures) helped to ensure that the financial management of the project was maintainedat a satisfactory level. The ICR (p. 6) also mentions that in Kazakhstan there was no additional workload related to conductingcensuses or other major work during the five years of project implementation. This represented a very favorable conditionallowing ARKS to undividedly focus on project implementation. The ICR does not mention whether the timing of the project wasdeliberately planned around a slack period, or if this was just a fortuitous coincidence. Irrespective, avoiding periods ofoverload is certainly important to increase the chances of success.
P121052 | Youth Employment Support | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/340301467993757725/text/ICRR-Disclosable-P121052-07-08-2016-1467993740812.txt | http://documents.worldbank.org/curated/en/340301467993757725/pdf/ICRR-Disclosable-P121052-07-08-2016-1467993740812.pdf | This tempering of the scope of a projectsobjectives, while focusing on delivery,canprovideabalanced approach that takes contextual factors into account. The objectives set for this emergencyresponse project were realistic andattainable while also providing strategic support to theclient.Flexibility in adapting community engagement aspects of a project can result in effective servicedeliveryand maximization ofadded value. In the case of the Youth Employment Project in Sierra Leone, suchflexibilitywas particularly important and allowed for a much needed on-site response to the Ebolaepidemic.When two principal components ofa projectoperate independently ofone another, anexplicit statement of how beneficiaries can move from one component to another can enhance overall design and coherence, andfurther strengthen the value added of a service delivery focus. IN this instance, the separation of the two components wasunderstandable from an administrative perspective; however, it would have been appropriate from a beneficiary-focusedperspectiveto make more clear how at least some beneficiaries couldgraduate from the cash-for-workintervention (Component 1) to the skills development/employment supportintervention(Component 2).Innovationsinvolving electronic control measures that can beintroduced in an emergency, post-conflict scenariocandemonstratereal opportunity for fiduciary and other (e.g. ME) assurance and accuracy going forward. Inthis case, in response to corruption allegations and an INT investigation, e-payments, scanned photo ID, and similar measures wereintroduced.
P121060 | Health Commodity Security Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/619291474941709493/text/000020051-20150312114623.txt | http://documents.worldbank.org/curated/en/619291474941709493/pdf/000020051-20150312114623.pdf | The following lessons are derived from the ICR (pp. 29-30):An emergency project does not necessarily benefit from the existence and implementation structures of an ongoing operation. This projectâ€™s reliance on the Ministry of Health and the Health Service Delivery Projectâ€™s experience for implementation arrangements created constraints that might have been avoided with a more careful consideration of the special needs of an emergency project.Bank policies and procedures are not always aligned with the need to respond rapidly to emergencies. In this case, subjecting agreed-upon UN procurement procedures to further review by the Bankâ€™s procurement services created delays and frustration.Commercial sector supply chain indicators are not necessarily appropriate for the public sector. In this case, indicators for fill rates and lead-time variability, introduced in an attempt to replicate the rigor of private sector supply chain management, had to be dropped because of the different way in which the public sector assesses risk.
P121075 | Ketsana Emergency Reconstruction and Rehabilitation Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2015 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/959871467992039943/text/ICRR14754-P121075-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/959871467992039943/pdf/ICRR14754-P121075-Box393191B-PUBLIC.pdf | The ICR (page 21-22) draws the following main lessons from this project.(1) A simple project design based on the best available preliminary damage and needs assets as used in this project could facilitate quick processing and start up of implementation.(2) Use of retroactive financing for eligible activities as used in this project could help in getting immediate positive impacts and reinforce collaboration with the government.(3) Targeting local contractors with simple measures could aid in ensuring better quality construction. The experience with this project was that although the quality of work by the local contractors was weak in the initial stages, a series of simple measures, implemented by the Managing Consultant aided in achieving important improvements in construction quality and progress.(4) If community participation is not possible during project preparation for an emergency operation, it would be helpful to conduct information sessions and outreach operations as early as possible during implementation.
P121116 | Sustainable Production Systems and Biodiversity | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/455221574349673500/text/Mexico-MX-Sust-Production-Systs-Biodiversity.txt | http://documents.worldbank.org/curated/en/455221574349673500/pdf/Mexico-MX-Sust-Production-Systs-Biodiversity.pdf | The following lessons are drawn partly from the ICR but with a number of adjustments oflanguage. Understanding local markets and market access mechanisms at the outset of a biodiversity-focusedagriculture project can contribute to increased differentiation and value of products. There is a substantial marketinformation element in biodiversity friendly land use projects, therefore understanding markets and market access is important. Inthis case, the project put considerable effort into differentiating products and developing levels ofcertification. The scale of local and national demand for higher value products in a land use project relying onbiodiversity friendly practices may limit the scale of biodiversity friendly activity that can be achieved unless therearesignificant international markets for someproducts. In this case, the size of markets for some nicheproducts may be insufficient toachieve greatly expanded adoption suggesting the need for sustained market research and nimblemarketing. In projects calling for substantial government counterpart budget, project design needs to take intoaccount federal budgetary regulations and practices and past counterpart funding performanceto try to reduce the risk ofunanticipated financing shortages. In this case, funding from several agencies fell short or was delayed, a risk not fullyaddressed in the PAD and, to some extent, predictable. Testing and applying cost efficient methods for measuringand tracking local biodiversity changes may improve the effectiveness and efficiency ofMEin biodiversity projects.The measurement of changes in biodiversity to evaluate the performance of project interventions in agricultural land useis costly and may become difficult to justify against the benefit stream. Therefore, it is important to find cost efficienttechnologies and methodologies. In this case, the high cost of statistically significant species monitoring over a sufficientlysustained period would be difficult to justify solely against the modest cost and short project time period.
P121152 | Second Land Administration Project (PRODEP II) | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/329271620137020972/text/Nicaragua-NI-Second-Land-Administration-Project.txt | http://documents.worldbank.org/curated/en/329271620137020972/pdf/Nicaragua-NI-Second-Land-Administration-Project.pdf | The following lessons are taken from the ICR with some modification of the language: The strengthening ofland rights require a continuous and consistent approach. The project experience shows that the governmentscommitment to land administration agenda, supported by the Bank through a long-term engagement, helped test and define projectmethodologies and results. Further, assigning the leadership for land reforms to one agency, in this case ProcuraduraGeneral de la Repblica (Attorney Generals Office PGR), further enhanced the enabling environment for projectcoordination and implementation. The in-house upgrading of the internationally developed IntegratedCadastre Registry Software (SIICAR) using local programmers and technical experts was critical for developing national technicalcapacity and sustainability of the software. By doing so,international standards and good practices can be betterintegrated into the system design and aligned with the national legal and institutional framework; and system maintenance andupdating will likely be more organically integrated into the agencies functions andservices. Cadastre and land regularization activities need to considersocial aspects inaddition to technical issues. The experience in Nicaragua shows that gaining the broad support of beneficiaries is asimportant as having adequate technical specifications and experience in land regularization. The project, based on lessons learnedfrom prior interventions, included a Communications Strategy and a Grievance Redress Mechanism to promote strong socialization,awareness, and the active participation of all beneficiaries, considering cultural and gender aspects.
P121167 | Ceara Rural Sustainable Development and Competitiveness | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/154151588084911774/text/Brazil-BR-Ceara-Rural-Sustainb-Competitiveness.txt | http://documents.worldbank.org/curated/en/154151588084911774/pdf/Brazil-BR-Ceara-Rural-Sustainb-Competitiveness.pdf | The ICR included six lessons. The following twoare emphasized with some adaptation of language: Toensure efficient execution of economic inclusion projects, analytics requires sufficient preparation and dedicated resourcesto conduct a realistic assessment oftarget beneficiaries, the capacity of supporting institutions and the operationalcontext.The projects experience showed that rigorous selection criteria combined with technical expertise whichhones in on building the organizational and business skills (and social cohesion) needed for PO growth and survival. Also, wellprogrammed, tailored interventions that equalize to the extent possible, access to project opportunities and potential to succeedare needed for PO growth and survival. Agri-business marketing expertise in both the Bank and Borrower teams is also essential toprovide necessary support during implementation. To ensure capturing the expected outcomes,the ME designneeds focused attention on all key themes of the PDO.PDO Indicators and Intermediate ResultsIndicators need to capture the breadth and depth of expected outcomes, be unambiguous and measurable, and set reasonable targets.While restructuring is an option in circumstances where an indicator loses relevance, a sound strategy for upstream design ofME can avoid repeated efforts to re-design and calibrate the RF, and disagreement over measurement methodology.
P121185 | National Highways Interconnectivity Improvement Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099220002212336977/text/P1211850c7df300ae084710da4484bd34ac.txt | http://documents.worldbank.org/curated/en/099220002212336977/pdf/P1211850c7df300ae084710da4484bd34ac.pdf | This review has drawn three lessons based on the information in the ICR.Engineering, procurement, andconstruction (EPC) contracts can decrease construction time and project cost compared to traditional item rate contracts if managedeffectively. The project introduced EPC contracts as an alternative to traditional item rate contracts that generallyresult in construction time and cost overruns. By shifting the design and construction controls and risks to the contractors, theEPC contracts can reduce such overruns. However, the success of this kind of contract type depends on its effective management.This includes ensuring that contractors have adequate cash flows based on realistically planned milestone payment conditions toallow regular payment for completed works and that approvals are processed in a timely manner such as changes in scope or extensionof time. Otherwise, as experienced in this project, contractors solvency can hamper project implementation and result inincompletion of works before project closing. These were some of the reasons why the average cost per kilometer or road under theEPC contracts, i.e., US$0.57 million, was similar to the average cost under the traditional item rate contracts with one importantdifference that the former included a five-year performance-based maintenance phase after project completion.Aweak theory of change can prevent a proper assessment of the achievement of project objectives.The project was tofinance technical assistance activities to enhance the institutional capacity of MORTH to better operate roads under itspurviewObjective 2. However, the outcomes expected from these technical assistance activities were not sufficientlyidentified. The causal pathways from project inputs and outputs to expected outcomes and the achievement of project objectives werebroadly valid but notdirect. It was not clear how the enhancement in the institutional capacity of MORTH would lead to bettermanagement of the highway network under its purview. Furthermore, the results framework did not include any indicator to capturethe achievement of this objective, to enhance MORTHs institutional capacity to better manage the roads under its purview.There is no evidence of MORTH operating these roads better compared to the situation before project start. These shortcomingsresulted in a Modest rating for the efficacy of the project in achieving this objective.Project implementationunits operating under state agencies can facilitate a smoother project implementation because of their close relationship with thelocal authorities. The implementation of road projects might be delayed because of issues related to utility and forestapprovals and land acquisition. In India, such matters fall under the jurisdiction of the local authorities. PIUs operating understate agencies can address such delays faster because of their close relations with the local authorities. However, this set-uplimits the federal entitys, i.e., MORTH, control over the pace of the project implementation. The ICR states that ahybrid approach, where MORTH employs the PIU but also pays an appropriate agency fee to a state that is linked to their services,could be considered (ICR, p.24).
P121186 | Water Resources and Irrigation Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099340006172238328/text/P1211860bc8c6907708cdc0682e4a89e49d.txt | http://documents.worldbank.org/curated/en/099340006172238328/pdf/P1211860bc8c6907708cdc0682e4a89e49d.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. To avoidcost overruns during implementation, it is important that projects involving infrastructure activitiesuse robust andrealisticcost estimates for civil works thatreflect market prices at the time of appraisal. The World Bank appraisalteam should be responsible for ensuring that appraisal costs reflect market prices within the country, regionally, andinternationally with appropriate levels of price and physical contingencies. A difference of 20%is acceptable and can becovered by contingencies. In the case of the WRIP, the failureto obtain reasonable cost estimates led to the relaunching ofseveral contracts, not having sufficient funds for implementation of more than half of the schemes, and subsequent implementationdelays and processing of additional finance and time to implement the original project.2.Irrigation projectsdesigned to increase agricultural productivity must include support to farmers in agricultural marketing to avoid price declinesdue toincreased productivity.Interviews with the men and women who own small farms and sell their productsalong national roads expressedsatisfaction with the newly improved irrigation. However, they are now concerned abouthow and where to sell the increased volume of products they are now able to grow. The experience of WRIP emphasizes the importanceof including agricultural marketing to enable farmers to sell their increased volume of products otherwise project areas mightexperience excess supply and depressed prices.The following lesson is emphasized by IEG:3. To ensure asatisfactory outcome of a complex irrigation project, design and preparation need to include a sound analysis of the implementationenvironment and realistic cost estimates. The project faced two critical challenges during implementation, first, theGovernment changed the irrigation law which deemed some aspects of the project irrelevant. A transparent dialogue with theGovernment during the preparation stage would have allowed the team to forsee such changes. Second, the cost estimates of therehabilitation of irrigation infrastructure were highly underestimated at appraisal, despite the project-financed feasibilitystudies. This necessitated additional financing to complete the envisioned activities. To accommodate price increases withincontracts, cost estimates need to be realistic and account for domestic, regional, and global estimates with traditional physicaland price contingencies, including projected rates of foreign and domestic inflation.
P121195 | MX Water Utilities Efficiency Improvement Project (PROME) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/519751495225988887/text/ICRR-Disclosable-P121195-05-19-2017-1495225973523.txt | http://documents.worldbank.org/curated/en/519751495225988887/pdf/ICRR-Disclosable-P121195-05-19-2017-1495225973523.pdf | The ICR (pages 18-19) draws the following main lessons from the experience of implementing this project.(1)Project design needs to take into account the limitations in the legal framework to introduce innovative delivery mechanisms (suchas Output-based disbursement) to ensure Borrowers Ownership. In the case of this project, the National WaterCommission (CONAGUA) did not accept the component on Output-based disbursement, given that national regulations did not allow it.Consequently, this project activity was dropped due to lack of demand on the part of the water utilities.(2)Adequatemechanisms for reporting and capacity for monitoring are pre-requisites for utility performanceimprovement programs. In the case of this project,lack of baseline data and a proper assessment of theinitialsituation in the utilities in terms of efficiencycontributed to the imprecise measurement of the impact of resources(Borrowers ICR, page 54) and there were no mechanisms envisaged at appraisal for gathering the information necessary tocalculate the indicators. Further, in instances where other investments are underway in the same sector, the project should includemeasures to track attribution of towards project-specific results.(3) Projects when launched on a large scaleshould be sufficiently structured to prioritize investments for achieving the best results. Spreading funding among a widerange of utilities of different size, capacities and objectives could dilute the effectiveness and efficiency of Bankresources.Proper enforcement of eligibility criteria could help in narrowing the number or type of sub-national entities tobe supported.(4). Utility performance improvements require investments across multiple types ofefficiencies. Well-performing utilities can achieve better results with the same level of funding as otherutilities. Such utilities can also be targeted to pilot output-based performance programs but it is critical to have thesupport of implementing agencies before designing innovative components.(5) The Banks added value forcountries with high capacity is in bringing global best experiences and practices to improve sector performance. In thecase of this project, resources both in terms of time and effort were expended on processing a number of small procurementpackages, instead of focusing on knowledge sharing and sector policy dialogue. To advance innovative approaches that requiresmall-scale procurement, the Bank could consider more flexible procurement rules with higher thresholds that promote efficiencywithout compromising quality.
P121210 | APL on Strengthening Regional Cooperation For Wildlife Protection in Asia | South Asia | South Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/989831518450090067/text/South-Asia-REG-Wildlife-Protection-BD-and-NP.txt | http://documents.worldbank.org/curated/en/989831518450090067/pdf/South-Asia-REG-Wildlife-Protection-BD-and-NP.pdf | There are four lessons, drawn from the ICR with some adjustment. A regional approach can be effective inaddressing transboundary and shared common issues provided there is strong and sustained commitment by participant governments.In this case, there was strong regional coordination between Bangladesh, Nepal and another non-participant partner, India,on strategic issues through regional meetings due to a building commitment to coordination on the illegal wildlife trade issuesbuilt on a rising commitment to the earlier Tiger Initiative. These proved quiteeffective in synchronizing policies, sharingexperience, coordinating wildlife law enforcement approaches and adopting new good practices. The challenge remains to sustainit. Regional projects focusing on global public goods are challenging to design and implement. This calls forstrong preparation analysis of participant capacities and commitments. In this case, project preparation was rushed. Thisresulted in a number of implementation delays that later had a significant bearing on project implementation andprogress. Projects aiming to pilot new approaches for cooperation on transboundary wildlife issues related towildlife management and illegal wildlife trade require a carefully designed Results Framework from the outset tomeasure and document changes in intermediate outcomes including especially institutional cooperation and capacity. In thiscase, indicators at the intermediate outcome level for measuring the success of regional cooperation were not well thought throughat the design stage.. In projects aiming, for the first time, to pilot new approaches in cooperation ontransboundary wildlife issues related to wildlife management and illegal wildlife trade, it is more important to design a programof comprehensive organizational capacity building than to narrowly address lower level activity-oriented training for short-termskills. In this case, looking atone alternative counterfactual, the project rightly focused on higher levelinstitutional strengthening beyond merely immediateskills training. Skills are not unimportant but, alone, would not haveaddressed the overarching institutional issues for the longer term.
P121210 | APL on Strengthening Regional Cooperation For Wildlife Protection in Asia | South Asia | South Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2017 | 2019 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/250431533557694267/text/128169-PPAR-P121210-P166769-PUBLIC.txt | http://documents.worldbank.org/curated/en/250431533557694267/pdf/128169-PPAR-P121210-P166769-PUBLIC.pdf | 7. Lessons â€¢ Given their design and implementation challenges, regional projects focusing on global public goods require adequate preparation time to conduct a thorough analysis of participant capacities and commitments. Because of high-level commitments made by World Bank management, the SRCWP was hastily prepared at the expense of a complete analysis of the capacities and commitments of the participating countries. This resulted in several implementation delays that later had a significant impact on project implementation and progress. â€¢ Regional projects aiming to pilot new approaches to collaboration on transboundary wildlife management and illegal wildlife trade require a carefully designed results framework. Such a framework is necessary to measure and document changes in intermediate outcomes, especially regarding institutional cooperation and capacity. In the SRCWP's case, indicators at the intermediate outcome level for measuring progress and success in regional cooperation were not well thought through at the design stage and later required revision to capture progress in this area more accurately. â€¢ Regional projects designed to build institutions and capacity for collaboration on transboundary wildlife management and illegal wildlife trade require a long-term investment to ensure success in achieving results. In the SRCWP's case, the World Bank's original decision to employ an APL to support regional initiatives for wildlife protection was well-advised, recognizing that this lending instrument would allow other countries interested in wildlife conservation to join the countries of South Asia and that regional capacity building to support wildlife conservation would require a follow-on set of projects. In the end, no other countries joined Bangladesh, Bhutan, and Nepal in the APL and there was no follow-on project to consolidate achievements and institutionalize regional capacities.
P121220 | Emergency Recovery Development Policy Credit | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/790131474586060950/text/000020051-20140625192410.txt | http://documents.worldbank.org/curated/en/790131474586060950/pdf/000020051-20140625192410.pdf | This Review supports the lessons that the ICR mentions, and adds the following:An emergency loan to a borrower that faces imminent fiscal stability risks should be focused primarily -- even exclusively -- on public finance issues.Resolving the issue of excessive public wages that undermines fiscal sustainability may be politically costly but possible, if there is sufficient political will and well organized communication strategy that explains long-term benefits of rationalizing civil service pay.Tax policy measures in many instances may be insufficient if they are not supported by necessary tax administration reforms. The example of Honduras indicates that although the Government was able to introduce politically difficult tax policy measures, their effectiveness was hampered by the lack of improvements in tax administration.The process of program preparation should be used for identifying areas where achievement of intended objectives may be difficult, and for making necessary arrangements in the design of the program to ensure sound program implementation. Further reliance on upstream political economy analysis can help tailor reforms to country conditions in a manner that is both pragmatic and monitorable.
P121231 | Governance eTransformation Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/672011507844559743/text/ICRR-Disclosable-P121231-10-12-2017-1507844546788.txt | http://documents.worldbank.org/curated/en/672011507844559743/pdf/ICRR-Disclosable-P121231-10-12-2017-1507844546788.pdf | Onelessonisselected from the ICR, with some adaptation of the language, and the second one is identified bythe IEG: It is important toset upright implementation arrangements and ensureownership of the ICT infrastructure with consideration of the overall political economy. Under this project, the decisionto anchor a Cloud system development for the government at the highest level of the government (the State Chancellery and engagingthe Prime Ministers office) ensured coordination but also posed risks such as change in the government and friction betweendifferent the implementing agency (eGC) and line ministries. The joint ICT technologycan be disruptive in terms of the needs to phase out old infrastructure and changes in staffing. The new, joint ICTinfrastructure would necessitate phasing out some of the legacy infrastructure, fully re-engineering workflow in some ministries,as well as staffing levels and skills. These issues are being addressed in a follow-up Bank project, asreported by theproject team.
P121263 | China GEF City Cluster Eco-Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/918171495815923291/text/ICRR-Disclosable-P121263-05-26-2017-1495815910843.txt | http://documents.worldbank.org/curated/en/918171495815923291/pdf/ICRR-Disclosable-P121263-05-26-2017-1495815910843.pdf | Two lessons are selected by IEG from a longer listpresented bythe ICR, with some adaptation of thelanguage: It is important tosupport strengthening capacity for consultant procurementin TA projects. Under this project, delays in appointing consultants for TA consultancies affected project completion. Thelack of experience of the PMO in complex consultancies caused delays in procurement. It isthe responsibility of the Bank toprovide training for TA assignments during preparation, including assistance to write theTORs. Effective communication among project participants at the national andlocal level is necessary for project success. Under this project, the IA was setup at the national level without a localPIU. The national PMO had effective communication with the local authorities (in this case the developers of the two hubs) to avoiddisengagement from ownership. But, ineffective communicationbetween the PMO and theMOF contributed to a delay inproject restructuring request.
P121271 | Integrated Coastal Zone Management | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/821161538145781490/text/Morocco-MA-GEF-Integrated-Coastal-Zone-Mgt.txt | http://documents.worldbank.org/curated/en/821161538145781490/pdf/Morocco-MA-GEF-Integrated-Coastal-Zone-Mgt.pdf | The the fourmost important lessons drawn by the ICR are the following (with some modification oflanguage):(1)Public consultation and community engagement are essential to building trustand ownership and to sustaining an ICZM approach on the ground. This project had a high level of commitment and ownershipat the community level, due partly to the involvement of the stakeholdersin thedesign of the project and the ongoingconsultations with project stakeholders throughout implementation.(2) Avoiding early implementation delaysrequires a carefully targeted, comprehensive and coherent training plan for implementing agency staff. Thisis particularly so in a project involving multi agencies. In this case, implementation delays in the initial years were due to acombination of factors including, the weak implementation capacity of the implementing agency to address procurement issues and thelack of clearly defined roles and responsibilities regarding procurement procedures.(3) Introducing new approachessuch as ICZM can benefit greatly from piloting and learning by doing followed by replication and scaling up activities.Given limited resources, a pilot approach can enhance the chances of effective allocation of limited financial and humanresources to activities that have been proven to work at various scales.(4)An actively engaged andsupporting Country Management Unit (CMU) is critical for a pilot project with inherent implementation risks. The delaysduring implementation in this project were resolved through the proactive follow-up by the CMU and high-level engagement by theCountry Director.
P121289 | Ningxia Desertification Control and Ecological Protection Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/582611617153773211/text/China-CN-Ningxia-Desertification-Control.txt | http://documents.worldbank.org/curated/en/582611617153773211/pdf/China-CN-Ningxia-Desertification-Control.pdf | The ICR (p. 39-40) provided lessons learned which were modified by IEG: Greater flexibility in regards toproject financing to allow for rapid reallocations of Bank financing in case of lacking counterpart financing is critical forfilling financing gaps and avoiding implementation delays. In this project, lack of counterpart financing resulted inimplementation bottlenecks such as planting entities not receiving timely payments on contracts, plantation quality monitoring andverification being deficient, and training activities not taking place until the project was restructured in 2016 and financing wasreallocated to cover a large proportion of counterpart obligations. Landscape projects benefit from incorporatingpolicy actions to address underlying adverse drivers. This project addressed the impacts of desertification andimplemented policy measures to avoid future desertification. However, the ICR (p. 39) stated that based on the experience of thisproject, a similar project could also benefit from providing technical assistance to prevent land degradation in the first placesuch as setting ecological limits, improving land use zoning, and mandating improved land and water use practices.
P121328 | Small and Medium Enterprise Development Facility | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/955121476739427442/text/ICRR-Disclosable-P121328-10-17-2016-1476740327379.txt | http://documents.worldbank.org/curated/en/955121476739427442/pdf/ICRR-Disclosable-P121328-10-17-2016-1476740327379.pdf | IEG concurs with the four lessons identified in the ICR, which are rephrased below:(i)Associatingtechnical assistance with finance can produce sustainable impact: By addressingdemand- and supply-side constraints to SME finance, the project ensured that SMEs will continue to receive finance for theirgrowth.The longer-lasting effect of the project was the institutional changes in PFIs as well as theacquired skillsprovided through training and experimentation.(ii) Engaging key stakeholders before launching new andspecialized financial instruments matters:RSFs are attractive financial instruments for the provision of relativelycheaper and longer-term financing. However, there must be extensive consultations with all stakeholders, especially the legalauthorities, at the design stage, to ensure that the technicalities are clearly discussed and agreed upon beforenegotiations.It is essential for future operations with RSFs to clearly communicate mechanisms, criteria, and conditions,provide incentives as appropriateand engage stakeholders on a regular basis.(iii) Flexibility in projectimplementation and design parameterscan be beneficial for project efficacy. The Bank team decidedto remain flexible and adjust the parameters of the LOC to prevailing market conditions, and this alloweda high demand fromPFIs and SMEs to be maintained. However, too much flexibility in the delivery of the training to SMEs yielded mixed results; thequality and focus of training sessions were more appropriate for entrepreneurs than for other categories ofbeneficiaries.(iv) Steering committees can play an important role, if used appropriately:Thesteering committee was never put to use, although the condition of having a steering committee was met.An effective steeringcommittee could have helped escalate issues such as the RSF that required urgent attention at a higher level.It is key tohave in place a balancedcomposition ofthe steering committee to ensure that stakeholders are represented at anypoint in time.
P121394 | Pakistan: Khyber Pakhtunkhwa (KP) and Federally Administered Tribal Areas (FATA) Emergency Recovery Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2012 | 2013 | ICRR | Less than 10 million |  | Moderately Satisfactory |  | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/223561475072014144/text/000020051-20140625224140.txt | http://documents.worldbank.org/curated/en/223561475072014144/pdf/000020051-20140625224140.pdf | The NCO provides several main lessons (p. 8), from which these are adapted:Consultations during the project preparation process need to be all encompassing. In particular, the Government and the Bank must carry out direct discussions with all potential stakeholders, including the military in conflict areas, ensuring full transparency and broad-based buy-in. In this case, even with a thorough post-crisis needs assessment that was endorsed by the Government, clearly the preparation process was not sufficiently inclusive to bring all relevant stakeholders on board.Sensitivity to the potential presence and impact of other donors must be taken into consideration. The combination of IDA and Multi-Donor Trust Fund funding sources for the project may have played a role in the KP provincial governmentâ€™s refusal to proceed with implementation. The NCO suggests that designing a smaller project relying solely on Multi-Donor Trust Fund grant funds might have been received more positively by key decision makers.
P121398 | MZ - Spatial Development Planning Technical Assistance Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2016 | 2018 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/520141499290590046/text/ICRR-Disclosable-P121398-07-05-2017-1499290583073.txt | http://documents.worldbank.org/curated/en/520141499290590046/pdf/ICRR-Disclosable-P121398-07-05-2017-1499290583073.pdf | The ICR presents seven general and four Project specific lessons. Three important lessons are summarizedbelow: Spatial Development Planning is a specific tool of cross sectoral scope and can be a powerfulinstrument for designing development interventions and attracting investments if fully institutionalized in a state agency, whichhas responsibility for national planning and that can ensure effective coordination and cooperation of different line ministriesfor its mainstreaming. If the cross sectoral coordination is limited, then the SDP can focus within the transport sector to improveuse of existing infrastructure systems in development corridors and to expand benefits from them. The effectiveness of theinstitutionalization depends on the demand from ultimate beneficiaries, ownership by the Government; and existing pre-requisitetechnical capacity. The TA lending operations, as shown by this Project as well as by similar recentTA projects related to housing in Mexico and the urban sector in Brazil, are more attractive to the Client and more effective ingaining and practically applying a new instrument and capacity if they are designed to compliment or follow an infrastructureinvestment Project. Selection and targeting of Corridor Development Initiatives should be based ontheir importance and competitive advantage for regional cross country transportation and trade, as well as on their existing andpotentially high economic impact.
P121414 | Sichuan Wudu Irrigated Agriculture Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/690901618234128037/text/China-CN-Sichuan-Wudu-Irrigated-Agric-Dev.txt | http://documents.worldbank.org/curated/en/690901618234128037/pdf/China-CN-Sichuan-Wudu-Irrigated-Agric-Dev.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. Toensurerealistic and achievable outcomes of irrigation projects,PDOs need to reflect the scope of the projectasnegotiated with the Borrower. It is essential to have a mutually agreed understanding on the sequencing of main systemsand on-farm works, and define the PDO accordingly. The agricultural productivity related indicators should be selectedrealistically and conservatively, as improvements in agricultural production lag irrigation works development and take longer thanthe typical duration of an investment project.2. For large scale and technically complex projects, out-sourcingME to areliable independent third-party institutioncontributes to efficient ME and ensures compliance withenvironmental and social safeguard policies. Third party external entities specialized in ME and safeguard issues arein a better position to exercise fair judgment and allow the Project Management Offices (PMOs) to focus on their core managementand coordination functions. The PMO employed a professional team responsible for project ME, and also external monitoringteams responsible for social aspects (including resettlement) and environmental safeguards, respectively, to carry out theirrespective tasks during project implementation. As a result, safeguard aspects were in full compliance with Bank policiesthroughout implementation, despite the large scale and technical complexity of the project.3. Engaging middleincome countries like China is important because it allows the Bank toshare knowledgeandbuild capacity incritical areas such associal development and environmental management. Although the Bank loan only coveredabout 15% of the entire second phase of the Wudu irrigation scheme development, Bank policies and procedures (particularly inenvironmental management and social development) were fully incorporated in the entire Phase II Wudu Scheme. In addition, theBanks close support to the development of the CDD based on-farm works in demonstration areas was key to its success andon-goingscaling up.4. Realizing the full potential of irrigation infrastructure calls for longer-terminvolvement in the overall scheme development process. In hindsight, an approach similar to the Multiphase ProgrammaticApproach would have allowed the Bank to engage with the client in structuring a longer, larger, and more complex engagement as aset of smaller linked operations (or phases), each with interim outcomes that link to make incremental change.Although theinstrument was not available at the time of appraisal, a similar long-term engagement would have enabled the Bank to support thedemonstration CDD approach for on-farm works management through the entire Phase II Wudu Scheme for the intended agricultureproductivity enhancement.
P121455 | State Employment and Expenditure for Results Project | Western and Central Africa | Nigeria | Blend | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099845112232154066/text/Nigeria000NG0S0ment0and0Expenditure.txt | http://documents.worldbank.org/curated/en/099845112232154066/pdf/Nigeria000NG0S0ment0and0Expenditure.pdf | IEG supports the following main lessons that the ICR draws from the experience of implementing this project, with someadaptation.1. A youth employment strategy using small public works as a tool can be an appropriate strategyforquick results in disturbedareas like the Niger Delta. However, such a strategy does not address the broaderchallenge of providing remunerative, safe and dignified work for all working-age groups.2. Innovative digitaltechnology can be helpful for tracking project performance. For example a geographic-information system-based digitaldatabase and third- party can successfully track performance, even if the project activities cover a widearea.3. Successfully implementing an Integrated Financial Information Management System requires competent humanresource and good infrastructure. Capacity building of the relevant agencies needs to be assured in jurisdictionsimplementing the system, as is the case in, for example, Edo State, which is stably operating its system.
P121492 | Enhanced Public Sector Efficiency Technical Assistance Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2020 | 2022 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/171641636393907998/text/Panama-PA-Enhanced-Public-Sector-Efficiency-TAL.txt | http://documents.worldbank.org/curated/en/171641636393907998/pdf/Panama-PA-Enhanced-Public-Sector-Efficiency-TAL.pdf | The ICR (pp. 21-22) contains many insightful lessons. Key among these, restated by IEG,are: IT solutionsare a means to an end, rather than an end in themselves. Public financial management reform projects will be most successful ifthey focus on broader reforms rather than primarily on information technology solutions. This project focused too exclusively onthe ISTMO and PanamaCompra3 systems rather than the contribution those systems should make to a broader reform actionplan. Project design must explicitly take existing technical capacity into consideration. In this case, the emphasis onperformance budgeting drew from enthusiasm for achieved success in several high-income countries (the United Kingdom, New Zealand,Australia), without taking into account that it was an innovative practice that required more technical capacity andownershipthan was available in Panama. Transitions from legacy IT systems require well developed change managementstrategies, carefully derived from political economy and institutional analysis, and integrated at the design stage. In this case,the interests and likely behaviors of several key stakeholders and system users were not anticipated andtaken into account.In the absence of agreed transition arrangements, supporting regulations, and political leadership, there is likely to behesitation and even obstruction.
P121495 | Tocantins Integrated Sustainable Regional Development | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099040323135017757/text/P12149500e942d0140b75807b5b439a1de6.txt | http://documents.worldbank.org/curated/en/099040323135017757/pdf/P12149500e942d0140b75807b5b439a1de6.pdf | The ICR draws the following lessons from the experience of implementing this project, with some adaptation oflanguage.1. If synergies between project components are carefully examined and articulated in multi sectoralprojects, there is a higher potential for project success. An integrated approach to development that involves transportmay exhibit potential for exploring synergies and building on mutually reinforcing benefits. In this project, while there wereclearly synergies between transport infrastructure investments and developing agribusiness, the synergies between transport andpublic administration and education were tenuous at best.2. A strong commitment of funding for road maintenancemay help in ensuring sustainability of outcomes in road sector projects.In this project, performance-based(CREMA) contracts for paved roads embedded an assurance of adequate maintenance for five years. The lesson is that even longercontracts could address the maintenance commitment even further. This would however require stronger assurances of stable fundingfrom road agencies.3. Roads projects supporting rural accessibility have the potential for improving all seasonaccess through proactively addressing the effects of climate change.The lesson is that a program aiming to improveall season access of rural populations needs to consider in detail the adverse impacts of floods and landslides and incorporateerosion-prevention measures into road works design.4. If a project design incorporates mechanisms for seekingupfront assurance of budget availability for counterpart funding activities, there is a higher possibility for smoothimplementation without delays. This project faced difficulties in the initial years as the State faced difficulties inproviding the counterpart funding.
P121514 | Sierra Leone - Financial Sector Development Plan Support Project | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/625621538871866326/text/Sierra-Leone-Financial-Sector-Support-TA-Project.txt | http://documents.worldbank.org/curated/en/625621538871866326/pdf/Sierra-Leone-Financial-Sector-Support-TA-Project.pdf | The ICR identified learned lessons which are summarized and rephrased below:(i) An effective governancestructure on the side of the borrower is key to smooth project implementation: The lack of an FSDP governance structureand frequent changes in the BSL leadership affected project implementation. For a project with components across multiple BSLdepartments and multiple financial sector stakeholders, there need to be a Financial Sector Steering Committee (FSSC) with directcommunication to decision makers, who could provide timely direction during project design and implementation. The absence of suchan oversight structure may severely affect the quality of projectimplementation.(ii)Prioritization and sequencing of reforms may enhance the potentialforeffective implementation in fragile environments: The project was ambitious andfocused on a wide set of objectives.Despite the countrys vast needs in the financial sector, support should have been focused on priorities for which the WorldBank has the relevant expertise and the Government ownership is stronger.(iii) When the PIU is weak, it is riskyto count on the capacity building planned in the contextof the project itself: The project planned to build capacitywithin the scope of the project itself and this resulted in limited upgrade of the PIUs ability to execute theproject.(iv) Staff working in fragile states require sufficient budget and time to effetively support thesupervision of World Bank projects: The implementation of this project illustrates the need for the World Bank and clientsto consider a broader set of instruments to accompany an Investment Project Financing (IPF) in accomplishing financial sectorreform and modernization.
P121515 | NHAI Technical Assistance Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/303591556310643632/text/India-IN-NHAI-Technical-Assistance-Project.txt | http://documents.worldbank.org/curated/en/303591556310643632/pdf/India-IN-NHAI-Technical-Assistance-Project.pdf | The following useful lessons adapted from the ICR are pertinent:It is crucial forthe World Bank to candidly and carefully assess the clients commitment to a technical assistance project and itsobjectives. While the adoption of recommendations was significant in theformulation of operational and strategictechnical assistance, there was little take-up of initiatives in the areas of core institutional reform and corporategovernance.Stand-alone technical assistance loans, especially large ones spanningoverfive or moreyears, may have some limitations in achieving significant improvements in institutionalperformance. Nevertheless, several transformational logistics and connectivity initiatives in this project had theirgenesis in the various TA studies undertaken.The World Bank should consider a range of options when selecting an appropriatetechnical assistance strategysuch as a series of TA loans, smaller, focused non lending TA, components of TA embedded inlarger lending operations, reimbursable advisory services,and development policy lendingand carefully tailor thechoice to the specific circumstances. Moreover, frequent changes of senior officials and key staff may mean that windows ofopportunity for institutional reform are limited. Projects with such objectives should be designed to move fast, within two tothree years at most, while ownership and commitment last.For institutions that have deep-rootedcultures and ways of operating, an incremental approach to change, which builds upon past gains and mixes low-hangingfruit together with bolder aims, may be more effective. Theconcept of introducinge-governance in NHAIwas a bold and ambitious move. However, its repeated failure and eventual exclusion from the project was necessitated due to acombination of lapses including: failure to build up the internal information technology (IT) capacity of NHAI, inadequate marketassessment, and focusing exclusively on NHAI rather than adopting a sector wide approach.It is amistake to assume that TA projects are easy to implement because they only involve consultant contracts. Consultancy contracts,especially ones related to institutional change, can be as challenging to procure and manage, if not more so, than works or goodscontracts. Implementation arrangements must be carefully analyzed and appraised, with special attention to ensuring thatthe client agency has the requisite technical skills, absorptive capacity, and clear lines of accountability and decision making.In these aspects, it is also extremely important to consider the role of other relevant institutions besides the primary client.According to the World Bank staff involved, the project would have benefited more from enhanced mobilization of the WorldBanks own subject matter experts in areas such as asset management, IT, performance monitoring, road safety, infrastructurefinance, and logistics, among others. Such inputs potentially would have helped to provide quick, just-in- timeinputs at crucial stages to facilitate the formulation, implementation, and absorption of the TA activities. In some specializedareas, such as specific IT systems, the World Bank should consider mobilizing third-partyexpertise.Dissemination ofTA findings and their links to practiceshould notbe anafterthought. Too often, findings are not communicated to relevant line ministries, states, and other stakeholders in forms thatare practically useful. With the rapid turnover of key personnel in government agencies, the knowledge generated, if notcaptured in a repository, is likely to be lost. Dissemination of information should be built into the project design and not be aone-time, end-of-project activity. Several such dissemination activities were planned under the NHAI Technical Assistance Project,but ultimately the pressure of completion pushed many of these to the back burner.
P121528 | BD Identification System for Enhancing Access to Services (IDEA) Project | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/613401551977533122/text/Bangladesh-BD-IDEA-Project.txt | http://documents.worldbank.org/curated/en/613401551977533122/pdf/Bangladesh-BD-IDEA-Project.pdf | Three lessons are drawn from the ICR (pages 34-35), with adaptation.New legislation, or amendments toexisting legislation, that are needed for anoperation should be planned for well in advance of project approval oreffectivity. The inclusion of data privacy and security clauses in the implementing rules and regulations to the NIRAapparently required a Parliamentary amendment to the NIRA, which was not anticipated at project preparation, and effectivelydelayed the implementation of the project by about two years. This ICR Review does not agree with the assessment of the ICR(page 34) that complying with a legal framework is not a suitable condition for disbursement ... because the executive doesnot have control over the actions of the parliament and that an investment project would benefit from not including apolitically-linked condition outside the control of the project and its implementing agency.This ICR Reviewconsiders the amendment to have been inevitable, given the requirement for data privacy and security in the NID system, and deemsthat the appropriate lesson should be that legislative actionsmust be planned for deep in advance of project approval oreffectivity.For technology-heavy operations, it is vital that borrower governments be competently supportedby suitable technical assistance, including possibly beyond the project completion date, to ensure the sustainability of theproject outcomes. The project benefitted from having an implementation support consultancy firm handle the contractmanagement for the project,considering thatthe NIDW and the BEC did not have the technical capacity and the operationalexperience for a large-scale ICT procurement. Going forward, there remain considerable technological challenges for theGovernment and the NIDW: (a) the inter-operability of the NID system relative to thecomputer systemsof variouspublic and private sector clients will be an issue as the NID system matures; (b) the National Enterprise Architecture (NEA) buslaunched by the Bangladesh Computer Council will haveto be implemented to enable the provisionby the Government ofelectronic services (e-services);and, (c) procurement and staffing related to these activitieswill continue to bechallenging. Hence,continuing technical assistance to the Government and the NIDW would be necessary goingforward.A national identification initiative requires an effective communications strategy. Accordingto the ICR, the strategic communications program for the project, delivered by a professional communications firm, was instrumentaland effective in building demand for the NID services. The communications effort also collected feedback information on theNID from both citizens and NID service users. It will be incumbent on the Government to strengthen the communicationsstrategy for the NID well beyond the project closing date.
P121590 | Third Minas Gerais Development Partnership DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/751561467992500847/text/ICRR14807-P121590-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/751561467992500847/pdf/ICRR14807-P121590-Box393228B-PUBLIC.pdf | IEG concurs with the lessons drawn by the ICR (ICR p. 20) with some adaptation of language:Adoption of results-based management may benefit from its integration into fiscal reforms. In Minas Gerais fiscal rationalization was a key reform objective that drove the management program. The combination of institutional adequacy and well-designed interventions drives performance in service delivery.Results based management reforms require a long-term commitment, and an adaptable environment. As in the case of Minas Gerais, the process evolved over time, and was adapted and refined. Reforms need sustained champions. One of the main factors of the success of the Choque de GestÃ£o (Management Shock) was the dedication of an incoming administration with a team of highly trained, dedicated professionals with a mission to implant results-based management. Government ownership and commitment is critical for the successful implementation and sustainability of an operation. In this case strong political leadership ensured the continuity of the results-based management reform agenda.
P121611 | Financial Sector Development & Regionalization Project I (FSDRP I) | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099145005232225089/text/P1216110d96f5e035082940c6618ff8aa0d.txt | http://documents.worldbank.org/curated/en/099145005232225089/pdf/P1216110d96f5e035082940c6618ff8aa0d.pdf | The ICR identified a series of findings and lessons discussed on the pages 26-27, and this review selected two lessons which arerephrased below:(a) A complex objective can be achieved by drawing onaconducive broad context, aphased implementation and additional financing. The idea of contributing to financial integration amongthe CEAcountries at different levels of economic developmentinitially appeared ambitious and unachievable.Tosucceed,the project drew from thegoal of free movement of capital as envisioned in the EAC Common MarketProtocoland the commitment of thepolitical leadership in the five member countries of the EAC. Moreover,theproject team selected phasedactivitiesthat wereconsidered as a common denominator for all countries, andtheir implementation produced results.Given the broad-based nature of financial sector integration, the projectsagenda was complex and wide ranging.The Bank team adopted a phased agenda: (i) first, the project team restricted activitiesto the fastest moving parts of the larger financial sector agenda,which respondedto the client demand. Second, theabove principle continued to guide the design and implementation of the AF and selectivity was exercised within the broad areas ofsupport.The project ended up beinga front runnerfor the regional integration in Africa and globally, and thechallenges faced were acceptable for any innovative project of this nature. With the Bank project teams close implementationsupport, the project picked up momentum toward the last years and was able to meet its developmentobjective.(b) Crafting theappropriateimplementingarrangements is as importantas the other key features of the project.The structure and location of the PAT were key to projectimplementation.The Project Administration Team (PAT) was supported by a Steering Committee and an EAC Executive Committeewith senior-level membership drawn from relevant institutions in the partner states that helped smooth decision-making. The PATrelied, notonly on the usual fiduciary staff, but also on the technical specialists in payments, insurance and pensions. Tocomplement theEAC Secretariatlimited technical capacity, theBank project t eamprovided the needed expertiseand just-in time advice.A clear articulation of the EACs commitment toward regional integration also provided asupportive and enabling framework under which most of the projects initiatives were premised. The adequate implementingarrangements coupledto the Banks team expertise were key to the results achieved by this project.
P121643 | Vietnam Inclusive Innovation Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/308921530293865449/text/Vietnam-Vietnam-Inclusive-Innovation.txt | http://documents.worldbank.org/curated/en/308921530293865449/pdf/Vietnam-Vietnam-Inclusive-Innovation.pdf | The ICR (pp. 19-21) offered many important and insightful lessons, including:Deep and carefulconsideration of local context is crucial, especially for innovative projects. In this case, inadequate attentionwas paid to the need for smaller, more rigorous piloting in a new environment; local institutional and political economyconditions; the adequacy of proposed mitigation measures within the operating environment; and, importantly, the specialconsiderations around innovation projects in countries with socialist foundations (where funding innovation directly toenterprisesremains counterintuitive to ministries responsible for science, technology, andresearch).New concepts require clear definition and explicit agreement by all relevant entities onthat definition, including codification in the Project Manual and/or Financing Agreement. In this case, the newmodel of inclusive innovation was not clearly understood by the PMU (MPI) and PIU (MoST), resulting in the rejection ofsome sub-project proposals by the PMU because they were not considered innovative orinclusive.Complicated, inter-ministerial projects require practical and clear implementationarrangements andcommitment to adhere to those arrangements. In this case, disagreement between the PMU (MPI)and PIU (MoST) on procedures for sub-project selection completely derailed implementation progress, with the MPI in particular nothonoring the independent technical review decisions made by the professional science and technology program managementinstitutions(NAFOSTED).
P121648 | Gaza Solid Waste Management Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099110623184014061/text/P12164803040a80600a21500bbf01089135.txt | http://documents.worldbank.org/curated/en/099110623184014061/pdf/P12164803040a80600a21500bbf01089135.pdf | The ICR (p. 27-28) provided several lessons learned, which were adapted by IEG: Flexibility andadaptability of project design and implementation might positively impact the project outcomes in challenging and volatileenvironments such as Gaza. In this project, when implementation experienced delays due to risks to the safety ofcontractors and the lengthy and difficult approval process for certain types of construction materials, the Bank team was able towork closely with the counterpart and find solutions to address these implementation bottlenecks. Combininginfrastructure investments with institutional capacity building might improve the sustainability of project outcomes. Thisproject demonstrated that building infrastructure in a fragile environment with limited financial resources requires institutionalcapacity building to own, operate, and maintain the infrastructure after project closure. Using Results-basedFinancing (RBF) can positively impact service quality and delivery. In this project, when the project received AF, RBFpayments were based on specific service improvements and financial targets, which provided additional incentives to JSC-KRM toimprove service quality delivery and to increase fee collection.
P121651 | Environmental Sustainability and Energy Sector (ESES) DPL3 | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2012 | 2013 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/466851468185965896/text/ICRR14819-P110643-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/466851468185965896/pdf/ICRR14819-P110643-Box394823B-PUBLIC.pdf | Please see the detailed PPAR evaluation carried out by IEG in parallel for more information.
P121651 | Environmental Sustainability and Energy Sector (ESES) DPL3 | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2012 | 2013 | 2016 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/833321468189848942/text/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.txt | http://documents.worldbank.org/curated/en/833321468189848942/pdf/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.pdf | 6. Lessons 6.1 The Bank can maximize its development impact by concentrating its strategic engagement including its lending and advisory support in sectors with track records of success. Even in large middle income countries, the Bank can sometimes maximize its impact by engaging in only a few sectors with heavy concentration of support, rather than trying to cover all sectors but being unable to sustain continuous engagement. Turkey chooses to engage with Bank in only a few sectors, based on track records of success in those sectors. The long term engagement of the Bank in the electricity has helped to build a critical mass of operations that allows for significant locally based expertise (multiple sector experts in the Bank's Turkey country office), relationships of trust with key stakeholders, and use of a range of instruments (including investment lending, analytic work, and policy lending) which have relative advantages in supporting particular sub-objectives. 6.2 A well-designed programmatic DPL can be a key instrument in the Bank's long-term engagement. The DPL instrument can leverage the Bank's strengths on technical advice, convening power, and credibility to help support sector reforms that can have substantial impacts. In this DPL series, the electricity sector reforms had a strong design and so were successful in supporting the government's goals of increasing private sector investment in electricity generation. In contrast, the design of the environmental pillar was less well designed and so the DPL provided little additional impact relative to a without-operation counterfactual. 6.3 Prior actions should focus selectively on those reforms that are critical to achieving project objectives but are difficult to undertake because of political or institutional resistance. These are the cases where the DPL's ability to apply some pressure can have an additional impact. In this operation, prior actions on electricity tariff reform, cost-based electricity pricing, and distribution company privatization important effects. 6.4 Prior actions should also ensure that they are additional to what would occur in the absence of the DPL operation. A DPL is unlikely to lead to implementation of major government policies that would not have otherwise occurred, especially in large middleincome countries; effective policy changes require a high degree of government ownership. But a DPL can help governments to increase the pace of reforms and their technical quality if the existence of a prior action or trigger is a significant motivating factor. In this operation, many of the environmental policy reforms were motivated primarily by engagement with the EU rather than the Bank and by a desire for EU harmonization to support potential accession, and so the existence of Bank DPL triggers had little additional impact. If a DPL is used primarily to establish a policy dialog rather than to achieve substantial development results through the prior actions then it may have little impact. 6.5 DPLs can achieve good outcomes when they serve as the culmination of a process of engagement, as in the electricity sector in Turkey. With sufficient background work, DPLs can have significant heavy policy actions from the first operation. This increases the impact, and reduces the risk of failing to achieve positive results should the planned programmatic series not be completed. DPLs may not work as well if used as the initial point of engagement for a sector, as in the environmental aspects of this operation. Hopes that policy dialog through a DPL will then lead to a pipeline of follow-up projects may not eventuate. 6.6 A comprehensive yet well integrated set of market reforms can provide credible signals and incentives to private investors. A wide set of market reforms can provide credible signal to investors; combined program of price reforms, market development, incentives for RE, privatization encourage large scale investment. The order of reforms can be important in determining successful\. privatization can be more effective if investors are confident that there will be clear market demand. 6.7 Changing laws and regulations may not have much impact on environmental outcomes when environmental management agencies are weak and lack implementation and enforcement capacity. In these cases a DPL may not be the most effective instrument for achieving environmental goals. 6.8 A Bank DPL may have little additional impact if the design does not fully incorporate the existing political and institutional motivations. In this case, the primary motivation of the government for many environmental reforms was on EU harmonization, and the Bank's DPL added relatively little to this effort. The Bank may have had more impact if it had covered environmental issues not already covered by the EU harmonization process.
P121671 | Sustainable Cerrado Initiative: Goias Sustainable Cerrado & ICMBio Cerrado Biodiversity protection project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2015 | 2021 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/764121611172158662/text/Brazil-National-Biodiversity-Mainstreaming-and-Institutional-Consolidation-Project-and-Sustainable-Cerrado-Initiative.txt | http://documents.worldbank.org/curated/en/764121611172158662/pdf/Brazil-National-Biodiversity-Mainstreaming-and-Institutional-Consolidation-Project-and-Sustainable-Cerrado-Initiative.pdf | Lessons 2.35 A critical element for the success of projects that seek to promote the mainstreaming of biodiversity across sectors, both public and private, is strong ownership and active participation by representatives of the various institutions involved throughout the project's life. This element was present for PROBIO 2 but was largely lacking in the case of GEF Cerrado, which was additionally complex because two levels of government were involved. 2.36 A firm up-front understanding of the underlying political, economic, and territorial contexts of the geographic area in which a project is seeking to establish new or expand existing protected areas is essential to properly gauge the possibilities of achieving such an objective. The most significant impediment to the creation of new protected areas in the Cerrado at the state level proved to be bureaucratic and political resistance to doing so. Neither of these constraints was identified as a risk at appraisal, even though it was well known that large parts of the Cerrado were already occupied by medium and large export-oriented commercial agriculture and ranching establishments. Project preparation would have benefited from a comprehensive stakeholder analysis, if not a full consultation, which would have allowed both the Brazilian government and the World Bank to better anticipate potential support for and opposition to the actions proposed. 2.37 Experience in Brazil (and elsewhere) has shown that government commitment to project objectives and design can shift significantly over time due to changes in administrations, both at the federal and state government levels. For GEF Cerrado, this risk was recognized at appraisal but assigned a low possibility of affecting project implementation. In retrospect, it should have been considered more seriously up front, especially given the project's unusually long gestation period. 2.38 Lessons from environment projects that use concessional financing, both successful and unsuccessful, can have policy implications that extend beyond the original project's intentions. Despite its considerable design shortcomings, implementation difficulties, and moderately unsatisfactory outcome, the GEF Cerrado Project directly contributed to evolving World Bank support for the biome. One of the main project outcomes was finalization of the Action Plan for the National Sustainable Cerrado Program, which aimed at preventing and controlling deforestation and fires in the biome and was largely implemented through nine later World Bankâ€“managed projects financed by trust funds from sources other than GEF.
P121673 | Social Assistance System Modernization Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/308931545426216900/text/Romania-SOC-ASST-SYST-MOD-Results.txt | http://documents.worldbank.org/curated/en/308931545426216900/pdf/Romania-SOC-ASST-SYST-MOD-Results.pdf | The ICR (pp. 24-26) provided several useful lessons learned,including:Government commitment and enabling legislation is critical for successful project implementation.This project was negatively impacted by frequentpolitical changes and challenges, such as the MoLFSP having ten differentministers and nine different state secretaries from five different political parties. Also, legislation and ministerial ordersnecessary to achieve the projects objectives were delayed or never passed.It is critical forDLI-based projects that funds flow directly to those who are accountable for the achievement of implementationresults. In this project the funds went to the Ministry of Finance, which maintained the same operational budget forNASBI, independent of the achievement of the DLIs. Using this results-based project to provide NASBI with a bonus if DLIswerebeingachieved could have provided additional incentives.Keeping the design of results basedfinancing projects simple and narrowing it to a specific program rather than the overall reform of the social sector allows foreasier modification of project design during implementation, should that provenecessary. This projects designwas overly complex and included the entire social assistance sector, making the management of the project challenging. Also,the design included DLIsthat were defined in detail, in terms of which steps needed to be taken to achieve planned outcomes.This made corrections or modifying steps to achieve the objectives challenging.Innovations inBank operations can be costly, and therefore it iscritical that there is space for learning from implementation experience.This project was the Banks first results-based financing project in the region and sector, and while the projectfaced several challenges it also provides many lessons learned on how to better design and implement DLI-based operations.
P121686 | LR: Youth, Employment, Skills Project | Western and Central Africa | Liberia | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/312821498487036154/text/ICRR-Disclosable-P121686-06-26-2017-1498487026364.txt | http://documents.worldbank.org/curated/en/312821498487036154/pdf/ICRR-Disclosable-P121686-06-26-2017-1498487026364.pdf | The ICR presentsa significant number of lessons at policy and implementation levels. Foremost among the former is the needto take account of capacity limitations and, where capacity is limited, to avoid complex solutions, as well as the challengesinvolved in a fragile context in ensuring basic integration and connection between interventions at programmatic and administrativelevels. With reference to lessons on implementation, the ICR emphasizes the need for transfer or progression routes between relatedinterventions in Components 1 and 2 and, in the case of Component 2, which it describes, at heart, as an Active Labor MarketProgram, the need for more concrete implementation mechanisms linking demand and supply. IEG notes these lessons and emphasizes thefollowing: Although theobjectives of the project were clearly relevant in a narrowly defined sense, theassessmentofrelevance, to be meaningful,has to be more than the desire to achieve something as set out inofficial policy or strategy. It must also take into account the issue of feasibility or deliverability, as attempts toachieve an unrealistic objective, such as originally articulated under the second objective of this project, can result insignificant wasted timeand effort. This is particularly the case in fragile contexts and a crisis response. In thoseinstances, simplicity and incremental concentration on making things work are appropriate.
P121731 | India: ICDS Systems Strengthening & Nutrition Improvement Program (ISSNIP) | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099021224143031616/text/P12173111cd8550731bf951fa6f6458837c.txt | http://documents.worldbank.org/curated/en/099021224143031616/pdf/P12173111cd8550731bf951fa6f6458837c.pdf | Employing specific and clear incentives can serve as important motivators to achieving results. Theprojects transition from input-driven funding to disbursement-linked indicatorseffectively enhancedstateinvolvement to achieve outcomes. Similarly, offering incentives to ICDS field functionaries for enhancing their performance,including timelyhome visits and organizingcommunity events, emerged as appropriate motivational tools, driving tangibleresults.Harmonized donor coordination can enhance efficacy and efficiency. The Multi-donor Trust fundmechanism, established in partnership with the Bill and Melinda Gates Foundation (BMGF), Childrens Investment FundFoundation (CIFF), and Tata Foundation, played a pivotal role in course correction by offering valuable technical assistance. Theharmonized donor coordination through a single trust fund proved effective in aligning efforts under a unified thematic frameworkand optimizing resource utilization.Leveraging technology can bolsteraccountability and efficiency.Through project implementation, the project demonstrated use of technology solutions like the ICDS-CAS and subsequently,the Poshan Tracker. These mobile technologies demonstratednotable advantages such as substantial time savings for fieldworkers, quality ofservice delivery, and the capacity to track outcomes in real time. By capitalizing on these innovations,the program demonstrated how technology integration can significantly enhance operational effectiveness and provide an accurate andup-to-date account of progress.An incremental and institutionalized approach to capacity building ensureseffectiveness and sustainability. The incremental learning approach, as executed in the program, encompassed identifyingissues, devising locally viable solutions, and gradually applying this knowledge in a phased manner. This involved addressingchallenges faced by functionaries in prior training rounds and implementing solutions in the subsequent months practices. Thestrategy focused on progressively building upon small increments of learning, gradually integrating all skills, comprehension, andactions into regular practice, and ensuring full internalization by the functionaries.Incorporating projectinterventionsinto national systems fosters long-term sustainability.Project initiatives such as theincentives-based payments were adopted as routine practice in the ICDS program. Similarly, the grievance redressal system willcontinue beyond the project. For instance, the grievance redress mechanism established as a helpline in Gujarat has evolved into atwo-way system, enhancing accountability between various tiers and empowering beneficiaries by providing them a platform forvoicing their concerns.Lessons learned from the project were integrated into the Government approach to combatmalnutrition.
P121755 | Afghanistan ICT Sector Development Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/482151542811071074/text/Afghanistan-Afghanistan-ICT-Sector-Development-Proje.txt | http://documents.worldbank.org/curated/en/482151542811071074/pdf/Afghanistan-Afghanistan-ICT-Sector-Development-Proje.pdf | The following four key lessons are taken from the ICR with some modification by ICRreviewer: In a country with capacity limitation and serious security issues that do not allow for muchhandholding, the project should be kept simple. Project complexity, especially in in the context of Fragility,Conflict, and Violence (FCV), may negatively affect the outcomes. Given the security and governance issues in Afghanistan and thelimited and indirect access of Bank staff to provide implementation support, the challenges in fully achieving all three objectiveswere huge and difficult to foresee at appraisal. The transfer of skills from consultants to theagencys staff is important. PMOs benefit from consultants to support project implementation; yet long-termdependence on consultants may hinder capacity building within the government agencies. The consultants in the PMO should be hiredto perform high-level strategic tasks, one of which should be training and mentoring (permanent) staff in the implementingagencies. Cross-sector coordination is important to make sure a dig-once policy isimplemented. Ensuring a dig-once policy in transport and electricity projects can improve efficiencyand possibly save a significant amount of money on the deployment of fiber optics. For such a policy to happen, good communicationis important to ensure that decisions at the central government level are transmitted to the implementation level. For example, theSalang-By-pass Road construction, one of the components of the Afghanistan: Tran-Hindukush Road Connectivity Project (P145347, IDAD0930, $250 million, approved on October 20, 2015, effective on January 17, 2016), includes the laying of communication/fiber opticducts based on detailed discussion between the Bank, Ministry of Public Work andMCIT. Special attention should be paid to the development of ME Framework inFCV countries. Especially in FCV countries that have major security concerns it is challenging to identify MEindicators that are trackable. It is important to ensure that the ME framework is designed to capture the most relevant datathat will feed into the evaluation of the projects PDO. This underscores the importance to formulate the theory ofchange, to identify the projects achievements, and methods by which the achievements will be met. It helps buildconsensus among all project stakeholders in the projects design, and casts a light on binding constraints to achieveexpectedoutcomes.
P121774 | Second Kerala Rural Water Supply and Sanitation Project (Jalanidhi II) | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/500951592314365788/text/India-IN-Kerala-RWSSP-II.txt | http://documents.worldbank.org/curated/en/500951592314365788/pdf/India-IN-Kerala-RWSSP-II.pdf | This review has drawn three lessons based on the ICR incorporating material on lessons listed on page 25 of theICR.Relying only on demand-responsive approach can fall short of ensuring long term sustainability of small-scalerural water schemes. In a demand-responsive approach, rural communities are responsible for the construction and operationof water schemes. They contribute to the construction cost and user charges are expected to cover the operation and maintenancecosts. The findings of independent studies show that the sustainability of community-operated water schemes tend to decrease in themedium and long term. Furthermore, if there is a major repair needed or a breakdown caused by natural disasters, as was the case inJalanidhi II, the communities may not have sufficient funds to cover these high costs or technical capability to repair the system.Therefore, a well-defined government-supported mechanism may be needed for financial, technical and institutional sustainability ofthe community-operated schemes.Government agencies can perceive community-operated water schemes as a threat totheir role in rural water supply and resist to such interventions resulting in slow project progress and jeopardizing theachievement of the development objective. The Kerala Water Authority (KWA) had an important role inproviding bulk water for the operation of multi-GP schemes and some small-scale water schemes operated by Beneficiary Groups.However, some KWA officers resisted developing this partnership perceiving that it would undermine the role of KWA in rural watersupply. This was one of the main reasons for project implementation delays, especially in multi-GPschemes.Achieving the objective to provide services to address second generation sanitation issuescannot be possible without properly determining the level of demand for such services and the priorities of beneficiaries andgovernment authorities. The project was designed to finance solid and liquid waste management (SLWM) systems and theconstruction of septic tanks which were classified as second generation sanitation technologies. These projectactivities, especially multi-GP SLWM systems, did not progress at all due to low demand. Furthermore, access to improved water hada higher priority for the Beneficiary Groups than sanitation and the local governments priority was to achieve 100 percentOpen Defecation Free Status in Kerala through the construction of household toilets. Consequently, the project was restructured inJune 2016 and the focus of the sanitation services shifted from SLWM systems and septic tanks to the construction of householdtoilets.
P121779 | Nicaragua Social Protection | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/834601529674470496/text/Nicaragua-NI-Social-Protection.txt | http://documents.worldbank.org/curated/en/834601529674470496/pdf/Nicaragua-NI-Social-Protection.pdf | From an evaluative standpoint, one main lesson emerges from this review: although social protection projects measure outcome atthe beneficiaries level, the main added value of the Banks interventiontends to lieat the deliverysystemslevel, which is harder to measure and to capture in an evaluation. The Banks comparative advantage stems fromembedded institution and capacity-building within its operations and working at a systems level. Developing single models, buildingMIS that can unify scattered registries of various programs into one system, and supporting the planning and monitoring function atthe central and decentralized levels are among the most important contributions of this type ofintervention.The ICR also emphasizes two important lessons (among others listed in thedocument): Having a single unified registry of beneficiaries can becentral to improving theefficiency and effectiveness of social protection services delivery.A single registry can be used to identify current andpotential beneficiaries and serve as a single mechanism toselect/target families forkey social protection services .Unifying information into a single registrycan helpovercome fragmentation and dispersion of information across variousprograms within one ministry. If done well, it can also serve as a multi-ministerial platform to support referral andcounter-referral systemsfor services that are overseen by various governmental entities, a significant source ofefficiency. Inter-ministerial collaboration is fundamentalfor the successful implementation of this type ofsystem-wide social protection project. At the community level, working across ministries to provide a range of essential servicesto extremely poor families requires a high level of inter-ministerial collaboration that can be aided by a process of mapping ofsocial actors and social services, as wella systemfor receiving demands from the population and channeling them to theappropriate government agency.
P121796 | Second Safety Net and Social Sector Reform Program | Europe and Central Asia | Latvia |  | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2011 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/934861474629254151/text/000020051-20140626103734.txt | http://documents.worldbank.org/curated/en/934861474629254151/pdf/000020051-20140626103734.pdf | Investing in economic and social data analysis in good times and on a regular basis is all the more relevant in a time of crisis. The existence of regular reviews of spending and outcomes in the social sectors allowed the Government to rapidly design a relevant strategy to respond to crisis.Reforming social insurance, especially pensions, during a crisis is very difficult. The reform experience in Latvia has shown that pension expenditures exhibit very high inertia in times of recessions and even extremely reform-minded governments are not able to quickly reduce spending on such programs. Pension spending actually increased by 27 percent in real terms over 2008-2010. Although the Constitutional Court ruling about the pension reform was very specific and related to the lack of consultation on allowing cuts in pensions, the Government did not pursue the proposed reform.Reforming the social sectors during good times creates fiscal space to react during economic downturns. Contrary to Latvia, some countries among the EU12 started earlier to implement policies aiming at counteracting the demographic decline, which is large and certain: per capita financing and school consolidation in education, improved targeting of social assistance, increased retirement age, hospital consolidation, and increased focus on primary care provision, among others. Taking early steps: (i) allows limiting the cuts needed when a crisis occurs as poorly targeted social insurance expenditure can boom during economic contraction, (ii) accelerates fiscal consolidation as structural reforms consume time and political capital before actually providing fiscal savings, (iii) provides fiscal space through deficit and debt reduction allowing for counter-cyclical policy through discretionary policies, and (iv) prevents massive lay-offs of public workers at a time of crisis when increased unemployment would command the exact opposite policy.Budget rules should take into account economic cycles. It is important to consider the trajectory of social protection expendituresâ€”particularly unemployment benefits and social safety net support programsâ€”across the economic cycle in designing fiscal rules and buffer stock savings mechanisms.
P121800 | MEDEC Low-Carbon DPL Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/720491474857133494/text/000020051-20140626120612.txt | http://documents.worldbank.org/curated/en/720491474857133494/pdf/000020051-20140626120612.pdf | The following lessons were selected from the ICR, with adaptation of language:Meaningful targets are difficult to define within a short time period of implementation of a single-tranche development policy operation. As a partial solution under this DPO, and given the lack of mid-year data for many of the indicators, the time period for measuring the targets was extended from 18 to 24 months. With multiple implementing agencies involved, it may help assign a coordinative role to one of the agencies. For example, the coordination under this operation was carried out by the Ministry of Environment that had an overall understanding of Mexicoâ€™s broad climate change program and could assume responsibility for the broader global environmental goals of this DPO.
P121836 | Public Sector Strengthening Program - APL1 | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/985251541085970397/text/Argentina-AR-La-Rioja-Public-Sect-Streng-Prog-APL1.txt | http://documents.worldbank.org/curated/en/985251541085970397/pdf/Argentina-AR-La-Rioja-Public-Sect-Streng-Prog-APL1.pdf | The ICR (pp. 29-31) presented several insightful lessons, including:It is important to ensure that riskmitigation measures do not create other risks. In this case, the risk mitigation measure of bundling technical assistanceactivities into a single, large contract was smart compensation for limited implementation capacity, but delays then accruedbecause of a shortage of entities interested and eligible to bid. A more thorough market study during project preparation wouldhave foreseen this development.There is value in direct World Bank support at the subnational level.In this case, institutional strengthening was invaluable for one of Argentinas provinces with the highest share of poorhouseholds, and the benefits of the Bank direct engagement was recognized by high-level provincial authorities and publicofficials.Subnational public management strengthening is a prerequisite for improvements in servicedelivery in any single sector. In this case, reforms in cross-cutting public administration platforms and processes have beenimportant foundations for strengthening rural water management, and other sectors (health, education, etc.) should benefit alsofrom these basic public management reforms.IEG adds one additional lesson:Ongoingpolitical economy analysis can help anticipate threats to development outcomes and build in sustainability measures prior toproject closing. In this case, fiscal tightening threatens budget predictability and the articulation between budgetingand planning.
P121877 | Tonga Energy Development Policy Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2011 | 2011 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/441151475071976169/text/000020051-20140625220402.txt | http://documents.worldbank.org/curated/en/441151475071976169/pdf/000020051-20140625220402.pdf | The ICR identified a number of sound lessons from this operation, but four of them are emphasized hereunder: (i) the feasibility of sectoral DPLs, (ii) the importance of early engagement before the design of a DPL operation, (iii) the donor coordination leverage, and (iv) the usefulness of a comprehensive approach.(i) Sectoral development policy operations can be quickly mobilized and achieve good results in the context of a strong reform momentum. The Bank has the ability to respond quickly to provide budget support when facilitated by strong government ownership of a reform agenda. When a government displays commitment to a sector-specific reform agenda, this can form an adequate foundation for the operation supported by a development policy loan. (ii) AAA is critical for operations supporting major reforms. Prior sector engagement and dialogue can provide vital foundation for identifying key policy reforms that can drive further progress in important sectors, dialogue and engagement. The Bank can draw on that engagement and related analytical work for the the preparation of a DPL, and subsequent operations. (iii) Close coordination and engagement with other development partners in the identification of policy priorities are useful in sectors where the Bank has limited knowledge and engagement. The Bank did not have sufficient presence and knowledge of the procurement and treasury instruction actions where other development partners had taken the lead. Close coordination with the Asian Development helped the GoT to spearhead reforms in the procurement area. (iv) The importance of a total sector approach, as opposed to isolated interventions in the sector, yields better results. Both technical assistance and investment support are more effective when there are real plans and opportunities to provide a comprehensive support to a sector.
P121883 | AFGHANSTAT: Strengthening the National Statistical System | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/291161482262223201/text/ICRR-Disclosable-P121883-12-20-2016-1482262202930.txt | http://documents.worldbank.org/curated/en/291161482262223201/pdf/ICRR-Disclosable-P121883-12-20-2016-1482262202930.pdf | The ICR (pp. 21-23) provides a comprehensive set of insightful lessons, including:Capacity development in a fragileenvironment requires relatively simple, straightforward project design, with activities appropriately prioritized and sequenced,with high-level dialogue over the entire project lifetime to ensure consistent ownership. In this case, the implementingagencys low capacity was not adequately taken into account, and it became overwhelmed with activities, especially when thetwinning arrangement failed and circumstances outside the projects control created leadershipturnover.Flexibility of project design is appropriate when initial conditions are unstable. In thiscase, excessively overloaded and rigid project design, with early definition of all components and fund allocation, workedpoorly. A less structured and more sequenced design, with triggers to be met before proceeding to a next stage andopportunities for restructuring in the event of unforeseen difficulties, would have drawn more focused attention to roadblocks andmay have prompted more timely and successful course correction.The Banks operational procedures canprovide important opportunities to identify and elevate implementation issues. In this case, early formal assessments of theresults framework, ratings in implementation status reports, andthe mid-term review findings should have raised flags aboutcurrent and looming challenges.
P122007 | National Roads and Airport Infrastructure Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099090424070520700/text/P122007-577dd682-cacf-4f34-8408-e10b8478a78a.txt | https://documents.worldbank.org/curated/en/099090424070520700/pdf/P122007-577dd682-cacf-4f34-8408-e10b8478a78a.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Preparation of necessary technical studies for major transport infrastructure investments at designwould help in minimizing implementation delays. In this project, the road designs were not prepared during preparation.This contributed to delays following effectiveness, as final engineering designs had to be prepared.2. Allocationof Bank financing could help in ensuring that capacity building activities are carried out in countries with implementationcapacity constraints. The design of this project had several activities aimed at building institutional capacities of theimplementing agencies and other relevant entities in the country context. However, Bank financing was not allocated for theseactivities and hence did not have leverage to ensure that these activities are implemented. Most of these activities were notcompleted due to lack of government funding.3. Adopting timely actions for addressing the situation can help incountries with capacity constraints. In this project, at Government request, the Bank provided Hands-on ImplementationSupport (HEIP) to help the government in implementing construction of bridges.
P122008 | Yunnan Technical and Vocational Education and Training Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/113621538352636541/text/China-CN-Yunnan-Tech-Voc-Ed.txt | http://documents.worldbank.org/curated/en/113621538352636541/pdf/China-CN-Yunnan-Tech-Voc-Ed.pdf | Lessons drawn from the ICR (pages 27-29): Project designcan effectively balance acentralized approach (to ensure proper oversight and facilitate implementation processes) with localized needs. In the caseof this project, the PPMO-centralized structured allowed for proper oversight and facilitated implementation with standardizedprocesses and documentation. However, local schools were given the flexibility to develop their own curricular focus, at theappropriate pace of implementation. Strong school-industry collaborations can make asignificant contributionto relevanceand sustainability of activities. In the case of this project, industries were broughtintosignificant partnerships with TVET institutions, and these partnerships were thenconcretized into replicableandfinancially sustainable models.
P122028 | MA-Ouarzazate Concentrated Solar Power | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2012 | 2017 | 2019 | ICRR | Less than 10 million | Highly Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/290781535683312705/text/Morocco-MA-Ouarzazate-Concentrated-Solar-Power.txt | http://documents.worldbank.org/curated/en/290781535683312705/pdf/Morocco-MA-Ouarzazate-Concentrated-Solar-Power.pdf | The following lessons are adapted from the ICR:Innovative project structuring that combines balanced riskallocation with cost reduction can provide a conducive investment climate for the public-private partnerships. Giventhe high technological risk inherent to this project, the government shouldered several risks usually taken by the private sectorin standard PPPs, including provision of common infrastructures, as well as financial and technological risks. A streamlinedtender process was used to (i) reduce the costs to developers through transparent tender processes and clear procurement rules, andthe availability of background technical, social and environmental studies, and (ii) reduce the costs of funding for the project bysecuring financing from several IFIs at concessional rates. The parastatal nature of MASEN allowed such structuring whichpositively impacted overall implementation.Strong commitment of the Government is a prerequisitefor energy transitions. The Governments commitment to the increased role of renewables in the countrysenergy mix, and it support to the implementing agency, MASEN, provided the right institutional basis for this project.Government support materialized through a general convention before project commencement, and through a specific conventionfor this project. The Government support mechanism is being maintained for the subsequent CSP projects (Noor II andIII.)
P122032 | ID-TF ADDITIONAL FINANCING OF PNPM RURAL III FOR GENERASI (COMM.CCT) SCALING-UP PROGRAM | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/475351467992516644/text/ICRR14851-P122032-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/475351467992516644/pdf/ICRR14851-P122032-Box394823B-PUBLIC.pdf | Main lessons to be drawn from this project are: Demand side efforts are sufficient to increase the rate of utilization of health and educational services. However, complementary supply-side interventions are needed for higher-level impact. For the improved provision of frontline services over the long term, it is necessary to ensure engagement between demand and supply-side reform efforts. Generasi was effective in increasing the rate of utilization of services and in increasing service provider and community efforts to provide basic services. However, community and frontline service providers are limited in their ability to improve aspects of service provision quality, which is affected by factors such as the procurement of inputs like vaccines and the district budgets for operations and maintenance. An effective gender strategy must focus on both women and men, rather than exclusively on women. Since men play a key role in decisions that affect maternal and child welfare, such as directing household expenditures towards health and education services and nutritious foods, it is important that also men are involved in health and education awareness raising efforts. Greater local (district) government engagement is needed to institutionalize and sustain project mechanisms Generasi was integrated in the national government budget cycle, but only to a limited extent in district budgets. This resulted in the absence of an exit-strategy at the local level, and limited the opportunity for local governments to build on the projectâ€™s achievements or optimize use of the assets invested in by the project.
P122039 | Social Safety Net Strengthening Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2020 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/560991629220283966/text/Tajikistan-SOCIAL-SAFETY-NETS.txt | http://documents.worldbank.org/curated/en/560991629220283966/pdf/Tajikistan-SOCIAL-SAFETY-NETS.pdf | The ICR provided a long list of lessons under three headings Policy, Implementation, and Sustainability the mostimportant of which from IEGs perspectiveare:Social assistance reform can be a long process, particularly in asetting with weak implementation capacity, but can ultimately deliver far-reaching benefits and consequences for both thegovernment and citizens. In this case, policy reform efforts preceded the project, and the project itself ran significantly overtime, largely as a result of weak implementation capacity. However, improvements to the social protection system ultimatelydelivered a more sustainable and efficient system that better met the needs of citizens through more accurate targeting. As alsonoted in the ICR, better targeting has both an equity and an efficiency dimension: those most in need receive benefits, and thereare social protection system-level savings associated with better targeting.In line with IEGs discussion of theconditions underpinning successful scaling up in Selected Drivers of Education Quality: Pre- and In-Service Teacher Training(2019), the design of a pilot intervention should always have scalability in mind. It is important that pilot projects clearlycommunicate their objective as a building block for a national program, to ensure sustainability of the effort. This requiresstakeholder commitment and capacity.Fiscal and operational sustainability beyond project closing is a concern,particularly as it relates to financing the MIS/IT systems operation, retention of staff, and ensuring adequate and predictablebudget allocations from the government. Ongoing maintenance needs to be built into all scaling-up efforts to ensuresustainable development.
P122047 | Guinea-Bissau Biodiversity Conservation Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/898631487646853577/text/ICRR-Disclosable-P122047-02-20-2017-1487646829547.txt | http://documents.worldbank.org/curated/en/898631487646853577/pdf/ICRR-Disclosable-P122047-02-20-2017-1487646829547.pdf | The following lessons were extracted from the considerably longer Lessons section of the ICR: The pace for establishing a conservation foundation that requires the participation of manynational and international actors is beyond the control of a Bank project. It is therefore unwise to set overlyambitious targets that assume certain donors/projects will come to the table on time, and to base the success of the project onthis timetable. Expectations of fund-raising velocity at appraisal need especially to take into account potential political andglobal economic complications in fragile economies such as Guinea Bissau. A realistic time-line for the start ofoperation of a fully-endowed foundation should include a transitional, dormant period when a foundation isstructurally, legally and administratively established but its endowment is insufficient to support financialoutflows. The stability of the Bank and Client core teams is an important element in successful projectimplementation: In this project they remained largely in place with a strong commitment to the over-arching vision for theprojects development objectives.This enabled the establishment an excellent working relationship based on mutualtrust, and supported by the benefit of institutional memory. This mutual understanding has been of great importance duringtechnically challenging projects in difficult country conditions. With international support, public institutionscan be sustained through repeated unrest and government turnover if they are administratively and financially autonomous.This is particularly true for institutions that serve national, regional and local interests, such as those thatsupport conservation and biological diversity. The institutional design in this project was critical to its credibility and successthrough unstable political condition. This contrasts with the instability of the more typical projects where the institutionresponsible for achieving the projects development outcome is embedded in a Government run agency withpolitically-appointed senior management.
P122065 | West Africa Agricultural Productivity Program APL (WAAPP-1C) | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/113401600092671097/text/Western-Africa-West-Africa-Agric-Prod-Progrm-WAAPP-1C.txt | http://documents.worldbank.org/curated/en/113401600092671097/pdf/Western-Africa-West-Africa-Agric-Prod-Progrm-WAAPP-1C.pdf | The ICR included 18 lessons. The following three are emphasized with some adaptation of language: Aregional approachto agricultural development allows bothrationalizingand optimizingthe use ofAfricas scarce resources; andachieving development impacts more rapidly in individual countries. Evidencefrom the WAAPP series showsthat a regional approach can rationalize and optimize the use of Africas scarce resourcesto develop regionally relevant mechanisms and tools and achieve development impacts more rapidly in individual countries andthroughout the region. The regional approach of the project was instrumental for successful collaboration in developing and sharingtechnologies and innovations (TI) across borders, as well as for streamlining trade in agricultural inputs and outputs. Thepeer learning and bench marking of progress reinforced the commitment of each participating country to achieve the developmentoutcomes. A regional approach allowsharnessing the benefits of modern technologies, overcoming the limitations of innovationsystems that are too small to produce meaningful results working alone, and increasing agricultural productivity for millions offarmers. A well designed and streamlined Results Framework is critical to fully capture the outcomes of aregional project. The WAAPP results framework was complex, with many indicators. Although the indicators were relevant,they were costly in terms of time and human and financial resources. For a regional project covering many countries, the resultsframework should be streamlined to include critical PDO and intermediate results indicators, which would ease data collection andanalysis at the national and regional level. A gender-responsive, gender-tagged regional project requires thedevelopment of a sound regional gender mainstreaming strategy, a gender screening tool, and national gender action plans.The projects gender strategy and action plans made it possible for the project to definitively adopt a gender approach, andreach the target for 40% of beneficiaries to be female.The project developed a clear understanding of mens andwomens activities in agricultural value chains, along with the gender constraints involved, to inform the research programand ensure that it would generate technologies addressing womens and mens specific constraints. The actors involvedin implementation received training to build a gender-sensitive team. Consequently, the project was able to address gender-specificneeds to improve productivity and income, close the gap in womens access to improved TI, and enhance familywelfare.
P122096 | Bihar Kosi Flood Recovery Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/608691559581464603/text/India-IN-Bihar-Kosi-Flood-Recovery-Project.txt | http://documents.worldbank.org/curated/en/608691559581464603/pdf/India-IN-Bihar-Kosi-Flood-Recovery-Project.pdf | IEG selected three lessons from the ICR, with some adaptation of the language:Anowner-driven housing approach can succeed when accompaniedby therobust implementation support and streamlined fundingmechanisms. The project was successful in setting up a hierarchical implementation support system from the implementingagency at the central level to each district and block level to reach out to each beneficiary and monitor the progress of housingreconstruction. However, it also required huge manpower and continuous capacity building and trainings to maintain sufficientsupport from each staff at the district and block level, which also resulted in slow progress. Further, to have project-dedicatedbank accounts of the beneficiaries from the start of the project and a strong monitoring framework was one of the important lessonsfrom the housing component. Both these measures were implemented later during project implementation, along with betterarrangements with banks for effective tracking of funds and appointing financial management support consultants since inception forlow-capacity implementing agencies.Community ownership and outreach can be an important contributorto the achievement of theproject objectives and maximizing impacts. The project promoted a build backbetter concept to the GoB and beneficiaries of the project. As a result, the targeted beneficiaries have chosenmore-resilient, better houses among different types of design, a design choice that was widely circulated among the surroundingnon-beneficiaries as well. Because of the owner-driven approach, the project also accommodated voluntary requests frombeneficiaries during implementation such as addition of toilet construction that resulted in high satisfaction of thebeneficiaries.Lack of a careful assessment of the institutional readiness forWorld Bank operations at preparation may lead to delays. Adequate risk assessment of the institutional arrangement wascritical, even though the project was prepared under the Emergency Recovery Assistance Procedure. The project faced operationaldelays in the beginning mainly because of the new setup of the institution to manage the project with limited understanding ofWorld Bank operations. In the process of implementation, strong ownership by the GoB and the adequate Government counterpartfunding helped theproject management unitandimplementing agenciesgradually build their capacityforthe project operation.
P122099 | C.A.R. Community Reintegration Project | Western and Central Africa | Central African Republic | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2014 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/720291468190758632/text/ICRR14814-P122099-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/720291468190758632/pdf/ICRR14814-P122099-Box393228B-PUBLIC.pdf | A number of lessons are derived from a longer list discussed in the ICR:In a fragile and post-conflict context, project design and implementation arrangements need to be kept simple. This project provided small grants for implementation to non-governmental organizations with substantial experience and capacity, which were operating on the ground. In fragile and post-conflict countries, a community- driven approach may be the best option when the Government capacity is weak and its presence is low. This project's bottom-up approach through communities could help make some improvements to the most vulnerable and conflict- affected population.Extra resources and effort should be put into generating baseline data in fragile and post-conflict contexts. In this project, lack of baseline data for many indicators made it difficult to clerly ascertain the value added by the project.
P122123 | Zambia: Livestock Development and Animal Health Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/946421550710466283/text/Zambia-ZM-Livestock-Develop-Animal-Health-Prj.txt | http://documents.worldbank.org/curated/en/946421550710466283/pdf/Zambia-ZM-Livestock-Develop-Animal-Health-Prj.pdf | The ICR included five lessons. The following three are emphasized with some adaptation oflanguage: Amultipronged approach and a balanced attentionare needed toestablishthe basisfor longer term and higher impacts on livestock production and productivity. Failure toaddress one aspect has the potential to seriously undermine parallel efforts. Animal health, feed, genetics, and herd management,need to be embraced simultaneously to achieve optimal results. Projects supporting livestock development shouldaddress theweakest elementsandfollow a balanced attention to themain drivers/constraints for livestock production andproductivity.Theproject was strong in animal health, butweak in complementary investments to raiseproductivity. Institutional strengthening takes time and a project should not rely too heavily onexpected reforms to achieve certain results. Development and adoption of new policies and strategies, legal reforms orsignificant changes in a system, may be required to improve performance and compliance with standards and best practices over time.However, a typical project timeframe may not allow them to materialize fully, if at all, considering the many constraints outsidethe projects control. Therefore, while efforts should be pursued to maintain and accelerate reforms where needed, projectsshould avoid including activities dependent upon such reforms. To capture the projectsachievements, the ME system needs to include clear baselines and measurable indicators that are aligned withactivities. It is important to ensure clarity upfront on indicator definitions and scope to avoid ambiguities and minimizemid-term revisions to indicators unless the scope of the project has changed. Baselines and targets need to be carefully thoughtthrough with a suggested footnote in each instance on source and justification for choices made. A separate practical and handyME indicator definition handbook including methodologies to capture indicators should be developed consultatively with theclient as early as possible before or at the onset of implementation. It is also crucial to manage the potential conflict betweenwell intentioned designand actual capacity for implementation (on the ground) to get ME right.
P122124 | Nigeria - State Education Program Investment Project | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Education | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/531841624623771924/text/Nigeria-NG-State-Edu-Program-Inv-Project.txt | http://documents.worldbank.org/curated/en/531841624623771924/pdf/Nigeria-NG-State-Edu-Program-Inv-Project.pdf | IEG draws severallessons from the ICR:Output-type objectives may be stronger when direct links areestablished to higher level outcomes. A major objective for the Nigerian education system is providing access to qualitybasic education.The project supported this by providing better learning tools: teachers and the schoolenvironment.However, it stopped short of examining the implications of project interventions on the teaching-learningprocess.Building formal relationships between the school system and the community can revive and mobilize both inthe face of adversity.The project advocated for community (and increased female) participation in school committees,and this active engagement on a broad front was intended tore-engage teachers and students in the schools, increase a senseof security in exposed communities, and lead to better monitoring of the school community.
P122139 | Industrial Waste Management and Cleanup Project | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099102824153011944/text/P122139-74060bf0-63fa-4d10-94db-2da1d44c1d72.txt | https://documents.worldbank.org/curated/en/099102824153011944/pdf/P122139-74060bf0-63fa-4d10-94db-2da1d44c1d72.pdf | The ICR (p.32-33) provided several useful lessons learned, which were adapted by IEG: Ensuring sufficientinstitutional capacity and ownership during project preparation through, for example, a phased approach might benefit projectimplementation. In this project, EPA was a relatively new agency with limited capacity, which resulted in implementationdelays. Considering this, the project could have benefitted from a phased approach, starting with smaller and fewer project sites,and scaling up to more sites once EPA built capacity to lead a more complex project implementation. Definingclear implementing arrangements including financial responsibility between the project site and the government during projectpreparation is critical for a smooth implementation. This project experienced implementation delays during theinitial project phase partially due to the government not deciding to lift the loan repayment requirements by a thirdparty. Designing an adaptable and robust Results Framework with a clear methodology and implementation structureis key for measuring the progress towards achieving theprojects objective, especially in legacy pollution clean-upprojects that are subject to high level of uncertainty. In this project, the target for the Bijela site was measured inpercentage rather than in tons, despite discovering more contaminated soil than anticipated, not sufficiently demonstratingthe positive outputs of project activities.
P122151 | Kiribati Road Rehabilitation Project | East Asia and Pacific | Kiribati | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/170711556730194425/text/Kiribati-Kiribati-Road-Rehabilitation-Project.txt | http://documents.worldbank.org/curated/en/170711556730194425/pdf/Kiribati-Kiribati-Road-Rehabilitation-Project.pdf | TheICR identified a number of lessons which could be categorized under five headings: (i) using projects tointroduce improved practices; (ii) identifying opportunities for leveraging and supporting other projects; and, (iii) establishingfoundations for future collaborations. Lessons were also drawn based on: (iv) the challenges of remoteness; and (v) capacitylimitations.IEGsummarizes them below: Roads projectscouldbe innovativein its design byintroducing suchimproved practices as catering for persons with disabilities, gendertargeting, protecting vulnerable users through hard infrastructure, awareness of the future impact of climate change in selectingappropriate pavements, and focus on occupational health and safety. The project design terms of reference called foruniversal design principles to be applied but it is also important to undertake thorough technical reviews of designdocuments in the procurement stage to make sure these principles are properly considered. Gender sensitive surveys were translatedinto project activities (e.g. location of bus stops and street lighting, employment opportunities for women duringconstruction).Afocus on hard infrastructure is a valuable starting point for all road safety activities.Proactive review ofthe records for injuries and monitoring compliance with occupational health and safety under the projecthelped ensure this remained a priority for the contractor. When the government face challenges inimplementing multiple projects with complementary activities, practical approaches can be developed to improve coordination betweendonors and between projects. For example, fundscan becombined with a project funds into a single procurementpackage, engaging one contractor. This not only can reduce the procurement effort, but also simplify supervision and safeguards,reducing the burden on both government and donors. Procurement and financial management activitiesof donor- financed projectscan be transferred to a centralproject management unit if established in the government. Jointco-financing particularly for fragile statesis a useful way to reduce the implementation burden on limited capacityimplementation agencies, however, it needs to be adapted to the specific project arrangement. The concept of having alead donor responsible for clearing all safeguard documents and procurement documents after giving dueconsideration of the views of other donors- proved to be a pragmatic solution. Conducting most missions jointly under this project,with aide memoires signed by all three donors, sent a clear and consistent message to the government regarding the projectsissues and progress. The use of joint co-financing, however, increased the demands on the project team as they needed to liaisewith other donors and include the additional layers of clearances. The nature of the co-financing should be tailoredto the project specifics and in some instances setting up framework arrangements with other development partners is key to reducingthe burden on low capacity implementing agencies. In remote small island states, such as Kiribati andother Pacific Island Countries, higher cost contingencies need to be factored into project design.Atthe timeof bidding for the road works under this project in Kiribati, the contractors priced the remoteness and risk of the projectfundamentally differently, as evidenced by the bids ranging in price by 30% (and also being 20% above the EngineersEstimate). This pattern has been observed across the Pacific and it would be valuable for further analysis to be done toinvestigate in detail how cost estimates could be made more reliable, both at appraisal and at the time of bidding. A substantialremoteness cost premium should be included in the cost estimates. Capacity limitations requirescertain approaches and can be factored in project design. Under this project, project timeline was unrealistic. Thesuccess of the project is directly dependent on the project manager and the local implementation team, and oftena scale- upof donor activity competes for a few people available to perform these roles. Intensive implementation support is required in theearly years. Efforts of development partners should continueto build capacity of local specialists and facilitate transfer ofskills from international specialists and advisors. Technical expertise for monitoring of consultants is required when governmentslack capacity. Expect the unexpected: civil works contracts should anticipate a time contingency in theimplementation schedule, in addition to the cost contingencies.
P122153 | Cameroon Mining Sector Technical Assistance Project | Western and Central Africa | Cameroon | Blend | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2012 | 2022 | 2024 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible |  |  | 1. In a highly politicized and complex sector such as mining, the project development objectiveneeds to be realistic and well defined. This project was overly ambitious.Given the nascent stage ofCameroonsmining sector, more narrow objectives and indicators might have been easier to reach and mighthave led tofurther phases for this kind of technical assistance.2. Counterparts for TA projects needto be ready for implementing the project to avoid or minimize problems during the implementation stage, with Bank assistance asappropriate. Prior to project launch, the implementation structures should have been established, the projectmanuals finalized, all the technical preparatory work completed, and policy-level commitments agreed. When there are constraints,such as set timelines due to IDA cycles, or some preparatory work on hold until loan approval, the use of PPAs or specializedgrants can help expedite the desired results. 3. The strategy to transferproject assets to an appropriate structure needs to be developed and agreed as early as possible, to ensure their effective andefficient management in the future, and to avoid derailing the sustainability of project achievements. This is especiallytrue in countries like Cameroon, which are characterized by political instability, poor governance, and weak capacity. Prior tofunding, policy-level decisions on the future use of outputs should be adopted, especially those intended as a public good. Aninstrument should be built in to mitigate the risk of reversing key policies and reforms during implementation, as was the casewith PRECASEM.4. The COVID-19 pandemic has highlighted the need to operatedifferently by being more adaptive, flexible, and innovative to better manage turbulence and uncertainty. The pandemic hasalso highlighted the need to expand internet access quickly and broadly to effectively reduce the risk of disruption during such acrisis situation.
P122178 | Turkey SME Energy Efficiency Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/265301597241751958/text/Turkey-Turkey-SME-Energy-Efficiency-Project-GEF.txt | http://documents.worldbank.org/curated/en/265301597241751958/pdf/Turkey-Turkey-SME-Energy-Efficiency-Project-GEF.pdf | This review has drawn two lessons incorporating material on lessons listed on pages 21-23 of the ICR.Flexibleeligibility criteria can facilitate the development of a sufficient subproject pipeline. The Debt Service Coverage Ratiocriterion was high for some otherwise-financially-viable SMEs to meet in every year to be eligible for financing. The number ofsubprojects increased after this criterion was lowered from 1.2 to 1.1 and removed for sub-loans below US$1.0 million. Furthermore,the inclusion of the eligibility criteria in the Loan Agreements required project restructurings when there was a need to revisethe criteria. Although this did not have a substantial adverse impact on the operational and administrative efficiency of theproject, some restructuring could have been avoided if the eligibility criteria had been included in the operationalmanuals.Subgrants can be critical, rather than the loan loss reserve funds, in demonstrating the successfulimplementation of the ESCO model but might not be sufficient for its sustainability. The experience of the projectconfirmed the findings of other projects with similar guarantee and credit enhancement schemes that loan loss reserve funds aregenerally insufficient to encourage the FIs to lend to small ESCO firms with weak balance sheet or limited experience. Followingthe introduction of GEF-funded sub-grants as incentives for ESCO subprojects at the second restructuring, there was a sharpincrease in the number of these subprojects. The project was successful in achieving the target set for alternative businessmodels, but due to the complexities and transaction costs of this model, absence of grants or similar incentives might hamper thesustainability of this model after project closing.
P122194 | HIGHER EDUCATION QUALITY IMPROVEMENT | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2013 | 2018 | 2019 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/545451553264129845/text/Peru-PE-HIGHER-EDUCATION-QUALITY-IMPROVEMENT.txt | http://documents.worldbank.org/curated/en/545451553264129845/pdf/Peru-PE-HIGHER-EDUCATION-QUALITY-IMPROVEMENT.pdf | 1. Transfer ofcapacity for project implementation and coordinationrequires up-frontdefinition and attention. The project counted on implementation services supported by a self-standing project coordination unit(PCU) within the ministry but financed by the project. The unit acquired invaluable experience and managed important processes thatwill outlive project financing. IBRD has been informed that several project activities will be entrusted to different unitsresponsible for these activities both within and outside of the Ministry of Education, but it is still unclear by whom the overallcoordination and important technical assistance will be carried out after the PCU loses funding. This could affect sustainabilityadversely.2. For reliance on a large number of inexperienced institutions to implement diverse improvementplans, provision of direct implementation services is preferable to grant funding, especially when supported by a successfulproject procurement management and monitoring system. In this project, this procurement arrangement helped monitor progress andensure implementation faithful to proposals. The monitoring helped identify TA needs that could be filled by intensive attention bythe PCU. As a result, the number of bidding rounds exceeded plans, and the number of improvement plans completed by project end was100%.3. The best designed indigenous peoples planning framework (or other safeguard response) does notin itself assure proper implementation, particularly if institutions responsible for implementation are multiple, inexperiencedand scattered. Monitoring is essential, and the results framework of the project should contain some related indicators, to feedinto supervision which needs to report on safeguards implementation. In this project, a decision was made at appraisal to have theIPPF apply to only one of the projects three components, which may have meant lack of access of targeted institutions to someearly essential TA. As a result, the targeted institutions lacked capacity to apply for services under improvement plans and wereneglected in the first seven rounds of competition. Late in project implementation, a decision was taken to reserve one of thecompetitions specifically for them, and TA was provided to ensure adequate quality applications. A high percentage of theapplicants met the standards in that round, and 100% completed improvement plans.
P122201 | BD: Leveraging ICT Growth, Employment and Governance Project | South Asia | Bangladesh | IDA | Non-FCS | Digital | Digital Development | IDA | IPF | 2013 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/841851595538001728/text/Bangladesh-BD-Leveraging-ICT-Growth-Employ-Gov.txt | http://documents.worldbank.org/curated/en/841851595538001728/pdf/Bangladesh-BD-Leveraging-ICT-Growth-Employ-Gov.pdf | The ICR (p. 31-33) included very useful lessons, which were adapted by IEG: The Information Technology(IT)/IT-Enabled Services (ITES) industry growth depends on a number of national and international macroeconomic factors. Therefore,delayed impacts of industry activities on growth, employment, exports and potential sectoral disruption need to be taken intoaccount when defining the projects objective and selecting indicators for measuring achievement towards theobjective. In this project, data was limited for the selected indicators and the project had to develop its own industrystudy and rely on academic institutions to ensure the reliability of the data. Building IT/ITEScapacity across functions and organizational hierarchies is beneficial for the entire sector to stimulate industry development.In this project, the digital business transformation training was particularly useful for local users to develop digitalleadership mindsets and networks to the local and international industry standards. Activitiestargeted to women can potentially result in higher female participation. In this project, students enrolled in the projectwere selected from different science/engineering subjects with a selection process that maintained a minimum gender ratio of 30percent to support womens participation. Also, communication activities were conducted by female spokes persons, targetingmedia channels, encouraging woman to become master trainers, and reaching out to women-oriented educational institutions. Theseapproaches resulted in the training of over 10,000 women.
P122202 | Georgia: Third Development Policy Operation | Europe and Central Asia | Georgia | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2018 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/352991530210847614/text/Georgia-first-second-and-third-development-policy-operations.txt | http://documents.worldbank.org/curated/en/352991530210847614/pdf/125186-PPAR-P112700-P117698-P122202-PUBLIC.pdf | 6. Lessons 6.1 The design of DPO programs during times of crisis usually involves a dilemma between providing predictable budget support to the client country, to help preserve stability, and deepening or expanding the reform agenda. Meeting the need of budget support entails a risk of undermining the quality of the reform program supported by the World Bank or the ability of the program to go beyond reforms that would in any case have been implemented by the authorities or supported by other development partners. In Georgia, the World Bank made the choice of providing predictable budget support mostly by extending and deepening the reforms supported by the precrisis operations (PRSOs), limiting the inclusion of new reform areas in the program. With a few exceptions, the content of the DPO series was broadly adequate to achieve the program objectives. The comprehensiveness of the World Bank's previous engagement on the reform agenda through the PRSO series, the World Bank's extensive analytical work, the government's commitment to the reform agenda and crisis mitigation program, and technical assistance (by the World Bank and other donors) to build capacity in key areas of the reform program were all factors that contributed to the positive outcome. 6.2 In the absence of unemployment insurance or other active labor market programs, scaling up Georgia's TSA program was the only option available to mitigate the shortterm impact of the crisis. As the TSA program was well designed and targeted, the World Bank's support was fully justified and helped extend protection to the vulnerable during the crisis. However, cash transfer programs, such as the TSA, are mainly geared toward the chronically poor, whereas many of those affected by crises are households falling into temporary poverty. Also, these cash transfer programs often lack the institutional flexibility in targeting and management information systems to quickly absorb households that may have poverty characteristics different from the chronically poor, which the programs conventionally target. Moreover, they do not include help for workers to return to productive employment. To improve country preparedness to mitigate the social impact of crises, program complementarity, adaptability, and servicelevel efficiency play an important role. The World Bank could advocate complementary social protection schemes\. formal sector contributory schemes; safety nets, including cash transfers relatively well targeted to the poor; and complementary categorical benefits. Developing relevant knowledge and data on groups that are most affected by crises is of key importance. The introduction of unemployment insurance would have merited support by the 2009â€“11 DPO program, especially to help address the possible employment impact of deeper trade integration entailed by the DCFTA with the European Union. 6.3 In a fiscally constrained environment, a move to UHC may not necessarily bring an improvement in the financial protection of the poor. In Georgia, some improvements in health coverage of the poor achieved under the MIP reforms supported by the DPO series were sustained under the UHC program, and access to inpatient services was further enhanced. However, despite a slight decline in out-of-pocket health spending, there was no decline in the share of households that experience impoverishing effects of out-of-pocket expenditures. Moreover, the structure of the current UHC system and incentives embedded in it are a major driver of costs and fiscal overruns that limit the authorities' fiscal space to improve the coverage of the most vulnerable. As shown by Georgia's move to UHC, it is strongly advisable that such transitions be well prepared, with good checks and balances and quality assurance mechanisms in place that help contain the potentially high cost of UHC systems. The World Bank could play a more proactive role in advising governments on the best way to prepare such transitions. 6.4 The World Bank can play a supportive role in helping to focus government's efforts even in policy areas where other development partners mainly drive country reforms. This was the case in Georgia with the trade-related reforms required for the DCFTA with the European Union. These would have been very likely implemented even in their absence as prior actions in the DPO series, as Georgia was keen to fulfill the requirements for starting the DCFTA negotiations with the European Union. However, including these reforms in the DPO series helped focus the government's efforts on reforms important for strengthening export potential over the medium term while, given capacity limitations, this focused effort helped avoid spreading resources thin. The World Bank could have added more value by advising the government on how to prioritize regulatory convergence with the European Union directives, based on the World Bank's prior experience with Eastern European countries during their accession negotiations with the European Union.
P122204 | Second Secondary and Local Roads Project (SLRP II) | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/372101582209293958/text/Georgia-Second-Secondary-and-Local-Roads-Project.txt | http://documents.worldbank.org/curated/en/372101582209293958/pdf/Georgia-Second-Secondary-and-Local-Roads-Project.pdf | The following lessons have mostly been derived and summarized from the ICR, with minor additions of the IEGevaluator:Introducingnew contracting methodsrequires the adaption of the World Banks standardcontract modal to the local context. In addition,flexibility in adjusting and improving the contract scope on a continuousbasis is needed.It also requires more time for bidding and implementation than conventional contracts, withwhich the RDand the construction industry are familiar. The implementation experience of the first OPRC inGeorgiademonstrated the need for flexibility and theability to adjustand improve thepilot at any stage ofits implementation. Although one of the objectives of the pilot OPRCwas to introduce a shift in the risk allocation betweenthe government and the contractor, the shift moved too much risk to the contractor and the risk allocation hadtoberevised after the failure of the first bidding process. The redesign of the contract scope and the revision of the biddingdocuments resulted ina successful second bid, butdelayed the project. In addition, even after thissecond attempt,the maintenance performance indicators needed to be refined after contract award because some of themwere irrelevant ordifficult to measure. Overall, this demonstrates the need to adapt the OPRC model in the World Banks standard biddingdocuments to the local context and circumstances, and to allocateadequate time for bidding and contractmodifications.The implementation of an OPRC pilot requires specialized technical support and training toavoid delays. To implement an OPRC for the first time in a country is technically complex and itintroducesnewconcepts to the sector. In this case, as already mentioned, the first attempt to procure the OPRC was unsuccessful. Although theRDbenefited from consultancy services at the design and supervision stages and the advice of the Bank task team, they mighthave further benefited from havinghighly specialized third party technical support available at key stages of the pilot. Theconsultant could also have providedtargeted training for key RD staff.Strong ownership in the RD andefforts by the Bank team to recreate this ownership after management changes are vital to introduce OPRCs. The experienceof the project highlights strongownership of the RD to introduce an OPRC pilot is a critical factor in itssuccessfulimplementation. It also demonstrated that there is a necessity for the Bank task team to proactivelywork with the clientduring managementtransitions. In this case, shortly after the start of the OPRC, changes in the RD management and at higherlevels in thegovernmentrequired substantial time for the new leadership to better understand and appreciate thebenefits ofthe pilot. This learning process stalled the implementation of the OPRC for several months. Itonly resumedwhenthe new RD management showed ownershipfollowingthe Bank teams efforts.Specialattention to the construction industry and a careful market analysis are necessary when preparing bidding documents andcostestimates for new road works contracting methods. In this case, the OPRC bidding process was launched withinsufficientattention to the capacity of the local construction industry and a careful market analysis. This led the biddingprocess to fail because the lowest bid was three times the cost estimate. The high prices were due to shortcomings in the costestimates and insufficient familiarity of the bidders with the new contract type.A careful market analysis prior topiloting the OPRC would have been useful. This analysis should have considered theallocation of risks, which needed tobecarefully described in the bidding documents and adequately priced in the cost estimates. Theanalysis could havebeenused to guide the procurementstrategy and improve the risk allocation in the bidding documents. An early and moreintensive dialoguewith potential bidders could have helped them understand the new contract type and pricetheir bidscorrectly.
P122217 | Burundi - Emergency Energy Project from IDA CRW | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2014 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/766421468185967502/text/ICRR14877-P122217-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/766421468185967502/pdf/ICRR14877-P122217-Box394823B-PUBLIC.pdf | IEG endorses the three lessons proposed in the ICR, and suggests a fourth one: In emergency operations, an experienced Bank team is required to strike a delicate balance between speed, implementation risk and project quality: Key features of an emergency project are (i) speedy preparation in order to address urgent needs on the ground (ii) weak client technical and institutional capacity, and (iii) uncertainty and changing conditions of implementation. The best way to minimize risks on the project efficacy is to put together an experienced team, which is conversant with Bank operations, and has some experience in implementing projects in emergency situations. Implementation challenges should be handled by adhering to preparation and procurement procedures tested in the context of the country or in similar situations. Tendering procedures in emergency operations should balance the need for speed and the management of procurement risk: For emergency operations, the procurement strategy should not be designed based on speeding project preparation and avoiding procurement complications, but in consideration of shortening the time during project appraisal and implementation, even if it requires exceptional procurement procedures such as sole sourcing or non-traditional procurement procedure.Particularly for emergency operations in fragile countries, strong technical support would need to be put in place timely to mitigate design and implementation risks: Recruiting the right technical people that will design and implement the key components is of paramount importance. Difficulties in this project arose from entrusting the design of the civil engineering of the thermal plant Regideso 's staff , and in recruiting the Ownerâ€™s Engineer without international competition. Another lesson identified by IEG is that in order to be fully effective in emergency situations, Bank teams should make efforts to distance themselves from the traditional mindset of normal situation: The objective and the outcomes of this project are not different from those of a normal project, and reflect the mindset of staff operating in a normal environment. This Bank team's attitude has also been observed in other fragile environments.
P122219 | Integrated Land Administration System Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR draws the following two main lessons from the experience of implementing this project.1. The projecttimeline and instruments needs to be carefully assessed in land administration projects. Banks experience with landadministration projects is that such projects take a long period of time to ensure successful outcomes. The reforms implementedunder this project took about twelve years. The lesson is that the Bank can take advantage of Investment Project Financing andAdditional Finance (AF) tools for projects supporting sectors that take inherently long periods of time to ensure outcomes, andthat task teams working on land administration projects may also wish to consider financing tools such as the use Multi-phaseProgrammatic Approaches for land administration projects.2.Functional integration andinterinstitutional cooperation can raise the potential for success in land administration projects. When this project wasunder preparation, Croatia maintained land registry and cadaster under separate entities. For many years, conventional wisdom hasbeen to integrate land registry and cadaster agencies in a single government entity for promoting effectiveness. This projectdemonstrated how functional integration of agencies can occur through harmonizing operational procedures. The development of theJoint Information System and its improvements in this project were crucial to the cooperation between the Ministry of Justice andPublic Administration (MoJPD) and the State Geodetic Administration (SGA). The lesson is that functional integration can be aviable alternative to consolidating land records under a single agency for other countries, particularly for those countries wherethe political economy is not conducive for discussions about institutional reforms.
P122221 | Economic Recovery Development Policy Loan | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/520741475102116706/text/ICRR-Disclosable-P122221-09-28-2016-1475102107542.txt | http://documents.worldbank.org/curated/en/520741475102116706/pdf/ICRR-Disclosable-P122221-09-28-2016-1475102107542.pdf | The ICR offers two valid lessons (adapted and summarized below).1) There is value in working within aprogrammatic series. This provides a useful frame of reference for maintaining the policy dialogue between the Government, the Bankand other key development partners, while being flexible in responding to changes in context as planned risks materialize and newones emerge.2) Designing a proper results framework requires that: (i) the PDO be realistic and clearlylinked to the reforms supported by the program; (ii) the scope and ambition of the reforms agreed under the program be commensuratewith the objectives, and that (iii) it is better to use outcome indicators (e.g. expenditures in constant prices) that areindependent or at least less dependent on GDP growth projections in a highly uncertain external and domestic crisisenvironment.
P122222 | Development Policy Loan 3 (DPL 3) | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2013 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/150451474555312380/text/000020051-20140625223916.txt | http://documents.worldbank.org/curated/en/150451474555312380/pdf/000020051-20140625223916.pdf | There are three main lessons that can be drawn from the experience of this DPL series:The Bankâ€™s ability to coordinate the design and supervision of its interventions with other key financiers, and to keep a constant dialogue with legislators and other stakeholders is essential to maximize impact and ensure sustainability of reforms, particularly if the latter are long overdue. Dialogue with the opposition is particularly crucial in this respect.The Bankâ€™s ability to assess progress in an independent fashion and demand compliance with agreed policy changes is the foundation of its credibility, particularly in front of the Borrowerâ€™s public opinion. This ability requires a solid analytical capacity, excellent knowledge of the local political economy, ability to withstand pressure to disburse, and willingness to discuss issues with and outside government.Political commitment to reform is crucial and needs to be broad based. The overall reform agenda under extremely difficult circumstances needs to have some degree of support from the opposition, as governments are often short lived during such periods. The Bank can help through dialogue, but without some common ground between government and opposition the risk of policy reversals may be too high.
P122226 | Competitiveness Developmenet Policy Operation | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/942391474943100049/text/000012394-20150108124221.txt | http://documents.worldbank.org/curated/en/942391474943100049/pdf/000012394-20150108124221.pdf | This evaluation draws the following three lessons from the experience of the DPO :First, a single-tranche DPO is likely to be an inadequate instrument to achieve intermediate and final development objectives that require implementation of the reforms and perhaps some time to act on those objectives. The Bank acknowledged this lesson in its initial design of the DPO as a programmatic operation and the recently approved DPO that sought more achievable objectives. Second, in a single-tranche DPO, intermediate indicators that simply describe the measures adopted do not do well as development outcome indicators. For example, the outcome from the elimination of a non-tariff barrier needs to be captured by its effect on an indicator set that measures overall export incentives or import restrictions.Third, M&E that simply focuses on measuring indicators of the results matrix is insufficient. It needs to go beyond this to assess impact on the development outcomes it seeks. This is particularly relevant in situations where the Bank moves forward with further operations in the same areas.
P122229 | Public Service Reform and Rejuvenation Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099011724210510662/text/P12222910bfdc40d41a1b91404e5b380feb.txt | http://documents.worldbank.org/curated/en/099011724210510662/pdf/P12222910bfdc40d41a1b91404e5b380feb.pdf | The ICR (p. 27) presents several insightful lessons, some of which are summarized and expanded upon here:It isrisky to burden a project that is struggling to make progress with new components. The ICR cautions that carefulconsideration is needed before adding components and complexity to a project in a difficult country, sector and projectenvironment. The project had not made progress in its first 18 months. However, instead of restructuring it by reducingcomplexity, the scope was expanded, and additional components and activities were added.This was largely done out ofexpedience, as another Bank project was closing, and unfinished activities were merged with this project. The ICR concludes thatthe implications of the AF in this project were not fully assessed, arguing that it would have been better to drop orreallocate some activities and narrow the scope.Multiple, weakly justified changes to a project can weaken itsfocus and ability to achieve its objectives. The ICR highlights the frequent changes through what it refers to asad-hoc additions and quick deletions of components and activities. It found there was no compellingexplanationdriving the changes. The changes were especially questionable given that they were not linked to theoriginal PDO or tiedto an expansion ofthe PDO (with the exception of adding provincial administrations to therejuvenation dimension).When governance and political economy issues present high risks, as with this project,more rather than less attention and resources should be given to supervision and monitoring. Political economy andgovernance risks that are not proactively addressed through rigorous mitigation measures can derail a project from achieving itsoutcomes. The Bank was clearly aware of these risks at appraisal, incorporatingmultiple mitigation and monitoring activities.However, these oversight and monitoring activities were implemented weakly or not at all. Although the Bank recognized seriouspolitical economy and governance issues at appraisalindeed, addressing weak governance was a rationale for strengthening thecivil serviceonly one ISR was conducted during the first two years of implementation and only one during the final twoyears. An MTR was conducted six years after effectiveness. It is almost no surprise that the Bank found the government had madeineligible payments worth close to US$5 million, leading to an 18-month suspension of project activities.If gendertargets are to be met, they need to be supported with gender-specific activities. The projects sub-indicatorthatset a target for 25 percent of trained YP recruits to be women was laudable. However, the projects failure to reachthe target (it hit 18 percent) was linked to the lack of specific activities to help reach the target. A belated attempt to rectifythis (180 out of the last group of 220 potential YP recruits were women) was stymied by COVID-19,and the cohort was nottrained or recruited. If gender targets are taken seriously, serious efforts need to be made at the start rather thanat theend of a project.Excessive project preparation time should be considered a warning sign that the targeted reformsare high risk. The project was 3.5 years under preparation, in part related to a pause in activity related to elections inNovember 2022, but also due to persistent political economy issues. Even so, the lengthy preparation proved to beinadequatemany activities that are normally addressed during project preparation were left to the implementation stage. And,as per the ICR, the project team was still working on preparatory planning and conceptualization over a year and a half aftereffectiveness. All this contributed to the project getting off to an extremely slow start with minimal progress towardachievement of the indicators as of February 2016 (ICR p. 25) which could have been flagged as an early indicator (orwarning) that it would be a troubled endeavor. The Bank could introduce an accountability mechanism for assessing reasons behindproject preparation delays, in cases where preparation has lasted for more than a certain period. This might offer aninstitutionally acceptable way for the Bank to cut its losses and accept sunk costs, without the pressure to move forward towardimplementation of highly risky projects, such as this one.
P122233 | Social Assistance Modernization Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2012 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR (p. 31-33) included several lessons learned, which were adapted by IEG: Employing a dualinvestment and results-oriented instrument for funding mid-term social assistance reform proved suitable, as it offered theflexibility to prolong the project in the face of unforeseen crises. This project supported the social assistance reformagenda for over 10 years, including through elections, the 2019 earthquake and the COVID-19 pandemic. These were times whenadvancing structural reform and ensuring political support was challenging. However, the investment instrument and theresults-based approach allowed to ensure continuity and provide incentives to move the reform agendaforward. Allowing for sufficient flexibility in project design and implementation might positively impact projectimplementation during times of crisis. In this project, during the COVID-19 pandemic the benefit was vertically deepenedand horizontally extended by including households registered in the NE registry, allowing for more people to benefit duringchallenging economic times. Establishing two-way communication channels between the Government and recipients iscrucial for the successful implementation of reforms and for conveying to beneficiaries the measures available to support themthroughout the reform process. In this regard, the project supported widespread presentations and campaigns conductednationwide, with the participation of the minister and ministry leadership, to explain to the public the reform measures taken forboth NE and DA programs. Additionally, the project facilitated the implementation of a Grievance Redress System (GRS) to collectfeedback from beneficiaries and refine reforms based on this input.
P122235 | AF Irrigation Restoration and Development Project | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2025 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099656304262229940/text/P12223504958270e509e3b084ed846d6c69.txt | http://documents.worldbank.org/curated/en/099656304262229940/pdf/P12223504958270e509e3b084ed846d6c69.pdf | The ICR included three lessons. The following threeare emphasized with some adaptation of language:1. Toachieve the desired impacts on agricultural productivity, irrigation interventions need to implemented simultaneously withacomplementary program of agricultural extension and a package of selected intensification measures, and improving marketlinkagesthat could further boost productivity and improve livelihoods. The project experience emphasized the needfora cohesive water in agriculture approach where modernization (rehabilitation) of irrigation canals isaccompanied by a complementary program of agricultural extension and a package of selected intensification measures could furtherboost productivity and improve livelihoods. Also, building high value market linkages would allow farmers to move beyondsubsistence farming. This requires operationalizing the institutional frameworks developed under the IRDP for improvedco-ordination between public institutions / government departments.2. The full utilization of hydrometinvestments requiresconcurrent investments in analytical products. The project experience demonstrated that withoutsystems, frameworks, and mechanisms for data sharing, adoption and/or development of analytical products, using data generated fromthe hydromet infrastructure for improving water resources management remains constrained.After 20 years of investing inbuilding, operating, and maintaining hydromet infrastructure, this still remains a major gap. While infrastructure provision haslaid the foundation for a robust water resources monitoring and advisory platform, its utility will however be defined byanalytical products developed at three levels;national, regional and local levels. The nationalfor snow melt andbroader climate impact analysis, the regional to cater to specific use based analytical products such as including acquiring andprocessing well-established and operational observational datasets on previous season snowpack,and at the local level fordriving local decision-making such assimplified updates on water availability and weather disturbances, andevapo-transpiration(ET) information, among others.3. Adapting to deteriorating security conditions requiresan agile, constructive, and multi-pronged approach for procurement, implementation, and monitoring. The project adoptedseveral strategies including smaller contracts executed by contractors, building trust and social cohesion with local communities,strengthening capacity of regional staff, and using technology-based ME such as remote sensing analysis. While localcontractor capacity was weak, employing local actors to deliver infrastructure projects in a smaller and more manageable mannerallowed for continued engagement during active conflict. It also helped bolster the social contract between local communities andproject authorities.
P122247 | Eighth Poverty Reduction Support Financing | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/363921473922352232/text/ICRR14924-P122247-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/363921473922352232/pdf/ICRR14924-P122247-Box396299B-PUBLIC.pdf | The following lessons are taken from the ICR (p. 35) with some adaptation of language:Â· The Governmentâ€™s commitment and ownership were the critical drivers to advance the reforms. This was especially evident after the shelving of follow-up operations as the Government managed to sustain the reform pace despite the fact that associated budget support was not available any longer.Â· Success of the Bankâ€™s support for a multi-sector reform program depends upon the quality of policy dialogue at the sectoral level, the extent to which the substantive agreements with sectoral counterparts in the government are reflected in the design of reform program at the central level, and the presence of respective sector staff in the country. IEG provides the following additional lesson: Â· Disruption in the implementation of the third PRSF series, which was supposed to support three operations, highlights the risk of excessive reliance on budget support in country assistance programs in countries that are exposed to regional political instability. In such circumstances, there is a high risk of external shock associated with a sudden change in donor sentiments that results in major cuts in budget support, aid shortfalls, and economic growth slowdown.
P122269 | BD Rural Water Supply and Sanitation Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/648871534390889841/text/Bangladesh-BD-Rural-Water-Supply-Project.txt | http://documents.worldbank.org/curated/en/648871534390889841/pdf/Bangladesh-BD-Rural-Water-Supply-Project.pdf | The ICR provided important lessons, the most relevant ones are as follows (with someediting): Large scale piped water scheme investments requireconsiderable upfront preparation in terms of market analysisand design to enable timely implementation. The project experience showed that approaches that engage private sectoractors in the delivery and management of water and sanitation services would benefit from detailed market analysis surveys prior tocommencing the design of business models and procurement processes, so that the availability and ability of private sponsors can beassessed more effectively. In addition, the technical designs of piped water schemes need to involve various actors, includingtechnical experts, local government and targeted communities, so as to ensure the designs match the needs (ICR, paragraph104). Private sector models have proven effective in mobilizing additional financial resources for thewater supply and sanitation (WSS) sectors and supplementing weak service delivery capacity, however the enabling environment foreffective private sector engagement needs to be developed. In this project the private sector played a critical rolethrough providing complementary financing to service provision, as well as supplementing local government capacity. As the ICRindicatedthe engagement of private sector enabled local government to play more of a facilitating and oversight role in theWSS sector. At the same time Government policies in Bangladesh led to reduced barriers to entry for the private sector andhence provided greater incentives for the private sector to engage in the WSS sector (paragraph 108). In addition, the capacity ofgovernment, both centrally and at the local level, needs be strengthened to providethese arms of governmentwith theskills and systems to more effectively carry out their leadership and regulatory facilitation roles.To ensure resources and services reach poor and vulnerable groups,effective mechanisms and indicators are needed.The ICR noted (paragraph 109) that despite the projects focus ontargeting the poorest households, politicalpressure led to in some cases to elite capture of sanitation facilities although it is noted that the Bankproject teaminformed IEG that not all identified poor households were interested to purchase latrines at subsidized rate, therefore the projectallowed middle income groups to receive latrines.Nevertheless (as mentioned in the ICR), a drawback of the businessmodel used in this project, was thatit focused on sponsors maximizing revenue and profit. Hence businesses reportedly focusedon customers who were able to afford services and pay tariffs. While there were some examples of pro-poor action, formal incentiveswere not built into the model to ensure poorer households were served and supportedwhen they were not able to affordservices. Since, the ME framework did not include disaggregated data on the poor and vulnerable, this issue could not beadequately tracked and addressed in thisproject.
P122319 | ZhangHu Railway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2020 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099045011302112814/text/China000CN0Zhangjiakou0Hohhot0Railway.txt | http://documents.worldbank.org/curated/en/099045011302112814/pdf/China000CN0Zhangjiakou0Hohhot0Railway.pdf | The following lessons have mostly been derived and summarized from the ICR, with minor additions by IEG after discussions withthe Bank task team:Limited Bank financing can provide project stakeholders with confidence thateconomic,fiduciary, and safeguard aspects of large infrastructure projects are adequately carried out.This andthe other fourhigh-speed rail projects financed by the Bank in China followed the World Banks policies and proceduresin financial management, procurement, environmental and social safeguard despite the Banks small financing contribution,i.e.two to five percent of project costs. Capacity assessments, trainings, establishmentof proper managementarrangements, and preparation of adequate financial management, procurement, environmental, and social documents were carried outand prepared. In addition, the Bank task team reviewed the Borrowers economic assessment and carried out its own assessment.All this gave project stakeholders confidence that these aspects of project implementationwere properly taken care of.For a railway or any other large infrastructure to be successful (and cost-effective)long-termplanning,strong government commitment, and an experienced implementation agency are essential. TheChinese government played a key role in putting a comprehensive system in place to enable the impressive creation, galvanization,and implementation of the railway program development. According to the Bank task team, the Chinese government made a long-termcommitment andinvested in everything necessary, such as the creation of engineering capacity and rolling stock development.This enabled the contractors to makelong-termcommitments, hence invest in human capital and equipment, and broughtcosts down. The China Railways Corporation took on the mainresponsibility for planning, financing, and implementingindividual projects. It created the infrastructuredelivery mechanisms,such as the joint venture companies with localgovernments. It was responsible for collaboration and coordination with local governments, and for the delivery of Chinasnational railway services. This, combined with legal and institutional powers, strong technical capacity, access to the operatingcash flows of the railways and the ability to borrow, gave China Railways the agility to plan and deliver projects very quickly.Cooperation between national and local authorities, aunified control over the project by China Railways, as well as theoverall commitment of the government and the implementing agencies, enabled the project to be a technical and environmentalsuccess.Although agglomeration benefits are important, they can only be partiallyassessed by projectend. The quantification of agglomeration benefits is important in evaluating the benefits of passenger railway projects.At appraisal, the agglomeration benefit model developed for the project captured the benefits to companies from direct cost andtime savings as the projects connectivity enhancements enablecompanies to locate or expand in the region. Althoughagglomeration benefits are recognized at a theoretical level in China, there areonly few quantitative studies on the topic.The agglomeration benefit model provided a comprehensive analysis and indicated meaningful benefits of the projectsagglomeration impacts. However, at project close, the Bank could not confirm the agglomeration benefits in the first years ofoperation because the planned onboard survey could not be carried out due to Covid-19 disruptions. These onboard surveys would atleast have provided the project with qualitative data on early impacts.Given that it usually takes about 10 years foragglomeration benefits to be fully realized, an assessment should be carried out in later years to evaluate the agglomerationbenefits. This could be done by IEG through project performance assessment reports.Good project preparationis an element for the success of large and technically complex infrastructure investment projects. In this project, anearly and good preliminary project design was the basis of the feasibility report and initial cost estimates. The subsequentdetailed design did not deviate significantly from the preliminary design. In addition, applicable standards and technicalspecifications for railway construction and material inputs were formulated and adhered to strictly. The project had an effectivequality control system both for contractors andproject management, and as a result no significant problems occurred duringtesting and commissioning of the railway line. All construction and supply activities were identified, and their inter-dependencewas established. Meticulous planning and control of critical activities prevented delays during construction. Red flags on laggingactivities were acted on quickly. Qualifications and experience of contractors were defined carefully, so that only those withcredible past performance and with adequate resources were able to bid for contracts. An efficient procurement team ensured on-timeavailability of materials.Timely land acquisition was another critical factor since for a linear project any break in landavailability is very disruptive. All this eventually ensured the success of the project.
P122320 | Ulaanbaatar Clean Air Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2012 | 2024 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111324151526648/text/P122320-a850eaad-58dd-4cc2-be10-b8eb68c45aad.txt | https://documents.worldbank.org/curated/en/099111324151526648/pdf/P122320-a850eaad-58dd-4cc2-be10-b8eb68c45aad.pdf | The following lessons were derived from the ICR (ICR, pages 30-31):1. Government commitment and consistentsupport arecritical when projects sustainability depends on policy and regulatory environment. In thereviewed Project, the stove program encountered challenges, as households found the stoves too costly without subsidization(including through tariffs). Separately, in 2019, the Government prohibited the usage of raw coal in UB and introduced refined coalbriquettes, which were not compatible with the clean stoves developed by the Project, and which had high caloric value, thusshortening the lifespan of the stoves. The lack of ongoing consistent policy and regulatory support for the program created risksto the sustainability of the clean stove component of the Project and therefore to the Projects long-term objective of PMemissions reduction.2. When projects introduce new and innovative technologies, a thorough market analysis, inaddition to technical analysis, during project preparation is critical for a successful project implementation. Theintroduction of the ETS heaters under Component D suffered due to a lack of adequate a-priori market analysis: the Project aimed toprovide access to the heater for 5000 households, but this target had to be reduced to 340. This happened because the followingdiscoveries were made during implementation: (i) the network system had to be upgraded to accommodate ETS heaters; and (ii) 89percent of households meeting the technical criteria could not afford ETS heaters. If a proper market analysis were conducted priorto implementation, these factors could have been incorporated into Project design.3. Setting insufficientlyambitious RF targets can reducethe usefulness of the ME system. The reviewed Project significantly exceededseveral RF targets, signaling that they were set too low. Since the Project underwent several restructurings, there was a missedopportunity to increase these targets. The overachievement across multiple indicators suggests a need for more rigorous andadequate target setting in future projects to pitch them at the correct level.
P122321 | JiTuHun Railway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/165821504732286499/text/ICRR-Disclosable-P122321-09-06-2017-1504732276433.txt | http://documents.worldbank.org/curated/en/165821504732286499/pdf/ICRR-Disclosable-P122321-09-06-2017-1504732276433.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptationoflanguage.(1) A unified and autonomous management structure canfacilitate the creation andimplementation of a railway program. In the case of this project, the China Railway Corporation was solely responsible forplanning, financing and implementation of individual projects and delivery mechanisms. This combined with legal and institutionalpower contributed to unified control over the problem and enabled timely completion of activities, despite the relatively marginalfinancial contribution from the Bank.(2). Although agglomeration benefits have been recognized in theory withrailway projects, there are few quantitative data to assess the results. This may be due to the longer time span requiredfor reaping the benefits. An ex-post analysis after five or ten years after the railways have been in operation could be undertakento assess the quantitative benefits.(3) A multi-project World Bank engagement can help in engaging in abroader policy dialogue aimed at institutional change. Although Bank financial contribution to this project was limited,it enabled the Bank to support aunified program of railway projects and enabled the Bank to provide holistic support throughpolicy dialogue with the Ministry of Railways and China Railway Corporation.
P122326 | Togo - Private Sector Development Support Project | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/469521493472870133/text/ICRR-Disclosable-P122326-04-29-2017-1493472857052.txt | http://documents.worldbank.org/curated/en/469521493472870133/pdf/ICRR-Disclosable-P122326-04-29-2017-1493472857052.pdf | The ICR (p. 18) notes several lessons. The outcomes highlight the need for simplicity and flexibility withrespect to design in an environment such as that which existed in Togo. Almost every aspect of the design of this project waseither unsuited for the situation that existed, or overly complex. Several parts of the project were not ready when it commencedand key contractors necessary for implementation had not been identified. Not having all parts of the implementation unitin place at an early stage hampered the effectiveness of the project. This is an important feature of successfulimplementation. The cumbersome and lengthy restructuring process resulted in a failure to salvage the project, eventhough the mid-term review had identified serious problems. Restructuring needs to be pro-active. Procurement processesneed to be addressed prior to effectiveness. The very short time between the approval of restructuring andthe closing of the project, which raises questions as to the efficacy of the redesign and why it was not extended to meet more ofthe original objectives.
P122329 | South Africa - Eskom Renewables Support Project | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2012 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099102924151097391/text/P122329-9d5db766-fb18-49b2-9907-698d75452f46.txt | https://documents.worldbank.org/curated/en/099102924151097391/pdf/P122329-9d5db766-fb18-49b2-9907-698d75452f46.pdf | The following lessons were derived from the ICR (ICR, page 23):1. Projects based on innovative technologies,despite being associated with higher risks, can produce significant development outcomes and incentivize a scale-up and knowledgesharing, provided that they are properly designed with respect to ambition and cost. The CSP component of the reviewedProject was designed as a large and costly pilot, which increased its risks and contributed to the failure of the bidding process.An innovative BESS program, while also large, was based on a phased approach and although considerably delayed, had a widecatalytic impact in South Africa and globally. The first phase contributed to a large investment in renewable energy, including inBESS capacity, by the private sector, and encouraged other countries to invest in solar battery storage. It also supportedEskoms acquisition and sharing of related knowledge and experience.2. When projects introduce new andinnovative technologies, it is important to focus due diligence not only on the feasibility of the technology, but also on theoptions for implementation structures, including private sector involvement when applicable. In the reviewed Project, ifsuch due diligence was conducted during the preparation stage, it could have suggested alternatives to a public sector projectdesign and involved private sector, since it was already showing interest in CSP. This could have helped to avoid the wasteof resources used to prepare the Eskoms CSP, which ultimately failed.3. For projects implemented in highlyregulated sectors, careful advance planning and consultations, as well as a clear agreement with the Borrower and/or governmentagencies on decision timelines, are critical. This can help ensure that the required regulatory licenses,authorizations, permits, and consents are secured on time. Implementation of the reviewed Project was plagued by delays ingrantingapproval and regulatory licenses for the BESS component.
P122370 | Emergency Support for Social Services | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2011 | 2013 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/948621474487871782/text/000020051-20140626111832.txt | http://documents.worldbank.org/curated/en/948621474487871782/pdf/000020051-20140626111832.pdf | The following lesson is suggested by IEG, drawing on the findings and analysis of the ICR:During preparation, an assessment of the capacity of a countryâ€™s reporting systems is likely to result in the choice of monitoring indicators and reporting requirements that the systems are capable of responding to. On the other hand, the choice of key indicators and reporting requirements that are beyond the capacity of systems to accommodate can result in capacity building during implementation, both of relevant staff and of the systems themselves. In the case of this project, the GoG strengthened its capacity to generate more reliable data on the number and wages of service staff, improved its systems in this light, and enhanced coordination between line ministries and the MoF through the process.
P122383 | Landscape Approach to Wildlife Conservation in Northeast China | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/099345001132214504/text/China000CN0Lan0h0to0Wildlife0Conser.txt | http://documents.worldbank.org/curated/en/099345001132214504/pdf/China000CN0Lan0h0to0Wildlife0Conser.pdf | The ICR provided five lessons. Some of them are summarized below because they may provide lessons of interests for otherbiodiversity projects.Collaborative communication between the Bank and stakeholders can ensure constructivecommitment and re-start stalled project implementation. In early years, this projects limited grant financing andlengthy preparation process made it challenging to attract the attention and maintain commitment of the participating entities andhigher-level authorities. According to the ICR, despite the initial communication challenges and delays, the World Bank teamcultivated a closer communication with the Government and later established an effective working relationship based on trust andrespect (para 95). At project closing, the project successfully completed the US$17.82 million project which also led to theGovernment establishing the new National Park of Northeast Tiger and Leopard with a total area of 14,600 km2, which was almostfourfold of the original project area of 3,697 km2.The participation of a high-level independent researchinstitution can lend credibility to a projects monitoring and evaluation. In this project, the Feline ResearchCenter in China, which was an internationally recognized center for technology and information exchange in feline conservationresearch, supported the design and implementation of the integrated monitoring program. It generated monitoring data andevidence-based analysis that were used to monitor tiger and other key wildlife populations and their prey and habitat, informedresource allocation and decision-making, and facilitated international cooperation. The Center contributed to improved conservationof habitat protection and recovery of biodiversity through using the monitoring data to guide SMART patrol and field surveys, whichplayed a critical role in increasing effectiveness of habitat protection. Moreover, it provided important inputs and capacitybuilding for the national monitoring systems which formed the basis for future scientific research.
P122391 | Rio de Janeiro Metropolitan Urban and Housing Development | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2011 | 2013 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/416321475112866061/text/000180307-20141202140444.txt | http://documents.worldbank.org/curated/en/416321475112866061/pdf/000180307-20141202140444.pdf | from the ICR:Natural disaster events can be catalysts for positive change. Although not dealing exclusively with natural disasters, tragic flooding and landslide events in the highlands north of Rio de Janeiro in January 2011, two months before the approval of this project, kept attention focused upon actions that reduced disaster risk as well as advancing their respective sectors.While commitment within individual agencies is a necessary condition for successful institutional development, so too is political leadership from top government authorities. Strong leadership from top RJ State authorities would have been required to effectively align priorities within the government with the goals set for the operation. However, other political economy determinants, such as national elections, at times took priority, compromising the cohesive delivery of the actions supported under the operation.Ensuring that tranche release conditions that have been met are not reversed later poses a difficult challenge for a DPL. In the case of this operation, a decree authorizing the competitive recruitment of staff for SEASDH was accepted as evidence of progress toward restructuring the agency. The later annulment of the recruitment process (on technical grounds) after most hiring had been completed could not have been anticipated..Engaging multiple agencies with uneven institutional capacity presents a clear challenge. While the nature of some operations, such as regional development interventions, require engaging with multiple government agencies, the implementation experience of this operation illustrates the difficulties of working with agencies that present uneven levels of institutional maturity, technical competency, and leadership. Metropolitan development operations require working with municipal, as well as federal entities and programs, additional layers that must be factored into project design. adding further complexity. Key policy actions under this DPL were linked to federal programs, ranging from federal housing programs to the favela pacification programs. This articulation with federal programs had both positive and negative implications. On the positive side, it helped created positive synergies between this DPL and federal programs, including building a critical mass of financial incentives in support of a consistent set of policy initiatives, which, in turn, prevented the RJ State from spreading even further its already limited institutional capacity. On the negative side, it resulted in some policy outcomes being outside the RJ State government's direct sphere of influence, limiting the operationâ€™s overall effectiveness. Working with municipalities in such type of operation does not mean that conditions linked to municipal performance beyond the stateâ€™s span of control should be included in the project design.from IEG:To be relevant, the design of a DPL, especially through the policy areas and performance indicators that it chooses should be firmly embedded into a explicit results framework. This framework should justify the linkages between progress measured by the indicators and the achievement of the objectives.A multi-tranche DPL policy design should ensure that the timing and conditions of tranche releases should be calibrated with the achievement of the operation's objectives. Shortly after this DPL's first tranche was released, the second tranche conditions were fully met, but shortly thereafter project performance weakened and the DPL was unable to achieve a Satisfactory outcome. Policy actions chosen for support and/or attention by a DPL should be on the same scale as the intended results of the operation. In this DPL, for instance, an action such as upgrading a single existing housing scheme could not be expected to contribute significantly to the DPL objective of promoting the provision of affordable housing on the scale needed at the level of the RJ metropolitan region.
P122398 | AFCRI-Central African Backbone - APL3 - Republic of Congo | Western and Central Africa | Western and Central Africa |  |  | Digital | Digital Development | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/832921580232701397/text/Africa-Central-African-Backbone-APL3-Congo-Rp.txt | http://documents.worldbank.org/curated/en/832921580232701397/pdf/Africa-Central-African-Backbone-APL3-Congo-Rp.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some modification oflanguage. Legal covenants or disbursement conditions need to beconsidered forcritical elementsof a project. ThePPP structure in this project was identified as a critical element for the effective and efficientoperationalization of the regional network. Through the lifetime of thisproject,there were major issues with matterspertaining to establishing PPP for the regional network.Measures such as inclusion of PPP as a legal covenant or conditionsfor disbursement, couldhave helped in overcoming such challenges.The ICR (paragraph 87) notes that such disbursementconditionshave been incorporated in the ongoing CAB projects in Gabon and the Democratic Republic ofCongo. A careful consideration ofpolitical economy considerations is required atappraisal. This project encountered serious implementation delays due to delays in counterpart funding. The experience ofthis project demonstrated thatfuture projects could benefit from having contingency funds factored in projectdesign. Project implementation can be facilitated through strongstakeholderengagement. This project required a significant amount of sensitization. The recruitment of acommunications specialist in the Project Implementation Unit in this project helped in promoting the project across stakeholdergroups.While stakeholder engagement early in the project was valuable, regular dialogue with the operators could have helpedinidentifying regulatory and policy bottlenecks, and could have provided a better understanding for the failure of the PPPand potential alternatives.
P122402 | West Africa Regional Communications Infrastructure Project - APL-1B | Western and Central Africa | Western and Central Africa |  |  | Digital | Digital Development | IDA | IPF | 2011 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099025008232210106/text/P12240208397000b808c2502e02d305e5b2.txt | http://documents.worldbank.org/curated/en/099025008232210106/pdf/P12240208397000b808c2502e02d305e5b2.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A regional approach to fostering broadband services can help in moving forward the agenda of regionalintegration. This project helped the small coastal countries of The Gambia and Guinea which were circumvented by theprivate submarine cable consortia, in connecting to the ACE submarine cable. Likewise, the project aided landlocked Burkina Faso indeveloping direct and virtual landing point in Ghana. Developing direct and virtual landing points through the region helps todrive an expansion to broadband coverage and a decrease in broadband prices, hence contributing to less heterogeneity in broadbandmarkets across the region.2. Government commitment on PPP and open access principles in itself may notguarantee open access. The lessons from The Gambia and Guinea showed that the PPP model does not guarantee open access andthat regulatory safeguards are required for realizing the intended outcomes. To ensure fair and equitable access, furtherregulatory frameworks needs to be in place, including the appropriate monitoring by the sector regulator of the terms andconditions for accessing the international capacity, to ensure that prices are appropriately set, that there is no collusionbetween the shareholders, and that the terms of access are nondiscriminatory to all players.3. The outcomeindicators may require regular assessment and modification in ICT projects. Compared to other sectors, thetelecommunication market evolve more rapidly, due to the fast pace of development of the underlying technologies. The lesson fromthis project is that targets and values of indicators in such projects need to be regularly assessed and revised against marketdevelopment trends for proper attribution of results.4. Flexible implementation strategies may help in operationsin Fragile, Conflict and Violence (FCV) countries. Lessons from Burkina Faso in this project demonstrated the need foradopting flexible implementation strategies, based on on the ground staff and closely monitoring the securitysituation.
P122414 | Yemen Private Sector Growth and Social Protection DPG | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/241271474503281963/text/000020051-20140625193323.txt | http://documents.worldbank.org/curated/en/241271474503281963/pdf/000020051-20140625193323.pdf | There are three main lessons that can be drawn from the experience of this DPG: A. The Bankâ€™s knowledge of country circumstances should allow it to identify high systemic political risks in advance and adapt project design to it. As political risks are rated by independent specialized agencies, their ratings should allow a corporate wide monitoring of such risk and mitigating measures. B. Simple design is essential in contexts characterized by political instability and weak capacity. C. The Bankâ€™s policy menu for private sector development is still too focused on business creation and access to credit, whose link to a possible supply response is tenuous at best. It is far from proven that a reduction in the number of days needed to register a business could spur growth.
P122419 | Support to Protected Areas Management | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/550521547507018948/text/ICR-Review-P122419-2-13-2019.txt | http://documents.worldbank.org/curated/en/550521547507018948/pdf/ICR-Review-P122419-2-13-2019.pdf | The ICR provided lessons on Government commitment, the income generating scheme, and government payments. They were focused onthe circumstances of this project without broader application.Lessons 2 and 3below arebased on IEGsassessment of lessonsaround the protection ofbiodiversity;lessons1, 4 and 5are (with some editing)based on the ICR.:1. Combining conservation and livelihood support can be aneffective two-pronged approach to protecting biodiversity in national parks.The project provides anexample,consistent withexperience elsewhere, of largely effective implementation in national parksof atwo-pronged approach to biodiversity conservation. In particular, the inclusion of income generating activities took pressure offthe conservation program, enabling a greaterimpact on the protection of biodiversity than conservationalone.2. Environmental and Biodiversity impacts are generallyinter-linked but differences in the objectives for changes inenvironmentand biodiversity call foradditionalindicators of change. This projects objectives were stated as enhancing protection ofbiodiversity, but measured impacts (changes inthe observeddensity of three herbivores) were related more to theenvironment than to diversityof numerous animal and plant species. Environmental changescould be measured asadditional vegetative growth, adding biomass as fodder foranimals such as large herbivoresand reducing soil erosion aswell asother environmental impacts; yetthe recovering vegetationmay belimited inthe variety ofspecies which maynot provide the diversity of food sources for a broader range of fauna than three large herbivores.Measurement of the changes in vegetation to assess improvements inthe conservation of natural resourceswill not provideadequate data to assess the extent to which biodiversityhasbeenprotected.3.. Assessment of changes in biodiversity is notadequate unless a representative cross section of species is monitored.Tracking of changes inbiodiversity was based on three large herbivores as proxies for biodiversity impacts.A broader range of animal and vegetativespecieswould have provided a greater understanding of changes inbiodiversity.4.The Protected AreaManagement Effectiveness Tracking Tool (METT) is an effectivetool for measuring the quality of parkmanagement.Rigorous use of the METT (combining 30 variables, including legal status, demarcation ofthe park, staff training, work with local communities, financial status, accounting, surveillance, development of touristfacilities, regulations, law enforcement, research, and visitor facilities) provided a reliable yardstick for regular monitoring ofprogress in the quality of park management.5. Monitoring biodiversity requiresadequate and timelyfunding.Experience during the project was that funds for expenditures onconservation (implementation of the METT, equipment and extra staff)were constrained, limiting the extent of trackingactivities - at the core of management of parks. Financial planning and expenditure through a dedicated, earmarkedbudgetsimprovethe availability and regularity of funding for critical activities.
P122470 | Seventh Poverty Reduction Support Credit (PRSC7) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2011 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/172141475111853059/text/000020051-20140626111920.txt | http://documents.worldbank.org/curated/en/172141475111853059/pdf/000020051-20140626111920.pdf | The lessons from the ICR are broadly supported by this Review: Clearly specified policy and institutional reforms are central to ensuring that outcome indicators in performance assessment frameworks are linked to concrete actions rather than vague aspirational goals. PRSCs will have the greatest impact when they focus on a road map of prioritized institutional changes and related policy measures. Progress can best be measured with indicators linked to concrete actions, while ensuring that effective monitoring will be achievable within the limits of statistical and M&E capacity.The risk to reforms can be mitigated by addressing potential political economy constraints throughout the reform process. Reforms to public resource management, and strengthening the legal and institutional framework for business development and efficient land use, will inevitably attract the attention of powerful interests. While some controversial reforms will be delayed or blocked by political processes, the risk of this can be mitigated through an inclusive consultative process, supported by careful analysis of under-appreciated benefits that can help to build coalitions of supporters.Reformers may gain better traction by shifting focus in response to changing conditions. Reform priorities can often be usefully adapted to better respond to changing economic and social conditions and international developments. Implementation challenges may also be resolved by switching focus to a different policy area where there is a critical mass of political support and/or implementation capacity, rather than pushing for results that are unattainable within the time frame of the series.Reform success requires that implementation capacity constraints be identified in advance in order to guide the design and provision of technical assistance. Poverty reduction programs tend to be ambitious and complex, requiring capacity at many levels for reform implementation, and appropriate and timely monitoring and evaluation. Meeting these challenges requires an adequately designed and targeted program of technical assistance, in the short run, coupled with sustained capacity-building support over the long run.
P122476 | Public Financial Management Strengthening Technical Assistance Project | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/694651604377722782/text/Senegal-SN-Public-Res-Management-StrengtheningTA.txt | http://documents.worldbank.org/curated/en/694651604377722782/pdf/Senegal-SN-Public-Res-Management-StrengtheningTA.pdf | Care should be exercised in ensuring the practicality of ME indicators. Applying PEFA and DeMPAindicators and targets limited the usefulness of ME indicators in measuring progress and impact of interventions. Suchindicators are multi-dimensional by nature and likely to capture influences that are beyond direct project contributions, giving anunbalanced assessment of achievements. Moreover, their timing may not be well-aligned with the timing of the project, whichwas the case in Senegal. To avoid such issues, ME for PFM Technical Assistance projects may bebetter assessed byindicators that are tailored to project characteristics and timing (targeting specific sector or program areas), which enables moreaccurate assessments.PFM reforms are likely to have a long gestation period and may require sustainedlonger-term support. In this case, the government has requested a follow-on e-governanceprogram-for-results operation. While a Technical Assistance project is convenient in order to establish the legaland regulatory framework for PFM, introduce IT systems and launch necessary training, such support needs to be sustained overtime.An IFMIS can be a useful tool in facilitating reliable, accurate and comprehensive management of thegovernment budget. The project introduced additional financing that made possible the acquisition of a fullyintegrated budget and financial management IT platform. This facilitated interfacing with other core systems to provide theauthorities with the tools to consolidate fiscal information and strengthen internal controls.
P122478 | AFCC2/RI-ACBF Regional Capacity Building Project | Other | Africa |  |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/133631556745444187/text/Africa-ACBF-Regional-Capacity-Building-Project.txt | http://documents.worldbank.org/curated/en/133631556745444187/pdf/Africa-ACBF-Regional-Capacity-Building-Project.pdf | Among the lessons presented in the ICR (pp. 45-46) two are of particular importance (presented here with someadaptation of language): Timely notification and the formulation of an agreed exit strategycan be expected to increase an institutions chances for sustainability after longstanding support is curtailed. Inthis case, discontinuing IDA support to the ACBF in the absence of clear communication and a road map towards independence hasplaced the institutions viability at risk. Avoiding perverse incentives can increase a projectsimpact. In this case, the requirement that ACBF sub-projects be limited to 15 countries provided an incentive to selectprojects where the likelihood of success was high, rather focusing on countries with the greatestneed.IEG adds two additional lessons: Linking the sub-projectsof a Bank-supported capacity-building institution to other Bank operations in the countries concerned can produce importantsynergies. In this case, forging such linkages does not appear to have been considered. Bank initiativesat regional and sub-regional levels frequently encounter difficulties in attracting necessary resources for supervision andadequate managerial attention. This, in turn, reflects the country-oriented structure of Bank operations and incentives.In this case, the ACBF complained of Bank managerial neglect. Moreover, Bank financial support to the Foundation prior to theproject was not accompanied by adequate supervision.
P122483 | ML-Fifth Poverty Reduction Support Credit | Western and Central Africa | Mali | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/525111474567084998/text/000020051-20140625225506.txt | http://documents.worldbank.org/curated/en/525111474567084998/pdf/000020051-20140625225506.pdf | The ICR provides some important lessons, several of which are adapted here:1. Development policy operations that do not carefully reflect on the experiences of similar previous initiatives can easily fall into the trap of repeating earlier mistakes. Despite the discontinuation of the previous PRSC series in Mali (which was ultimately assessed unsatisfactory), the Bank immediately recommenced with a new series, before a self-evaluation of the experience could be completed and before the Bank and Government could formally review the reasons for poor performance. Yet the new program sought many of the same policy changes, even though the underlying political environment had not evolved. This diminishes the Bank's credibility in encouraging important reforms, as PRSC support can be seen as guaranteed irrespective of the results.2. Technical assistance is critical to help a low capacity administration implement a complex reform program. In Mali, the technical assistance project that was intended to be implemented in parallel with the PRSC was significantly delayed, only becoming operational in August 2011, at the end of the series. This delay hampered the program, in this case with regard to improving capacity to deliver decentralized services. Programs that are intended to be complementary with other Bank activities--technical assistance, analytical and advisory services, investment lending, etc.--should be adjusted as the timeline for delivery of those products changes.3. The selection of indicators appropriately matched to program objectives, with ambitious but realistic targets, signals the importance the Bank places on development outcomes. For PRSCs 3-5 in Mali, many indicators were dropped mid-course, replaced, or altogether ignored, a symptom of lack of realism. More than a few were focused on inputs and processes. Baselines were highly unreliable. It is thus not surprising that the Government did not take seriously its responsibility to monitor results.In addition, IEG offers the following lesson:4. Stretch reforms in areas with strong entrenched interests or that are politically sensitive require deeper commitment than typical reforms, and should be limited in number for a given operation or series. In Mali, these included introducing private participation into the cotton sector, creating a mechanism to increase electricity tariffs in line with costs, and reducing the focus on incentives in investment promotion. Each of these reforms was delayed considerably and ultimately failed. Given the obvious challenges in implementing each of these reforms as evidenced by past efforts, an approach that focuses the Government's energy and political capital on one key issue head on, while laying the groundwork and building consensus for the others, may be more effective.
P122486 | Karnataka Watershed Development Project - II | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/245301624952054865/text/India-IN-Karn-Wtrshed-II.txt | http://documents.worldbank.org/curated/en/245301624952054865/pdf/India-IN-Karn-Wtrshed-II.pdf | The ICR presents seven relevant lessons and their aspects which have broader application beyond this project. According tothis review, the key lessons and broader aspects are summarized below (ICR, paras. 74 84).(a)Science-based approaches can be a central element in the next generation of integrated watershed projects. Theproject successfully demonstrated a new model for integrated watershed development support, based on strongerscience-based evidence. Previous World Bank-supported watershed development projects in India, including the first KWDP, pioneeredand scaled up participatory watershed improvement and improved ME. KWDP-II improved the effectiveness of integrated watershedmanagement by developing, through technical partners, better science-based planning, decision support tools, and the capacities touse them. The GoK now has better systems and capacities to conduct improved watershed development and disseminate this knowledge toother states and countries. This enhanced model of watershed development is of particular relevance in states/countrieswheredevelopment planning isintegrated with livelihood interventions, and where integratedwatershed managementprograms can be supported by the required technical and financialresources.(b) A LandResource Inventory (LRI) is a valuable tool for managing watersheds effectively. The project was successful in developinga LRI at the micro-watershed (MWS) level and combining it with additional layers of data in a digitized library and using decisionsupport system (DSS) tools. This multi-layered database resulted in a 3540 percent reduction in watershed planning time anda 70 percent reduction in planning costs per detailed project report and per hectare. It also made watershed managementinterventions more relevant to the specific conditions in the field and made better use of government resources because of thetargeting accuracy at which investments could be made. The lesson is that future watershed management projects could benefit byadopting this LRI tool and approach, as a core element in their design, adjusted as needed for local conditions, capacities, anddata availability.(c)The LRI can also integrate/converge government agencies interventionsaround a useful extension tool. The establishment of the portal and the dissemination workshops carried out within the GoKallowed government agencies to access the digitized library and make use of the information to plan their watershed developmentinterventions in an integrated manner. The wide outreach to farmers through RSKs enabled farmers to access plot- level informationfrom their mobile phones and use it to better manage their lands in terms of crop and soil conservation techniques, selection ofcrops and inputs, and timing of interventions. The lesson is that agricultural development projects, through the extensioncomponent, consider the benefits, rationale of and most suitable approach for establishing LRIs as sound measures of integrationand extension, while contextualizing/adapting them to local conditions.(d)Establishing aconsortium of qualified local scientific and technical partners can be an effective arrangement for supporting theGovernment in the design and implementation of watershed management investments. Instead of hiring consultingfirms, this project partnered with a group of highly capable state-based scientific and technical agencies, which took an activerole in the design, development, and implementation of key project activities. This project experience demonstrated that thisstructure had several advantages, pertinent to the context of watershed management. . For example, the consortium approach,contextualized for each case, can lead to better coordination of implementation and enhanced cost savings in projectmanagement.(e) In countries where government staff turnover is frequent, the project shows the benefit ofallocating additional implementation time to accommodate repeat trainings and learning curves, and to work out a delegation of theprocurement clearance authority. Implementation delays occurred due to frequent turnover of senior officials and oftrained procurement staff in key departments (WDD and DoH). A key lesson was the value of issuing a Government Order whichgave the procurement clearance authority to other key actors (in this instance, the WDD Commissioner, PEC, and PPMU). The projectalso showed the benefit of providing a one-year extension to complete key project activities and accommodate the GoK staff andmanagement learning curves.(f) Using existing government training centers can reduce capacitybuilding costs. The project showed that it was able to take advantage of existing and new government trainingcenters/facilities for much of the capacity and institution building. This approach illustrates the lesson ofsavingprojectfunds compared to using and paying for private sector suppliers, provided the government centers are high quality andcan develop suitable programs.(g)Since national programs may change over time (because of changes inthe Government and/or setting of new national priorities), this project showed that projects which rely on the implementation ofnational programs should remain flexible to accommodate unforeseen changes. The 2014 general elections resulted in the(apparently) unforeseen closing of the Integrated Watershed Management Program (IWMP) and the launch of the Prime MinisterKrishi Sinchayee Yojana Plan (PMKSY - another government initiative), which threatened the financing and implementationofphysical conservation investments. This challenge was eventually overcome by making use of and/or reallocating available projectresources to implement essential physical (or other) interventions in sample micro watersheds( MWSs).
P122540 | LB: PCB Management in the Power Sector Project | Middle East and North Africa | Lebanon | IBRD | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099015002232227422/text/Lebanon000LB0000Power0Sector0CLOSED.txt | http://documents.worldbank.org/curated/en/099015002232227422/pdf/Lebanon000LB0000Power0Sector0CLOSED.pdf | The ICR (p.27-28) included several lessons learned: Even small grants can can be catalytic in achievingpolicy, institutional, and investment change. Even though the external financing for this project was only US$2.5 million,this project was able to achieve results beyond its original scope by contracting international expertise and was therefore able todeliver outcomes that were fundamental to eliminating a serious environmental threat in the country and also fulfilling theobligations of an international convention to eliminate dangerous carcinogenic chemicals. When designing aproject, governmentfinancial regulations, though different from World Bank preferred procedures, can be accommodated but maycause delays in the disbursement of funds. For example, procurement procedures practiced by Lebanon differfromthe Banks procedures. In this project the grant proceeds were integrated into the national purse and therefore theimplementing agency needed to access the grant money through an Emergency Advance Decision adding layers ofbureaucracy and delaying disbursement.
P122546 | COTE D'IVOIRE - Emergency Youth Employment and Skills Development Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099525007272217496/text/P1225460f8a9c606709491015b5f56187dc.txt | http://documents.worldbank.org/curated/en/099525007272217496/pdf/P1225460f8a9c606709491015b5f56187dc.pdf | The following lessons are a subset of the seven relevant and insightful lessons presented in the ICR, some slightly reworded byIEG to be more succinct: Jobs and skills development projects can be remarkably successful in post-conflictcountries, especially when project designs adapt to a changing country environment and the flexibility of World Bank support andprocedures are fully exploited.In this project, the original design accommodated the countrys immediate post-conflictneeds and evolved, with AF and an extended implementation period as the country emerged from the post-conflict situation, toinclude a focus on rural areas and more capacity and institution building at central, regional, and locallevels. Labor-intensive public works programs that include training and savings opportunities are important for providingeconomic integration of vulnerable groups and can be effective in raising their earnings, improving their psychological wellbeing,and improving their post-program employment prospects. Entrepreneurship training and seed funds are critical for newentrepreneurs to begin and sustain their businesses. During this project, individual savings, though substantial, were notsufficient to fund income generation initiatives completely.However, as a complement to individual savings, the developmentof a competitive seed funding mechanism to support good business plans and the proactive role of Regional Councils working withlocal financial institutions proved to be effective. Two factors can make critical contributions to the success ofinternship and apprenticeship programs: (i) payment of participants to offset their indirect/opportunity costs and compensation ofcompanies for taking the participants on board; and (ii) the undertaking of impact evaluations and tracer studies to assess programeffectiveness, inform needed adjustments, and document the usefulness of the programs for participants andcompanies. Ensuring the existence of a sound regulatory framework is essential for addressing systems weaknesses, whichin this casewere undermining the potential of the vocational education and training system.Systems reform undertakenunder the AF significantly enhanced capacity, including private sector participation and the introduction of a dual apprenticeshipprogram, combining theory with on-the-job experience.
P122616 | Malawi - Financial Sector Technical Assistance Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/505521565729476880/text/Malawi-MW-Financial-Sector-Technical-Assistance.txt | http://documents.worldbank.org/curated/en/505521565729476880/pdf/Malawi-MW-Financial-Sector-Technical-Assistance.pdf | Lessons identified in the ICR are summarized and rephrased below: (i) Realism of activities andreadiness for execution are the predictors of a successfulproject outcome. The high-quality technical studies thatunderpinnedthe project activities identified at appraisal, and theadvance procurementof the technical consultantswere key factors that helped expedite progress toward pursued project outcome and objective. For instance, project design drewheavily from the conclusions of the 2008 World Bank-IMF Financial Sector Assessment Program report.(ii) The PIUcan be used to reinforce ownership of project achievements through end-userinvolvement throughout the projectlifecycle. The RBMworked together with the PIU and facilitated stakeholder consultation and engagement on allactivitiesrelated to financial market infrastructure upgrade, and ensured that stakeholder engagement was infused into theproject throughout its lifecycle as an iterative process. The goal was to gather views of key stakeholders and arrive at commonpositions of the future design of the technical solutions, through a participatory and inclusive process.In this context, amapping and identification of stakeholderswas undertaken in the early stages of the project to obtain a complete picture ofkey sector players.(iii) Proactive actions by the implementing agency and the PIUteams can help strengthenlocal technical capacity.This is especially critical when defining the technical specifications of the technologicalsolutions to be acquired as well as the commissioning of the solutions.Special emphasis went to ensuring continuity inparticipation by key stakeholders and actors throughout the project lifecycle and at critical project implementation periods to acton trends and other signals before they become issues.Retention of adequate skills mixes on the PIU teams and sharedplatformwere key to building capacity and had implications on the implementation and monitoring of innovativeactivities.(iv) Sustainability of project resultscan begenerated from deliberately investing inongoing relationship building.When a project involves multiple stakeholders, it is critical that theimplementation agency and PIU teams maintain good and productive relationship with all of them.There is a need to haveupfront conversationson the nature of the technical solutions and business model and what is required from everyone to makeit work and succeed.The development and implementation of shared infrastructures such as a national switchwas a complexprocess requiring the active involvement of all stakeholders andsupported by technical working groups that bring togetherboth bank and non-bank financial sector actors to consider all project outputs and proposals for the target architecture of theinfrastructure and operating business model. The PIUfacilitated the transfer of good practices and sharing of lessons andexperiences. Formal and informal pathways were established for consistent communication to continually build the relationship amongstakeholders.
P122629 | North East and Red River Delta Regions Health System Support Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099522411222110140/text/Vietnam000VN0NORRED.txt | http://documents.worldbank.org/curated/en/099522411222110140/pdf/Vietnam000VN0NORRED.pdf | Lessons drawn from the ICR (pages 27-28) and additional lessons from IEG: Certain elements of the project designcan help to build ownership and thus contribute to achieving outcomes and ensuring sustainability. In the case of thisproject, the bottom-up planning mechanisms helped to ensure strong alignment of selected activities with local needs andpriorities, andthe requirement to use own budget to partially finance the quality improvement plans ensured continued fundingand proactivity in promptly resolving implementation problems. While a projects theory of change may be sound, aninadequate results framework can inhibit proper assessment of outcomes. In the case of this project, the original projectindicators (reduced referral rates) were appropriate but were not feasible for collection by the participating hospitals, and therevised project indicators (number of patients benefitting from new hospital techniques) were not directly linked to the projectobjective to increase efficiency in the use of hospital services.
P122640 | Disaster Risk Management Development Policy Loan with a CAT DDO | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2011 | 2015 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/129651468186255312/text/ICRR14751-P122640-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/129651468186255312/pdf/ICRR14751-P122640-Box393191B-PUBLIC.pdf | Lessons from the ICR:The policy dialogue on DRM could be made more efficient by improving the indicators of the policy matrix. DPLs support governments in implementing reforms to improve their policy and institutional framework. The impact of the reform program is closely related with the quality of the policy matrix, which should include specific, measurable and attributable outcome indicators with baselines and targets, given their importance for the quality of the policy dialogue.Reporting responsibilities and monitoring arrangements should be agreed with the Borrower in the early stages of the operation to improve the effectiveness and monitoring of the policy measures supported by DPL. In the case of El Salvador, the submission of consolidated written progress reports would have helped ensure consistency in the quality and level of detail provided across the participating institutions.
P122667 | Vietnam Climate Change Development Policy | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2012 | 2013 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/539571485476416938/text/Vietnam-VN-Vietnam-Climate-Change-DPL.txt | http://documents.worldbank.org/curated/en/539571485476416938/pdf/Vietnam-VN-Vietnam-Climate-Change-DPL.pdf | The lessons highlighted in the ICR (paras. 71-75, pp. 29-30) areapplicable to similar operations, especially:1.An effective cross-sector platform is needed to achieve significant progress on policy and institutional reforms that addressclimate change;2. Convergence of programs and resources between line ministries, across development partners, and betweennational and sub-national levels of Government is also necessary for achieving progress on climate change reforms; and,3.High level engagement with the government, supported by strategic and targeted technical assistance and knowledge, is essential toachieve reforms on climate change.In addition, as IEGs recent learning evaluation with regard to environmental(including climate change) development policy operations has found, the following lessons, whichare also illustrated by thepresent DPO series,are also of relevance:1. Strong and persisting Government and other stakeholder commitment toprogram objectives and policy actions, including that of key Finance and Planning Ministries, as well as that of other implementinginstitutions, is essential;2. The Bank should be willing to join ongoing policy-based programs if it can clearlyaddvalue by helping to better focus them and prioritize policy actionsthatare of especial importance in achieving theirgeneral objectives (i.e., climate change adaptation and mitigation in the present case) as well as through itssupervision/implementation support; this can also help to enhance donor coordination and local capacity with regard to policysupport in a particular country;3. Climate change development policy operationsare more effective if they arefocused on a limited number of high priority policy areas, counton strong government commitment and based onsolidbackground analytical work and are used in conjunction with other Bank and donor-supported technical assistance and investmentoperations, including in the present case with respect to water resource management, energy efficiency, and natural disaster riskmanagement; and,4. Task team leadership arrangements in which responsibilities are shared by internationalspecialistsbased in Headquarters and local ones basedin the field can help the Bank toprovide more efficient andeffective implementation support, including to other participating donors that are present on the ground, while also ensuring thatBank polices and operational requirements are fully met.
P122692 | Ghana Local Government Capacity Support Project | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/468931561735305968/text/Ghana-GH-Local-Government-Capacity-Support.txt | http://documents.worldbank.org/curated/en/468931561735305968/pdf/Ghana-GH-Local-Government-Capacity-Support.pdf | The ICR (p. 32-33) provided lessons learned which were adapted byIEG: Inorder to ensure long-term capacity building in local governments, it is critical to include regional government entities that cancontinue their support after the project closed. In this project local governments initially received technical andmentoring support from Regional Technical Advisory Teams (RTATs) which consisted of consultants with required technical expertise.However, since such intense support would not be sustainable in the long-run, capacity was built within the Regional CoordinatingCouncils (RCCs) to take over from the RTATs and support local governments. Activities such as usingmedia network and radio and holding stakeholder meetings can be effective for raising awareness of communities and governmententities. This project conducted several effective initiatives to raise awareness such as establishing a socialaccountability unit, holding regular social public expenditure financial accountability meetings, institutionalizing townhallmeetings, establishing a media network across several regions, and conducting media campaigns and awareness and educationaloutreaches.
P122694 | Environmental Land Management and Rural Livelihoods Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/624581558014153035/text/Tajikistan-Env-Land-Mgt-and-Rural-Livelihoods-GEF.txt | http://documents.worldbank.org/curated/en/624581558014153035/pdf/Tajikistan-Env-Land-Mgt-and-Rural-Livelihoods-GEF.pdf | Lessons provided in the ICR (pages 26-27) are appropriate and synthesizedas follows:1 . Support to beneficiaries through directinvestments is most effective when complemented with facilitation support and capacity building. This builds commitment,engagement and ownership throughout the project cycle, including: active participation in community-based planning anddecision-making; transparent and informed prioritization of local needs; and sustained adoption of sustainable practices.Institutional capacity of the implementing body and facilitating organizations is equally important to ensure well-preparedsub-projects and effective project oversight.2 . Establishing mechanisms to engage with local government helpsgain buy-in and support from decision-makers, who can elevate critical project issues and interventions within the localdevelopment agenda. Strengthening relationships between communities and local government reinforces commitment, buildsownership and contributes to the sustainability of project outcomes.3 . Local representation within projectimplementation units is critical to encouraging community buy-in, maintaining dialogue between beneficiaries and otherstakeholders, and ultimately, achieving success in community-driven development (CDD).4 . Creating astrategic knowledge management and dissemination system at project inception can support, and broaden, the outreach of effectiveproject tools and approaches. Curating and disseminating information helps raise interest, awareness and understanding ofproject activities. Knowledge platforms also help facilitate coordinated, multi-stakeholder dialogue and learning across local,regional and national levels for greater impact. Ensuring the sustainability of such knowledge platforms requires a well-definedvision, mandate and financial strategy.5 . Building resilience to climate change, and measuring aprojects contribution to this aim, is complex and challenging. Yet, innovativemethods such as a participatory well-being index can help build the evidence-base for project outcomes. Combininginnovative metrics with robust ME based on guiding principles of resilience operations, strengthens evidence-based evaluationand learning.
P122699 | PUBLIC FINANCE AND SOCIAL PROGRESS DPL | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/902151474577896336/text/000020051-20140626115814.txt | http://documents.worldbank.org/curated/en/902151474577896336/pdf/000020051-20140626115814.pdf | There are two lessons from this operation that can be put to good use in future DPL operations: While the identification of risks at appraisal is critical; their monitoring and mitigation require attention during implementation. Even if the Bank dialogue with the Government is continuous, great care has to be paid to internal political polarization that can became a hindrance to the the pursuit of reform, and eventually trigger the need for risk mitigation measures being taken.Policy reforms supported by the Bank's operations require continuous support from key internal stakeholders. When internal dialogue among the Government and these stakeholders on issues related to policy reforms and indebtedness is polarized, the Bank should step up the level of dialogue and ensure that all relevant segments of the society are included in the policy debate.
P122700 | Angola Learning for All Project | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099042623164557539/text/P122700038c0250e00a4ef0443a6f715921.txt | http://documents.worldbank.org/curated/en/099042623164557539/pdf/P122700038c0250e00a4ef0443a6f715921.pdf | The ICR (p. 37-38) provided a variety of useful lessons learned which were adapted by IEG: When a Bank operation plans to implement highly technical activities, such as learningassessments, it is critical to provide technical assistance through local or international expertise to build capacityfirst. In this project, it was overly ambitious to envision the establishment of a system for studentassessment completely implemented by the Ministry of Education given its low technical capacity. When introducingfinancial mechanisms such as school grants, conducting an analysis of the flow of funds can ensure that the mechanism will work outand schools can become as autonomous as planned. In this project, due to flow of fund issues from the central level to theschool level, the project decided to centrally distribute the same package of materials to all schools not allowing for addressingthe individual needs of each school. When data quality during project preparation is poor, collecting data ofadequate quality and revising the indicators in the Results Framework allow for better monitoring. The 2017 restructuringof this project revised the targets of some indicators to reflect the reality on the ground and provide a better understanding ofthe definitions of some indicators. However, some definitions were still not sufficiently clear and did not allow for effectivemonitoring.
P122735 | Metro Colombo Urban Development Project | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR (p. 22-23) included several lessons learned which were adapted by IEG: Projects involving largeconstruction works require sufficient time for preparation including technical preparation, resettlement and land acquisition aswell as procurement processing. This project was not ready for implementation when it was approved by the Board resultingin several implementation delays due to several challenges including procurement and resettlement issues. Choosing instead aMulti-Phase Programmatic Approach (MPA) as the lending instrument would have allowed for adequate preparation time during phase 1of the MPA and focus on construction and sustainability in the subsequent phases. Ensuring smoothcoordination between implementing agencies is critical for successful project implementation. In this project, there wereimplementation delays due to the lack of coordination between the implementing agency and the PLAs, such as the Colombo MunicipalCouncil resulting in an incomplete resettlement and therefore an incomplete construction of the Norris canaldiversion.
P122738 | Disaster Risk Management Development Policy Loan with a CAT DDO | Latin America and Caribbean | Panama | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2012 | 2021 | 2023 | ICRR | >=50 million & <100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/099301112232230910/text/P1227380f62f620f80bc62015928434462f.txt | http://documents.worldbank.org/curated/en/099301112232230910/pdf/P1227380f62f620f80bc62015928434462f.pdf | The review draws the following main lessons from the ICR. which are based on theexperience of implementing this operation,with some adaptation of language.1. A clear understanding of the Governments disaster risk reductionpriorities and its immediate and longer-term policy commitments can be useful in designing a successful DPL with a CAT DDOoperation. Even before this operation was prepared, the Bank team engaged in a disaster risk reduction policy dialoguewith key Government authorities. This dialogue facilitated proper identification of policy instruments that were important to theGovernment.2. The timely assessment of progress is important, in the event of a renewal of a DPL with CATDDO. Such an assessment may uncover new areas or identify changes to the results framework. For example, for the secondrenewal of this operation, although the Government had already met the targets for the results indicators, the Bank and theGovernment agreed to adopt non-mandatory expanded values for some targets. This expansion helped to advance the DRM policy dialogueand maintain the Governments access to the Banks specialized technical assistance.3. TheBanks inclusion of public health emergencies as drawdown triggers for new DPLs with a CAT DDO operations could beuseful. In the context of the ongoing COVID-19 pandemic, the difficulties experienced in Panama due to the explicitexclusion in the Loan Agreement of public health as a drawdown trigger demonstrated the need to explicitly indicate in theoperations Loan Agreement that certain public health related emergencies can qualify for drawdowns.4.The value added of a DPL with a CAT DDO may well go beyond its role as a source of quick liquidity in the aftermath of acatastrophic event. This operation was renewed twice and the second renewal was at Government request when the loan hadbeen fully disbursed. This demonstrates that in addition to the financial function of the instrument, borrowers value the policyadvice and technical assistance as part of the operation.
P122764 | Ethiopia Women Entrepreneurship Development Project | Eastern and Southern Africa | Ethiopia | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2025 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062323175531435/text/P12276407662ec0a80acdf06473c05a0529.txt | http://documents.worldbank.org/curated/en/099062323175531435/pdf/P12276407662ec0a80acdf06473c05a0529.pdf | Three lessons are drawn from the ICR, with some adaptation.Lending to women-owned MSEs is a viable business ifthe right incentives are provided. This project showed that demand for credit by women-owned MSEs was robustinan economy where women-owned MSEs were significantly more under-served by the financial system than men-owned MSEs. Theproject fundfor the credit facility was disbursed two years ahead ofschedule. The credit facility attractedparallel financing from other donors, more than twice the original IDA credit. Participating microfinance institutions tappedtheir own funds and the Development Bank of Ethiopia, a revolving fund, to continue lending to women-owned MSEs, beyond theoriginal scope of the operation. The average loan was over four times largerthan assumed, indicating demand bygrowth-oriented MSEs in the missing middle. The repayment rate by women-owned MSEs was higher than inthe rest of the loan portfolios of the participating financial institutions. Interest rates were partly subsidized. The highloan repayment rate suggests that, given the right incentives, women entrepreneurs can be a viable segment for loanfinancing.Technical assistance to MSE lenders is as vital to entrepreneurship development and finance as technicalassistance to MSE borrowers. This project provided technical assistance to MSE lenders including supportforthe preparation of an institutional development plan for the Development Bank of Ethiopia, assistance in implementinginstitutional development plans at microfinance institutions, and the training of loan officers at microfinance institutions.The servicesaimed to upgrade institutional and technical capacity at MSE lenders to foster lending to women-owned MSEs,including growth-oriented MSEs that needed more sizable loans. The capacity building and training helped participatingmicrofinance institutions serve women-owned MSEs which were not their traditional clients, according to theICR.Knowledge gained through rigorous evaluation strengthens project impacts. This projectpartnered with the Africa Gender Innovation Laba World Bank unit thatconducts impact evaluations to assessthe outcome of development interventions in Sub-Saharan Africa focused on the gender gap in earnings, productivity, assets, andagency to produce evidence on what works in interventions that support women entrepreneurs. The evaluationscovered, among others, innovations to reduce collateral requirements and psychology-based business training.According to the ICR, the evaluations made attracting other donor financing for this project easier. The findings from theseevaluations have since informed the design of similar Bank operations supporting women entrepreneurs in Indonesia, Mexico, Nigeria,and Turkey.
P122770 | IN Uttar Pradesh Water Sector Restructuring Project Phase 2 | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2021 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099082001312315121/text/P1227700593bf30360b211073fecadf87a3.txt | http://documents.worldbank.org/curated/en/099082001312315121/pdf/P1227700593bf30360b211073fecadf87a3.pdf | (Reference ICR paras. 100 to 110).The ICR lists a number of lessonsfrom the Project experience whichhave relevance for similar projects carried out in comparable environments. From these, IEG derives the followinglessons:The role of institutions in molding appropriate water management practices is critical to the successand sustainability of an irrigation-based mode of agricultural production. Sustainability of ID investmentsrequires the building of ownership by users and institutional capacity. The use of a phased approach (over a span of two projects)towards the restructuring of the water sector while improving the performance of irrigated agriculture helped in developing thenecessary ownership and institutional capacity.Sustaining beneficiary engagement and interest arecritical for deriving the benefits from rehabilitated or newly built ID structures: The Projectsexperience has shown that farmers require support in adopting improved water management and agronomic practices that raiseproductivity while conserving resources. The outcomes under the Project demonstrated the feasibility of voluntary adoption ofvarious resource-saving agronomic practices through training, capacity building, and showcasing opportunities for cost savings.Water User Associations (WUAs) proved instrumental in dissemination of relevant knowledge. It was observed that WUAs constitutedthrough substantial community and mobilization and with support from non-governmental organizations became functional faster andperformed better than those set up by the government agency (UPID). Since WUAs typically require 4 to 5 years of consistent supportto become fully functional, additional external support through NGOs could prove helpful.More explicittargeting and outreach to vulnerable groups is required to enhance benefits accruing to women, land-poor (or landless) farmers, andmarginalized social groups. While the Project achieved its target for number of women farmers, the overall proportionwas low. A detailed gender gap analysis and creation ofa Gender Action Plan (GAP) during project preparation could havehelped increase the extent of female participation.
P122776 | Central African Backbone - APL4 - Gabon | Western and Central Africa | Gabon | IBRD | Non-FCS | Digital | Digital Development | IBRD | IPF | 2012 | 2021 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/480541624281726591/text/Gabon-Central-African-Backbone-APL-Gabon.txt | http://documents.worldbank.org/curated/en/480541624281726591/pdf/Gabon-Central-African-Backbone-APL-Gabon.pdf | The ICR draws the following main lessons from the experience of implementing this project, which are presented herewithsome adaptation of language:1. Policy reforms aimed at creating an enabling environment for the ICTsector can help in private sector participation and bring about transformational change in the sector.Governmentdemonstrated strong commitment to reforms, by establishing an independent regulator justbefore this project was approved.This project included activities aimed at institutional strengthening of the regulatorand other stakeholders in conductingPPP negotiations. The lesson from this project is that policy reforms are crucial for private sector participation in the ICTsector, and bringing abouttransformational change in terms of boosting broadband penetration.2.Implementation arrangements that foster stakeholder coordination are crucial for successful implementation. Theimplementation arrangements of this project included a high-level supervisory body (the Fiber Optic Commission) led by thePresidency and representatives from the relevant ministries. The special advisor to the President was part of the Fiber OptionCommission, and played an important role through continuous follow-up on implementation activities.The commitment at thehighest level proved useful in implementing this project.3. Country Management Units (CMUs) could be leveraged toexpedite activities that require cross-country coordination.Since theCMUs are well connected to the politicalestablishment and decision makers in the countries they cover, the project could have leveraged the Cameroon CMU - which coversGabon, Cameroon, and Equatorial Guinea, to expedite the signature of the interconnection Memorandum of Understanding withEquatorial Guinea and the ongoing construction on the Cameroonian side prior to the closing date of this project.
P122785 | Higher Education Research for Innovation and Competitiveness Project | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/687441592313828102/text/Montenegro-HIGHER-ED-COMPTET.txt | http://documents.worldbank.org/curated/en/687441592313828102/pdf/Montenegro-HIGHER-ED-COMPTET.pdf | The ICR (pp. 29-31) included several lessons, adapted here by IEG: Assessing and understanding the localpolicy context to include factors outside the immediate sector is critical for project implementation. This project wasbased on the Bologna standards and requirements for EU accession, which allowed the Bank and government to design a highereducation project that received strong stakeholder ownership. Investing in substantial capacity development forestablishing national systems in quality assurance, quality culture, research, and innovation is critical for ensuring long-termreforms to higher education. Deep structural reforms take longer than the Banks project implementation period. Byinvesting in building capacity, reforms can continue after aBank-financed project closes. In order toensure sustainability of project outcomes, strengthening the collaboration of the involved ministries is beneficial. Inthis higher education project, the Ministry of Science, Ministry of Economy, and Ministry of Education all played a critical rolein financing, designing, and implementing policies for innovation and human capital development. Creating a dedicated innovationagency might help to ensure an efficient collaboration between the different ministries.
P122793 | Economic Management Competitiveness Credit 1 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/407791529969380247/text/Vietnam-Econ-Mngmt-Competitiveness-Credit-1.txt | http://documents.worldbank.org/curated/en/407791529969380247/pdf/Vietnam-Econ-Mngmt-Competitiveness-Credit-1.pdf | The following lessons are drawn from the ICR:Care should be exercised in designing multi-sectorprograms. A focused program, addressing a limited number of sectors or issues, may achieve more coherentoutcomes. The EMCC series may not have been unduly broad in its sectoral focus, but it addressed numerouspublic sector, financial sector, and private business themes all important but in drawing in several stakeholderswith at least partly dissimilar agendas, it risked uneven implementation, as happened in EMCC.Aprogrammatic operation introduces flexibility. Programmatic, multi-year programs sometimes need to adjust theirpolicies and their indicators to changing circumstances, or to better understanding of the issues as implementation advances.The EMCC went through a few transformations of PDO, of indicators, even of policy objectives all of them based onlearning by doing, i.e. during program implementation.Design and implementation of a programmaticoperationideally draws on inputs from many sources. Where local stakeholders and development partners areactive, and technical assistance and analytical work abound, an operation should engage such sources. The EMCC series is anexample. Inaddition to the direct relationship with the Borrower, the series also actively engaged other stakeholders,both local and external, and drew on ongoing research.
P122796 | Ghana Third Agriculture Development Policy Operation | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2011 | 2012 | 2017 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/707151490035515853/text/112622-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/707151490035515853/pdf/112622-PPAR-PUBLIC.pdf | 4. Lessons 189. The experience of these two programmatic DPO series provides the following lessons. 190. In a sector such as agriculture, in which responsibilities are fragmented across many different directorates and agencies, impact could be heightened by broadening engagement beyond key counterparts in the leading ministry to other directorates charged with delivering program results. In this case, the World Bank's dialogue and engagement was largely through counterparts in the MOFA's PPMED. Although other directorates participated in the selection and identification of prior actions, insufficient efforts were put in to sensitization and capacity building for implementation of reforms. There was a limited understanding of the budget support instrument among many key stakeholders beyond PPMED and lack of ownership in implementation of reforms. Weak coordination within MOFA and the weak leverage that PPMED had over other agencies linked to prior actions hampered PPMED's capacity to track subsequent implementation. 191. Rigorous assessment of government commitment and ownership is needed not only at the design stage but throughout implementation. In Ghana, the government engagement was high with respect to identifying and meeting prior actions but subsequent implementation of reforms was weak. 192. Potential synergies between sector and general budget support operations could be enhanced by more effective coordination and monitoring and feedback between the two. In these two agriculture DPOs, it was assumed at the design stage that the general public financial management reforms supported by PRSCs and economic governance DPOs would also benefit MOFA. However, public financial management reforms did not perform as expected. This illustrates the need for feedback to the sector operation so that measures can be taken to compensate. Additionally, in the agriculture sector, many reforms are needed beyond MOFA's jurisdiction, some of the crossjurisdictional reforms may be best incorporated into national-level budget support. In the second series, MOFA was cautioned by MOFEP to only agree on budget support triggers and targets over which MOFA had direct control. This makes sense from the standpoint of ensuring that targets are met in the short term, but it limits the utility of sector budget support in tackling critical bottlenecks in the sector that are covered by other ministries, directorates, and agencies. The completion reports of both series argue that actions beyond the jurisdictional mandate of the sector ministry would be better managed under MDBS. This too requires greater coordination and ongoing feedback and monitoring between sector and macro level teams. Prior actions that can improve coordination across ministries, directorates, and agencies should be considered. 193. Defining DPO series objectives in concrete and measurable terms and scaling ambition down to what the actions in the operations can realistically be expected to influence can improve the demonstration of impact and enhance attribution. In both of the series reviewed the overly general formulation of objectives made it difficult to connect to the outcomes of the various policy areas to the very ambitious series objectives. The results framework did not establish a clear causal chain between the prior actions and the overall series objectives. The mismatch between the identified outcomes and the prior actions and performance indicators added to the difficulty in establishing the contribution of the series prior actions to the series objectives. Prior actions geared toward policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement and impact.
P122800 | CI: Post-conflict Reconstruction and Recovery Grant (PCRRG) | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/191821474633158423/text/000020051-20140626110626.txt | http://documents.worldbank.org/curated/en/191821474633158423/pdf/000020051-20140626110626.pdf | Â· A country emerging from a prolonged and severe crisis can still achieve significant progress as long as its government demonstrates ownership and commitment to reform.Â· The effectiveness of a Bank development policy operation can be enhanced by its complementarities with other Bank-financed operations and the efforts of other donors in the reform areas.
P122803 | BJ- Poverty Reduction Support Grant - PRSG 7 | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/684481475075448933/text/000020051-20140626000149.txt | http://documents.worldbank.org/curated/en/684481475075448933/pdf/000020051-20140626000149.pdf | The ICR draws important and valid lessons about anticipating resistance to change and capacity constraints when designing reform programs. It recommends an opportunistic approach, pressing harder when the environment is conducive, as was the case after the election of March 2011. It also credits switching from a programmatic series to a stand-alone operation with generating the necessary commitment to reform.Nevertheless, the benefits of a stand-alone operation are unclear. For one thing, it may have shortened the focus of the Bank's engagement with the new Government at a pivotal moment, whereas a programmatic series could have been instrumental in mapping out a longer term action plan. For another, it was detrimental to the performance of the operation itself. At the very least, it would have been preferable to reach a decision earlier on during preparation and/or to monitor more closely the results of the reformulation.
P122806 | TG-Economic Recovery & Gov. Grant 4 | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/524101474943598815/text/000020051-20140625195555.txt | http://documents.worldbank.org/curated/en/524101474943598815/pdf/000020051-20140625195555.pdf | The main lesson from this operation is that, contrary to earlier IEG findings, progress in economic governance reforms can be achieved in fragile environments if the timing and the incentives are appropriate. Performance achieved under this operation derives in part from (i) the progress made under three previous stand-alone operations which supported reforms in the same areas and (ii) the commitment of the authorities through the four consecutive policy grants. Other lessons similar to those indicated in the ICR are as follows. First, in-country supervision of operations and deployment of expertise are key to achieving results when a country's technical capacity is weak and the Bank is operating under a tight operational budget. Second, the design of a DPL should pay attention to the clear definition of prior actions to ensure consensual agreement among stakeholders. Clarity on these issues can favorably impact the monitoring and achievement of results.
P122807 | GN-DPL 1 | Western and Central Africa | Guinea | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/904821475071712138/text/Guinea-Reengagement-and-Reform-Support-1.txt | http://documents.worldbank.org/curated/en/904821475071712138/pdf/Guinea-Reengagement-and-Reform-Support-1.pdf | Re-engagement programs can serve as instruments for promoting reforms and achieving substantial results that go beyond the objective of clearance of arrears and re-engagement. That said, strategic reform agenda need to be realistic in terms of what is possible to achieve under a single operation with a short implementation period, which was not entirely the case with this operation.It is important to identify issues at early stage of project preparation that are politically sensitive and may affect the program outcome. The example of the review of mining contracts granted under the military rule indicates that sensitive issues deserve more scrutiny to determine how best to be incorporated in the program.
P122808 | Ghana Fourth Agriculture Development Policy Operation | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2012 | 2013 | 2017 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/707151490035515853/text/112622-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/707151490035515853/pdf/112622-PPAR-PUBLIC.pdf | 4. Lessons 189. The experience of these two programmatic DPO series provides the following lessons. 190. In a sector such as agriculture, in which responsibilities are fragmented across many different directorates and agencies, impact could be heightened by broadening engagement beyond key counterparts in the leading ministry to other directorates charged with delivering program results. In this case, the World Bank's dialogue and engagement was largely through counterparts in the MOFA's PPMED. Although other directorates participated in the selection and identification of prior actions, insufficient efforts were put in to sensitization and capacity building for implementation of reforms. There was a limited understanding of the budget support instrument among many key stakeholders beyond PPMED and lack of ownership in implementation of reforms. Weak coordination within MOFA and the weak leverage that PPMED had over other agencies linked to prior actions hampered PPMED's capacity to track subsequent implementation. 191. Rigorous assessment of government commitment and ownership is needed not only at the design stage but throughout implementation. In Ghana, the government engagement was high with respect to identifying and meeting prior actions but subsequent implementation of reforms was weak. 192. Potential synergies between sector and general budget support operations could be enhanced by more effective coordination and monitoring and feedback between the two. In these two agriculture DPOs, it was assumed at the design stage that the general public financial management reforms supported by PRSCs and economic governance DPOs would also benefit MOFA. However, public financial management reforms did not perform as expected. This illustrates the need for feedback to the sector operation so that measures can be taken to compensate. Additionally, in the agriculture sector, many reforms are needed beyond MOFA's jurisdiction, some of the crossjurisdictional reforms may be best incorporated into national-level budget support. In the second series, MOFA was cautioned by MOFEP to only agree on budget support triggers and targets over which MOFA had direct control. This makes sense from the standpoint of ensuring that targets are met in the short term, but it limits the utility of sector budget support in tackling critical bottlenecks in the sector that are covered by other ministries, directorates, and agencies. The completion reports of both series argue that actions beyond the jurisdictional mandate of the sector ministry would be better managed under MDBS. This too requires greater coordination and ongoing feedback and monitoring between sector and macro level teams. Prior actions that can improve coordination across ministries, directorates, and agencies should be considered. 193. Defining DPO series objectives in concrete and measurable terms and scaling ambition down to what the actions in the operations can realistically be expected to influence can improve the demonstration of impact and enhance attribution. In both of the series reviewed the overly general formulation of objectives made it difficult to connect to the outcomes of the various policy areas to the very ambitious series objectives. The results framework did not establish a clear causal chain between the prior actions and the overall series objectives. The mismatch between the identified outcomes and the prior actions and performance indicators added to the difficulty in establishing the contribution of the series prior actions to the series objectives. Prior actions geared toward policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement and impact.
P122810 | FOURTH NATIONAL PROGRAM FOR COMMUNITY EMPOWERMENT IN RURAL AREA (PNPM IV) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/205501468189568406/text/ICRR14736-P122810-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/205501468189568406/pdf/ICRR14736-P122810-Box393183B-PUBLIC.pdf | The ICR (p. 21) identifies several valuable lessons, including the following:When designing a Results Framework for a project, it is important that indicators and targets relevant to desired project outcomes are clearly defined, and that these indicators are continuously tracked during project implementation. In this project, the selected indicators were weakly linked to project objectives and only measured on an ad hoc basis, which did not allow for continuous progress tracking.Since the quality of facilitators is essential for the success of a community-driven development program, it is important to provide appropriate training and competitive salaries. Facilitators should be trained before they are sent to the field and be continuously informed about revisions that are made to standard operating procedures and other important guidelines. In this project, salaries were raised in order to attract qualified facilitators in Papua and West Papua.
P122812 | AGRICULTURAL COMPETITIVENESS IMPROVEMENT PROJECT | Europe and Central Asia | Azerbaijan | IBRD | FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041823173034087/text/P1228120a576150e80befd0781c90cc6b12.txt | http://documents.worldbank.org/curated/en/099041823173034087/pdf/P1228120a576150e80befd0781c90cc6b12.pdf | The ICR outlines five sound strategic lessons and recommendations which have broader application for Azerbaijan and for othercountries which are promoting agricultural competitive development. The three most relevant lessons and implied strategicrecommendations are consolidated and summarized below (for further details, especially on recommendations, see ICR, paras.111 115).Lesson 1: The development of agribusiness value chains is a composite and multistep activity whichrequires long term efforts as evidenced by the time it took to fund eligible sub-projects. Review of the availablesub-projects completion reports generated three core sub-lessons on designing and implementing value chain developmentsub-projects. First, when identifying value chains, it is critical to consider their proximity to markets and storage facilities,as well as the business enabling environment and constraints associated with public infrastructure particularly road accessfor farmland and building sites. Second, value chains need continuous support to access innovation and technology to raiseproductivity, reduce costs and stay competitive, and require a strong emphasis on farmer-level measures to boost productivity (highquality inputs, farmer training) and improve market access increases the likelihood of successful value chain development. Third,enabling women to expand their access to financial services (ref. components 2 and 3) requires additional supporting projectinterventions which the project introduced and carried out (including grants and partnership arrangements), and which need to befurther institutionalized and scaled up, also as part of implementing a broader gender strategy as a core component of value chaindevelopment.Lesson 2: ACIPs investments in public goods and services enabled increased and productiveprivate sector participation. This included support to private seed growers, contribution to the privatization ofveterinary services, as well as support to agribusinesses and agricultural value chain sub-projects, which contributed to improvedjob opportunities and increased income. In addition, the project enabled private participation in service delivery and largerinvestments in the agricultural sector by minimizing/eliminating competition of public livestock support services by: (a) focusingon governments role of public services provider (in regulations, monitoring, quality assurance and control, food safety,disease surveillance); and ultimately contributing to building effective agricultural value chains and food safety system; and (b)investing in public good aspects by providing various types of well-focused training/capacity building, drafting, approving andimplementing appropriate new laws and regulations, and promoting wider public awareness and riskcommunication/interventions.Lesson 3: The countrys fragile/conflict context and ACIPs technicalcapacity did not compromise its success, and these pre-conditions require effective design and implementation management.ACIP was operating in a fragile/conflict context, and was characterized by a comprehensive design including an integratedset of activities, which at times may be discouraged by the World Bank as posing implementation risks. However, during ACIPsimplementation, this complexity promoted strategic synergies and contributed to sustaining project results. Although projectdesign should endeavor to minimize project complexity, a technically complex project, especially in a conflictcountry context, requires greater implementation effort, and the projects engagement in various areas and with differentactors can provide flexibility to adjust, and therefore the merits of project complexity should be carefully assessed at projectappraisal, and managed during implementation, including the prudent use of project restructuring(s). Also, ACIPs experiencewith subprojects supported with grants can be a good model to replicate in fragile and conflict settings.
P122826 | URBAN WATER SUPPLY PROJECT | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099032724085528926/text/P1228261c002d005c1b2e5130c797edd256.txt | http://documents.worldbank.org/curated/en/099032724085528926/pdf/P1228261c002d005c1b2e5130c797edd256.pdf | This review has drawn three lessons based on the information in the ICR.The FCV context in a project countrycan be a major barrier to basic infrastructure sector reforms necessary for the sustainability of basic public services.The sustainability of the water supply services developed under the project and the larger Kabala Project depended on thewater sector reform in Mali, which would have improved the financial equilibrium of the water sector. This was to be achievedthrough a tariff reform under the project, but such a reform did not materialize despite the significant efforts of the World Bankproject team and the other donors. The main reason was the frequent changes in the government because of the military coups andpolitical instability in the country. Therefore, conditioning the sustainability of project outcomes on sector reforms might not bea feasible approach in FCV context countries.The addition of secondary urban centers in the scope of waterprojects can increase the development impact and increase inclusion in an FCV context country that would help address one of themain drivers of poverty and fragility. The project was originally designed to improve water supply services and increaseaccess to water in Bamako, the capital of Mali. Following the successful implementation of the original project and some creditsavings, it was decided to expand the project scope, under an additional financing, by adding six urban centers to reduce thecountrys regional disparities in access to water services that were exacerbated by the FCV situation in the country (ProjectPaper on a Proposed Additional Credit, Report No: PAD1792, p.4). While the demand for household connections in these urban centersmaterialized lower than the level estimated at the time of additional financing, the project, nevertheless, achieved to connect anestimated 224,600 people to piped water who would otherwise remain without access to water. The consumer surveys conducted atproject closing showed that people connected to water under the project were satisfied with the reliability and quality of thewater supply service.The absence of a leak management system in a water infrastructure project connecting newinfrastructure with older segments of the existing network can adversely affect the availability of water for the consumers andweaken the financial viability of the water utility. After the commissioning of a new water treatment plant under theKabala Project in 2018, the network efficiency in the water supply network in Bamako dropped by six percent because of theincreased number of leaks in the older segments of the network caused by increased water pressure. The deterioration in the networkefficiency continued through to project closing resulting in a 35 percent of non-revenue water. Same adverse results were witnessedin similar projects implemented in West Africa (ICR, p.26). The poor connection of the new infrastructure built under the projectto the existing network contribute to higher number of leaks. Such leaks result in lower availability of water for the existingcustomers and prevents the connection of new customers to the network, while causing a significant financial loss to the waterutility because of high amount of non-revenue water. Therefore, the implementation of a leak management system under such waterprojects could significantly contribute to the achievement and sustainability of the project outcomes.
P122841 | Stormwater Mgt. and Climate Change Adaptation Project | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/754151621906984180/text/Senegal-SN-Stormwater-Mgt-Climate-Change.txt | http://documents.worldbank.org/curated/en/754151621906984180/pdf/Senegal-SN-Stormwater-Mgt-Climate-Change.pdf | The following lessons are derived from the ICR with some modification of the language:1.Cross-sectoral approaches can lead to a win-win situation for both sectors whenenvironmental considerationsunderpin technical disaster risk management solutions. This can also support higher sustainability of project outcomesandmay be financially beneficial as compared to single sector approaches. The project was based on an integrated approach tostormwater drainage, which combined a watershed analysis with engineering drainage solutions. This approach supported a restorationof the natural pathways for evacuating the stormwater using gravity drainage infrastructure all the way to the ocean through anatural slope in the ground. This was a cheaper approach as compared with a standard one to invest in a pump-based sanitation. Itwas also innovative for Senegal and represented a new vision on flood management, where sustainable land management objectives aremainstreamed into (DRM) infrastructure sector.2. Community engagement in cleaning and waste management canbe critical for the sustainability of outcomes of urban drainage infrastructure projects, especially in densely populated informalsettlements. Activities aimed at community engagementcan lead to behavior change, foster ownership of drainageinfrastructure by communities, and limit the risk of conflicts. The project dedicated a full-fledged component on communityengagement targeting both national and local actors. The project engagedCommunity Based Organizations (CBOs) to work withlocal communities to improve and maintain the cleanliness of public spaces and drainage infrastructure. An impact assessmentpublished in June 2017 concluded that this led to behavioral change. Increased community engagementresulted in improvedfunctioning of thedrainage infrastructure. As a result, the neighborhoods with such community engagement were less affectedby floodingand reported reduced levels of both illness and income loss due to flooding, as compared with neighborhoods wherecommunity engagement did not take place.3. Supporting institutional action and provision of continued financing(for example, the establishment of a sanitation fund and sustainable financing for OM in this project) may facilitate thesustainability of project outcomes. A long-term engagement with the main stakeholders in the country (critically, thegovernment) might be a necessary condition.
P122847 | Lao Seventh Poverty Reduction Support | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/662231474634349460/text/000180307-20141201111524.txt | http://documents.worldbank.org/curated/en/662231474634349460/pdf/000180307-20141201111524.pdf | IEG concurs with the lessons derived by the ICR, including the importance of:(1) Complementarity between policy and institutional dialogue through PRSO and existing investment and technical assistance projects is critical for the success of reforms.(2) Adapting to the political economy of reforms, identifying champions in government with a reasonably well-defined reform agenda and engaging with a broader range of actors, and selecting focused sector engagement were PRSO work has a clear comparative advantage.In addition to these lessons from the ICR, IEG notes the importance of selecting performance indicators, ex ante, which can be benchmarked and monitored.
P122916 | Mineral Governance Support Project | Western and Central Africa | Guinea | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099140106132232181/text/P12291609bcd28051087530a07022b79b8b.txt | http://documents.worldbank.org/curated/en/099140106132232181/pdf/P12291609bcd28051087530a07022b79b8b.pdf | Key lessons learned from project implementation. The ICR contains substantive lessons learned from theoperation. The following additional lessons are suggested:In a country environment characterized by frequentpolitical instability it is important to conduct analytical work in readiness for a window of opportunity when it becomes possibleto engage key stakeholders in a broad-based dialogue to build consensus on policy reforms. This is because in times ofinstability and tensions it is difficult to engage all key stakeholder in policy dialogue. In Guinea, The World Bank hadundertaken substantial analytical work in the mining sector which enabled it to support a broad-based stakeholder engagement whenthe transition to a democratically elected President occurred in 2010. With the World Banks support, the GoG was able toundertake substantial legal and regulatory reforms. It may be preferable, on criticallyimportant reform issues to allow dialogue to continue for some time rather than to rush to second best alternatives.Consensus building on policy reforms can be difficult, especially when there are vested interests or serious divergences of viewsamong key stakeholders. One of the key reforms supported by the project was the development and adoption ofa Build-Operate-Transfer convention defining the rules, roles and responsibilities and obligations in the construction, ownership,operation and use of ancillary mining infrastructure. The BOT was drafted by 2015 but it took four years before it was adopted dueto complex policy and legal issues and differences of view among key agencies, including on procedural issues. However, theGoGs adherence to the process and focus on this important policy reform finally led to a successful outcome agreed by allthe key stakeholders.
P122941 | Comoros Development Policy Grant 2 | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/326431475113518453/text/000012394-20150310101520.txt | http://documents.worldbank.org/curated/en/326431475113518453/pdf/000012394-20150310101520.pdf | This Review supports the lessons cited in the ICR, especially the need for technical assistance, and difficulties of reforms that may affect the balance of power between different factions and levels of the government. The review adds the following lessons:Prior actions that are of one-off character do not always become institutionalized unless a supportive framework is created. This relates to the prior actions on quarterly reporting on budget and bi-monthly reporting on civil service recruitment that were not followed up systematically. It is important that the Government decrees and other regulatory acts that Bank's programs are supporting provide clear mechanisms to make certain actions periodic and reduce risks of policy reversal.Although in a fragile and weak capacity environment preparing and implementing a series tends to be difficult, the fact that the follow-up operation was put together and approved in a relatively short period of time indicates that there might be too much of risk aversion from Bank's side and, accordingly, lost opportunities in terms of possible benefits from longer-term programmatic engagements through a DPO.
P122943 | IDP Living Standards and Livelihoods Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/728421610494362837/text/Azerbaijan-IDP-Living-Standards-and-Livelihoods.txt | http://documents.worldbank.org/curated/en/728421610494362837/pdf/Azerbaijan-IDP-Living-Standards-and-Livelihoods.pdf | The ICR (p. 37-38) section on Lessons and Recommendations was heavily focused on findings with manyrecommendations. Lessonsthat IEG gleaned from the ICR are summarized below. Investments intemporary IDP housing and ensuring adequate maintenance are challenging since the housing is supposed to be temporary and housingis not owned by IDPs. There are indications in the ICR that sustainable investments and quality maintenance toensure adequate living conditions are critical to the health, schooling as well as theeconomic and social development ofIDPs. Therefore, the lesson from this project is that long-term maintenance plans for infrastructure maintenanceneedtobe developed during project preparation andimplementation with the possibility that beneficiaries make current and futurecontributions to the cost of maintenance in order that infrastructure is sustained. Future social assistance andemployment programs can build on community mobilization as developed in this project, especially for reachingwomen.SFDI and its network of regional consultants learned that they needed to establish a level of trust with IDPcommunities before they could work with them in this project, Consequently SFDI and its network of regional consultants builtstrong relationships with IDP communities which were beneficial in their future work together..
P122944 | Second Rural Investment Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2020 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/282231591977142128/text/Azerbaijan-RURAL-INVSMT-AZRIP-2.txt | http://documents.worldbank.org/curated/en/282231591977142128/pdf/Azerbaijan-RURAL-INVSMT-AZRIP-2.pdf | The following two lessons in the ICR stood out as important and relevant to other CDD-type projects and are presented here withsome editing.Building strong community ownership and links between communities and local governments ensuresthat communities maintain infrastructure through active partnership with local authorities. Operations andmaintenance of community-driven investments in rural infrastructure are usually inadequate after the project interventions arecompleted. The project established community infrastructure committees and supported them to strengthen their sense of ownershipand relationships with local governments. This contributed to the finding of independent technical audits that 98 percent ofinfrastructure financed by the preceding and this project remained in good or fair condition after 10years.Selecting livelihoods investments based on existing local expertise or existing market needs strengthentheir commercial viability. During the project implementation, communities identified the livelihoods microprojectsbased on two key criteria: (i) existing expertise within communities, such as poultry incubation; and (ii) existing market needsdue to the lack of supply chain, such as milk collection and fodder processing facilities. The livelihood investments selectedbased on existing expertise enabled the communities to initiate and sustain activities with minimal technical assistance. Thelivelihood investments selected based on existing market needs enabled the communities to swiftly begin providing services to otherbusinesses and producers at the local level.As a result of successful selection of livelihood investments, 92 percent ofcommunity-led enterprises were active and commercially viable at project closing.
P122950 | Benin Cities Support Project / PAURAD | Western and Central Africa | Benin | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/833231634922104595/text/Benin-BJ-Cities-Support-Project.txt | http://documents.worldbank.org/curated/en/833231634922104595/pdf/Benin-BJ-Cities-Support-Project.pdf | Following are three of the five lessons offered in the ICR, with minor additions from IEG (ICR, paragraphs74-78). Customized capacity development interventions may best enhance readiness by cities to implementdecentralization reform.In this project, thetwo-step implementation arrangement allowed thedelivery ofneeded infrastructure while capacities in delivering decentralized services at both the city and central levels were bolstered.This approach also showcased howincreased autonomy ofcities and municipalitiestoexecuteinvestmentsthat deliver services to their constituents. Atclosing, beneficiary cities showed improvements in urban managementperformance and delivered investments in a timely manner. Two city/municipal capacity assessments identified wherelonger-term reforms and support were needed:(i)in localasset management, and (ii) local resourcemobilization.Areas of future local capacity development supportmay include (i) interventionsusing thisprojectsexperiences; (ii) allow cities or municipalities to planand implementcivil works aftertheircapacities improve; and (iii) consider changing needs of the recipients, such as city or municipality size/tier ofgovernment/geographic situation etc. Using an existing window for intergovernmental transfers may provide acentral entity with the incentive to make the systemwork effectively. In this project, funds were coursed through anearmarked window of FADeC.Thesectoral ministry test ran itsfiscal transfer system (FADeC) and provided a level ofownership for the project to work, rather than establishing a standalone mechanism. FADeC was an important vehicleforsectoral ministries to transfer earmarked funds to cities and municipalities in accordance with locally determined priorities whilemaintaining an oversight role.Optimaluse of the FADeC by line ministries may include further incentives and supportsuch asimprovingthe predictability of transfers,regularnotification by the central government to cities andmunicipalities on their allocations, and creatinga more systematic transfer of responsibility of decentralized services tocities and municipalities. A multidimensional approach may be useful to encouragewomen participation inlabor intensive public works. In this projectmore proactive measures mayencouragewomen toparticipatein labor intensive, civil works e.g., road construction/rehabilitation, and street cleaning. Measures may includeworking with contractors to: (i) use flexible task-based payment to attractwomen to worksites; (ii) reachout towomens groups, since working in groups fosters safety and help overcome perceiveddanger; (iii) provide childcarefacilities and allowflexible working hours; (iv) sensitize employees and subcontractors on gender-based violence codes ofconduct; (v) seta quota, where possible, for minimum participation by female workers.
P122982 | Indonesia Development Policy Loan 8 | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2012 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR presents a comprehensive list of useful lessons, not only from DPO 7 and 8, but also from the previous series thatremain relevant (ICR, p. 21-23). Particularly noteworthy are the following: A high quality professional workingrelationship between the Bank and key counterparts, both at a policy and working level, is key to a successful reform program. Sucha relationship benefited, in this case, from the presence of a large Bank team in the country office. relationship determines therelevance and impact of prior actions, facilitates implementation and ensures the appointment of counterparts with a high enoughrank to champion the reforms. In areas where this was not the case, implementation lagged or did not take place. Ageneral or umbrella DPO, like those in this series, can be kept manageable by limiting the number of prior actions andpolicy areas, and by providing complementarity to Bank interventions in specific sectors where further operations can be designedwith a view to deepening the reforms.
P122990 | CG Rep: Transparency & Governance Repeat Project | Western and Central Africa | Congo, Republic of | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2015 | 2016 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/661791468029104437/text/ICRR-Disclosable-P122990-06-21-2016-1466536563895.txt | http://documents.worldbank.org/curated/en/661791468029104437/pdf/ICRR-Disclosable-P122990-06-21-2016-1466536563895.pdf | The ICR provides several useful and insightful lessons, including:Particularly in challenging politicalenvironments, the internalization of governance reforms takes a long time. This projects preparation incorrectly assumed thatthe reforms initiated under the predecessor project would take only a few months to complete, and therefore it inappropriatelyadded additional ambitious reforms to its agenda.Ambitious and potentially controversial reforms cannotrely on a single champion. In this case, the project lost support from the Minister of Finance after a cabinet reshuffle in 2012,but the projects structure did not easily allow for a refocusing on those key agencies that were performing relatively welland could have benefited from enhanced Bank support.In a situation of high political risk, ring-fencingactivities and using dedicated PIUs to ensure adherence to Bank fiduciary rules is no guarantee of delivery on results if the PIUitself has limited capacity and lacks active support from political authorities. In this case, the government undermined thePIUs effectiveness by repeatedly assigning it to other tasks outside the project.IEG adds thefollowing lesson:Repeater projects are unlikely to succeed, even in a favorable international context, inthe absence of strong government commitment and effective learning of lessons from predecessor projects. The context forthisproject-- a reform program initiated by the HIPC debt relief of 2010 -- should have justified and extended thereach of reform efforts, but the opportunity was missed to adjust course after TGRP I, and the project could not sustain momentumafter a less supportive government came to power in 2012.
P122998 | Public Finance Management Technical Assistance Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2014 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/100801548953937214/text/Russian-Federation-Public-Finance-Management-TA-Project.txt | http://documents.worldbank.org/curated/en/100801548953937214/pdf/Russian-Federation-Public-Finance-Management-TA-Project.pdf | Among the lessons presented in the ICR (pp. 35-37), two are of particularimportance:Over-complex project design can hamper both implementation and supervision. Inthis case, the large number of activities and sub-components, and their varied criticality as means of attaining the objectives,not only made monitoring implementation progress onerous, but also made it difficult to evaluate the projects achievements.The complexity of design was compounded by that of implementation arrangements.It is important toundertake restructuring as early as possible. In this case, a restructuring involving major modifications in the resultsframework was only undertaken 18 months prior to closure. Coupled with the Authorities decision not to request an extension, thisleft insufficient time for the new framework to become an effective monitoring and evaluation tool.IEG addsone additional lesson:Careful thought given to the adoption and use of appropriate outcomeindicators can facilitate supervision and evaluation. In this case, the indicators were inadequate. Four of the five PDOswere assessed through single indicators and there was no PDO indicator for outcome area 5. The chosen indicators could, therefore,provide at best only a partial measure of project achievements. Moreover, some of these indicators were derived from exogenoussources, such asDoing Business or the Open Budget Index. The data frequently becomes available with a significanttime lag. Such gauges have a diminished usefulness as a feedback tool unless accompanied by other indicators generated by theproject itself, and by an in-depth assessment of their relevance to country circumstances.
P123044 | Emergency Recovery Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2011 | 2014 | 2015 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/904681475873352127/text/000020051-20150309155846.txt | http://documents.worldbank.org/curated/en/904681475873352127/pdf/000020051-20150309155846.pdf | IEG draws the following lessons from this operation:Quick disbursing loans with significant frontloading can be very useful under situations of economic emergencies, as was the case for the Kyrgyz Republic in 2010.However, such emergency lending that focuses on short term gains will need to be followed by operations with longer term and policy-oriented objectives. In the Kyrgyz Republic this emergency operation was followed by other Bank operations.In countries that are inexperienced with Bank procedures and requirements, it is very useful to have experienced PIUs, as was the case for this project, especially with the PIU in the Ministry of Finance.Projects â€“ including in particular emergency projects where quick disbursements are important â€“ need to address up front any needs for on-lending or similar arrangements. In this case the EPP did not even discuss how resources were going to be passed on to beneficiaries, which led to delays before the subsidiary loan agreements could be agreed. The project development objectives of emergency operations need to be aligned with the rapid response, short-term nature of the interventions. Explicit inclusion of higher level objectives such as macroeconomic issues in the development objectives will need to be considered carefully since this would require explicit measurement and accountability for expected results which may not always be realized given the nature of some such operations.
P123073 | Second Restoring Equitable Growth and Employment Programmatic Development Policy Loan | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/960341474905787421/text/000020051-20140625224719.txt | http://documents.worldbank.org/curated/en/960341474905787421/pdf/000020051-20140625224719.pdf | IEG concurs with the ICR that a flexible approach of DPL series can be helpful in supporting reforms and maintaining dialogue over the longer run. However, in countries such as Turkey where the Bank's exposure is significant, a more focused approach may be needed. Going forward, a focused approach will be all the important given the Bank's limited capital -- an issue raised in IEG's recent evaluation of the Bank's crisis response. Great selectivity places a premium on strong analytical work and ongoing country dialogue.IEG also concurs with the CPSCR: both policy dialogue and attention to M&E are essential for DPL series to achieve their objectives. Equally important are political incentives for Governments to sustain reform efforts over the medium-term.This ICR review also notes that the trade-offs between the shorter crisis response and longer term structural reform goals of policy based operations should be made explicit. Attempting to achieve both objectives within a single series (such as the REGE-DPL) can be especially challenging. Furthermore, DPLs that provide short term external financing in the absence of an IMF program should first seek explicit agreement on the macroeconomic framework and the Government's fiscal stance.
P123093 | West Africa Regional Communications Infrastructure Program - APL2 | Western and Central Africa | Western and Central Africa |  |  | Digital | Digital Development | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099031502122392585/text/P1230930b185d0081099f00b9c16c1b2a46.txt | http://documents.worldbank.org/curated/en/099031502122392585/pdf/P1230930b185d0081099f00b9c16c1b2a46.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Robust policy dialogue with the public and private sector can be very useful for designing a PPP modelwith open access principles that are tailored for country circumstances. Through proactive engagement in both Mauritaniaand Togo, the Bank was able to identify the appropriate PPP arrangement that ensured open access.In Togo, the approachenabled a strong private partner to join early in the process. This brought the necessary expertise when it was most needed. InMauritania, timely consultations with sector stakeholders and coordination with other donors enabled a design where the privatesector plays acentral role and can benefit from the advantages of fair and nondiscriminatory access toconnectivity.2. A careful consideration of the timeline is especially required in ICT projects to avoidrepeated extensions of the project closing date. Given that the creation of a special purpose vehicle and implementationrequirements in general take a long time, this aspect needs to be factored in ICT projects.The IEG draws thefollowing lessonfrom this project.Given the fast pace of changes in the ICT sector, it would be useful torevise the targets for the indicators if need be through the project restructurings. This would give a better picture of theprojects accomplishments.
P123128 | Grenada Safety Net Advancement Project | Latin America and Caribbean | Grenada | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/455041572276104628/text/Grenada-GD-Safety-Net-Advancement.txt | http://documents.worldbank.org/curated/en/455041572276104628/pdf/Grenada-GD-Safety-Net-Advancement.pdf | The ICR (pp. 29-30) offered several lessons and recommendations, including the following lessons restated byIEG:Project progress is facilitated by keeping its design in line with implementationcapacity.Under the project, the original design was unnecessarily complex in a limited capacity setting at entry.Implementation improved after a project restructuringsimplified its scope and design.Whenadopting innovative approaches such as results-based financing, ensuring the clients full understanding facilitates theapplication of such approaches.Under the project, reaching anadequate level of understanding of complexdisbursement mechanisms required more time than standard investmentlending.In-house support facilitates the development of a managementinformation system, as was experienced under the project, along with the importance of filling critical staff positions atan early stage of project implementation.In addition, IEG identified a lessononcrafting objectives more carefully to match strategy and a single projects potential for meaningful impact.While the projectintent and actual activities judiciously aimed at improving targeting, inclusion of vulnerable groups, andreducing fragmentation of the social protection system, these strategic directionswere not well captured by the objectivesstatement to strengthen the basic architectureof the CCT Program and the capacity to implement it.
P123133 | China: Gansu Qingyang Urban Infrastructure Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/929301605042383726/text/China-CN-Gansu-Qingyang-Urban-Infrastructure.txt | http://documents.worldbank.org/curated/en/929301605042383726/pdf/China-CN-Gansu-Qingyang-Urban-Infrastructure.pdf | The following lessons have mostly been derived and summarized from the ICR, with minor additions byIEG:Focusing on strong project management capacity building, combined with a wide variety of hands-on activities,and striving for innovation can lead to results beyond the project outcomes.During the project, QingyangMunicipality and Xifeng District made considerable progress in building their capacity through theimplementation of theproject activities, training, and study tours to other Chinese cities and abroad.All this led, for instance, to theSponge City Program, which scaledthe projects drainage rehabilitation program up to thecitywidelevel. It also led to theextension of the integrated pipe ditch approach of the projects road component to all mainarteries of the city.Innovation can be an essential driver fornew solutions andchallenges the projectimplementation agencies to strive for higher levels. Under this project, the construction of the Easternbypass usingthe dyke technique instead of an originally planned bridge increased the land capacity in an environment with geographiclimitations.The Beijing Dadao Huoxiangou Gully Highfill is the largest volume backfill project in the Loess Plateau.Similarly, theGIS system was a great success and is expected to be expanded to other utilities in the nearfuture.Securing adequate resettlement funds and having the necessary administrative procedures for landacquisition in place before carrying out the resettlement survey, negotiations, and agreement signing are important conditions forthe success of aproject.Under this project, thesignificant resettlement cost increase was mainly due tothe unavailability ofresources after the start of the negotiationswith project-affected people. Thishappenedbecause, while waiting for the availability of the resettlement funds, floor areas andattachments within eachhouse plot considerably increased.In addition, the compensation policy changed during the project. These two factors couldhave adversely affected the achievement of development objectives. Therefore, if a project haslarge resettlement challenges,the timing of resettlement activities,payments, and civil works needs to be alignedto avoid costincreases.Flexibility in the use of loan proceeds for land acquisition can help overcome animplementationimpasse. As mentioned, under this project,the significant resettlement cost increase putthe project at risk.The flexibilityprovided for the use ofloan proceeds for resettlement payments eventually permitted the completion ofthe works and achievement of the outcomes. The Bank task teamalso canceled an activity that did not impact the final outcomebut released the pressure on thecounterpart financing. This brought the project back on track.
P123134 | Dar es Salaam Metropolitan Development Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099110623183529801/text/P1231340ba60f509e098fd034ad96491c02.txt | http://documents.worldbank.org/curated/en/099110623183529801/pdf/P1231340ba60f509e098fd034ad96491c02.pdf | This review has drawn three lessons based on the information in the ICR.A Series of Project (SOP) approach canbe effective in achieving urban development outcomes by facilitating the sustained engagement of the central and localgovernments. This project was the first of an SOPa programmatic approachto improve urban services andincrease metropolitan governance capacity incrementally in Dar es Salaam and Tanzania. While achieving immediate results ininfrastructure development in Dar es Salaam, the first phase encountered obstacles in achieving the metropolitan governance reformbecause of the change in central governments preferences. However, the SOP approach was effective in creating an environmentfor sustained engagement with the government and pursue reforms in politically sensitive topics over a longer period. The successof the first phase led to a renewed government interest in metropolitan governance reform, which will be implemented under thesecond phase of the SOP.High project implementation readiness because of advanced preparation of civil works atappraisal can significantly increase the likelihood of successful delivery of project outputs and expected outcomes. Theproject hired international consultants during appraisal for the design and cost estimation of civil works and the assessment ofenvironmental and social risks. These consisted of low-income area upgrading plans, detailed engineering designs, costestimates and draft bid documents for the drainage works, local road, and community-upgrading (ICR, p.19). As a result ofthese advance preparations, the project was ready to tender 30 percent of the civil works at project start. This contributedto the successful completion of the civil works. However, insufficient engagement with utilities adversely affected projectimplementation (see next paragraph).The lack of data for underground utility infrastructure and insufficientengagement with the utilities during project preparation can significantly jeopardize project implementation. As discussedin the previous paragraph, the project was at an advanced implementation readiness when project started; however, insufficientengagement with the utilities resulted in implementation delays. Additionally, the data regarding the location of undergroundutility infrastructure was insufficient. This resulted in project implementation delays until underground water pipelines werelocated and diverted. These delays were one of the main reasons for project closing date extensions in addition to the delays inthe payment of compensations to project-affected people because of lack of funds.
P123146 | Costa Rica Higher Education Improvement Project | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/569151614717878628/text/Costa-Rica-CR-Higher-Education.txt | http://documents.worldbank.org/curated/en/569151614717878628/pdf/Costa-Rica-CR-Higher-Education.pdf | Lessons drawn from the ICR (pages 27-28): In the context of strong Borrower capacity, the Bank can add furthervalue through introducing new approaches and addressing cross-cutting implementation issues. In the case of this project, theBorrower demonstrated high commitment and strong implementation capacity, therefore, the Bank was able to focus its support onintroducing the results-based management approach and ensuring its success and sustainability. Also, the Bank was able tofocus its support oncoordination ofcross-agency matters such as procurement involving multiple agencies. Theinstitutional improvement plan approachis aneffective tool forachieving results while allowing flexibility fordifferingmeans to a common end. In the case of this project, given the variety of highereducation institutions participating with differing visions and missions, subprojects varied greatly among institutions with eachaddressing challenges specific to each institution. However, the consistency in institutional structures helped facilitateachievement of the overall project objectives.
P123151 | Basic Education Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2013 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/364861550069209069/text/Peru-PE-Basic-Education.txt | http://documents.worldbank.org/curated/en/364861550069209069/pdf/Peru-PE-Basic-Education.pdf | The following lessons are taken from the ICR with some adaptation oflanguage:Government commitment is a necessary condition, particularly when implementing politicallysensitive reforms, but it is also necessary to build awareness for the changes and of the reasons for them. TheGovernment requested adding implementation of the Teacher Reform Law to the operation. Itknew that implementation ofthe Lawwould be politically difficult. Following a teacher strike and ministerial resignations, a plan was put in placeto address theconcerns expressed by teachers, and the Ministry moved forward with the performance evaluation ofteachers. The plan involved consultation and outreach with teachers, unions, and local authorities. It also involvedtraining principals to be able to evaluate teachers in their schools. This reinforced public awareness of the need for changeand increased political support for reform.Timely project restructuring can facilitateimplementation and have impact on results.The restructuringswere importantto increase the projectsrelevance to the borrowers priorities.They also helped to increase the scope of the project and thus increase itsimpact.Conditions of effectiveness should match the instrument and should be reserved for criticalissues. In this case, the Bank was financing eligible budget activities through a Sector-Wide Approach, which meant thatindividual activities were not required to begin implementation. Yet, effectiveness was held up for the approval of theOperational Manual, which required multiple levels of review. This process was made more difficult, as there were changingadministrations.Thus, effectiveness conditions should focus on the most criticaldimensions.Implementing an effective teacher evaluation system needs to balance multipleaspects. Initially, the evaluation of teachers was lenient with standards so that the majority could pass.However, an evaluation systemshould not focus on removal of teachers. Rather, there is a need to ensure a critical mass ofteachers in the system. The evaluation aimed to identify training needs.Thus, when designing an evaluation system, it isimportant to understandits goal. An evaluationsystem requires transparency to ensure teachers understandthemetric and process.A communication campaign was critical tobuild public awareness and gain their support.
P123196 | LR-RRSP4 Budget Support | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The first three lessons are taken from the ICR with some adaptations; the fourth is drawn by IEG:In fragile countries, it is essential to select the prior actions carefully, which should be critical to the governmentsoverall reform program, and take into consideration implementation capacity. Such an approach is necessary not only to reduce thetransaction costs for the Authorities, but also to increase the probability of full action implementation and long termsustainability. In this case, only three previous actions were selected, all of which were critical to the Governmentsoverall program, and fully owned. The harmonization of external support contributes to the reduction of transactioncost for the Government. The Common Assessment Framework (CAF) plays an important role in harmonizing such support. The effect ofthe CAF in reducing the transaction cost on the government could be even greater with more commitment to the instrument, since thedialogue is centered on a single agreed matrix. There was stilla great deal ofbilateral dialogue, at the initiativeboth Government and of the external partners. It is important to engage with political actors outside the Executivebranch, particularly the legislature and civil society. In the case of Liberia, the political economy of the country was such thateven though the Presidents party was in the majority in the Legislature, the President was not necessarily the leader of theparty in the legislature. Thus, in spite of the Executives endorsement of a Bank operation, the legislature had the capacityto override it. An earlier engagement with political party leaders and other key players could have led to a more successfulresult. In fragile and post-conflict countries, the establishment of a steering committee representing governmentand external partners is a critical tool to coordinate the national construction agenda. This was the case of Liberia, where aLiberia Reconstruction and Development Committee (LRDC), was established, chaired by the President of Liberia herself,andcomposed ofthe Ministers of Defense, Finance, Planning and Economic Affairs, and Public Works, as well as majorpartners including the United Nations, the United States, China, the World Bank Group, the European Commission, the InternationalMonetary Fund, the African Union and the Economic Community of West African States.
P123201 | Cities and Climate Change | Eastern and Southern Africa | Mozambique | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/401241630075790853/text/Mozambique-MZ-Cities-Climate-Change.txt | http://documents.worldbank.org/curated/en/401241630075790853/pdf/Mozambique-MZ-Cities-Climate-Change.pdf | 1. When local capacity needs areassessed and reflected in the project schedule at start, both efficacy andefficiency are positively affected. In relation to the MPGs which were successfully utilized in the project as mechanismsto incentivize own-source revenue generation, sufficient implementation capacity at local level was critical, and creating itrequired more time than expected. The time was needed for the preparation of technical design and safeguards instruments,procurement of contractors, and supervision of works for the MPG subprojects.2. On-the job training can becritical for project longer-term resultsand inclusion oftechnical experts in teams to provide continuous on-the-jobtraining and advice canbe asolution. Projects results from municipal institutional strengthening wereuneven and slow until on-the-job support was extended in response to the request of the beneficiaries. This led to a significantimprovement. As a result, 78 percent of the participating staff assessed training as excellent and 45.5 percent said they wereready to transfer the acquired skills to other staff members.3. Support to national agencies needs to be clearlyaligned withproject outcomes, and sufficient incentives need to be provided to foster necessary reforms. There arethree lessons learned in this respect. First, there needs to be a mechanism at national level toincentivize the implementation of key reforms. In the project, the absence of such mechanism led to delays and cancellation of someactivities, including the development of a municipal financial management system. Second,disbursement-linked indicators for Investment Project Financing may be useful for similar projects to incentivize reforms that aredifficult to implement. In the project, expected results from the national level support for policy and institutional reform werenot fully defined and not reflected in the RF and therefore could not be monitored. Third, a PIU withinone of the counterpart line ministries might not be the best option because it can jeopardize inter-ministry coordination. In theproject, the PIU was within the MAEFP, but an independent PIU could have supported urban development and decentralizationobjectives, which are by definition cross-sectoral, and better at balancing the interests of all sectorsinvolved.4. It is important that infrastructure construction works in densely populated areas are performed underspecial OHS and community protection measures including traffic safety plans. OHS-related capacity building toimplementing agencies and contractors is needed to ensure safety. This would include training and certification of drivers andoperators, remote speed control systems, and detailed monitoring, in addition to specific contract covenants (for engineers andcontractors) in case of non-compliance with the community safety protection measures. In Beira, four fatalities in the communitywere caused by accidents involving projects construction vehicles.5. Post-construction technical support iscritical for sustainability of project outcomes in countries with low institutional capacity. The project supportedclients capacity to operate and maintainimproved drainage system in Beira during its first year of operation(commissioning phase). This included the allocation of technical consultants to oversee and guide Beiras AutonomousSanitation Services (SASB) in the daily operation of the system over a period of 12 months, as well as extensive training of theSASBs personnel, preparation and validation of operation manuals and protocols, acquisition of additional spare parts, andsimulation exercises for emergency response during critical events. It significantly contributed to adequate performance of thedrainage system to Cyclone Idai and other extreme events, minimizing flooding in the areas drained by the system.
P123204 | Water Management and Development Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2019 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/327661598039086395/text/Uganda-UG-Water-Mgmt-Dev-Project.txt | http://documents.worldbank.org/curated/en/327661598039086395/pdf/Uganda-UG-Water-Mgmt-Dev-Project.pdf | The ICR (p. 28-29) included several lessons learned: Creating a sense of ownership is important for thedesign and sustainability of investments. This project benefited from community participation in the development ofthe CMPs and in the selection process for investments to be made under the project. Even if these consultations slowedimplementation down, it created a sense of community ownership which will be important for the sustainability of theseinvestments. Starting to build capacity within the counterparts during project preparation is critical forensuring a successful project implementation. This project was the first Bank project to be implemented by the MWE andNWSC. Staff needed a significant amount of training in critical areas such as preparing infrastructure designs, procurement,financial management and safeguards resulting in implementation delays. Timely coordination withdevelopment partners is beneficial for achieving development outcomes. Also, ensuring better timing of the financingand that all parallel contracts and financing close simultaneously benefits project implementation. In this project, the Bank teamcoordinated with the KfW when it became clear that Bank financing was not sufficient for the Gulu Phase 1 works.
P123241 | 2nd. Programmatic Debt and Fiscal Sustainability Development Policy Loan | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/157771474663158112/text/000020051-20140626110946.txt | http://documents.worldbank.org/curated/en/157771474663158112/pdf/000020051-20140626110946.pdf | The ICR draws a number of familiar lessons. One of these lessons concerns the need for care in designing a results framework close enough to the operation to allow attribution. The FSDPL's indicators were too high-level and were subject to the influence of external factors such as the macro environment which were not under the Government's control. Another lesson concerns the sequencing and timing of complex reforms. These must be carefully programmed and expectations about short-term outcomes must be realistic.The second issue could have been addressed by coordinating more closely with other development partners, namely leaving macro type issues to the Fund and focusing on more structural and institutional reforms where the Bank has more comparative advantage. The FSDPL tended to confuse these. While the impetus for the program may have stemmed from the urgent macro situation, the policy measures themselves were not particularly aimed at macro adjustment.
P123242 | 2nd. Programmatic Public Sector, Competitiveness and Social Inclusion Development Policy Loan with Drawdown Option | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2018 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons are drawn from the ICR:.Business regulations need to be aligned with businesspractices. In this series, the Government and Parliament laid down a legal and regulatory framework hoping that itwould make participation in formal capital markets attractive. This turned out not to be the case: a more careful analysis ofprivate sector incentives could have promoted an approach that would have been more attractive to the privatesector.Technical assistance can be an essential complement to development policylending. In this project, an institution-building technical assistance loan provided financing as well as knowledgeand advice to agencies implementing the reforms. Government officials stressed to the ICR mission that the technicalassistance loan was crucial for implementing key components of the DPL, such as the transition to performance budgeting, expansionof e-government and reform of customs.World Bank participation in a high-income country in acrisis situation provides market signaling that can encourage policy reforms. Prior to the series, the governmentwas facing fiscal financial constraints that threatened to delay or even stop progress on key policy reforms, including inparticular the ones that subsequently would be addressed under the PSCSI series. The series, especially its first phase,brought the government the means and confidence to continue with its reform process (ICR, p.11)..
P123255 | Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2017 | ICRR | >=100 million | Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/618551481138726701/text/Panama-PA-DPL.txt | http://documents.worldbank.org/curated/en/618551481138726701/pdf/Panama-PA-DPL.pdf | IEG concurs with the ICR lesson (pp. 25-26) with some minor adaptations:Strong Governmentownership of the reform agenda, based in the Government strategy, is essential to ensure the implementation and sustainability ofDPL programs. In the case of this DPL series, the Government engaged in the project implementation and continued to support thePDOs beyond the closing of the project.A simple design, based on the learning from previousoperations in the country, establishes an appropriate pace for reform implementation. In the case of this DPL series, it isconcentrated in four specific objectives clearly aligned with the Governments quinquennial Strategic Plan, instead ofcovering an extensive array of areas.Flexibility to account for rapid responses to changingcircumstances in the implementation of the projects is critical for ensuring effective delivery, especially in the case ofunexpected shocks. IEG would add that changes in the program need to be reflected in the results framework. In the case of this DPLseries, the procurement-related actions needed to be adjusted due to unforeseencircumstances.Strong analytical groundwork and complementary technical assistance are essentialto ensure adequate program implementation. This DPL series focused on areas of strategic relevance where the Bank had previouslyestablished a record of strong technical capacity and had cross-country experience.A fifth lesson should beadded:A solid fiscal basis along with excellent tax collection management are needed toguarantee the long term the sustainability of extensive social policies. In the case of this DPL series, so far the advancements inthe former areas are not enough, although the Government is engaged in supporting the PDOs beyond the DPL series.
P123255 | Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2022 | PPAR | >=100 million | Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099601406022230862/text/IDU10d434fcc1bc2814f331957c12f2bfc273f07.txt | http://documents.worldbank.org/curated/en/099601406022230862/pdf/IDU10d434fcc1bc2814f331957c12f2bfc273f07.pdf | 3. Lessons 3.1 This evaluation of the Panama DPL series affords the opportunity to reflect on lessons for future development policy operations in Panama. These lessons may also be of relevance to operations in other countries in similar situations. Ã¢â‚¬Â¢ Development policy financing design requires realism and clarity about risks to implementation. This entails clearer articulation of the results chain that links prior actions to desired outcomes. For Panama, a closer examination of the results chain would have highlighted the ambition of some of the targets and drawn into question their feasibility over the operationÃ¢â‚¬â„¢s time period. Ã¢â‚¬Â¢ Social protection reform in Panama was a matter of political will rather than resource availability. This is evident in the substantial expansion and better targeting of social protection, without increases in government revenue, suggesting that government revenue was, in fact, not the binding constraint nor a necessary condition for the strengthening of social protection. 1International Consortium of Investigative Journalists and 100 international media partners began publishing massive documentary evidence of foreign taxpayersÃ¢â‚¬â„¢ presence in Panam a, some of which was with the purpose of tax evasion and potentially illicit activities (Fitzgibbon and Hudson 2021). 2 Under prior action 3, the government (i) signed double taxation conventions with 10 countries; (ii) signed the Agreement for Tax Cooperation and the Exchange of Information Relating to Taxes with the United States; (iii) enacted Law 33, which empowers the Data Gaps Initiative to obtain information to comply with any international agreement that provides for the exchange of information in tax matters, regardless of the relevance of the information for domestic tax purposes; and (iv) enacted Law 2 of 2011. Under prior action 7, the government adopted a custody regime for bearer shares to facilitate identification of the ownership of said type of shares. Both sets of actions directly responded to the issues that had resulted in noncompliance under the Global Forum peer review phase 1 (OECD 2010; appendix A). 3 Prior action 10 defined activities and improvements in the office of debt management to ensure that the country issues treasury notes and establishes a primary dealer program. Prior action 11 was aimed at restructuring the debt management office so that it was in alignment with international best practices (appendix A). 4The first prior action required the government to widen the tax base, reduce tax exemptions, and increase the value-added tax rate from 5 percent to 7 percent (for further details, see appendix A). 12 5When the series was being prepared, the government was engaged in widening of the Panama Canal, a major $500 million dollar project. The International Finance Corporation financed part of that project, but the World Bank did because of significant concerns about the quality of the procurement process. 6Enhanced Public Sector Efficiency Technical Assistance Loan Project, which supported reforms in the areas of public financial management and procurement, and World Bank TreasuryÃ¢â‚¬â„¢s technical assistance on debt management. 7 This was documented in Implementation Completion and Results Reports for development policy loan DPL1 (June 2011, July 2011, and November 2012); DPL2 (July 2013 and February 2014); and DPL3 (March 2014). The World Bank and the International Finance Corporation collaborated well, with the International Finance Corporation having a larger presence in the field in Panama. The International Finance Corporation was initially involved in the dialogue on international tax transparency. 13
P123315 | Strengthening Institutional Capacity and Management of the Education System | Middle East and North Africa | Djibouti | IDA | FCS | Human Development | Education | IDA | IPF | 2012 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/295681564509013806/text/Djibouti-Strengthening-Institutional-Capacity-and.txt | http://documents.worldbank.org/curated/en/295681564509013806/pdf/Djibouti-Strengthening-Institutional-Capacity-and.pdf | The ICR provides useful lessons of which IEG notes, in summary, the following:Sound analyticalunderpinning is critical to identifying key areas of intervention: the institutional audit of the Ministry carried out at the endof an earlier project was key to laying out priorities that led to the main design features of the currentproject.To effect progress towards results-based management, it is important to align Annual Work Plans(AWPs) with the national strategy and the ministers management needs. Such alignment gives a sense of clarity, importanceand accountability to the staff who are responsible for the AWPs. Putting in place a dashboard for the Minister provided him withtimely information on the status of activities on a timely basis, which helped improve accountability and the focus onresults.Continued support is critical especially in a low capacity context: the hiring of a local,independent consultant who was located in the Banks country office in Djibouti was a key factor in ensuring end-of-projectimplementation success.IEG adds the following:This project demonstrates how management ofthepolitical economy is critical to successful project implementation.Theproject started out withstrongpolitical and administrative support; however, shortly after preparation, the projects champion was transferred out of theministry and this impacted progress. For example,regular donor meetings at the Ministry ceased, project progress anddisbursementslowed. However, the Bank team remained in contact and dialogue with the new administration and, ultimately,worked with the Government to request a Level 2 restructuring that extended the project closing date by twelve months and allowedfor the achievement of almost all results targets.
P123323 | Ningbo Municipal Solid Waste Minimization and Recycling Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/878751622737441606/text/China-CN-Ningbo-Municipal-Solid-Waste-Recyclin.txt | http://documents.worldbank.org/curated/en/878751622737441606/pdf/China-CN-Ningbo-Municipal-Solid-Waste-Recyclin.pdf | The ICR provides a number of useful lessons (paras 93 to 97). The following are highlighted by IEG with some modification to thelanguage: Separation at source can be introduced at a large scale over a relatively short time but requiresright conditions. The project experience shows that these conditions are: (i) strong government commitment, (ii) capacityto roll out an integrated waste management system that supports separation at source, and (iii) effective public outreach. InNingbo, while the higher levels of government were engaged with planning, securing resources and addressing implementationdifficulties, the neighborhood committees were working on explaining the separation process and requirements and guiding householdshow to best comply with the new program.The Bank project helped to establish a well-integrated infrastructure and systemincluding: equipment at the front end where the waste is separated; the separate containers are serviced timely; separated waste ishandled as a separate stream and not mixed; the cleanliness and appeal around the disposal areas - all of which contributes to thewillingness of households to comply with the new separation program. The community awareness and engagement campaign wasfar-reached and intensive. A public-private partnership (PPP) arrangement for solid waste treatmentcan be promoted through a two-staged procurement process which allowed inputs from prospective bidders to shape the design of thetechnical solution and explore what contractual arrangements could be supported by the market. The PPP for Kitchen WasteTreatment Facility used this approach and was successful and is been studied for replication within China. The experience confirmedthat a market test could inform both the design, the aptitude and willingness of the market to share the risk with the publicsector within a PPP arrangement. Ningbos kitchen waste treatment facilityhas proven theviability of treating household kitchen waste through anaerobic digestion processes at scale and can be used as a reference forother projects.Anaerobic digestors for municipal/household kitchen waste might be challenging to operate due tofluctuating composition of the feedstock. Ningbos experience shows that large capacity digestors for less homogeneoushousehold kitchen waste can be successful.
P123352 | Nigeria Lagos Second State Development Policy Credit | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/276651577723799247/text/Nigeria-NG-Lagos-State-DPO-II.txt | http://documents.worldbank.org/curated/en/276651577723799247/pdf/Nigeria-NG-Lagos-State-DPO-II.pdf | Three lessons are drawn from the ICR (page 29), with some adaptation. The predecessor to this programmatic series,the stand-alone FLSDPO, drew similar lessons.Sub-national operations should carefully consider the degrees ofdependence of the sub-national government on the central government and define prior actions and results targets that do not undulypenalize the sub-national government for actions not under its control. The fulfillment by Lagos of the programsstate-level fiscal balance and debt ratio targets depended on thestatus of inter-governmental revenue transfers.Sub-national operations should consider the institutional capacity of sub-national agencies to implement reform plans. Insome cases, technical assistance may help upgrade the capacity of state agencies.The state government agencies met theprogram targets for audit and for financial management but missed the outputs for procurement reform.Theprogrammatic approach can help sustain the momentum of a medium-term reform program during changes in political leadership to theextent that they commit the government to a multi-year reform path and keep the policy dialogue active. The programmaticapproach to SLSDPO and TLSDPO, and the close linkbetween the two operations and the FLSDPO, helped ensure that the Banksengagement and dialogue with the state government was ongoing and continuous even as the stateheld its gubernatorial electionin March 2015,prior tothe completion ofSLSDPO and before the approval of TLSDPO. The continuity of thereform program could have been compromised without the programmatic approach, which had securedthe states commitment tothe medium-term initiative before the new electoral cycle.
P123353 | Nigeria Edo State First Development Policy Operation | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2014 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/623721473923615547/text/ICRR14927-P123353-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/623721473923615547/pdf/ICRR14927-P123353-Box396299B-PUBLIC.pdf | This assessment highlights three lessons drawn by the ICR:In subnational projects, success in a reforming a state government may trigger reforms in other states. In this case, success in Lagos encouraged reforms in Edo State.Complementary technical assistance (TA) may be a critical ingredient of development policy operations. Edo Stateâ€™s program benefited from the availability of TA funding from the Edo State SEEFOR project, particularly in establishing the ICT platforms required by the DPO.The lack of timely data will undermine M&E systems. The Edo State DPO education component suffered from indicators that were not being captured easily, as the education IT platform supported by the project had not been fully implemented.Operations supporting public financial management (PFM) reforms would benefit from up-to-date Public Expenditure and Financial Accountability (PEFA) exercises both at inception (in this case, 2012) and closing (2014). Such exercises would provide a richer comparison of achievements than a subset of bare PFM indicators.
P123367 | Savings and Credit Sector Consolidation and Financial Inclusion Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2012 | 2018 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/710091526397044238/text/Mexico-MX-Savings-and-Credit-Sector-Loan.txt | http://documents.worldbank.org/curated/en/710091526397044238/pdf/Mexico-MX-Savings-and-Credit-Sector-Loan.pdf | The ICR provided the following key lessons relevant to projects similar to this one but beyond Mexico- presented here withsomemodifications and editing:Reforms that involve hundreds of heterogeneous institutionswith bottom-up governance require long-term support and commitment. International experience and prior projects (includingthe two previous Bank-projects supporting BANSEFI) show that the need for training ofofficialssuch as in SCEs needs tobepermanently sustainedbecause these small institutions rotate key positions - often through an electionprocess.Efficiency assessments and other feedback mechanisms should be reinforced during projectimplementation to ensure that expenditures in IT components are being directed toward achieving the desired outcomes.Projects that include a technoloqical component should be designed and implemented in line with the changing technologicalenvironment, and be continuously monitored. The changing regulatory requirements and the quick evolution of technology requires anadequate and up-to-date design for the investment in technology, which generally tend to require significant capital investment.The technology needs to be flexible enough to adapt to changing contexts and well aligned with the requirements from the demandside. Most importantly, continuous monitoring during implementation is needed to ensure an efficient use of resources towards theachievement of the development outcomes. For example, in the case of this project, an IT audit was not implemented at the mid-termreview to assess the efficiency and efficacy of the technological platform.Indicators provideuseful insights into the achievement of PDOs but do not necessarily provide a complete account of all outcomes.Projects should include a relevant and measurable set of performance indicators, consistent with the PDOs and the projectsexpected outputs. Timely revisions of monitoring indicators to reflect the evolving realities of the project on the groundweremade in this project.Strong government and industry commitment to a project agendais a precondition for success of Bank projects. In particular, strong coordination among public and private sectorstakeholders is necessary when designing solutions for financial sector development. For this project, the agreement signed with aprivate network of banking agentswas a key factor in significantly increasing the number of correspondent banking agentswithin a short period of time.
P123374 | STP DPL - PUBLIC MANAGEMENT AND GOVERNANCE | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/544951475094024486/text/000020051-20140625230650.txt | http://documents.worldbank.org/curated/en/544951475094024486/pdf/000020051-20140625230650.pdf | IEG concurs with the importance of two of the four lessons in the ICR, which are reworded with different emphasis here:Supervision and implementation support at key moments can be critical for the success of Development Policy Operations (DPOs). But supervision missions tend to coincide with preparation missions for follow-on operations, or in some instances do not occur at all. There is a risk that single-tranche DPOs will be inadequately supervised. Those that do not specify at the outset details of the supervision plan and budget may be less likely to achieve the program objectives.Close attention to potential changes in the external environment is necessary in small island states. DPOs in these countries can yield more consistent results when they integrate mitigation measures against external shocks into the operation, and consider alternative policy and financing approaches should the external environment deteriorate.In addition, IEG adjusts the lesson on M&E:Outcome-oriented, rather than output-oriented, monitoring and evaluation can help guide officials in program implementation as circumstances change. A results and M&E culture is required to achieve this goal. In a low capacity setting, simple monitoring indicators are important to jump-start this culture, coupled with effective outreach.
P123384 | Danang Sustainable City Development Project (SCDP) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099550006282231847/text/P12338403573430690959a0961e9401cd01.txt | http://documents.worldbank.org/curated/en/099550006282231847/pdf/P12338403573430690959a0961e9401cd01.pdf | The ICR presented five lessons from the operations, with some modificationsbelow: Complex publictransport investments may require standalone project financing. In this project, the pioneering BRT-related transportinvestments was a novel, complex solution to traffic congestion and was highly dependent on consumer behavior. This componentallocated with significant investmentswould requirehighly technical expertise, realistic assessment of implementationcapacity, and government commitment to support the implementation of an ambitious design to address traffic congestion. Theinnovation was dependent on swaying consumer behavior and would have required more customized consultations with beneficiaries togain some confidence and a generous comfort level from end users to support innovative solutions. BRTinvestments may failwithoutlong-term political commitment, positive public demand and perception, and strongimplementation capacity.This project and the Hanoi Urban Transport Development Project (P083581) both sought totransform a commuters core mode of conveyancefrom private motorbike to public system. In both cases, the projectproved highly ambitious and targeted consumer behavior and preferences. In this project, consumer preference swayedgovernment commitment to move ahead with planned investments. Corrective measures or design adjustments were introduced based onend user feedback. A strong communication strategy may include aspects of influencingpublic behavior to gain support for anew system. Projects that may require land acquisition in Vietnam would benefit from early localcoordination. In this project, land acquisition and related compensation functions were legislated to local districtauthorities. Cities established Land Fund Development Centers to collect data on persons eligible for resettlement andrehabilitation, approve documentation. Inadequate coordination led to delays. Land acquisition processes and compensation decisionstook more time. Local authorities need to be consulted early to streamline procedures or incorporate design features in investmentsthat would minimize land acquisition or resettlement and rehabilitation of Project Affected Persons.These early consultationsmay foresee choke points in implementation and design measures to overcome delays. AdditionalFinancing may be served by a realistic assessment of physical and financial progress of additional components to befinanced. In this project, the May 2017 AF funds were committed for the Components 1, 2, and 3. However, activities underComponent 2 were ongoing. A detailed assessment of the progress of all the activities under Component 2 may have identified thoseactivities that could proceed without waiting for actions precedent. In this way, premature additional commitments may beavoided. Experienced Project Management Units may continue to benefit from support when implementingtransformative projects. In this project, the city and the PMU were familiar with World Bank policies after previously implementing two Bank-financed projects. However, this project was more complex, involved more than one sector, and was dependent onconsumer behavior to achieve the PDO. The PMU had to implement activities in sectors they had no capacity or experience, resultingin delays. Continuous capacity building, such as hiring consultants, highly technical advisors familiar with local policies andconditions may supplement initial capacity shortcomings. Ongoing capacity support to even an experience PMU would help achieve aprojects objectives.
P123394 | Punjab Health Sector Reform Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/742461585594527598/text/Pakistan-Punjab-Health-Sector-Reform-Project.txt | http://documents.worldbank.org/curated/en/742461585594527598/pdf/Pakistan-Punjab-Health-Sector-Reform-Project.pdf | The ICR (p. 45) offered several useful lessons, including the following adapted by IEG: The engagement andcoordination of development partners canensure that agreed outcomes are pursued consistently. In this case, differentpriorities regarding ME caused misalignment with original project objectives and distance betweenpartners. Intricate project designs, particularly reform-oriented, have a better chance of success if they fully addressthe existing technical capacity, commitment, and challenging contexts. In this case, the Bank team did not consider theimplementation performance experience that severalhealth and nutritionprojects had faced in the past,mostnotablythe lack of capacityin the implementing agency to manage such a complex project. Projects using theDLI modality require that governments ensure adequate allocation of resources to fund DLI activities. In this case, there was nospecific PC1 for the achievement of the DLIs, causing each department to use limited budget from the existing PC1 to meet theobjective. Whena countrys commitment toan original project design changes, timely restructuring canalign a projects PDOs, indicators, inputs, and targets with the new priorities and context. In this case, two elections and anew government led to a change in the focus of the project, canceling some indicators related to institutional strengthening andcreating a new component to improve the delivery of nutrition and family planning services.
P123399 | Niger Safety Net Project | Western and Central Africa | Niger | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/680971621878976538/text/Niger-Niger-Safety-Net-Project.txt | http://documents.worldbank.org/curated/en/680971621878976538/pdf/Niger-Niger-Safety-Net-Project.pdf | The following lessons are drawn from the ICR: In a context of recurring shocks,high poverty rates, and limited resources, multi-year government cash transfers can be effective in mitigating the welfare effectsof climatic shocks and contributing to resilience.In Niger, cash transfers targeting poor households increasedconsumption by about 10%, largely benefitting households affected by droughts. Cash transfers also fostered these householdsresilience by facilitating savings and economicdiversification. Cash-plus programs can yield morecost-effective results for household well-being than cash-only.The project included measures to improve humandevelopment and human capital outcomes (e.g. child health and nutrition, reproductive health, early child stimulation, etc.) andpromote productive inclusion as integral elements of the cash transfer intervention. Project evaluations showed that cash-plus canboost investments and diversify off-farm income-generating activities, leading to significant increases in revenues and profitscompared to cash-only. However, in including cash-plus measures, cultural sensitivities may influence take-up. In thiscase, some beneficiaries perceived some interventions, notably ones relating to parenting, child development, and womensempowerment as foreign to local culture (ICR, para. 38). This points to the need to focus on better understanding culturalbarriers, for instance through participatory research, when seeking cost-effective results.Thesustainability ofcash for work microprojects and their impact on resilience can be enhanced with participatory planning,securing land tenure, and ensuring an adequate time span for effective changes to take place.The project introduceda community-based participatory approach to the design, management, and maintenance of microprojects. Legal documentssecuredland tenure and ensured long-term asset utilization. Likewise, cash for workprojects were extended to two years. Thesemeasures contributed to sustainability of the public assets created through the projects.
P123437 | WBG - PRDP Support IV | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Governance | SPF | DPF | 2012 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/260791475080248996/text/000020051-20140626001708.txt | http://documents.worldbank.org/curated/en/260791475080248996/pdf/000020051-20140626001708.pdf | Lessons from the ICR are all supported: 1. In a high risk, fragile and conflict state context, some challenging reforms in public financial management can be effectively supported by a development policy operation when linked with the government's own medium term economic program, and with complementary TA and other assistance from the Bank and other development partners. 2. Targeted outcomes should be those that the authority has control over, or at least scope for some influence. 3. To ensure good M&E, results need to be measurable with baselines, and causally linked to the actions supported. 4. The technical challenges of implementing reforms need to be anticipated in advance, and actions supported calibrated to ensure they are realistic.
P123447 | Rural Roads Infrastructure Improvement Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/858811534709177053/text/P123447-ICRR.txt | http://documents.worldbank.org/curated/en/858811534709177053/pdf/P123447-ICRR.pdf | The ICR (pages 34-35) draws the following three lessons from the experience of implementing this project, withsome modification of language.(1)Structured prioritization for road investment withgovernment support can promote community involvement, andimprove the impact of a roadproject.The rural roadsprioritized bythe Ministry of Transport and Commerce (MTI) werethosehaving the highest impact in improving access to markets in the productivity zones. Further, MTI promoted thelabor-intensive rural road construction modality through community level involvement.(2) Ruralroads projects can help in integrating gender considerations.This project promoted employment to women through theCommunity Modules of Adoquines (MCAs), which reached 46% of women participation during the project. Women were trained to work asthe president, accountants and in administration. This enabled them to participate in the decision making.The gender-basedsurvey conducted atclosure indicated that this participation increased their income by three or four times compared to levelsbefore the project.With government support, the project protected women in the worksite by taking measures against sexualharassment.(3) Conducting pilot project and capacity building activities can encourage sector wide roadimprovement efforts. This project conducted various pilot activities such as establishinga road network database forinvestment planning and microenterprise for improving the sustainability of the Community Modules of Adoqunies. These were combinedwith capacity building activities aimed at improving the financial sustainability of the Road Maintenance Fund and supporting theimplementing agencys capacity to monitor performance. The combination of these activities besides aiding projectimplementation, encouraged the Government to take a comprehensive approach to road improvement.
P123447 | Rural Roads Infrastructure Improvement Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2018 | 2021 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/267971598636432404/text/Nicaragua-Fourth-Roads-Rehabilitation-and-Maintenance-Project-and-Rural-Roads-Infrastructure-Improvement-Project.txt | http://documents.worldbank.org/curated/en/267971598636432404/pdf/Nicaragua-Fourth-Roads-Rehabilitation-and-Maintenance-Project-and-Rural-Roads-Infrastructure-Improvement-Project.pdf | 3. Lessons 3.1 Rigor in the selection of roads to be financed and continued support for road planning can help countries use resources effectively and create a planning culture. Under both projects, roads were selected to improve access based on technical, economic, and social criteria. The requirement for rigor from all donors (which provided a substantial amount of the road budget) in road selection combined with sustained technical assistance over time helped establish a system and culture of planning in the country. This achievement was facilitated by limited staff turnover at technical levels in the road departments. 3.2 Contract features and strict enforcement appear critical to taking full advantage of performance-based routine maintenance contracts. In Nicaragua, weaknesses in performance standards and incentives, limited understanding of the latter by some microenterprises, and no strict enforcement, among other factors, prevented the contract type from delivering its full potential. The experience showed that contractual requirements need to be set realistically based on available capacity and resources, and strictly enforced. 3.3 Upgrading rural roads to all-weather access needs to be comprehensive. Under these projects, bridges and major drainage elements were not included as part of the civil works due to restrictions in the use of funds by the community-based concrete block surfacing units. Therefore, weaknesses in bridges and drainage elements still prevented people from traveling after heavy rains. 3.4 Providing limited technical assistance support in many areas with little upfront preparation might restrict project results. In both projects, several of the technical assistance activities were not comprehensive and were vaguely defined and prepared. Instead of tackling many issues only superficially, it might have been better to concentrate on a few critical areas with strong governmental buy-in or potential for buyin. In such cases, support could have been more substantial and more thoroughly prepared. 3.5 Close stakeholder involvement and post-completion outreach strategies might increase the usefulness of project-financed studies. In this case, the outcomes of several critical studies have only been partially used. This is a risk for all technical assistance activities; however, for studies that impact or require actions from parties other than the direct contractual counterparts, a close involvement of these parties in study design and implementation and a strategy to implement the proposed recommendations might have increased use of some studies. 3.6 A strong results framework is likely to facilitate results measurement. These projects (i) lacked definitions of concepts, such as access and mobility; (ii) had different indicators in different parts of the Project Appraisal Document, including some without baselines and targets, so no information was collected for several; (iii) used core indicators to measure outcomes not fully attributable to the projects; (iv) lacked intermediate indicators to capture results of technical assistance activities; (v) included baselines and targets to be defined during project implementation; and (vi) had several inadequate outcome indicators. This made results measurement unnecessarily complicated. 1This is the most recent data available on rural poverty. Overall, poverty went down from 29.6 percent in 2014 to 24.9 percent in 2016 (INIDE 2016). This report does not distinguish between urban and rural poverty; according to World Bank staff, the 2016 data have compatibility issues with the 2014 data. Cuesta and Chagalj (2019) point out that poverty fell annually from 2014 to 2017 as a result of positive real per capita growth and declining unemployment rates. For 2018, after a contraction in gross domestic product, rising unemployment, and declining affiliation to social security, the simulations show that the poverty rate went up by 4.8 percent, equaling approximately 300,000 more Nicaraguans in poverty. 2In 2010, labor force participation was 76.2 percent of the working age population and the employment rate was 92.2 percent of the labor force. In 2018, labor force participation went down to 74.6 percent, but the employment rate slightly increased to 93.5 percent (Castro-Leal and Porras-Mendoza 2019). The 2018 crisis might have worsened unemployment (see endnote 1). 3 The additional financing agreement defines eligible emergency as an event that has caused, or is likely to imminently cause, a major adverse economic or social impact to the recipient, associated with a natural or manmade crisis or disaster. 4 Understood by IEG as an enhanced ability to get to or from rural communities and producers. 5The road users survey surveyed 1,670 people, including 490 drivers, 542 pedestrians, 213 producers, and 425 households, in the influence area of four project road sections after their completion. It was not a before-and-after study because of the lack of a baseline. 6This study uses a before-and-after methodology in communities that were part of the Fourth Roads Rehabilitation and Maintenance Project. 7According to the study, the presence of a community-based cobblestone paving project in one's municipality increases the likelihood of having one's principal access point paved by 16.4 percentage points. The finding is robust to inclusion of a rich set of controls, including indicators for presence of other telephone and electric grid infrastructure. Notably, the magnitude of the estimate barely changes after we include these controls. The significance of the 'Empresa' indicator, a dummy indicator for municipalities that had roadbuilding projects constructed by contractors with heavy machinery and not cobblestone surfacing units, is not robust to the inclusion of control variables. 8This is based on the 2018 Ministry of Transport and Infrastructure traffic counts and back of the envelop counts by IEG during the mission. 9 The study argued that because of their stiffness, concrete blocks, if laid over well-stabilized bases, are better suited to carry heavier loads without rutting, which is common for asphalt pavements with heavy traffic. The study compared the deterioration patterns of different pavements and concluded that, with only routine maintenance, an asphalt road would hold steady for approximately 12 years and then begin an accelerated deterioration; whereas, concrete block roads would hold in steady condition for 15 years and then deteriorate slowly. Their design life is 30 to 40 years compared with 20 years for asphalt pavements. 10The core road network is the network that carries most of the traffic. Nicaragua has a total road network of 24,769 kilometers. The maintenance of the noncore network is the responsibility of the municipalities, which receive 20 percent of the fuel surcharge from the Road Maintenance Fund (Fondo de Mantenimiento Vial; FOMAV). IEG did not ascertain if these resources are adequate to maintain the noncore network because this was not part of the project scope. However, two of the three mayors interviewed by IEG mentioned that they used these resources to surface roads, which is a likely indication that they neglect maintenance. 11The maintainable part of the core network are the roads in excellent, good, and regular condition, which in 2019 consisted of 7,198 kilometers. The remaining roads of the core network cannot be brought up to a regular condition through maintenance and need a different type of intervention. 12When Peru shifted to competitive bidding for rural roads maintenance and reduced support to community-based microenterprises, the latter started to disappear and were mainly replaced with small companies. This is likely because the community-based microenterprises were not sufficiently entrepreneurial to participate in biddings or not competitive enough to win bids. Although a switch from community-based maintenance microenterprises to small companies a priori is not a bad and requires less support from the road agency, Peru's road agency staff at the national and municipal levels mentioned that the maintenance quality of small companies was inferior to microenterprises because (i) they do not have the same care for the roads as microenterprise members living along a road on which they depend for access, and (ii) companies need to make profit. In addition, the social spirit of the model of providing people along the road with opportunities to earn money and acquire some entrepreneurial skills was lost. 13 The World Bank helped establish pavement and bridge management systems and create a planning capacity and culture in Nicaragua since the late 1990s. Through the two projects that are the subject of this Project Performance Assessment Report, the World Bank provided financing to (i) update the Highway Design and Maintenance database; (ii) carry out road inventory and condition surveys; (iii) create an economic prioritization tool, consisting of a multicriteria matrix for data-based ratings of road projects in productive areas based on strategic, social, economic, poverty-related, technical, and environmental factors; (iv) acquire data collection equipment; and (v) for training. 14 MTI's road inventory in ArcGIS is for the total national network, not only the core network. 15The study also mentions that the lack of evidence on short-term employment creation might be partially explained by imperfect survey harmonization across survey rounds. 16The selection of the interviewees might have been biased toward people without stable jobs because the latter might be more interested or have time to follow the municipalities' invitation s. 17The operations manual for the community-based concrete block surfacing units does not include age limits for board members, but the requirements are mainly designed to target recently graduated university with no or limited experience. 18The supervision consultant also pointed out that the equipment of the concrete block surfacing units had been transferred to the municipalities, so the microenterprises had to start from zero. Therefore, if the purpose is to give continuity to the concrete block surfacing units, a way should be found to enable them to keep this equipment, possibly by renting or leasing it out. 19This finding applies to the first days of the field visits, when IEG noticed a lack of understanding of the service standards and their evaluation for payment purposes. After commenting on this fact to FOMAV officials, IEG found that the supervision consultants and most microenterprise members interviewed subsequently dominated well the service standards and evaluation procedures. 20The study on financial sustainability and institutional strengthening of FOMAV assessed the technical, financial, organizational, and institutional capacity of FOMAV; assessed its legal framework; prepared a priority five-year maintenance plan; and proposed recommendations with the necessary legal changes to implement them. This was important considering that FOMAV had only recently been fully operationalized and its financial resources were limited.
P123457 | Bangladesh Integrated Agricultural Productivity Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2012 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/425301506353336156/text/ICRR-Disclosable-P123457-09-25-2017-1506353326173.txt | http://documents.worldbank.org/curated/en/425301506353336156/pdf/ICRR-Disclosable-P123457-09-25-2017-1506353326173.pdf | The ICR lists several lessons, of which three key ones are summarized below with adjusted language:Planning and adopting a central mechanism that combines the generation, promotion, and monitoring the useof new technologies into one process is a good way to stimulate effective supervision and coordination among the various projectstakeholders. Such a mechanism can significantly contribute to improving linkages between researchers, extension agents,farmers, and other project stakeholders through coordinated decentralization of activities and strong communityinvolvement.Active target beneficiary involvement in the decision-making on adequate technologies andvarieties for agricultural cultivation are key to encouraging their participation in outreach activitieswith otherfarmers. Farmer group structure, technical guidance from extension agencies, and in-kind project support promoted by aproject can lead to notable spillover effects and a more rapid, sustainable spread of new technologies.Input-Output cards filled out by farmers along with Activity Diaries kept by community facilitators assisting thosefarmers can serve as a self-monitoring tool to achieve greater accountability in ME. With the adequate training ofits users, a unified ME online information system based on these monitoring tools can provide real time project information atall levels (local, regional, central) for better decision-making and monitor the achievement of key milestones.
P123457 | Bangladesh Integrated Agricultural Productivity Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2012 | 2017 | 2024 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099034009262326072/text/SECBOS02013b810ac0ad7a0b7e618134792.txt | http://documents.worldbank.org/curated/en/099034009262326072/pdf/SECBOS02013b810ac0ad7a0b7e618134792.pdf | 3. Lessons 3.1 A design based on participatory demand-driven technology research and adoption programs, with strong community mobilization efforts, attracts strong buy- in from farmers; however, sustainability of the design requires continued monitoring and technical support. The project intervention of involving farmers through a group- based approach (for example, FFSs) encouraged farmersâ€™ participation in technology dissemination and ultimately adoption. One key factor was the projectâ€™s strong emphasis on community mobilization, including the phased process of dissemination 12 and adoption, which helped farmers learn about new technologies from their peers and ultimately brought trust and ownership to project activities among farmers. Although this model was quite successful not only in this project but also in the region, unless sustained effort is put into building the capacity of these farmer organizations, the results achieved by the project may not be sustained after the project is closed. 3.2 Improving links between research and extension and farmers requires strong governance and oversight structures to be in place. This was evident in the ex post review of this project, which found that sustainability is threatened by a lack of public financing of these links to ensure the utility of the outcomes as public goods. The project was implemented by eight different institutions, and IAPP created a platform that established clear roles and responsibilities for each of them and provided a mandate for the institutions to work together. The research institutes (the Bangladesh Agricultural Research Institute, the Bangladesh Rice Research Institute, and the Bangladesh Fisheries Research Institute) that generated new and improved varieties of seed closely coordinated with the extension agencies, such as the Department of Agricultural Extension, the Department of Fisheries, and BADC (which was not always the case before the project). These activities were implemented through effective governance and oversight arrangements that included several committees, which existed at the national, regional, and district levels and which met regularly to guide project management. These mechanisms were critical for improved project planning, monitoring, and coordinating activities of implementing agencies. Following the closure of the project, links have been weak because of insufficient budgets. If links between research and extension become weak, technology development and its adoption at the farm level will also be weak. Therefore, continued resources are needed for such governance structures and links to be sustained. Although private funding of agricultural research exists, often financed by industry groups, there is justification for the allocation of public resources to research-extension-farmer links to achieve a more efficient agricultural sector. For this, there is evidence of broad spillover benefits for a wide range of beneficiaries in many sectors of the economy based on a wealth of research on agricultural technology and rural development (Johnston and Mellor 1961 and numerous subsequent studies). 3.3 Monitoring and evaluation systems need to be built, not only to separately assess the impact of single project interventions but also to track multiple interventions, such as the joint effects of irrigation and improved seed technologies on yield increases similar to those achieved in this project. The projectâ€™s emphasis on seed and irrigation technologies was relevant and addressed key constraints of increasing agricultural productivity among small-scale and marginal farmers. It is obvious that rice will not do well without irrigation. Research from Bangladesh shows that farmers who have irrigation systems tend to be faster adopters of new rice varieties 13 and continue for longer periods of time (Ahmed, Hernandez, and Naher 2016). In the project, extension of technical advice to farmers was provided by the Department of Agricultural Extension, whereas a separate agency with the Ministry of Agricultureâ€” BADCâ€”was mandated to work on irrigation technologies at the farm level. In some areas, irrigation activities were paired with technology dissemination activities. However, in a significant number of cases, the IEG assessment missionâ€™s field visits found that there were separate groups of farmers that the project worked with to support either the adoption of improved rice varieties or irrigation efficiency, but not both. In such cases, it would have been important for the projectâ€™s monitoring and evaluation system to have assessed the impacts of the joint effects of irrigation and improved rice seeds on yield increases. 1The Global Climate Risk Index ranks Bangladesh as the worldâ€™s seventh most affected country over the period of 2000â€“19 (Eckstein, KÃ¼nzel, and SchÃ¤fer 2021). 2The Bangladesh Agricultural Development Corporation is a parastatal agency that has the mandate for multiplication of foundation seeds and production of certified seeds, mainly for seeds of key notified crops. The notified crops are those that have higher government regulation because of their importance for food security. These crops are rice, wheat, potato, jute, and sugarcane. 3The Seed Certification Agency has the legal mandate for seed certification and undertakes variety and quality testing services for seed varieties developed by research institutions before they are released. 4A third-party impact evaluation was conducted at project end by a local consulting firm covering treatment and control group approach. The third-party evaluation surveyed 17,250 farmers at endline (that is, about 5 percent of the Integrated Agricultural Productivity Project sample), including 8,750 crop farmers, 3,000 fish farmers, 3,000 livestock farmers, and 2,500 water users, using a stratified random sampling method; a baseline study was reconstructed using a recall method (World Bank 2017b). 5The Development Impact Evaluation initiative used a randomized controlled trial method based on a panel data set of 1,732 households constructed from three rounds of surveys (baseline in 2012, midline in 2014, and endline in 2015). The assessment covered crop and fisheries activities. 6When rice is grown under continuous flooded soil conditions, it can contribute to the formation of the anoxic environment, leading to the production and emission of methane (Smartt et al. 2016). 7Scaling up of investments in buried pipes was based on information provided by a Bangladesh Agricultural Development Corporation official. 14 8The government provides subsidies to fertilizer, which increased eightfold from mid-2005 to 2015 (World Bank 2016a). 9 The National Agricultural Extension Policy was updated in 2012 with greater focus on providing decentralized and demand-responsive extension services to farmers. The lead agency to implement this policy is the Department of Agricultural Extension. The key principles of the National Agricultural Extension Policy are (i) increasing production (horizontal and vertical) and productivity as a whole; (ii) cost-effective, efficient, decentralized, and demand-responsive extension services; (iii) targeting and mobilizing farmer groups and their federations; (iv) bottom- up planning and implementation; (v) coordinated and integrated extension services through the National Agricultural Extension System; (vi) development of agribusiness and contract farming for export promotion; (vii) adoption to climate change and development of specialized extension service for climatically distressed areas; (viii) broad-based extension support (in-time input support and subsidies, credit, price enhancement, and so on); and (ix) digitalized agricultural extension servicesâ€”e-agriculture (Government of Bangladesh 2012). 10The Global Agriculture and Food Security Program is a multilateral financing platform related to improving food and nutrition security in the worldâ€™s poorest countries. It was established after the 2007â€“08 food price crisis. The seedlings of this variety can tolerate salinity of 12â€“14 decisiemens per meter for three 11 weeks and 6 decisiemens per meter for a whole cropping season. 12Increased soil and water salinity because of sea level rise in Bangladesh is expected to result in a 15.6 percent yield reduction in high-yielding rice varieties by 2050 (World Bank 2019). 13Following the closure of the project, the umbrella organization (Sara Bangla Krishok Jote) was selected in October 2016 to receive additional grants from the Global Agriculture and Food Security Program to further support institutional and technical capacity. 14Fish farmers interviewed did not tend to have marketing challenges. There was high demand for fish, which was either sold in local markets or to traders who collected fish from the farms. As of 2013, there were approximately 200 seed companies with 17,000 registered and 50,000 15 mobile seed vendors with a market value of over $125 million (Genoni et al. 2021). In 2021â€“22, the total demand for crop seeds was 1,254,836 metric tons, but supply of crop seeds 16 was 405,939 metric tons (USAID 2023). 17The World Bank report (Genoni et al. 2021) states that the fisheries subsector in Bangladesh is considered a diversification success story. This success has been due to the efforts of the private sector and a domestic market where 90 percent of farmed fish (excluding shrimp) are sold. Enabling factors are related to expansion of rural road networks, rising affordability, and access to new technology. The domestic market has been the main trigger behind aquaculture transformation. 15 18The Missing Middle Initiative was launched in 2016 as a pilot project of the Global Agriculture and Food Security Program, which aimed to directly support producer organizations. Bangladesh was one of the first countries to receive a grant, and the project is under implementation, which helps facilitate access to finance and complementary services (extension, capacity building, technology, or access to markets) to smallholder farmers through their producer organizations. 16
P123480 | LA-Poverty Reduction Fund II | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/852891516804702122/text/Lao-Peoples-Democratic-Republic-LA-Poverty-Reduction-Fund-II.txt | http://documents.worldbank.org/curated/en/852891516804702122/pdf/Lao-Peoples-Democratic-Republic-LA-Poverty-Reduction-Fund-II.pdf | The ICR (p. 25-26) included several lessons:1 . Filling local capacity gaps through external experts andspecialized studies can be useful for project implementation and longer-term capacity building. In this project,relatively weak analytical and supervision capacity was addressed through hiring consultants, who were able to support criticalareas such as ME, community participation, nutrition, and engineering, through their expertise allowing to move projectimplementation forward while building local capacity at the same time.2 . Developing detailed step-by stepprocedures for critical project areas can help to simplify and smoothen implementation. In this project, the ProjectOperation Manual was kept simple and was continuously updated while support was provided on an ongoing basis. This had a positiveimpact on the projects implementation and quality.3. Supporting sub-projects in conducting Operations Maintenance (OM) activities, especially to preserve and improve rural access roads is critical for their longer-termsustainability. In this project, villages were allowed to use part of the sub-grants for OM activities and supportedto establish rural Road Maintenance Groups in order to preserve the investments made under this project. The ICR (p. 26) statesthat most PRF sub-projects were functional after four to six years if operation and OM committees remained active exceptroads. Therefore, this project tried to address this challenge accordingly.
P123503 | Mali Emergency Education For All Project | Western and Central Africa | Mali | IDA | FCS | Human Development | Education | RETF | IPF | 2013 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/146251545142365481/text/Mali-ML-Emergency-Education-for-All-Project.txt | http://documents.worldbank.org/curated/en/146251545142365481/pdf/Mali-ML-Emergency-Education-for-All-Project.pdf | Lessons drawn from the ICR (pages 29-30) and adapted by IEG: Local participation,in specific measures, can be effectively utilized in emergency contexts to facilitate implementation. In the case of thisproject, selection criteria in tender documents were relaxed to allow for bids by local firms, which was valuable in conflict areaswhere strong understanding of the local context was critical to completing construction activities. Local communitiesandnon-governmental organizationswere also used for third party monitoring in areas where field visits and directsupervision by the project team was difficult. Maintaining policy dialogue in a crisis context can build trust with thegovernment and also catalyze resumption of engagement by other donors. In the case of this project, the Bank had continuedengagement in the education sector even while other donors had withdrawn,facilitating subsequent implementation of anemergency operation.
P123505 | Fiscal Risk Management Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2014 | 2015 | ICRR | Less than 10 million |  | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/737051475788615743/text/000180307-20150409085919.txt | http://documents.worldbank.org/curated/en/737051475788615743/pdf/000180307-20150409085919.pdf | The NCO drew well-considered lessons from the experience of the operation, including: Implementation may suffer when key institutions such as the entity in charge of loan implementation and the financial agent for the loan are not firmly identified during preparation, so that they cannot be swiftly put in place after loan signing. If the Bank pays insufficient attention to fully ascertaining the countryâ€™s public debt rules and disseminating the Bank's instruments to stakeholders, it may find its lending instruments not fully consistent with those rules. Specifically, rules or interpretations that borrowing should be earmarked to specific expenditures may impede development policy lending, as DPLs provide general budget support, not financing of specific expenditures. The Bankâ€™s experience in Mexico shows that loans prepared well in advance of elections had a good implementation record. Conversely, DPLs prepared close to election dates, as in the case of the Fiscal Risk Management Operation, are prone to disruptions following changes in government teams upon elections. This suggests that DPO operations may need to be synchronized with the political cycle to minimize disruptions and reversal in government commitments. A further lesson from the experience of this operation is that an emphasis on Bank knowledge services may be particularly relevant for client countries with ample access to alternative sources of finance.
P123513 | Third National Urban Water Sector Reform Project | Western and Central Africa | Nigeria | Blend | FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099205105232214055/text/P1235130f0fbe50e30b1b20bc74016abd55.txt | http://documents.worldbank.org/curated/en/099205105232214055/pdf/P1235130f0fbe50e30b1b20bc74016abd55.pdf | The ICR (pages 35-36) identifiedseveral lessons, of which the main ones are presented below with paraphrasing fromIEG:Implementation readiness needs to be ensured to achieve early service improvements and thereby create a betterenabling environment for achieving reforms. In this project, investments were not ready for implementation, thus resultingin an imbalance among the key partners between focusing on either investments or reforms. Had the benefits from improved servicesbeen delivered much earlier, there would have been a more conducive framework for productive dialogue with the incumbent and newgovernments on the necessary policy, institutional, and regulatory reforms. The state governments may have been more willing andable to take the necessary actions, had the communities already been benefitting from service delivery.Sector reforms must be supported by efforts to sensitize stakeholders and a better understanding of thelocal political economy and governance context. Although the importance of political economy and governance issueswere considered, and mitigation measure were proposed, the Banks intensive involvement and effectiveness were lacking.Special efforts, including from Bank management, would have contributed to deepening the project teams understanding of theevolving political and governance dynamics at the sector and country levels. There was initially strong leadership duringpreparation and implementation, hence some reform momentum may have been achieved.However, the continued heavy reliance onsuch leadership proved risky, given the major changes after elections or administrative reshuffling. Finally, there was clearly aneed for wider and deeper consultations to sensitize stakeholders on reforms.A long-term programmatic engagement(beyond a single project) and the right lending instrument are required to achieve major institutional changes and deeperreforms. The project promised significant reforms such as utility autonomy, efficiency, and governance and regulatoryimprovements. Achieving reforms requires the prior delivery of services, which would build credibility, and follow an iterativeprocess (particularly for regulatory reforms - these outcomes require long-term programmatic engagement with the federal and stategovernments, sustained partnerships with stakeholders (civil society, development partners, government officials), strategiccommunication, and agility to build on evolving opportunities. Traditional investment project finance may not be the rightinstrument for such a long-term engagement. A programmatic approach through a development policy lending or Program-for-Resultsfinancing would have been a better choice, which allows states to graduate based on performance and creates an incentive through alonger time frame.
P123531 | Health Sustainable Development Goals Program-for-Results | Eastern and Southern Africa | Ethiopia | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | PforR | 2013 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041923195522835/text/P1235310c601d00940959307b7687b4eccf.txt | http://documents.worldbank.org/curated/en/099041923195522835/pdf/P1235310c601d00940959307b7687b4eccf.pdf | The ICR (pp. 31-33) offered severallessons and recommendations, including the following lessons re-stated by IEGReview:The challenging context in countries with large disparities in access and persistent gaps underscoresthe importance of sustained, long-term engagement in human development. While Ethiopia made steady and impressive progressin health advancements, much more remains to be done to have a major and sustained impact on maternal and child health. A follow-onoperation is ongoing. Designing interventions that are appropriate for different regions (agrarian, nomadic, urban) will take time,including for a thorough understanding of what works and how different regions can be incentivized to revamp their health services.The large number of internally displaced people and the complexity of conflict after-effects require specialized and well-tailoredsupport to restore and further advance maternal and child health services.A Program for Results can becomplemented by Investment Project Financing components to provide specific technical support, capacity building, and targetedstrengthening. To bolster capacity, the World Bank and development partners provided hands-on-support on a wide range ofissues, such as for civil registration, vital statistics, fiduciary capacity of the SDG Performance Fund, National NutritionProgram, health financing and fiduciary systems in the health sector.The consistent availability of reliableinformation facilitates tracking of program progress, performance assessment, identification of challenges, and sustenance of donorharmonization. Harmonized donor support facilitated the production of regular Demographic and Health Surveys; annualfacility readiness surveys; assessment of Community-Based Health Insurance; and nutrition surveys. The timely availability of dataenabled the verification of DLIs. Donor support also contributed to an enhanced Health Management Information System.
P123567 | Niger Second Emergency Food Security Support Project | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2011 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/118541468188670039/text/ICRR14809-P123567-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/118541468188670039/pdf/ICRR14809-P123567-Box393228B-PUBLIC.pdf | The ICR included Seven lessons, the following are emphasized with some adaptation of language:Collaboration and coordination with other donors and working with strong, established NGO partners (such as veterinarians without borders) are key elements for success. Coordination and collaboration with other donors at the design phase helped the Project to narrow its focus geographically and to incorporate best practices (for example on targeting), leading to a simpler project with broad-reaching impacts. Government leadership was also critical to the success of this coordination.Emergency operations should focus on relief aspects as their first priority. The projectâ€™s experience shows that emergency operations are most effective when they prioritize actions oriented on the immediate restoration of productive assets for food-insecure rural households, instead of trying to tackle the deep causes of the recurrent food crisis (such as irrigation systems). In low capacity, fragile and conflict-affected countries, infrastructure projects require patience, and enough implementation time. While working with an established PIU and basing activities on pre-existing designs helped to move the project forward from day one, the project experience demonstrated that implementation time (2.5 years) was short given the significant infrastructure works undertaken by the Project.
P123673 | SENEGAL Tertiary Education Governance and Financing For Results | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/342401580232897003/text/Senegal-SN-Tertiary-Educ-for-Results-FY11.txt | http://documents.worldbank.org/curated/en/342401580232897003/pdf/Senegal-SN-Tertiary-Educ-for-Results-FY11.pdf | The ICR (pp. 35-37) provided lessons, adapted here by IEG: Effective accreditation mechanisms areessential for ensuring quality ofhigher educationprograms and institutions. In this project, the NQAAscapacity was strengthened, allowing it to evolve into an effective accreditation body. Also, NQAA has been open to having itsperformance evaluated by an external entity and has collaborated with other regional accreditation entities to continue to buildcapacity and to learn how its own processes and procedures can be strengthened. Performance-based contracts are auseful tool to improve results and ensure transparency and monitoring of HEIs. In this project, PBCs were a useful toolfor HEIs to negotiate annual budgets based on targets and results, fostering the dialogue between the institutions and the Ministryof Education and Finance. Buy-in on all different levels in the higher education sector is important to ensure asuccessful reform process. In this project, university rectors were on boardwith support forproposedreformsat their universities. This had a positive impact on project implementation and will support the sustainability ofproject outcomes.
P123679 | GM-Budget Support -DPL (First in the series) | Western and Central Africa | Gambia, The | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/909361473934514382/text/ICRR14948-P123679-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/909361473934514382/pdf/ICRR14948-P123679-Box396299B-PUBLIC.pdf | IEG agrees with the four lessons identified in the ICR, and rephrased below: (i) Launching a programmatic series in an unstable macroeconomic and political environment with weak governance is risky and requires important mitigation efforts. The lesson? from this experience is not to postpone the program series, but to be aware of the high risks associated with the operation, to identify adequate mitigation measures, and to be prepared to change course if necessary, as was done in this case. (ii) To be successful, a DPO needs to focus on policy areas and reform measures where there is an ongoing policy dialogue and for which the Borrower has a clear reform action plan. The operation was successful where the DPO supported actions that maximized the synergies with the Bank's investment portfolio in telecommunications, education and the IFMIS. Results were limited with the energy sector actions, because the Bank did not have a complementary IDA investment project.(iii) Stability in the composition of Government teams has major impact on the achievement of development objectives in policy lending. Capacity building and economic adjustment efforts tend to succeed when key performing civil servants are retained in position for a reasonable period of time, and when there is institutional stability. For instance, senior management in the education sector has remained relatively intact for many years, and this likely contributed to more robust outcomes than in other areas. On the contrary, the more senior levels of the Gambian civil service underwent a high turnover of staff as well as frequent organizational reforms that have weakened development progress and the sustainability of achieved reforms.(iv) The design of outcome indicators needs to adequately capture the policy efforts and the reach? of the reforms supported by the operation. Setting properly formulated output indicators is critical in assessing the efficacy of an operation, and using quantitative targets that measure outputs instead of desired outcomes cloud the performance of the development policy operation.
P123685 | GW-Economic Governance Reform Grant III (EGRG 3) | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/955591474505723839/text/000020051-20140625193230.txt | http://documents.worldbank.org/curated/en/955591474505723839/pdf/000020051-20140625193230.pdf | Lessons learned from the ICR and from IEG's review are two-fold:(i) The main lesson from this operation is that progress in economic governance reforms can be achieved in post-conflict environments, if the timing and the incentives are appropriate. Performance achieved under this operation derives in part from the progress made under the two previous programmatic operations.(ii) Reforms favoring a private sector-led growth take more time to produce results, because domestic and foreign investment take more time to materialize, even when doing business measures have been implemented.
P123706 | Improving Maternal and Child Health through Integrated Social Services | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/927731631217666470/text/Haiti-HT-Improving-Maternal-and-Child-Health.txt | http://documents.worldbank.org/curated/en/927731631217666470/pdf/Haiti-HT-Improving-Maternal-and-Child-Health.pdf | The ICR (p. 33-24) included lessons learned which were adapted by IEG: Carefully assessing potentialimplementing agencies during project identification and preparation is critical to ensure institutional support and capacitythroughout implementation. This project experienced implementation issues due to the challenges of different entitiesproviding and reporting on health services. Especially the institutional support by the MSPP and the institutional capacity of FAESwere underestimated. RBF has the ability to change the behavior of health care providers. Achievementsunder this project show that incentives can support the prioritization of preventative MCH care services and the homogenization ofclinical and reporting protocols in a highly decentralized and diverse landscape of health care services. Theimplementation of an RBF mechanism requires substantial Technical Assistance due to the substantial organizational changes beingintroduced. In this project, the Bank provided TA at both the service provider level and MSPP level to support thedevelopment of a strong stewardship capacity.
P123729 | Jiangxi Shangrao Sanqingshan Airport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/963701569871614521/text/China-CN-Shangrao-Sanqingshan-Airport-Project.txt | http://documents.worldbank.org/curated/en/963701569871614521/pdf/China-CN-Shangrao-Sanqingshan-Airport-Project.pdf | Lessons identified in the ICR are summarized and rephrased below: Technical Assistance reports can playan important role in dissemination of the benefits of theGreen Airport approach for future airport expansion in China andaround the world.The Technical Assistance reportssupported under the Project not only documented the gooddesign, implementation and operationalapproaches that the airport conducted for carbon reduction, but also provided severalrecommendationsto improve performance.The ME system also played a key role in incentivizing the local implementingagencies to obtain the EDGE certification. A public-private partnership operation model can improvethe efficacy of the airport operation. In this project,SMG signed an operation concession agreement withtheJiangxi Airport Group (JAG) to operate the Shangrao airport. This greatly improved the efficacy of operationsandmanagement. Use of new technologies can be used to enhance project management andsupervision.New technologies adopted during project implementation, including theuse of an unmanned aerialvehicle mounted with camera for supervision, and red sandstone constructionduring the rainy season, greatly improved projectmanagement and operational efficiency, and reducedproject costs. Early procurement planning,including theidentification of Bank financed activities, as well as advanced contracting can facilitatesuccessfulimplementation. The project experience demonstrates that the timely award of the most important airfieldworkscontract, which was procured through International Competitive Bidding using prequalification, was keytosuccessful implementation
P123760 | Mexico Forests and Climate Change Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/860551543249938935/text/Mexico-MX-Forests-and-Climate-Change-SIL.txt | http://documents.worldbank.org/curated/en/860551543249938935/pdf/Mexico-MX-Forests-and-Climate-Change-SIL.pdf | The ICR (p. 33-34) includes several lessons learned which were modified byIEG: Strengthening inter-institutional linkages is critical to ensure long-termsustainability and inclusion of different areas of a sector. In this project key public agencies in the rural sectorsuch as CONAFOR and SAGARPA signed an agreement to improve inter-institutional coordination in forest landscapes and implementjoint activities regarding REDD+, restoration, integrated watershed management, development of PES schemes, and improved monitoringsystems. Ensuring the inclusion of all key public agencies of the rural sector allowed to address underlying factors ofdeforestation and degradation. Making different sources of financing available allows for a broader engagement inthe sector and addressing several aspects of a sector. This project benefited from the Banks financing aswell as two Trust Funds, allowing for engagement in different areas such as piloting an innovative approach at the territoriallevel that fostered multi-sectoral coordination or providing a strategic platform for engagements on sustainable and low-carbonrural development.
P123820 | Remote Rural Communities Development Project | South Asia | Bhutan | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/303111561752340328/text/Bhutan-BT-Remote-Rural-Communities-Development.txt | http://documents.worldbank.org/curated/en/303111561752340328/pdf/Bhutan-BT-Remote-Rural-Communities-Development.pdf | A lack of designated project, unit, and team management and implementation capacity can significantly affect projectoutcomes. The project implementation was affected by the lack of a dedicated project management team, frequent staffturnovers, and weak commitment by designated staff due to heavy work overload and lack of incentives. The implementing entityneeded to ensure that there was a dedicated project management unit staffed with full-time staff for key positions, includingproject management, procurement, financial management, and ME specialists. The World Bank could help to ensure this throughcovenants and supervision.Supplementinghard investments withsoft investments is critical for achievingdesired development outcomes, particularly where there is weak institutional capacity at the district and local levels.The project had limited scope for soft investments, as the government was unwilling to draw on credit/loan resources. TheBanks expectation that additional grants could be mobilized for this purpose also failed to materialize. The lack ofsoft investments hampered the development outcome and the efficiency of the project.Building afunctional ME system is critical to monitoring progress, identifying issues, and assessing outcomes and results and makingmid-course modifications. A lack of availability of accurate ME data significantly affected project implementationand constrained timely identification of the key issues faced by beneficiaries. Project evaluation was also hindered by thescattered, irregular, and incomplete ME data. Selection of accurately defined outcome and results indicators, as well asrelevant proxies, is critical for accurately measuring results and impacts, and for effective implementation of MEactivities.Close, frequent, and consistent Bank supervision can detect problems early on and work with the clientto identify solutions. For example, close supervision would have helped identify semi-defunct irrigation systems early on,allowing for immediate repairs and avoiding unplanned but important changes in project activities (e.g. extra installation ofhigh-efficiency irrigation), undertaken in order to maximize attainment of projectobjectives.Ex-ante market assessment must underpinBank-financed operations that seek to increase market access or market values. Marketissues, as evidenced by the project, cannot be addressed through a selection criterion that requires having existing marketlinkages. That is, selection of groups with existing market access does not guarantee that they will not (or do not) also facemarket access issues. Farmers should also have skin in the game for viability and sustainability of investments inproductive assets.Additional lesson from IEG:Assumptions in the Results Chain warrant very closeattention by local implementing partners, prior to implementation, to minimize design and implementation issues. Theassumptions set out in the results chain were critical to the success of the project, yet almost all did not hold, and underlaymany of the challenges the project faced. Given the high percentage of failed assumptions, some mitigation of project challengesmay have been possible upon closer and early examination of these assumptions.
P123828 | Second Rural Transport Improvement Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR included five lessons. The following three are emphasized with some adaptation oflanguage:1.Harmonizing and mainstreaminginstitutional initiatives within a broader, comprehensive assetmanagement strategy is important to address the remaining gaps towards sustainable road maintenance.Accessibilityimprovement and institutional strengthening for sustainable road maintenance are important objectives, but downstream focus shouldshift to asset management and resilience of rural infrastructure. RTIP 2 has helped LGED acquire the tools, resources, andexpertise to deliver large-scale capital investment projects for road improvement and maintenance.It is also important toensure climate resilience of the rural infrastructure through a data-driven, context specific and flexibleapproach.Similarly, a long-term approach is needed to embed climate-proofing in the entire process of planning, datacollection, data management, design, material selection, impact analysis, and revision of the approach based on changes incircumstances.2. Implementing infrastructure projects in monsoon areas need to carefully sequence projectactivitiesto award the contracts after the monsoon or just before the dry season in order to avoid implementationdelays.The project experience showed thatthe contractors could not mobilize or advance work during the rainyseason for the contracts awarded right before the monsoon season. Such contracts generally took an additional year for the works tobe completed.3. Future improvement of new roads need to be carefully studied to ensure that road aspects meet theintended use. Such studies can help make the designs context specific and ensure higher performance of new/rehabilitatedstructures for future roads.TheLGEDs Road Standard did not consider vehicle axle load and type, which led to thedesigns not being customized. On the other hand, maintenance roads were designed without considering the remaining life of thepavement or the remaining strength of the existing road materials, which led to early damage of maintained roads. It would bebetter if the existing pavements are dismantled altogether, and new construction includes widening of embankments. Also pavementpreservation should be considered in areas where pavement damage is common due to environmental factors.
P123845 | Afghanistan Capacity Building for Results Facility (CBR) | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/730921587144073224/text/Afghanistan-AF-ARTF-CB-for-Results-Facility.txt | http://documents.worldbank.org/curated/en/730921587144073224/pdf/Afghanistan-AF-ARTF-CB-for-Results-Facility.pdf | The following are key lessons deriving from the ICR: Designing a project based on incorrect or incompleteassumptions can negatively influence project implementation and outcomes. This projectsinitial design misreadthe level of political commitment. The tier system was overly complex and required commitment from high-level officials to see itthrough. At the time, the priority CBR ministries were led by acting ministers, which led to lack of commitment and ownership ofthe project. In addition, overestimating the ministries capacity to absorb and manage the project jeopardized projectoutcomes. Unclearterms of referencefor multipleimplementing agenciescan complicatecoordination and unravel planned synergies. The dual projectimplementation structure with two PSUs MoF andIARCSC resulted in lack of coordination and leadership, a problem that was exacerbated bylimited capacity. Strongimplementing partners with adequate authority and clear rolesenhance implementation success. Third-partyverification is critical in ensuring the transparency and quality of recruitment, particularly in fragile settings.Third-party agencies can independently carry out robust ex-ante quality assurance and shield against politicalintervention. A demand-driven approach can encourage ad hoc requests, which can negatively affect projectresults. This projects recruitment allocation allowedit to meet many important ad hoc needs across government.However, it ultimately contributed tolimited impact across too manyLMAs.
P123879 | Subnational Institutional Strengthening | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2014 | 2024 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | Strategic prioritization and early assessment of local capacities are important for effective projectimplementation. Integrating foundational elements, such as updated cartography, into the project design from the outset isessential to prevent delays in project implementation and cost overruns. Establishing clear selection criteria for beneficiarymunicipalities is vital to shield the process from political interference and ensure that interventions are tailored to localneeds. To accommodate the diverse capacities and challenges of municipalities across the country, particularly those affected byarmed conflict and natural hazards, it is crucial to simplify planning instruments and adopt flexible, fit-for-purpose schemes.Building local capacity should remain a priority, with ongoing support from the central government through training, virtual tools,and targeted assistance.
P123900 | Productive Social Safety Net Project | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2020 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/144051593453523607/text/Guinea-GN-Productive-Social-Safety-Net-Project.txt | http://documents.worldbank.org/curated/en/144051593453523607/pdf/Guinea-GN-Productive-Social-Safety-Net-Project.pdf | The following lessons are drawn from the ICR:Projects in low capacity environments are best keptsimple. With a complex design, project implementation faced institutional challenges that could havebeen reduced with greater attention to administrative capacity and the pacing in the introduction of new systems. In theproject, that pacing was only introduced as challenges were encountered. While the urgency of implementation may have beenwell-founded, the reality on the ground ultimately sets the pace.Continuity in Bank teams canfacilitate implementation. Closing of the project was delayed by two years. While the delay may reflect a morerealistic timetable for the establishment of a social protection strategy or a functioning safety net system, a high turn-over ofteam leaders is also likely to have contributed, and the ICR (p. 33) points to the possibility of consequent misunderstandings andmodifications as factors contributing to slowing down implementation.
P123922 | Integrated Disaster and Land Management Project | Western and Central Africa | Togo | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2012 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/727901528139387981/text/Togo-TG-Integrated-Disaster-and-Land-Mgt.txt | http://documents.worldbank.org/curated/en/727901528139387981/pdf/Togo-TG-Integrated-Disaster-and-Land-Mgt.pdf | The following two lessons were derived from the ICR:1. A community-based,participatory combined approach to disaster risk-reduction and sustainable land management is critical to reducing floodvulnerability. For example, the identification, implementation, and sustainability of the subprojects by the communityitself was an important entry point to mobilize communities around solving tangible problems, while improving their well-being andlivelihood opportunities. As a result, the combined disaster risk-reduction and sustainable land management practices wereappreciated by the communities (ICR, para 114).2. Efficiency analysis duringproject implementation might improve sustainability and scale-up of activities. For example, the process of preparing theefficiency analysis at the time of completion suggested the need for a more structured and systemic use of financial and economicdata during the project implementation. Cost-benefit analysis and the use of comparative data can support decision-makingprocess to maintain or abandon an activity during the implementation process (ICR, para 120).The following lessonwas derived by IEG:3. Sustainability of community projects needs to be planned from thebeginning. For example, in Togo a few months after the operation was completed, an urban drainage canal started to fillwith garbage and used water from neighboring houses or silting of water reservoirs. As a result, sustainability efforts wereplanned for and implemented. Some of these efforts included: establishing a local maintenance community, income-generatingactivities to support maintenance costs, and a process for continuous dialogue with local authorities and technical watersanitation and forest services to supervise any potential infrastructure to the canal after project completion (ICR, para 38).
P123923 | RUSSIA FOREST FIRE RESPONSE PROJECT | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/839831585691369922/text/Russian-Federation-FOREST-FIRE-RESPONSE.txt | http://documents.worldbank.org/curated/en/839831585691369922/pdf/Russian-Federation-FOREST-FIRE-RESPONSE.pdf | The ICR (p. 30-31) included several lessons learned which were adapted by IEG: In order to ensure aneffective forest fire response a mix of policy, institutional support and investments in the capacity on the ground isneeded. Even though the design of this project entailed all these aspects, the activities were mainly reduced toinvestments in technical capacity and equipment. This resulted in limited project outcomes and an ongoing threat of catastrophicfires in the selected regions. Overly complex implementation arrangements with multiple implementing agenciesworking across several regions easily experience delays and lack of clarity in terms of responsibilities for end results.In this project, two different implementing agencies worked across five regions and 25 Protected Areas resulting in delays and lackof clarity over responsibility over end results and limited oversight from the implementing agencies leadership. Allthese aspects had a negative impact on project outcomes. A combination of engaging with the private sector,cooperating across regions, and introducing technologies would allow for an effective forest sector development. Theseproject regions benefitted from as systematic planning approach to solving complex issues of forest fire prevention, detection, andsuppression through exposure to international expertise, innovative ideas, and technologies which otherwise would not be availablethrough the normal budgeting processes.
P123933 | Capturing Coral Reef and Related Ecosystem Services (CCRES) | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/773381574283885435/text/Philippines-CCRES.txt | http://documents.worldbank.org/curated/en/773381574283885435/pdf/Philippines-CCRES.pdf | The ICR presented three lessons, two of which summarized below are of broader applicability:1. The projectillustratesthat multi-partner, multi-country, multi-stakeholder projects are complex to design and challenging toimplement. This is particularly the case for TA projects with limited financial resources. Associated lessonswerethat: (i) project design should be realistic in terms of what can be achieved during its planned implementationperiod and (ii) World Bank implementation support needsto be gauged accordingly. In the present case, having adedicated andexperienced implementing agency helped to overcome the challenges posed by these complexities.2.Both top-down and bottom-up approaches are necessary even in small TA projects such as this one; while the latter may bewelcomed by local stakeholders but may be insufficient to achieve longer-term institutionalization. The correspondingrecommendation was that projects such as the present one should continue to engage with local communities but also target uptakemeasures with provincial and national governments to aid institutionalization and demonstrate the positive impacts of theinnovative models developed.The grantees completion report adds several other operationally relevant lessons based onthe project experience (ICR, Annex 5, pg. 54), specifically that it is essential to (i) dedicate more timeat the beginning of the project to develop a clear activity plan with concrete deliverables per year; (ii) establish feedbackmechanisms (surveys) earlier on in the project to improve tracking; and (iii) address uptake strategies at the beginning of theproject by bringing together experts in translation of research and end users to discuss and develop a roll-out plan. Hadthese lessons been followed, the project might have been even more efficient and effective.
P123960 | Social Assistance System Strengthening Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/677981611585572950/text/Vietnam-VN-Social-Assistance-System-Strengthenin.txt | http://documents.worldbank.org/curated/en/677981611585572950/pdf/Vietnam-VN-Social-Assistance-System-Strengthenin.pdf | The ICR (p. 36-38) included usefullessons learnedthat were adapted by IEG: Consulting andcollaborating with various stakeholders involved in project implementation is critical to ensure buy-in, especially when it comesto introducing major changes. In this project, the project team worked with stakeholders at the provincial andcentral levels to introduce a new payment modality, which replaced payment by local staff with an independent payment agency(VNPost). However, the project team did not sufficiently address the opposing views by local staff when it came to supportingout-of-school children, resulting in implementation challenges, and it did not anticipate institutional and procedural challengesinvolved in program consolidation. Without sufficient attention to building capacity at the local and centrallevels during project preparation and developing a plan to maintain and reward trained and skilled staff, project implementationand the sustainability of project outcomes are likely to suffer. In this project, government staff did not have sufficientcapacity to operationalize the new MIS during the first year of project implementation, resulting in implementationdelays. When government programs are being reformed, proactive adjustments in resource allocation and staffingwill typically be necessary to address temporary disruptions. This project experienced a high staff turnover and reductionat the local level because of government administration reform resulting in local staff having to take on additional tasks andcarrying out project activities such as learning to use the new system and updating data into the system. This resulted inirregular updates of the database.
P123961 | Vietnam Road Asset Management Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099031224094538560/text/P123961178c7ca0771b4c519484c8e2d00d.txt | http://documents.worldbank.org/curated/en/099031224094538560/pdf/P123961178c7ca0771b4c519484c8e2d00d.pdf | The following lessons were derived from the ICR with some modifications to the language by IEG: Technicalinnovations may enhance implementing entities institutional capacity to perform beyond their traditional roles andadministrative remit. The decision to acquire the Road Asset Management System/Road Asset Management Frameworkstrengthened the institutional capacity of the Ministry of Transport and the Department for Roads Viet Nam, which made use ofreliable data that guided them to use data to manage the Vietnam Road network effectively and efficiently at the national,provincial and district levels. Public and private sector partnerships can be effectively utilized to overcomepublic sector inertia and institutional lethargy. By introducing performance-based contracts (PBC), the project empoweredthe private sector to participate in the road maintenance scheme of the Government of Vietnam. This invariably brought efficiencygains that resulted in better road maintenance, which would go a long way in improving the safety of road users. PBCs can ensurethe successful implementation and sustainability of road maintenance. If careful analysis and planning precedesthe implementation of new activities in a well performing project, the additional activities may have greater potential forsuccess. In the context of this project, the additional activities were ambitious, considering the capacity of theimplementing agency, the financial constraints of the PPC, and thetime left for implementation without extension. Whendiscussing additional activities, in-depth assessment, selectivity, clearly defined activities with timeline and risk mitigationmeasures were factored in to provide a clear view of what would be possible to accomplish prior to projectclosing.
P123974 | Haiti Business Development and Investment Project | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2013 | 2022 | 2024 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099072723202512004/text/P12397405f06ed01b099ab0556242dc7318.txt | http://documents.worldbank.org/curated/en/099072723202512004/pdf/P12397405f06ed01b099ab0556242dc7318.pdf | Three lessons are drawn from the ICR, with some adaptation.The development of value chains offers a viableapproach to a business development and investment facilitation program anchored on MSMEs. This restructured projecttargeted sectors in which the economy had a comparative advantage: in agriculture coffee, cocoa, avocado, mango, honey, andvetiver oil; and in light manufacturing apparel. It targeted markets in which countries had preferential tradearrangements the U.S., Canada, and Europe. And it picked three interventions that would be crucial to help MSMEsovercomemarket and coordination failures in their drive to linkto value chains and accessforeign marketsbusiness development services, logistics services, and pooled matching grants. The successor operation, theHaiti Private Sector Jobs and Economic Transformation Project will scale up this strategy. According to the ICR, the Bank hassince adopted this approach in similar industrial support and value chain competitiveness projects in Belarus, Cote dIvoire,Croatia, the Dominican Republic, Egypt, Jordan, Peru, and Tunisia.The Immediate Response Mechanism shouldhelpfirms continue or restart business operations during disasters, but planners need to be aware of theoperating assumptions for this emergency measure to be effective. In this project,the scheme uptake was only53 percent among eligible beneficiaries, bogged down by the high administrative cost ofdelivering emergency assistance duringa crisis and the poor state of the electronic and mobile payments system in Haiti. In countries where the electronic andmobile payments system was relatively more developed and more widely used, the uptake was 70 percent. InaBanksocial protection project in Haiti, the uptake by eligible beneficiaries was 85 percent, but using cash payments, according to theICR.The in-country presence of task teams is beneficial in FCV country settings where institutional capacity isweak, and project experience is limited. In this project, the field presence of the task team leader in Haiti duringthe early phase of project implementation helped the Bank understand the rapidly changing country context for the operation.The field presence of the task team leader also facilitated the second restructuring of the project, which shifted the focus of theoperation from the development of new integrated economic zones to the development of value chains in agriculture. The Bankhad a limited in-country presence during the later phase of project implementation. An important procurement could not becompleted in time, and monitoring and evaluation work lagged.
P123994 | Indonesia Second Power Transmission Development Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2014 | 2020 | 2021 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/521251624948423584/text/Indonesia-Second-Power-Transmission-Development.txt | http://documents.worldbank.org/curated/en/521251624948423584/pdf/Indonesia-Second-Power-Transmission-Development.pdf | Uncertainty about the investments to be financed under the project could adversely affect project implementation andresult in lower achievement and cancellation of loans. The project was to finance substation projects under two groups.The technical feasibility studies of Group 1 substation projects had already been reviewed and approved during project preparation,and they were ready for implementation. However, the technical feasibility studies of the Group 2 projects were to be preparedafter project start, and the project was to finance these projects upon the Bank teams appraisal of each one of them againstan agreed set of eligibility criteria and acceptance for financing. However, the finalization of the list of projects for Group 2was delayed by more than two years. As a result of changing government priorities, the project implementing agency, i.e., PLN,cancelled most of the substation investments under Group 2 that led to a cancellation of a big part of the projectloanaround $145 million. On the other hand, the 37 substations projects under Group 1, which were ready for implementationat project start, were completed and all substations were energized two years before the extended project closingdate.While acknowledging that [i]t was a major and fast shift in sector and specific investment priories that led tosignificant revision and reduction of identified and otherwise quite certain investments,the project team commented intheir email dated June 28, 2021 that emphasis on uncertainty, which by design is embedded in framework type operations, maybe slightly misleading as a lesson from this operation.A weak ME system can fail to fully capture theachievement of the project outcomes or establish full attribution between the project activities and outcomes. The MEsystem was designed in accordance with the PLN reporting system. The intermediate results indicators were sufficient to capture theincrease in the transmission substation capacity. However, the outcome indicators, i.e., increase or growth in electricitysales were insufficient to capture the project outcomes in meeting growing electricity demand in project areas, becauseother factors affected the achievement of these indicators, such as tariff changes, economic downturn, and efficiency in increasein appliances. Indicators, such as the number of new customer registrations, the increase in customers electricityconsumption, and customers applications to increase the power capacity, were not included in the results framework. Theindicators did not have the specificity and granularity to capture project outcomes and were insufficient to test the links in theresults chain resulting in weaker attribution.
P124006 | First Connectivity Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2013 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/762731467998766625/text/ICRR14703-P124006-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/762731467998766625/pdf/ICRR14703-P124006-Box393183B-PUBLIC.pdf | This evaluation highlights three lessons drawn by the ICR:Although an operation supporting reform in broad widely cross-cutting areas may have a stronger transformative impact, it also may bear a higher risk of achieving only a fraction of its objectives.A wide cross-cutting DPL does not automatically elicit the coordination efforts that engaging multiple agencies requires, so that inadequate coordination may impede the achievements sought.Electoral cycles may slow down the momentum of reform, particularly with the bureaucratic, administrative, and legal impediments that may arise during those periods.
P124041 | IN: Development Policy Loan (DPL) to Promote Inclusive Green Growth and Sustainable Development in Himachal Pradesh | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2013 | 2014 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/479601508188992268/text/India-IN-HP-DPL-Green-Growth.txt | http://documents.worldbank.org/curated/en/479601508188992268/pdf/India-IN-HP-DPL-Green-Growth.pdf | The ICR draws the following five lessons from the experience of implementing this project, with some modification oflanguage.(1) Experience from implementing sector investment projects can be useful indesigning policyreforms targeted under Development Policy Funding (DPF). In this operations, lessonsfromprior externallyfunded investment projectshelpedidentifypolicy or institutional gaps. Thissectorexperience helped theBank in working collaboratively with the Government of HPin designing thecombination of policy and institutionalreforms that was requiredto carry the agenda forward. For instance, the experience gained from implementing the Bankfunded Rampur Hydropower power helped in identifying what was required at the policy and institutional level forLocal AreaDevelopment Committee (LADF) policy reforms and theMid- Himalayan Watershed Development Projects lessons were helpful insuggesting changes to watershed level planning.(2) Programmatic Development Policy Financing (DPF) can at times bemore effective than standalone operations for supporting sustained policy reform. This operationthrough aseries of two DPL operations helped in collaboration between the HP government and theBank and this helped ineffectivedelivery of development outcomes.(3) A relationship of trust and communication between the Bank team and theclient was key to the success of this innovative DPF initiative. In this case communication between the Bank and theclient through a combination of factors including supervision by alocally based task team leader and skilled and senior stafffrom Washington, DC. andfrequent visits and close interaction with government officers, aided in responding to critical needsof the state.Thisensured appropriatesupport in a timely fashion.(4)Advisory Servicesand Analytics (ASA) can providevital technical support to the borrowers policy actions. A number ofASAs were conducted to support the DPL under the auspices of this operation. The findings and results of these providedtechnical support for policy reform formulation and subsequently implementation.(5) Delivering climatefinance through budget support operations can be beneficial to both the development and global environmentalobjectives. In this project, financing through the Clean Technology Fund (CTF) supported a reform programforGreen House Gas (GHG) emission reductions and other environment and social improvements. However, given that theexperience with this operation showed thatthe process of reconciling and coordinating processing requirements for the CTF andIBRD DPF was not easy, greater harmonization of processes and procedures might be needed for using either CTF or other climatefinance instruments.
P124045 | Tanzania Productive Social Safety Net | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/426251601510346040/text/Tanzania-TZ-Productive-Social-Safety-Net.txt | http://documents.worldbank.org/curated/en/426251601510346040/pdf/Tanzania-TZ-Productive-Social-Safety-Net.pdf | The ICR provided lessons at both the strategic and operational levels the most important of whichare:Programs such as PSSN can operate more effectively within an accepted national social protection/socialsafety net policy or framework to be sustainable. While there were attempts at developing policy-level strategic documents onsocial protection in Tanzania, those are still at a review, nonoperational stage. Presently, PSSN continues therefore to operate ina policy vacuum, while it should be a part of a broader social protection policy and set of interventions. The current plan for thePSSN does not extend beyond 2023, and it is not clear what happens beyond that date. The Government should begin thinking activelyabout the future of the PSSN, which is a much-needed policy tool in the fight against poverty in Tanzania. Institutionalizing PSSNwithin a clear legal and policy framework would greatly contribute towards ensuring the programsfuture.Building systems around safety nets programs takes time. For all the achievement of PSSN, it needsto be acknowledged that the URB is a registry of TASAF programs and not yet a social registry per se. In the context of PSSN II,and as per the projects design, the Government and donor partners should advance their discussions on how to move the URBtoward becoming a social registry that, at a minimum, links the PSSN beneficiaries to complementary interventions. This wouldrequire some policy actions on the Governments side and is becoming even more relevant in the context of unexpected shockslike the current COVID-19 crisis.The ongoing COVID-19 global pandemic has all but highlighted theimportance of programs such as PSSN in cushioning the impacts of crisis on poorest households throughout the world Thecurrent crisis has also highlighted the importance of emergency response preparedness with respect to social assistance programs,and of having a well-established information system or registry to adapt programs to rapidly changingcircumstances.With respect to targeting, a combination of community targeting and Proxy Means Test promotesthe inclusion of genuine beneficiaries as both inculcate transparency in beneficiary identification. Community targeting uses CBfacilitators who are trained to use locally developed poverty criteria to identify poor households and conduct surveys using thePMTquestionnaire. This increases communities confidence on the program. More generally, a participatory approach to targetingincreases ownership of project and process. The accuracy in targeting was far better compared with other countries as it minimizedinclusion and exclusion errors. This could, at least in part, be because of the programs reliance on local staff who betterunderstand the local environment and culture which, in turn, increases accountability and supervision of the respective localgovernment authorities. This approach is critical for building long-term sustainability.
P124054 | ML-Strengthening Reproductive Health | Western and Central Africa | Mali | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/433741529435041422/text/Mali-ML-Strengthening-Reprod-Health-FY12.txt | http://documents.worldbank.org/curated/en/433741529435041422/pdf/Mali-ML-Strengthening-Reprod-Health-FY12.pdf | The ICR (p. 36) provides several key lessons from the project, including:Implementationarrangements and project coordination are key for project execution. First, oversight and implementationfunctions should be separated for accountability purposes. In this case, project activities were spread across manynational implementers, and the Steering Committee was managed as a collective by the implementers, thus being engaged in day-to dayimplementation as well as project oversight. This institutional arrangement provided minimal accountability in achievingdecentralized project outcomes. Second, the project coordination unit (PIU) should have sufficient strength to leaddecision-making and be sufficiently insulated from political turnover. The strength of the PIU to lead implementation(project activities, disbursements, and outcomes) was limited, since it was positioned at a nexus between multiple nationalagencies, requiring approval from the Secretary General of the MOH and agreements of other national implementers to move activitiesforward. The positioning of PIU thus limited its leadership to advance project activities. The next project should consider havinga few carefully selected ministerial and non-government leaders on the Steering Committee, with a PIU that can align to governmentstrategy and manage decentralized activities, insulated from political changes. Project facilitators could be placed in each regionto build capacity within the government. Furthermore, collaboration with UNICEF and other agencies should continue to builddecentralized capacity in the regions and districts, while providing closer technical support.Amulti-stakeholder approach to behavior change communication strategies has great potential to stimulate demand to use healthservices. The C4D program leveraged the collective influence of multiple key change agents to address barriers to serviceuse. It used a positive deviance approach that brings role model mothers and husbands (NGOs, Husband Champions) toinfluence other women/men to use or support RH/FP services. It also engaged community and religious leaders to communicate messagesto encourage husbands and women in the community to use RH/FP services. Moreover, focus groups conducted by UNICEF wereinstrumental to identifying lessons for promoting demand-side changes.Field visits constitute a keycomponent of a solid monitoring and evaluation framework. During implementation, the Steering Committee did not collect orreview data to make its decisions, and there were few field visits. The MOH later reversed this practice, seeingthatfield visits could provide data to assess how to improve the project (improve training, supply of supplies, etc.) andmake corrective actions. Field reports from the C4D program and RBF pilot (i.e. simple dashboard, communication, diagnostic andmeeting tools) were used to support the governments decision making.
P124085 | Congo: Forest and Econ. Diversification Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2012 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | A financing structure that heavily depends on unstable counterpart funds increases the financial risk for a project.Thus in such cases limiting counterpart contribution can reduce this risk.In this project it proved too risky tocount so heavily on the governments contribution (two thirds of project budget). When the government funds dried up duringthe second year of implementation, the projects ambition had to be reduced drastically through a Level 1 restructuring in2015.The following three lessons in the ICR stood out as important and relevant to similar sector projects in developingcountries and are presented here with some editing:When a complex sector reform project is aimed, better resultscan be achieved if the complexity and ambition of project interventions follow an incremental approach in parallel with buildingthe required capacity of the government. Given the MSDFEEs lack of experience with the implementation ofWorld Bank-funded projects, the project initially could have focused on a narrower range of activities, leaving the morechallenging activities at a later stage. Phasing / sequencing may also help a project adjust more easily to changes when governmentcounterpart funding is available.Investments in technology are necessary but not sufficient for improvinggovernment efficiency; also staff incentives and organizational culture could be considered to ensure institutionalsustainability. The project made a considerable investment in helping the MSDFEE develop information management systemsbut did not do so in addressing the incentives that would ensure sustainability (staff incentives, organizational culture). Thesystems built by the project were left abandoned after the project. It isimportant to identify at appraisal the incentivesthat will make institutions comply sustainably with the changes that the project proposes.Involvement of localpartners helps to improve implementation performance especially in remote project locations, when the capacity of the government islimited. The results of the project could not have been achieved without the involvement of several non-public sectorpartners that were already active in the remote areas where the project operations took place (local and international NGOs andprivate firms). Local NGOs were mobilized to support livelihood activities, international NGOs were contracted to strengthen parkmanagement, and private sector enterprises (forest companies) were also mobilized for road rehabilitation. Working with localpartners also helped in achieving sustainability of project results after project closure.
P124091 | SL: WAREHOUSE RECEIPTS FINANCING PROJECT | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/237911474895370554/text/ICRR-Disclosable-P124091-09-26-2016-1474895360044.txt | http://documents.worldbank.org/curated/en/237911474895370554/pdf/ICRR-Disclosable-P124091-09-26-2016-1474895360044.pdf | IEGconcurs with the findings, recommendations and lessons identified in the ICR.In particular, IEGconcurs with the three lessons rephrased below:(i)The statement of thePDO needstoset theexpectedgoalsappropriately at a higher level instead of too narrowly,in order toreflectproject achievementsmore broadly and comprehensively. The PDO statement could have been written in away that targets the provision of innovative financial services to farmers, instead of too narrowlyin terms ofdeveloping an electronic and negotiable warehouse receipts financing program.As the progress made by the projectwasshort ofa negotiable instrument,the outcome fell far below the attainment of the PDO asstated.(ii) The limited project outcome confirms thatwarehouse receipts can be a viable financial instrumentfor rural farmers in areas with surplus production. While only one warehouse was operational by the closing of theproject, the project had a positive demonstration effect from the single operational warehouse. Benefits were evident by December2015, as 49 farmers were making use of the storage facility, and 19 farmers, including women, had obtainedloans.(iii) Design simplicity and proactivityin the timing and depth of the projectrestructuringcan contribute to better project performance. Setting up a Warehouse Receipt FinancingSystem,with an electronic tradable instrument requires a great deal of time and preparation, andinvolves a number oflegal and regulatory actions that can take time.The Bank team could have reached better results if it hadrestructuredthe project when it became clear that original targets were unachievable. With long delays, the Bank teamaccessed to a Government s requestto include domestic household-level storage facilities for B-onions, and this resultedin substantial benefit to the farmers. In the hindsight, a swift restructuring would have benefitted to the country than keepingthe original targets that could not be achieved.
P124109 | Kenya Transport Sector Support Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/882231624280945715/text/Kenya-KE-Transport-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/882231624280945715/pdf/Kenya-KE-Transport-Sector-Support-Project.pdf | Three lessons were selected from the ICR, with modification of the language: Proper project planning andharmonization of work plans and budgets is essential. This will ensure availability of funds to pay for work done and willin turn allow contractors and consultants to proceed with works without interruptions as well as ensure that the ResettlementAction Plans are implemented early enough before commencement of works, and relocation of utilities is synchronized with theprogram of works. Hence, losses arising from interests on delayed payments and cost overruns will beminimized. Effective contract management is essential for the successful performance of aproject. The project implementation teams need to ensure that contract clauses are reviewed and fully understood by allteam members during preparation of the contract. Development and utilization of Key Performance Indicators for monitoring ofprogress of works in contracts is essential. Inclusion of the provision of social-economicinfrastructure and services to support host communities enhances the benefits of a project. To upgrade roads tosustainable services, infrastructure such as schools, dispensaries, market facilities etc. plays an important role andcomplementsthe improvement of the quality of life of beneficiary communities. This increases communities support for theproject and such interventions should be incorporated in the scope of project where appropriate.
P124134 | Haiti - Education for All Project - Phase II | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/409591555103032908/text/Haiti-HT-Education-for-All-Project-Phase-II.txt | http://documents.worldbank.org/curated/en/409591555103032908/pdf/Haiti-HT-Education-for-All-Project-Phase-II.pdf | Lessons drawn from the ICR: Ina context ofweak country monitoringsystems, intervention-specific monitoring mechanisms can provide an immediate feedback loop to both improve implementation andprovide data for project assessment. In the case of this project, phone surveys, scorecards, and site visits were introducedto provide data and address quality of implementation. While multiple project restructurings provide the flexibilitynecessary in fragile situations,they can also pose difficulties in properly assessing project achievements. In the caseof this project, the objectives, indicators, and targets were modified on multiple occasions, and thus it was a challenge toidentify trends from project start to finish.
P124174 | Vietnam Power Sector Reform DPO2 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2012 | 2014 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial |  |  | Five lessons are drawn from the ICR (pages 57-60), with some adaptation.One, the implementation of a complexmulti-part, multi-period, multi-operation, sector reform DPO requires a singular attention to the end-program goals and objectives.Delays in one period must be compensated for by accelerated action in another to keep the reform momentum going. Shortfalls in onereform area must be remedied by compensatory effort in another to keep the program goals within reach. Considering that a delay indivesting from power generation may have dulled private investor interest, Vietnam must now considerother meanstoincrease investment in new generation capacity in the light of rising demand for electricity.Two, technical progresswith a reform effort must be matched by political action --- that is, progress with the political steps needed to secure the reformoutcomes. The development of generation market rules, the installation of an information technology system, and the conduct ofactual trading in electricity made for robust technical progress with creation of a competitive market for power generation. But,the technical gains would have been hollow without a willingness by the Government to cede complete political control over thetariff setting and adjustment system to a rule-based mechanism.Three, a sector reform program must always berealistic, both with the scope and scale of the reformsas with the timeline. The realism of prior actions and expectedoutcomes must be rigorously scrutinized both during appraisal and implementation, including with regard to the macro-economicenvironment and the political setting in which the reform plan is to be pursued. The pressure to disburse the loan proceeds,for budget support purposes in a DPO like the PSRDPO, is ever present, but the option remains that the budget support can be scaledback to match the measure of progress made with the reform program.Four, a market reform program entails more thanjust transparency in the operation of the market, it also invokes transparency in theenactment of policy and institutionalreforms. Transparency of the Governments decisions is vital to gaining the confidence of stakeholders that the reforms aregeared to the public interest. It was important in the implementation of the PSRDPO that the prior actions required of theGovernment and that the results of various reform initiatives were disclosed and disseminated to market participants and to thepublic.Five, an energy sector reform program requires substantial technical assistance, which the Bank and theborrower must commit to provide, including on an ongoing basis. The PSRDPO benefitted from technical assistance provided duringprogram preparation, in the implementation of various technical aspects of the reform program, and for the design of the next stepin the long-term plan --- the creation of a competitive wholesale market. The Bank successfully mobilized grant funding for some ofthese requirements and supplied its own technical expertise for many other activities. The Government should financially supportother technical assistance requirements.
P124181 | Sustainable Management of Natural Resources and Climate Change | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2012 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099062123105066670/text/P12418108126f4091086f601545d70c74c0.txt | http://documents.worldbank.org/curated/en/099062123105066670/pdf/P12418108126f4091086f601545d70c74c0.pdf | The ICR included six lessons. This review has highlighted the following four with some adaptation of language with broaderapplicability.Sustainability and use of the digital information system (DSS/SNIA) that the project helpedestablish should be built based on long-term financial investment and Government commitment. During projectimplementation, the DSS/SNIA project was developed and madeinteroperable with other databases in the country.Stakeholders in the field used it to make decisions about their farming practices. There was also evidence that Governmentsdecisions and declarations (e.g., emergencies) used information from this system. For such a system to be more effective andincrease utilization, outreach and communication activities should be constantly held. Further, longer-term financial investmentsare needed to retain technical teams of various skill sets to manage and maintain such a system requiring periodic updates andinnovations.Digital traceability systems can have multiple usages besides phytosanitary monitoring andcontrol. Uruguays cattle traceability system is globally recognized. The SNIA system has also incorporated thetraceability of honey, rice, and fruit containers. Based on Uruguays experience, such traceability systems use can beenhanced for phytosanitary monitoring and control and as a monitoring tool in measuring progress towards international goals,enforcing laws and policies, and promoting a countrys products in international markets.To promote acountry as a green/sustainable producer, greater collaboration between public and private sector agencies isneeded. This project was led by MGAP, which invested in technologies and practices that aimed to promote and retainUruguays reputation as a sustainable/green producer. To get an independent assessment of MGAP practices, increasedcollaboration with agencies such as the Ministry of Environment with the mandate for monitoring environmental issues (e.g., waterquality emissions, among others) is essential. Further, private sector buy-in is critical, and they would also need to be a keypartner to take responsibility for promoting sustainable intensification and climate adaptation.Pilot projects canbenefit from good quality impact evaluation. MGAP conducted impact evaluation studies of Call for Proposals.Considering that the project financed many pilots that attempted to demonstrate proof of concepts related to technologies andpractices in water and land resources management, irrigation, livestock management, dairy, etc., the impact evaluation was helpfulnot only for assessing results but also for document learnings so that future interventions can be improved.IEGadds the following lesson:During project preparation, greater effort is required in designing a ResultsFramework with measurable PDO and outcome indicators. In this project, soon after implementation, it was recognized that several PDO and Intermediate Results Indicators were weak in reflecting the projects outputs and outcomes. All PDO indicatorshad to be revised; most IRIs were changed, deleted, or revised as part of the projects first restructuring.Suchsituations can distract the project and delay project activities, while projects with good results frameworks can focus on projectimplementation and achieving results.
P124268 | Economic Revitalization of Khyber Pakhtunkhwa Project | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2012 | 2022 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following lessons are derived from the ICR (p. 29 and 30): A flexible and adaptable design formatching grants scheme can help addressing changing needs during the implementation and can increase success of the program.In the case of ERKF, initially selection process for MG beneficiaries was clear. However, right after the AF went intoeffectiveness, SMEDA received more than 10,000 applications at the same time which were difficult to manage. As a result, the PMUand SMEDA had to design a simplified approach for applications screening and establish a strong MIS gathering all financialand ground data to help a quicker processing of applications as well as monitoring. The flexible and adaptable design contributedto this achievement. Conducting extensive stakeholder and beneficiary consultations before and duringimplementation in a fragile country context can ensure relevance and help achieving expected results of the projects. TheWB team conducted extensive dialogue and intensive consultations with TDPs, the private sector and concerned departments duringpreparation. The project design was built on the result of these consultations. During the implementation, close dialogue continuedbetween the parties. This enabled necessary revisions/adjustments in the component structures leading towards improvements inimplementation in accordance with the changing circumstances. Sustained government commitment andownership at the provincial level can help overcoming implementation issues resulting from low capacity and weaknesses in the keyimplementing agencies. Throughout the implementation of ERKF, the GoPs and GoKPs ownership and commitmentwere at the highest levels. The project provided considerable technical assistance and financial support to the key implementingagencies in KP and erstwhile FATA. The commitment of the relevant authorities coupled with strong technical assistance resulted insuccessful project implementation.
P124341 | MNA Micro, Small and Medium Enterprise Financing Facility | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2012 | 2019 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/309471559251745773/text/Tunisia-TN-MSME-Financing-Facility.txt | http://documents.worldbank.org/curated/en/309471559251745773/pdf/Tunisia-TN-MSME-Financing-Facility.pdf | The ICR draws the following three lessons from the experience of implementing this project, with some adaptationof language.(1) Introducing diversifiedcredit instruments by financial institutions can leadto broadening the range of SME beneficiaries. In this project the addition of instruments such asmicrocredit toformal banking credit models helped in meeting the credit requirements of a broad rangeSMEs.(2) Given that the results framework capturing the changes in the loan portfoliosamong PFIs may not adequately capture the overall social and economic impact of an LOC, it would be useful to supplement theresults framework with impact evaluation exercises. The experience of this project showed that while the projectsuccessfully attained its objectives in terms of credit intermediation, the impact evaluation exercises, provided more informationwith regard to geographic and sectoral targets, generating employment and the ability to target women and youth with suchinterventions.(3) A carefuldesign of reporting requirements during implementation is requiredto ensurethat project funds are being used efficiently, especially in activities pertaining to informalenterprises. For example, in this project, there were difficulties associated with monitoring the impact of microcredit onthe employment created by informal enterprises (the SMEs receiving credit) because reporting requirements were not adequatelydesigned.
P124351 | Kafue-Muzuma-Victoria Falls Regional Transmission Line Reinforcement Project | Other | Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/725301553113811405/text/Africa-ZM-Regional-Transmiss-Line-Reinforc-RI.txt | http://documents.worldbank.org/curated/en/725301553113811405/pdf/Africa-ZM-Regional-Transmiss-Line-Reinforc-RI.pdf | The ICR (pages 27-28) draws nine lessons from the experience of implementing this project. Of these, the fourmost important lessons are the following, with some adaptation of language.(1) Advance preparationof major procurement packages can help in speeding upimplementation. This is particularly importantfor projects envisioned to be fast track implementation projects. Arrangements such as project preparation advances or retroactivefinancing to advanced preparation of major bidding packages for the project need to be considered for helping to increase the speedof project implementation.(2)Project design for brownfield projects needcareful planning for outages given the need to coordinate the contractors plan with theability to grant outages. Such projects may require longer project implementation periods. The implementation of thisproject was subject to delays due to the reluctance on the part of ZESCO to grant long outages on the transmission corridor forworks on account of theimportance of this corridor for demand and export considerations. (Thissingle line was the maintransmission corridor from Kafue Town to Victoria Falls and onward to Namibia).(3) Projects,especially those with wider geographic scope like transmission lines, must include a framework for assessing Gender-Based Violencerisks and responding to such issues. Such a framework should take into account the recommendations of the Gender-BasedViolence task force of the Bank.(4) Insufficient coordinationwithco-financierdevelopment partners regarding their operating constraints can delay implementation and undermine theattainment of project objectives. Project teams should consider a clear split of objectives among development partners tominimize changes to the PDO if delays ensue from constraints with the co-financiers. The full realization of the PDO of thisproject of improvingreliability of electricity services along the corridor was contingent upon the completion ofanEuropean Investment Bank-funded activity.
P124441 | Jordan First Programmatic DPL | Middle East and North Africa | Jordan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2014 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/212101519233350555/text/Jordan-JO-First-Programmatic-DPL.txt | http://documents.worldbank.org/curated/en/212101519233350555/pdf/Jordan-JO-First-Programmatic-DPL.pdf | The following three lessons are taken from the ICR with some adaptation of language: Reforms that havepreviously proved elusive can be promoted through explicit inclusion in the results framework. The DPL made these reformsa core part of its aims. Strong supervision, TA and close collaboration supported the implementation of many of thesereforms. Flexibility in adjusting the indicative triggers and results indicators while remaining true to thedevelopment objectives can help a series to attain its goals. The shift in focus to reforms that would be possible underthe existing legislative framework allowed the series to continue, and provided more time to build the institutional capacity toimplement the new legal framework once it became effective. Implementation strategy needs to be spelled outclearly in a program document. Implementation arrangements were only briefly elaborated in the Program Documents. A moreexplicit implementation strategy, for instance with a formal steering committee and a schedule for reviewing the resultsindicators, could have strengthened the DPLs ability to compete with the Authorities other day-to-daypriorities. IEG adds the following two lessons: When designing operations in countries orregions facing political instability or security issues, it is important to carefully assess the implementation risks and take thenecessary mitigation measures. In this case the program could have focused on a narrower set ofreforms. Extensive and in-depth consultations with all key stakeholders at the preparation stage can facilitatethe implementation of the program. In this case, involving Parliament in the dialogue only began at a relatively latestage. Had it been done earlier, some of the legislative delays might have been avoided.
P124514 | Bangladesh Local Governance Support Project II | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/488611520613617350/text/Bangladesh-BD-Local-Governance-Support-Project-II.txt | http://documents.worldbank.org/curated/en/488611520613617350/pdf/Bangladesh-BD-Local-Governance-Support-Project-II.pdf | The ICR pointed to a number of lessons (ICR, paragraphs 62-71) culled from the overall Local Governance Support Project (LGSP),which consisted of a progression of intervention in support of local government decentralization in Bangladesh. LGSP III iscurrently under implementation following the close of LGSP II. The most important lessons are thefollowing: Decentralization requires along-term commitment by both the government and its development partnersto gradually transform long held governance arrangements.Time and absorptive capacity of recipient institutionsareimportant inputs to designing progressive interventions such as predictable andtransparent intergovernmental transferprograms like block grants. For example, in this project, intergovernmental transfers were carried out using transparent formulas,predictable with a commitment made every three years by the national government to the UPs who, in turn, used the resources to planlonger term investment priorities identified after direct consultations with constituents. Institutional development atall levels of governmentand communities of constituents requires a continuous effort. Alternative arrangements for trainingand mentoring of critical staff are essential to build sustainable capacity at the local levels. In this project, DistrictFacilitators trained about 63,000 UP officials on public financial management, procurement, safeguards andmonitoring. Right sizing and proper sequencing of intergovernmental transfers are important. For example, UPs neededadequate block grant allocations that would allow them to deliver on their mandates without encouraging rent seeking and patronageactivities. Introducing performance based grants provided a competitive incentive to subnational governments to performwell in key governance areas and undertake accountability measures within the purview of local governments. For example, UPsimproved tax revenue collections, increased participation by constituents, and improvedplanning, budgeting andreporting. When designing managementinformation systems (MIS) to accompany the changes introduced to supportdecentralization efforts, a realistic assessment of the availability of key personnel andinfrastructure such as a stable anduninterrupted power supply and proper internet band-width are helpful while its absence could inform alternative measures to ensureachievement of implementation targets.
P124614 | Rajasthan Agricultural Competitiveness Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2020 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099240005192212241/text/P124614076dfdb07008685036f6bba3129c.txt | http://documents.worldbank.org/curated/en/099240005192212241/pdf/P124614076dfdb07008685036f6bba3129c.pdf | The ICR included seven lessons. The following three are emphasized as having potentially broader application beyond thisproject. There has been some adaptation of language compared with the ICR:1. In water-scarce situations the Bankand the Government can achieve greater sustainability of agriculture and climate changeresilience by strengthening incentivesfor climate-resilient crops. This projectdemonstrates the feasibility of motivating voluntary adoption of lowwater-use crops and more water-efficient practices by subsidizing water-saving technologies and linking farmers to markets forthose crops. Most farmers in this project area were profit-driven entrepreneurs and unlikely to make farming decisions only forenvironmental outcomes, especially if there is an additionala private cost involved.2. Projectspromoting climate-resilient agriculture need toemphasize community institutions that promote market linkages rather thanexclusively water-focused institutions.Farmer institutionsproved to becritical for achieving economiesof scale, market access, and sustainable production. Organizing small-scale farmers into multi-task groups(MTGs) andcollaborative farmer producer companies (FPCs) to aggregate input and output marketing for high value, water-efficient cropsare also needed to motivate adoption of water-efficient production practices through improving market linkages. Farmersrelatively higher interest in MTGs compared to community water institutions highlights their importance inpromotingclimate-resilient agriculture.
P124615 | Mozambique Public Financial Management for Results Program | Eastern and Southern Africa | Mozambique | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | PforR | 2014 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/494491586368304918/text/Mozambique-MZ-PFM-for-Results-Program.txt | http://documents.worldbank.org/curated/en/494491586368304918/pdf/Mozambique-MZ-PFM-for-Results-Program.pdf | The following Lessons are drawn from the ICR:All stakeholders should be involved in a programfrom the beginning to minimize misunderstandings during implementation. The Program had multiple stakeholders atdifferent levels of the political structure in Mozambique, and with different functions. A common platform for fulfillment in this case PFM for Results served as a uniting reference point for the Bank, government entities, anddonors.Understanding priorities in a complex environment is essential. The Programhad a strong results framework that set out the logic of the intervention, defined priorities and facilitated dialogue whenimplementation issues arose.Information and logistics are key elements in a results-based operationthat operates at several levels. Timely availability of financial resources was key to ensuring a well-functioningeducation system and timely availability of necessary drugs for addressing major health issues. One factor of success was thetimely intra-governmental and inter-sectoral information flows
P124625 | Hwange-Sanyati Biological Corridor Project | Eastern and Southern Africa | Zimbabwe | Blend | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/271661608752441506/text/Zimbabwe-ZW-HSBC-Project.txt | http://documents.worldbank.org/curated/en/271661608752441506/pdf/Zimbabwe-ZW-HSBC-Project.pdf | The following lessons in the ICR stood out as important and relevant to other projects in the natural resource management sectorand are presented here with some editing.1. Piloting a land rehabilitation project in a participatory manner,where a common social asset is under threat, can ensure community engagement and lead to sustainable land restorationefforts. For example, the gully prevention measures and soil rehabilitation around social assets, such as the hospital andschools in Chireya, supported the communities to strengthen their capacities on land use and resource management. It also generatedcohesion among community members for committing to land restoration efforts for the long-term. This participatory approach could beapplicable to other natural resource management projects of the Bank to effectively engage communities in restoration, especiallyif benefits will only be visible in the long-term for limited beneficiaries.2. Developing businesses for communityconservancies requires supervisions from project initiations and considerations on promoting livelihood opportunities beyondwildlife tourism. The project was not able to fully explore income-generating opportunities for the community in theSidinda conservancy due to the delay in building community capacity for finalizing the business plan for the Sidinda conservancyand its limited focus on wildlife management for tourism. As it required time to build community capacity, projects need toimplement such activities early in the project with a clear methodology. The Sidinda conservancy and similar communityconservancies in the country and the region need livelihood opportunities beyond wildlife tourism, to cope with thedownwardtrend of tourism and the external shocks such as the COVID-19 pandemic. Promoting community-private partnerships is away to leverage financial and technical resources for promoting income-generating activities which do not fully relied on tourism.Facilitating market linkages could support the sustainability of expected income streams from the alternative livelihoodoptions.3. Preserving transboundary ecosystems requires a long-term commitment to the region, which can be ensuredby a Transfrontier Conservation Area (TFCA) program. The project confirmed the need for supporting and funding the regionin the long-term in order to achieve sustainability of the project interventions in the corridor-level. The Bank has relevant priorexperience to manage pooling resources for a TFCA program from various sources including bilateral donors. Such a program wouldalign with the Banks current national and regional priorities.4. Assessing and managing climate changerisks needs to be continuous throughout project implementation. While the risks of climate change were considered duringpreparation, the changes in precipitation patterns induced the drought during the project and posed unprecedentedtechnicaland financial challenges, such as the insufficient grazing for wildlife in HNP and the difficulties in wildlife restocking inSidinda. Incorporating climate risk monitoring as a core part of projectsupervision, as well as strengthening capacities to mainstream climate change in the sector at national and community levels, wouldreduce unexpected implementation delays caused by environmental conditions.
P124629 | Statistics for Result Facility | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | RETF | IPF | 2012 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/827051468147007516/text/ICRR-Disclosable-P124629-06-23-2016-1466684691203.txt | http://documents.worldbank.org/curated/en/827051468147007516/pdf/ICRR-Disclosable-P124629-06-23-2016-1466684691203.pdf | IEG concurs withseveral insightful lessons in the ICR, including:Stability in task team leadershipis a key ingredient for smooth project implementation. In this case, heavy turnover early in the project period left theimplementing agency without necessary guidance, stalling timely problem solving until a stable, committed task team was put inplace.In an environment with multiple donors and especially pooled funding arrangements, strong governmentownership and management around a well-defined national strategy is key to achievement of results. In this case, top governmentofficials appeared at NISR outreach and dissemination events, budget allocations to NISR were increased, and governmentrepresentatives chaired Steering Committee meetings, all contributing to coordinated delivery of outputs in a consistent and timelyfashion.Clients may not always be fully aware that the Banks presence can change the rules of a jointfinancing mechanism. In this case, the implementing agency was not well briefed on the procurement and financial managementimplications of Bank requirements, resulting in early miscommunications and delays.
P124639 | PMGSY Rural Roads Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2021 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099210008262214684/text/P1246390b8db85054083e2076922d2cb29b.txt | http://documents.worldbank.org/curated/en/099210008262214684/pdf/P1246390b8db85054083e2076922d2cb29b.pdf | Three lessons are taken from the ICR.Results-based financing of large-scale national programs can be aneffective and efficient way of achieving development impact. The project scope included project activities dispersedovera large geographical area consisting of multiple sates. The activities required procurement of around 12,000 contractsover nine states, the management of which would almost be impractical under a conventional investment project financing.Results-based financing through disbursement linked indicators facilitated the World Banks support to the already on-goingPGMSY and allowed thedisbursement of US$1.6 billion for rural roads development. However, successful implementation ofresults-based financing depends on extensive preparation such as identification of relevant DLIs and eligible expenses, andcompliance of country systems with the requirements of the World Banks fiduciary and safeguardspolicies.DLIs with strict requirements can adversely affect disbursement and project implementation. Theoriginal DLI matrix was not clearly defined nor flexible to account for unforeseen challenges. The inability to meet some strictrequirements of the DLI matrix was the main reason for slow disbursement. For example, clear weightage was not given in casehabitations were connected to the road network but the road could not be utilized fully due to various different reasons such assafety concerns and partially incomplete features. Similarly, DLI requirements for staff accreditation training could not be metbecause only one module was completed instead of two because of the onset of COVID-19 pandemic. Some flexibility wasintroduced to the DLIs at the project restructuring in 2014 and Additional Financing in 2018 after which disbursementsaccelerated.Insufficient implementation period for complex investment activities can result in cancellation ofproject funds and under-achievement of project outputs and outcomes. An additional financing in the amount of US$500million was approved in 2018 to scale up the project scope both in terms of construction of more roads and the inclusion of climateresilient and road safety features in road designs. However, the implementation period of these activities was estimated at 30months, which was unrealistic. The onset of COVID-19 in March 2020 adversely affected project implementation, too. Towards projectclosing, it was decided that some project activities could not be completed in time, and a time extension would not be grantedbecause the project closing date had already been extended by a total of five years and it was uncertain how project activitiescould be implemented during COVID-19 pandemic. As a result, US$230 million from Additional Financing was cancelled, and at the timeof project closing in December 2020, most of the output targets expected under Additional Financing could not be achieved.
P124648 | Mineral Development Support Project | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2018 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/228681565214267871/text/Burkina-Faso-BF-Mineral-Development-Support-Project.txt | http://documents.worldbank.org/curated/en/228681565214267871/pdf/Burkina-Faso-BF-Mineral-Development-Support-Project.pdf | A multi-faceted approach is critical to improving the public sectors capacitytokeep up with thewell-advanced private sector. The mining sector in Burkina Faso and other countries is driven by the private sector, whilethe capacity of supplying relevant infrastructure including policy, information, and human capital is often lacking. In BurkinaFaso, policies and regulations were outdated; transparent and scientific geo information was not maintained; governments were notcoordinated; limited human resources for both private and public sectors were available. The project took an approach to opt in theconcerned elements that were linked to private sector engagement, spanning from policy and regulations to tertiary education andinternational EITI mechanism. Although there still needs an improvement in reducing skill gaps for the private sector, the projectwas successful in engaging with the private sector.The success of the multi-faceted approach in the mining sectorhinges upon the inter-institutional coordination. The project applied the EITI++ approach, which focused on access toresources, monitoring of operations, and collection of taxes and royalties. This approach required various coordination,particularly between the ministry of mines, finance, and environment. The project observed the lessons to establish an enablingcoordination mechanism in (i) the capable project management unit; (ii) frequent supervision missions; (iii) authorized focal-pointfrom the respective ministries.Engagement of multiple institutions needs a structure to prioritize the activitiesand assignment of the specific role with some incentives. The project involved various institutions such as the ministryof finance, line ministries and agencies concerned with the mining sector, schools and communities. To encourage effectivecoordination among the stakeholders, the project established a mechanism to prioritize the activities with the allocation offunding strategically. The focal point assigned in each institution helped the process. To incentivize the focal point to engagewith the project, the government spent extra costs for the focal points even though it was not defined in the financingagreement.
P124663 | Caixa Solid Waste Management and Carbon Finance Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2012 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062024184032796/text/P124663-9b1fc755-07a1-467b-8165-3a5f5b0776bb.txt | https://documents.worldbank.org/curated/en/099062024184032796/pdf/P124663-9b1fc755-07a1-467b-8165-3a5f5b0776bb.pdf | The ICR (p. 31-33) provided several lessons learned, which were adapted by IEG with some modification oflanguage: A programmatic approach implemented by a financial intermediary can be efficient for identifyingand financing multiple Carbon Finance sub-projects at scale. In this project, Caixa acted as an effective financialintermediary between the CPF and the companies generating the CERs. Also, it was more efficient for the Bank to deal with a singlepartner to implement multiple ERPAS. Furthermore, many Brazilian municipalities did not have the legal structure or institutionalcapacity to promote private sector participation. Private sector entities would have faced significant risks to engage directlywith municipalities without having support from a financial institution such as Caixa. Complementing CarbonFinance with other financing can allow for effective engagement with local stakeholders in the public and private sector.After this project Caixa and landfill operators continue to show interest in expanding Carbon Finance operations within the SWMsector in Caixa and to develop alternative ways for trading carbon credits generated beyond the Carbon PartnershipFacility. Performance incentives or penalties might strengthen compliance with the deadlines of sales, purchaseconditions and reporting and/or achieving targets in terms of CERs. In this project, while there were contractualobligations between Caixa and the CPF, as well as between Caixa and the landfill operators, remedial measures for lack ofcompliance at the ERPA as well as at the sub-ERPA level couldhave been applied immediately to allow for better programmanagement.
P124715 | Cote d'Ivoire - Emergency Infrastructure Renewal Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/550141636493697729/text/Cote-dIvoire-CI-Emergency-Infrastructure-Renewal.txt | http://documents.worldbank.org/curated/en/550141636493697729/pdf/Cote-dIvoire-CI-Emergency-Infrastructure-Renewal.pdf | The following three lessons have beensummarizedfrom the 5 presented in the ICR with minor additions from IEG: (ICR,paragraphs 129-133): Future multi-sector emergency operations in a post conflict setting may find usefulstrengthening institutional capacity beyond those of the PCU.In this project,capacity building activitiesembedded experts in each implementing agency. Similar operations may benefit from reaching out not just to implementing entitiesbut alsothe private sector(contractors and consulting firms) to enhance capacity. Mitigation measures to addressinstitutional capacity risks may include early technical assistanceto entities to aid in updatingdetailed studies forcomplex activities (e.g., storm water basins, large drainage systems etc.) before contracting for works, Periodic technical auditsmay identify non-compliance early and corrective capacity measures applied in time. Conflict or confusion duringimplementation may be avoided by clarifying responsibilities between the PCU and the implementing entities. In this project,entities implementing the works may be better suited tomonitor compliance with environmental safeguards at the worksitelevel, rather than the PCU. A clear structure for co-financing or recipient contributions may result inresponsive mobilization ofresources. In this project, the government overcommitted its resources for co-financingand caused implementation delays, including compliance with safeguards. Parallel or co-financing using government resources maybenefit from including effective risk mitigation measures by identifying early indicators of delay and alternative measuresto respond to these.Future parallel financing operations may includean engagement framework with clear, actionablecorrective measures. Additional Financing to emergency operations may best focus on the emergency responseonly. In this project, the AF was provided when an emergency response was no longer needed. The AF activitieswereimplemented usingthe same complex financial flows under the emergency operation, including the difficultiesassociated withuse of counterpart financing Implementation delays continued with AF activities. Limiting AFtobridge financing gaps or address cost overruns of original emergency activities may be better use of the AF.Activities to expand sectoral outcomes may be better addressed by new project preparation to avoid implementation delays or costoverruns inAF activities.
P124720 | Dem Rep Congo - Western Growth Poles | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/793191635196555433/text/Congo-Democratic-Republic-of-DRC-Western-Growth-Poles-Project.txt | http://documents.worldbank.org/curated/en/793191635196555433/pdf/Congo-Democratic-Republic-of-DRC-Western-Growth-Poles-Project.pdf | The ICR presents ten lessons arising from this project (ICRR, paras. 89 98, which also provides project-specificaspects, of which some were achieved, and others not achieved). This ICRR focuses on consolidating key elements of the ten lessonsinto five strategic lessons. These lessons focus on the broader significance of the projects experiences,drawing conclusions which are applicable for other projects, especially in the context of a Fragility, Conflict and Violence (FCV)environment. The ICR (paras. 89 98) provides further details on the experiences arising from this project, which providedthe basis for the relevance of the strategic lessons which are applicable to other projects/countries.(a) Lesson1: The importance of judicious project design in a Fragility, Conflict and Violence (FCV) context, whichtakes into account the following five key complementary elements: (i) importance of careful assessment of weakinstitutional capacities of the most relevant entities, involving public private and civil society sectors;(ii)including in the design process contingency planning and multiple cost evaluation scenarios, to ensure flexibility andrealism, given FCV aspects which may trigger changes during implementation;(iii) the relevance of taking a sequencedand sound approach to expanding the role of a weak private sector, building on relevant recent initiatives;(iv) takinga phased nation-wide approach, to lay the groundwork for subsequent sustainability, scaling-up and replication in othergeographical areas/zones; and(v) importance of formulating a sound results framework and effective operationalmonitoring and evaluation/ME system, including the formulation, from the outset, the most relevant result indicators(e.g., by gender, scale of operation and operational);(b) Lesson 2: Vital relevance ofensuring from the design stage three core complementary elements regarding sound formulation of appropriate institutionalarrangements and roles:(i) early and sound implementation capacity assessments (or audits)of the most relevant entities (for both public and private sectors); (ii) appropriate, clear andcomplementary arrangements and roles of relevant entities involving public, private and beneficiary/other stakeholdersectors, to stimulate expanded role of the private sector, especially in countries emerging from FCV;(iii) appropriateand clear partnership arrangements to help ensure effective implementation, results, capacity building and sustainability,including: the role of relevant entities such as the IFC; fostering and strengthening partnerships with strategic localentities; promoting the role of NGOs to provide implementation support and capacity building;(c) Lesson3: Appropriately designed and targeted technical assistance/TA and training activities are vital to helpensure the most appropriate support and approach to enhancing implementation capacities of each of the key institutional actors, atvarious levels, consistent with their appropriate roles. (d) Lesson 4: Timely Contracts and MeetingSafeguard Requirements: Importance of ensuring major project-financed contracts and safeguard requirements of key projectcomponents/activities are prepared and finalized during the early phases of project implementation. Under this project, theseaspects were not adequately prepared, and resulted in project delays and reduction in the original targets and results. Also, theBanks technical support role during preparation and early implementation to the relevant entities can play a vital role,especially since contracts/safeguards need to meet Bank (and other financier(s), as relevant) requirements.(e)Lesson 5: Intensive and Appropriate WB Implementation and Sustained Support: (i) Adequate, timely and sustained WBimplementation support, with necessary human and financial resources, can play an essential role, especially when working in weakcapacity and FCV environments.(ii) Also, these type of projects show the importance of ensuring adequate Bank staffcontinuity and travel and/or presence in the project area, especially in a large country like DRC. Having more frequent missionsand of shorter duration, managed from the field, can enable taking corrective measures much earlier and avoid significant delays inproject implementation.(iii) Another aspect of appropriate WB support which can also contribute to sustainability ofproject benefits applicable to other projects is the vital role of timely follow-up Bank-financed projects. This support caninclude providing sustained support for continued strengthening of the most relevant public sector entities (e.g., agriculturalseeds, research and extension systems, SMEs) to help enhance an improved business environment and practices.
P124775 | Ghana - West Africa Regional Fisheries Program | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/664421564509538969/text/Ghana-GH-West-Africa-Regional-Fisheries.txt | http://documents.worldbank.org/curated/en/664421564509538969/pdf/Ghana-GH-West-Africa-Regional-Fisheries.pdf | The ICR presents several useful lessons, the most important of which are:1. Study and understand thesectors political economy during project preparation. Failure to adequately understand this resulted inalimited understanding of the risks both to project implementation and to the projects ultimate effectiveness. As theICR states (para. 91) a key impediment to the achievementof the projects governance objective was weak politicalcommitment to transition to more sustainable fisheries management, which invariably required a reduction in the fishing effort inboth the artisanal and industrial segments. In this regard, the ICR recommends, appropriately, that projects aiming toaffect sectoral reforms where conflicting interests are identified or suspected should thoroughly analyze the sectorspolitical economy to undercover stakeholders interests and incentives and put in place adequate measures to address thesefindings. More specifically, this should be a required part of the up-front project social assessment.2.Where high-level government commitment cannot be secured, place more emphasis on local actions. Inthis regard, the ICR (para 93) indicates that if a government does not demonstrate a firm commitment to controlling theindustrial segment an alternative approach to improving the health of fisheries and fishing communities livelihoods could be afocus on providing fishing communities with legal access rights and promoting co-management systems in as many fishing communitiesas feasible. This approach has proven to be effective in Senegal and Liberia, where fishing communities with legal accessrights introduced new harvesting rules, local surveillance, stock enhancement measures, and local site monitoring, resulting inincreased catch rates and the reappearance of species. This, however, requires considerable time and support to communities tosucceed. Although not mentioned in the ICR, this lesson also testifies to the advantages of undertaking and Bank support fora regional program such a WARFP as it permits cross-country comparisons, learning,and sharing of experience.3.An internal discussion is needed on how the World Bank addresses breaches of covenants. As indicatedabove, several legal covenants were only partly complied with or not at all, but the Bank hesitated to take strong action inresponse. A more detailed consideration as to why this was the case is justified in order to provide clearer guidance to staffencountering similar situations in the future.In addition to the above, this review concluded that the project illustratesthe following lesson:4. Greater attention should be given by Bank operational staffto the quality (andrealism) of project Results Frameworks and to the implementability of associated ME arrangements during project preparationand appraisal. In the present case, there were design shortcomings in the original Results Framework that were only partlyresolved at the time of restructuring and hindered the eventual full assessment of project outcomes. Greater effort is neededduring appraisal and midterm reviews to ensure that original and revised Results and ME Frameworks are logical andrelevant.
P124848 | China:Fujian Meizhou Bay Navigation Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/740621591985072690/text/China-CN-Fujian-Meizhou-Bay-Navigation.txt | http://documents.worldbank.org/curated/en/740621591985072690/pdf/China-CN-Fujian-Meizhou-Bay-Navigation.pdf | The following lessons are adapted from the ICR:Embedding strategic institutional strengthening support ininfrastructure lending projects can be a good way to address institutional gaps in infrastructure development and servicedelivery.The design and timing of institutional strengthening and capacity building interventions, even ifaccounting for arelatively small amount of loan financing, can generate significant impact beyond the physicalinfrastructure and the project lifecycle.For this, TA design needs to take a diagnostic approach to help client identifyinstitutional and capacity gaps, and an analytical tool to inform upper-stream design and enforcement in a systematic and effectiveway.Appropriate indicators need to be developed for measuring results from institutional and capacity buildingactivities. This project shared the common challenge facing Bank projects on measuring results from institutionalstrengthening and capacity building activities beyond the output level, due to the absence of appropriate indicators, includingcorporate indicators.Supporting best practice for environmental sustainability in ports andlogisticsprojects can lead tomainstreaming the development of green ports.The project supported MeizhouBays development as a green hub port. With the successful adoption of two biological compensation programs, the projectdemonstrated best ESIA practice and went beyond Chinas EA standards and Bank compliance requirements for environmentalsafeguards. This good practice can be mainstreamed.
P124905 | Nigeria Erosion and Watershed Management Project | Western and Central Africa | Nigeria | Blend | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2012 | 2022 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099111023175535521/text/P1249050d5b8430740a3b60f9a7c516282f.txt | http://documents.worldbank.org/curated/en/099111023175535521/pdf/P1249050d5b8430740a3b60f9a7c516282f.pdf | The following lessons are derived from the ICR with some modification of language. Where projects arerequired to supervise structural work sites in numerous distant areas, remote monitoring through the use of technologies such as360 degree cameras, drones and satellite imagery can complement physical monitoring, reduce costs, and enable supervision where itmay not be possible because of restricted travel. The project used remote monitoring when travel was restricted duringCOVID. The project implementing units were able to remotely check the work done by contractors who were paid by the percentage ofwork done. In decentralized operations, an ME system that tracks both physical progress and financialtransactions (such as physical completion percentage and financial payments made), in addition to the results framework indicators,can strengthen both monitoring and financial management. The weak connection between physical progress and financialtransactions in the system caused significant difficulties in tracking pending payments during the last 12 months of the projectwhen substantial work was completed. Where subunits such as states implement the projects but without a fixedshare of funds allocated to them, setting up an allocation mechanism that is based on states meeting certain fund-use criteria, canreward states that utilize funds and ensure effective use of funds. Using statements of expenditures (SoE) insteadof Interim Financial reports (IFRs) can also avoid large balances from initial advances remaining unutilized in somestates.
P124939 | Hurricane Tomas Emergency Recovery Loan | Latin America and Caribbean | St. Vincent and the Grenadines | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2014 | 2015 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/118471475115641746/text/000020051-20150113011119.txt | http://documents.worldbank.org/curated/en/118471475115641746/pdf/000020051-20150113011119.pdf | Selected lessons adapted from the ICR:In emergency response operations, simplicity in project design and sustained implementation support are key to achieving the development objectives in a timely manner.Implementation of emergency civil works in low-capacity countries calls for institutional arrangements that allow rapid execution while ensuring adequate quality control. In hindsight, a more clearly spelled out articulation of roles and responsibilities could have been defined, for instance: allowing for private firms to provide design of works and giving MoTW the responsibility and adequate resources to supervise appropriately.Enhanced Bank support is particularly important in post-disaster settings as governmentsâ€™ capacity is often already stressed in dealing with increased pressure and multiple donor demands for recovery. Such enhanced implementation support requires more Bank resources, which are not always supported by the available budgets provided to task teams.In the context of Small Island Developing States, integrating resilience into development (and reconstruction) of infrastructure requires a long term approach to build capacity in the appropriate ministries.
P124942 | Mekong Integrated Water Resources Management Project- Phase II | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/869011618843517428/text/Vietnam-Mekong-IWRM-Project-Phase-II.txt | http://documents.worldbank.org/curated/en/869011618843517428/pdf/Vietnam-Mekong-IWRM-Project-Phase-II.pdf | The ICR offered four lessons and recommendations informed by the project operations that teams may consider when preparingsimilar multi-country operations in the future (ICR, paragraphs 81-84). Three of those lessons, with minor edits are presentedbelow: Countries that adopta trans-boundaryintegrated water resources management model are bestserved by starting with national agencies that havewater resources planning capacity to adopt the principles of integratedwater resources management.In this project, the government passed a law to promoteintegrated waterresources planning strategy.Anew agency, MONRE, was assigned tooversee both the development and protection ofVietnams water resources and was immediately challenged by the complex processes and various stakeholders involved.Theproject was designed to buildthe capacity of MONRE and its line agencies using tools and methods that wouldestablishnational processes related to water resources monitoring, river basin WRP, and water resources modelling. As thesesystems take root,the agencies involved wouldthen balance internal and external WRP needs. Specifying studies andbackground WRP assessments such as river basin profiles at design stage may help inform nascent agencies on thecriticalsequence of processes in integrated water resources planning.The project recommended that a visualization of four or fiveprocesses may be helpful to demonstrate the entire WRP process and pointto capacity gaps that need to be addressed toachievean integrated water resources management, first internally and then beyond its boundaries. Anintegrated water resources management project is complex and would benefit from clearroles and responsibilities of keystakeholders, and laying out coordination mechanisms.Inthis project, MONREs line agencies had unclearresponsibilities. For example, theauthority to request/sign off on budget allocations was unclear. Each agencysresponsibilitytoward river basin water resources planningand water resources modelling was also unclear. Clarifying theroles and responsibilities of theline agencies in data collection, water modelling, and water planning, among others,wouldallow for the effective use of computerized tools such as a decision support system (DSS)to support waterresources planning. WRP. The unclear functions among the MONRE line agencies negatively affected the initial implementationof such a tool. Teams considering similar projects in the future would be best serve by adequately assessing the capacities of thevarious agencies involved in project management, data collection, water modelling, and water planning, amongothers.Coordination and sharing dataamong relevant agencies nationwide, linking water resources management, and usingtools such as DSS, are critical considerations for sustainable water resources management. When choosingindicators for projects that cross boundaries or rely on decisions by entitiesother than the implementing agency, commitmentsat appraisal may be useful toachieve outcomes. In this project. the results framework included an outcome indicatorthat waseventually dropped at restructuring becauseit required a signed agreement between the Prime Ministerandthe Government of Cambodia, which was beyond the power of the project implementing agencies.Trans-boundaryindicators, such as the projects indicator on sharing of water resources data collected from the upgraded and newlyconstructed water resources monitoring stations, also includeddecision points outside the control of the implementingentities. Indicators that involve action bythird parties require commitment from those parties before or during appraisal toachieve the proposed outcomes.
P124978 | Changzhi Sustainable Urban Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/748591569871538781/text/China-CN-Changzhi-Urban-Transport.txt | http://documents.worldbank.org/curated/en/748591569871538781/pdf/China-CN-Changzhi-Urban-Transport.pdf | The following four lessons have been selected from the ICR because of their potential relevance for future urban transportprojects financed by the Bank, other aid institutions or donors. IEG has modified some of the language in theICR: Insecondary cities, expensivemass transit systemsmightnot benecessary toincrease public transport modal share and enhance urban mobility. The package of interventions implemented under theproject in Changzhi revealed successful to incentivize public transport use. The packageincludedlow-cost bus prioritylanes and complementary measures, integrated road development, and intelligent traffic and bus management. It wasappropriatefor the levels of demand, capacity, and fiscal affordability in this secondary city, which was ramping up itsurban transport system. Even large cites may not have the demand and financial support for BRT, commuter rail, or metro. Therefore,bus priority lanes and the other measures can be a cost-efficient alternative for other secondary cities to satisfythecurrent public transport demand and mitigategreenhouse gas emissions while setting the stage for later interventionswhen conditions are ready. The design of bus priority lanes needs to fit into the citys context,traffic, road conditions, and passenger demand. Thebus priority lanes and stops in the first corridor -ChengxiRoad -were placed in the median, ignoringthe conditions of a narrow four-lane road with a high-level of vehicular andNMT traffic. Therefore, the corridor didnotfully achieve the benefits of a multimodal corridor. It also resultedinhesitation on the part ofthe city government as towhether or notcontinue with the remainingcorridors.After Chengxi Road, the city modified the original cross-section concept and implemented curbside bus lanes in theremaining three corridors. Thesewere much better accepted by thepublic. Public consultation is key togood urban transport investment outcomes. As a result of the detailedplanning of public consultations and activeengagement of the citygovernment and the Bank team, the three rounds of public consultations were well attended by residentsand road users. In these public consultations attention was paid to the needs of the different demographic and income groupsthrough a good representation of women, poor people, people with disabilities, and elderly residents. The public providedconstructive feedback on expected/achieved benefits and proposed refinements in public transport operations. Thesuccess ofurban transportprojects depends on adaptability to changes in transportpreferencesand proactivityto such changes.Nearly all urban transport projects will face changes during implementation, includingchangesin client leadership and institutions,thefiscal capability,national and city policies,anddevelopment priorities. Thisproject was no exception. Itexperiencedmany challenges, including weakimplementationcapacity, concerns with median bus lanes, and a late request for a right of way expansion from the city ofChangzhi.The key to the projects turn-around after the slow start was the ability of the city of Changzhi and the Bankteamto engage in a dialogue to adapt to the changing priorities of the city and proactively address issues as they arose. Theimplementation experience of this project is a good example of successfully implementing an urban transport project despite suchchallenges.
P125018 | West Africa Regional Disease Surveillance Capacity Strengthening | Western and Central Africa | Western and Central Africa |  |  | Human Development | Health, Nutrition & Population | RETF | IPF | 2014 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/361821530283618243/text/Western-Africa-3A-West-Afr-Disease-Surveillance-FY12.txt | http://documents.worldbank.org/curated/en/361821530283618243/pdf/Western-Africa-3A-West-Afr-Disease-Surveillance-FY12.pdf | Lessons drawn from theICR, adapted by IEG:When designing and implementing regional projectswithwide geographic coverage, somesteps can strengthen country ownership, which is important for theprojectseffectiveness and sustainability of results. Country ownership can be strengthened bygiving the participating countries some decision-making power over how the funds will be spent in their respective countriesthrough financial agreements; The experience ofthis project indicatesthat havingMOUs between ECOWAS membercountries and WAHO was clearly not sufficient to ensure country ownership,and the design should have allowedsomeflexibility for the participating countries to designactivities andhaveaccesstofunds. Developing aneffective communication strategyat the outset toimprove the awarenessof all the stakeholdersin participating countries throughout the lifecycle of the project cansignificantly improve the country ownership and contribute to sustainingtheresults after the closure of theproject.It can also be effectivein managing the participating country expectations when the project has a catalyticnature and small budget. In this case,lack of an effective communication strategy on how best to promote the projectacross ECOWAS member countries and to advocate for disease surveillance as a priority agendacontributed to the perceivedindifference displayed by some countries to the project. The projects visibilityamong the stakeholdersand DPs wassignificantly increased after such communication strategy was put in place. The effectivenessofa regional project can be improved bymaking sure thatthere are focal points assigned from each implementingpartner agency. Thiscan improve the PMUs coordination effortswhenthe implementation structure is complex and includesmanysub-contractedpartners working in different countries. In the project,the reportingdifficulties experienced with some implementing partners were due to the lack of dedicated individuals assigned to theproject.Lessons drawn by IEG: Inprojects ofhighcomplexity and of a catalytic nature (i.e. intended to demonstrate the commitment of a key development partner in this area andto stimulate further resource mobilization), a strong results framework andrigorous ME design andimplementationcan helpdistill credible data and evidence on what works and what doesnt to improve the design andimplementation of scale-up operations. Collecting gender-segregated data in projects aimedto strengthen human resources, even if theproject is not designed to havegender-sensitive activities, canyieldvery useful baseline information.In this case,the collected datadisaggregated by gender and country of origin hasrevealed significantgender disparities. This information has been effectively used bythe subsequent larger projects(REDISSE program)to designgender-sensitive activitiestargeting gender disparities detected bythisinitialproject.
P125021 | Hunan Forest Restoration and Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/866391590522338942/text/China-CN-Hunan-Forest-Restoration.txt | http://documents.worldbank.org/curated/en/866391590522338942/pdf/China-CN-Hunan-Forest-Restoration.pdf | Lessons directly from ICR:The depth and quality of extension is critical for the success of a forestprojects physical works (para 102). The importance of extension was foreseen during preparation and budgeted for,with recognition by both Bank and PMO staff that the greatest challenge would be changing traditional forestry mindsets andmethods. Despite this recognition and preparation, this challenge exceeded expectations and corrective action was required (such asincreased training and new extension materials, among other measures, see Section III.B.). Substantial budgeting, earlypreparation, and use of demonstration forests can help smooth the crucial adoption of required mindsets and technicalskills.Early establishment of demonstration forests can maximize the effective promotion of the projectsobjectives, intended benefits, and practical techniques (applicable to forest and agriculture projects) (para 102).Demonstration forests, physical demonstration of techniques and results were critical in convincing initially skepticalparticipants (ICR paras 21, 41, 59, 68). Additionally, the project could draw on earlier plantings that exemplify a projectsobjective (i.e. repurpose forests and pilot plots established using similar techniques).Mechanisms to incorporateresearch activities with other project activities promote knowledge spillovers and help ensure research is relevant (applicable toprojects with research components) (para 104). Requiring researchers to take part in extension activities (as in thisproject) helps researchers produce materials that are timely and relevant to the project (such as operational handbooks) as well aslearn from field experience. Similarly, close integration of research activities and monitoring and evaluation (for instance, byhaving ME functions undertaken by research units) likely increases the quality of ME (through research staffsunderstanding of experimental design and commitment to rigor).Geographic information systems (GIS) data would be avaluable addition to forest projects ME programs (applicable to forest, environment, and agriculture projects)(para 105). Given that such long-term monitoring is crucial in forest projects (which deliver ecological and landscape benefitsover many decades), GIS data of plot locations would allow for the use of publicly accessible satellite imagery for evaluatinglong-term outcomes such as forest planation extent, density and possibly diversity, providing a means of third-party verification(in addition to site-inspections) and impact.Additional lesson from IEG:Where embedding innovativeapproaches is central to achieving project objectives, behavior and/or perception-based indicators are needed to firstly,demonstrate their impact on PDO achievement and secondly, make a credible assessment of PDO sustainability. Three ofthe four lessons in the ICR (above) relate to what the ICR describes as the central challenge of the project embedding the innovative practices (paras 67 and 96) in order for project objectives to be achieved and outcomes to be sustained.Therefore, indicators that capture the central role of behavior and perception changes, can help ensure a) sufficient projectresources for training, demonstration and extension activities from the outset (see first three lessons above) and b) stronger datageneration in support of demonstrating sustainability of the PDOs.
P125022 | CN: Beijing Distributed Solar Photovoltaic Scale?Up Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/340401623977328291/text/China-CN-Beijing-Distributed-PV-Scale-Up.txt | http://documents.worldbank.org/curated/en/340401623977328291/pdf/China-CN-Beijing-Distributed-PV-Scale-Up.pdf | IEG derives the following lessons drawn from the ICR:1. It is critical to conduct thorough marketsurveys and consultation to test a new business model in an emerging sector prior to its implementation. In thecurrent project, the RESCO model being piloted proved more challenging to implement than anticipated at appraisal, on account ofthe reluctance of schools to participate. Part of the reason may have been that the market survey conducted at preparationwas limited to a small number of schools, and consultations carried out lacked in-depth insight into the willingness issue.With more detailed insight, target installation capacity might have been tailored to a smaller scale or scope of the project tohave been widened to include more sectors at the outset.2. Close coordination between two interlinkedprojects can help bring about successful project outcomes. The second component in this project, prior torestructuring, involved TA for developing local capacity for scaling up commercially viable solar energy deployment, which was acriticalassumption for the success of this project. Although this component was formally dropped at restructuring andsubsumed by another parallel project, CUSBEERE, the teams continued to coordinate closely and conducted supervisions jointly, whichcontributed to the successful outcome of the current project.3. Successful testing of a new businessmodel in an emerging sector amid evolving policy environment calls for close interaction and coordination with the client, to beable to monitor evolving policy, proactively resolve any issues arising and make time adjustments to the project.For the current project, the RESCO model was a new business model to be piloted in the distributed renewable energy sector with thesupport of the national subsidy policy. The Bank team established a constructive dialogue mechanism with key stakeholders, tobe able to respond with agility to any issues arising (e.g. in relation to grid connection or fiduciary aspects). This helpedbuild trust between the Bank team, the implementing agency and key stakeholders, and allowed the for the timely restructuring ofthe operation and the eventual, successful accomplishment of key project targets.
P125024 | Commercial Agriculture and Value Chain Management Project | Western and Central Africa | Gambia, The | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/181851612891514178/text/Gambia-The-GM-Commercial-Agriculture-Value-Chain.txt | http://documents.worldbank.org/curated/en/181851612891514178/pdf/Gambia-The-GM-Commercial-Agriculture-Value-Chain.pdf | The ICR included eight lessons. The following three lessons are emphasized with some adaptation oflanguage: Outcome targets need to be carefully considered at the appraisal stage to ensure that the projectcould achieve its outcome.Overly optimistic targets, missing baseline andcontrol groups and late restructuringcan make attribution trying and critically affect project outcome. The Bank must ensure that targets are based on reasonableassumptions, with clear road maps for setting baseline values and, when appropriate, establishing well developed control groups.Also,early restructurings could help rectify any weaknesses in the Results Framework and allow enough time forthe achievement of results. In fragile countries, ensuring safeguard and environmental compliance requiresactive support from the Bank specialists. The project experience demonstrated that the lack of guidance by the Bank teamon environmental and social safeguards as well as the lack of environmental and social specialists in the Project ImplementationUnit (PIU),critically affected safeguards compliance for four years. Bank teams need to provide regular and extensiveguidance on environmental and social compliance from project inception. Environmental and social safeguard experts need beappointed by the PIU for the duration of project implementation. Experts could be drawn from other PIUs who already built thenecessary capacity and would allow for cost sharing. The capacity of beneficiaries needs to carefully assessed atappraisal in order to design adequate activities that can be successfully implemented.Limited knowledge about themanagement and technical capacity of Micro, Small and Medium-sized Enterprises (MSMEs), producer and youth groups or theirinadequate consideration in project design can jeopardize their successful engagement in the project. The Bank team shouldtherefore properly assess the capacity of MSMEs, producer and youth groups at appraisal to inform project design on value chainactivities. For example, the Bank must ensure that matching grant schemes are adjusted to the lenders capability withrespect to the beneficiaries contribution. Also, effective operation of WUAs needs governing by-laws in place, and farmersneed to besensitized and trainedto ensure proper ownership of irrigation infrastructures.
P125032 | Timor Leste Road Climate Resilience Project | East Asia and Pacific | Timor-Leste | Blend | FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099050224111032257/text/P1250321bcd6370811806313be45abd2a1a.txt | http://documents.worldbank.org/curated/en/099050224111032257/pdf/P1250321bcd6370811806313be45abd2a1a.pdf | Alternative cost-effective road maintenance programs could be identified to supplement the contractors defectliability coverage. The PAD discussed experience from community-based rural access road programs supported by the ILO, theADB,and the EU which showedboth the important contribution made to the income of the participatinggroups, andalso the strong community support for the road programs on account of the enhancedaccessibility provided by the roads. WorldBank projects in India and Nigeria haveimplemented maintenance models using women-led groups. The project dropped theparticipatory activities during implementation but the model can be considered in future operations.A longerpreparation and implementation period can reducethe need for multiple restructurings. The project was prepared inrecord time which helped to take advantage of IDA funds prior to the cycle closure but this led to a broadly defined project scopeand unrealistic timeline which was corrected over multiple restructurings. Each restructuring required time and resources to bediverted from implementation and supervision.The Banks safeguards policies could help improve clientcapacity.The projects safeguards actions helped the client put in place a resettlement compensationmechanism, grievance redress mechanism, and gender-based violence response and mitigation system that lasted beyond the projectcycle and was expanded to other client projects. It was helpful that transport sectorstakeholders were well-coordinated andcontinue to support various aspects of institutional development.
P125105 | Pakistan Flood Emergency Cash Transfer Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/971811475786040866/text/000020051-20150312114358.txt | http://documents.worldbank.org/curated/en/971811475786040866/pdf/000020051-20150312114358.pdf | The ICR (p. 17) identifies several valuable lessons, including:In case of an emergency situation, a phased response can be effective: the first phase to provide immediate relief for victims by focusing on their most urgent needs, while the second phase emphasizes recovery by to recapitalize assets and restore livelihoods. However, if immediate needs have not yet been met, sufficient flexibility in how benefits can be used is necessary. Emergency operations require an effective communication campaign to inform beneficiaries or avoid misinformation among beneficiaries. In the case of this project, lack of information about eligibility put pressure on the grievance system.Emergency projects face the challenge of balancing accuracy (to avoid inclusion errors) versus simplicity (to guarantee fast implementation) of the targeting mechanism. This project had initially high inclusion errors; however, these were addressed through a solid grievance mechanism.
P125120 | Greater Maputo Water Supply Expansion Project | Eastern and Southern Africa | Mozambique | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099210108262227569/text/P12512007f14ec09909107068b9aff99307.txt | http://documents.worldbank.org/curated/en/099210108262227569/pdf/P12512007f14ec09909107068b9aff99307.pdf | The ICR (paras. 77to 82) lists a number of lessons and recommendations derived from the Projects experience. Basedthereon, IEG derives the following lessons relevant for similar projects carried out in comparableenvironments:The benefits to the population from an increase in the supply of treatedclean water (the PDO inthe Project) can be constrained by a deterioration in water service reliability levels. Thenumber of hours per daysupplied to the population in Greater Maputo in 2021 was below the levels at the start of the Project. This is ascribed inpartto the rapid growth in population (about 40 percent) in the Greater Maputo area between 2013 and 2021 and the highincidence of non-revenue water (NRW) in the Project area that affected the operational performance of the utility. A lesson learnedis that the Project design and implementationneed to address these constraints in a holistic manner.Theoperational and financial performance of the waterutility can be significantly affected if potential operational challengesforthe service provider are not adequately anticipated and remedial measures provided through the project design. Inthe case of the Project, high levels of NRW and weaknesses in reliability of supply remained a challenge through the implementationperiod and affected the operational and financial performance of the operator (AdeM). The Project did not include NRWreduction andreliability improvement components, or related activities. While the incidence of NRW and reliability ofwater supply weretracked throughout the implementation period, no remedial measures were provided through the Project. Moreconsideration should be given to ensuring the sustainability of development outcomes through improvements inoperationalperformance.Inadequate assessment of implementation risks and a lack ofappropriatemitigation measures can lead to substantial delays in project completion and delay realization of theProjects benefits.The Projects implementation risk was significantly underestimated given the need tocarry out detailed designs, procurement processes, and environmental compliancefor the large construction contracts (SabieWTP and Corumana-Machava transmission main). The issues with these large contracts delayed project completion by almost twoyears.Flexibility and careful consideration are required regarding thechoice of implementationarrangements for larger works, taking into consideration the country context. The Projects experience showed that useof multiple consultants (preparation of technical designs and specifications; supervision of works, and works construction) forimplementation of transmission mains) proved to be complex and time consuming, with several flaws emerging in the constructionphase. A Design and Build (DB) model was used for expansion of the distribution network. This did not yield the expected timesavings and the client and World Bank specialists concluded that the country context required a single contractdesign-supervision for works like the transmission main and distribution network. However, in the case of complex activities likethe WTP involving the provision and installation of high-tech equipment as well as civil works, the DB model rendered a betterresult.Financial covenants related to tariff reform and ensuring adequacy of tariffs cannot by themselves ensureimproved financial performance by the project implementing entity unless accompanied by complementary requirements for the utilityto improve its operational performance. In the case of the Project, the utilitys financial performance was affectedby persistence of high levels of NRW and weaknesses in reliability of water supply which affected revenue collection. Underthese circumstances, it would not be appropriate to simply raise tariffs to full-cost recovery levels as was required under theProject. The Projects experience showed that investment projects should also provide direct support for strengthening theutilitys operations.
P125127 | MZ-Education Sector Support Program | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2020 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/905031635545005508/text/Mozambique-MZ-Education-Sector-Support-Program.txt | http://documents.worldbank.org/curated/en/905031635545005508/pdf/Mozambique-MZ-Education-Sector-Support-Program.pdf | Lessons drawn from the ICR, adapted by IEG: The sector-wide approach, while complex, can be an effectivemechanism for support to an entire sector system. In the case of this project, there was strong coordination among donors toavoid overlap of interventions, clear alignment with sector strategy and priorities, clear monitoring arrangements to assessprogress and make adjustments throughout the project period, and a strong supervising role of the Bank to ensure quality ofimplementation. Third-party (private) parties can play a critical implementation role in establishing new programs.In the case of this project, the third party providers introduced ECD interventions that represented a new sub-sector for theMinistry of Education, thereby ensuring effective implementation that achieved results, yet also supported capacity developmentsuch that ECD could become institutionalized as a sub-sector within the Ministry. The third-party providers enabled theMinistry to gain valuable experience in implementing ECD in rural communities, curriculum development, institutional structures,community mobilization, and ECD center construction.
P125151 | Plan Belgrano Water Supply and Sanitation Services Development Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062324235016947/text/P125151-a42af9ed-1ca0-4dc9-9659-37eb01a54564.txt | https://documents.worldbank.org/curated/en/099062324235016947/pdf/P125151-a42af9ed-1ca0-4dc9-9659-37eb01a54564.pdf | 1. Successful implementation of a framework project calls for long-term planning:As demonstrated by the project, framework project implementation can be risky and lengthy. The experience of theproject was that start-up and preparatory activities took relatively long, with works starting only two and a half years afterproject approval. A key lesson is that contingency scenarios are needed in order to mitigate against the risk of political,economic and management changes taking place during implementation.2. Providing widespread access to waterto rural indigenous populations calls for creative and low-cost solutions that go beyond large-scale infrastructureprojects: The project demonstrates that the use of small-scale solutions, such as rainwater harvesting, can play animportant role, especially in remote areas with dispersed populations. Use of such low-cost and simple design solutions notonly helped address the problem of water scarcity but also empowered local communities to become more self-sufficient and resilientin accessing clean water. The involvement of local organizations and NGOs with local expertise not only facilitated theimplementation of the project but meant that solutions were more likely to meet their needs and be sustained overtime.3. Improving the sustainability of WSS services can be a long process that calls for a more conduciveenvironment for efficient resource allocation and service delivery: The project showed that it was essential to takea comprehensive approach that included both a focus on service providers improvements and efforts to enhance the enablingenvironment. This called for addressing coordination mechanisms at the national, federal and local levels, and investing inbuilding capacity and governance of WSS providers.
P125202 | FIRST SUSTAINABILITY AND COMPETITVENESS DEVELOPMENT POLICY LOAN | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2013 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/390801528406490157/text/Seychelles-SC-Sustainability-Competitivenes-FY13.txt | http://documents.worldbank.org/curated/en/390801528406490157/pdf/Seychelles-SC-Sustainability-Competitivenes-FY13.pdf | IEG concurs with the main findings and lessons in the ICR, inter alia:(i) Small island settings areparticularly challenging for information technology enabled reforms. In the case of Seychelles, capacity and connectivity gapsdelayed and made difficult system development and adoption.(ii) The quality of the Banks overallengagement is crucial, including how various instruments such as analytical work, policy-based lending, technical assistance andinvestment operations, along with the work of other partners, reinforce and complement each other.(iii)Progress is possible in small countries with limited capacity using cross-sectoral DPL series, as long as care is given in definingappropriately scaled targets.
P125205 | Saint Lucia Hurricane Tomas Emergency Recovery Loan | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/616071473923369379/text/ICRR14926-P125205-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/616071473923369379/pdf/ICRR14926-P125205-Box396299B-PUBLIC.pdf | The ICR includes a number of useful lessons, including:It is difficult to carry out major infrastructure works within the standard three-year timescale of an emergency response project. This project supported assets such as a major bridge, which was not completed during as of project closure.Initial cost estimates of rehab/retrofitting work need to be made conservatively to avoid a scenario where the scope of the project needs to be dramatically reduced. In this project, an insufficient level of contingencies meant that some planned activities had to be dropped when it was determined that other works would be more expensive than planned.Maintenance planning and budget needs to be part of rehabilitation work. In this project, sustainability is at risk because of a lack of sufficient maintenance budgets given tight fiscal constraints.World Bank procurement procedures need to take into account the limitations and realities of the small island state context. Expectations that all bidders will be companies or that it will be possible to generate 3 or more bids for works may not be realistic in a small state context. In this project, simplification of procurement procedures helped to enable faster implementation.
P125229 | Health Sector Development Support Project | Eastern and Southern Africa | Zimbabwe | Blend | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2012 | 2024 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099605011272134127/text/Zimbabwe000ZW00elopment0Proj00FY120.txt | http://documents.worldbank.org/curated/en/099605011272134127/pdf/Zimbabwe000ZW00elopment0Proj00FY120.pdf | The Interim ICR (pp. 30-32) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:Health services under RBF are improved with concurrent health system strengthening, and bothRBF mechanism and health system strengthening are mutually reinforcing. The project strengthened important systemcomponents, including institutional aspects at the local level, accountability, human resource skills, key equipment and supplychains for drugs and supplies, infrastructure maintenance, and health information.Piloting informsthe full rollout of RBF operations. The project started as a pilot in two rural districts before being scaled up, in linewith the good practice that learning-by-doing informs further operational expansion. Apart from technical aspects ofimplementation, the scale-up of RBF in Zimbabwe entailed building a common understanding, appreciation, and consensus amongstakeholders. The process of reaching a common understandingwas facilitated by the pilotingphase.Sustained dialogue with Development Partners enhances synergy. The Bank Team engagedwith Development Partners during project preparation and continued its dialogue during implementation through the National RBFSteering Committee and through meetings held by the Health Development Partners Group. This engagement enhanced synergy in terms ofactivities and resources, driven by shared goals related to maternal and child health, and culminating in additional support beingextended to all rural districts.
P125232 | Third Sustainable Livelihoods Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2014 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111824150523694/text/P125232-4ba0e62a-46ea-4836-8ad4-a1a01712f5fd.txt | https://documents.worldbank.org/curated/en/099111824150523694/pdf/P125232-4ba0e62a-46ea-4836-8ad4-a1a01712f5fd.pdf | The following are some relevant lessons presented in the ICR with some language adjusted by IEG:When specificcapacity building activities are targeted as identified in needs assessments, this can contribute to effective learning by thegovernment officials. In this project capacity building activities were linked to the results of the APA scoringexercise, with also served to identify needs among officials, so that the training and the technical assistance was targeted forthe officials of the districts and sub-districts that most needed them, in specific areas.Predictability andconsistency of local transfers may contribute to enhanced commitment of local authorities and citizens. The LDFssources of finance, since 2013, are linked to international commodity prices susceptible to wide fluctuations based on forcesoutside the Governments control, which exposes programs such as the LDF to levels of unpredictability that can undermine therelevance of the fund to local planners and credibility to local citizens.
P125237 | Malawi Nutrition and HIV/AIDS Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/456141567707349633/text/Malawi-MW-Nutrition-HIV-AIDS-Project-FY12.txt | http://documents.worldbank.org/curated/en/456141567707349633/pdf/Malawi-MW-Nutrition-HIV-AIDS-Project-FY12.pdf | The ICR (p. 34) offered several useful lessons, including the following adapted by IEG: Oncea needfor course correction is agreed by the World Bank team, clients, and relevant stakeholders,timely restructuringcanaligna projectsPDOs, indicators, inputs, and targets withthe evolving context and operatingenvironment.In this case, even though the Bank team and the GoM had identified the need for major revisionsat thebeginning of the project, action was not taken until the 2016 restructuring, leading to shortcomings, implementation challenges,and, as a consequence, shortcomings in the projects efficacy and efficiency. Full engagementofenvironmental and social safeguards specialistscan ensure that appropriate safeguards instruments are preparedandthat there is fullcompliance withestablished frameworks and plans. In this case, neither development norimplementation of environmental management plans were adequate and timely, producing delays and negativelyimpacting projectoutcomes. A straightforward ME system with well-defined indicatorsand systematic monitoring andtracking candeterminewhether and whenrestructuring is necessary, and what the scope of any restructuring shouldbe. In this case, lack of on-time information and accurate reporting led to delays and gaps in projectimplementation. Implementation using country structures (for example, District Nutrition CoordinationCommittees, Area Executive Committees, and community frontline workers), and enhancing the capacity of those structures where andwhen needed,can ensurethatinterventions and outcomesare sustained beyond the life of the project. In thiscase, as the project relied on NGOs to implement community-based activities; theDistrict Councils may not have thenecessaryexperience to continue these activities, putting sustainability at risk.
P125272 | NIGER - Shared Growth Credit I | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/511341480428355323/text/Niger-NIGER-Shared-Growth-Credit-I.txt | http://documents.worldbank.org/curated/en/511341480428355323/pdf/Niger-NIGER-Shared-Growth-Credit-I.pdf | There are three key lessons of general applicability that may be drawn from the preparation and implementation of these threeoperations:Especially in a difficult country context, it is advisable to limit the programs scope and objectives soas to involve the minimum necessary number of sectors, ministries and agencies. In this case, the wide range of reform measures andcorrespondingly large number of concerned agencies stretched weak governmental coordinating capacity beyond its limits. A relatedlesson is that, where coordination is required, the Ministry chiefly responsible for program implementation should have theauthority, experience and connections to carry out its task effectively.While it is acknowledged that the impact of mostDPOs would only be felt in the medium term after the closure of the program, ME design can nonetheless advantageously includeintermediate indicators of progress in meeting objectives that can be more closely related and attributable to the prior actionsand other measures supported by the program.Exclusive reliance on prior actions alone may lead to an erroneous impressionof the programs achievements. In many cases, sustained follow-up is required to make the reforms effective, and it isimportant that program monitoring take this fully into account and implement remedial action where necessary. Examples from thisprogram include the need to survey enterprises regarding visits by taxation officials, and to carry out physical inspections ofimportant procurement contracts.
P125288 | UG Science and Technology Support | Latin America and Caribbean | Guyana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2018 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/850971530283542276/text/Guyana-GY-UG-Science-and-Technology-Support.txt | http://documents.worldbank.org/curated/en/850971530283542276/pdf/Guyana-GY-UG-Science-and-Technology-Support.pdf | The following lessons are adapted from the ICR:Beneficiaryinvolvement leads to capacitydevelopment and sustainability of project outcomes. In this project, faculty members of the universitygainedknowledge and built skills throughactivitiesofthe six Technical Committees that were established to collaborateon and advance the projects sub-components. As a result,these faculty membersnowpossess theknowledge and skills tocontinue workingon curriculum reform, research, and facilitiesmanagementLack ofa communications strategy makesit difficult to managebeneficiaries expectations. In thisproject, it took some time for instructors tointegrate new laboratoryequipment with new and improved course content. Both administrators and students expressed some dissatisfaction with resultingdelays in the full use of UGs upgraded laboratory facilities. A formal communications strategy, preferably developed atproject start to guide messaging during the course of implementation, could have helped to set expectations about the use of newequipment.Lack of capacity in impact assessment makes it difficult tomeasure longer-termproject outcomes. The first cohort of students to benefit fully from the projects interventions will graduate withbachelors degrees in mid-2019. The project timeline could not encompass assessments of the projects impact on labormarket outcomes for UG graduates (employment rate, earnings, employer perceptions of graduates technical knowledge, etc.).However, it would likely have been feasible to incorporate a capacity building element into the project to prepare UG to undertakethis important follow-up workafter the project closed.
P125298 | Lao Eight Poverty Reduction Support | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2013 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/801361525441447738/text/Lao-Peoples-Democratic-Republic-Lao-PDR-PRSO-8.txt | http://documents.worldbank.org/curated/en/801361525441447738/pdf/Lao-Peoples-Democratic-Republic-Lao-PDR-PRSO-8.pdf | The ICR offers several lessons listed below:Clarifying the DPOinstrument to all implementing agencies and having a robust coordination mechanism are important in terms of line ministriesunderstanding of the overall program. In this case, line ministries perceived reforms as MOF-led, which led todifficulties in implementing reforms. The limited understanding of the DPO instrument in implementing agencies resulted in weakincentives and hampered the ability of the Secretariat to coordinate activities.Ensuring the rightinstitutional lead is in place is key to moving reforms forward. In general, this seems to have been the case in the PRSOoperations. Some areas of the operation may have stalled partly as they were implemented by one institution, while otherparts of the agenda were the domain of other agencies. This factor can be overcome with appropriate dialogue and coordination withall stakeholders during program preparation.Complementary technical assistance can support theimplementation of reforms in a low capacity environment. For example, multi-donor trust fund (MDTF) contributions in theform of technical assistance helped in achieving simplified trade and business requirements.IEG adds thefollowing lesson:In designing a results framework, weak links between prior actions and the expectedoutcomes will impede achievement of the intended outcomes. In the fiscal area, for example, prior actions onweakly defined fiscal reforms for natural resource sectors were unlikely to achieve the intended outcome (a fiscal standard inplace) within the life of the program.
P125359 | Nepal: Community Action for Nutrition Project (Sunaula Hazar Din) | South Asia | Nepal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/658201528207931770/text/Nepal-NP-Community-Actionfor-Nutrition-Project.txt | http://documents.worldbank.org/curated/en/658201528207931770/pdf/Nepal-NP-Community-Actionfor-Nutrition-Project.pdf | The ICR (pp. 30-31) offered several useful lessons, including the following lessons restated byIEG:1. Activities based solely on community selection tend to focus on tangible outputs -- such aslatrines, piped water, and stoves -- rather than on less tangible,but equally important, outputs--such asbreastfeeding or reproductive health. This pattern was demonstrated under the project, as shown by the selection percentages(ICR, p. 16, Table 4).2. The implementation of an innovative operation such as Rapid Resultsfor Nutrition Initiatives in settings with limited human resources requires overcoming a steep learning curve. The projectadapted by hiring additional human resources in each district to facilitate RRNIs, and additional capacities for ME andfinancial management. The project focused on hiring married women as coaches because they tend to stay in their communities,thus providing more stability (Section 4).3. Collaboration with development partners in emergencyrelief facilitates effective responses. Under this project, the Bank team worked jointly with UNICEF and the Ministry ofFederal Affairs and Local Development to undertake relevant nutrition activities, as UNICEF had a comparative advantage inproviding effective relief operations in nutrition and sanitation.
P125359 | Nepal: Community Action for Nutrition Project (Sunaula Hazar Din) | South Asia | Nepal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2017 | 2022 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/932501626703631551/text/Nepal-Sunaula-Hazar-Din-Community-Action-for-Nutrition-Project.txt | http://documents.worldbank.org/curated/en/932501626703631551/pdf/Nepal-Sunaula-Hazar-Din-Community-Action-for-Nutrition-Project.pdf | 3. Lessons 3.1 A community-driven implementation approach may not enforce the multisectoral design approach of the project to address the multiple determinants of nutrition. Although both approaches were intrinsically adequate given the country context and the multiple determinants of nutrition, their combination imposed risks for the convergence of interventions to respond to all households needs, since some goals were not fully appreciated and hence not chosen by communities. Project experience indicated that communities may not have appreciated the value of certain outcomes and opted for more tangible investments. Hence, a more supply-driven approach combined with a thorough, systematic, documented, and unbiased gauging of community demand through an ex ante needs assessment before designing the menu of goals might be needed to ensure that all community needs are addressed synergistically. 3.2 Equal RRNI-cycle time frames across the menu of goals can slant the selection of goals toward those for which technical know-how is already available and hence overshadow the spirit of flexibility of the CDD approach. The short RRNI-cycle implementation, aggravated by slow fund flows, and without more emphasis on capacity building of local governments, imposed task trade-offs in the selection of goals by communities. Since not all the goals of the menu could equally be easily achieved in 100 days, some wards rejected the implementation of particular goals. This was true of the goal of increasing animal-sourced protein consumption, whether through subprojects of operating chicken coops or rearing buffaloes or goats for their milk production. Communities may have needed more time to show visible outcomes and more local services and technical support accompanying the demand-driven empowerment support to implement this type of subproject and build on efforts of the RRNIs for sustainability. 3.3 In settings with limited human resources, the implementation of an innovative operation such as an RRNI requires a robust operational planning that takes into account a steep learning curve and strong preparatory arrangements that address weak capacities at entry and adequate project readiness at entry. At midcourse, the project identified capacity gaps and provided additional human resources in each district to facilitate RRNIs and capacity support for monitoring and evaluation and financial management. Initial readiness can be promoted through the early completion of basic procurement measures and the early preparation of an operations manual, which are already known to be standard good practices. 3.4 Good collaboration with specialized development partners in emergency relief facilitated the effective responses that maintained the focus on nutrition and on the original intent of the project. The World Bank's task team worked jointly with UNICEF and the Ministry of Federal Affairs and Local Development to launch nutrition activities that addressed an urgent humanitarian crisis, since UNICEF had a comparative advantage in nutrition and sanitation relief operations. 3.5 In CDD projects that support the achievement of goals yet to be chosen by communities, and which are thus unknown at the outset, additional efforts to collect more granular baseline data at the ward level can facilitate the assessment of the project achievements at completion. The project was one of the first initiatives in Nepal and in the world to implement the RRNIs on a large scale, so it was important to conduct a rigorous evaluation. However, the impact evaluation measured projects gains at the VDC level regardless of the goals chosen by wards, thus limiting learning and biasing the assessment. As a result, the impact evaluation reported less successful outcomes in goals that were less often selected. The selection of goals by beneficiary communities was unknown at entry; therefore, it was tricky to set outcome indicators and targets from the onset. For instance, only 6 percent of communities selected practicing proper and consistent breastfeeding and as a result, the project was deemed unable to achieve the target 1World Bank national accounts data, and OECD National Accounts data files. DataBank Microdata Data Catalog. World Bank, Washington, DC. 2See figure D.2 in appendix D (Maternal and Child Nutrition Study Group 2013; UNCNC21 2000; UNICEF 1990, 2015). 3The original cost of $40 million (25.9 million special drawing rights) combined an International Development Association credit of $22 million and an International Development Association grant of $18 million. The original expected spending on Rapid Results for Nutrition Initiativeswas overestimated because the extent of community demand was not well known, and this resulted in making funds available for the added third component on earthquake relief. The original cost was revised to $35.9 million due to fluctuations in SDR exchange rates. The actual cost at closing was $31.6 million (88 percent of planned costs). Appraisal was finalized on May 29, 2012, and the project was approved on June 26, 2012 and became effective on August 24, 2012. A Mid-Term Review was undertaken on February 15, 2015. The project was restructured on June 30, 2015 to revise the development objectives, results framework, and procurement, disbursement, and institutional arrangements, and to reallocate funds to earthquake relief. The project closed as planned on June 30, 2017. 4 This shortcoming was not in the methodology of the impact evaluation that was supported by the European Commission, UK Aid, and the South Asia Food and Nutrition Security Initiative administered by the World Bank. Its rigorous design used a random selection of 282 village development committees and its surveys were adequate. The evaluation included rapid house listing; main household questionnaire; women and children questionnaire; and baseline, midline, and endline surveys. But the gap was in its final results presentation, using total denominators, thus diluting granular findings within subgroups.
P125389 | Belarus Privatization | Europe and Central Asia | Belarus | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2010 | 2020 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/806651588684520047/text/Belarus-BY-Privatization.txt | http://documents.worldbank.org/curated/en/806651588684520047/pdf/Belarus-BY-Privatization.pdf | Three lessons are drawn from the ICR (page 32), with some adaptation.SOEs need to be prepared forprivatization, including through corporate restructuring as necessary and with improvements to corporate governance.In this project, manySOEs in Belarus, as elsewhere in Central and Eastern Europe, carry non-core assets that makethemun-attractive to the market. They also suffer from poor productivity and debt overhang. In these cases,pre-privatization corporate restructuring would be necessary. Often, funding and other support for restructuring are notavailable, but should be. Moreover, SOEs in Belarus are also saddled with corporate governance issues, includingover-staffing. Improvements to corporate governance prior to privatization would also be necessary.Co-financing by the government of privatization activities might help strengthen government commitment to aprivatization project. In this project, a modest government financing contribution could have raised theprojects profile,strengthened adherenceto decision timelines, and facilitated the implementation of theproject. The government contribution could have also been used to pay: the NAIP staff salaries,professional servicesfor SOE corporate restructuring prior to privatization, orsuccess fees to financial advisers (commissions paid to an advisor,typically an investment bank, for successfully completing a transaction).Technical assistance for SOEprivatization can be combined with assistance for FDI promotion. In this project, the NAIP was created as both anSOE privatization and FDI promotion agency. In general, there are synergies between SOE privatization and FDI promotion,where SOEs are offered for sale to foreign investors. Skills and experience with SOE valuation, tender document preparation,and contract negotiation are also valuable to preparing and offering joint ventures and PPPs, among other modes of FDI, to foreigninvestors.
P125405 | National Community Empowerment Program In Urban Areas For 2012-2015 | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/597311588953553357/text/Indonesia-National-Community-Empowerment-Program.txt | http://documents.worldbank.org/curated/en/597311588953553357/pdf/Indonesia-National-Community-Empowerment-Program.pdf | The ICR draws the following four main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Strong government ownership at all levels is crucial to overcome project challenges. Thesuccess of this project highlighted the importance of strong ownership for stakeholders at all levels of government. This isparticularly important for CDD projects.2. Concentrating investments in poor urban areas with the highestpopulation densities may result in higher impact then spreading investments widely to reach all poor populations within an urbanward (kelurahan). Under the earlier projects, investments were dispersed widely in an attempt to reach all poorpopulations within the urban ward. This project experimented a different method for targeting investments by scaling up an advancedneighborhood development scheme, which provided increasing financing to the poorest areas with higher population densities based onmedium term plans and spatial planning that was linked to city development planning. The lesson is that to achieve povertyreduction a targeted approach will often provide better results than a broader approach.3. Both specialgrant allocations and gender sensitive meeting arrangements can help in increasing female participation. This projectaimed at increasing female participation through training and a pilot initiative in Aceh where special grants were provided toimprove womens access and control of the decision making. The lesson is that female involvement in project managementcan be achieved.4. Online training (targeted for groups) may be critical for a national program that isimplemented across a wide geographical area and diverse target groups. This project required annual training 4,000facilitators and more than 120,000 people at the urban ward level. The training was achieved through newer forms of training suchas through online training. The lesson is that modern training techniques can be effectively used in the context ofdevelopment projects for rapid and cost-efficient training programs
P125414 | FATA Urban Centers Project (FUCP) | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/365281489672893685/text/ICRR-Disclosable-P125414-03-16-2017-1489672876487.txt | http://documents.worldbank.org/curated/en/365281489672893685/pdf/ICRR-Disclosable-P125414-03-16-2017-1489672876487.pdf | The ICR included 13 lessons and recommendations, most of which are useful reflections on project implementation inafragile and conflict-affectedenvironment. The notes below expand on the most relevant.a. The ICRnotes that starting small to learn lessons for scaling up pays dividends. Although this is an appropriatelesson, the project links to scaling up are not clear from the ICR or ISRs. Scaling up responsibilities were left with the projectcounterparts. This may be appropriate, but without some explanation of the likelihood of that scale-up occurring, or explanation ofwhat the counterpart agencies are doing to prepare for that while the project is underway or immediately after the project iscompleted, it is difficult to assess the links between the relatively small investments of this project to the potential forscaling up.b. Post-crisis contexts tend to be data scarce. While information is being collected for data-baseddecisions, it is critical to roll out visible but quickly implementable investments immediately to restore trust ofaffected communities with authorities and build goodwill. This observation highlights a lesson in the need for emergencyprojects in fragile and conflict affected environments such as FUCP to have a sufficiently flexible Results Framework, so as to beable to respond to the changing operating environment. The processes should be in place for amending Results Frameworks (e.g.mid-term review), and projects in these environments should be designed with such flexibility in mind.f. Contractualcontrols may not work optimally in situations where adjudication and arbitration mechanisms are weak or non-existent. Alternativemechanisms for dispute resolution and performance tracking need to be developed, in addition to schedule of payments anddeliverables. Performance based mechanisms including incentives and penalties may be useful to a degree, and need to bebuilt-in to isolate the effect of external factors such as security incidents, forced stoppage of work, etc. There is also a needto anticipate challenges in contractual controls given the relatively weak state of justice institutions, as evidenced by theproject delays resulting from land owners reneging on agreements (para. 27 of ICR).
P125425 | Economic Recovery Support Operation | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/616981474564270294/text/000020051-20140626075549.txt | http://documents.worldbank.org/curated/en/616981474564270294/pdf/000020051-20140626075549.pdf | A single-tranche operation can be an adequate response to a post-emergency situation, but it is preferable - as in this case - for such an operation to be prepared with the prospect of a subsequent development program.An operation with high government ownership as in this case, where most of the specific prior actions were prepared largely by the government, may have better prospects for sustainability and for avoiding backsliding.
P125445 | Mongolia Global Partnership for Education Early Childhood Education Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2012 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/156531467993788222/text/ICRR-Disclosable-P125445-07-08-2016-1467993776047.txt | http://documents.worldbank.org/curated/en/156531467993788222/pdf/ICRR-Disclosable-P125445-07-08-2016-1467993776047.pdf | The ICR includes usefullessons (p. 19), modified by IEG: For projects with a short implementationperiod,simple design andassurance ofthe governments approval ofproject activities are both necessaryforcompletionduring the defined project period. In this project, even though the design was simple and the approvalprocess for the new wood-framed construction had begun prior to effectiveness, it took the government 15 months to approve thekindergarten design, resulting in a significant implementation delay. Project-specific surveys areuseful tools forassessing the immediate impact of the project activities. In this project, a parent satisfaction survey was conductedtodefine the importance of early childhood education on childrens development.
P125447 | Community Climate Change Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2013 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/581201513954124522/text/ICRR-Disclosable-P125447-12-22-2017-1513954117580.txt | http://documents.worldbank.org/curated/en/581201513954124522/pdf/ICRR-Disclosable-P125447-12-22-2017-1513954117580.pdf | The following lessons are adapted from the ICR (para 74): Awareness-building on climate changeconsequenceswas critical for project implementation as for many beneficiaries,the negativeconsequences were laid out in terms ofincreasing damages and risks to their livelihoods. Without this conceptual linkage, their participation would not have been ascomplete. Building climate resilience in highly vulnerable and poor communities depends on the communities first understanding thatinstead of responding to almost yearly disasters, they need to respond to permanently new and different climatic conditions. Thisshift in mind-set is important as a base for discussing and finding new climate-resilientactivities. Beneficiariesare more receptive to innovations and new initiatives for income generatingactivities (IGAs) when: (a) their basic needs were met first; and (b)indigenous knowledge was merged with IGA innovations.Community contribution is a key factor behind continued engagement and project sustainability beyondclosing. ME needs careful attention at the design and the implementation stage. The project designshould be flexible to allow refinement in the results framework and adequate resources must be allocated for ME training anddata collection when a project involves so many different partners with varying capacities.
P125483 | Jordan Second Programmatic DPL | Middle East and North Africa | Jordan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The following three lessons are taken from the ICR with some adaptation of language: Reforms that havepreviously proved elusive can be promoted through explicit inclusion in the results framework. The DPL made these reformsa core part of its aims. Strong supervision, TA and close collaboration supported the implementation of many of thesereforms. Flexibility in adjusting the indicative triggers and results indicators while remaining true to thedevelopment objectives can help a series to attain its goals. The shift in focus to reforms that would be possible underthe existing legislative framework allowed the series to continue, and provided more time to build the institutional capacity toimplement the new legal framework once it became effective. Implementation strategy needs to be spelled outclearly in a program document. Implementation arrangements were only briefly elaborated in the Program Documents. A moreexplicit implementation strategy, for instance with a formal steering committee and a schedule for reviewing the resultsindicators, could have strengthened the DPLs ability to compete with the Authorities other day-to-daypriorities. IEG adds the following two lessons: When designing operations in countries orregions facing political instability or security issues, it is important to carefully assess the implementation risks and take thenecessary mitigation measures. In this case the program could have focused on a narrower set ofreforms. Extensive and in-depth consultations with all key stakeholders at the preparation stage can facilitatethe implementation of the program. In this case, involving Parliament in the dialogue only began at a relatively latestage. Had it been done earlier, some of the legislative delays might have been avoided.
P125495 | Bridges Improvement and Maintenance Program | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Transport | IDA | PforR | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/594351561474032793/text/Nepal-NP-Bridges-Program-Support.txt | http://documents.worldbank.org/curated/en/594351561474032793/pdf/Nepal-NP-Bridges-Program-Support.pdf | The following are the key lessons from the ICR (paras 99 and 100) with some adjustment in language and content by the ICRreviewer:For the successful use of the PforR instrument, the Government vision, the timing, and the availabilityof adequate planning and monitoring tools matter. In this case, the PforR instrument was effective in supporting theDORs bridge program, which had already been part of the Governments vision and plan to improve Nepals vitalbridge sector. However, this program was not effective due to several issues, including a non-transparent bridge prioritizationprocess and poor construction quality. The RSDP had helped the DOR develop the BMS, which could be used for program planning fromthe beginning. It was also used for program monitoring. Therefore, it was an opportune moment for the Bank to support theDORs bridge program.Even if the implementation agency has extensive World Bank experience, comprehensivetraining at the beginning of program implementation is important if the PforR is a new instrument for the agency. The DORhad extensive experience in working with the Bank, and it was considered capable of managing fiduciary, social and environmental,and technical aspects of the SRN Bridge Program. However, the PforR was a new instrument with different processes and mechanismsand it took time to adapt to it. The DORsprocurement capacity contributed to the efficient program implementation, butthere were issues in managing works quality effectively given the poor performance of the field officials and weakcontrol structures. The SRN Bridge Program initially also suffered delays due to the clients limited understanding of thePforR requirements, especially for financial management, budgeting, managing social and environmental risks, and planning of theProgram interventions. Providing comprehensive training from the outset could have avoided problems and savedtime.Elevating OHS standards to internationally accepted level is challenging. The SRN Bridge Program hadbeen leading the effort to make construction sites safer. By program completion, it had made substantial progress in this regard byenforcing OHS measures on all sites and providing safety equipment to construction workers. However, the main challenge was toelevate Nepalese standards to internationally accepted/Bank standards. Fines and penalties for OHS breaches need to correspond tothe expected level of performance and risk associated with the implementation of works. Inadequate fines for OHS breaches canresult in inadequate performance by contractors and passing on of responsibilities. Other measures need to be properly enforcedfrom the beginning too, such as the submission and approval of the qualifications of OHS staff and the organizational chart andensuring that sufficient OHS officers are on-site to ensure a proactive rather than reactive approach to OHScompliance.Lack of bridge work construction quality can jeopardize the program results. Poor constructionquality had been identified as a risk at appraisal and was a constant issue throughout implementation. The main reason for the poorconstruction quality was the lack of resources in terms of DOR supervision staff and their limited experience to supervise theconstruction of new bridges. The PforR instrument contributed to enhance the quality assurance mechanisms by introducing anindependent verification mechanism and establishing the necessary procedures. A QAP was also introduced as one of the actions ofthe PAP. However, this was not sufficient. The issue could have been mitigated by hiring qualified consulting firms to undertakethe construction supervision and provide capacity building in quality control and assurance to the DOR staff.
P125496 | Integrated Modern Agriculture Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099322204262271933/text/P12549609cf6d00110be5b0d99028a60ce1.txt | http://documents.worldbank.org/curated/en/099322204262271933/pdf/P12549609cf6d00110be5b0d99028a60ce1.pdf | The ICR listed five lessons. The following two are highlighted that have broader applicability: Aframework such as Climate Smart Agriculture provides a conducive structure for addressing integrated challenges of climate change,food security and capacity building of farmers skills. The package of interventions that focused on investments inirrigation infrastructure, combined with dissemination of knowledge and institutional development of farmer organizations (WUAs,FCs, FAs) was critical to yield the results that the project achieved. According to the PAD (paragraph 28), projects that focusedon one dimension (e.g., infrastructure) may be easier to implement, but often do not lead to impacts such as improving farmerincomes without additional investments in on-farm technologies, and institutional support. Due to the integrated ClimateSmart model, as stated by the ICR (paragraph 89), the project was influential in mainstreaming the integrated approach intonational government policies and investment programs. Investments ininstitutional development of key stakeholders, particularly farmer organizations (WUAs, FCs FAs) are essential for the adoption andsustainability of technological change in agriculture. One of this projects key components focused on institutionalstrengthening and capacity building of farmers through trainings, awareness building, education, and technical assistance onclimate-smart agriculture, and in establishment of WUAs for improved OM of on-farm irrigation infrastructure. Asillustrated by the case studies (Annex 7), participation and ownership of farmer organizations in project interventions werecritical in the uptake and adoption of new technologies and climate-resilient practices promoted by the project.
P125506 | SN:Casamance Development Pole Project | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099442511222126269/text/Senegal000SNCa0lopment0Pole0Project.txt | http://documents.worldbank.org/curated/en/099442511222126269/pdf/Senegal000SNCa0lopment0Pole0Project.pdf | The ICR provides well-articulatedlessons, which highlight the benefits of community led, holistic and collaborativeapproaches to development interventions in fragile or post-conflict affected settings.Lessons summarized from theICR: Addressing the challenges of inclusion, fragility and sustainability characteristic of post-conflictsituations require multi-faceted investments tailored to local circumstances. This project supports experiences elsewherewhich demonstrate that addressing complex challenges in conflict affected settings requires holistic (i.e. economic, social,political, environmental), flexible approaches. Addressing inequalities through multi-faceted productive investments, aroundclusters with a territorial lens, is key, particularly to support agriculture production, improve transport infrastructure, andstrengthen connectivity with markets to create more job opportunities. This usually calls on multiple actors to collaborate and usetheir comparative advantages while being well anchored with local actors and tightly aligned with localobjectives. Economic empowerment of marginalized groups like women and youth are best supported by a focus on keyvalue chains with a holistic approach. Womens and youth participation in development processes are constrained bysocial structures and cultural norms which can negatively impact their ability to develop income generating activities and accessmarkets for their products. Future interventions should shift emphasis from supporting production only to addressing supportdownstream to access the market. This means considering in a holistic way the social, economic, and physical infrastructure needsof women and youth, in alignment with local traditional norms. Interventions must include corresponding indicators that can trackimpacts and are sufficiently disaggregated. Community based, holistic approaches strengthen social cohesion andresilience to shocks. The citizen engagement pilots provided the basis for ongoing strengthening of partnerships betweencommunities, healthcare systems, local governments and the private sector. Over the longer-term, development efforts canbuild on the network of trusted community leaders and facilitators as developed under PPDC to support community outreach andawareness, cooperate in vocational and skills training, and prepare for and respond to emergencies such as those arising fromclimate change and pandemics. This approach would be further strengthened if combined with information and communicationtechnologies such as the Geo-Enabling for Monitoring and Supervision (GEMS) would fit well within a fragilitycontext. Participatory planning, programming, budgeting and ME processes improve and guideimplementation. It is important to have a results framework that adequately captures the voices of beneficiaries directlyand throughout the project cycle, so that the understanding of barriers and impacts of PDO is informed by their perspective andfeeds into project design and implementation. The Citizen Engagement Committees provided a voice to beneficiaries and enabled thePPDC to cross check and ground truth project results throughout the project cycle. Integrating the twin conceptsof pole development and decentralization holds strong potential for long term development. Combining the macro levelcomparative advantages of a region, such as the agricultural potential of the Casamance Region, with the micro level understandingof social, economic, physical infrastructure constraints is key to advancing sustainable development at both levels. Bothapproaches reinforce each other. They also include specific institutions that should interconnect, such as the creation of regionaldevelopment committees with local participatory mechanisms (e.g., the citizen engagement committees created under PPDC), andgrassroots institutions such as POs, cooperatives and women/ youth groups.
P125509 | DRC Catalytic Project to Strengthen the INS | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | RETF | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/747631590060243455/text/Congo-Democratic-Republic-of-ZR-Catalytic-Proj-Strengthen-the-INS.txt | http://documents.worldbank.org/curated/en/747631590060243455/pdf/Congo-Democratic-Republic-of-ZR-Catalytic-Proj-Strengthen-the-INS.pdf | The following lessons are drawn from the ICR:Capacity constraints influence the sequencing ofactivities. In this case, while project design had project components feeding into each other staff training andan improved working environment were prerequisites for statistical production and disseminationsequencing was too ambitious in view of implementation capacity. More care could have been exercised inassessing the balance in terms of requirements for implementing the different components.Successful projectpreparation matches key indicators with realistic time frames for achievement. In this case, the initial set of outcomesdepended on actions that, while desirable and likely to be achieved over some longer time period, were unlikely to be completedduring the life of the project, requiring the introduction of new outcome indicators and targets.Incrementalrecurrent cost implications can inhibit successful outcomes. The experience of the operation, especially theunsatisfactory outcome on dissemination of statistical information, underlines the importance of being clear about the recurrentfinancing implications of a completed project.
P125528 | Dioxins Reduction from the Pulp and Paper Industry | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/135091584389933822/text/China-CN-Dioxins-Reduc-from-Pulp-and-Paper.txt | http://documents.worldbank.org/curated/en/135091584389933822/pdf/China-CN-Dioxins-Reduc-from-Pulp-and-Paper.pdf | The ICR drew seven lessons and recommendations from the projects experience. The following arethreelessons, mentioned in the ICR that have potential implications for other Bank-financed projects, with some adaptation oflanguage.1. Upstream analytical work may be particularly important, when addressing new sectors. Thisproject was prepared based on an analytical study conducted with the support of the Canada POPs Trust Fund. This work allowed theBank team and the implementing agency to gain knowledge of the sector and build networks with industry partners. The lesson is thatpreliminary analytical work can aid in quick preparation of the project.2. A combination of pilot demonstrationand enabling environment can aid in sector-wide transformation. This project relied on a relatively straightforwarddesign, that addressed the two key barriers that were identified through two complementary components (one focused on technicaldemonstration and one focused on sector policy and regulatory framework). The lesson is that combining demonstration withpolicy interventions is more likely to be successful in projects where new technologies are involved.3.Performance-Based Financing (PBF) sub-grants following commercial practices for procurement can be an efficient way to engageenterprises. Procurement under the PBF sub-grants in this project followed commercial practices that were acceptable tothe Bank, ensuring value for money in the process that met the mills business requirements andwas in-line with theirbaseline investments. The lesson is that the PBF modality, together with independent and credible verification,can be aneffective way of transferring grant resources to enterprises that were investing their own significantly largerresources.
P125565 | Electricity Sector Support Project | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2022 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061224175027171/text/P125565-d383960a-4f3d-45f0-ab45-d16fccc59b94.txt | https://documents.worldbank.org/curated/en/099061224175027171/pdf/P125565-d383960a-4f3d-45f0-ab45-d16fccc59b94.pdf | The ICR identified several lessons and recommendations arising from the experience of project implementation, and the mostsalient lessons are paraphrased as follows;Joint or co-financing with other donors needs to benefit from carefuldesign to avoid creating a context of additional administrative burden. The PoC with EIB took 23 years to negotiateand there was still no clarity on practical coordination or approach to simplify review and clearance. In future, it would be moreefficient to ensure regular donor coordination meetings and agree for all donors to rely on ones supervision to avoidparallel processes adding an additional layer and significantly higher risks of delays.Simplifiednational procedures should be discussed and arranged during project preparation and arrangements shouldmade to accommodate more efficient processing for the project. Procurement delays were quite significant and there weremany layers of approval, review, and then registration for the various contracts with processing times that were neither swift norconsistent. Given the number of contracts to be processed and the importance of relying on existing systems, it would have beenuseful to have determined clear procedures and reliable timing for the various steps to be monitored by a higher authority withinthe ministry responsible for oversight.Project indicators should be selected carefully to ensure that these can befully attributed to the project and capture the results adequately. While there may be common indicators used, the designand scope of the project, the simplicity and flexibility of the indicators, and the ability to capture data that is specificallyrelevant for the project (and not just the sector) are key to ensure that the project can demonstrate tangible and qualitativeimpacts. In this case, the losses indicator and quality of service indicators were relevant but had attribution issues, so there isscope to explore alternative measures. There should also be consideration for further reinforcing and building the ME capacityof the PIUs.
P125584 | MDTF KP Emergency Roads Recovery Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | RETF | IPF | 2012 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/392271488326383686/text/ICRR-Disclosable-P125584-02-28-2017-1488326378009.txt | http://documents.worldbank.org/curated/en/392271488326383686/pdf/ICRR-Disclosable-P125584-02-28-2017-1488326378009.pdf | The ICR (paras 67 to 71) contains five lessons of which three have general application beyond the project. These are notedbelow: Transport projects need to create awareness and build capacity for institutionalizingsafeguards for all national roads built by the client. In this project Pakhtunkhwa Highway Authority and theGovernment of Khyber-Pakhtunkhwa demonstrated reluctance to devote staff and resources to social and environmental compliancebeyond fulfilling minimum Bank and other project requirements. In emergency projects anumber of countries have used Information and Communications Technology (ICT) methods in the supervision of road works ininsurgency prone areas. This project could have used these innovative project monitoring mechanisms insteadof conventional monitoring (physical supervision of works by the Task Team). Informalcoordination and review arrangements are not a substitute for formal reviews and appropriate record keeping (such as AideMemoires Mid-term Review).
P125595 | Ghana - PPP Project | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/534361557936370499/text/Ghana-Ghana-PPP-Project.txt | http://documents.worldbank.org/curated/en/534361557936370499/pdf/Ghana-Ghana-PPP-Project.pdf | The following lessons are taken from the ICR with some adaptation of language: Vested interestsoften oppose PPP projects, which suggests that there needs to be substantial focus on SOE reform and regulation at project outset.Strong links between SOE reform and PPP reform are necessary. If a law is essential for project completion, analyzingpolitical economy issues at the outset raises chances for success, especially in thoseprojects involving difficult areas,such as PPPs .If such a law is essential for project implementation having it in place at the outset might be a precondition forproceeding with the project.IEG adds an additional lesson. If multi-phaseprojects are anticipated, the first project is often designed with the follow-on in mind. If circumstances change and the follow-onis cancelled, major redesign of the first project is often warranted.
P125597 | Kabul Municipal Development Program | South Asia | Afghanistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2014 | 2025 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099225104262240524/text/P1255970b18abf066096930e3c729cc746b.txt | http://documents.worldbank.org/curated/en/099225104262240524/pdf/P1255970b18abf066096930e3c729cc746b.pdf | The ICR listed lessons from the operationfor teams toconsider in FCV environments. Some of those lessons are listedbelowwith slightmodifications. Having alocal entity with anoperational mandate toimplement a project with subnational activities rather than anational agency with regulatory oversightmayavoidimplementation delays. The previous Kabul Urban RehabilitationProject was implemented by thenational Ministry of Urban Development. Implementation wasdelayedbecause the national agency had to negotiate withlocal municipal officials who were responsible for service delivery that the national entity was regulating. . In this project, thelocal government implemented the activitiesand avoided delays. The infrastructure outcomes were achieved in atimelymanner. Engaging the community strengthen ownership of urban upgrading. In this project, the bottom-upapproach ofcommunity consultations through Gozar CooperatingShuras (GCS) acceleratedsubprojectimplementation by providing feedback in the design of the area upgrading,theoperation and maintenance (OM)mechanism of community solid wastemanagement, and addressing disputes after receiving training in the Grievance RedressMechanism (GRM). The GCSwas also used to increase women participation in the project through 1,387 consultation sessions andelecting 94 women to the GCS(ICR,paragraph 63,footnote 23). The consultative mechanism usingthe GCS gaveresidents in a difficult operating environment a means for conducting asocial contract withitsgovernment. Careful navigation ofcenter/local relationships maylead topositiveoutcomes. In this project, activities were focused at improvingthe financial management of Kabulmunicipality.Perception of a central government hold on local concerns led municipal officials to bereluctanttouse acustomized MIS system that the Ministry of Finance was already using. This tension required constant dialogue toopenly addressconcerns and led to the eventual adoption of customized AFMIS modules for use by the Kabul municipality. Thisis relevant in fragile settings where institutional relationships and oversight are not always clearand capacitynascent. When faced by contracting challenges such as weak capacity, increasing security risks, and a lack ofwilling international consultants a strategy ofreducingreliance on international consultants, where practicable,adjusting outcome indicators that rely on them, and the use of technology may be useful considerations at design. In thisproject, implementing technical assistance-heavy institutional reformcalled for posting international consultants but theproject faced thechallenges brought by the willingness of available consultants to faceincreasing security risks. Theserisks also led torapid turnover rates of politically appointed leadership, renegotiated priorities, reconstitutedinstitutional set-ups such as tendering boards, procurement and contracting delays, andreluctance from internationalconsultants to conduct on the groundinstitutional reforms. This delayed the delivery of technical assistance, delayedinitiation, reduced completion of project activities. Target outcomes were originally set with some of these risks in mindbut mitigating measures proved to be inadequate. Future project design may need to consider the use oftechnology (audio andvideo conferences, remote communications, rather than in-person appearances) to deliver technical services, to encourageconsultants who would otherwise be deterred by difficult travel and living arrangements. The COVID-19 pandemic highlightedthebenefits ofthis course of action, such as in the teams conduct of virtual supervision missions at the time of thepandemic (ICR, paragraph 105). Even small improvements in financial management can increasetransparency,accountability and may improve expenditure management. In this project, the institutional reform infinancial management envisioned for the Kabul Municipality was meant to assist the local government in making informed decisionsabout expenditure allocation that met the needs of its residents. Ambitious andlikely to be tempered by identifying areaswhere capacity improvements may serve as foundational building blocks. In implementing some modules under the customized AFMIS, themunicipalityidentified ghost workers, ensured the timely payment of staff, and reduced fuel consumption. While these were notsufficient to achieve the projects outcome indicator, a taste of these small improvements may help motivate local movers andshakers to aspire for further improvements.
P125600 | Third National Program for Community Empowerment in Rural Areas - Disaster Management Support | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/960551472755488385/text/ICRR14882-P125600-PUBLIC.txt | http://documents.worldbank.org/curated/en/960551472755488385/pdf/ICRR14882-P125600-PUBLIC.pdf | The ICR formulated six key lessons, the most important ones are as follows (with reformulation of language):A clear and measurable results framework is essential to be able to adequately measure project outcomes and results. The development objectives should be clear and measurable and outcome indicators need to be linked to measure the overall achievement. Also, indicators and targets and baselines should be specific and clear. Measurements or studies undertaken after the project has been completed may be useful for long-term assessment, but cannot be relied on for management purposes as they do not enable early detection of implementation weaknesses requiring management attention. Disaster-affected communities need extra facilitation resources and remote areas present additional unique challenges. Communities need adequate support â€“ in the form of additional, experienced social and technical facilitators with local cultural knowledge â€“ to ensure sound implementation. Incentives (e.g. emergency allowances, the addition of â€œspecial skillsâ€ in professional facilitation qualifications, or priority for future advancement) should be developed that encourage experienced, skilled workers to step-up in times of disasters, and for any new recruits to be allocated to more stable environments. In recurrent, high-risk areas (such as around volcanoes), Community Disaster Risk Management mechanisms need to be integrated into the village planning process. In Indonesia, the Disaster Management Law and the Village Law can be mutually supportive in these areas, and good community participation as part of the annual process can help provide pro-active risk reduction and formulation of disaster management strategies. Community Disaster Management projects could benefit from broad approaches that not only include on infrastructure rehabilitation but also urgently build local capacity for communities to work together to respond more effectively to disasters. Project support just to address disaster damage may be too little: substantial support for community efforts to assess, plan, prioritize and implement activities, that may be difficult at the early stages right after the disaster, are also required. This particularly so for communities which did not lose physical assets but were economically effected by the disaster due to the downturn. For example two sub-districts receiving block grants had no physical damage from the disaster, but suffered severe economic downturns as a result and therefore these communities had difficulty developing sub-projects linked to the disaster. For the very early stages of recovery community-administered cash-for-work programs may be more appropriate.
P125689 | KG Financial Sector Development Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2021 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099192003102323090/text/P12568906c5ee20620bff00a0189682fe90.txt | http://documents.worldbank.org/curated/en/099192003102323090/pdf/P12568906c5ee20620bff00a0189682fe90.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A careful design and adjustment of the development objectiveshelps in better monitoring ofproject performance. In this project, the project scope was drastically reduced following the second projectrestructuring. However the Project Development Objective (PDO) was not revised to align it with the actual scope of the project.This negatively impact ratings as the project outcomes were assessed against bigger objectives than what could be achieved throughthe project interventions.2. A comprehensive approach may be required for modernizing a state-ownedenterprise. This project broadly aimed at modernizing the state-owned Kyrgyz Republic Post Office (KPO) and expanding therange of financial services provided by KPO. However, the project e project activities were confined to improving the ICTinfrastructure of KPO. The lesson is that reforms needed a major change in the corporate culture and institutional structure thatwere well beyond the scope of this project.3. Securing and institutionalizing high-level political commitment canhelp in overcoming delays during implementation. In this project, the Project Coordination Unit (PCU) did not havesufficiently high administrative profile and leverage. The lesson from this project is that when several government agencies andministries are involved in project implementation, forming a steering committee headed by a senior official at the PrimeMinisters office would signal a high-level political commitment and facilitate resolving implementation issues moreefficiently.4. A careful consideration of the full array of Bank instruments is required for a sectorreform. In this project, the project activity of privatizing the state-owned Ayril Bank was cancelled even before theproject became effective due to political resistance. On hind sight it might have been useful for the Bank to support a measure onprivatization of state-owned banks with a robust Advisory Services and Analytics (ASA) program and a specific prior actionunder a Development Policy Financing.
P125694 | Mauritius First Public Sector Performance Development Policy Loan | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2012 | 2013 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/402661467987847004/text/ICRR14811-P125694-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/402661467987847004/pdf/ICRR14811-P125694-Box393228B-PUBLIC.pdf | The first two lessons are drawn from the ICR. The third is drawn by IEG. In an environment where the reform agenda may be challenging, it may be better to focus on areas that can draw consensus to move forward. In Mauritius, the DPL focused on achieving short term gains to build consensus in a situation with multiple stakeholders.Strengthening social protection and improving competitiveness can be mutually reinforcing. The immediate social effects of efficiency-enhancing trade reforms can be mitigated by a stronger safety net that alleviates adverse impacts on vulnerable groups or individuals, if appropriately coordinated. Monitoring and evaluation needs particular focus in development policy operations. Such operations may include broad institutional changes where outcomes may be difficult to observe in the short term. Under such circumstances appropriate proxy indicators might be developed â€“ for instance combining partial quantitative outcomes with changes in internal processes to establish that changes are having tangible positive results.
P125740 | Tanzania - Basic Health Services Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2017 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/992701498236394601/text/ICRR-Disclosable-P125740-06-23-2017-1498236384632.txt | http://documents.worldbank.org/curated/en/992701498236394601/pdf/ICRR-Disclosable-P125740-06-23-2017-1498236384632.pdf | The ICR (p. 28-30) identified several valuable lessons, including the following: When a SWAp comprises bothon-budget and off-budget sources,it would be beneficial to have measures in place for consolidating the parallel sourcesunder the SWAp umbrella, for greater harmonization, to ensure complementarity and to avoid competing demands on humanresources. The functioning of ME should be a priority from the start of the project rather than towards the end.Bank teams should proactively revise the results framework if problems are identified (e.g. define SMART indicators for whichregular updates are available). Wherever possible, the results framework should include indicators that are already being trackedby the government to avoid the need to rely on additional player(s) for reporting on the projects outcomes. However, ifME systems rely on country systems, additional measures should be instituted that provide adequate quality assurance. In thiscase, the project could have factored in alternative mechanisms for validating/triangulating data, for example through regularsurveys, instead of relying fully on the HMIS. Similarly, third-party verification administered jointly with the government wouldhave been useful. The institutional arrangements of a project should match the country capacity. During design, rigorousassessment and/or in-depth analytical work should be undertaken to institute implementable activities. The institutional andfinancial arrangements of the pooled and non-pooled portions of the project continued as two parallel interventions. Also, it wouldhave been useful to have a detailed project operation manual so that subsequent teams could easily understand the project conceptand implementation arrangements. Frequent changes of Bank task team leaders (TTLs) can adversely affect implementationand outcomes. It is important to have well-organized handovers. The change in TTLs happens for a variety of reasons, but when thereare relatively frequent changes, as was the case for this project, systematic TTL handover is needed, as well as managementoversight of operational risks posed by frequent turnover.
P125799 | Judicial Performance Enhancement for Service to Citizen Project ("Mahkamati") | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2012 | 2017 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/631781516889734820/text/Morocco-MA-Judicial-Performance-Enhancement.txt | http://documents.worldbank.org/curated/en/631781516889734820/pdf/Morocco-MA-Judicial-Performance-Enhancement.pdf | The ICR offers several good lessons, including on the need for client ownership. These are summarized below using somewhatdifferent wording. Client ownership is a critical factor in successful project implementation.The implementing agency (MdJL) initially requested budget support; however, the Bank proposed this modest investment operation as afirst step towards a sector reform program that might lead to future budget support to the sector. Although the agency agreed, tobe consistent with the government, they were not fully on board, and ownership decreased further following a change in leadershipand priorities at MdJL.The modalities offered by the World Bank in support of reform efforts needto be aligned with the countrys institutional absorptive capacity and preferences. In this case, the loan amountwas limited, implementation required a major effort to follow applicable World Bank procurement and financial management rules, andthere was increasing perception that this effort and the amounts spent had low value added in comparison to the support to thesector from the EU.Project design should not be disconnected from the reality on the ground andshould adequately reflect political economy factors. For a bottom-up approach to work effectively, it would have requiredboth the client and the Bank to ensure effective involvement with pilot courts, local stakeholders, and civil society organizationsat the earliest stages and certainly during preparation. These efforts could not be left to the implementationstage.IEG adds another lesson:Institutional development support requires anagile approach that can adapt to changing circumstances to ensure ownership. This projects flexible design couldhave been easily adjusted to align with the governments National Charter for Judicial Reform as it evolved. Instead, theproject went on for too long without necessary decisions by the Bank or the borrower to make changes to improve its performance.Given the diminished ownership, a joint decision could have been reached earlier to close the project, and thus minimize costs ofprocesses not leading to expected results.
P125803 | Road Rehabilitation and Maintenance Program | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Infrastructure | Transport | IBRD | PforR | 2013 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/480981618847964828/text/Uruguay-UY-Road-Rehabilitation-and-Maintenance-P.txt | http://documents.worldbank.org/curated/en/480981618847964828/pdf/Uruguay-UY-Road-Rehabilitation-and-Maintenance-P.pdf | IEG usesthe following lessons from the experience of implementing this operation, with some adaptation oflanguage.1. The Program-for-Results (PforR) lending instrument can be useful for engagement at the sectorlevel. This approach provided the opportunity forthe Bank to thoroughly discuss sector-level issues toestablish abetter road network.This discussion committed not only the Ministry of Transport and Public Worksthatwould have been almost the only implementing agency in atraditional investment lending operation, but also the Ministry ofEconomy and Finance- the main financier of the program. This lending instrumentproved largely superior to previousinvestment lendingengagements in Uruguay, in terms ofinstitutional strengthening results.2. Themodalities of the PforR instrument needto be clarified at design. In this operation, the flow of fundswasorganized in such a way that the loan proceeds were disbursed directly to the treasury, with no earmarking to the Ministryof Transport and Public Works. While this could have demotivated theimplementing agency, the ministryproved tobe committed to meeting thetargets.This issue (that is the implementing agency does notdirectly receivetheloan proceeds) needs to be clarified forcountries using theinstrument for the first time.3. Thedisbursement-linked indicatorsneedto be selective on the governments program action plan. Inthisoperation, the governments program action plan was focused and concise in the original operation. However,followingthe approval of Additional Financing, the disbursement-linked indicators were too numerous, and consequently therewas a limitedbuy-in by government officials for some of them.
P125805 | Port au Prince Neighborhood Housing Reconstruction | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/462051519872352726/text/Haiti-HT-Neighborhood-Housing-Reconstruction.txt | http://documents.worldbank.org/curated/en/462051519872352726/pdf/Haiti-HT-Neighborhood-Housing-Reconstruction.pdf | As an instrument to transit displaced persons out of post-disaster camps, rental cash grants can be used to provide arapid response. The project had apositive experience with Rental Support Cash Grant and supported the development ofinstitutional tools for future disaster efforts to address the displacement of affected people. The project Operational Manualcould be used a tool, in other post disaster projects, to develop shelter solutions for displaced persons other than camps. In thefuture, targeting, and the sustainable and gradual phasing out ofa rental subsidy program, should be betterconsidered.Regular monitoring and follow up on the renters and clear alternative plans for the renters, who could notafford to stay after the phasing out of the rental subsidy, need to complement this instrument.Using aprogrammatic approach to project design in emergency situations can speed up implementation. In the reviewed project, theprogrammatic approach simplified project restructuring when it turned out that many of the relocated people were renters and notowners and it would be therefore necessary to support rent rather than housing.Community engagement can beinstrumental to managing disaster risks appropriately and efficiently, and support sustainability of the reconstructionefforts. However, in a post-crises environment, it is difficult to ascertain information about the make-up of thepre-crisis community. its identity, andinter and intra community perceptions and tensions that need to be mitigated alongsideinvestment decisions. Community engagement can also have the ill-effect of creating a perception that international donors aredelegitimizing the role of the state, and the way that it would like to be perceived. These political economy issuesneed to be handled with sensitivity.Disaster preparedness is critical and requires upfront investment in disasterrisk management capacity at several levels (national, local and within communities).The lack of available andupdated information on the quality of Haitis housing stock and other related housing data undermined projecteffectiveness.
P125805 | Port au Prince Neighborhood Housing Reconstruction | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2017 | 2019 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/742691559073488200/text/Haiti-Port-Au-Prince-Neighborhood-Housing-Reconstruction.txt | http://documents.worldbank.org/curated/en/742691559073488200/pdf/Haiti-Port-Au-Prince-Neighborhood-Housing-Reconstruction.pdf | 4. Lessons 4.1 In the case of catastrophic disasters or in fragile settings, the need to address humanitarian needs and disaster recovery may preclude significant impact on disaster vulnerability reduction.. The project was most effective in reducing disaster vulnerability through housing construction works carried out directly under the project, where improved structural standards could be monitored and implemented. Yet, these works were the least effective in supporting the return of the population to their communities; they concentrated substantial resources in supporting a relatively small number of households, they were challenging and slow to implement, and they were unable to meet the urgent housing needs of the displaced population. The general public was able to construct housing at much higher quantities and speed than donor projects â€“ but they did so without reducing their disaster vulnerability, because of limits in their financial resources, access to quality materials, and technical knowledge. 4.2 International NGOs can be effective project implementers in an emergency context where government capacity has been weakened. In Haiti, the earthquake further undermined already weak government capacity. International NGOs were able to implement construction works more rapidly than would have been possible in a government project. They may have technical expertise, community trust, and financial management capacity. However, the organizations also brought high costs, and missed 21 opportunities for building government capacity and fostering government legitimacy. In this case, the benefits outweighed the drawbacks. 4.3 Investments in infrastructure can have a larger impact on neighborhood recovery than those from direct housing reconstruction. In Haiti, qualitative evidence suggested that infrastructure works especially roads helped to catalyze investment in housing and businesses. In contrast, direct housing reconstruction was difficult to implement and had only a moderate effect on neighborhoods, as most housing reconstruction was private and especially informal selfâ€reconstruction. There was still a case for an integrated approach that included some housing support to signal good practice design and construction. 4.4 Disaster preparedness is critical and requires upfront investment in disaster risk management capacity and in relevant data and analytics, including geospatial data. The lack of available data in Haiti weakened response and reconstruction capacity in several ways. A lack of knowledge about housing ownership status contributed to an initial project response that did not do enough to support renters and landlords. The lack of an adequate land registry made it difficult to implement works, as it was difficult to identify legitimate owners. Lack of hazard maps and geotechnical data made it challenging to site new works. These kinds of data gaps were challenging to fill after the disaster had struck. 4.5 Projects seeking to support durable responses to crises in FCV countries may still need to include transitional measures, and to target durable measures towards vulnerable households. The initial project design was focused on durable development support\. housing and infrastructure (as compared to humanitarian or transitional assistance). During implementation it was recognized that many IDPs in temporary shelters constructed as humanitarian support were not sufficiently supported by the project approach, and a rental grant was added as a transitional measure. The project showed that cash grants for housing rental can be an effective approach for supporting internally displaced persons to rapidly transition from postâ€disaster camps to regular housing. The use of a rental support cash grant played a major role in allowing for camps to be wound down and closed. However, it did not provide durable housing solutions, and more than half of supported households were unable to sustain themselves in their new housing. This suggests that such programs must be complemented by other programs that support economic and social development efforts for displaced households. 4.6 Pilot efforts may have limited impact if they are not able to demonstrate a replicable model. Under the project, social housing pilots with joint ownership were generally implemented successfully. But achieving widespread results (for housing provision, increased density, or housing for the vulnerable) would require a model that could be scaled up. The pilots applied an almost fully subsidized rent to own model, where beneficiaries made only modest payments for a single year before gaining title. This meant that the model was heavily reliant on international donor grant funding. Consequently, there has been no replication of the model, and planned future multiâ€unit housing in Haiti are limited in scale and are not targeted towards vulnerable households.
P125837 | FYR Macedonia Policy Based Guarantee | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2013 | 2016 | ICRR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/708411473924023369/text/ICRR14928-P125837-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/708411473924023369/pdf/ICRR14928-P125837-Box396299B-PUBLIC.pdf | See PPAR for details.Â·
P125837 | FYR Macedonia Policy Based Guarantee | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2013 | 2016 | PPAR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/407921468951268611/text/106177-PPAR-P157216-PUBLIC-ppar-macedonia-policy-0716.txt | http://documents.worldbank.org/curated/en/407921468951268611/pdf/106177-PPAR-P157216-PUBLIC-ppar-macedonia-policy-0716.pdf | 6. Lessons 6.1 This operation offers several lessons for the future design of PBGs. Some may be of broader interest for the use of the instrument, while others are more project specific. 6.2 Regarding broader lessons for the use of the PBGs, the following three could be considered. 6.3 First, The PBG remains a fairly unknown and underutilized instrument globally, despite its potential. Therefore, the World Bank could usefully and systematically inform the borrowers of the PBG option and discuss its benefits and risks. Recent regulatory reform by OPCS, which brought PBGs under the umbrella of DPO policy regulation, is an important step in the direction of mainstreaming PBGs as a specific type of DPO. 6.4 Second, PBGs appear to be a suitable instrument of providing financing for the budget for other countries, expanding the World Bank's toolkit of DPO varieties. PBGs could potentially have wide applicability, especially, for example, in many small, vulnerable economies with substantial external financing needs and with a solid track record of macroeconomic performance, debt management, and policy reform and a good dialogue with the World Bank. But PBGs could also be relevant to larger World Bank borrowers with large, temporary financing needs combined with strong macro management and reforms. Demand for PBGs is likely to increase during periods of elevated market risks and worsened access and terms of sovereign borrowing. Anticipating these conditions and changes in demand for PBGs could be factored into the Bank's regional lending strategies. 6.5 Third, PBGs have the potential to leverage and increase the turnover of World Bank capital on the margin from the perspective of the country lending allocation. IBRD guaranteed â‚¬100 million of the total principal of â‚¬130 million. And with the PBGs, World Bank capital is released and available for existing and new client borrowers much earlier (after the five to seven years that PBG maturities typically have) compared with traditional DPOs (over 20 years). 6.6 It is important to recognize the potential risk to World Bank capital and, indeed, its financial standing associated with a potential default on one or more guarantees in the future. There is a risk of contagion to other PBG borrowers and consequent downgrading of World Bank client sovereign ratings. While this risk is currently small because of the small number of PBG operations, greater use of the instrument will require close monitoring and continuous risk assessments at the regional and global levels. 6.7 Several project-specific lessons have emerged, which may be of broader interest for the future design of PBGs. 6.8 First, while the direct financial benefits of PBGs to improve market access and terms of external borrowing, and the ability of a country to borrow more than under a traditional DPO, are substantial, there are other, indirect benefits. Those benefits could be usefully highlighted and explained to potential future borrowers based on the early PBG experience. For example, the borrower is able to establish itself in the eyes of international investors and broaden the investor base, which can be very useful for small countries that are not well known to international lenders. Also, by providing substantial external financing to the budget at the right time, PBGs can help temporarily both macroeconomic stability and economic activity by relieving pressure on the domestic banking system and allowing domestic banks to provide more credit to the private sector. 6.9 Second, strong and relevant design and high achievement is much more likely when the operation's design is informed by considerable knowledge work, intensive and longerterm World Bank engagement and dialogue, and, especially important, a relationship of trust between the World Bank and the Borrower. 6.10 Third, it is important to recognize that a PBG is no free lunch. The substantial financing it provides should not be used by clients to postpone but to facilitate reforms and necessary adjustments. Hence, a strong reform program is essential. Also, while the bullet repayment feature temporarily relieves repayment and fiscal pressure, it could add to borrower risk of repayment in the future unless it is accompanied by ex-ante provisions equal to the amount required under a standard annual repayment schedule. Repayment options and their pros and cons should, therefore, be discussed at length with the client. Standard repayment schedules should normally be preferred and bullet repayments should be accompanied by a World Bank recommendation (or requirement) to the Borrower to make annual provisions. 6.11 Fourth, this operation shows that the World Bank is particularly effective when it promotes the regional and global public good of country-to-country learning during preparation of similar projects in different countries. This is especially the case when testing relatively new instruments as was the case with PBGs. The FYR Macedonia PBG benefitted from consultations the FYR Macedonia government held with the government of Serbia on the costs and benefits and technical details of the operation. The World Bank took an active part in these consultations and encouraged this productive learning. The World Bank team itself has shown that the lessons from the first PBG in the region on Serbia were absorbed and integrated into the design of the FYR Macedonia operation. 6.12 Fifth, financial sector supervision and regulation can help preserve macroeconomic and financial stability in the face of substantial external shocks and adverse local conditions. At a time when many a country in Europe faced bankruptcy or major interventions of systemic banks, FYR Macedonia's fiscal and monetary authorities managed to maintain stability by a combination of active monitoring, a focus on stability, and anticipation of the impact of regional shocks.
P125866 | Mali RRSC | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/545101474940385440/text/000012394-20150310110014.txt | http://documents.worldbank.org/curated/en/545101474940385440/pdf/000012394-20150310110014.pdf | This evaluation draws three lessons from the experience of the RRSC:1.A good design is likely to benefit from a full analysis of risks, attention to putting in place robust mitigation measures, and designing appropriate targets that reflect those risks and mitigation measures.2.An M&E setup that clearly distinguishes outputs from outcomes may make it a more useful implementation management instrument.3. Where an operation seeks institutional changes, the likelihood of success will benefit from early design and preparation of those changes, not just from an outline that broadly defines what those changes are.
P125890 | Economic Governance Technical Assistance and Capacity Building | Western and Central Africa | Guinea | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099061923141037787/text/P1258900bbcb8d0020be2d0561a4a15a3ec.txt | http://documents.worldbank.org/curated/en/099061923141037787/pdf/P1258900bbcb8d0020be2d0561a4a15a3ec.pdf | The following five lessons are informed by the ICR and project documents (ICR, pages 24-25).Political economymatters, and it is important to be cognizant of vested interests and manage them carefully, especially for projects promotingcomplex and sensitive reforms. Comprehensive PFM and HRM reforms require adequate preparation including political economyanalysis, wide political and social ownership, consensus-building efforts, and feedback loops. Withoutsuch thoroughpreparation, the likelihood of success is low, undermining the achievement of potentially substantial, long-run gains for thecountry and society. While the initial design was aligned with government strategy, providing a sound policy base and relevance, itwas not realistic relative to the context. It benefited from some analytical underpinning, but no political economy analysis wasconducted to better understand the enabling environment for PFM and HRM reforms.Ensuring realism, prioritization, andsequencing of PFM and HRM reforms and testing the credibility and commitment of the government in pursuing such reformsisessential. The first-ever democratically elected government in Guinea developed a comprehensive and ambitious governance reformprogram to address the enormous challenges ahead. In attempting to support GoG priorities, project implementation suffered from ahighly complex and overly ambitious project design (and re-designs) that did not adequately account for the political economy ofPFM and HRM reform nor the credibility, commitment, and consistency of the government in pursuing such reforms. In such contexts,it is important not to take for granted that a democratically elected government would be fully committed to pursuing reforms.The governments political commitment and ownership should be analyzed and tested and be reflected accordingly in the projectdesign. Design should also adequately account for existing capacity limitations and the overall fragile environment.Foroperations with a long duration and high staff turnover, it is necessary to ensure candid reporting, which can help to mitigateinstitutional memory loss and provide reliable data for decision-making. Throughout implementation, there was a high turnoverof TTLs and procurement specialists, which meant the project could not maintain and benefit from the institutional memory on thepart of the WB. Three restructurings and one AF over ten years made it difficult for new project team members to track activities,indicators, and results, thus undermining the use of data for informed decision-making. A clear ToC,informed by rigorous analytical products, should be the foundation for developing project activities that provide data for acoherent ME framework. The absence of rigorous and targeted political and economic analyses conducted at appraisal and thelack of a ToC were major shortcomings that undermined the utility of the ME for informing implementation and measuring impact.This made it difficult for the ICR team to develop a coherent and comprehensive storyline for the ten-yearproject.WBTask Teams should be encouraged to close underperforming operations and develop follow-on projects thatincorporate lessons learned, especially in countries that experience protracted and unpredictable political transitions. Thenumerous changes made to the project across an AF and three separate restructurings in a country beset by a challenging transitionto democratic rule made it difficult to keep focused on the higher-level reform PDOs. The projects financing more than tripledand its implementation timeline expanded from four to ten years, while repeated redirection of its scope and resourcing contributedto uneven efficacy across all areas that the project attempted to engage. In such situations of substantial re-set and re-design,it would be better to initiate dedicated and organic policy dialogue and analytical underpinning that could lead to newproject/program design.
P125943 | Disaster Risk Management Development Loan with a CAT DDO | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2012 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/211281468186530132/text/ICRR14794-P125943-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/211281468186530132/pdf/ICRR14794-P125943-Box393191B-PUBLIC.pdf | The following lessons were summarized from the longer discussions provided in the ICR:(1) For DRM policy frameworks with multiple action areas across different sectors and a wide range of stakeholders, there needs to be a strong consultation process with various line agencies, civil society, the private sector, and academia, The consultative process via a Working Group can provide a vehicle for mainstreaming DRM in sectoral development.(2) Development Policy Operations with CAT-DDOs can help introduce broader concepts for Disaster Risk Financing and Insurance. As contingent credit, the CAT-DDO could be an affordable source of financing and complements existing market-based disaster risk financing instruments, such as insurance, catastrophe bonds, reserve funds, etc. These instruments can be combined to retain the risk from smaller, more frequent events, or to transfer the risk from less frequent, higher-impact events, based on an assessment of risks, desired coverage, available budget, and cost efficiency. These assessments can be supported through technical assistance, and implemented as part of a countryâ€™s overall DRFI strategy. (3) The â€˜soft triggerâ€™ for disbursement, which is a standard feature of the CAT-DDO instrument, needs to be supported by strong analytics in order to optimize the timing of drawdowns. (4) DPLs with a CAT-DDO can provide the opportunity to elevate DRM issues to oversight agencies (in particular, Finance, Budget, and Economic Planning) that may not otherwise be deeply engaged in the policy dialogue. (5) The implementation of a programmatic technical assistance to support the policy areas of the CAT-DDO can facilitate substantive policy dialogue, enhance implementation effectiveness, and sustain policy actions even after full disbursement of the loan. It is important for the Bank to provide adequate resources for implementation and technical assistance to sustain the policy dialogue with a broad set of DRM stakeholders. (6) Complementarity between ongoing World Bank investment projects and the DPL with a CAT-DDO can generate mutual leverage for achieving development objectives. This was particularly well illustrated by the policy actions related to addressing disaster risks in Community Driven Development and Conditional Cash Transfer operations, whereby the CAT-DDO provided the policy framework to pursue reforms which were implemented through the investment projects.
P125943 | Disaster Risk Management Development Loan with a CAT DDO | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2012 | 2015 | 2018 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/562121500310794328/text/114746-PPAR-P125943-P160285-PUBLIC.txt | http://documents.worldbank.org/curated/en/562121500310794328/pdf/114746-PPAR-P125943-P160285-PUBLIC.pdf | 6. Lessons 6.1 The CAT DDO proved to be a useful instrument in the Philippines for achieving the dual objectives of supporting fundamental DRRM reforms and providing quick-release financing for disaster recovery and reconstruction. The CAT DDO's strength stemmed from its being a budget support operation, which ensured attention of the finance ministry and other top level policy makers to DRRM issues. This was critical for getting all the relevant agencies on board and to integrate DRRM considerations into their regular work programs. Through this operation, the instrument has shown its ability to change the dynamics of the World Bank's dialogue with the country, facilitating a deeper and more comprehensive discussion about DRRM and allowing the World Bank to contribute its expertise at the macro level. At the same time, the CAT DDO, with a disbursement trigger, guaranteed access to financing when funds were most needed. 6.2 As with all policy reforms, in-depth analytical work and well-targeted technical assistance were critical for achieving results. In the decade before the approval of the CAT DDO, the World Bank and other agencies conducted several studies on the hazard profile and exposure of the Philippines and the social impacts of tropical storms on the poor. The recommendations from these studies, along with those from cross-country analysis of comprehensive DRM frameworks and actions, formed the basis for the design of this operation. Program implementation benefited tremendously from the GFDRR-funded technical assistance, which was prepared in parallel with activities fully aligned with the reform actions supported under the CAT DDO. The World Bank's comparative advantage in disaster risk financing was consistently recognized by all stakeholders consulted for this evaluation. In the context of this operation, there were multiple confusions over the purposes of a CAT DDO and proper use of the loan proceeds. Both the World Bank and the government understood that the contingent line of credit was to be used as partial financing to meet the immediate funding needs in the aftermath of severe natural disasters, but the government also stressed the budget support nature of the loan. To some extent, this explained the difference in expectations between the World Bank and the government as to how the CAT DDO resources should be used. In addition, there were inconsistencies between World Bank literature on the different applications of the various disaster risk financing instruments and the Program Document of this operation, regarding the types of disasters for which the CAT DDO resources were intended. Further clarification in World Bank documents and better communication between the World Bank and the counterparts would improve program design and facilitate its implementation.
P125952 | Pakistan: Second Sindh Education Sector Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/641021576777403518/text/Pakistan-PK-Second-Sindh-Education-Sector-Project.txt | http://documents.worldbank.org/curated/en/641021576777403518/pdf/Pakistan-PK-Second-Sindh-Education-Sector-Project.pdf | Lessons drawn from the ICR (pages 32-34), adapted by IEG: A results-based approach using disbursement-linkedindicators (DLIs)can be effective in helping a government move forward with a challenging reform agenda. In the case ofthis project, the disbursement incentive provided strong motivation to the government to follow through with difficult policychanges in the areas of school management and consolidation, although less so in the highly politically sensitive area of teacherrecruitment and rationalization. Central stakeholders indicated that focusing on DLIs helped to build consensus on sharedgoals. Leveraging the capacity of the private sector can be an effective means to improve access to schooling inrural and underserved communities. In the case of this project,an establishedpublic-private partnership with aperformance-based aspect - participating instudent testing - helped to not only increase access but toaddressquality of education. Country context is an important consideration in selecting key project indicators. In thecase of this project, the reality that late entry into schooling was common among children was not recognized at the time ofME design, thusthe original key indicator of net enrollment rate was not a sufficiently robust indicator tomeasure achievement.
P125958 | Pakistan: Second Punjab Education Sector Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/884651514478499347/text/ICRR-Disclosable-P125958-12-28-2017-1514478491838.txt | http://documents.worldbank.org/curated/en/884651514478499347/pdf/ICRR-Disclosable-P125958-12-28-2017-1514478491838.pdf | Lessons drawn from the ICR: The use of a results-based lending instrument createseffective incentives forgovernment action, and alsohelps to increasefocus on outcomes. In the case of this project, the use of tenDisbursement-Linked Indicators, several of which were critical to key education sector reforms,helped to ensure that policyactions were followed through and also helped to clearly identify the desired outcomes. The selection oftheoriginalPDO-level indicator did not adequately take into account local context. In the case of this project, the trendtowards late-age entry into the formal school system had a significant impact on Net Enrollment Rates, while School ParticipationRates were more accurate measure of the objective to increase child participation. Moreover, the shift to a new operationalmodel (inclusion of private sector) also warranted a reconsideration of measurement approaches.
P125961 | Afghanistan Rural Access Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099250003012230609/text/Afghanistan0000Rural0Access0Project.txt | http://documents.worldbank.org/curated/en/099250003012230609/pdf/Afghanistan0000Rural0Access0Project.pdf | This review has drawn two lessons based on the information in the ICR.Large scope and wide geographic spread ofa project can complicate procurement and contract monitoring in a fragile and conflict country. The project had a simpledesign consisting of rehabilitation of secondary and tertiary roads and construction of bridges, along with technical assistance incapacity strengthening for the sustainability of project outcomes, but the project scope was large covering all 34 provinces in thecountry. Coupled with the limitation on contract sizes, this resulted in hundreds of contracts overwhelming the procurement andcontract management capacity of the PIUs, especially that in the MPW. The ICR (p.26) states that increasing the size of contractsto the extent possible in a fragile and conflict context by geographic clustering could be considered for more efficient projectmanagement and to optimize resources for monitoring.In fragile or conflict countries, where project sites cannotbe visited due to security concerns, utilization of third party monitoring (TPM) can improve project monitoring andevaluation. The project team was not able to visit certain project areas because of worsening security situation. Afterthe onset of the Covid pandemic, the project team could not visit the country. The project hired a TPM for conducting visits toproject sites to observe and report project implementation. This TPM helped the project team to carry out effective supervision.The reports of the TPM company resulted in identifying non-compliant issues with fiduciary and safeguards policies, and in shiftingsome road works from MPW to MRRD, due to the heavy workload of the former, so that those works could be completed on time (seeSection 9.c ME Utilization above).Involvement of local communities in rural road projects in fragile andconflict countries can critically affect project outcomes. The rural communities were consulted in the selection of roadsto be rehabilitated under the project. Regular engagement with local communities and elders ensured successful implementation ofproject activities in an increasingly unstable political situation. The project provided technical assistance support to thecommunities in building local capacity to maintain the roads after project closure. The capacity built under the project should besufficient to maintain the roads to ensure sustained access of rural communities to these roads in the absence of a functioninggovernment in the country and insufficient funds.
P125964 | Mongolia Livestock and Agricultural Marketing Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/783941544713368475/text/Mongolia-MN-Livestock-and-Agricultural-Marketin.txt | http://documents.worldbank.org/curated/en/783941544713368475/pdf/Mongolia-MN-Livestock-and-Agricultural-Marketin.pdf | The ICR provided comprehensive lessons. The most relevant ones follow with some modification oflanguage.Public-private partnerships can be effectively developed on the areas of animal health andbreeding through the use of unique fee-for-service models. The project strengthened the public-private partnership bymaking targeted cold chain interventions for ensuring timely supply of quality vaccines. Likewise, it developed business models foranimal nutrition and animal breeding services (nucleus flocks) for overall improvement in productivity and quality of livestock.Partnership between the Government and the private sector can be done through performance-based contracts or output-based contractsto ensure greater efficiency and wider reach among herders.Matching grants can serve as effectiverisk capital instruments for building a productive assets base and making market connections for farmers, cooperatives andagro-processors. Microgrants helped vulnerable households invest in productive assets, thus kick-starting theirlivelihoods for increasing and diversifying consumption. Cooperatives and private sector enterprises used matching grants toleverage private capital/bank loans to deepen their service offerings and enter into productive partnerships (formal contracts)with herder households. Matching grants could be institutionalized under the Governments own program for incentivizing localgovernments and private sector for achieving higher productivity and unit value realization in the livestock sectordevelopment.Collaborative research initiatives in terms of research, innovation, and knowledgetransfer through extension can contribute to the enhancement of market competitiveness and may also improve access tomarkets. The project experience revelated that public extension system has nearly collapsed in the country. The Governmentneeds to expand and strengthen the local extension service delivery system for systematic research dissemination and adoption,particularly, in areas relating to climate-smart farming, production/processing, and affordable water. Risk reduction initiativesand eco-system services are needed to mitigate risks of extreme weather.A PIU integrated withimplementation structures of national programs for livestock and animal health can create opportunities for sustaining andmainstreaming project achievements. The strategic leadership of the project embedded in the Ministry of Food Agricultureand Light Industry with the PIU providing technical support for certain critical functions and enhancing capabilities forinnovative delivery can be helpful to mainstream the project activities.
P125996 | Distribution Efficiency Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/896941579623652622/text/Vietnam-VN-Distribution-Efficiency-Project.txt | http://documents.worldbank.org/curated/en/896941579623652622/pdf/Vietnam-VN-Distribution-Efficiency-Project.pdf | The ICR presented five useful lessons from the project. They are summarized below with some changes in presentation byIEG:To increase the likelihood of achieving PDOs, projects need to be designed in close alignment with governmentstrategies and objectives; have high technical relevance and solid preparatory work; maintain strong government ownership duringpreparation and implementation; and receive support from strong governance structures. Power system planning inVietnams energy sector is centrally managed but decision-making is collective. This process requires that all sub-projectsfor implementation should be aligned with the National Energy Development Strategy (NEDS). The lesson from implementing thisproject was that the collective decision-making process ensured that there was sufficient buy-in from the management and staff ofthe power companies, which increased incentives for successful project delivery.The achievement of outcomesdepends on technically sound analysis of sub-projects and maintenance of technical expertise within the sector. The PCscarried out a series of technical studies during project preparation to facilitate the detailed design of specific projectactivities. All five PCs conducted surveys during project preparation to assess the potential for smart grid technologies ineach PC, identify implementation challenges, and propose technologies for future development. This laid the groundwork for definingthe longer-term road map for introducing new technologies such as smart meters, SCADA, unmanned substations, and improvement in thebusiness services such as call centers, customers satisfaction, and so on. Technical resources also typically remainedwithin the energy sector, thus achieving technical stability within the sector institutions (MOIT, ERAV, EVN, and PCs), and therebyensuring continuity and sustenance of the project outcomes.The successful implementation of a large, complexproject requires close and effective supervision--both by the Implementing Agencies (IAs) and the Bank teamand capable staffin the IAs. Project management was complex given the large number ofsub-projects under three different componentsthat were implemented by five different IAs. The lesson was that the structure of project implementation encouraged decision makingat the lowest practicable level, to facilitate quick decision-making during implementation. The field-based Bank task teamconsisted of experienced team members, which facilitated close monitoring of project implementation. The project management boardestablished in each IA also had strong and capable teams, with cross-cutting technical and project managementskills.Flexibility in project managementincludingaspects of physical scope and approvalsisessential for the sustained success of large complex projects. The lesson from this project was that it was essential thatthe PCs (the implementing agencies) be able to quickly adjust to unexpected conditions as they arose. The project benefited fromthe flexibility of the phased approach to project implementation as decisions on sub-project selections were made based on thosewhich had the flexibility to be implemented more quickly. Continuously introducing further flexibility during projectimplementation also helped to shorten time for critical decisions.Involving all relevant stakeholders includinglocal authorities early in the project preparation process is critical to successful safeguard activities. Land acquisition and resettlement activities required for investments are becoming increasingly difficult in Vietnam. The project suffered delaysdue to delayed approvals for land acquisition, and in some cases, the works portion of five sub-projects could not be completedwithin the project lifetime; hence the project financed only the relevant material supply. The lesson from this projectsexperience was that there are benefits from early consultations with the relevant local authorities outlining the benefits andpotential impacts of the project and receiving their consensus before project implementation. For further strengthening theimplementation of social safeguards, the areas where more emphasis was needed included the following: (a) information disclosureand consultation at project preparation, in a more targeted/tailored manner; (b) implementation of developmental activities (forexample, training) provided to ethnic minority communities; and (c) close collaboration with the local authorities to match theproposed developmental support and local needs.
P125999 | PK Punjab Irrig Agri Productivity Improvement Program Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062823191024387/text/P1259990abed5a0d20a1a7069379df52f1b.txt | http://documents.worldbank.org/curated/en/099062823191024387/pdf/P1259990abed5a0d20a1a7069379df52f1b.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1. Toincrease the impact of infrastructure investments, a sustained dialogue between stakeholders and relevant institutionsonirrigation tariffsisrequired. Project results show that waterpricing is important to ensure the uptake of high-efficiency irrigation technology. The existing irrigation tariff structureprovides no incentive to adopt water conservation practices. Water pricing reform is necessary to invest in maintaining theirrigation infrastructure, discourage inefficient water use, and increase demand for water-saving technologies. Policy dialogue onsuch reform was ongoing during project implementation, and the irrigation tariffs were doubled in 2020. However, these rates stilldo not reflect the cost of water delivery.2. Increasing farmers access to financing sources can facilitatethe adoption of modern irrigationtechnologies. The high upfront investment cost and lack of access to financialservices constrain adopting of high-efficiency irrigation systems (HEIS). It is important to mobilize funding to help farmersparticipate in the technology market and increase demand for productivity enhancing solutions. This requiressupportingthefinancial sector to develop lending products/instruments suitable for the needs of farmers, particularly for productivityenhancement technologies (like HEIS).3.To ensure the successfulimplementation ofactivities,operational design should carefullyassess the strengths and weaknesses of existing institutional structuresinvolved in implementing project activities. While On-Farm Water Managements(OFWM)strong capacity toimplement water efficiency activities was well known, the support they needed to implement the next phase of strengthening valuechains was notwell understood. Because of this, the project could not implement the pilot on post-harvest processing andvalue addition as expected. Subsequent investments in irrigation need to include value chain development capacity within theimplementing arrangements.
P126033 | Regional Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/814031537536518091/text/Georgia-REG-DEV-1.txt | http://documents.worldbank.org/curated/en/814031537536518091/pdf/Georgia-REG-DEV-1.pdf | The ICR (pages 29-31) draws nine lessons from the experience of implementing this project. Of these, this review foundthatthreelessons were most important with broad application to similar projects that might be financed by theBank. These lessons are summarized below with some editing.(1) A deep understanding of country context isrequired for projects introducing an innovative design. Although this project was prepared based on extensive research andclose collaboration with government and other stakeholders, implementation was significantly delayed in the initial years due tothe weak implementation capacity of the Municipal Development Fund. Further, the potential issues associated with operatingand managing the assets were not identified by the preparation teamalthougheventually these were resolved by theMunicipal Development Fund in the final years of the implementation period. The ICR points out that lesson is thatshortcomings of project design that create implementation problems can be largely related to the rushed finalizationof project preparation, thus further underlying importance of patience in preparing innovativeoperations.(2). Given that forecasts of tourist demand are extremely difficult,thedesign of tourist development projects needs to provide flexible implementation plans to accommodate uncertain demand.In this project, some investments associated with tourism visitor centers were deemed to be not necessary, becauseof the relatively weak demand for tourism services and commercial space inspecific locations. Thepointisthat such investmentsshould be delayed despite their inclusion in the project design. Indeedsuch investmentswere, appropriately, not pursued in this project.(3) The project demonstrated the need fordeveloping appropriate methodology on ME frameworks fortourism development projects. Some of theindicators used in this project to measurethe extent to which the project activities contributed to improving theinstitutional capacity to support the development of a tourist-based economy could not be used because the attribution of thedevelopment of a tourist-based economicto improvements in institutional capacity in the tourist industry could not beestablished.
P126034 | Programmatic Development Policy Operation 1 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/475621515525895819/text/Kyrgyz-Republic-DPO1.txt | http://documents.worldbank.org/curated/en/475621515525895819/pdf/Kyrgyz-Republic-DPO1.pdf | The ICR distilled seven lessons: (i) the number of prior actions and areas covered by DPOs should be parsimonious; (ii) theprogrammatic nature of the operations should be reinforced; (iii) the critical foundation of success is a viable fiscal position;(iv) implementation of reforms can be strengthened through a unified and robust ME framework; (v) prior actions should focuson reform themes with demonstrated commitment of the authorities; (vi) design of prior actions should focus on critical actionsrather than only the first steps; and (vii) a candid assessment of commitment and capacity risks should be undertaken together withmitigation proposals.IEGconcurs with these lessons, and underscores the importance of maintaining arealistic scope when tackling difficult institutional reforms in a challenging environment. Although the issue of governmentcommitment and ownership was among the lessons from past DPOs that influenced the design of this series, it was, nonetheless, acause for the slower than expected progress in some policy areas covered by the series, and remains a lesson for future DPOs. Thechallenge appears to lie in recognizing genuine commitment from lip service,different levels ofcommitment acrossgovernment agencies, and thedistinction between commitment andimplementation capacity.
P126034 | Programmatic Development Policy Operation 1 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2022 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/099632207202288774/text/IDU086b92c0d03f960479009d680d3797f3c505b.txt | http://documents.worldbank.org/curated/en/099632207202288774/pdf/IDU086b92c0d03f960479009d680d3797f3c505b.pdf | 3. Lessons 3.1 The findings of this PPAR lead to several operationally relevant lessons. 3.2 In a high-risk context, DPOs that are narrower and more targeted may have a greater chance of success, with implementation supported by complementary interventions (for example, investment lending and advisory services and analytics). The scope of the DPOs reviewed in this assessment was quite broad, and few results were achieved linked to the critical constraints facing the country. Furthermore, the operations required the coordination of many ministries. A more targeted approach would allow for closer follow-up through policy dialogue focusing on fewer prior actions and on the agencies that demonstrated strong reform commitment. 3.3 Discussion of risks to the success of budget support operations should reflect the compounding of risks from other, parallel budget support operations. Several of the reforms supported by these operations were also supported by the Energy Sector 23 DPO and the Economic Governance DPO. Each of the operations was considered high risk. The Implementation Completion and Results Report Reviews noted that the risk to the sustainability of development outcomes was high. The mitigation measures that the teams identified in the program documents were insufficient; nevertheless, at each stage, the program documents expressed optimism that the reforms would be implemented. This suggests that a closer examination of the compounding of risk could have resulted in the cancellation of the second operation of the first series. 3.4 Analytics that take a broader view of the constraints to achieving a DPOâ€™s objectives (in this case, those related to private sector development) are needed to ensure a relevant design, and more narrowly targeted analytics can help justify specific reforms. The DPO series benefited from some standard Bank Group analytics to examine specific issues, but an overarching framework for identifying and prioritizing constraints to private sector development was missing, and the teams did not draw on available analytics from other donors. 3.5 The focus on governance and competitiveness was appropriate but raises questions regarding whether DPOs were the right modality in the Kyrgyz Republic to achieve reforms that frequently are slow to come to fruition. In the case of the Kyrgyz Republic, political will flagged early, but the World Bank continued to waive important triggers to provide budget support. In both series, policy actions in the initial operation were not followed by critical next steps, which compromised achievements. 1 A simplified business registration and taxation regime. See OECD (2020). 2 This Project Performance Assessment Report utilizes the objective that appears in the Independent Evaluation Groupâ€™s Implementation Completion and Results Report Review, which is consistent with development policy operation (DPO)1 and DPO2. The specific project development objectives of each of the operations are available in
P126038 | Competitiveness DPL | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2013 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/660941468618634941/text/ICRR-Disclosable-P126038-07-15-2016-1468618624574.txt | http://documents.worldbank.org/curated/en/660941468618634941/pdf/ICRR-Disclosable-P126038-07-15-2016-1468618624574.pdf | Among the lessons highlighted in the ICR are: Lending operations of the WBG, including DPLs, need to beunderpinned by adequate diagnostics and technical assistance programs. Examples include the analytical services oncompetitiveness and a technical assistance program under the Competitive Industry and Innovation Program Trust Fund that had beendone in FYR Macedonia. This array of knowledge work paved the way for this programmatic series of DPLs. DPLs oncompetitiveness can advance the mission of the WBG by leveraging the strengths of the private sector. For countriesthat aspire to become members of the EU, aligning program objectives and actions with the EU accession agenda is an effective wayto ensure adequate implantation of the reform program.
P126094 | Tunisia Governance and Opportunity DPL | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/959121474906205528/text/000020051-20140626002750.txt | http://documents.worldbank.org/curated/en/959121474906205528/pdf/000020051-20140626002750.pdf | IEG supports lessons discussed in the ICR. There are several important lessons drawn by the country team: (i) the adequacy of multi sector multi donor DPLs to consolidate the policy dialogue which is especially valuable in a transition environment, but the unsuitability of single tranche DPL operations for ambitious institutional reforms, (ii) the necessity of having an efficient government coordination mechanism with strong leadership and clear responsibility to monitor and sustain the implementation of an ambitious reforms program, (iii) the importance of technical assistance in policy areas where the government doesn't' have expertise/experience and where an innovative approach is required to change administrative practices, (iv) the need for a quality M&E framework to effectively assess the progress and outcomes of reforms, and (v) the benefit of locating the TTL and most of the team in the field, particularly for a complex operation involving other co-financiers based in the field, to efficiently and continuously interact with the authorities and donors. IEG adds another lesson, namely, the importance at the design stage to selectively and carefully sequence first-order policy reforms based on (i) specific political economy analysis of reforms in critical sectors, and (ii) an assessment of capacity constraints and other constraints inherent in the transition period.
P126130 | Tajikistan Health Services Improvement Project (HSIP) | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2023 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099090324180523389/text/P126130-d4c560fc-12a0-40e4-841a-e9221d82acf2.txt | https://documents.worldbank.org/curated/en/099090324180523389/pdf/P126130-d4c560fc-12a0-40e4-841a-e9221d82acf2.pdf | The following lessons drawn from the ICR are slightly edited by IEG:When tracking and assessing coverage ofpriority PHC services, the failure to ensure data to estimate service coverage within the targeted population groups and catchmentareas of the project can undermine the proper assessment of a projects outcome. In the case of this project,DHS survey data were initially used, but they were only disaggregated at the level of the region, not at the level of selectedhealth facilities supported under the project, or even at the district level, and so were not sufficiently representative.The projects subsequent reliance on administrative data pointed to the importance of (a) capturing in the numerator allhealth service providers in a geographic area; and (b) the availability of reliable data on the denominator derived (or calculated)from the administrative data. Moreover, ensuring ME capacity to measure all relevant service indicators is important early ina project.When a pilot of a complex reform like PBF is not closely aligned with a countrys financial andtechnical capacities and when exploring and crafting a feasible vision for scaling is not part of the pilot process from theoutset, Government ownership and propensity to continue such a reform post-project is likely to fall short. Theproject addressed highly relevant challenges with an evidence-based design. But while the magnitude of PBF bonuses likelycontributed to impacts, the bonuses posed a fiscal challenge and nationwide scaling remained beyond GoT capacity. Greater andearlier focus on fiscal sustainability, technical capacity building beyond the pilot areas, and deeper collaboration of PCG expertsand MoHSSP may have increased the probability of scaling up under GoT financing.A further deepening ofinstitutional integration and daily collaboration betweenMinistries of Finance and ofHealth and Social Protection ofthe Population is likely to enhance Government ownership and sustainability of health financing reformspost-project. The project was the first health operation in Tajikistan under which the Minister of Health and SocialProtection of the Population headed the PCG. Still, coordination between the Ministry of Finance and MoHSSP, as a crucialactor for health financing reforms, remained limited in practice and contributed to lack of GoT ownership and meaningful dialogueabout sustainability. The follow-on operation attempts to overcome these obstacles by: (a) closely coordinating design withMoF and MoHSSP at Minister-level; (b) an institutional arrangement making MoHSSP department heads leads for appropriate componentsof the projects reform falling within their domain; and (c) an Intersectoral Committee chaired by the Prime Minister withMinisters of Finance and Health and Social Protection of the Population functioning as deputy chairs to coordinate health financingreforms.Paying more acute attention to the challenges of attracting and retaining healthcare workers is likely toinform and enhance the design of training and selection of candidates, as well as broader financing and human resource reforms inthe health sector. The IE revealed that even the large salary incentives under PBF did not increase health workerretention rates, given the strong pull of better income opportunities for Russian-speaking specialists in surrounding countrieslike Russia. This challenge might be better assessed and addressed in future sector-wide reforms.
P126155 | Malawi - Rapid Response Development Policy Grant | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2013 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/413671475071039084/text/000020051-20140626123907.txt | http://documents.worldbank.org/curated/en/413671475071039084/pdf/000020051-20140626123907.pdf | The ICR draws a number of appropriate lessons: (1) Strong Government leadership and political will are essential ingredients to a successful operation; (2) A longer term partnership and alignment with the Government's priorities are instrumental in enabling a quick response to short term needs; (3) Coordination with other development partners and complementarity with other Bank activities facilitated the preparation of a coherent strategy. Perhaps the most important lesson is: (4) It is challenging for DPOs to address governance issues.
P126157 | Rural Service Delivery and Local Governance Preparation and Pilot | East Asia and Pacific | Papua New Guinea | Blend | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2014 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/109331549924204221/text/Papua-New-Guinea-Rural-Service-Del-and-Local-Govenance.txt | http://documents.worldbank.org/curated/en/109331549924204221/pdf/Papua-New-Guinea-Rural-Service-Del-and-Local-Govenance.pdf | The following four lessons were extracted from theICR:1. The ward-level grant size needs to be adjusted topopulation size and needs of the community. For example, the original grant size of US$17,000 was not sufficient to meetall the standard building designs. Costs of materials and transportation to remote locations were under-estimated. Thesame size grants spread across all LLGs, while it seemed fair, did not take into account population density and therefore was notequitable. With adjustable grants, the investment per person can remain roughly equal across various wards and districts(ICR, pg. 32).2. Communities need substantial support to prepare, design, andimplement sub-projects, particularly in remote and rural areas. For example, communities that received additionalsupport from community facilitators and technical facilitators were able to implement the sub-projects more successfully. Trainingneeded to be followed up with substantial follow up support and coaching. Having standard designs, bills of quantities and budgettemplates which can be adjusted by the community groups proved to be a workable solution for communities (ICR, pg 32).3. Sub-project selection process needs to be streamlined at the ward level. Forexample, the Bank over-estimated the capacity of LLGs and the local communities to develop detail Ward profiles and developmentplants in a participatory manner. Furthermore, there was limited information on to objectively assess which wards were the poorest.Trying to select wards on a need-basis and through a competitive process did not work as expected. In the follow-up project,communities are expected to submit an expression of interest and based on an initial assessment, then communities will be asked todevelop a full proposal.4. Coordination with provincial and districtlevel authorities to ensure operational and maintenance funding needs to take place during the selection process.For example, while LLGs technical committees consulted with district and provincial level agencies for their endorsement ofproposed sub-projects, securing funding for reoccurring costs was difficult. Where possible, written commitments to coverreoccurring costs, especially related to teachers, health service providers, medicine, etc., must be included in proposals orexpression of interest stage. The project recommends that provincial and district staff also attend LLG committee meetings tobuild buy-in and follow through their commitments to support reoccurring costs (ICR, pg. 33). Alternatively, subprojects shouldfocus on issues that do not require government support such as water catchments, small access roads, provision of transportation(motorboat), and infrastructure needs (bridges). The ICR suggests that given the high ERR for the water catchment projects,and the high completion rate, focusing on water and station projects could also fit with the recommendation for geographic orsector converse in an FCV context (ICR, pg. 33).
P126162 | Institutional, Tax Administration, Social and Investment (INSTANSI) DPL | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2013 | 2013 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/213471468178157482/text/ICRR14693-P126162-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/213471468178157482/pdf/ICRR14693-P126162-Box393183B-PUBLIC.pdf | IEG draws the following lessons from the experience of preparing and implementing this DPO series:It is important to have consistent, clear and specific objectives (as noted in the section 2.a, this was not the case). This was further exacerbated by the fact that the ICR had a different interpretation of the objectives. Careful consideration to the internal coherence of a program supported by a DPL series and ensuring the appropriate number of operations is envisaged from the outset would help achieve significant reforms. In this case, in practice, there was limited synergy between the two pillars, one of which was heavily diluted at the time of the second operation. Furthermore, reforms being supported may need to be sustained over a longer period than that covered by the series. In such cases, a series of individual DPLs may be more appropriate than a programmatic series. Otherwise, programmatic lending may not be the best instrument when there is significant uncertainty surrounding policy options of the Government and stand-alone DPLs may provide greater flexibility and lead to better results.Systematic formal supervisory reporting can assist monitoring when there are significant modifications to the program. There were such changes in design between the first and second operation, and the cancelation of the third DPL had implications in terms of results and policy dialogue that could profitably have been brought to management attention in a timely manner. The date when an indicator is measured would need to be consistent with the operationâ€™s implementation period. In this case, results were to be measured some 12 months after the closing date, and there was uncertainty over whether there would be a third operation. This could have been removed by extending the period of formal supervision (and hence the closing date) for a year later.
P126180 | Sierra Leone Energy Access Project - Sierra Leone Infrastructure Development Fund | Western and Central Africa | Sierra Leone | IDA | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2013 | 2018 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/583991528139466935/text/Sierra-Leone-Sierra-Leone-Energy-Access-Proj-SLIDF.txt | http://documents.worldbank.org/curated/en/583991528139466935/pdf/Sierra-Leone-Sierra-Leone-Energy-Access-Proj-SLIDF.pdf | The IEG selected the following main lessons from the ICR, with some modification of language.(1) Implementationreadiness at appraisal and adequate ME are essential for effective supervision. This is particularlyimportantin fragile environments. Delays in launching of this project due to inadequate preparation of bidding documents and inadequatestaff in the Project Management Unit (PMU) and weakness in the PMU hampered the collection and dissemination of the informationrelated to project implementation progress.(2) One option that could prove effective in strengtheningtechnical capacity of the institutions is bringing in external expertise during implementation. In this project two yearsafter effectiveness, the project was experiencing delays, because of the lack of technical know-how on the part of the implementingagencies.(3) Progress in reforming the energy sector may require infrastructure investments along with changes inpolicies governing the energy sector. Some of the policy measures that helped in realizing the outcomes were factors suchas unbundling the sector, tariff increases and the prepayment system in revenue collections.(4) The involvement ofbank specialists at design could help in improving compliance with social and environmental safeguards. In this projectinsufficient attention on the part of both the Bank and the borrower to oversee compliance with social and environmental safeguardsundermined compliance of safeguards relating to involuntary resettlement during implementation.
P126193 | Second Phase of the APL on Strengthening Regional Cooperation for Wildlife Protection in Asia | South Asia | South Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/791831518531517207/text/South-Asia-REG-Wildlife-Protection-Phase-2-Bhutan.txt | http://documents.worldbank.org/curated/en/791831518531517207/pdf/South-Asia-REG-Wildlife-Protection-Phase-2-Bhutan.pdf | The following lessons are adapted from the ICR with some adjustment of language. Regionally shared goalsacross a group of countries that include country specific investment opportunities for participants can provide incentives forcollaboration in addressing transboundary conservation challenges provided there is strong and sustained commitment byparticipating governments. In this case, there was no possibility of dealing with illegal wildlife trade withuncoordinated or poorly coordinated individual actions. Tracking the trade and shifting supply and demand pressuresin illegalwildlife products inevitably requires coordination and cooperation across boundaries. An institution such as SAWEN was essential tobroaden the scope and scale of regional cooperation and, once established, to sustain it. Regional projectsfocusing on global public goods need substantial time to prepare because they are difficult to design and implement and requirestrong prior analysis of participants capacities and commitment and of participants coordination.In thiscase, a hastily prepared project resulted in initial implementation delays that took time to rectify with an inevitable impact onthe projects early progress. Projects piloting novel approachesto cooperation ontransboundary wildlife issues need to have measurable indicators from the outset that will trace at leastintermediateoutcomes if not, where feasible, outcomes in terms of changes in illegal trade. In this case, indicators were not wellformulated and there was a risk of not demonstrating success early enough and consequentlylosing meaningful countryparticipation and engagement. Such indicators initially may reach only to intermediate outcome levels, leading later to themeasurement of true outcomes in reduced illegal wildlife trade and regional cooperation. In projects addressingtransboundary conservation, including illegal wildlife trade, a sustainable approach can only be built on the establishment ofinstitutional capacities across and between participating countries and in the development of cooperation processes. Inthis case, a less ambitious alternative would have been to merely strengthen the training of borrower staff to enhancecapacity to tackle activities aimed at conservation and prevention of illegal trade but this would have been a half measure withlittle prospect of sustainabilityor growth of sustained cross boundary coordination.
P126193 | Second Phase of the APL on Strengthening Regional Cooperation for Wildlife Protection in Asia | South Asia | South Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2017 | 2019 | PPAR | Less than 10 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/193081549297156311/text/132872-PPAR-P126193-P166768-PUBLIC.txt | http://documents.worldbank.org/curated/en/193081549297156311/pdf/132872-PPAR-P126193-P166768-PUBLIC.pdf | Lessons 7.1 Robust upstream work that builds strong and sustained commitment by all governments participating in a regional approach to wildlife protection is a necessary condition for success. In the case of the SRCWP in Bhutan, there was strong regional collaboration with Bangladesh, Nepal, and India on strategic wildlife conservation issues generated in regional meetings on curbing the illegal wildlife trade even before the project began. These regional meetings proved quite effective in synchronizing national policies, sharing useful experiences, coordinating wildlife law enforcement approaches, and disseminating effective new practices for adoption by the participating countries. 7.2 Projects involving multicountry collaboration on global public goods are challenging to design and implement, making the provision of adequate preparation time critical for conducting necessary analyses of participating country commitments and capacities. The SRCWP in Bhutan was hastily prepared, at the expense of a thorough analysis of the government of Bhutan's institutional capacity to implement the project and the capacity of the nongovernmental sector to develop adequate technical proposals and implement appropriate investment subprojects. This resulted in initial implementation delays that had a significant bearing on project implementation and progress. 7.3 Projects piloting new approaches to multicountry collaboration on transboundary wildlife management present challenges that require a carefully designed results framework to measure and track progress in achieving project objectives. In the case of the SRCWP in Bhutan, the initial indicators for the development objective and intermediate outcomes were not well developed at the design stage and required revision to capture project progress in achieving objectives clearly and accurately. 7.4 Projects designed to build national institutions and capacity for multicountry collaboration on transboundary wildlife management require a long-term investment to ensure successful outcomes. In the case of the SRCWP in Bhutan, the use of an APL to support regional initiatives for wildlife protection was well-advised, recognizing that the APL instrument would allow other countries interested in wildlife conservation to join the countries of South Asia, and that regional capacity building to support wildlife conservation would require long-term technical and financial support (more than a one-project, five-year commitment). In the end, no other countries joined Bangladesh, Bhutan, and Nepal in the APL, and there was no follow-on project to consolidate achievements and institutionalize regional capacities. A strategic opportunity was missed.
P126207 | BF- First Growth and Competitiveness Credit (GCC-1) | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2018 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/165181512660871959/text/Burkina-Faso-First-Growth-and-Competitiveness-Credit.txt | http://documents.worldbank.org/curated/en/165181512660871959/pdf/Burkina-Faso-First-Growth-and-Competitiveness-Credit.pdf | This review draws the following three lessons (with the first two from the ICR):1. Inadequate consultation with allrelevant stakeholders increases the risks that draft legislation submitted as a prior action will not pass opportunely to achievethe expected effects. The draft mining code and anticorruption legislation suffered from inadequate vetting, resulted in lateapproval, and had no impact during the program.2. In low capacity environments, objectives to buildcapacity may be more appropriate than objectives to achieve the long-term welfare goals of added capacity. Capacity building mayhave been what the less ambitious DPO4 program objectives (to enhance the governments ability in three areas) aimed for.However, such enhancements need to be measured. For example, enhanced government ability to reduce costs in agriculturerequires evidence to link reforms to cost reductions. Implementing reforms (by capitalizing the input fund) alone is not evidenceof the expected outcome.3. Mitigation of risksis unlikely tobenefit from mitigation measureswith impacts that are dependent of the risks that the measures aim to mitigate. For example, reforms to expand cotton productionwill hardly qualify as a mitigation measure for the risk of unanticipated production and/or price shocks on cotton production.
P126207 | BF- First Growth and Competitiveness Credit (GCC-1) | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2018 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/494031533935601565/text/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.txt | http://documents.worldbank.org/curated/en/494031533935601565/pdf/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.pdf | 6. Lessons â€¢ When political risks are high and capacity is strained, design is better focused on a few key priorities. This series covered too many areas, and some key binding constraints were not addressed. The series might have been more successful with a sharper focus on more realistic objectives accompanied by a simpler design. â€¢ The success of budgetary support depends on the suitability of the instrument to the country environment. In a context of political turbulence and uncertainties about the government's ability to undertake long term reforms, the World Bank could have ended the programmatic series after the third operation and made the fourth operation a stand-alone. Alternatively, the World Bank could have implemented a series of stand-alone operations after the second programmatic series when it became apparent that the political and policy environment was rapidly changing. â€¢ Lack of clarity on the respective roles and responsibilities of central and local governments and of the private sector undermines policy actions. It is important to ensure that there is a shared vision and that the need for reform is recognized and accepted by all parties. In this case, there was a lack of clarity among different stakeholders during implementation of the reforms on decentralization and fertilizer distribution. â€¢ When M&E is not adequately resourced or implemented, there can be delays in the identification of problems and the application of remedies. M&E weaknesses can be compensated by leveraging information available elsewhere, or through specific impact assessments and perceptions surveys. â€¢ There may be a trade-off between the promise of continuous and predictable financing, urgently needed in times of crisis, and the strength of the reform program. In Burkina Faso the emphasis was on continuous financing even when reform performance was waning. â€¢ The lack of broad consultations with stakeholders when the World Bank is designing a complex reform program could lead to unsatisfactory results. In this case, the lack of consultations with an important stakeholder association (the Confederation Paysanne du Faso) on fertilizer distribution affected the achievement of results of one of the first objectives. Also, some development partners and civil society organizations had limited knowledge of the reforms pursued in the G&C series. â€¢ Consultation with all important stakeholders is critical to inform program design. In this case, development partners, civil society organization, and academia complained to the PPAR mission about inadequate consultation by the World Bank. â€¢ Inadequately resourced implementing agencies will likely be unable to carry out agreed reforms. Under-resourcing may be an indication of low government commitment, which needs to be addressed through policy dialogue. It is also important to ensure that agencies have appropriate technical capacity and systems in place, and that potential political obstacles at the local level are being addressed.
P126210 | Chongqing Urban Rural Integration Project II-Health | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2012 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099230001132229397/text/China000CN0Cho0ural0Integration00II.txt | http://documents.worldbank.org/curated/en/099230001132229397/pdf/China000CN0Cho0ural0Integration00II.pdf | The ICR (pp. 33-34) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:Increasing population access to hospital care through infrastructure development is facilitatedby improved service quality and competencies of health personnel and hospital managers. Constructing hospitals andequipping them could narrow infrastructure gaps, but hospitals can contribute to improved health outcomes only if health personnelhave adequate skills to function in line with clinical guidelines and protocols. The project design combined activities related toinfrastructure development with service quality improvements, capacity building, and health system reforms to maximize theachievement of intended outcomes.Providing sufficient preparation time and resources enhancesimplementation readiness, notably for projects with high technical requirements and design complexities, such as in hospitalinfrastructure development. Under the project, construction was delayed because preparatory arrangements, includingconstruction designs and bidding documents, were not completed. A reasonable scheduling balance can be reached to meet bothproject delivery expectations and implementation readiness requirements.The provision of specifictraining to hospital directors who monitor major civil works at their hospital sites can facilitate effective oversight.As major construction at existing hospital locations is relatively infrequent, hospital directors usually have limitedexperience in coping with construction complexities. Most hospital directors opted for multiple small contracts instead ofintegrated contracts, thus overloading and complicating implementation and its sequencing, including for procurement and contractadministration. Specific training programs can be provided during project preparation, before launching actual implementation, toequip the involved hospital directors with essential know-how about the development and delivery of hospital constructionprojects.Additional lesson identified by IEG Review:Augmenting staffresponsibilities by accumulating project tasks on top of existing full-time workloads without compensation can result in high andpersistent staff turnover that has negative impacts on project implementation. Under this operation, projectresponsibilities were assigned to hospital management teams and key staff of project implementation units, who were full-time staffwith pre-existing responsibilities. Regulations in China disallowed financial compensation. The additional workload resulted in ahigh and persistent turnover combined with repetitive training and a steep learning curve for newcomers, all hindering a steadypace of project implementation. Other forms of suitable incentives could be explored with the authorities and concernedstakeholders in future operations.
P126226 | Eighth Poverty Reduction Support Credit (PRSC8) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/172141475111853059/text/000020051-20140626111920.txt | http://documents.worldbank.org/curated/en/172141475111853059/pdf/000020051-20140626111920.pdf | The lessons from the ICR are broadly supported by this Review: Clearly specified policy and institutional reforms are central to ensuring that outcome indicators in performance assessment frameworks are linked to concrete actions rather than vague aspirational goals. PRSCs will have the greatest impact when they focus on a road map of prioritized institutional changes and related policy measures. Progress can best be measured with indicators linked to concrete actions, while ensuring that effective monitoring will be achievable within the limits of statistical and M&E capacity.The risk to reforms can be mitigated by addressing potential political economy constraints throughout the reform process. Reforms to public resource management, and strengthening the legal and institutional framework for business development and efficient land use, will inevitably attract the attention of powerful interests. While some controversial reforms will be delayed or blocked by political processes, the risk of this can be mitigated through an inclusive consultative process, supported by careful analysis of under-appreciated benefits that can help to build coalitions of supporters.Reformers may gain better traction by shifting focus in response to changing conditions. Reform priorities can often be usefully adapted to better respond to changing economic and social conditions and international developments. Implementation challenges may also be resolved by switching focus to a different policy area where there is a critical mass of political support and/or implementation capacity, rather than pushing for results that are unattainable within the time frame of the series.Reform success requires that implementation capacity constraints be identified in advance in order to guide the design and provision of technical assistance. Poverty reduction programs tend to be ambitious and complex, requiring capacity at many levels for reform implementation, and appropriate and timely monitoring and evaluation. Meeting these challenges requires an adequately designed and targeted program of technical assistance, in the short run, coupled with sustained capacity-building support over the long run.
P126229 | YF Innovation Serbia | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/686311487006393129/text/ICRR-Disclosable-P126229-02-13-2017-1487006379122.txt | http://documents.worldbank.org/curated/en/686311487006393129/pdf/ICRR-Disclosable-P126229-02-13-2017-1487006379122.pdf | The four lessons are drawn from the ICR (pages 37-38), with some adaptation.One, a capable national innovationagency is integral to a national innovation system. The IF developed into a well-functioning institution responsible forstimulating innovative activities in the enterprise sector in the Serbia. Itwas staffed by qualified and committedprofessionals, who are competent and fairly compensated. Itwas highly regarded by entrepreneurs who are beneficiaries of itsprograms, as well as by its peer institutions in other countries. It will serve Serbia well if it continues to nurture the IF.Additional rounds of capacity building and staff renewal to meet new client needs will strengthen the institutions capacityto respond to changing local and global innovation challenges.Two, governance mechanisms are vital to the effectiveand efficient delivery of support for innovation activities. The IF operated a transparent beneficiary enterprise selectionprocess. It placed a premium on the merit and commercialization potential of candidate projects. Its decisionswere made by anindependent Investment Committee. Itwas responsive to guidance from a professional global advisory team. Consequently, the IFemerged as a credible institution. It developed the ability to mentor enterprises. And, it built up the capacity to absorb anddistribute European Union funds for innovation projects.Three, the horizontality of innovation policy matters innascent innovation ecosystems. A horizontal innovation policy involves placing the broader strategic approach above departmentalgoals, by integrating objectives and priorities across various policy sectors (OECD, Governance of Innovations Systems,2005). In the post-transition economy of Serbia, dominated by entrenched state enterprises and government research developmentinstitutions, it was widely expected that the innovationproposals would be limited to information and communication (ICT)technology and to digital technology projects in the Novi Sad and Belgrade areas. By adhering, however, to a horizontal policy thatemphasized merit and commercialization potential, the IF discovered a robust pipeline of projects across diverse economic sectorsand geographic locations.Four, visibility helps an innovation program gain momentum. In this regard, the Bank canpick up lessons from the European Union by advertising project activities more prominently, sharing lessons learned more widely,and celebrating successes more openly. The project opening ceremony allowed the IF management team, the Investment Committee, andthe advisory board to discuss the project objectives and to showcase their institutional capacities transparently, a move thatassuaged the initial skepticism of the entrepreneurial and the research communities. The project closing ceremony celebrated theadvances made by the innovation ecosystem over the course of the project, showcasing the more than fifty entrepreneurs whodisplayed their products and prototypes, the investor groups that supported the start-ups and spin-offs, and the IF and the RDIsthat strengthened their capacity to help stimulate innovation by enterprises.
P126263 | Bangladesh: Repatriation and Livelihood Restoration for Migrant Workers | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2012 | 2014 | ICRR | >=25 million & <50 million | Highly Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/317511474665090108/text/000020051-20140626104447.txt | http://documents.worldbank.org/curated/en/317511474665090108/pdf/000020051-20140626104447.pdf | Lessons from ICR1. Simplicity of project design. This project was implemented quickly the way an emergency should be due to the linear simplicity of its design, clearly defined activities, and an easily identifiable target group.2. Experience acquired during an emergency could be used to provide similar assistance elsewhere. In this project, even though it was only for a one-time cash grant, the manual developed for the cash allowance could serves as a "guiding document for future emergencies." (p. 25).The BMET has developed experience in repatriation and delivery of cash transfers through this project.3. The Bank should do some preparation work even for emergency operations. Rigorous analytic work need not inform design but, "the Bank needs to take stock of the situation." (ICR p. 24). In this case a beneficiary assessment would have been informative and not necessarily slowed down project implementation. Other assessments of workers in other conflict countries and sustainable social protection for migrant workers would also have been useful.4. High returns are possible without incurring high administrative costs. The administrative costs were only 2% of the direct costs of repatriation and reintegration.
P126274 | Programmatic Development Policy Operation 2 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  |  |  | The ICR distilled seven lessons: (i) the number of prior actions and areas covered by DPOs should be parsimonious; (ii) theprogrammatic nature of the operations should be reinforced; (iii) the critical foundation of success is a viable fiscal position;(iv) implementation of reforms can be strengthened through a unified and robust ME framework; (v) prior actions should focuson reform themes with demonstrated commitment of the authorities; (vi) design of prior actions should focus on critical actionsrather than only the first steps; and (vii) a candid assessment of commitment and capacity risks should be undertaken together withmitigation proposals.IEGconcurs with these lessons, and underscores the importance of maintaining arealistic scope when tackling difficult institutional reforms in a challenging environment. Although the issue of governmentcommitment and ownership was among the lessons from past DPOs that influenced the design of this series, it was, nonetheless, acause for the slower than expected progress in some policy areas covered by the series, and remains a lesson for future DPOs. Thechallenge appears to lie in recognizing genuine commitment from lip service,different levels ofcommitment acrossgovernment agencies, and thedistinction between commitment andimplementation capacity.
P126278 | Kyrgyz Second Health and Social Protection Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/651761607123838626/text/Kyrgyz-Republic-HEALTH-SP-2.txt | http://documents.worldbank.org/curated/en/651761607123838626/pdf/Kyrgyz-Republic-HEALTH-SP-2.pdf | The ICR (pp. 35-36) offered a series of candid and valuable lessons, including:Long-term use of the SWApmechanism can create challenges in balancing high-level dialogue and donor coordination with a focus on concrete actionsand results. In this case, a decision was made at the end of the project to pursue a follow-on PforR approach in lieu of continuingsector support.Continuity and effective stewardship at the ministerial level is key. In this case, highstaff turnover in the Ministry of Health, high turnover of ministers, and lack of a strong governing board at the Mandatory HealthInsurance Fund revealed the need for sustainable capacity building.Synergies between the health and socialprotection agendas must be identified at the design stage in a joint project. In this case, separating the health andsocial protection elements into two disconnected components prevented the full realization of the potential benefits of linkage,eventually requiring restructuring to make the connections more focused and explicit.
P126297 | Second Programmatic Upper Secondary Education Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2012 | 2014 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The following lessons are selected from the ICR:The DPL Programmatic Series was the most suitable Banklending instrument to provide general budgetary support while accompanying a reform program. The DPL Series allowed adjustment tothe pace in which policies were implemented and was also helpful for policy continuity despite changes in the administration andruling party in December 2012.In countries with strong technical capacity such as Mexico, DPLs canusefullyfocus on those elements of the reforms that will benefit most from Bank engagement. In this operation, the Bank triedto respond to the clients technical demands while being selective in choosing in which areas to support the Government basedon team composition and availability of resources.Complementary technical assistance can help to inform theGovernment reform and achieve the DPL Series objectives. In this operation, the technical collaboration between the Bank and theGovernment helped shape the policies introduced by the upper secondary education reforms based on evidence and international bestpractices. The provision of just-in-time technical assistance helped overcome the main obstacles faced during implementation of thereformAligning DPL Program indicators to official indicators helps decrease the ME burden of the Program for theGovernment and allows the team to obtain more reliable and timely information. When the Bank team aligned its indicators to theofficial indicators in DPL 3, ME was greatly improved because the implementing agency had more pressure to periodicallycollect and report data on official indicators.Introducing school accreditation processes requires taking intoaccount schools starting conditions and their ability to improve the education services they provide. Gaining fullaccreditation to enter the upper secondary education system proved to be challenging for most schools in Mexico. In many instances,schools found it difficult to comply with the full accreditation criteria and many lacked the necessary resources to complete theaccreditation process. To tackle these issues, as in the Mexican case, policies might consider allowing schools to gain temporaryaccreditation if they comply with a set of minimum criteria of quality and commit to specific quality improvements over a certainperiod of time.
P126321 | KENYA: NATIONAL URBAN TRANSPORT IMPROVEMENT PROJECT | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/794161572633349492/text/Kenya-KE-National-Urban-Transport-Improvement.txt | http://documents.worldbank.org/curated/en/794161572633349492/pdf/Kenya-KE-National-Urban-Transport-Improvement.pdf | Severalimportant lessons were selected fromthe ICR, with some adaptation of the language: Incountries where the sectorpolicy environment is changing rapidly, but the degree of a new policy impacton the projectdesign isunknown, the project design needs to be flexible or the Board approval could be postponed.The projectexperience shows that the impact of adoption of the Integrated National Transport Policyand the subsequent focus on masstransit on the design of the project was unknown until 2013. While the project restructuring was necessary at an earlier stage torespond to the shiftin focus, the restructuring process was halted. When such situations occur, the project team needs toundertake an additional risk analysis, present the anticipated issues to management, and obtain guidance and support from theBanks Country Management Unit and GP management. Urban transport projects are typicallycomplex, involve a variety of stakeholders, and require longer planning and implementation periods. The existence of alead agency and a champion for the project is critical for success, including for managing the diverse interests. Rigorousstakeholder analysis needs to be conducted, and institutional arrangements must be clarified and streamlined, either as part of theproject or before the project commences. Continuous engagement is critical to preserve the momentumof institutional and policy reforms in the urban transport sub-sector. Several efforts were initiated under this project including the increased focus on urban transport and mass transit, and priority actions of the commuter rail master plan.These mayeasily stall without sustained engagement. Likewise, sustained capacity building will be essential to ensure theNairobi Metropolitan Area Transport Authority (NaMATA) is able to fulfill its role coordinating and leading urban transportinitiatives in Nairobi Metropolitan Area (NMA), including hosting dialogue among key stakeholders and establishing coordination andimplementation mechanisms.
P126324 | KI: Telecommunications and ICT Development Project | East Asia and Pacific | Kiribati | IDA | FCS | Digital | Digital Development | IDA | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/898991587584086454/text/Kiribati-KI-Telecomms-and-ICT-Development.txt | http://documents.worldbank.org/curated/en/898991587584086454/pdf/Kiribati-KI-Telecomms-and-ICT-Development.pdf | The following lessons are adapted from the ICR. To ensure sufficient human capacity and retention ofskilled staff for overseeing the ICT sector, there should be greater collaboration between the Pacific Island policy makers andregulators and more efforts to share expertise and retain knowledge. There is a need for mentoring and short-term industryattachments in addition to on-line collaboration including sharing of experiences and best practice. While capacity building usinginternational forums and conferences are valuable for learning, in-country assistance for staff training may provideadditionalopportunities for skills enhancement. Measures are needed to protect especially new internetusersfrom the vulnerability associated with cyber security. Government could request development partners to workwith them to develop a plan to increase local awareness and there should be legislation introduced as a foundation for suchastrategy. The involvement of the private sector in the reform process is critical to enhance the ICTsector service provision in a sustainable manner.Properly sequenced reforms that create an enabling environment forprivate sector participation would mean having a level field and equalopportunity for the privatesector. Technological innovation through the use of satellite connectivity and encouraging the use of distributednetworks (where the core of the telecommunications exchange is offshore) arethe key to success in small and isolatedmarkets. Although cable remains the most robust solution for international connectivity, satellite connectivity optionsare often the best solution for connecting isolated and sparsely connected islands.
P126325 | IN Maharashtra Rural Water Supply and Sanitation Program | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | PforR | 2014 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099000002152225524/text/India000IN00Maha0RWSSP.txt | http://documents.worldbank.org/curated/en/099000002152225524/pdf/India000IN00Maha0RWSSP.pdf | The ICR (paras. 102 to 104) lists a number of lessons from which IEG derives the following lessons that are relevantforsimilar projects implemented in comparable environments:1. Clearly defined program boundaries improve PfRimplementation readiness: A lesson from this project was that the definedprogram boundaries only identified general focusareas (e.g. peri-urban, water-stressed) instead of defining the program in terms of specific geographic areas or investments. Thiseffectively shifted the burden of identifying the specific content of the program into the implementation period. thereby causingdisbursement delays and extra costs to the client.Future projects should identify PfR boundaries as specifically as possibleor clearly justify when this is not possible.2. Program DLIs feasibility and design should align with theclients implementation capacity and should include sub-DLRs for more predictable achievement of DLIs: The initial programresultsand DLIs were designed from a sectoral perspective without fully considering the states implementation capacity.Adding simple definitions and specific quantitative targets makes it more feasible for the state to implement the interventions andfacilitates the DLI verification process and assessment of achievements. Future PfR operations should include DLIs with associatedsub-DLRs to achieve morepredictable achievements of DLIs and facilitate the implementation process.3. Peri-urbanareas need focused policies for water supply and sanitation: The experience under the project demonstrated the special natureof peri-urban areas which are rural by classification but increasingly urban in terms of population density, economic structure,and aspirations. Finalization of selection criteria contributed to substantial delays in the implementation of the peri-urbanareas.
P126339 | Egypt Emergency Labor Intensive Investment Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2012 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/809401529102078660/text/Egypt-Arab-Republic-of-EG-Emergency-Labor-Intensive-Investment.txt | http://documents.worldbank.org/curated/en/809401529102078660/pdf/Egypt-Arab-Republic-of-EG-Emergency-Labor-Intensive-Investment.pdf | The ICR offered several lessons and recommendationsthat need not be repeated verbatim here. In thefollowing, some of the more novel/interesting lessons from the ICR are rephrased in a synthesized fashion, while also adding froman IEG perspective: Simple design, simple objectives, and the use of one implementing agency only isappropriate for emergency operations. Using an experienced implementing agency with a track record of implementingBank-financed projectscan helpa project achieve its goals. For the Bank to have such a relationship--and, in this case,for the SFD to have built this experience--does not happen by chance. An element of continuity over the long term in some of theBanks social protection engagements contributed to this favorable situation. Adapting targeting mechanisms duringimplementation can help toaddress and reachdifferent vulnerabilities. In this case, as new data became available, itwas used, for example, to update the allocation of funds to different types of subprojects, thereby enabling the project to finetune what categories of vulnerable people it reached. Adjustments to the length of work contracts and the timing of when work isperformed can also be used to fine-tune targeting. Results-based monitoring and active use of data during supervisionenhances achievement of project objectives. In this case, framing supervision discussions around the results framework, using thecollected data, and identifying the underlying causes of implementation challenges helped steer actions toward outcomes rather thaninputs and outputs. It also helped steer World Bank technical support. Actions plans developed this data-driven way duringsupervision missions helped the project improve its performance. There is a clear role for citizen engagement and socialaccountability in labor-intensive public works.Thesefactorscan help foster trust and community engagementinpublic worksprograms. A number of different citizen engagement mechanisms were used and showed potential:consultations and stakeholder mapping; community score cards for benchmarking performance;community voluntary committees witha role in design and oversight of subprojects; andsocial audits of subprojects. There was also use of independentverification. However, these thingsare not free. Adequate capacity building for civil society is needed to reap the fullbenefits of citizen engagement.
P126343 | SWAp for Parana Multi-sector Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/571831618848518063/text/Brazil-BR-Parana-Multi-sector-Development.txt | http://documents.worldbank.org/curated/en/571831618848518063/pdf/Brazil-BR-Parana-Multi-sector-Development.pdf | The ICR (pp. 38-40) offered several useful lessons, including the following lessons restated byIEG: Project design benefits from substantial assessment of the maturity and realism of the project context,the clients reform program, and its institutional capacity through sustained dialogue at the project preparation andimplementation stages. In this case, implementation was hampered by lack of readiness at approval, underestimation ofinstitutional capacity constraints both on the Bank and the government sides, superficial analytical underpinnings, and lack ofconsideration for the macro-fiscal context and more generally the socio-political context. Setting meaningfulresults frameworks requires deep knowledge and regular updates. The above shortcomings at appraisal, which persistedthrough project implementation, were reflected in theweaknesses of the results framework. Addressing themsuccessfullywould have required stronger analytical and knowledge inputs and continuous monitoring of the main assumptions underlying theprojects theory of change. Proactive and hands-on project supervision and periodic adjustment inproject activities is critical for project success. Managing complex multi-sector operations atthesub-national level, where Bank knowledge is traditionally more limited, requires generous preparation and supervisionbudgets. This last lesson is the consequence of the three lessons above, calling for more substantive preparation andsupervision work.IEG adds two lessons: Results-based project disbursement modalitiesare not a substitute for results-based public sector management. ME is not just a question of procedures but involvesarange ofprocesses, protocols, competencies, knowledge, and discernment that cannot be summarized in a manualdescribing procedures to follow. The project-supported activities could have been designed as an experience on which to develop abroader ME capacity building program, but there are no indications in the Bank documents, including the ICR, thatthiswas the case. Institutional reforms alone are unlikely to compensate for constraints that are due to sub-optimalpolicy. In this case, institutional reforms on public finance management (specifically raising tax revenue throughimproving tax management and containing the wage bill by strengthening payroll management and control)are unlikely to addressfiscal space constraints without adequate related fiscal policies, namely tax and salary expenditure policies.
P126346 | Disaster Risk Management and Reconstruction | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/520071625011615481/text/Haiti-HT-Disaster-Risk-Mngmt-Reconstruction.txt | http://documents.worldbank.org/curated/en/520071625011615481/pdf/Haiti-HT-Disaster-Risk-Mngmt-Reconstruction.pdf | 1. Stakeholder consultations and continued collaboration (including bottom-up participation), as well as long-termengagement with the client are critical for achieving results, especially in the poor FCV countries. WorldBanks long-term engagement with the Haitis government and communities paid off and led to the formulation andadoption of the National DRM Strategy, and a policy dialogue with the Client over the years led to the preparation and adoption ofthe DRM legal and institutional framework, and the enactment of the National DRM System after more than ten years in the making.This was a transformative outcome.2. The multi-sectoral approach and DRM mainstreaming are critical to achievingsustainable DRM outcomes and promotingDRM in the core sectors of the economy, including transport. This approach wasinitiated in Haiti by the World Bank in 2005 and succeeded through several DRM projects. The transport component adapted to acomplex and changing situation in Haiti through three successful approaches: (i) the earmarked funds in stand-by mode wereefficiently disbursed after a catastrophic event (i.e., after Hurricane Matthew); (ii) innovative, reliable, less expensiveengineering solutions, such as new gabion reinforcement techniques to increase the resilience of transport infrastructure inflood-prone areas; and (iii) trained and empowered men and women for Labor intensive work (LIW), building unique skills that wouldcontinuously be needed for resilient local transport upkeep.3. DRM knowledge managementisessentialforinforming decision making. The Bank helped build scientific capabilities and their use forthe DRM decision making. When these systems are fully operational under the ongoing PGRAC, they will help formulate more effectivestrategies, design policies, support early warning systems (EWS), and prioritize programs and projects with real time monitoringcapabilities that allow for proper evaluation and recalibration.4. While there is limited time for the preparationof emergency projects, it is important to use accumulated experience in Haiti to pay more attention to the design of the resultsframework (RF). The experience of this project demonstrates that a poorly designed RF can cause a need for projectrestructuring and lead to complications with the evaluation of project achievements.
P126349 | Zambia Third Poverty Reduction Support Credit | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/629931474633174326/text/000020051-20140626112412.txt | http://documents.worldbank.org/curated/en/629931474633174326/pdf/000020051-20140626112412.pdf | The broad thrust of the lessons in the ICR is supported:Success will be more likely in reform areas which coincide with the Governmentâ€™s own priorities and where the Bank has other instruments to engage outside the budget support frameworkWhile a budget support framework can provide a platform for sustained dialogue, by itself it has limited leverage in influencing Government policy and institutional actions in situations where official development assistance is sharply declining as a share of Government resources. The Bank should be cautious in proceeding with programmatic approaches such as PRSCs when government commitment is uncertain, and donor priorities are shiftingThe Bank should effectively manage transitions within the Bank team to ensure that reform programs stay on track, and relationships are protected between the Bank, Government, and development partners.There is a need to develop more granular, outcome indicators of public sector performance that are achievable within the term of a PRSC series. Sectoral operations are important to carry out alongside PRSCs in supporting energy sector reforms, with energy outcome indicators that address core issues of sustainability. In addition, the Bank should use indicators in policy operations that are forward looking, and not seek targets that have already been achieved prior to the appraisal of such operationsThe Bank should also carefully consider the implication of changes to the basic underpinnings of the macro framework, such as a sharp uptick in the fiscal deficit, during implementation of a PRSC programFinally, a lesson learnt from PRSC3 is that in the face of waning commitment to the original program from Government and donors, closing the series early and moving forward on a new programmatic basis may yield better development outcomes than persisting with the original design.
P126351 | Bahia Inclusion and Economic Development DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2015 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/533971488217684611/text/ICRR-Disclosable-P126351-02-27-2017-1488217676774.txt | http://documents.worldbank.org/curated/en/533971488217684611/pdf/ICRR-Disclosable-P126351-02-27-2017-1488217676774.pdf | IEG draws the following lessons from the DPO:1. Achievement of objectives is likely to suffer when the expectedoutcomes are not well-matched to the objectives. To reach an objective as broad as reducing social inequality, anoperation needs to identify the critical outcomes that will be make a difference for that objective, underpinned by a credibletheory of change that covers the complex array of variables with a bearing on the objective. Alternatively, anoperation can seek more modest objectives (e.g., improve access to education), where outcomes (e.g., increased enrollment andimproved test reforms) clearly depict the more limited objective and where needed reforms (e.g., teacher training) can be morereadily identified.2. A lack of outcome indicators is a serious constraint on the value of ME. TheDPOs efforts on primary education are a case in point. It was one of the few areas where ME design included adequateoutcome indicators (results of standardized testing and completion rates). In the event, unexpected developments impeded thecollection of data on these indicators and the impact of those efforts could not be assessed. In several other areas, designedindicators only covered outputs (e.g., pilot risk maps) that will not suffice to assess the extent to which the expected outcome(reduction of the impact of disasters) was achieved.3. Some risks may be difficult, if not impossible, tomitigate. The deterioration of Brazils macroeconomic conditions resulted in fiscal constraints that undermined publicexpenditures on government services, on which several of the DPOs outcomes depended. A possible approach to mitigation ofthis risk is planning on protection of critical social expenditures in the event of fiscal retrenchment. These expenditures wouldbe likely to include those on which many of the DPOs outcome depended.
P126355 | Sierra Leone - Fifth Governance Reform and Growth Credit | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | This review supports some of the lessons cited in the ICR, especially the importance of having a functional Multi-donor BudgetGroup that will assist in the design, formulation and selection of indicators discussed with government. Other lessons cited in theICR with adaptation in language include the following:(i) The Ministry of Financeplays a critical role in ensuring that agreed reforms are implemented by various government agencies. In this case, the Ministry ofFinance did not effectively use its budgeting and resource allocation powers to compel the Ministry of Education to focus on agreedreforms. As a result, the education sector target was not met.(ii) The use of aprogrammatic series provided an opportunity for mid-term corrective measures to be taken by the team towards theachievement of the targets. The Bank team had an opportunity to re-evaluate their indicators after the first twooperationsand introduced new indicators during the thirdoperation (SL-GRGG 6)to help them achieve thedesired outcomes.(iii) Selecting prior actions from the Progress Assessment Frameworkdesigned and discussed with government and other development partners works well and aids monitoring. In this case, the policyreforms were derived from the governments own reform agenda and harmonized with the reforms supported by developmentpartners. This created ownership from all stakeholders during the implementation and monitoring of the Progress AssessmentFramework.
P126357 | Second Support to the Education Sector Project PASEN II | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/390031570651379947/text/Nicaragua-NI-2nd-Support-to-the-Education-Sector.txt | http://documents.worldbank.org/curated/en/390031570651379947/pdf/Nicaragua-NI-2nd-Support-to-the-Education-Sector.pdf | The ICR identified three lessons (p. 25). Among these, IEG highlights and adapts the following:When targetingstrategies are notaligned with government preferences, project implementation and efficacy can suffer. In this project, whichused a geographic targeting approach, this type of misalignment arguably createda sense of fracturing betweenbeneficiaries and non-beneficiaries. Specifically, the targeting approach for Paquetes Solidarios was notaligned with government preferences and, for this reason, it was abandoned at the first restructuring when the government decidedto expand and fully fund Paquetes Solidarios nationally. Yet, the geographic targeting approach continued for otherproject activities such as aiding teachers for participating in TECPE workshops. This created a sense of fracture betweenteachers from targeted municipalities (who received support for transportation costs) and teachers fromnon-participating municipalities (who did not receive support for transportation costs).Choosing PDOindicators that rely on data collection methods outside the control of the project is risky, especially if adequate mitigationmeasures are notin place. Thisproject was unable to measure PDO Indicator #2 (within-year retention rate),asthe data collection and calculation methods were affected by factors outside the control of the project. Projects thatusePDO indicators whosedata collection methods (and/or implementation) are outside the span of the control of theproject can mitigate this risk by identifying at appraisal (i) thelikelihood of changes in data collection methods and (ii)backup indicators.
P126361 | Kihansi Catchment Conservation and Management Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/763711607639836411/text/Tanzania-TZ-Kihansi-Catchment-Conservation.txt | http://documents.worldbank.org/curated/en/763711607639836411/pdf/Tanzania-TZ-Kihansi-Catchment-Conservation.pdf | The following two lessons in the ICR stood out as important and relevant to other projects on biodiversity conservation and arepresented here with some editing.1. Reintroduction is a long-term process that will require dedicated resources,careful monitoring and continued research. The close monitoring of released population of the KST under the project foundthat the rate of survival after reintroduction was higher in babies and sub-adults than adults. This could be linked to adaptationand immunity considerations since the KST have been bred for several generations in captivity. Releasing more babies, sub-adults,and gravid females in the wild would improve chances of a self-sustaining population. Moreover, the release of the KST under theproject started before the sufficient population was bred in the reproduction facilities, considering the captive population thatneed to remain within the facilities. An expansion of captive breeding facilities to increase the total KST population and thenumber of them being released would be critical for sustain the achievements of the project.2. A multi-sectorproject needs strong involvement from relevant sectors. The Project Implementation Unit (PIU) was located in the NationalEnvironment Management Council (NEMC), which reported to the Vice Presidents Office and was not tied to any of theministries in the relevant sectors. This positively affected the project to coordinate multi-sector stakeholders with differentexpertise and priorities, proceed with procurement, and conduct ME.
P126364 | Education Quality Improvement Project | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/297531582576666346/text/El-Salvador-SV-Education-Quality-Improvement.txt | http://documents.worldbank.org/curated/en/297531582576666346/pdf/El-Salvador-SV-Education-Quality-Improvement.pdf | The ICR (pg. 23) provided several lessons, including the following: There is trade-off between speed ofpreparation and technical soundness of project design. For this Project, a swift preparation was required to take advantage of thepolitical window of opportunity. This short preparation timeline, however, did not allow for the use of thecapacity-buildingtrustfunds to inform project design nor for a full diagnostic of the infrastructure needs of beneficiary schools, which ledto an underestimation of the costs and the depth of the interventions needed. The following lessons were alsoidentifiedby IEG: ME capacity as well as an institutional culture that values rigorous assessment iscritical to effective ME implementation. In the case of this project, the countrys capacity to implement anexperimental impact evaluation wasoverestimated. As reported in the ICR (page 19), although MINED was able to collect datafor monitoring purposes, the institutional culture did not give importance to rigorous measurement of impact and thusthere waslimited ownership from MINED. Despiteseveral trainings and intensive support for theimpactevaluations design and implementation, the data collected was not sufficiently robust to be used asintended. Continuous support to upper secondarystudentsfrom initial access/transition from lower secondaryall the way through tograduation greatly facilitates the objective to improve graduation rates.In the case of thisproject, project activities were largely focused on lower secondary education, in order to increase likelihood of lower secondarystudents continuing on to upper secondary, where sustained support is also needed.
P126372 | Recife Swap Education and Public Management | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2012 | 2020 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099625012162124476/text/Brazil000BR0Re0p000Educ0Public0Mgmt.txt | http://documents.worldbank.org/curated/en/099625012162124476/pdf/Brazil000BR0Re0p000Educ0Public0Mgmt.pdf | The ICR (pp. 30-31) provided several insightful lessons,two of which are restated here:Changes ingovernment administration after project approval can have significant impacts on project implementation. Project designshould take the possibility of such changes into account and prepare implementation support plans to address proactively anyresulting changes in priorities and/or the Borrowers implementation support team.Multisectoral projects canbe effective in addressing issues common across government agencies in a coherent manner, but they are complex to implement andrequire careful linkages across the various sectors involved. In this case, the linkages between education and publicsector management were strong conceptually, given the impact of public sector management on education management andeducations importance in Recifes overall public budget. In practice, however, the institutional arrangements governingthe originally planned activities proved too complex, and many planned activities under the public sector management component weredropped.
P126408 | Support to Uruguayan Public Schools Project | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2013 | 2017 | 2018 | ICRR | >=25 million & <50 million | Highly Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/834721528379545372/text/Uruguay-UY-Support-to-Public-Schools-Proj.txt | http://documents.worldbank.org/curated/en/834721528379545372/pdf/Uruguay-UY-Support-to-Public-Schools-Proj.pdf | The ICR (p. 25) included several useful lessons learned, adapted by IEGbelow:1. Addressing competing demands on teachers, and increasing their timeavailabilityand commitment, facilitate successful in-service training:Under theproject,the implementation of in-service teacher training courses was challenging due to the lack of trainers and the significant timecommitment that was required by teachers to complete the course. The project overcame this challenge by decreasing the amountof hours required for face-to-face training, implementing school visits by trainers to reduce the time commitment on the part ofteachers, and creating virtual courses.2. Careful planning and allocating anadditional budget for unexpected expenses are important for the institutionalization of in-service training: In thisproject, the government provided an additional budget to support the ongoing institutionalization, improvement and expansion ofteacher training. Unexpected expenses wereencountereddue to difficulties in obtaining qualified trainers within thecountry. Therefore, the project had to hire international experts to support the design of the courses/materials and to trainthe trainers. Also, more teachers (including non-FTS teachers) than expected participated in the newly-available trainings,which increased training costs. The inclusion of virtual courses, which was not planned at appraisal, requiredfundingfor the provision of materials and licensing costs for theplatform.3.Collecting additional data on the use of extended classtime is useful to assess the value-added of FTS. In Uruguay, there is no regulation for the use of extended classtime of FTS, and its usevaries across schools. Data on how extended school time was being used allowed administratorsto ensure an optimal use of the extended school day across more schools.
P126424 | Indonesia: PNPM Peduli | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/795021468188361825/text/ICRR14902-ICRR-PUBLIC-P126424-Box396265B.txt | http://documents.worldbank.org/curated/en/795021468188361825/pdf/ICRR14902-ICRR-PUBLIC-P126424-Box396265B.pdf | The Implementation Completion Report offers five lessons of which the following are the most important (with some reformulation of language):Local level civil society organizations (CSOs) are critical in reaching hard-to-reach groups and direct funding to these organizations enables them help shape policy and play a more strategic role on emerging policy issues of national interest. The project experience showed that working with Executive Organizations enabled the Project to tap into their partner CSOsâ€™ field expertise to reach beneficiary groups not easily accessed â€“ physically or socially. In addition, CSO partners can play a useful role in filling the gap in accessing and delivering services to those groups for whom the government is less able to reach, particularly in remote locations or where available services do not meet the specific needs of the most marginalized and excluded groups. Economic poverty alleviation efforts and livelihood improvement is a useful but not sufficient entry point for reaching excluded groups. A multifaceted approach is needed to address the complexity of exclusionary systems/practices, particularly related to issues of stigma and systemic discrimination. Empowerment of excluded citizens requires a rights-based approach involving the whole community, rather than only focusing on meeting direct and immediate material needs. Performance indicators need to capture comprehensive information about changes to the lives of beneficiaries, for example, in access to services (health, education legal and financial); in increased social interaction between groups (thus measuring social cohesion); and in attitudinal changes and increased participation in community life. Such Projects would also need to monitor and measure efforts for knowledge management and policy influence to be able to adapt and link the investment with the broader development agenda.Adapting World Bank financial and administrative processes and requirements when granting to (national) CSOs makes them more accessible and functional for local CSO partners in the field, while still meeting globally accepted fiduciary and governance. The project experience showed that this involves the World Bank ensuring performance for results, rather than compliance, to avoid delays in implementation while still adhering to fiduciary principles. Adhering to these modified guidelines provides the CSOs with an opportunity to ensure that their internal systems are up to standards necessary for effective functioning as well as their long-term legitimacy.IEG adds an additional lesson: For small-sized grant-funded pilot projects ensure that financing is adequate. This project had a very limited initial budget that had to be topped-up several times. An approach could be adapted whereby a full budget envelope is indicated prospectively at project inception, with tranches captured through amendments to existing Grant Agreements. This method would not only reduce transaction cost of processing trough several Additional Financing, but also would provide more certainty and clarity about the project's financial resources.
P126425 | KP/FATA Governance Reforms | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2012 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/182281498488045880/text/ICRR-Disclosable-P126425-06-26-2017-1498488033703.txt | http://documents.worldbank.org/curated/en/182281498488045880/pdf/ICRR-Disclosable-P126425-06-26-2017-1498488033703.pdf | The ICR (pp. 19-20) offers several useful lessons, including:It is a challenge, especially in fragileenvironments, to balance the need for flexibility with the imperative of well-defined objectives, scope, and outcomemeasurements. In this case, flexible design translated into lack of prioritization and measurement of achievementwell into the project period.Focused support to intermediary/cross-cutting institutions can be an efficientway to support line departments; however, those entities require clear mandates to avoid overburdening. In this case, supportto the ISUs was leveraged to generate important synergies, but capacity constraints produced delays.Wheremore than one distinct geographic area is involved, particularly in fragile contexts, the imperative for efficiency andcross-learning can be less important than the specific needs of each area. In this case, three separate projects would haveenabled better tailoring to those specific needs and ultimately may have reduced implementation bottlenecks. As the ICRnotes, this lesson has been incorporated into the design of three separate follow-on projects.IEG adds thefollowing lesson:Although data reliability and availability can be complicated by a conflict-affectedcontext, it is possible, through intensive implementation support and capacity building, to address capacity gaps even inchallenging contexts. In this case, due to effective support for ME Directorates at the province level, monitoringreports and an impact evaluation were produced in time to guide allocation of resources after restructuring and assess projectachievement.
P126426 | Pakistan: Revitalizing Health Services in KP | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/885901483114713124/text/ICRR-Disclosable-P126426-12-30-2016-1483114697154.txt | http://documents.worldbank.org/curated/en/885901483114713124/pdf/ICRR-Disclosable-P126426-12-30-2016-1483114697154.pdf | The ICR (p. 26) includes useful lessons learned,including the following: When a project isbeing implemented in a fragile, post-crisis environment, taking weak capacity and other implementation constraints into accountwhen deciding on the projects scope and time frame for project implementation is key to success. In this project, an initialphase for capacity building in critical areas such as procurement, contracting out, and ME would have been beneficial forsuccessful project implementation. Conducting an in-depth political analysis and ensuring the buy-in of all stakeholdersis critical for successful project implementation. In this project, the highest government level was committed to theimplementation of the project; however, this commitment did not translate into action at the implementing agency level due topolitical complexity and loose enforcement of internal regulations, resulting in significant implementation delays. In afragile, post-crisis environment, contracting out of healthcare services to NGOs/contractors, where traditional service provisiondoes not work, can be effective. However,this project demonstrated the challenges related to this modelwhen beingimplemented in a weak capacity environment. These challenges includeddelays in payments to contractors, lack of contractmanagement capacity, and reporting delays by contractors.
P126440 | Third Rural Sector Support Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2019 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/470321561587853428/text/Rwanda-RW-Third-Rural-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/470321561587853428/pdf/Rwanda-RW-Third-Rural-Sector-Support-Project.pdf | The ICR included three lessons. The following are emphasized with some adaptation of language: Importantimpacts can be achieved when a strategically relevant program/approach is continued and perfected over time. The projectexperience emphasized the importance of continuity and strategic articulation. This is what happened during the three phases of theproject, which built one upon another. Despite its difficult start,the first phasemanaged to turn around and providevaluable lessons and direction to the next two phases. The Governments long-term vision for the agriculture sector,articulated in the Vision documents and in the successive Strategic Plans for the Transformation of Agriculture (PSTA) generations,was equally a determining success factor. It enabled pursuing a coherent policy in the sector and government commitment to stay oncourse, across over a decade ofthe programinterventions, under a stable regulatory and institutionalenvironment. Successful agriculture-food value chain development requires the following elements:sensitization, technology dissemination, aggregation, value chain partnerships, complementary infrastructure, andsoft-skill development. The project focused on sensitization, demonstration plots and farmer field schoolstodemonstrate the achievable benefits.This facilitated technology dissemination which ensured both a reduction in the inputcosts and high adoption rates among producers.Aggregation of farmer organizationsempowered small agricultural producersto establish themselves up-and down-stream along their respective value chains. Through supporting a holistic approach to valuechain development, the project ensured that no gaps were left on the path from farm to market.
P126449 | Piaui Green Growth and Inclusion DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2012 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/421631468001176445/text/ICRR14633-P126449-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/421631468001176445/pdf/ICRR14633-P126449-Box393183B-PUBLIC.pdf | Several important lessons are highlighted by the ICR, the most important of which are: 1. Strong client ownership and leadership are essential for adequate DPL preparation and implementation. 2. The design and implementation of complex policy reforms require strong inter-institutional leadership and coordination. 3. In cases where the Borrower is relatively weak in policy implementation, the Bank should consider developing an investment operation in tandem with the DPL, although because the proposed complementary SWAP did no go to the Board as scheduled, this operation did not provide evidence as to the effectiveness of this approach. 4. In cases where the prior actions recognized by the DPL include the creation of a new program, it might be necessary to request a detailed analysis of the budget for its implementation. Moreover, new programs (such as Piaui Digital) could have benefited from a cost-benefit analysis to strengthen their action plans. While such assessments should not be part of the DPL, they could be undertaken with the support of a small parallel technical assistance loan.
P126454 | Xinjiang Yining Urban Transport Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/604971545410249203/text/China-Xinjiang-Yining-Urban-Transport-Improve.txt | http://documents.worldbank.org/curated/en/604971545410249203/pdf/China-Xinjiang-Yining-Urban-Transport-Improve.pdf | IEG selected several lessons from the ICR, with some adaptation: Capacity buildingis key to sustain the success of innovative components, such as integrated transport corridor management, speed cameras, busmanagement systems and functional road classifications. Urban transport interventions can contribute to thereduction of Green-house Gas emissions, through traffic management measures and acquisition of low-emissionbuses. Land acquisition and resettlement should be carefully coordinated. While theICR states thatland acquisition should be completed before procurement processing, this may serve to delay overall projectimplementation more than necessary. The ICR rightlypoints thatland acquisition and resettlement should beaccelerated to a high pace at the very beginning of an urban transport project.IEG providesfollowing additional lessons: Much care should be given to the definition of monitoring indicators,so the issues mentioned above can be avoided (geographical areas, traffic fatality reporting). When public transport is to beimproved, indicators of bus service efficiency and quality could be added to the mere reporting ofridership. Future projects should add a component focusing on specific traffic safety measures, ratherthan just assuming that speed cameras and traffic management will take care of that issue.
P126465 | RIO STATE DEVELOPMENT POLICY LOAN III | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/981211467999675001/text/ICRR14892-P126465-Box394872B-PUBLIC.txt | http://documents.worldbank.org/curated/en/981211467999675001/pdf/ICRR14892-P126465-Box394872B-PUBLIC.pdf | The ICR suggests the following three lessons:1. A reform where the interests of implementing agencies are not well-aligned has limited chances of being achieved. This seems to have been the case of the public investment reform, where the Finance Secretariat coordinated poorly with the Planning Secretariat, the agency in charge of that reform.2. A combination of better incentives and institutions is a sound underpinning for successful reforms. The education reforms supported by the DPL combined an institutional change (merit-based appointments) with a good incentive (bonuses on good results) and seems to have been successful.3. A consistent and persistent engagement with a client will help improve results by helping build knowledge and expertise. In particular, the ICR underscores that programs are more likely to succeed when there are high level professional teams involved in the design stage.
P126465 | RIO STATE DEVELOPMENT POLICY LOAN III | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2013 | 2014 | 2021 | PPAR | >=100 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/140921623855295292/text/Brazil-Rio-State-Fiscal-Efficiency-for-Quality-of-Public-Service-Delivery-Development-Policy-Loan-DPL-III.txt | http://documents.worldbank.org/curated/en/140921623855295292/pdf/Brazil-Rio-State-Fiscal-Efficiency-for-Quality-of-Public-Service-Delivery-Development-Policy-Loan-DPL-III.pdf | 3. Lessons 3.1 DPLs supporting institutional reform at the subnational level in areas such as tax administration, public financial management, education, and health require a long-term strategic vision and sufficient time for implementation, even when government ownership is strong. Stand-alone DPL operations at the state level, like the one reviewed in Rio, are unlikely to achieve such objectives without significant and sustainable complementary support. Institutional reform is a medium-to-long-term effort that requires continuous support to the executing agencies to build on lessons learned and reduce the chances and costs of mistakes. An investment loan anchored on a longer-term institutional partnership with state implementing agencies could have been a better tool for supporting the underlying reforms. 3.2 It was difficult to achieve fiscal sustainability in Rio state by reforming only a few technical aspects of tax administration without accounting for important issues such as pensions, dependence on unstable oil revenues, weak institutions, and chronic corruption. 3.3 Institutional transformation in tax administration relies in part on fiscal performance. Therefore, an assessment of the state's fiscal situation, its implementation capacity, and medium-term perspectives could have improved the program's design. This would have been particularly relevant in Rio state, which at the time was in a dire financial situation and lacked the bandwidth to properly prepare and execute the 12 loans it was simultaneously negotiating with multiple lenders. 3.4 Interest-group politics in Rio state undermined the progress and impact of the reforms. It would have been ideal to ensure that the associated risks were identified and addressed at the design stage of an operation. 3.5 The following aspects may require additional attention\. â€¢ Understand the underlying incentives behind reforms. The experience of Rio state indicates that auditors and inspectors of the tax administration service had little to no incentive to improve performance because most were already at the top of their pay scales. â€¢ Make sure agency staff have the technical capacity to implement reforms. The experience of Rio state shows that the tax administration office staff lacked qualifications in information technology and could not carry out the changes in hardware and software required for reforms to succeed. â€¢ Effective monitoring is essential to enhance the chances of program success. Preparing a joint World Bankâ€“executing agency monitoring plan before loan approval would have improved the chances that the agency had taken the steps needed to execute the program and the World Bank had allocated resources to monitor it.
P126470 | SN- Second Governance and Growth Support Credit | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons are drawn from the ICR:Budget support series should pay attention toabsorptive capacity. While budget support provides the opportunity for ambitious coverage and tacklingmanyissues, absorptive capacity in government agencies will often be the limiting factor; it needs to be carefully weighed againstpotential overreach in program design. The GGSC series was ambitious, increasing the burden on both Bank staff and theadministration, and placing the quality of reforms at risk.Prior actions need to be followedup. The passage of laws and regulations the usual contents of prior actions is a first step inreform; once passed, they also need to be put into practice, and this requires the necessary skills and, often, access to companiontechnical assistanceto build up those skills. Significant delays were experiencedin a number of instances in thisprogram, notably the application of financial regimes for universities experienced significant delays due to a lack of follow-up inthe Ministry of Finance that was in charge of the setting the budget nomenclature.
P126504 | Enhancing the Climate Resilience of the West Coast Road | East Asia and Pacific | Samoa | IDA | Non-FCS | Infrastructure | Transport | RETF | IPF | 2013 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/337261636757240807/text/Samoa-Enhancing-Climate-Resilience-West-Cst-Rd.txt | http://documents.worldbank.org/curated/en/337261636757240807/pdf/Samoa-Enhancing-Climate-Resilience-West-Cst-Rd.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Low capacity environments may require longerimplementation periods.Theimplementation timeline of five years for this project proved to be unrealistic and the closing datewas extended by acumulative 28 months. The lesson is that the standard five-year implementation period may not be sufficient for small island stateswith low implementation capacity.2. Identification of Right-of-waybefore commencingdesignanddesign optimization based on visual inspection can help in reducing land acquisition delays.Significantdelayswere experienced in the initial years of this project, due to the uncertainty over the extent of the legal right of way forWCR.3. Remote supervision of civil works can be done under an emergency like the COVID-19;however thiscannot permanently replace actual physical supervision. In this project the impact to disruptions caused by COVID -19 wasmitigated by fortnightly meetings with the Land Transport Authority. Nevertheless to properly supervise the technical aspects ofsuch projects, it is important for engineers and safeguards specialists to visit the actual project road regularly.
P126507 | Ho Chi Minh City Green Transport Development | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2015 | 2024 | 2024 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099032024144566453/text/P12650718180b80bc1901b18b3be54db8ea.txt | http://documents.worldbank.org/curated/en/099032024144566453/pdf/P12650718180b80bc1901b18b3be54db8ea.pdf | The following lessons are selected as most relevant, from the ICR (rephrased):Transport projects may be morelikely to succeed when there is an institutional framework with an established dynamic of cooperation and strong politicalleadership. Maintaining a high-level political champion and dedicated technical focal points who areresponsible for implementing the decisions is key. In this project, a continuous political buy-in and commitment fromthe authorities was missing (the political changes weakened the original leaderships commitment), and some importantpolitical and technical risks materialized.A BRT approach is likely to be more successful if tailored to thenew contexts and as part of a more integrated vision. Despite the BRTs diverse, successful interventions in othercountries, this approach was more questionable in the case of Vietnam. Specific contexts regarding safety, reliability,convenience,meeting local demand, etc, are to be analyzed in each case. The specific factors in each country lead torealizing the need to considerother alternatives, which also facilitates getting more political support for the finallychosen technology as the most optimum public transport strategy.In rapidly changing urban environments, projectsmay get more traction through well-prepared and ready-to-go interventions. There is often a disconnection between bigmaster plans that take time to start implementation and the need for short-term pragmatic investments that address the problem andprovide results early in the process. In this project, implementation depended heavily on a major initial contract that had alengthy procurement process and got delayed, blocking the interventions. Projects financed by the Bank should be grounded on acomprehensive package of priority actions and interventions (policies, investments, service improvements, new systems andmechanisms, and institutional development).Technical and project management capacity gaps of the client may hinderproject implementation if not addressed early. In this project, many new urban and transport planning concepts wereintroduced (the BRT, feeder modes, and Transit-Oriented Development were all new), and the lack of capacity negatively affectedimplementation.
P126516 | Cabo Verde - Transport Sector Reform Project | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099120123100515933/text/P126516038723f0bb091210d7eb93811cf8.txt | http://documents.worldbank.org/curated/en/099120123100515933/pdf/P126516038723f0bb091210d7eb93811cf8.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1.Successful SOE reform needsa long-term, continuous and stable engagement, including in terms of projectmanagement.The project experience demonstrated that, in terms of country support, TSRP benefitted from previousexperience and presence of the World Bank in the transport sector in Cabo Verde, building on RSSP (20052012) and nowinforming the design of the Improving Connectivity and Urban Infrastructure in Cabo Verde Project (P178644) in preparation. Thislong-term relation is needed in terms of SOE reform (from laying the groundwork to effective private sector participation throughpublic-private partnerships or privatizations). It also helped create, step by step, a convening environment to expose, test andramp up the countrys interest andexperience on performance-based road contracts, PBMC approaches taking time to beunderstood, accepted, and adopted. Also, in terms of project management, the stability of the dialogue and monitoring benefittedfrom a limited turn-over of World Bank task team leaders (four TTLs over the nine years of the projects implementationduration), which ensured institutional memory, continuity, and consistency from preparation to implementation andcompletion.2.PBMC contracts can be a useful tool toeffectively and efficiently deliverroadinfrastructurein the national network in good or reasonable condition. The TSRP allowed to mainstream and see thebenefits of the concept of performance-based contracts to Cabo Verderoad network. The project was successful in getting PBMCsto be implemented country wide. Efforts need to be maintained in finding the more suitable type of PBMC contracts thatreflectnational and international experience.3. To avoid unanticipated supply constraints in smallermarkets, road/infrastructure projects need to carefully assess the impact of the project demand on the local supplyof inputmaterials and labor.The project experience showed thathigh demand for cobblestone could not be met by theexisting supply, aggravated by the difficulty to mobilize manpower for such physically hard work. In smaller markets, a project cancreate tensions in some of the supplies and on the availability of workers (and their willingness to work, depending on thehardness of the task); it is better to anticipate and integrate such constraints from the design stage.The project design mayneed to be modified given unanticipated market constraints during implementation. For the project under preparation, the decisionwas made to focus on cobblestone material for some targeted islands only, and to use asphalt concrete in others.
P126537 | Energy and Mineral Sector Strengthening | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/260171575055270911/text/Brazil-BR-Energy-Mineral-Sctr-Strengthening.txt | http://documents.worldbank.org/curated/en/260171575055270911/pdf/Brazil-BR-Energy-Mineral-Sctr-Strengthening.pdf | The ICR (pages 35-36) draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1) A flexible design for Technical Assistance (TA) activitiesallows forcontinuous clientsupport in the face of shifting priorities. This can beparticularly important for a middle-income country that iswilling to borrow for policy TA. The flexible design in this project enabled the Bank to respond to thenew governmentspriorities in the gas sector.(2) Specific studies and reports targeting improvedregulations can increaseefficiency in the energy sector, while leveraging private investments. The study of Contractual Balance in EnergyMarket, with its recommendations, enabled the government to measure and solve theproblem of over contracting in the energysector, which benefitted both the government and the contracting parties.(3)The dissemination of projectoutcomes through workshops for highergovernment management and other stakeholders can aid in continuousgovernmentcommitment. In this project, workshops during implementation proved helpful in clarifying to the manysector stakeholders the importance of the targeted interventions.
P126576 | Agriculture Production Support Project | Western and Central Africa | Chad | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/755051523628199176/text/Chad-CD-Ag-Production-Support-Project.txt | http://documents.worldbank.org/curated/en/755051523628199176/pdf/Chad-CD-Ag-Production-Support-Project.pdf | The ICR included thirteen lessons. The following are emphasized with some adaptation of language: Anemergency projectis less effective when designed as a long-term development project. The projectsimplementation showed that trying to build complex CDD systems resulted in less effective emergency operations. These are mosteffective when they prioritize actionsand focuson the immediate restoration of productive assets for food-insecurerural households. Gender/Poverty targeting mechanisms need to ensure that project resources reach thetarget beneficiaries. The project experience demonstrated that targeting mechanisms thataresimple, verifiableandbased on objective criteria (for example: simple eligibility criteria such as: group characteristics (women who are headof households, households hosting refugees, disabled group, landless groups,, ), geographical criteria, criteria based onasset ownership, criteria based on vulnerability faced by different groups including seasonal factors, shocks (disasters,conflict,..)can foster transparency, minimize political interference in project resource allocation and ensure that projectresources reach the target beneficiaries. Simple, practical standardized designs for sub-projects mayenhance subproject quality, sustainability and cost-effectiveness. Field evidence from this project show that simplepractical standards (including engineering, aspects of technical, financial and economic feasibility, OM, cost parameters)enhanced the quality and outcomes of subprojects.
P126579 | AFR RI-The Eastern Electricity Highway Project under the First Phase of the Eastern Africa Power Integration Program | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | IEG derives the following lessons from the ICR:1. In a complex cross-border project, sequencing ofconstruction contracts calls for close oversight: As demonstrated by the project, sequencing the completion ofconstruction contracts in parallel and co-dependent on each other proved to be hugely challenging, making the role of an oversightbody critical. Despite the project having elaborate arrangements for project oversight, including a Joint ProjectCoordination Unit, a Joint Steering Committee and a Joint Ministerial Commission, the arrangements were never fully realized.In practice, pressing issues that surfaced during the co-financiers implementation support missions requiring higher-levelinterventions were brought piecemeal to the utility CEOs and relevant ministers by them, and not fully resolved. Goingforward, it will be important to ensure that participant countries trading power on the interconnector establish problem-solvingarrangements at the appropriate levels when the co-financiers have ended their implementation support.2. Ininfrastructure projects involving land acquisition with large numbers of PAPs, it is prudent to delay the launch of bidding onconstruction contracts until PAPs have assented to the wayleave and/or payment of compensation for PAPs has commenced:The project experienced several years of delay in identifying and seeking the assent of PAPs in Kenya, which led tomultiple collateral impacts. Works projects already completed were vandalized, and contractors had to be remobilized toremedy the damage. An inadequate budget provided by the Government to KETRACO led to delayed compensation payments to PAPsand late payments to contractors, prompting more contractor claims, and the cycle continued. Contractors making bids on suchprojects typically factor in the likelihood of delays based on the experience of past projects, so bids might not be as competitiveas they might otherwise have been.3. For a complex project involving two or more countries, use of a specialpurpose vehicle (SPV) can offer advantages over reliance on PIUs: The project showed that PIUs in both countrieswere dependent upon allocation of funds (which were sometimes inadequate) in the annual government budget cycles. TheKenya-Ethiopia interconnector was however revenue-generating, and an SPV structure would have enabled a portion of the revenue tobe retained and utilized for managing consultants, paying compensation to PAPs and financing training courses and otheractivities. This would have allowed the supervision of construction and mobilization of technical consultancy resources tohave been handled more effectively than arrangements that relied upon PIUs housed within the two utilities.
P126580 | PH - PH Development Policy Loan 2 | East Asia and Pacific | Philippines | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2015 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR distills the following main lessons: A programmatic multi-year DPL can provide an effectiveplatform to support reforms and institutional development. Complementary knowledge and technical assistance, as well asclose coordination among different teams and partners are vital for results. ME frameworks need to take into accountdata gathering constraints. When supportingenhanced fiscal management, acareful balance needs to bestruckbetween the risks and criticality of supporting legislative reforms, and between revenue and expenditure in budgetmanagement reforms.IEG concurs with these lessons, which are grounded in the experience of this operation. Inparticular, given the complex political economy in the Philippines,they underscore the importance of broad consultation andconsensus building thatneeds toinvolve the legislature from the outset in the discussion ofcritical policyreforms, when these depend on legislative endorsement.
P126583 | Second Disaster Risk Management DPL with Catastrophe Deferred Draw Down Option | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2013 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099300512232216987/text/P1265830ae430207b0b751081465b2153d9.txt | http://documents.worldbank.org/curated/en/099300512232216987/pdf/P1265830ae430207b0b751081465b2153d9.pdf | The ICR draws the following main lessons from the experience of implementing this operation, with some adaptation oflanguage.1. In cases where subnational entities are responsible for the monitoring of the results indicators, ithelps if extensive support is provided to them by way of technical assistance at the design stage. In this operation, therather limited progress in achieving results particularly in the initial years, were due to the weak capacity of themunicipalities.2. Strong analytical underpinning and timely technical assistance during implementation can help insecuring government ownership. In this operation, the analytical base and technical assistance provided by the Bankgreatly helped in getting the government committed to the reforms.3. It is useful to have a report on theachievements and progress during implementation. The operations renewals offer the opportunity to update or adjust theresults indicators depending on the progress achieved so far.4. Although the Cat-DDO was originally designed tocover emergencies due to natural hazards, the COVID19 pandemic demonstrated the importance of being able to use drawdowns in theface of a health emergency, such as epidemics or pandemics. This health emergency in Colombia highlighted the importanceof clearly defining the Cat-DDO activation eligibility criteria.
P126586 | GZ:Government Services for Business Development | Middle East and North Africa | West Bank and Gaza |  | FCS | Other | Trade & Competitiveness | SPF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/498291490624797233/text/ICRR-Disclosable-P126586-03-27-2017-1490624778642.txt | http://documents.worldbank.org/curated/en/498291490624797233/pdf/ICRR-Disclosable-P126586-03-27-2017-1490624778642.pdf | The first four lessons are drawn from the ICR (page 14), with some adaptation, and the fifth by the IEG.One, theBank needs to carefully consider a governments institutional capacity when selecting the financing instrument for anoperation. The project was designed as a recipient-executed grant operation, but should have been more appropriately packaged as aBank-executed technical assistance operation. The MNE lacked the experience and the technical capacity to implement the projecteffectively and efficiently. A technical assistance operation would have allowed the MNE to steadily gain experience andfamiliarity with Bank projects, processes and procedures and to progressively develop the institutional capacity to implement theproject and similar operations in the future. A Bank-executed operation would have given the Bank a firmer hand over theimplementation of the project, including control over procurement and the hiring of consultants. A Bank-executed technicalassistance project needs alternative donor funding, however.Two, the Bank has to re-examine a project proposal when amajor operative assumption fails to materialize. The project was intended to complement the Palestinian Marketplace Project (PMP),a larger multi-donor initiative to support private sector development in the West Bank and Gaza. In which case, the relativelylarge operational outlay for the project (US$820,000 of the US$3.0 total project cost) could have been justified in view of therole that that the project played in creating the institution --- the Business Development Unit at the MNE --- that would spearheadthe implementation of the much larger PMP. The subsequent exclusion of the Bank in the PMP ought to have raised the question ofwhether the project was still justified as a stand-alone operation, with a large administrative cost (US$820,000) and a smallproject amount (effectively US$2.18 million, after deducting the project management cost).Three, the Bank needs to bewary of the institutional framework and of changes in the institutional framework within which a project operates. The MNE, theimplementing agency of the project, was restructured after the project was approved, but before it became effective. The projecthad assumed that the MNE was a centralized agency. The restructuring de-centralized the organization, mandating it to deliverservices to the private sector through regional offices. The Bank also appears to have been unaware of the limits placed by thecivil service law on the number of staff that any West Bank and Gaza government organizational unit can hire, constraining theheadcount at the PIU.Four, recruiting and retaining experienced and skilled staff for a term assignment at a projectmanagement unit is not always an easy task, and more so at government salaries. The staffing problem was heightened in this case bythe fact that the project was a private sector development initiative, an operation that required combined private sector andpublic sector work experience of the prospective staff. The fragility, conflict, and violence setting of the West Bankand Gaza made recruiting well-educated and highly-experienced staff doubly difficult.And five, the Bank and agovernment may want to consider contracting a management consulting firm to supply the range of technical experts required for aproject, if hiring individual consultants proves unworkable. The Bank and a government may also want to consider contracting aprocurement services provider, when undertaking procurement activities in-house proves difficult. A government may embed staff inthe firm to gradually gain experience with the function. Procurement and consultant recruitment were unduly difficult in thisproject. Resorting to competent private firms may have offered a solution.
P126596 | Enhancing the Climate Resilience of Coastal Resources and Communities Project | East Asia and Pacific | Samoa | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099555006152223818/text/P126596053ca1c0280b14e02136af53c080.txt | http://documents.worldbank.org/curated/en/099555006152223818/pdf/P126596053ca1c0280b14e02136af53c080.pdf | The ICR presented four lessons and recommendations in Section V. The following lessons in the ICR can be relevant to otherprojects on enhancing climate resilience in coastal areas, and are presented here with some editing.Overly broadobjectives with unclear expected outcomes and incomprehensive Results Framework can weaken a climate resilience enhancingprojects relevance of design. Although the PAD listed expected outcomes, some were not captured by the resultsframework (ICR, para 82). As resilience is multi-dimensional and may take a long time to achieve, the PDO may need to be narrowedfurther to the types of interventions and time frame that a project is expected to cover.Nature-based adaptationsolutions (e.g., mangrove protection and fish reserves) may not match with vulnerable and poor coastal households short-termpriorities and immediate needs. Under the project, communities tended to prioritize resilience investments that addressedtheir immediate needs based on gender roles (e.g., water supply infrastructure) (ICR, para 113). Nature-based solutions wereimplemented at the district level by specialized agencies. Projects that use a participatory approach to define adaptationsolutions need to be aware of priorities among different demographic and gender groups and guide the process accordingly. Givingwomen prominent roles in sub-project selection at the community level would be crucial. The ridge-to-reefapproach may offer a good model for adaptation that promotes longer-term, structural change by gradually helping coastalcommunities settle in safer upland areas, but it takes long time to implement. The project encouraged the coastalcommunities to voluntary resettle to inner areas by: (i) using participatory climate risk and resilience plans (i.e., CIM Plans) toprioritize adaptation investments; (ii) making village- and district-level investments within a given catchment and administrativearea; and (iii) targeting the most vulnerable with basic services and livelihoods; however, the approach took seven years and ahalf (ICR, para 114). This adaptation has shown good results under this project. For example, piped water systems further inlandhelped coastal communities settle more permanently in safer upland areas, and upper watershed management aimed to decrease coastalerosion and flooding (ICR, para 51).
P126611 | Liaoning Coastal Economic Zone Urban Infrastructure and Environmental Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2020 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/408401593209160055/text/China-Liaoning-Coastal-Economic-Zone-Project.txt | http://documents.worldbank.org/curated/en/408401593209160055/pdf/China-Liaoning-Coastal-Economic-Zone-Project.pdf | The operations offered five lessons and recommendations presented below that teams could consider insimilar futureoperations: Technical assistance interventions may benefit from early identification and adequatefinancing. In this project, just-in-time technical assistance in transport and asset management informedthe PanjinPublic Transport Authorityhow to deliver optimal bus services. Armed with a better appreciation for OM needs in theinvestment life cycle, authoritiesincreased thecities annual road maintenance budgets, from 8 to 15percentat project closing. Interventions in transport services are best served by a menu of possible technical assistanceneeds and accompanied by sufficient budgetary resources to carry them out to coincide with opportunisticneeds. Demonstrating cost effective solutions may boostlocal governments resolve to champion supportfor greenalternatives to conventional water supply.In this project,in Lingyuan, over 12 million cubicmeter of reclaimed wastewater was sold to 6 largeindustries, equivalent toUS$4.3 million in revenues for the localgovernment and savings of around US$3.6 million in operating costs for the industries. Lingyuan decided to buildasecondwastewater treatment plant after the project closed. The local government experiencedthat using reclaimedwastewatermitigated urban water scarcity, improved efficiency inwater use, reduced water pollution, minimizedgroundwater extraction, and improved water ecosystems. Their experience demonstrated that they could recover costs, facilitatesavings for industries served by reclaimed waste water, and that together, the local government and industry could contribute togreen growth. Other cities could follow their success in recycling municipal wastewater by adopting appropriate policies andenforceable regulations that allowed the government to recover their costs, generate revenues,and provide industries withsavings. Critical assessment of the risks associated with the availability of counterpart funds maymitigate implementation challenges. In this project, two of the participant cities and one with a subcomponent critical tosubstantially achieving outcome dropped from the project because of the lack of access to counterpart funds. Critical assessment atappraisal may propose appropriate mitigating measures or identify alternative activitiesto replace project components thatmay drop to remain focused on achieving the projects objectives. Similarly sized cities may be encouraged toreplicatethe results of innovation in green mobility. In this project, the innovations adopted by Panjin Citytransformed its public transport systems through better routes, better services, and improved infrastructure. Less polluting busesalso gave the national government a model for replication by similarly sized cities. These innovations in Panjin City demonstratedhow other cities could pursue greener and more inclusive growth strategies. Improved surroundings may fosterfurther improvements outside of the project. In this project, residents of Kundian saw that paved dirt roads around theirhomes allowed them increased access to major thoroughfares, signaling access to more developed urban areas but also improved theirimmediate surroundings. Residents because more conscious of improving the appearance of theriver near the roads. Residentsreportedly discontinued dumping their waste in the river after seeing these improved roads. The Environment Bureau provided trashbins along the paved roads and made more frequent waste collection. The Water Resource Bureauprovided proper embankment ofthe river outside of the project requirements. The improved surroundings introduced by the paved dirt roads led to improving thearea surrounding the river beside those dirt roads.
P126663 | Improved Investment Climate within the Organization for the Harmonization of Business Laws in Africa (OHADA) | Western and Central Africa | Western and Central Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099121223213031115/text/P1266630a13fe006f0b8d6009dfa916b74e.txt | http://documents.worldbank.org/curated/en/099121223213031115/pdf/P1266630a13fe006f0b8d6009dfa916b74e.pdf | The ICR identified a few lessons and recommendations, and this review highlighted two lessons, as summarizedbelow.Coordination, decision-making,and conflict-resolution mechanisms need more scrutinyin the designof regionalintegration projects.The project design centralized the fiduciary functions in thePS OHADAdesignated as the PIU. Implementation arrangements designatedthe Permanent Secretary asthe Project Coordinator withpowers to decide on activities to be implemented by the other affiliate institutions of OHADA CCJA and ERSUMA. Because thePermanent Secretary disagreed with the content and scope of ERSUMA-led activities, these were delayed, resulting in the inabilityof the project to disburse fully. In future projects with multiple beneficiary institutions relying on a centralized PIU, it isimportantto (i) clarify theroles and functions,avoid making the head of an organization project coordinator, andhire a dedicated technical project coordinator or give more technical implementation autonomy to satellite institutions, and (ii)identify high-level steering committees with representativesof member countries to increase accountability of beneficiaryentities. Moreover, country commissions, which depend on governments and not OHADA, were not specifically assigned by the projectto monitor and collect data on the implementation of UAs at the country level. This has limited the projects ability to tracklong-term outcomes and the impact of the investment climate reforms in the member countries.A more effectivelending instrument to fund regional technical assistance must be thought throughto warrant results on the ground.The World Bank usually uses the Development Policy Operation (DPO) or Program for Results (P4R) to trigger reforms.Inthe context of the OHADA operation, a DPO was nota viable option as it is not possible to use such an instrument inregional operations with regional institutions. The PforR did not exist at the time of the project design andassumes that theregional organization being supported has resources that can be used up front and later reimbursed. Based on the above and theoverall results of the project, the IPF was the only viable lending instrument to support OHADA. In the future, the World Bankshould pilot a hybrid instrument in the context of operations with regional organizations, blending both policy reform triggers andinvestments.
P126722 | Municipal Water Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2015 | 2016 | ICRR | >=10 million & <25 million | Highly Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/616131467230358571/text/ICRR-Disclosable-P126722-06-29-2016-1467230344955.txt | http://documents.worldbank.org/curated/en/616131467230358571/pdf/ICRR-Disclosable-P126722-06-29-2016-1467230344955.pdf | The ICR draws the following main lessons from implementing this project.(1) An enabling environment is required forencouraging private sector participation and sustained service delivery.This is particularly so for Former Soviet Unioncountries where the prices that consumers have to pay for water supply and sanitation services remain low. This could haveimplications for the financial sustainability of the utility.(2) A tailoring of the PPP to the conditions of thelocal service area is required. This project showed PPP arrangements that worked in Armenia were less effective in AWSC servicegiven the disparities in asset base, customer base and OM requirements.
P126722 | Municipal Water Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2015 | 2018 | PPAR | >=10 million & <25 million | Highly Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/455721532982382009/text/127226-PPAR-P126722-P166560-PUBLIC.txt | http://documents.worldbank.org/curated/en/455721532982382009/pdf/127226-PPAR-P126722-P166560-PUBLIC.pdf | 7. Lessons The sustainability of development outcomes is enhanced when the World Bank maintains its strategic and operational engagement over time, especially when social and political risks are high. The World Bank has played a pivotal role in reforming the water sector in Armenia since the late-1990s by helping to create the environment to bring in private operators, achieve operational efficiency, and improve financial sustainability as part of a PPP program. Given the remaining challenges, the World Bank can continue to play a key role in the sector in terms of lending, but especially so through sector analysis and advice to help ensure that the improvements in management, operations, finance, and water supply for customers can be sustained. The World Bank's continuous advice and technical assistance, provided in parallel with lending and in coordination with other donors, can result in effective partnership with the government and the private sector. The experience in Armenia across four World Bank-financed projects since the late-1990s shows that the PPP achievements resulted from the sustained partnership involving the government, private operators, other donors, and the World Bank. While the World Bank and donors financed most of the investments under the PPP contracts, the technical and advisory assistance during preparation and supervision were especially important as Armenia became increasingly open and sought advice on the implementation of PPPs. The World Bank played a lead role in this process during the early years and slowly retrenched as the PPP reforms became more mature and other donors financed the second generation of reforms. Tailoring of the EMC to the conditions of the local service area can help achieve results. The nature of several activities shows how, under the EMC, approaches to improving access and availability were adapted to local conditions. In some towns and villages where people had been getting water for free from wells and public standpipes, the AWSC was able to increase metering and collection by instituting a very popular lottery where only paying customers can purchase a ticket and win a monetary price. The lottery, according to the ICR, increased the number of paying customers from 30,000 to 200,000. Similarly, to reduce illegal connections, the AWSC introduced a program that identified customers who purchased energy and were not water customers. The AWSC then installed thousands of new, more accurate meters. This led to an increase in average domestic metered consumption from 88.5 l/c/d to 119 l/c/d. Improved metering also laid the groundwork for improved leak detection and a full-scale NRW reduction plan that tackles technical losses. The lesson that can be drawn from these efforts is that approaches to deal with paying-for-service provisions, must take into account local conditions and opinions.
P126735 | Strengthening Public Management and Integrated Territorial Development | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2014 | 2017 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/193301526393407556/text/Brazil-Strengthening-PM-and-Int-Territorial-Dev.txt | http://documents.worldbank.org/curated/en/193301526393407556/pdf/Brazil-Strengthening-PM-and-Int-Territorial-Dev.pdf | IEGselected the following main lessons from the ICR, with some modification of the language.(I) MultipleProject Implementation Units (PIUs)within different state agencies could undermineprojectownership.This project showedthat having multiple PIUs (as opposed to having astrong PIU with full time and well trained staff) could increase the risks associated with separate anddisconnectedactivities and this could contribute to undermining projectownership on the part of the different stateagencies.(2) It is necessary to have a clear and specific PDO and not align disconnected sectoral agenda under abroad and unclear PDO.This project showed that lack of a clear PDO could undermine monitoring projectperformance.(3) A common rationale may be useful for addressing coordination problemsinprojects dealing with multi sectors. In this project, there was not much of an incentive foreffective cross-sector collaboration, at both the Bank and Borrower sides.This resulted in excessive coordination problemsand inefficiencies, which affected implementation.(4) Restructuring should be processed early on toaddressimplementation problems. Even though restructuring processes are time-consuming and cumbersome and maybeevenpolitically difficult,it would be useful to processrestructuring,as soon as structural issues that needcorrection have been identified. This could help incountering the highcost of delays and unsatisfactory results atproject closure. In this project, although restructuring was considered, it was not completed.(5) Clear Bankleadership is required for complex multi-sector projects. One common communication and leadership problem duringimplementation of this project was due to the multiplicity of communication channels on the Bank side (and on the Borrowersside). Bank sector specialists had their own agendas with their respective state counterparts, including on the projectscope.(6) Given that metropolitan management is an ambitious but critical agenda for the Bank, a programmaticengagement over a longer time frame may be required for such projects. The experience of this project showed that sincesuch projects require the Bank and the Borrower to address issues such asenabling environment for multi-jurisdictionalcoordination. The project time frame needs to be realistically considered at preparation.(7) Technical assistanceloans should be timely attached to Development Policy Loans (DPLs) for enhanced institutional commitment and impact. Theexperience of this project demonstrated that Technical assistance loans should focus on the areas of specific DPL operations thatare currently under preparation.
P126740 | Solomon Islands Development Policy Operation 1 | East Asia and Pacific | Solomon Islands | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2014 | 2016 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/848131467988951331/text/ICRR14886-P126740-PUBLIC.txt | http://documents.worldbank.org/curated/en/848131467988951331/pdf/ICRR14886-P126740-PUBLIC.pdf | The first two lessons are taken from the ICR with some adaptation of language, and the third is drawn by IEG: Budget support combined with broad policy dialogue arrangements may help achieve reforms. In the Solomon Islands, the Core Economic Working Group, a coordination mechanism involving key government and donor interlocutors led by the Bank, combined with the Economic and Financial Reform Program (a common Government matrix for key reforms backed by budget support), was instrumental in achieving the DPO reforms.Modest reform goals may be appropriate for gradual reformers. Reforms that are uncomplicated and feasible may help build up momentum for additional change. PFM is an example, where the reform path is fairly long and needs to be broken down in steps that a gradual reformer can focus on and achieve.Even modest reforms may take time to achieve full development outcomes. The Solomon Islands DPOs achieved progress in PFM but full results, where the value of the reforms for the population at large materializes may take more than the usual time horizon covered by a DPO program.
P126744 | Relaunching Agriculture: Strengthening Agriculture Public Services II Project (GAFSP - IDA) | Latin America and Caribbean | Haiti | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061423090532084/text/P1267440df10a60e40975f08c30272eb42d.txt | http://documents.worldbank.org/curated/en/099061423090532084/pdf/P1267440df10a60e40975f08c30272eb42d.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Building institutional capacity is important in fragile settings and while capacity-buildingactivities can slow the initial pace of implementation, they can yield significant long-term benefits.This projectsought to build the capacity of the Ministry of Agriculture, Natural Resources and Rural Development (MARNDR) by placing theresponsibility for coordination on the MARNDR, rather than having a parallel Project Implementation Unit (PIU) and relying onrelevant departments for the technical supervision of project-supported activities in their areas of purview. While this approachcontributed to delays in the initial years, it resulted in significant improvements in how the Ministry performed its mandate, aslines of responsibility were clear and capacities were reinforced.2. The use of locally-based operators indelivering services and locally-based project coordination staff can help in integrating local communities. In thisproject when restrictions on mobility due to gang violence and the COVID-19 pandemic impeded close field-level follow-up by theCentral Project Coordination Unit, project implementation was able to continue, due to the decentralized operators in the projectareas and supervision by locally based teams of the Project Coordination Unit. Such an approach can also help in building capacityin a fragile context.3. Strengthening community capacity and facilitating civil engagement can help improveresults and reduce social risks. In this project, close collaboration between the Departmental Agriculture ConsultationTable, irrigators associations, rural producers organizations and other local institutions helped prioritize and defineinterventions that yielded major dividends in terms of commitment.4. Adapting flexibly and respondingrapidly to changing circumstances is especially important in a fragile country context. The implementation of this projectwas undermined by large and diverse external shocks (political, macroeconomic, climate-related, animal and plant-related and by aglobal pandemic).The projects strong grounding in strategic priorities established by the Ministry of Agriculture, NaturalResources and Rural Development and its flexibility in responding to changing priorities and emerging challenges and the Bankshelp through project restructuring proved invaluable for its success.
P126749 | Belo Horizonte Urban Development Policy Loan | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2013 | 2015 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/828511473924948803/text/ICRR14931-P126749-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/828511473924948803/pdf/ICRR14931-P126749-Box396299B-PUBLIC.pdf | The DPL's lessons, which are well formulated and appropriately derived from the DPL's own implementation experience, are paraphrased below:It is important to ensure the coherence of the various PDOs in multi-sector operations.In the case of this DPL, the PDO related to sustainable urban governance was less connected than the two other PDOs. Moreover, its level of technical and political complexity was not compatible with an integrated multi-sector operation.Re-appraisal may be needed when there are substantial delays between approval and effectiveness. Two years elapsed between the appraisal and effectiveness of this DPL, hence the baselines and many of the targets in the Results Framework were already obsolete when the DPL became effective.Sub-national operations offer significant potential for cross-fertilization and economies of scale.This DPL has shown that successful innovations in subnational operations could be replicated in other states and municipalities. There are also potential economies of scale and harmonization benefits by interacting simultaneously with municipal, state and federal stakeholders.Policy actions in a DPLâ€™s Policy Matrix should be commensurate with the intended results.Modest targets cannot be expected to contribute significantly to a more ambitious policy area. In this DPL, for example, the rehabilitation of 250 housing units could not make a meaningful contribution at the municipal level to the goal of improving living conditions and including poor and vulnerable citizens.Significant reforms such as that of the civil servantsâ€™ pension system require a proportional level of effort at preparation.In this DPL, greater effort should have been made to (i) analyze the (lack of) institutional capacity for pension reform and (ii) ensure the feasibllity of pension reform from the technical, economic and political perspectives.
P126773 | West Africa Region Fisheries Program AF Guinea, Sierra Leone & Liberia | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099062623122019196/text/P1267730c5341c0b20bdaf061a8e41fe0e6.txt | http://documents.worldbank.org/curated/en/099062623122019196/pdf/P1267730c5341c0b20bdaf061a8e41fe0e6.pdf | The ICR (p. 40-41) included several lessons learned: Fisheries management reforms require a medium tolong-term horizon given the need to engage with multiple stakeholders and address behaviors that are deeply routed in tradition andoften related to the poorest segment of the population. The design of this project was too ambitious in some areas such asin controlling capacity and access in the small-scale segment resulting in not being able to build a broad consensus on effectivefisheries management, demonstrate results, and develop viable models. Since there will not be a follow-on project, there is a highrisk of putting the project outcomes at risk. Community Management Associations (CMAs) are an effective mechanismfor introducing new harvesting rules, local surveillance, enhancement measures and local site monitoring to recover fish stocks andsustain fisheries productivity in managed fishing areas. This project was able to establish or strengthen CMAs. The nextstep will require defining access modalities for artisanal fishermen outside the community and improving coordination among variousCMAs sharing resources. Performance based management linked to disbursements can be a critical tool to provideincentives for a swift implementation, but it is important to allow for a smooth application. In this project, theeffectiveness of the tool was impacted by the complexity of implementation arrangements due to issues such as i) complicatedprocesses related to indicator definition, measurement, success metrics, and allocation of proceeds making implementation andmonitoring difficult for PIUs; ii) contracting independent verifiers made coordination between the RCU and the two PIUschallenging; iii) backloading of technical audits towards the later years for cost reasons left limited time and space forrecipients to use the funds and apply corrective measures to improve performance; iv) pre-defined program of eligible activitiesleft little possibility for adjustments; and v) requirement of aspecific RCU-contracted financial audit which was deemed notnecessary in retrospect given the regular annual audit of financial statement.
P126782 | LIFELINE ROAD NETWORK IMPROVEMENT PROJECT | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099011924171037414/text/P12678218a9d1e01d1bda811485ca5ad807.txt | http://documents.worldbank.org/curated/en/099011924171037414/pdf/P12678218a9d1e01d1bda811485ca5ad807.pdf | The ICR draws the following two lessons from the experience of implementing this project, with some adaptation of language fromthe ICR.1. Building upon successful implementation of a previous project may raise the potential for success.This project on lifeline roads was prepared, while the previous lifeline project was ongoing. The Project ImplementationUnit was familiar with the Banks fiduciary requirements. Further, priority investments and detailed technical design andbidding documents had already been completed even before Bank approval for this project. This contributed to the commencement ofproject activities immediately after effectiveness.2. Additional effort may be required to develop a sustainablerural road strategy for the long term. This project aided in developing and operationalizing a Road Assessment ManagementSystem (RAMS) for prioritizing asset management appropriately. However, the more significant challenge was to ensure adequatefinance for the future.The RAMS system needs to be supplemented by sufficient sectoral budgeting to ensure that therehabilitated roads are not undermined for want of maintenance activities.
P126791 | Public and Social Sector Transformation Project (PSST) | Latin America and Caribbean | Antigua and Barbuda | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/212481543249370447/text/Antigua-and-Barbuda-AG-Pub-Soc-Sctr-Transformation.txt | http://documents.worldbank.org/curated/en/212481543249370447/pdf/Antigua-and-Barbuda-AG-Pub-Soc-Sctr-Transformation.pdf | The ICR identified a number of lessons emerging from the projects experience (section V, paras 67 to71):1.Vanilla operations are optimal when engaging with afirst-time Borrower with limited institutional capacity. Breadth and complexity of reforms matter,and thesemust be matched withthe capacity of the Borrower to undertake change. It is not advisable to engage with newBorrowers in major politically-sensitive reforms that involve complex multi-sector operations. Similarly, dialogueand implementation are more challenging when dealing with Borrowers that are unfamiliar with fiduciary, procurement, management andsupervision requirements of Bank operations.2 . The chain is as strongas its weakest link. Change management at lower levels of government needs to be strong. In theface of public sector reforms, potential resentment between established civil service and non-established public employees,asin the case of Antigua and Barbuda, is something that needs to be thoroughly studied. At project preparation the degree ofresistance to change cannot be overestimated, especially in view of upcoming elections and the likelihood of change of leadershipand overarchingpriorities. 3. Instead of aiming for large overall, public sectorreforms, in a context such as Antigua and Barbudas, a focus on technical aspects cantailordecisions to the Borrower context. In this case, difficultredistributions of authority ingovernance of the civil service, in particularfrom the Public Service Commission to a new entity responsible for civilservice management,were unlikely to be adopted.4. New Borrowers requireintensive and continuous Bank engagement. This project confirmed that that first-time operations call for early,constant, and intensive support from appraisal throughout implementation ofan operation.Lessons suggested by IEG:1. Support for reform champions among stakeholdersis key to moving forwardaprocess of change.When thescope of reform requires newmindsets, culture and attitudes at alllevels, from leadership to lower-level civil servants, anticipatedoutcomes are highly unlikely to be achieved in the absenceof broad stakeholder ownership and commitment. The Bank should be ready to facepolitical challenges, provide supportforallies,andbecome involved in additionaldialogue to help unlock impasses.2.Political economy analysis is paramount during project preparation in an environment of imminent electionstounderstand, and perhaps even anticipate,potential discontinuity of interest in reforms initiated by an outgoingadministration.
P126813 | Ma'anshan Cihu River Basin Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099520007272257748/text/P126813068158407208ae10cd8d1c099323.txt | http://documents.worldbank.org/curated/en/099520007272257748/pdf/P126813068158407208ae10cd8d1c099323.pdf | The following lessons in the ICR stood out as important and relevant to other projects and are presented here with someediting: Flood control measures, drainage service, and water environmental improvements can be effectivewhen approached from an integrated river basin management perspective. In this project, the design of rehabilitation worksfor the tributaries and main river and recovery of water retention capacity was based on hydraulic computer modeling of the wholebasin drainage system. For example, the definition of the capacity of upgraded pumping stations was articulated with the expectedgain in hydraulic capacity from the rehabilitation of tributaries, main river, and ponds. Likewise, the improvement of the riverwater quality (owing to reducing untreated wastewater discharges) was coordinated with complementary measures to control futurecontamination (water quality monitoring system). The alignment of project outcomes with themunicipalitys long-term development objectives is dependent on the availability of the municipalitys planninginstruments. This project greatly benefited from the Maanshan city urban master plan, the Cihu River BasinEcological Environmental Integrated Rehabilitation Plan, and municipal drainage plans. Without such plans, river basinrehabilitation is commonly approached as a stand-alone project with no articulation with other development objectives of otherplans. The use of information technology (IT) offers opportunities to strengthen the capacity ofgovernment agencies in charge of river environmental protection. The use of a digital platform for real-time monitoring ofriver water quality coupled with an Early Warning System (EWS) provided the Environmental Protection Bureau (EPB) with a new andefficient way to monitor and control the degradation of the Cihu River Basin water quality. Through the digital integration ofmonitoring data on water quality and wastewater pollution sources, analysis of water quality status, and a water pollution modelingplatform, the EWS enabled the EPB to detect and respond to pollution events in real time.
P126817 | Guangxi Laibin Water Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/468861608175359745/text/China-Guangxi-Laibin-Water-Environment.txt | http://documents.worldbank.org/curated/en/468861608175359745/pdf/China-Guangxi-Laibin-Water-Environment.pdf | The main lessons adapted from the ICR are:When cities are experiencing rapid urban growth, proactive measuresare necessary to mitigate risks related to potential changes in local master plans.The City of Laibin experiencedunprecedented urban growth after project start-up. This resulted in substantial amendments to the local master plan and land useplans, affectingproject implementation and causing the project scope to be reduced. Measures to consider for such risksinclude, at the project preparation stage, conducting in-depth review of local plans in the context of local urban growth trendsandavoiding, to the extent possible, project investments in areas subject to potential land use planning changes, or subjecttoambitious urban development schemes. During project implementation, continuous consultation with the local government andlocal urban planning authorities is essential to inform and support any necessary adjustments to projectdesigns.Failing to estimate land/resettlement complexities and costs realistically can delay implementation,particularly in rapidly urbanizing areas. The land acquisition and resettlement costs in the project were more than threetimesthe estimate at appraisal, partly due to an underestimate of persons affectedand partly due to new compensationstandards. Implementation delays occurred due to the challenges of mobilizing additionalcounterpart funds. Special attentionshould be paid to the land/resettlement costs in peri-urban areas which are experiencing rapid urban sprawl withescalatingconstruction of private buildings.An integrated approach to flood risk management has proved to beeffective in fast growing cities.The integrated approach used in the project, which combined structural andnon-structural measures, proved to be effective in flood risk reduction and flood control in Laibin. However, the non-structuralaspects need to be supported by strong results indicators. Measures that could have been used includedplans, tools andsystems embedded in the citys administrative procedures,the testing and use of the emergency warning system andplans,as well as measures to take over the OM responsibilities for the new assets. Furthermore, there should have beenmeasures of OM delivery.When most bidders are unfamiliar with the World Banks procurement policy andprocedures, holding orientation sessions can be highly beneficial.Many new bidders in China were not familiarwith the tender and contracting processes applied in World Bank-financed projects. Followingdomestic practices, oftenresultedin unrealistic or unresponsive bids and in time-consuming issue resolutions during construction. Several bids underthis project were rejected due to bidders unfamiliarity with the requirements, and some implementation delays were caused bycontractors not being familiar with processes for variation orders. Orientation of bidders prior to bidding helped ameliorate thisissue. Pre-bid orientation sessions in addition to training activities and workshops can help mitigate thissituation.
P126832 | CH GEF Municipal Solid Waste Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099350002142216484/text/China000CH0GEF0lid0Waste0Management.txt | http://documents.worldbank.org/curated/en/099350002142216484/pdf/China000CH0GEF0lid0Waste0Management.pdf | The ICR listed several lessons that emerged from the project. Three of those lessons with a broader application are summarizedbelow with adjusted language:Bank intervention that is timed well and is in line with country policies/regulations can have better results. When the project was being prepared in 2014, the Government of China introduced a newdioxin emission standard for incinerators to be implemented by January 2016. This regulation provided the basis for the project toset targets which were in line with the countrys environmental regulations and enforced compliances from the implementingagencies.The customized road map based on the logical framework for BAT/BEP compliance can lead to greaterownership from the demonstration incinerators and were a key to success. The following logical framework: pre-audit -OEPA - dioxin baseline monitoring - OIP - BAT/BEP investment plan - implementation - verification thatwas developed and then adopted by the participating incinerators helped improve their operations, and brought in several benefits,including related to cost saving. The co-financing brought in by the incinerators for further technical improvements was a clearevidence of their ownership.Community outreach and data disclosure based on detailed social assessments iscritical in getting the publics support for environmental projects. During project preparation, detailed socialassessment which was gender-informed was prepared. Based on the assessment, the project undertook training for the communicationstaff of the demonstration incinerators, developed targeted communication messages, specifically focusing on women who were foundto have limited understanding and awareness of the emissions but had greater concerns of the health impacts of pollutionlevels. The ICR (Paragraph 92) indicated that the disclosure of air pollutant information by incinerators helped build trustand accountability, improved the flow of communications between stakeholders, and allowed for early grievance redress.
P126833 | FATA Rural Livelihoods and Community Infrastructure Project (RLCIP) | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/970271574705327553/text/Pakistan-PK-FATA-Rural-Livelihoods-Infra.txt | http://documents.worldbank.org/curated/en/970271574705327553/pdf/Pakistan-PK-FATA-Rural-Livelihoods-Infra.pdf | The ICR (p. 30-32) included several useful lessons learned which were adapted by IEG: The sustainabilityof project activities is a critical aspect when designing a project, especially in areas of fragility, conflict and violence (FCV)since any marginal gain made has a positive impact on beneficiaries when it is maintained in the long-run. This projectwas not designed to ensure the financial sustainability of OM activities and functional OM committees resulting inuncertainty regarding future funding. Thorough assessments during project preparation are essential even in anemergency operation to ensure successful outcomes. In this project, livelihood activities were designed under theassumption that there was a demand for them. However, the Bank team did not take into account the agronomical conditions for thepoultry and bees to survive and limited the activities to agriculture and livestock when only 7.2 percent of the land in FATA wascultivable and over 80 percent of the FATA population were employed outside FATA. Also, the distribution of swing machines had anegative impact on women who already worked in this area before project implementation started since it saturated the market.Finally, the skill trainings for youth was not market-driven and therefore did not support them in finding ajob. Defining the capacity of local institutions and quality of governance environments and plan projectactivities accordingly can have positive impacts on FCV projects. In this project, no activities were implemented underthe Additional Financing due to the corruption court case between the project staff and the FATA secretariat and the merge betweenFATA and the province of Khyber Pakhtunkhwa. Developing a functional ME system that includes fragility,conflict and violence specific indicators is critical for a successful project implementation. In this project, the lackof a ME data did not allow for the identification of implementation bottlenecks and modify project implementationaccordingly. Also, the lack of fragility, conflict and violence specific indicators undermined the assessment and theopportunity to learn from this project.
P126848 | Support for Capacity Dev't of the AUC and other African Union Organs | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099061024142510101/text/P12684814c5bfe0d3191fd14eac2d245b15.txt | http://documents.worldbank.org/curated/en/099061024142510101/pdf/P12684814c5bfe0d3191fd14eac2d245b15.pdf | This review agrees with the lessons outlined in the ICR (p. 12), and adds the following lessons: Projectsaimed at capacity building and institutional reform can serve as catalysts for deeper regional integration.Regionalintegration initiatives, such as those facilitated by the AU and RECplay a vital role in promoting economic growth, enhancingtrade, and addressing common challenges collectively. By supporting institutional capacity building at the regional level andenabling the AUC to better leverage its capabilities and resources, the project contributed to strengthening regional cooperationand integration efforts.Nonetheless, it is crucial to acknowledge that the AUCs role primarily lies in advocacy andfostering partnerships, as the responsibility for implementing regionalintegration initiatives andagreements ultimatelyis the mandate ofmember states. The uptake of activities to deepen regional integration depends onthe readiness and motivation of member states. When member states perceive their national interests as beingsupported and enhanced by regional initiatives, they are more likely to commit to and actively participate in regional integrationefforts. This alignment is crucial not only for the initiation of projects but also for their sustained implementation and success.Effective regional integration therefore requires a harmonious approach where both national and regional objectives are seen asmutually reinforcing, leading to collective benefits such as improved economic stability, increased trade, and stronger politicaland economic alliances. This synergy can help overcome potential resistances and challenges, facilitating smoother cooperationacross different governmental and regional levels.
P126856 | CN-Jiangxi Poyang Lake Basin and Ecological Economic Zone Small Town Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/217611613512125604/text/China-Jiangxi-Poyang-Lake-Small-Town-Project.txt | http://documents.worldbank.org/curated/en/217611613512125604/pdf/China-Jiangxi-Poyang-Lake-Small-Town-Project.pdf | The operation offered five lessonsthat may benefit task teamsin designing future similar operations. These have beentaken from the ICR with slightly modified language: Integratinghard and soft interventions may be acost effective means toimprove delivery of public services in small towns. In thisproject hardinfrastructure investments such as transport and water infrastructure were accompanied bylow-cost softinterventions to achieve least cost and sustainable public services. These soft activities included: (i) technicalassistance to develop strategic sector development plans, (ii) a smart transport management system thatdemonstratesinnovation and efficiency in delivering services to maximize benefits from thatservice, and (iii) greeninfrastructure, e.g., constructed wetlands, asnature-based solutions to wastewater management and anearly warningsystem for floodstoenhance the resilience oftowns. Strengthening capacity of small townsmay be used as incentives to coordinatethe implementation of multi-sector sub-projects scattered in manylocations.In this project, the project management office was in a government department that hadalreadydemonstrated its coordination capacity. However, these offices may not necessarily have technical experts insub-projectsthatlocal authoritiesdecideto implement. Acorrective measure was to convene a panel of expertsfromrelevant sector authorities to strengthen the local Project Management Officestechnical capacity.This approachenhanced project ownership among the sector agencies. Technical and management innovationsmay bedemonstrated in pilotactivities.in Gongqingcheng City a pilot sub-project demonstratedasmarttransport management system. The pilot useddrones, big data, and cloud technologiesto improve roadsafety.Anotherinnovationwas piloted in flood protection to address public health concerns such as the incidenceofschistosomiasis. Still another innovation was pilotingan endowment insurance mechanism to assurefarmersofbasic income after their lands wereacquired. Projects may find restructuring a useful mechanism whenimplementing projects in centrally planned environments. In this project,centrally directed strategies adjustedpriorities. Changes in components were anticipated because prior similar small-town development projects in China also encounteredchanges in priorities and replacement sub-projects readily identified. Restructurings were effectively used to achieve new targetsthat adjusted to the changes in priorities and strategies, both at the central and local government levels, but did not clarify thePDO. Using customized ME tools may be exploited to support implementation. In this project, aManagement Information System (MIS) was customized to monitor project progress and results. Indicators were linked to physical andfinancial progress, counterpart funding, loan disbursements, procurement and contracts payments. In addition, third party entitieswere contracted to monitoring safeguards compliance. Their monitoring of safeguards assisted in rapidly identifying possible chokepoints and informed the adoption of corrective measures. Bank teams may find using customized MIS and third party safeguardsmonitors helpful in implementing projects with moveable targets and changeable components.
P126875 | Energy Sector Capacity Building Project (ESCBP) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/428801579036305139/text/Tanzania-TZ-Energy-Sector-Capacity-Building-Prj.txt | http://documents.worldbank.org/curated/en/428801579036305139/pdf/Tanzania-TZ-Energy-Sector-Capacity-Building-Prj.pdf | Three lessons are taken from the ICR with some adaptation of language.The absence of an independent projectmanagement unit (PMU), especially in projects with multiple beneficiaries and complex designs, will highly likely result in poorproject implementation and failure to achieve the project outcomes. The Ministry of Energy (MoE), the main projectimplementing agency, did not establish an independent PMU, but assigned members of staff on a part-time basis, who also continuedwith their daily line duties. This resulted in coordination problems with other project beneficiary institutionssix underMoEand adversely affected the procurement activities. Project implementation efficiency and procurement pace improved onlyafter the assignment of dedicated staff for project implementation and establishment of project management teams in beneficiaryinstitutions.The project objective to develop public private partnerships (PPPs) in power generation was overlyambitious and unattainable for a technical assistance project with only a five-year implementation period. Structuring aPPP is a very complex process. In addition to the establishment of the legal and regulatory framework, it requires lengthy and verydetailed negotiations with potential investors. Even with a well-established legal and regulatory framework, achieving financialclosure for a PPP project in five years is highly optimistic. A more realistic objective would be the formation of a sound legalframework and preparation of the bidding documents.The preparation of a Training Needs Assessment (TNA) in advancecan improve project implementation and project efficiency. The Government of Tanzania was supposed to complete a TNAbefore the start of project implementation to be used as guidance for training demands. The TNA was not prepared, and the projecthad to address training requests on an ad-hoc basis without adequate prioritization. This resulted in inefficient use of projectfunds and slowing down procurement activities. A TNA was prepared after the Mid-Term Review and, with other changes in projectimplementation arrangements, the project implementation gained pace in the last year of the project. Nevertheless, these changeswere not sufficient to complete most of the project activities and almost half of the project funds could not be disbursed atproject closing.
P126877 | RW-Support to Social Protection System | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2012 | 2013 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/715091481556285121/text/Rwanda-RW-Support-to-Social-Protection-System-1.txt | http://documents.worldbank.org/curated/en/715091481556285121/pdf/Rwanda-RW-Support-to-Social-Protection-System-1.pdf | The following lessons learned are derived from the ICR:Coordinated efforts across developmentpartners well aligned with Government priorities provide important support to reforms. Although always the driver of thereform effort, the GoR counted upon needed financial and TA supportfrom its development partners,all under awell-coordinated and functioning donor-government group, the SWG, using regular backward- and forward-looking JSRs to ensurecollaboration in monitoring progress and in implementing well-coordinated policies and programs.Aprogrammatic DPL can provide a powerful instrument in establishing an efficient integrated safety net, responding flexiblyto support its evolution. Several factors facilitated the success of the programmatic DPL: The sectoral policyreforms were central to the World Banks CPS, complementary to and well-coordinated with other World Bank-financed operationsand non-lending services, and accompanied by critical TA needs. Effective development partner coordination, throughpolicy support to the Government, implementation support, technical support, and external consultants, provided mostly by the donorpartners, was achieved under the framework of the SWG. Implementation of the SSPS Program was characterized by acontinuous process of implementing, monitoring, evaluating where possible, analyzing, and adjusting based on lessonslearnedthe programmatic nature of the DPL allowed the flexibility to constantly refine, adjust, and adapt the program toimplementation experience and newly identified priorities and challenges.Development of consolidated MISrequires several iterative steps and takes time. Programs and projects that support this type of activity shouldfactor this into implementation schedules. A corollary lesson is that if broad, ambitious visions are developed, these need to beaccompanied by clear, achievable implementation plans based on a thorough understanding of needs, use cases, and institutionalcapacity.IEG observation:A programmatic DPL can provide the continuity that isnecessary to put in place and develop a comprehensive safety net that aims at promotion as well as protection. This isespecially the case when building a system from scratch in an environment of constrained resources. It offers the security ofpiloting and gradual expansion of a program; and the gradual introduction and harmonization of multiple programs. It may beparticularly useful in allowing the build-up of targeting systems and registries over a period of time, explore delivery methods,and develop links with sector ministries and agencies that affect both supply and demand.
P126897 | TG-Economic Recovery & Gov. Credit 5 | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/887201475116498078/text/000180307-20141203053430.txt | http://documents.worldbank.org/curated/en/887201475116498078/pdf/000180307-20141203053430.pdf | Lessons noted by the ICR are self-explanatory and are noted synthetically below. In a politically uncertain environment a well-designed and closely supervised operation can deliver results. In a country that has recently introduced democratic governance, there would be a need to better understand the political dynamics of reform, if only to ensure that the policy objectives and the pace of changes are feasible and achievable.
P126902 | Mauritania Basic Education Sector Support Project (BESSP) | Western and Central Africa | Mauritania | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/305701568988960644/text/Mauritania-MR-Basic-Educ-Sect-Sup-Proj-BESSP.txt | http://documents.worldbank.org/curated/en/305701568988960644/pdf/Mauritania-MR-Basic-Educ-Sect-Sup-Proj-BESSP.pdf | The ICR lists six lessons (p. 41-43). Among these, IEG highlights and adapts thefollowing: Improving learning through pre-service training requires improving the poolof candidates entering teacher training institutes and ensuring that these candidates complete training for its entire duration.These two challenges impacted the quality of the pre-service training delivered by the project. Because of a nationwideshortage of primary teachers, the ICR noted that the three-year training program had to be shortened totwo years for somecohorts. Additionally, the ICR noted that ENI admitted students from a poor pool of candidates (ICR, p. 41). The combination ofthese two factors made the production of qualified teachers by ENIs highly challenging. Projectdevelopment objectives must be commensurate with project activities and, when including an equity objective, clearly identify thebeneficiary groups for which improved equity is expected. The formulation of the PDO did not capture the intended outcomeof the activities under component 3, namely strengthening management of the education sector. Likewise, the projectincluded activities that could plausibly lead to improvement in the learning environment; however, this aspect was left out fromthe PDO formulation. Finally, the formulation also included an equity dimension that did not specify the inequities that theproject was trying to remedy, namely gender and regional (rural vs. urban) inequities in access to lower secondaryeducation.
P126903 | Mauritius - Priv Sec Competitiveness Development Policy Loan (PSC - DPL) | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2012 | 2013 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/381321467992518785/text/ICRR14870-P126903-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/381321467992518785/pdf/ICRR14870-P126903-Box394823B-PUBLIC.pdf | Among the lessons highlighted in the ICR are:Built-in flexibility allows the government to adapt the reform program as needed over time. The programmatic series acknowledged areas where the country made significant efforts beyond what was expected. In the lagging areas, the necessary building blocks were put in place to ensure that the reforms take place progressively as in the case of the restructuring of the Development Bank of Mauritius where consensus for reform existed but the timeline was extended to take into consideration negotiations with another government on the selection of a strategic advisor. The knowledge package accompanying the DPL contributes to reform planning and implementation. The Mauritian Government had recently cancelled two Investment Loans but continued to request the Bank for technical assistance, analytics and policy dialogue. This brings to the forefront the issue of Middle Income Countries that can raise finds on the open market but still wish to maximize access to the Bankâ€™s advisory services, analytics and technical assistance without the associated administrative requirements of lending instruments. This calls for continuous improvement of Bank lending instruments to suit the requirements of this â€˜emergingâ€™ client segment.Collaboration facilitates learning. The programmatic DPL series was prepared in tandem with the Public Sector Performance (PSP) DPL series and led to an integrated dialogue with the client and joint internal processing and targeting for better results. This program involved the tripartite collaboration among WBG sectors â€“ FPD, HDN and PREM - under a tight time line. According to the ICR, â€œsimultaneous preparation and processing of the two operations allowed the teams to cross-fertilize ideas and foster partnership in the interest of a higher quality product for the client.â€
P126964 | Nigeria Youth Employment & Social Support Operation | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/846921635527372969/text/Nigeria-NG-Youth-Employment-Soc-Support-Operat.txt | http://documents.worldbank.org/curated/en/846921635527372969/pdf/Nigeria-NG-Youth-Employment-Soc-Support-Operat.pdf | The following lessons are drawn from the ICR:A long project implementation period can be anopportunity to gradually introduce more complex approaches into a fragile environment. This project introducedsingle registries at scale into an essentially fragile environment, initially allowing the project to keep it simple and graduallyadd complexity when the mechanism and the context it was operating in was better understood.Careshould be taken in conditioning livelihood support on IDPs returning home. Under this operation, research showedthat preferences of IDPs - stay, return, or go somewhere else - varied, in this case with some 40 percent wanting to return home,indicating that IDPs themselves might be given the choice of what to do depending on their own judgement of the circumstances theywere in.
P126974 | Africa Higher Education Centers of Excellence Project | Western and Central Africa | Western and Central Africa |  |  | Human Development | Education | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/867961636226009047/text/Western-Africa-African-Centers-of-Excellence.txt | http://documents.worldbank.org/curated/en/867961636226009047/pdf/Western-Africa-African-Centers-of-Excellence.pdf | Lessons drawn from the ICR (pages 37-39): Strong institutional ownership and leadership areessentialcomponents for a successful Center of Excellence. In the case of this project, there appeared to be a reasonable correlationbetween an ACEs success and the institutional support it received, pointing to the need for ensuring adequate incentives forinstitutions to provide an enabling environment. Moreover, the strength ofACE leaders was an essential variable. Incases where there was slow implementation at an ACE, change in center leadership alone led tonotable improvements inperformance. This experience highlighted the needto incorporate leadership development in future projectdesigns. Strong linkages between ACEs and their respective national governments can increase impact onthe highereducation sector. In the case of this project, ACEs operated under the authority of their national governments, with NationalReview Committees established to supervise ACE performance at the country level and toensure alignment with the nationalgovernments strategic agendas. Support at this highlevelallowed forlessons from the development of ACEs toimpact the broader higher education institutions and systems in their country. Capacity to engage the private sectoris essential to ensure knowledge transfer.In the case of this project,collaborative knowledge partnerships withprivate-sector entities included participation of industry representatives on curricula boards and ACE advisory committees,research consultancies and internship placements and partnership with visiting faculty from industry. However, while there was somesuccess in placing masters and Doctoral students in internships in private sector settings, overall this was the biggestchallenge for many of the ACEs. This experience highlighted the need to incorporate capacity building on engagement with theprivate sector in future project designs.
P127015 | Climate Resilient Participatory Afforestation and Reforestation Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2013 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/884751513954651964/text/ICRR-Disclosable-P127015-12-22-2017-1513954639035.txt | http://documents.worldbank.org/curated/en/884751513954651964/pdf/ICRR-Disclosable-P127015-12-22-2017-1513954639035.pdf | The ICR points out several; important lessons derived from this project Attention needs to be given in afforestation projectsto the issue of the timing of project effectiveness inrelation to the need to start before the planting season begins, for the same reason, delays in project processing that might delayeffectiveness need to be addressed quickly. Forest rehabilitation projects need to be designedtoensureshort-term livelihood incentives for forest communities. The quick realization of these benefits isanimportant element in facilitating the adoption of effective forest resource management practices. Asustained project implementation period isneeded for keeping forest-dependent communities engaged in an afforestationactivity since it takes time to change attitudes and build ownership in the management of forestresources. Since plantation maintenance after an afforestation project closes isessential forsustaining early achievements, it is important to confirmearly in the project planning processgovernmentscommitment to continue support. Community afforestation support selection criteria need to beconsistent. In this project, conflicts arose as a result of different selection methodologies used by the Foundation andtheForestry Department. This could have been avoided if all participating institutions had agreed to utilize the samemethodology for the selection of beneficiary communities. Allowing limited harvesting of forest products (asopposed to total protection) provides forest-dependent communities with a stake in the benefits and an incentive toparticipate.
P127033 | China Renewable Energy Scale-Up Program Phase II | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040723171541775/text/P127033079eb300c60912703f3e1dad9c07.txt | http://documents.worldbank.org/curated/en/099040723171541775/pdf/P127033079eb300c60912703f3e1dad9c07.pdf | The following lessons were derived from the ICR with some modifications by IEG (ICR, pages 39-41):1. Technicalassistance projects can have transformational national-level impacts when they use a framework designed to comprehensively addressthe issues, support strategic interventions to leverage maximum impact, apply a sufficiently flexible design to be able to adapt toevolving circumstances, and obtain a high-level client commitment. CRESP II is a good example of a project which successfullylowered major barriers to a national scale-up of RE; applied a flexible design which evolved with the shifts in markets andclients needs; and secured critical government reforms by providing relevant analytical justification for the necessaryinterventions and aligning them with the countrys development objectives. Designing and supervising the implementation ofsuch complex, transformational, and evolving operations require a high-capacity institution, such as the World Bank, as well ascounterpart teams that are equipped to provide both continuous high-level support and adequate management of the day-to-dayoperations. The projects experience provides lessons about the design and efficacy of TA operations that could be applied toother WB projects.2. RE integration is a major emerging challenge to RE development and scale-up, and the project offerslessons on how power systems can be made more flexible for integrating variable RE technologies (such as wind and solar).The project, with the benefit of its adaptable design, undertook important studies that identified solutions, which led to keydecisions and generated buy-in for committed subsequent implementation of reforms. RE integration is an area where the WorldBanks applied experience has been limited. Solutions to RE integration challenges will become increasingly relevant forother developing countries as the share of variable RE in their electricity supply grows, and the projects experience inthis area will be more and more useful for new operations.3. Projects with adaptable design (such as CRESP-II) also needto have adaptable ToCs and adaptable RE frameworks (with indicators and targets that can be adjusted during implementation ifspecific circumstances, defined at design, change), which was not the CRESP-II case. At the time of CRESP-II appraisal, the WorldBank operational policy did not require a ToC, but now is an integral part of project design. Having an adaptable ToC and anadaptable RF the ones that can be progressively adjusted during implementation to reflect the modifications in the projectdesign would support the documentation of the logical links from project activities to intermediate and PDO-level outcomesand the achievement of project objectives.4. Many impacts of policy reform may only be felt after a number of years, aswas the case with CRESP-I. Many aspects of CRESP-II are likely to be the same. Therefore, it is important to not only ascertainshort-term results (i.e., by project closing), but consider proxy indicators that substantiate the likelihood of reforms takinghold and having a long-term impact (e.g., the renewable energy pilots leading to approach being adopted country-wide; standards foroffshore wind). Long-term impacts can be proxied during the project implementation period based on evidence of expansion,replication, and measures of continuity.
P127035 | Green Energy Schemes for Low-carbon City in Shanghai, China | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/332401586964788647/text/China-Shanghai-low-carbon-city.txt | http://documents.worldbank.org/curated/en/332401586964788647/pdf/China-Shanghai-low-carbon-city.pdf | The rehabilitation of existing buildings, especially residential buildings, could improve the efficiency of greenenergy interventions and contribute to carbon dioxide emissions reduction. As discussed in Efficiency section above, theretrofit subprojects had higher EIRRs than the new building and large distributed generation subprojects. Nevertheless,rehabilitation of existing buildings was not conducted as planned at appraisal, due to the inadequate government policies andsubsidies, and the insufficient investmentsand guarantees. Moreover, the retrofitting of residential buildings facedadditional challenges regarding multiple ownershipand conflicting interests. Addressing these challenges would improveefficiency and efficacy of project interventions on low-carbon city development. Collection ofgood quality data in an efficient way is essential for enhancing the efficacy of achieving energy savings. At appraisal,the level of project financing was to be based on models calculating incremental costs of building investments. Duringimplementation, modeling for all subprojects provedchallenging given the available time and skillsets. Efficient methods tocollect, aggregate, and analyze data on energy savings would be important to monitor implementation status and achievements ofproject activities on developing EE buildings. Moreover, producing data on energy savings was not readily available. Payingattention to these factors would support the governments to benchmark and establish subsidies related to the EEbuildings.
P127036 | China GEF Large City Congestion and Carbon Reduction Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/576401569871411455/text/China-China-GEF-Large-City-Congestion-Project.txt | http://documents.worldbank.org/curated/en/576401569871411455/pdf/China-China-GEF-Large-City-Congestion-Project.pdf | The following are lessons from the ISR with some modification in language from IEG: Leveraging existingknowledge sharing and dissemination channels may enhancethe demonstration effect of the project.In this case,project theTransFORM platform was used toeffectively engage a wider network and broader audiences in China on projectissues at a much lower cost. This enabled toscaleup the demonstration effects of national and local activities, whichis reflected in the much larger number of people trained than originally envisaged. Projects focusingonpolicy development, which involveboth the national and local governments, may help the Bankstrengthen its conveningpower in the sector. The Bank teamprovided international experience and involvedpolicy makers and leaders inthe MOT, the project implementation units, pilot cities, and academia during the preparation and implementation ofseveralstudies. This createda platform through whichtheBank deepened the engagement with the nationalgovernment and strengthened its convening power in the transport sector. TheBank increased its role ininfluencingpolicy development in the MOT. Itprovided the MOT leadership with key inputs to deliberate on policydevelopment, including to preparethe 13th Five-Year Plan and several key policydocuments. Involvingnational and local governments through upstream and downstream interventions mayimprove PTD and TDM approaches. The influencing power of national policy on cities can encouragelocalgovernments to take action. This is more cost-effective compared to dealing with individual cities on an individual basis. Thedemonstrationsactivities inthe pilot cities created a feedback loop to shapenational policies becausethenational government and major think tanks involved the pilot cities in consultations during policyformulation. An incremental approach to TDM may enhancethe chances of its success. ImplementingTDM measures is challenging because of the resistance ofthe affectedpeople.Under this project, the pilot cities,with the supportof the national government, were able to avoid resistance by usingan incremental TDM approach. Thisapproachmodulatedthemenu of pricing policies, restrictions, and interventions to thepolitical and economicrealities of each city. It started with a gradual implementation of the measures with the least resistance, such as the parkingpolicies.
P127038 | Economic Competitiveness Support Program DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/500971519142075887/text/Morocco-MA-Economic-Competitiveness-Support-Prog.txt | http://documents.worldbank.org/curated/en/500971519142075887/pdf/Morocco-MA-Economic-Competitiveness-Support-Prog.pdf | The following lessons from the ECSPs implementation experience need to be taken into account when designing futureinterventions intended to enhance competitiveness. The lessons were derived from the ICR, with someadaptation:The DPLs should be accompanied by downstream technical assistance to increase theirdevelopment impact. The upstream phase could include strong Bank technical assistance for several key prior actions,notably those related to increasing institutional and coordinating capacities, designing legal reforms of the corporate laws,and developing a methodology and a guide for assessing cost and benefits of investment decisions. Moreover, downstream support forachieving the program indicators should also be envisioned to help maximize the impact of theprogram.The satisfactory involvement of the private sector could prove to be a key factor indelivering strong reforms. The Bank should ensure that private sector is involved in defining prioractions and reform areas with the government. In this Morocco DPL series, the private sector indicated satisfactorycollaboration with the Government on the implementation of business environment reforms, especially those related to the CommonBusiness Identifier, the revised law on payment delays, and the suppression of minimum capital requirements for limited liabilitycompanies. The National Business Environment Commission has also gone beyond just involving the private sector in theimplementation phase, but has now started involving the private sector in the identification phase of reforms toundertake.Strong ownership, coupled with robust coordinating body at the implementing agency level,need to be prerequisites for loan disbursement. In the case of this Morocco ECSP loan series, theimplementation agency was not responsible for driving the key reforms. This fostered a dispersed program, involving multipleministries, without one that fully owns the program. One implementing agency (CNEA in this case) should be in chargeof cross-cutting competitiveness topics, considering its specific role for business environment reforms and its mandate ascoordinator of reforms across multiple ministries in the competitiveness space. Also, loan operations should focus on a limitednumber of issues in the competitiveness and private sector development realms to avoid such dispersion and ensure strongownership.Continued coordination among ministries and a reinforced dialogue at thenational-regional level is key for the competitiveness agenda going forward. The Bank was able to act asa catalyst to harness a strong coordination of business environment reforms by providing upstream and downstream technical supportto CNEA. The Bank should continue to push for inter-ministerial coordination beyond the realm of business environment, and movetoward inclusion of other competitiveness topic areas within the framework of a robust inter-ministerial dialogue. Further, goingforward, coordination and collaboration needs to also occur at the national-regional level, in light of the new advanceddecentralization program that is a key priority area of the new Government program.Theimplementation of a monitoring and evaluation (ME) system is key to determining the long-term efficacy of reforms. Astrong ME system is key to track program results in a timely manner, proactively identify issues with program performance andcontinue tracking results beyond the life of the program. The limited resources dedicated to ME for this program resulted inBank-driven data-collection efforts at the request of the Bank team conducting supervision missions.
P127079 | Local Governance and Service Delivery Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/981201575907725713/text/South-Sudan-SS-Local-Governance-Service-Delivery.txt | http://documents.worldbank.org/curated/en/981201575907725713/pdf/South-Sudan-SS-Local-Governance-Service-Delivery.pdf | The ICR draws the following threelessons from the experience of implementing this project, with some adaptation oflanguage.1. Community driven development (CDD) activities can yield possible outcomes,even infragilesettings. Although civil war and economic collapse limited the geographical coverage of this project, this projectdelivered significant results incounties where they were implemented.Projects with a CDD component can be a usefulentry point for staying engaged and building state-society relations even when other development interventions that rely on a morefunctioning centralized state are more challenging.2. A proper sequencing of activities is clearly required incountries deemed to be fragile. In this project, someaspects of design (such as, intergovernmental fiscal transfersand a centralized technical assistance model of local governance), were clearly ambitious. The experience of this project showsthat such activities should succeed(not precede), only after peace has been consolidated.3. A carefulconsideration of the ME arrangements is required for projects in countries deemed to be fragile. This is particularlyso in countries where field supervision may berestricted for security considerations. Incorporating third party monitoringarrangements need to be considered early on in such settings. In the case of this project, third party monitoring corroborated theProject Management Units (PMU) own reporting. Incorporating this earlier would have helped the task team, PMU, and theCountry Management Unit considerably.
P127080 | Burundi Sixth Economic Reform Support Grant - First Operation in the series of 3 | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/186921519396416565/text/Burundi-BI-ERSG-VI.txt | http://documents.worldbank.org/curated/en/186921519396416565/pdf/Burundi-BI-ERSG-VI.pdf | In addition to the lessons presented in the ICR, IEG draws four main lessons from the experience of designing and implementingthisseries: Effective ownership of the program by sector ministries and agencies requires systematic capacitybuilding. In this case, the risks attached to Ministry of Finance control and ownership of the design, implementation andmonitoring of the reform program were recognized, and attempts were made from the outset to involve the sector agencies in thediscussion. Later they were assisted by specialists who designed medium term expenditure programs for the sector agencies. However,little use was made of these instruments, since the staff of the sector agencies had neither the relevant expertise norinstitutional incentives to adopt the instruments as their own. For reforms involving privatization,extensive and in-depth consultation with all major stakeholders can help design a program that is acceptable to, and consistentwith the ambitions of, affected parties. In this case, the previously successful privatization of a number of coffeewashing stations led to the assumption that the privatization of the remainder would also succeed. This, however, did not takeaccount of the changing perceptions and developing ambitions of the coffee growers. Pursuit of reformsthat do not have the necessary degree of political backing is unlikely to be successful. Although the series supported thedevelopment of a new Mining Code and the establishment of a commission to guide the country towards membership of the EITI, thelack of progress in negotiations with the international body, together with the fact that not one of nine benchmarks for membershipwas achieved, suggests that political buy-in for the necessary degree of transparency in the mining sector was not strongenough. A modest and incremental approach towards assisting the very poor and vulnerable can paydividends, especially in a fragile country context. Careful data building efforts, combined with flexibility in terms ofthe institutional framework and attention to local voices, can result in an important increase in the percentage of the very poorcovered by at least one social safety net.
P127086 | AFCRI-Sustainable Groundwater Management in SADC Member States | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Water | GEF | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099240006152211602/text/P127086067a56201b0a89a0f7a5dc7f5456.txt | http://documents.worldbank.org/curated/en/099240006152211602/pdf/P127086067a56201b0a89a0f7a5dc7f5456.pdf | Two lessons are taken from the ICR with modification of language.Dependence of transboundary organizations ontheir own financial basis can adversely affect the sustainability of their institutional capacity and operations because of lack ofsufficient funds. According to the agreement establishing GMI, member states will not finance the institution. GMI has tobuild its own long-term financial basis to finance its operations and maintain institutional capacity. During projectimplementation, the institute successfully generated income from project management fees and training events and conferences, butit relied on grants to cover more than 80 percent of its costs. Since sourcing grants is not a feasible option for long-termfinancing, the institutes operations and institutional capacity can be adversely affected if mechanisms for a strong andfinancially sustainable institution are not fully developed and operationalized.Complex institutional set-up andadministrative processes to establish a new entity that has a central role in project implementation can result in significantdelays. The GMI was to be established as a not-for profit company according to South Africa laws and act as projectimplementation entity, as well, which was a complex set up. The involvement of 16 SADC member states, which was not avoidable, andthe placement of the GMI within the University of Free State further complicated the establishment of the institute. Suchcomplications resulted in a delay of 24 months in early stages of project implementation. This led to a project restructuring andextension of project closing date.
P127088 | Adaptation of Nicaragua's Water Supplies to Climate Change | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/338431551317458382/text/Nicaragua-NI-Climate-Adaptation-and-Water-GEF.txt | http://documents.worldbank.org/curated/en/338431551317458382/pdf/Nicaragua-NI-Climate-Adaptation-and-Water-GEF.pdf | The ICR (p. 27-28) provided several lessons learned which were adapted by IEG: Including stakeholders onall various levels is critical for building stronger capacity. In this project, MARENA and FISE involvedmunicipalities, community organizations, and beneficiaries throughout project implementation through holding workshops, sharinginformation, and providing training. This resulted in being able to build strong adaptation capacity and resilience on therural, municipal, and national levels. Putting in place a strong financial management system is especiallyimportant for projects that include more than one implementing agency. This project faced several financialmanagement issues that had been undetected. Once the Bank identified these issues and provided close supervision to address them,important lessons learned were derived which were helpful for project management and Bank supervision during the final year ofproject implementation. Being able to adapt a projects approach is critical for a successful projectimplementation. In this project, the government and the Bank adapted the methodology for the CED program which helped toactivate payments to participating farmers allowing for an on-schedule, on-budget and more sustainable implementation of thecommunity sub-projects.
P127105 | Rwanda - Governance & Competitiveness TA Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/103541490017367808/text/ICRR-Disclosable-P127105-03-20-2017-1490017360630.txt | http://documents.worldbank.org/curated/en/103541490017367808/pdf/ICRR-Disclosable-P127105-03-20-2017-1490017360630.pdf | Instead of identifying lessons, the ICR provideda list of recommendationsand findings derived fromthe projectdesign and implementation, whichunderscoredthe importanceof credible results chain, the needofrealismin assessing capacity, timeframes and uncertainty, the advantage ofleveraging sequencing and complementarity, andensuringthe Governments central role in coordination.IEG draws two lessons: Governanceand competitiveness improvements are not a one-shot operation, theyare long-term and multi-sector goals and have tobe continued and sustained.Toward this end,the Borrowersucceeded to secure the support of external partners(AfDB, IFC)whopledged resources to build on achieved results and push for the sustainability of achievedoutcome. Careful sequencing of project activities can significantly increase synergies between components andamplify the expected outcome. The capacity-building activities (including ME) that were part oftheproject could have been better linked with implementation and help avoid delays. In addition,as staff retentionwas aserious issue, itwas arguably better to address that first before training staff who are subsequently likely toleave.
P127143 | DJ Geothermal Power Generation Project | Middle East and North Africa | Djibouti | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2020 | 2021 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/511141624027774670/text/Djibouti-DJ-Geothermal-Power-Generation-Project.txt | http://documents.worldbank.org/curated/en/511141624027774670/pdf/Djibouti-DJ-Geothermal-Power-Generation-Project.pdf | Three lessons are taken from the ICR.If the cost of the high-risk exploratory drilling phase of a geothermalresource development project is not appropriately estimated including an allocation for contingencies, it can result in lowinterest from contractors and critically affect the achievement of project outcomes. At appraisal, project costs wereestimated based on international industry benchmarks. In estimating the costs, conditions specific to Djibouti, a country withlimited experience in geothermal resource development, were not taken into consideration, such as logistical constraints, theremote geographical location of the project site, the size of the drilling program and the overall country risk. The project budgetwas much lower than the actual costs of implementing such a high-risk drilling program in the Djibouti country context. Twocompanies bid for the implementation of the program, of which only one satisfied the bid requirements, but the bid was much higherthan the cost estimated at appraisal. This delayed the implementation of the project because of lengthy negotiations, and atproject closing, the expected outcomes were not achieved.An early start of the procurement processes of the maincontracts for key professionals during project preparation can prevent lengthy delays in project implementation. Since theskills and experience of the borrowers staff in geothermal resource development was limited, the project was to hireprofessionals to key positions, such as project director and geothermal adviser. The procurement processes were not started duringproject preparation and bidding documents were not prepared. These were to start after project effectiveness, which was delayed byalmost one year. Subsequent coordination issues among the donors further delayed the hiring of these professionals. After thecompletion of the hiring processes, the project director and the geothermal adviser arrived in Djibouti in the second half of 2015,more than two years after project approval.Weak and fragmented coordination among donors can adversely impactproject implementation. The Bank was the lead donor of the project, and the AfDB and the FDA were the co-financiers. Aprotocol or a memorandum of understanding defining the coordination mechanisms among the donors was not concluded during projectpreparation. Donors had different procurement processes that conflicted with each other. The first hiring process of the projectdirector was cancelled because of these conflicting procurement processes. These led to significant delays in projectimplementation.
P127156 | SECOND ROAD AND SAFETY IMPROVEMENT PROJECT | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099235006232220485/text/P12715608ecaea0b60acf60cb2f4fffa592.txt | http://documents.worldbank.org/curated/en/099235006232220485/pdf/P12715608ecaea0b60acf60cb2f4fffa592.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Flexibilityin adjusting and improving design during implementation, while remaining focused onthe overall objectives, can help realize thedevelopment results. This is particularly relevant in countries wherecertain risks arehigh. In this project, the Bank not only proactively restructured the project in the face of implementationchallenges but also through active implementation support andprocurement approaches.2. A Government-financedProject Implementation Unit (PIU) can be useful in sustaining implementation capacities and commitment at the national level.This approach presents a midway approach between a (typically) Bank-financed PIU designed to oversee a specific projectand the use of the existing structure of national agencies/ministries. While still having technical independence the PIU in thisproject demonstrated eagerness to accelerate implementation, driven by the higher government objectives.3. Weakindicatorsfor monitoring road safety undermine attribution to development results. Better road safety outcomesare the result of various factors,with better road designs being one of them. For better attribution of results to theproject activities, it would be useful if theBank could more fully develop guidelines for measuring road safetyimprovements.
P127163 | GZ-Second Municipal Development Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2013 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/499251540500602923/text/West-Bank-and-Gaza-GZ-Second-Municipal-Development-Project.txt | http://documents.worldbank.org/curated/en/499251540500602923/pdf/West-Bank-and-Gaza-GZ-Second-Municipal-Development-Project.pdf | The4 lessons based on the projects implementation experienceinclude the following(from theICR, paragraphs 81-84, with some adaptation): Local government sector reform, whichencompasses institution building warrants a long term engagement to realize development outcomes, particularly in a fragileenvironment. When other donor partners provide a strong evidence of their commitment to the long term reform agenda,recipient authorities are better assured thatthe absorptive capacity of various stakeholders (e.g., central and localgovernments) would be considered during implementation. Opportunistic engagements could be pursued that would lead to the long termgoal. In this case, the first engagement at the municipal level introduced transparency and accountability measures (MDP1)thatwere then adopted to inform how municipal services were delivered (MDP2). The experience and lessons learned strengthenedthegroundwork for adding financial sustainability factors in delivering these municipal services effectively andefficiently(MDP3). Continuing to build institutional capacities andshowcasing processes that work at that governmentlevel, improves the chances that transparent and accountable practices at the municipal level could takeroot. Strong donor coordination allows for pooling donor resources to expand the reachof an operation. In this case, each donor benefited from pooling their resources to address municipal developmentcollectively and expand the scope of the project to reach more municipalities than if each donor pursued individual operations.However, one drawback learned was that different financing arrangements (cofinancing, parallel financing, counterpart financing)resulted in complex fund administration that inadvertently favored certain municipalities or delayed project start up by requiringprior project approval. Future operations with other donors participating would benefit from pooling resources into a single fundthat would use harmonized policies and processes. Such a simplified arrangement would lead to (i) a larger pool that could allowfor a more equitable allocation of funds across local governments; (ii) reduction of transaction costs with one system applicabletoallsubproject selection and appraisal; (iii) development of a national system to guide implementation; and (iv)enhanced role of the MDLF as the primary source of financial and capacity building support tomunicipalities. Design for interventions in Palestine could include a contingencycomponent that would allow for rapid response to emergencies. In the case of this project, AF provided for anadditionalcomponent within the project framework. This required a restructuring that could be avoided if there were acontingent option with triggers agreed upon during preparation. The municipal sectorspecific lessonsincluded: (i) making availablefeedback mechanisms to beneficiaries involving satisfaction inhow projects are identified and implemented, including grievance and redress of complaints,to better inform servicedelivery; (ii) grants allocated tolocal governmentsneed to ensure that the frequency, timing, and size of these grantsdo not limit local government investments programming; (iii) capacity enhancement efforts need to be customized to the needs of therecipient local government and not prescribed or limited to a reduced subset; and (iv) in Palestine in particular, after thesubstantial engagement in building capacity in the sector, local governments may be ready to pursue transformative capitalinvestment planning.
P127187 | South Sudan Health Rapid Results Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Human Development | Health, Nutrition & Population | SPF | IPF | 2012 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/296021597417982997/text/South-Sudan-SS-Health-Rapid-Results-Project-FY12.txt | http://documents.worldbank.org/curated/en/296021597417982997/pdf/South-Sudan-SS-Health-Rapid-Results-Project-FY12.pdf | The ICR (p. 44-46) provided useful lessons learned, adapted here by IEG: Project implementation readinessis critical for ensuring successful project implementation, even though it is especially challenging in an FCVenvironment. This project was not ready for implementation for several reasons: the CSDO was not hired until five monthsafter project effectiveness, the PMU staff had not been trained; the TPM had not been appointed; and major procurement activitieshad not been completed. The ICR (p. 45)listed critical components of readiness thatwould have benefited projectimplementation, including: i) training of PMU, implementing agencies staff, and the project steering committee; ii)agreement on the results framework and on robust data collection and verification systems; iii) development of detailed project,financial management, procurement, and social safeguards implementation manuals; and iv) drafting of bidding documents for theinitial implementation period. Conducting a competitive procurement process for key implementing entities such asthe CSDO is critical for ensuring that the most capable entity is awarded the contract to implement the project. Inthis project, the MOH suggested a direct contract with a single CSDO, an NGO thatwas already operating in Jonglei and UpperNile. However, this resulted in significant implementation challenges for several reasons: i) the CSDO lacked a robust financialmanagement and control system, which had a negative impact on the projects financial integrity. By the time the projectclosed, the project had US$11.4 million of undocumented spending; and ii) even though the CSDO was already operating in the twostates, it failed to circumvent the problems related to annual flooding and significant migration. Complexproject management structures are particularly challenging in an FCV environment with weak capacity. In thisproject, the PMU within the MOH was responsible for overseeing the large contract with the CSDO, which enjoyed a great level offlexibility inspending project funds. However, the PMU did not have the needed capacity to oversee all these activities, inaddition to the procurement of pharmaceuticals and the TPM contract. Theperformance-based contractforaservice delivery contractneeds to include indicators that thecontractor has control over. In thisproject, the CSDO was removed from direct service delivery, since the service was provided by NGOs, CHDs, and other entities.Therefore, paying the CSDO on service delivery indicators that the CSDO had no control over and for which data verification waschallenging might not have had the intended impact. Instead, the CSDO could have been paid for outputs it was directly responsiblefor such as timely, complete, and accurate pharmaceutical supply.
P127200 | TOGO Community Development and Safety Nets Project | Western and Central Africa | Togo | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/716291545425848721/text/Togo-TG-Community-Development-and-Safety-Nets.txt | http://documents.worldbank.org/curated/en/716291545425848721/pdf/Togo-TG-Community-Development-and-Safety-Nets.pdf | The following lessons are taken from the ICR (page 32-33 and previous pages), with some modification oflanguage:A combination of financing infrastructure and a community-driven development approach thatbolsters local coordination can contribute to re-building social fabric after a conflict. A community-driven developmentapproach in tandem with financing for infrastructure can provide access to services and buildings, create a sense of ownership, andspur engaged and accountable local governments.Small-scale community-driven approaches can be aneffective tool in fragile contexts and in conflict-affected poor countries, particularly when dedicated, professional, highlycompetent staff and support are deployed. The reasons why a very complex project such as this one worked well in thispoor, fragile, and conflict-affected context may be manifold, and the project team highlighted a few potentially crucial elementsin emails to IEG dated May 2, 2018. The TTL who initiated the project was experienced and dedicated and set up a professional Bankteam from the outset. The PIU also had competent and dedicated staff from the start. Furthermore, this was not a new approach inTogo; the country had already been implementing CDD projects for three decades prior to this project. Finally, implementation wasmainly done through AGAIBs, which are non-governmental entities placed very close to the field and communities. Those organizationswere also capacitated with competent and dedicated staff who had the right specialties to carry out implementation at the communitylevel. The stability of AGAIB staff also permitted capitalization on lessons learned from one project to theother.Individual income-generating activities (IGAs) may have a better rate of return thancollective IGAs. Experiences from this project suggests that individual IGAs, although their returns were low, had anoverall higher rate of return than the collective IGAs. The reasons behind these lower returns for associative entrepreneurship maymerit further study.
P127201 | Vietnam Climate Change Development Policy 2 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2013 | 2014 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | The lessons highlighted in the ICR (paras. 71-75, pp. 29-30) areapplicable to similar operations, especially:1.An effective cross-sector platform is needed to achieve significant progress on policy and institutional reforms that addressclimate change;2. Convergence of programs and resources between line ministries, across development partners, and betweennational and sub-national levels of Government is also necessary for achieving progress on climate change reforms; and,3.High level engagement with the government, supported by strategic and targeted technical assistance and knowledge, is essential toachieve reforms on climate change.In addition, as IEGs recent learning evaluation with regard to environmental(including climate change) development policy operations has found, the following lessons, whichare also illustrated by thepresent DPO series,are also of relevance:1. Strong and persisting Government and other stakeholder commitment toprogram objectives and policy actions, including that of key Finance and Planning Ministries, as well as that of other implementinginstitutions, is essential;2. The Bank should be willing to join ongoing policy-based programs if it can clearlyaddvalue by helping to better focus them and prioritize policy actionsthatare of especial importance in achieving theirgeneral objectives (i.e., climate change adaptation and mitigation in the present case) as well as through itssupervision/implementation support; this can also help to enhance donor coordination and local capacity with regard to policysupport in a particular country;3. Climate change development policy operationsare more effective if they arefocused on a limited number of high priority policy areas, counton strong government commitment and based onsolidbackground analytical work and are used in conjunction with other Bank and donor-supported technical assistance and investmentoperations, including in the present case with respect to water resource management, energy efficiency, and natural disaster riskmanagement; and,4. Task team leadership arrangements in which responsibilities are shared by internationalspecialistsbased in Headquarters and local ones basedin the field can help the Bank toprovide more efficient andeffective implementation support, including to other participating donors that are present on the ground, while also ensuring thatBank polices and operational requirements are fully met.
P127203 | Rebuilding Energy Infrastructure and Access | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099325002072212224/text/Haiti000HT0Reb0gy0Infrastr000Access.txt | http://documents.worldbank.org/curated/en/099325002072212224/pdf/Haiti000HT0Reb0gy0Infrastr000Access.pdf | IEG derives the following lessons, drawn from the ICR: The momentum of a post-natural disasterreconstruction effort cannot necessarily be relied on in a fragile political and social context. For this project inHaiti, the Bank made a deliberate decision to support relatively ambitious objectives, assuming that the commitment to reforms andperformance improvements generated by the earthquake reconstruction would be sustained. However, this ignored the fundamentalrealities of a fragile country, which included very low levels of trust between State and citizens, limited governmenteffectiveness, weak institutions, concentration of productive assets in the hands of a few and highinequality. The principles of simplicity and selectivity are best followed for projects in FCVsituations. As the World Bank Group Strategy for Fragility, Conflict, and Violence 2020-2025advocates,investment operations in FCV countries should be modest in both scope and objectives, especially when it comes to policy andinstitutional reforms. If country conditions improve, allowing a project to reach or exceed expectations, then the project can bescaled up using Additional Financing or via a follow-on operation. Policy conditionality may not improveinstitutional performance in the absence of political will. The project was designed to make infrastructure investmentsconditional on a reform of EDHs management structure. However, this reform was never implemented, and on-grid and off-gridelectricity infrastructure development was deferred until too late. It might have been more prudent to have avoided theconditionality and allowed the physical investments and the institutional development run on separate tracks.
P127204 | Niger - Competitiveness & Growth Support | Western and Central Africa | Niger | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2021 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099300010112234243/text/P127204025b7170b50bbed0815a94b7a1e8.txt | http://documents.worldbank.org/curated/en/099300010112234243/pdf/P127204025b7170b50bbed0815a94b7a1e8.pdf | The ICR contains the following lessons which IEG presents with some modification of wording:Establishment ofjoint public-private consultation groups can help stimulation of business activity. The experience under the projectdemonstrated such bodies contributed significantly to development of strategies and actions plans to stimulate the businessenvironment. These joint groups also supported identification of target reforms and thus increased ownership by the relevantentities.Having strong champions in the government supporting reform processes can help better identification andrapid implementation of these reforms. In the case of this project, the commitment to reforms by the Head of State himselfand Minister of Trade who effectively pushed for cross-cutting and difficult reforms. Overall, the commitment and ownership of GoNremained strong through the implementation. This contributed to achievement of the objectives significantly.Lowquality preliminary analytical studies can decrease project implementation efficiency. In the case of the project, theanalytical studies did not adequatelyidentify environmental and social safeguards related issues. The construction siteoriginally chosen for the Maradi refrigerated slaughterhouse, was not appropriate. The site was moved about 8 kilometers awayfrom the current site as it was better suited on grounds of proximity to a watercourse, larger area, distance from residentialareas, and lower environmental impact. These delayed the implementation of the rehabilitation of the Maradi slaughterhouse as thenew site required additional approvals and processesWhen introducing a matching grants program, particularly in anFCV context, determining an appropriate rate of beneficiary contributions can increase success of the program. In the caseof Niger, beneficiary contribution of around 30 to 60% proved to be too high and had a negative impact on the implementation of theprogram. At appraisal US$ 9.1 million of local beneficiary contribution was expected. At project closing the contribution amountwas US$ 1.10 million only.
P127208 | Economic Reconstruction and Growth Development Policy Credit | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2016 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/374731467996679688/text/ICRR14849-P127208-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/374731467996679688/pdf/ICRR14849-P127208-Box394823B-PUBLIC.pdf | The ICR argues that a multi-tranche or programmatic operation would have strengthened the Government's incentives to achieve the objectives. Even if a single-tranche, standalone format is deemed appropriate under the circumstances, adequate attention to incentives, for instance through proposed follow on operations, might lead to better outcomes.An important issue is the Bank's involvement in Government operations, specifically the extent to which it should engage directly with line ministries (or other stakeholders) about a project where communication and direction from the central authorities is weak. The ICR suggests that such interventions should be approached cautiously. But, where appropriate including a communications strategy in the implementation arrangements might ensure a better understanding of the project and M&E framework.Better coordination among donors can make a critical difference. Consider two examples where outcomes were very different. The decision to change from SYSGEP to SID, which contributed to the program going off track, was based partly on a recommendation from the Agence Francaise de Developpement. Meanwhile, consolidation of bank accounts, where the target was achieved, owes some of its success to IMF support for the move.
P127209 | Private Sector Rehabilitation & Agribusiness Development | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/666331612293250314/text/Guinea-Bissau-Priv-Sec-Rehab-Agribusines-Dev-PSRAD.txt | http://documents.worldbank.org/curated/en/666331612293250314/pdf/Guinea-Bissau-Priv-Sec-Rehab-Agribusines-Dev-PSRAD.pdf | The ICR draws the following two mainlessons from the experience of implementing this project, with some adaptation oflanguage.1. A simple design with Bank support can ensure success in fragile countries. Thekeyaspects that contributed to the success of this project, included building strong relationships with non-state actors, micro- levelreforms, a simple design with limited number of outcome indicators, simple and effective institutional arrangements, interventionsthat were evidence-based (based on a survey of cashew farmers), hands-on involvement by the Bank team and connecting throughlow-key digital solutions where possible.2. Guidelines and Bank procedures need to be accessiblein fragilecountries. The requirement that procurement and financial management documents be produced only in English and French (andnot Portuguese) proved to be inappropriate in this project, given that selection committee members and other stakeholders hadlimitations in these languages. The lesson is that procurement and financial management documents need to be produced in theappropriate local language.
P127212 | Participatory Service Delivery for Reintegration SPF | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2012 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/839841468301154457/text/ICRR-Disclosable-P127212-06-09-2016-1465497998252.txt | http://documents.worldbank.org/curated/en/839841468301154457/pdf/ICRR-Disclosable-P127212-06-09-2016-1465497998252.pdf | Lessons drawn from the ICR (pages 19-20): Public-private partnerships can be a useful modality for local,participatory, demand-driven service delivery. In the case of this project, despite initial implementation delays inestablishing institutional arrangements, NGOs were an effective vehicle for the provision of employment and basic social services,as determined by the local communities. Linking vocational training and short-term employment opportunities to theprofile of local job markets is essential, particularly to ensure transferability of vocational skills. In the case of thisproject, gaps in local service delivery were identified as potential employment opportunities for semi-skilled workers.
P127226 | Saint Lucia Disaster Vulnerability Reduction Project | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062724190534369/text/P127226-7a70fac6-1597-461b-8396-31c69c86e3b9.txt | https://documents.worldbank.org/curated/en/099062724190534369/pdf/P127226-7a70fac6-1597-461b-8396-31c69c86e3b9.pdf | The ICR provided three lessons (ICR, p. 25-26).The review reformulated two of them, which were the most strongly linked tolessons drawn from actual experiences during project implementation. The reformulation wasbased on the results of theReviewand the TTL interview:1. The Projects broad framework approach allowed forflexible funding across various sectors but overwhelmed implementing agencies, leading to delays, increased costs, and insufficientfocus on sustainability and local ownership, suggesting a more focused approach may be beneficial. The Project leveragedfunding from 5 different sources, which covered manydifferent sectors and interventions and provided flexibility to allow thegovernment to respond to emerging priorities. However, this approach quickly overwhelmed the implementing agencies, resulting ininitialimplementation delays. Project management costs and the size of the PCU team doubled duringimplementation. Thecomplexity of project implementation left little bandwidth tofocus on sustainability of investments and making sure there isfinancing and sufficient local ownership for a successful handover. A more focused approach would leave more space to focus onOM, roles and responsibilities and to do it well.2. The Climate Adaptation Financing Facility(CAFF)lacked alignment with GoSLs climate programs and monitoring frameworks, highlighting the need for strongerconnections with key climate agencies to ensure ownership, sustainability, and potential government-led continuation ofthe program. The CAFF supported climate adaptation by offeringaffordable credit to households and businesses to makecritical investments in water storage capacity, renewable energy generation, etc. The program demonstrated adaptability when it wasexpandedthrough a Business Recovery Program (BRP) to address financial impacts on businesses from COVID-19. However, theintervention was not connected to climate policy makers in the key climate agencies and the CAFF monitoring framework lackedalignment with monitoring of climate plans and strategies, such as the National Adaptation Plan (NAP) and the Nationally DeterminedContributions (NDC). Focusing on strengthening the connection was particularly important to support ownership and sustainabilitysincethe CAFFwas implemented by the Saint Lucia Development Bank (SLDB), a corporate entity, and not a governmentagency like the other activities under the Project.A strengthened alignment between CAFF and key climate agencies could havestrengthened ownership, and enabled climate agencies toreceive and act on feedback from CAFF, and perhaps realize the valueof CAFF, increasing the chances of a government-led continuation of the program.
P127241 | Tanzania - Intermodal & Rail Development Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099072423100047269/text/P127241021b9600c60a51101bdc12a46be4.txt | http://documents.worldbank.org/curated/en/099072423100047269/pdf/P127241021b9600c60a51101bdc12a46be4.pdf | Rail projects relying on railway reforms may experience significant delays if a strong buy-in from differentlevels of government is not sufficiently secured. It is crucial for rail projects relying on such reforms to have a strongbuy-in from different levels of government when implementing challenging institutional reforms. In the case of TIRP, thedetermination and buy-in from relevant agencies and the ministry were evident through their efforts to amend the Tanzania RailwayAct of 2017. In addition, intermediate targets that show progress on difficult institutional reforms help monitor and adjust thecourse of such reforms as required. Since the need for an amendment to the law only became clear during implementation and affectedthe timeline, intermediate targets on the progress of reforms tends to be useful. If sufficientflexibility is not built into the project design, its inability to respond to changes in institutional arrangements may impact itsimplementation. Teams should consider this risk, especially when working in an economy that is heavily investing ininfrastructure and its related capacity and set up adequate mitigation measures including establishing requirements that willretain the trained or already experienced personnel for the transition period; and building extra time in project implementation toaccount for potential changes. ME can be affected if the Institutional arrangementsare not implemented as designed.Addressing this challenge would require enhancing the capacity of implementingagencies in developing and implementing robust ME designs and frameworks. The project faced shortcomings in the ME designand implementation and established institutional arrangements for results monitoring were not followed adequately, as describedearlier.
P127245 | Rio de Janeiro Strengthening Public Sector Management Technical Assistance Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2013 | 2018 | 2020 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/251601579636901753/text/Brazil-BR-Rio-de-Janeiro-Mun-Strengthening-PSM.txt | http://documents.worldbank.org/curated/en/251601579636901753/pdf/Brazil-BR-Rio-de-Janeiro-Mun-Strengthening-PSM.pdf | The following lessons are drawn from the ICR, with some adaption of language by IEG: Lack ofstrong ownership by government entities and implementing agencies compromises the potential success of a project. Considering notproceeding with a project under these circumstances is a viable option for the Bank. In this case, the ICR (p. 34) reported thatthe Municipality expressed low interest in the project during preparation and only agreed to it because of strong advocacy by theBank team and management. Weak institutional capacity of counterparts compromises the potential success of a project andshould be incorporated into design. In the case of this project, the ICR (p. 15) stated thatthe Municipality showedlow capacity to prepare and implement activities. Implementation support, particularly when counterparts are notfamiliar with World Bank procurement practices, is a critical factor in determining the likelihood of success. In the case of thisproject, the ICR (p. 24) stated that shortcomings in procurement management jeopardized project implementation.IEG adds the additional lesson:Ensuring that the PDOs and the components of a project are consistent is acritical factor in project design. In the case of this project, there were substantial gaps between the two.
P127253 | Balochistan Disaster Management Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2012 | 2016 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/460941505920549900/text/ICRR-Disclosable-P127253-09-20-2017-1505920540311.txt | http://documents.worldbank.org/curated/en/460941505920549900/pdf/ICRR-Disclosable-P127253-09-20-2017-1505920540311.pdf | The lessons are taken from the ICR with some modification of language: Sequencing of activities can bebeneficial for projects aimed at capacity building and institutional strengthening. A simple design with concreteobjectives, structured to allow the project to build on successes gradually may facilitate successful implementation, especially inlow-capacity environments. A strong capacity enhancement plan is an important element in building disastermanagement capacity. A strong capacity enhancement plan encompasses technological innovation, human resource developmentand provision of goods. Reverse supervision missions and recruitment of Third-Party Validation Firmsmay be useful ways to supervise and monitor project in Fragile, Conflict and Violence (FCV) affected environments. Insituations where the Bank team is not able to visit the project site due to volatile security situations, reversesupervision missions can be undertaken where project staff travel to Headquarters for supervision missions. Third-Party Validationfirms can be hired to undertake regular monitoring and validation work in the instances where Bank staff will not have fieldaccess.
P127254 | Zambia Strengthening Climate Resilience (PPCR Phase II) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2013 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092223103020658/text/P1272540f8ba6002608eeb05fa992cf7e9b.txt | http://documents.worldbank.org/curated/en/099092223103020658/pdf/P1272540f8ba6002608eeb05fa992cf7e9b.pdf | The ICR (p. 33-34) included several lessons learned, which were adapted by IEG: Engaging with the privatesector in productive initiatives may enhance climate resilience efforts. This project piloted an innovative approach bylinking small producers, enterprises, and markets. This activity supported private enterprises to venture into profitableactivities and value addition of selected value chains. Ensuring appropriate deployment and sustainability ofdifferent initiatives requires clear mandates and roles. This project supported the integration of climate changeconsiderations into district planning, which was supported by the seventh and eighth NDPs mandating all districts to mainstreamingclimate change into planning and programming. If appropriate and measurable PDO indicators are not applied, itmay jeopardize the measurability of project achievements. The Results Framework included a few PDO indicators thatmeasured outcomes that were beyond the projects influence. This resulted in the challenge of attributing the results of thefirst objective solely to project activities. Engaging with high-qualityNon-GovernmentalOrganizations (NGOs) and facilitators may contribute to successful project implementation. In thisproject, the PIU prepared the Participatory Adaptation Implementation Manual (PAIM) that clearly laid out the responsibilities andtasks for NGOs. After NGOs were selected and started to support vulnerable communities in the preparation and implementation ofsub-grants, the Provincial Project Implementation Unit (PPIU) and local staff oversaw their performance. NGOs that were notperforming appropriately were warned. If their performance did not improve, they were replaced by well-performing NGOs.
P127258 | Sustainable Coffee Landscape Project | Eastern and Southern Africa | Burundi | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2019 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/306581561754242022/text/Burundi-BI-Sustainable-Coffee-Production.txt | http://documents.worldbank.org/curated/en/306581561754242022/pdf/Burundi-BI-Sustainable-Coffee-Production.pdf | The ICR listed three lessons learned from the project. They are summarized below with someediting.Introducing shade-grown coffee in Burundi was significant and transformational - butdifficult. Changing deep-rooted practices requires investment of sustained national effort: In this case, changing fromsun-grown coffee trees (from colonial times) until now when the shade-grown coffee technology project was introduced. The ICRstates that it was an exchange visit to see successful shade-grown coffee practices in Colombia that instigated the Ministry ofAgriculture to request this project. Demonstration sites were set up for sustainable land and water management practices, anda shade-grown coffee manual was prepared for national adoption. The lesson is that difficulties facing transformationalchange can be overcome by a strategy of demonstration.Integrating indigenous communities in the protection ofnatural forest reserves is invaluable for sustainable and continued protection of forests: In this project the integrationof the landless Batwa community, which without changes in their traditional livelihood strategies posed a threat to forestconservation and biodiversity, were encouraged through participation in forest rehabilitation using cash-for-work activities whichenabled them to acquire land and contribute to forest protection. It is anticipated that this model will be replicated andscaled up in the context of the forthcoming Landscape Restoration and Resilience Project, to be financed by the WorldBank.The use of an existing World Bank-experienced project management unit can provide a useful mechanism for anew project to reduce implementation risks at start up. In this project the use of the earlier PRODEMA projectimplementation unit helped accelerate this projects implementation and alleviated the impact of delays caused by politicalunrest, prolonged drought as well as delays in collecting baseline study data.
P127303 | Mozambique - Integrated Growth Poles Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/696101617973617212/text/Mozambique-MZ-Integrated-Growth-Poles-Project.txt | http://documents.worldbank.org/curated/en/696101617973617212/pdf/Mozambique-MZ-Integrated-Growth-Poles-Project.pdf | Three lessons are drawn from the ICR (pages 34-35), with some adaptation.Channeling assistance to farmersthrough support for structured commercial arrangements with agribusiness firms offers a viable mechanism tosimulateagricultural development. This project supported the extension ofIDCF grants to finance businesslinkage sub-projectsbetween smallholder producers, individually or through their associations and cooperatives,andagribusiness value chains. These linkage projects, known variously as contract farming or out-grower schemes,coordinatecommercial relations between producers, processors, and traders and leadto a vertical integration of theagricultural value chain. They provide agribusiness firms with opportunities to explore local markets,stimulatedomesticdemand, controlproduction to dampen price volatility, and source locally for export markets. At the sametime, they provide smallholder farmers ready access to farm inputs, seasonal credit, and technological knowhowandhelpfarmers toimprove productand quality standards.The use of local development authorities to managegrowth poleprojects has the advantage of better integratinglocal needs in government decision-makingprocesses. In this project, the Zambezi Valley Development Authority, the Integrated Development Agency of theNorth, and theUnit for Coordination of Integrated Development in Nampula helped plan and coordinateinfrastructureinvestments that were linked to local demand, including food production for mining towns in Tete, water infrastructure for theNacala Special Economic Zone, and out-grower schemes among smallholders and agribusiness chains in Zambezi Valley and the NacalaCorridor. For the IDCF, a localinvestment committee in Zambezi Valley and another local investment committee in theNacala Corridor reviewed and approved proposals for IDCF grants. According to the ICR (page 35), the use of local authoritiesstrengthened institutional and technical capacity at the local level, allowed for the prompt response to project implementationissues, and ensured better monitoring of project results.Output and performance-based road contracts provideincentives to deliver quality and efficient services.According to the ICR (page 65), this project successfullyadopted output-based contracts, which had been used elsewhereglobally,for the maintenance for the R604 and R605 roadsin Tete. Inan output andperformance-based road maintenance contract, the contractor is paid on an output basis,maintaining the road at a specified service standard, rather than on an input basis, as occurring under traditional maintenancecontracts. By paying contractors based on the level of service they deliver, output-based contracts provide a clear financialincentive for contractors to meet performance standards. Private contractors are also incentivized to improve theirefficiency and minimize waste because they are compensated at a set level for performance. With the useof this approachin Tete, the National Road Administration hasbuilt up the capacity to introduce and manage these contracts and has sinceadoptedthem for other road maintenance projects in Mozambique, according to the ICR.
P127308 | Second Science & Technology Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/115331614021594370/text/Croatia-Science-and-Technology-II.txt | http://documents.worldbank.org/curated/en/115331614021594370/pdf/Croatia-Science-and-Technology-II.pdf | Three lessons are drawn from the ICR (pages 31-32), with some adaptation.A strong and stable institutionalframework for research and innovation is essential to advance a countrys RD and innovation goals. In thisproject, the merger between HAMAG and BICRO disrupted the ready implementation of the capacity building efforts and research andinnovation programs supported by the Bank. The merger was politically motivated and not properly studied, according to theICR (page 20), as the two agencies served different SMEs with incompatible objectives. The Bank alsostroveto preserve the ability of the UKF/CSF to conduct high-quality scientific work following UKFsmerger withCSF, according to the ICR (page 20). Croatia received the recommendations of an international panel of experts for thegovernment to reorganize and restructure its 25 public research institutes. The implementation of the recommendations wouldstrengthen the governance of RD and innovation programs in the country.Spending by stakeholders of theirown in-country resources for research and innovation strengthens the sustainability of RD and innovation developmentprograms. In this project, Croatia tappedthe EU structural and investment funds to finance its research andinnovation programs. But, according to the ICR (pages 31-32), the EU resources were more suitable for supportinginterventionsthat were mature and stable, with the EU financing procedures being highly complex and less amenable toinitiatives that were novel and experimental, needingflexible funding structures. The use of the governments ownbudgetary resources would allow for the funding of newerand more discretionary approaches to RD and innovation.But more importantly, the use of their own resources provide stakeholders the ability to sustain their RD and innovationprograms in the long run, whether the programs are mature and structured or novel and experimental.Governmentstaff who are more knowledgeable of research and innovation concepts, processes, and dynamics are able to support RD andinnovation programs more effectively. In this project, the Bank supported capacity building at public agencies toqualify for, and manage, EU funds. While staff at these agencies were trained at, and gained expertise in, the preparation ofapplications for EU project funding, they wereless knowledgeable about, and familiar with, RD and innovation topicsthemselves, according to the ICR (page 32). The lack of expert knowledge at the Project Implementation Unit of RD,coupled with the inexperience atengagingprivate research institutes and business firms in the innovation ecosystem,slowed the implementation of the project, according to the ICR. Future research and innovation programs could benefit notonly from the development ofadministrative skillsat project implementing agencies, but also from the readyavailability, either acquired externally or developed in residence, of substantive technical expertise, experience, andaptitudein research and innovation.
P127314 | Poverty Reduction Support Grant (PRSG-8) | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2016 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/642251469189437185/text/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.txt | http://documents.worldbank.org/curated/en/642251469189437185/pdf/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.pdf | 6. Lessons 6.1 Ghana again became a substantially indebted country that must direct a substantial share of its revenues to debt servicing, and it did so within a decade after a major debt relief under the Heavily Indebted Poor Countries Debt Initiative. This highlights the importance of prudent macrofiscal management in post-HIPC countries, and emphasizes that the World Bank has to place in its policy lending for helping its clients to preserve borrowing space. 6.2 Adequate macroeconomic management is a critical precondition of budget support (which relates to the previous lesson). The World Bank made the right choice to focus on restoring fiscal discipline as part of risk mitigation for the Economic Governance and Poverty Reduction Credit in 2009. Similarly, its choice not to deploy development policy operations (DPOs) in 2013â€“14 because of the lack of an adequate macroframework was also correct. Ghana's case also shows that the World Bank is not a substitute for the IMF in a challenging context that requires a comprehensive macroeconomic program. In this respect, Ghana is a good example of World Bankâ€“IMF cooperation. 6.3 Ghana's case shows that DPOs deployed in an extremely weak public financial management environment are unlikely to be successful. Ghana experienced a deterioration in resource allocation during 2008â€“12 because of debt-financed expenditure hikes that led to interest payments of about 7 percent of gross domestic product per year, taking precious resources away from pro-poor spending, thus undermining Ghana's overall growth and poverty reduction agenda and the effectiveness of the World Bank's budget support. This emphasizes the importance of the quality of public resource use in both public financial management and public resource allocations, as a pre-condition of budget support success. 6.4 Donor coordination on budget support can be difficult in a challenging environment like that in Ghana in 2008â€“13. Assessment of eligibility for budget support is still a controversial area in relationships between various donors. Despite a move toward performance criteria based on agreed-to actions, various donors may interpret different shocks differently, which will affect donor coordination. Dealing with macro and fiscal mismanagement when macroframework is not formally a part of the performance assessment can be an especially contentious issue. 6.5 Fiscal pressure can crowd out discretionary expenditures, and service delivery sectors are especially vulnerable. The World Bank can use DPF operations to take a crucial role in protecting pro-poor expenditures in such an environment. 6.6 Giving due weight to the underlying factors of fiscal imbalances and addressing them appropriately is crucial. Measures taken to contain the public wage bill and mitigate fragmentation of bank accounts were insufficient to translate into lasting results. 6.7 The World Bank has a crucial role in providing advisory services that are complementary to budget support. A more proactive engagement in estimating the fiscal impact of the single spine salary reform introduction could have helped in designing a phased approach consistent with the long-term budgetary envelope.
P127317 | LR-Poverty Reduction Strategy Credit I | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/359881613078088736/text/Liberia-LR-PRSC-I-FY13.txt | http://documents.worldbank.org/curated/en/359881613078088736/pdf/Liberia-LR-PRSC-I-FY13.pdf | This review broadly concurs with the 4 lessons from ICR, and offers additional suggestions:Lesson 1: Importanceof sustained measures for good fiduciary practices to be ingrained in government operations, which also underscores the needfor a thorough and systematic ex ante risk assessment of risks to achieving development objectives and articulation ofmitigation measures. Excessively overburdening the fragile and low capacity system with complex technical reforms (IPSAS-basedreporting, introduction of ASYCUDA and IFMIS, payroll reform, etc.) is fraught with major risks to sustainability and thecredibility of reforms in the long term, once there is no direct donor support and hand-holding.Lesson 2: Need forgood communication with all stakeholders from the start to avoid preparation and implementation delays. At the beginning of theseries Parliament was not fully informed that the budget support was in the form of an IDA credit and not an IDA grant and neededadditional assistance on how to ratify such agreements, which took additional 11 months between the Board approval anddisbursement. In addition, an extended and sizable program such as this series would have benefited from a better upfrontunderstanding of the political economy risks and scenarios.Lesson 3: Need to keep the range of policy areasflexible, to better respond to exogenous shocks such as the Ebola crisis, which occurred after the start of the series andhighlighted the weaknesses in Liberias health caredelivery system.Lesson 4: Capacity for reform incountries like Liberia, requires heavy TA to support a successful reform program. The TA also encouraged stronger governmentcommitment and willingness to reform. The key TA support was particularly helpful in the areas of PFM, land reform and inelectricity sector reforms. At the same time, ongoing TA support for implementation (absolutely critical in an environment likeLiberia) also needs to be accompanied by strong and clearly targeted capacity building measures and indicators to ensuresustainability of achievements.
P127319 | Liberia Integrated Public Financial Management Reform Project | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/663911524677803327/text/Liberia-LR-Integrated-PFM-Reform.txt | http://documents.worldbank.org/curated/en/663911524677803327/pdf/Liberia-LR-Integrated-PFM-Reform.pdf | Lessons are drawn from the ICR: Complex project design should be avoided especially in lowcapacity environments, and development partners and Government efforts should be carefully sequenced and aligned. The factthat the project had five components, twenty subcomponents with a number of activities under each subcomponent had caused problemsrelated with coordination and also dilution of government focus. The consolidation of project activities into few major areas withclear responsibility on the Government side would make the implementation easier. In order to avoid overly complex and ambitiousdesign, the PFM reforms should be sequenced starting with ensuring basic financial controls and ordinarily annual budget process,and addressing more advanced reforms such as MTEF or fiscal risk monitoring during follow up operations. Teamsshould avoid using composite indicators like PEFA that are not designed and managed for project-level MEpurposes. PSMP IIs efforts to use innovative, CPIA-based indicators in order to reduce ME costs provedto be unworkable in practice because the data was not sufficiently granular to capture project- level impacts and were subject tounanticipated adjustments to methodology. Indicators based on project-generated data and produced on a regular basis may be bestsuited for public sector reform projects. The results frameworks intermediate indicators should be streamlined toreduce the administrative burden, and facilitate the clients efforts to monitor and report on their progress. PEFAassessment could be used to assess overall impact of the reform, but not project implementation. The results indicators should bemore focused on the specific capacity and system performance issues that will be addressed under theproject. ME should be a management tool for any project, not a compliance exercise. Teams shouldcontinually review and explain to internal and external audiences how project interventions are expected to lead to results andimpacts of importance. As part of the constant dialogue around the results chain, the project results framework should be reviewedand updated periodically,
P127319 | Liberia Integrated Public Financial Management Reform Project | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2017 | 2021 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/545461610560356570/text/Liberia-Integrated-Public-Financial-Management-Reform-Project.txt | http://documents.worldbank.org/curated/en/545461610560356570/pdf/Liberia-Integrated-Public-Financial-Management-Reform-Project.pdf | 3. Lessons 3.1 Effective support for enhancing revenue mobilization and administration can benefit from combining technical assistance with logistical support. The project, in a coordinated effort with donors, contributed to the establishment of the Liberia Revenue Authority by providing technical assistance for the establishment of its framework and development of its organizational structure, and financing logistical equipment and tax automation systems. With enhanced efficiency of tax administration, government revenue has increased significantly. 3.2 The use of PEFA composite indicators as results indicators is often not advisable. In the IPFMRP, a PEFA produced in 2008 provided a solid analytical underpinning for designing the project. However, seven composite PEFA indicators used as results indicators made it difficult to follow the results framework. Selecting appropriate indicators is critical to monitoring progress toward achieving PDOs. 3.3 Superficial reviews and overoptimistic ratings in ISRs can negatively affect project implementation and outcomes. In the IPFMRP, the task team did not recognize the lack of progress on results indicators and instead provided overoptimistic ISR ratings. Raising concerns more clearly could have better motivated the government to act on key project activities that had been delayed. The Mid-Term Review was a missed opportunity to address implementation problems and improve the results framework. 3.4 Effective and sustainable PFM reforms require continuous engagement to overcome political challenges. For political reasons, project implementation was often difficult or delayed in some critical activities, such as the establishment of the TSA and the IFMIS rollout. The seriousness of these risks was underestimated at appraisal. A lack of engagement at the political level has undermined the achievement of project development objectives.
P127328 | Emergency Safety Nets project (Jigiséméjiri) | Western and Central Africa | Mali | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2023 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099091024181032116/text/P127328-f957c436-3f45-4db4-aaad-bae919f3ff25.txt | https://documents.worldbank.org/curated/en/099091024181032116/pdf/P127328-f957c436-3f45-4db4-aaad-bae919f3ff25.pdf | The ICR (pp. 35-38) produced a series of insightful lessons and recommendations, with highlights including:Inlow-capacity and conflict-affected settings, safety net project design can benefit from simplicity and gradual scale-up.In this case, the initial direct cash transfers were effectively piloted and expanded, but challenges affected the addition of morecomplexity with the income-generating and labor-intensive public works elements. The one-year period set to implement eachlabor-intensive public works cycle led to procurement issues that produced significant delays. Ultimately, the project did notproduce evidence of the potential benefits of labor-intensive public works compared to administratively simpleralternatives.Fragility and conflict can challenge the implementation even of well-planned monitoring andaccountability mechanisms. In this case, initial ME activitiesincluding a careful impact evaluationwerecarried out as planned, but monitoring activities following additional financing were affectedby the insecure context,leaving the project with no assessment of the impact and cost-effectiveness of the income-generating and labor-intensive publicworks activities.IEG adds the following lesson:In cases where conflict and crisis are severely impactingkey elements of project implementation, significant project restructuring can focus implementation on what is working. Inthis case, the direct cash transfers were well-targeted to poor and vulnerable households, and the social registry was developedand used effectively even in a highly challenging context. However, persisting with the struggling labor-intensive public worksactivities represented a missed opportunity (ICR, p. 34) to reallocate funds toward other well-performingsub-components that could have better contributed to achievement of project objectives.
P127331 | First Programmatic Reducing Vulnerabilities for Growth Development Policy Credit | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2014 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/228571474897127418/text/000020051-20140626110859.txt | http://documents.worldbank.org/curated/en/228571474897127418/pdf/000020051-20140626110859.pdf | This Review supports the findings (called lessons) cited in the ICR, especially the need for addressing macro and fiscal stability issues in DPCs implemented in volatile environment through prior actions and outcome indicators. The review adds the following lessons:It is important to address the unfinished agenda of previous policy lending operations that remain relevant for program objectives. This can contribute to a more successful operation.If key conditions underpinning budget support operations, such as public expenditure management, are not in place or not being addressed by the program, the Bank would need to continue working on program preparation to ensure these conditions are met before approving the program.Quality monitoring frameworks with adequate indicators are important ingredients for an operation's success not only because they enhance evaluability of the program, but they also help to guide the program toward success. Weak relevant indicators may undermine Government's focus on reforms.
P127332 | Second Programmatic Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2017 | ICRR | >=100 million | Satisfactory |  |  | Moderately Satisfactory |  |  |  | IEG concurs with the ICR lesson (pp. 25-26) with some minor adaptations:Strong Governmentownership of the reform agenda, based in the Government strategy, is essential to ensure the implementation and sustainability ofDPL programs. In the case of this DPL series, the Government engaged in the project implementation and continued to support thePDOs beyond the closing of the project.A simple design, based on the learning from previousoperations in the country, establishes an appropriate pace for reform implementation. In the case of this DPL series, it isconcentrated in four specific objectives clearly aligned with the Governments quinquennial Strategic Plan, instead ofcovering an extensive array of areas.Flexibility to account for rapid responses to changingcircumstances in the implementation of the projects is critical for ensuring effective delivery, especially in the case ofunexpected shocks. IEG would add that changes in the program need to be reflected in the results framework. In the case of this DPLseries, the procurement-related actions needed to be adjusted due to unforeseencircumstances.Strong analytical groundwork and complementary technical assistance are essentialto ensure adequate program implementation. This DPL series focused on areas of strategic relevance where the Bank had previouslyestablished a record of strong technical capacity and had cross-country experience.A fifth lesson should beadded:A solid fiscal basis along with excellent tax collection management are needed toguarantee the long term the sustainability of extensive social policies. In the case of this DPL series, so far the advancements inthe former areas are not enough, although the Government is engaged in supporting the PDOs beyond the DPL series.
P127338 | Climate Resilient Infrastructure | Latin America and Caribbean | Belize | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099300412232214730/text/P12733804eb7f607c0901504fb764c633b3.txt | http://documents.worldbank.org/curated/en/099300412232214730/pdf/P12733804eb7f607c0901504fb764c633b3.pdf | According to theICR, the projects operational experience informedthe following four lessons,slightlymodified below (ICR, paragraphs 95-98): Investingin risk information systemsstrengthens thedesign of infrastructure works. In this project,activities led to the development of LiDAR surveys to generate floodmodels and led to a 1:25 year flood return period standardfor roadworks. Data was used to design a climate resilient PGHighway.MIDH adopted the standards to decidefutureresilientinfrastructure designs to be financed by otherdonors. Designing and implementing climate and disaster resilient infrastructure needs to be matched byadequate experience and capacities of the recipient institutions. In this project,integratingclimate anddisaster resilientroad infrastructure was new to Belize. National institutions did not have experienced orthe capacityto define suchinvestment activities and prepare accompanying bid documents.This capacity gap was not carefullyconsidered during project design. Mitigating measuresmay avoid delays. Small Island Developing States(SIDS) may benefit from establishingan umbrella PMU to mitigate the limited availability of expertise. In thisproject, Belize hada limited number of experts familiar with procedures and requirements of Bank financedoperations.The SIF and PMU staff from the previous MDP proved to be an effective strategy for implementing this project. Measures suchasa procurement unit within SIF were designed tomitigate the lack of procurement capacity. This and similar effortswere to ensure that institutional knowledge and capacities are retained. Capacity would then be ready for future donor-fundedprojects. The SIF board had not approved the proposal but if adopted, SIF would havequalified staff and serve as the centralmanagement entity for future operations. This could be further explored in Belize and other SIDS. A non-technicalimplementation agency, like the SIF, may facilitateimplementation. In this project, the SIF experience in managingdonor-funded projects and workingwith multiple ministries and partnershelpedthe rapid response to manage CERC.The SIF PMU mobilized other ministries, government institutions, and private sector partners.SIF establishedeffectiveworking relations with the Ministry of Agriculture, the Ministry of Human Development, National Bank of Belize, andthe private telecom operator Digicell to implement CERC activities.
P127388 | Moldova Education Reform Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099010524204015339/text/P12738816db1db0ba183541eba9e74c42b7.txt | http://documents.worldbank.org/curated/en/099010524204015339/pdf/P12738816db1db0ba183541eba9e74c42b7.pdf | The ICR (pp. 36-37) offers multiple insightful lessons, reframed here by IEG:Caution should be exercised whenusing learning outcomes as outcome-level indicators. Project timelines are subject to unexpected interruptions and delays,and even with an implementation period where all interventions run like clockwork (ICR, p. 36), it may not be realisticto expect tangible evidence of improved learning outcomes over a single projects lifespan. In addition, reliance on formalassessmentswhich may be conducted with infrequent and variable timingcan produce lags in identifying where and when aproject has fallen off track in progressing toward learning targets. It is unlikely that countries without established assessmentsystems can both create and implement them in time to show results under a single project. Moreover, national assessments arefrequently updated or otherwise adjusted, possibly as a part of a projects interventions, making comparability over time anissue.Projects that do not thoroughly analyze the extent and nature of issues to be addressed during the designphase are likely to encounter delays and require restructuring. In this case, school quality standards were not welldefined prior to project launch, and an inventory of the physical condition of schools had not been carried out. As a result, theextent of required rehabilitation works was not well understood, in terms of both the number of schools that required upgrading andthe extent of works that were needed in each. Once this preparatory work was completed, almost two years into the projectslifetime, significant restructuring and adjustment of ambition wererequired.Consolidation of school networksis politically and social challenging, requiring strong and sustained political will, comprehensive planning, measures to monitorand mitigate risks, engagement with stakeholders, transparent communication, continuous evaluation, and proper allocation ofresources to compensate those impacted by the reforms. In this case, the project made substantial progressdue to theestablishment of clear rules and procedures for all aspects of the reform, effective communication campaigns, and capacity buildingin support of reform implementation. Even with this progress, however, some aspects of planned reformin this case, teachercareer and remuneration reformproved too challenging toimplement.
P127408 | First Programmatic State Owned Enterprises Reform DPL | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/599621584995310781/text/Serbia-YF-First-SOE-Reform-DPL.txt | http://documents.worldbank.org/curated/en/599621584995310781/pdf/Serbia-YF-First-SOE-Reform-DPL.pdf | The ICR draws a number of lessons, of which two are of particular interest and restated asfollows:Structural SOE reforms require a long period of engagement and implementation before achievingexpected outcomes. In the case of Serbia, the ICR reports that it took five years from the first identification to completionin 2016 and yet some of the impact of the new laws passed are yet to be realized. Maintaining the policy dialogue and the provisionof critical support over the medium term is essential for realizing the full impact of the series.Secondly,when a DPL series has not completely addressed challenges related to structural SOEs reforms, continuing the series with otherprogrammatic operations with follow-up actions or technical assistance may be appropriate. Serbia has a relatively large SOE sectorwith large fiscal costs that could potentially affect real sector growth. In this case, the series tackled short term reformswithout sufficient time and attention to achieving longer term results. The management of the fiscal costs of SOEs still requiressupport. After implementation of the series, Serbias SOE governance still shows significant gaps against OECD bestpractices, with room to improve SOE governance frameworks across all dimensions (IMF, 2019:58). There is room for moretransparency, assessment, and reporting to improve the governance and performance of SOEs, and the Bank is continuing to supportSOE reforms with a follow-on DPL series.
P127411 | CV-DPL 4-PRSC VIII | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/905221498832765678/text/Cabo-Verde-CV-DPL-4-PRSC-VIII.txt | http://documents.worldbank.org/curated/en/905221498832765678/pdf/Cabo-Verde-CV-DPL-4-PRSC-VIII.pdf | The ICR appropriately draws the lesson that in countries with low capacity, design of budget support operations must berealistic, selective and focused on a limited number of areas of high impact, taking into account the time horizon for the reformimplementation. Excessive ambition can affect implementation.IEG addsthree furtherlessons:First, the results framework as an operational toolis weakened unless they show clear links from objectivesto reform areas, prior actions and target indicators. Absent such clear articulation of linkages, it is very difficult to attributethe Bank supported activities to the program objectives and measure and assess their contribution.Second, the relevanceand criticality of prior actions may be diminished if they consist only or largely of legislative actions and not measures thatdemonstrate enforcement and a strong will to implement reforms.Third, in the absence of an IMF program during aBanks budget support series, the Bank would be well advised to consider public debt related monitoring and target indicatorsto help achieve macro-fiscal stability.
P127433 | First Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2013 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/450711468186274707/text/ICRR14887-P127433-PUBLIC.txt | http://documents.worldbank.org/curated/en/450711468186274707/pdf/ICRR14887-P127433-PUBLIC.pdf | The ICR distills a number of pertinent lessons:The Bank's value to a high income client like Poland lies in its knowledge base and analytical strengths rather than its financial resources. Flexibility and responsiveness contributed to the operation's value. A program is more likely to be be effective if it is rooted in an established partnership and shared priorities.Strong ownership is essential as well as a consultative process where reforms are potentially contentious.Bank support for an EU member state must be consistent with the economic governance framework of the EU.
P127433 | First Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2013 | 2019 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/340071559242287976/text/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/340071559242287976/pdf/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.pdf | Lessons 8.2 The Independent Evaluation Group draws the following lessons\. â€¢ Development policy lending can help mitigate global economic and financial shocks and protect vulnerable groups in high-income countries when accompanied with timely, high-quality, and responsive technical assistance that supports the reforms. The series were appropriate to reinforce the credibility of the authorities' commitment to reform, while providing technical solutions for the reform program's design and implementation. The DPLs enabled dialogue on important reforms the government was undertaking based on its analytical and advisory work. â€¢ Where a high-income country is required to implement constitutional provisions, or agreed reforms with a regional body, providing support for the implementation of such reforms is likely to enhance the likelihood of success. In the case of Poland, policies limiting fiscal deficits and overall debt levels were required both by EU agreements and constitutional provisions. Though these policies were complex, the government committed to implementing them because of the importance of EU accession agenda to Poland's economy. However, policies not so required by the EU were more easily reversed, for example, the increase in the retirement age. â€¢ RAS are a promising tool for engaging governments in high-income countries when Bank Group staff demonstrate the capacity to produce timely and highquality analytical products in response to government requests. In the case of Poland, the government appreciated the quality and responsiveness of World Bank staff to their analytical needs. However, World Bank adjustment to the different business model could have been better managed. Staff had the (sometimes difficult) task of explaining to the government why the World Bank needed to charge high-income clients for services, while still requiring sole source procurement and retaining intellectual property rights. The World Bank and government are now working together to make RAS mutually beneficial and a new tool for engagement. â€¢ Coordinating with other partners in situations where the World Bank is not the largest stakeholder is important for successful implementation of reforms. In the case of Poland, the EC and the IMF are the dominant development partners providing more funds or guaranteed resources to the government. â€¢ Analyzing the political cost of implementing proposed reform measures is an important part of policy lending. Such an analysis would have been particularly useful in relation to the pension and labor market reforms these two series attempted to support. It is notable that Ministry of Finance staff requested such advice in the future to guide the implementation of new reforms.
P127435 | Results-Based Rural Water Supply and Sanitation Under the National Target Program | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | PforR | 2013 | 2020 | 2020 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/912501592589127834/text/Vietnam-VN-Rural-Water-Supply-Sanitation-P4R.txt | http://documents.worldbank.org/curated/en/912501592589127834/pdf/Vietnam-VN-Rural-Water-Supply-Sanitation-P4R.pdf | This was the first PforR program in Vietnam,in the East Asia region of the World Bank, and in the Water Sanitationsector.Four additional PforR operationsin Vietnam followed this operation. The ICR offered six lessons andrecommendations, four of these are below: PforRs as a financing mechanism allow for adoptingprocedures that optimize the flexibility offered by results-based financing.In this Program, processes were adjustedto address the challenges of the systems in place. These included timely releases of budgets and transfers from the centraltothe provincial governments, coordinating annual investment planning at the local level, allocating achievable targets, andimproving results verification to justify disbursements. Another example was separating the DLIs for the water sector from thesanitation sector. Making theDLIs sector specific allowed one sector to disburse accordingly while the other sectorexperienced delays. The lesson learned from this operation call for carefully analyzing government systems and procedures to beused under the program, simulatingrecommended improvementsto ensure that effective funding flows or pre-financingarrangements would be seamless inserted into existing processes.Confirmed effective improvements could beincluded intothe Program financing agreement, the PAP, or POM. Strong implementation support is critical for success.This program was founded on an existing NTP/NRD program. This PforR operations providedbudget support to provincialgovernment investment programs based on achieved periodically verified results. Institutional capacity limitationsat theProvincial level were acknowledged, hence, the program included capacity building TA. Thiscomponent was addressed by anadditionalparallel grant financing. Components of that TA program responded tothe capacity gaps in implementing theprogram. By program closing, with effectiveBank supervision, technical assistance offered, a jointly established strongverification protocol, and a PAP that was informed by best practices, all of the DLIs were achieved. The PforRinstrumenthelpedaddress long-term institutional barriers, and reshaped sector incentives with the help of the capacitybuildingTA that targeted the provincial implementation agencies in conjunction withthe program. The lesson learned fromthis operation for future PforR operations was that sufficient scope and funding should be included for institutional and capacitybuilding tapping into resources such as other Bank instruments (e.g., an Investment Project Financing), or grants from other donorpartners. The Program could be used to encourage the private sector to participatein deliveringruralwater supply and sanitation services. In this program, private sector providersfinancedand operatedsustainable water schemes in the 8 participating provinces. Private sector entities were convinced by clear, time bound investmentplans and predictable availability of financing based ontransparent results-based indicators.The lesson from thisoperation was that the private sector entities were likely toinvest in a sector governed by a legal and transparentregulatory framework.
P127435 | Results-Based Rural Water Supply and Sanitation Under the National Target Program | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | PforR | 2013 | 2020 | 2022 | PPAR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099652406032228425/text/IDU082007bcb0931e0475b0bab905a5c7814c204.txt | http://documents.worldbank.org/curated/en/099652406032228425/pdf/IDU082007bcb0931e0475b0bab905a5c7814c204.pdf | 3. Lessons 3.1 The experience from this PforR suggests the following lessons: 3.2 PforR design needs to be closely aligned with national policies and regulations, particularly regarding financial management. To avoid frictions and imbalances in financial management, the design of PforRs needs to ensure that cash deficiencies do not occur in the provincial and subnational annual budgets because of differences between the disbursement schedules of the government system and the PforR operation. An exacerbating factor is that the Vietnamese budgeting and transfer system did not have a mechanism for adaptable performance-based transfers from the central government to 19 provinces to enable results-based budget allocations (World Bank 2020a). In 2020, the government of Vietnam also issued a decree (No. 56/2020/ND-CP) that official development assistance and concessional loans be used to finance only capital expenditures and not recurrent expenditures, which prevented the development of a new PforR operation. 3.3 Both the design and implementation of the PforR need to exercise equity and inclusivity in targeting beneficiaries to avoid selection bias against hard-to-reach ethnic and the poorest minorities and to reduce their vulnerability in the long term. Results- based operations designed with DLIs have a built-in incentive to focus on achieving results efficiently, which could cause the provincial agencies to stay away from serving the vulnerable populations and areas. When selecting and prioritizing communes to be intervened under the RWSS PforR, there was an incentive to focus more on achievability of DLIs than reaching out to those with the greatest need. It resulted in inadequate representation of poor and ethnic minorities as target beneficiaries in relation to their share of the total population. Concrete measures need to be adopted to ensure that results-based operations provide implementing agencies with incentives to work in challenging areas, for example, the integration of poverty alleviation as a DLI target. 3.4 The existence of an enabling environment for private participation could enhance the effectiveness of PforRs. The results-based approach fosters the mobilization of private actors. The national policies and regulations promoted public-private partnerships, which were reflected in the design of the RWSS PforR. PforRs need to assess and harness opportunities to allow private enterprises to lead improvements in cost recovery ratios of water supply schemes. The experience with the Results-Based RWSS under the NTP PforR shows that VietnamÃ¢â‚¬â„¢s favorable enabling environment for private sector participation has enhanced the operationÃ¢â‚¬â„¢s implementation effectiveness by improving the financial and operational sustainability of the countryÃ¢â‚¬â„¢s RWSS sector. 1Access to hygienic water in rural areas as reported in the National Target Program on Rural Water and Sanitation 2012Ã¢â‚¬â€œ15 document, approved by Prime MinisterÃ¢â‚¬â„¢s Decision 366 (cited in World Bank 2012c). Ã¢â‚¬Å“HygienicÃ¢â‚¬ is equivalent to the World Health OrganizationÃ¢â‚¬â€œUnited Nations ChildrenÃ¢â‚¬â„¢s Fund Joint Monitoring Program for Water Supply and Sanitation definition of Ã¢â‚¬Å“improved water sourceÃ¢â‚¬ or a source that Ã¢â‚¬Å“by nature of its construction or through active intervention, is protected from outside contamination, in particular from contamination with fecal matter.Ã¢â‚¬ 2Access to clean water in rural areas as of 2010, as reported in the National Target Program on Rural Water and Sanitation 2012Ã¢â‚¬â€œ15 document, approved by Prime MinisterÃ¢â‚¬â„¢s Decision 366 (cited 20 in World Bank 2012c). Ã¢â‚¬Å“CleanÃ¢â‚¬ water, according to the Ministry of Health definition, refers to specific water quality parameters defined in the standards QCVN 02: 2009/BY. 3Clean water, according to Ministry of Health definition, refers to specific water quality parameters defined in the standards QCVN 02: 2009/BY. Sustainable water systems are those which, two years after the start of operation (defined as the month in which the first water is supplied, billed, and paid for by customer households), satisfy the following characteristics: (i) provide clean water, as defined by the Ministry of Health standards (QCVN 02: 2009/BYT) including, if necessary, specific control and measures for arsenic; (ii) the system is operating under a recognized management model; (iii) at least 85 percent of the number of planned system connections are working (providing water 24 hours a day, seven days a week and allowing for a 10 percent failure rate on a monthly average) and have had bills issued and paid; (iv) net revenue from tariffs is sufficient to cover operation and maintenance costs; and (v) nonrevenue water is less than 25 percent the month before verification is conducted (World Bank 2013). 4Cost recovery was defined in the Operational Manual (Vietnam 2016, page 40): Ã¢â‚¬Å“Operation and maintenance costs are covered by operating revenue from tariffs for the last 3 months of the reporting period.Ã¢â‚¬ 5 As defined by Standard QCVN 01:2011/BYT (World Bank 2013). 6Because the economic conditions of the rural populations in the participating provinces were relatively good, they showed a preference for building latrines with long periods of durability. Most of the sanitation facilities built under the PforR were septic tanks, which cost more than organic composting latrines that were mainly used in more remote areas. 7The national standards and regulations applied to the Results-Based RWSS under the NTP PforR included QCVN 01:2011/BYT, which was the National Technical Regulation on Hygienic Conditions for Latrines; and QCVN 02:2009/BYT, which was the National Technical Regulations on Domestic Water Quality (applied to small-size water plants with capacity less than 1,000 cubic meters per day night; Vietnam 2016). 8The procurement measures were first introduced to Vietnam under the Urban Water Supply Development Project (P073763) and were replicated in other projects. 9Vietnam East Meets West Foundation Global Partnership on Output-Based Aid (GPOBA) Rural Water Supply Development Project (P104528, fiscal years 2008Ã¢â‚¬â€œ12). The project development objective was to increase sustainable access to piped water services to low-income households in rural central provinces of Vietnam through an innovative community-based approach, involving public-private partnership. An independent verification agent hired by GPOBA verified outputs in the water programs and reported quarterly to the World Bank and GPOBA with recommendations regarding eligible subsidy payments. GPOBA changed its name to the Global Partnership for Results-Based Approaches in February 2019. 10The number of visits to the website is per the Wayback Machine internet archive (https://web.archive.org/) as of February 26, 2020. Accessed the internet archive on October 29, 2021. 21 11The number of visits to the website is per the Wayback Machine internet archive (https://web.archive.org/) as of July 22, 2017. Accessed the internet archive on October 29, 2021. 12 The number of visits to the website is per the Wayback Machine internet archive (https://web.archive.org/) as of July 22, 2017. Accessed the internet archive on October 29, 2021. 13The amounts of private sector investments in the water and sanitation sector are per the World BankÃ¢â‚¬â„¢s Private Participation in Infrastructure Project database (https://ppi.worldbank.org/en/ppi). Accessed on October 29, 2021. 14Comparison provinces were Hoa Binh, Thai Nguyen, Hai Duong, Nam Dinh, and Nghe An. Those were the provinces in the Red River Delta and a number of northern provinces that share similarity of geographic conditions with Thanh Hoa and Phu Tho. 15 See http://nuocsachnongthon.thuyloivietnam.vn/ 16Six provinces used the mobile phoneÃ¢â‚¬â€œbased M&E system for water connection information, five provinces used it for household sanitation information, and three provinces used it for information on sanitation facilities in public buildings. 22
P127441 | BJ-PRSC 8-Eighth Poverty Reduction Suppo | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/794301475117727597/text/000012394-20150310082001.txt | http://documents.worldbank.org/curated/en/794301475117727597/pdf/000012394-20150310082001.pdf | The following three lessons have been selected as being of particular importance from those presented in the ICR, with some adaptation of content and language.(i) A good understanding of the political economy dynamics at play is needed to engage in transformational reforms. The volatile and shifting links between key public and private players can hamper the sustainability of structural reforms needed to boost economic growth, as witnessed before and during the PRSC-8 preparation and implementation period in the port and cotton sectors and the lack of results in terms of perception of corruption and the broader business climate. Public private partnership arrangements need a sound legal and regulatory framework to ensure their transparency, fairness, efficiency and sustainability. (ii) Obstacles due to resistance to change and lack of capacity should not be underestimated. Selectivity and simplicity of design are essential for success in such environments, as are attention to and realism about the scope and pace of reform.(iii) It is indeed important to provide well-targeted analytical and advisory services and technical assistance in support of key reforms where government capacity is weak and also in preparing the ground for future commitments, when the Government is ready to adopt an ambitious medium-term reform agenda.IEG adds the following two lessons: (iv) In this operation outcome indicators were linked directly and narrowly not to the operationâ€™s specific objectives, but only to the prior actions. However, while outcome indicators that are limited in scope, of modest ambition, and very narrowly defined may be easy to monitor and also to achieve, they do not provide robust contributions to the key associated outcomes necessary towards achieving the development sub-objectives of the operation. (v) In the presence of significant resistance to reforms and high uncertainties, a stand-alone budget-support operation is certainly more appropriate than a programmatic series, as the ICR also states. However, even more appropriate would have been switching the planned budget support operation to a small technical assistance project, until that time when the necessary commitment to and actions on important reforms would have been truly deserving of support with a programmatic series. Such an alternative could have been equally or more effective in maintaining the policy dialogue, financing technical analyses, and providing strong incentives to move faster on the reform agenda, while minimizing new foreign debt (though concessional in nature).
P127449 | Cote d'Ivoire PRSC 1 | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/422211530284091123/text/Cote-dIvoire-CI-PRSG-1.txt | http://documents.worldbank.org/curated/en/422211530284091123/pdf/Cote-dIvoire-CI-PRSG-1.pdf | The following lessons are adapted from the ICR:When the disbursement objective of a DPOpredominates, program design should be less ambitious. The tradeoff between budget support and reform implementation inthis series led to instability in the triggers and the policy matrix. More importantly, it compromised some potential achievementsbecause of the failure to delay disbursement until key reforms were made (ICR, p. 32). In such contexts thereshould be explicit mention in the PD of the primacy of the disbursement objective.The effectiveimplementation of reform programs requires effective sequencing. The lesson from reform program in Cote dIvoireillustrates the need to allow adequate time for their completion. Politically sensitive reformscentral to the performance of the economy require the participation of Bank staff in their design. Outcomes in CotedIvoire demonstrate that if appropriate measures are not adopted by government authorities, the reforms should be excluded,and the viability of the entire program should be reviewed in depth. IEG adds the followinglesson:Reform programs with large numbers of prior actions are difficult to implement. TheCote dIvoire DPO series illustrates that reducing the number of prior actions would provide the program with more focus
P127449 | Cote d'Ivoire PRSC 1 | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2022 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/768421642544309047/text/Côte-d-Ivoire-First-Second-and-Third-Poverty-Reduction-Support-Credits.txt | http://documents.worldbank.org/curated/en/768421642544309047/pdf/Côte-d-Ivoire-First-Second-and-Third-Poverty-Reduction-Support-Credits.pdf | 3. Lessons 3.1 This assessment offers the following lessons. 3.2 Designing a DPO series with many unrelated prior actions may undermine the achievement of results. The large number of prior actions made it difficult to monitor, prioritize, and focus implementation on the most critical areas. 3.3 A clear results chain is needed to focus on critical actions and monitor results. A more explicit linking of actions to outcomes could have helped reduce the number of prior actions and ensured that critical barriers were addressed. A clearer results chain would also have facilitated results indicators oriented more toward desired outcomes than intermediate steps. 3.4 When critical reforms require sequencing over an extended period for effective implementation, they should be complemented by institutional measures for sustained implementation and technical assistance to build the necessary capacity. Evidence to assess the efficacy, sustainability, and impact of reforms with respect to governance and the business climate began to emerge three to four years after series completion. Reforms to the legal and institutional framework take time to implement and may succumb to pushback if not supported by appropriate technical assistance to strengthen institutions. As the groundwork laid during a DPO series may bear fruit only gradually, monitoring and evaluation requires a focus on intermediary outcomes in the medium term and final outcomes over a more prolonged period. 3.5 In postconflict situations, the urgent need for budget support provides an opportunity to accelerate reforms, but the reform package must be aligned with political sensitivities and uncertain country conditions. In this case, a combination of sound macroeconomic fundamentals and the governmentâ€™s readiness to implement reforms enabled CÃ´te dâ€™Ivoireâ€™s postconflict DPO series to enhance the governmentâ€™s ability to function and pursue reforms for long-term economic growth. By taking advantage of political will in the postconflict situation, DPOs helped accelerate reforms that address basic constraints to private sectorâ€“led growth. Many reforms that were not politically sensitive were effectively implemented and sustained, especially when related to the regional economic body (WAEMU). Nonetheless, in taking advantage of the opportunity to advance legal and institutional reforms to improve the investment climate in CÃ´te dâ€™Ivoire, DPO design should assess the political will to overcome potential resistance from vested interests and include measures to mitigate the risks to implementation of actions that are retained. 40
P127463 | Strengthening Service Delivery for Growth, Poverty Reduction and Enviromental Sustainability in the State of Ceará PforR | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | PforR | 2014 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/112661593451459007/text/Brazil-BR-Strength-Serv-Delivery-Cear-PforR.txt | http://documents.worldbank.org/curated/en/112661593451459007/pdf/Brazil-BR-Strength-Serv-Delivery-Cear-PforR.pdf | The ICR draws the following three lessons from the experience of implementing this project, with some adaptation oflanguage.(1) The PforR instrument can be useful for supporting improvements in governance, with appropriate DLIsbut need to be carefully and discretely targeted.The experience of this operation showed that thewhile theDLIs were appropriate for the areas associated with family assistance and improving water quality, they were of limited use for thearea associated with improving skills development. The level of ambition regarding how the P4R would drive reform in all sectorswas limiting given the scale and reach of where the reform agenda was directed.(2) While complementingthe PforR instrument with a technical assistance component financed through an IPF instrument, can help in producing improvementsacross several result areas, it is necessary to include indicators for monitoring activities associated with the IPFinstrument.Lack of indicators for monitoring the activities financed through the IPF instrument, besides creatingaa bias towards a greater weight given to the PforR actions, undermine aproper evaluation of the projectsaccomplishments and do not allow clearer insight in how each instrument informs the other.(3) Betterformulating of target values is required for PforR operations. In this operation, some indicators reached their targetlevels early in the project, implying that the targets were modest in terms of the level of ambition.
P127486 | SUSTAINABLE AGRICULTURE AND CLIMATE CHANGE MITIGATION PROJECT (GEF) | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2013 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/396731544713311712/text/Uzbekistan-SUST-AGR-CL-CH-MITIGATION-GEF.txt | http://documents.worldbank.org/curated/en/396731544713311712/pdf/Uzbekistan-SUST-AGR-CL-CH-MITIGATION-GEF.pdf | The ICR included four lessons. The following lesson isadopted from the ICRwith some adaptation oflanguage: Lack of adequate assessment of the situation and needs of small farmers in projectdesign may lead to lack of uptake as the content of the matching grants packages might not be relevant or adequate for the intendedbeneficiaries. The projects experienceemphasized the need to betterunderstand the constraints faced bysmall farmers. These could include: access to credit, the minimum size of viable investments or access to knowledge about renewableenergy or energy efficient technology. Although investments in biogas digestors were key to reduce carbon emissions, theprojectsexperience revealedthat these technologies require volume and scale to become efficient andcost-effective. The novelty of this type of investments and the requirement for volume and scale up were possibly anotherconstraint for small farmers to apply for matching grants.The following lesson is drawn byIEG: Adequate assessment of relevant aspects of the project and implementation arrangementsmay ensures a satisfactory Quality at Entry and smoother implementation experience. The project design suffered from anumber of shortcomings that undermined implementation. Carrying out adequate assessments and necessary studies might resultina longer preparation stage, butwarrants a better understanding of local conditions. In turn, this ensures thatrelevant mechanisms are in place to facilitate smooth implementation of the project.
P127490 | Sustainable Financing for Biodiversity Conservation and Natural Resources Management | South Asia | Bhutan | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/994191574279170435/text/Bhutan-BT-Biodiversiy-Conservation.txt | http://documents.worldbank.org/curated/en/994191574279170435/pdf/Bhutan-BT-Biodiversiy-Conservation.pdf | The ICR provides a substantial set of ten lessons and recommendations (ICR, section V). Some of the more significantlessons are itemized below. Some of these lessons may well be useful for other operations of this nature in othercountries. The Annual Stakeholder workshop has been a valuable tool not only for providing on-goingtraining to grantees, but for allowing these implementing partners across agencies to share knowledge and experiences with eachother. The Technical Advisory Panel (TAP) is a valuable partner in the grant assessmentprocess. However, their specific technical value added is not always clear. The terms of reference for the TAP, its makeup, and the timing of its contributions to the assessment process should be carefully reviewed with the aim of looking to improveits ability to contribute more on technical issues during application review. Despiteincorporating increased flexibility into budgeting for sub-projects, the financing cycle and fund disbursement are stillproblematic for some grantees, at times resulting in challenges in completing activities essential for achieving objectives.The Bank raised the issue during Project implementation, including discussion with MoF, however it was apparently not practicableto modify the cycle at that stage. BTFEC Management Board should consider high-level discussions with the MoF and otherrelevant authorities to look into how the fund flow process can be simplified. In addition, the availability of funds should beassured throughout various seasons to ensure smooth implementation of activities regardless of the end/beginning of the fiscalyear. The inclusion of the restoration of cultural and religious sites and othercommunity-centered activities in projects has been instrumental in creating awareness and a positive relationship between parkstaff and community members in selected protected areas which resulted in increased reporting by community members of unregulatedactivities and enhanced sustainability of results. The development of strong community connections and enhanced rural livelihoodslays the groundwork for true co-management which will be essential for biodiversity conservation in Bhutan and other countries asthey continue to develop. Long-term success of rural and community-level infrastructureactivities, e.g., provision of electric fencing and their power sources are often undermined by a lack of financing formaintenance. BTFECs implementing partners now require a 30 percent down payment of total cost to be contributed bycommunities and put in an established maintenance fund. This has ensured both community commitment and the long-term sustainabilityof investments and positive social and conservation impacts.It was evident that some of theprocesses implemented through the Project have put some strain on BTFECs human resources capacity, particularly the rigorousnew ME system (as noted in Section 9 above). Given that BTFEC secretariat operated prior to (and during) the Projectwith a small staff complement of 6 people, it should be assessed whether the staffing level of the Secretariat needs to beincreased to accommodate the demands of the new modes of operation, particularly the new ME system and the expected higherlevel of grant-making activity.
P127508 | Building Resilience to Climate Related Hazards | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2013 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099300003292220501/text/P127508018127c05d0a9190f5dea7a2fbab.txt | http://documents.worldbank.org/curated/en/099300003292220501/pdf/P127508018127c05d0a9190f5dea7a2fbab.pdf | The ICR (p. 28) provided several lessons learned, which were adapted by IEG: For highly technical andcomplex projects such as hydromet and early warning services projects, it is critical to provide substantial technical support andto consider a multi-phased long-term engagement. This project required capacity building, especially in the DHM, duringthe initial years resulting in slow implementation progress. Also, a longer-term multi-phase approach taking into account thecascading implications of the key elements of the hydromet value chain would have been moreappropriate. Considering a SI for hydromet programs to bring together a group of key technical providers tosupport system design, implementation planning, procurement, and capacity building can be challenging. In this project,the hiring of a SI was challenging for several reasons such as immaturity of the System Integrator (SI) market, lack of SIslocal presence and client engagement, lack of clients capacity to manage a big consultancy, and the requirement forhigh-level approvals of the SI contract within government. An alternative option for providing technical support could bedeveloping prototypes that can be scaled up gradually and leveraging innovative technologies.
P127543 | Local Government Development Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/796221591653628583/text/Mauritania-MR-Local-Government-Development-Project.txt | http://documents.worldbank.org/curated/en/796221591653628583/pdf/Mauritania-MR-Local-Government-Development-Project.pdf | The following lessons were derived from the ICR with some modification of language: ContinuousCapacity Building Efforts May Sustain Capacity Gains as long as there is Staff to Receivethese.Mauritanias decentralization agenda beganin the 1980s.Different approaches wereadopted to build its legal and policy framework, planning, and human resource capacity at different administrative levels. Thisproject supported the PNIDDLE program as a comprehensive initiative to address local capacity gaps and strengthen localadministrations to deliver local services. However, to achieve capacity gains from training, there has to beadequate staff toreceive that training.In rural Mauritania,attracting and maintaining qualified staff was difficult. The level ofactivity of rural local governments was limited.Some rural local governments started to share staff to attract more competentprofessionals. The new operation underpreparation will support the local government human resource reform agendaandpropose financially sustainable measures informed by the lessons of this project. The lesson from this operation was the need tohave and retain adequate staff to carry forward the capacity gains fromtraining and technicalassistance. UsingConditional Performance-Based Grants may be an Effective and an Efficient Strategy toBuild Capacity. In this project,investment financing for local services was linked to good local governmentadministration performance. The performance-based mechanism rewarded good performance using predictable and transparent indicatorsassessed independently. The lesson from this operation was the effective approach brought by using the achievement of capacitybuilding factors to qualify for investment projects that delivered basic services. Numerous ParticipatingLocal Governments ina Single Operation may Provide Data and Evidence for an Effective Decentralization Strategy.In Mauritania, precedent local government projects targeted a limited number of local governments. In this project, the 100participating local governments represented a third of the national population and covered 10 of the 13 regions of the country.This project served as a laboratory for decentralization and showed local governments how to best deliver basic services. Thisproject helped develop critical tools that apply to all local governments, such as the performance evaluation system, includingauditing (with some simplification measures already discussed during project implementation, such as self-evaluation, to help withthe financial sustainability of the tools), the technical support system needed, including with procurement, and determining humanresource needs of rural local governments. The lesson from this project shows that performance assessment from a big enough samplemay identify customized capacity building tools such as the decentralized procurement regulations as evidence informulatingan appropriatedecentralization strategy. A gender action plan may be useful tofacilitate womens participation in capacity building projects. In this project, womens participation inlocal administration and local elective offices were mandated. Not very many women (16 percent) benefited from the trainingprograms inlocal administration funded under this project. Giving women voice may have been better guided by a gender action plan,presently included in investment projects financed by the World Bank. A gender assessment at closing may also help identifyspecific actionable steps for continuing to engage women in the area of local administration. The lesson from this project was thatgender action plan may prove useful in offering measures to give women voice in delivering improved services toconstituents. A low cap on the size of subprojects may improve a projects allocative efficiency but maydiscourage the financing of priority projects. In this project, water services and waste management were listed aspriorities during the consultative process of creating the Commune Development Plans. With a low cap on project size (the averagewas US$90,000), these projects were not tabled because of their inherent long gestation, longer periods of analyzing feasibility,and higher risks associated with environmental and social safeguards compliance. The lesson from this project was that establishinga cap on subprojects may be premature until informed by the priorities identified by the consulted beneficiaries.
P127585 | Tanzania Renewable Energy CDM Program of Activities | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2014 | 2024 | 2025 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099092024110520947/text/P127585-10f78dcc-81f6-4808-98da-2ee79dea3db4.txt | https://documents.worldbank.org/curated/en/099092024110520947/pdf/P127585-10f78dcc-81f6-4808-98da-2ee79dea3db4.pdf | The following lessons were derived from the ICR (based on ICR, pages 21-22):1. Designing an easy-to-implementmonitoring plan prior to project implementation is criticalfor the timely delivery of the expected project outcomes.The design of the reviewed Project did not account for the limited capacity of the SPP operators and the REA. The sub-projectdevelopers struggled to satisfy the quality requirements for emission reduction monitoring and certification, which resulted indelays in obtaining the CERs. This led to bottlenecks in the functioning of the Revolving Facilityand, ultimately, to theneed to reduce the Projects scope, as one-half of the potential sub-projects were not able to participate in the revolvingscheme. The Project could have taken these issues into account at the design stage by including capacity-building activities in theimplementation plan, thus creating a basis fortimely and proper monitoring and reporting by the sub-projectdevelopers.2. Designing an efficient stakeholder communication mechanismand usingit to provideinformation about the projects benefits early on is critical for timely project implementation and satisfactoryperformance. In the reviewed Project, having such a mechanism would have supported government ownership at the time whenthe change of government (and of policies towards the private sector) occurred by clearly communicating Projectbenefits.3. When developing a revolving fund in a country with a high investment risk, it is important to ensurethat risk estimates are sufficiently robust during project design.The reviewed Project intended to provide subsidiesthat would cover 5-10 percent of the sub-projects cost, with the assumption that itwould be enough tobridgetheequity gap; however, itwas an underestimate, as the sub-project developers were often unable to cover the rest of thebanks upfront capital requirement. More generally, the level of the financial institutions risk aversion in Tanzaniawas reflective of such critical factors as insufficient development of financial institutions, high risk of new businessdevelopment, and regulatory uncertainty. Developing a carbon finance project in such high-risk environment was challenging, and thereviewed Project was not able to fully mitigate these risks.4. SPPs area preferred option for developingoff-grid electricity in rural areas, thus providing significant economic and social benefits to the communities; and small powerproducers (SPPs) social and environmental responsibility can be essential for community trust and support.The reviewed Projects experience demonstrated that social and environmental (including water resource conservation)sustainability of the SPPsub-projects was an important factor in community support to the sub-projects and to the off-gridelectricity overall.
P127665 | Second Economic Recovery Development Policy Loan | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/403331475102055400/text/ICRR-Disclosable-P127665-09-28-2016-1475102046649.txt | http://documents.worldbank.org/curated/en/403331475102055400/pdf/ICRR-Disclosable-P127665-09-28-2016-1475102046649.pdf | The ERDPL2 ICR offers two valid lessons.TheBanks analytical work and fair advice (honest broker) facilitate policy dialogue within the administration, and canhelp support needed policy reforms in the country. This was reiterated several times by the government, which sought to keep theprogrammatic series in place, to ensure internal consensus for the reforms, and seeing the operation as a stamp of externalapproval for its reforms. Analytical work, sustained policy dialogue, and a Bank team in the fieldcan improve the quality of good design, and smooth processing of the operation, once there is political commitment for thereform.
P127676 | RUSSIA HYDROMETEOROLOGICAL SERVICES MODERNIZATION | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2014 | 2023 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111324150518515/text/P127676-ad8a7ea6-472c-47da-a540-4d21cd6ae20b.txt | https://documents.worldbank.org/curated/en/099111324150518515/pdf/P127676-ad8a7ea6-472c-47da-a540-4d21cd6ae20b.pdf | The following lessons were derived from the ICR (ICR, pages 28-29):1. Follow-up projects, anchored in theprecursor operations ME framework, offer a valuable opportunity to measure longer-term outcomes and validate the theoryof change. The reviewed Project followed the component structure and Results Framework of its predecessor, including thesame key outcome indicator (lead time of weather forecasts) over a cumulative time of 17 years. A long and consistent time seriesof data provided evidence of investment impacts and justified the mid-course activity corrections (including changes in thespecifications and scope of supercomputer procurement). This indicator was institutionalized by the borrower as an officialsectoral KPI to help guide the agencys further operations and development.2. An adaptive managementapproach is beneficial for the procurement of high-value ICT assets, with the systems integration taking precedence over thepre-identified individual procurement packages, even if it leads to delays in implementation. In the procurement ofhigh-value ICT systems (hardware and software), systems integration requirements are key, and an adjustment of individualprocurement packages to make sure system requirements are satisfied is often required, calling for adaptive procurement managementapproach. This is because the rapidly evolving technology and changes in sectoral regulations make it difficult to lock in largeICT procurement packages at start, and it may be preferential to revise and possibly delay the planned ICT procurement if anassociated systems integration solution is not yet ready. In such cases, postponed procurement can deliver higher-performing ICTassets (for example, supercomputers with more than double capacity) and help to avoid a premature installation of high-value ICTassets before the systems full operational readiness. The reviewed Project benefited from adaptive procurement managementand from hiring a systems integrator expert to supervise it, based on the lessons learned from the predecessorproject.3. In technically complex projects involving multiple reviews and revisions of the proposed solutions,clear guidelines and timelines for decision-making processes are critical for their efficient implementation. An up-frontagreement with the borrower on the terms of reference for the project management body, such as a steering committee, can bebeneficial. The reviewed Project experienced delays because such guidelines were not prepared: the PMCs terms of referencedid not spell out its performance standards, which allowed for delays in decision-making. Once the agencys senior leadershipinstituted clear and tight decision-making standards, the implementation sped up.
P127723 | Sao Paulo State Sustainable Transport Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099710003162236648/text/Brazil000Sao0P0le0Transport0Project.txt | http://documents.worldbank.org/curated/en/099710003162236648/pdf/Brazil000Sao0P0le0Transport0Project.pdf | IEG reports the following main lessons that the ICR draws from the experience of implementing this project, with some adaptationof language.1. The World Bank Groups guarantee products can help in leveraging public investments andmaximizing finance for development. This project included Multilateral Investment Guarantee Agencys(MIGA)guarantee as credit enhancement instrument which allowed additional private financing at favorable conditions. Thisadditional financing from international private lenders allowed the scope of activities to be scaled up. Such instruments canbe helpful to secureadditional resources for Banks client countries with access to funding from internationalsources.2. A multi-sector project can deliver better results in the long term but requires greater coordinationand capacity by the implementing agencies. Although most of the investments in this project aimed to rehabilitate roads,this was a multi-sector project that included critical aspects of road safety, environmental management and disaster riskmanagement. The project had as many as five implementing agencies. Burdensome bureaucratic processes of n some of the implementingagencies contributed to substantial delays during execution. The lesson is that centralizing in one Project Implementation Unit canhelp in avoiding thebureaucratic delays(In this project only the fiduciary responsibilities were centralized with theRoad Agency.3. Investment projects that close before civil works are fully completed or with pending safeguardsissues require a post-closing plan and a commitment from the client to carry it out. In this project, this requirement wasmade to the Sao Paulo State and the Bank continues to monitor progress on the pending safeguard issues.
P127734 | Tax Administration Modernization Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2016 | 2024 | 2025 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111524133519136/text/P127734-1b2e882e-aeab-400f-b744-6b2bad9f7a82.txt | https://documents.worldbank.org/curated/en/099111524133519136/pdf/P127734-1b2e882e-aeab-400f-b744-6b2bad9f7a82.pdf | The WBGs experience with the TAMP in Moldova highlights several insightful lessons noted in the ICR which IEG agrees with.This ICRR would like to offer one additional lesson: While reallocating funds for urgent needs, such as COVID-19relief, can provide immediate benefits, it can detract from core objectives, leaving critical reform areas, like tax modernization,unaddressed. With 80.0 percent of project funds initially allocated to IT infrastructure, acquiring a new integrated ITMS,and improving tax process, this project aimed to modernize the tax administration to improve tax collection and compliance.However, the projects disbursement pattern (10.0 percent over the first four years) indicated a lack of governmentcommitment to implementing key planned activities and achieving these objectives. Reallocating funds meant for critical structuralreforms to address urgent but unrelated needs detract from addressing critical development challenges.
P127743 | Rural Alliances Project II | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2024 | 2025 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099112124122068611/text/P127743-46305a54-048e-498c-90f2-d463ab2ad491.txt | https://documents.worldbank.org/curated/en/099112124122068611/pdf/P127743-46305a54-048e-498c-90f2-d463ab2ad491.pdf | The ICR included eight lessons. The following three lessons are emphasized:1. Adequate funding sources need tobe identified to fund complementary municipal public infrastructure investments in roads, bridges, and irrigation systems, whicharecrucial to improvesmall producers production and sales. PAR III accordingly includes municipal investmentsfocused on climate resilient, resource-efficient, and energy-efficient infrastructure. However, given the varying levels ofmunicipal fiscal capacity in Bolivia, the requirement for municipal cash counterpart contribution can severely limitparticipation in more vulnerable areas of the country. Alternative funding sourcesare needed formunicipalities withpressing need for such infrastructure to enable their participation. Options might include up-front OM agreements in lieu ofcash contributions, a sliding scale of contributions or, in the neediest cases, the Projects payment of 100%ofinfrastructure cost bearing in mind potential sustainability issues. While tangible contributions in cash are consistent with theprinciple of subsidiarity, thus avoiding potential distortions in a grant-based approach, solutions are needed to include poorermunicipalities.2. Aninstitutionalized, well-designed, and well-executed ME allowstimely, informeddecision-making. The projects Geo-referenced Management Information System (SIGG), used to plan, monitor, reportand control project implementation permitted timely, informed decision-making, and resulted in a large pool of good quality datainvaluable for the BCR, ICR and design/preparation of the follow-on PAR III. The Acompaantes played a crucial role in datacollectionand field input. Similarly, EMPODERAR has embraced high-quality, well-planned, and systematic IE with baselines,enabling repeat validation of the project methodology and approach over time and the confidence to innovate within an establishedand successful framework of support to SPO. The projects approach to ME demonstrates that establishing and sustainingsound ME practices and systems, and working with proven ME professionals, pays off and merits continued advocacy tosector teams and project leadership.3.The Alliance model can generate a triple win byincreasing production, decreasing the carbon footprint, and building resilience. The projects experience demonstratedthat thecombination of TA to adopt climate-smart agricultural technologies and practices, fixed investments to increaseproducers adaptive capacity, and ample resources for larger-scale municipal infrastructure explicitly designed tocombat/mitigate climate events, created a more resilient food production system with transformative and sustainable social andeconomic benefits. For future projects, climate resilience objectives could be considered to be explicitly stated in project PDOsand supported by activities capable of maximizing such impacts.
P127754 | Development Policy Operation 1 New Series | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2014 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/940691580226644344/text/Armenia-DPO-1-New-Series.txt | http://documents.worldbank.org/curated/en/940691580226644344/pdf/Armenia-DPO-1-New-Series.pdf | The following lessons are taken from the ICR with some modification of language by IEG.A series of 4 DPOs can often beexcessive. Changing conditions could necessitate significant changes to the program, which complicates design, implementation andevaluation. In Armenia, by the time the fourth DPO commenced circumstances had changed substantially compared with the first DPO.Armenian authorities indicated that two DPO series that each had 2 programs could have improved performance.Excessively broad PDOs complicate design, greatly increase the difficulty of effective implementation, complicate monitoring andmakes effective evaluation highly problematic. In the case of Armenia, the numerous changes the failure to translate triggers in apreceding DPO into prior actions in subsequent DPOs complicated achieving the targets of the program.Pressuresto disperse can compromise the effective implementation of a programmatic series. Furthermore, it can also lead to shortcuts beingtaken to comply with prior actions. This results in less effective or delayed reforms. In the case of Armenia, the pressure todisperse resulted in a tax law that contains many weaknesses, and laws and regulations in the mining sector that were not fullyeffective.IEG adds the following lessons.Undertaking numerous changes to results indicatorsand modifying targets greatly complicates both program implementation and evaluation. In the case of Armenia, widespread changes inresults indicators made the effective monitoring and evaluation of the program extremely difficult.Whendesigning a Monitoring and Evaluation Framework, it is important to ensure that the indicators relate to outcomes and not toinputs. In the case of the Armenia DPO series, numerous indicators measured inputs.If a DPO series has an overarchingobjective, including indicators that provide information on whether it is being achieved strengthens the evaluation of its success.In the case of Armenia, job creation was the overarching objective, but there were no indicators containing employment data
P127759 | IRRIGATION SYSTEM ENHANCEMENT PROJECT | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/400361607353170688/text/Armenia-IRRIGATION-SYSTEM-ENHANCEMENT-PROJECT.txt | http://documents.worldbank.org/curated/en/400361607353170688/pdf/Armenia-IRRIGATION-SYSTEM-ENHANCEMENT-PROJECT.pdf | The ICR provides 4 detailed lessons, of which the following lessons are retained (with languageadapted):Support for the enhancement of irrigation systems needs to integrate water delivery with servicedelivery. In Armenia, where a minimum level of irrigation infrastructure is available, support to the irrigation sectorhas traditionally focused on improving water delivery. However, water delivery cannot be addressed without addressing servicedelivery or water rights governance at the same time. The development of the irrigation sector needs an integrated model thatcombines investments in infrastructure to improve water delivery with investments in improved service delivery and water-rightsgovernance at different levels of water users. Moreover, irrigation development needs to incorporate institutional strengtheningwhen the sector-wide institutional reform in the irrigation sector is still in a relatively early stage of development. In thisproject, however, there is no mention of the quality, uptake, and impact of service delivery, and therefore it provides no evidenceon whether the rehabilitation of the irrigation system enhanced the irrigation sector as a whole inArmenia.Projects investing in irrigation infrastructure need a feasibility phase to understand and adapt theproposed solutions to the on-the-ground realities of the topology, local capacity, and social context of the irrigationinfrastructure. The most significant design flaw of this project was the lack of on-the-ground feasibility study of thecondition of the irrigation infrastructure and network as well as a limited understanding of the needs and perceptions of thedifferent stakeholders involved.Site selection for irrigation development need to look beyond the agroeconomicbenefits of an irrigation scheme and include the perception and concerns of all stakeholders (within and around the irrigation scheme) that rely on the same source of water. Local communities in and around the water source of two targeted schemes raisedconcerns about broader-level water availability and the impact of the infrastructure works on the environment as well as culturalheritage. These complaints by local communities illustrate the obvious need to involve all local stakeholders in decisions on whereand how to develop irrigation sites.
P127764 | SOUTH KARAKALPAKSTAN WATER RESOURCES MGMT IMPROVEMENT | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2014 | 2024 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062824135023147/text/P127764-a79d48fc-584a-4412-94a6-23cb9772316b.txt | https://documents.worldbank.org/curated/en/099062824135023147/pdf/P127764-a79d48fc-584a-4412-94a6-23cb9772316b.pdf | The review has drawn three lessons from the project:Stakeholder engagement and consultations with beneficiariescan inform realistic intervention models. The project faced challenges in introducing mechanized cotton harvesting due tolow farmer acceptance. Recognizing cultural and institutional norms can be crucial in balancing ambitious targets with practicalconsiderations. Thorough stakeholder engagement and realistic assessments of on-the-ground demand and capacity may enhance theeffectiveness of future projects.When social inclusion measures in community development organizations are limitedto participation quotas, an incomplete understanding of actual inclusion can result. Although the project established aquota for womens participation in farmer field schools and WCAs, it was unclear if this led to meaningful representation,voice, and decision-making role. When project interventions and monitoring benchmarks are limited to tracking participation alone,the deeper aspects of inclusion, such as agency, may be left unaddressed. This highlights the importance of evaluating not just thepresence but the active engagement and influence of marginalized groups within these organizations.Beneficiarysurveys can serve as a valuable tool for triangulating evidence and complementing the results framework. Projects have alimited number of results indicators to track both implementation progress and capture outcomes toward the achievement of the PDO.Supplementing these indicators with additional sources of information, such as national data, impact evaluations, and beneficiarysurveys, can provide a more comprehensive understanding of project impacts. In this project, beneficiary surveys were conducted attwo critical points, covering a large sample size, which provided valuable insights into outcomes such as income changes, cropdiversification uptake, water availability, and other aspects of the theory of change. This approach enabled a deeper analysis ofthe projects effectiveness and helped to validate the reported results.
P127775 | China Guangdong Agricultural Pollution Control | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2021 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060623110516648/text/P127775053dfc207d0849a02102cdf0f905.txt | http://documents.worldbank.org/curated/en/099060623110516648/pdf/P127775053dfc207d0849a02102cdf0f905.pdf | The ICR presents six relevant and sound lessons, supported by project experience, which have broader application beyond thisproject, for China and other countries. Below are strategic aspects of the 4 more important lessons (ICR, paras. 89 94).Lesson 1: An integrated approach involving both livestock and crop management is needed to effectivelydemonstrate a rural circular economy. The project integrated investments in LWM facilities and environmentally friendlycrop production systems and also provided technical assistance and capacity building to pig farm owners and smallholder farmers. Asa result, the project was able to effectively demonstrate a rural circular economy in which treated livestock manure and waste isused to replace chemical fertilizer use, thereby reducing GHG emissions and NPS pollution.Lesson 2: Subsidies playa critical role in helping reduce risk of adopting new technologies and practices by small-scale farmers. Smallholderfarmers willingness to participate andadopt new technologies and practices such as those related to agriculturalpollutant reduction depends largely on financial incentives provided in the first few years to help farmersmanage theirinvestments and associated risks. In addition, sufficient financial profitability, which enabledtemporary subsidies giventheir public good features,was critical for the new technologies and practices to be sustained and upscaled in GuangdongProvince and nationwide.It was also vital to ensure sound and explicit rationale for the subsidies (e.g., sound farmerincentives and positive externalities to improve water quality/ICR, para. 16, and Annex 4 for details), and a clear phase out planto ensure sustainability.Lesson 3: Digital agriculture tools facilitate targeting of support to farmers andmonitoring of beneficiaries and input suppliers. Simple but innovative application of the Identification Card (IC) cardsystem in procuring and financing agricultural inputs and services enabled the project to target the delivery of subsidies tosmallholder farmers, which significantly improved the projects implementation efficiency, ME, and the transparencyof project interventions.Lesson 4: Local academic and research institutions can provide fit-for-purposetechnical solutions to farmers. By closely working with the most relevant academic and research institutions, the projectwas able to develop, pilot, and adopt methodologies for monitoring and measuring the reduction of pollutants entering waterwaysfrom crop production systems. In addition, relevant institutions helpedsustain the effective and improved application oftechnologies andmonitoring processes.
P127787 | Competitiveness and Savings Development Policy Loan (CSDPL) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/151221468178188137/text/ICRR14861-P127787-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/151221468178188137/pdf/ICRR14861-P127787-Box394823B-PUBLIC.pdf | IEG draws the following lessons:Â· A single-Tranche DPO may not achieve significant progress towards outcomes such as competitiveness and savings behavior because effective reform implementation takes time, further reforms may be needed, and necessary changes in the behavior of economic agents also take time. Indeed, objectives may take a long period of time to be achieved. Turkeyâ€™s World Economic Forum competitiveness scores in the areas covered by the DPO (efficiency in goods and finance) has made little or no progress since at least 2007, when the Bank started a series of DPLs covering growth, competitiveness, and employment.Â· A poor definition of objectives will undermine the focus of a DPO on development outcomes. Some of the DPO sub-objectives (on the CML and NBFI regulations) were inadequately defined by focusing on regulatory outputs, not on development outcomes. Furthermore, the limited scope of the indicators in the DPO (e.g., selected Doing Business indicators), which reflected the limited scope of the reforms the DPO supported, was not well-tailored to the broad scope of the objectives (boosting competitiveness).Â· Monitoring changes in investments in various financial instruments (pensions, capital market, non-bank institutions) will not indicate progress in the domestic savings rate. They may reflect portfolio shifts instead and include external sources of saving.
P127807 | Tax Administration | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/572111599335343738/text/Tajikistan-Tax-Administration.txt | http://documents.worldbank.org/curated/en/572111599335343738/pdf/Tajikistan-Tax-Administration.pdf | Three lessons are drawn from the ICR (pages 26-27), with some adaptation.Havingafunctionalintegrated tax management information system is a keyelement in tax administrationreform. In this project, an off-shelf ITMIS was procured and customized to meet the Tax Committees businessprocess requirements. It was also installed over a phased implementation period, allowing for learning. According tothe ICR (page 26), the off-shelf package was theappropriate information technology solution (despite the Tax Committeespreference for an in-house solution) as the implementing agency had limited technical capacity and was not fully equipped for anre-engineering task. Moreover, the non-proprietary solution offered a source code for future software modification, animportant feature for the sustainability of the IT system moving forward. However it is acquired, an ITMIS is critical to themodernization of tax administration. According to the PAD (pages 10-11), the ITMIS was included in this project, having beenan important part of successful tax administration reform efforts elsewhere.Projects with complex ICTactivities should be providedlonger lead times for preparation and implementation, as well as more robust technicalassistance. In this project, the Bank provided expert technical adviceand assistance to the Tax Committee forthe ITMIS procurement, including with writing technical specifications and preparing terms of references for services(seeSection 8.B). Still, the procurement process was delayed. Beyond procurement, a comparatively longer implementationperiod is also necessary for the design and implementation of an ICT system, including for testing, calibration,andreconfiguration, if necessary. It also takes time to build up capacity among government staff toworkwith digitaland computer systems. According to the ICR (page 27), it was ambitious to complete this project in five years, the originalimplementation period.With tax administrationmodernization being an ongoing concern, itwould be optimal for governments toplan for broadening and deepening tax administration reforms in the medium- tolong-term. In this project, with the Tax Committee having acquired basic digital literacy with an ICT-backed system,the government may well consider the next steps to strengthening its tax administration system. The ICR (page 27) listsvarious next-generation measures that the government can consider: (a) a compliance risk management tool; (b) reductions in advancetax payments; (c) a more independent and transparent Appeals Body; (d) the increased use of automated procedures to select taxaudits; and (e) annual taxpayer surveys.
P127813 | Coral Reef Rehabilitation and Management Program - Coral Triangle Initiative (COREMAP-CTI) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2014 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099082323175036010/text/P1278131fa844c541f2c6141561bc4e1b3a4c64f0869.txt | http://documents.worldbank.org/curated/en/099082323175036010/pdf/P1278131fa844c541f2c6141561bc4e1b3a4c64f0869.pdf | The ICR (paras 112-117) presented six lessons. Two of them are presented below rephrasing as these might be relevant for thefuture operations aiming to achieve coastal ecosystem conservation through community-based management.COREMAPcould have benefited from activities related to establishing long-term operational financing to ensure the legacy of the COREMAPapproach beyond the lifespan of the project. The government recognizes this need and has prioritized the establishment ofa blue finance regulatory framework and potentially an instrument to support the financing of MPA management and the livelihoods ofcoastal communities. These needs will be addressed in the World Banks recently approved US$210 million Oceans for Prosperity LAUTRA Project (P13391).COREMAP leveraged developmental partner financing to scale up impacts and workedtogether with partner organizations for a strong development outcome. Combined financing from the Bank and donor partnerswas integral to COREMAPs success, and the World Bank-financed activities were replicated with financing from other partners inother parts of Indonesia. Knowledge exchange for project implementation was fostered through joint missions and the exchange ofaides-mmoire among developmental partners.IEG draws the following additional lesson from thisproject.COREMAP-CTI discontinued COREMAPs community-centered approach due to the shift in coastal resourceauthority from district to provincial levels of government by Law 23/2014, diminishing the outcomes achieved through theprograms long-term engagement. The preceding operations in the COREMAP programmatic series facilitatedcollaborative and community-based management of coastal ecosystems by involving district and community institutions, which alignswith the objective of decentralizing the management of coral reefs and associated coastal ecosystems. COREMAP-CTI cancelled thecommunity-based management activities, making a drastic shift in its approach for improving coastal ecosystems management.Considering that the succeeding LAUTRA project reintroduced the community-driven development approach to the project design again,further research and analysis would be needed to better understand the context and background of the suspension of thecommunity-centered approach in the post-restructuring COREMAP-CTI.
P127822 | Second DPL in support of the Plan Maroc Vert | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/571301467987909640/text/ICRR14830-P116557-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/571301467987909640/pdf/ICRR14830-P116557-Box394823B-PUBLIC.pdf | IEG supports the three lessons identified in the ICR, has rephrased them below:(i) Incentives for for stakeholders: In the case where incentives for the Finance Ministry and the sector ministry are aligned, the synergy is powerful. In these circumstances, the Bank can still add considerable value beyond just resource transfer by further analytic work to help finalize and operationalize the program and to prepare for its implementation;(ii) Ownership/Coordination: An additional value of Bank support using a DPL operation is to help create a platform for agencies collaboration that otherwise may have divergent agendas. The Bank can also contribute to transparent, evidence-based and objective dialogue around thorny issues, including political economy constraints to reform implementation.(iii) Value added of DPLs and MTEF: The linking of a DPL to a sectoral MTEF aligns incentives for both the Finance Ministry and the line ministry, and provides investment resources to accompany and help implement reforms that otherwise might not take place or might not yield their intended returns.
P127837 | Access and Renewable Energy Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/918511593554421429/text/Bolivia-BO-Access-and-Renewable-Energy.txt | http://documents.worldbank.org/curated/en/918511593554421429/pdf/Bolivia-BO-Access-and-Renewable-Energy.pdf | Rural electrification projects implemented in remote areas and under difficult physical conditions require effectivecoordination among a multiple number of actors. The lesson from this project is that the implementing agency needs to befully operational from the early stages of the project to minimize delays during implementation.Decentralizedmodels for rural electrification require efficient coordination between the national and subnational agencies. Theexperience from this project showed that hybrid models, where the two-level agencies share executive and financial roles(particularly the ownership of assets and debt obligations), added to the complexity of the implementation process. The lesson fromthis project is that given the challenges of a decentralized policy it is preferable to that the project needs to be executed,either at the national level or at the subnational level.
P127861 | JO-Badia Ecosystem and Livelihoods | Middle East and North Africa | Jordan | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/886811525715605259/text/Jordan-JO-Badia-Ecosystem-and-Livelihoods.txt | http://documents.worldbank.org/curated/en/886811525715605259/pdf/Jordan-JO-Badia-Ecosystem-and-Livelihoods.pdf | Lessons that can be drawn from this project, partly taken from the ICR,are:(i)A straightforward andeasily implementable project design is especially important in environmentally and culturally sensitive areas. In thiscase, the projects relatively simple design took these characteristics into account and contained appropriate interventionsboth in terms of local ecological differences and the nomadic nature of part of the beneficiary population.(ii) Inproject areas where local culture can make full project participation by women problematic, there is aneed to carry outthorough assessment oflocal cultural and other constraints to the achievement of the gender objectives and targets.In this case, the difficulty in fully attaining the gender targetas a result ofcultural resistance was underestimatedand thus, in retrospect, proved to have been overly ambitious.(iii) In a community participation project, it isparticularlyimportant for success and sustainabilityto provide adequate resources up front tobuild beneficiaryconfidence and participation in project decision making. In this case, the need to build trust was essential and theprojectsability to doso was a contributing factor to its successful, if somewhat delayed,implementation.
P127867 | China: Qinghai Xining Urban Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2022 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099155006292238131/text/P1278670c4bec904008c5009cd151294ba3.txt | http://documents.worldbank.org/curated/en/099155006292238131/pdf/P1278670c4bec904008c5009cd151294ba3.pdf | The following lessons are drawn from the ICR (paragraphs 108 110), withsomeadaptation: Close collaboration with stakeholders is critical for introducing innovativesolutions such as integrated corridor management, intelligent transport system, and electric public transport fleet. TheXining Municipal Government (XMG) and thePMO had no prior experience with the new technology. The Bank team closelycollaborated with the client in helping the selection ofthe right technologies and approaches through workshops and effectivepreparation and implementation support, so that the PMO could more easily adopt the newtechnologies. Using Social Network Services (SNS) based communications for official documentrepository and Grievance Redress Mechanism (GRM) can improve efficiency and accountability of the World Bank and itsclients. In this project SNS Mobile Apps were used for frequent communication and improved the efficiency of transmittingproject related data and files such as texts, audios, videos, documents edited on mobile phones, and geocoded data for GeographicInformation System-based technologies, even in contexts where computers and broad band internet were not available. Supervision ofthis project especially toward the project closing, including the preparation of the ICR, utilized SNS extensively in communicatingand transmitting data with the PMO and among team members.
P127876 | SERBIA ROAD REHABILITATION AND SAFETY PROJECT | Europe and Central Asia | Serbia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2021 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/189721624990107107/text/Serbia-ROAD-REHABILITATION-AND-SAFETY-PROJECT.txt | http://documents.worldbank.org/curated/en/189721624990107107/pdf/Serbia-ROAD-REHABILITATION-AND-SAFETY-PROJECT.pdf | The ICR draws the following fourlessons from the experience of implementing this project, presented with some adaptationof language.1. Amodest hybrid approach in introducing Performance-Based Management Contracts (PBMCs) can beeffective in countries with capacity considerations. The hybrid approach wasintroduced gradually in thisprojectas capacity was builtlocally for usingPBMCs. The PBMCs were implemented eventually.The hybrid typeof PMBC combined features of both method and performance-based contracts. Such an approach can be useful in countries with weakcapacity at the outset.2. Procurement arrangements needs to be carefully considered at preparation in co-financedprojects.This project experienced significant delays in procurement due to the need to secure two-objections (onefrom the Bank and one from the European Investment Bank (EIB). The ICR notes that although the Bank team thought that they hadreached an understanding with the EIB on procurement arrangements, it failed in implementation.A lesson is that the teams atthe preparation stage co-financiers should agree and document theprinciples ofcollaboration between the institutions,and ideally delegateprocurement decisions to one of the institutions. Since this will likely not be thelastcollaborative project, principles of collaboration between the institutions should be pursued with senior management and agreementreached at design for future projects.3.When deciding on whether to use the Disbursement-LinkedIndicators (DLI), several factors need to be considered, i.e.,assessing whether the Bank and theclient havethe required experience, and whether there aresufficient Independent Verification Agents (IVA).4.Given frequent and intense climate events in a country, it is important to include climate resilient infrastructure in projectdesign to minimize vulnerability ofphysical assets to natural hazards. In May 2014, a state of emergency wasdeclared in Serbia after the heaviest rain and worst floods since records began 120 years ago. The cross-sectoral coordinated workby the Ministry of Transport, the Ministry of Emergency and other bodies was key in responding to the events, and extended to theintegrated planning and preparedness.It would be also useful to include the Contingency Emergency ResponseComponent(CERC) in transport projects to enableimmediate response to emergencies.
P127949 | AFCC2/RI Horn of Africa Emergency Health and Nutrition Project | Other | Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2013 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/162281475074832094/text/000020051-20140626121049.txt | http://documents.worldbank.org/curated/en/162281475074832094/pdf/000020051-20140626121049.pdf | UNHCR as an implementing agency of an emergency relief project can generate substantial efficiency gains. A project can benefit from UNHCR's well - established supply chains and leverage economies of scale in procurement that would not be possible through a separate stand-alone project. The possibility of retroactive financing can encourage and enable rapid implementation start-up in an emergency response context.This operationâ€™s Board waiver enabled substantial policy exceptions to standard IDA lending terms, which granted the operation substantial flexibility. An emergency response project can benefit significantly from such flexibility in terms of rapid preparation, efficient implementation, and achieving results. Support to refugee camps may entail important spillovers to nearby communities. An emergency response project could benefit by anticipating such during project design.
P127955 | Solid Waste Sector DPL3 | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2013 | 2014 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/861761491230125301/text/Morocco-MA-Solid-Waste-Sector-DPL3.txt | http://documents.worldbank.org/curated/en/861761491230125301/pdf/Morocco-MA-Solid-Waste-Sector-DPL3.pdf | The Lessons are derived from the ICR document with some modification of language.1 . Sector reform takes time:reforms should start simple and gradually get more complex. There is a greater chance to succeed with more complex reformsif tangible results from simpler reforms are present first.2 . Focusing on improving systems rather thanjust training is more effective in achieving long-term results. Capacity building and training should bedesigned to improve the performance of a system and not only of individual skills.3 . WorldBank-supported reforms should be fully aligned with Government priorities for greater success.4 . In theright context, the use of DPL in sector reforms can be a very effective instrument. The DPL instrument can offer analysis,a reform planning framework, implementation support, and convening power by the World Bank while maintaining full governmentleadership and ownership of the reforms themselves.5 . Providing Local Governments with responsibility over theentire Municipal Solid Waste chain at the local level is a key lesson for success. Responsibilities for collection anddisposal of solid waste are often fragmented across several administrative boundaries.The experiencesuggeststhatgreater success can be achievedwhen responsibility of the entire system at the local level (collection, streetcleaning, disposal, recycling, etc.) is concentrated under one entity.
P127956 | MA-Inclusive Green Growth DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2014 | 2015 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/195211534374058319/text/Morocco-MA-Inclusive-Green-Growth-DPL.txt | http://documents.worldbank.org/curated/en/195211534374058319/pdf/Morocco-MA-Inclusive-Green-Growth-DPL.pdf | Several lessons highlighted in the ICR are important andare consistent with thosein IEGs own recent assessmentof environmental DPLs:1. Government ownership at all levels is essential to ensure effective implementationof policy reforms for green growth. As the ICR (para. 122, pg. 30) stated, this is demonstrated by the DPL thatincluded the concerted effort of several agencies including the MEF, MAGG, MAPM, MEMDD (Ministry of Energy, Mines, and SustainableDevelopment) as well as national agencies, such as the Moroccan Agency for Tourism Development; National Aquaculture DevelopmentAgency (ANDA), and Oum Er Rbia River Basin Agency (ABHOER).2. In-depth knowledge of the country and sectorsis a key factor for ensuring adequate design of an operation and its successful implementation.The ICR (para. 124,pg. 30) adds in this regard that the ongoing dialogue that the World Bank already had in Morocco, coupled with the extensiveupstream and sectoral analytical work have contributed towards adequate design in terms of the selection of prior actions; outcomeindicators and targets....; and for issues that need attention from high-level decision makers, especially in finance and planningministries.3. Supporting the DPL with Advisory Services and Analytics (ASA) and investment project financingcontributes to successful implementation of policy and sectoral reforms and achievement of outcomes. The ICR (para. 125,pp. 30-31) observes, more specifically, that this DPL series has been well supported directly and indirectly...through ASAand investments, including grants, for example, a Multi-donor Trust Fund (MDTF) grant for ASA and support dialogue; MDTF support tothe ABHOER; GEF grant for integrated coastal zone management (ICZM); Partnership for Market Readiness (PMR) ASA on energyefficiency in buildings; and a grant from the EU Climate Change MDTF to support technical assistance activities onagro-meteorology, green taxes, groundwater governance component, and ICZM.To these can be added:4.Effective DPLsinvolvingactions in various sectors require a strong coordinating mechanism as well as adequate ownershipof the policy reforms and actions by the participating sector institutions. This too was an important lesson drawn fromIEGs recent review of environmental DPLs which clearly applies to this programmatic series as well.
P127966 | Kazakhstan - Youth Corps program | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099200003242318901/text/P12796600430f70d10a76c009cfd6c66e07.txt | http://documents.worldbank.org/curated/en/099200003242318901/pdf/P12796600430f70d10a76c009cfd6c66e07.pdf | The ICR (p. 24-25) provided several lessons learned, which were adapted by IEG: Measuring communityengagement and life skills can be challenging due to measurement tools relying on self-reporting and the lack of benchmarking.This project developed a synthesis report to provide additional data and allow for triangulation of evidence.However, even the synthesis report had to heavily rely on self-reporting. Including commercial activity insub-project grants for community support may increase the likelihood of sustainability. Although project grants were notintended to include commercial activities, approximately one third of sub-projects continued after project closure. This findinggenerated an ICR recommendation suggesting that future operations can include sub-projects with both commercial and non-commercialactivities to increase the sustainability prospects of sub-projects. Developing a rigorous targetingmechanism is critical for ensuring that the most vulnerable beneficiaries are being reached. This project used a targetingmechanism that reduced the possibility of a selection committee influencing the selection outcomes.
P128012 | Bangladesh Ghorashal Unit 4 Repowering Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2024 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062724184037816/text/P128012-df3c3a25-e394-446c-a3d3-3658e937d0be.txt | https://documents.worldbank.org/curated/en/099062724184037816/pdf/P128012-df3c3a25-e394-446c-a3d3-3658e937d0be.pdf | The ICR presented several lessons, of which the two below (with paraphrasing by IEG) had the most prospects for broaderapplication and replicability.Focusing on the political economy and market analysis is essential during projectdesign and preparation. Although the replacement of high-cost liquid fuel was a major benefit of the project, it was onlypartially achieved due to major political economy factors. First, whereas there was an undersupply 3,000MW of electricity duringthe preparation stage, there was an oversupply of 10,000MW at project closing. Second, there were issues with thegas supplyshortage.Third, theuse of private sector generatorsinvolved costly capacity payments and are very likely to benon-compliantwith the merit order dispatch policy due to other vested interests. While there is already a merit orderdispatch policy in place, it appears that it is not strictly followed due to inefficiencies in its implementation system, whichdetracted from implementation success and the achievement of project outcomes. These highlight the need for greater focus on thepolitical economy and market analysis as early as the project design stage. Much earlier and greater emphasis on analyzing marketmovements would also help to encouragestudies on upstream gas supply and to identify measures to mitigate potential risks todownstream demand. Finally, new reforms and concrete measures are needed to link economic dispatch to SCADA so that inefficienciesin the dispatch process are removed.In low-capacity environments, the use of an Independent Procurement Panel(IPP) could be considered but needs to be matched with the country clients full ownership. While theprojects use of an IPP was a generally successful story, it contributed to the clients lack of ownership. Whereapplicable and needed, the use of independent experts could be considered to providetechnical and procurement advice to theclient during the procurement process.
P128013 | MH: First ICT Sector Development Operation | East Asia and Pacific | Marshall Islands | IDA | FCS | Infrastructure | Transport | IDA | DPF | 2013 | 2014 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/316191498832815061/text/ICRR-Disclosable-P128013-06-30-2017-1498832808311.txt | http://documents.worldbank.org/curated/en/316191498832815061/pdf/ICRR-Disclosable-P128013-06-30-2017-1498832808311.pdf | There was a lack of borrower readiness for a development policy operation in the ICT sector. The delays andpolitical opposition to reforms in the ICT sectorhighlight the difficulties of such sector reforms and the challenges ofopening monopolies to competition. A thorough political economy assessment is an essential tool to support ambitiousreform programs. The interests of incumbent monopolies, especially private shareholders, management and workers, capacity issues,and government readiness all play a role. The robustness of the governments consultation and decision making processes alsoneed to be evaluated carefully, especially to avoid situations where a lack of information, or misinformation, may be used byopponents to undermine the credibility or desirability of reforms. Political economy issues or concerns may be aggravated if theGovernments decision-making processes are weak and consultation processes are ineffective, especially in countries whereshared decision- making is favored. The Bank needs to undertake realistic assessments of the political economy situation and ensurethat operations include actions to resolve likely areas of opposition or resistance Thoroughriskidentification and mitigation is essential in sector reform. The two key risk factors that caused the Program tofailweak capacity of the public sector and opposition from the incumbent operator to sector reformslean against theuse ofthe DPO instrument, with its basis of policy and institutional actions as conditionality. In this context, closeimplementation support or capacity building by the Bank might have added to misconceptions on the part of opponents that reformswere being forced by the Bank. In countries with high budget deficits and related macroeconomic weaknesses, DPOs can createincentives to commit to unattainable reforms in order to trigger the release of budget support, notwithstanding a lack of readinessor consensus among key stakeholders. Public sector capacity constraints are especially challenging to deal within the context of a DPO. Sufficient capacity and sustained commitment are necessary to deliver on reforms. There needs tobe strong linkages between the DPO and associated technical assistance. In this case the failure of the TA inter alia led to thefailure of the program.
P128023 | First Governance and Competitiveness Development Policy Operation | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/473731498832876028/text/Sao-Tome-and-Principe-STP-DPO-PROGRAMMATIC.txt | http://documents.worldbank.org/curated/en/473731498832876028/pdf/Sao-Tome-and-Principe-STP-DPO-PROGRAMMATIC.pdf | IEG concurs with the three findings and lessons spelt out in the ICR, whichemphasized: (i) the importance of thecoordinating role of the Government, whichensures that all key partners are aligned behind the reform agenda supported by theDPO, (ii) the central role of theimplementing agencies, whose mission is to track day to day progress toward outcome, andfinally (iii) the limited budget allocations to small countriesare a handicap for more Banks engagement and efficacy onthe ground.Most importantly, IEG finds that the key lesson from the implementation of this program isthatefficacy of a DPOfollows to a major extentthe Governments seriousness and commitment to reform. Itisthe above engagement that generates the support of both internal and external stakeholders, and makes possible anappropriate tracking of thedaily implementation and any needed correction.
P128048 | Afghanistan Access to Finance | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099445006092210224/text/P12804806e8db905c0a0330c23d99ff8f3b.txt | http://documents.worldbank.org/curated/en/099445006092210224/pdf/P12804806e8db905c0a0330c23d99ff8f3b.pdf | The following two lessons are taken from the ICR with some adaptation of language:Provision of productiveassets, training, basic health can increase the development impact of financial aid to ultra-poor households in helping them engagein income generating activities and bringing them out of poverty. The evidence from the project confirms the globalexperience that for a significant development impact, programs, such as TUP, need to combine financial means with productiveassets, training and basic health. The project provided in-kind and financial assistance together with training and basic healthcoverage to 12,698 households. Eighty eight percent of these households started generating sufficient income that they dropped outof the social safety nets. Additionally, 64 percent of them had interactions with microfinance institutions. According to theimpact evaluation conducted at project closing, the share of households below the national poverty line decreased by 20percent.Lack of project implementation and institutional capacities of the counterparts can adversely impactproject achievements. Although this is a generic lessons-learned, the experience gained in this project once againshowed that project implementation capacities of the agencies are critical in achieving project outcomes; hence, projectobjectives. implementation by delaying completion of necessary processes and progress. At appraisal, the capacities of the projectimplementation agencies were not adequately assessed. While a detailed procurement plan was prepared at appraisal, the projectimplementation agencies had significant difficulties in managing complex and large procurement packages in accordance with theBanks procurement rules. This led to a delayed start of project activities under Component 1 adversely affecting theprojects efficacy and efficiency. Furthermore, the Ministry of Finances lacked sufficient understanding of the creditguarantee facilitys functioning. Coupled with high staff turnover and difficult political environment, this contributed tothe delayed signing of the Implementing Partner Agreement and lower achievement of project outcomes related to the guaranteefacility.
P128072 | VN - Central Highlands Poverty Reduction Project (CHPov) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/961581624414400367/text/Vietnam-VN-Central-Highlands-Poverty-Reduction.txt | http://documents.worldbank.org/curated/en/961581624414400367/pdf/Vietnam-VN-Central-Highlands-Poverty-Reduction.pdf | The ICR (p. 26 to 28) included several lessons learned, which were adopted by IEG: Establishing strongand formal institutional linkages across all participating entities is critical for ensuring the sustainability of projectoutcomes. The project financedthe private sector to fill a technical assistance gap left by relevant agriculturedepartments. However, the sustainability of this arrangement was not fully addressed byproject close. Enabling strong supervision of local works through community members and technical expertsallows for higher quality outcomes and stronger local ownership. In this project, Commune Supervisory Boards receivedbasic training for supervising civil works. In addition, a technical supervision firm conducted technical reviews and spot checksat the provincial level and larger works contracted by districts. Furthermore, a supervising engineer oversaw all works that weredirectly implemented by the community but contracted out. Despite all these measures, the project faced quality issues indicatingthat linkages between different supervision entities were not sufficiently strong. Reaching the most isolated EMgroups requires specialized outreach activities and language skills. The local authorities in this project facedconstraints in their ability to reach and support more isolated communities. However, through specialized outreach activities theproject was able to obtain high participation from women and indigenous EM groups.
P128096 | Pakistan: Promoting Girls' Education in Balochistan (PGEB) | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2013 | 2015 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/135741468020159426/text/ICRR-Disclosable-P128096-07-08-2016-1468020140563.txt | http://documents.worldbank.org/curated/en/135741468020159426/pdf/ICRR-Disclosable-P128096-07-08-2016-1468020140563.pdf | Lesssons drawn by the ICR, adapted by IEG: Implementation in clear partnership with the government contributessignificantly to the sustainability of operations and the rebuilding of trust among citizens. In the case of this project,the governments direct involvement led to its adoption of several project processes (school site identification andtest-based teacher selection) and the absorption of contract teacher salaries for at least oneadditional year after projectclosing. The transparency of these processes also helped to restore citizen trust in governmentservices. Preparation of alternative monitoring arrangements helps to ensure continuous implementation despiteavolatile security situation. In the case of this project, the use of third party monitoring and satellite technologyplayeda critical role in project implementation and monitoring.
P128140 | MU -Second Public Sector Performance DPL | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/402661467987847004/text/ICRR14811-P125694-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/402661467987847004/pdf/ICRR14811-P125694-Box393228B-PUBLIC.pdf | The first two lessons are drawn from the ICR. The third is drawn by IEG. In an environment where the reform agenda may be challenging, it may be better to focus on areas that can draw consensus to move forward. In Mauritius, the DPL focused on achieving short term gains to build consensus in a situation with multiple stakeholders.Strengthening social protection and improving competitiveness can be mutually reinforcing. The immediate social effects of efficiency-enhancing trade reforms can be mitigated by a stronger safety net that alleviates adverse impacts on vulnerable groups or individuals, if appropriately coordinated. Monitoring and evaluation needs particular focus in development policy operations. Such operations may include broad institutional changes where outcomes may be difficult to observe in the short term. Under such circumstances appropriate proxy indicators might be developed â€“ for instance combining partial quantitative outcomes with changes in internal processes to establish that changes are having tangible positive results.
P128201 | BT: DPC 2 | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/185681473933127833/text/ICRR14945-P113069-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/185681473933127833/pdf/ICRR14945-P113069-Box396299B-PUBLIC.pdf | This assessment suggests the following two lessons:1. A two year DPC Program focusing on a limited number of actions of doubtful criticality, and with modest technical capacity in Government is unlikely to achieve much progress in achieving welfare results. If these are to materialize later, such programs need follow-up by complementary actions that may help to yield a return in the shape of measurable economic outcomes.2. Monitoring of progress in a DPC will be difficult when baselines and targets are reflected by indicators that do not clearly quantify an achievement. Under the Bhutan DPOs, baselines and targets were enumerated in a way that would not be expected to measure adequately the extent to which an intended outcome was to be achieved. As a result, the extent of progress towards these could not be properly assessed.
P128208 | SL Public Sector Pay & Performance | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2018 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/834831565013528659/text/Sierra-Leone-SL-Public-Sector-Pay-Performance-FY12.txt | http://documents.worldbank.org/curated/en/834831565013528659/pdf/Sierra-Leone-SL-Public-Sector-Pay-Performance-FY12.pdf | The first three lessons are taken from the ICR, with some adaptation of language, and the fourth is drawn byIEG: Alertness to incentivescan influence collaboration in results-based lending. Teamsneed to assess the incentive effects of individual DLIs on agency collaboration. In the Sierra Leone case, the client notedthat the pay-off was a public good and achieving DLIs was unlikely to result in any proportionate budget increase for the agenciesconcerned. Changing country circumstances can affect project outcomes. Teams need to assess theeconomic and political circumstances that may disrupt project design and require adjustments, for instance during mid-termreviews. In Sierra Leone, the project could have benefited from an early realization of the implications on civil servicereform of changingfiscal space. While focusing on DLIs, the results framework is alsorelevant. An exclusive focus on DLI sequencing when managing a DLI-based project may not sufficiently define thereform path. In Sierra Leone, a greater focus on the results framework and intermediate indicators might have better broughtforth issues on the feasibility of certain reforms. It might have better focused the teams attention to changes in theresults framework as DLIs were being adjusted (during the 2014 revisions). Introduction of new lendingmodalities, with which Bank staff are also unfamiliar, is best avoided in institutionally challenging contexts. If,nonetheless, they are utilized, then project outcomes requireprovision for adequate training on both the Bank and Borrowersides, and by enhanced resource availability for supervision. In this case, the use of the DLI model was not accompanied bysufficient training, and the allocations made for supervision would have been barely adequate even without the DLI model, given thedifficulties of the operating environment.
P128239 | South Sudan Private Sector Development Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 2012 | 2016 | 2018 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/779131520264708225/text/South-Sudan-South-Sudan-PSD-Project.txt | http://documents.worldbank.org/curated/en/779131520264708225/pdf/South-Sudan-South-Sudan-PSD-Project.pdf | This review concurs with four lessons and recommendations identified by the ICR inthe following four areas: (i)whileusing aBusiness Plan Competition award as a collateral for a bank loan is an option, there are implementation challenges in alow capacity andfragile environment, (ii) in a conflict-afflicted environment, flexibility and simplicity inthedesignshould be the norm torespond to unexpected occurrences,(iii)in a fragile, conflict andviolence (FCV) environment, the team should prepare for the worst, while hoping for the best in terms of the security situation inthe country, and (iv)investments in Apex Microfinance Institutions can make positive contributions to increasing financialinclusion in fragile environments.A fifth lesson ignored during the project design, and which was confirmed by the projectimplementation is that the projects design shouldtake very seriously into accountthe political and securityrisks in fragile environments,because the risk for a post-conflict country to fall back into instability is veryhigh.
P128251 | Tunisia - Governance, Opportunities and Jobs DPL | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/128361579621782945/text/Tunisia-TN-Governance-Opportunities-Jobs-DPL.txt | http://documents.worldbank.org/curated/en/128361579621782945/pdf/Tunisia-TN-Governance-Opportunities-Jobs-DPL.pdf | The following lessons are drawn by IEG:A complex transition requires careful considerationof trade-offs between ambition and feasibility in project design. In Tunisia, political pressures and economic challengescalled for broad multi-sectoral interventions, but success might have been greater with a more careful assessment of institutionalcapacity in key reform areas.Reforms are especially prone to being undermined by their weakestlink. In Tunisia, employment reforms were affected by the lack of ownership of the employment agency. In such instances,other actors, for example non-governmental organizations, can be helpful through outsourcing.
P128258 | Power Sector Reform: Development Policy Credit | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2014 | 2015 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/815501539271842285/text/Pakistan-PK-Power-Sector-Reform-DPC.txt | http://documents.worldbank.org/curated/en/815501539271842285/pdf/Pakistan-PK-Power-Sector-Reform-DPC.pdf | Fivelessons are drawn from the ICR (pages 22-24), with some adaptation of language.1) A dedicated sectorenergy reform operation (as opposed to inserting a limited number of prior actions in a multi-sector or general macro-economicsupport operation) can be more useful in countries facing severe energy sector challenges. The DPOs allowed for themodification of indicators and targets that could better reflect changing circumstances and evolvingpolicy dialogue. Forinstance, the targets for reducing subsidies were revised in the face of governments commitment to maintaining subsidies forpolitical economy considerations. Likewise, the government was able introduce, as complementary measures, a mechanism based ontariff surcharges and a Tariff Rationalization Fund to maintain nationally uniform tariffs in the face of windfall gains producedalongside falling oil prices during the operation period.(2). The governments ownership of reform isnecessary for the success of a development policy operation.In this operation, the governments ownership andinvolvement in the reform of the power sector was focusedduring preparation. The government issued notifications regardingreducing subsidies, increasing tariffs substantially and setting a cap on circular debt.When these priorities were no longerpresent, the leverage of the Ministry of Finance (MoF) over the Ministry of Water and Power (MWP) diminished and MWP no longer wasascommitted tosector reforms as it was during preparation. This contributed to the limited efforts at sector reformsduring DPO2.(3) A balanced approach among instruments targeting federal and sectoral levels can help bring aboutmore sustained results. Federal DPOs have supported IMFs programs to stabilize the macroeconomy byproviding budgetary support for reforms aimed at improving energy sector sustainability and private sector growth. A morestrategically balanced mix of budget support with other Bank instruments could help leveraging more sustainableresults.(4) Close collaboration with the International Monetary Fund can benefit a DPO program. Closelyaligned positions among donors could help in pushing through difficult reforms. Collaboration with the IMF could have played a rolein effective completion of the IMF program.(5) In the context of a DPO operation, it can be difficult to implementreforms, even when a requisite prior action has been taken. To help improve the collection rates and reduce distributionlosses of Discos, one prior action in DPO 1 had required the outsourcing of collections of Discos. Even though the prior action wasmet, only two distribution companies proceeded with the outsourcing of the collection of feeders with losses of 50% or above.
P128276 | Coastal Embankment Improvement Project - Phase I (CEIP-I) | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099113024145523923/text/P128276-a1ca74b0-d539-431f-9e9e-600c02635928.txt | https://documents.worldbank.org/curated/en/099113024145523923/pdf/P128276-a1ca74b0-d539-431f-9e9e-600c02635928.pdf | The operation offered eight lessons. Three are presented below with minor adaptation oflanguage: Obtaining a better understanding of climate change impacts on coastal polders may lead todeveloping models to address risks from climate variability. In this project, comprehensive monitoring, and morphologicalassessment of the coast, including long-term monitoring, research, and analysis of the coastal zone were initiated. However, agap remains in understanding the complex interplay among the natural phenomena, human intervention, and climate change forces thatthe coast experiences. To bridge this knowledge gap, the next phase of coastal investment could include empirical evidence on keycoastal processes, such as geomorphology, land subsidence, tectonic effects, erosion, sea level rise, tidal dynamics, rivermorphology, shoreline changes, and salinity intrusion. The next phase could also focus on the maintenance and further developmentand application of the tools developed under this project to inform the design of new investments in the coastal zone. For example,Bangladesh could develop a more detailed storm surge forecasting system for the coastal zone and the polders using the hydraulicmodels developed by this project. Nature-based solutions may enhance resilience, effectiveness, and communityownership of infrastructure interventions in polders. In this project, nature-based engineering designs were integratedinto the rehabilitation of polders. Such designs were meant to strengthen embankments. Afforestation programs on the slopes ofembankments and foreshore areas formed part of the design to protect against the impacts of climate change. This approach enhancedphysical infrastructure and made use of the benefits of ecological systems for a sustainable, long-term resilience againstenvironmental threats. Squatters who benefited from the afforestation program were boosted by the publics support for theprogram and did return to the embankment slopes because cutting trees to construct houses illegally on the slope of the embankmentwere discouraged. Investing in embankment protective works may be an effective means to address riverbank erosionin a timely manner. In this project, the more expensive proposition from financing embankment protective measures tofortify riverbanks against erosion may prove to be more cost effective. The approach would not require land acquisition.Implementation would not be delayed by having to acquire new land if the alternative, retiring anembankment, were usedinstead. Communities would be more resilient sooner because the lack of having to acquire new land would be sidestepped. Potentialsevere impacts on livelihoods and assets would be avoided because a new embankment would be operational sooner.
P128284 | SN- First Governance and Growth Support Project | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/608921530222166121/text/Senegal-First-Governance-and-Growth-Sup-Project.txt | http://documents.worldbank.org/curated/en/608921530222166121/pdf/Senegal-First-Governance-and-Growth-Sup-Project.pdf | The following lessons are drawn from the ICR:Budget support series should pay attention toabsorptive capacity. While budget support provides the opportunity for ambitious coverage and tacklingmanyissues, absorptive capacity in government agencies will often be the limiting factor; it needs to be carefully weighed againstpotential overreach in program design. The GGSC series was ambitious, increasing the burden on both Bank staff and theadministration, and placing the quality of reforms at risk.Prior actions need to be followedup. The passage of laws and regulations the usual contents of prior actions is a first step inreform; once passed, they also need to be put into practice, and this requires the necessary skills and, often, access to companiontechnical assistanceto build up those skills. Significant delays were experiencedin a number of instances in thisprogram, notably the application of financial regimes for universities experienced significant delays due to a lack of follow-up inthe Ministry of Finance that was in charge of the setting the budget nomenclature.
P128307 | PK: Sindh Agricultural Growth Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2021 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099045001122324893/text/P12830703a3ef60c408231027fb382a458b.txt | http://documents.worldbank.org/curated/en/099045001122324893/pdf/P12830703a3ef60c408231027fb382a458b.pdf | Demand-driven projects should have flexible arrangements in delivery of activities. The projectsadministrative document that described project activities was prepared in 2011. It listed 40 items related to equipment andmaterials demanded by the farmers based on consultations and studies. The project got approved in 2014, and with the delays, by thetime the project was ready to implement the activity, only 10 items were relevant for the farmers. The project then facedchallenges in revising the list due to the complex administrative procedures of the Government. In such circumstances, design andimplementation of project activities should be flexible, particularly in demand-driven projects where interventions are based onfarmers needs which can change due to the local circumstances.Formation of producer groups can be animportant vehicle for market access. In the dairy value chain, formation of producer groups that were given the necessarytraining and technical support helped aggregate milk supply at the local level. With increase in quality milk supply, newopportunities came up to sell milk directly to large private buyers instead of relying on milk collectors. In the absence ofmiddlemen, farmers received better prices and became more knowledgeable about market-related issues.Completion ofbaseline surveys should be a dated covenant in projects legal agreements. The baseline survey for the project wasonly completed in late 2017, whereas the project was approved in 2014. Though this projects activities were delayed and as aresult, the baseline survey was still able to meet its objective of documenting pre-project baseline situation, it would have beenbetter to include this important activity as part of a legal agreement of a project, thus giving it the needed attention to becompleted on time.
P128309 | Second Emergency Agricultural Productivity Support Project | Western and Central Africa | Guinea | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2016 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/162111468036854606/text/ICRR-Disclosable-P128309-06-16-2016-1466080955061.txt | http://documents.worldbank.org/curated/en/162111468036854606/pdf/ICRR-Disclosable-P128309-06-16-2016-1466080955061.pdf | PUAPA-2s experience yields the following lessons, of which lessons 3 and 4 are adaptations from theICR:1. Development projects should consider longer-term perspectives and an exit orcontinuation strategy. This can also apply to investment-oriented emergency response projects. PUAPA-2 was anemergency response Grant supporting development of productivity enhancing infrastructure and agricultural services. With a 2 year project period, there was time during implementation to consider appropriate developments after the project. But theAppraisal and ICR reports are limited in their discussion of post-project activities. Preparation during PUAPA-2 implementation ofeither a continuation/scale-up or of an exit strategy would have likely set the project in a more strategic perspective, betterable to sustain the projects developments and to respond to Guineas future agricultural development needs. (section 3b of this ICR Review).2. Sufficient time should be provided for implementing aninvestment-based Emergency Response Project.PUAPA-2 was funded as an Emergency Response Grant under the FoodPrice Response Multi-Donor Trust Fund. With its investments in irrigation, marketing infrastructure, threshing and dryingfacilities, consolidation of a farmer-based seed multiplication system, and improvement of agricultural extension services, PUAPA-2was more like a standard investment type of operation than an emergency action program, but investments require adequate time. Theprojects irrigation rehabilitation investments had significant impact on productivity, albeit with a longer lead time thanthe shorter-term actions such as input distribution. Irrigation was, thus, asignificant contributor to PUAPA-2s productivityenhancement goal. Yet an investmentoriented type of operation such asPUAPA-2 would typically require more than the 2 years provided for the project, and this materialized, with a 22 percent extension of the closing date. If an emergency responseproject is designed as an investment program to reduce future vulnerability (as compared with short-term actions such as foodsubsidies or community assistance), the financing source should be able to provide adequate time for reasonable expectations on theproject duration required. (section 3 b of this ICR Review)3. Capacity building may be anecessary part of successful involvement of an ancillary agency. APROMA, which had built up capacity underPUAPA-1, successfully coordinated a complex project. The National Office for Studies and Planning, which was entrusted withexternal monitoring and impact assessment, did not have the necessary experience and made no progress. (section 10 of this ICRReview).4. Community organizations can be effective distributors ofinputs.Inputs were procured by APROMA, and then distributed to farmers through Guineasnetwork of farmer organizations. Farmer organizations were closely aligned with communities, enabling greater responsiveness tofarmers than government services. (section 11 b of this ICR Review).5. The design ofprocurement processes needs to be adapted to local governance and field conditions. Initial presumptions thatinternational competitive bidding would apply to much of the civil works, proved impractical given the small size of contracts,often dispersed in remoteareas; and the Ebola crisis further reduced interest of international contractors. Switching to localbidding, and resolution of cumbersome government clearance processes, substantially speeded up project implementation. (section 11b of this ICR Review).
P128332 | AFCC2/RI-African Medicines Regulatory Harmonization Project | Other | Africa |  |  | Human Development | Health, Nutrition & Population | RETF | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/508861537473504141/text/Africa-African-Medicines-Reg-Harmonization.txt | http://documents.worldbank.org/curated/en/508861537473504141/pdf/Africa-African-Medicines-Reg-Harmonization.pdf | The ICR (pp. 31-33) offered several useful lessons, including the following lessons restated byIEG:Harmonizing medicines registration regionally is a long and complex process, and its ultimateattainment can be facilitated by a phased approach.The project experience suggestedthat standardizingregistration requirements, aligning them with national polices and legal frameworks, and building institutional capacity at thenational level in all of the countries involved werepre-requisites to the actual attainment of regional harmonization ofregistrationsystems for medicines.Bridging the gap between less-resourced NMRAs and strongerNMRAs facilitates the attainment of the collective regional objective for harmonizing medicines registration systems.The project twinned strong NMRAs with less resourced NMRAs, provided substantial training, and facilitated peer-to-peerlearning through joint assessments and joint inspections.Project experience also suggestedthat further additionalsupport was needed to bridge the gap, including for legal and political support, human resources, andinfrastructure.Defining concrete institutional roles, responsibilities, and division of laborfor various agencies, and revisiting these during implementation, enhances effective coordination and implementationperformance. Under the project, generic terms of reference were developed for various project actors, but duringimplementation, the respective roles and division of labor became blurred, resulting in coordination shortcomings and duplicationof efforts.
P128378 | Skills Development and Innovation Support Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099315001032250912/text/North0Macedoni0t0Innovation0Support.txt | http://documents.worldbank.org/curated/en/099315001032250912/pdf/North0Macedoni0t0Innovation0Support.pdf | The lessons are drawn from the ICR.A strong governance model is likely to promote sustainability in a newinstitution. Despite a challenging political environment with several changes in leadership, the FITD was able tominimize political interference in its operations. Bulwarks against such interference were not only written procedures and astrong monitoring system, but also an emphasis on organizational values, competent staff (in most cases drawn from the privatesector) supported by international experts, and a selection process of beneficiaries that emphasized objectivity. Theemphasis on apparent objectivity seems to have been recognized and appreciated by clients.Impact evaluations canhelp raise the relevance of a program. The project used a rapid impact evaluation to choose between differentfinancing measures used by a new grant program for secondary TVET. This allowed the program to early on enhance the impact ofits funds by targeting the most effective financing measures.Introducing new instruments takes time to gainacceptance. The bulk of FITD funding (75 percent) was disbursed during the last 18 months of a seven-year projectperiod. The initially projected five years were not sufficient to design quality instruments, build institutional capacity,build awareness and launch calls for bids, and overcome trust issues about objective selection of beneficiaries.
P128393 | Second Lao Environment & Social Project (formerly Protected Area and Wildlife Project) | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060724144540724/text/P12839315cdf0f06b1afeb1e91619e491f0.txt | http://documents.worldbank.org/curated/en/099060724144540724/pdf/P12839315cdf0f06b1afeb1e91619e491f0.pdf | The ICR (p. 38-39) included several lessons learned which were adapted by IEG: A programmatic approach inthe natural resource sector in low-capacity environments can build capacity over time and contribute to sustained and amplifieddevelopment achievements. This project made significant progress in building capacity and improving the quality ofenvironmental management systems. However, these project results require continuous financing and capacity-building support througha strategic programmatic approach to ensure the achievement of the long-term goals of improved conservation, biodiversityprotection, enhancement of ecosystem services, and reduced wildlife trafficking. Designing a robust and realisticME framework, and strengthened efforts on capacity building of clientscan improve monitoring of complex projectsimplemented in low-capacity environments. This project consisted of a large number of sub-projects. Due to theweakcapacity of SDAs and the complex ME framework, often did not report on their indicators in a robust and timely manner.As a result, EPF found it challenging to aggregate and report all indicators. Projects addressing verylimited capacity across a range of national and sub-national institutions simultaneously can allow for taking advantage ofsynergies. In this project, strengthening the capacity of various entities at different levels across the country allowedfor entities to collaborate, support, and learn from another.
P128416 | DANUBE REGION WATER AND WASTE WATER SECTOR CAPACITY BUILDING PROGRAM | Europe and Central Asia | Europe and Central Asia |  |  | Sustainable Development | Water | RETF | IPF | 2012 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051723145534716/text/P128416055c84c05d0af030ee8ce8349128.txt | http://documents.worldbank.org/curated/en/099051723145534716/pdf/P128416055c84c05d0af030ee8ce8349128.pdf | The ICR included eight lessons. the following are emphasized with some adaptation of language:1. Goodcoordination with co-donors can enable synergies and increase impact of the intervention. Organizing regular donorcoordination meetings from the beginning of the program can prevent any potential overlaps or duplication of effort among the manydonors in this field.2. A TA program ina country can fostersymbiotic and mutually reinforcingrelationships for expanding investment operations among countries in the region with similar sectoral issues.To thatend, several important investment operations resulted from the activities of the Program. Establishment of suchsynergy has served as an important element of the Program and constituted a strong argument for the World Banks involvement.The synergy between such a TA program as the DWP and the World Banks investment operations provided important opportunitiesto multiply effects and achieve better results. Going forward, the Program can consider building of further synergies with otherregional and global initiatives that can enhance ongoing efforts.3. Regional programs can be a successful approachto initiate cooperation between regional countries facing similar challenges.The regional nature of the program isthe cornerstone of its success. Since many of the target countries are faced with similar challenges, the program facilitated theestablishment of helpful partnerships, enabled the countries to learn from each other, while building healthy competition toencourage progress towards improving service delivery to the ultimate beneficiaries. Given the transboundary nature of the DWP,water represents a critical shared resource over which regional cooperation can further be built and enhanced for an improvedmanagement of the shared resources and ensuring water security.
P128434 | Mozambique Climate Change Development Policy Operation | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2013 | 2013 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/346681520728179052/text/Mozambique-MZ-Climate-Change-DPO.txt | http://documents.worldbank.org/curated/en/346681520728179052/pdf/Mozambique-MZ-Climate-Change-DPO.pdf | The following three lessons learned which had general applicability beyond this project were, with some editing,derivedfrom the ICR:1. Progress on climate change-related policy and institutional reforms requireseffective inter-sectoral coordination and dialogue because climate change affects many sectors. For example, inMozambique, building upon the coordination functions of Ministry of Planning and Development and Ministry of Environmental Affairs,the preparation of the National Strategy for Adaptation and Mitigation to Climate Change strategy marked a significant shift andprovided the initial platform for inter ministerial collaboration (ICR, para 84).2. Highlevel engagement with the government, supported by strategic and targeted technical assistance, is essential to achieving reformson climate change. While the World Bank had given technical assistance to various sectors in Mozambique, engaging with theMinistry of Planning and Development and the Council of Ministers ensured that climate change policy reforms was a prioritydevelopment issue (ICR, para 85). Moreover, having a coordinating body helped ensure that sector-level climate changepriorities were discussed and resolved by the Council of Ministers (Bank task team).3. Toensure sustainability of reforms climate resilience needs to be mainstreamed into sector strategies and be reflected in actualbudget. For example, policy actions strengthening the extension service to promote the uptake by farmers of conservationagriculture. This led to a new risk management capacity within the crop production department, and the opening of the extensionservice to the private sector for services, related to conservation agriculture (ICR, para 88)
P128437 | Ocean Partnerships for Sustainable Fisheries&Biodiversity Conservation | Other | World |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2019 | 2021 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/748891596640329304/text/World-ABNJ-Oceans-Finance-Facility-GEF.txt | http://documents.worldbank.org/curated/en/748891596640329304/pdf/World-ABNJ-Oceans-Finance-Facility-GEF.pdf | The ICR (p. 24-25) included a few lessons learned: The Banks country focused business model andInvestment Project Financing are not suitable for a global project with a focus on areas beyond nationaljurisdiction. This project included four different regions, and four different EAs, requiring intense supervision.However, despite the projects global scope, the supervision budget was not adjusted to allow for the required supervision.Also, given the EAs lack of experience with Bank procedures, financing the project through a Bank-executed (BE) AdvisoryServices and Analytics (ASA) might have been a better fit. Establishing a permanent expert group for fisheryprojects could be beneficial for providing feedback and ensure knowledge transfer between projects. In this project,a group of experts within the GloTT was established which generated and disseminated focused knowledge on improving ABNJ fisheriesglobally, by developing and presenting various reports and academic papers.
P128443 | Guinea - MSME Development Project | Western and Central Africa | Guinea | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/986011544713249595/text/Guinea-GN-MSME-Development-Project.txt | http://documents.worldbank.org/curated/en/986011544713249595/pdf/Guinea-GN-MSME-Development-Project.pdf | Three lessons are drawn from the ICR (pages 35-36), with some adaptation.Political commitment at all levels of government and in all phases of the project life cycle, and notjust during project preparation,is vital to the success of an operation. The ICR cites the apparent lack ofownership of the project by theauthorities during the project preparation phase such that the project was re-designed severaltimes before approval. But there was also poor commitmentby the Government during the mobilization phase, by the MISMEand the technical staff of the otherimplementing agencies during project implementation, and by the Government after projectclosing asevidenced by the latters inability toconduct the impact evaluation of the project as required.Institutional capacity is highly crucial in projects in fragile, conflict and violence(FCV) environments. The Ebola health crisis and the ensuing economic crisis of 2014-15 shifted the Governmentsattention away from the project and to more pressing national priorities. A more institutional capable government would havebeen able to devote attention to the project as well. There are other cases of institutional weakness:(a)theAPIP, originally under the MISME, was moved to theOffice of the Presidentin 2014, distracting from the implementationof the project;(b) the MISME was headed by three different Ministersduring the life of the project; and, (c) there wasinadequate coordination and communication between the PIU and project stakeholders.The ICR even speculates thattheinstitutional setup for the project would have been strengthened if the Bank chose as the principal counterpart athird-party institution such as the Ministry of Finance to play a neutral role between competing beneficiary institutions.The authorities must consider financial sustainability of reform measures when planning reformoperations. In an environment in which resource availability is uncertain or constrained, the financialsustainability of an intervention has to be carefully consideredduringproject design. The ICR raises questionsabout the ability of the Government to continue to fund the operation of the Support Center in the medium- to long-term.
P128443 | Guinea - MSME Development Project | Western and Central Africa | Guinea | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2013 | 2018 | 2022 | PPAR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/290051633370471003/text/Guinea-Micro-Small-and-Medium-Enterprises-Development-Project.txt | http://documents.worldbank.org/curated/en/290051633370471003/pdf/Guinea-Micro-Small-and-Medium-Enterprises-Development-Project.pdf | 3. Lessons 3.1 For effective PPD, it is crucial to have (i) a champion at the highest government level who can bring the public and private sector together to identify and implement business environment reforms, and (ii) agreement among various private sector associations to identify a private sector representative who can lead the dialogue on their behalf. These two conditions will avoid delays in adopting business environment reforms or the risk of adopting reforms that will be implemented without private sector buy-in and involvement. 3.2 Projects should include measures to ensure sustainability of support centers that provide capacity building to MSMEs after project closing. 3.3 Design and implementation of credit registries should be based on international best practice standards. Selecting a company with successful experience in several countries to support implementation of the credit registries is a key factor of success. The World Bank and IFC can effectively join forces by providing funding (the World Bank) and capacity building to help government counterparts select adequate companies. 3.4 Integrating a rigorous impact assessment into the design of World Bank projects supporting MSMEs would help discern the causal effects of project interventions on MSME development.
P128516 | Modernizing Higher Education Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050124112542784/text/P1285161216e9e09b1bcd21bf97679714b0.txt | http://documents.worldbank.org/curated/en/099050124112542784/pdf/P1285161216e9e09b1bcd21bf97679714b0.pdf | The ICR (p. 33-34) included several lessons learned which were adapted by IEG: Separating theimplementing agency from political cycles, bureaucratic delays, and weak incentives allows for more implementation autonomy thatmight positively impact project implementation. In this project, project implementation was closely linked to existinginstitutional arrangements within the government which allowed for capacity building. However, it also resulted in implementationdelays due to leadership turnover, procurement challenges, and insufficient reward mechanisms for thePMT. Defining technical gaps during project design and then pairing technology upgrades with intense capacitybuilding ensures the sustainability of modern infrastructure. In this project, the identification of technical gaps duringthe design stage allowed for funding and allocating time for user training appropriately. Investing in digitallyenabled higher education might positively impact resilience of the higher education system. In this project, the COVID-19pandemic demonstrated the importance of virtual tools such as the HEMIS for management and the e-library for learning to ensure theresilience of the higher education sector.
P128534 | Cameroon Social Safety Nets | Western and Central Africa | Cameroon | Blend | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2023 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099101624221011100/text/P128534-e5176cfc-2594-449c-a2d6-d6ce9d4101db.txt | https://documents.worldbank.org/curated/en/099101624221011100/pdf/P128534-e5176cfc-2594-449c-a2d6-d6ce9d4101db.pdf | The ICR (pp. 33-34) included several lessons and recommendations, including the following lessons re-stated by this ICRReview: Pilot programs can pavethe way for cash transfers and public works programs to address needsof poor and vulnerable populations. This was the first operation of its type in Cameroon, a country thatisrelatively new to the SSN agenda. It showed that both cash transfers and public works programs can be successfullyimplemented and, in the case of the cash transfer program, achieve and exceed targets for reaching poor and vulnerablepopulations. The establishment of an MIS system upfront to identify and track beneficiariescanbeeffective, alongside increasing beneficiaries to refugee communities, even though it took time for thegovernment to take ownership of the SSN agenda. Gender sensitivity can be enhanced by giving considerationto childcare for women, and by addressing gender-based violence (GBV) issues. The project provided childcare for womenthrough mobile creches that were added as part of support to female LIPW workers and were consideredbeneficial. Gender-responsiveness and sensitivitywas also seen in Bank follow-up to a gender-basedviolence (GBV) fatality in a beneficiary household. This incident triggered the Bank undertaking a multi-year collaboration withthe Africa Gender Innovation Lab including qualitative research on integrating Intimate Partner Violence (IPV) prevention intosocial safety net programs, development ofan intervention to reduce IPV among cash transfer beneficiaries in Cameroon, and animpact evaluation to measure its effectiveness. Feedback from the treatment group of the intervention was positive, and theintervention was continued as a follow-onsafety net project. TheBanks follow-up on the GBV incident whichtriggered a series of work on GBV in cash transfer beneficiaries is noteworthy.
P128573 | LS- First Growth and Competitiveness DPG | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/304821498076267710/text/ICRR-Disclosable-P128573-06-21-2017-1498076259680.txt | http://documents.worldbank.org/curated/en/304821498076267710/pdf/ICRR-Disclosable-P128573-06-21-2017-1498076259680.pdf | This review supports the following ICR lessons:DPOs supporting fiscal consolidation should adopt targetsthat address structural reforms specifically aimed at cutting expenditures and mobilizingrevenues.Programmatic lending limited to no more than 2 year programs could give more flexibility to adjustthe program to changing circumstances. Lesothos economy is fragile and very dependent on the external environment because ofits dependence on Southern African Customs Union revenues and remittances. When faced with a more favorable environment, thegovernment tends to relax fiscal conditions which leads to delays in the reform agenda.In countrieswith low implementation capacity, all operations should include capacity building or should be linked to other ones that provideit. Most critical is providing capacity building in the area of fiscal policy given the central role that fiscal consolidationplays in the sustainability of the countrys macroframework.
P128628 | CONGO - Rep. Skills Development for Employability Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Human Development | Education | IDA | IPF | 2014 | 2023 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | Lessons from the ICR (p. 26):Effectively ensuringgirls participation in and benefit from skillstraining programs employment necessitates deployment of a range of strategies.Project design included varioustargeted efforts to promote the participation of girls/young women in training programs, to encourage them to pursue traditionallymale-dominated trades, and to apply for financing from the Competitive Fund (CF). First, the project provided higher stipends toyoung mothers to offset the costs of childcare. Second, in an effort to encourage girls to pursue skills training in traditionallymale-dominated trades, a higher stipend was offered to those girls who chose to pursue training in these trades and, additionally,videos were developed to show girls training in and working in these areas. Third, the project set sub-targets for many of theindicators to ensure girls participation and to promote gender equity under the project,in terms of theirparticipation in training programs and in benefitting from the CF. Moreover, with regards to the CF, the set targets forproposalssubmitted by women or women-led cooperatives provided increased incentives for women to take on amanagement/leadership role in developing and potentially managing a business. A combination of such targeted efforts, together, canbe important in effectively addressing some of the barriers girls and young women facein acquiring skills, accessingemployment, and earning higher salaries.Effective and targeted communications can play an important role in thereach and implementation of large skills training projects. The importance of effective communications in projectsthatinclude multiple actors, competitive selection, and a focus on equity cannot be underestimated. Strong communicationsrelated to eligibility criteria, selection processes, and timelines for the various training programs and for the CF are importantin ensuring transparency, encouraging applicants to apply to the programs, and managing their expectations. Additionally, theestablishment of processes for youth to issue a grievance or to provide information related to their applicationscan add somelevel of legitimacy to a projects approach. Finally, the project demonstrated the important role that targeted communicationscan play in girls decisions to apply to the program, to participate in training, andto pursue skills training inmale-dominated trades.Coupling skills training activities with financial supportcan enhance positive programoutcomes. The projects support to a CF reflected an understanding that youth receiving training under the projectwould need additional support to enter the informal labor market, and in establishing their own small businesses. The decision toestablish a first-ever CF in the education sector that could financially support trainees business plans was consistent withfeedback from previous cohorts and reflected growing global evidence that highlights the importance of providing technical andfinancial resources to have the greatest impact on employment outcomes of youth engaged in these programs. Such funds shouldprovidetrainees with support to develop technically sound and feasible business plans and the necessary resources toimplement them.
P128644 | Sudan Basic Education Recovery Project | Eastern and Southern Africa | Sudan | IDA | FCS | Human Development | Education | RETF | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/142401591030750707/text/Sudan-Sudan-Basic-Education-Recovery-Project.txt | http://documents.worldbank.org/curated/en/142401591030750707/pdf/Sudan-Sudan-Basic-Education-Recovery-Project.pdf | Lessons drawn by the ICR, adapted by IEG: The Community Empowerment Model (CEM) for school construction can beeffective in building local ownership, sustainability,and capacity, given the right design elements. In the case of thisproject, the CEM approach included community mobilization, training, and sequencing of construction agreements (two successivecontracts for one-block classrooms rather than one contract for a two-block classroom) to ensure learning-by-doing, and radioadvertising to attract small-size local contractors. Communications campaigns can help improve monitoring of textbookdistribution and accountability.In the case of this project, publicity campaigns were launched to prepare for the arrival ofthe books, letters were sent to the State-level Ministries of Education with the itemized number of books per school,advertisements were taken out in national newspapers to alert parents to the upcoming deliveries, and a paper trail of thedistribution process was created from states to localities to administrative units to schools to enhanceaccountability. Rapid results surveys can be effective and cost-efficient in a low capacity context, as a supplement tomore in-depth, sophisticated data collection foran education management information system.In the case of this project,responses to simple questionnaires were submitted electronically via tablets, thereby increasing the timeliness and quality of datacollection to inform project decisions.
P128768 | Burkina Faso Electricity Sector Support Project | Western and Central Africa | Burkina Faso | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2023 | 2025 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | https://documents.worldbank.org/curated/en/099101524104022500/text/P128768-d0d7a50c-08fe-4c58-8ecf-947ea71d2f82.txt | https://documents.worldbank.org/curated/en/099101524104022500/pdf/P128768-d0d7a50c-08fe-4c58-8ecf-947ea71d2f82.pdf | The following lessons were derived from the ICR (ICR, pages 28-29):1. In the FCS context, over-ambitiousprojects have limited chances to fully reach the intended outcomes, and the best approach might be re-focusing them on simplified,achievable objectives early-on. The reviewed Project was already ambitious at approval, as it simultaneously aimed at: (i)improved energy reliability, (ii) increased energy access, and (iii) enhanced energy efficiency (at approval); while also launchingcomplex and innovative rural electrification activities (installation of hybrid mini-grids and Solar Home Systems (SHS), a newactivity under AF1). Its ambition increased with the new activities added at the third restructuring of November 2016: constructionof two solar PV power plants; support to the Ministry of Energy in the negotiations of the independent power producer(IPPs)/public-private participation (PPP) projects; and facilitating solar PV integration into the network. During 2014-2020, thesecurity situation in Burkina Faso was deteriorating, and in FY2020-25 it was classified as an FCS country; as such, theProjects aspirations were now out of reach. The Bank team could have considered scaling down the Projects objectivesmuch earlier, when the security situation started to deteriorate, to avoid a situation when critical targets are notreached.2. Project implementation significantly depends on the effectiveness of the PIU, and strengthening theimplementation structures and human resources, as well as securing reliable PIU financing, is critical to avoid delays andinefficiencies. In the reviewed Project, the Project Implementation Unit (PIU) staffing and financing issues were asignificant factor in implementation delays; and the PIUs weakness in relation to the safeguards and fiduciary management,exacerbated by the insufficient funding of the PIU by the counterpart, led to weak project management, delays, and, ultimately,missed intended targets. Better considerations of the institutional anchoring of the Project and of the reliability of PIU fundingat the time of Project preparation would have been a good mitigation strategy. 3. In the FCS context,fiduciary issues require heightened attention, including in relation to the contract payment terms. In the reviewedProject, procurement and financial management (FM) were challenging throughout Project implementation, especially when the OP 7.30was triggered by military coups and all pending payments and processing of withdrawal applications were paused. Settlingprocurement and FM issues contributed to implementation delays; and the problem with the non-reimbursed advances made tocontractors often could not be resolved.4. Capacity building to support the safeguards compliance, providedprior to the start of Project implementation, can be a critical measure mitigating implementation delays and ensuring that theresources needed for the compensation of persons affected by the project are available on time. The reviewed Projectexperienced an 11-month suspension in 2019 due to a noncompliance with environmental and social safeguard requirements: the preparation of safeguards instruments was delayed, and the works for rural electrification under Component 2 had to be suspended until thesafeguards instruments (Environmental Management Plan (EMP)/Resettlement Action Plan (RAP)) were prepared and approved by the WorldBank. Moreover, the PIU did not flag the breach caused by the start of the works in location for which safeguards instruments werenot finalized.
P128831 | Madagascar-Irrigation and Watershed Management Project - PHRD | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2014 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/260191541609116796/text/Madagascar-MG-BVPI-PHRD-Rice.txt | http://documents.worldbank.org/curated/en/260191541609116796/pdf/Madagascar-MG-BVPI-PHRD-Rice.pdf | The ICR included seven lessons. The following are emphasized with some adaptation oflanguage: Projects promoting rice intensification should also focus on improving irrigationinfrastructure to ensure adequate amounts of water reach the fields. Without rehabilitation and maintenance of theirrigation infrastructure, water losses increase,which eventually leadsto a decrease in yields. The availability ofirrigation water to farmers is critical in order for intensification activities (improved inputs andgrowing practices) toachieve the desired yields. Without proper amounts of water, plants become stressed, and intensification activities fail to achievethe desired results. Productivity-enhancing projects should always include market access activities toencourage surplus production by smallholders. Smallholders respond to market incentives, and in the absence of marketingopportunities (due to remoteness and/orlack of information), it is unlikely that they will perceive a benefit in producing amarketable surplus. Thus, supporting market access is key (by building feeder roads, or creating productive partnerships, amongothers). An Economic and Financial Analysis (EFA) at the appraisal stage isrequired to be abletoconfirm project efficiency at completion. It is always important to compare the pre-project and post-project EFAsbefore concluding whether the project achieved its anticipated economic benefits or if the investments were justifiable and stillrelevant.
P128832 | VILLAGE INNOVATION PROGRAM (VIP) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/330041619821238441/text/Indonesia-ID-VILLAGE-INNOVATION-PROGRAM-VIP.txt | http://documents.worldbank.org/curated/en/330041619821238441/pdf/Indonesia-ID-VILLAGE-INNOVATION-PROGRAM-VIP.pdf | The following lessons were based on the ICR with some editing and languagechanges: Supporting complex institutional reform, such asinstitutionalization of community driven development(CDD) projects requires coordinated policy, collaborative operationalengagement, and adequate time. For example, to institutionalize this CDD project, Indonesia implemented a new law that ledto multiple legal, regulatory and technical changes to its operations and processes. These included new approaches to fundingflows, audits, oversight and capacity-building systems. It also required changes to governance at different levels, as wellas a high degree of coordination and communication between a range of stakeholders. The transition period was 2 years, but ittook longer to firmly establish the reforms at all levels of government and community management not to mention the geographicalphasing required (ICR, para. 102). Decentralizationrequires a focus on leadership andinstitutional capacity, in addition to technical implementation capacity. As a result for further coordination andcollaboration across the multiple actors, the project included an explicit institution-strengthening component focused on civilservants and core government planning and budgetary systems (ICR, para 107). Addressing gender gaps needs to be intentional from design toimplementation to evaluation. For example, the project failed to achieve its targets related to genderparticipation. One reason for this was that the implementing agency did not make adequate use of monitoring data that wereavailable and the Bank did not systematically review progress and tackle shortcomings during supervision (ICR, para. 109). Thatsaid, the project also did not adequately measure the type of contribution that female participants made. In order to makeadvancements in womens participation mainstreaming a gender approach throughout the project and addressing barriers to entryand participation are needed. Measuring and tackling these barriers will improve not only gender related targets but also projectoutcomes.
P128867 | Jiangxi Wuxikou Integrated Flood Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/305871619633524840/text/China-Jiangxi-Wuxikou-Flood-Management-Project.txt | http://documents.worldbank.org/curated/en/305871619633524840/pdf/China-Jiangxi-Wuxikou-Flood-Management-Project.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1.Successfulflood management needs is a risk-based that integrates both structural and non-structural measures. Floodrisks are expected to increase under climate change. Therefore, flood management needs to adopt a risk-based approach, whichrequires leveraging risk identification (through the Decision Support System-DSS) to inform the use of risk-reduction measures(i.e., reservoir operation, people evacuation, etc.). The project experience showed that hard infrastructure is most effective whenit is supported by non-structural measures including: integrated flood risk management planning, improved flood forecasting andearly warning capacity, and community flood awareness and preparedness. The enhanced flood forecasting and early warning capacityfacilitated by the DSS can inform the operation of the hard infrastructure (i.e., the reservoir) so that the effectiveness of thehard infrastructure is strengthened.2. Flood-protection dams, especially multi-purpose ones can offer substantialsocio-economic benefits against natural disasters, especiallyunder climate change, and therefore are worthy investments, butneed to becarried out with sufficient risk mitigation measures to address the potential technical, environmental, and socialrisks.Under the project, social and environmental risks need to be identified and mitigated with due diligence. Damsafety was a key consideration during project preparation and implementation. In terms of environmental risks, the project hasconducted Cumulative Environmental Impact Assessment, which identified that this dam would have limited impact on the environment.Environmental impact mitigation measures were conducted.The project also included one specific component on resettlement andgranted a one-year extension to the closing date to ensure that the resettlement work was completed satisfactorily. Therecommendations made by the panel of experts were also important to the quality of dam safety management, as well as theenvironmental and social risk mitigation of the project.3. Resettlement efforts are successful when they areadaptive and flexible, and take a participatory and consultative approach.Reservoir resettlement normally lastsseveral years, during which time local socio-economic contexts can change substantially. Resettled peoples needs will alsochange with their socio-economic contexts. Thus, in order to mitigate the negative social impacts and enhance the long-termsustainability of project outcomes, resettlement management needs to be adaptive and flexible. Also, the resettled peopleschanging needs can be well taken into account through a participatory and consultative approach. Resettled people should be fullyconsulted before and during project implementation and their suggestions and requests need to be fully incorporated into projectimplementation. In addition, resettlement can be linked to governmental development programs, which not only allows for leveraginggovernment counterpart funding, but also enhances long-term project sustainability.
P128869 | Morocco Second Competitiveness DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following lessons from the ECSPs implementation experience need to be taken into account when designing futureinterventions intended to enhance competitiveness. The lessons were derived from the ICR, with someadaptation:The DPLs should be accompanied by downstream technical assistance to increase theirdevelopment impact. The upstream phase could include strong Bank technical assistance for several key prior actions,notably those related to increasing institutional and coordinating capacities, designing legal reforms of the corporate laws,and developing a methodology and a guide for assessing cost and benefits of investment decisions. Moreover, downstream support forachieving the program indicators should also be envisioned to help maximize the impact of theprogram.The satisfactory involvement of the private sector could prove to be a key factor indelivering strong reforms. The Bank should ensure that private sector is involved in defining prioractions and reform areas with the government. In this Morocco DPL series, the private sector indicated satisfactorycollaboration with the Government on the implementation of business environment reforms, especially those related to the CommonBusiness Identifier, the revised law on payment delays, and the suppression of minimum capital requirements for limited liabilitycompanies. The National Business Environment Commission has also gone beyond just involving the private sector in theimplementation phase, but has now started involving the private sector in the identification phase of reforms toundertake.Strong ownership, coupled with robust coordinating body at the implementing agency level,need to be prerequisites for loan disbursement. In the case of this Morocco ECSP loan series, theimplementation agency was not responsible for driving the key reforms. This fostered a dispersed program, involving multipleministries, without one that fully owns the program. One implementing agency (CNEA in this case) should be in chargeof cross-cutting competitiveness topics, considering its specific role for business environment reforms and its mandate ascoordinator of reforms across multiple ministries in the competitiveness space. Also, loan operations should focus on a limitednumber of issues in the competitiveness and private sector development realms to avoid such dispersion and ensure strongownership.Continued coordination among ministries and a reinforced dialogue at thenational-regional level is key for the competitiveness agenda going forward. The Bank was able to act asa catalyst to harness a strong coordination of business environment reforms by providing upstream and downstream technical supportto CNEA. The Bank should continue to push for inter-ministerial coordination beyond the realm of business environment, and movetoward inclusion of other competitiveness topic areas within the framework of a robust inter-ministerial dialogue. Further, goingforward, coordination and collaboration needs to also occur at the national-regional level, in light of the new advanceddecentralization program that is a key priority area of the new Government program.Theimplementation of a monitoring and evaluation (ME) system is key to determining the long-term efficacy of reforms. Astrong ME system is key to track program results in a timely manner, proactively identify issues with program performance andcontinue tracking results beyond the life of the program. The limited resources dedicated to ME for this program resulted inBank-driven data-collection efforts at the request of the Bank team conducting supervision missions.
P128891 | Ethiopia Promoting Basic Services Program Phase III Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/772491580234568379/text/Ethiopia-ET-Promoting-Basic-Services-Phase-III.txt | http://documents.worldbank.org/curated/en/772491580234568379/pdf/Ethiopia-ET-Promoting-Basic-Services-Phase-III.pdf | Lessons noted by IEG:A transparent interface between the general public and service providers can promoteeffective decentralized financial transfer systems.In this project, donors, including the Bank, relied on existingtransfer mechanisms to expand and raise the quality of basic services. This was backstopped by citizen oversight that was madepossible due to increased transparency of public agencies at national and sub-national levels in reporting on results. This wasmade possible by strengthening local accountability and transparency systems that facilitated citizens engagement,such as simplifying budget and service delivery information, providing budget literacy training, and using media and communityorganizations to transmit information. In financing basic services, be it through centralized or decentralized systems, teams needto ascertain that mechanisms to ensure accountability are in place.Mechanisms forfacilitating collaboration between government agencies and donors can ensure better project outcomes even under difficultcircumstances. The political and economic risks need to be carefully assessed and project implementation arrangementsdesigned accordingly. In Ethiopia, the project faced potentially severe political disruptions during implementation, and partly asa result of that, experienced delays in implementation, and gradually a shift in the form donor coordination would take, as DPsincreasingly focused on more narrow interventions. Nonetheless, in no small part due to the collaborative arrangements under PBS 3(and its predecessors) shared results frameworks, monthly development partner meetings major adverse effects wereavoided beyond DFIDs withdrawal.
P128904 | WS: Pacific Regional Connectivity Program: Phase 3 - Samoa | East Asia and Pacific | Samoa | IDA | Non-FCS | Digital | Digital Development | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099022024083022179/text/P1289041f21f8308b18fd6132947ce4e567.txt | http://documents.worldbank.org/curated/en/099022024083022179/pdf/P1289041f21f8308b18fd6132947ce4e567.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A Series of Projects can be an efficient and effective approach to carrying out projects in aregion. This approach enabled the Bank team to align the Project to a long-term regional goal and build partnerships withother development partners. This approach can arguably contribute to cost savings. For instance, the Bank team updated thefinancial, economic, and technical analysis of the previous Bank-financed phases, and this helped in cutting preparation time andcost. Based on the experiences from other phases of the project, the preparation team also understood the potential risks ofcollaborating with the private sector and used grant covenants and disbursement conditions to ensure open access andnondiscriminatory pricing of new international bandwidth.2. It would be useful to have insurance coverage for theactivities procured under a project. Although aManagement Information System (MIS) was procured under this project,the system was lost in an office fire in April 2020. As there wereno back-up copies of the softwareor insurance againstlosses and failure, this was not a sustainable outcome. This is particularly important, especially forcostly digitalinfrastructure.3. A careful consideration of the time required for enacting legislation can help in reducingdelays during implementation. The lesson from this project is that, especially on a pivotal bill such as the NationalDigital Identification (NDID) that has far-reaching consequences such as data protection, privacy, and inclusion, it would beuseful to allocate additional time for thorough deliberation and the drafting process for diverse perspectives to be heard andincorporated into the drafting of the bill.
P128905 | Nepal Agriculture and Food Security Project | South Asia | Nepal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/117641555688992501/text/Nepal-Nepal-Agriculture-and-Food-Security-Proj.txt | http://documents.worldbank.org/curated/en/117641555688992501/pdf/Nepal-Nepal-Agriculture-and-Food-Security-Proj.pdf | The following three lessons areselected fromthe five presented in the ICR (with some editing) because of theirpotential broad relevance to other Bankoperations:1 . Female crop or livestock producers can be more productive than male counterparts. For example,an FAO study prepared in connection with the implementation of this project showed that when women gained access to the sameresources as men, they were 20 to 30% more productive, especially when it came to livestock production (ICR, para. 51). Giventhe considerable outward migration of men from Nepalhas resulted in thefeminization of the agriculture sector theproject targeted rural women. The ICR reflected, that in these circumstances giving priority attention to theconstraints women face in the specific value chains in which they play a dominant role can pay highdividends.2 . Nutritionally Sensitive Agriculture (NSA) systems, which integrate agriculturaldevelopment, food security, nutrition, and public health, can enhance income and overall well-being of rural poor and vulnerablepopulations. For example, the project was able to integrate both productive and reproductive/livelihood householdactivities by involving the producers group at the grassroots, mostly womens groups (ICRP, para. 52). Theproject reflected the need to also include Civil Society Organizations (CSOs,) and formal farmers organizations andcooperatives.3 . Participatory approaches to agricultural extension, through Farm Field Schools,supported farmers individual involvement and proved adaptable to local needs. For example, Farm Field Schools(FFS) was the vehicle to train farmers. These schools provided farmers with an opportunity to share their experiences in crop andlivestock practices under improved and traditional management (ICR, para. 53). According to the ICR, farmer facilitatorstrained under FFS within the targeted communities were able to train other farmers and help sustain skill development (ICR, para.53).
P128909 | Liberia Health Systems Strengthening | Western and Central Africa | Liberia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099425008222229674/text/P12890909997310e10bebf0b934fa8a1165.txt | http://documents.worldbank.org/curated/en/099425008222229674/pdf/P12890909997310e10bebf0b934fa8a1165.pdf | The ICR (pp. 44 - 47) offered several useful lessons and recommendations, including the following lessons slightly adjusted bythis IEG Review:Piloting performance-based financing programs facilitates subsequent roll-out. Theproject started as a PBF pilot at Redemption Hospital before being rolled out in phases until it encompassed eight hospitals.Piloting allowed learning-by-doing before scaling up. This lesson confirms similar findings from other countries such as Cambodia,Haiti, Burundi, Afghanistan, and Rwanda.Virtual verification can be applied in pandemic circumstances.The project adjusted to the COVID-19 environment and increased the use of virtual meetings. The Independent Verification Agencypiloted virtual verifications at sites that had good internet connectivity, suggesting that virtual verification can be used inother PBF operations and may contribute to reducing verification costs.Performance-based financing empowersparticipating health facilities and the community. The project PBF empowered hospitals, County Health Teams, and thecommunity to take more granular responsibility in overseeing their respective health facilities. Stakeholders had a greaterobligation to increase accountability for outcomes. This was further facilitated by capacity building at MOHSW to enable it toguide and support lower sectoral levels. A medical residency program can act not only as a training program,but also as a strategy to increase specialized service delivery in related facilities. Medical doctors in the postgraduateresidency program provided specialized care at facilities where medical residencies took place. Hence, an increase in specializedservices was realized in a relatively short period of time in the selected health facilities. Furthermore, hospitals entered intoagreements through Memorandums of Understanding with the trained specialists to remain in place for a specified period of time.While some commitments were not honored, this arrangement contributed to sustaining a reasonable level of specialized skills at agiven facility.
P128919 | Zhengzhou Urban Rail Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099350105182242596/text/P1289190ad05410310b379051005444acb8.txt | http://documents.worldbank.org/curated/en/099350105182242596/pdf/P1289190ad05410310b379051005444acb8.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The World Bank can help through its knowledge base in securing private sector financing for publicinfrastructure investments, especially in middle-income countries. This project used a A + B Public-PrivatePartnership (PPP)model, a form of PPP for urban rail projects. Under this arrangement, the private sectorfinancedequipment costs and operational and maintenance costs for Line 3 for twenty five years. Although the Bank did notfinance the PPP component, the Bank added value through mobilizing its global knowledge and expertise. This helped to set thedirection for the Banks engagement in China from being a financier under Investment Policy Lending (IPL) to adding valuethrough technical assistance and knowledge transfer.2. Countries need to invest inresilience and climatechange adaptation measures in urban projects, given the increasing trend in urbanization in many countries. The July 2001flooding incident exposed weak points in city planning and management in this project and highlighted the room for improving thecitys flood preparedness and response system. The lesson from this is that to improve urban resilience, cities need to scaleup its climate adaptation measures, including upgrading construction standards, complemented by effective flood forecasting, earlywarning and emergency response system.3. Transit Oriented Development (TOD) and integration of the varioustransport modes needs to be incorporated inurban projects.Thisproject and two other urban rail projectshighlighted the significant challenges to Chinas long-term decarbonization agenda. The lesson is that the Bank needs tocontinue its engagementon TOD and help China in addressing the institutional challenges associated with TOD and integrationof the modes in urban projects.
P128938 | Pacific Aviation Investment - Kiribati | East Asia and Pacific | Kiribati | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/293921588775236693/text/Kiribati-Pacific-Aviation-Investment-Kiribati.txt | http://documents.worldbank.org/curated/en/293921588775236693/pdf/Kiribati-Pacific-Aviation-Investment-Kiribati.pdf | The following lessons were adapted from the ICR: Regional projects can provide an opportunity to overcomethe capacity constraints for implementing a project in a remote location with serious resource constraints. Given thetechnically complex and sizable civil works investments in a capacity constrained country like Kiribati, the regional approach toprocurement has proved to be effective. Procurement delays and complications were minimized through the central procurementteam. A central approach to procurement may be perceived as foreign andexpensive. The government officials of Kiribati perceived the Technical and Fiduciary Services Unit (TFSU)services as foreign, and felt their interests were not properly defended by TFSU. The government complained about the cost of TFSUservices and believed they were unfairly treated compared to other PAIP countries. Continuous consultation and engagement from theBank helped showcase the benefits from using TFSU. Institutional strengthening and capacitydevelopment in isolated states requires more time than anticipated. Given the capacity constraints in financial managementand procurement capacity as well as technical aviation and regulatory expertise. the five-year project implementation timeline atappraisal was unrealistic. The project had to be extended by 2.5 years.
P128939 | Pacific Aviation Investment - Tonga | East Asia and Pacific | Tonga | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/598111600099244835/text/Tonga-Pacific-Aviation-Investment-Tonga.txt | http://documents.worldbank.org/curated/en/598111600099244835/pdf/Tonga-Pacific-Aviation-Investment-Tonga.pdf | The following lessons were adapted from the ICR: More detailed cost estimates are needed in remote andcapacity constrained environments.Civil works under the project were often found to be more expensive thanoriginally estimated, which caused some delays. The terminal building works were put for tender twicebecause the estimatedcost was much lower than the budget proposed by bidders, and the final cost was 70 percent higher than the estimate. At appraisal,preparation of detailed cost estimates and bill of quantities would help with more accurate estimates. Also,given remoteness,perceived risks and limited competition, higher cost contingencies should also be factored into project design. Lower capacityenvironments may require longer implementation periods, the standard five-year implementation period is unlikely to be sufficientin small island states. The project had to be extended twice. Its important to have indicatorswithinthe projects control.For instance, the design of one of the PDO indicators relied on a third party audit fromICAO, which need not follow the projectsME timeline. Tracking the impact of the project can be better servedby using indicators for which data generation is more directly controlled by the project. A proper needs (andcapacity) assessment is needed to tailor the project activities to the local context. For example, for the construction ofthe Air Traffic Control Tower,the implementation team used designs of other control towers in small island states asthebase and adapted them to suit local needs. This provided a a lower cost solution than designing the building fromscratch. Regional procurement harmonization for relatively small scale and dispersed situations cansave on processing times and costs.Given the technically complex and sizable civil works investments forrunways, navigation aids and other specialized equipment, the regional approach to central procurement proved to be effective.Procurement of the same goods for several countries in one tender helped to reduce cost (compared to procuring specializedequipment for each country separately). Appropriate mechanisms should be put in place to ensure thatcost-sharing for centralized services across countries takes place in the intended manner. The cost of the Technicaland Fiduciary Services Unit (TFSU) was to be shared by all Pacific Aviation Investment Program countries. However, some countriessuch as Kiribati and Vanuatu failed to pay their dues. As discussed in the quality of supervision section (8b), this was mitigatedthrough the inclusion of insurance mechanism for TAL, which allowed up to US$100,000 to be disbursed from the PacificRegional Infrastructure Facility (PRIF) multi donor trust fundto cover any payment default by one or more beneficiaries ofTFSUservices.
P128940 | Pacific Aviation Investment - Tuvalu | East Asia and Pacific | Tuvalu | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2012 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099060724175533839/text/P12894016598580461ba731f963e9513c36.txt | http://documents.worldbank.org/curated/en/099060724175533839/pdf/P12894016598580461ba731f963e9513c36.pdf | The following lessons have been derived and summarized from the ICR.Climate change preliminary assessments.There is a need to adopt an interdisciplinary approach, combining knowledge from hydrology, geotechnical engineering,climate science, and infrastructure management to conduct climate change preliminary assessments into the preparation of allprospective infrastructure projects throughout the Pacific region. This necessity arises from the regions heightenedvulnerability to the exacerbating effects of climate change.Aviation sector reform efforts should take a holisticapproach. A robust institutional framework, development of both regulatory documentation and human resourcecapacity building are needed to achieve sustainable, effective implementation of the eight critical elements of a safety oversightsystem guided by the requirements of compliance with the provisions of ICAO SARPs, procedures, and aviation best practices. Thiscan be achieved in the FCV context by strengthening regional agencies and national regulatory and operationalauthorities.A proactive maintenance strategy of aviation assets in the Pacific is crucial.Continued monitoring of pavement conditions and assessment of vulnerability to prevailing environmental and climateconditions are required to take timely action and slow degradation to maintain the continuity of flight services into the islandstates, for which air connectivity is a lifeline.Selection of realistic and measurable indicator targets.Well defined indicators, realistic in the client country context and clearly attributable to the project, will enhanceproject ME. Even in the case of regional projects, attention should be paid to the specific conditions of thebeneficiary countries, in particular when working in an FCV context.
P128950 | Real Estate Registration Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2025 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/643621588600862916/text/Bosnia-and-Herzegovina-REAL-ESTATE-REGISTRATION-PROJECT.txt | http://documents.worldbank.org/curated/en/643621588600862916/pdf/Bosnia-and-Herzegovina-REAL-ESTATE-REGISTRATION-PROJECT.pdf | The ICR offered six lessons from this operation that others implementing projects in BiH or elsewheremayfinduseful(ICR, paragraphs75-80). Four of these are presented below: Designing a project in two-phasesacknowledges limited borrower capacity and supporting service infrastructure. This project was the second of two steps tomodernize land administration in BiH. This modular approach recognized that post conflict societies requirea longer timeframeto achieve unity. An incremental approach to transformation requires both sides of the conflict to reach a sharedvision andbuild upon less risky approaches. Such an approach, however, means that the benefits from data harmonization / REC creation mayreach some owners later than others. Sequencing the implementation of IT systems in a modular (phased) approachmay improve the way it works in the long run. A phased, step-by-step approach to development and rollout works well andcan be easier to implement than a system that seeks to do everything from the start. Starting from a basic registration system,project software was progressively expanded and introduced new modules as the institutional capacities of theagenciesincreased. Using experienced in-house experts plus donor expertise also helped to build both software and ITcapacity.The increased capacity will be invaluable in guiding the IT sector, particularly in RS, where the RS GA intends toreplace its cadaster and land registration software. Working closely with the Governments at the stateandsubnational levelsmay avoid delays in loan effectiveness and overcome obstacles to implementation.This projecttook 11 months to become effective. Project implementation was adversely affected. The 2018 CPF Performance Learning Review inBiHfound that complex signing and ratification procedures are chronic issues in achieving loaneffectiveness. World Bankteams working with BiH should consider the Performance Learning Review recommendations to map out all administrative processes toavoid similar issues in the future. Indicators require readily available data tomeasure the financialsustainability of a real estate registration system. The PDO included an element related to the financial sustainabilityof the FBiH real estate registration systems. The results framework initially included indicators to measure the revenues and costsof these systems. During implementation, the FBiH GA realized it was not possible to monitor these indicators. In FBiH, thereremained two registries - the cadastre (under the jurisdiction of79 municipalities)and the land registry (under thejurisdiction of 31 municipal courts).The FBiH GA oversaw the cadastresystem but the Land Registration Offices (LRO) andcadaster offices did not have their separate records of revenues and expenditures. The attribution ofproject support to afinancially sustainable real estate administration system could not be easily determined. The AF will obtain implementingagencies business plans to include accurate data on the revenues and costs of the FBiH and the RS real estate registrationsystems. Also included are policy discussions on a sustainable institutional framework for real estate registration in the FBiH andself-funding status in both entities.
P128966 | MDTF FATA Emergency Rural Roads Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | RETF | IPF | 2013 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/499071488326333507/text/ICRR-Disclosable-P128966-02-28-2017-1488326328693.txt | http://documents.worldbank.org/curated/en/499071488326333507/pdf/ICRR-Disclosable-P128966-02-28-2017-1488326328693.pdf | The ICR contains three lessons of which one has general application beyond the project. It is notedbelow:Implementation of emergency projects in conflict areas with security issues inevitably poses seriouschallenges in terms finding and retaining qualified stafffor the project management unit. Inthis project, the director was changed four times and there were changes in other key staff, which affected project implementation.A more sustainable option is to not set up a separate PMU but train the implementing agency staff who are responsible forproject implementation.
P128968 | BR Marine Protected Areas Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/550891614701880704/text/Brazil-BR-Marine-Protected-Areas-Project.txt | http://documents.worldbank.org/curated/en/550891614701880704/pdf/Brazil-BR-Marine-Protected-Areas-Project.pdf | The ICR (p. 21-23) included several lessons learned, which were adapted by IEG: Including keystakeholders from as early as project conceptualization can have a positive impact on ownership and involvement. In thisproject, the Bank team collaborated with the science department at Petrobras from the beginning onwards. The collaboration alsoincluded Petrobras providing key data and eventually led to Petrobras supporting the projectfinancially. Engaging local communities increases longer-term sustainability of project outcomes. Inthis project, in each PA management councils were formed, which developed their own regulations. Also, those PAs, which organizedlarge meetings where relevant stakeholders were able to comment, achieved better results and stronger commitment as demonstrated inthe defense of the PAs against environmental incidents.
P129000 | South Sudan Rural Roads Project (SSRRP) | Eastern and Southern Africa | South Sudan | IDA | FCS | Infrastructure | Transport | SPF | IPF | 2012 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/467481504639478988/text/ICRR-Disclosable-P129000-09-05-2017-1504639470904.txt | http://documents.worldbank.org/curated/en/467481504639478988/pdf/ICRR-Disclosable-P129000-09-05-2017-1504639470904.pdf | The ICR listed eight lessons. The following lessons were selected by IEG (with someediting):1. Denominating works contracts in USD or in an equivalent stablecurrency, as well as including price variation clauses in contracts, may mitigate risks associated withthe devaluation of local currency in fragile environments. In the case of this project inflation and depreciation inthe value of local currency caused significant fluctuations in the prices of goods and services needed as inputs to execute theworks. Consequently, the performance of works in this project was negatively impacted because no contractual provision had beenmade for price escalations resulting from such fluctuations, which caused delays in construction and claims for compensation due tohigher costs in local currency terms.2. Innovative options should be sought toensure the continuous monitoring of the execution of works in the face of insecurity, includingthird-party monitoring. In a fragile and conflict environment, project sites may often become inaccessible,impeding independent or direct supervision of works, including the verification of expected outputs for payment. For this project,the delay in such payments may result in contractual claims. As a mitigation measure, the team could consider involving athird-party monitoring agent or United Nations Agencies to supervise the implementation of project activities in insecurelocations. Furthermore, the teamcould study the possibility of using high resolution satellite data to remotely monitor worksprogress.3. The provision of institutional strengthening support to governmentinstitutions should be carried out in a manner that ensures sustainable skill and knowledgetransfer. The Bank, throughout its continuous engagement with South Sudan, provided hands on support to beneficiaryinstitutions, particularly to the project management team, through TA by hiring expert consultants specialized in different areasrequired for project implementation (FM, procurement, ME, safeguards). This support included training and workshopsaiming at achieving skills and knowledge transfer to government employees over time. However, the knowledge transfer arrangementswere not sufficiently effective, resulting in over-reliance on consultants. It is also worthy of noting that theGovernmentdid not havethe capacity to absorb the consultants after the project closing, which has impeded retainingtechnical assets that could continue providing institutional support as well as knowledge transfer. To address this issue, theterms of reference for the consultantscould have been designed in such a way that knowledge transfer milestones aredeliverables linked to payment. For instance, one of the deliverables couldhave beenthat by the end of the firstquarter, the government employee attached to the FM consultant should be able to independently prepare and submit quarterly IFRs.Other regular training and capacity building support programs for Government employees should also beexplored.4. The establishment of grievance redressing mechanism (GRM) establishmentin development projects could enable communities to take ownership of the project. The development of a GRM under theproject proved vital as it did not only facilitate conflict resolution/management, but also enabled communities living along theroads to take ownership of the project. It served as a means to engage with citizens and facilitated the identification of sitesfor materials and work camps for the contractors, as well as hiring of workers from communities along the roads.
P129156 | Sudan Sustainable Natural Resources Management Project | Eastern and Southern Africa | Sudan | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099121324125510649/text/P129156-55a81603-37bd-40fa-a599-305eda401f7b.txt | https://documents.worldbank.org/curated/en/099121324125510649/pdf/P129156-55a81603-37bd-40fa-a599-305eda401f7b.pdf | The ICR identified several lessons. Three that are rooted in project experience and likely to be widely applicable are presentedhere with some adjustments.Establishing inter-agency mechanisms can be an effective way to obtain engagementacross various government sectors (ICR, Para 108). The establishment of such mechanisms at the central and state levelswas instrumental in fostering a shared sense of ownership and effective oversight across government sectors. They greatlyfacilitated the projects adoption of an integrated land approach, as demonstrated by the effective integration of wildlifeconservation measures into forest and rangeland interventions.By involving communities through participatorymanagement, projects can build social capital and empower communities to take ownership of natural resources (ICR, para109). The communities organized by the project took part in planning and implementation. For example, they took the leadin managing community nurseries. Community-led restoration of degraded land and other initiatives helped reduce conflicts betweenfarmers and pastoralists.Participating in regional knowledge platforms, such as Building Resilience throughinnovation Communication and Knowledge Services (BRICKS), can benefit projects by enhancing ME performance and buildingcapacity (ICR, Para 111). The BRICKS platform offered this project continuous guidance on ME data collection,analysis, and reporting. The guidance and tools provided by BRICKS/Sahara and Sahel Observatory (OSS) helped the project adopt GPStechnology to collect field data and integrate the data into a Geographical Information System. Through knowledge exchange oncommunity-led restoration, the project gained insights from the experiences of other counties in implementing community-ledrestoration initiatives.
P129267 | Gabon Investment Promotion & Competitiveness Project | Western and Central Africa | Gabon | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/450351593207424685/text/Gabon-GA-Investment-Promotion-and-Competitiv.txt | http://documents.worldbank.org/curated/en/450351593207424685/pdf/Gabon-GA-Investment-Promotion-and-Competitiv.pdf | Three lessons are drawn from the ICR (pages 29-30), with some adaptation, and will be relevant to similar projects.Business plan competitions, despite their headline value, may not be an economically efficient method to promoteenterprise development, or even highly effective without an enabling business environment. In this project,twobusiness plan competition episodes delivered all project targetsfor business formation, job creation, and SMEfinancing. However, the business plan competition also posted a negative economic rate of return and negative net presentvalues at various discount rates. Moreover, the job creation numbers were difficult to verify, according to the ICR. The ICRalso cites evidence elsewhere that: judges of contestantsinbusiness plan competitions do poorly at pickingwinners; there is generally a valleyof death inearly-stage financing (i.e.,difficulty ofcovering the negative cash flow in theearlystages of a startup, before new products or services drawrevenue fromreal customers); and SMEs created at competitions will not likely grow without more conducive business ecosystems.Lessemphasis on start-ups and greater support to operating businesses, including through access to finance interventions, would be abetteralternative.It is efficient for governmentsto give project implementation units thepowers necessary for them to fulfill their responsibilities.In this project, the Project Implementation Unitat the Ministry of Investment Promotion had supervisory and fiduciary responsibilities over the project. But, the ProjectImplementation Unit lacked decision-making authority, according to the ICR. Rather, authority rested with ANPI-Gabon, whichwas created under thisproject to coordinate the governments investment promotion, business registration, and SME supportactivities.Private sector development requires more strategic interventions than simplifying businessregistration and rationalizing the governments investment promotion apparatus. In this project, the creation ofthe ANPI-Gabon as the single body for investment promotion, business registration, and SME support was a good start. But inGabon, as in other developing countries, there are many more critical areas for improving the investment climate and fosteringenterprise development: governance reforms at SOEs, provision of investorprotections, assurances of contract enforcement,easing theburden of government regulation, ensuring the efficiency of the legalframework in settling disputes, settingthe norms of shareholder governance, and fostering an entrepreneurial culture.
P129282 | Regional Trade Facilitation and Competitiveness DPO | Other | Africa |  |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2019 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/208121549909314524/text/Africa-Regional-Trade-Facilitation-Competitiv.txt | http://documents.worldbank.org/curated/en/208121549909314524/pdf/Africa-Regional-Trade-Facilitation-Competitiv.pdf | The ICR has the following lessons with which this review agrees. Regional programs in which twocountries are involved in reforms are more likely to succeed if the two countries have more similar economic strengths or attachequal importance to the proposed reform agenda. For example, transit trade is more important for Togo than for CtedIvoire, andTogos economic relationship with Burkina Faso is more equal; Policy operations like the tworeviewed usually need technical assistance for carrying out many of the changes the operations support. Accompanying technicalassistance is essential for implementing the reforms; Difficult reforms require more than two years to work through thevarious stages to ensure implementation; Greater attention needs to be paid to prior analysis when designing a program.Both the poverty and social impact analysis and the political economy study identified potential losers and the risk of vestedinterests obstructing the reforms. These studies do not seem to have been adequately taken into consideration; Greatercarein definingresults indicators and targets eases program monitoring and assessment ofresults.IEG adds the following lesson, related to the penultimate bullet pointabove:Reforms carry with them changes in incentives. For reforms to succeed, it is necessary that theimplicit incentives the reforms create are aligned with the true incentives that are required to generate the expected results ofthe program.
P129326 | MA MSME Development Project | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/342831537371685408/text/Morocco-MA-MSME-Development.txt | http://documents.worldbank.org/curated/en/342831537371685408/pdf/Morocco-MA-MSME-Development.pdf | Three lessons are drawn from the ICR (pages 25-26), with adaptation.PCGs can encourage PFI lending to VSEs, apartfrom lending to SMEs. The number and volume of PFI loans to VSEs rose the largest among three categories of MSME lending inMorocco over 2012-17. PCGs for VSE loans were highly valued by PFIs, according to the ICR. It also helped that lendingcriteria were simplified andguarantee processes were streamlined (guarantees were approved within 48 hours)tofacilitate lending to VSEs(four PFIs rampedup guarantee usage forVSE loans).Projectsimplemented by existing institutions with a strong capacity and successful track record are best placed to achieve success.Established in 1949, the CCG had a long operating history and a successful record of PCG operations. The choice of the CCG asimplementing agency obviated the need to create a new institution, with attendant organizational pains.The CCG had strongorganizational capacity and strong management skills, according to the BAM, which supervised the financial institution. Ithad a low turnover of staff managing the project and performed its duties efficiently, according to the ICR.Complementary TA strengthens project implementation. The project was accompanied by technical assistance, which furtherstrengthened the capacity of the CCG and improved capacity in the banking system to serve MSMEs in Morocco. Although notembedded in the financing operation, the technical assistance was conveyed through the MENA Regional MSME TechnicalAssistanceFacility.
P129342 | Piaui: Pillars of Growth and Social Inclusion Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099171502172336826/text/P1293420d251060600bd890b3b7be342428.txt | http://documents.worldbank.org/curated/en/099171502172336826/pdf/P1293420d251060600bd890b3b7be342428.pdf | The ICR (pp. 37-38) offered some lessons and recommendations, including the following lessons re-stated by IEGReview:Intense land disputes arising from land tenure regularization programs can be minimized by close andcontinuous communications with all interested population groups. The project strengthened the capacity of the State LandAgency and judiciary mechanisms and started working with two groups (agrarian settlements and Quilombola communities). As a result,other groups felt that they were left out, triggeringcomplaints. The project could have expanded its consultations andengagement by reaching out to all interested groups to seek their feedback and to clarifyits approach to landregularization.The concomitant utilization of a Development Policy Loan with a parallel Investment ProjectFinancing, both prepared in close coordination, provides a powerful approach to support reforms. The structure of the DPLsupported the IPF objectives and set in motion prior actions needed to put in place the legislative and institutional framework forthe implementation of investments under the IPF and for improving public sector management. Areas of alignment and complementarityincluded secondary education, access to chronic disease services, registration of groundwater, land tenure regularization, andparticipation in rural productive value chains.
P129381 | Ghana Partnership for Education | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2013 | 2017 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/689041498487098434/text/ICRR-Disclosable-P129381-06-26-2017-1498487086340.txt | http://documents.worldbank.org/curated/en/689041498487098434/pdf/ICRR-Disclosable-P129381-06-26-2017-1498487086340.pdf | Lessons drawn from the ICR: Project design built on tested pilot interventions, along with capacity buildingsupport, contributed significantly to smooth and timely uptake of project interventions. In the case of this project, thedecentralized institutional arrangements, grants program, and unqualified teacher training program had all been recently pilotedand lessons learned were incorporated in the project design. Continued capacity support to local government and school staffwas also included. Transparent and objective targeting criteria ensured appropriate political support and effectiveimplementation. In the case of this project, clearly defined criteria based on education and poverty indicators ensured thatthat funds were targeted to the districts most in need, and limited political capture of benefits. The unqualifiedteacher training program appears to be a cost-effective alternative to the more formal diploma program.In the case ofthis project, data demonstrated significant lower costs. including in underserved areas, alongside similar performanceratingscompared tothe more conventionally trained teachers. However, while the participants in the unqualifieddiploma program appear more likely to remain in the underserved areas (as they are more likely to speak the local language and arefrom the local community), there is also a higher attrition rate in completing the training.
P129397 | Montreal Protocol Hydrochlorofluorocarbons (HCFC) Phase-out Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2014 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/142981556892455506/text/Argentina-Montreal-Protocol-HCFC-Phase-out-Project.txt | http://documents.worldbank.org/curated/en/142981556892455506/pdf/Argentina-Montreal-Protocol-HCFC-Phase-out-Project.pdf | The lessons are taken from the ICR (paragraphs 66-69) with some modification of language.Asector-plan approach rather than an enterprise-level approach may provide a clear and effective strategy for achieving full ODSphase-out. The project was based on an overall sector evaluation rather than on an enterprise-level basis. An individualenterprise approach would not give a clear picture on how the country could completely phase out the remaining ODS consumption. Thesector plan approach developed under the project provided the necessary overall picture and helped to determine the appropriatestrategy on how to address the remaining consumption with a differentiated approach to major enterprises andSMEs.The use of retroactive financing (RF) arrangements as part of a project design can provecritical to achieve timely results and resolve effectiveness delay. As indicated in paragraph 67 of the ICR, the flexibleapproach to retroactive financing was beneficial, since due to the delay in reaching effectiveness, major works needed to becarried out in advance of payment by the Project. Given the Banks participation in the design of this component of theProject, it was possible to apply all the Bank requirements to the planning and execution of the relevant activities. Whilenot a normal situation, including the additional flexibility for retroactive financing in the design of this component allowed theworks to be carried out in a manner that ensured that Bank safeguards and other requirements weremet.Subsidies aimed at cleaning industries might have a better uptake if complementarymeasures are also put in place, including addressing the needs of the targeted enterprises. As indicated in paragraph 68of the ICR, the targets for chiller replacements were not met. The upfront financial subsidy covered only 20-33% of the equipmentcost of chiller replacements. Substantial additional upfront subsidies, clear financial benefits such as reduced operating coststhat have a real impact on the business, and/or enforceable regulations requiring compliance by private sector entities wouldpotentially have been necessary to reach the target. It is suggested in the ICR that fuller financial models of theconversion at the targeted enterprises were needed, which would have been beneficial, however the specific enterprises were notknown at the outset of the Project when the targets were being set. It would have been beneficial to undertake reviews andrecalibrations of relevant targets over time as the serious obstacles to meeting them becameevident.Promotion of project teams that are integral parts of line ministries rather thanseparate units may improve the Banks ability to add value and institutional strengthening. Working with nationalline ministries and existing government structures may prove effective in strengthening national institutions rather than creatingparallel structures with separate PIUs/PCUs. The cost of this may however be less effective and efficient project execution due toa potential lack of capacity within national bureaucracies compared to professional PIUs/PCUs. Which approach to take may need tobe addressed on a project by project basis, taking account of specific country or counterpart capacities and circumstances.
P129401 | Guiyang Rural Roads Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099910012232134350/text/China000Guiyang0Rural0Roads0Project.txt | http://documents.worldbank.org/curated/en/099910012232134350/pdf/China000Guiyang0Rural0Roads0Project.pdf | The ICR draws the following two lessons from the experience of implementing this project, with some adaptation oflanguage.1. An adaptive design and implementation scheme can be helpful in preparing rural roadsprojects. Theadaptive approachused in this project consisted of identifying and preparing for only one of thefive batches ofroadsatappraisal. The subsequentbatches were to be identified during project implementationbased on a set of pre-defined criteria.This approach aided in speeding up projectpreparation time and improved thereadiness for implementation.2. A counterpart funding assurance mechanism can be an effective tool to avoida funding shortage and resultant implementation delays, but it needs to be enforced.The mechanism employed inthisproject required the participating local governments to submit a fund guarantee letter together with their annual projectproposals and deposit their funding upfront in a designated project account.After weak enforcement of this mechanism in theinitial years, which led to delays in some civil works,the mechanism was effective, andthe availability of counterpartfunding functioned as a criteria for identifying subsequent batches.
P129408 | RI-Regional Pastoral Livelihoods Resilience Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061623180511099/text/P1294080fba41a002086d507a560a709e19.txt | http://documents.worldbank.org/curated/en/099061623180511099/pdf/P1294080fba41a002086d507a560a709e19.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1. Having aregional partner in place to provide key oversight, support, and coordinateimplementation guidance may enhance theprojects potential to address regional pastoralism challenges successfully.The project experience showed thatIGAD s involvement in the project resulted in strong coordination in implementing activities and cohesive results. Theregional approach of the project helped address conflict management, harmonized disease control actions, and identification ofinvestments in jointly used cross-border water and market infrastructure.2. Joint planning and monitoringplatforms between participating project countries mayfacilitate the exchange of information, lessons, and knowledge/skills inregional projects.This facilitated institutional learning across the three countries and facilitated the sharing ofsuccessful approaches to key interventions, such as traditional methods of rangeland management, which IGAD documented in policybriefs that were produced. Furthermore, joint facilitation was found to be the most effective way of controlling cross-borderdisease outbreaks.3. Diversifying into activities less prone to risk can provide a buffer for pastoral communitiesto better withstand and recover more quickly from shocks, including conflict. The project could have providedmorefor additional interventions that could bring about significant returns to investments made in livelihood activities,especially stronger business facilitation and access to markets. While livelihood activities undertaken were viable, more couldhave been done in terms of assessments of those activities that could potentially yield better returns thanlivestock and movemore communities out of livestock herding given the growing risks, compounded crises and uncertainty faced bypastoralists.
P129431 | Anhui Xuancheng Infrastructure for Industry Relocation | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2013 | 2021 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/857211624299727878/text/China-Anhui-Xuancheng-Infr-for-Indust-Reloca.txt | http://documents.worldbank.org/curated/en/857211624299727878/pdf/China-Anhui-Xuancheng-Infr-for-Indust-Reloca.pdf | Key lessons adapted from the ICR areas follows:Enterprise selection criteria for industrial zones shouldalign closely with the objectives ofthe zones. Flexible entry criteria to a zone can cause short term gains such astax revenues, but long-term disadvantages includingenvironmental degradation, lack of economic sustainability andfirmsleaving,as occurred in Phase 1 of XETDZ. The Zone Administrations consistent application of a high- screeningprocesssecured enterprises that were both environment friendly but have stayed and grown.A price adjustmentclause to all contracts canensure timely delivery and performance of contractors in cases where there aresignificantchanges in the commercial environment.The project experienced significant price increases of material forcontractors, which caused time-consuming reviews by the PMO and reduced the motivation of contractors to complete some works,resulting in implementation delays. This was particularly the case in contracts of less than 18 months in duration, forwhichthere was no price adjustment clause. To mitigate this risk, a price adjustment clause should also be consideredfor civilworks contracts of less than 18 months.Plan infrastructure facilities for the long term but build in phases toavoid undue over-capacity.The WWTP and its site were planned for a total capacity of 50,000 tons per day but only25,000 tons per day capacity was built initially taking into accountdemand projections. This practice allows forfutureexpansion, if and when required.Site visits anddemonstrations of resultscan help build stakeholderconfidence and acceptance of interventions.To address villagers concerns about the WWTPs effluentoutfall, the PMO arranged study tours to WWTPs with similar site characteristics where effluent discharge approaches weredemonstrated. This engagement, combined with an adjustment of the design, led toadapted and fully accepted designs, whichbuilt trust between the villagers and the Zone Administration. Such experiential activities should be included in stakeholderdialogue and consultations during early project preparation for buy-in up front to avoid issues during implementation andconsequent delays.Adjust the size of industrial parks to the anticipated effective demand. Specialeconomic zones and industrial parks are popular in developing countries as vehicles forattracting investments and promotingeconomic development.However, if theyfail to achievecompetitive advantage theyend up consumingland,and sometimes public resources such as tax incentives, without adequateeconomic, social, or environmental outcomes. The sizeof the XETDZ Phase 2 area was reduced based ona revised demand projection to achieve better outcomes and improved developmentefficiency.
P129472 | Senegal Health & Nutrition Financing | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/821421592604236801/text/Senegal-SN-Health-Nutrition-Financing-FY14.txt | http://documents.worldbank.org/curated/en/821421592604236801/pdf/Senegal-SN-Health-Nutrition-Financing-FY14.pdf | The ICR (pp. 39-40) offered lessons and recommendations, including the following lessons, restated byIEG:Program ownership at all government levels is essential to ensure the success of RBFschemes.Under the project, the RBF program was accepted but not actually owned by the sector, resulting in slowimplementation.Ensuring the success of a project requires carefully designed institutionalarrangements, and a level of support proportionate to the capacity of entities involved. Under the project,institutional arrangements required striking a balance between using government systems and pursuing adaptations in financialmechanisms and staff incentives to facilitate effective implementation. Despiteimplementation challenges, an investment project can lay the foundation for a future partnership between the Bank and the Client,with agreed modes of support tailored to the Clients needs. Although RBF implementation in Senegal was challenging,both parties collaborated to develop a follow-on operation, and used the learning experience of theproject and some of itsmethods, such as quality check-lists and aweb-based platform, and added focus on results in the follow-on project to improvethe quality of health care and management practices.
P129489 | MZ First Agriculture Development Policy Operation AgDPO-1 | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/345771530232496113/text/Mozambique-MZ-Agriculture-DPO-1.txt | http://documents.worldbank.org/curated/en/345771530232496113/pdf/Mozambique-MZ-Agriculture-DPO-1.pdf | Summary of lessons learned: DPO series objective should beconcrete and measurable, linked to toimplementation. Achievements stemming from prior actions should be strongly focused on the PDO and well-measurable. Dataavailability and instrument should be well planned in advance. It is important to ensure that any risks related to dataavailability are identified and accounted for upfront before concluding project preparation, and inform the Results Framework (ICR,para 80). Technical assistance facilitates the positive results of a DPL. The team rightly identified the need to buildboth administrative and technical capacity of institutions that implemented reforms and was instrumental in shortening the learningcurve (ICR, para 81) The design of a programmatic series should account for the risk of cancellation, particularly if itis a common occurrence in the region. The termination of the third operation in the series could have been mitigated by bettersequencing. (ICR, para 83).
P129524 | MZ-Social Protection project | Eastern and Southern Africa | Mozambique | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099140002232318834/text/P1295240ef6cf5060089d60e29f433317a0.txt | http://documents.worldbank.org/curated/en/099140002232318834/pdf/P1295240ef6cf5060089d60e29f433317a0.pdf | The ICRoffered several lessons and recommendations, including the following lessons restated byIEG: Adoption of a flexible approach in project design with long term vision can pay off toestablish the building blocks of a safety net system. Despite being relatively complex, Banks choice of public works programover preferred cash transfer allowed Mozambique and the Bank to work together and support the vulnerable population when they wereexposed to shocks. Coordination and communication between Government and other development partners isimportant to support the long-term vision. The ICR noted that sustained dialogue with the Government and other partnershelped Mozambique to build a broader view of the social protection system rather than a fragmented set ofinterventions. Labor-intensive PWP can play a key role for gender empowerment and climate changeresponse. The PWP evolved to have greater flexibility to reach more vulnerable households and ensured more womenparticipation. With this adaptation of eligibility criteria and flexibility, the intervention was more inclusive and moresuccessful to tackle post-emergency needs. In the context of climate change response, the ICR (Annex 8) mentioned that PWP was alsoused in sub-activities such as mangrove reforestation, infrastructure repairs, access roads rehabilitation to reduce climate changeimpacts after Idai, Kenneth and Eloise cyclones. Establishment of PIU in a context of weak institutional capacityand lack of previous work experience with WB projects implementation can be more effective and efficient. The ICRmentioned that since INAS did not have previous experience in working with WB projects, the lack of a PIU was reflected in a slowerimplementation at INAS, despite the additional support provided by technical staff. Drawing a parallel with similar socialprotection projects with PIU in Ethiopia, Tanzania, Rwanda, and Burundi, the ICR stated that implementation was stronger when PIUsled implementation with the agencys regional offices.
P129539 | Second Serbia Health Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099012524164042458/text/P12953912389d20f91a98d1baa1f31a74df.txt | http://documents.worldbank.org/curated/en/099012524164042458/pdf/P12953912389d20f91a98d1baa1f31a74df.pdf | The following lessons selected are the most relevant of the eightlessons presented in theICR: Continuous involvement of the Bank in a specific sector can buildtrust amongst actorsin thatsector. Thisproject built on long-term World Bankengagement in the transformation of the health care systeminSerbia. Engagement of all stakeholders in the preparation,implementation and evaluation of aproject canensure synergistic effects, ensure active participationand institutionalize responsibility. In this project,smoothadoption of the Health Care Network Optimization Plan was facilitated by the process of its developmentwhichincluded both public discussions and a broadconsultative process.IEG offers an additionallesson: Health system quality indicators that focus on outputs such as utilization provide insufficient evidence todetermine improved quality. In this project, despitenotable achievements in outputs such as new clinical pathways andfinanced quality improvement projects, there was insufficient evidence to demonstrate the translation of these outputs intoimproved quality.
P129563 | Anhui Yellow Mountain New Countryside Demonstration Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/924111623173233738/text/China-Anhui-Yellow-Mt-New-Countryside-Demo.txt | http://documents.worldbank.org/curated/en/924111623173233738/pdf/China-Anhui-Yellow-Mt-New-Countryside-Demo.pdf | The operation offered five lessons that may benefit task teams in designing future similar operations. Four of these have beentaken from the ICR with slightly modified language (ICR, paragraphs 86-90) A cost-effective combination ofhard investment (infrastructure) andsoft interventions (skill building,promotionalactivities) couldimproveservices and create rural jobs.Investmentsin roads, water systems, andwastewater facilities,were accompanied bysoft interventions to strengthen OM capacityfor thesebuilt assets. Improvedirrigation was accompanied by training inagricultural practices. Beneficiaries hadimprovedaccess tomarkets and economic opportunities, and gained OM know-howto extend the life oftheproject-assistedassets. Skills fostered entrepreneurship to improvethe rural economy and help sustainthe villageenvironment. Integrating human capital development with cultural heritage tourism could help sustain neweconomic ventures. Human capital and institutional capacity were simultaneously developed whileinfrastructureinvestmentspreservedcultural heritage. The strategycombined skill building in tourism serviceswhiledeveloping or preserving cultural heritageassetsandpromoted the adoption of modern agriculturetechnologies to generate new business ventures. The communities improved their living conditions, thus contributing to the social,economic, and environmental sustainability of the villages. In 2018, the government adopted thisintegrated approach in itsRural Revitalization Strategy for local governments rural development programs. Creating a basketofeligible investments may allowrapid replacement ofdropped investments when prioritieschange.More projects than were budgeted were included in the feasibility studies and appraisedat preparationthat participating villages identified. As a result, when unforeseen circumstancessuch as loan savings or change ininvestment priorities or investments that were eventuallyself-funded, replacement activitieswerereadily availablefor implementation. Balancing betweendemonstrating impact and expanding geographic coverage may be usefulto consider. Sixty eight villages (out of 165, ICR, footnote 1) coveringa wide geographic spread providedthemunicipal government with a critical mass to showcase howcombining improvements in hard infrastructure servicescould be combined with soft capacity enhancements to bring about income generatingopportunities. Numerous factorswere involved in selecting participation byvillages and determining eligible infrastructure investments and capacityinterventions to ensure successful project outcome.Future similar projects that may involve numerous small-scale investmentsover awider area may benefit from using results-based factors to balance site selection and choiceofinvestments.
P129565 | West Africa Agricultural Productivity Program 2A | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/219351574696583170/text/Western-Africa-West-Africa-Agric-Productivity-Prog-2A.txt | http://documents.worldbank.org/curated/en/219351574696583170/pdf/Western-Africa-West-Africa-Agric-Productivity-Prog-2A.pdf | The projects implementation and management experience yield the following lessons, of which lessons 1 and 4 are adaptationsfrom the ICR:1. A regional (multi-country) approach for a technology development program enables better accessto international expertise, economies of scale in researching technologies, cross-border exchanges of new technologies, andpotential for constructive competition between participating countries.WAAPP-2A,supporting a combination ofcountries, was large enough to get technical support from international centers of excellence, whereas each country alone wouldhave attracted less support. Likewise, research and dissemination of some technologies Is too costly for any one of the countriesacting alone. In this case, performance benchmarking encouraged constructive competition between thecountries.2. .A technology development program needs to be results-based.In this case,the ICR reviews the development and adoption oftechnologies without articulating the results of such technologies. Thefocus in the results framework ison numbers of participants, area under new technologies, number of technologies, etc.Theultimateoutcome of a project such as WAAPP-2Awould beincreased productivity and incomes. Withoutreviewing results (yields, net incomes, and, as relevant, labor savings, soil water retention, etc.) the ultimateoutcomesfrom new technologies are less evident.3. An integrated combination ofagricultural research andextensionsupported bya media agricultural information system can be an effective way oftransmitting knowledge andencouraging adoptionof new technologies. In this case, WAAPP-2A linkedagricultural extension and research. Ghana in particular developed a web-based agricultural information system with 880,000hits per annum. Ghana used the web as a core part of farmer outreach. The extension staff used web information intheir contact with farmers,leveraging its impact. Importantly, the research programwas applied research focused onagricultural needs and contained a grant program to finance independent activities to generatetechnologies.4. A sustainable funding mechanism is essential to assure long-term sustainability of aregional and cross-country technology development program.In this case, the overall WAPPAA program relies on thepolitical will of participating countries for funding of the national and regional programs. This is based on each countrysannual budgeting process with year by year prioritization between sectors and within sectors influenced by political considerationswhich may provide insufficient or unreliable funding. As a promising initiative, the Ghana WAPPAA -2A program has initiated amechanism for producer organizations to contribute funding for theagricultural research and technology development programs.Agricultural commercialization is expected to make suchfinancing easier.5. Building theinstitutions, expertise and processes for development of agricultural technologies is a long-term process requiring continuedfinancial and technical support. This project was an Adaptable Program Loan, a more suitable long/medium-termfinancing vehicle than a conventional loan, andan instrument thatcould beincreasingly adaptive asexperienceis gained.6. Safeguards need clear articulation in the PAD and clearcorrespondingassessment in the ICR,including reviewduring project implementationenabling adaptation asneeded.The ICRs discussion of environmental and social safeguards, and, to a lesser extent, fiduciary matters,provided few details on issues and actions, and the safeguards themselveswere not tabulated. The PAD had similarshortcomings.
P129597 | First Competitiveness and Growth Development Policy Operation | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2013 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/751011498859529284/text/Georgia-DPO-I.txt | http://documents.worldbank.org/curated/en/751011498859529284/pdf/Georgia-DPO-I.pdf | IEG draws the following four lessons from the experience of this series:1. Incomplete results chains will undermineefficacy assessments. In this Program, the first objective was materially equivalent to the reforms that underpinned it.Trade-related reforms (e.g., on food/feed safety, competition) comprised the stronger legislation sought under theobjective. In this case achievement of the reforms (enactment and implementation) is equivalent to achievement of the objective andthus there is no meaningful efficacy assessment exercise.2. Monitoring indicators that do not accuratelyreflect objectives will also undermine evaluation. An example in the Georgia Program is the indicator used to reflect generaleducation quality, which was defined as the share of teachers that attended training on learning processes. While this indicatormay be related to actual learning, it does not measure it directly. The point of an evaluation in this case is to assess whethersuch training actually was effective in raising student test scores. Another example is the indicator for accessibility of healthservices, which was defined as the percent of theoretical coverage (Decree introducing Universal Health Coverage). The latter doesnot reflect actual health attention to the covered population.3. Attention to the more specific risks of anoperation (in addition to the broad political, macroeconomic, and capacity risks) will better anticipate implementation problems.The Georgia program suffered delays on a number of reforms (e.g., international standards, trade facilitation, and power) thatmight have been anticipated with a more detailed articulation of risks.4. An unfocused set of objectiveswill detract efficacy as it does not allow for synergies across objectives. In the Georgia DPO, areas such as customs efficiency,targeted social programs, and power sector reliability were mutually unrelated and thus unlikely to support each other.
P129600 | Benin Global Partnership for Education Program | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/409081559158643489/text/Benin-03-Global-Partnership-for-Educ-Program.txt | http://documents.worldbank.org/curated/en/409081559158643489/pdf/Benin-03-Global-Partnership-for-Educ-Program.pdf | The ICR (p. 38-39) provided lessons learned, summarized here byIEG: Equipping a project implementation unit with adequate staff can ensure stability andcontinuity of project implementation during political changes. In this project, the governmentsadministration changed in 2016, resultingin the restructuring of the education ministries and re-organization of leaddirectorates responsible for project implementation. Even though it took some time for the new staff in the education ministries toget up to speed, the presence of the project implementation unit was critical for ensuring knowledge transfer and keepingimplementation delays to a minimum. Having complementary data sources available in case of delays in nationaldata collection is critical whena projects ME relies on national data for measuring progress towards the PDO.In this project, three out of seven PDO indicators were dependent on data collection from the EMIS. However, EMIS datacollection was often delayed by several months, complicatingassessment of these indicators when the projectclosed. Establishing feedback mechanisms to allow for continuous and regular assessment of project activities iscritical for making adaptations when necessary. In this project, the assessment of teacher competencies and subjectspecialization allowed for modifications in teacher training by grouping teachers according to their capacity and subjectspecification.
P129633 | Improving Climate Data and Information Management | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2023 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061223153537272/text/P129633025a57f0d40a223073cfec4fad4a.txt | http://documents.worldbank.org/curated/en/099061223153537272/pdf/P129633025a57f0d40a223073cfec4fad4a.pdf | The ICR (p. 27-28) included several useful lessons learned which were adapted by IEG: Expertise withinimplementing agencies and continued capacity building may ensure the sustainability of project outcomes. In this project,the Water Resources Authoritystaff installed all the equipment within the water monitory system resulting in cost and timesavings since no externa specialist had to be hired. Also, when the Meteorological Service of Jamaica(MET Service) lost staffdue to retirement, it provided training across all divisions instead of outsourcing the installation, operation, and maintenance ofthe systems. Identifying and engaging with local stakeholders can positively impact projectimplementation. This project conducted stakeholder mapping and a feedback mechanism during the initial phase to ensurerepresentation of all local stakeholder groups in the needs-assessment process as well as their feedback resulting in identifyingthe most viable and widely accepted solution from a broad range of proposals, which further ensured project effectiveness andsustainability. The availability of a Project Preparation Grant (PPG) may allow for designing aproject that is technically sound and identifying potential implementation bottlenecks. In this project, the ReportState of Jamaican Climate allowed for conducting all the necessary technical assessments, developing the hydro-metneeds prioritization, as well as conducting extensive stakeholder engagement.
P129640 | Bolivia Climate Resilience - Integrated Basin Management | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099010002232265003/text/Bolivia000BO0P02000Basin0Management.txt | http://documents.worldbank.org/curated/en/099010002232265003/pdf/Bolivia000BO0P02000Basin0Management.pdf | The ICR presents five lessons arising from this project (ICR, paras. 115 119). This review highlights the two mostrelevantlessons,which could be applicable toother countries/similar type of projects.Lesson 1:Importance of establishing and strengthening strategic alliances among key stakeholders, especially for complex projects(ICR, para. 117): At the time of preparation and early stages of implementation, the project used only a fewalliance-building instruments. During implementation, the project developed and used additional formal and informal alliances, withdifferent stakeholders, which contributed to project performance. Para. 117 provides 3 positive examples of effective alliances,together with their tangible results. The lesson fromthis project is:Work out and ensure strong alliancesat the project design stage with relevant stakeholders (and not only Government actors), and to nourish thesealliances during implementation, using various project activities.Lesson 2: Relevance of formulating andimplementing a clear strategy to achieve sustainable project results (ICR, para. 118): This project, especially involvinga strong capacity-building orientation, illustrates the importance of ensuring a clear and sound strategy for achieving theproposedstrategic PDOs and project sustainability, from the project design stage, and throughout projectimplementation, notwithstanding some shortcomings in the PDOs for this project. The ICR shares a positive example ofhow the project-supported network of installed hydrometeorological stations was sustained through shared responsibilities among therelevant entities. In this instance, SENAMHI used its expertise in the design of the network and selection of stations, whereas theparticipating municipal governments committed to the maintenance of the network. These shared arrangements ensured that: (i)quality data areaccessible and shared between participating entities; and (ii) the stations are in continuous operation.Accordingly, this project highlights the lesson of the importance ofensuring appropriate collaborative arrangements andsupportive mechanisms for the sustainability of OM requirements of relevant project activities (e.g., in this project,the arrangements for various monitoring activities and the extensive investments in infrastructure for IRBMsub-projects).
P129647 | Peru Strengthening Sustainable Management of the Guano Islands, Isles and Capes National Reserve System Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/912391580140880068/text/Peru-PE-Strengthening-Sust-Mgmt-Guano-Islands.txt | http://documents.worldbank.org/curated/en/912391580140880068/pdf/Peru-PE-Strengthening-Sust-Mgmt-Guano-Islands.pdf | The ICR (p. 22-24) provided lessons learned which were adapted by IEG: Planning adequate time forbuilding capacity and providing training at the beginning of implementation of a project intended to improve environmentalmanagement and protect biodiversity is an important aspect of project design. Also, sufficient time needs to beallowed for collaborating and building consensus with local communities and among different stakeholders. In thisproject, SERNANP had limited experience in managing marine and coastal ecosystems and participatory planning processes whichresulted in initial implementation delays and in some collaborative sub-projects only being executed only during the last year ofproject implementation. Also, the Chincha-Ballestas Island Site Plan was developed under a participatory process involving 22 localcommunities and stakeholders. While this took some time, it resulted in greater ownership and bettercollaboration. Public financing for biodiversity and ecosystem services will require subsidizing from othersources. Therefore, it is important that fund-raising efforts for the endowment of conservation funds start early iftargets for capitalization are to be achieved and the sustainability of biodiversity and ecosystem conservation is to beensured.
P129652 | Development Policies for the State of Sergipe | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | DPF | 2013 | 2015 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/174921467994142052/text/ICRR-Disclosable-P129652-07-08-2016-1467994133106.txt | http://documents.worldbank.org/curated/en/174921467994142052/pdf/ICRR-Disclosable-P129652-07-08-2016-1467994133106.pdf | The ICR (pp. 26-27) provides several important and useful lessons, including:It is a challenge toidentify appropriate and monitorable results indicators for broad policy actions. In this case, someof the indicatorsmeasured broad performance of the State rather than specific actions attributable to the Operation, while others were too narrow tocapture thefull scopeof the policy action and objective.Coordination across different levels ofgovernment requires careful and specific attention. In this case, approvals and other bureaucratic issues from levels ofgovernment not directly involved with program implementation created bottlenecks that could have been avoided through pre-signedagreements or other anticipatory, proactive mechanisms.IEG adds one additionallesson:Achievement of objectives involving the extremely poor require actions and indicators targeted atthis group. In this case, full measurement of achievement of the objective to expand economic opportunities for the extremelypoor was not possible due to non-specified targeting and measurement.
P129663 | Afghanistan: System Enhancement for Health Action in Transition Project | South Asia | Afghanistan | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2018 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/413971578586269801/text/Afghanistan-System-Enhancement-for-Health-SEHAT.txt | http://documents.worldbank.org/curated/en/413971578586269801/pdf/Afghanistan-System-Enhancement-for-Health-SEHAT.pdf | The ICR (pp. 46-47) offered several lessons and recommendations, including the following lessons re-stated byIEG:Contracting with NGOs facilitates effective delivery of health services in fragility, conflict, and violencesettings.Under the project, contracted NGOs were able to effectively provide basic packages of health services,forge alliances with local leaders, and adapt to specific local situations in ways that would not have been possible for governmentstaff.Investing in robust monitoring and evaluation facilitates oversight, implementation guidance, andassessment of intended results based on reliable data. Under the project, adequate spending on quality ME, enhancedby an independent agency, resulted in proper household and facility surveys andimpartial verification of routine data,followed by rigorous data analysis, disclosure,and publication.The consolidation of resources fromdevelopment partners in one trust fund can enhance the potential of meeting project needs in a rational manner, and in promoting analigned vision for a collective development agenda with the government. Under the project,the consolidation offinancing was instrumental in reaching the above benefits. Also, a capable national team was able to leverage the consolidatedfinancing mechanism in pursuing the attainment of project development objectives.
P129688 | Third Phase Community Based Rural Development Project | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/696591580221959305/text/Burkina-Faso-BF-APL-3-Com-Based-Rur-Dev-III.txt | http://documents.worldbank.org/curated/en/696591580221959305/pdf/Burkina-Faso-BF-APL-3-Com-Based-Rur-Dev-III.pdf | The ICR proposed four lessons. The following two lessons were drawn from those in the ICR (para.94-97), with some changes inpresentation:A demand-driven communitydevelopmentwithout a clear targeting strategy at entry and aneffective incentive mechanism to attract participation runsa highrisk of underachieving itsobjectives.In this project the example was that, despite astrong focus at project design onfinancing natural resource management and local development of income generating enterprisesusing a community drivendevelopment (CDD) model, in practice the communities preferred investing available funds in social public goods with immediatebenefits rather than long term development programs.The lesson is that without a mechanism in the Financing Agreement thatframes the direction of the demand for funding andestablishes a threshold for each potential type of microproject,strong operational guidance, and effective communication to the beneficiaries, a CDD typeprojectis likelyto underachieve its development objectives.Sustainability and continuous enhancement of decentralized support andautonomous financing are essential to achieve sustainable development.In thisprojectsatisfactory results were achieved in building technical and institutional capacity for theimplementation of local development plans, but sustaining that capacity in the longer term to achieve higher order objectives suchas poverty reduction after the project closed could not be assured since there was no plan to continue collaboration betweencommunities and municipal/regional planning.There is therefore a considerable risk that technical and institutional capacityand budgeting institutions cannot be maintained due to inadequate financingand that development projects already constructedwill not be maintained, infrastructure will deteriorate. Consequently, new development programsmay divert local financingfrommaintenance to new operations, and hence the original projects will finally be abandoned. The lesson from this project is thatthe momentum of sustainable rural development can only be maintained with strenuous efforts to ensure long term local technical andfinancial resourcesand strong institutions to overcome the cycle of funding of new projects replacing previous projects.
P129713 | DRC Urban Development Project FY13 | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099520008312244277/text/P12971307847c50a40aeef02bf414a86e59.txt | http://documents.worldbank.org/curated/en/099520008312244277/pdf/P12971307847c50a40aeef02bf414a86e59.pdf | The ICR provided 7 lessons and recommendations (ICR, paragraphs 92-98). The more important ones are presented below with slightmodifications: Civil servants may implement projects to build institutional capacity but may best beapproached in an incremental manner to mitigate implementation challenges.In this project, civil servants were toimplement the project to build their future project implementation capacity. However, at project start, it became evident thattheir limited experience and skills sets were not sufficient to advance the project. Expert consultants who filled all positions inthe PIU were matched with counterpart civil servants to transfer knowledge. Appraisal did not adequately identify the underlyingcapacity constraints in an FCV context, the impact of low salaries, lack of incentives, and close relations with the politicalleadership, making them prone to short-term political priorities. There wasno evidence that knowledge transfer took place. Anin-depth analysis of gaps in skills and otherconstraints, such as salaries and bonuses, prior experience, and reportingstructures may offer a basket of options in using civil servants to implement projects. A more incremental approach tostrengthening capacity while gradually transferring responsibility may be a good strategy. Technical assistancefor building capacity needs to design modalities that do not encourage poor performance. In this project, the FCBT helpedlocal governments improve their APA scores. However, the local government administrations relied on this assistance reflecting thelimited absorptive capacities of local governments. The Permanent Secretariatwas also unable to supervise and direct the workof the FCBT. Clarifying roles and responsibilities between the municipal authorities and the FCBT, with corresponding resourceallocation (time and human resources) would enhance outcomes. Performance-based financing systems may helpestablish accountability mechanisms at the national and local levels. In this project, designincorporated performance factors such as public consultations on budget planning and implementation, and external audits of localgovernment accounts. These helped strengthen the accountability of the local authorities to its constituents. However, DRC mayorsare nominated rather than elected. As a result, they also have a strong accountability to higher-level authorities that nominatedthem. This arrangement undermines the design of the performance-based approach to establish accountability toconstituents. Operationalizing citizen participation at the design stage may strengthen the outcomes of localgovernment service delivery. In this project, the FCBT was to support the community participation aspects of the project.A citizen engagement approach started after the MTR in 2017. NGOs were recruited to support this approach in each city In March2021. Before project close, the NGOs facilitated the creation of community structures in a constructive collaboration with localgovernments to maintain infrastructures. Local governments provided technical support and minor equipment. However, the processesneed more time to fully stabilize. Local governments without prior planning experience in preparing urbanneighborhood-level investments need strong Institutions to address land and resettlement issues. In this project, theinitial performance-based investments were delayed several years because of difficulties in settling the management arrangements(of a local park in Matadi) and assuring land availability (for commercial facilities in Kikwit). In the end, these investmentswere dropped. That decision may have been avoided if the local development plans carried out during project preparation hadincluded operational considerations for settling land swaps or managing needs of public space. The experience led to limitingactivities under component 2A to school rehabilitation due to relative technical simplicity, known operating arrangements, andabsence of land ownership issues.
P129742 | WBG - PRDP Support V | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2013 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/856121475112557573/text/000012394-20150109151002.txt | http://documents.worldbank.org/curated/en/856121475112557573/pdf/000012394-20150109151002.pdf | The following lessons are taken from the ICR with some adaptation of language:The reform momentum can be safeguarded only through a combination of strong client commitment and predictable donor financing for the budget. This operation was nestled within the national plan, was selective in its approach, and leveraged additionality in donor financing. Firm attention to macroeconomic fundamentals is a necessary condition for success, where fiscal adjustments have to be adequate and the budget has to be sufficiently financed, which in turn entails full and predictable donor financing. There are advantages in designing single-tranche operations with a medium-term agenda in mind to preserve flexibility in a highly uncertain environment. They are useful as a platform for the reform dialogue and as a stepping stone to future operations and potentially to a programmatic medium term series of grants or credits.An effective, relevant and timely data - based monitoring and evaluation system can be utilized to assist implementation, take corrective actions, and to provide feedback to future reform design.
P129769 | Natural Resources and Environmental Governance Technical Assistance | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/145601514756550555/text/ICRR-Disclosable-P129769-12-31-2017-1514756542522.txt | http://documents.worldbank.org/curated/en/145601514756550555/pdf/ICRR-Disclosable-P129769-12-31-2017-1514756542522.pdf | The ICR (p. 22) includes lessons learned adapted by IEG:1 . It is important for the Bank to stay engaged with agovernment to continue the dialogue on critical topics also during unfavorable fiscal times. This project showed thatprogress in a critical area can also be made with a technical assistance project when there is no appetite/fiscal space for alarger scale operation.2 . Addressing the management of natural resources through a multi-sectoral approach forachieving sustainable outcomes is critical but also challenging and requires strong leadership. This project aimed tobring practitioners from various sectors together to create and enhance synergies, and promote collective processes and jointdecision making. However, since there was no strong senior leadership team in place, the project lacked timely policy guidance,technical expertise and collaboration across all sectors.
P129774 | Morocco Social and Integrated Agriculture | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/818491572557725091/text/Morocco-MA-GEF-Social-Integrated-Agriculture.txt | http://documents.worldbank.org/curated/en/818491572557725091/pdf/Morocco-MA-GEF-Social-Integrated-Agriculture.pdf | The ICR (p. 23-24) included several lessons learned, which were adapted by IEG: Identifying and assigningland rights during project preparation supports a timely project implementation and could be used as an eligibility criterion forsub-project sponsors. As an example, in this project, the contribution of the farmer associations to sub-projectswas typically in the form of land. However, the process of legally assigning land rights resulted in implementation delays and thelesson that legally assigning land rights is always subject to institutional risks. In order to ensure thesustainability of sub-projects that are part of the commodity production chain, attention needs to be paid to the commercialviability of these sub-projects. This project provides an example of a program aimed to train trainees from theprivate sector in order to create linkages with private investors, traders, and entrepreneurs to integrate small farmers in localmarkets in a vertical integration of the agri-food chain that was fostered by the public financing of PMV Pillar II projects.However, the number was substantially decreased to 50 trainees during the 2016 restructuring due to weak demand. The Bank teamstated that the reason whythe private sector showed less interest than expected was that althoughfarmers, officials andthe general public at the local level readily grasped the project purpose and value, the larger scale commercial sector preferredto await the results of the pilot project before engaging.The lesson is that theinterest of the privatesectorat the pilot stagewas simply over-estimated at appraisal in the absence of any evidence that UVs could provideevidence ofactual long-term profitability.
P129791 | Fujian Fishing Ports Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099100923095545569/text/P12979106d6fa60a50b6b0067cc2058ad26.txt | http://documents.worldbank.org/curated/en/099100923095545569/pdf/P12979106d6fa60a50b6b0067cc2058ad26.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. Toeffectively addressdisaster risk reduction, the projects design needs to reflectawell-articulatedintervention, including structural and nonstructural measures for vulnerability reduction. While infrastructure-relatedinvestments took the largest share of this project, nonstructural measures, such as establishing an EWS and enhancing trainingcapacity for fishers, were equally weighted in terms of relevance toward PDO achievement. The effective response from theXiapu County Typhoon Defense Emergency Command Center and port administrators over the EWS trial operation stage and theemergency response drills have proven the efficacy of combining structural and nonstructural measures to reduce the vulnerabilityof exposed communities and assets. The project experience demonstrated that new infrastructure enhanced protected and shelteredareas from natural hazards, and the use and training on the EWS and emergency response plan enabled articulated response from portadministrators, fishers, and fishing communities and enhanced the countys long-term resilience.2. Atthe appraisal stage, infrastructure investment projects need to conductan in-depth analysis of potential non-conduciveregulatory challenges to ensure timely implementation of activities.The project faced challenges securing ocean workpermits, highlightingthe need for an in-depth assessment of the country and sectors regulatory framework to informproject preparation. Despite later efforts from governments and relevant departments of Fujian Province, Ningde City, andXiapu County, the approval of ocean work permits was not obtained within the time frame set by the World Bank (by the end ofDecember 2019) for four of the selected fishing port projects. Thissignificantly reduced the project scope (from six to threeports) and implementation delays.3.ME design needs to reflect the causal links between activities,outputs, and outcomes and includerelevant indicators to assess project achievements accurately.The experiencein this project showed that causal links are not always evident when defining outcome indicators. The original PDO indicatorsfailed to be exclusively attributable to the activities financed by the project. The tricky point was that by reducing thevulnerability of fishing communities, as stated in the PDO, the project contributed effectively to reducing storm disaster risk.However, disaster risk is driven as well by other factors on top of physical exposure and vulnerability of communities and assets,which was the target of the project-supported activities. For example, the actual number of deaths and economic losses duringtyphoons varies by the events intensity and duration (hazard-related factors) and fishers behavior to respondappropriately to EWS (cultural factors), among many others. There was no causal link between the project-supported activities andthe change in these other factors, soall original PDO indicators were replaced in the April 2017 restructuring.
P129793 | GPRC-2 Supplemental Financing | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2012 | 2016 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/326001473923015585/text/Niger-First-Growth-Policy-Reform-Grant-Second-Growth-Policy-Reform-Credit-and-Second-Supplemental-Financing-to-Growth-Policy-Reform-Operation-Projects.txt | http://documents.worldbank.org/curated/en/326001473923015585/pdf/Niger-First-Growth-Policy-Reform-Grant-Second-Growth-Policy-Reform-Credit-and-Second-Supplemental-Financing-to-Growth-Policy-Reform-Operation-Projects.pdf | The main lessons, taken from the ICR, with some adaptation of language, are:(a) Programmatic operations can be useful in the context of an unstable and rapidly changing political climate, by allowing the Bank to remain engaged, maintain a dialogue with successive governments and retain the broad thrust of reforms agreed at the start of the operation. That said, a volatile political climate is not ideal for implementation of a DPO series, which calls for continuous commitment by the authorities (even when administrations change), as there is a real risk of dilution of agreed reforms. (b) Development Policy operations, providing budget support, can be helpful in providing rapid support to countries - especially those with a narrow revenue base - in dealing with external shocks. However, for a programmatic series to be successful, design factors play a key role. It is critically important to ensure that prior actions address the key obstacles in the main policy areas of the program.
P129825 | LAOSTAT-STRENGTHENING THE NATIONAL STATISTICAL SYSTEM PROJECT | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/242281549907482294/text/Lao-Peoples-Democratic-Republic-STATISTICS-FOR-RESULTS-PROJECT.txt | http://documents.worldbank.org/curated/en/242281549907482294/pdf/Lao-Peoples-Democratic-Republic-STATISTICS-FOR-RESULTS-PROJECT.pdf | The following three lessons are taken from the ICR with some adaptation oflanguage: If the capacity of the implementing agency is not thoroughly addressed at thedesign stage, then implementation and achievement of intended results will likely not be realized. It is necessary toundertake a detailed assessment of the organizational and operational capacity of the agency. The experience of the projectindicates that this was not adequately addressed in design. While this issue should have been learned from the experience of theSwedish International Development Agency, it is a sufficiently common failing in World Bank project design that it needs continuingemphasis. When identifying and selecting project indicators, due consideration must be given to theiravailability, accessibility, and timeliness. Specifying user surveys without paying due attention to their cost and thecapacity of country counterparts limits their sustainability. This applies, for example to the user satisfaction surveys in Laos.There were also difficulties and delays in obtaining SCI scores. These problems compromised the ability to address issues at asufficiently early stage. Sustainability of the development outcomes can depend on the availability of furthersupport to the implementing agency after closure. In this case any shortcomings still exist with respect to the ICTinfrastructure, the capacity of those administering ICT systems, and to the ability to upgrade thesame. IEG adds an additional lesson Using international indices asoutcome indicators is of limited usefulness for two reasons. First, such statistics usually only become available withsignificant delays and are therefore of limited or no use in monitoring the progress of the project. This was the case with thisproject. Second, by their nature, these statistics are rarely customized to the specific needs of the country in which the projectis taking place so that local particularities are not taken into account.
P129828 | Ethiopia General Education Quality Improvement Project II | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/861851625090671113/text/Ethiopia-ET-GEQIP-II.txt | http://documents.worldbank.org/curated/en/861851625090671113/pdf/Ethiopia-ET-GEQIP-II.pdf | The ICR(pp. 32-33) offeredseveral lessons, including the following adapted by IEG: Textbookcompetitive pricing and a few up-front procurement actions can generate savings and increase efficiency. The combined useof international competitive bidding that bundled textbook development, printing, and distribution; the use of quality and price astenders evaluation criteria; a copyright agreement allowing the government to reprint at no additional cost; and large printruns generated US$25 million in savings. In conflict-afflicted contexts such as Ethiopias, the use ofrapid surveys and digital data collectioncan supporttimeliness of regulardata collection. Datacollection from remote and poorly connected areas, as well as manual data collection,were challenging factors fortheprojects completion and timely generation of statistics that fed the EMIS. In conflict or violencecontexts, strong attention to realism in defining indicators and setting targets is important especially in projects withdecentralized implementation. In its final year, this projectlacked time to accommodate for implementation delays,hindering target achievement. When considering extensions and restructurings, activities including building social cohesion,provision of psychological support to conflict-affected children and their families, empowerment of girls, and preventionofgender-based violenceand early marriage are also important dimensions to consider inrestructurings. Careful attention to having systems to track textbook distribution and ensure that textbooks andteaching material reach schools is essential. Similarly, in this project, encouraging thegovernment to maintainfinancing for continuous textbook provision independent from development partners wasbeneficial.This review adds an additionalkey lesson, related to booksprocured: Buying teaching and learning materials does notproduce impact if studentsleavetextbooks at home and do not use them. When defining characteristics of books to be procured and distributed,factors such as weight and bulkiness of the books, as well asbags for carrying them, are important considerations, the moreso if a set of students must travel long walking distances to and from school. The 2019project exit evaluation showed lowtextbook utilization in all grades in classrooms due to inconvenient dimensions of carrying the books.
P129847 | Mozambique Mining and Gas Technical Assistance Project | Eastern and Southern Africa | Mozambique | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099030224152540636/text/P12984718e4ba20e319af711230571dfa85.txt | http://documents.worldbank.org/curated/en/099030224152540636/pdf/P12984718e4ba20e319af711230571dfa85.pdf | (Reference ICR paras. 83 to 87).The ICR lists a number of lessons drawn from the Projects experience whichhave relevance for similar projects carried out in comparable environments. From these, with some adaptation, IEG draws thefollowing lessons:Flexible and adaptive project design is desirable to capture emerging trends and nationalpriorities.The relatively simple design of the component structure allowed the opportunity at the AdditionalFinancing to makecritical adjustments and restructuring to improve decisions and practices by learning from outcomes of theprevious actions. This was particularly evident in the case of development of a domestic gas infrastructure which requiredintroducing relevant policy changes and strengthening interconnectivitybetween GoM agencies.Uptake ofproject outputs is directly dependent on national priorities, particularly where the outputs or outcomes depend upon parliamentaryprocesses. During the implementation of the Project, a shift in attention to developing billsfor the energy sectordelayed preparation of bills for the petroleum and mining sectors.Procurement proved to be challenging due to thecomplexity of the Project with many beneficiaries and activities. The lesson learnt is to allocatesufficientsupervision time in projects of this complexity as well as to continue to have frequent contact with the PMU through onlinecorrespondence and calls.Too rapid dissolution of the PMU after project closing can create challenges forcompleting fiduciary activities. In the case of the Project, proper completion of the financial management activities,including closing of the books, was adversely affected by the premature dissolution of the PMU. It is important to build a timebuffer between the conclusion of the last procurement activity and the closing date.Proper planning is required,to the extent possible,in arranging for the transition of Task Team Leaders (TTLs) in the World Bank supervision team toprevent disruptions and shorten the learning curve for the new incoming TTL. This includes early identification, knowledgetransfer, structured handover, a shadowing period, and full access to relevant documentation and reports. This wouldreducethe burden on the PMU and allocate additional time to facilitate the takeover.
P129861 | West Bank and Gaza: Education-to-Work Transition | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Education | SPF | IPF | 2012 | 2022 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099750001172318670/text/P12986104d6ce706d0bbbf04c5ce4252954.txt | http://documents.worldbank.org/curated/en/099750001172318670/pdf/P12986104d6ce706d0bbbf04c5ce4252954.pdf | The ICR (pp. 26-27) offered several lessons and recommendations, including the following lessons restated by the IEGReview:The Quality Improvement Fund grant mechanismis an effective tool to lower unemployment of younggraduates. Under the project, the model was found to be effective in reducing graduate unemployment, as it alignededucation and training programs with the needs of employers while promoting both relevance and quality of study programs. The QIFmodel also validated the value of public-private partnerships that benefited both students and employers.Sustainedsupport can build institutional capacity, but financial sustainability remains challenging. The continuity of financialand technical support provided to the QIF approach by two consecutive Bank-supported operations contributed to its effectiveness inreducing unemployment among graduates. However, additional resources could have further expanded its outcomes and deepened itsimpact. Financial sustainability remains uncertain and raises justifiable concerns, as market needs evolve constantly and rapidly.Adapting and aligning study programs and competency-based education with evolving market demands affirm the importanceofcontinued support to such educational adaptations to keep pace with evolving labor market needs.Integrating agender perspective into the design, implementation, and monitoring of development projects can contribute to alleviating genderinequalities. While it is understood that gender equality has far-ranging determinants and requires wider and deeperefforts, gender aspects and mainstreaming were promoted by the project within its scope. The project had an inbuilt gender balancerequirement in the QIF mechanism, and each QIF proposal and its results indicators matrix were required to make explicit referenceto how gender balance wouldbe promoted and monitored. In connection with this lesson, the ICR pertinently provided animportant recommendation to promote programmatic engagement for broader sector reform that targets equality in the labor market andjob insertion for females, beyond education and training access.
P129920 | Bangladesh: Rural Electricity Transmission and Distribution Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2021 | 2023 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099425207182254301/text/P1299200643cbe06c08e20039359b24805b.txt | http://documents.worldbank.org/curated/en/099425207182254301/pdf/P1299200643cbe06c08e20039359b24805b.pdf | (Reference ICR paras. 89 to 94).The ICR lists a number of lessons drawn from the Project experience whichhave relevance for similar projects carried out in comparable environments. From these, IEG derives the followinglessons:Investment in infrastructure coupled with policy and regulatory reforms canallow efficientutilization of assets and sustainability of project outcomes: Under the GoBs objectives at the time, expansionofpower generation and low-voltage networks wereto be addressed through other investmentsthat wouldcomplement the IDA-financed RTDP. The Projects design therefore focused on addressing weaknessesin the medium-voltageand transmission networks that were constraining additional supply of electricity to the distribution network in theProject-supported rural areas. While the planned investments were successfully carried out, sustainability of the gainsrequirethat appropriate operations are carried out to address issues such as inefficient dispatch and lack ofwholesalemarkets that constrain the efficiency of the overall system. Optimization of dispatch operation is being addressedunder the successor World Bank financed Power System Reliability and Efficiency Improvement Project (P159807) approved in2017.To ensure accurate measurement of the Project outcomes and benefits, it is important to design acomprehensive and quantifiable Results Framework that is adaptable to changing conditions: In the case of the Project,the effects of complementary expansions in power generation and improving electricity grid coverage were not adequately captured inthe Results Framework. This resulted in an understatement of the benefits realized under the Project.Earlypossession of land is critical for projects focusing on infrastructure creation: Land acquisition processes can becumbersome and protracted. Learning from experience under earlier projects, to expedite acquisition of land, BREB decided veryearly in the Project to purchase land on a willing buyer - willing seller basis rather than follow the cumbersome processes of landacquisition. BREB was successful in this and the early handover of land to the contractors was an important factor in timelycompletion of infrastructure facilities, particularly the transmission grid enhancements for whichchanges to route alignmentare more difficult to make than for expansion of electricity distribution systems.Institutionalizing ofthe environment and social safeguards management in project implementing agencies helps in adequate and timely resolution ofsafeguard challenges during project implementation: The Project design supported establishment and capacity buildingof Environmental and Social Units in BREB and PGCB to mainstream environmental and social considerations in all BREB and PGCBoperations.This contributed to the proactiveness of the implementing agencies and the Bank task team in timelymonitoring of environmental and social issues, their mitigation, and achievement of overall compliance with environment and socialissues.
P129929 | NP: Financial sector stability DPC | South Asia | Nepal | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2013 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/824251467998479731/text/ICRR14691-P129929-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/824251467998479731/pdf/ICRR14691-P129929-Box393183B-PUBLIC.pdf | The ICR lists a number of lessons that seem warranted based on the experience under this operation. Key ICR lessons include: (i) it is important to quickly respond to a clientâ€™s request for assistance, even if the political structure is uncertain; this in turn helps the Bank to be regarded as a valued partner; (ii) taking the risk of supporting initially difficult reforms through a stand-alone DPC helps to build a momentum for further reforms; (iii) there should be sufficient time given for completion of reforms after funds are disbursed; (iv) availability of TA resources and effective/seamless donor coordination supporting the implementation of policies are keys to success.
P129961 | Sustainable Forest and Landscape Management Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/291211585691761056/text/Bosnia-and-Herzegovina-SUSTAINABLE-FOREST-LANDSCAPE-MGT.txt | http://documents.worldbank.org/curated/en/291211585691761056/pdf/Bosnia-and-Herzegovina-SUSTAINABLE-FOREST-LANDSCAPE-MGT.pdf | IEG has drawn following lessons based on those reported in the ICR (para 112-119) with some changes inlanguage: For a demonstration project to be replicable and guide policy, careful planning isrequired. In this project there were deficiencies in the monitoring of the results on demonstration plots and an absenceof control plots. Consequently, it was not possible to assess whether the results of the demonstration plots were attributable tothe project or not. The lesson is that to gain any benefit from a demonstration project it needs to be carefully implementedand appropriate counterfactuals need to be established if the demonstration plots are to be useful for technical or policypurposes. Cost and complexities in investing in information systems and new technology are often underestimatedresulting in implementation delays. In FBiH, insufficient funds and the underestimation of the task at hand to upgrade theFMIS information system resulted in project implementation delays. The lesson is that the costs of upgrading existing informationsystems or investing in new technologies need to be properly assessed at appraisal, and that sufficient funds need to be availableto procure competitive service providers.IEG draws the following additional lesson:Projects thataim to enhance the weak capacity of decentralized government institutions need to assess the root causes of this weakness duringappraisal. This project aimed to enhance the low capacity of the forestry stakeholders (regarding policies, strategies andplanning) inthe context of the decentralized and complex institutional and policy framework of the different entities of BiH.However, while the project sought to address the complex decentralized forest policy in BiH, the implementation of the projectitself was negatively affected by the complexity of the institutional setting, and especially so in FBiH. The lesson is that aprojects appraisal needs to properly assess how a weak decentralized government could affect implementation capacity andpose a risk for project outcomes.
P130012 | Nigeria Agriculture Sector Development Policy Operation | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2013 | 2015 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/108471473086844801/text/Nigeria-Agricultural-Transformation-DPO.txt | http://documents.worldbank.org/curated/en/108471473086844801/pdf/Nigeria-Agricultural-Transformation-DPO.pdf | The first four lessons are drawn from the ICR, with some adaptation (ICR, pages 35-36), and the last, is from the IEG.One, the strategy of leveraging public policy reform with private sector development has a high payoff. In the case of theAgDPO1, theGovernment terminated its monopoly over the procurement and distribution of seeds and fertilizers in favor of theprivate sector. The policy reform has earned good results, with farmers gaining greater access to, and adopting, the improved seedand fertilizer technology and the private sector developing and delivering on a business competency while the government rightfullyfocuses on regulation.Two, DPOs can benefit from complementary TA activities, including analytical work,andcomplementary funding support from the borrower government, if not from other development partners.It was crucial to havemobilized TA in the implementation of the AgDPO1, in view of the FMARDs comparatively weak capacity for public policyanalysis. The operation identified a number of policy studies that could aid policy decision making but could not pursue many ofthem for lack of resources. It could also have benefitted the AgDPO1 to have received complementary funding fromtheGovernment for certain activities --- the conduct of the GHS LSMS and the conduct of studies supportive of policymaking. Funding support from other development partners would have also been helpful.Three, it cannot beemphasized enough that multi-sector and inter-governmental reform programs require coordination among national agencies andcooperation between the central government and subnational governments. The design and implementation of the ATA was the product ofclose collaboration between the Nigerian federal and autonomous state governments (ICR, page 9). But there were also cases where alack of coordination between federal agencies caused slippages in AgDPO1 implementation --- the Fertilizer Bill was ratified by theFEC but not submitted to the National Assembly in time because of objections from the Federal Ministry of Industry, Trade andInvestment.Four, for any sector management program that invariably includes a public financial management (PFM)activity, budget planning tools are a necessity. In the case of AgDPO1, the Medium Term Expenditure Framework would have served toprovide insight into theGovernments budget management practices and problems. Timely budgetary releases to the FMARDproved to be a serious issue with the implementation of the AgDPO1.Five, the Bank and borrower governments shoulddesign the ME framework for the eventuality that a two- or multi-part DPO is reduced to a stand-alone DPO if work on successoroperations gets bogged down. The ICR had to improvise on an approach and methodology for conducting a mandatory evaluation on thefront-end DPO using end-of-series PDO outcome targets (ICR, page 21). This ICRs approach worked well, but could havebenefitted from a clear definition of what the evaluation standards would be when the evaluator has end-of-series programmatictargets but only mid-term results.
P130013 | Kazakhstan Energy Efficiency Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2013 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062823175532807/text/P130013157bbb5a21fa2114b181aa0d174eaaed186cd.txt | http://documents.worldbank.org/curated/en/099062823175532807/pdf/P130013157bbb5a21fa2114b181aa0d174eaaed186cd.pdf | The following lessons were derived from the ICR(ICR, pages 37-38):1. Considering existing regulations(specifically, building standards and codes) was critical for the financial sustainability of the sub-projects. The sub-projectsthat were implemented later during the Projects life demonstrated higher financial viability, because of learning bydoing: it turned out that EE in improvements affecting structural items, such as walls and roofs, trigger building codes andtherefore increase costs, making sub-projects financially unsustainable and creating barriers for a scale-up. At the same time,limiting EE heating-related investments to non-structural items, such as windows and doors, and combining them with investments inelectricity savings, was yielding positive returns. As a result of this learning experience, the Project was able to adjustsub-projects design and achieve positive financial returns at closure. The alternative would be subsidization of the EEsub-projects through either budgetary support or carbon pricing.2. Health and safety issues need to be an important focusarea when implementing EE projects in public and social facilities. The Projects experience was that shutting down theoperations of social facilities to implement the sub-projects was rarely possible. Health and safety safeguards were thereforeimportant, especially when the sub-projects were implemented in schools and kindergartens and children were in the same buildingduring construction. Waste management and mitigation of health and safety hazards were critical to avoid accidents. In futureprojects, it would be important to consider how the works should be implemented to guarantee the safety of the public and staffwhile minimizing the disruption to the functioning of the facilities.3. In countries like Kazakhstan, where EE reforms areat their initial stage and energy sector reforms are in the process of being implemented, incentives for the private sector toinvest in EE projects in public and social facilities are low; therefore, sustainability of such projects depends on theavailability of public funding, specifically, from local governments. Budget allocation process in many cases needs to be adjustedaccordingly, and related policies and regulations introduced. This issue, although discussed briefly in the Projects PAD andincluded in some of the Projects technical assistance outputs, could have been a more integral part of the Project design,which is an important lesson for future EE projects in public and social facilities.
P130014 | Vietnam Irrigated Agriculture Improvement Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099855006302213711/text/P1300140697c080460bb4d0400da3649fa7.txt | http://documents.worldbank.org/curated/en/099855006302213711/pdf/P1300140697c080460bb4d0400da3649fa7.pdf | The ICR included five lessons. The following three are emphasized with some adaptation oflanguage:1.Combining irrigation infrastructure improvement and agriculture technology enhancement as anintegrated operation with appropriate interventions maximizes synergies and ensures that multiple needs are addressed in oneoperation. The project successfully combined interventions from the irrigation sector along with thosefrom the agricultural sector. Such an approach is innovative and addresses multiple needs in one operation. This creates asynergistic effect on both sectors as they are interdependent, andbenefits from one sector spill over smoothly to the other.In conclusion, cross-sector and cross-disciplinary approaches maximize the greatest synergies.2. The long-termsuccess and sustainability of the irrigation and agriculture sectors, is enhanced by the ability of relevant institutions toadequately plan for effective OM. The project experience emphasized that improving the capacity of institutions todesign, operate, and maintain irrigation infrastructure as well as CSA practices are critical elements to ensurelong-termsuccess and sustainability of the irrigation and agriculture sectors. This was done through designing and adoption of OMplansalong with training sessions for different institutions. Training was also given to farmers to help them understand howCSA practices canimprove their crop productivity and resilience to climate change. The project also spent considerable effortto develop technical guidelines, norms, and standards to be adopted for broad utilization by the sector. These combinedinterventions created the conditions for better OM and long-term adoption of CSA practices.3.Improvingdam safety management of small reservoirsensures water security for multiple uses by downstream communities, and reduces thedownstream risks from potential dam failure. The project supported the issuance of guidelines on dam safety management forsmall reservoirs. The economic optimization from dam safety improvement should be encouraged by modernizing downstream irrigationinfrastructure so that people could maximize the benefits gained from both dam safety and irrigation modernization while practicingclimate-smart agriculture techniques.
P130048 | Program for Economic Resilience, Investment and Social Assistance in Indonesia | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/427471498068061410/text/ICRR-Disclosable-P130048-06-21-2017-1498068053369.txt | http://documents.worldbank.org/curated/en/427471498068061410/pdf/ICRR-Disclosable-P130048-06-21-2017-1498068053369.pdf | The ICR drew a wide range ofsignificant and important lessons from the experience of designing and implementing thePERISAI. The most important is the need for clarity among all financing partners regarding the conditions under which theAuthorities may request a drawdown of the DDO. Ideally there should be full agreement on such conditions, but this may be difficultto achieve in view of the different legal stipulations and other procedures under which each partner operates. If no such agreementis possible, then development partners need to communicate clearly, and from the outset, to each other and to the Borrower theconditions under which they would disburse.Three other noteworthy lessons cited in the ICRare:First, the contingent financial instrument could be more effective for insurance purposes if the loan terms were morecomparable to those of other financing available to the Government. In this case, although the maturity and grace period (seven andtwo years) were considerably less than those of the PESF (25 and ten years), the interest rate (six months LIBOR plus 50 basispoints), was well below the opportunity cost of Indonesian borrowing, even in normal times. This increased the incentive to usethePERISAI as inexpensive financing.Second, although there is wide consensus on the Borrowersside that the insurance provided bya DPO-DDO is highly beneficial, a constraint on requesting further similaroperations is the fact that such loans count 100% against and increasingly narrow Bank global lending headroom and countryborrowing limits. Consideration might, therefore, be given to developing alternative methods of contingentsupport.Third, regular meetings to monitor progress and implementing needed changes can be a more effectivetool if agencies responsible for all aspects of the program are represented. In this case, monitoring of some key dimensions of theprogram had to rely exclusively on Bank supervision efforts and coordination with staff on both the Borrower and Bank side involvedwith parallel operations in the sectors concerned.
P130051 | Development Policy Operation - DDO | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201961467041187197/text/ICRR-Disclosable-P130051-06-27-2016-1467041177552.txt | http://documents.worldbank.org/curated/en/201961467041187197/pdf/ICRR-Disclosable-P130051-06-27-2016-1467041177552.pdf | The ICR identifies a number of important general and specific lessons drawn from the experience of preparing and implementingthis operation. The most important general ones are: The Deferred Drawdown Option (DDO) was appropriate in thiscase, and would be worth more active promotion as an instrument for clients who seek risk insurance to adverse exogenous shocksrather than direct financing. This operation demonstrated the clear benefits to policy-based lending arising fromin-depth country and sector knowledge. Both the Bank and the Borrower were able to build upon a substantial body of thoroughanalytical work and on the experience from previous policy and investment lending in Romania and elsewhere. The outcomesof policy-based operations can be greatly enhanced by the constant availability of technical and procedural advice from the Bank.In this case, the implementing agencies engaged the appropriate sector staff in the local Bank office and in Washington on avirtually continuous basis to discuss policy choices and decisions. The option of involving, when necessary, theintervention of the highest level officials (in this case, the Prime Minister) can be critical to the success of politicallycontroversial reform measures.
P130051 | Development Policy Operation - DDO | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2012 | 2015 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/533961502286034775/text/112699-PPAR-P160286-P130051-PUBLIC.txt | http://documents.worldbank.org/curated/en/533961502286034775/pdf/112699-PPAR-P160286-P130051-PUBLIC.pdf | 6. Lessons 6.1 The design and implementation of this DPL-DDO offers valuable lessons on World Bank support for critical institutional reforms and for strengthening client capacities to respond to exogenous shocks. Three lessons emerge as the most important. 6.2 The design of the reform program benefited from a solid foundation of country knowledge acquired through thorough analytical work. It also built on the reform program supported by the programmatic DPL series and took into account the lessons learned through these operations. The success of difficult institutional reforms in the energy sector underscored strong government commitment to the reform process, which was strengthened by the liberalization road map agreed with the European Commission. Commitments taken in parallel with reforms linked to the obligations of EU membership are hence likely to lead to more tangible results. In contrast, insufficient drive to carry out difficult reforms led to slow progress in revising the reimbursable drugs list, while disruption created by major institutional reforms, such as tax administration reform, which required massive reallocation of staff and the establishment of new organizational structures, was underestimated and ultimately slowed down the restructuring of the tax administration agency. 6.3 Difficult institutions reforms require sustained political commitment and support from development partners. More specifically, tax reforms are key to improving tax collection and reducing the compliance burden for taxpayers and businesses, but they are also potentially threatening to the status quo, which provides wide discretionary powers and rent-seeking opportunities. Tax reforms require high-level political support from the Ministry of Finance and possibly the prime minister's office, as well as technical capacity from the tax administration agency. In Romania, political support has been weak. This has negatively affected the outcomes of the DPL-DDO and of the subsequent tax administration project. The reduction of the number of regional offices has not materialized due to considerable political opposition. Budget support operations have the power to focus the minds of political decision makers, but once the money is disbursed the commitment fades. Continuous World Bank pressure at the highest political level, as well as a strong commitment to provide the necessary technical and financial resources, may be required to implement tax administration reforms. 6.4 DPL-DDOs can be used as an effective mechanism for crisis support and for supporting a borrower's medium-term debt management strategy. In the case of Romania, the operation was initiated to provide insurance against exogenous shocks by augmenting the size of the government's fiscal buffer. At a later stage, the government saw the DPL-DDO as an appropriate instrument of debt management and withdrew the loan proceeds in tranches to optimize its debt profile. This demonstrates the versatility of the DPL-DDO instrument and its ability to meet client demand for flexible, innovative financial instruments for managing a spectrum of risks.
P130089 | Zoonoses Control Project (ZCP) | South Asia | Nepal | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2012 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/855471468001179196/text/ICRR14685-P130089-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/855471468001179196/pdf/ICRR14685-P130089-Box393183B-PUBLIC.pdf | The ICR identified seven key lessons learnt. Of these, the following lessons are noteworthy despite the fact that they repeat similar lessons from other projects The competence and commitment of the project management team is an important factor in the success of any project. This is not a new lesson. However it was a particularly relevant lesson in this project because the dedication of project management and staff and their effective collaboration with the World Bank was crucial in ensuring that the project's objectives were achieved despite the long delays in releasing funds. This reinforces lessons from many other projects, namely the importance of committed high quality leadership for successful implementation. A strong Monitoring and Evaluation system is critical for coordinating activities across implementing agencies but this does not ensure comprehensive data collection. Again this is not a new lesson. The decision to centralize the monitoring, evaluation, and planning unit (in the Department of Livestock Services designated as the key implementing agency) promoted accountability, reduced transaction costs, and strengthened collaboration across the three implementing agencies thus enhancing the implementation of the One Health approach. However, data collected were not sufficiently comprehensive. Project-related surveys should be timely and systematic. The Knowledge, Attitude, and Practice surveys were not carried out in a timely and systematic manner. As a result, it was not possible to use the survey to assess the views of the potential beneficiaries on the performance of the project.
P130091 | Private Sector Competitiveness | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/215661610725678700/text/Tajikistan-PVT-SECTR-COMP.txt | http://documents.worldbank.org/curated/en/215661610725678700/pdf/Tajikistan-PVT-SECTR-COMP.pdf | The ICR identified (para 94) several important lessons and recommendations arising from the experience of the projectimplementation. This review selected three which potentially provide usefulinsights for similar projects.They arerephrased and summarized below: Simplicity in design is an indispensable ingredient for a successful projectimplementation. This technical assistance project was complex, and thishindered its smooth implementation. It tookthree restructurings to straighten out the projects implementation, and it required enough resources to hire internationalexpertise to oversee the completion of difficult reforms supporting the improved business registration practices, increasedefficiency of the payment systems infrastructure, and institutional reforms in the mining sector. It also tookcoordinatedwork by the Bank team and the countrys counterparts to complete the complex institutional improvements and reforms. Thelesson is that projects, particularly technical assistance projects, need to have a simple design in order that the technicalsupport provided is effectively and fully absorbed. Hiring appropriate experts with credible andrelevant established expertise is key to implementation of complex technical reforms.TheBank and Governmentteams enlisted the support oftwointernational task team leaders,one based at headquarters and the other based inthe country office. They brought together their expertise tofacilitate project supervision, including close partnershipwith and timely training of country counterparts in the implementation of reforms such as the modernization of a national paymentsystem infrastructure and the digitization of data documenting the nations geological resources. The lesson is that theappraisal of a technical assistance project needs to include the preparation of high quality terms of reference and biddingdocuments to ensure the smooth and rapid procurement of the technical assistance services required for a project. When undertaking reforms supporting private sector development, the Bank team needs toconcurrently establish a partnership with the International Finance Corporation (IFC).The original projectdesign did notplan to factor in aregulatory framework for a successful establishment of the collateral registry.Apartnership with a parallel IFC projectresulted in the enactment of the Secured Transaction Law,which became asuccessful complementary investment supportingthe collateral registry infrastructure in the Ministry of Justice.Thelesson is that projects support forthe establishment of a collateral registry would not have been fully successfulwithout the IFCs expertise and contributions.
P130150 | Financial sector and Investment climate Reform and Modernization DPL | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2013 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422031468190187428/text/ICRR14675-P130150-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/422031468190187428/pdf/ICRR14675-P130150-Box393183B-PUBLIC.pdf | The following lessons are taken from the ICR with some adaptation of language:The extensive background analytical work is critical for successful preparation and implementation of DPL. It is not just a key element in identifying the priorities for reform program, but also a tool for consensus building among the government counterparts. In the case of FIRM, this helped to advance the policy dialogue and allowed the DPL to be prepared in six months. The presence of a strong agency capable of serving as a coordinator within the government became an important driver of successful policy reforms in the financial sector. In the case of FIRM and related operations, the Ministry of Economic Affairs has shown a leadership role in guiding and overseeing reform progress across a large number of stakeholders, some of which are formally independent from the Government.The following lesson is drawn by IEG: Weak prior actions, which do not provide for actual policy change, amplify the risk of an inadequate policy reform follow-up. This risk is likely to be further aggravated if the project design does not include special monitoring and supervision arrangements to track actual policy development after the project approval.
P130157 | Montenegro Financial Sector Policy Based Guarantee | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Other | Other | IBRD | DPF | 2012 | 2014 | 2016 | ICRR |  | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/646121473936764782/text/ICRR14951-P130157-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/646121473936764782/pdf/ICRR14951-P130157-Box396299B-PUBLIC.pdf | Please see the detailed PPAR evaluation for more information.
P130157 | Montenegro Financial Sector Policy Based Guarantee | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Other | Other | IBRD | DPF | 2012 | 2014 | 2016 | PPAR |  | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/426901469129589230/text/106282-PPAR-P157445-Box396277B-OUO-9-montenegro-0716.txt | http://documents.worldbank.org/curated/en/426901469129589230/pdf/106282-PPAR-P157445-Box396277B-OUO-9-montenegro-0716.pdf | 8. Lessons Â· PBGs can potentially be a useful instrument for supporting countries facing large external financing needs. Â· PBGs implemented in a context of challenging macro-fiscal situation and large financing needs need to incorporate a consistent macro-economic framework with necessary macro and fiscal actions for risk mitigation. Â· The choice of a PBG as an instrument should be based on robust macro and fiscal projections indicating that financing framework is sustainable and macro risks are mitigated. Montenegro's case indicates that eligibility for a PBG cannot be decided based on general announcements by the government that lack details. The case highlights once again the criticality of Bank-Fund cooperation. Â· Comparing the aggregate interest rate of PBG-supported debt instruments with counterfactual market rates may not be enough for assessing the extent of reduction in the borrowing costs associated with the transaction. Estimating the change in sovereign risk perceptions, although a challenging task, may give more accurate assessment of the impact of the program.
P130164 | Rajasthan Road Sector Modernization Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099050423040030393/text/P1301640b1a4d202008b910ba796c7180f1.txt | http://documents.worldbank.org/curated/en/099050423040030393/pdf/P1301640b1a4d202008b910ba796c7180f1.pdf | The ICR provided the following lessons (presented here with some minor modifications): Lack of fullendorsement of programs by the key decision makers at preparation can negatively affect project outcomes. The introductionof new systems required endorsement from relevant stakeholders early on during implementation process to ensure ownership. Forexample, full operationalization of the Road Asset Management System (RAMS) did not occur by project closure because of the lack ofbuy-in from the Finance Department and the Public Works Department. The implementation of efficientbusiness processes is likely to benefit from additional preliminary studies. Sound preparation before project approvalwith studies carried out to showcase the relevance of proposed activities to achieve specific outcomes (such as the need to developa proper Road Asset Management System), is best practice. In-depth upstream discussions/workshops with the client inparticular the finance and technical departments, should alsobe considered for mostprojects. The mutation process (that is the actual transfer of the land title ownership and not justof the land use or destination)for the donated land is difficult,so clear guidelines need to bedeveloped. Some commendable work was done in the project to make sure that the land ownership was legallytransferred. This knowledge can be replicated in future projects in Rajasthan or possibly other states inIndia.IEGs Lesson: To avoid cost and time overruns and contractadministration issues, forest and other administrative clearances need to be inplace prior to awarding contracts.The project experience shows that some of the road works were dropped due to forest clearance issues.
P130182 | Education Improvement Project | Europe and Central Asia | Armenia | IBRD |  | Human Development | Education | IBRD | IPF | 2014 | 2026 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099335003182234781/text/P130182038ccba0a80b5b90b02b307e7330.txt | http://documents.worldbank.org/curated/en/099335003182234781/pdf/P130182038ccba0a80b5b90b02b307e7330.pdf | The ICR (p. 26) offered several insightful lessons, some of which are highlighted here:Projects in sectorswhere the Bank has prior experience can benefit from a mix of tried-and-tested activitieswith more innovative interventionsthat entail higher levels of risk. In the case of this project, the pre-school community-based microprojects and CIF hadalready been through proof-of-concept at the project design stage, allowing for rapid start-up and freeing human and financialresources to focus on more ambitious new undertakings like the rehabilitation and equipping of highschools.Projects that span several different levels of education can benefit from a unifying focus; at minimum, aplausible, coherent theory of change is required for each separate objective covering a different education level. In thecase of this project, some interventions (those related to data monitoring and performance, as well as curriculum revision) werenot tightly connected to any of the three objectives, and the formulation of the second objectivediscouraged an emphasisonoutcomes. This was particularly disappointing given previous experience working in the sector.Achievementof objectives cannot bedemonstrated in the absence of appropriate indicators. In the case of this project,achievement of the second objective was limited to counting outputs because of the way the objective was framed, and there were noindicators to measure achievement of the third objective (nor did the ICR provide additional data tocompensate).
P130184 | WARCIP APL 1C - Benin | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2013 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/871771519774058234/text/Western-Africa-WARCIP-APL-1C-Benin.txt | http://documents.worldbank.org/curated/en/871771519774058234/pdf/Western-Africa-WARCIP-APL-1C-Benin.pdf | The following were the main lessons drawn by the ICR from the experience of implementing this project, with some adaptation oflanguage(page36-38).(1) The PPP model by itself may not guarantee competition. The PPP structure,as adopted in Benin, was restricted to the existing shareholders and this presents a barrier to entry to new or small serviceproviders.(2) Better arrangements at design are needed to ensure divestment of government shares.Thegovernments shares in the PPP created (Groupement dInterest Economique (GIE) were not divested, asdesigned.(3) Given that compared to other sectors (such as health and education), theICTmarket evolvesmore rapidly,indicators in ICT projects mayneed to be revised more often and reassessed against current market development trends. In thisproject, targets setat appraisal for indicators such as the percentage of population with access to internet services were surpassed by the second halfof the project, partly due to project outputs and partly due to other domestic and international factors such as lower cost fornetwork rollout and more affordable end user handsets. Arevision of indicators and reassessment of targets duringimplementation would have been useful for a more realisticassessment of theproject.
P130193 | Punjab Skills Development | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/660611635796562031/text/Pakistan-Punjab-Skills-Development.txt | http://documents.worldbank.org/curated/en/660611635796562031/pdf/Pakistan-Punjab-Skills-Development.pdf | The ICR (pp. 29-31) offered a series of insightful lessons, including:A results-based financing approach, withcarefully defined disbursement-linked indicators, increases focus on results, but there should be flexibility, perhaps in the formof scalable targets,to allow and incentivize achievement beyond pre-defined DLI targets. In this case, the originalDLI target for industry partnerships was achieved early, and a large number of additional agreements were not recognized throughincremental disbursements.A competitive grant funding mechanism that channels funds to both public and privatetraining providers can help increase access to skills training across multiple dimensions. In this case, the privateproviders were more responsive to labor demand, but public providers reached larger numbers of trainees and were more likely toprovide opportunities to trainees from marginalized areas.
P130202 | Revenue Administration Modernization Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/151101585946707541/text/Romania-RAMP.txt | http://documents.worldbank.org/curated/en/151101585946707541/pdf/Romania-RAMP.pdf | Lessons in the ICR are deemed appropriate. IEG adds these additional, closely related lessons: A risk-based approach to supervision is needed when there are difficulties in sustainingthe dialogue in a changing macroeconomic and political context. In this case, the team should have increased the quality ofsupervision to maintain more continuous dialogue with government counterparts and keep better abreast of a dynamicsituation. Complex IT procurementrequires sufficient technical staff to ensure technical readiness, fullunderstanding on trade-offs of basic design parameters such as COTS vs bespoke, and agreement on the reasons for selecting one orthe other before project effectiveness. In this case, the project was rushed to approval before improved business processes were inplace, and before there was full agreement on technical staff requirements. The Bank kept urging government during implementationto add to the IT departments capacity in order to support this work, but NAFA didnt appoint the needed specialists. Inaddition, NAFAs IT department never supported the justification for COTS.Task teams should fully articulatekey political economy issues in the risks section of the PAD and/or in a standalone annex. In this case, such an assessment mighthave flagged the frequent changes in government and pointed towards a longer and more cautious approach to design, with lessambitious targets. It might also have found that vested interests were worried about the disruption to legacy rents caused by ITsystems and would take actions to slow down or halt reforms. This could only be addressed by decisive action by the countrysleadership in favor of reform.
P130222 | LA-Scaling-Up Participatory Sustainable Forest Management | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099071123172036605/text/P1302220fbd82f0cc08f370b9fe9371a5f8.txt | http://documents.worldbank.org/curated/en/099071123172036605/pdf/P1302220fbd82f0cc08f370b9fe9371a5f8.pdf | The following lesson in the ICR was particularly relevant:Village-level support programs are more likely to besuccessful when backed by strong and effective implementation arrangements. The modality to deliver assistance to thevillagesmust be adapted to the countrys institutional hierarchy and decentralization level. In this project, thehighly decentralized design of the village grants and the verydiversified portfolio of (on-demand) micro-scale agriculturalproduction systems posed a challenge to track and assess the overall extent of efficacy.The following lesson is drawnbyIEG:If a novel and pilot concept is introduced as a key project intervention without enough precision ofits goals or sufficient technical preparation, it might cause ambiguity and confusion among stakeholders and reduce theirbuy-in.In this project, the concept and modus operandi around the Forest Landscape Management Plans werentdetailed enough, which created a perception of ambiguity. The project was tasked with exploring ways to operationalize FLM throughstakeholder consultations. A clearer understanding of what piloting forest landscape management would entail in Lao PDR, backedbydedicated analytical work at the design stage, could have made the project design more realistic.
P130276 | Pastoral Community Development Project III | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/972731589551371865/text/Ethiopia-Pastoral-Community-Development-III.txt | http://documents.worldbank.org/curated/en/972731589551371865/pdf/Ethiopia-Pastoral-Community-Development-III.pdf | The ICR provided valuable lessons. The most important follow with some modification of language: Capacitybuilding support provided by Mobile Support Teams (MSTs) can bridge gaps in institutional capacity for projectimplementation. The key factors of success for the project implementation were the MSTs. The MSTs were highly capableteams with comprehensive skillsets to provide implementation and TA support at the woreda level. They were the backbone of theproject and helped reduce the challenge of high staff turnover at the woreda level by serving as a backup for the woreda expert whomight have moved on from the project. In low capacity contexts, WB projects need to consider a dedicatedmechanism. A holistic approach for livelihood interventions can help achieve substantial results for CDDprojects. The design of the project was informed by the practical lessons learned during the two previous operations.During the previous projects the Rural Livelihoods Program was only a subcomponent which in combination with the CommunityInvestment Fund subcomponent constituted Sustainable Livelihoods Enhancement. However, in this project livelihood creationwas given due attention and it was a separate component constituting the following three subcomponents: (i) Promotion of newpastoral SACCOs, (ii) Identification and development of livelihood opportunities, and (iii) Promotion of adaptive research andinnovative practices. Together, the three subcomponents ensured that the project followed an integrated approach to establishing aproper setting for developing livelihoods. This holistic livelihood intervention has led to considerable positive impacts in termsof the income increase and poverty alleviation of beneficiaries in the project areas. Adequate timefor planning in the first year of implementation is key for CDD projects. According to the project design, the first yearof the project was to be spent on the planning and capacity building of the project following principles of CDD. The three-yearimplementation plan was formulated during this exercise, which built the necessary foundation for the project to be implementedeffectively. Though this three-year plan was refined during the life of the project, it provided a useful perspective and startingpoint to the project team on how to implement the activities. CDD projects need to pay special attention to planning and capacitybuilding to ensure a strong foundation for project implementation.
P130299 | National AIDS Control Support Project | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/872401624992249938/text/India-National-AIDS-Control-Support-Project.txt | http://documents.worldbank.org/curated/en/872401624992249938/pdf/India-National-AIDS-Control-Support-Project.pdf | The ICR (pp. 46-48) provided lessons and recommendations that were grounded in the projects experience but, in many cases,extended that experience to other disease areas and contexts. They included:Peer networks can be effective agentsof communication and change, as this projects experience illustrates. This lessonled the ICRtopertinently recommend the use ofpeer networks to advanceCOVID-19 vaccinationprograms.Differentiated care models that provided client-specific services can facilitate the delivery of preciseand targeted interventions. During this project, the fast-tracking of ART refills, decentralized ART dispensation atcommunity support centers, multi-month dispensation, and community-led dispensation produced reduction in wait times and improvedtreatment adherence. Similar differentiated care strategies might be effectively extended to treatment and management of chronicdiseases.Successful interventions are underpinned by good data. This projects success was predicatedon the findings of well-crafted and implemented epidemiological and behavioral surveys and surveillance. The ICR observed thatcontinued progress will depend on continuing the projects efforts to integrate HIV data with other routine data in the healthsector, so that individuals can be followed through the entire continuum of care.
P130328 | DJ Crisis Response - Social Safety Net Project | Middle East and North Africa | Djibouti | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2019 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/512561601510253423/text/Djibouti-DJ-Crisis-Response-SSN-project.txt | http://documents.worldbank.org/curated/en/512561601510253423/pdf/Djibouti-DJ-Crisis-Response-SSN-project.pdf | The lessons learned are drawn from the ICR and adapted by IEG. It is possible to design and implement anambitious project in the context of crises, bridging the gap between short-term emergency assistanceand longer-termdevelopment. The project was designed under the IDA Crisis Response Window but contained both emergency and development aspects.Activities combined a short-term, quick response to a drought to prevent the loss of human life and to preserve human capital withmedium-term activities targeting sustainable changes in nutritional practices through behavior change. Project activitiesalsolaid the foundation for providing a well-targeted national safety net system. Community-based nutritionpromotion can be a powerful instrument to help improve health and nutrition practices. This community approach combined targetedcommunication, leader role models (mre conseillres), and positive reinforcement of good behaviors bybringing mothers in a community togetherthrough peer-to-peer interactions. The sessions provided tailoredinstruction onpre-natal care and for mothers with children under two years of age (up to the age offive years in rural areas). The sessionsprovided a platform to detect potential stunting of participating children and to provide a home visit for more individualizedcounseling and a referral to a health clinic if necessary. Targeting demand-side changes in behavior requires sufficientsupply-side services. Inadequate or missing health facilities or services can constrain up-take of positive behavior changes.Needed investments on the supply-side include those in education, health, and water and sanitation.
P130339 | India Second Kerala State Transport Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2021 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099635011012224526/text/P1303390281d1b07e0a60d0295105bb9e2d.txt | http://documents.worldbank.org/curated/en/099635011012224526/pdf/P1303390281d1b07e0a60d0295105bb9e2d.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Community engagement and a bottom up approach may be useful in designing effective road safetyinitiatives. This project addressed road safety issues through physical infrastructure and behavioral change interventionson a high risk corridor. The activities were designed based on community engagement and involvement of village, school faculty andstudents, as well as community monitoring at 17 locations on the demonstration corridor. This decision to involve the localplanning agency and the think tank National Transportation Planning and Research Center (NATPAC) helped in developingevidence-based road safety interventions and customizing road safety standards to local requirements for the vulnerableroad users.2. Systematic capacity building and training in road safety can help in designing road safetyinitiatives at the sub-national level. The Challenge Fund in this project aimed at introducing road safety practices atthe sub-national level. However, in this instance, the limited progress made towards this end was largely due to the inadequatecapacity in the districts to formulate policies.3. Steps taken early during preparation can help inaddressing the issue of inadequate contractors. This project faced the dual challenges of attracting out-of-statecontractors due to the artificial entry barriers and sub-optimal capacity of the local contractors. The lesson was that loweringentry barriers, helping build capacity in the contracting industry can help in building a strong and vibrant contractingindustry.4. Well-designed project components can help in supporting comprehensive institutional development, evenif not explicitly included in project design. The components supported not only road rehabilitation and road safetyat design, but subsequently introduced climate and disaster resilience aspects. This helped in better mainstreaming climate anddisaster screening activities (although they were not initially included in the original design).The borrowerscomments in Annex five draws a further lesson.Given that natural disasters can very quickly damage theassets,it would help to anticipate and design more fail proof roads. Although this may incur higher initial investment costs, the Government may accept cost, considering the heavy losses incurred when the roads are damaged because ofdisasters.
P130343 | MENA- Desert Ecosystems and Livelihoods Knowledge Sharing and Coordination Project | Middle East and North Africa | Middle East and North Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/957501544713152319/text/Middle-East-and-North-Africa-MENA-DELP-Regional-Project.txt | http://documents.worldbank.org/curated/en/957501544713152319/pdf/Middle-East-and-North-Africa-MENA-DELP-Regional-Project.pdf | The lessons are taken from the ICR (page 22) with some modification in language: A clearly definedquality assurance mechanism isimportant to ensure high international standardsforknowledge managementprojects. It is essential to clearly define the objective and expected impact of each knowledge sharing activity liketraining, workshop, and study tour. For projects whose main aim is knowledge management and sharing, design elements should includeinternal and external quality assurance procedures and mechanisms (including appropriate peer reviews) to ensure high internationalstandards. Such an approach should be supported with the appropriate level of financial resources at the designstage. For multi-country projects, having clear parameters on ownership and participation by each beneficiarycountry, especially in national activities, is importantto ensure achievement and sustainability of projectoutcomes. Full implementation can be ensured by having detailed tracking mechanisms and parameters inplace. In order to assess theimpact of knowledge management projects, timely knowledge sharing anddocumentation of behavior change is necessary. A clearly defined objective for each knowledge product and an impactassessment mechanism before and after the event (i.e. training, workshop, study tour, document, etc.) will allow the feedback to beused in real time to inform future knowledge management.
P130413 | Fourth East West Highway Improvement Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/724901624670690855/text/Georgia-EAST-WEST-HIGHWAY-4.txt | http://documents.worldbank.org/curated/en/724901624670690855/pdf/Georgia-EAST-WEST-HIGHWAY-4.pdf | The lessonsare drawnwith some adaptation of language.1. The overlap of design andplanning from one section of road to another, and from one project to another, can speedimplementation of a whole strategicroad corridor but comes at a cost. Such approach under this project required anextraordinary effort, EIAcoordination, multi-donor coordination, and multi-project phasing. The adoption of a programmatic approach could have deepened thelevel of the Banks engagement. This is particularly the case with governance interventions such as road safety andinstitutional development, where many stakeholders are involved, and interventions are required over a long period of time. Theprogrammatic approach would also be suitable for the phased approach followed in developing the highway (earlier phases includeconstruction of specific sections, while preparing studies for the subsequent sections).2. Capacityassessmentneedsto take into accountsector-level, not just immediate project considerations. The risk ofpoor program and donor coordination causing a problem for the RD was assessed as low under this project because the Bank was theonly IFI assisting the government in the road segment of this project and because there is a good inter-donor and donor-governmentcoordination. However, the long list of activities that needed to be procured and managed in the country as a whole, and involvingother donors (EIB, ADB, AIIB), led to the RDs capacity being stretched and affected the timeliness of delivering theproject.3. Awide range of components and responsible government agencies can reducethe level ofdiligence at preparation. For example, the readiness of the Contractors Association to support delivery was not assessedas adequately as aspects related to the larger components. The large number of activities placed pressure on RDs teams,particularly when several new projects were being prepared. Projects should be prepared with streamlined implementationarrangements in mind and should be designed with more attention to executing agencies capacities, not only to implement thesubject project, but also the pipeline of projects that will be prepared and implemented in parallel. The study on assessing thecapacity of RD should have taken place during project implementation.4. In ME design, theoutcomeindicator increase in asset value of aroad corridor may not convey meaningfulinformation. It is the cumulative book value of recently made investments. It is not a financial asset valuenor a measure of economic benefit. It does not measure the change in the value of adjacent land arising from the transportimprovement. If it is to be useful as a measure of government and IFI commitment to the corridor as a whole, it should bere-defined in more formal financial terms or economic terms, or as the economic benefit of higher land value.
P130421 | Second Regional Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/462351607628645849/text/Georgia-REG-DEV-2.txt | http://documents.worldbank.org/curated/en/462351607628645849/pdf/Georgia-REG-DEV-2.pdf | The ICR (p.29-30) included several lessons, which were adapted by IEG: Cultural heritage projectsthatinclude retrofitting, restoration, and adaptive reuserequire specialized workers and time, which needto betaken into account in the project design. In this project, these factors were not sufficiently taken into account whenpreparing the project, resulting in delays during implementation. Also, several designs prepared by government agencies had to beadjusted to the actual situation, also resulting in delays in construction and the necessity to revise works for severalsub-projects due to poor quality resulting in additional costs. Designing a Results Framework thatmeasures the impact of project activities needs to be put in place before project implementation starts.In thisproject, major changes in ME such as hiring an ME consultant and revising the Results Framework only took place one yearbefore project closure. This makes the extent to which the projects theory of change was accurate and operationalquestionable as well as to what extent reliable data was collected. Learning from previous projects,especially if the current project is a follow-on project, is critical and helps to develop mitigation measures to ensure thatprevious issues do not materialize again. In this project, the first RDP was only effective for eight months before thisproject became effective, not allowing to learn from the first RDPs implementation experience. Therefore, the Bank teamcould not take previous lessons learned into account, which resulted in several implementation issues (similar to the ones of thefirst RDP) such as the PIU not having the necessary capacity to perform its procurement functions resulting in implementationdelays.
P130459 | Development Policy Loan 2 | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/450711468186274707/text/ICRR14887-P127433-PUBLIC.txt | http://documents.worldbank.org/curated/en/450711468186274707/pdf/ICRR14887-P127433-PUBLIC.pdf | The ICR distills a number of pertinent lessons:The Bank's value to a high income client like Poland lies in its knowledge base and analytical strengths rather than its financial resources. Flexibility and responsiveness contributed to the operation's value. A program is more likely to be be effective if it is rooted in an established partnership and shared priorities.Strong ownership is essential as well as a consultative process where reforms are potentially contentious.Bank support for an EU member state must be consistent with the economic governance framework of the EU.
P130459 | Development Policy Loan 2 | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2019 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/340071559242287976/text/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/340071559242287976/pdf/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.pdf | Lessons 8.2 The Independent Evaluation Group draws the following lessons\. â€¢ Development policy lending can help mitigate global economic and financial shocks and protect vulnerable groups in high-income countries when accompanied with timely, high-quality, and responsive technical assistance that supports the reforms. The series were appropriate to reinforce the credibility of the authorities' commitment to reform, while providing technical solutions for the reform program's design and implementation. The DPLs enabled dialogue on important reforms the government was undertaking based on its analytical and advisory work. â€¢ Where a high-income country is required to implement constitutional provisions, or agreed reforms with a regional body, providing support for the implementation of such reforms is likely to enhance the likelihood of success. In the case of Poland, policies limiting fiscal deficits and overall debt levels were required both by EU agreements and constitutional provisions. Though these policies were complex, the government committed to implementing them because of the importance of EU accession agenda to Poland's economy. However, policies not so required by the EU were more easily reversed, for example, the increase in the retirement age. â€¢ RAS are a promising tool for engaging governments in high-income countries when Bank Group staff demonstrate the capacity to produce timely and highquality analytical products in response to government requests. In the case of Poland, the government appreciated the quality and responsiveness of World Bank staff to their analytical needs. However, World Bank adjustment to the different business model could have been better managed. Staff had the (sometimes difficult) task of explaining to the government why the World Bank needed to charge high-income clients for services, while still requiring sole source procurement and retaining intellectual property rights. The World Bank and government are now working together to make RAS mutually beneficial and a new tool for engagement. â€¢ Coordinating with other partners in situations where the World Bank is not the largest stakeholder is important for successful implementation of reforms. In the case of Poland, the EC and the IMF are the dominant development partners providing more funds or guaranteed resources to the government. â€¢ Analyzing the political cost of implementing proposed reform measures is an important part of policy lending. Such an analysis would have been particularly useful in relation to the pension and labor market reforms these two series attempted to support. It is notable that Ministry of Finance staff requested such advice in the future to guide the implementation of new reforms.
P130474 | Management and Protection of Key Biodiversity Areas in Belize | Latin America and Caribbean | Belize | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2020 | 2020 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/437101590112582822/text/Belize-BZ-Mgmt-and-Protection-of-KBAs.txt | http://documents.worldbank.org/curated/en/437101590112582822/pdf/Belize-BZ-Mgmt-and-Protection-of-KBAs.pdf | The ICR (p. 22-23) included several lessons learned: Building and sustaining government ownership at alllevels is critical for a timely delivery of project results and outcomes. In this project, technical contributionsfrom the technical departments was limited and commitment to monitoring, reporting and coordination among implementing agencies wasweak and had a negative impact on project implementation. The complexity of a project needs to match the localtechnical capacity and level of financing. In this project design was complex, partly as a result, the Bank was not ableto build sufficient local capacity due to financial constraints in regards to project management. Engaging withlocal communities is critical to ensure positive outcomes and their sustainability. In this project, some stakeholderssuch as co-mangers of PAs in the KBAs were not aware of the project and were therefore unwilling to participate in the assessmentof priority rehabilitation and resilience opportunities.
P130492 | ENVIRONMENTAL SERVICES | Europe and Central Asia | Albania | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099600006022227499/text/P13049204f59630620977c05bf147158d3e.txt | http://documents.worldbank.org/curated/en/099600006022227499/pdf/P13049204f59630620977c05bf147158d3e.pdf | The ICR provided five lessons. Some of them are summarized below because they may provide lessons of interest for otherenvironmental services projects.Ensuring buy-ins for piloting Payment for Environmental Services (PES) schemesrequire careful preparation. While two PES pilots were prepared by this project, their implementation was delayed becauseof the lack of preparation regarding three necessary conditions, namely: (i) time for the required technical and socioeconomicstudies to be conducted; (ii) commitments from the service users to pay for the environmental services; and (iii) identification ofa champion within the Government (ICR, para 92).Designing a project component aligned with an existing grantscheme such as the EUs Instrument of Pre-Accession and Rural Development (IPARD) can provide opportunities for resourcemobilization for congruent practices. Thisproject modeled the IPARD-like grant program after a previous similarprogram in Montenegro. Capacities of the government agencies and the grant recipients were built throughlearning-by-doing under the grant program. In particular, the Agricultural and Rural Development Agency strengthenedits capacity and reputation as the administrator for the anticipated IPARD forestry measure through experience with this project(ICR, para 94). As a result, the accreditation package with a forestry measure was successfully submitted and is being reviewedforIPARD III funding for 2022-2027.
P130512 | Lao PDR Second Trade Development Facility Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/157211581110624420/text/Lao-Peoples-Democratic-Republic-Lao-PDR-Trade-Development-Facility-2.txt | http://documents.worldbank.org/curated/en/157211581110624420/pdf/Lao-Peoples-Democratic-Republic-Lao-PDR-Trade-Development-Facility-2.pdf | The introduction of a challenge facility provides flexibility to adapt to new challenges duringimplementation. The introduction of a challenge facility under the project made resources available torapidly respond to small emerging priorities in public agencies that fit within the governments trade integrationstrategy. For instance, an electronic procedure for obtaining certificates of origin were developed, and a toxic chemicalslaw was prepared. While the facility turned out to be aflexiblemeans to respond to small priority activities, italso created a risk of expanding the scope of the project and involving too manystakeholders.A well-defined results framework can be especially useful whenimplementing technical assistance projects. TDF-2 was a technical assistance project that included capacity buildingand building for reform.During preparation and implementation, new opportunities arose that expanded on the project and,while useful and ultimately justified, contributed to postponements in implementation that a more rigorous results framework mighthave avoided. In particular, the experience underlines the disadvantage of not having a clearly defined theory ofchange. Export promotion was stressed in the PAD, while the PDO focused on diversification more generally. Designing aclearer theory of change in the beginning, outlining how supported reforms, including ones initiated under the challenge facility,were going to affect economic outcomes, might have facilitated the selection and design of activities.
P130548 | Sri Lanka Strategic Cities Development Project | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099022503012341899/text/P13054802c4bd20710ad5e08df377a36fb1.txt | http://documents.worldbank.org/curated/en/099022503012341899/pdf/P13054802c4bd20710ad5e08df377a36fb1.pdf | Three lessons were derived from the operations, with one added from the result of the experience in procurement. These arepresented below with slight modification (ICR, paragraphs 76-78): When implementation capacity is notcarefully assessed, it may affectthe effective use of Additional Financing (AF). In this project, AF was to be usedfor activities in Jaffna to achieve regional balance. The proposed activities in Jaffna were appraised using a framework approach.A framework approach in design calls for a general agreement of the major sectors to be financed under the project with specificstudies, detailed designs, and implementation planning to be carried out after the Board approval (ICR, paragraph 44). This meantthat Jaffnas implementation capacity was notadequately assessed beforehand. As a result, almost 50 percent of the US$55million AF credit to finance additional activities in Jaffna wascancelled because it lackedimplementation capacity.Design was delayed and the activities would not be completed during the project period. The AF is a useful instrumentforactivities that can be realistically implemented within the AF credit/loan timeline. A complex implementationdesign involvingmulti-city and multi-sectoral projects may jeopardize the projects achievements. In thisproject, design called for urban upgrading, preserving cultural heritage, reducing the risk from floods,and city-widetransport reform across three different cities. This designproved difficult to implement. Thelimited resourcesinmulti-disciplinary sector expertise in Galle, Kandy andJaffna, limited its project management and implementationcapacity. Multiple agencies at central and local levels were needed to collaborate closely. This newly introducedarrangementled to furtherimplementation delays. Asimpler design, such asmulti-city but focusing on a specific sector, or apilot multi-sectorproject in a single city with sufficient capacity may have been a more useful sequenceto addresscity-wide challenges. AF would then be used as an instrument to expand the project based ontheevidence. Ensuring flexibility in construction contracts may facilitate accommodation of externalshocks. In this project, external shocks included the Easter Sunday bombing, the COVID-19 pandemic, and thecountrys deteriorating economic condition. These shocks led to lack of materials that caused delays and price escalation ofmaterials and works.Future projects may designconstruction contracts to includea cost escalation methodology toaccount for rapid escalation of commodityand building materials prices, exchange rates fluctuations, or war elsewhere in theworld that may affectsupply chains. A joint procurement andcontract administration unit within thePMU maybenefit implementation.In this project, the procurement unit was separate from contractadministration.Contract administrationoperated independently under the supervision of a Deputy Project Director butwithoutadequate capacity for contract management. This resulted in delays in contract management andenvironmentalcompliance issues. The project could have benefitted from a single unit for contract administration and management, with adequatequalified staff (ICR, paragraph 65).
P130694 | AFCRI-Nile Cooperation for Results Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Water | RETF | IPF | 2013 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099810012012132584/text/Eastern0Africa00for0Results0Project.txt | http://documents.worldbank.org/curated/en/099810012012132584/pdf/Eastern0Africa00for0Results0Project.pdf | IEG derives the following lessons drawn from the ICR:1. In identifying regional investment opportunities,being demand-driven is a necessary but not sufficient condition on account of changing contextual factors and competition overlimited resources. There is a need to involve the appropriate departments within line ministries throughoutpreparation. Secondly, site selection for national lending should balance national benefits and regionalconsiderations. Thirdly, there is a need to align financing prior to undertaking design studies, to ensure that theinvestment is mobilized. Bank teams would also need to provide structured guidance on processes, clearances and validation offindings on national investments prepared by regional entities, especially for investments where a financier has yet to beidentified. Rapidly shifting geopolitical contexts demand maintaining a flexible technical design, aided by advancedstrategic planning and intermittent strategic evaluation. To facilitate this, to the extent possible, teams must leverageadditional resources to supervise technical assistance and provide implementation support.2. In terms ofproject design,the structuring ofresults and outcomes around metrics that clearly link to project objectives andoutcomes will help capture the projects achievements better. The experience of the project shows thatrevisiting the PDO indicators to provide a clearer logic would have aided in assessing and fully capturing NBIs manyachievements. As such, teams should take steps to tailor the results framework, as necessary, using fact-finding andintermittent strategic evaluation to ensure that targets are set or recalibrated appropriately.3. Deepeningthe World Banks engagement in the transboundary cooperation agenda, together with other development partners, is importantto the achievement of specific development outcomes and enhancing delivery of prioritized services. For instance,whole NBI has demonstrated significant progress to date, it would like to improve cooperation within the organization and moreeffectively use institutional partnerships to demonstrate results and service delivery impact. It could also leverage otherorganizations and specialize itself in order to have a clear lead role in the ecosystem of organizations.
P130710 | Low Income Community Housing Support Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099052824173033465/text/P13071014ba76b09e1a3321c0d9585a75e7.txt | http://documents.worldbank.org/curated/en/099052824173033465/pdf/P13071014ba76b09e1a3321c0d9585a75e7.pdf | The following lessons are extracted from the ICR (rephrased):Community mobilization is more likely to succeedwhen facilitating expertise is made available. The project contracted a single DS firm to provide TA on socialmobilization, community development, engineering design and construction supervision. The lack of an effective skills mix impactedthe quality of social mobilization and community engagement in favor of infrastructure development.Theinstitutionalization and sustainability of community organizations are more likely to be successful if a multidimensional approachis in place. Although community organizations had been created and supported by a previous government project,additional investments were needed to build their capacity but were not adequately addressed during project implementation. Thisaffected the quality of community processes and sustainability of community organizations., which would have benefitted fromdecentralizing funding and financial ownership.If the constraints of land and tenure security are not addressed,this may jeopardize any efforts at improving poor housing and living conditions for the urban poor. The scarcity of landand the tenure insecurity was a critical urban development challenge in this project in Bangladesh, conditioning project success onthe improvement of land transfer procedures (they took 7 years in Kobdaspara). The modernizing and simplification of landadministration and acquisition systems seems to be a prior key constraint to be addressed to allow for housing improvementinterventions to be relevant and successful.IEG draws the following lesson:When a strong focus is placedon ME capacity and systems, pilot initiatives will likely yield the operational learning capital expected from them.In this project, the knowledge production was not as expected due to the lack of expertise and capacity to manage therequired ME.
P130735 | BF-Youth Employment & Skills Development | Western and Central Africa | Burkina Faso | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/276811622225970891/text/Burkina-Faso-BF-Youth-Employment-Skills-Development.txt | http://documents.worldbank.org/curated/en/276811622225970891/pdf/Burkina-Faso-BF-Youth-Employment-Skills-Development.pdf | Lessons drawn from the ICR, adapted by IEG (pages. 37-38): Complexity of project design canhinder fullysatisfactoryachievement of a PDO that was set at theappropriate ambition level (albeit with subsequent revision oftargets). In the case of this project, the PDO took into account the novelty of the objective and the low capacityenvironment; however, the implementation arrangements were complex, including a multitude of public and privatesectorimplementing agencies (with resultant long decision chains) and varying capacity levels, and multiple types of trainingprograms. In a labor market characterized by sufficientavailability but low quality of employment, interventionsaddressing the quality of jobs and related monitoring can capture important labor market impacts. In the case of thisproject, interventions were designed to lift youth into more productive, better paying jobs, not necessarily employment perse. The original results framework did not include indicators to measure these impacts but a project evaluation wassubsequently included to provide evidence of achievement along the lines of quality of employment. Job-training in and ofitself is insufficient if the PDO includes insertion into the labor market. In the case of this project, measuring supplyside achievements (i.e. the number of youth trained or the proportion of youth who completed the training) does not reflectsuccessful integration into the labor market. Additional interventionsthat match supply with the existing labordemand, provide access to capital for self-employment opportunities, and enable beneficiaries to increase savings can beeffective.
P130786 | Urban Scale Building Energy Efficiency and Renewable Energy | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2013 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/343511620937537646/text/China-Urban-Scale-BEE-and-RE.txt | http://documents.worldbank.org/curated/en/343511620937537646/pdf/China-Urban-Scale-BEE-and-RE.pdf | Of the several lessons in the ICR, the following two have high value for broad applicability and replicability in similar Bankprojects in the future.Evidence-based policies piloted at the city and regional levels can facilitate thereplication of such policies nation-wide by informing positive statutory and regulatory changes. The project was designedas a research-pilot-adopt-replicate model for policy development to promote LOCAL urban forms and increase energy efficiency inlarge public and commercial buildings. Based on the theoretical framework that was formed by methodical research, the LOCAL urbanform policies and energy performance benchmarking and disclosure methodologies were piloted in Beijing and Ningbo. The results ofthese pilots were used to create consensus on the applicability of these solutions. These were also replicated in two more cities,i.e., Qingdao and Chongqing, during project implementation. Despite some risks associated with the different economic anddevelopment levels of other cities for the nation-wide replication of the outcomes, the research-pilot-adopt-replicate model, acommon model used in China, was successful in introducing these new and innovative solutions to the country.Energyefficiency primary data need to be made available in order to enable the valuation of energy efficiency improvements, which couldresult in the substantial replication of such improvements. The introduction of energy performance benchmarking anddisclosure methodology and guidelines resulted in a transparent and consistent system of data recording, evaluation, and sharing.Lack of data about energy performance of buildings was a major barrier to the implementation of energy efficiency improvements.Availability of such data also supports long-term planning of building energy efficiency improvements. Through comparison anddisclosure of energy efficiency data, the decision-makers can determine whether a building should be retrofit or rebuilt in a mostcost-effective way.
P130801 | Regional Coordination for Improved Water Resources Mgt. & Capacity | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | GEF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/782271538143122636/text/Egypt-Arab-Republic-of-Regional-Coordination-for-Improved-Water.txt | http://documents.worldbank.org/curated/en/782271538143122636/pdf/Egypt-Arab-Republic-of-Regional-Coordination-for-Improved-Water.pdf | The ICR listed six lessons. In brief they were: (i) Linking research to practice is key for development effectiveness;(ii) Successful demonstration of innovative technologies ensures sustainability and helps create demand; (iii) Simplicity of designoptimizes the impact; (iv) Relevance of the project is imperative to ensure strong political support and government ownership; (v)Technological innovations cannot be sustained without local expertise;and (vi) Viability of small scale grants and standaloneprojects.IEGs summary of the main lessons, based in large part on the ICR, were asfollows.Technical and scientific cooperation with advanced institutions can help developing countries builddomestic capacity and access modern technologies. This project has enabled the transfer, validation and operationalizationof various WISP tools for improved water management and decision making within the NARSS in Egypt. This was made possible throughextensive capacity-building program in collaboration with NASA, John Hopkins University, Wisconsin University, and the Institute ofRemote Sensing and Digital Earth and Chinese Academy of Sciences (RADI/CAS). NARSS in turn worked directly with the relevantline ministries(including the MWRI, MALR, and Ministry of Environment, among others) to ensure that the data andmethodology developed is transferred to these entities for improved water resources and agricultural management. The lessonwas that leveraging its convening power, the Bank was able to support the mobilization of international and regionalexpertise to transfer and operationalize various WISP tools, validate new technologies, and then customize and adapt them for usein Egypt. International cooperation for technology transfer works better when the technology is sourced fromdifferent countries and can be accessed from alternative suppliers. The performance of this project was severelythreatened because of a temporary change in U.S. Financial Aid Policy to Egypt that led to NASA stopping all technical assistanceactivities provided to Egypt for about two years. This resulted in serious delays in all activities related to and depending on thetransfer of the Land Information System (LIS) from NASA. This prompted the NARSS to work on finding alternative options toimplement project activities and acquire the needed software. The situation only improved in late 2015 when NASA provided the LISsoftware to the NARSS after agreement with USAID/NASA and NARSS was finally reached in December 2015 following the change in US aidpolicy. The NARSS was however able to install and operationalize the ETWatch System (independently of LIS) to measure the ET fromspace and produce maps for excess water usage in agriculture activities. The experience in this project showed that this was madepossible through the partnership with the Chinese Academy of Sciences, facilitated by the World Bank, which provided hands-ontraining programs in China on the ETWatch System for scientists and researchers from the NARSS, MWRI, andMALR.Anticipated benefits from technology transfer are imperative to ensure strong political support andgovernment ownership. Given the relevance of the project to the governments strategic needs, leaders at all levelsof government focused on the projects progress and implementation management, and set up effective interdepartmental,multilevel cooperation mechanisms. This commitment and ownership were important for completing activities despite the two-yeardelay that affected the progress of the project. This experience confirmed again the need for the World Bank, together with itsclients, to take necessary measures at the design stage to clarify the relevance of projects to meet the higher-level governmentpriorities and strategic needs.Small scale and standalone technical assistance projects cannot ensuresustainability and scaling up of technology transfer. Despite the effectiveness of this small standalone GEF grant forfacilitating the transfer of technology and support for capacity building in Egypt, the rollout of the WISP tools at the nationallevel requires substantial financial resources and large-scale capacity enhancement. The lesson is that a small projectactivity cannot facilitate the scaling up of innovative technologies unless it is linked with follow-up programs or ongoinglarge-scale investment projects.
P130819 | HN Safer Municipalities | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/855921580145988741/text/Honduras-HN-Safer-Municipalities.txt | http://documents.worldbank.org/curated/en/855921580145988741/pdf/Honduras-HN-Safer-Municipalities.pdf | The ICR presented nine lessons to consider at design stage that could help strengthen future similar project interventions inFragility, Conflict, and Violence settings. IEGadded one more cited elsewhere in the ICR but equally important (ICR,paragraph 31). Some of these lessons are presented below: A robust Theory of Change may strengthen riskassessment. This project did not have an initial Theory of Change at design stage. One was established at restructuring. Arobust Theory of Change would have provided a means to assess shocksduring implementation such as the ones encountered inthis project. For example, the reversal of policy regarding the source of municipal financing ofits localized violenceprevention interventions, loss of leadership in the countrypolicy dialogue, and fiduciary issues may havetriggeredcorrective measures or strategies to avoid slowing downimplementation since these points were methodically monitored as partof Implementation Status Reporting. There could be early warning signals incorporated into the results framework that addresscompliance with Bank policies at the sub-project level (e.g., safeguards, procurement) to avoid disrupting the trust momentumestablished among project beneficiaries. In this project, the expenses associated with the ineligible procurement method resultedin a fiduciary process that delayed the release of stipends to at-risk youth who were participating in interventions designed tofoster their return to the community. Beneficiaries were not mollified by promisestoquickly resolve this issue.Grievance Resolution Mechanisms could also be used to provide frequent feedback for better communication on how issues were beingresolved. Periodic review of the country context in fragile, conflict, and violence settings may provide anopportunity to redouble efforts to achieve the PDO. This was the first World Bank funded standalone violence preventionproject. The challenges it faced during implementation compounded its achieving the PDO. For example, a change in government wouldhave triggered a lookout for any policy or incentive changes, or movements among alliances who have a stake in theoutcome ofthe project to alert on possible implementation hiccups. Appropriate strategies could be adopted in a timely fashion toensurethe project achieved its intended results. In addition, periodic review could point toadding resources for staffsupportin communications and partnerships particularly when the project requires a multi-sectorcoordination. Limitinga menu of different kinds ofinterventions to balance cost effectiveness withcommunity demand may lend to measurable impact on violence prevention.For example, to recover public space, optionsthat use CPTED methodology could be limited to a few that directly provide causal relations with reduced violence in a targetneighborhoods. Adding longer term elements to assisting at risk youth (e.g., credit, apprenticeships, internships) may providegreater impact. A social sense of belonging and agency are also important considerations inassisting at risk youth (ICR,paragraph 31).
P130835 | KP Southern Area Development Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/307031624302320172/text/Pakistan-KP-Southern-Area-Development-Project.txt | http://documents.worldbank.org/curated/en/307031624302320172/pdf/Pakistan-KP-Southern-Area-Development-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Project design needs to betailored to suit the local context, with appropriately identified riskand mitigation measures. With an implementation period of only two and half years and a limited implementing capacityoperating in a fragile environment, the Community-Driven Development (CDD) was inappropriate given the realities on theground.Further, the activities to increase access to productive infrastructure were ill-suited to improve livelihood options,because they revolved around agriculture and livestock raising, in an area where only eight percent of the land wasarable2. Capacity building strategy for CDD operations is required for sustainability of projectoutcomes. In this project, although efforts were made to link community based platforms with relevant governments at thedistrict level, they were not followed through and none of the community groups werelegally or formallyregistered.3. ME framework needs to be carefully designed, implemented and utilized to inform qualitymanagement and decision-making. This project was affected by the poor quality of data. TheBank did not have a cleargrasp of implementation challenges and consequently did not address the key design constraints. Further, the lack of a survey atclosure precluded monitoring performance of activities that were attributable to the project.
P130847 | Competitiveness DPL 2 | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Among the lessons highlighted in the ICR are: Lending operations of the WBG, including DPLs, need to beunderpinned by adequate diagnostics and technical assistance programs. Examples include the analytical services oncompetitiveness and a technical assistance program under the Competitive Industry and Innovation Program Trust Fund that had beendone in FYR Macedonia. This array of knowledge work paved the way for this programmatic series of DPLs. DPLs oncompetitiveness can advance the mission of the WBG by leveraging the strengths of the private sector. For countriesthat aspire to become members of the EU, aligning program objectives and actions with the EU accession agenda is an effective wayto ensure adequate implantation of the reform program.
P130864 | TR Third Access to Finance for SMEs (SME III) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/130691582042131572/text/Turkey-TR-SME-III.txt | http://documents.worldbank.org/curated/en/130691582042131572/pdf/Turkey-TR-SME-III.pdf | Three lessons are drawn from the ICR (pages 23-24), with some adaptation.The use of quantitative PFI andSME eligibility criteria and theirinclusion, together withSME loan terms and conditions, in legal covenants of FILoperations help ensure that lending to SMEs observe commercial and financial viability standards. In this project,quantitative criteria were drawn for the eligibility of PFIs to act as lenders and SMEs as borrowers. The quantitativecriteria, covering among others the assetsize andprofitability of PFIs, coupled with theinclusion of thesecriteriaas covenants in the Loan Agreement,were designed to screen outtroubled financial institutions from theproject. Similarly, the project alsoestablished quantitative criteria for the eligibility of SMEs and quantitativeconditions for SME sub-projects, setting them as legal covenants,to reduce the risk that the loan funds would be wasted onnon-performing SME loans.Potential market competition (between an apex bank and PFIs) should be consideredcarefully in the choice of an apex bank in a financial intermediary lending operation. TheBank had carefullyconsidered the financial condition and record of financial performance ofthe candidate institution, its credit and riskmanagement practices, and the overall the quality of its corporate governance.But, the Bankshould be carefulabout selecting an apex bank that competes with PFIs in the same target market of the FIL operation. In this project, ZiraatBank encountered problems collecting information from PFIs; according to the ICR, it was difficult for PFIs to share data about itscustomers and its portfolio withthe apex bankbecause the PFIs and the apex bank were competitors in the same leasingmarket.Mandates to introduce new financial products should be supported by technical assistance to thesponsoring financial institutions. This project required the PFIs to introduce new leasing products, but only one PFImanaged to offer one new product to the market over the five-year life of the project. The ICR explains that there wereinstitutional, market, and project design constraints to the introduction of new leasing products (see Section 4). Technicalassistance tothe government, the apex bank, and the PFIs would have helped uncover and address these issues, including withchanges to the project design or with proposals for additional financial sector development measures.
P130865 | Nigeria Polio Eradication Support Project | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099435103022234770/text/Nigeria000NG0P0ation0Support00FY130.txt | http://documents.worldbank.org/curated/en/099435103022234770/pdf/Nigeria000NG0P0ation0Support00FY130.pdf | The ICR (pp. 37-39) offered several important lessons and recommendations, including the following lessons, partially re-statedby IEG:Leveraging partner capacities, expertise, and field presence of UN agencies significantlycontributes to project progress toward achieving its objectives. Given that most of the project funds were channeledthrough WHO and UNICEF, the government utilized the well-functioning presence of these agencies on the ground, including forreaching communities in all states, particularly in FCV settings in the North. Strong capacities and financial managementstructures of UN agencies were effectively utilized to ensure availability, uninterrupted supply, and timely delivery of vaccinesto children, with close monitoring. Although costs were relatively higher compared to solely using public delivery structures, thefact that project operations were undertaken effectively with quality considerations and in a timely manner prevented long-drawnefforts and made the use of UN agencies less costly in the long term.Systematic collection,analysis, and use of real time data for decision-making are key for improved vaccination performance and for providing promptsupport to lagging areas. Prior to the project, only administrative data and irregular survey data were available.State-wide data could not adequately guide effective local targeting and course corrections. Learning from polio eradicationefforts that instituted the use of Lot Quality Assurance Sampling surveys, the project adapted this method for routineimmunization, resulting in systematic and robust data collection at the lowest administrative level, and allowing quickdecision-making and course corrections in real time, including for supporting immunization officers and providing extra resourcesin remote communities. The method was institutionalized by the national and state emergency routine immunization centers, thuscontributing to improved routine immunization coverage.Innovative service delivery strategies inFCV settings facilitate the achievement of intended immunization results. A set of interventions developed to reach targetpopulations in security-compromised areas played a key role in the final push towardpolio eradication and routineimmunization improvement. These interventions included monthly security risk assessments; carrying out hit and runand catch-up campaigns based on evolving and changing security situations; assigning permanent health teams fromwithin the community; and enhanced routine immunization services with the addition of attractive pluses such asmulti-vitamin supplementation, malaria diagnosis, and provision of biscuits for children through health camps. Communityinvolvement and ownership facilitated such interventions, and included participation of LGA Chairmen, traditional leaders, andreligious leaders, all contributing to improved vaccine acceptance and demand generation.IEGs reviewidentifies an additionallesson that builds on an importantrecommendation made by the ICR on capacity integration (p.36):National capacities that were developed by the project for immunization programs can be effectively leveragedto strengthen other programs by integrating such capacities with other programs in the health sector. Leveragingcapacities that were built to enhance polio and routine immunization was initiated during the project period. For example, theEmergency Operation Center Model used by the polio program was leveraged as part of the acknowledged successful national responseto the 2014 Ebola outbreak. Improved surveillance capacity, mechanisms, and data management facilitated the national response toCOVID-19, and the cold chain equipment and transport logistics are being used in the ongoing deployment of COVID-19 vaccines. Thegovernment institutionalized the use of performance and accountability frameworks for management at national and sub-nationallevels. The sector intends to apply enhanced surveillance capacities to non-communicable diseases, thus benefiting program areasbeyond vaccine-preventable illnesses.
P130871 | Regional Communications Infrastructure Program Phase 5 - Uganda | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Digital | Digital Development | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099073123151552374/text/P1308710f04e0c0c109799015e78b83a9f2.txt | http://documents.worldbank.org/curated/en/099073123151552374/pdf/P1308710f04e0c0c109799015e78b83a9f2.pdf | The ICR Review draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Drawing lessons from regional projects can help design and implement ICT projects. Thepreparation of this project benefitted from being part of the broader Regional Communication Infrastructure Program (RCIP). Theinclusion of Uganda as the fifth phase of the Regional Communication Infrastructure Program (RCIP) enabled greater efficiencies inthe design of the project, enabling a common set of indicators, standards, and scope to be used both in the design of the projectand the structuring of implementation arrangements. However, drawing from the implementation approach of the previous RCIPprojects, the project could have improved the connectivity outcomes for this project through greater involvement of the privatesector in deploying the National Backbone Infrastructure (NBI) through Public-Private Partnership (PPP) or direct investmentmodels.2. Using clear, industry-standard indicators can help in the ME of ICT projects. Inthis project, the indicators were industry standard indicators that were also used in other phases of the RCIP. Hence, noadditional data was required for monitoring the project activities.3. Deeper engagement with the privatesector can improve the efficiency and sustainability of outcomes in ICT projects. When this project was approved in 2015,the digital ecosystem in Uganda was in its infancy. Since then, the ICT sector has matured, with new private sector players in newmarket segments.Ensuring future interventions such as this would help create a more conducive environment for the privatesector.
P130878 | Financial Reporting and Oversight Improvement Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2013 | 2018 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/706801570458522644/text/Malawi-MW-Fin-Reporting-and-Oversight-Improveme.txt | http://documents.worldbank.org/curated/en/706801570458522644/pdf/Malawi-MW-Fin-Reporting-and-Oversight-Improveme.pdf | This review concurs with the ICRs enumerated lessons and adds to them: ME should be a critical aspectof methodically evaluating a complex project. An implementing unit should continuously review progress and explain to both internaland external stakeholders how the declared interventions are contributing to positive change. The design, at the veryinception, of a dependable, realistic and comprehensive results framework, especially suited to the project, with intermediateresults indicators, is a sine qua non for any complex project. Where the procurement of an IT system (new IFMIS)is the foundation for the project and implementation of many of the key activities are under it, every effort and focus must bemade to prioritize its timely procurement and operation. The inability and failure to timely procure a new IFMIS was a core reasonfor the projects lack of success. Where procurement and associated training are important factors in the projectand involves the introduction of complex information systems and their application, highly experienced technical assistance/supportand expertise is always essential. The presence of expertise in design, training, procurement, monitoring of implementation at allstages of implementation and including introduction of disaster retrieval systems, is necessary from the inception to the close ofa project especially dedicated to financial reporting and oversight improvement. Exogenous risks (such ascash-gate), as well as other unanticipated events, require quick mitigating responses. The changes and remedies to beintroduced and how they impact on the implementation units must be effectively and quickly communicated to all implementing units.Further, when such exogenous events do occur and clearly impact the project, it may be best to discontinue the project rather thanextend it, since the Bank runs a reputational risk to continue to support a project that was precisely designed to prevent theoccurrence of this type of event. In complex projects, the presence of a TTL on the ground is necessary tooversee critical activities, communicate with stakeholders and suggest restructuring where necessary both for preventive andproactive responses. Where the project concerns transformation of MDAs accountability, transparency and ownershipto ensure good governance in the public finance sector, it is vitally important to secure the commitment of the GOM at the highestlevels to ensure that project activities are completed, that they are well aligned with the Governments policies and toensure accounting, auditing and reporting are all in conformity with the applicable laws and regulations.
P130888 | Building Resilience through Innovation, Communication & Knowledge Svcs | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/908601590063755291/text/Western-Africa-BRICKS-PSG.txt | http://documents.worldbank.org/curated/en/908601590063755291/pdf/Western-Africa-BRICKS-PSG.pdf | Sustainability of development outcomes would be strengthened if implementing agencies and beneficiaries could adaptinnovative knowledge management tools in their core structures. When designing projects that include creation of web-basedtools, exit strategies for sustainability of the digital platforms should be thoroughly considered in terms of financial and humanresources. Towards that, one may stay away from creating the tools linked essentially to a time-bound, World Bank funded program.It would be recommended to ensure that projects were designed to support implementing agencies to secure their own budgets andtechnical staff to maintain and update the web-based tools after project closure.Funding gaps could affect theachievement of development outcomes, especially for regional projects that are costly and time consuming. BRICKS was ableto implement only about 30 percent of the support requested, partially because of the lack of financing, whether from theBRICKS limited budget or from the SAWAP projects. Dedicated budgets from national projects or national annual work plansshould include regional activities.
P130891 | MN: SMART Government | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Digital | Digital Development | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099073123152535656/text/P1308910e019cc08d0b9ac0598f0c3159fa.txt | http://documents.worldbank.org/curated/en/099073123152535656/pdf/P1308910e019cc08d0b9ac0598f0c3159fa.pdf | The following lessons are based on those provided in the ICR, with minor adjustments.1. The need to collaboratewith multiple government agencies who have varying interests and capacity levels creates risks to project outcomes. For thatreason, stakeholder management was identified as a major risk for the Project. To mitigate this risk, a Project Steering Committee(PSC) comprising representatives from the beneficiary agencies and headed by the Chief Cabinet Secretary was established andprovided oversight and across key stakeholders. The appointment of the Chief Cabinet Secretary was strategic, leveraging thePSCs authority and sphere of influence to achieve alignment and collaboration across the whole of government. Suchimplementation arrangements proved to be good practice and couldbe replicated in projects implemented in similarcircumstances.2. Complex project design can create implementation challenges. The Project was complex, covering a widespectrum of technically complicated activities that ranged from the installation of large-scale IT systems and networkstodata standards and productions, portal development, policy and regulatory frameworks for open data, and digitalization of publicservices. Managing the Project required the Bank team to provide technical assistance to different agencies on a day-to-day basis,as well as to coordinate and collaborate across different implementation agencies. This became critical at the second restructuringof November 2019, when the Project needed to be turned around. The team supported the PIU and beneficiary agencies through weeklyproject meetings and many ad-hoc meetings with the agencies related to both technical and implementation issues. It is importantthat sufficient budgetary resources are available for task teams to provide thisimplementation support with close follow-ups.The lesson is that such assistance could have been anticipated and sufficient resources made available to support the client withcapacity and technical know-how.3. Monitoring and implementation is critical for the achievement of project objectives.The Bank team closely supported the implementation agencies in strategically re-orientating their focus on project disbursementsand result targets. The Bank team worked with the implementing agency and the PIU to help them understand the importance ofdisbursements and associated results targets, explained the relevance and measurements for each result indicator, prioritized andsequenced the various project activities, and undertook the necessary actions on the prioritized activities to improveProjects performance. Achievement of Project objectives would not have been possible without thisemphasis onME.
P130903 | MA Accountability and Transparency DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/590791529101817898/text/Morocco-MA-Accountability-and-Transparency-DPL.txt | http://documents.worldbank.org/curated/en/590791529101817898/pdf/Morocco-MA-Accountability-and-Transparency-DPL.pdf | Three lessons are drawn from the ICR (pages 22-24), with some adaptation. There is valueto frontloading areform program when aclearly identifiableopportunity for transformative change emerges. The ArabSpring of 2010-11 and the ratification of a new Constitution in 2011 createdsuch anopportunity for economic andgovernance-related reforms in Morocco. The Hakama I and Hakama II development policy operations, whichaimed to promoteaccountability and transparency in the management of public resources and to foster open governance,loaded many legal,policyand institutional initiatives upfront in the program timeline to catch thereform wave goingforward. Sustained policy dialogue serves to nurture a reform process. Continuous dialogue amongdevelopment partners, governments and stakeholders keeps the focus on the policy agenda andmotivates progresswithreform actions. The Banks country dialogue with Morocco on accountability, transparency, and governancehelpedto encourage theAuthorities, albeit with some delay,to appoint members of the procurement body CNCP,enact the ATI Law,and move forward with the petitions system. Harmonization of operational demands on borrowers bydevelopment partners supporting multi-donor programs assists in the successful implementation of such programs. The Bank, EUand AFDB took a unified approach to their public-sector governance reform programs in Morocco and assumed the burden not only ofpolicy, and but also of operational, coordination. The Government did not have to comply with the separate operationalrequirements of three different external agencies.
P130903 | MA Accountability and Transparency DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2014 | 2015 | 2020 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/824781581458449816/text/Morocco-First-and-Second-Transparency-and-Accountability-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/824781581458449816/pdf/Morocco-First-and-Second-Transparency-and-Accountability-Development-Policy-Loan.pdf | 6. Lessons 6.1 Better use of knowledge and improved knowledge management contribute to the quality of operations. This assessment noted several areas where the design and implementation of World Bank operations could have been improved\. â€¢ Poor overall public expenditure outcomes for improving shared prosperity reflect inadequate intraand intersectoral allocations. The former is being managed through outcome-oriented budgeting. The latter has not been a focus because of a lack of basic diagnostic studies. Recent studies of the public investment program undertaken by the World Bank and the IMF partly addressed this issue. However, a comprehensive PER was last performed more than two decades ago. A new one should be a priority, especially given the number of DPFs being pursued in Morocco. â€¢ Lessons from experience received pro forma treatment. It is not enough to cite a lesson; its effect on the operation design should be explained. â€¢ It is important to preserve key information to maintain institutional knowledge that can inform future operations and policy dialogue. 6.2 Monitoring and evaluation require greater attention during design and implementation. â€¢ Inadequacies in reporting requirements and information conservation undermined the ability of the World Bank and its management to monitor progress. More frequent aide-memoire are needed, especially after each mission and when there is a significant gap between operations within a DPF series (in this case, two years). â€¢ The indicators selected should be aligned with the time segment of the longerterm program from which they are derived. In this case, some indicators were not fully attributable to or were misaligned with (more ambitious than) the project development objectives or what could be achieved and measured during implementation (approximately three years). â€¢ Implicit assumptions that the reform will eventually improve intersector allocations and service should be validated. This can be accomplished with parallel assessments (in this case, through technical assistance). 6.3 Greater transparency and better information management are needed to sustain dialogue as World Bank teams and counterparts change. â€¢ Key elements of the dialogue need to be recorded, per World Bank requirements, and periodic reporting by the borrower should be envisaged as part of the project design and in the financing agreement. The World Bank team should prepare more frequent progress reports when warranted (for example, after a supervision mission) and when there is a significant delay between operations in a series. â€¢ It is important to ensure a smoother transition when task teams change, especially when the program that is part of the policy dialogue is implemented over lengthy periods. 6.4 It would be helpful to assess a cluster of mutually reinforcing World Bank operations jointly. Including an assessment of the economic growth DPF series might be considered (World Bank 2013a). In this case, other potentially relevant operations would have included the parallel technical assistance provided by the World Bank and other donors (for example, assessing how complementary financing enhanced DPFs) as well as other donor support to Hakamaâ€”notably the EU's support based on the collaborative approach already developed elsewhere (World Bank and European Commission 2015). 1 Referred to as the Organic Budget Law in World Bank documents. However, Organic Finance Law represents a more accurate translation of the original name in French (loi organique relative a la loi de finances). See\. http\.//lof.finances.gov.ma/sites/default/files/loi_organique_130-30_fr18.pdf. 2 https\.//pefa.org/sites/default/files/assessments/reports/MA-May09-PFMPR-Public.pdf https\.//pefa.org/sites/default/files/assessments/reports/MA-Sep16-PFMPR-Public-with-PEFACheck.pdf 3 Even though the Public Expenditure and Financial Accountability review was completed in 2016, it was only made public in 2018 and does not capture the expected favorable effects of the Hakama reforms on public financial management systems. 4The elements of the reforms were as follows\. deepening national identity and social cohesion; the rule of law, regionalization, and governance; job creation and economic development; national sovereignty and social development; and strengthening social services. (See World Bank 2018c.) 5A recent World Bank blog on Asia explained that Reforming the public sector is a constant process to address emerging challenges stemming from an increase in economic sophistication and expanded citizens' expectation....Typically, significant challenges emerge from the enormous scale and complexity of the reform tasks to be undertaken. This requires levels of commitment, coordination and collaboration that may be without precedent for those involved even when the circumstances are most favorable. https\.//blogs.worldbank.org/governance/addressingchallenges-public-financial-management-and-public-sector-reform-east-asia. 6The hiatus was due in part to uncertainty and limitations on International Bank for Reconstruction and Development allocation for Morocco before the World Bank's capital increase. 7The European Union also supported Hakama through budget support. Its analysis also concluded that a sound basis for lending through budget support was present (European Commission 2012). 8The blog post is available at https\.//www.cabri-sbo.org/en/blog/2018/programme-basedbudgeting-reform-in-morocco-challenges-and-lessons-learned. 9 https\.//www.finances.gov.ma/fr/Pages/plf2019.aspx. 10https\.//www.huffpostmaghreb.com/entry/plf-2019-adoption-en-commission-de-la-premierepartie-du-projet-de-loi-de-finances_mg_5be94545e4b0769d24cf0a2a. https\.//www.medias24.com/MAROC/ECONOMIE/ECONOMIE/187409-PLF-2019-un-budgettout-sauf-social-selon-l-opposition.html. 11The World Bank Group's 2018 Strategic Country Diagnostic for Morocco provides additional information\. The potential of the existing PPP framework has not been fully exploited . . . 55 percent of the total volume of infrastructure projects involving private sector participation were PPP, the rest consisted of other forms of private sector participation using merchant and partial contracts (World Bank 2018c). 12The following list of relevant audits pertaining to reforms under Hakama are publicly available at http\.//www.courdescomptes.ma/fr/Page-27/publications (portal), which includes http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-annuel/rapport-annuel-de-lacour-des-comptes-au-titre-des-annees-2016-et-2017/1-215 (annual report); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-annuel/rapport-preliminairesur-lexecution-du-budget-de-letat-pour-lannee-2016/1-203 (2016); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-thematique/rapport-surlevaluation-du-systeme-de-la-fonction-publique/2-200 (public finance system); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-thematique/synthese--secteurdes-etablissements-et-entreprises-publics-au-maroc/2-146. 13According to a World Bank study, Citizen engagement in the Hakama DPL stands out in two ways\. First, the DPL itself is based on extensive public consultations in the framework of the National Dialogue on citizens' new constitutional rights, government consultations on different aspects of reform as well as online consultations and a nano survey to gather citizens' feedback on the reform agenda. Second, the reforms supported through the DPL directly enable increased citizen engagement in Moroccan public space. Citizens are given the opportunity to access and comment on draft laws, submit petitions, voice their concerns and priorities in public consultations, and benefit from e-government services. http\.//pubdocs.worldbank.org/en/977051497970145435/Case-3-Morocco-Rebuilding-Trustbetween-Citizens-and-Government.pdf. For more information about Morocco joining the Open Government Partnership, see the U.S.- Middle East Partnership Initiative website at https\.//mepi.state.gov/morocco-ogp. 15To view the Open Budget Survey 2017 for Morocco, see the International Budget Partnership website at https\.//www.internationalbudget.org/open-budget-survey/results-by-country/countryinfo/?country=ma. 16For example, the petitions regarding French in schools and women's inheritance rights\. https\.//www.moroccoworldnews.com/2019/04/269557/morocco-intellectuals-petition-french and https\.//www.moroccoworldnews.com/2018/03/242922/moroccan-public-personalities-signpetition-womens-inheritance-rights. 17For more information, see the legal analysis of the Second Draft Law on the Right of Access to Information\. https\.//www.article19.org/data/files/medialibrary/37263/Morocco-analysis-RTI-lawdraft-two-final-version.pdf. 18See the Rule of Law Indexes for 2012â€“13 and 2019\. https\.//worldjusticeproject.org/sites/default/files/documents/WJP-ROLI-2019- Single%20Page%20View-Reduced_0.pdf and https\.//worldjusticeproject.org/sites/default/files/documents/WJP_Index_Report_2012.pdf. 19 The platform is at https\.//www.eparticipation.ma/fr. 20The mission was provided with a full list of e-government services (approximately 80) now available online. 21See http\.//www.unpan.org/Library/MajorPublications/UNEGovernmentSurvey/PublicEGovernanceS urveyintheNews/tabid/651/mctl/ArticleView/ModuleId/1555/articleId/58649/Default.aspx. 22The Country Partnership Framework for fiscal years 2019â€“24 proposed an Advisory Services and Analytics program that includes a new Public Expenditure Review (World Bank 2019, 66). 23
P130925 | Second Governance and Competitiveness Development Policy Operation | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | IEG concurs with the three findings and lessons spelt out in the ICR, whichemphasized: (i) the importance of thecoordinating role of the Government, whichensures that all key partners are aligned behind the reform agenda supported by theDPO, (ii) the central role of theimplementing agencies, whose mission is to track day to day progress toward outcome, andfinally (iii) the limited budget allocations to small countriesare a handicap for more Banks engagement and efficacy onthe ground.Most importantly, IEG finds that the key lesson from the implementation of this program isthatefficacy of a DPOfollows to a major extentthe Governments seriousness and commitment to reform. Itisthe above engagement that generates the support of both internal and external stakeholders, and makes possible anappropriate tracking of thedaily implementation and any needed correction.
P130972 | Productive and Sustainable Cities Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2013 | 2013 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/280921496929771575/text/Colombia-CO-Productive-Sust-Cities-DPL.txt | http://documents.worldbank.org/curated/en/280921496929771575/pdf/Colombia-CO-Productive-Sust-Cities-DPL.pdf | The first two lessons are drawn from the ICR (pages 20-21), with some adaptation, and the third by IEG.One,political commitment to DPL reform programs can often be strengthened by a governments active participation in analyticalwork that support the reform objectives, extensive consultations with public and private stakeholders, and a deliberate effort tointegrate the DPL reform programs into national development plans. Colombias inter-ministerial Misin para elFortalicimiento de las Ciudades prepared 17 papers that provided a solid technical foundation to the institutional and policyreforms. The commission held at least 12 consultations with diverse stakeholders. In addition, the Government held at least oneconsultative event for each of the nine DPLI and eight DPLII prior actions. Importantly, the reform objectives wereembedded in the National Development Plans for 2010-14 and 2014-18.Two, DPL operations involving local governmentsshould deliberately make allowances for differences in institutional capacity, governance structures, and political setting betweennational and local agencies. In thisDPL, local governments were responsible for implementing many reform measures. Localunits needed more time to build consensus and to allocate resources to support reform objectives. They also needed greater effortto gain technical knowledge and to strengthen their capacity to implement reform measures. Moreover, they had to contend with localpolitical cycles --- the local government elections of 2015 ushered in many new local administrations, new local councils, and newlocal staff that had to be introduced to the objectives and content of the reform effort.Three, DPL operations needas much careful fiscal resource planning and programming as they do policy reform planning and sequencing. The central Governmenttook two years to commit budgetary resources to the Road Safety Agency (ASV) which was created in 2013. The Transport Planning Unit(TPU) and the Transport Regulatory Commission (TRC), also created in 2013, had yet to start operations in end-2015 due to lack ofbudgetary support. The ICR also reports that local governments took a longer time to allocate resources to DPL activities. It mighthave been that the imperatives of fiscal restraint in 2013-15 were more compelling than the need to promptly start the newagencies. Still, with expenditure reallocations being always available as an alternative funding option (according to the IMFArticle 2017 Article IV), these episodes illustrate that more careful fiscal planning is needed to support planned DPLoperations.
P130972 | Productive and Sustainable Cities Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2013 | 2013 | 2020 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/426591583968971309/text/Colombia-Programmatic-Productive-and-Sustainable-Cities-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/426591583968971309/pdf/Colombia-Programmatic-Productive-and-Sustainable-Cities-Development-Policy-Loans.pdf | 6. Lessons 6.1 Several lessons emerged from this assessment of the Colombian DPL series. 6.2 Tacit assumptions that additional fiscal outlays will be forthcoming to support prior actions in DPOs can create risks to the sustainability of policy reforms. Risks to sustainability were detected in components that required additional fiscal resources, such as the extension of subsidies (for example, the PVG), matching grants (for example, the CP), or the creation of new entities (for example, the creation of a transport regulation commission and a planning unit). Their implementation was dynamic at times of adequate fiscal resources (2012â€“14) but lost momentum when the fiscal space tightened (2014â€“18). During periods of fiscal stress, the government can reduce budget allocations to flexible budget items, such as those involved in the DPLs. 6.3 When designing prior actions that require local-level implementation, it is important to consider municipal capacity and the time required to enact local-level reforms. In the case of the Colombia urbanization DPLs series, delays occurred because of low technical and institutional capacity at the local level; in some cases, only the largest cities were able to make progress. The Colombian decentralization model that provides full local autonomy presents difficulties in the implementation of policy reforms at the local level. Although the government has enabled local interventions in national laws and decrees, municipalities can autonomously decide when to implement certain enacted policies depending on the balance with other priorities and resource availability. 6.4 In designing multisectoral DPOs with many prior actions across sectors, which include local implementation requirements, municipal capacity building may be required. Central government agencies, the World Bank, or other international financial institutions can deliver the support. As an instrument, a DPL is designed to support the central government budget without earmarking financing to sector ministries that are part of the operation. Parties responsible for overseeing implementation indicated that their willingness to work on this operation depended on securing complementary support. The DNP and line ministries must do most of the design work and are responsible for implementing policies and complying with targets. In fact, for complying with their commitments, in some cases, they needed to source other finance from development partners to make sure the policy measures were achieved. 6.5 In the context of multisector DPOs, it is critical that prior actions be directly linked to results indicators so a clear line of sight and envisioned impact is identified ex ante, thus supporting a strong design at entry. In these DPLs, the results were expected to trigger policy and institutional change in support of more productive, sustainable, and inclusive cities in Colombia. Some results were defined more in terms of outputs broadly attributable to specific reforms, and in some cases, these were processes and actions rather than results. For example, structuring the NDP 2014â€“18 with a territorial or regional approach that takes into account the SoC framework is an action, and the number of conceptual design or feasibility studies supporting travel demand management policies is a process. In these instances, it is difficult to discuss the causal links between actions and results that should be indicative of having triggered changes that signal the achievement of the development objectives. 1Since the late 1960s, subnational governments have been enabled to constitute associations, for example, through the creation of metropolitan areas in the case of municipalities. However, these association mechanisms are voluntary. The institutional arrangement does not mandate functions or provide governmental resources to associations as the Constitution does for departments and municipalities to deliver the delegated services. 2An analysis on the impact of the Contratos Plan highlighted the need to introduce the following adjustments\. (i) build the capacity to monitor the content and commitments agreed to in the CP; (ii) strengthen the organization of the teams involved in the implementation of the CP through a detailed definition of roles and responsibilities; (iii) address the issue of the responsibilities and commitments attributed to the sectors in the CP (it was not possible to demand compliance to the sectors at any territorial level); (iv) define other and additional sources of funds for the CPs; and (v) enable a horizontal articulation among regions. 3The 1968 Constitutional Amendment granted legal status to metropolitan areas. In 1979, Decree No. 3104 introduced specific requirements and operational regulations for metropolitan areas, and in 1994, Law N. 128 added specific provisions related to their administrative responsibilities and financing sources. Under that regulatory setup, the decision to create a metropolitan area was at the departmental assembly level, and municipalities had little influence in this decision. The governance plan did not require all municipalities to participate; only the presence of the core municipality and two additional ones are required in a metropolitan area's governing board. 4Valle de Aburra (Medellin and its surrounding municipalities), created in 1980, is the metropolitan area with the most development prospects. According to interviews held during the evaluation mission, authorities mentioned that its success has been mainly the result of the shared view of the necessity of municipal cooperation for regional development, the long-term planning approach, and the availability of resources to operate and execute their plans. Medellin has contributed significant resources to the metropolitan area. Additionally, the metropolitan area could possibly raise its own resources from the environmental surcharge, pollution fee, and the service provision fee. The main elements of the metropolitan area of Valle de Aburra's metropolitan planning are included in the Metropolitan Development Plan prepared for 2008â€“20. Authorities commented that they are working on a new one with a 10-year horizon. In addition, their actions are guided by the Metropolitan Land Use Guidelines, the Basin Management Plan, the Integrated Solid Waste Management Plan, the Metropolitan Mobility Master Plan, the Plan for the Territory Occupation, the Land Management Standards, and the Metropolitan Strategic Housing and Habitat. 5 See the INRIX 2018 Global Traffic Scorecard at http\.//inrix.com/scorecard/. 6 Colombian housing policy gained new momentum at the beginning of the current decadeâ€”in 2011, the National Development Plan 2010â€“14 (Prosperidad para Todos) chose the home building sector as one of the five engines of growth, and in 2012, the Santos administration created the Ministry of Housing, Cities, and Territories (Ministerio de Vivienda, Ciudad y Territorio; MVCT). The ministry emerges from splitting the Ministry of Housing and Environment into two entities\. the MVCT and the Ministry of Environment. The new policy design introduced a segmentation among the poor households and set up a financial instrument to assist each segment according to its saving capacity. The policy's primary purpose was to reach the poorest families. Because of low or no saving capacity, the poorest and most vulnerable families, in practice, had been excluded from previously implemented financing arrangements, accumulating a high quantitative deficit of affordable housing in this segment of the population. 7 Under the previous system, although the policy differentiated between public housing for lowincome families and public housing for the poorest households, based on housing unit costs, there were no distinctions within the second heterogenous segment, where some households may have some mortgage-paying capacity. Originally, the designed subsidy program was similar for both public housing for low-income families and the poorest households. The subsidy was extended to families to facilitate access to credit from financial institutions, that is, to achieve the financial closure for extremely low-income households. However, the financial closure was not achieved in many cases because of the low saving capacity of poorest households and the prudent attitude of the Colombian banking sector, meaning that a substantial percentage of budgeted resources for housing subsidies was not executed. Also, the participation of the private sector in the construction phase was not conducted under clear rules. Corrupt practices have been identified, the quality of construction was often inadequate, and many projects never came to fruition (Herrera 2019). Law N. 1537 of 2012 included other important principles intended to make the participation of the private sector more efficient. For example, the law establishes that payments to private developers are made at the end of the project against delivery of finished housing and requires minimum technical construction standards. To avoid geographical concentration, the new policy enabled subnational governments with land availability to participate in the program (Herrera 2019). 8 The new government is planning to suspend the program because of its high fiscal cost. 9Families began to live in condominiums with multiple neighbors and social interactions, while in fact, numerous benefited families had previously lived in houses in the countryside or on the outskirts of the city, relatively isolated from each other. As a result, families were not familiar with rules governing the vertical property, such as administration fees and garbage management. In other cases, numerous families used to obtain their subsistence from activities or businesses developed inside their home, which is impossible under condominium rules. Large families started to live in housing with better conditions but of smaller size, which caused overcrowding. 10Territorial entities and the government of Colombia were forced to develop social support programs. The MVCT has worked in four action lines (community organization, rights and duties, security and communal harmony, and productive development) through alliances with nongovernmental organizations and based on workshops and cooperative activities under the National System of Social Accompaniment and Social Infrastructure to the Free Housing Program. Actions taken at the local level have reinforced these efforts. In the case of Medellin, for example, the Housing and Habitat Social Housing Institute of Medellin (Instituto Social de Vivienda y Habitat de Medellin), which is in charge of managing the municipality of Medellin's housing programs, deployed measures of social support successfully. The mission found that these programs' success at the local level varies according to the city's institutional capacity.
P131013 | National Agricultural Innovation | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099355506302234985/text/P1310130a3c29e02f08fbe054447db7b6a4.txt | http://documents.worldbank.org/curated/en/099355506302234985/pdf/P1310130a3c29e02f08fbe054447db7b6a4.pdf | The ICR included four lessons. The following two lessons are emphasized with some adaptation oflanguage:1.Competitive grants can be usedas an effective tool for directing resources to promoteinnovation in response to user demand. This will requiremeasures in place to ensure the technical quality of theactivities that are funded, and provided that the allocation of resources can be protected from elite capture. Theproject experience demonstrated that the competitive grant programwas successful in directing resources toward demand-driveninnovation needs and leveraging matching resources from beneficiaries.2. To ensure the successful outcome ofinstitutional reforms, project preparation activities must carefully assess the political economy considerations to properlycalibrate the risks associated with proposed institutional reform efforts. The Bankunderestimated the challengesassociated with implementing institutional reforms. While the projectmade significant progress in strengthening INIA, yet theinstitutional reforms achieved under the project fell short of expectations. The planned institutional reforms of INIA did not goas far as expected because of resistance by powerful interest groups (especially the labor unions operating in the sector) that theauthorities were unwilling or unable to confront.
P131027 | DRC Inga 3 and Mid-Size Hydropower Development TA | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2017 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/880221525389649223/text/Congo-Democratic-Republic-of-ZR-Inga-3-and-Mid-Size-Hydro-Dev-TA.txt | http://documents.worldbank.org/curated/en/880221525389649223/pdf/Congo-Democratic-Republic-of-ZR-Inga-3-and-Mid-Size-Hydro-Dev-TA.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some modification of thelanguage (ICR, pages 32-33).(1) Clear commitments on strategic directions need to be secured upfront from theultimate decision-making authority in fragile environments like the DRC. This would help in mitigating the Banksexposure to reputational risks associated with potential deviation from strategic decisions agreed upon atappraisal.(2) Political commitment is required for a large-size project with significant fiscal impact.Building coalition at the national and regional levels (for example, including with South Africa in this project) and leveragingpolitical buy-in could help in mitigating the risks associated with political stakeholders inclined to prioritize speed overquality of preparation.(3) A careful assessment should be made at design, whiling combining in a same project, twocomponents characterized bydifferent and independent risk profiles. In this project, having an independent technicalassistance project focused on mid-size hydropower projects run in parallel, could have accelerated the implementation of theseactivities while preserving if from collateral cancellation linked with the governments decisions on non-correlated matters(that is, Inga 3BC).(4) Continuous coordination between development partners contribute to effectively speakingwith one voice to the government.In the case of this project, while the Bank cancelled the project activities in thewake of the governments unilateral decision, the activities by the other development donor were still ongoing when thisproject was cancelled by the Bank.
P131028 | PE Social Inclusion DPL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/744511468332961164/text/ICRR-Disclosable-P131028-06-09-2016-1465496133943.txt | http://documents.worldbank.org/curated/en/744511468332961164/pdf/ICRR-Disclosable-P131028-06-09-2016-1465496133943.pdf | The review draws the following lessonsfrom among the lessons from the ICR:1. The involvement of variousstakeholdersrelevant to the sector significantly facilitated the initiatives being introduced, ensuring that they hadsignificant institutional support.2. Maintaining communications with the counterpart is crucial when executingcomplex reforms. In this case that was done, both through the DPL mechanism and through a number of othermechanisms that allowed a continuous dialogue on structuring reforms to individual programs.3. In thatperspective, a combination of instruments - DPLs, technical assistance, non-lending technical assistance, andSWAPs in key sectors (health and education) proved to be an effective means to provide considered and timely responses to MIDIS onthe whole area of social inclusion. A key element when a variety of instruments are being used, iscoordination.
P131029 | Social Inclusion TAL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/289181555103593530/text/Peru-PE-Social-Inclusion-TAL.txt | http://documents.worldbank.org/curated/en/289181555103593530/pdf/Peru-PE-Social-Inclusion-TAL.pdf | The ICR (p. 27-29) provided useful lessons learned, adapted here byIEG: When designing a technical assistance operation, it is useful when the objective is well defined but the instrument can beused in a flexible manner. In this project, the objectives of the project were quite broad and well aligned with theneeds of the sector and the new ministry, leaving room for the projectto beflexiblein adding, testing, andrevising innovative activities throughout implementation when needed. This approachappreciated by the government, whichwas faced with less flexibility inuse of its own resources. Combining different innovative financingmethods allows for a long-term engagement to achieve the desired development outcomes. This project was part of along-term partnership between the government and the Bank and was to provide the financial resources to initiate and sustain policyreforms that were triggered by the Social Inclusion Development Policy Loan. These two different instrumentsin combinationfacilitatedaddressing the technical and policy needs of the sector over two decades.
P131049 | Climate Resilience: Transforming Hydro-Meteorological Services | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2013 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/696181612281273732/text/Mozambique-MZ-Hydro-Met-PPCR.txt | http://documents.worldbank.org/curated/en/696181612281273732/pdf/Mozambique-MZ-Hydro-Met-PPCR.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A comprehensive and programmatic sector engagement can have a transformational impact on the hydro-metagenda. This project hadstrong links to the broader sector agenda(including through a prior Bank-financedDevelopment Policy Operation, a pilot program for climate resilience) and other investments in water resources. Thisengagementproved effective in providing the setting for sustainability and sectorimpact.2. Hydro-met investments targeting local level beneficiaries must ensure their early andcontinuous engagement, through tailoring hydro-met information to end user needs. In this projects pilots, early andproactive engagement resulted in an effective coordination between government entities at various levels and the beneficiarycommunities. At the same time, the early engagement with local level beneficiaries enabled setting effective systemswereadapted to the local reality.3. Developing pilots can demonstrate how to effectively advance innovativeconceptsto real life solutions and provide thebasis to locking in strong financial sustainability. Theimpact-based approach followed in this project provided an effective example of impact-based forecasts daily to end users. Theimplemented pilots further demonstrated implementing agencies can adopt new technologies with better information.
P131084 | Mali Rural Electrification Hybrid System Project | Western and Central Africa | Mali | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2023 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099092024161020826/text/P131084-2052699d-f0bd-4d59-a738-dff86c65cc97.txt | https://documents.worldbank.org/curated/en/099092024161020826/pdf/P131084-2052699d-f0bd-4d59-a738-dff86c65cc97.pdf | IEG derives the following lessons drawn from the ICR:1. The Bank Groups re-engagement in theenergy sector in FCV countries calls for sustained and resilient commitment to the client. This project lasted morethan ten years in a politically unstable environment, ravaged by insecurity, compounded by the impact of a global pandemic.What helped was that the Bank and Government maintained a dialogue throughout the period of implementation, so as to be able todevise arrangements to keep the project alive, despite a growing insecurity, in localities where project activities were beingimplemented. The Banks willingness to remain engaged during a challenging period enabled the operation to commission arenewable energy infrastructure throughout the country, connect new households and communities to electricity, or improve energyservice for close to a million beneficiaries.2. Public-private participation is a key ingredient toachieving efficiency and sustainability in the provision of energy services in rural areas. The project aimed tointroduce market incentives for distributors of lamps and economic undertakings by women associations, through the provision ofsubsidies and promotion policies from Government entities to prime the pump. While hybrid plants were owned by the State,they were managed by private operators via a contractual arrangement with AMADER and the operator. The latter oversawelectricity distribution, payments and collection of revenues, while AMADER ensured tariff regulation and monitoring of theoperations of the mini networks. The project also trained women in cooperative management, entrepreneurship, accounting andhandling of gas-powered equipment, marketing and labeling techniques for local products. These two initiatives were key tobringing in greater efficiency in the sector using private operators and launching economic units managed bywomen.3. For countries with a dispersed rural population off-grid mini plants and SHS are a recipe forprovision of affordable energy services. Off-grid mini plants and SHS are cost-effective approaches to expansion ofenergy services to dispersed populations, being tailored to rural conditions in terms of cost and maintenance. In countriesinthe Sahel, with abundant sunshine, the use of solar technology is an efficient way of bringing about rapid expansion ofelectricity access to relatively remote areas, until such time as the grid infrastructure can eventually be extended there.
P131094 | Disaster Risk Management Project | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099205006092216710/text/P1310940e49b8a0cd0a4c305dbae602a603.txt | http://documents.worldbank.org/curated/en/099205006092216710/pdf/P1310940e49b8a0cd0a4c305dbae602a603.pdf | The following lessons were mostly derived from the ICR with minor modifications by IEG (ICR, paragraphs97-103): A successful operation benefits from a starting point of a strong institutional capacity,lowproject management staff turnover,responsiveness to self-identified needs, and transparency.In this project,the government committed to the participatory approach introduced by thepreceding Bank-financedDRMprojectapplyinga participatory approach in the design ofmunicipal level DRM plans (PMGRs) andemergencyplans (PEMs). Residents from the municipalities and communities were enjoined to identifyand implementstructural andnonstructural DR mitigation measures. This approach, plus thesteadypresence of a qualified project implementationunit,contributed to the projectssuccess. For future consideration, havingpermanent qualified staffatthe municipal level may help ensure continuity and achieve more efficiency. Integrating DRMin territorial planning leads torisk-informeddevelopment plansand fostersaculture ofprevention.In this project, a risk management approach formed part of thestandardized methodology forterritorial planning. Themethodology helps other institutionsframe their planning instruments. The PMGRs and PEMsplanning instruments showed how these contributed to strengthening the local framework for resilience. However, territorialplanning with DRM features requireeffective implementation. PMGRs and PEMs are living instruments,requireperiodicupdating and would call forinvestments in human capital. Resources would be neededto keep the systemoperational, conduct continuoustraining, and compensation packages to attract andretain experts,e.g.,meteorologists, hydrologists, and geologists. Engaging Indigenous Peoples andAfro-Honduran population facilitatesinclusiveDRM. In this project, the pilot participatory methodologyenjoined indigenous and Afro-Honduran peoples to help analyzerisks, vulnerabilities,and designPMGRs, andPEMs. The mitigation works, supervision, and maintenance activities in these plans empoweredtheself-determination ofthese communities. Citizen engagement was the foundation for inclusive DRM Gender Equality(https://www.gfdrr.org/en/inclusive-drm).This consultativeparticipatoryapproach gave COPECOa betterunderstanding of the needs and risks faced by thesevulnerable communitieswhile building their preparedness and DRMcapacity. CERC effectivenessmay benefit from a flexible approach to the approval process.In this project,CERC was activated twice - the first in June 2020 in responsetoCOVID-19,and in May2021 in response to the impact of the storms. The emergency procurement of limited goods in response to these emergencies amountedto about US$0.5 million. In both cases, funds were made readily available.However, the documents to triggerCERCtookaround 3 months for the first emergency and 5 months for the second one. The overall period from the time the emergencywas declaredtoimplementationtook5-7 months and rancontrary toa rapid response.Morefeatures allowed under Bank policies need to be explored.
P131120 | ZR Support to Basic Education Program | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Human Development | Education | RETF | IPF | 2013 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/558951518099281932/text/Congo-Democratic-Republic-of-ZR-Support-to-Basic-Education-Program.txt | http://documents.worldbank.org/curated/en/558951518099281932/pdf/Congo-Democratic-Republic-of-ZR-Support-to-Basic-Education-Program.pdf | IEG concurs with lessons learned as set out in the ICR (p. 25), including the following regarding operations in a fragilecontext: Enhancing Ministry of Education capacities (e.g., technical management of schoolconstruction andtextbook production, strengthening teamwork) in a fragile context, while effectively delivering a program,can serve as a bridge towards sustainable development. In this case, the project involved Ministry of Education staff in day-to-dayactivities, thereby deepening experience and the ability to deliver services on an ongoing basis, and enhancing technical expertise(e.g., school construction, textbook production) and teamwork. Social accountability can be successfully used in fragilecontexts to promote accountability at local and national levels. The project used a web-based platform to engage with parents andcommunities, and this served as a catalyst for social development through effective information sharing and citizenoversight. Effectivepreparation and strategic monitoring of civil works in a fragile context is one of themost critical stepsfor achieving targeted results in terms of both quality and quantity.The project managed toconstruct and rehabilitate a significant number of classrooms, and to build latrines, water points, and staff offices; however,cost overrunsresulted in the numbers and/or specifications of classrooms and water pointsbeingreduced. The ICRnotes (pg. 33) that a thorough assessment at appraisal stage, overseen by skilled employees, and the capacity of the privatesector to procure and deliver construction materials in a timely manner as well as the selection of the construction sites, are keyto effective risk assessment and for setting realistic timeframes and cost estimates.IEG alsoconcurs with the broader observation regarding the importance of taking a longer-term perspective in addressingfar-reachingreforms, and the associated theory of change. This project (PROSEB) was preceded by PARSE and is followed by the EQUIP projectinvolving significant buy-in from stakeholders based on shared understanding of challenges,and ongoingdevelopmentofinstitutional capacity.
P131138 | ENPI East Countries FLEG II Program | Europe and Central Asia | Europe and Central Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/492041509655223252/text/ICRR-Disclosable-P131138-11-02-2017-1509655213024.txt | http://documents.worldbank.org/curated/en/492041509655223252/pdf/ICRR-Disclosable-P131138-11-02-2017-1509655213024.pdf | IEG has selected three lessons fromthe ICR, with some adaptation of the language: Projects thatfocus on introducing institutional changes through technical assistance aremore effective when they are aligned with thecountrys agenda and when there is good cooperation with policy makers and advisors. UnderProgram II, countryengagement was stimulated by the ability of country counterparts to develop their own activities in line with theirpriorities. Government-led multi-stakeholder platforms can be highly effectivemechanisms for promoting country ownership, but can also dilute the overall programcoherence. Under this Program, the National Program Advisory Committee (NPACs) proved highly effectivefor engaging countries. They institutionalized decision-making, drew in expertise beyond government, while fostering dialoguebetween and within government and with civil society. At the same time, granting this level of control to individual countries madealignment with overarching project goals more difficult. Regionalactivitiestend tobe moredifficultto organize and promote than national or subnationallevel activities. Under this regional Program,activities at the regional levelreceived less emphasis thanenvisioned. It was easier for countries to develop national or sub-national activities that fit into their priorities. Regionalactivities depended more on outside actors (e.g. Program managers) to take the initiative and promote cross-bordercollaboration.
P131194 | DJ Improving Health Sector Performance | Middle East and North Africa | Djibouti | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099042823143022751/text/P13119408635b70d9089510ba1c3d185c81.txt | http://documents.worldbank.org/curated/en/099042823143022751/pdf/P13119408635b70d9089510ba1c3d185c81.pdf | These lessons are drawn from the ICR, pp. 25-26, and restated by IEG.RBF should not be attempted unless robustand reliable ME and HMIS are assured. Strong ME and HMIS are essential for the functioning of RBF, whichrequireseffective measurement and performance reporting as the basis for payments. Mechanisms are also needed to enable facilitystaff to understand and address factors that hinder their success.The lack of data and data systems, and reluctance of thegovernment in Djibouti to release data, made the decision to introduce RBF highly risky, perhaps questionable.In acountry with a large population of refugees, migrants, and/or displaced people, unifying health service provision for these groupsand the host communities supports improvements in equity. Having parallel service delivery in refugee camps/settings canbeinefficient and inequitable. When there are large population influxes, unless the capacity of the health system to supplyquality services is bolstered, access by the host population and new arrivals and the quality of care are likely to becompromised.Strengthening institutional capacity especially to implement new health programs orreforms - requires sustained effort. Health reforms that require new mechanisms, information flows, and behavioralresponses take time and sustained support and institutional capacity building. Even with strong MOH commitment, new skills andbehaviors take time to acquire and hone with practice.Staff mobility and turnovermust also be taken into account andmay require repeated training and sustained support for skill-building.
P131201 | Lao PDR - Small and Medium Enterprise Access to Finance Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/632601632835055220/text/Lao-Peoples-Democratic-Republic-Lao-PDR-SME-Access-to-Finance.txt | http://documents.worldbank.org/curated/en/632601632835055220/pdf/Lao-Peoples-Democratic-Republic-Lao-PDR-SME-Access-to-Finance.pdf | Three lessons are drawn from the ICR (page 27-28), with some adaptation.Lines of credit are not a panaceafor all problems with SME finance and must be matched by interventionsthat address structural impediments to SMElending. In this operation, a fourth of the project funds was devoted to technical assistance to help address issuesassociated with information asymmetries andcollateral requirements in SME lending. Technical assistance was deliveredto participating financial institutions to improve their SME strategies, banking products, and credit underwriting practices.Technical assistance was also delivered to SMEs to develop their business development and financial management capacities andskills. Moreover, technical assistance was obtained from the IFC to helpdevelop the countrys credit informationsystem and secured transactions business (where the lender acquires a security interest in collateral owned by the borrower).Altogether, these efforts should help increase the preparedness of financial institutions to lend to SMEs and improve their accessto credit.Drawdowns from a line of credit byfinancial institutions should be staged and linked toperformance. Although subsidiary financing agreements betweenthe DOSMEP andparticipating financialinstitutions allowedadvances of up to US$2 million upon signing of the agreement, good practice showed that funds transferredintranches and linked to resultsboosted performance by the participating financial institutions. In this project,participating financial institutions requested the DOSMEPfor fund transfers, submitting a list of loans made with supportingdocuments including the original loan applications filed by the SME borrowers. Participating financial institutions thatactually extended loans to SMEs foreligible sub-projects gained priority over the project funds.Continuing policy dialogue with the monetary authorities and banking supervisors helps strengthenthe enablingenvironment for SME lending.In this project, policy decisions by the Bank of the Lao PDR posed challenges toproject implementation. In December 2015, the central bank capped local currency deposit rates and the spread between thelocal currency deposit and lending rates at an average 4 percent. In December 2017, the central bank capped the spreadbetween foreign currency deposit and lending rates at 3 percent and limited loanfees to 3 percent of the approved loanamount. In February 2018, the central bank capped the interest rates in the interbank marketon the Laotian kip, theThai baht, and the US dollar for maturities ofone-week to one-year. According to studies in 2019, the seriesofinterest rate caps exerted pressure on the banks return on assets and return on equity, distorted prices in thefunding market, boosted re-dollarization, and motivated a shift to unregulated providers. Continuing policy dialogue by theBank with the authorities and the private sector helped convince the central bank to remove the interest rate caps in 2019.
P131212 | Ninth Poverty Reduction Support Credit (PRSC 9) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/643161529528179818/text/Mozambique-MZ-PRSC-IX.txt | http://documents.worldbank.org/curated/en/643161529528179818/pdf/Mozambique-MZ-PRSC-IX.pdf | It is easy to be beguiled by strong country economic performance and assume that policy integrity exists where it mightnot. Extensive in-depth analysis of political economy issues should be an integral part of DPL program design. Caution iscalled for before basing program design and policy actions on the doing business indicators. In this case, reforms to promoteprivate sector development should have focused on the misuse of Mozambiques capital stock by its SOEs, not on the number ofdays to start a business. A comprehensive private sector assessment should be the basis on which private sector development reformprograms should be based. Implementation capacity constraints should be meticulously evaluated and incorporated into DPOprogram design (ICR, 38-9).
P131228 | DABS Planning And Capacity Support | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/960501633012354945/text/Afghanistan-DABS-Planning-And-Capacity-Support.txt | http://documents.worldbank.org/curated/en/960501633012354945/pdf/Afghanistan-DABS-Planning-And-Capacity-Support.pdf | The ICR draws the following main lesson from the experience of implementing this project, with some adaptation oflanguage.1.Regular coordination between the Project Implementation Unit (PIU), upper management and theWorld Bank, allows for quicker solutions to problems. In this project,there were procurement issues with respect tothe activity of constructing the training center.In order to deliver training in line with project objectives and DABSstrategic vision, the needed training equipment (similar to equipment used in the field), was very specific.The procurementnotices were advertised three times,due to the lack ofmarket response.Faced with this bottleneck, an exceptionwas made following discussions between the PIU, upper management and the World Bank to adopt a single-source procurementmethod.The lesson from this project is that regular supervision meetings, ideally with a strong in-field presence, can helpin quickly identifying problem areas and comingup with solutions. This is especially important forprojectsinfragile environments.The ICR review draws the following main lessons from this project.1.Startingprocurement planning and implementation activities earlycan help in reducing procurement delays. Thisis especially likely to be the caseinfragile environments withsupply shortages of qualifiedcontractors.2. In capacity building projects it is necessary to use appropriate outcome indicators. Inthis project, capacity building activities aimed at developing specific training courses and curricula. In projects of this nature,it would be useful to measure the efficacyof training, ideally through aformal certificationof the people trainedunder the project.
P131235 | Uttarakhand Decentralized Watershed Development II Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062723175066757/text/P1312350df18b403a08e37056e423e3f948.txt | http://documents.worldbank.org/curated/en/099062723175066757/pdf/P1312350df18b403a08e37056e423e3f948.pdf | The ICR included three lessons listed below. They have the potential for broader application in similar environments andare repeated with some adaptation of language:1. Building climate change resiliencethrough science-basedplanning can establish linkages and secure synergies between improved environment services and enhanced productionsystems.The project demonstrated the role of science-based planning in establishinglinkages and securingsynergies between improved environment services and enhanced production systems. Visible benefits accrued regarding expandingirrigation coverage while adopting new technologies to make the most of such services. Green technologies (such as solar pumps andmicro-irrigation) reduced dependence on conventional fuels while sustaining water supplies under rainfedconditions.2. Developing rainfed areas by applying an integrated watershed approachcan createclimatechange mitigation and adaptation opportunities. By promoting the efficient use of natural resources, the project improvedthe waters horizontal and lateral movements. It increased the area and production of biomass in both arable and non-arableareas. This led to carbon sequestration and reduced GHG emissions, which can be capitalized for improving rural livelihoods throughpayment for environmental services and linking with carbon credit markets.3. Connectingagriculturalsurpluses with markets in a sustainable manner requires the promotion of agribusiness thatinvolvesincentivizing productivity and increasing incomeopportunities. While enhancing the systemefficiencies, farmer-owned agribusiness ensures a platform for generating demand for local high-value products, maintainingsustained growth, diversity, and quality in production. The project experience demonstrated that Agri-Business Growth Centers(ABGC)is a promisingmodel that provides services to farmers groups(linkages to markets, promotingdiversification and providing capacity building assistance, branding of recognized quality products from farmers, assisting withquality control management, andresponding to market demands needs). ABGCsneed tostrengthen market intelligence todevelop and expand producer-driven markets for diversified local production from rainfed areas.
P131263 | Rural Electrification and Renewable Energy Development II (RERED II) Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099121124134520222/text/P131263-67c17df9-f47f-4f9b-b458-e4a996c22620.txt | https://documents.worldbank.org/curated/en/099121124134520222/pdf/P131263-67c17df9-f47f-4f9b-b458-e4a996c22620.pdf | This review has drawn three lessons based on the information in the ICR.Adequately conducted market analysis atthe appraisal stage can help increase the projects effectiveness and avoid the revision of project objectives. Theproject was designed to implement 7.25 million CFLs to promote efficient energy consumption, which was the second objective of theproject. However, early in project implementation, the ME findings showed that there was an uptake of CFLs in the marketwithout any subsidy using the concessional funds. This led to project restructuring and a deletion of the second project objectivewithout any CFL activity having been implemented. A detailed market analysis conducted at appraisal could have identified theuptake in the market and the CFL component could have been excluded from the project scope.Shortcomings in theformulation of project objectives and the theory of change can critically affect the adequate assessment of the projectsachievements. The project objectives were to increase access to clean energy and promote efficient energy consumption, butthe project activities were also expected to lead to development of a solar services market. These activities did not directlysupport the achievement of the output-oriented project objectives within the projects theory of change, nor were the marketdevelopment related outcomes captured by the projects formulation. This also resulted in adoption of inadequate measures toensure the sustainability of the achievements in market development by preventing market distortion and financial viability of thesector.Continuous policy dialogue with the authorities can be critical in changing a projectsimplementation direction and preventing the use of concessional funds for redundant activities. The project was to installsolar home systems and construct solar mini-grids and gas plants for captive power use in areas where grid was not expected toexpand in the medium term. However, the Government of Bangladesh accelerated the expansion of the electricity grid into projectareas. The expansion of the grid was supported by the World Bank under a continuous policy dialogue. This resulted in the earlycessation of installation of solar home systems and construction of min-grids, the implementation of which had already been slowbecause of higher than estimated initial capital costs.
P131290 | E-Health Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2023 | 2024 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099010224174028999/text/P13129018d84230591af621b618ebbedc83.txt | http://documents.worldbank.org/curated/en/099010224174028999/pdf/P13129018d84230591af621b618ebbedc83.pdf | The ICR (page 33 - 35) provided several lessons and recommendations that are were restated by the IEGreview: When the World Bank is financing a first project in a clients sector, especially if the operationis complex, a realistic understanding of the clients capacity, experience with World Bank policies and procedures, and abilityto handle the technical requirements of the project can limit the challenges and shortcomings during implementation and can lead tobetter performing and achieving projects. Digital health projects can benefit from an enhanced review process toadequately assess technical risk. Digital health is a growing area of need in modern health systems. Yet it is also a highlytechnical area with multiple risks, and numerous projects have failed to achieve intended objectives from low- to high-incomecountries.An enhanced and early technical review and risk assessment of digital health projects, similar to reviews conductedfor environmental or social risks, can adequately evaluate the technical risk of an overly designed project in a low-capacitycontext. This review can lead to a reconsideration of the projects scope and complexity, especially when risks cannot bemitigated. Considering the unique capacities and levels of development in each country when designing and implementingprojects can lead to more effective implementation and better outcomes. Projects and investments that have been successful in onecountry cannot easily replicated in another country, especially when it comes to complex sectors like healthcare. In the case ofthe project in Mongolias health sector, the aim was to follow the model of an e-Health project in Estonia. However, thecapacity and level of development of information technology in Estonia and Mongolia were significantly different. The ICR suggestedthat instead of trying to directly replicate Estonias system, it can be more effective to help the MOH prioritize and dividethe design and implementation into smaller parts for phased implementation. Instead of immediately implementing a complex HIEP, itcan be more feasible to start with a less technically complex PACS. The project design cannot rely on the implementationof its critical activities in a different project, even if both projects are financed by the World Bank. If activities aredependent on other sectoral initiatives as with the SMART project, a higher-level implementing agency or a smaller e-Health projectintegrated as a component of the SMART Project can be more effective. It emphasizes the need for greater complementarity in projectdesign. For example, the design of the HIEP under the e-Health project, required the definition of the systems EnterpriseArchitecture (EA) that was being financed under the SMART Project. Delays in developing the EA under the SMART Project led todelays in the design and implementation of the HIEP which led to unaccomplishment of project outcome and objective. Whenclient commitment fluctuates, achieving results is not feasible and other factors compromise the projects objectives andrelevance, the World Bank can carefully reconsider whether continued engagement is justified and can make a decision whether tocontinue supporting a project or not even with prior investments in time, effort and sunk costs.
P131305 | National Safety Net Program for Results | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | PforR | 2014 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/982311635774013246/text/Kenya-National-Safety-Net-Program.txt | http://documents.worldbank.org/curated/en/982311635774013246/pdf/Kenya-National-Safety-Net-Program.pdf | The following lessons are drawn from the ICR:Institutional strengthening is facilitated when a confirmed sourceof financing is readily available. This project included a significant number of time-bound institutional reforms(release of project funds triggered by policy reforms) where timelyavailability of technical assistance financing was a keyfeature for moving forward.External shocks create opportunities for program reform. The experienceof a drought drew attention to the need for, and served as a catalyst for introducing, a safety net buffer against similar futureevents
P131323 | Senegal River Basin Climate Change Resilience Development Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062824181027567/text/P131323-f7b0312d-b5d6-4308-8d10-982f6f86aafd.txt | https://documents.worldbank.org/curated/en/099062824181027567/pdf/P131323-f7b0312d-b5d6-4308-8d10-982f6f86aafd.pdf | The ICR (paras 95-101) provided seven lessons. Four of those lessons as well as two relevant recommendations from the ICR arepresented here with rephrasing as these may be useful for the other projects on coordinated management of water resources at aregional level.Solid institutional arrangement to strengthen communication between regional organizations fortransboundary water resources management and their member states may help successful project implementations. Based onlessons from the first phase of the series of the Senegal River Basin Multipurpose Water Resources Development Program, the projectestablished National Cellules, in each Member State to monitor and coordinate project activities (ICR, para 96). The ProjectImplementation Unit (PIU) in the Organization for the Development of the Senegal River (OMVS) had specific focal points for eachMember State and component and conducted regular meetings with national cells and Implementing Agencies to trackproject progress (ICR, para 96). Nevertheless, the lesson needs to be interpreted with an awareness regarding a potential tradeoffbetween advantages of having a PIU where high-performing consultants could accelerate implementation and disadvantages of missingopportunities to further strengthen OMVS as an institution (Teams Response).Effective communication betweentask teams and Country Management Units (CMUs) may contribute to the success of regional projects. CMUs do not haveregional projects in their portfolio, although the CMUs oversee the World Banks dialogues with the countries. It is vitalfor task teams to engage CMUs to leverage the Bank-country dialogue and address country-specific challenges. An example of thissuccessful collaboration was seen in Mali, where the task team and CMU worked together to overcome implementation hurdles inirrigation investments, boosting the projects delivery and increasing the area equipped from 200 hectares to 1,549 hectares bythe projects end (ICR, para 97).Inadequate monitoring of quality of procurement and contract management maycause critical challenges for procurement and contract management. Under the project, someimplementing agenciesstruggled with awarding contracts and displayed poor management, particularly in Mali and Guinea; however, the PIU of OMVS faceddifficulties monitoring procurement and contract management due to its limited capacity to collect relevant information (ICR, paras71 and 98). To address the lesson, the ICR (para 98) recommended future projects to: (i) implementoversight mechanisms toensure appropriate contract durations; (ii) verify the eligibility of companies for multiple contracts; (iii) approve advancepayment amounts at the PIU level, which would be enabled by the legal transfer of project implementation responsibility from theMember States to OMVS; and (iv) the PIU and the World Bank to review procurement documents to ensure timelines align with theactual scope of works, considering seasonal constraints on ground activities.Limited flexibilities in the fundreallocations and the use of remote supervision techniques may disrupt the implementation timeline and prevent on-site visits bythe World Bank in FCS areas. The project experienced the impacts of coups and of limitations derived from FCS in twoMember States, which impacted implementation timeline in these countries and limited the World Banks capacity to visit thesites (ICR, para 100). To address the lesson, the ICR (para 100) recommended to introduce greater flexibility to reallocate fundsfrom the affected Member States to those that were performing well and to use remote supervision techniques, such as progressmonitoring apps or remote sensing, to facilitate earlier course corrections.
P131331 | Enhancing Education Development Project | South Asia | Maldives | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/358341555103520796/text/Maldives-Enhancing-Education-Development-Project.txt | http://documents.worldbank.org/curated/en/358341555103520796/pdf/Maldives-Enhancing-Education-Development-Project.pdf | The ICR (p. 23-24) provided valuable lessons, adapted here by IEG: Inorder to ensure positive project outcomes and sustainability of knowledge built among education officials for future activities, itis critical to provide continuous capacity building activities during project implementation. In this project,atoll- and island-level education officials were trained on an ongoing basis to achieve technical and management support forschools to implement education development activities. When a project introduces a new system midwaythrough implementation, it is important to find a way to avoid disruption of project implementation. In thisproject, a new procurement system was introduced in the middle of project implementation, resulting in several challenges due tolack of capacity to implement the new system, inflexibility of the system, and slow internet speed. These challenges weremitigated through training and capacity development. Activities to strengthen school-basedmanagementcontribute toownership and sustainability ofimprovements. This project provided training forsenior management teams in school leadership and management skills, trainingfor school boards, and training of trainers forteacher resource center coordinators, all aimed at strengthening school-based management. The ICR (p. 14) quoted aparticipant assaying, understanding on how to make our school improvement plans was a huge step for us to make plans,and toimplement and monitor them for the betterment of our schools.
P131394 | BD: Reaching Out of School Children II | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2021 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099145110192281290/text/P1313940da63460300a3e00e6a7c6d3102e.txt | http://documents.worldbank.org/curated/en/099145110192281290/pdf/P1313940da63460300a3e00e6a7c6d3102e.pdf | The following lessons are a subset of the seven relevant and insightful lessons presented in the ICR, slightly recast byIEG: Non-formal education, delivered at the community level with support from communities and NGOs,offers a useful model for improving access and retention of out-of-school children, while also improving quality, even in the faceof exogenous challenges.This delivery model can be adapted to various settings (deprived rural and urban areas andcamps for displaced populations) and to different types of education (basic and pre-vocational).The project demonstrated thevalue of informal education as an effective, low-cost mechanism for service delivery to groups that would otherwise not have accessto education, and in a way that is responsive to local context. Successful adaptation of the (original) ruralmodel of service delivery to accommodate urban slums can be achieved by clustering several (four to eight) LCs in one compound,providing a near-complete school environment, as opposed to individual, more dispersed LCs in rural settings.Theurban slum experience has also shown that an accelerated model, facilitating the completion of the five-year primary cycle in threeyears, can be accommodating of the needs and constraints of older (eight- to 14-year old) students from poor and vulnerablefamilies.Urban settings also present the challenges of frequent family migrations, an important cause ofdropouts. Mobile vocational training centers provide an effective model for delivering skills training inhard-to-reach areas.They help overcome barriers to participation including safety, cost, and travel time, especiallyfor marginalized beneficiaries, thus prompting increased participation of vulnerable adolescents, especiallygirls. The contracting of a specialized agency for teacher training can be effective and efficient, andexperience points to the importance of enhanced monitoring of training.Experience and feedback also suggest room forfurther strengthening of teacher training, especiallysupplementing foundation training with two days of teacher observationand feedback, andproviding more support to trainees (increased budgets for expenses, caregivers during their absence, andtraining materials).
P131408 | BZ Marine Conservation and Climate Adaptation | Latin America and Caribbean | Belize | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2021 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/158711625019941733/text/Belize-BZ-Marine-Conserv-Climate-Adaptation.txt | http://documents.worldbank.org/curated/en/158711625019941733/pdf/Belize-BZ-Marine-Conserv-Climate-Adaptation.pdf | The following lessons in the ICR stood out as important and relevant to other projects on marine conservation and climateresilience, and are presented here with some editing.1. Embedding project activities on adaptation measures intoministries work plans has the potential to mainstream climate resilience in government policy and activities. Theproject aimed to incorporate adaptation actions into activities that were already underway or planned by different governmentministries and departments. This approach strengthened government ownership; enhanced inter-agency coordination by supportingdiscrete activities undertaken by different agencies; and helped to ensure that changes in policy and regulations were achievedduring the project lifetime. The project also adopted this approach with respect to the management of protected areas, for thefirst time developing and incorporating climate change indicators into the METT assessment process.2. Nature-basedsolutions designed in a participatory manner and implemented in a multi-pronged approach can enhance climate resilience of anecosystem and achieve social and environmental benefits. The nature-based adaptation measures supported by the project,including the expansion of replenishment zones, protection of mangroves, and coral restoration, were expected to enhance coastalprotection, carbon sequestration, a sanctuary for marine flora and fauna, sustainable fisheries management, and tourism, whichwould generate environmental and economic benefits. The project employed an equitable and participatory approach by consultingwithcommunities and implementing partners throughout the project duration. While such approach required substantial time andresources, it strengthened community involvement in natural resources management. Moreover, the project employed a multi-prongedstrategy that combined actions on legislation, coral restoration, and community livelihoods, while implementing these actions in asequence to achieve intended results, for example, providing livelihoods support prior to regulatory measures taking effect). Thosesuccessful practices suggested a potential for scaling up the activities to cover the whole coastline of the Belize Barrier Reef inthe future.3. Community-driven livelihoods activities may require considerable effort and capacity during projectdesign and early implementation to initiate them in an effective and timelymanner. The projects highlyparticipatory approach to engage affected communities in identifying and developing sub-projects to ensure transparency,inclusiveness, and prioritization of local needs was aligned with the project objective. However, the approach required significantfacilitation support and capacity building that was not sufficiently provisioned during project design and early implementation.There were initial delays in preparation and implementation of alternative livelihoods sub-projects. After the MTR, the projectaccelerated the community-driven livelihoods activities by focusing on a smaller number of sub-projects with higher contribution tothe project and expanding implementation support through a consulting firm with solid local experience in livelihoods activities.Assigning time and resources in the early stages of project design and implementation have a potential to ensure an adequate timefor generating tangible results.
P131408 | BZ Marine Conservation and Climate Adaptation | Latin America and Caribbean | Belize | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2021 | 2024 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099606007112433647/text/SECBOS-1db89a23-09a4-42f3-bcbf-4e35c51b3bb2.txt | https://documents.worldbank.org/curated/en/099606007112433647/pdf/SECBOS-1db89a23-09a4-42f3-bcbf-4e35c51b3bb2.pdf | 4.1 Enhanced World Bank technical presence may be needed in large ocean states when implementing projects in complex regulatory environments that also require an understanding of local norms. Projects that change the rules of engagement for coastal and marine resource users require extensive beneficiary engagement and knowledge of local norms. In large ocean states without a physical World Bank presence, the World Bank may need to delve deeper into these policy nuances during design and strengthen its physical presence to support adaptive management decisions throughout the project life.4.2 Livelihood subprojects designed to reduce the vulnerability of coastal communities can innovate by offering a menu of nonextractive and regenerative marinebased livelihood projects rather than mirroring what is often done in terrestrial spaces. Bottom-up approaches used for subproject selection are participatory but may not be a useful approach for introducing new marine-friendly diversified income streams. In the case of Belize, examples could have included community-based fish farming; stone crabclaw harvest; polyculture of marine products; seafood certification; and eco-labeling. The World Bank has supported such innovative activities, for example, in Indonesia, where its Coral Reef Rehabilitation and Management Program used alternative livelihood grants as a means of piloting and scaling up innovative marine resourceâ€“ based activities. 4.3 Although small grants can help catalyze and demonstrate diversified livelihood opportunities, beneficiaries require iterative support and links to a broad range of technical and financial services to generate sustained income over time. Evidence from the World Bankâ€™s global community-driven development project experience indicates that successful livelihood enhancement or diversification efforts require a deeper analysis of labor markets, links to business support services and institutions, and a longer time horizon than that of a typical donor-financed project to show success (Wong and Guggenheim 2018).4.4 A blue economy approach can help solve coastal and marine resource conflicts, especially in situations where conservation activities restrict resource access. Updated guidance and training are needed for staff engaging on conservation and climate adaptation projects in marine and coastal areas to better align these activities with blue economy aims.
P131440 | Public Sector Management and Social Inclusion Development Policy Loan | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2019 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/356611622122987377/text/Uruguay-UY-Public-Sct-Mgt-SocInclusion-DPL-DDO.txt | http://documents.worldbank.org/curated/en/356611622122987377/pdf/Uruguay-UY-Public-Sct-Mgt-SocInclusion-DPL-DDO.pdf | This review concurs with three lessons drawn by the ICR: Evaluations should be undertaken closer to programclosure, even in the case of extensions. The time lapse between design and evaluation makes it difficult to trackknowledge. Technical assistance is a critical contribution by the World Bank and a strong comparative advantage amongUruguays development partners. Capacity constraints are a serious risk, especially in a country of Uruguays size, anddid materialize. The IBTAL, which spanned several DPLs, hence provided critical complementarity to theDPL. Finally, the DPL served an important purpose for strengthening Uruguays resilience, as shown by thefact that the Government did execute the DDO in 2019. At that time, economic growth had stagnated, due to contagion from Argentinaand Brazil and lower global commodity prices all of which had been identified as substantial risks to Uruguaysstability. IEG adds the following lessons: To facilitate ME, PAs should be unpacked whenthey contain several actions that have different objectives. This was the case for PA7 which involved VAT reductions andexemptions, but with two different purposes and with very different outcomes. There may be a trade off between thepace of reform and the level of ambition of targets. Although targets were considered low for some RIs, the reforms have beenmaintained and have continued to advance throughout the extension of the DPL. Program design needs to clarifyrelationships to previous operations. The DPL is a stand-alone operation, and yet, some PAs appear more closely associated withprevious DPL reform areas than to the present one. Examples include reforms related to e-invoices, involving private banks ingovernment payments, and raising e-transactions through credit cards which appear to foster financial deepening. Where reform areasstill overlap between operations, the relationship to previous DPL targets could be explicitly clarified.
P131441 | Global Partnership for Education (GPE)-4 | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2018 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/220591529937500751/text/Tajikistan-Global-Partnership-for-Education-GPE-4.txt | http://documents.worldbank.org/curated/en/220591529937500751/pdf/Tajikistan-Global-Partnership-for-Education-GPE-4.pdf | Lessons drawn from the ICR, adapted by IEG: Early learning centers, or other forms ofcommunity-based early childhood education programs, can be a viable model for expanding preschool education enrollment. Theuse of existing facilities, topped up with preschool-focused materials and trained teachers, can lead to enrollment levelscomparable to public preschools. Incorporating ME implementation support in the project design can be aneffective way to demonstrate the value and use of ME data in decision making. In the case of this project, the activeutilization of ME systems left in place a higher quality system but also a culture of ME in the Ministry. Aglobal donor assistance program can provide an effective umbrella framework through which external donor support can becoordinated.In addition, the sustainedexternal funding and technical assistance can lead to significantachievements as well as capacity development. In the case of this project, the careful definition of donor activities, andthe regular meetings of the joint donor group, helped to ensure achievement of outcomes.
P131464 | Landscape Approach to Forest Restoration and Conservation (LAFREC) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099052223174523609/text/P1314640ab96ea0770b2050c95deb413499.txt | http://documents.worldbank.org/curated/en/099052223174523609/pdf/P1314640ab96ea0770b2050c95deb413499.pdf | The ICR (p. 34-35) provided several lessons learned, which were adapted by IEG: Promoting protected areasto the status of biosphere reserves and involving local communities in their management and conservation may contribute tosustainable development. In this project, the accreditation by UNESCO of the Gishwati-Mukura Forest Reserves wascapitalized on by local community producers, which improved the marketability of local products and access to regional, nationaland global markets. When a Bank project involves different entities across the government, it is critical toallocate ownership of the project activities to the appropriate authorities. In this project, the Rwanda MeteorologicalAgency was not given sufficiently an oversight role even though its role is critical for the sustainability of the Flood EarlyWarning System (FEWS). Even though the project was extended twice to complete activities for the handover from the RwandaEnvironmental management Agency to the Rwanda Meteorological Agency, the handover has not taken placeyet. Collaborating with local education institutions can contribute to long-term sustainability of the landscapeapproach. This project collaborated with the University of Rwanda to through the education and research component, whichbuilt national capacity to support this and other programs in the future since graduates from the University might work for thegovernment one day.
P131550 | Transport Corridors Project | Middle East and North Africa | Iraq | IBRD | FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Strong leadership and experienced staff can be important factors contributing to successful projectimplementation. The TCP was able to build on PMT staff that was previously established for the ERRP and bring inadditional specialists to oversee various aspects of project implementation. It also benefitted from the decentralization of theregional team and was able to address project demands effectively. Enhanced human resource capacity, continuity of staff within theimplementing agency, and institutional learning from the Transport Corridors Project (TCP) contributed to similar successes withinthe Transport component of the Emergency Operation for Development Project - P155732 (EODP), instilling confidence in governmentimplementing agencies to undertake priority interventions in the sector.Successful implementation of complexinfrastructure projects in FCV hinges on strong client partnership, proactivity, and responsiveness to rapidly changingcircumstances. The TCP team had a strong partnership with the client. Adaptability and flexibility are essential in suchenvironments, and despite facing uncertainties like war and COVID-19, the project team demonstrated resilience and resourcefulnessby taking proactive measures to ensure continuity. Their ability to adjust plans in response to changing circumstances was pivotalin achieving project targets, highlighting the importance of responsiveness in effective implementation.Adoptionof measures such as a Safe System approach and a commitment to routine maintenance can be highly effective in improving the safetyof road networks. The scope of the road rehabilitation works along Expressway 1 included the installation of guardrails,road markings, reflectivity enhancements, and road edge shoulders to enhance safety. This aligned with the principle of the SafeSystem approach that emphasizes that road projects should focus on measures such as crash barriers that reduce fatalities andserious injuries, as opposed to crash reduction measures. Despite the considerable time and resources invested in planning,procuring, and installing guardrails, the results have been highly effective, with reduced fatalities. In addition, theclients commitment to routine maintenance and timely replacement of damaged components is essential to maintain theeffectiveness of these safety systems.
P131558 | Transmission Efficiency Project (TEP) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099530012062229427/text/P1315580fe65690e2092c3082fb08a71ab3.txt | http://documents.worldbank.org/curated/en/099530012062229427/pdf/P1315580fe65690e2092c3082fb08a71ab3.pdf | This review has drawn three lessons based on the information in the ICR.Readiness of sub-projects intransmission infrastructure investments before project start can accelerate project implementation and facilitate earlierachievement of project objectives. The first group of eight sub-projects to be financed under the first component hadalready been selected with feasibility studies and bidding documents ready at the time of project appraisal. This readiness wasmostly because of the sub-projects being a part of the NPTs investment program, and it ensured the start of the biddingprocess even before loan effectiveness. All of the eight sub-projects were completed by the original project closing date ofDecember 31, 2019. Four of the twelve sub-projects that were selected during implementation were incomplete by the original projectclosing date.Inadequate preparation of a major technology that is being introduced for the first time canadversely affect project implementation and the achievement of project objectives. At appraisal, only a roadmap wasprepared for the introduction of smart grid technology in transmission substations. The kind of the smart grid technology to beused was not decided at appraisal. During project implementation, the discussions on the type of the smart technology to be used inthe project that would have a system wide impact took a long time. Once a decision was made on the type of the technology, thepreparation of the regulations required an additional 12 months. Overall, the approval process lasted for more than four years, andat the time of the original project closing date, there had been no progress in the implementation of upgrading of substations withsmart grid technology under the second component. This led to a two-year project closing dateextension.Overestimation of project cost at appraisal can lead to cancellation of large loan savings. Avery conservative methodology was used during appraisal that led to a significant overestimation of the project cost. The actualproject cost was much lower than the cost estimated at appraisal, partly because of the sharp decrease in steel costs. A loansaving of around US$150 million (around 30 percent of the loan amount) was put on hold and could not be used for other sectors andpriority activities as they were committed to this project. The amount was cancelled at project closing. The ICR (p.32) states thatthis constrained the Banks resources as well as the Governments sovereign guarantee capacity. Suchapproach was observed in similar transmission projects in other countries, all of which led to no-use or inefficient use of loansavings from cost overestimation at appraisal.
P131558 | Transmission Efficiency Project (TEP) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2022 | 2024 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099026109262383942/text/SECBOS07ad950a0ab0b8e20b71534b0e4ad.txt | http://documents.worldbank.org/curated/en/099026109262383942/pdf/SECBOS07ad950a0ab0b8e20b71534b0e4ad.pdf | 3. Lessons 3.1 The readiness of subprojects for implementation before project effectiveness is critical for timely achievement of project objectives. It is even more so if an advanced technology is being introduced for the first time. In this project, 8 out of 12 transmission subprojects had their feasibility studies and bidding documents ready at the time of project appraisal and were completed on time. The remaining 4 subprojects that were finalized during implementation remained unfinished at the original project closing date. However, the greatest delay arose from the delay in finalizing the selection of technology and adopting the regulation for selected smart grid technology, requiring a two-year extension of the closing date. In retrospect, although a road map was prepared at approval for the introduction of smart grid technology in transmission substations, the learning curve and due diligence on the part of the borrower in choosing the appropriate smart grid technology were underestimated. 3.2 Overestimation of project costs at appraisal locks up funds and strains the governmentâ€™s sovereign guarantee capacity. The actual cost for this project was 30 percent lower than the appraised cost, partly due to a sharp decrease in steel prices and strong competition among bidders, but largely due to conservative estimates of EVN and NPTâ€™s planning functions. 3.3 Planning for the expansion of the transmission network must keep pace with electricity demand and generation expansion plans, particularly the increasing share of renewable sources, to prevent the loss of performance gains from past investments. PDP7 (2011â€“20) has been extended until the adoption of PDP8 and does not reflect the current and emerging investment needs for the power grid. This is adding to costs 19 through increased transmission losses and network congestion resulting from a rapid increase in VRE over the past three years. 3.4 Delayed planning has a direct impact on the financial situation of the utility and grid performance. In this case, the increasing costs (from cost of financing, transmission losses, and grid congestion) that could be mitigated by planning, coupled with unremunerative tariffs, affect the financial sustainability of NPT and result in underinvestment for current and future needs. If not addressed in a timely manner, such underinvestment would negatively affect grid performance. There is clear recognition among sector officials of the impact of the delay in adopting PDP8. 3.5 A sustainable transmission tariff allows the power grid company to finance its capital expenditures more effectively while attracting private sector investments. A transmission tariff below the economic cost for NPT is the main reason for underinvestment and difficulties in mobilizing long-term financing. Although NPT has been able to turn around from negative return on equity in 2015 to 10.9 percent return on equity in 2019, keeping this key parameter of profitability at a sufficient level remains a challenge. The low return on equity is also the main reason for the lack of private investments in power transmission, which are allowed under the countryâ€™s public- private partnership law. 3.6 Land acquisition for transmission lines and substations can be a lengthy process and requires close collaboration between the utility and local authorities. Land acquisition is a major driver of the cost and timeliness of investments in transmission lines and substations. The key ingredients to timely and expeditious land acquisition, based on NPTâ€™s experience, would be (i) proactively collaborating with local authorities and affected communities and (ii) balancing the variations in the time spent for the land acquisition process across provinces or states. 20
P131592 | SREP-Supported Extended Biogas Project | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099655008112292325/text/P131592034409b01d0acac0cbf7f20b58d3.txt | http://documents.worldbank.org/curated/en/099655008112292325/pdf/P131592034409b01d0acac0cbf7f20b58d3.pdf | The ICR included four lessons. The following two are emphasized with some adaptation of language:1. For aninnovative pilot project that aims to introduce a new technology in the country involving the private sector, the Bankssupport combinedwith the governments subsidy mechanism areuseful for initial market creation through costbuy-down and risk-sharing.Projects aiming to createa market for a new technology need to incorporate criticalelementsinto the projects design and supervision arrangements to ensurea transition towards commercial marketviability after the project period.For an innovative pilot project that aims to introduce a new technology in the countryinvolving the private sector, the Banks support combinedwith the governments subsidy mechanism areusefulfor initial market creation through cost buy-down and risk-sharing.Thisincreases interest fromprivate developerson a new technology and help create a market. However, it takes time to fully develop a new market where the requisite expertiseand technologies can be obtained locally in a cost-effective manner.Therefore, theBanks extended support isneeded formarket development beyondthe projects completion and the graduation from the subsidy to ensurethatthe sub-projects will continue to be commercially viable. In particular, a longer implementation period, flexible projectdesign, and/or hands-on supervision ideally with theBank teams in-field presence arehelpful arrangements toproactively respond to the changing needs in the sector over the project period until the market is sufficientlydeveloped.2. If ME design does not include a Results Framework (RF) with indicators that capture the causallinks toward the PDO outcomes, accurate assessment of project outcomes will be challenging.For anoperation supporting sub-projects whose amount of energy output, construction period, and capital outlay significantly varydepending on their size, such differences should be well considered when designing the RF, indicators, and disbursementarrangements. One of the main rationales for developing the RF is that it enables quantifying the value of the funds invested inactivities and how they translate into development impacts across a ToC. Given this, an intermediate indicator that only counts thenumber of sub-projects developed under the operation and does not take into account the sub-projects outputs is notsufficient to capture the causal link toward the PDO outcomes or longer-term impacts. Future operations will need to either prepareseparate intermediary indicators by project size or better model the causal link across the ToC. Furthermore, the disbursementarrangement should reflect the difference in nature between larger and small sub-projects.
P131655 | Pacific Islands Regional Oceanscape Program Forum Fisheries Agency | East Asia and Pacific | Pacific Islands |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099062023092024391/text/P131655095136d0230988705d90e909b8f0.txt | http://documents.worldbank.org/curated/en/099062023092024391/pdf/P131655095136d0230988705d90e909b8f0.pdf | This review reiterates the lessons provided in the ICR (paragraphs120-126), with some minor additions1. Long-termengagement. Pacific Islands Regional Oceanscape Program needs to be considered as a long-term multiphase process and engagement.From this ICRR we noted that regional projects can benefit from being grounded first in a diagnostic of country issues rather thanoverall regional issues.2. Region-specific challenges and implementation readiness. PROP was the World Banksfirst engagement in Pacific Islands oceanic and coastal fisheries. Participating countries and institutions had little to noexperience with managing World Bank-financed projects. Region-specific challenges, in part due to the fragile institutionalcontextthere are capacity constraints, significant hands-on-support needed, and the overall challenges of reachingstakeholders beyond capital cities due to the dispersed nature of the countries must also be considered at design.3.The theory of changewas overly complex, not well articulated at design and employed a hub and spoke regional model where acountry led approach could have avoided the need for restructuring in 2018. The programs theory of change was demanding,complex, and ambitious given the institutional capacity, time, political, geographical, and financial constraints by the clientcountry. The idea of leveraging regional institutional capacities (from the FFA, SPC, and others) for effective implementation ofnational project results chains was weakly developed, poorly understood, and/or owned by countries and thusoperationalized suboptimally.4. There very limited consideration of gender equality in the project design, which isa critical dimension when implementing effective CBRM. Continued financing of the CBRM process through the MFMR and project can beinformed by (a) new research and lessons learned about the adoption of CBRM in the region; (b) consultation with SPCsPacific Framework for Action on Scaling up Community-based Fisheries Management: 20212025,to assess howto best engage in either direct community-based fisheries management or/and its enabling work; and (c) recent analytical work aboutgender inequalities in access to productive resources, assets, services, and opportunities, such as the Country Gender Assessmentof Agriculture and the Rural Sector in Solomon Islands, conducted by the Food and Agriculture Organization (FAO) and SPC in2019.25. The Forum Fisheries Agencies convening power as a regional organization is limited by its mandate. Theorganization is a regional advisory body providing expertise, technical assistance, training and other support to its members whomake sovereign decisions about their tuna resources. Thus, the role that FFA was expected to play according to the PROP design thatwas political and involved coastal managementwas not aligned with the its mandate and created expectations that could not bemet.
P131659 | KM-Electricity Sect. Recovery Proj(FY14) | Eastern and Southern Africa | Comoros | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2018 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/635641567538954069/text/Comoros-ESRP.txt | http://documents.worldbank.org/curated/en/635641567538954069/pdf/Comoros-ESRP.pdf | The following lessons were derived from the projects implementation experience (with some paraphrasing byIEG):The World Banks analytical engagement and strong client buy-in are particularlyimportant in fragile and low-capacity countries. MA-MWEs Recovery and Development Plan (RDP), prepared duringappraisal and adopted by the GOC soon after the beginning of the project, ensured that both scope and design of the project weretargeting the most critical levers for project success. Moreover, the key parameters of the RDP subsequently served as the basisfor the performance contract between MA-MWE and the GOC adopted a year later. Without the analytical foundation and officialadoption of the RDP, the project would neither have the needed relevance nor the client buy-in to successfully pursue the mostcritical utility reforms.Simple, well-targeted interventions based on proven solutions to criticaloperational challenges can have significant positive impacts within a short time frame, even in the most difficult country context.The simple project design and avoidance of activities that are not critical to achieving the PDO were instrumental inachieving results within a difficult governance context. An even more focused approach exclusively aimed at utility governance mayhave allowed a faster and more effective achievement of the PDO.If adequately communicated andtargeted, measures to reduce electricity theft and nonpayment can yield large financial benefits without triggering significantopposition from vested interests. The projects support of targeted communication campaigns was key inMA-MWEs successful reduction of nontechnical losses.Womens groups can be effective infostering positive change by appealing to social norms and individual responsibilities, especially in an FCV context with weakenforcement of property rights and chronically poor payment behavior for public services. The engagement and empowermentof womens groups to lead campaigns against electricity theft and meter fraud was particularly powerful within the context ofthe matrilineal Comorian society.If it is not explicitly addressed, the lack of provisions forIDA-funded warrantee contracts and maintenance services that extend adequately beyond a projects closing date can become amajor threat to project sustainability. The World Banks inability to finance long-term warrantee contracts ormaintenance services beyond a projects closing date is a major limitation that needs to be addressed appropriately duringproject preparation. Warrantees of MIS and related hardware typically last 510 years, hence projects must either be extendedaccordingly or governments have to credibly ringfence the necessary funds in their budgets. However, for typical FCV environmentssuch as the Comoros, the latter is not an option due to the perceived risk of Government default on contractpayments.In an FCV context, the intervention of resident experts can make the difference betweenproject success and failure. The intervention of experts must be well prepared and carefully managed to ensure: (a) thedefinition of a robust executive mandate including decision-making authority and detailed key performance indicators; (b) therecruitment and embedding of the right experts within the client organization; and (c) robust provisions for retaining experts andtransferring knowledge. Teams tend to underestimate the complexity of these challenges while overestimating the capacity of PIUs tomeet these requirements. In this project, the experts value added was reduced by GOCs categorical refusal to grantexperts more than just an advisory mandate. The lack of a managerial role made the experts vulnerable to the frequent change ofMA-MWEs senior management. Given the PIUs lengthy recruitment and unsuccessful attempts to hire financial and technical resident experts, the services of a specialized recruitment agency were utilized. Although costly, suitable experts wereidentified sooner, contracts were negotiated faster, and the experts were retained or quickly exchanged asneeded.
P131660 | SKILLS DEVELOPMENT PROJECT | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/864301614722271699/text/Malawi-MW-Skills-Development-Project.txt | http://documents.worldbank.org/curated/en/864301614722271699/pdf/Malawi-MW-Skills-Development-Project.pdf | The ICR presented four lessons of which IEG emphasizes two as follows:DLIs can be used with direct institutional-levelengagement to strengthen institutions, build accountability, and drive results. The use of DLIs was an innovation in Malawi andhelped increase the results orientation of teams and the focus on delivering for results. The ICR also suggested that directdisbursement of funds to implementing agencies based on the achievements of agreed-upon results can support ownership and deliveryof results.The use of Open Distance e-Learning (ODeL) modalities require additional support to instructors and students toensure the quality of services. The ICR noted that the use of ODeL in Malawi as a mechanism to increase access to skills trainingprograms has allowed the country to increase enrollment, particularly among students in rural areas. Such increased access requiresadditional support to be provided to both instructors and students. Instructors require additional support and training in terms ofdesigning online learning activities and on ways to maintain student engagement and support. Students also require support,particularly in relation to ongoing academic support to ensure they can engage with fellow classmates, instructors, and studentservices. IEG notes that lessons regardingthe introduction of distance learning modalities and the range of support requiredfor success are of particular importance in the context of Covid-19 and beyond.
P131666 | Rwanda Second Support to Social Protection System | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2013 | 2014 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following lessons learned are derived from the ICR:Coordinated efforts across developmentpartners well aligned with Government priorities provide important support to reforms. Although always the driver of thereform effort, the GoR counted upon needed financial and TA supportfrom its development partners,all under awell-coordinated and functioning donor-government group, the SWG, using regular backward- and forward-looking JSRs to ensurecollaboration in monitoring progress and in implementing well-coordinated policies and programs.Aprogrammatic DPL can provide a powerful instrument in establishing an efficient integrated safety net, responding flexiblyto support its evolution. Several factors facilitated the success of the programmatic DPL: The sectoral policyreforms were central to the World Banks CPS, complementary to and well-coordinated with other World Bank-financed operationsand non-lending services, and accompanied by critical TA needs. Effective development partner coordination, throughpolicy support to the Government, implementation support, technical support, and external consultants, provided mostly by the donorpartners, was achieved under the framework of the SWG. Implementation of the SSPS Program was characterized by acontinuous process of implementing, monitoring, evaluating where possible, analyzing, and adjusting based on lessonslearnedthe programmatic nature of the DPL allowed the flexibility to constantly refine, adjust, and adapt the program toimplementation experience and newly identified priorities and challenges.Development of consolidated MISrequires several iterative steps and takes time. Programs and projects that support this type of activity shouldfactor this into implementation schedules. A corollary lesson is that if broad, ambitious visions are developed, these need to beaccompanied by clear, achievable implementation plans based on a thorough understanding of needs, use cases, and institutionalcapacity.IEG observation:A programmatic DPL can provide the continuity that isnecessary to put in place and develop a comprehensive safety net that aims at promotion as well as protection. This isespecially the case when building a system from scratch in an environment of constrained resources. It offers the security ofpiloting and gradual expansion of a program; and the gradual introduction and harmonization of multiple programs. It may beparticularly useful in allowing the build-up of targeting systems and registries over a period of time, explore delivery methods,and develop links with sector ministries and agencies that affect both supply and demand.
P131688 | Comoros Economic Governance Reform Grant | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/699621525886124829/text/Comoros-KM-Economic-Governance-Reform-Grant.txt | http://documents.worldbank.org/curated/en/699621525886124829/pdf/Comoros-KM-Economic-Governance-Reform-Grant.pdf | The ICR presents important lessons on the positive role of technical assistance activities on DPO performance, theconstraints placed by difficult relations between the central and island governments, and the additional Bank supervision that alow capacity context requires. IEG adds the following two lessons:1. 1. In low capacity settings,objectives on economic management and governance are likely to materialize slowly. In such settings, programs in those areas needto be designed with longer term horizons, where initial outputs (e.g., gradual consolidation of government accounts) lead to longerterm outcomes (e.g., efficiency gains in cash management) at the conclusion of the program.2. The privatesector can help overcome low capacity constraints. The award of a license to a private telecom operator in Comoros contributedsignificantly to expand access. The built in capacity of a private operator can help overcome Government limitations. The telecomreforms contrast with power sector reforms, where low operational and financial capacity makes progress more difficult andlongerto achieve.
P131709 | Coastal Watersheds Conservation in the Context of Climate Change Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/292141592085978801/text/Mexico-MX-Coastal-Watersheds-Conserv-Project.txt | http://documents.worldbank.org/curated/en/292141592085978801/pdf/Mexico-MX-Coastal-Watersheds-Conserv-Project.pdf | Based on the lessons in the ICR, this review has summarized the main generally applicable lessons which this review hashighlighted with some editing.When communities work together it facilitates knowledge exchange andstrengthens bonds across them. These bonds can lead to the creation of coalitions which continued to operate after thisprojects closure, such as the Coalition of Organizations of the Jamapa-Antigua Bio-basin. In addition, community enterprisescan be strengthened by regional networks with their support for enlarging scale for activities such as collective marketing, andcommunity integration into the local economy as they were in this project.Participation in environmentalmonitoring inspires communities to raise awareness on the importance of natural resource conservation and management. Forexample, the community that monitored water quality and biodiversity built a sense of stewardship towards the resources andenhanced monitoring methodologies through creation ofCommunity Biological Monitoring (Monitoreo Comunitario de laBiodiversidad -BIOCOMUNI) and application of the National Biodiversity Monitoring System (SNMB) under coordinationofNational Commission for theKnowledge and Use of Biodiversity (Comisin Nacional para el Conocimiento y Uso dela Biodiversidad -CONABIO).Communicating protective area (PA) creation plans early on can ensure that theseplans are aligned with policy objectives for conservation and climate change. In this project coordination betweenthe national government and communities to integrate the PA creation plans into pre-existing conservation plans avoided overlaps intarget areas, leading to acceleration in PA creation process. At the local level, communicating plans for PAs early minimizedconflicts among existing resource users, reducing potential opposition against restrictions in land use and access associated withthe PAs.
P131763 | First Programmatic Development Policy Loan | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory |  | Moderately Unsatisfactory | Modest |  |  | IEG draws three lessons from the DPO series: 1. The success of tax policies will hinge on the adequacy and governance of taxadministration. The DPO series envisaged reforms of tax rules and administration that may have helped success on income taxrevenues. However, success is largely elusive, particularly on indirect taxes, as weak governance continuei to undermineimplementation of policy reforms. 2. Monitoring and evaluation of an objective to improve budget management will be difficult ifnot underpinned by data such as that collected by a Public Expenditure and Financial Management Assessment (PEFA). As a result, theresults from the changes in the budgetary framework could not be fully assessed. 3. The effectiveness of social expenditures wouldbenefit from integration across social programs and across government levels. The DPO series focused only on programs, where theZero Hunger Pact developed an institutional arrangement (the Municipal Councils of Food andNutrition) to implement a centralgovernment program at the local level. Integration across social programs, of which there are at least 75 in Guatemala, would berequired to improve the effectiveness of social expenditures through means-tested targeting.
P131763 | First Programmatic Development Policy Loan | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2020 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/714901575473880311/text/Guatemala-Enhanced-Fiscal-and-Financial-Management-for-Greater-Opportunities-DPL-Series.txt | http://documents.worldbank.org/curated/en/714901575473880311/pdf/Guatemala-Enhanced-Fiscal-and-Financial-Management-for-Greater-Opportunities-DPL-Series.pdf | 5. Lessons 5.1 The Independent Evaluation Group draws three lessons from the development policy operation series. They are additional to the lessons provided earlier, in the Implementation Completion and Results Report Review stage, which largely remain valid today. â€¢ Tax administration and tax policy reforms in the face of major governance issues and long-standing opposition from influential interest groups are unlikely to be successful, even if backed by the World Bank's analytical support, policy dialogue, and financing; under these conditions, directly and indirectly targeting the governance issues over a longer period would be more appropriate. â€¢ Achieving progress on results budgeting requires strengthening of capacity, political commitment, sound M&E indicators, and cross-agency collaboration. â€¢ Achieving results in policy lending requires a sound results framework, a credible theory of change, close linking of objectives with policy actions, and outcome-oriented target indicators.
P131765 | Eastern Dedicated Freight Corridor - II | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062024195013369/text/P131765-0a690bac-6e39-43d2-be1a-a1980f5e2976.txt | https://documents.worldbank.org/curated/en/099062024195013369/pdf/P131765-0a690bac-6e39-43d2-be1a-a1980f5e2976.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The Banks long-term strategic support may raise the potential for success in enabling State OwnedEnterprises (SOEs) harness commercial financial markets and introducing fundamental changes in a countrys railsector. The time frame for large-scale, long-term reforms in a countrys rail sector are typically long. Thesestrategic reforms require the SOEs to evolve from a traditional government-funded organization to a commercial, market-focused andoperationally efficient entity. Likewise, long-term engagement by the Bank can enable the Bank to facilitate adoption of soundsocial, environmental and fiduciary policies.The lesson is that Banks long-term support may be necessary to facilitatesuch reforms.2. Careful planning for managing and coordination of land acquisition may be required, in countrieswhere subnational entities are involved in land acquisition. In India, national-level projects rely on state governmentsfor the complex process of land acquisition. The process in this project required intensive coordination between the DedicatedFreight Corridor Corporation Limited (DFCCIL), the state government land offices, the contractors and local governments. Over time,as land acquisition delays impeded construction, DFCCIL became much more systematic in coordinating land acquisition as it came torealize that coordination with local authorities was in the interest of timely project completion.3. A carefulassessment of the World Banks capacity and the contractors capacity may be required when new contracting structures areintroduced for the first time. This project conceptualized the Design-Build lump sum contract to ensure equitable risksharing between DFCCIL and the contractors. However, the project failed to foresee the time required for Banks internalapprovals, financial challenges faced by contractors and delays in land acquisition by DFCCIL. This contributed to the delays inthe initial years.
P131775 | Vietnam Climate Change Development Policy 3 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2014 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | The lessons highlighted in the ICR (paras. 71-75, pp. 29-30) areapplicable to similar operations, especially:1.An effective cross-sector platform is needed to achieve significant progress on policy and institutional reforms that addressclimate change;2. Convergence of programs and resources between line ministries, across development partners, and betweennational and sub-national levels of Government is also necessary for achieving progress on climate change reforms; and,3.High level engagement with the government, supported by strategic and targeted technical assistance and knowledge, is essential toachieve reforms on climate change.In addition, as IEGs recent learning evaluation with regard to environmental(including climate change) development policy operations has found, the following lessons, whichare also illustrated by thepresent DPO series,are also of relevance:1. Strong and persisting Government and other stakeholder commitment toprogram objectives and policy actions, including that of key Finance and Planning Ministries, as well as that of other implementinginstitutions, is essential;2. The Bank should be willing to join ongoing policy-based programs if it can clearlyaddvalue by helping to better focus them and prioritize policy actionsthatare of especial importance in achieving theirgeneral objectives (i.e., climate change adaptation and mitigation in the present case) as well as through itssupervision/implementation support; this can also help to enhance donor coordination and local capacity with regard to policysupport in a particular country;3. Climate change development policy operationsare more effective if they arefocused on a limited number of high priority policy areas, counton strong government commitment and based onsolidbackground analytical work and are used in conjunction with other Bank and donor-supported technical assistance and investmentoperations, including in the present case with respect to water resource management, energy efficiency, and natural disaster riskmanagement; and,4. Task team leadership arrangements in which responsibilities are shared by internationalspecialistsbased in Headquarters and local ones basedin the field can help the Bank toprovide more efficient andeffective implementation support, including to other participating donors that are present on the ground, while also ensuring thatBank polices and operational requirements are fully met.
P131778 | Obsolete Pesticides Management Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099225006292240997/text/P131778027156a04d08c9905b2abb35f7ce.txt | http://documents.worldbank.org/curated/en/099225006292240997/pdf/P131778027156a04d08c9905b2abb35f7ce.pdf | The ICR (para 100-104) provided five lessons. Some of them are presented below with editing because they may provide lessons ofinterests for other obsolete pesticides management projects.Regional disposal of obsolete pesticides andassociatedwastes in Cte dIvoire can be an option for future similar projects in other countries in theregion, given it is pursuant to international and regional agreements (i.e., the Basel, Rotterdam, and Bamako Conventions)and environmental standards and safeguards. The disposal firm contracted under the project, Ruegg Matray Group CtedIvoire, disposed of the obsolete pesticides and associated wastes in line with environmental standards and with reasonablecosts of disposal (ICR, para 57). Considering that FAOs pricing models have not changed over the past decade, the cost ofdisposal has the potential to drop further with economies of scale and additional experience (ICR, para100).Narrow focus on disposal of stockpiles of obsolete pesticides and associated wastes can limit effectivenessof projects to incentivize stakeholders to shift from chemical pesticides to biopesticides. The Results Framework lackedPDO indicators to measure an important development result regarding the reduced use of obsolete pesticides, as described inSections 4. While the Integrated Pest Management approach was tested under the project by piloting the use of biopesticides tomanage brown pod rot and providing training to farmers to reduce reliance on toxic pesticides (ICR, para 101), insufficientevidence was captured in the Results Framework regarding what outcome was achieved by these activities.Ifgovernments commit to co-financing of project components and not in-kind contributions, it might pose a risk of delaying projectimplementation. The project activities to develop and operationalize the pesticides inventory was delayed because theGovernment was not able to provide its committed amount in full and in a timely manner (ICR, para 103). Constraints and changesthat may affect execution of governments budgets include fiduciary constraints within budget years, changes in staffing, andother conflicting demands (ICR, para 103).
P131825 | Health Professionals Education and Training for Health System Reforms | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099555010192223025/text/P131825076d4710e90aa690f3e3ba33b11a.txt | http://documents.worldbank.org/curated/en/099555010192223025/pdf/P131825076d4710e90aa690f3e3ba33b11a.pdf | The ICR (p. 37)identified some lessons and recommendations, including the following lessons moderately re-stated by IEGReview:In countries undergoing decentralization, strong collaboration in planning and implementation among centraland subnational level stakeholders promotes the potential for improved health professionals education and itssustainability. The project benefited from collaboration between the Central Project Management Unit, several ministries,training institutions, and Provincial Departments of Health. Various bodies were involved in the transfer of new medical techniquesand the installation and operation of new equipment. Local project implementers were medical and pharmaceutical colleges staff whowould contribute to the sustainability of project outcomes beyond the project life.Medical education reforms arefacilitated by extensive consultations and by leveraging international expertise. The project stimulated consultations andused existing support from other partners, including international expertise. The project linked with ongoing efforts to buildtraining programs at medical universities and colleges. This contributed to shortening the time required for developing andimplementing competency-based training programs.
P131850 | Enhanced Nutrition for Mothers and Children | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/966301607123582139/text/Pakistan-Enhanced-Nutrition-for-Mothers-and-Child.txt | http://documents.worldbank.org/curated/en/966301607123582139/pdf/Pakistan-Enhanced-Nutrition-for-Mothers-and-Child.pdf | These lessons are drawn from the ICR (pp 37-39), and restated by IEG.Projects that have performed poorly forseveral years are strong candidates for substantial restructuring and corrective measures. The process of restructuring isan opportunity to address implementation bottlenecks, correct shortcomings in project design, and adjust to new circumstances. Itis not realistic to hope that projects will self-correct without taking action to change the institutionalarrangements or other factors that are slowing project implementation. A clear-eyed assessment during the MTR of the reasons thatexpectations are not being met can help identify changes needed to improve project outcomes.Explicit and legallybinding TA arrangements may be preferable to loosely defined, opportunistic TA support from partners and development partners.When governmental implementing agencies lack the capacity and expertise needed to implement a project, it is important toensure that adequate TA is available as needed. Relying on TA available through co-financed parallel programs of developmentpartners may not be adequate. Instead, a well-coordinated, dedicated source of external TA with secure financing (such as through aTrust Fund) outside of the Governments regular budget may be important for providing the implementing agencies with thesupport they need to achieve the project goals.
P131864 | Kabul Urban Transport Efficiency Improvement Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | RETF | IPF | 2014 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099422004262212581/text/P1318641a261627511ba41497019acd1bca456368937.txt | http://documents.worldbank.org/curated/en/099422004262212581/pdf/P1318641a261627511ba41497019acd1bca456368937.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A simple design would be helpfulespecially in countries withfragile settings.Thedesign in this project entailed the project to be implemented with local capacity, despite the deteriorating securitysituation in the country.2. The strong local presence of the Bank team can help in projectimplementation. The continuity of the local presence of the Bank team in this project helped the project agencies toestablish a close working relationship with the Bank.3. Adapting theWorld Bank guidelines for fragile,conflict and violent countries can aid ineffective project implementation. For example, relaxing some of theprocurement post qualification requirements given the fragile context, made it possible for a greater number of local contractorsto participate in the bidding process.4. A careful examination of the availability of internationalconsultantsis especially required in fragile countries. The project was unable to find consultants forundertaking institutional strengthening activities and this eventually led to the cancellation of these activities in thisproject.
P131921 | EU/IPA Energy Sector Technical Assistance Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2014 | 2018 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/339861530232432774/text/Turkey-EU-IPA-Energy-Sector-TA-Project.txt | http://documents.worldbank.org/curated/en/339861530232432774/pdf/Turkey-EU-IPA-Energy-Sector-TA-Project.pdf | The following are lessons learned from the ICR (paras 112 to 114, and 116) with someparaphrasing:1 . The project showedthe high potential of maximizing finance for development through large scaletechnical assistance services in Middle Income Countries. The development impact of this TA proved the high value added ofEU/World Bank joint operations and developed a brand-new business line to accommodate the MENRs capacity-building demand.Eventually, the tools produced, audits conducted, and feasibility studies drafted ended up mobilizing considerable privatesector financing for RE and EE. Furthermore, the observed outcomes during the implementation period are just the initial steps ofthis achievement and further expansion is expected. On the other hand, the regulations developed based on the project outputs,helped to level the playing field in energy sector; particularly the natural gassubsector.2 . For the EU/World Bank jointoperations, the design of implementation arrangements, particularly their procedural and operational compatibility, deserves utmostattention. In the tripartite legally binding operations, procedural hurdles of any party can result in a domino effect inthe preparation and implementation period. Therefore, in the design stage, the procedural risks must be identified in detail,including the mitigationmeasures.3 . The results framework must be designed properly to accurately assess the impact of the RETFTA at this scale. It is a challenging task to design an attributable, measurable, and realistic RF for large-scale TAoperations with a list of consultancy services. Therefore, an experienced ME specialist should be included in the task teamsat the design stage to avoid any vagueness in the RF design. The weak RF design caused weak ME utilization and difficulty inassessing the overall performance of this operation.
P131945 | Madagascar Emergency Support to Critical Education, Health and Nutrition Services Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2018 | 2018 | ICRR | >=50 million & <100 million | Highly Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/825401529101979917/text/Madagascar-MG-Emerg-Supp-to-Critical-Ed-Health-Nu.txt | http://documents.worldbank.org/curated/en/825401529101979917/pdf/Madagascar-MG-Emerg-Supp-to-Critical-Ed-Health-Nu.pdf | Useful lessons arederived from the ICR:It is important for an emergency operation to have arealistic objective and a simple and flexible design. As per the ICR, and given the emergency context of the operation, setting arealistic objective and maintaining flexibility, by keeping a significant unallocated amount of resources, were key to thesuccessful implementation and outcomes of this operation (ICR p. 35). This project incorporated lessons learned from anotheremergency operation in Madagascar, and changes during implementation proved the usefulness of having the flexibility of unallocatedresources to respond to a locus infestation. In addition, a simple design for a multi-sectoral operation not only benefited fromprevious experience but also tapped into government ownership and willingness to experiment with innovative interventions (ICR p.35).Procurement rules are prudently adapted to country characteristics. Small countries like Madagascar maynot have the scale tofollow standard procurement rulesthat require international and competitive bidding. Whiletransparency and due diligence in procurement has to be assured, the Bank could show more flexibility and understanding in suchcases and provide government teams with realistic solutions to avoid unnecessary delays.
P131945 | Madagascar Emergency Support to Critical Education, Health and Nutrition Services Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2018 | 2021 | PPAR | >=50 million & <100 million | Highly Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/328771596217161648/text/Madagascar-Emergency-Support-to-Critical-Education-Health-and-Nutrition-Services-Project-and-Additional-Financing.txt | http://documents.worldbank.org/curated/en/328771596217161648/pdf/Madagascar-Emergency-Support-to-Critical-Education-Health-and-Nutrition-Services-Project-and-Additional-Financing.pdf | 3. Lessons 3.1 A multisectoral approach that delivers health, nutrition, and education services, food security, income-generation activities for women, strong behavior change interventions, and women's empowerment to the same families or communities can have a synergistic and impactful effect on the health and nutrition of children and their mothers. Poverty and low access to critical services are both causes and consequences of malnutrition. Global evidence has proven this, and heartfelt exchanges with the beneficiaries of this project have corroborated this. Beyond multisectoral interventions supported by the project, better health and nutrition cannot be achieved without improved water and sanitation and other critical services, including agriculture, security, and roads. 3.2 The effectiveness and efficiency of national nutrition efforts are contingent on the responsible central-level agency fully assuming its primary function of multisectoral coordination. For this to happen in Madagascar, ONN's authority and convening power for multisectoral coordination of nutrition activities needs to be reasserted by the prime minister's office (within which it is appropriately housed). Additionally, the National Council for Nutrition and its Permanent Office need more of an interface between the prime minister's office and ONN to ensure more frequent meetings, briefings, communications, and decision-making. ONN's structure also needs to reflect this priority function. 3.3 The roles and comparative advantages of the regions and districts in the strategic management and implementation of service delivery, including the support and encouragement of cross-sectoral synergies, will continue to be underexploited as long as the government's structure is highly centralized. Government's current structures and processes result in a high concentration of planning, programming, resource allocation, and decision-making responsibilities at the central level, which constrains the flow of resources and decision-making power to these levels. 3.4 Successful mobilization of resources, planning, programming, and priority setting (including managing the tensions between the national goals of expanding nutrition coverage and strengthening existing services) will be difficult to achieve without investments in building ONN's capacity and strengthening its convening authority. These disciplines are critical for catalyzing all sectors and actors to contribute to the nutrition agenda in line with their comparative advantages, ensuring that national priorities are served within the financing envelope, providing the basis for programbased monitoring and evaluation, and holding all sectors and actors accountable for delivering on their expected contributions. 3.5 Improved aid effectiveness and sustainability depend on development partners working closely with the national nutrition agency and the regions, supporting their development plans and priorities, and on an evolution from projects to program support. Given that the public budget for nutrition has been declining for many years and the need for sustaining and further expanding services is great, prioritizing nutrition funding and improving aid effectiveness is critical for the optimal allocation and use of resources. The onus is on ONN to build on its initial efforts to inventory and analyze the large range of partners contributing to various nutrition efforts across regions. The regional and operational levels have a crucial role to play in the allocation and use of resources for optimal coverage and optimal results. 3.6 The World Bank can play a pivotal role in supporting ONN in assuming its multisectoral coordination role, in advocating to the highest levels of government the importance of prioritizing nutrition as a means of achieving its development objectives and allocating more budgetary resources to this end, and in supporting government's decentralization process to empower regions to realize their potential in the fight against malnutrition. The World Bank's comparative advantage lies in its own multisectoral mandate and experience, its access to the highest levels of government, its Country Partnership Framework (which supports decentralization), and its long and rich experience in nutrition both in Madagascar and elsewhere. 3.7 Emergency operations can provide a unique opportunity for embarking on broader development efforts. However, the inclusion of such development support without attention to sustainability can undermine gains postproject. The project's successful support to development, in addition to emergency efforts, is attributable to the availability and use of a strong evidence base for the three individual sectors (both global and country-specific), creative ideas supporting and nurturing cross-sectoral synergies for a more holistic approach to child development, and a long tradition of operations research and learning in the human development sectors. The opportunities of additional financing for nutrition, an education project developed soon after the emergency operation was launched, and an eventual follow-on health and nutrition project might have been more fully exploited for addressing sustainability in all of its dimensions, especially financial and institutional. Prospective 3.8 This project has laid the foundation for a more holistic and synergistic approach to human capital development, which is a key pillar of the World Bank's program in Madagascar. This approach is currently supported by a series of ongoing investment operations, including a multiphase programmatic approach to improve nutrition outcomes through investments to strengthen community health and nutrition services; the Social Safety Net Project supporting conditional cash transfers and cash-for-work schemes with information and incentives for adopting behaviors favoring the well-being of vulnerable women, children, and families; and the Basic Education Support Project to improve learning in primary schools through investments to strengthen teacher quality, school readiness, school health and nutrition, and sector performance and management. These investment operations are complemented with a recently approved (March 2020) human capital development policy operation. One of the first of its kind in the World Bank's Africa Region, this policy operation aims to improve the qualifications, distribution, and performance of human resources in the health and education sectors; enhance the availability and predictability of financial resources for the social sectors; and strengthen legal protections for women and children. 3.9 Additionally, the World Bank recently completed a review of its portfolio in an effort to further strengthen and broaden its support to human capital development. In complement to the above-cited social sector projects, the portfolio review assessed opportunities to invest in additional sectors and further exploit cross-sectoral synergies to build human capital. This has culminated in plans to identify projects and components supporting nutrition-sensitive sectors critical to Madagascar's nutrition agenda\. agriculture/food security; and water and sanitation. Beyond these, the World Bank in Madagascar is exploring still other investments in human capital development, including roads and electricity. 3.10 The World Bank's expanding multisectoral approach to human capital development (including reductions in chronic malnutrition) highlights the importance and urgency of the lessons emanating from this evaluation. Both the World Bank and the government of Madagascar have an opportunity to exploit synergies and enhance the impact of these ongoing and planned operations (along with other ongoing and new investments) by ensuring that they are coordinated to support the same vulnerable communities and families and that they are directly supportive of national programs and priorities. This calls for increased attention to the critical, unfinished agenda of strengthening the institutional framework and capacities for Madagascar's nutrition program at all levels of government and encompassing all partners to achieve needed improvements in cross-sectoral coordination, strategic program management, resource mobilization, and aid effectiveness. 1Almost all other donors withdrew their assistance after the March 2009 political crisis. Agence Francaise de Developpement is the only one that remained. Others began returning around 2013. 2Poverty rate, as defined here, is the share of the population living below the poverty line of $1.90 per day purchasing power parity. 3Hery Rajaonarimampianina was sworn in as president in January 2014, and Andry Rajoelina was sworn in as president in January 2019. 4Minimum diversity of food is the percentage of children ages 6â€“23 months receiving five of eight recommended food groups. Minimum acceptable diet is the percentage of children ages 6â€“ 23 months receiving a minimum diversity of food and minimum number of foods. 5Forty-one percent of people have access to potable water (32 percent of rural residents versus 69 percent of urban residents), 6 percent of people have access to basic sanitation services (4 percent of rural residents versus 15 percent of urban residents), and 23 percent of people have access to basic hygiene, which is the availability of soap and water for handwashing (18 percent of rural residents versus 38 percent of urban residents). 6The World Bank estimates Madagascar's total population at 26.3 million in 2018, of which 16.5 million are rural residents. The annual growth rate is estimated to be 2.67 percent. 7The eight Madagascar Action Plan commitments were (i) responsible governance; (ii) connected infrastructure; (iii) educational transformation; (iv) rural development and a green revolution; (v) health, family planning, and the fight against HIV/AIDS; (vi) high-growth economy; (vii) cherish the environment; and (viii) national solidarity. 8The World Bank's Interim Strategy Note, issued in December 2011 (almost two years after the political crisis and about the time of project preparation) notes that no other formal government strategy had been issued. 9This action was taken in line with the application of the World Bank's Operations Policies and Bank Procedures 7.30 (dealing with de facto governments). 10High-impact, low-cost interventions include information, education and communication (health behaviors, nutrition, and breastfeeding), vitamin A supplements, vaccinations, malaria prevention and treatment (including long-lasting insecticide-treated nets), treatment of diarrhea with oral rehydration salts and zinc, and integrated management of childhood illnesses. The project also supported health sector support to school health and nutrition activities, including distribution of antihelminth treatment and participation in other school health and nutrition events. 11The nutrition package of services included growth monitoring for children under five (with a focus on children under age two), nutrition awareness and education through culinary demonstrations, support to school-based nutrition activities, and referral to health facilities for severely malnourished children. Seven nutrition interventions will be prioritized\. (i) growth and development monitoring and promotion, (ii) promotion of nutrition for pregnant women (using the life cycle approach), (iii) promotion of vegetable gardens and products rich in micronutrients, (iv) support for providing food to vulnerable groups, (v) food fortification, (vi) micronutrient supplementation (iron, folic acid, and multimicronutrients), and (vii) deworming treatments for children ages 0â€“5 years and pregnant women. 12Discussions with central-level Ministry of Education officials revealed a shortage of qualified teaching staff as a key impediment to education coverage and quality. This is partly because of an inadequate public budget to cover teachers' salaries. Many rural schools have community teachers who are volunteers from the community and do not have the requisite training. Exchanges with teachers and parents during field visits corroborated these findings and raised the issue of very large and growing class sizes, which also undermine teaching and learning quality. 13The government's 2013 school food, nutrition, and health program seeks to support and integrate multisectoral efforts in all 22 regions to improve food intake, nutrition, water, sanitation and hygiene, and health in the school environment, all supporting the overall objective of improving academic performance. 14The two regions that experienced increases are both in the south and are also the most vulnerable to increasingly frequent environmental disasters (cyclones, droughts, and locust infestations), which adversely affected nutrition status. It is possible that community-based nutrition interventions and emergency interventions to address acute malnutrition after disasters may have mitigated negative trends. 15A stand-alone education project was designed, approved, and launched shortly after approval of this project, and it assumed the education sector development content. The Activity Initiation Summary was signed on May 31, 2012, and the project was approved on November 29, 2012 for a six-month preparation. 17The human-centered development approach explores with project beneficiaries constraints to improved care and feeding of their children and how to address them. 18Postmission exchanges with the World Bank and Office National de Nutrition indicate that there was ongoing activity to review and revise Office National de Nutrition's legal status, but as of mid-December 2019, no updates were available.
P131965 | Mozambique Conservation Areas for Biodiversity and Development Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/767531606767437327/text/Mozambique-MozBio-Program-Phase-1.txt | http://documents.worldbank.org/curated/en/767531606767437327/pdf/Mozambique-MozBio-Program-Phase-1.pdf | The ICR provides 5 detailed lessons, which are stated to be incorporated in the design of the second MozBio project. Three ofthe lessons are summarized here (with language adapted).Lesson 1: Landscape Approaches are key for makingconservation and livelihood development compatible. The projects support to livelihoods through subprojects was toosmall in scale and not always sufficiently connected to conservation efforts and community needs. This underlines the need forconservation projects to collaborate closely with other initiatives in the targeted CA landscapes. Particularly activities in theagriculture and forestry sector should be streamlined with conservation as a conservation project by itself will not be able totransform rural livelihoods and impact the many different dimensions of rural living conditions.Lesson 2: It isimportant for livelihood activities to carefully balance short-term economic needs and capacity building when engaging localcommunities in natural resource management. Long-term capacity building allows communities to become active partners inconservation-based tourism rather than merely recipients of revenues generated by investors. Key elements to achieve this includeadequate zoning with clear boundaries for community land and strengthening community governance capacity for managing anddeveloping natural resources under their jurisdiction.Lesson 3: The implementation of livelihood activitiesby service providers requires clear guidelines, close collaboration with CA administrations, and strong communityownership. Service providers are central in community engagement, but many lacked the flexibility and capacity toeffectively engage communities. In addition, some livelihood activities were detached from the conservation work of the CAadministrations, which not only risks undermining conservation but also constitutes a missed opportunity for the visibility of CAadministrations in communities. Collaborating with other initiatives under a landscape approach may provide opportunities for usingalternative institutional settings for service provision.Based on the discussion in the previous sections and the abovelessons, the additional lesson drawn by the ICR review is that an integrated approach to biodiversity conservation andhuman development should pay equal attention to both conservation and livelihood efforts. They are equal tools to achievethe common goal of biodiversity conservation in remote areas characterized by high rates of environmental degradation and poverty.It is not sufficient to allocate a minor part of the budget to subprojects to compensate poor peoples restricted access tonatural resources in CAs and hopefully improve their livelihood to reduce environmental pressure. Local communities need to beconsulted, actively engaged, and given ownership; while the implementation of activities requires capacity building and sufficientfunds. If resources are too limited, projects need to make decisions on which aspect to focus on (conservation or development) andcoordinate the other activities in an integrated landscape management approach.
P131973 | Housing Finance Development Program | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/249821582043222448/text/Nigeria-NG-Housing-Finance-Development-FY14.txt | http://documents.worldbank.org/curated/en/249821582043222448/pdf/Nigeria-NG-Housing-Finance-Development-FY14.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A right implementation partner is necessary for project success. In this project,the Project Administration Unit in the Central Bank of Nigeria was entrusted with the responsibility of implementing the project.This created potential for conflict of interest. Further, the PAT lacked resources to handle administration and meetfiduciaryrequirements. These factors contributed to implementation delays.2. Addressing demand side constraints to thehousing finance market isnecessary but not sufficient when designing housing finance projects. Although supply-sideconstraints were recognized at design, this project decided to focus on demand-side issues under the following key assumptions: (1)setting the refinancing facility would induce the Primary Mortgage Lenders to lend to people at lower income ladder;(2)theconstruction industry would respond through supplying more low-cost housing;and (3) the supply-side constraintswould be addressed byother complementary donor-funded projects. The assumption provided to be unfounded asnot allsupply-side issues had been addressed by complementary projects.3. A longer-term programmatic approach as opposedto a stand-alone operation may be appropriatefor activities associated with housing finance. Given that housingfinance involves a multi-sectoral agenda and that once a liquidity facility is set up, it takes time to attract financialinstitutions to adopt its instruments, issue bonds and make an impact, a more focused, long-term multi-phased approach may bebetter suited forhousing finance projects.
P132101 | Emergency Infrastructure Preservation & Vulnerability Reduction Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/522671567607058835/text/Madagascar-MG-Emerg-Infra-Preservation-Vulnerabil.txt | http://documents.worldbank.org/curated/en/522671567607058835/pdf/Madagascar-MG-Emerg-Infra-Preservation-Vulnerabil.pdf | The following are threekey lessons from the ICR (para 85) with some adaption inlanguage: Multi-sectorial projects can be agood tool to address regional development challenges,especially in poor and fragile countries. With limited funds available and multiple needs, the approach under the projecthelpedaddress the priority needs in various sectors. In addition, theapproach was more efficient in terms of projectpreparation efforts and costs. It is also likely to have a greaterimpact becauseall sectoralinterventions wereconcentrated in the same area instead ofbeing fragmented and dispersed. This multisector project constitutedto someextentan integrated regional development approach linked to theregional development objectives highlighted incountrys policy documents. Involving experienced project implementation agencies and havingstrong leadership is a critical success factor for multi-sectorial projects. According to the task team,theimplementation agencies under this project had already experiencein implementing World Bank projects. Thisexperience wasessential tomanage the differentpriorities and achievepositive resultsand learning. Inaddition, the difficulty to find a common interest in the project beyond each specific sector was overcome through strong projectimplementation leadership. Data collection and results measuring need strengthening.Monitoring and evaluation under the project had shortcomings and experienced difficulties. In addition, the country lacksthequantitative data to measuremedium to long-term outcomes of this type of multisector projects. Therefore, the collection ofdata, for instance, on traffic, population impacted, incomes, and vulnerability, wouldease the preparation, implementation,and evaluation of future projects. It would also help in the governments decision-making process. Furthermore, for futureprojects,funds should be allocated to undertake an impact evaluation orsome less costly survey work.This wouldenable to better understand the potential impacts of this type of projectsonpoverty and the peoples lives.Although this lesson, as formulated, is specific to Madagascar, it is applicable to many other countries.
P132123 | AFCC2/RI-South West Indian Ocean Fisheries Governance and Shared Growth Project 1 | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092523190022714/text/P13212306e689b0010a66004159417d058a.txt | http://documents.worldbank.org/curated/en/099092523190022714/pdf/P13212306e689b0010a66004159417d058a.pdf | The ICR (p. 44-45) included several important lessons learned, which were adapted by IEG: Differentcountries absorption capacity and circumstances present challenges for regional projects. These challenges might be solvedby designing country-level fishery projects that include a regional component. In this project, priorities andcircumstances of countries changed during implementation, resulting in different implementation progress and performance levels,reducing the ability to aggregate results at the project level. Also, each country had to fulfill certain requirements beforeproject implementation started, which countries met at different times, resulting in a lengthy preparationprocess. Finding the right balance between visible short-term results and long-term reforms is critical for thesustainability of project outcomes. In this project, in Comoros and Tanzania, the fisheries infrastructure budgetincreased during implementation since the governments wanted to present visible results with immediate impact on communities.However, exchange rate losses and COVID-19 related price increases resulted in unfished infrastructures andreforms. Local co-management structures can be an effective tool to engage communities in decision making andimplement actions. In this project, in all three countries, agreements with local administrations to manage priorityfisheries in assigned fishing grounds empowered co-management structures legally and financially. Ensuringsustainable regional integration requires a financial commitment by countries. SWIOFC, despite several years of supportthrough other Bank projects, is still dependent on donor financing since member countries face several competing budgetary demandsand the advantages of regional cooperation have not been sufficiently understood. To ensure the sustainability of SWIOFC, it wouldbe beneficial to cost SWIOFCs core actions, define annual government contributions, with donors financing anygap.
P132154 | China: Nanchang Urban Rail Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/664621622177745946/text/China-Nanchang-Urban-Rail-Project.txt | http://documents.worldbank.org/curated/en/664621622177745946/pdf/China-Nanchang-Urban-Rail-Project.pdf | The following lessons have mostly been derived and summarized from the ICR, with minor additions byIEG:Infrastructure financing can be astrong lever for institutional strengthening and sustainable urbandevelopment in high-capacity countries with limited need forBankfinancing. By financing a small portion of anurban rail infrastructure project,in Nanchangthe Bank got a seat at the table to influence the broader urban transportand development agendaand ensure soundresettlement and environment managementpractices. The Bank used thisinvestment project to engage on integration, TOD, LVC, and universal accessibility,and help build thecapacity in theseareas. This led to important progress on all aspects. Even if the Bank only financed a small portion of the project, its safeguardspolicies applied to Line 2 as a whole, ensuring strict resettlement and environmental practices, especially in terms ofconsultation. Financing a small part of a complex infrastructure might become a model for the Bank to provide technical assistance,advice, and capacityinhigh-capacity countries with limited need for Bankfinancing. Earlyand intensive coordination is critical for an urban rail system to achieve its potential as a mass transitmode. Thesuccess of amass transit mode is dependent on integration and thisrequires simultaneous (i) physicalintegration(interconnection between different transport infrastructure), (ii) operational integration(multimodal service planning), and(iii) fare integration (interoperable fare technology as well ascomprehensive fare and subsidy policy across the entiretransit system). With this in mind and beingaware of the necessity to timely coordinatewith many different actors, theBank asked the client to set up a project leadership group. Thisgroup included the vice-mayor,deputy municipalsecretary general,URCschairmanand keymunicipal line agencies, such as Finance Bureau, Development andReformCommission, Urban Management Commission, Planning Bureau, ConstructionCommission, Land Resources Bureau,Environmental Protection Bureau, HousingManagement Bureau, Price Bureau, Traffic Management Bureau and Bus Company.Thegroup prepared, agreed, and implemented the integration plan jointly, and this was thekey for the successful publictransport integration. The project did not have such coordination group to support the construction of Line 2. This causedsignificant delays in the re-location of utilities and the implementation of the temporary traffic deviation, which both depend oncoordination.The lack of joint urban rail andbroader transport and land use planning made the urban railproject implementation more cumbersome. Compact urban development requiresderegulated land use towards higherdensity and mixed land use along the entirealignment of the urban rail system. Such systemwill only deliver premium inproperty values in its influence area if it is integrated with the stations and surrounding space, forming astation-centrictransportation, housing, catering, shopping, entertainment, and culture space. In this project, the land useaspects to ensure the necessary density and mixed land usefor the rail system had to be retrofitted on a case-by-case basis.The project identified the potential areas for development along the urban rail systemand ensured the necessary zoningchanges to achieve the higher densities and mixed use. This required a lot of discussions and was cumbersome.A more efficientway of proceeding could have been to carry out the urban rail planning jointly with a revision of the land use and zoningplanning.In a project with multiple stakeholders, animplementation arrangement with a single implementationagencymight jeopardize the completeuse ofproject resources. The Nanchang project was implemented by URC,which isresponsible for the reimbursement of the loan. Therefore, it was not possible for other project stakeholders to usethe unused loan proceeds to enhance the integration experience, and these aspectshad to be cancelled. For instance, if thebus company had been an implementation agency, they could have used some ofthe loan proceeds to provide additional feederservices or other elements to enhance the integration experience. However, ahigher implementationcomplexity due tomultiple implementation agencies needs to be weighed against its potential benefits.
P132157 | TN-Oases Ecosystems and Livelihoods Project | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2020 | 2020 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/282941593552743491/text/Tunisia-TN-DELP-Oases-Ecosystems-and-Livelihoods.txt | http://documents.worldbank.org/curated/en/282941593552743491/pdf/Tunisia-TN-DELP-Oases-Ecosystems-and-Livelihoods.pdf | The ICR (p. 23-24) included several lessons learned which were adapted by IEG: Combining adaptationmeasures to strengthen oases resilience and economic measures to strengthen peoples resilience are critical forsustainable biodiversity protection and conservation. This project aimed at reducing poverty through micro-projectsand supporting alternative livelihoods while also protecting and preserving a variety of species and habitats. This could have apositive impact on the project outcomes sustainability. Building capacity and raising awareness is criticalfor the sustainability of newly introduced innovative agricultural techniques and practices. In this project, localmunicipalities and grass-roots organizations were involved in planning and implementing activities resulting in a higher chance ofproject outcomes being sustainable and creating conditions for scaling up activities at national and regional levels.
P132173 | Rural Water Supply and Sanitation Project for Low Income States | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2020 | 2022 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/846681629853884604/text/India-IN-RWSS-for-Low-Income-States.txt | http://documents.worldbank.org/curated/en/846681629853884604/pdf/India-IN-RWSS-for-Low-Income-States.pdf | The following lessons were adapted by IEG from the ICR.Proper task sequencing could be a key factor forinstitution building. Infrastructure investments and institutional building can create a positive and mutually reinforcingcycle if they are sequenced properly. In this project, pressure to launch the procurement of large-scale infrastructure withoutsound institutional capacity led to significant implementation delays and negative incentives to abandon time-consuming capacitybuilding activities. It would have been better to put greater emphasis on client-led reform prior to, and during projectpreparation and embed time and resources for institution building in water scheme contracts.Weak projectmanagement could significantly underminethe achievement of project objectives. In this project, chronicunderstaffing and underqualification of PMUs at national, state and district levels negatively impacted many aspects of theoperation including safeguard compliance, procurement efficiency, implementation speed, and technical quality of infrastructure.Major reasons include the clients lack of priority and prior commitment towards project management, scarcity of qualifiedhuman resources, optimistic implementation arrangements at appraisal, and the Banks ineffectiveness in addressing theissues.The lack of a sustainability framework prior to investments could contributeto substantial risks todevelopment outcomes. For Investment Project Financing, once funding is approved, the focus tends to shift toinfrastructure development and it becomes often more difficult to change or establish necessary policies. In this project, Assamwas the only state that established an OM policy for rural water schemes. Lack of OM policies in other three states ledto lack of financial resources required for OM and posed a significant risk to sustainable operation of water schemes.
P132208 | TG - Economic Recovery and Governance Credit 6 | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/963911498229133804/text/ICRR-Disclosable-P132208-06-23-2017-1498229128526.txt | http://documents.worldbank.org/curated/en/963911498229133804/pdf/ICRR-Disclosable-P132208-06-23-2017-1498229128526.pdf | The ICR presents several useful lessons. These include the importance of selectivity and consensus building for reformprograms.(i) Selectivity: Policy operations in situations of limited government capacity should avoidoverly ambitious reforms across many areas. In this case, the lack of government capacity manifested itself as one of the majorobstacles to achieving development outcomes. The EGGC6 should have been more selective in its support for reforms, given thegovernments capacity constraints.(ii) Consensus Building: A consultative approach can help buildconsensus for difficult reforms. As recognized in the ICR, many of the results under the EGGC6 were not achieved due to the lack ofa critical mass of support for reforms. Vested interests were identified as a key risk during appraisal, but the Program failed tobuild a broad consensus among stakeholders in support of reforms.IEG also agrees with the ICR that Bankoperations can be enhanced when there is good cooperation with other DPs, taking advantage of respective comparativeadvantages.
P132210 | Second Growth and Competitiveness Grant | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest |  |  | This review draws the following three lessons (with the first two from the ICR):1. Inadequate consultation with allrelevant stakeholders increases the risks that draft legislation submitted as a prior action will not pass opportunely to achievethe expected effects. The draft mining code and anticorruption legislation suffered from inadequate vetting, resulted in lateapproval, and had no impact during the program.2. In low capacity environments, objectives to buildcapacity may be more appropriate than objectives to achieve the long-term welfare goals of added capacity. Capacity building mayhave been what the less ambitious DPO4 program objectives (to enhance the governments ability in three areas) aimed for.However, such enhancements need to be measured. For example, enhanced government ability to reduce costs in agriculturerequires evidence to link reforms to cost reductions. Implementing reforms (by capitalizing the input fund) alone is not evidenceof the expected outcome.3. Mitigation of risksis unlikely tobenefit from mitigation measureswith impacts that are dependent of the risks that the measures aim to mitigate. For example, reforms to expand cotton productionwill hardly qualify as a mitigation measure for the risk of unanticipated production and/or price shocks on cotton production.
P132210 | Second Growth and Competitiveness Grant | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/494031533935601565/text/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.txt | http://documents.worldbank.org/curated/en/494031533935601565/pdf/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.pdf | 6. Lessons â€¢ When political risks are high and capacity is strained, design is better focused on a few key priorities. This series covered too many areas, and some key binding constraints were not addressed. The series might have been more successful with a sharper focus on more realistic objectives accompanied by a simpler design. â€¢ The success of budgetary support depends on the suitability of the instrument to the country environment. In a context of political turbulence and uncertainties about the government's ability to undertake long term reforms, the World Bank could have ended the programmatic series after the third operation and made the fourth operation a stand-alone. Alternatively, the World Bank could have implemented a series of stand-alone operations after the second programmatic series when it became apparent that the political and policy environment was rapidly changing. â€¢ Lack of clarity on the respective roles and responsibilities of central and local governments and of the private sector undermines policy actions. It is important to ensure that there is a shared vision and that the need for reform is recognized and accepted by all parties. In this case, there was a lack of clarity among different stakeholders during implementation of the reforms on decentralization and fertilizer distribution. â€¢ When M&E is not adequately resourced or implemented, there can be delays in the identification of problems and the application of remedies. M&E weaknesses can be compensated by leveraging information available elsewhere, or through specific impact assessments and perceptions surveys. â€¢ There may be a trade-off between the promise of continuous and predictable financing, urgently needed in times of crisis, and the strength of the reform program. In Burkina Faso the emphasis was on continuous financing even when reform performance was waning. â€¢ The lack of broad consultations with stakeholders when the World Bank is designing a complex reform program could lead to unsatisfactory results. In this case, the lack of consultations with an important stakeholder association (the Confederation Paysanne du Faso) on fertilizer distribution affected the achievement of results of one of the first objectives. Also, some development partners and civil society organizations had limited knowledge of the reforms pursued in the G&C series. â€¢ Consultation with all important stakeholders is critical to inform program design. In this case, development partners, civil society organization, and academia complained to the PPAR mission about inadequate consultation by the World Bank. â€¢ Inadequately resourced implementing agencies will likely be unable to carry out agreed reforms. Under-resourcing may be an indication of low government commitment, which needs to be addressed through policy dialogue. It is also important to ensure that agencies have appropriate technical capacity and systems in place, and that potential political obstacles at the local level are being addressed.
P132216 | Burkina Faso Public Sector Modernization Program | Western and Central Africa | Burkina Faso | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | PforR | 2016 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099200006102219559/text/P13221604a212c08a08729011745acbc984.txt | http://documents.worldbank.org/curated/en/099200006102219559/pdf/P13221604a212c08a08729011745acbc984.pdf | Several lessons are drawn from the ICR.Public administration reforms are likely to be more effective whensituated in a longer-term perspective. In this operation, the PSMPs longer-term strategic planning provided aperspective on reform that allowed it to introduce results-based interventions that, through their outcomes, were likely toencourage and facilitate further reforms.Good understanding of context and a gradual approach to change canenhance outcomes, especially in an uncertainenvironment of fragility, conflict and violence. Theoperation was adapted: rather than initiating major restructurings, adding new activities, or extending the operation, the Bankteam moved to close it and develop a new operation.A dedicated Treasury Special Account (TSA) can serve as astrong fiduciary risk mitigation measure for PforRs.The TSA was instrumental in securing PSMPs resources andprotecting them from reallocation, which can be a risk for PforR funds that are fungible in the state budget and therefore can bediverted to national emergencies.In discussing lessons of experience, the ICR could have been more specific than was thecase.Building public trust was a strong motivating factor behind project design and a political necessity for thenew government that was seeking to build public confidence in it by strengthening institutions. The program sectors werechosen as weak performing ones and ones with a direct and tangible impact on the public.
P132234 | Pakistan: Punjab Public Management Reform Program | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | PforR | 2014 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/408111579621944092/text/Pakistan-Punjab-Public-Management-Reform-Program.txt | http://documents.worldbank.org/curated/en/408111579621944092/pdf/Pakistan-Punjab-Public-Management-Reform-Program.pdf | The following lessons are drawn from the ICR.Implementation can benefit from governance-sectorreform momentum and political ownership. A key factor for success of this operation stemmed from the fact that it wasintroduced to explicitly support a wider-scale governance reform program in Punjab, with the main components aligned to thisbroader initiative.A results-based operation can provide the right financial and non-financialincentives to deliver intended results. This PforR aimed at improved transparency and resource management rather thanmeasurable qualitative or quantitative improvements that might have been difficult to attribute to the Program. PDO indicators wereassociated to realistic targets, and Disbursement-Linked Indicators (DLIs) were carefully selected to provide the right incentivesfor achieving the intended development outcomes, in a context characterized by implementation challenges and capacity constraints.The Program focused on strengthening the institutional capacity of a few key agencies, which helpedensure that cross-cuttingreforms were effectively implemented.
P132268 | Solid Waste Management OBA Pilot in West Bank | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/914761550771240811/text/West-Bank-and-Gaza-GPOBA-Solid-Waste-Mgt-West-Bank.txt | http://documents.worldbank.org/curated/en/914761550771240811/pdf/West-Bank-and-Gaza-GPOBA-Solid-Waste-Mgt-West-Bank.pdf | The ICR provided several key lessons from the project operations, as well as those from parallel, complementary operations. Onlythose lessons that relate to the project ICR, slightly edited, are noted below: Performance based payments(subsidies) need to be simple and easy to understand even as it include quantitative methods. In this case, the project usedformula based and quantitative approach to calculate and disburse payments and subsidies. The project-specific MIS monitoredperformance and fostered transparency. Transparent, frequent, and clear communication by the implementing agency with itsconstituents, offering MIS generated quantitative evidence allowed for opportunistic adjustments to achieve the PDOs. Updates,changes in subsidy disbursement criteria, changes in incentives, and review of peer performance, fostered a competitive spiritamong participant local governments to improve. The implementing agency fostered participation by its constituent localgovernments, consulting and engaging them to hear concerns and adapt local practices into viable options to ensure success inachieving the PDO, such as in the design of a reward system that allowed poorer performers a chance to improve and earn paymentsmissed in past disbursement periods. There was also the appropriate co-billing arrangements where waste charges are allowed to rideon utility bills such as electricity or water bills, even building permits, and in some cases, marriagecertificates. When introducing a new approach or solution, first time participant local government units require astrong, well designed capacity building program backed by adequate resources. Design could cover technical, hands-on training,customized advisory services, and small size workshops. For example, in this case, limited funds delivered one trainer per 60participants. There was no standard cited but conventional practice points to less participants per trainer for better materialabsorption and retention. Another example is that workshops and consultations revealed differing jurisdictions over assets and avariety of workable options needed to be considered Flexible, innovative, just-in-time approaches serve to strengthenpartnership efforts with the private sector to work in a fragile state such as the West Bank. The ICR did not specify an examplebut the procurement process noted above (see Section 10 (b) Procurement) provided a window to that creativity. Another wasintroducing exclusionary clause in adjusting aggregated, governorate level performance targets for subsidy payments to avoid themoral hazard of rewarding local governments who perform poorly but benefit from the better performers. Still another was the use of restructuring to adjust the incentive scheme because performance was outpacing initial targets in the second year. TheWorld and the IFC collaborated by acknowledging the strengths that each institution brought to offer a fragile environment anintegrated, cost effective, and participative solid waste management service delivery. The World Bank constructed the landfill andhelped to establish the institutional capacity to manage a sustainable sanitary disposal service, while the IFC, drawing on outputbased assistance to operate and maintain the landfill and disposal facilities, structured the private sectorparticipation.
P132270 | First Phase of the Central Asia Road Links Program | Europe and Central Asia | Central Asia |  |  | Infrastructure | Transport | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/955241605768774683/text/Central-Asia-Central-Asia-Road-Links-Phase-1.txt | http://documents.worldbank.org/curated/en/955241605768774683/pdf/Central-Asia-Central-Asia-Road-Links-Phase-1.pdf | The ICR draws the following three main lessons from the experience of implementingthis project, presented with someadaptation of language:1. The regional dimensions of a project needto be fully considered for a project withregional IDA financing. ThePDOs in this project aimed at improving connectivity between the Kyrgyz RepublicandTajikistan, along priority cross-border links in the Batken Oblast. However, all the priority links were in theKyrgyzRepublic. The border issues and performance of the two countries were not part of the project design, and the onlyevidence of cross-border collaboration or dialogue between the two countries was in the regional forum.2. Theabsorptive capacity of the implementing agency or in the country contextneeds to be carefully considered atdesign.This project aimed at administering a user satisfaction surveythrough an Information Technology (IT)system. The implementing agency had neither the financial nor the human resources foradministering such asurvey. Useofstandard sociological surveys and focus group discussions shouldbe considered in countries with remote areas, whereeither the internet penetration is weak, or the local authorities do not have the capacity or resources to maintain high technologysupport.3. The sustainability of project investments, especially in road sector projects, needs to be carefullyframedat design. The High -Speed - Weigh -in Motion (HSWIM) equipment and road maintenance equipment are necessaryto improve road operations and maintenance practices. While the original cost of this aspectwas US$1.7 millionbyproject completion, the actual costwas five times the original amount at US$8.2 million. Spending ofthismagnitude should be accompanied by activities that support a long-term view in managing road assets, including throughaxle load control and capacity building to maintain a functional Road Asset Management System (RAMS).
P132277 | Jiaozuo Green Transport and Safety Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099205105232237430/text/P132277005386903e0803702c52b14c5de0.txt | http://documents.worldbank.org/curated/en/099205105232237430/pdf/P132277005386903e0803702c52b14c5de0.pdf | The ICR (p. 27-28) included several lessons learned, which were adapted by IEG: For complex projects withmultiple cross-sector activities and implementing entities that are not familiar with Bank processes, it is critical that the Bankallows for sufficient learning time before project implementation starts. In this project, the PMO did not have anyexperience with Bank processes. Even though the Bank team provided trainingin critical areas, disbursement and implementationwere delayed resulting in the need to extend the projects closing date. To ensure sustainability, theprojects design needs to include interventions in several areas that address the complexity of reducing traffic fatalitiesThis project included a variety of different activities such as improving existing infrastructures and enforcementcapacity, providing road safety training and building institutional capacity allowing to tangle the challenge from differentangles. The government needs to ensure adequate consultations with key stakeholders at all levels, including atthe community level, which is critical for a smooth and successful project implementation. In this project, the Bank teamdid not foresee that the construction of the interchange at north square of railway station would be challenging even though theland was state owned. However, neighboring residents were using it for recreational activities and no replacement was nearby. As aresult, the project activity had to be cancelled.
P132289 | Kali Gandaki A Hydropower Plant Rehabilitation Project (KGAHPRP) | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/802451530304931845/text/Nepal-Kali-Gandaki-Rehab.txt | http://documents.worldbank.org/curated/en/802451530304931845/pdf/Nepal-Kali-Gandaki-Rehab.pdf | 1 . The sequencing of preparation activities made it necessary to secure the services of consultants to developthe detailed technical design of the project before proceeding with the major rehabilitation works. The delay in procuring theseconsultants led to a cascade ofproject delays that eventually resulted in the project closing before the majoractivitieswere completed. While the consultancy was essential since the rehabilitation could not begin without thetechnical designs, the process may have been expedited if NEA carried out advance procurement for the consultants prior to Boardapproval. This could have enabled the consultancy to be in place by the time the project was approved/made effective, or at leastprovide a head start to the process which may have limited the delays.2 . When aninterdependent set of investments are being made, it is important to maintain financial support until completion of all tasks orprojects can be exposed to considerable risks to achieving or sustaining results. From an investment perspective, once theMIVs and the turbines were rehabilitated, the project reached a stage where the remaining activities had to be completed or itwould expose the project to greater risks of sustaining damages to the newly installed assets. Given these circumstances, thedecision not to extend the project closing date, especially considering that the detailed project designs were completed byclosing, could lead to additional delays as NEAwas placed in a position where it has toseek alternative sources offunding. Such delays can expose the newly installed assets to further damage from sedimentation, cavitation and floating debris,since these interdependent issues are not addressed sufficiently addressed as intended by the project.
P132306 | NIGER COMMUNITY ACTION PROGRAM PHASE 3 | Western and Central Africa | Niger | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/920721619442848176/text/Niger-Niger-Community-Action-Programm-Phase-3.txt | http://documents.worldbank.org/curated/en/920721619442848176/pdf/Niger-Niger-Community-Action-Programm-Phase-3.pdf | The ICR (p. 32-33) included several lessons learned, which were adapted by IEG: Conducting aninstitutional financial and economic assessment, especially for a lengthy Bank engagement, is critical for ensuring itssustainability. Niger, as the worlds poorest country, faces a very weak fiscal position, which will not allow thegovernment to support the continuation of local development once project support ends. Therefore, identifying futurefinancing options before the 16 years long program closed would have been essential to ensure the sustainability of projectoutcomes. When the project is aiming to provide opportunities for women it is critical, during projectpreparation, to assess project activities in terms of gender inclusion. While this project supported women withcertain micro-projects, it did not invest in capacity building for women in critical areas such as financial management andbudgeting.
P132308 | National Immunization Support Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099080723181029867/text/P1323080a26f4b0d90bf2f00b8bcca0facb.txt | http://documents.worldbank.org/curated/en/099080723181029867/pdf/P1323080a26f4b0d90bf2f00b8bcca0facb.pdf | The ICR (pp. 28-29 and pp. 67-68) provided several lessons and recommendations, including the following lessons re-stated by IEGReview: Partnerships and coordination among development partners can provide effective support to the immunizationagenda within one project mechanism. Under the project, this resulted in more than five years of joint investment decision-making,supervision, policy dialogue, and effective coordination. In addition, using the buy-down mechanism of the Bill and Melinda GatesFoundation helped the country in alleviating incremental debt obligations during a period of turbulent economiccircumstances. The strategic focus on strengthening the immunization program at subnational levels isresponsive to province-specific development challenges and allows the central government and development partners to promote acontinued engagement with provinces that showed lagging performance, and to jointly identify options for advancing universal healthcoverage, including immunization. The availability of timely, reliable, and verified data on immunizationcoverage helps in identifying weaknesses in immunization programs and in guiding corrective actions. Under the project, MEfindings were instrumental in identifying under-performance in urban centers and slums, resulting in intensified efforts andoversight. The institutionalization of a national pooled procurement mechanism for vaccines, based onprovincial demands, can ensure a continuous and uninterrupted supply of competitively pricedvaccines. Fostering community-led approaches, links, and mutual trust can facilitate the expansion ofimmunization service delivery and demand generation. The project facilitated community engagement mainly through Civil SocietyOrganizations working in low-coverage catchment areas. The project also sensitized political bodies and religious leadership tohelp in advancing immunization efforts.
P132314 | MSME Development Project for Inclusive Growth | Middle East and North Africa | Jordan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099305003292270859/text/P132314012078304809ae9007c7c6758a29.txt | http://documents.worldbank.org/curated/en/099305003292270859/pdf/P132314012078304809ae9007c7c6758a29.pdf | Three lessons are drawn from the ICR (pages 35-36), with someadaptation, and a fourth is added by this ICRReview.A line of credit operation can be finely targeted to expand access to finance for underserved segments ofthe MSME market. This project had distinct targets for MSMEs owned by young entrepreneurs, MSMEs owned by womenentrepreneurs, and MSMEs located in governorates outside of Amman. All the targets, set at appraisal and confirmedwiththe additional financing, were exceeded at project closing. The project also had an indicative target for term finance,which was exceeded at closing, and, following the additional financing, put a special focus on MFIs and micro enterprises, with theresult that the number of MFIs participating in the line of the credit and the number of micro enterprise loans exceededexpectations. The design and performance of this project indicates that a line of credit operation can be targeted at veryspecific beneficiaries.An institutionally and operationally capable apex institution is vital to the success of afinancial intermediary lending operation. In this project, the CBJ, the countrys monetary policy making bodyand bank supervisor, acted as the apex institution for on-lending by commercial banks, Islamic banks, and MFIs to MSMEs. Thecentral bank was selected because it had market knowledge and a good governance structure, was a sound institutionwith acompetent Board, had strong management capacity, and therefore could be credibly responsible and accountable, according to theICR. The apex institutionis credited with the strong performance of the project, which disbursed US$47.7 million, 95.4percent of the original loan, within a year after project start. The choice of an apex institution is not necessarilyconfined to acentral bank but, rather, must consider a capable and credible institution with good governance andstrongmanagement.Close coordination among donors working on different but related parts of SME developmentbenefits an access to finance project for MSMEs. In this project, the line of credit for MSMEs was complemented bytechnical assistance provided by multi-donor trust funds managed by the Bank, including the InfoDev, Enhancing GovernanceandStrengthening the Regulatoryand Institutional Framework forMSME Development ProjectTransition Fund, andWorld Bank-IFC MENA Regional MSME Technical Assistance Facility. The project also benefitted from related operationsfunded by other donors and supporting the MSME sector, including for a partial credit guarantee fundand advisory services fora microfinance strategy.Careful economic analysis of an MSME line of credit operation helps to better assess thenet benefit of the operation to the economy. In this project, the Bank and the government missed an opportunity tosystematically assess the economic efficiency of the line of credit operation. A formal cost-benefit analysis would have beendemonstrablyinformative considering the achievement of the project in nearly doubling the target expansion in the volume ofMSME lending and exceeding the job creation goal by one-and-a-half times. The assessment would have also been valuable ininformingthe design and choice of results targets of future line of credit operations that distinctly focusonunder-served sections of the MSME sector, including youth- and women-owned or managed enterprises and those operatingoutside of economic capitals and business centers.
P132317 | Philippine Rural Development Project | East Asia and Pacific | Philippines | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 2015 | 2026 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/735071619040172496/text/Philippines-Philippine-Rural-Development-Project.txt | http://documents.worldbank.org/curated/en/735071619040172496/pdf/Philippines-Philippine-Rural-Development-Project.pdf | The ICR draws the following lessons from the experience of implementing this project, with some adaptation oflanguage:1. Reforms that are not imposed from the top, but based on the experiences of subnational entitiescan aidin securing stakeholder commitment.This project departed from the earlier projects in the Philippines in that LocalGovernment Units (LGUs) were involved in prioritizing the infrastructure investments that could best further their interests. Thishelped in securing their commitment. Further the incentive framework through attractive cost sharing between the Department ofAgriculture was central in encouraging the participation of LGUs.2. Having comprehensive and publicly-accessible(web-based) Operations Manuals which were validated and understood by field level staff can be helpful in facilitatingproject startup. The experience from this project technical/managerial follow up service support needs to be built into projectdesign to help ensure the sustainability of newly established enterprise.3. The strict adherence to all-weather standardsin the construction of farm-to-market roads and subsequent Operations and Maintenance, while substantially more expensive toconstruct than gravel roads, can be useful in countries that are vulnerable to natural disasters (such as typhoons).Inaddition, IEG adds the following lesson:1. A well-designed and implemented ME system that produces regularmeaningful results is extremely helpful in tracking high level outcomes that determine the trajectory and priorities of projects.Where this is done well, the justification for further funding and component priorities becomes easier and the impact is amplified.Using multiple approaches to triangulate results amplifies where there are successful investments and areas where changesmight be made. This is extremely useful in very large programs across multiple regions.
P132381 | Third Export Development Project (EDP III) | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099010924093037235/text/P1323811a6d2530281a2cb134907b301cc3.txt | http://documents.worldbank.org/curated/en/099010924093037235/pdf/P1323811a6d2530281a2cb134907b301cc3.pdf | The following are lessons learned from the ICR with some paraphrasing: For complex projects with multistakeholders, a performance-based finance model can help leverage beneficiaries commitment. The EDP III projectinvolved high number of activities, many reform actions and many beneficiaries which created challenges to implement. To improvebeneficiary commitment and achievement of project results, a performance-based financing mechanism with disbursement conditions(i.e., legal amendments related to Dhamen Finance; operationalization of the use of TOS and Smart Gate by STAM; implementation ofdeveloped investment plans by TFDCVC in the case of EDP III) can be included in the project design. Extensiveconsultation and external expertise support to beneficiary institutions can help increase ownership of innovative approaches andcan ensure their sustainability.While EDPI and II relied on consultants for the management of the matching grantcomponent, EDP III targeted a better balance between operational efficiency and long-term sustainability and was designed to beimplemented by government entities (CEPEX). Although this contributed to sustainability it was partially effective as a result ofimportant implementation challenges related to the lack of stability in CEPEX management, the COVID-19 pandemic, insufficientstaffing within the Tasdir+ team. In this regard, adequate consultation for ownership, sufficient assessment of implementationconstraints of beneficiary entities as well as identification of mitigation measures and mobilization of specific expertise tocompensate for capacity constraints can support ownership of innovative approaches by the beneficiary institutions and theirsustainability. Alignment of export development support mechanism with the national export strategies andanchoring it in government institutions can produce additional benefits to existing and/or future national programs and mechanisms.Within the scope of EDP III, the matching grant program was integrated into CEPEX, and lessons learned from theimplementation of this program can contribute to improvement of existing programs under CEPEX as well as development of new ones.For example, lessons of targeting beneficiaries in sector and market segments aligned with the countrys export developmentstrategy; supporting medium-term development plans presented by companies; and improved reach of MSME firms to avoid capture bywell-connected firms can feed Tunisias existing or new programs. In the context of political,institutional change and in the presence of capacity constraints, keeping the number of activities and stakeholders limited andfocusing on the activities with the highest priority can help full achievement of the projects objective. TheEDP III addressed a wide range of reform agenda involving high number of stakeholders. The political instabilities and highturnover experienced in many of the beneficiary institutions resulted in implementation delays and even cancellation of significantnumber of activities. The project with fewer selected activities and beneficiaries would have been more suited to the political andinstitutional context and achieve its planned objective.
P132405 | Niger - GPE - Support to Quality Education Project | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/716521591644358445/text/Niger-NE-Support-to-Quality-Education-Project.txt | http://documents.worldbank.org/curated/en/716521591644358445/pdf/Niger-NE-Support-to-Quality-Education-Project.pdf | The following lessons are drawn from the ICR and summarized by IEG: The provision of technical assistanceto the Ministries through an AMO (support to contracting authority) arrangement can be effective both in ensuring projectimplementation andin building national capacity.The staffing of an AMO with knowledgeable experts (includingfor procurement, financial management and ME) helped ministries manage the complex tasks required, including overseeing theconstruction of classrooms and curriculum reform implementation, among others. The financing ofscholarships for girls who live far from secondary school can bea viable, cost-effective approach to improving the retentionof girls in schools.Much cheaper than building boarding schools and/or covering the cost of transportation, thesescholarships finance the costs of girls staying with host families. Additional interventions (e.g., interventions to support lifeand social skills and remediation support) may further enhance girls retention rates. The establishment of arobust ME system is important to enable the assessment of efficacy of investments in pedagogy and capacity building, amongothers.While the projects ME system did support the tracking of progress towards PDO achievement, someaspects of the project could not be assessed.These included the impact of school feeding, andtraining and capacitybuilding provided to the ministries and teachers. The factoring of acountrys evolving fragility andconflict situationinto a projects design and implementation can support more context-appropriate design and moreaccurate cost estimates.Nigers fragility and conflict situation havedeteriorated substantially over thelast few years.Construction costs in low security areas will incur higher costs (as in the case for the Diffa region).Anumber of creative interventions may be appropriate for girls safety and security (including technology and lodging with hostfamilies), in areas where schools may be closed due to insecurity or where girls cannot go safely to school.This callsforflexibility in project design in fragile contexts.
P132418 | Efficient & Sustainable City Bus Services | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099310103142233912/text/India000Effici0ble0City0Bus0Service.txt | http://documents.worldbank.org/curated/en/099310103142233912/pdf/India000Effici0ble0City0Bus0Service.pdf | The ICR developed the following useful lessons:Engaging with the state governments, along with the national andcity governments, should be considered in future projects concerned withbus service efficiency and sustainability.Astrong need was expressedfor the creation of aState Technical Unit to bring the necessaryattention andfocus to the projectand to support citiesin planning, design, financing, and management of bus services. The Bank couldalso consider using the Program for Resultsapproach when dealing with multiple cities under same operation to implementsimilar interventions as a part of existing or new Government programs.Centralized procurement, standardizedtemplates and formats can all help fast-track procurement and ease the processes for medium-sized cities with weak procurementcapacity. Under ESCBS, the cities with limited ability and capacity each went through a steep learning curve for theprocurement of equipment and ITS/MIS. Having a centralized or standardized procurement process, with recommendations on systemdesignspecifications and a list of empaneled vendors, should be considered forfuture similar projects and programs.Thiswould also eliminate the individual negotiations that the cities may have to navigate (onspares, training, etc.) infuture, and will help standardize and bring about economies of scale.Lack of continuity of officials andteams can affect project outcomes and consistent capacity building efforts are critical for successful implementation. Theproject lost valuable time due to the frequent transfer of officials and the consequent efforts needed to restart the dialogue withthe Bank. Even the key positions in the operations teams (e.g., traffic manager) were either absent/ vacant or were affected byhigh attrition at both city and state levels. The lack of adequate qualified staff with continuity is in large part due to thepolicy and regulatory environment in Indian cities not yet assigning adequate priority to urban bus transport. The Bank has alreadymade good progress in furthering the policy dialogue and needs tocontinuefor the long-term sustainability of thesector.A two-pronged approach to developing capabilities and the enabling environment can helpto leverageprivate sector support. ESMAP showed greater emission reduction by involving private operators in the training. Efforts oncapacity building for the private sector (such as consultants, vendors, and service providers) in bus operations, maintenance,ITS/MIS, designing/planning arecritical and help in scaling up impact. At the same time, the creation of an enablingenvironment by putting in place appropriate risk sharing anddispute resolution mechanisms, timely payments, and acollaborative approach with private operators can help support much needed market development to achieve the necessary scale up inavailability of bus services in the country.The project shouldexplicitly include the dissemination of theresults in the four demonstration cities. While dissemination was envisaged under the training and TA activities, itwouldbe a good idea for similar demonstration projects to include the dissemination of results as part of projectactivities.
P132425 | Sustainability and Competitiveness DPL 2 | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2014 | 2018 | ICRR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | IEG concurs with the main findings and lessons in the ICR, inter alia:(i) Small island settings areparticularly challenging for information technology enabled reforms. In the case of Seychelles, capacity and connectivity gapsdelayed and made difficult system development and adoption.(ii) The quality of the Banks overallengagement is crucial, including how various instruments such as analytical work, policy-based lending, technical assistance andinvestment operations, along with the work of other partners, reinforce and complement each other.(iii)Progress is possible in small countries with limited capacity using cross-sectoral DPL series, as long as care is given in definingappropriately scaled targets.
P132431 | BJ-Forest & Adjacent Land Mgmt Addit Fin | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2013 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/258681542038027710/text/Benin-BJ-Forest-Adjacent-Land-Mgmt-Addit-Fin.txt | http://documents.worldbank.org/curated/en/258681542038027710/pdf/Benin-BJ-Forest-Adjacent-Land-Mgmt-Addit-Fin.pdf | The following three lessons were the most apposite among the six included in theICR,1. Invest in participatory bottom-up consultative approaches to forestmanagement. For example, the project invested in developing participatory community forest plants and creating aparticipatory boundary marking process. While these processes took additional time and required technical specialists, the extendedapproach improved collaboration and decreased conflict (ICR, para. 92).2.Targeted and specific interventions may be more effective than broad-reaching approaches. For example, this projectsought to work on 19 gazetted forests. However, in forested areas where there was a higher level of concentration of projectactivities, the deforestation rates were lower (ICR, para. 93). This project experienced an over-stretched budget and wastherefore unable to support all the operational costs and surveillance missions. For future projects, consider focusingimplementation activities in targeted areas.3. Income generating activities require technical supportfor effective implementation. For example, the income-generating activities of this project were successful at increasingincome, empowering women, and reducing pressure on forests. However, for these activities to be successful, technical support inthe form of basic accounting, marketing, and disease prevention (agriculture and livestock raising) is required (ICR, para.95).
P132443 | District Heating Efficiency Improvement Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2020 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/610681635168390203/text/Moldova-DIST-HEAT-EFFIC-IMPR.txt | http://documents.worldbank.org/curated/en/610681635168390203/pdf/Moldova-DIST-HEAT-EFFIC-IMPR.pdf | The ICRidentified a number of appropriate lessons, andthis review has takenthree of them which arereformulatedbelow.(i) A business-minded leadership, supported by a committed Government,can steerchange that can concomitantly contribute to solvingtechnical and managementissues of a failing public heatingcompany.The projectsucceeded to rehabilitate and modernize a failing district heating system, and toimprove the reliability,the quality of heating services, and the financial viability ofa public heating company.Acritical factor of success was a business-mindedleadership which accomplished not only a smooth corporate restructuringprogram, but also to rapidly shift the company culture from a supply-driven to aconsumer-driven orientation. The company newleaders brought together key sector stakeholders, including the Government, and this helped to improve the service quality and toreassure the DH consumers in the long-term viability of theDH system.(ii) A negotiated and fair tariffsystemcan contribute toa sustainable investment in a regulated heating system.To ensure thesustainability of the investment in a heavily regulated heating sector, it is important that the investment lending be conductedhand in hand with the adoption of a fair tariff systemachieved througharegulatory dialogue between the IFI, theutility, the regulator and the Government.The tariff reforms supported by the project wereachievedbecauseofnegotiation and agreements amongthe GoM, the regulator (ANRE), the TE management andthe international financialinstitutions. Without this concerted outcome regarding the adoption of a fair tariff system, the project could not have reached theprogress toward the expected objectives.(iii) Acommunication campaign targetingthe generalpublic of beneficiaries aboutanewcentralized heating system and reconnection to the DH networkcancontribute to the success ofan investment and reform project.The importance of the communication campaign andpublic outreach has been underlined by the projects results. Similar to other Bank-funded projects, there was a strong needto increase the level of end-users awareness and understanding of costs and financing mechanisms associated with the DHsupply and the efforts made by the utility to optimize the service delivery and ensure reliable heat and hot water supply. To thisend, the projects citizens engagement interventions helped ensure that consumers are aware of the available financingoptions and interests of the DH customerswere fully taken into account.
P132490 | Kyrgyz Global Partnership for Education (GPE) - 3 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2018 | 2019 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201291559056180678/text/Kyrgyz-Republic-Kyrgyz-Global-Partnership-for-Education.txt | http://documents.worldbank.org/curated/en/201291559056180678/pdf/Kyrgyz-Republic-Kyrgyz-Global-Partnership-for-Education.pdf | Lessons drawn by the ICR, adapted by IEG: A strong and clearly laid out resultschain, translated into a strong results framework and ME design, can aid project performance and reporting onachievements. In the case of this project, the well-focused results chain with attributable outputs and outcomes, andrelevant and measurable indicators on access and quality, led to effective monitoring and feedback loops. Community-basedkindergartens can be a low-cost alternative to preschool education when the goal is to expand access in remote areas. In thecase of this project, local contributions via facilities and teacher salaries helped to lower costs, and assessments showed thatlearning outcomes improved in poor areas with this alternative model.
P132500 | Myanmar National Community Driven Development Project | East Asia and Pacific | Myanmar | IDA | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099020524135023699/text/P1325001b96a1b00f1908e1e3887e1adc2e.txt | http://documents.worldbank.org/curated/en/099020524135023699/pdf/P1325001b96a1b00f1908e1e3887e1adc2e.pdf | The ICR formulated several useful lessons. The most relevant ones, with IEGs modification, are asfollows:Sound donor coordination under one program through a common platform can be an effective way to achievepositive results on community driven development projects, particularly in FCV environments. The project established acommon platform for CDD that other development partners could buy into. The NCDDP was able to bring together the UK, Italy andJapan in an on-budget government program by providing quality assurances and building effective implementation systems that madethe project the largest donor-supported government program in the country. Given the highly fragmented donor landscape and lowgovernment capacity in Myanmar at the time of project preparation, this was a notable accomplishment.CDD projectsdesigned in FCV contexts may benefit from working with independent facilitating partners (FPs) to support project implementation,where they serve a dual purpose of augmenting government capacity and providing a more neutral or trusted interlocutor forcommunity engagement. In the case of Myanmar, where there was little government experience and visibility with communitiesand local development and limited capacity outside of the implementing departments national office, working with FPs provedinvaluable in getting the project up and running at scale relatively quickly. The NCDDP also provides helpful lessons onoutput-based contracting of such FPs (to help reassure governments that they are getting value for money for these larger servicecontracts) and partnership arrangements between government and FPs that helped to enhance project implementation processes further.A corollary to this lesson is the importance of investing in government capacity to both oversee the delivery of services by suchkey FPs and to take on key functions over time as appropriate.Specific conflict mitigation mechanisms andapproaches are necessary for working in conflict contexts, particularly in those areas where control is contested between the stateand non-state actors. The NCDDP used a range of approaches that proved successful, these included: i) conducting aconflict assessment prior to the final selection of participating townships; ii) early up-front and ongoing engagements withnon-state political actors in these areas where work is planned; iii) recruitment of local staff for community facilitator roles toensure local knowledge (including language and culture) and networks are integrated in project implementation; iv) conflictsensitivity training for local government and community-based project staff; and v) allowing time and opportunities to build trustbetween the government and the EAOs, which in the NCDDP happened by allowing certain areas of the township (villages or villagetracts) to opt out of participation for a number of years until EAOs gained confidence in the value of the project. Theseapproaches enabled project access to areas restricted to other government programs. When security challenges emerged, the projectresponded flexibly by suspending and, where possible, resuming actions to ensure the safety of project stakeholders.
P132510 | Mauritius Second Private Sector Competitiveness DPL | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/381321467992518785/text/ICRR14870-P126903-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/381321467992518785/pdf/ICRR14870-P126903-Box394823B-PUBLIC.pdf | Among the lessons highlighted in the ICR are:Built-in flexibility allows the government to adapt the reform program as needed over time. The programmatic series acknowledged areas where the country made significant efforts beyond what was expected. In the lagging areas, the necessary building blocks were put in place to ensure that the reforms take place progressively as in the case of the restructuring of the Development Bank of Mauritius where consensus for reform existed but the timeline was extended to take into consideration negotiations with another government on the selection of a strategic advisor. The knowledge package accompanying the DPL contributes to reform planning and implementation. The Mauritian Government had recently cancelled two Investment Loans but continued to request the Bank for technical assistance, analytics and policy dialogue. This brings to the forefront the issue of Middle Income Countries that can raise finds on the open market but still wish to maximize access to the Bankâ€™s advisory services, analytics and technical assistance without the associated administrative requirements of lending instruments. This calls for continuous improvement of Bank lending instruments to suit the requirements of this â€˜emergingâ€™ client segment.Collaboration facilitates learning. The programmatic DPL series was prepared in tandem with the Public Sector Performance (PSP) DPL series and led to an integrated dialogue with the client and joint internal processing and targeting for better results. This program involved the tripartite collaboration among WBG sectors â€“ FPD, HDN and PREM - under a tight time line. According to the ICR, â€œsimultaneous preparation and processing of the two operations allowed the teams to cross-fertilize ideas and foster partnership in the interest of a higher quality product for the client.â€
P132515 | Support to the Subnational Transport Program Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2024 | 2025 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons are based on the ones presented in the ICR, with some adjustment to language:If theprojects objective and PDO indicators are not well aligned to the activities financedby the World Bank and to what theProject can effectively leverage, there is a risk that the project will a) not be able to achieve the set targets (as theyare irrelevant to the project) and b) will not be able to measure the outcomes, as was the case here. In the present case,the project was an Investment Project Financing (IPF) of limited amount aimed at supporting a much wider program, but the WorldBank had limited leverage on program activities that were not directly connected to what it was financing. This resulted in arestructuring that substantially revised the ME framework.A robust analysis that considers the implementingagency capacity and the contributions of World Bank technical and cross-support teams could ground expectations better and maycontribute to higher readiness for implementation for infrastructure projects. The lack of an established methodology andidentified interventions were the main source of implementation delays of this project. It made the Project vulnerable to politicalinfluence and hindered its readiness for implementation. To improve this, a transparent and participatory process for roadselection, with clearly defined criteria based on objective attributes can be established at appraisal. This could ensure thatinterventions are identified and earmarked in a timely manner, reducing the risk of delays.Ifa focus onclimate change resilience is not ensured in the project design and implementation, there is a high probability that project roadsmay not be maintained and may deteriorate quickly. This is particularly important in countries like Peru that are highlyvulnerable to frequent and intense climate-induced hazards and have difficult landscapes. Future project designs may focus onpromoting and innovating in rural road maintenance schemes, enhancing the resilience of rural road infrastructure, andincorporatingmechanisms for effective disaster risk management to ensure long-term sustainability of the network. Routinemaintenance planning and funds may be included in the project design to ensure sustainability of theinvestments.Developing road-specific safeguard documents for the first round of investments at preparation maycontribute to smoother safeguards processes in the cases where there are gaps between the World Bank safeguards and nationallaw. Such discrepancies may cause confusion and delay implementation if a strategy to solve the controversies is notdeveloped. This Project suffered several delays due to the implementation of the safeguards and the discrepancy between World Bankand national laws. Additionally, having a clear and documented process for approving subproject-required safeguard documents andterms of reference can help streamline the review and approval.
P132562 | CN-Hubei Xiaogan Logistics Infrastructure | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099112123134558566/text/P1325620dfe2390780b83d00ac5a35af1ca.txt | http://documents.worldbank.org/curated/en/099112123134558566/pdf/P1325620dfe2390780b83d00ac5a35af1ca.pdf | The project offered the following lessons (ICR, paragraphs 90-93): An integrated logistics service centerwithmodern technology may improvelogistics efficiency. In this project,Chinasrole in globaltrade was hampered byits lagging logistics sector. Xiaogan and other Chinese citiesaimedtomodernize theirlogistics sector. Before the LIMC was built, the functional departments of AEZ werein different places causingoperationalinefficiencies in the Xiaogan Logistics Park. In this project, the traffic command center used ITStoadjusttraffic signalsbased on traffic. This use of the ITS increasedroute efficiency and minimizedidlerunning/emissions at traffic lights. The Logistics Public Information Platformenabled matching cargo demandwithtrucking supply,minimizing empty return trucks, and sharing trucking capacity going in the same direction. As aresult of these innovations,Xiaogan LP has attracted more businesses (although no data provided). The government is beginningto support further development of the sector - the inclusion of integrated logistics service centers and the use of ITS (noevidence provided). The Project Management Officehas reached out to the small and medium-sized companies in the parktopromote the use of the functionalities of the Logistics Public Information Platform, for example,shared use of deliverytrucks, and cargo matching on return journeys (but no survey or report to indicatehow many have used, started to use, orintend to use the functions). The PMO iscollaborating with the supplier of the new technologies to recruit and trainengineers for the continued operation of the systems after the project closing. Usingbig data from thetraffic command center on the Logistics Public Information Platform may improvethe efficiency of the park and businessdevelopment in Xiaogan.In this project, the AEZ originallyreliedon manual data collection and datacollected by other enterprises. The AEZ wasto tap the digital delivery, the ITS and associated technology, and the LogisticsPublic Information Platform to develop a new ME framework for the park based on data collected by the systems suchasaverage travel time, rates of empty trucks that continue to run, and warehouse usage. Decision-makers would use the data toinformpolicy, leading to a path where logistics centers usebig data for ME. A strong governmentcommitmentand those of other stakeholdersmay contributeto a successfulproject, notwithstanding challengesposed by thepandemic. In this project, initialimplementation was delayed due to low capacity,landacquisition, compensation, procurement, and contract management. In addition, flooding and the COVID-19 pandemic further delayedimplementation being nearthe Wuhan area. A change in project leadership on the World Bank side helped bolster confidence incompleting the project. An in-depth analysis of recent experience with the relationshipbetween higher costestimates at appraisal and canceled funds during implementation may be useful. In thisproject,US$35 million incost savings led to cancelled funds. Cost estimates used at appraisal werehigh and competitive bids led to savings.Thepractice of using the higher cost estimate for infrastructure investmentsin the World Banks China portfolio may need to be revisited.An in-depth analysis of recent similar experiences other recent China projects may benefit futureoperationsnot only for the China program, but also for other countries.
P132585 | ID-TF HEALTHY AND BRIGHT GENERATION (GENERASI) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/787881571763994291/text/Indonesia-ID-TF-GENERASI-PROGRAM.txt | http://documents.worldbank.org/curated/en/787881571763994291/pdf/Indonesia-ID-TF-GENERASI-PROGRAM.pdf | The ICR offered 7 lessons from the project operations that could benefit future similar projects. Three of these lessons arepresented below with minor editing: Both men and women have important roles to play in deciding how toimprove maternal and child health and nutrition. In this project, a gender strategytargeted an increase in maleparticipation in maternal and child health and nutrition. This gender strategy included clear target indicators for male and femaleparticipation, and was widely disseminated to all stakeholders. Frequent reminders gavestakeholders strong signals that thebenefits from improved maternal and child health and nutrition could be achieved sooner or increased by involving both male andfemale parents in the decision making process. This effort could also be a useful approach to breaking down gender barriers indelivering basic social services. Community driven development (CDD) may be a useful platform to deliver healthand education services by integrating bothdemand and supply side interventions. In this project, these servicesweredelivered to the village and community levels in which they targeted the remaining non-service users in poor, ruralcommunities. On the demand side, this project empowered community and village residents by giving them training and capacitybuilding tools to increase the effectiveness of service delivery. These included social accountability tools such as socialmapping, community scorecards, and social monitoring. These tools improved their ability to influence howthecommunityallocated village funds for basic social services and allowed villagers to target those who had notbeenserved before.On the supply side, incentives were offered to service beneficiaries and providerstoincreaseavailable services and their utiilzation(ICR, paragraph 36). Usingperformance based grants allows communities to set priorities based on local conditions and constraints. In this project,the performance based nature of the grants motivated village cadres to target improvements in enrollment in primary and secondaryschool. At the time of implementation, non Generasi investments in village education programs increased. The targets were reachedbut updating the original targets and providing additional incentives for good performance could have convinced the community toincrease allocation for the sector, improving outcomes. Periodic review of targets could also be an opportunity to validate theeffectiveness of the incentive system of a performance based grant. The experience in this project showed that the link betweenincentive and performance called for a better understanding by the community participants.
P132616 | Emergency Support to Education For all Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/460571544637854791/text/Madagascar-MG-Emergency-Support-to-Education-for-Al.txt | http://documents.worldbank.org/curated/en/460571544637854791/pdf/Madagascar-MG-Emergency-Support-to-Education-for-Al.pdf | The ICR (p. 34) provided several useful lessons and recommendations, some of which are adaptedhere: Negotiating the details of partnerships with other entities during project preparationis beneficial for avoiding implementation delays later in the project. This project planned to collaborate withUNICEF for the purchase of school kits. Due to higher prices for school kits in the UNICEF catalogue, the project ended upprocuring them throughinternational competitive bidding,resulting in a one-yeardelay. The mid-term review can be an important point to assess gains and reorientactivities where appropriate. In this case, the mid-term review provided an opportunity for increased overallambition due to exchange rate gains, expanding the projects geographic range and the scope of activities likely to have themost impact on achievement of development goals.
P132617 | Chad Education Sector Reform Project Phase 2 | Western and Central Africa | Chad | IDA | FCS | Human Development | Education | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099430008222232746/text/P13261703e8e7e0800b9c50d3ddbc17ce4e.txt | http://documents.worldbank.org/curated/en/099430008222232746/pdf/P13261703e8e7e0800b9c50d3ddbc17ce4e.pdf | The ICR (pp. 39-40) offers several insightful lessons, including:Mobile payment systems can bea viableapproach to providing timely payments to teachers and other service providers even in fragile contexts, and especially whenbeneficiaries are scattered across vast geographic areas. This project was instrumental in establishing a system formobile payments that included a database that has increased efficiency in payments without duplication.Developmentof digital platforms for education can start effectively with relatively small first steps, such as the digitization ofupper-secondary school materials through virtual libraries. The experience gained through this projects development of digitalmaterials for upper-secondary school science education allowed the education ministry and school librarians to support on-linelearning during the COVID-19 pandemic, and is being used in theBank-financed follow-on project to begin to digitizein-service teacher training content at the primary level.
P132621 | Yunnan Highway Asset Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050523194040345/text/P1326210a573f2063099d406a7d2b4ea1b5.txt | http://documents.worldbank.org/curated/en/099050523194040345/pdf/P1326210a573f2063099d406a7d2b4ea1b5.pdf | The review draws the following lessons from the ICR, with some adaptation of language.1. Management commitmenthelp in successfully implementing the project. In this project, the Yunnan Highway Bureau (YHB) maintained a stableprojectmanagement team during implementation and YHBs top management provided dedicated support in developing and operatingthe integrated management system, the Road Asset Management System (RAMS), the asset valuation manual and accounting guidelines.With this support, the consultants completed several rounds of large-scale consultation to identify business needs and proceduresand carried out trial operations prior to roll-out.2. Packaging contracts and conducting market surveys can helpin managing procurement. This project packaged goods contracts in big size, which attracted large suppliers and aided inintensifying competition. The final prices of the contracts were much lower than the estimated costs. The lesson is that carryingout a market survey before preparing bidding contracts, can help in providing a solid base for setting technical and qualificationrequirements.3, Comprehensive interventions may be required to achieve efficiency of road assets management.This project introduced the road assets management approach and included activities to strengthen YHBs weaknesses inservice delivery. This approach incorporated value management into YHBs asset management, the data collection instrument,monitoring value, demand analysis and fund allocation and training YHB staff on road maintenance. Given that this project wasprepared alongside an ADB financed project, the Bank preparation team sought to add value by focusing on road asset managementapproach, rather than supporting road rehabilitation or other maintenance works excepts piloting selected innovative maintenancetechnologies. These interventions together improved the overall efficiency of the YHBs asset management.
P132623 | Sustainable Livelihoods and Adaptation to Climate Change | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/752331607368256315/text/India-IN-Climate-Change-Livelihoods.txt | http://documents.worldbank.org/curated/en/752331607368256315/pdf/India-IN-Climate-Change-Livelihoods.pdf | The ICR included six lessons. The following three lessons are emphasized with some adaptation oflanguage: ME design for a climate-change related project needs to includea clear definitionofresilience and a methodology to measure it ina standardized manner to adequately assess outcomes.Theprojects experience demonstrated thatdespite the Banks efforts, it was not easy to arrive at an appropriatemethodology to define and measure a farmers extent of climate resilience and the ideal target value for a project to aspirefor. The methodologies to define resilience in terms of adoption of key practices or to measure the extent of resilience orrecovery after an adverse weather event are not evident. Research efforts to define resilience and measure it in a standardizedmanner would help future projects in design, monitoring and project-end evaluation. Post completion support isrequired for a climate-change related project toensure sustainability of the project technologies with a focus on landlessfarmers.Despite intensive and focused efforts in this pilot, farmers reported unwillingness to continue somepractices beyond the project period. Further research is required to understand the reasons and to provide support in the future.Around a third of the farmers in this project were landless and able to practice only diversification as a resilience measure sincethey had not leased-in farm lands. Future climate resilience projects may consider including non-farm livelihoods, in particular tosupport landless farmers better and to provide more holistic resilience. Weather forecasting throughmobiletechnology combined with climate resilient practices are critical elements to improve the sustainability oflivelihoods.Weather forecasting through mobile phone applications enabled women farmers to adjust their farmingschedule and better manage farming operations of their crops. This, combined with the application of climate resilient farmingtechnologies improved the resilience of farming communities to sustain their livelihoods.
P132652 | TAJIKISTAN AGRICULTURE COMMERCIALIZATION PROJECT | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061823211547288/text/P13265203325210f50a13805f59e801963a.txt | http://documents.worldbank.org/curated/en/099061823211547288/pdf/P13265203325210f50a13805f59e801963a.pdf | Of the lessons noted in the ICR the following two are highlightedin this review with some editorialchanges.Continued input needto be provided to the agri-food sector so that access to finance and newtechnologies is maintained to ensure that development is sustainable.This project shows that external support to theagricultural sector in lower income countries, where resource poor small farmers predominate and agro-enterprises are poorlyequipped and generally do not use state-of-the-art technology, usually requires at least two full project cycles to ensuresustainability and a follow-on project is already underway. Initially weak public sector capacity, especially in agriculturalextension, which is alsotypical in many low-income countries, also requires strengthening or finding private sector extensionalternatives to weak MOA extension services.The scope for greater import substitution of foodstuffs indeveloping countries is easier and a higher priority in the medium term than export marketing.Theend-of-project impact assessment report (page 25) found that 98 percent of ACP beneficiaries did not export their products to othercountries, which is consistent with the fact that market opportunities are good in domestic markets in developing countries, andinternational market opportunities (particularly for landlocked countries) are very challenging to access. To compete in exportmarkets, providing greater value addition (as opposed to exporting raw or unprocessed products) is a priority, as pointed out bythe Deputy Minister of Agriculture inthe Ministryresponse to the ICR. Selective publicsupport to specificcommodity value chainsmay be appropriateto strengthen regional and eventually internationalcompetitiveness.
P132665 | India: Enhancing Teacher Effectiveness in Bihar | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | PforR | 2015 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099205012142110567/text/India000IN0Bihar0Teacher0Education0ICT.txt | http://documents.worldbank.org/curated/en/099205012142110567/pdf/India000IN0Bihar0Teacher0Education0ICT.pdf | Lessons drawn from the ICR (pages 31-33) and adapted by IEG: Under the PforR instrument, the Action Plan agreedupon with the government can identify actions (with expected completion dates) that are deemed necessary for achieving projectoutcomes, but should not be a substitute for project readiness. In the case of this project, although the Action Plan items wererelevant and accurate, they were in fact measures that were necessary fora successfulproject launch and initialimplementation period; instead, despite early expected completion dates, they were not fulfilled until two years into the projectperiod.Along similar lines, the Borrowers procurement requirements were satisfied under the PforR component, but the IPFcomponent required compliance with more complex Bank procurement procedures, and these were met with significantdelays. Incremental technological innovations topush small reformsin a large-scale education systemcanhavea higherlikelihood of success compared to more disruptive technological changes. In the case of this project,developing simple apps (for example, monitoring teacher attendance) and online systems (for example, applications forteacher training courses) enabled incremental behavior changes and actions that contributed to project outcomes.
P132667 | Benin Youth Employment Project | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/431581591803740154/text/Benin-BJ-Youth-Employment-FY14.txt | http://documents.worldbank.org/curated/en/431581591803740154/pdf/Benin-BJ-Youth-Employment-FY14.pdf | The ICR (pp. 34) offered several lessons and recommendations, including the following lessons restated byIEG: A strong communication strategy, decentralized delivery, customized content aligned to target groups,andincentives for maximum participation such as provision of childcare and subsidies for lunch and travel are importantfactors for determining the success of employment training programs such as this youth employment project inBenin. Early joint preparation by Bank and Client to develop operating modalities for the project facilitatescoordination and fund flows. Project background work e.g. beneficiaries surveys help ensure that projectwould address context-specific constraints.
P132698 | SKILLS DEVELOPMENT PROJECT | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/939221603901500583/text/Sri-Lanka-Skills-Development.txt | http://documents.worldbank.org/curated/en/939221603901500583/pdf/Sri-Lanka-Skills-Development.pdf | The ICR (pp. 31-33) included several key lessons learned, adapted here by IEG: Identifying a stablelocation for basing theproject management unitso that it is not affected by ministerial and leadership changes has apositive impact on project implementation. In this project, theproject management unitwas movedamongeight different ministries and was subject to continuous changes in leadership at various levels resulting in implementation delaysand significant loss of institutional memory. Also, due to these changes, the dialogue with the government stopped, resulting in atwo-year stalemate and the cancellation of IDA resources. Tying appropriate incentives to targets to ensuretimely achievement of DLIs is critical in a results-based operation. In this project, all DLIs were of equal weightindependent oftheir significance for achieving policy reforms. Process-linked DLIs were achieved much more easily thanoutput- or outcome-linked DLIs. Linking the output-outcome results to higher value amounts during the final years of implementationmight have helped to place greater emphasis and incentives among different actors to achieve the desiredresults. Coordinating and cooperating with other development partners positively affects strengtheningproject outcomes and avoiding duplications. This project and a project by the ADB were prepared at the same time. Whileboth entities agreed to coordinate, there were significant differences in the DLI design and project result targets. This resultedin inefficiencies and ultimatelya government notto usethe Banks financing for theprojectstechnical assistance component. Also, the government having to work with two different DLI designs might haveadded an extra administrative burden.
P132709 | TN-Governance, Opportunities and Jobs DPL-2 | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons are drawn by IEG:A complex transition requires careful considerationof trade-offs between ambition and feasibility in project design. In Tunisia, political pressures and economic challengescalled for broad multi-sectoral interventions, but success might have been greater with a more careful assessment of institutionalcapacity in key reform areas.Reforms are especially prone to being undermined by their weakestlink. In Tunisia, employment reforms were affected by the lack of ownership of the employment agency. In such instances,other actors, for example non-governmental organizations, can be helpful through outsourcing.
P132742 | Afghanistan - Second Skills Development Project | South Asia | Afghanistan | IDA | FCS | Human Development | Education | IDA | IPF | 2013 | 2021 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099140009282267111/text/P13274208ab3380dc09710005be6e793c13.txt | http://documents.worldbank.org/curated/en/099140009282267111/pdf/P13274208ab3380dc09710005be6e793c13.pdf | The ICR (pp. 27-28) offered several insightful lessons, including:Successful implementation of technical andvocational education projects hinges on design that matches ambition with realities of project context. In this case, eventhough the Ministry of Education had limited capacity and the DMTVET was struggling to deliver basic services, the original projectset higher-level goals for accreditation, certification, and demonstrating increased earnings of TVET graduates. Setting the bartoo high can dilute a projects focus on more fundamental, achievable results.Introductionofresults-based financing can produce desired results only when the counterpart fully understands the modality. Inthis case, capacity at all levels was insufficient to benefit from the RBF incentive structure, a situation that deteriorated evenfurther when the project came under new institutional arrangements and leadership.Institutional capacity buildingcan be usefully incorporated as a TVET project objective in contextswhere the skills development sector isrelativelynew and the foundations for sectoral development are not yet set. In this case, capacity was overestimated at the outset,and the project struggled throughout its lifetime to match capacity with planned activities and outcomes.
P132748 | Developing Market-based Energy Efficiency Program in China | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2017 | 2024 | 2025 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Technicalassistance (TA) projects could generate significant catalytic impact with limitedresources.The experience in the project has been that small grants can play an importantrole innudging implementation to greater efficiency. Even small grants, when nimble and effective, have a complementary effect to largelending programs. Theinherent flexibility of TA projects ensures that theycould respond more quickly to a dynamicpolicy environment. Thus, small TA projects can cost-efficiently support the achievement oflarger and long-term impacts, suchas theenergy efficiency and environment programs in China in this particular case.Alignment of localdevelopmental needs with global public goods can elicit strong buy-in from key stakeholders.The projectsuccessfully demonstrated the ability to align local development needs such as air pollution management with the objectives ofglobal public goods such as reduction in coal consumption and carbon reduction. Given that the single biggest issue at appraisalwas Chinas air pollution crisis, this alignment ensured that there was a strong buy-in for the project from localstakeholders and government officials. The World Bank was able to successfully do this by positioning the project as a climatemitigation initiative withGEF support from its climate change window that would enable the delivery of significant GHGemission reductions.Monitoring, reporting and verification systems (MRVs) can play an integral role in thesuccess of both energy efficiency and emissions trading schemes.MRV systems play an important role inenabling an efficient market-based mechanism since it provides the necessary credibility to the reporting of GHG emissions. Theproject has worked with the Chinese government in improving energy consumption MRV and developing market-based energy consumptionrights trading scheme. Other complementary initiatives such as the expansion of the market for China Certified Emission Reduction(CCER) and development of the green electricity certificate (GEC) have helped enhance the market-based pricing mechanisms. Thesehighlightthe importance of coordination of MRV stakeholders and the need to integrate MRV systems across EE and emissionstraining schemes to achieve positive outcomes.
P132750 | Project for Strengthening the National Rural Transport Program | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/870281614622962798/text/Nepal-SNRTP.txt | http://documents.worldbank.org/curated/en/870281614622962798/pdf/Nepal-SNRTP.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The design elements need to directly address thekey challenges associated withroadmaintenance activities.Given that maintenance of rural roads often receives inadequate attention due tolack of prioritization andinadequate fundingin developing countries, the project adopted a maintenancefirst approach, through sequencing project activities with road maintenance activities taking precedence overroadrehabilitation activities. Further, the design leveraged a small amount of IDA financing to mobilize several multiples ofgovernment spending towards road maintenance.2. The estimated costsat design needs to be updated atappraisal. In the case of this project, the selection of roads was made two years aftereffectiveness. Thecosts of these activities proved to be much higher than expected at appraisal. This necessitated rather significant reduction intargets.3. The design of rural roads project should aim at providing jobs for local communities.Inthis project, routine maintenance groups were mobilized for routine maintenance predominantly from the local areas near each roadand trained for providing routine maintenance. In this project, the impact study showed that 2,700 maintenance workers from localcommunities received temporary employment. This included 64% women and 37% indigenous people.
P132754 | AGRICULTURE PRODUCTIVITY AND NUTRITION IMPROVEMENT PROJECT | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060324223025874/text/P1327541daf18909f189c4108e40ec59a7c.txt | http://documents.worldbank.org/curated/en/099060324223025874/pdf/P1327541daf18909f189c4108e40ec59a7c.pdf | The ICR included five lessons, the following three are emphasized with some adaptation of language:1. Projectsaiming to support rural livelihoods could benefit froma comprehensive cross-sectoral approachcomprising irrigation,agriculture, and nutrition. The experience of the project showed that such approachprovided synergistic benefits interms of agricultural productivity and food and nutrition security. The project also demonstrated the value of implementing projectactivities aimed at all households in the same geographical areas, that is, in the selected WUAs, the same AAs and samevillages.2. To increasing agricultural production and improve food security, irrigationrehabilitation interventions should be clearly linked to on-farm agricultural support. Farmers were able to obtainhigh-quality seeds and, in conjunction with improved irrigation water supply, training, and agriculturalmachinery. Thisenabled farmers to increaseproductivity and change their cropping pattern to higher-value crops. It is noted that there are481 WUAs in the country, with only 31 covered by the project, leaving considerable scope for future activities.3.To improvenutrition of vulnerable households,the SHG methodology canbe a successful approach to introduce qualityseed and increase productivity on household plots. Self-help groups (SHGs) are comprised of 5-7members, 90% of which are expected to be women. The key characteristic is that SHGs are a small group of womenwho work together effectively as demonstrated through the project experience.This approach enabled theimprovement ofnutrition for vulnerable households, especially for women. Good social mobilization and season-long trainingwere an essential part of this methodology. Similar programs will be valuable in the future to ensure that projects represent allhousehold members and women-headed households.
P132757 | Second Shared Growth Credit | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2017 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | There are three key lessons of general applicability that may be drawn from the preparation and implementation of these threeoperations:Especially in a difficult country context, it is advisable to limit the programs scope and objectives soas to involve the minimum necessary number of sectors, ministries and agencies. In this case, the wide range of reform measures andcorrespondingly large number of concerned agencies stretched weak governmental coordinating capacity beyond its limits. A relatedlesson is that, where coordination is required, the Ministry chiefly responsible for program implementation should have theauthority, experience and connections to carry out its task effectively.While it is acknowledged that the impact of mostDPOs would only be felt in the medium term after the closure of the program, ME design can nonetheless advantageously includeintermediate indicators of progress in meeting objectives that can be more closely related and attributable to the prior actionsand other measures supported by the program.Exclusive reliance on prior actions alone may lead to an erroneous impressionof the programs achievements. In many cases, sustained follow-up is required to make the reforms effective, and it isimportant that program monitoring take this fully into account and implement remedial action where necessary. Examples from thisprogram include the need to survey enterprises regarding visits by taxation officials, and to carry out physical inspections ofimportant procurement contracts.
P132768 | Pernambuco Equity and Inclusive Growth DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2013 | 2015 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/782201469050748761/text/ICRR-Disclosable-P132768-07-20-2016-1469050742931.txt | http://documents.worldbank.org/curated/en/782201469050748761/pdf/ICRR-Disclosable-P132768-07-20-2016-1469050742931.pdf | The review highlights the following lessons from the ICR:World Bank support gives a strong, centralexecuting agency clout to both request monitoring reports and demand results, while at the same time playing a catalytic role inimproving its relations with other executing agencies. The EIG DPL facilitated the establishment of partnerships,working together towards a common goal, between SEPLAG and the other executing agencies. Implementation support teams shouldidentify opportunities for such partnerships, which are facilitated by synergies across DPL components in terms of themes (such asME in this DPL case) and long-term engagements with the client through different, but consolidated, operations. They shouldalso support each agencys programs as well as empowering a central agency in the coordination acrosscomponents.If Government priorities are well established, then aligning a DPL with them makessense. The EIG DPL was aligned fully with the Governments priorities, and its Results Framework wasdeveloped, in the words of one official, based on priorities for both the Government and the World Bank, with indicatorsthat were not superimposed, but rather selected from among those of the Government.
P132775 | China: Gansu Rural-Urban Integration Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099033123080025285/text/P1327750bb2c600ab0978a0aa3d09527273.txt | http://documents.worldbank.org/curated/en/099033123080025285/pdf/P1327750bb2c600ab0978a0aa3d09527273.pdf | The ICR draws the following lessons from the experience of implementing this project, with some adaptation oflanguage.1. A simple and flexible project design that reflects a countrys priorities helps in addressingchallenges during implementation. The roads selected in this project were based on the priorities identified in the Wuweiand Linxia plans. Having the selection criteria established in the PAD as opposed to fixed selection of roads provided thegovernments with flexibility to select interventions during implementation while adjusting to changingcircumstances.2. A careful consideration of environmental and social risks is particularly needed in roadprojects. In this project, the implementing agencies took steps to reduce resettlement impacts and consulted with theProject Affected Persons to refine road alignments to reduce overall project risks. These risks were lowered further byprioritizing roads with lower environmental and social impacts.3. The project underscored the importance ofcapacity building activities. The experience of this project demonstrated that even in countries with very well-developedinstitutional capabilities such as China, technical and management capacity can vary across levels of government, agencies andjurisdictions. For example, technical capacity of the local transport bureaus was limited at the county-level in Gansu and theproject responded to addressing the institutional capacity gaps in a targeted manner.
P132786 | BJ PRSC 9 Poverty Reduction Support Cdt. | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/760541528388810575/text/Benin-BJ-PRSC-9-Poverty-Reduction-Support-Cdt.txt | http://documents.worldbank.org/curated/en/760541528388810575/pdf/Benin-BJ-PRSC-9-Poverty-Reduction-Support-Cdt.pdf | The ICR (pp. 30-31) highlights several useful lessons with which IEG concurs,including:Political economy considerations are essential to the timing, sequencing, and level ofambition of reform. In this case, there was inadequate consideration of internal resistance and vested interests inopposition to governance and cotton sector reforms. Better consideration of these political concerns may have led to a moregradual approach, keeping in mind the need to construct a legislative, institutional, and regulatoryenvironment conducive toreform. It is also important to note that the process of policy dialogue around governance and broad political economy issuescan have longer-term impact, outside the results framework of a single operation or series ofoperations.Political cycles often create risks of deteriorating macroeconomicframeworks. In this case, the 2016 election involved electorally timed interventions in fiscal policy and somereversal of structural reform. Timing the implementation of reform measures to align with political cycles can mitigateagainst reversals and keep authorities engaged in agreed reform processes.IEG adds the followinglesson:Attribution of observed results can be ensured only through carefully designed prioractions. In this case, particularlyin relationto PPPs and agricultural diversification, the prioractions were inadequately specified to lead to intended outcomes.
P132786 | BJ PRSC 9 Poverty Reduction Support Cdt. | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2022 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/746991630422633137/text/Benin-Ninth-and-Tenth-Poverty-Reduction-Support-Credit.txt | http://documents.worldbank.org/curated/en/746991630422633137/pdf/Benin-Ninth-and-Tenth-Poverty-Reduction-Support-Credit.pdf | 3. Lessons 3.1 Relevant lessons from previous operations need to be taken on board in the design of new DPF operations. The design of this PRSC series appears to have not taken on board several important lessons identified by World Bank staff from previous operations. Some of them include (i) the importance of a targeted reform agenda, where the development objectives are clearly defined and the results indicators are well specified; (ii) the need for a realistic understanding of political economy and the associated risks related to high resistance to change within the government and by vested interests; and (iii) the importance of limiting the scope of the program, given limitations in administrative capacity. 3.2 Prior actions need to be substantive, that is, be critical to reforms with value added. Prior actions under PRSC-9 were quite soft, meaning that they could not credibly be associated with significant contributions to the objectives, and several triggers (for approval of PRSC-10) on governance and cotton sector reforms were either revised or moved to subsequent operations and later dropped altogether. 3.3 The World Bank should design projects with a clear understanding of the likely winners and losers; failure to do this raises the probability that projects are not implemented as planned or sustained over time. An understanding of political economy must encompass the private sector and other informal centers of power. If internal decision makers are to take informed risks, the World Bank should be candid in its ex ante assessment of the fundamental forces with direct involvement or interests in the reforms supported. 3.4 Distributional impact analysis from DPF-supported reforms should inform the design of operations. There is a lack of evidence on whether the DPF-supported reforms were pro-poor ex ante and ex post because the series did not conduct distributional impact analysis.
P132821 | AFR RI-Central African Backbone SOP5 | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Digital | Digital Development | IDA | IPF | 2015 | 2022 | 2022 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099155006262292474/text/P13282109c27f304109b4f0f8fd7a341b70.txt | http://documents.worldbank.org/curated/en/099155006262292474/pdf/P13282109c27f304109b4f0f8fd7a341b70.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Political economyconsiderations need to be carefully considered while designing disbursementconditions. It is important to take into account politicalrealities in the country before complex and potentiallyunimplementable reforms are included as disbursement conditions in an investment project. The imposition of sub-optimal conditionscan reduce flexibility and limit implementation options. This may be particularly relevant in fragile environments and in afast-evolving sector with high private sector participation like the ICT sector.2. An Investment Project Financing(IPF) may not necessarily be the right vehicle for adopting major sector reforms. Theenactment of a new telecom lawis subject to may uncertainties beyond the direct control of an investment lendingproject. OtherBankinstrumentssuch as theDevelopment Policy Operations (DPOs) and Disbursement-Linked Indicators (DLIs), may beappropriate foradvancing sector reforms.3. Ideally Bank financing for investments need to beused in areaswherecommercial incentives are insufficient to attract large-scale private investments. In this project, by the time the linkwas built, grant funding was used for constructing a long route that was commercially viable.
P132833 | Transport Connectivity and Asset Management Project | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099101824130531103/text/P132833-79454847-e45b-4721-a139-77f48a951ddc.txt | https://documents.worldbank.org/curated/en/099101824130531103/pdf/P132833-79454847-e45b-4721-a139-77f48a951ddc.pdf | The following lessons have been derived and summarized from the ICR, with additions by IEG after discussions with the Bankteam:Sufficient awareness and capacity to manage and overseesafety at work sites can helpavoid orreduce the risk of accidents.The project initially had only one dedicated person responsible for environmental andsocialactivities in the central PMU because of hiring restrictions. In this period, three roadfatalities occurred.Since then, the GoSL has increased its staff to manage and oversee safety at work sites and implemented all actions required by theBank. Among others, this included to traincontractors on OHS and raise awareness on the importance ofsafetyatwork sites,adopt work site safety guidelines, implement internal traffic control plans, and carry out worksitesafety audits. This helped avoid further fatalities at work sites. It underscores the importance of diligent management,vigilant monitoring, and raisingawareness of work site safety in infrastructure projects.Insufficientattention to capacity strengthening when working at the subnational level mightjeopardize project implementation and putproject outcomes at risk.In its design, theproject put little focus on activities to strengthen the capacityof the provincial road agencies to implement the project and more effectively manage road works in general. The project design, asrestructured in 2019, only included a couple of studies at the provincial level, not aimed at strengthening the road agenciescapacities, and referred tothehiring of consultants to support project implementation. As a result, the project hadinsufficient consultants to support contract management and ensure compliance with OHS requirements, and serious problems occurred.The Center of Excellence, not mentioned in the 2019 restructuring paper,was a success, but it may not be retained due tofiscal constraints. Hence, theproject is not likely to sustain the capacity gains in the provincial road agencies without anydonor-financed follow up activity.A carefully designed capacity strengthening program for subnational road agencies, focusingon key activities, such as contract management or road work planning, mighthave help avoiding some of thesepitfalls.Proactively adapting project interventions to address the evolving needs of a country and a sector canhelp advance projectimplementation andsustainoutcomes even in a volatile environment. Flexibility inadjusting the scope of the project to address the changing government priorities and thecrisis response needsandadjusting implementation strategies to overcome the challenges of the volatile environment helped thisprojectprogress in its implementationand achieveoutcomes during a highly turbulent time. This illustrates the importanceof(i) adopting an adaptive and flexible approach in project implementation, (ii) responding proactively and rapidly toaddress evolving needs, and (iii) increasing Bank support and strong collaboration between the Bank and thegovernmentduringchallenging times.The project is anexample of the Banks ability to demonstrate thelevel of flexibility and proactivity necessary to adapt to evolving and urgent needs.Althoughdifficult,contract enforcement can helpcomplete civil work contracts in difficult situations. After COVID,several civil works contractors did not perform as expected in terms of speed and quality. Cancelling a non-performing road workcontract is a difficult decision for a road agency because contracting the works again can take a year. In this period, thecommunity remains with uncompleted road works,which can even cause road safety risks. Prices are also likely higher. Inaddition, contractors often have access togoodlegal support and might start and win lengthy court proceedings.Inthis project, because of the insistence of the Bank team, the GoSL took strong actions and cancelled a few the non-preformingcontract. This send a signal to contractors, and in several other cases, the GoSL was able to convince non-performing contractorsto subcontract part of the remaining works and so complete the contracts successfully.Astrong championand continuous Bank presence and support can help ensure that a road asset management system is successfully implemented and used.In thisproject, the head of the road asset management division was a strong and passionate believer in road assetmanagement. In addition, the Bank team continuously and strongly insisted on the need for asset management and supported the RDAcontinuously during the implementation of the system. The Banks perseverance in this area also helped convince the RDA toformalize the road asset management division, allocate adequate funds, and use the system as their basis for roadplanning.
P132846 | Forests and Community | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2022 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099072723103527449/text/P13284600e077c00b092430f3fef05943b0.txt | http://documents.worldbank.org/curated/en/099072723103527449/pdf/P13284600e077c00b092430f3fef05943b0.pdf | IEG draws the following lesson:When a project that is restructured with considerable downsizing of its scopedoes not update its Economic and Financial Analysis, the economic efficiency may be difficult to measure ex-post, as the originalEFA no longer represents the baseline of comparison. In this project, the lack of an EFA at mid-term review also hinderedthe ability to decide on investment priorities based on data, eventually leading to additional project restructurings and thereallocation of resources among disbursement categories.The following lessons drawn fromthe ICR, with someadjustments made by IEG, are deemed particularly relevant:When sufficient political will and institutionalcapacity are present, projects with a strong community participatory planning component with new target populations are more likelyto be successful. In this project, not all Provinces had the same disposition towards the involvement of indigenous andcampesinos communities. Those with better disposition and higher technical capacity were more successful in facilitatingparticipatory planning.An appropriate level of precision and detail of a projects investment mayenhance the projects execution rate and achievement. Carefully defining the geographic scope of the interventions andfocusing the project implementation on a narrow but thoroughly detailed and known set of investments strongly aligned with the keyexpected results (instead of offering a broad, untested, or loosely defined set of investment alternatives) is essential to keepthat balance, particularly in cases of constrained implementation capacities. This is supported by the fact that once the projectscope was reduced, the execution rate and achievement of results significantly improved.
P132873 | Hebei Rural Renewable Energy Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR included four lessons. The following three are emphasized with some adaptation of language:1.Anintegrated approach, involving both planning feedstock supply and nurturing market demand through careful consideration of theevolution of the policy environment and the market may contribute to effectively demonstrating and realizing a rural circulareconomy. The project experience demonstrated that the enterprises achieving sustainable operations are: (a) an existinganimal farm business and have additional backup feedstock in the vicinity, (b) able to integrate the facilitys productsales/applications with local development needs and priorities, (c) actively nurturing the sales channel and market demand of theproducts, and (d) mindful of policy and market changes and proactively adjust their operational strategy (such as the feedstock mixand corresponding pretreatment equipment), accordingly.2.Multi-sectoral coordination for, and alignment ofpolicy design may ensure achievement of the intended outcome. During the implementation of the project, governmentpolicies gradually shifted away from promoting biogas facilities as a source of clean energy towards the multiple benefits ofbiogas, including generating biofertilizers for land fertility and productivity. Lack of timely sectoral coordination and clearimplementation rules or programs for the promotion of multiple benefits of biogas during the policy transition period createdconfusion for local governments and undermined the policy viability and financial performance of the biogas facilities as designedfollowing earlier policies.3. Financial incentives can helpenergy-producing facilities adopt newtechnologies and reachfinancial viability. Financial incentives provided to the facilities, especially during theinitial several years to de-risk their investment, largely determine the willingness of facilities to participate and adopt newtechnologies and practices. In addition, profitability is critical for the new technologies and practices to be sustained andupscaled in Hebei and nationwide. Policy reform to guarantee long-term incentives (instead of program-based subsidies, whichusually last for only a few years) will provide confidence to the sector and promote scale-up. Policies to expand sustainablefinance, such as an eco-compensation policy that pays for the methane reduced by the facilities or expanded opportunities to enablevoluntary carbon markets to purchase such carbon credits, will support this purpose very well.
P132944 | Naghlu Hydropower Rehabilitation Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2016 | 2025 | 2024 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099100223183516316/text/P1329440d0f27d06b0a210075990ec4dd8c.txt | http://documents.worldbank.org/curated/en/099100223183516316/pdf/P1329440d0f27d06b0a210075990ec4dd8c.pdf | This review has drawn three lessons based on the information in the ICR.In an FCV status country, prioritizingthe rehabilitation and/or overhauling of large generation assets can deliver high economic results in a relatively short period.It is observed that despite decades long armed conflict, major generation assets in Afghanistan were significantly in goodshape without any irreversible damage. Such assets do generally continue generating electricity even during heightened armedconflict periods. Therefore, Naghlu Hydropower Plant did not have any major damage to its dam or hydroelectric parts before thestart of the project. The project completed the rehabilitation and overhauling the power plants units within the planned period,and the hydropower plant was able to use its all four units at the same time. Even after the Taliban takeover, DABS was able tocontinue with the rehabilitation of the flushing gates, which partially contributed to the improvement of dam safety and thesustainability of power generation. Therefore, in FCV status countries, following an initial adequate assessment, prioritizinglarge generation assets that have survived armed conflict can yield high economic results.In high security riskenvironments, hiring resident engineers familiar with legacy systems and equipment of the power plants can be more effective todeliver results in hydropower plant projects rather than trying to hire consultancy firms that might be reluctant to work in suchenvironments. One of the main reasons for the delay in the implementation of the dam safety works was the reluctance ofinternational engineering companies to visit the project site. The hiring of two resident engineers who were familiar with thelegacy Russian systems and equipment at the Naghlu hydropower Plant was effective in delivering results both in therehabilitation and overhauling of the units and the partial improvement of the dam safety through the rehabilitation of theflushing gates. These resident engineers were embedded in the hydropower plant staff and provided technical assistance to theDABS staff in hydropower plant operation and maintenance. Their technical expertise was also crucial in scoping therehabilitation works both at Naghlu and Darunta Hydropower Plants and the preparation of the tender documents. Hiring of residentengineers was also significantly less expensive that hiring of engineering firms.The cost of line-drops to connecthouseholds to the distribution grid can be a major barrier to increasing access to electricity in rural areas. The projectfinanced the expansion of the distribution grid to a limited number of villages in the project area, but the cost of the line-dropswas excluded from the project financing. This proved to be a major bottleneck because the households did not have sufficientfinancial means to cover the cost of connecting to the grid. Therefore, although the project brought electricity to the villages,fewer households than expected were connected to the grid. This was a significant weakness in the project design that restrictedthe impact of the project on addressing the drivers of fragility through inclusive growth and social inclusion.
P132979 | Kenya Urban Water and Sanitation OBA Fund for Low Income Areas | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Water | RETF | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/844091633546386522/text/Kenya-Kenya-Water-and-Sanitation-OBA-Fund.txt | http://documents.worldbank.org/curated/en/844091633546386522/pdf/Kenya-Kenya-Water-and-Sanitation-OBA-Fund.pdf | This review has drawn three lessons based on the ICR incorporating material in section 5. Lessons and Recommendations of theICR.Provision of technical assistance support and output-based grants to water utilities can be a sustainablemodel for mobilizing private finance for water supply and sanitation infrastructure investments to increase access.Through technical assistance, the project supported financially stronger and well-managed water service providers (WSPs) to preparebankable water supply and sanitation subprojects to be financed by commercial banks. The banks determined financial and operationalviability of each subproject to provide commercial financing. Although the output-based grants were not tied to the commercialloans, most of the WSPs used grants to pay off a part of the loans to decrease the financing costs and provide affordable servicesto customers by eliminating the need to raise tariffs. Availability of commercial financing for water supply and sanitationinfrastructure investments also eases the debt burden on the central government and makes the use of limited government fundspossible for increasing access in the service areas of financially weaker water utilities that could not secure commercialfinancing. Given the continued interest of commercial banks to continue lending in this model, a project pipeline of US$15 millionwas already identified at project closing that would be eligible for commercial financing.Rigid results-basedfinancing criteria can adversely affect disbursement and project efficiency. Originally, the disbursement of 65 per centof the output-based grants was conditional upon the achievement of the household connections and 25 per cent upon the demonstrationof service delivery for three months. However, to connect households to water supply and sanitation services, the WSPs invested insignificant upstream water supply and sanitation infrastructure during which the WSPs could not benefit from the grants to pay offa part of the commercial loans reducing some of the financing costs. This resulted in a very low disbursement rate until the lastimplementation year of the project, increased the financial burden on the WSPs because of accrued interest and loweredprojects efficiency.An early identification of consultants to be hired under the project to support waterutilities in the preparation of subprojects can prevent lengthy delays in project implementation. Consultants to be hiredunder the project were to provide technical assistance support to the WSPs in the preparation of bankable subprojects. However, theWSPs did not have the capacity to draft the terms of reference for hiring these consultants. Consultant procurement process tooklonger than expected and consequently led to delays in securing financing for subprojects, completing subprojects, and disbursingproject funds. The WSPs could have also benefited from such pre-qualified consultants in reaching out to commercial banks early inproject implementation and address the unfamiliarity of the banks staff with the water sector.
P132982 | Results-based Road Maintenance and Safety Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099120523143541918/text/P13298209762c802b0866001b22826c3d73.txt | http://documents.worldbank.org/curated/en/099120523143541918/pdf/P13298209762c802b0866001b22826c3d73.pdf | The ICR included two lessons which are emphasized with some adaptation of language.1.Road maintenance iscritical to improving resilience and climate change adaptation, but Output and Performance-based Road Maintenance Contract (OPRCs)must continually adjust as climate variability grows. Critical to the success of OPRCs is the assignment of risk betweenparties. Climate change has major implications for OPRC contracts because it affects the risk exposure of both parties. Withoutclear expectations around climate risk, neither the asset owner nor the companies bidding for performance contracts will adequatelyaddress the risks. Contractors cannot be held accountable for risks that are not specifically cited or linked with performancecriteria. At present, climate change risks are generally carried by the asset owner through force majeure provisions of thecontract, and treated as unforeseen events, with repair costs reimbursed to the contractor. This impacts the overallcost of the OPRC, and where extreme weather events are becoming commonplace, reduces the efficacy of OPRC as a contractingmodality. In the case of the RRMSP, the project financed emergency works on roads affected by adverse weather events at a totalcost that was 10%higher than budgeted. As weather becomes more erratic and severe, OPRCs will need to adapt, without whichthey could lose their cost efficiency.2.OPRCs can help strengthen sustainable and efficient road assetmanagement as they create both in the market and within government an expectation of stable and predictable funding flows throughmedium-term budgeting. In turn, the efficient use of resources through the OPRCs increases the credibility ofbudget requests, leading to increased outlays for maintenance, as evidence in the increased funding allocated to the new OPRCs.These are important steps towards accessing commercial financing via bonds and market instruments that will allow the country tofinance the road sector in a more efficient manner. However, more needs to be done to add credibility to the process. In thiscontext, a well-functioning RAMS, anchored by a SLA, can provide the critical foundation for adequate road sector financing for thecountrys ambitious road sector development program.The following lesson is emphasized by IEG:3.Road rehabilitation and maintenance projects need to reflect updated reports on road conditions and limit the time needed toprocess and award contracts to ensure smooth implementation by contractors. The project experience demonstrated that thelengthy time that took place from the identification of road conditions to awarding contracts resulted in costlier rehabilitationbecause the conditions of the roads continued to deteriorate, and more work was needed.
P133000 | Huainan Mining Area Rehabilitation Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR (p. 32-33) included several lessons learned: Planning sufficient time for in-depth consultationwith stakeholders and affected communities during project preparation when land acquisition is required might avoid implementationdelays. In this project, the underestimation of land acquisition requirements led to implementation delays and the need toextend the closing date. A well-prepared and approved regional development plan in post-mining region could helpguide project design and implementation. The project area was located in post-mining regions overlapping the ShungengshanNational Forest Park and a new urban development area. Given the context of complicated land acquisition issues and the high riskassociated with urban development, the Shungenshan Sustainable Area Development Master Plan (SSADMP) provided the necessaryguidance for project design and implementation, which helped the project achieve not only its primary objective of restoring theecological environment of the site but also created public spaces, benefiting a larger number ofresidents. Continuous discussions from the beginning of project preparation until project closure about OMarrangements might positively impact the sustainability of project assets. In this project, the Bank team discussed withthe counterpart OM arrangements early in project implementation and developed an asset management plan, including a financialplan for the operator to become a market-driven company with a gradual decrease in government budget allocation while creatinglocal jobs.
P133017 | Guilin Integrated Environment Management | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099256312232286256/text/P1330170133be8005084300ba20ee9a25de.txt | http://documents.worldbank.org/curated/en/099256312232286256/pdf/P1330170133be8005084300ba20ee9a25de.pdf | The ICR (paras. 82 to 86) lists a number of lessons derived from the Projects experience. Based thereon, IEG derives thefollowing lessons relevant for similar projects carried out in comparable environments.Integrated plant andnetwork management for urban water and wastewater utilities can improve operational effectiveness and efficiency.Theseparation of plant and network management has been identified as a main issue affecting performance of urban water utilities inmany countries. While water and wastewater plants are typically managed by utilities, networks are often managed by othermunicipalgovernment departments (as in China). The Project financed not only the upgrading of WWTPs but also the wastewaternetworks, which enabled improved efficiency and helped reduce thepollutants discharged to the naturalenvironment.Appropriate innovative technologies can contribute to significant improvement in urban water andwastewater services.The Project designincluded an innovative water supply management systemthat builds on a cloud-based information platform and enables the smart operation of water utilities to improve operationalefficiency, reduce non-revenue water, improve energy efficiency, and increase service quality. In addition, pilot activities forimprovedsludge dewatering and composting and preparing a pilot pollution inventory study would provide valuable informationfor future environment related interventions in China.Institutional, technological, and financial measurestaken in a complementary manner can improve the sustainability of improved water and sanitation services. TheProject design included: (i) establishing and building capacities of the involved institutions; (ii) adopting reliable, easy tooperate, and affordable technologies; and (iii) ensuring the financial sustainability of the utilities through appropriate tariffadjustments and reducing operating costs through the Project interventions. This enabled GWSC and GSC to have sufficient revenuesto cover their operating expenses as required under the agreed financial covenants in the Loan Agreement.
P133018 | Zhejiang Rural Water Supply and Sanitation Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099355006172238655/text/P13301809acbba0420b2790d2d0a79bd9f9.txt | http://documents.worldbank.org/curated/en/099355006172238655/pdf/P13301809acbba0420b2790d2d0a79bd9f9.pdf | The ICR provided various lessons, some of which are summarized as follows:In a situation where projectimplementation covers a large number of scattered village subprojects, the framework approach may help to streamline projectpreparation and implementation. The project implemented the framework approach, which allowed the counterparts to proposethe potential interventions batch by batch and helped prioritize the project intervention according to emerging needs andstreamlined the project preparation. This also allowed the adaptive management of learning by doing. The lessonslearned from early implementation particularly on technical matters and OM were incorporated into the design and selection ofthe next batchs intervention. The good technical and OM experiences were further scaled up in the followingimplementation.There is a greater chance of ensuring sustainable OM, when community participation is employedallowing ownership of communities. Participatory and consultative approach was adopted throughout the project, andthe local communities participated in the process of planning-design-construction-OM. The early involvement of localcommunities in deciding the locations of sewers, septic tanks, and sewage treatment stations could avoid questions and delaysduring the project implementation. The governments transferred the ownership of some small facilities to villagers, who areresponsible for the day-to-day maintenance. The project showed that with increased ownership, villagers usually take better care ofthe facilities and make efforts to keep them functional, which further reduces the OM burden on the watercompanies.The capacity strengthening of professional water companies is a key factor in achieving theoutcomes. The project included comprehensive interventions to enhance the technical, financial and institutionalcapacities of the professional water companies at county level. As a result, these companies are able to look after the wholeprocess of master planning, engineering design, construction, and OM of rural WSS schemes in the villages. This institutionalsetup has proven successful and served as a pilot for similar rural WSS activities. Since 2020, the Ministry of Water Resources andthe Ministry of Housing, Urban and Rural Development (MOHURD) have also encouraged local governments to transfer OM of schemesfrom communities/local governments to professional water companies.
P133021 | Chad Value Chain Support Project | Western and Central Africa | Chad | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/804211621649050122/text/Chad-Value-Chain-Support-Project.txt | http://documents.worldbank.org/curated/en/804211621649050122/pdf/Chad-Value-Chain-Support-Project.pdf | The ICR chapter (p.31-34) on lessonslearned was expanded unduly, andwas a mix of evaluative material, findings andrecommendations.From that material, this review identified four lessons summarized below, which are common to most projectsimplemented in a Fragile, Conflict and Violence (FCV) context.(i) Bank knowledge isan important ingredientto addressthe multiple design and implementation challenges in an FCV context. Knowledge for this project refersspecifically to the appropriate lessons learnedby the World Bankin implementing projectsin similar environmentsandsectors,and to any recentanalyticalwork on the country and the sectors of interest.The design ofthis projectdid not rely fully on lessons learned fromprevious World Bank operations, particularly the need foraproject designtoreflectthe Government commitment to the project objectives, and tohave in place aneffective implementation capacity. Moreover, the design was not supported by sound research and appropriate risk assessments tobetter understand the meat and milk chainsduring preparation, and it underestimated the real cost of rehabilitation ofplanned infrastructure. These shortcomings related to limitedknowledge werea mainsource ofimplementationchallenges and the modestoutcomeachieved by this project.(ii) Specialized expertiseisindispensable to design and implement a project aimed at improving a value chain:This project was aboutmodernizing a specialized meat and milk chain, and was to usea matching grant facility. Modernization of a specialized valuechain with an innovative instrument, specialized expertise commensurate to the complexity of the sector and new instrument isrequired. Implementation of this project encountered a lack of competences in the Bank and borrower teams, faced delays ofactivities and needs for extensions, and poor choice of construction site locations, to name a few of the challenges.Thisunderscores that the project raisedsensitive mattersof healthy nutrition and the risk of contamination through meat andmilk, and the critical consequent need for the project preparation to draw from accurate sectoral technical studies.Thereforehygiene-related technical studiesand technical specifications for infrastructure needed to be ready beforeeffectiveness.Similarly, when establishing a Matching Grant Facility (MGF) in a low-capacity environment, implementationshould have included prior mandatory training on the scheme itself. Neither the PCU staff nor the beneficiaries were clear on whatthe two windows of matching grants were and how they could access them.A Matching Grant consultant was hired after theproject restructuringto help strengthen the PCU staff capacity in managing the Matching Grant scheme. The absence of therequired specialized expertise affected negatively the project performance and efficiency.(iii) Projectefficacyis negatively affected by a limited dialogue among stakeholdersand the absence of a Bank team on theground:Since the outset, the Bank team had difficulties to establish a strong rapport withthe Government,whichdid not take full ownership of this project, despite several efforts from theWB teams to engage them (ICR para68-69). To illustrate this,the rehabilitation of the Farcha slaughterhousewas not completed because the Government didnot disburseits contribution. The lack of Government commitmentaffected the smooth running of the Project CoordinationUnit, notably throughthe quick rotation of project coordinators and financial specialists, some of whom lacked the requiredexpertise, and the infrequentcoordination meetings.Onthe Bank side, theproject supervision was difficult,because of geographical distance from the client, as thefirst Task Team Leader (TTL) was first based in Burkina Faso prior tomoving to Washington, DC.The remote supervision, lack of capacity and responsiveness of the PCU,and deepening ofcollaboration issues, contributed to implementation delays in the first three and a half years that could not beresolveduntil the TTL was replaced.(iv) Fully associating key project stakeholders and the privatesectorin particular can pave the wayto sustainability of the projectoutcome:Theprojectneeded to create stronger engagementwith key players, including the Governmentofficials, the private sector representatives, and experts in the targeted value chains at the different phases ofprojectappraisal, design, and implementation. The project design should have incorporated more gender-related activities, including thetraining of more females who are in charge of the milk value chain.Toward increasedsustainability andclients ownership in a fragile and politically volatile environment like Chad, ensuring the participation of private sectorstakeholdersis a critical factor. One major component of theproject aimed at rehabilitating slaughterhouses andbuildingmilk collection centers.While some of these activities were not completed, the ICR reports (para 105) that twoprivate companies mighttake them over. More time and full support by the CMU would have helped increase sustainability andclient ownership given the nature of the business environment.
P133045 | State and Local Governance Reform Project | Western and Central Africa | Nigeria | Blend | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2015 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099405005312223826/text/P13304506f5f220190a2940e1dbc5e0f475.txt | http://documents.worldbank.org/curated/en/099405005312223826/pdf/P13304506f5f220190a2940e1dbc5e0f475.pdf | The ICR (pp. 28-30) presents a series of lessons and recommendations emerging from the projects experience. IEGsummarizes the most persuasive lesson below:The experience of creating a fund to incentivize performance when severalstates or local governments at varying stages of development and with widely different capacity are participating in a singleproject can accelerate project implementation.Inthis project, the Performance Challenge Fund was establishedtoencourage theparticipating states to accelerate implementation, and it did. Mindful of the heterogeneity between states,progress was measured from the baseline of each state. A monetary reward from the Performance Challenge Fund for the states thatmade good progress on performance at the mid-term review served as an incentive for the states to focus on results in projectimplementation. Allowing the states to allocate the proceeds of the Challenge Fund to project components 1 and 2, based on theneeds of each component, allowed for flexibility in the projects design. While putting in place such incentives, care needsto be taken to recognize inherent/initial disparities.
P133069 | Shaanxi Small Towns Infrastructure Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099215012102112702/text/China000Shaanx0Infrastructure0Proje.txt | http://documents.worldbank.org/curated/en/099215012102112702/pdf/China000Shaanx0Infrastructure0Proje.pdf | The following lessons in the ICR stood out as important and relevant to other projects and are presented here with somerevisions in editing: A competitive approach to selecting counties/districts for investments can create apositive implementation dynamic among participating counties/districts. The traditional approach in China is that eachcounty/district receives a fixed amount for infrastructure investments. The project took an innovative approach to counties/districts selection based on predefined criteria that emphasized alignment with national and local development strategies, strongownership and commitment from townships, disparity in infrastructure service in urban and peri-urban areas, demands for addressinginfrastructure deficit and insufficient services, and adequate institutional arrangements/readiness for becoming a pilot model forsustainable small-town development (ICR para 9). The selection of investments was also strategic to ensure efficiency and technicalsoundness by focusing on investments with a reasonable scale of resettlement impacts, technical soundness, and quality of servicesin built-up areas (ICR para 53). This competitive approach generated incentives among the counties/districts to submitwell-designed proposals, which proved effective because these well-designed interventions secured the county/districtgovernmentscommitment and strong support from the start. Complementing investmentactivities with capacity strengthening for OM can lead from reactive to proactive maintenance. Before the project,local authorities placed high priority on building new infrastructure over OM of existing infrastructure, resulting ininefficient use of public resources. This project introduced systematic asset management systems to support the long-term successand sustainability of public infrastructure investments and service delivery. This included, among others, public utilityregistrations, infrastructure mappings, and approval process of maintaining municipal assets. This led to a change from reactive toproactive maintenance of infrastructure, such as the timely clearing blockages in sewers and carrying outrepairs. Innovative approaches for community outreach can help enable inclusive public participationto build ownership and facilitate implementation. Engagement with communities and beneficiaries in selecting project sitesand designing the services is critical for communities to understand project outcomes and impacts. The project introducedinnovative methods for community outreach, including the use of social media and digital tools complemented with conventionalpublic participation methods. This allowed a wide range of citizens to be engaged throughout project preparation andimplementation. The project used TV news, WeChat, and TikTok platforms to facilitate broader community discussions aimed atdeveloping consensus on the level and type of investments to maximize the benefits for local communities. These innovativeapproaches provided timely and transparent information to affected people, created social support from affected communities, andimproved the quality and effectiveness of construction works incorporating the feedback loops.
P133070 | Sierra Leone - REVITALIZING EDUCATION DEVELOPMENT IN SIERRA LEONE | Western and Central Africa | Sierra Leone | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/295281617290433745/text/Sierra-Leone-SL-Revitalizing-Ed-Development-FY14.txt | http://documents.worldbank.org/curated/en/295281617290433745/pdf/Sierra-Leone-SL-Revitalizing-Ed-Development-FY14.pdf | The ICR (p. 36) offered several lessons and recommendations, including the following lessons restated byIEG: Flexibility in project design and implementation arrangements can enable response during crisis. TheBanks ability and decision to add an Ebola-related component using the additional financing helped thegovernment tomanagethe risks ofthe Ebolacrisis in the education sector. Digital technologiescanbeeffective and important tools for continued education during a crisis. The project provided an emergency response to theEbla crisis through television and radio programming. The experience from project implementation was helpful in enabling thegovernments response during the current COVID-19 crisis. Successful operation in low capacity and fragile contextsrequires participatory approaches and field support. The project was helmed by the ministry (MEST) butbenefited from thepresence of operational staff in the field by receiving timely implementation support.
P133079 | GAMBIA - READ: Results for Education Achievement and Development Project | Western and Central Africa | Gambia, The | IDA | FCS | Human Development | Education | IDA | IPF | 2014 | 2019 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/372931561750965295/text/Gambia-The-READ-Project.txt | http://documents.worldbank.org/curated/en/372931561750965295/pdf/Gambia-The-READ-Project.pdf | The ICR (pp. 35-36) offered several lessons and recommendations, including the following lessons restated byIEG:The Banks proactive engagement during periods of economic crisis can be instrumental inensuring continued service delivery and sustained progress towards the achievement of development objectives. TheBanks strategic decision to provide additional financing to the Government of Gambia when it faced a severe fiscal crisisensured that project progress was maintained and subsequently scaled up.High participation ofsenior officials in project supervision facilitates informed decision-making. The Minister, Permanent Secretary,Deputy Permanent Secretary, and Directors of the Ministry of Basic and Secondary Education visited one out of the six Regions everytwo months for one week. Hence, all regions were visited every year. The high-level officialsbecame familiar withboth physical and learning challenges through interactions with school heads, teachers, and students, and the findings were sharedat the Coordinating Committee Meetings. The ministrys senior management team became familiar with the challenges facedby the schools and their needs, thus facilitating decisions in response tothose needs.Donkeycarts can provide a viable though unconventional solution to schooling access in difficult areas. In order toaddress access barriers in difficult areas, the project used donkey carts for transporting young children to school, as thechildrenwould not have been able to walk long distances. The government provided the donkeys, and the project fundedthe carts. This approach strengthened community engagement and accountability: communitieshad to care for and feed thedonkeys, and in return they could use the animals for other tasks during the remainder of the day, after transporting the childrento and from schools. This arrangement constituted a sustainable and low-cost transport solution for some of the most remotevillages serving 2,000 school children daily and was continued after project closing.
P133107 | Sierra Leone - Sixth Governance Reform and Growth Grant | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | This review supports some of the lessons cited in the ICR, especially the importance of having a functional Multi-donor BudgetGroup that will assist in the design, formulation and selection of indicators discussed with government. Other lessons cited in theICR with adaptation in language include the following:(i) The Ministry of Financeplays a critical role in ensuring that agreed reforms are implemented by various government agencies. In this case, the Ministry ofFinance did not effectively use its budgeting and resource allocation powers to compel the Ministry of Education to focus on agreedreforms. As a result, the education sector target was not met.(ii) The use of aprogrammatic series provided an opportunity for mid-term corrective measures to be taken by the team towards theachievement of the targets. The Bank team had an opportunity to re-evaluate their indicators after the first twooperationsand introduced new indicators during the thirdoperation (SL-GRGG 6)to help them achieve thedesired outcomes.(iii) Selecting prior actions from the Progress Assessment Frameworkdesigned and discussed with government and other development partners works well and aids monitoring. In this case, the policyreforms were derived from the governments own reform agenda and harmonized with the reforms supported by developmentpartners. This created ownership from all stakeholders during the implementation and monitoring of the Progress AssessmentFramework.
P133114 | Heilongjiang Cold Weather Smart Public Transportation System | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099400008312238055/text/P13311405b40430c60893d0de4b14d9feb6.txt | http://documents.worldbank.org/curated/en/099400008312238055/pdf/P13311405b40430c60893d0de4b14d9feb6.pdf | The following lessons have been derived and summarized from the ICR, with minor additions by IEG after discussions with the Banktask team:For project implementation agencies without previous World Bank experience, delays in contracting aproject management consultant is likely to lead to a slow project implementation start and inadequate initial progress reporting.In this case, theproject management consultants for the two PMOs were only contracted after two and three years ofimplementation. This led to slow project implementation, in particular slow procurement and inadequate results reporting. Oncethese consultants came on board, project implementation picked up and all project implementation ratings improved. Therefore, itmightbe helpful to prepare for the project management consultants hiring already during project preparation to ensure goodprogress in early years of implementation.It is also important to train the PMOs during project preparation and earlyimplementation to ensure that they can make full use of the training and solve implementationproblems in a timely andeffective manner.Not taking advantage of synergies and establish close collaboration in projects involving severalcities is a missed opportunity for learning from each other.Although the two cities included similar activities,except for component 4 in Harbin, they had limited direct coordination and exchange of synergiesor lessonseven if theyare located in the same province. Each of thecities implemented the project separately and did not closely collaborate. Inaddition, Harbin had greater project implementation capacity than Mudanjiang, showninthe superior quality of theirprogress and ICR reporting. If the two citieshad worked more closely together, for instance through jointmeetings,sharing of reporttemplates and other tools, and exchanging good practices, especially Mudanjiangmighthave benefitted. In addition, because the project had a provincial PMO, this entity could have been the catalysttoidentifysynergies,facilitatecapacity building, and enablethe sharing of lessons. Therefore, thisappears as missed opportunity in this project.Land acquisition takes time and,if not started early, maydelay project implementation. Inthis project, resettlement started late and took a long time because of lengthypreparation and coordination amongcity departments. This delayed project implementation. Therefore, the land acquisitionprocess should start early during project implementation to avoid delays and build in flexibility of the implementationtimeline.Effective communication between the borrower and the Bank task team is a key enabler for projectsuccess.The Bank task team who initially supported this project lacked structured and regular day-to-day interactionand follow-ups with the borrower. This led to communication difficulties between the parties. According to the ICR, para 123, thesedifficulties were barrier to progress at the early stage of implementation. The new Bank task team instituted a well-establishedand structured communication process, which together with effectivecoordination mechanisms,resulted in a significantproject implementation progress since 2018and was appreciated by the client. Therefore, a well-established andstructuredcommunication process from the start of implementation and throughout the project with pre-set regular coordinationand progress update meetings is recommendable.The successful demonstration that new technologies can work underspecial conditions might lead to their mainstreaming.Under this project, the promotion of new energy vehiclesincluding hybrid and LNG buses in this project on a pilot basis wasan important success story. The pilot carried out underthe project showed that the operation of hybrid and LNG buses in auniquely cold weather in the project cities can workwithout problems. This experience built confidence in the technical viability of hybrid or electric fleets, and inHarbin, ledto thepurchase ofan additional 3,906buses, showcasing the impact of the project further. According to the Banktask team, Mudanjiang was also pleased with the new technology, but did not have the means to purchase additionalvehicles.In cold climates, heated facilities can play an important role in making public transport moreattractive. The project initiated a warm concept for public transport. In Harbin, the project introduced theThree-Warm Program, which includes warm bus stops, warm vehicles, and warm bus parking. In Mudanjiang, the projectintroduced the warm-heart bus wait program to mobilize shops and restaurants near bus stops to provide in-door waitingspace to passengers. Passengers appreciated the heated waiting facilities and vehicles. The warm bus parking contributed to thetimely start of engines and hence the reliability of public transport services.
P133116 | China-Qinghai Xining Water Environment Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099245005192218252/text/P1331160f35b7203d0b696048dce1e6ad33.txt | http://documents.worldbank.org/curated/en/099245005192218252/pdf/P1331160f35b7203d0b696048dce1e6ad33.pdf | The ICR included four lessons. The following three lessons are emphasized with some adaptation of language:1.Ifpublic and private financing are both available to support urban development, there is a higher chance that urban development needswill besuccessfully met. The project experience showed thatpublic financing for water management in turnallowed the entry of commercial financing for other developments. For example, the benefits from collection of wastewater andimproved ecological environment resulted in increased land value in the project area and subsequent development area. Thisecological development by the Government using public resources, in this case international development financing, had dual benefitas it attracted private sector investment in the area, through housing and retail, and therefore improved the growth rates,economic vitality, and standard of living; and the sale of land provided revenues to the Government allowed counterpart funds to beused for further development of essential infrastructure and provision of public services. This therefore shows the benefit ofGovernment investing early in public services provision, such as a good ecological environment, to stimulate commercial financingand development of vibrant communities with high standard of living.2. If consistent institutional strengtheningand a focused design are emphasized in Bank-funded operations, there is a higher chance that implementation will be effective andobjectives will be achieved. The ownership, commitment, and capacity of the client combined with the focused andrealistic design were an essential combination for smooth implementation and achievement of all objectives despite project delays.These aspects ensured project sustainability in terms of embedded capacity for OM of assets. Moreover, LID interventions andthe demonstrable project outcomes in reducing water pollutions drew the attention and commitment of leaders at all levels ofGovernment, as evidenced in requested for tours of the project-financed infrastructure. Consistent capacity building throughoutimplementation transformed the PMO from paper-based to digital project management, allowing for greater effectiveness. Althoughthere was initial slow uptake and quality issues with the MIS, in the end, the MIS was the backbone of thiscapacitytransformation.3. If a high level of implementation readiness combined withclose projectimplementation support are availed to the project, there is a higher chance that implementation will be consistent and results willbe timely delivered. Implementation readinessallowed for the early launch of some procurement processes. Moreover,the short status review missionsstrengthened regular contact and support quickened the pace of implementation. Moreover, thisevident support from the Bank encouraged the provincial government authorities to build trust and confidence in the project,resulting in the Governments strong commitment and support.
P133117 | Chongqing Small Towns Water Environment Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060923164515038/text/P1331170d945f9098083cb0965ee6bab320.txt | http://documents.worldbank.org/curated/en/099060923164515038/pdf/P1331170d945f9098083cb0965ee6bab320.pdf | The ICR included four lessons. The following three are emphasized with some adaptation oflanguage:1.Integrated flood risk management is more effective with deeper and more comprehensive structuraland nonstructural measures, leveraging both gray and green infrastructure. Flood management needs to adopt a risk-basedapproach, which requires proper flood risk mapping and careful verification after the infrastructure systems are selected anddesigned during project preparation to inform the use of risk reduction measures (that is, dike construction, emergency plan, floodawareness raising, and so on). For future project preparation, flood risk maps need tobe developed by the clients basedon modern technologies, including satellite images, and improved social, economic, and topographic data during project preparationto inform project interventions as well as to identify appropriate project outcome targets. In addition to gray infrastructure, awide range of green infrastructure, including wetlands and ecological embankment, can also be utilized to complement and maximize aseries of social economic and ecological co-benefits beyond flood risk management.2. Developing an accuratebaseline assessment is critical to ensuresmooth project implementation and completion.A more detailed baselineassessment for geological conditions that included the identification of landslide risks is needed to inform to inform constructionsite selection; and minimizelandslide risks during implementation. Also, assessing theflood protection area andpopulation based on flood risk mapping and high-resolution population data is needed to prioritizeproject interventions andhelpavoid unnecessary restructuring processes. In addition, an accurate baseline will help in avoiding overestimation ofpopulation growth in small- and medium-size cities and towns as well as cost overestimation.3. Developingamultihazard risk management system, especially in mountainous regions, requires establishing an effective life-cycle system fromplanning, supervision, and response to remediation. An effective disaster risk management system is critical for managingmultihazard risks especially in mountainous regions, such as mountain torrents, earthquakes, and landslides. Preparation ofprojects in mountainous regions requires putting in place a comprehensive and effective system for managing those risks from alife-cycle perspective, from improved risk identification during project preparation, adopting of design changes to mitigate thoserisks, to close implementation supervision and communication, emergency preparedness and response, and appropriate remediationmeasures adopting the concept of Building Back Better. Local governments and project implementing agencies need to beinvolved in the entire process to enhance their project ownership and take responsibilities in disaster response andremediation.
P133129 | Argentina Youth Employment Support Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2015 | 2022 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099040005242240993/text/P13312906a066d083094010ed210df97bfd.txt | http://documents.worldbank.org/curated/en/099040005242240993/pdf/P13312906a066d083094010ed210df97bfd.pdf | The ICR (pp. 29-30) offered several insightful lessons, some of which are restated here:Output-based financing forskills development and training programs can be fine-tuned by project design teams to incentivize not just production of desiredoutputs, but also their relevance and quality -- in other words, not just more outputs but also betterones. In this case, payments to training providers rewarded not just enrollment but also completion. Following this model,incentives to employers could reward aspects such as tutoring and mentoring, as well as permanent hiring. Payments to EmploymentOffices could go beyond enrollment to focus on beneficiaries eventual insertion into the labor market.Project designteams targeting vulnerable youth for a skills development and training program can be maximally inclusive byaddressing thediversity of sources of vulnerability within the target population. Vulnerability can stem from gender, indigeneity, socio-economiccharacteristics, and geographic location, all of which might require different strategies for outreach, intervention, and serviceprovision.In an uncertain macroeconomic environment, the usefulness ofoutcome indicators related to skills trainingand active labor market interventions can be negatively impactedif those indicatorsdepend onfluctuating overallemployment levels. In this case, key outcome indicators initially focused on changes in employment outcomes without considering thepossible influence of macroeconomic factors outside the projects control.
P133133 | Sustainable Land Management Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/836131570649770928/text/Ethiopia-Sustainable-Land-Management-Project.txt | http://documents.worldbank.org/curated/en/836131570649770928/pdf/Ethiopia-Sustainable-Land-Management-Project.pdf | Largely based on the lessons identified in the ICR, IEG draws the following four lessons for the future.Long termmaintenance of SLM interventions is likely to be necessary to attain significant agricultural productivity gains. The experiencefrom SLMP-2 shows the need toprovide reasonable time to achieve regeneration of land andstabilization of ecologicalfunctions indegraded areas, as well as a mechanism and supporting elements to allow watersheds to graduate from project-basedassistance and continue sustainable management of restored landscapes.Sustaining the benefits from SLM investments wouldrequire strengthening of capacity and institutions for improved watershed management at the local level. SLMP-2 has supported localcapacity development through technical assistance for SLM and participatory land use planning at the Kebele level. The communitieswere also able to develop local norms for area closures, cut-and-carry systems and restricting free grazing of pastures on communalland.For continued maintenance of the SLM structures, SLMP-2 ispreparingthe intervened watersheds for graduationthrough (a) building local government capacity to design and manage SLM plans and interventions, (b) strengthening communityincentives for investment in, and maintenance of, SLM through land certification, and (c) improving returns to sustainableproductive activities by promoting CSA and forging connections to value chains.The decentralized implementation anddecision making process for SLM requires well-designed ME system. The SLMP-2 experience shows that careful thought must begiven to the ME system, including the Results Framework, theory of change, and key learning questions to beaddressedensuring that this system will be focused on results-based measurements instead of activity-based ME. Inaddition to identifying relevant indicators, an effective ME system would requiredetailed indicator protocols toprovide clear procedures (including frequencies)for indicator data collection. The ME system alsoneeds to includeclearly defined plans for baseline data collection, results monitoring, evaluation and learning efforts.Design ofparticipatory watershed management approachesinvolving individual land usersand communities requires complementarytechnical interventions and management practices. More specifically, the SLMP-2 experience shows that :(i) Area closures to limitfree grazing for addressing land degradationrequire complementary interventions forfodder production to reducepotential trade-offs in livestock production practices; (ii) SLM initiatives need to take into consideration the livestockpopulation in the micro-watershed in relation to the carrying capacity of the area; (iii)capacity building of the extensionsystems to support implementation and future management of biophysical structures; and (iv) adoption of climate smart SLM wouldrequire options that improve income and livelihoods, includinglinks to value chains that reinforce incentives for themaintenance of SLM investments.
P133133 | Sustainable Land Management Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2014 | 2019 | 2021 | PPAR | >=25 million & <50 million | Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/126731603826296434/text/Ethiopia-Sustainable-Land-Management-Project-I-and-II.txt | http://documents.worldbank.org/curated/en/126731603826296434/pdf/Ethiopia-Sustainable-Land-Management-Project-I-and-II.pdf | 3. Lessons 3.1 The watershed management approach can lead to significant land restoration when appropriate structural and biological measures are introduced to treat the affected landscape with active participation of the local community. Treatment of the upper catchment and the fast-growing gullies with reinforced gabion check-dams and vegetative cover was critical in controlling soil erosion from its source upstream. Demand-driven community participation is key for the uptake and effectiveness of watershed interventions. In some highly erodible catchments (for example, the Dalocha watershed in Gimbichu), the resource-poor communities were willing to contribute labor but required a supply of capital items for treating large gullies. The lesson is that natural resource restoration advanced significantly when the right SLM practices were implemented to arrest and reverse degradation. 3.2 Area closures are relevant for the restoration of degraded lands but require increased investments for alternative supply of forages to convince the local communities to forgo these benefits during the process of natural regeneration. Livestock feed is a very limited resource in many land-scarce and intensively cultivated highlands. Some communities that agreed initially to enforce area closures were highly reluctant or unwilling to implement area closures unless alternative sources of fodder and fuelwood were available (for example, some microwatersheds in Upper Guder, Amhara). Controlled harvesting of livestock feed and beekeeping activities within area closures facilitated compliance. The lesson is that a supply of alternative sources of livestock feed and fuelwood, information about the long-term costs of traditional freegrazing systems, and a shift to a phased approach to area closures, which allows communities to successively put more communal land into conservation, can all enhance the local acceptability and viability of this model for land restoration. 3.3 Farm productivity growth requires arresting both the on-site and off-site soil erosion to prevent degradation of farmlands and to enable investments in modern farm inputs. Given the geospatial interdependence within watershed landscapes, farmland restoration and the use of productivity-enhancing inputs significantly depends on controlling the off-site erosion originating upstream. A good example is the farm productivity growth in the Adikelkel microwatershed (in Enderta, Tigray), where arresting soil erosion and runoff originating from the upper reaches was critical to achieving sustainable intensification and productivity growth on farmlands in the lower valley. The lesson is that farm productivity growth requires arresting both the on-site and off-site soil erosion that leads to degradation of farmlands and therefore lowers incentives to adopt SLM practices and modern inputs. 3.4 Effective demonstration of up-front economic and livelihood benefits is fundamental for smallholder farmers to protect and maintain the SLM practices introduced on their lands through project support. Past soil and water conservation investments promoted through governmentand donor-supported programs were not sustained by farmers mainly because of limited local participation and ownership and the focus on structural measures that do not bring short-term benefits. In Ethiopia, many smallholder farmers are unable to forgo immediate benefits for long-term sustainability gains. The lesson is that the SLMP, under the two phases, was able to overcome this challenge through proactive local participation and the demonstration of up-front economic benefits, such as increased crop and livestock production and other incomegenerating activities, which are critical for continued interest in and maintenance of the soil and water conservation structures. 3.5 In drought-prone areas, small-scale irrigation is the key enabler for translating the benefits of land restoration into reduction in household vulnerability to climate shocks through income diversification and protection against droughts. Small-scale irrigation is the most cherished component of the SLM package in Ethiopia and has become the game changer in creating incentives for improved watershed management. Water harvesting and small-scale irrigation also offered opportunities for income and dietary diversification, allowing households to grow high-value fruits and vegetables throughout the year. This created additional income and employment and reduced the pressure to migrate to the cities or other areas, especially for youth. Small-scale irrigation also provides protection against drought (for example, the Weinalem microwatershed in Raya Azebo, Tigray). The key lesson is that in high-pressure and drought-prone productive landscapes like the Ethiopian Highlands, water harvesting and small-scale irrigation establish strong links among land restoration, resilience, and reduction in human vulnerability. 3.6 Market-oriented agroforestry interventions (for example, Acacia decurrens) that bring sustainable income for smallholders can be vital ingredients in creating incentives for the adoption of biological measures for land restoration and improving resilience to climate shocks. Agroforestry systems, such as Acacia decurrens, that bring additional benefits through nitrogen fixation while also generating cash income are vital win-win options for land restoration, income growth, and asset creation. The lesson is that in the microwatersheds where such market-oriented agroforestry practices have been supported (for example, Akusty in Fagita Lekoma, Amhara), this has induced transformational changes in restoring highly degraded landscapes, creating employment, generating income, and reducing poverty and out-migration. 3.7 Watershed management programs can have differential impacts on the landless, women, and youth, but such trade-offs can be reduced by promoting inclusive livelihood activities and land certification to reallocate communal land. The SLMPs promoted off-farm youth employment and gender-inclusive programs, including the keeping of small ruminant livestock, poultry, and bees. In addition, many communities adopted the sharing of grass and biomass from treated communal lands, actively benefiting the poor and landless. Reallocation of communal land to landless youth has also created incentives for improved management while generating some employment and income benefits, especially when opportunities for youth migration are limited. The lesson is that, although area closures in some locations forced women to travel long distances in search of fuelwood, this challenge was mitigated in some cases through onfarm agroforestry production in conjunction with controlled harvesting of biomass in closed areas. 1Sustainable land management is defined by the Food and Agriculture Organization of the United Nations as the use of land resources, including soils, water, animals, and plants, for the production of goods to meet changing human needs, while simultaneously ensuring the long-term productive potential of these resources and the maintenance of their environmental functions (http\.//www.fao.org/nr/land/ sustainable-land-management/jp/). Typical SLM practices include the following\. physical soil and water conservation; flood control and drainage; water harvesting and runoff management for multiple uses; soil fertility management and biological soil conservation; agroforestry, forage development, and forestry; and gully control. 2 The second-level land certificates use geospatial data to better define a plot's location, size, and boundaries to provide landholding rights. These certificates show all the different parcels managed by farm households and include women as equal landholders. These improvements from the initial first-level certificates are expected to facilitate access to finance (serving as collateral), facilitate land rental and lease transactions, and help resolve land-related disputes. 3 Structured discussions with focus groups and key informants, including communityand woreda-level watershed teams, were held to solicit information on the extent of adoption of SLM practices; changes in the levels of soil erosion, runoff, and vegetation cover; use of improved inputs; crop and biomass yields; and changes since the beginning of the SLMP, separately for farmland and communal lands. As outlined in the protocols (see appendix C), this information was summarized in detail for each case study and was used to provide a performance rating in terms of achievement of the project objectives. The IEG team also assessed the livelihood and vulnerability effects in terms of changes in food security, water security, and outmigration. 4Given the sampling approach, the distribution of ratings in each region does not represent the regional situation. The interpretation is only valid at the aggregate level (across the three regions). This applies across all the tables where similar ratings are presented. 5 The separate performance ratings for Sustainable Land Management Project I and SLMP II shown in appendix C are consistent with the joint performance ratings given for reducing land degradation and improving land productivity. 6These findings are consistent with other evidence showing that the returns on SLM investments are higher in drier areas, where rainfall is a binding constraint to productivity growth and SLM offers moisture conservation benefits that facilitate land regeneration and yield growth (for example, Kassie et al. 2008, 2009). 7 However, the Implementation Completion and Results Report for SLMP II stated that some 9,661 landless youth were issued second-level land certificates or other legal documentation to use communal landholdings in exchange for restoring land. 8The regional coordination units also serve as the coordinators of the watershed management and SLM activities supported by other donors (for example, the International Fund for Agricultural Development, KfW, and the German Agency for International Cooperation).
P133184 | Lusaka Transmission and Distribution Rehabilitation Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060623153031399/text/P1331840413fa70090897f082b7d4c0d6dd.txt | http://documents.worldbank.org/curated/en/099060623153031399/pdf/P1331840413fa70090897f082b7d4c0d6dd.pdf | The following lessons were derived from the ICR with minor modifications by IEG (ICR, pages 30):1. The modalities ofcoordination among Projects co-financiers need to be discussed in detail and agreed upon among the donors and the Borrowerprior to Projects approval. Clear articulation of the added value of both contributions needs to be thoroughly covered inthe design and the responsibilities linked in the relevant theory of change.2. To improve the effectiveness oftransmission investment projects, technical readiness for implementation needs to be enhanced. Key stakeholders need to worktogether to ensure that pre-engineering work and safeguards assessment are thorough to allow a fair and productive bidding processand a timely implementation start. In the reviewed Project, detailed engineering designs and specifications were only completed twoyears after project effectiveness.3. Staffing the PIU with employees of the implementing agency is good practice forefficient implementation and sustainability of projects. ZESCO had extensive experience in implementing partner-financed projectsof the scope and magnitude of the Project, and therefore integrating the unit within ZESCOs operations was efficient, costeffective and led to greater ownership. Moreover, the technical expertise gained by the ZESCO staff will scale up ZESCOcapabilities to oversee the electricity network and improve the sustainability of achieved outcome.4. Large scaleinfrastructure projects are rarely likely to have Moderate safeguards risks given the considerable complexity ofworks. Stronger emphasis on mitigation approaches to the threats at design stage is likely to limit the potential damage that comesfrom these activities.
P133193 | Protecting Vulnerable People Against Noncommunicable Diseases Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099102023110016558/text/P1331930931b3408f0a51107f58c180306d.txt | http://documents.worldbank.org/curated/en/099102023110016558/pdf/P1331930931b3408f0a51107f58c180306d.pdf | Lessons drawn from the ICR (pages 29-20), adapted by IEG: A well-designed system of incentives can help promotecooperation in a federal, decentralized health care system. In the case of this project, TLIs provided attractive results-basedfinancial incentives for provinces, municipalities, and CAPsto align their actions with the strategic priorities of thenational ministry. This promotedthe adoption of an integrated approach toward NCDs and their risk factors at theprovincial level, as well asthe homogenization of standards of NCD care throughout the country. TLIs also helped fosterintersectoral cooperation within provinces to address the challenges posed by NCD risk factors (i.e. health and educationsectors). A solid ME system along with external control mechanisms can help to create effectiveaccountabilityand transparency, and thereby support achievement of outcomes. In the case of this project,the sophistication of theME system had beendeveloped incrementally over almost two decades, thus the institutional capacity was in placetosupport a complex operation. External controls such as certification instruments at the CAPS level and third-partyverification of provincial level outputs helped to ensure the effectiveness ofTLIs. In some cases, these wereevenmultiple layers of control mechanisms, with the certification of CAPS achievements reported by provinces in turn beingexternally verified.
P133195 | Argentina Second Rural Education Improvement Project - PROMER-II | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099310112232216221/text/P13319501c904e009093a400e28361c7f63.txt | http://documents.worldbank.org/curated/en/099310112232216221/pdf/P13319501c904e009093a400e28361c7f63.pdf | The ICR (pp. 40-41) presented a series of insightful lessons, including: Accurate and timely baselinedata are essential to good target-setting. In this case, reliance on out-of-date baselines necessitated revisions ofindicators and downscaling of outcome targets relatively late in the project period, with negative implications for theprojects outcome rating. Aligning a project with overarching strategic priorities in a sector can help itwithstand shifts in political economy over its lifetime. In this case, the project supported high-level governmentpriorities to enhance both access to secondary education and all dimensions of rural education. This congruence helped theprojects core priorities remain relevant through three changes of government, five different education ministers, and internalunit reorganizations in the education ministry. Although some exogenous factors affecting the costof workscannot be foreseen, the impact of variables related to geographic location, scope, and price variationcan be minimizedthrough exhaustive prior identification and planning. In this case, significant modification of goals related toinfrastructure was required because of inadequate prior planning, including estimates, as well asmajorcurrencydevaluation and inflation.
P133226 | Lebanon Fiscal Management Reform 2 | Middle East and North Africa | Lebanon | IBRD | FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2014 | 2017 | 2018 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/127421518127314514/text/Lebanon-LB-Fiscal-Management-Reform-2.txt | http://documents.worldbank.org/curated/en/127421518127314514/pdf/Lebanon-LB-Fiscal-Management-Reform-2.pdf | The ICR (pp. 18-20) reports extensive lessons emerging from the project, including:In apoliticallyvolatile and uncertain environment, project implementationmay be impacted bypolicy shifts and otherunpredictableevents thatwill requireadapting the projects approach towards achieving the objectives.In this case, the absence of a budget lawrendered progress along most project dimensionsmerely a theoreticalexercise.Government commitment to a dedicated and well-functioning project implementation arrangement iscritical to implementation success. In this case, the absence of a project manager for the majority of the project periodcaused severe delays and bottlenecks, opening the project to micromanagement.Simplicity is the bestapproach in a fragile, politically complex environment. In this case, focus was spread across too many ambitious components,given the challenging overall context.
P133261 | Guizhou Rural Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099063023164574850/text/P13326101257fc0d009fc202bf2cd6dbc0e.txt | http://documents.worldbank.org/curated/en/099063023164574850/pdf/P13326101257fc0d009fc202bf2cd6dbc0e.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1.Establishing productive partnerships between cooperatives and enterprises can be an effective approach to leveraging private sectorinvestments to strengthenagricultural value chains and reducepoverty. The project experience demonstratedthatfarmer cooperatives have proven to be an effective development model for strengthening agricultural value chains andreducing poverty. The innovative model piloted by this project was scaled up by the government and World Bankprograms.2. Insurance against natural disaster risks can be a useful tool to reduce farmersvulnerability against climate risks.The pilot insurance scheme demonstrated its impact on lowering theoperational and climate risks but further efforts are needed for tailored products to address the specific needs of thecooperatives. Farmers in the project area are vulnerable to nature disaster risks, for which more well targeted insurance schemesneed to be developed to address specific needs of the cooperatives.3. Creating an enabling environmentthrough infrastructure development is key tosupporting and developingmarket linkages. Public investments ininfrastructure opened access to markets, lowered transportation and storage costs, and reduced post-harvest waste. It was alsoinstrumental to productivity increases (irrigation) and production upgrading (market infrastructure).
P133288 | Argentina Renewable Energy for Rural Areas Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2024 | 2025 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099121324175575190/text/P133288-1f6f6102-1656-4b9c-b415-d0e2781bac75.txt | https://documents.worldbank.org/curated/en/099121324175575190/pdf/P133288-1f6f6102-1656-4b9c-b415-d0e2781bac75.pdf | This review has drawn three lessons based on the information in the ICR.Inadequate preparation at the appraisalstage when a project is to be implemented by numerous provincial governments can result in significant implementation delays.The project was to be implemented in 20 provinces. This required the signing of 20 agreements between the FederalGovernment and provincial governments. The project was not ready for implementation when it was approved because institutionalarrangements, design of technical specifications, and procurement process were not completed (ICR, p.16). The completion of theseaspects of the project took approximately three years. The project was approved in 2015, but full implementation could only startin 2018. Given that the project had a predecessor that was implemented between 1999 and 2012 (i.e., PERMER I), the project underthis review would have been expected to have had a higher level of preparedness at the start of itsimplementation.If the changes in the project scope are not adequately reflected in the project objectiveformulation through revisions, this can result in gaps in the projects theory of change and underachievement of the projectobjectives. The project was restructured three times because of the narrowing of the project scope and cancellation of theproject funds. These changes resulted in the cancellation of the project activities under the second component such as acquisitionand installation of solar water heaters, solar heating systems, cookers and ovens. The implementation of these activities wereexpected to provide energy-related services to rural households, which is a part of modern energy services together with access toelectricity. The cancellation of these activities made it impossible to achieve the energy-related services objective of theproject. Since the formulation of the project objective was not revised in accordance with the narrowing of the projectsscope, this created a gap in the projects theory of change. Therefore, the assessment of the projects efficacy inachieving the project objective is assessed to be modest resulting in an unsatisfactory outcomerating.Insufficient procurement capacity and complex procurement arrangements can adversely affect the operationaland administrative efficiency of a project. The project implementation suffered from procurement issues through to projectclosing. The complex procurement arrangements involving 20 provinces, each of which had different capacity level, resulted insignificant implementation delays, one of the main reasons for project closing date extensions. Only for the first component, 90contracts were signed. There were delays in evaluation, selection, and award processes. Frequent changes in the authorities or inthe organization of the sector also caused delays in approving the procurement steps. Despite the projects support toprocurement, 34 contracts were still pending at project closing, which were later transferred to the Clean Energy for VulnerableHouseholds and Communities Project (P178553). The ICR (p.23) states that PERMERs procurement experience warrants asystematic review that could be particularly useful in identifying areas to improve and draw lessons for futureoperations.
P133312 | Energy for Rural Transformation III | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099062024185015481/text/P133312-5c6f0fa6-8a6a-45ae-9abc-573a2b5e5f38.txt | https://documents.worldbank.org/curated/en/099062024185015481/pdf/P133312-5c6f0fa6-8a6a-45ae-9abc-573a2b5e5f38.pdf | This review has drawn three lessons based on the information in the ICR.Insufficient capacity, implementation,and supervision of the safeguards policies can adversely affect the achievement of project results and objectives. Projectimplementation significantly suffered from issues related to the implementation of the Involuntary Resettlement and Forestssafeguards policies. These issues were not appropriately reported in the progress reports. About one year before project closing,the project team identified that 50 percent of the distribution line works were completed or started without the compensationpayments to the project-affected people and the agencies that are in charge of forests. The projects non-compliance with thesafeguards policies continued during and after project implementation. The low readiness of the project at the start of projectimplementation was a one of the main reasons because the distribution line extensions to be constructed under the project were notidentified (except two line segments); therefore, Resettlement Action Plans could not be prepared. The weak capacity of the projectimplementing agencies was another reason for the insufficient implementation of the safeguardspolicies.Strengthening of the project implementing agencys institutional capacity during projectpreparation and setting up of a dedicated project implementation unit can be critical in successfully implementing complexprojects. Although the project was the third in a three-project series, the main project implementation agency, i.e., REA,had insufficient project implementation capacity. The project did not finance any upfront capacity strengthening activities duringproject preparation. As the ICR (p.35) reports project preparation did not include establishment of an ERT-3 dedicated teamat REA and staffing levels and composition were inadequate for a much larger project size than the previous ERT phases. Ittook three years after the start of the project for a PIU to be formed but it still had insufficient capacity. The merger of REAunder the DEMD was another setback in project implementation because some specialists left the project, and the institutionalmemory was lost. Procurement, safeguards policies implementation, and contract management suffered from insufficient implementationcapacity.Insufficient assessment of the capacity offinancial markets can result in low achievement of theproject results expected from credit and guarantee facilities offered under a project. The financial intermediaries thatwere to benefit from the projects credit and guarantee facilities found these products risky and marked up the interestrates. These products that were to be used for the financing of solar PV systems were new to the financial market, and because ofthe risks involved in financing solar PV systems, the financial intermediaries offered higher interest rates to hedge their risks.The absence of subsidies to end users for the installation of the solar PV systems was another shortcoming of the project design.The insufficient assessment of the marker resulted in lower demand for these financial products and fewer number of solar PVsystems installed by households.
P133326 | Poverty Alleviation and Agriculture-based Industry Pilot and Demonstration in Poor Areas Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2015 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092723083036018/text/P1333260d36b5f0050bdd90d06012c139bf.txt | http://documents.worldbank.org/curated/en/099092723083036018/pdf/P1333260d36b5f0050bdd90d06012c139bf.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1.TheMETT proved to be a useful instrument to systematically assess the cooperatives in order to establishprofessionalfarmer institutions. Building professional farmer institutions takes time and concerted effortsincludingcapacity building and business development plans duly supported by technical and advisory services.The METTallowstargeted guidance and support tofarmer institutionsfor improving capacity. This needs to proceed at a paceand in a manner according to the knowledge/skills base and absorptive capacity of the target group which is oftenoverestimated.2.Improvingpublic infrastructure and services not only enhanced local connectivity andmobility, but alsoachieved economies of scale; and reduced production and transport costs. Farmer cooperativesbenefitted from the improved infrastructure and support services provided by the provincial governments to complement the projectinvestments. Improved roads, irrigation and drainage, internet, utilities, quality testing and certification facilities, andextension services improved local farmers and cooperatives mobility, product processing and value addition, andaccess to input and output markets; and reduced pre- and post-harvest losses.3.Effective links to markets isacritical element to ensure sustainable business success. Through developingthe entire value chain andestablishing successful market connections, the cooperatives were able tosell their products at better prices in the nichedomestic and international markets and earn higher profits. There are several key ingredients to this success including: businesscontracts with the private sector to invest in their value chains; registration of the trademark/brand name as a mark of highquality and recognition of the product; quality certification, that is, green product and organic product; and the use of allavenues (traditional wholesale markets, direct sales to supermarkets and businesses, and e-commerce channels) to access local,regional, national, international, and niche markets.
P133327 | TAJIKISTAN SECOND PUBLIC EMPLOYMENT FOR SUSTAINABLE AGRICULTURE AND WATER RESOURCES MANAGEMENT PROJECT | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/660511619452584150/text/Tajikistan-PAMP-II.txt | http://documents.worldbank.org/curated/en/660511619452584150/pdf/Tajikistan-PAMP-II.pdf | The ICR lists a number of useful lessons. The following are highlighted by IEG with some modification to thelanguage:1. The inclusion of relevant technical assistance in the project design could enable enhancement offarm productivity.Surveys under the project revealed that irrigation related interventions need to be clearly linkedto agricultural on-farm support and improvement of the food value chain. The feedback indicated that farmers need to be trained touse water efficiently and to switch to better farming methods. Further gains could be realized from providing support forimproving the value chain and providing a linkage to markets.2. The project demonstrated that public worksprograms to counter periods of high unemployment and negative effects of economic shocks can prove successful, but cannot serve asa social safety net as some groups may be excluded from the benefits from these programs, like for example, people withdisabilities or those unable to undertake heavy labor. The government needs to supplement such programs with other means directedto the target population.3. A lack of appropriate project level indicators to measure increase in crop yields maylead to difficulties in attributing a potential increase in crop yield to the project. Under this project, yield increasescould not be attributed to the project, not only for lack of relevant indicators but also as factors beyond access to irrigationmay affect crop yields, such as for example weather and climate conditions and the farmers access to farm inputs andtechnology.4. Without a flexible design and implementation approach it may proved difficult to effectivelydeal with emergency situations. This project needed to deal with an emergency situation under the second restructuring,and it then became apparent that a somewhat more flexible design and implementation approaches wouldhave enabled betterresponsiveness.
P133333 | Senegal Quality and Equity of Basic Education | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099090623115514194/text/P1333330d963d70a70b32800176e97087d4.txt | http://documents.worldbank.org/curated/en/099090623115514194/pdf/P1333330d963d70a70b32800176e97087d4.pdf | IEG has synthesized the lessons presented in the ICR (pp. 40-41) as the following:Establishing a feedback loopfrom central, decentral, and school levels that uses the information from student learning assessments shifts the focus to improvedlearning, which is a necessary step. One of the mechanisms the project used was performance-based contracts thatresulted in schools, head teachers, and school management committees examining learning data, after receiving capacity developmentto discuss how to use resources provided by MOE to improve learning.This was complemented with other actions to supportlearning by central and decentral levels: training (to understand the data and how to improve teaching practices) andinspection.The government has expanded the approach throughout the country.These actions are important and necessary,but not sufficient, to improve student learning. Otheractions are also needed across the system to ensure system coherence insupport of learning: curriculum and teaching, capacity across all levels of the system, and politicalcommitment.Sound policy dialogue based on evidence and contextual understanding can play a role in creating apathway between the conventional education system and the Koranic education system. This project strategically launched acompetitive process to support Daaras that were willing to integrate French and mathematics into their traditional curriculum. Thiswas done through awareness-raising, continuous dialogue, the involvement of Koranic teachers, and patience, as well as contextualunderstanding. These sustained effortsled to the introduction of French and mathematics in the project-supported Daaras. Theprojects evaluationshowed the approach was working and opened an important dialogue on expansion of the activities toother Koranic schools. This is important for the country to have children with literacy and numeracy skills, since the level ofeducation is related to individual future earnings and poverty.This also shows the importance of the Banks contextualunderstanding and dialogue.Emergency crisis situations such as the global pandemic require flexibility and canpresent opportunities for change. The outbreak of COVID-19 showed that the Bank team was able to react quickly tounforeseen events and to find the means in the financing agreement to help the country deal with unexpected situations. During thepandemic, formal schools were closed; however, Daaras remained open. Because of the health concerns and needs of the Daaras, theproject supported 1,000 Daaras with food, sanitation kits, and sensitization on social distancing. Additionally, the project teamand MOE held discussions to establish mechanisms to ensure learning continuity during the pandemic. As a result of these timelydiscussions, the Banks follow-up operation aims to provide learning continuity throughout the education system through digitaltechnology, broadcast, and radio.Changing attitudes and access to mathematics and science for all students --regardless of ability and gender -- requires a comprehensive approach. This project had an incomplete set ofactivities to improve access to math and science,which was a design weakness. Other activities directly changingteachers skills and attitudes and behaviors would also be needed. Moreover, the governments national scienceimprovement strategy was delayed.As a result, some on the Orientation Committee viewed access to mathematics and science as only forcapable learners. In a decentralized system such as Senegals, central-level actions are necessaryto supportaccess to mathematics and science in the form of well-defined strategies and decrees, butimplementation also requiresbuilding capacity among decentralized levels to ensurethe competencies and awareness that all learnersneed access tomathematics and science. It also requires provision of resources and training for decentralized levels and teachers. Projectimplementation shows the importance of engaging with diverse group of stakeholders, particularly in relation to gender norms.
P133338 | CAMEROON--Equity and Quality for Improved Learning Project | Western and Central Africa | Cameroon | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/872171597418493804/text/Cameroon-CM-GPE-Support-to-Education-Sector.txt | http://documents.worldbank.org/curated/en/872171597418493804/pdf/Cameroon-CM-GPE-Support-to-Education-Sector.pdf | The ICR(pp. 49 to 50) offeredseveral lessons for projects, including the following adapted byIEG: Flexible disbursement-linked indicators (DLIs), which are easily understood by keystakeholders and adjustable to incentivize reforms, promote the achievement of development objectives. DLIs ensure thatfunds benefit the implementing entities and ease implementation in complex geographical and political contexts. The unfamiliarityofa national team with the DLI approach can negatively impact the timely compliance with the planned schedule. Similarly,crises like the ones from refugees and anglophone region in Cameroon, also lead to disruptions in Government expenditures, causingdelays that compromise the efficiency of DLI financing (ICR, p. 42). The use of existing government structuresrather than a separate implementation unit, complemented by Bank backstopping, facilitates implementation and ownership.Such combination facilitated high government ownership, the timely provision of appropriate capacity building, and the use ofeffective coordination mechanisms. In addition, the presence of at least one locally based staff helped to strengthen theBanks supervision ability and ensured completion of planned activities. When selecting project developmentindicators, the unavailability of baseline data is a challenging factor for measuring progress toward the achievement ofobjectives. Data that is irregularly administered and controlled by an entity not involved in the project, or affected byexogenous factors such as insecurity worsening, hindered the projects ability to collect baseline data and to assess keychanges sought by the project. The CEQUILs absence of baselines caused that the increase in quality of learning could not bedetermined. In conflict-afflicted contexts such as Cameroons, easy-to-implement interventions that adjustto local situations reduce the risk of not achieving outcomes. The CEQUIL project demonstrated that rapid resultstrategies and the budget transparency Initiatives helped accelerate implementation and foster governance, although notsufficiently enough to ensure smooth activity implementation.
P133352 | HT Center and Artibonite Regional Development | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2021 | 2021 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/807131624279233730/text/Haiti-HT-Ctr-Artibonite-Reg-Dev.txt | http://documents.worldbank.org/curated/en/807131624279233730/pdf/Haiti-HT-Ctr-Artibonite-Reg-Dev.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. In fragile and conflict affected countries, a simple project designtailored totheimplementation capacitiesmay be helpful in ensuring project implementation and results. This multisectorproject with multiple entities proved challenging in Haitis operational context.2. Transferring contractsbetween Bank-financed operations should be used as a last-resort solution. The grant for this project was partiallycancelled from this project andtransferred to another project. Given thattransferring contracts between projectsrequires a significant amount of time and resources, such a course of action, should only be adopted as a last-resort solution(especially when multiple contracts needto be transferred).3. In capacity-constrainedenvironments, recourse to Delegated Project Management (MDOD) may facilitate implementation and allow implementing agencies tofocus on their core competencies. The recruitment of MDODto implementroad works and other market works provedto be instrumental in speeding up implementation following the project restructuring in this project.
P133380 | AFCC2/RI-Zambezi River Basin Development Project | Other | Africa |  |  | Sustainable Development | Water | RETF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/876511585336840634/text/Africa-Zambezi-River-Basin-Development-Project.txt | http://documents.worldbank.org/curated/en/876511585336840634/pdf/Africa-Zambezi-River-Basin-Development-Project.pdf | Incorporating a realistic time-frame for large hydropower projects that span more than one country client,especially those with less capacity, can be critical to improving project design. The project was restructured three timesto extend the project closing date and encountered several delays that increased project cost. The project component outputs werenot completed at project closing. A more realistic time-frame- knowing the complexity of these types of projects with low capacityclients- could have helped avoid these delays and costs. Anticipating the need for and planning stronger capacitybuilding support for clients with less experience in conducting feasibility studies for large complex hydroelectric schemes canmitigate risks related to implementation (like procurement) more effectively. The ICR states that while the risksidentified during preparation were generally accurate and mitigation measures were in place, there were still delays to theproject. Having well-designed governance structures for projects that are transboundary in nature involvingmore than one government can positively impact the speed at which decisions can be made to move the project forward. TheICR mentions that one of the causes for delays in implementation was the slow pace of decision making due to the need for agreementfrom high level government officials of two countries.
P133424 | Public Financial Management Improvement and Consolidation Project | Western and Central Africa | Sierra Leone | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099102323084541467/text/P1334240d840580280a3c80cf54a3c680e1.txt | http://documents.worldbank.org/curated/en/099102323084541467/pdf/P1334240d840580280a3c80cf54a3c680e1.pdf | ThisICRR expands on some of the key lessons fromthe ICR (pp. 38-40), which are: Theimplementation of a PFM reform strategy requires all stakeholders to be fully engaged, with dedicated focal points across thegovernment toensure that issues are addressed in a timely manner, and that the implementation of activities may be adjustedto evolving circumstances. The introduction of modern information technologyprocesses requires a number ofprerequisite measures to ensure a seamless transition from existing systems in place, which is particularly important in fragileand conflict-affected countries such as Sierra Leone. Such measures include, most notably, a clear description ofprocessesand requirements, adequate training of users and external auditors to ensure that new systems are fully utilized, and capacitybuilding for key users and auditorsto undertake their roles effectively in the PFM system. Thegovernments capacity to implement a project must be carefully considered at appraisal, and adequate technical assistanceshould be provided throughout project implementation.The ICR also elaborates on the factors that should beconsidered at the project design stage of any future PFM project in Sierra Leone based on the PPAR of the predecessor project thatwas undertaken (i.e., the Integrated Public Financial Management Reform Project dated March 28, 2018). These factors consistof: The existence of extra-budgetary funds that are not subject to parliamentary scrutiny (including for example theuse of donor funds). Supplementary budgets that are not submitted to Parliament and include variations on approvedbudgets. Centralized payment approval processes that lead to inefficiencies. Connectivity issues that limit thelikelihood that citizens can access information published on websites and open data portals. SAI dependence on the MoFfor adequate funding. Weak risk management and control environment at MDAs and local councils Low buy-in for anenhanced role for audit committees and enhanced PAC scrutiny
P133445 | Liberia Accelerated Electricity Expansion Project (LACEEP) | Western and Central Africa | Liberia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092523094537736/text/P13344504db4320820ad8709ede1b720010.txt | http://documents.worldbank.org/curated/en/099092523094537736/pdf/P13344504db4320820ad8709ede1b720010.pdf | IEG derives the following lessons drawn from the ICR:1. The Bank Groups reengagement in the energysector in FCV countries calls for sustained coordination and dialogue with both Government and other development partners (DPs) toachieve maximum synergy. This project was part of a multiphase programmatic approach for providing support to theenergy sector, and the World Bank was engaged with several other DPs, such as USAID/MCC, JICA, EU and the African Development Bank(AfDB), who were all engaging with Liberia through key investments in the sector. The process of coordination andharmonization of the priorities and contributions of individual DPs to the countrys short-term and medium-term goals was notwithout challenges which explains some of the shortcomingsin the projects results (e.g. the weaknesses intechnical and institutional capacity). The coordination was helpful however in enabling a comprehensive program to bedeveloped to support the modernization and diversification of the countrys electricity sector, with the Bank providingseminal support to Liberias energy subsectors, and each DP providing specific investment support in electricity generation,transmission and management.2. Having an ME specialist within the PIU matters for close projectmonitoring and implementation reporting. As Liberia was a post-conflict country, technical capacity was scarce inthe PIU, notwithstanding which the hiring of an ME specialist was not considered a priority. During implementation, andby project closing, the absence of such a specialist made project monitoring and implementation reporting definitely morechallenging. This also affected ICR preparation (see ICR, p.33), as the PIUs institutional memory was found to belacking, as there were no specific ME staff to monitor, record and report on the projectsimplementation.3. Planning in the electricity sector needs to go beyond short- and medium-termobjectives. Under the project, construction of HFO storage tanks was prompted by a short-term need without along-term view. When electricity generation progressively switched over from thermal to hydro generation, the storage tanksconstructed ended up being underutilized. Current hikes in HFO prices viewed against more recent developments in renewableenergy suggest that focusing on purely short-term needs can lead to suboptimal decisions in a longer-term context.
P133446 | Electricity Supply Accountability and Reliability Improvement Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/587321607723922360/text/Kyrgyz-Republic-Electricity-Supply-Accountability.txt | http://documents.worldbank.org/curated/en/587321607723922360/pdf/Kyrgyz-Republic-Electricity-Supply-Accountability.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Advanced project preparation, including bidding documents for procurement of goods and works, can helpin speeding project implementation. The preparation of this project was expedited by the resources from the Europe andCentral Asia (ECA) Capacity Development Trust Fund Grant. This helped SE in preparing the investment program, including priorityinvestments based on transparent and justified criteria, and bidding documents for procurement of goods and works. This aided inspeeding implementation.2. Dissemination of international best practices can be critical forutilitiesoperations. This project continuously provided proactive capacity building to SEs personnel through workshops andstudy tours in Uruguay, Georgia, India, Italy and Kenya to learn frominternational experience ongovernance, procurementand financial management.3. To ensure sustainable development in the medium and long term, institutionalreforms are necessary. Although SE has put in place some governance improvement measures, SE and other utilities will beable to better plan and recover its capital and maintenance expenses and improve its financial standing, only withamedium-term tariff policy that enables cost recovery, accompanied bysocial protection schemes that encourage energyconsumption.
P133456 | Sichuan Chongqing Cooperation: Guang'an Demonstration Area Infrastructure Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099090723132032346/text/P1334560e513560bd0957c07095db3086b9.txt | http://documents.worldbank.org/curated/en/099090723132032346/pdf/P1334560e513560bd0957c07095db3086b9.pdf | The operations led to four lessons with slight modifications below (ICR, paragraphs 79-82) Towns maybridge the rural-urban divide by adopting area-based economic policies and urbanization strategies. This project usedadequate infrastructure and other urban servicesas a springboard to show how local governments may address the urban-ruraldivide. Regional disparities, smaller cities, and towns within metropolitan areas maybe effectivelinks.Improvedservice delivery, transportation networks, and educational and employment opportunities may facilitate better connectivity and morelivable urban areas and, with the skills training, lend itself to addressing poverty. Technical assistancemay complementinfrastructure investments to provide a comprehensive urbanization and city planning approach.Long-term planning and infrastructure are interlinked as increasedlivability is made possible by improved service delivery,attracting additional investment and opportunity. The project designed its TA to maintain and operate the current infrastructureinvestments andsupport the long-term objectives of attracting investors and tapping into growing sectors of the regionaleconomy. This has been strengthened by building capacity for project delivery, asset management, capital investment planning,private sector participation, and investment promotion and branding, which will benefit the towns beyond the projectcompletion. Projects in China that require land acquisition and resettlement may benefit from securing permitsearly, designatingstaff to monitor progress, or reducing resettlement needs. In this project, implementation delayswere due toland acquisition and resettlement needs.Lengthy government approval processes following Chinese law.coordination needs because of different agencies managing various affected structures, such as fiber optic lines and power gridtowers that would be affected by road construction.To mitigate resettlement and compensation-related delays, necessarypermits may benefit from advance planning. design Investments may benefit from avoiding or reducing relocation needs. Designatingkey personnel in the respective local governments and focal points to coordinate the processes across various agencies may helpavoid implementation challenges. Multi-city projects may offer knowledge-sharing opportunities.Inthis project, two towns implemented two similar activities. Promoting their coordination allowed for opportunities to exchangeideas and learn from each other on effective measures to improve service delivery and factorstoincreaseefficiency.The implementation arrangement, withan umbrella Project Management Office PMO, andactiveparticipationin the World Bank supervision missions led to practical capacity-building activities. These jointefforts facilitated opportunities to gain experience from each other andincreased vertical and horizontal coordinationbetween government agencies. Multi-sectoral coordination also improved the LVS training curriculum and calibrated the courses torespond to regional industry employment needs.
P133531 | Shanxi Gas Utilization | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2014 | 2021 | 2023 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099315011232235656/text/P13353103f2d07098086c303ffcc49b01aa.txt | http://documents.worldbank.org/curated/en/099315011232235656/pdf/P13353103f2d07098086c303ffcc49b01aa.pdf | IEG derives the following lessons drawn from the ICR:1. When a project outcome is contingent onGovernment policies, reforms and regulations, that need to take place to enable project implementation, there is a need to managethe risk that these reforms may not take place in time, or be modified by changing priorities and circumstances. Inthe case of the project in question, the change in central and provincial energy strategy, which resulted in the CHP plants beingused for peaking purposes only, undermined their commercial viability, and hence the outcome of theproject.2. Covenants should be used if the commitment of the client is confirmed and the Bank has thecapacity to act in the event of non-compliance. For the project in question, a revision of electricity tariffs wasessential to the success of the operation. However, the upfront commitment of the Government was less definite that appearedat the outset. When the tariff covenant was breached, the Bank had no real recourse and had to accept the non-compliancedespite the negative impact on the projects outcome. 3. Given the complexity of energytransition, the Mid-Term Review can play a critical role in providing the opportunity for a restructuring to adjust the design:In the case of the project in question, country and sector priorities changed, necessitating a more fundamentalrestructuring of the operation in terms of design and objectives - than actually took place, for the project to produce asatisfactory outcome.4.Clarity is needed on the role of gas in the overall energy strategy of acountry, when financing a project based on gas utilization. Usage of gas in the power sector of countries previouslydependent on coal has seen challenges as a result of volatility in price of gas, at a time when reduced costs of renewable energyand battery storage. This has made gas power less viable as base load for power plants, resulting in gas power being utilizedonly as peaking units to stabilize the grid. Against this background, there is an urgent need forboth the provincialand central governments in China to review and clarify their energy sector strategic priorities as regards the use of gas, goingforward.
P133557 | Education Sector Strategy Support Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2013 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/757171553265438107/text/Nicaragua-Education-Sector-Strategy-Support.txt | http://documents.worldbank.org/curated/en/757171553265438107/pdf/Nicaragua-Education-Sector-Strategy-Support.pdf | The ICR lists six lessons (p. 28). Among these, IEG highlights and adapts thefollowing:Ensuring donor coordination at entry in multi-donor projects and ensuring that design isaligned with implementation capacity are critical for avoiding implementation delays. On the one hand, the lack ofagreement between the WB and the EU at entry led to a lengthy negotiation to settle the terms of the agreements thatdelayed implementation. On the other hand, the project design overestimated the implementing agency capacity to manageinfrastructure works. This overestimation led to important implementation bottlenecks that required intense supervision to becorrected.In addition, IEG also add another lesson related to monitoring andevaluation:Demonstrating nationwide education quality improvements requires evidence that schoolresources and teacher quality inputs reached a critical mass of schools and teachers in all school districts. In theabsence of this data, the credibility of a project achievements with respect to nationwide education quality improvements can bediminished. Given data constraints, the ICR did not include this data which had to be later provided by the World Bank team tostrengthen the results narrative.
P133590 | Second Kampala Institutional and Infrastructure Development Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099050324175020398/text/P1335901f69c440b41b63012e0e268cad14.txt | http://documents.worldbank.org/curated/en/099050324175020398/pdf/P1335901f69c440b41b63012e0e268cad14.pdf | The operationofferedthe following lessons: Segmenting the implementation of a road projectmay overcome challenges to rights of way by allowing the resettlement and compensation processes for unchallengedsegments toproceed and limit implementation delays. In this project,practices were adopted to move implementationforwardeven as resettlement processes were challenged.Roadworks were divided into sections, and contractors startedconstruction on sections where the right of way was fully acquiredwhile resettlement issues on others wereaddressed.The project addressed resettlement related complaintsby sharingclearresettlement and compensation guidance withallstakeholders,PAPs, and local leaders. Applying an integratedapproach to planninginfrastructure improvements in a neighborhood may benefit implementation. Thisproject took a linear sequenceapproach to infrastructure planning and upgrading. This led to occasionalflooding and damaged sections as completionsproceeded down the line. This generated complaints. Time consuming contract variations were used to resolvethese.Anintegrated area-wide infrastructure improvement planmaybetter address various infrastructure needs of affectedneighborhoods without causing unnecessarydisruptions or overflowsin neighboring areas. Aneffective communication strategy may facilitateimplementation. In this project, significant challenges resultedfrom alack of accurate information on the location of utilities, delays in relocation of utilities and high relocationcosts.Those affected by proposed improvements may benefit from periodic updates onwhat to expect, timelinesinvolved,locations, and implications on their daily existence. Improved coordination and effective information sharing wouldimprove on planning of these services, reduce conflict or misunderstandings, and may result in savings of time andmoney. If appropriate outcome indicators are not identified reflecting aholistic view of urban mobility(e.g., indicators to measure travel times, road safety, pedestrian use, etc.) the project may lack the evidence to measuresignificant outcomes.In this project, the ME indicators were not sufficient to reflectvarious aspects ofurban mobility. A more comprehensive approach would have included the convenience, safety, and comfort of urban mobility,fromthe points of view of pedestrians and riders of both private and publictransportvehicles. Includingmitigating measures in designing infrastructure investment may overcome low OM capacity. In this project,mitigating measuresdid not address the sustainability risks to infrastructure investment (roads, streetlights, traffic cameras,drainage channels, etc.) Detailed OM plans and budgetsmay be usedto guide development partners and otherstakeholders onrealistic obligations.Financial and otherresources may be classified intoshort and mediumterms. Obligationstomaintain the infrastructure assets could be part of the design package,includingsettingup clear processes and conducting information campaigns such as when acquiringrights of way are needed. Keeping records andestablishing clearrights of way for infrastructure may help define uncontestable reserves and protect futureneeds.
P133591 | Ethiopia Water Supply, Sanitation and Hygiene Project | Eastern and Southern Africa | Ethiopia | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099000008312220716/text/P133591051c02e05c0ade101216ad1d1fda.txt | http://documents.worldbank.org/curated/en/099000008312220716/pdf/P133591051c02e05c0ade101216ad1d1fda.pdf | IEG derives the following lessons drawn from the ICR:Successful harmonization of donor support requires theactive involvement and strong commitment from the government and development partners. Bringing multiple developmentpartners together in one program required considerable negotiation and compromise on the part of the development partners to reachagreement on what fiduciary and safeguards policies would apply. The leadership of the Ministry of Finance and Economic Developmentwas critical in encouraging the development partners to reach agreement on a programmatic approach. The commitment and leadershipof World Bank team was instrumental in driving the process forward, even following Board approval of the Bank-financedproject.Using a programmatic sector-wide approach in a fragile-country context helps to reduce conflict.Pooling development partners resources created a large enough budget envelope to reach communities across the country. The use ofone plan, one budget, one reporting system and one consolidated WASH account, meant that the same approach applied across thecountry, minimizing tensions between regions.Overcoming capacity gaps requires continuous and tailoredsupport. There are significant regional differences in capacity of implementing agencies, particularly at the local level.The project did not sufficiently tailor training programs to reduce the capacity gaps, which remained evident throughout theproject implementation period. More intensive efforts to build the capacity of weaker implementing agencies would help to close theregional capacity gaps.Ensuring that plans and designs for infrastructure are ready by effectiveness and thatimplementing agencies have filled key staff positions reduces implementation delays and increases efficiency. Some of theplans and designs for large urban water systems were undertaken during the project implementation period, which delayedconstruction of works. Some implementing agencies did not hire key personnel, such as project managers and safeguards specialists,long after effectiveness. Learning from these lessons, phase 2 of the project includes criteria that newly-nominated woredas mustcomply with before managing project-financed activities. These criteria include establishing (or strengthening) woreda water teams,assigning qualified personnel to plan and manage the activities at each sector office, nominating a focal point to providesafeguards oversight. Further reducing delays, rural piped water schemes that cross woreda boundaries, are managed at the regionallevel, instead of at the woreda level.
P133592 | Ethiopia Urban Local Government Development Program II | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | PforR | 2014 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/498001615841290441/text/Ethiopia-ET-Local-Govt-Dev-Project-II.txt | http://documents.worldbank.org/curated/en/498001615841290441/pdf/Ethiopia-ET-Local-Govt-Dev-Project-II.pdf | The ULGDP II PforR aimed to build capacity and help strengthen a governments resolve to use urban development as a buildingblock to economic growth. The ICR offered nine lessons that were considered in the follow-on PforR Urban Infrastructure andInvestment Development Program and thattask teams may consider for similar future operations.Some of these arepresented below with slight modifications. Effective decentralization that strengthens local governmentsrequire a long term commitment and partnership. This program benefited from a series of urban operations. The governmentused lessons from these operations to pursue decentralization by strengthening institutional capacities ofcities. Incorporating an incentive to exceed performance targets provides participating localgovernmentsan avenue to own investment results. In this program, ULGs, who exceeded performance targets wererewarded with 20 percent more resources to their regular population-based allocation. Performance grants accounted for 35 to 85percent of their local capital budgets. Additional resources meant more local infrastructure investments.The governmentsynchronized its commitment to use all levels of government, from federal, to regional, to local governments, to achieve thisgoal. The different levels of government have different ways to address local government capacity gaps.In this program, implementation discovered that federal support may be timed differently or require a different set of technicalskills (e.g., conduct of Annual Performance Assessments) from capacity support provided by regional entities (e.g., value for moneyaudits). This lesson informed the follow-on PforR program to include an Investment Project Financing window for targetedinstitutional capacity building. Strengthening indicators by including professionaldesignelementsmay helpensure the quality ofinfrastructure investments. In this program, some ULGs did notengage professional design or supervision consultants for their projects and ran the risk of poor quality of completedworks.DLIswere achieved withoutthese aspects of contracted works. Mechanisms to address capacity gaps that reduces the risk of poorly executed works may be needed. One way this risk was mitigated in this project was the conduct of value formoney audits of completed projects. But ex ante mechanisms through clearelements of indicators may prove usefultoo. Having viable business plans and OM arrangements of infrastructure early on increases the chances ofoperationalizing completed infrastructure. In this program, some infrastructure such as abattoirs andmarkets did nothave business plans or OM arrangements prior to completion. Such plans mayidentify potential private sectorparticipation in investing inrevenue generatingeconomic infrastructure and could identify challenges posed by importrestrictions or availability of trained manpower to run the completed infrastructure investments. Adopting anindependent monitoring and evaluation (ME) function increases accountability and transparency of government sponsoredprograms. In this program,an independent consultant conducted the ULG performance assessments using consistentindicators monitored under the ME systemto trigger disbursements. Predictable periodic reporting helped establishaccountability. Achieving targets facilitated transparency. Challenges faced in monitoring and achieving indicators in publicfinancial management, for example, informed the additional performance indicators adopted under the follow-on PforR program.Astrong ME system usingindependent performance verificationincreases transparency and fosters accountabilityin delivering services at all levels of government.
P133613 | Ethiopia Geothermal Sector Development Project | Eastern and Southern Africa | Ethiopia | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099122324155539400/text/P133613-b67fdada-929a-479a-8801-43eba118ef6e.txt | https://documents.worldbank.org/curated/en/099122324155539400/pdf/P133613-b67fdada-929a-479a-8801-43eba118ef6e.pdf | The following lessons were derived from the ICR (ICR, pages 20-21):1. Limiting project ambition and scope withconsideration of the countrys institutional capacity and resource limitations can support the achievement of outcomesbetter. In the reviewed Project, the scope was overambitious, and the Project had to be restructured as a result, with asignificantly reduced scope. The limited capacity of the EEP and PIU, and the design that separated procurement of drilling rigsand drilling services, added to implementation risk. An adequate assessment of this risk at the design stage was needed but notconducted, negatively affecting Project performance. 2. Proper analysis, strategy formulation andimplementation planning ahead of project commencement provides an important basis for effective and efficient projectimplementation. In the reviewed Project, implementation plan had deficiencies, and the process of negotiating a new planwas lengthy and complicated, affecting Project outcomes. If an adequate assessment were done during Project preparation, theeventually negotiated (by the government, EEP, and the Bank) efficient implementation strategy could have been pursued from startand delays avoided.3. Absorption of the geothermal exploration risk by public sector is a win-win strategy becauseit supports de-risking of the geothermal development overall and enables private sector participation at the next (less risky)phases of geothermal plants construction and operation. Comparison between the reviewed Project and parallelprivate sector concessions demonstrated that the upfront investment required for the exploration stage is too large and risky forthe private sector, and when the upstream and downstream activities are combined in a private sector project, the expected returnmight be even lower.4. Ensuring adequate implementation capacity and systems at the project preparation stageprovedcritical for successful implementation. In the reviewed Project, the PIU was established and staffed, but therelated due diligence had shortfalls, and not all systems were ready, including those for procurement and financial management(FM). Procurement capacity needed strengthening, but this process was delayed. The FM system was not fully in place. Projectperformance would have significantly benefited if all systems were in place at the start of implementation and retained throughoutimplementation.
P133620 | Strengthening Safety Nets Systems - MASAF IV | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050104272218095/text/P1336200c06c340b108103069b1d0d77dda.txt | http://documents.worldbank.org/curated/en/099050104272218095/pdf/P1336200c06c340b108103069b1d0d77dda.pdf | The ICR provided useful lessons learned (p. 39-41), which were adapted by IEG: Linking different coreprograms that support livelihoods with each other is critical for helping the ultra-poor and vulnerable communities. Inthis project, beneficiaries of safety net programs (for example the SCT and PWP) were connected to other programs that aimed toenhance their skills, incomes, and livelihoods (for example LiSD/COMSIP) allowing for a wider approach to support the ultra-poorgetting out of the poverty trap. Consolidating accounting and reporting requirements/procedures between differentdeveloping partners (DPs) would improve efficiency. The multiplicity of accounting procedures and requirements ofdifferent DP put a burden on project implementors at the district and national level. If a program wide e-payment system does notexist, the Integrated Financial Management Information System (IFMIS) should be used for financial recording, transactions, andreporting by local and national authorities. Communicating results and providing information about the GRM iscritical for the sustainability of a program. In the case of the SCTP many beneficiaries are still not fully aware ofimportant processes such as beneficiary targeting and selection procedures resulting in doubts of the fairness of the beneficiarylist. Also, providing information about the GRM would allow communities to raise concerns.
P133653 | Municipal Governance and Services Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051123151066617/text/P1336530ed714c0ea09eba026479cf18554.txt | http://documents.worldbank.org/curated/en/099051123151066617/pdf/P1336530ed714c0ea09eba026479cf18554.pdf | The ICR (p. 28) included several lessons learned, which were adapted by IEG: For performance-based grantsto have long lasting effects they need to be institutionalized. The experience of this project indicates thatperformance-based grants are effective in promoting governance reforms at the ULB level. However, these grants need to beinstitutionalized and the following steps need to be taken: i) designating the entity responsible for administering theperformance-based program; ii) scaling-up the program to cover all ULBs; iii) making monitoring and publishing the performance ofall Local Government Institutions (LGIs) by the government mandatory; iv) providing an incentive for LGIs to benchmark andconstructively compete with each other; v) establishing a legal basis for the National Government to allocate funds forperformance-based grants on an ongoing basis either from internal government resources or from development partners; and vi)establishing a strategy for LGIs to graduate. Providing local entities with the right tools andunderstanding as well as encouraging them to plan beyond their respective political jurisdictions can allow for the identificationof larger scale investments that benefit more people. In this project, the introduction of Capital Investment Planningallowed ULBs to identify larger scale investments with greater impact on their constituents. When acountry has systematic procurement challenges it is critical to identify appropriate mitigation measures during projectpreparation. This project experienced procurement related delays and might have benefitted from multiple smallerconsultancy packages to reduce the risk associated with larger contract procurement.A lesson added byIEG: Participation and empowerment of women was a fundamental feature of this type of project resulting inthe project exceeding the target for female beneficiaries. In this project, sub-projects were prioritized through alocal participatory process with women actively engaging and presenting the plans. Also, the project promoted greater economicopportunities for women through the Social Management Plans, which provided commercial infrastructure for women. As a result,the project benefitted 3.34 million women against a target of 1.67 million.
P133663 | Malawi Economic Recovery Development Policy Operation 1 | Eastern and Southern Africa | Malawi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2016 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/168691467996667603/text/ICRR14889-P133663-PUBLIC.txt | http://documents.worldbank.org/curated/en/168691467996667603/pdf/ICRR14889-P133663-PUBLIC.pdf | IEG agrees with the three lessons identified in the ICR and rephrased below: (i) IEG concurs with the finding that there are immense risks linked to a partial reform syndrome, a situation where governments undertake reforms at a superficial level, and produce the form but not the substance of modernized institutions. The breakdown of Malawi's PFM that occurred in 2013 underscores the need for a thorough grasp of the local political economy of reform and the importance of looking beyond the formal rules-based systems, and a good understanding of the underlying informal arrangements that allowed for collusive behavior to take place.(ii) Lessons from the 2013 theft point to the need for increased use of independent verification methods to confirm the actual status of reform measures adopted, particularly with regards to PFM systems and controls, and more specifically to careful exploitation and use of the PEFA reports and recommendations.(iii) The experience of this operation points to the need for a strong focus on timeliness of fiscal information and integrity of fiduciary systems. In particular, establishing the integrity and strength of fiduciary systems and expenditure controls need to be the priorities in any future budget support operations. Furthermore, this experience suggests the need to narrow the scope of structural reforms to the most macro-critical areas where achieved progress would be harder to reverse after the completion of an operation.
P133664 | Macroeconomic Stability for Competitiveness and Growth Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2017 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/956271593553374456/text/Ghana-GH-Macro-Stability-for-Competitiveness.txt | http://documents.worldbank.org/curated/en/956271593553374456/pdf/Ghana-GH-Macro-Stability-for-Competitiveness.pdf | IEG draws three lessons from the series, which overlap those of the ICR.IEG concurs with theobservation in the ICR that a policy-based guarantee can be a useful instrument for debt restructuring. In the case of Ghana, therefinancing of the debt reduced pressure on the government and on the exchange rate that arose from the very short-term nature ofthe countrys debt.Close working relations between the government and the Bank strengthens not onlyspecific reforms incorporated into the series but can also enhance more generally a government reform program. In the case ofGhana, the extensive analytical foundation and continuing diagnostic work not only allowed the series to be prepared within a shorttime frame when the need arose as a result of the crisis, but also provided a foundation for the future preparation ofassistance.When elections overlap series operations, continuity risks can be reduced by briefing keyopposition politicians on the rationale for reforms, progress to date and expected results. An awareness of electoral cyclesis necessary in order to ensure that significant changes in government priorities do not compromise the final operations in aseries. In Ghana the change of government in 2016 and its changing priorities led to the cancellation of the thirdoperation.
P133687 | Mozambique - Financial Sector DPO | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2015 | 2015 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/957821561383950690/text/Mozambique-Financial-Sector-DPL.txt | http://documents.worldbank.org/curated/en/957821561383950690/pdf/Mozambique-Financial-Sector-DPL.pdf | Two lessons are drawn from the ICR (pages 29-30), with some adaptation, anda third is added by this ICR Review.Solid analytical grounding, close donor coordination, and extensive technical assistance are important in thepreparationand implementation of structural reforms in the financial sector, particularly where institutional capacity isweak. Challenges to the stability and development of the financial sector in Mozambique weredaunting, but thecountrys capacity toplan and implement sector reformprograms was weak. The Bank, the IMF and otherdonorsextended TA to the government to help upgrade the implementation capacity of the BDM andBDMcapably issuedregulations to improve risk management in banks. However, the BDM faced capacity constraints proceeding to the next set ofreform measures and was delayed in raising the minimum capital requirements for banks and in establishing a crisis managementcommittee, two measures that were designated as triggers to FSDPO II but instead delayed as triggers to FSDPO III.Governments mustmake mid-term assessments of a programmatic series and be flexible to adjust course ifnecessary. The moderate accomplishment of the third objective suggests thatthe government could have carefullyassessed progress with the implementation of the reform plan before the closing of FSDPO II in mid-2016 to determinewhetherthe program had not made enough progress with the third objective to develop the long-term financial markets,beforeproceeding withplans for the FSDPO III. Following the cancellation of FSDPO III, the government returned tofocus on a more elementary concern associated with the first objective to reinforce financial stability by securing approval forthe Bank Resolution and Deposit Insurance Strengthening Project financed by FIRST. The focus on banking stabilitywouldturn out to beappropriate considering that two banksfailed in 2016 --- Moza Banco, the countrys fourth largestbank,in September, and O Nosso Banco, a small bank about 77 percent-owned by the ISSM, in November.Good governance in both the public and private sectors are essential in a reform program. In viewof the heavy damageinflicted on the economyby the governments failure to correctly report on its public debt, itis imperative that development programs in Mozambique, including this financial sector reform program, continue to emphasize goodgovernance principles and practices in both the public and private sectors. The imperative becomes even more urgentconsidering reports that the undisclosed loans were not only concealed, but also misused (indictments were handed out in January2019 against several government officials, bankers and private persons). Issuance of new bank NPL and risk managementstandards and passage of the AML/CFT law and rules under FSDPO I were a good start at promoting good governance inbanks.
P133705 | Second Community Agriculture Resource Management and Competitiveness Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099081423172036861/text/P133705076ff6a00209aeb05a2f5fdd26de.txt | http://documents.worldbank.org/curated/en/099081423172036861/pdf/P133705076ff6a00209aeb05a2f5fdd26de.pdf | The following lesson is drawn from IEG:Analyzing the key factors of performance of projects that havesubsequent phases helps to capitalize and build operational knowledge in the sector. In this project, key lessons learnedfrom CARMAC 1 guided the design of CARMAC 2. An analysis of how the lessons have been applied in CARMAC 2 and what results theyhave produced, extracting new lessons from CARMAC 2, may build important operational knowledge in the sector.The followinglessons are derived and rephrased from the ICR as they are found particularly relevant:Continuity of governmentownership of a project is essential for the success of its implementation. Institutional changes underpinning the projectimplementation resulted in a partial loss of the governments ownership of the project, leading to delays and impacting theimplementation quality. Working closely with the government during the implementation and keeping professional standards high atthe PIU level was crucial for maintaining trust, preserving institutional memory of the implementation process, and ensuringconsistency in implementation.Establishing a baseline for the demand-driven project components is critical formeasuring project outcomes. Where project elements are primarily demand-driven (such was the case for the value chains inthis project), it is important to ensure that baselines are established for the participating sub-activities to allow for goodprogress monitoring and subsequent evaluation of results and impacts.Matching grants, when implemented with asolid and efficient management mechanism, can serve as a good tool for private capital mobilization and could be a good model forfragile and conflict settings. The approach is flexible and can be adapted to fit the needs of many different targetgroups, value chains, and production environments. It can serve different target populations and is a replicable model in fragileand conflict settings.
P133706 | MM-Reengagement and Reform Support Program | East Asia and Pacific | Myanmar | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2014 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/181581475096761808/text/000020051-20140626130746.txt | http://documents.worldbank.org/curated/en/181581475096761808/pdf/000020051-20140626130746.pdf | The lessons from this operation are primarily relevant to other operations with countries which have had a protracted period of disengagement with the Bank and international community. Lessons from the Myanmar Reengagement program are: First that close coordination with other development agencies in order to develop a joint strategy can speed processing, improve coherence, and lower transactions costs for the client. Second, it is important to identify opportunities for reform that are not too complex or institutionally demanding but can still be transformative and gain wide social support. In addition to supporting reform of the exchange rate management system, one of the most visible signs of economic distortion and mismanagement, the program also aimed to increase real spending on core social and human development services that can generate popular support for reform. Third, the method in which the bridge financing was designed and transacted rapidly while meeting the needs of all parties, may help guide such experience in future reengagement operations.
P133731 | CG-Statistics Capacity Building Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2014 | 2024 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061024131519454/text/P1337311a5001308018ad5109bce0cd558f.txt | http://documents.worldbank.org/curated/en/099061024131519454/pdf/P1337311a5001308018ad5109bce0cd558f.pdf | Twolessons are drawn from the ICR, with some adaptation.In operations where government counterpart is theprincipalsource of project financing, the government mustfirmly earmark funds for the project. The Bankalso needs to verify the ready availability of these fundsin a dedicated account at the public treasury. In thisproject, the Government committed to financing US$28.2 of the project cost, and the Bank, US$4.8 million. It took theGovernment 10 months to release the initial US$3.6 million of its commitment, delaying the effectiveness of the project by as manymonths. Then the Government could not finance the balance, necessitating a restructuring of the project and the first AF ofUS$25 million.The Bank needs to clearly and explicitly verify operational assumptions embedded in a projectsdesign and assess all angles of operational risk. In this project, several assumptions turned into operationalproblems. For example, it was assumed that the performance-based payproposal would be readily accepted by the staff ofthe Institut National des Statisques. However, the staff deemed the demands for performance pay to be toohigh. In another case, it was expected that international experts and the local staff would work together smoothly.However, resentment about international-local pay disparities derailed cooperation.
P133738 | Enhanced Fiscal and Financial Management for Greater Opportunities DPL | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/709401467301122486/text/ICRR-Disclosable-P133738-06-30-2016-1467301111406.txt | http://documents.worldbank.org/curated/en/709401467301122486/pdf/ICRR-Disclosable-P133738-06-30-2016-1467301111406.pdf | IEG draws three lessons from the DPO series: 1. The success of tax policies will hinge on the adequacy and governance of taxadministration. The DPO series envisaged reforms of tax rules and administration that may have helped success on income taxrevenues. However, success is largely elusive, particularly on indirect taxes, as weak governance continuei to undermineimplementation of policy reforms. 2. Monitoring and evaluation of an objective to improve budget management will be difficult ifnot underpinned by data such as that collected by a Public Expenditure and Financial Management Assessment (PEFA). As a result, theresults from the changes in the budgetary framework could not be fully assessed. 3. The effectiveness of social expenditures wouldbenefit from integration across social programs and across government levels. The DPO series focused only on programs, where theZero Hunger Pact developed an institutional arrangement (the Municipal Councils of Food andNutrition) to implement a centralgovernment program at the local level. Integration across social programs, of which there are at least 75 in Guatemala, would berequired to improve the effectiveness of social expenditures through means-tested targeting.
P133738 | Enhanced Fiscal and Financial Management for Greater Opportunities DPL | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2020 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/714901575473880311/text/Guatemala-Enhanced-Fiscal-and-Financial-Management-for-Greater-Opportunities-DPL-Series.txt | http://documents.worldbank.org/curated/en/714901575473880311/pdf/Guatemala-Enhanced-Fiscal-and-Financial-Management-for-Greater-Opportunities-DPL-Series.pdf | 5. Lessons 5.1 The Independent Evaluation Group draws three lessons from the development policy operation series. They are additional to the lessons provided earlier, in the Implementation Completion and Results Report Review stage, which largely remain valid today. â€¢ Tax administration and tax policy reforms in the face of major governance issues and long-standing opposition from influential interest groups are unlikely to be successful, even if backed by the World Bank's analytical support, policy dialogue, and financing; under these conditions, directly and indirectly targeting the governance issues over a longer period would be more appropriate. â€¢ Achieving progress on results budgeting requires strengthening of capacity, political commitment, sound M&E indicators, and cross-agency collaboration. â€¢ Achieving results in policy lending requires a sound results framework, a credible theory of change, close linking of objectives with policy actions, and outcome-oriented target indicators.
P133777 | Financial sector stability DPC2 | South Asia | Nepal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2015 | 2016 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/561371612292643120/text/Nepal-NP-Financial-sector-stability-DPC2.txt | http://documents.worldbank.org/curated/en/561371612292643120/pdf/Nepal-NP-Financial-sector-stability-DPC2.pdf | Three lessons are offered, including two adapted from the ICR (page 32).Close collaboration among majordonors is vital to the success of broad national reform programs, particularly where the institutional and technical capacity forprogram design and implementation needs augmenting. In this program, the Bank and the IMF jointly prepared theNepal FSAP of 2014 which informed the prior actionssupported by this program. The legal departments of bothorganizations also helped review the draft BAFIA and the draft NRB Amendment Act. DFID and FIRST provided significanttechnical assistance and advisory services through their staff and international consultants. According to the ICR, the closecollaboration between the Bank and DFID was exemplary, starting in 2012, and consisting of joint missions, employment of experts,capacity-building activities, and large resource contributions for program design and implementation.Reformchampions in a countrys bureaucracy are needed for the implementation of complex reform programs where the politicalenvironment is uncertain and potentially volatile. In this program, the Bank worked closely with reform champions inkey positions at the Ministry of Finance and the NRB who were knowledgeable about the financial sector, held strong convening powerover stakeholders, and made compelling arguments for policy and structural reform. These key executives kept theirorganizationswell informed of the program rationale,design, and implementation plan.Thereform-mindedbureaucracy at the Ministry of Finance and the NRB pressed on with the medium-term program notwithstanding the politicaluncertaintyfrom frequent changes in the national leadership and the civil disturbancerelated to the drafting ofthecountrys new federalist Constitution.Governments can successfully takeadvantage of theopportunities offered by crisis situations to motivate reform programs. In this program, the liquiditycrisisof 2011, the failure of many financial cooperatives in 2013-14, and the devastating earthquake in 2015 exposed the vulnerability ofNepals banking, cooperatives, and insurance sectors to macro-financial shocks and to natural disasters. In response, theauthorities committed to a comprehensivereform program to recapitalize and restructure the countrysfinancialinstitutions and to strengthen the legal and institutionalframeworkfor bank supervision, bank resolution, financialcrisis management, operational risk management, deposit insurance, payments and settlement, and transparency. The demand forpost-crisis recovery helped firm up broad political support for the reforms.
P133780 | UG Teacher and School Effectiveness Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/933781624637744738/text/Uganda-UG-GPE-Teacher-and-School-Effectiveness.txt | http://documents.worldbank.org/curated/en/933781624637744738/pdf/Uganda-UG-GPE-Teacher-and-School-Effectiveness.pdf | The ICR (p. 37-39) included several lessons learned, adapted here by IEG: Enabling an active communitydialogue to raise awareness and engagement is critical for obtaining a broader buy in by all stakeholders and sustainable long-termoutcomes. In this project, dialogues with the community were organized in project districts that allowed local governmentofficials and community leaders to connect with many stakeholders including parents, teachers, and local council officials, toensure better understanding of project implementation. Critical topics such as teaching in local languages in the lower primarygrades, and children attending local ECE programs to support their growth and development and improve their readiness for primaryschool entry, were discussed. Assessing institutional capacity at the central and district government levels iscritical for designing an adequate andimplementation timeline and setting realistic targets. In this project, theBank underestimated institutional capacity constraints at the central and district local government levels, which resulted inimplementation delays and financial management and procurement issues. Also, given the capacity constraints it turned out that thetarget set for school construction was unrealistic. The project required restructuring to extend the projects closing date byone year and to decrease the target. Designing an ME framework with a clearly stated objective andindicators that encompass all outcomes of the objective is critical for being able to measure implementation progress and ensureattribution. Inthis project, there was a disconnect between the objective and the activities included in theproject, resulting in monitoring issues and the need for several restructurings. Ensuring that school designstake natural disasters into account is critical for the sustainability of constructions/rehabilitations of schools. Inthis project some constructions were exposed to natural hazards including floods and as a result required repair. In order to avoidcostly repairs it is usefulto screen designsfor disaster risks (for example topographical and geological assessments)to ensure that climate-proofing measures are being implemented.
P133791 | FYR Macedonia Public Expenditure PBG | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | ICRR |  | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/988861473935370297/text/ICRR14950-P133791-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/988861473935370297/pdf/ICRR14950-P133791-Box396299B-PUBLIC.pdf | Please see the PPAR for more information.
P133791 | FYR Macedonia Public Expenditure PBG | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2016 | PPAR |  | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/540671469190196702/text/106281-PPAR-P133791-Box396280B-PUBLIC-disclosed-7-21-16-ppar-macedoniapublic-0716.txt | http://documents.worldbank.org/curated/en/540671469190196702/pdf/106281-PPAR-P133791-Box396280B-PUBLIC-disclosed-7-21-16-ppar-macedoniapublic-0716.pdf | 12. Lessons Â· PBGs can potentially be a useful instrument for supporting clients facing large external financing needs. Â· PBGs implemented in a context of challenging macro-fiscal situation and large financing needs need to incorporate a consistent macro-economic framework with necessary macro and fiscal actions for risk mitigation. Â· Positive impact of important public expenditure measures (wage control, reforms in health procurement, and better targeting of social protection) can be eroded if the program lacks an overarching fiscal and debt framework. As FYR Macedonia's case illustrates, fiscal savings achieved through these important measures can be dissipated by introducing non-priority spending such as ad-hoc pension increases or controversial capital expenditures. Â· Comparing the aggregate interest rate of PBG-supported debt instruments with counterfactual market rates may not be enough for assessing the extent of reduction in the borrowing costs associated with the transaction. Estimating the change in sovereign risk perception, although a challenging task, may give more accurate assessment of the impact of the program
P133798 | Open Government and Public Financial Management | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2015 | 2016 | 2019 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/764731552419810792/text/Tanzania-TZ-Open-Govt-PFM-Development-Credit.txt | http://documents.worldbank.org/curated/en/764731552419810792/pdf/Tanzania-TZ-Open-Govt-PFM-Development-Credit.pdf | Design considerations should include the political environment. Teams need to make an explicit andconcerted effort to assess the political context and the degree of ownership at the outset. While the Tanzanian politicalenvironment appeared tranquil, elections were close, they were being fought hard and, in many instances, changed the direction andemphasis of policy, including influencing the aims of the OGPFM operations.Absorptivecapacity is essential. Teams need to take into consideration the institutional capacity of the environment intowhich projects are introduced. The OGPFM series was prepared and launched at a time when numerous similar DPOs were beingintroduced after a hiatus of over a decade. In this case, it generated high transactions costs that might have been avoidedwith better attention paid to signals in the environment, including the long processing time. Greater attention is needed atthe CMU level to the cumulative burden on institutional capacity of all Bank-supported operations under preparation andimplementation at any point in time.Government ownership is crucial. Teamsneed to be alert to signs of flagging ownership by the Borrower. Long processing times in preparation may indicate that thereforms being proposed are not adequately supported. They require a careful assessment of the reasons underlying thedifficulties in moving faster.
P133803 | India Ecosystems Service Improvement Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2018 | 2024 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050124191028032/text/P1338031cf5714044183e611a71e4c3616b.txt | http://documents.worldbank.org/curated/en/099050124191028032/pdf/P1338031cf5714044183e611a71e4c3616b.pdf | The ICR (para. 63-68) included several lessons learned which were adapted by IEG: Using technology toolscan be effective for planning, implementing, and monitoring forest management activities and improve the efficiency andeffectiveness of such activities. In this project, the State Forest Departments used GIS and mobile apps to identify floraand fauna. Using the app reduced the time and effort required for monitoring, allowing field staff to focus more on conservationand protection activities. Combining investments on forest and non-forest lands can unlock greater economic andecological benefits. In this project, the integration of sustainable land and ecosystem management outside of forests aspart of forest restoration, provided a wider range of economic and ecological benefits such as enhancing land productivity,diversifying livelihood opportunities, and increasing ecosystem services. To make forestry financially attractivefor rural communities and for attracting private sector financing, critical policy and institutional reforms are necessary.In this project, strategic investments in NTFP value chains enhanced economic returns for the rural poor by setting upforestry-enterprises amongst forest-dependent communities and connecting them with economic opportunities.
P133811 | Emergency Crisis Recovery Project | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2014 | 2015 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/887491468178157225/text/ICRR14715-P133811-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/887491468178157225/pdf/ICRR14715-P133811-Box393183B-PUBLIC.pdf | The following lessons are formulated by the evaluator, based on the ICR:In fragile environments, strong institution-building support is essential when scaling up to meet an emergency. While the agency of choice may have the capacity that allows it to operate under normal circumstances, it may not have the resources to cope with a shock to the system. SWF proved not to have the resilience to take on an intense cash transfer process without the support provided by the ISP (and the EU), and even then, capacity was strained.Even emergency operations require a rigorous capacity assessment. The urgency with which an intervention is needed should not override good design. Expecting to address and solve issues during implementation may prove to be much more challenging and time- and resource consuming than during preparation. The preparation team did not sufficiently focus on such relatively complex challenges as monitoring and evaluation during preparation, leaving it up to the ISP to address them. This did not work well.Maintain continuity of staff in emergency projects. Maintaining continuity of staff is always advisable, but especially so when implementing under timetables of emergency â€“ there may be much less time to understand issues and build relationships than under a regular operation.
P133828 | Irrigation and Land Market Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2024 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062324234514001/text/P133828-5b139bc1-76a9-413e-b139-0244cbd1d112.txt | https://documents.worldbank.org/curated/en/099062324234514001/pdf/P133828-5b139bc1-76a9-413e-b139-0244cbd1d112.pdf | The ICR formulated several lessons, some key lessons are summarized as follows:Pairing irrigation and landmanagement engagements can lead to strong synergies. In this project, farmers in the selected areas benefitted fromimproved irrigation and drainage services and more secure land tenure. Together, these aspects can create a betterenvironmentfor farmers to invest in their farms and especially in more efficient irrigation infrastructure (such as drip irrigation), sincethe fear of losing their land or of not getting water is greatly reduced.To avoid unreasonable interruptions inwater supply during irrigation season, irrigation civil works need to take place outside the irrigation season; thus, it is best toallocate sufficient time for such civil works. While the project took measures to supply farmers with irrigation watereven while civil works took place (via temporary earthen canals), civil works are unpopular and difficult to conduct during theirrigation season, which spans from May to September in Georgia. Furthermore, the timeline should also consider that it often takes11.5 years to progress from the design to the commencement of civil works. Thus, ample time should be allocated to completesuch works.Citizen engagement via detailed training and consultation with farmers, particularly during the designphase, is essential for understanding and addressing local needs and demands for irrigation as well as establishing collectiveorganizations to manage the systems. This approach will ensure maximum cooperation and support from farmers during theimplementation phase and avoid changes to the design and delays in the implementation of civil works. Furthermore, this approachwill also help with establishment of collective organizations, such as WUOs, which requires careful planning and lengthyconsultations, especially in former Soviet countries where collective efforts often evoke negative emotions. Projects shouldstart the mobilization process as early as possible, even in parallel with designs, to allow adequate time for raising awarenessand educational outreach.Farmer extension services via technical field training are essential when introducing newirrigation technologies and it is best to engage technical training providers to provide this service. The pressurizedpipe system with double hydrants for on-farm delivery used in the KS irrigation scheme was the first of its kind in Georgia.However, the project did not invest up front in farmer training to demonstrate to water users how to operate and maintain thisinnovative system. Given that this transition requires technical field trainings for farmers and that the construction andsupervision contractors cannot be relied on to train all water users, project funds should be earmarked for dedicated technicaltraining providers to provide this training at various stages (at design, construction, and handover) to farmers to ensureits utilization and sustainability.
P143025 | Lao PDR Ninth Poverty Reduction Support Operation | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible |  |  | The ICR offers several lessons listed below:Clarifying the DPOinstrument to all implementing agencies and having a robust coordination mechanism are important in terms of line ministriesunderstanding of the overall program. In this case, line ministries perceived reforms as MOF-led, which led todifficulties in implementing reforms. The limited understanding of the DPO instrument in implementing agencies resulted in weakincentives and hampered the ability of the Secretariat to coordinate activities.Ensuring the rightinstitutional lead is in place is key to moving reforms forward. In general, this seems to have been the case in the PRSOoperations. Some areas of the operation may have stalled partly as they were implemented by one institution, while otherparts of the agenda were the domain of other agencies. This factor can be overcome with appropriate dialogue and coordination withall stakeholders during program preparation.Complementary technical assistance can support theimplementation of reforms in a low capacity environment. For example, multi-donor trust fund (MDTF) contributions in theform of technical assistance helped in achieving simplified trade and business requirements.IEG adds thefollowing lesson:In designing a results framework, weak links between prior actions and the expectedoutcomes will impede achievement of the intended outcomes. In the fiscal area, for example, prior actions onweakly defined fiscal reforms for natural resource sectors were unlikely to achieve the intended outcome (a fiscal standard inplace) within the life of the program.
P143032 | 2nd DPL to Support Inclusive Green Growth and Sust Devlp in HP | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR draws the following five lessons from the experience of implementing this project, with some modification oflanguage.(1) Experience from implementing sector investment projects can be useful indesigning policyreforms targeted under Development Policy Funding (DPF). In this operations, lessonsfromprior externallyfunded investment projectshelpedidentifypolicy or institutional gaps. Thissectorexperience helped theBank in working collaboratively with the Government of HPin designing thecombination of policy and institutionalreforms that was requiredto carry the agenda forward. For instance, the experience gained from implementing the Bankfunded Rampur Hydropower power helped in identifying what was required at the policy and institutional level forLocal AreaDevelopment Committee (LADF) policy reforms and theMid- Himalayan Watershed Development Projects lessons were helpful insuggesting changes to watershed level planning.(2) Programmatic Development Policy Financing (DPF) can at times bemore effective than standalone operations for supporting sustained policy reform. This operationthrough aseries of two DPL operations helped in collaboration between the HP government and theBank and this helped ineffectivedelivery of development outcomes.(3) A relationship of trust and communication between the Bank team and theclient was key to the success of this innovative DPF initiative. In this case communication between the Bank and theclient through a combination of factors including supervision by alocally based task team leader and skilled and senior stafffrom Washington, DC. andfrequent visits and close interaction with government officers, aided in responding to critical needsof the state.Thisensured appropriatesupport in a timely fashion.(4)Advisory Servicesand Analytics (ASA) can providevital technical support to the borrowers policy actions. A number ofASAs were conducted to support the DPL under the auspices of this operation. The findings and results of these providedtechnical support for policy reform formulation and subsequently implementation.(5) Delivering climatefinance through budget support operations can be beneficial to both the development and global environmentalobjectives. In this project, financing through the Clean Technology Fund (CTF) supported a reform programforGreen House Gas (GHG) emission reductions and other environment and social improvements. However, given that theexperience with this operation showed thatthe process of reconciling and coordinating processing requirements for the CTF andIBRD DPF was not easy, greater harmonization of processes and procedures might be needed for using either CTF or other climatefinance instruments.
P143040 | Second Development Policy Operation | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2015 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons are taken from the ICR with some modification of language by IEG.A series of 4 DPOs can often beexcessive. Changing conditions could necessitate significant changes to the program, which complicates design, implementation andevaluation. In Armenia, by the time the fourth DPO commenced circumstances had changed substantially compared with the first DPO.Armenian authorities indicated that two DPO series that each had 2 programs could have improved performance.Excessively broad PDOs complicate design, greatly increase the difficulty of effective implementation, complicate monitoring andmakes effective evaluation highly problematic. In the case of Armenia, the numerous changes the failure to translate triggers in apreceding DPO into prior actions in subsequent DPOs complicated achieving the targets of the program.Pressuresto disperse can compromise the effective implementation of a programmatic series. Furthermore, it can also lead to shortcuts beingtaken to comply with prior actions. This results in less effective or delayed reforms. In the case of Armenia, the pressure todisperse resulted in a tax law that contains many weaknesses, and laws and regulations in the mining sector that were not fullyeffective.IEG adds the following lessons.Undertaking numerous changes to results indicatorsand modifying targets greatly complicates both program implementation and evaluation. In the case of Armenia, widespread changes inresults indicators made the effective monitoring and evaluation of the program extremely difficult.Whendesigning a Monitoring and Evaluation Framework, it is important to ensure that the indicators relate to outcomes and not toinputs. In the case of the Armenia DPO series, numerous indicators measured inputs.If a DPO series has an overarchingobjective, including indicators that provide information on whether it is being achieved strengthens the evaluation of its success.In the case of Armenia, job creation was the overarching objective, but there were no indicators containing employment data
P143060 | Georgia Competitiveness and Growth DPO2 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2013 | 2014 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | IEG draws the following four lessons from the experience of this series:1. Incomplete results chains will undermineefficacy assessments. In this Program, the first objective was materially equivalent to the reforms that underpinned it.Trade-related reforms (e.g., on food/feed safety, competition) comprised the stronger legislation sought under theobjective. In this case achievement of the reforms (enactment and implementation) is equivalent to achievement of the objective andthus there is no meaningful efficacy assessment exercise.2. Monitoring indicators that do not accuratelyreflect objectives will also undermine evaluation. An example in the Georgia Program is the indicator used to reflect generaleducation quality, which was defined as the share of teachers that attended training on learning processes. While this indicatormay be related to actual learning, it does not measure it directly. The point of an evaluation in this case is to assess whethersuch training actually was effective in raising student test scores. Another example is the indicator for accessibility of healthservices, which was defined as the percent of theoretical coverage (Decree introducing Universal Health Coverage). The latter doesnot reflect actual health attention to the covered population.3. Attention to the more specific risks of anoperation (in addition to the broad political, macroeconomic, and capacity risks) will better anticipate implementation problems.The Georgia program suffered delays on a number of reforms (e.g., international standards, trade facilitation, and power) thatmight have been anticipated with a more detailed articulation of risks.4. An unfocused set of objectiveswill detract efficacy as it does not allow for synergies across objectives. In the Georgia DPO, areas such as customs efficiency,targeted social programs, and power sector reliability were mutually unrelated and thus unlikely to support each other.
P143064 | Liberia: Public Sector Modernization Project | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2021 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099905007122235272/text/P143064015007a01e0ace60b091269e1814.txt | http://documents.worldbank.org/curated/en/099905007122235272/pdf/P143064015007a01e0ace60b091269e1814.pdf | In addition to the lessons included in the ICR, IEG adds these lessons: A public sector modernization projectthat measures the projects direct effect in terms of administrative processes should include a parallel assessment of theimpact on the quality and the efficiency of public service delivery. The project activities were intended to gradually generate apositive impact on the quality and the efficiency of public service. It would have been useful to have a results indicator toassess this, as well as any unintended negative impact the project activities may have had. For example, with all the positivepersonnel assessments enabled by the project, one would expect the overall performance of the seven ministries to improve. Whilethe full impact of such reforms takes longer than the project duration to be realized, there may have been initial stageimprovements that could be measured. Sufficient and continuous professional development is needed so that public sectorworkers can sustain improvements in the delivery of public services. Liberia is confronted with significant capacity constraints,which limit gains in the quality and in the efficiency of public service delivery. Sufficient and sustained professionaldevelopment would be required to sustain improvements in public service delivery. Professional development would also create moreand better employment opportunities for civil servants, which would create an added incentive for raising individual professionalperformance. Limited capacity states achieve better results by focusing on a few key reform measures that arerealistically sequenced and get coordinated support from development partners. However, reform successes need to be graduallyscaled up to protect advances made and widen the benefits. In the Liberia case, civil servants in the participating ministries maybe lured by positions in the rest of the public sector, which might be offering higher salaries and allowances without beingsubject to annual performance reviews. A plan for gradually modernizing the rest of the public sector and making it subject to thesame conditions as in the seven participating ministries will be needed.
P143184 | SUSTAINABLE PROD. IN AREAS PREVIOUSLY CONVERTED TO AGRICULTURAL USE | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/520991612891302881/text/Brazil-BR-ABC-Cerrado.txt | http://documents.worldbank.org/curated/en/520991612891302881/pdf/Brazil-BR-ABC-Cerrado.pdf | The following lessons were drawn from the ICR with some adjustments in language: The combination oftraining and customized technical assistance provides a significantly stronger incentive for producers to adopt ABC technologiesthan training alone. The project conducted an experiment comparing the effectiveness of training only versus training incombination with customized technical assistance that was tailored to the needs of each agricultural producer. The impactassessmentresults showed that the combined approach was more effective to drive adoption as well as to increase the share ofland converted to ABC technologies. Yet, the higher costs of 45 percent per hectare of adopted ABC technology of the combinedapproach compared to training only (ICR, Annex 7F) call for a careful comparison of expected benefits and costs for the specificcountry conditions. Training and technical assistance can be effective instruments to promote ABCtechnologies independent of financial incentives. The project results demonstrated that knowledge gaps were key barriersto the adoption of ABC technologies among agricultural producers, which could be overcome by the provision of training and/ortechnical assistance. Financial barriers were also relevant, but largely overcome by the (predominantly cattle) producersthemselves after realizing the financial (and environmental) profitability potential of the technology change. Future experimentscould test if there are differences in overcoming knowledge and financial barriers among crop farmers. For experimental pilot project designs the identification and classification of potential beneficiarygroups a priori is important to maximize relevance for scale-up. The project at hand planned its design with theassumption that a portion of beneficiary producers would be interested in the project-supported credit line for investing in ABCtechnologies. However, the project implementation revealed the dominance of cattle farmers who did not take up such credit givenpreference for financing through private resources. Depending on the type of beneficiary group(s) targeted with the results of anexperimental project, a careful identification and characterization of treatment/control groups during project preparation isessential to increase the potential for scale-up and external validity. Investing in rigorousimpact evaluations is vital to prove the effectiveness of innovative concepts and address counterpart hesitations. Whilethe cost and technical capacity needed for a project-level impact evaluation are not justified in every case, they are worth it forpilot projects that aim to prove an innovative concept or technology in a new environment. As such, results of carefullyimplemented experiments provide invaluable findings that inform future policymaking and familiarize country counterparts with newconcepts for potential scale-up.
P143184 | SUSTAINABLE PROD. IN AREAS PREVIOUSLY CONVERTED TO AGRICULTURAL USE | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2020 | 2023 | PPAR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099328405172314911/text/SECBOS07ee7b74015094b80a868d579c578.txt | http://documents.worldbank.org/curated/en/099328405172314911/pdf/SECBOS07ee7b74015094b80a868d579c578.pdf | 3. Lessons 3.1 The first lesson is that agencies signed up to deliver training and technical assistance are likely to deliver good results if they have a strong decentralized presence and well-established outreach to producers. In the absence of a strong public extension service of comparable capacity from one state to the next, the private agency, SENAR, 14 was a sound choice, because it had a network of regional offices and close ties to producer associations. Building on its long experience with training farmers, SENAR proved capable of learning to be an effective provider of on-farm technical assistance. One indication of its effectiveness is that farmers remembered most of what they had learned when tested six months after attending training. 3.2 Second, once they have been persuaded of the profitability of adopting improved farming practices, farmers with adequate means will be willing to pay for technical assistance. Given that the project provided technical assistance free of charge, it was possible that farmers would not continue to use technical assistance at their own expense once the project ended. This was not the case. The pasture renewal techniques adopted by farmers offered a satisfactory financial rate of return. The project uncovered a substantial latent demand for knowledge about the technology most relevant to the farmers in this region (pasture renewal), and farmers proved willing and able to pay for technical assistance after the project ended. The project demonstrated that knowledge, not access to credit, was the constraint to adoption. However, there are two caveats: Given that most of the participating farmers were primarily engaged in raising cattle, they had the means to self-finance by selling some of their herd; they didnâ€™t needâ€”and were generally reluctant to useâ€”credit. Financing could be a bigger constraint for crop producers of a comparable enterprise size. Moreover, the project did not address the needs of small-scale farmersâ€”an oversight in project design that was only partially corrected during implementation. These farmers are more likely face financing constraints, which will reduce their use of technical assistance provided for a fee. 3.3 Third, impact evaluations that rely on randomized control trials can produce compelling findings about the constraints to adopting new farming technologies; however, it is challenging to accommodate the needs of control-group farmers who are denied project benefits, and the design of these impact evaluations may actually reduce project impact. The two peer-reviewed articles published in scientific journals after project completion are a testament to the substantive findings from the impact evaluation. However, SENAR, the agency responsible for training and providing on- farm technical assistance, and MAPA initially doubted that the impact evaluation would add value. Staff in SENARâ€™s regional offices did not readily commit to the evaluation and had difficulty managing the disappointed expectations of farmers assigned to the control group. These farmers had taken the initiative to sign up for the project and, by virtue of that, probably had the motivation to adopt the technology being promoted. Many of those who were assigned to the control group dropped out, qualifying the projectâ€™s impact to some extent. This loss might have been mitigated if these farmers had been offered some guarantee of future training and technical assistance. 15 3.4 Further consideration is needed as a consequence of the design of the randomized control trial. The designers of the project had an incentive to generate findings that would be statistically representative of a wide geographic area. This resulted in a scattershot approach: the farms selected for inclusion in the project were highly dispersed, resulting in no critical mass of technology adoption in any one area, reducing the scope for positive reinforcement through spillover effects between contiguous farms, and possibly lowering the likelihood of sustainability. The follow-on project addressed this limitation by taking a landscape approach that aimed to address all the farmers in selected watersheds. But the limited uptake of the various technologies originally proposedâ€”and the resulting lack of data on what workedâ€”are significant limitations to these interventions. 3.5 Fourth, the gains from a one-off evaluation of impact are likely less substantial than the rewards from building a systematic and well-integrated system of monitoring that remains in place for the long term. Monitoring is essential to verify that the technologies adopted are consolidated over time. Given the limited amount of time between the first and second interview rounds, it is not clear if the positive results demonstrated by the impact evaluation depended largely on projections made during the second round (farmersâ€™ reported intentions) rather than observations of new practices that were already fully embedded. In the absence of follow-up data from monitoring, it is not clear if farmers will continue to deforest or will revert to old practices. 3.6 IEG has a couple of further concerns about the integrity of the monitoring system. To begin with, the system can only be as good as the field technicians who are relied on to input data. There is a shortage of technicians with a skill set and mind-set conducive to close observation of the farm-level changes that are significant to environmental impact. In the Cerrado biome, the technicians hired by SENAR are, first and foremost, experts in animal husbandry; it is less clear that they have the interest or skills needed to closely track the impact of farm-level changes on the environment for any given farm and, more importantly, for the landscape beyond the farm. With respect to the monitoring of deforestation trends, it is concerning that SENARâ€™s system, SISATeG, is not yet integrated with Sistema Nacional de Cadastro Ambiental Rural (National System for Rural Environmental Cadastre), the State Forest Bureauâ€“ maintained system responsible for verifying that the resources identified by the forest cadastreâ€”resources protected by lawâ€”are indeed preserved. Also, there is unrealized potential for SENAR to make fuller use of the impressive remote-sensing capabilities now available that allow tracking of landscape changes at the submunicipal level. 3.7 Fifth, this assessment confirms an age-old lesson: technology transfer depends on effective collaboration between research and extension agencies. The design of the 16 assessed project made insufficient attempt to ensure that the capacity of the research agency, Embrapa, was fully committed. SENAR and Embrapa did not work together closely during implementation. This was as much the consequence of a failure to budget adequately for Embrapaâ€™s participation as it was of any difference in the incentives of the staff in these agencies. Also, future projects are advised to take an iterative approach to the design of training materials and technical assistance packages. The one-off intervention that this project envisaged for Embrapa did not allow for modifications in response to feedback from trainers and farmers about what worked best. It is important to note, however, that the follow-on project incorporated this lesson in its design. The terms of the collaboration between SENAR and Embrapaâ€”and other agencies participating in the projectâ€”were more clearly spelled out, and the working relations between the two agencies are much closer. Embrapa now directly trains SENARâ€™s field technicians, helping to ensure that the formerâ€™s knowledge and skills are more fully transmitted. 1 Project components were as follows: (a) producer training (estimated spending = $3.4 million; actual spending = $2.8 million), which consisted of (i) identifying rural producersâ€™ and farm techniciansâ€™ demand for low-carbon emissions agricultural technologies in 9 of the 11 Cerrado states, and (ii) providing training in prioritized Low-Carbon Emissions Agriculture (ABC) technologies and farm management; (b) field technical assistance (estimated spending = $5 million; actual spending = $4.9 million), which involved the development and implementation of a technical assistance pilot project for selected rural producers; (c) project management, monitoring, and evaluation (estimated spending = $2.3 million; actual spending = $2.6 million), including (i) project implementation and coordination, as well as monitoring and evaluation of project activities and impact based on an experimental design, and (ii) activities promoting institutional learning and the exchange of experiences among participants. 2Component 1 includes actions aimed at â€œ(iii) strengthening of governance and institutional capacity at MAPA [Ministry of Agriculture, Livestock and Food Supply], SFB [Brazilian Forest Service], MCTIC/INPE [Ministry of Science, Technology, Innovation and Communication/National Space Research Institute], Embrapa [Brazilian Agricultural Research Corporation; Empresa Brasileira de Pesquisa AgropecuÃ¡ria], and SENAR [National Rural Learning Service; ServiÃ§o Nacional de Aprendizagem Rural]â€ (World Bank 2022, 10). 3A fiscal unit ranges from 5 to 100 hectares, and the size range varies between municipalities, reflecting agroclimatic constraints on productive potential (Project Appraisal Document, 4). 4This change is acknowledged in the aide-mÃ©moire of the World Bank mission conducted from May 16 to 20, 2016 (World Bank 2016). 17 5â€œ[Although family farming is mentioned 25 times in the Ministry of Agricultureâ€™s presentation of ABC+ . . . , no targets are defined for this group of producers.]â€ â€œEmbora a agricultura familiar, agricultor ou produtor familiar sejam mencionados 25 vezes no PO do ABC+ . . . , nÃ£o hÃ¡ qualquer meta definida para este grupo de produtoresâ€ (Garcia et al. 2021, 5). 6 The original nine states were Bahia, Distrito Federal, GoiÃ¡s, MaranhÃ£o, Mato Grosso, Mato Grosso do Sul, Minas Gerais, PiauÃ­, and Tocantins. The four initially slated to receive technical assistance were GoiÃ¡s, Mato Grosso do Sul, Minas Gerais, and Tocantins. â€œThese states were prioritized by MAPA and SENAR based on the following criteria: (i) number of target producers; (ii) ABC Plan technologies already applied; (iii) number of extension agents; (iv) area deforested in 2009/2010; (iv) institutional strength of SENAR. Following the 2015 depreciation of the Brazilian Real and the consequent higher availability of resources (as the FIP grant was denominated in US$), the state of MaranhÃ£o was also added to the list in May 2015â€ (World Bank 2020, 6). 7Data are from the 2017 agricultural census. In the nine states originally covered by the project (Bahia, Distrito Federal, GoiÃ¡s, MaranhÃ£o, Mato Grosso, Mato Grosso do Sul, Minas Gerais, PiauÃ­, and Tocantins), the total area in farms was 215.6 million hectares, of which 84.8 million hectares (39 percent) were in pasture and 27.1 million hectares (13 percent) were in crops (IBGE 2019). 8 The project promotes the following â€œlow-carbon emission agricultural practicesâ€: restoration of degraded pasture, livestock intensification, crop-livestock-forestry integration system, and crop- livestock system. On page 33 of the Project Appraisal Document, the land area where these practices have been adopted is cited as one of the project development objective indicators (World Bank 2018). 9â€œIn Brazil, the Atlas of Brazilian Pasturelands reports that 57 percent of the total 173 million hectares of pasture lands were degraded by 2018. More critically, the Atlas registered that approximately 40 million hectares of pasture suffer from a severe level of degradation. In contrast with this georeferenced estimate, rural producers recognize only 12 million hectares of pasture to be in poor condition on their properties, as reported on the last Agricultural Census, conducted in 2017. Discrepancy between geoprocessing analysis and the producersâ€™ self-reported measure of degraded conditions of their own pasturelands is expected. The difference may have several causes. Producers may have different subjective perceptions about what they consider to be a degraded pasture. They may also have incentives to under-report degraded land area to avoid regulatory sanctionsâ€ (Feltran-Barbieri and FÃ©res 2021, 3â€“4). 10The same source notes that â€œthe design of the project, however, did not establish a specific definition of attributions, internal guidelines, and resource flows between these institutionsâ€ (World Bank 2020, 19); that â€œa combination of lack of clear guidelines for the institutionâ€™s role in the Project, dotted hierarchical decision lines, and misaligned incentives of career researchers (more focused on academic research than on policy advisory) made the contribution of Embrapa to the Project score below its potentialâ€¦the institution maintained a low track record of participation in field activities and collective events, which could have been otherwise leveraged to spread more knowledge around low-carbon technologiesâ€ (20); that â€œad hoc surveying and analysis of quality of technology adoption, which had to be validated by Embrapa, was not 18 undertaken throughout project implementation, and was only included in the impact evaluation data collectionâ€ (22); and that â€œEmbrapaâ€™s estimate of the Projectâ€™s impact on greenhouse gas emission and carbon sequestration was delayed until after project closing and was produced only for pasture rehabilitation (the most adopted ABC technology) instead of additional technologies as originally establishedâ€ (22). 11On March 29, 2022, Embrapa reported that more than 50 of SENARâ€™s field technicians participated in a training session run by Embrapa under the auspices of the World Bankâ€“ supported Integrated Landscape Management in the Cerrado Biome Project(Paisagens) (Embrapa 2022). 12â€œIn Brazil, lectures given by researchers in local communities are one of the most common strategies for transferring technology to milk farmers. In one of these lectures, given in 1997, Embrapa researcher Artur Chinelato realized the limits of this strategy when a farmer asked who would teach the farmers to use the technologies presented and what the continuity of the proposals presented would be. This led a group of five researchers from Embrapa Sudeste to launch Balde Cheio, as a practical teaching method, using a dairy farm as a classroom for technicians and farmers. The initial syllabus consisted of a set of technological practices, tested on experimental farms belonging to educational and research institutions that could be adapted to different situations, locations, and farmer profiles (Novo et al. 2016; Chinelato 2018)â€ (Chiodi Bachion et al. 2022, 3). But there is another angle to consider. Shortly after project preparation (in 2014), the National Agency for Technical Assistance and Rural Extension was created in response to the decline of public agricultural extension services in many Brazilian states, as well as in response to the perception that only a small part of EmbrapaÂ´s research reached the small and medium producers. An Independent Evaluation Group interviewee notes that its creation was affected from the start by ideological divergencies regarding the target public of the agency (family agriculture versus commercial agriculture). 13The first randomization protocol was not stratified by area and therefore proved to be unworkable. Thus, in one municipality (CorumbÃ¡ in GoiÃ¡s), of the 22 eligible producers, 19 were assigned to the control group, meaning that there were not enough producers eligible for training to justify the provision of said trainingâ€”and many of those assigned to the control group declined to continue working with the project. This error was partially remedied in phase 2, but participant attrition was a continuing problem (Faveri and Camboim 2019, 20). 14The final composition of the experimental groups assigned 663 of the participating producers to the control group; these producers represented 48 percent of all participants (BraganÃ§a et al. 2022). 15Project start-up (the date of grant â€œeffectivenessâ€) was August 2014; producer training was not completed until three years later (July 31, 2017); technical assistance was not completed until January 31, 2019 (Faveri and Camboim 2019, 40). 19 16The fiscal year 2019 Integrated Landscape Management in the Cerrado Biome Project (P164602) had an effectiveness date of March 1, 2019; the Mid-Term Review was dated August 30, 2022, and the closing date, as projected at midterm, is December 29, 2023. 17â€œThe GGE [State Management Group; Grupo Gestor Estadual] are composed of representatives of the agricultural and livestock sector in each State and have the function of establishing an ABC technology introduction plan that meets the real needs of their State. The GGE assist farmers and ranchers with the introduction of sustainable practices and with access to credit offered by the ABC Programâ€ (World Bank 2014b, 32). 18Baseline interviews were conducted between October 12, 2017, and January 30, 2018. Follow-up interviews were conducted between March 11, 2019, and May 8, 2019 (Faveri and Camboim 2019, 40). 19The same report notes, â€œSENARÂ´s system, while yielding immediate answers, would benefit from complementary actions of checking the precision and veracity of TMA [on-farm technical assistance] staff entries into the SISATeG system through on-the-ground or aerial, as was actually foreseen in the appraisal Results Frameworkâ€ (World Bank 2022, 27). 20
P143185 | Development of systems to prevent forest fires and monitor vegetation cover in the Brazilian Cerrado | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099042123165524404/text/P14318500a51c70650ad3c078c55ba1707a.txt | http://documents.worldbank.org/curated/en/099042123165524404/pdf/P14318500a51c70650ad3c078c55ba1707a.pdf | The ICR (paras 101-107) presented five lessons. Three of them are presented below with rephrasing because these lessons may beuseful for future projects related to the biome-level environmental monitoring.Newly targeting the Cerradosavanna-forest biome is a necessary change from the prior operations with nearly exclusive emphasis on the Amazon rainforest forreducing deforestation and GHG emissions in Brazil. Progressively increasing recognition on the importance of the Cerradobiome for the economy, biodiversity conservation, and adaptation and mitigation of climate change has expanded funded initiativesin the area. A more intentional focus on addressing the issue of land-use change (Brazils primary source of GHG emissions)in both the Amazon and the Cerrado is of paramount importance and would be a bold initiative to better account for and reduce GHGemissions at the national and global levels.The Project demonstrated the transformational potential of a tightlyfocused, science-based project led by experienced, technically sound, and sophisticated institutions. INPEs solidexperience with activities like those of the Project but focused on the Amazon was a key advantage in replicating that successfulexperience in the Cerrado biome, thereby minimizing uncertainty and difficulties in implementation and delivery. The synergiesbetween three executing institutions, INPE, UFG and UFMG, enhanced and strengthened the development of the information systems,datasets, and tools. The complementarity between the technical expertise of INPE and UFMG enabled the development of informationand first-of-its-kind modelling approaches (e.g., Fires risk, fire spread forecasts). Improved estimation of GHG emissions for theCerrado biome contributes to enhanced global accountability of Brazil, considering its commitments in the context of the UNFCCC andtowards 2025. Developing and scaling up of monitoring and accountability systems for other biomes of Brazil (which are incrediblyvast and biologically diverse in nature) contribute to global climate change efforts and deliver benefits beyond the nationalborder. As an outcome, the Project represents a persuasive argument for engaging in larger-scale environmental monitoring projectsin Brazil. This is especially so when the agencies demonstrate excellence and national capacity (even in times of shiftinggovernment priorities and uncertain budgeting prospects), and when a disciplined approach limits project scope to a set ofessential, nationally proven, and well-integrated activities that build upon the expertise of the agencies involved inimplementation.The systematic provision of better information systems is a cost-effective public investment topursue improved planning, response, and action on deforestation and fire risk. Access to accurate data, information,technology, and forecasting knowledge represents a game-changer at multiple levels within government and society, with the addedvalue of increased awareness and validation of results. The application of such monitoring and modelling systems is particularlyimpactful when it is implemented to bridge the gap within institutional environments which are not used to such technology systemsto effectively engage complex coordination efforts to the benefit of progressing its operations in office and field settings (e.g.,local fire brigades, ICMBio, local stakeholders). The TerraBrasilis platform allows institutional and public users anywhere inBrazil (and abroad) to rapidly access deforestation information, analyze and verify it, and apply it to their specific purpose. Thedevelopment of a state-of-the-art fire risk ignition and spread probability models is a major advance in the effort to control andprevent fires in the Cerrado biome with no equivalent anywhere in the world. These results will require continued support andexpansion moving forward.
P143197 | LS-PFM Reform Support Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/290801592605249927/text/Lesotho-LS-PFM-Reform-Support-Project.txt | http://documents.worldbank.org/curated/en/290801592605249927/pdf/Lesotho-LS-PFM-Reform-Support-Project.pdf | These lessons are selected from the ICR (p. 30-31):- For effective implementation of a project such a PFMRSP, thefollowing factors are important: project scopeand activities need to be consistent withcountry andthegovernments implementation teams capacity; for efficient functioning of IFMIS activities, there needs to beMEofeach IFMIS activity and its milestones; and a Reform Steering Committee needs to better understand projectimplementation risks.- End-user capacity building to improve understanding of core accounting principles is an importantaspect of sustainability.Building capacity in contract (vendor) management is also important.- PFM reform is notjust a one-time project. It is a continuous process, where budget resources must to earmarked for maintaining systemsand capacities as they evolve.
P143202 | Emergency Agriculture Support Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2015 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/225231468189272893/text/ICRR14752-P143202-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/225231468189272893/pdf/ICRR14752-P143202-Box393191B-PUBLIC.pdf | The ICR (p. 16) identifies some valuable lessons including the following:Reliable in-country data is critical for the preparation of an emergency project when there is not sufficient time to collect and analyze data before project implementation starts. In this project, MAFI was lacking capacity for the continuous collection and monitoring of data in the agriculture sector. Therefore, the data for the amount of beneficiaries and hectares of land owned/rented by those beneficiaries was significantly underestimated and did not allow for optimal planning. If countries are likely to experience climate change and disaster events more frequently, a more systematic approach to address these events is critical. Even though Moldova had experienced another drought and heavy flooding quite recently, the project could not rely on an institutionally embedded national natural disaster management system.
P143242 | Solomon Islands Development Policy Operation-2 | East Asia and Pacific | Solomon Islands | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/848131467988951331/text/ICRR14886-P126740-PUBLIC.txt | http://documents.worldbank.org/curated/en/848131467988951331/pdf/ICRR14886-P126740-PUBLIC.pdf | The first two lessons are taken from the ICR with some adaptation of language, and the third is drawn by IEG: Budget support combined with broad policy dialogue arrangements may help achieve reforms. In the Solomon Islands, the Core Economic Working Group, a coordination mechanism involving key government and donor interlocutors led by the Bank, combined with the Economic and Financial Reform Program (a common Government matrix for key reforms backed by budget support), was instrumental in achieving the DPO reforms.Modest reform goals may be appropriate for gradual reformers. Reforms that are uncomplicated and feasible may help build up momentum for additional change. PFM is an example, where the reform path is fairly long and needs to be broken down in steps that a gradual reformer can focus on and achieve.Even modest reforms may take time to achieve full development outcomes. The Solomon Islands DPOs achieved progress in PFM but full results, where the value of the reforms for the population at large materializes may take more than the usual time horizon covered by a DPO program.
P143274 | Justice Sector Institutional Strengthening Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2014 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099061323085516176/text/P14327402d56a102c0ba960459acabf1d9a.txt | http://documents.worldbank.org/curated/en/099061323085516176/pdf/P14327402d56a102c0ba960459acabf1d9a.pdf | Lessons from the ICR:1. Effective oversight and supervision by the Borrower (Government)are important, even if day-to-day project management is outsourced to an external partner. The decision to contract out the projectimplementation to a private firm was intended to address capacity gaps and insulate the procurement process frompotentialcorruption. However, it appears that the contractor lacked the experience and capacity to implement the project,resulting in it becoming a non-performing project during the first 3-4 years of implementation. The downside of engaging a privatesector contractor was also thatno project management capacity was built up in the responsible government agencies or unitsforpossible future interventions (notwithstanding the PADs claim that it would facilitate skills transfer). Later, theintroduction of UNDP as a service provider had the same effect. If the Borrower hada more direct role in project management -whether by assigning government officials to a dedicated PIU as originally envisaged or through embedding the responsibility forproject management/ implementation to a specific government agency - implementation progress could have been much smoother andfaster, and some residual capacity might have been left in the different branches of government.2.Bank support tothe justice sector requires sufficient diagnostic and analytical work, including political economy and/or stakeholder analysis toidentify potential winners and losers, and to design a path forward to success. This is particularly important when the Bank makesan initial investment in the sector. This type of analysis could have helped the team to gain a deeper understanding of the issuesaffecting the justice sector and, in particular, the sensitivities of different stakeholders, and may have resulted in a better,less ambitious but more realistic project design.3. Judicial independence is a means to ensuring impartiality ofdecisions. Organizational independence of the judiciary does not, in itself, guarantee impartiality, and there are examples ofwell-functioning judicial systems where the MOJ acts as the court administrator. When the judiciary does not have the capacity toimplement development projects and available alternatives are considered including the executive branch thearrangements need to be exhaustively discussed and agreed upon between the parties.
P143283 | First Development Policy Operation | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2019 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/443421559241384297/text/Moldova-Development-Policy-Operation.txt | http://documents.worldbank.org/curated/en/443421559241384297/pdf/Moldova-Development-Policy-Operation.pdf | The most important lesson in the ICR is the following (with some adaptation of language):(1)Development policy objectives that are broad in terms of thematic and sector coverage are likely to encounter implementation andcoordination difficulties, particularly in countries with weak administrative capacity.This is confirmed byexperience from these operations, where attempting to address several diverse policy areas at the same time stretchesimplementation capacity and complicates the monitoring of impact.IEG draws the followinglessons:Unless political economy dimensions are carefully considered at the design stage,achievement of a DPOs objectives is likely to be jeopardized. In thiscase, the timing of the operation was less than optimal, since implementation suffered frompolitical turmoilfollowing parliamentary elections. Also, more account should have been taken of the influence of powerful oligarchs over reformprograms, especially in the financial and agricultural sectors, and an analysis made of how this might havebeenmitigated.Sectors presenting especially difficult challenges may be more appropriatelyaddressed by separate, dedicated operations. Here the issues in the financial sector were of such magnitude and complexityas to affect Moldovas macroeconomic stability as well as general confidence in the economy. Under such circumstances,including financial sector reform as one of six distinct policy areas overstretched the countrys limited implementationcapacity. Still more importantly, the reforms that were attempted were sufficient in both number, depth and scope to go to theheart of the problems facing the sector.
P143302 | Ethiopia Competitiveness and Job Creation Project | Eastern and Southern Africa | Ethiopia | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024215013395/text/P1433021e93cbc0491bb3814554f11707fe.txt | http://documents.worldbank.org/curated/en/099053024215013395/pdf/P1433021e93cbc0491bb3814554f11707fe.pdf | The ICR identified a few lessons and several findings and recommendations which are delineated on pages 38-39of theICR. This review has identified two lessons which are rephrased below.When designing and implementing aproject having an IP agenda, a strong engagement and a sustaineddialogue between the Bank and the Borrower teamsarecritical toreconcile and align the Bank IP experience and preferencesand theGovernment policies and priorities.Designing and implementing an IP agenda is a colossal task that has important political economy and micro andmacroeconomic implications. Theprocess of establishingan IP requires a sustaineddialogue between theBankand the Government teams to ensure alignment of views and approacheson how betterto build and manage the IP and toreconcile the roles and responsibilities of the public and private sectors in this exercise. If this alignment falters, thereare important implementation consequences.For this project, the main reasons behind the delays in the timelycommencement of the infrastructure developmentand the skills development and linkages programs were the changes in mandatesand leadership within the government related to the IP agenda. This led to conflicting interests and a lack of ownership of theproject, its plans, and institutional dynamics. The shift in government priorities towards Hawassa was critical. The resultingchanges in the scope and design of the project, the modalities, and the timeframe for implementation affected the various projectcomponents and, ultimately, the achievement of the main development objective of job creation. In that regard, the World Bank needsto reflect on how to resist major changes in project design which risk undermining a projects economic viability and theachievement of its objectives.EstablishingIP entails addressing important environmental and socialsafeguards issues and requires adequate financial resources and timely hiring qualified expertise to manage implementationchallengesand emergencies. On the one hand, by the project closing, there were still groundwater supply andwastewater management challenges. On the other hand, displaced persons associated with Bole Lemi I and Kilinto were resettled andcompensated by the government prior to project approval.Ultimately, access to land to lay power cables was blocked by BoleLemi I PAPs, who were resettled before the World Bank engagement, as a way to leverage more compensation. In the case of Kilinto,livelihood restoration for PAPs, who were moved by the government before the World Bank engagement, was the issue that continues tochallenge the project team 10 years after resettlement. The World Bank should either build all necessary resettlement into projectdesign or else find ways to strengthen the borrowers ownership of social safeguards. Timely hiring of qualified expertsand proper budgeting of sufficient resources to fund resettlement and compensation are key to ensuring thesafe closing ofprojects supporting the IP establishment, and it isessential to mobilize global expertise and knowledge and buildinstitutional capacity and systems at the early stages of the program.
P143332 | Cote d'Ivoire - Productive Social Safety Net | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2024 | 2025 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099112624212539286/text/P143332-d0fc388f-7170-45dc-949f-03db71cececf.txt | https://documents.worldbank.org/curated/en/099112624212539286/pdf/P143332-d0fc388f-7170-45dc-949f-03db71cececf.pdf | These lessons are drawn from the ICR, pp. 29-31, with restatement by IEG.Investments in well-designed,efficient government systems and institutionalization of programs can provide strong foundations with long-term benefits.The development of effective social protection delivery systems is an investment in government ownership and in acountrys ability to deliver well-targeted benefits, and respond to new urgent needs. The country was able to leverage thenew systems to respond to the urgent needs created by the COVID-19 pandemic. The 2020-2021 large expansion of the cash transfer andtraining program demonstrated that a well-designed and well-performing government social safety net program can easily be leveragedto accommodate external pro-poor funding. Continued improvements in the delivery system can ensure that the system remains theprogram of choice for any actor seeking to work through government to reach poor households across thecountry.Incremental innovations, systematically tested before scaling up, are key to success and requiresubstantial implementation support resources. The project gradually introduced the full package of support, includingdigital delivery mechanisms, starting with a relatively small cohort of beneficiaries (5000 households). New elements of theeconomic inclusion package were introduced on a pilot basis, tested, adjusted, and then expanded. This approach provided a chanceto test interventionsand scale up those that worked well. It also enabled strong ownership by government and implementingactors, and finetuning of practices in the field. Two Rapid Social Response grants supported these efforts, helping meet thecrucial need for implementation support resources for analytics and technical assistancein countries with limited experienceand capacity.Leveraging digital platforms can help reduce delivery costs and are well-accepted. Thedigital cash transfer mechanism proved robust, efficient, and low cost, especially when a new digital bank, Wave, entered themarket, and offered very low fees. The project created a secure data platform thatprotected personal informationandincluded measures to minimize possible negative effects of digitization.It did so by active outreach, communicationactivities that brought into the project those at risk of being excluded from digital platforms, and cooperation with otheragencies at the local level. Beneficiary families without access to a mobile phone were able to designate a trusted recipient fortheir funding, and a robust grievance redress mechanismhelped ensure that benefits reached the intendedbeneficiaries.Impact evaluations require strong planning and preparation, and often run into difficulties anddelays. This makes strong, persistent implementation support important, and also emphasizes the importance ofalso using otherrigorous surveys and analyses to provide evidence on project effectiveness and efficiency. Even when adequately resourced,impact evaluations are complex to design and implement. Although methodological challenges prevented full use ofthisprojects impact evaluation results, several other surveys and qualitative evaluations provided useful insights.Complementary monitoring tools and evaluations and adequate resources for implementation, technical assistance, and supervision ofME plans are all important to being able to assess the impact of programs.
P143334 | FIP: Environmental regularization of rural lands in the Cerrado of Brazil | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053124095588211/text/P1433341d7d33404c192781ae1af6a299d0.txt | http://documents.worldbank.org/curated/en/099053124095588211/pdf/P1433341d7d33404c192781ae1af6a299d0.pdf | The ICR included five lessons. Three lessons are emphasized with adaptation of language to support broaderapplicability.The collection of land ownership data disaggregated by gender and social group would increase theaccuracy and impact of policymaking and support targeted to vulnerable or marginalized groups. CAR does not currentlydisaggregate land ownership data by gender or social group. In the future, enriching the data with disaggregated information ongender and social groups would help mainstream these considerations in policymaking and target initiatives intended to supportunderrepresented or marginalized groups.Effective land management and environmental regulation demand theintegration of targeted outreach, robust data integration, and accessibility. The success of increasing rural landregistration in the Cerrado biome highlights the importance of tailored outreach efforts to engage diverse stakeholders, includingsmall, family, and collective landholders. By leveraging targeted communications, these harder-to-reach groups can betterunderstand their responsibilities under environmental regulations, such as the Forest Code.Continuous updates ofonline rural cadaster systems are needed to continuously enhance accessibility, usability, and thus relevance tostakeholders. For example, integrating and aggregating land data in private land registration systems like SICAR wouldprovide valuable insights for coordinated land conservation efforts. This includes leveraging advanced technology to analyze datacomprehensively and propose optimal land-use strategies. Further integration of cadaster systems offers insights into rural landcharacteristics, facilitating informed decision-making on environmental regularization and sustainable land use. To ensure theeffectiveness of environmental regularization policies, it is imperative for governmental agencies to actively analyzelandholders compliance with environmental regulations and provide necessary support for rectification and restorationefforts.
P143367 | AFCC2/RI-African Forum for Agricultural Advisory Services Second Multi-Donor Trust Fund | Other | Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2014 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/203681551191014925/text/Africa-AFAAS-Second-MDTF.txt | http://documents.worldbank.org/curated/en/203681551191014925/pdf/Africa-AFAAS-Second-MDTF.pdf | The ICR (p. 24-25) provided useful lessons learned:It is critical for a projects design to identify and clarify institutional areasto be supported according to the financing available. This project supported the entire Strategic and Operational Plan ofAFAAS without having secured the necessary financing. This resulted in the hiring of fewer staff at AFAAS and relying more onconsultants, which might have had a negative impact on capacity building within AFAAS. Ensuringfinancial sustainability of institutions being supported under a project is critical. In this project, AFAAS has been andcontinues to rely on donor funding which puts a critical risk on the sustainability of AFAAS. Also, this uncertainty impacts theplanning of activities and the effectiveness of activities due to a limited time horizon. It could have been beneficial if theproject had included asub-component which supported the development of a resource mobilization strategy and built capacitywithin AFAAS for sustainable resource mobilization. Country Fora (CF) are an effective way tofoster reforms and strengthen public sector support for AEAS systems. In this project, the CF model was built on existinginstitutions and used local expertise resulting in the emergence of champions and volunteers that were critical for establishingthe CF.
P143382 | Tamil Nadu and Puducherry Coastal Disaster Risk Reduction Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2020 | 2022 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099045005202293756/text/P14338201389c40ca09b070593f589a8b69.txt | http://documents.worldbank.org/curated/en/099045005202293756/pdf/P14338201389c40ca09b070593f589a8b69.pdf | The following lessons have been derived and summarized from the ICR, with minor additions by IEG after discussions with the Banktask team:It may bemore effective to upgrade existing fisheries facilities than to construct newones. This project showed that existingand already used facilities by local communities have an advantage overnewfacilities because communities are familiar with them and feel comfortable.Under theprojects fisheriescomponent, newmodern facilities, such as the fish market in Puducherry, remained underutilized due to fishingcommunitieslow awareness a reluctance to changewhereasthe four upgraded existing fish markets wereextensivelyutilized and were completed at a fraction of the cost and time. When possible, existing infrastructureshouldbe upgraded and/or retrofitted instead of starting new greenfield projects.Designing evacuation shelters asmultifunctional shelters can enhance their likelihood of use and maintenance. The project showed that shelters thatalso functioned as schools or health centers and are located near households that care for them, are more likely to be used andmaintenance than shelters that served only evacuation purposes.Coupling the implementation of new infrastructureand systems with strong community capacity buildingprograms to increase awareness on their existence and use can maximizetheir utilization and the benefits to target populations. This projects evacuation shelters and the early warningsystem saw varying degrees of use, and community awareness was oneof the biggest factors in determining community use andmaintenance. For instance, shelters initially poorly maintained and lacking ownership, saw improved use and maintenance after theformation of evacuation shelter maintenance committees and the CBDRM training programs. Similarly, villages varied in theirawareness of these systems after completion and their knowledge on how to prepare and/or evacuate. While community capacitybuilding components tend to be treated as an afterthought, the project showed significant multiplier effects from the successfulimplementation of the CBDRM program and the incorporation of DRR principles into the school curricula. Therefore, more resourcesshould be devoted to design, implement, monitor, and evaluate these interventions to increase and track their benefits andspillover effects. In addition, trainings, mockdrills, and other experiential capacity buildingprograms should beincorporated from the beginning to enable timely emergency responses.The development of a digital engagementmechanism does not guarantee communities engagement with and enhanced awareness of local disaster risk information.While the potential of theTN-SMART mobile application to reach target populations in Tamil Nadu efficiently has been widelyrecognized, to date, it has not been successful in reaching various publics, with a little over 200,000downloads by citizensin a state that has the second highest number of rural smartphone users. The appshould increase its user friendliness andprovide relevant local information at a more granular level. Futureinterventions should explore the integration of mobileapps and the CBDRM programs to increase both thereach of the app and the accessibility of the trainings to remotecommunities.
P143408 | Samoa Aviation Investment Project | East Asia and Pacific | Samoa | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/346121636636911874/text/Samoa-Samoa-Aviation-Investment-Project.txt | http://documents.worldbank.org/curated/en/346121636636911874/pdf/Samoa-Samoa-Aviation-Investment-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project.1. The regionalapproach can beagoodoption for remote island countries with a limited IDA allocation.Being part ofan IDA regional programallowed Samoa to access additional regional IDA resources for large scale investments in the aviationsector. This project also demonstrated that a regional approach to central procurement can beeffective in generating costsavings, as compared to procuring specializing equipment for each country separately.2.While regionalprograms help in harmonizing solutions across participating countries, such programs need to allow some flexibility for countriesto tailoractivities tospecific country circumstances. In this project, the same set of results indicators wereused for all the participating countries. While this project was able to achieve the requirements of the results indicator, it wasthe only project that was able to do this. The lesson of this project is thatresults indicators in a regional program needsto take into consideration each countrys context.3. Remoteness premiums need to be factored into projectbudgeting, especially when there are limited benchmarksfor a certain sector. For countries like Samoa withsubstantial remoteness premiums, the costs of shipping, equipment, maintenance and expert staff are usually two to three timeshigher than in less remote countries. The lesson is that higher cost contingencies needs to be factored into the project design atappraisal.
P143417 | The Agriculture Investment and Market Development Project | Western and Central Africa | Cameroon | Blend | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2022 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/099700006212230053/text/P1434170d9459c0070a1800c87b33878259.txt | http://documents.worldbank.org/curated/en/099700006212230053/pdf/P1434170d9459c0070a1800c87b33878259.pdf | The ICR presents seven main lessons and recommendations from this project (ICR, paras. 114 120). The four most relevantlessons have been consolidated and further sharpened, and which are based on project-specific conclusions, and which can beapplicable to other projects in Cameroon and other countries, including those in an evolving FCV environment, are summarizedbelow.(a) Lesson 1: Relevance of assessing adequately, working out and agreeing on Government counterpart budgetavailability during Project preparation and prior to Project approval. During project implementation, it appears like thespecific arrangements for ensuring adequate level and timing of counterpart funds from the Government were not clear andfunctional, which contributed to project delays. Since 2020, the Government established a new system of providing projectcounterpart funds, through a centralized basket managed by the Ministry of Finance. As a result, all development projects competefor these counterpart funds, which are limited, and therefore, the project is not assured of getting the counterpart funds whenneeded, resulting in a low level of mobilization and execution of counterpart funds. Accordingly, the lesson from this projectexperience highlights the importance of agreeing on and complying with the specific budgetary allocations for the project, andtherefore, if properly done, this can enhance the likelihood of ensuring adequate allocations during implementation, and theprospects for strong project results;(b) Lesson 2: Importance of securing from project design and approvalstages a clear understanding and agreement of the local conditions and capacities of project stakeholders to engagerealistically in project activities. The project introduced producer beneficiaries, POs and cooperatives to innovativeapproaches to production, processing, marketing, business partnerships, and accessing finance. Implementation delays and challengesrevealed that these innovations and arrangements were not well understood, realistic and worked out, resulting in project delays,changes in scope and substantial sustainability risks. Accordingly, similar or future projects, from the design stage, if there isa realistic and phased approach to designing and carrying out the relevant project innovations, this could enhance the prospects ofensuring adequate local capacities for effective and timely project implementation, and strong and sustainable results;(c)Lesson 3: Importance of adequate understanding and support for the post-production aspects of commodity supply andpurchase contracts to ensuring the prospects for successful operationalization of productive partnerships (PPs). Most ofthe project focus was on increasing cassava productivity with little regard to product specification requirements of agribusinesses(e.g., quality, cleanliness, consistency of supply). As a result, even when beneficiary farmers were able to increase theirproductivity, they still had challenges meeting all of the requirements of the agri-businesses (ABS). Attention to thesepost-production aspects, including flexibility in purchase contracts and involving and strengthening small and medium-sizedinformal agri-businesses (ABs), as integral parts of the Project design, if properly addressed, could enhance the prospects ofaddressing adequately the challenges that many producers and POs face in effectively engaging in the PPs and promoting a morevibrant and competitive agroindustry;(d) Lesson 4: Formulating and carrying out appropriate and well-focusedinstitutional reforms in key subsectors may contribute to successful implementation and sustainability of similarprojects. Seed multiplication cooperatives were the least successful under the AIMDP. These cooperatives could not increasetheir business turnover because they faced unfair competition from non-certified seeds. The Project strengthened capacity forcertification, but little was done to prevent contraband. During planting season, markets were flooded with non-certified supply ata lower cost, rendering cooperatives unable to compete. MINADER tried to intervene, but it lacked the mandate and capacity topolice and prevent such invasions. This project experience illustrates the importance of similar project(s) assessing and designingcarefully the institutional-related risks of success and sustainability of relevant project components, and therefore, ifadequately addressed, could enhance the prospects of effective project implementation and sustainable results.
P143492 | BR DGM for Indigenous People and Traditional Communities | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099062923175111276/text/P1434920a04f140fd0acc008f2daf8e6ba6.txt | http://documents.worldbank.org/curated/en/099062923175111276/pdf/P1434920a04f140fd0acc008f2daf8e6ba6.pdf | The ICR (p. 34-36) included several lessons learned, which were adapted by IEG: Strong communityengagement during the design and implementation of the project requires more time but can lead to sustainability of projectoutcomes. In this project, stakeholders were involved from the beginning and as a result never questioned the design,structure, eligibility rules and choice of NEA. However, strong engagement of grassroot communities with little experience requirestraining and continuous technical support. Empowering IPTC communities to execute their own sub-projects canresult in them becoming key actors in the field. In this project, IPTC communities started to act in unity across ethnicdiversity and geographical distances, and as guardians of the natural resources of the territory they live in. This approach willbe critical for active engagement of the IPTC communities in the area of land use, land and forest management, and mitigation ofand adoption to climate change.
P143588 | Sierra Leone Safety Nets Project | Western and Central Africa | Sierra Leone | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | The ICR (pp. 30-31) defines the following lessons generated through this project: Mainstreaming citizenparticipation in anti-corruption efforts and GRM mechanisms ensures systematic citizen engagement and strengthens the integrity ofSSN systems. Citizen engagement that promotes transparency and accountability was a built-in feature of the project intandem with the GRM. ACC became part of project implementation mechanisms and was increasingly involved in securing projectintegrity and setting new policies, such as the GBV code of conduct for all staff and partners involved in the projectimplementation. The project GRM platform has been mainstreamed within ACCs entire operations, enabling effective preventionof and response to fraud and corruption while ensuring that benefits reach the intended beneficiaries. Other donor-supportedprojects are now using the GRM platform, including the follow-on PSSNYE. The availability of a prefinancedcontingency budget in existing SSN systems increases shock-responsiveness. The provided funding from GRiF forenhancing systems for shock response, as well asthe retention of US$4 million of IDA funds as a contingency budget to fundthe expansion of cash transfers if needed, enabled quick rollout and provision of much-needed emergency cash transfers under theproject in response to the COVID-19 crisis. This experience, combined with the governments interest in enhancing its abilityto respond to shocks through an existing safety net, led to the inclusion of a contingency budget and a zero-financed ContingentEmergency Response Component in the follow-on PSSNYE project to support a third phase of the ECTs to vulnerable female- andelderly-headed households and households with persons with disabilities in urban areas. Moreover, the ECT provided through theproject is expected to remain the governments main response mechanism to shocks and natural disasters for the foreseeablefuture. Mainstreaming a more regular collection of national-level socio-economic data enables better measurementof SSN interventions impact on poverty and vulnerability. The lack of national-level, more up-to-date andcomprehensive socio-economic data, including data on poverty, labor markets,and inflation, made it difficult to accuratelyassess through a pre-post analysis the projects effectiveness and efficiency. A regularized and closelymonitored procedure for reviewing and adjusting cash transfers size can ensure that transfers are meaningful and increaseSSNs shock-responsiveness. One reason for cancelling US$2.45 millionat project closing was that noadjustments of the local currency equivalent of the US dollar transfer size were made, even though the country experienced a largedepreciation of the national currency, which is usually accompanied by inflation. Measures aimed at increasingfinancial inclusion and expanding service providers geographic coverage can help ensure the timelinessoftransfers. As this project demonstrated, a hybrid payment systemcombining electronic and physicalpaymentscan be successfully applied for deliveringpredictable and timelycash transfers to a limited number ofbeneficiaries in a largely cash-based economy. However, in places with low financial inclusion and low penetration of serviceproviders affected by shocks and movement restrictions, such systems may not be sufficient for ensuring the predictability andtimeliness of scaled-up cash transfers. As the experience of this project showed, due to the limited personnel dedicated to theprojects cash transfers delivery, planned earlier in line with a much lower caseload, it was a challenge to coversimultaneous payments of beneficiaries across the country under the rapidly expanding program needs. This was addressed bydelivering payments in tranches and phases across districts, which ensuredthat beneficiaries received the full amount of theenvisaged cash transfers and guaranteed transparency and security througheffective oversight and monitoring ofpayments.
P143594 | LB-Environmental Pollution Abatement Project | Middle East and North Africa | Lebanon | IBRD | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099010324165034118/text/P1435941b829670ef1a28c106a7a18cd6b1.txt | http://documents.worldbank.org/curated/en/099010324165034118/pdf/P1435941b829670ef1a28c106a7a18cd6b1.pdf | The ICR (p. 29-30) included several lessons learned which were adapted by IEG: Failing to develop apipeline and scoping of specific enterprises and subprojects during project preparation can delay implementation. In thisproject, no pipeline of participating enterprises was established during preparation, which resulted in implementation delays. Whenthe project prepared AF in 2019, 12 enterprises were already onboard to receive sub-loans under the AF which would have enabledfaster implementation. Allowing financing mechanisms for subprojects to adapt to changing circumstances can helpwith project implementation. In this project, a national financial crisis occurred, which threatened projectimplementation as the commercial banks could no longer meet the initial conditions of the subsidiary financing mechanism. Adaptingthe subsidiary agreement between the central bank and the commercial banks enabled the commercial banks to resume lending, whichenabled the project to continue its activities, while other projects had to be closed early. Failure to lay outsufficient indicators to assess all aspects of the PDO can cause project restructurings and hinder project ratings. Thisproject had to be restructured in 2018 since the Results Framework did not include any outcome indicators to assess the secondaspect of the PDO (Strengthening the monitoring and enforcement capabilities of MOE). It is possible that achievements of thesecond aspect of the objective would have been higher if an adequate set of indicators would have been used to measureimplementation progress and identify bottlenecks.
P143596 | RESULTS-BASED NATIONAL URBAN DEVELOPMENT PROGRAM IN THE NORTHERN MOUNTAINS REGION | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | PforR | 2014 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099081423173060126/text/P14359603c5e780620b2120531621c9c9c9.txt | http://documents.worldbank.org/curated/en/099081423173060126/pdf/P14359603c5e780620b2120531621c9c9c9.pdf | The ICR presented six lessons from the operation,slightly paraphrased below (ICR,paragraphs83-88): Well-defined results assessment protocols and a credible and comprehensive verification system mayhelp achieve the planned outcomes. This program used a transparent ME system at national and city levels, linking itwith the MIS and independent verification. The verification-based disbursement process was an important learning-by-doing tool thatincentivized results. The verification protocols included the engagement of a credible independent agent with clearresponsibilities and capacity. World Bank quality assurance improved the credibility of the performance assessment SAV conducted.Cities claimed that SAV verificationimproved the quality of their infrastructure investments. DLIs and PAPsmaytarget inclusive urban management,strengthen management capacity, andcontribute topoverty reduction inthe target area.In this program,DLIs were used tostrengthencapacities at the city andnational levels. DLIs focused on improving the cities capacity and systems to plan and implementurban infrastructureinvestments. National capacity to support cities in urban managementprocesses alsoimproved. PAP actions ensured thedelivery of quality infrastructure that benefited the poorer, vulnerable groups such as womenand ethnic minorities in thesetarget areas. Adding expenditure and payment strategies may boost a citys ability topre-financeinfrastructure works. In this program, payment delaysto contractors resulted fromthecitys inability topre-finance infrastructure works. DLI advances, and available counterpart funds alsoprovedinsufficient. MTIP also hadinadequateallocationsfor both IDA and counterpart funds. Future design mayfind adding expenditure and contractor payment strategies helpful to help cities address their lack of capacity to pre-financeinvestments. If national policies do not reflect support for cities to generate their own resources andsetlocal taxes and user fees for service delivery to residents, this may affect the cities capacity to sustain the assets theybuildand the service delivery provided to their residents.The cities fiscal condition would be enhancedif they could increase their revenues from their sources. In this program,cities increasingly assumed more responsibilitiesto deliver urban infrastructure and services to residents. These cities often lacked the management capacity to plan, implement, manage, and sustain the financing needsof the investments and provide for OM from their resources. The 12 percent annualincrease target for revenues set at appraisal in response to high inflationrates proved unachievable. This was compounded bya change in tax and public financial management policies set at the national level that negated local resource mobilizationefforts. PforRfinancing is ausefulinstrument to improve the performance of both national andsub-national governments. In this program, the result indicators focused on improving the performance ofboth thenational and sub-national governments. DLItargetsenhanced the national governments capacity and improved systemsfor urban policy and implementation support to cities. The program demonstrated the effectiveness of creating synergies inassisting two aspects in delivering infrastructure services. One focused on strengthening the national agencies policyenvironment and oversight system, while the otherincreasedtechnical support to cities.
P143645 | TZ First Power and Gas Sector DPO | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2018 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/959181529101751996/text/Tanzania-TZ-First-Power-and-Gas-Sector-DPO.txt | http://documents.worldbank.org/curated/en/959181529101751996/pdf/Tanzania-TZ-First-Power-and-Gas-Sector-DPO.pdf | The first three lessons are drawn from the ICR (paragraphs 94-96, pages 39-40), with some adaptation; the fourthisdrawn by IEG.Power sector reform programs that advance the electricity access agenda, among otherobjectives, need to incorporate the access effort in program design more explicitly. The DPO recognized the Governmentsobjective to expand access to electricity but failed to explicitly model the initiative in the programs results framework.Consequently, the DPO did not anticipate the increase in TANESCOs arrears despite over-achieving its income targetsasthe electricity company tripled its new connections in three years.Engaging the Tanzanian government on a policyframework for the development of the natural gas industry was worth the effort, notwithstanding the poortally on the programresults indicators. The steep decline in global oil and gas prices in 2014-16 slowed down the gas sector reform momentum inTanzania during the program period. However, theGovernment succeeded in developing thelegal framework for the upstreamgas industry, setting the development agenda for the entirety of the countrys energy supply chain that would be vital to thecountrys future economic prospects.Initiatives to expand the participation of the private sector in energysupply need to be informed by politicaleconomy analysis. A small number of controversial and poorly executed PPP contractscast a long shadow on the outlook for PPPs in Tanzanias power sector. A new Bank document, Rethinking Power SectorReform, lays out an agenda for more closely integrating political economy considerations in power sector reform programs.Astrong link between prior actions and reform implementationincreases the chance of DPOs achievingtheir objectives. The program missed mandating a timeline for the execution of policy and institutional reform plans adoptedby the Government in fulfillment of the prior actions, leaving elements of the reform program exposed to reversal and stalling asnew developments muted the urgency of the reforms, a new government assumed office, and political preferences shifted.
P143650 | Maternal and Child Nutrition and Health Results Project | Western and Central Africa | Gambia, The | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/364421619714232912/text/Gambia-The-GM-Maternal-Child-Nutr-Hlth-Results.txt | http://documents.worldbank.org/curated/en/364421619714232912/pdf/Gambia-The-GM-Maternal-Child-Nutr-Hlth-Results.pdf | The following lessons are a subset of the nine relevant and insightful lessons presented in the ICR, slightly reworded by IEG tobe more succinct:Learning initiatives and solid analysis during preparation can beinstrumental in improving project design and implementation.For this particular project, these included:a pre-pilot learning experience grant; participation of the project team in a South-South Learning Exchange to observe RBF programsin Rwanda, Burundi, and Zimbabwe; and project preparation studies that established background and baselines for projectdevelopment.A RBF design can be both innovative and effective in its approach to supply- anddemand-side interventions, which, in turn, serve to increase the utilization of maternal and child health and nutritionservices.The projects piloting of community-based RBF was an important complement to supply-sideRBF approaches aimed at improving the availability and quality of service delivery.Community-based RBF increased the use ofpreventive services (Vitamin A supplementation, deworming, antenatal care visits), improved health workers responsiveness tocommunities, and raised the bar for greater involvement of communities in improving health and nutritionoutcomes.Strong government commitment to RBF is key to its successful implementation andsustainability. The approach required significant technical support and institutional arrangements that guidedoverall implementation.Two years before project closing, the Ministry of Finance and Economic Affairs, National NutritionAgency, and Ministry of Health developed and launched implementation of a Sustainability Road Map (addressing financial,institutional, and operational sustainability), and allocated annual budgetary resources for 2019 and2020.Also key to the successful implementation of RBF is capacity strengthening at all levels:central, regional, and local levels. Training on RBF management, ME, and other guidelines and policiesequipped the project team, regional health directorates, and the Department of Community Development to encourage and overseeincreased utilization of health services.Training of village development committees and village support groups enhanced theirability to mobilize community engagement, participation, and ownership, leading to changes in attitude, behaviors, and practicesand an increased demand for health and nutrition services.Paper-based health datamanagement runs the risk of clerical data issues, which have repercussionsfor data accuracy and RBF operations andpayments. Project experience points to opportunities to shift toward electronic systems toimprove datacollection and management and to facilitate data verification.There is also scope to digitalize the Quality of Care checklistand link it to the demographic and health information system.A multi-sectoral approach iscrucial to ensure better health and nutrition outcomes, but this requires additional support from other sectors.This holds especially true for the agricultural sector, given the food and nutrition security crisis and responsethatemerged during project implementation.South-South exchanges and learning visits could be relevant for inspiringbetter cross-sectoral coordination and implementation, along with the development of clear roles and responsibilities forimplementation.IEGs review offerstwo additionallessons:A well designed and implemented RBF approachcanstrengthen the qualityandresilience of health and nutrition service provision, and achieve formidable results, even in the face ofa difficultcountry context. This project was designed andimplemented when The Gambia was facing many significantchallenges: a coup dtat, presidential elections, poor economic performance causinghardships to households,erratic rainfall, andincreasing food and nutritioninsecurity.And yet,the projectachieved a highlysatisfactory outcome. Resilience to political changes can be attributed at least in part to the RBF approach and itsdisciplined focus on service quality. It set quality standards andenabled service providers to attainthose standardsthrough its payments for performance. This gaveproviders the liquidity, flexibility, and incentiveto maintain andfurther improvethat quality during a period of political change and uncertainty.It alsoearned the strongappreciation and support of communities, whovoiced their desire with the newadministration (during itsinitialfield visits)to maintain this approach post-project. Moreover, the strong results focus of RBF triggered projectrestructuring and additional financing, designed to ensure the achievement of the PDO in lightofheightenedvulnerabilitiesin the country duetoincreasing poverty and food and nutritioninsecurity.A strong results focus throughout implementation, characterized by the continuedupdating of resources, interventions, and results framework in response to emerging challenges and opportunities, is likely toenhance project performance and outcomes. The Banks team was proactive in refining many aspects ofproject design, financing, and outcome measurement, undertaken during the course of five restructurings andincluding twoAdditional Financings.These efforts, harmonized with RBF performance indicators in supply-side, demand-side, andadministrative contracts, kept all actors focused on the monitoring and achievement of the PDO.
P143652 | Benin Multisectoral Food Health Nutrition Project | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2020 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/497441593010756471/text/Benin-BJ-Food-Health-and-Nutrition-Project.txt | http://documents.worldbank.org/curated/en/497441593010756471/pdf/Benin-BJ-Food-Health-and-Nutrition-Project.pdf | These lessons are drawn from the ICR (with editing):Good institutional arrangements, fromnational to community levels, are important to the success of community-based nutrition programs in reducing stunting.Consistent, coherent and visible policy at the national level that engages all key sectors, clarity on the key roles thateach sector needs to play that facilitates multisectoral collaboration at each level, and support and capacity-building forimplementing partners, notably communities, all contribute to effective and sustained action.Local governmentownership ofa project is as important as community mobilization. In this case, municipality-level multisectoralplatforms fostered formal partnerships across decentralized services, enabled sharing of information, provided a visible way formayors to show their commitment, ensured that nutrition was integrated into municipal annual workplans and budgets, and increasedaccountability for nutrition outcomes in the community.Several factors contribute to effective communication forbehavioral change: messages on improved behaviors that make sense in the context of the culture (values,beliefs, etc); relate to powerful motivations such as ensuring child health and survival; are possible to act on; are frequentlyreinforced and supported by opinion leaders and influencers; and whose possible result is evident, such as in local testimonies andexemplars of exclusive breastfeeding for 6 months, or successful home gardens or successful treatment and recovery.
P143661 | Competitive Industries Project for Khyber Pakhtunkhwa | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2013 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/621151485213528742/text/ICRR-Disclosable-P143661-01-23-2017-1485213518092.txt | http://documents.worldbank.org/curated/en/621151485213528742/pdf/ICRR-Disclosable-P143661-01-23-2017-1485213518092.pdf | The five lessons are drawn from the ICR (pages 19-20), with some adaptation.One, notwithstanding the inherentrisks in emergency situations and in conflict and fragile areas, the Bankcan supportrelevant projects that constructthebuilding blocks for long-term development, by using a start small, learn, and scale-up approach. Projectsshould have simple and concrete development objectives to build on successes gradually. Realistic, even if modest, outcomes thatare achievable within a projects duration yield demonstration effects that can lead to more ambitious results in thelong-term.Two, emergency response projects need to allow for flexible implementation arrangements.Implementation will need to be responsive to changes in the security setting, in the political order, including in thepolitical leadership, and in economic conditions. Flexibility may involve amending the project objective, changing the output andoutcome targets, or even cancelling non-performing components and activities. Project task teams should be prepared forsome failure and be empowered to modify project elements to turn a troubled operation around.Three,Bank-supported projects in conflict and fragile areaswill requirea detailed and incisive assessment of the politicalrisks to the project, both during appraisal and during implementation. Country risks are significant in emergency conditionsand a better understanding of the countrys political situation affords project planners the opportunity to considerpolitical risk mitigation measures and project implementation managers the ability to react quickly to political developments andchallenges.Four, government ownership of, and commitment to, a project is most vital and crucial in a fragileenvironment as it can determine the success or failure of the operation. Ownership and commitment is also difficult to ensureand can change at any time during project preparation and implementation. A stakeholder analysis can help shed light on the degreeof government ownership of and commitment to a project. It can also help inform the Bank on how topersuade a government toaddress policy, institutional, and operational issues confronting a project.And, Five, close attention toprocurement issues and activities is necessary in a low institutional capacity context. When there is limited capacity, theBank should consider outsourcing the procurement function rather than struggling to build the capacity to conduct procurementin-house. It normally takes some months, however, to engage private procurement agent, so the process needs to be started earlyon.
P143751 | Second Tamil Nadu Road Sector Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2021 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099300412232210846/text/P143751005f9b00a2090a30defa6bf1dcfb.txt | http://documents.worldbank.org/curated/en/099300412232210846/pdf/P143751005f9b00a2090a30defa6bf1dcfb.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Longer term engagement can help in driving reforms and building stronger institutions. Thisproject built on the sector dialogue developed under the previous Bank-financed transport project on innovating contractingformats, road safety and road sector policy. This longer-term engagement helped in implementing an institutional reformprogram.2. Data driven multi sectoral approach can help in addressing road safety issues. This projectadopted decision-making based on crash data to identify road safety infrastructure investments to manage post-crash response andtrauma care. The road safety infrastructure investments and enforcing mandatory wearing of a helmet, monitoring speeding andawareness campaigns helped in reducing fatalities in the project-intervened areas.3. Establishing dedicateddecentralized land acquisition unit with required staff and resources can help in facilitating land acquisition. Theimpact evaluation conducted at project closure confirmed that in eight of the 13 contracts land was handed over on time and hencedelays in construction were avoided.
P143774 | Cambodia PFM Modernization Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2014 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/356131524772146433/text/Cambodia-Cambodia-PFM-Modernization-Project.txt | http://documents.worldbank.org/curated/en/356131524772146433/pdf/Cambodia-Cambodia-PFM-Modernization-Project.pdf | The ICR (pp. 20-21) offers several valuable and insightful lessons and recommendations,including:Sequencing matters, especially when attempting complex reform in a low-capacity context. Inthis case, the predecessor projects (Public Financial Management and Accountability Project, 2006-2013) outcome was ratedUnsatisfactory by an IEG Project Performance Assessment Report (PPAR), which observed that the FMIS contract award collapsedafter five years of failed procurement (p. ix). PFMRP built on this experience, taking a phased approach. TheFMIS design started initially with payments and receipts transactions at treasury offices, before rolling out other modules andgoing into other organizational units. These and other design changes allowed for a successful procurement of anFMIS.Deliberate and careful change management activities, grounded in high-quality political economyanalysis,are central to the success of potentially controversial reforms. In this case, the reform process was put atrisk by middle-level managers whose divergent perspectives and competing interests could have significantly impededimplementation. A combination of committed MEF leadership and Bank change management interventions created an environmentthat respected and engaged all key stakeholders, acknowledging their concerns and providing them with pathways to identify andinhabit their roles in the new system.IEG offerstwo additional lessons:Clearand well-articulated objectives facilitate the conceptualization and implementation of a coherent, plausibletheory ofchange. In this case, although the initial key outcome measures were overly broad, the clarity of the objectives facilitatedthe project teamsflexible adjustment ofthe results frameworks details. As a result, achievements weretrackable, demonstrable, and clearly linked to intended outcomes.Information technology procurements canachieve efficiency by focusing in the initial stageson high-value expenditures. In this case,a relatively smallproportion of transactions, but the bulk of expenditures, were covered by the FMIS(see ICR, Annex 7).
P143781 | Côte d'Ivoire: Poverty Reduction Support Credit 2 | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2015 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  |  |  | The following lessons are adapted from the ICR:When the disbursement objective of a DPOpredominates, program design should be less ambitious. The tradeoff between budget support and reform implementation inthis series led to instability in the triggers and the policy matrix. More importantly, it compromised some potential achievementsbecause of the failure to delay disbursement until key reforms were made (ICR, p. 32). In such contexts thereshould be explicit mention in the PD of the primacy of the disbursement objective.The effectiveimplementation of reform programs requires effective sequencing. The lesson from reform program in Cote dIvoireillustrates the need to allow adequate time for their completion. Politically sensitive reformscentral to the performance of the economy require the participation of Bank staff in their design. Outcomes in CotedIvoire demonstrate that if appropriate measures are not adopted by government authorities, the reforms should be excluded,and the viability of the entire program should be reviewed in depth. IEG adds the followinglesson:Reform programs with large numbers of prior actions are difficult to implement. TheCote dIvoire DPO series illustrates that reducing the number of prior actions would provide the program with more focus
P143801 | Cameroon - Multimodal Transport Project | Western and Central Africa | Cameroon | Blend | FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest |  |  | The ICR draws the following two main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Factoring in the effects of climate change and building asset maintenance, may raise the potential forsustaining investments in road sector projects. As the effects of climate change are increasingly affectinginfrastructures, it may be useful to conduct analytical studies to study the effects of climate change. It may also be useful tocarry out policy dialogue with the authorities on financing mechanisms for routine road maintenance activities.2.Innovative solutions to evaluate and monitor road and railway projects may be particularly useful in complex securityenvironments. Given the difficulties experienced in this project on monitoring outcomes, the project used geospatial data,remote sensing data and satellite imagery for visual inspection of outcomes.3. A series of complementary projectsmay be required to improve the competitiveness of a largely dysfunctional railway network.The lesson from thisproject showed that a stand-alone project may not be sufficient, given thesubstantial investments required to rehabilitate anetwork of almost 1,000 Km.
P143841 | Afghanistan: National Horticulture and Livestock Productivity Project | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099325103292210489/text/P14384109846f0028081a50c56d91e300d2.txt | http://documents.worldbank.org/curated/en/099325103292210489/pdf/P14384109846f0028081a50c56d91e300d2.pdf | The ICR presents nine main lessons arising from this project (ICR, paras. 98 103). The five most relevant lessons whichinclude project-specific conclusions, and which can be applicable to other similar projects in Afghanistan and in other countries,especially in a FCV environment, are summarized below.(a) Lesson 1: Ensuring demand driven andparticipatory methods, and relying on strengthed public services are effective and sustainable in achieving the intended results,as long as they are complemented by adequate and effective capacity building approaches/activities for existing and relevantgovernment and community organizations.The project made a drastic change from the previous Bank-financed HLP project byrelying entirely on existing government and community organizations to implement the investment packages, with the activeengagement of community organizations (but with some limited external technical support). The very weak capacities of Governmentand communities in a very challenging FCV environment, led to the projects moderately unsatisfactory performance. Thus, theproject experience highlighted the importance of adopting a more realistic and gradual reduction of external TA support,phased/linked to the progress in building local capacities;(b) Lesson 2: Promotingactive and meaningful participation of women in project design and implementation, coupled with adequate consideration of localsocial and cultural norms, are important parameters for the sound design and effective implementation of agricultural-basedprojects in low- income countries. It was noteworthy that the project targeted a large proportion of beneficiariesto be women (40% of total beneficiaries) through appropriate and women-specific horticultural and livestock activities (e.g.,kitchen gardening, micro greenhouses, poultry). The project also provided training support to women beneficiaries, with specialattention to the selection of venue, transportation, and facilitation;(c) Lesson 3: Sound and functional MEsystem from early stages of implementation helps with identifying challenges in project design and implementation and with ensuringrealistic targets and sound design for the AF phase. The ICR showed that NHLPs weak ME system was a keyfactor behind many of the projects shortfalls and failures to address key challenges (e.g., overly ambitious projectscope/targets, which were enabled by poor quality data, contributing to false expectations and to poor decisions involvingunrealistic scale-up of targets during the AF phase in 2016). These unreliable data quality and resulting ME weaknessescontributed to poor decisions, resulting in unrealistic scale-up and targets during the projects restructuring and AF stagein 2016. Accordingly, the experience of this project highlights the importance of ensuring from the design stage a functional andreliable ME system of the project to help guide key design and subsequent restructuring/AF decisions;(d)Lesson 4: Promoting sound design and implementation of the projects fiduciary arrangements, especially in a challenging FCVenvironment, is vital to help ensure efficiency, effectiveness and accountability of project results. Theprojects in-depth fiduciary review highlighted various challenges and corresponding specific lessons which underscore theimportance of ensuring these specific fiduciary aspects are addressed adequately during the projects initial design stageand throughout implementation. The nature and scope of these specific issues are highlighted in the ICR (para. 103).This ICRR focuses on highlighting 3 specific lessons which can be used as a check-list for the design stage of fiduciaryaspects of similar projects in other countries, contextualized to the specific country/project conditions. These lessons include:(i) importance of ensuring consolidation and other appropriate mechanisms (e.g., voucher system) of procurement packages, where feasible, as it would reduce the number of contracts under post-procurement review, which, if not reduced, could increase thegovernance risks;(ii) importance of ensuring robust monitoring, including third-party monitoring and added fiduciaryoversight by the Banks project team to help mitigate risks;(iii) importance of the Bank project team providingadequate and effective oversight on key aspects involving human resource management, staff hiring, payroll, financial reporting,without micro-managing; and(e) Lesson 5: With COVID or other crisis conditions, this project highlighted theimportance of the Bank developing an operational contingent instrument and mechanism for fast crisis response,without disrupting the implementation of on-going projects. With the COVID epidemic, the Banks on-goingproject portfolio was adjusted to make funds available and deployed to support COVID emergency response, especially with respect toemergency food security response. There was an absence of existing Bank financing instruments to address this COVID crisis.Therefore, this re-allocation of funds from existing projects, including NHLP, resulted in the following adverseeffects: led to significant disruptions of the Bank portfolio of the projects, increased delays in theimplementation of NHLP, and the agriculture portfolio was largely reduced (ICR, para. 104).
P143842 | Nigeria Partnership for Education Project | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Education | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/826911623418852916/text/Nigeria-P143842-NG-Partnership-for-Edu-Project.txt | http://documents.worldbank.org/curated/en/826911623418852916/pdf/Nigeria-P143842-NG-Partnership-for-Edu-Project.pdf | Lesson 1: Demand-side interventions aimed at alleviating key constraints related to poverty and socialnorms can be effective in addressing entrenched and complex economic and social constraints to girlseducation. Experience under the project indicates that the provision of scholarships and community mobilizationinitiatives tied to school and community-based initiatives can raise awareness about the importance of education for all, andfacilitate the entry of girls into the school environment and ensure that girls remain in school.Lesson 2:Increasing teachers motivation and accountability can be critical to improving student learning outcomes.Interventions such as the provision of State-level investment grants, learning materials, and training of teachers are unlikely tobe effective if teachers are absent, lack motivation, and are unaccountable for student learning. Project data show that even afteryears of project implementation, teacher absenteeism remained a major unaddressed challenge in participating States. Numerousfactors may enhance or reduce teachers motivation including policies on selection, salary, and career growth, as well asschool-level factors such as working conditions, availability and quality of support for teachers, and accountability systems.Understanding and addressing these factors is important to improving the quality of teaching in the classroom and, ultimately,student learning outcomes.Lesson 3: Raising schools and communities awareness about projectinterventions, including on eligibility requirements and selection processes, can be critical to ensuring inclusivity and buildingtrust. Under the project, communities and schools lacked awareness about the grant and scholarship selection processes andrequirements, leading to delays and confusion in the early years of implementation. Investing in awareness-raising and communityengagement activities early on, even during preparation, can help prevent delays and build trust and partnership with beneficiarycommunities.
P143843 | Maternal and Child Health and Nutrition Services Support Project | Western and Central Africa | Togo | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099025012202128961/text/Togo000TG00Mat0Child0Health0Support.txt | http://documents.worldbank.org/curated/en/099025012202128961/pdf/Togo000TG00Mat0Child0Health0Support.pdf | The following lessons were derived from: the ICR (and reworded by IEG), IEGs own review of the PAD and ICR, and itsdiscussion with the ICR Main Contributor:Failure to nurture and support the full involvement ofthegovernment in the design and implementation of a Bank-funded project is likely to undermine the potential for strong countryownership, which, in turn, risks jeopardizing the sustainability of a projects developmentoutcomes.Fragile countries with limited human and financial resources need a strong, in-country presence ofBank staff to ensure a sound and ongoing dialogue, a well-designed project with strong national and local ownership, andan iterative, respectful process of trouble-shooting, learning, and adaptation.The quality and potential of theBanks contribution to this project was undermined by the rapid succession of four TTLs, all based in Washington, whoseresponse time and dialogue fell short of needs.Moreover, in this context, analytic work both prior to and during projectdesign and implementation may have enhanced the evidence base of the governments malaria and nutrition programs and theBanks contribution thereto.In a low capacity country, with weak evidence and ME capacity, investmentsin strengthening HMIS are critical to establish the importance of an evidence-based culture. In this project, theBanks investments in building HMIS capacity at every level of the system, which enabled the collection and reporting ofinformation at every level of the health system, did indeed stimulate an improved capacity and appreciation for theproduction and use of information for decision-making.This component contributed to the governments interest andleadership in undertaking the first DHS in the countrys history.The importance of meeting the informationaldemands of a well-defined project results framework cannot be overemphasized, for the purposes of: learning, dialogue,evidence-based decision-making, adaptation, and sector ME capacity building.In the case of this project, the Bank couldhave been more rigorous, proactive, and supportive on a number of ME fronts, including: Provision of technicaland financial support for the undertaking of national surveys to ensure the availability of viable end-of-project data on keyindicators; The undertaking of an assessment of beneficiary perspectives (including both women who accessed services andthose who did not) that would assess financial and other impediments to utilization; An earlier restructuring of theresults framework; Consistent clarity (building on the PADs ME plan), especially during restructuring andfinal evaluation, in the definition of indicators, data sources, and geographic scope of measures (whether data are national or fortwo project regions or countrywide).More than the tally of data on indicators, evaluation requires thetriangulation and analysis of qualitative and quantitative data and the assessment of results chains to understand aprojects cause and effect, attribution, contribution, and counterfactual.Evaluation is important not only toassess a projects performance, but also (and more importantly) to factor learning from evaluations into ongoing and newinvestments.
P143844 | DRINA FLOOD PROTECTION PROJECT | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/541521634574489848/text/Bosnia-and-Herzegovina-Drina-Flood-Protection-Project.txt | http://documents.worldbank.org/curated/en/541521634574489848/pdf/Bosnia-and-Herzegovina-Drina-Flood-Protection-Project.pdf | The ICR included six lessons. The followingthree are emphasized with some adaptation of language:1. Toensure timely implementation, project readiness must be assessed and ensured as much as possible beforeeffectiveness.The project entered effectiveness without technical and operational readiness for infrastructuredesign, which caused substantial delays and subsequent restructuring during implementation. The project was hastily prepared underbudgetary limitation of both the RS and FBiH that lacked resources to implement design studies on its own and optimisticassumptions that the civil works identified by past studies would not require substantial adjustment in design. The operationaltimeline set out during preparation also underestimated the time required for the procurement and implementation of engineeringdesign studies, associated environmental and social studies, and mandatory safeguardprocesses.2.Proactive and participatory engagement with citizens is key to successful land acquisitionand project implementation. Public hearings need to be conducted as often as possible until the project and localstakeholders reach full understanding and agreement. Every possible measure, including roundtable workshops, participatoryconsultation approaches, and use of visualization tools (videos and computer graphics of as-built infrastructures), needs to beemployed to facilitate public understanding. The project experience suggests that compliance with the Bank procedures was notnecessarily sufficient in engaging local stakeholders. Local landowners were opposed to the dike alignment in Bijeljinadespitethe disclosure and consultation process in compliance with World Bank safeguard procedures.Interviews with thePIU and World Bank team indicated alack of interest among the project beneficiaries during the consultation process despitethe PIUs efforts in publicizing the project through various channels (such as TV, radio, andnewspaper).3.Continuous maintenance efforts with due consideration of climate change impact areimportant to ensure sustained project benefit and should be built into the design of floods management projects.Thecontinued fulfillment of project benefit requires periodic maintenance of the infrastructureconstructed/rehabilitated. In the long run, the infrastructure may also need reinforcement or expansion considering the threats ofgrowing intensity and frequency of heavy rains due to climate change. The project recognizes maintenance of public infrastructureas the responsibility of local municipalities, and establishment of effective maintenance mechanisms was not embedded in theprojects scope. Inclusion of such mechanisms, including integration of climate adaptation measures, would bolster thesustainability of investments. Use of community engagement is also an effective approach to ensure long-term maintenance andmanagement of infrastructures as well as to raise disaster awareness among public citizens.
P143849 | CG Rep. Health Sector Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/666181619623006829/text/Congo-Republic-of-CG-Health-Sector-Project.txt | http://documents.worldbank.org/curated/en/666181619623006829/pdf/Congo-Republic-of-CG-Health-Sector-Project.pdf | The ICR identified some lessons and recommendations, including the following lessons re-stated byIEG:The support system surrounding Performance Based Financing is key to achievingresults. In this project, the support system included tools that were put in place during implementation suchas training, coaching, supervision, verification mechanisms, statistical record keeping, treatment protocols, and scorecards.Facilities maintained records of accounts, performance, and rewards.PBF was further supported by a law enacted in 2019,paving the way for its institutionalization. An imbalance in human resourcesdistribution can be an adverse consequence of PBF. Contract structures attracted health workers from other healthfacilities that were not under the PBF program, creating an imbalance in staffing distribution.Inaddition, the task team identified a lesson during interactions with IEG:Setting up a budget for essential healthservices program based on a veryvolatile funding stream is likely to have negative consequences on the servicesprovided. In this project, health services under PBF were discontinued due to the lack of funding that resulted from asharp decline in oil prices and revenues, and the decline was consequential because theBorrowers counterpart financingconstituted 80% of total project costs.
P143914 | GABON - SUSTAINABLE MANAGEMENT OF CRITICAL WETLANDS ECOSYSTEMS | Western and Central Africa | Gabon | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099405101272236950/text/Gabon000GA00Su0mt0Critical0Wetlands.txt | http://documents.worldbank.org/curated/en/099405101272236950/pdf/Gabon000GA00Su0mt0Critical0Wetlands.pdf | The following lessons in the ICR can be relevant to other projects on natural resource management and conservation, and arepresented here with some editing.1. Sustainable financing for conservation of wetlands can potentially enhancea flexibility in budget allocations to finance essential costs to implement field activities within and beyond the protectedareas. Under the project, provision of operational costs addressed issues of the recurring shortages of humanresources funding due to the inflexible usage of natural resources management budgets that overly focused on surveillanceactivities within the protected areas. Tapping multiple financing options, including conservation trust funds, endowment funds,green bonds, and debt-for-nature swap, can enable versatile budget allocations to the environmental and social activities in thefields.2. Strengthening local capacities on financial management and transferring accounting responsibilitiesto decentralized entities can enhance project effectiveness and sustainability of results. The projectsupported capacity development in local entities by: (i) opening project accounts in the field to enable transferring money on theground; (ii) utilizing local ANPN offices; (iii) utilizing the decentralized accountant capacity built under the past GEF-fundedproject; and (iv) incorporating Ramsar subcommittees and CCGLs into site management. Building upon the projectsachievements, establishing financial management control systems with appropriate accounting software would support thedecentralized financial management to function well.3. Integrating the landscape approach into project designcan enhance stakeholders understanding on issues affecting conservation of wetlands and their biodiversity in thelong-term. Mapping of human activity, flora, fauna, and ecosystems at the project design stage articulatedcomplex and intersectoral issues to be addressed by the project components and activities. The landscape approach needs to bedirectly linked to structured national Land Use Plan approaches and local development planning to further enhance itseffectiveness.
P143915 | Safety Net and Skills Development | Eastern and Southern Africa | South Sudan | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/247341584536261927/text/South-Sudan-Safety-Net-and-Skills-Development.txt | http://documents.worldbank.org/curated/en/247341584536261927/pdf/South-Sudan-Safety-Net-and-Skills-Development.pdf | Lessons from the ICR (page 29-30), adapted by IEG: The use of third parties asimplementingpartnerscan be very effectivein fragile andconflict-affected settings, especially insituations wheregovernment capacity and systems are nascent and access to project locationsis limited. In the case of this project, theengagement of UNOPS as implementing partner --supported by a commercial bank as the payment service provider -- helpedmitigate the capacity gap, enabled access to remote and insecure areas,and mitigated high fiduciaryrisks. A project design that addressesthe specific daily needs and challenges of women is an effectiveway to promote gender equity and inclusion. Discussions with implementing partnersand beneficiaries revealed that thetargeting process usually took place in the morning, which was the time ofday that women wereusually available at homeor in the neighborhood. Meaningful participation of women in public works activities was then achieved through: (a) participationof women in the selection of public works activities and in the community structures; (b) work activities and payment sites were inclose proximity to beneficiaries houses; (c) assignment of work tasks based on physical ability (the ICR expressed this aslight and appropriate work for women), including consideration for pregnant and lactating mothers included in the worknorms; (d) selection of work hours taking into account womens household obligations; (e) provision of work site shelter forchildren during work hours; and (f) zero tolerance towards violence. An additional lesson drawn byIEG: Capacity building measures to expose national institutions to international expertisecan be effective indeveloping nascent capacity. In the case of this project, the twinning arrangements withtheTechnicalSupportTeamwith international experts, knowledge exchange, and study tours, contributed to theproject implementation unitstransition from one staffed fully by international consultants to one with a majorityofnational staff. In addition,working closely with international NGOs, a United Nations agency and a commercialbank also opened opportunities to learn new skills and build capacity.
P143921 | Croatia & Bosnia & Herzegovina GEF Adriatic Sea Environmental Pollution Control Project (I) | Europe and Central Asia | Western Balkans |  |  | Sustainable Development | Water | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/133941573058364728/text/Western-Balkans-Adriatic-Sea-Env-Pollution-Control-I.txt | http://documents.worldbank.org/curated/en/133941573058364728/pdf/Western-Balkans-Adriatic-Sea-Env-Pollution-Control-I.pdf | Based on the projects design shortcomings, the ICR (p.30-2) provides a number of lessons. One lesson belowcombines elements froma number ofthe lessonsin the ICR stands out andis summarized below. IEG hasadded a suggested lesson.-Agreementsamong stakeholders on critical necessary conditionsfor project success are needed in advance of project implementation.Without advance agreements between clientcountries and the Bank on the availability of crucial resourcessuch asinstitutional capacity,projects willfail.In this project, the lesson was that expectations of stakeholdercapacities and future levels of engagementwere based onagreed responsibilitiesidentified at appraisal (see PAD, page 41) but agreements were not sustainedduringimplementationleading to a lack of ownership and accountabilityon the part of theauthorities (seeICR, page 59). As a resultimportant objectives such as the contracting of construction work for addressing the leachateproblems at theMostar landfill were not achieved. In such situations, a strong ME role by the Bank is allthe more important.IEG considers that the following related lessonis relevant.-Constructive collaboration based on mutual benefits and shared costscan be a basisfor achieving communal environmentalgoals. The improved landfill site at Sitnica was successful in reducing nutrient leaching levels and has thepotential for enhancing the re-cycling of many waste materials on a financially sustainable basis. The lessonis thatthe choice ofthe site wasstrategically appropriateand had theconstructive collaboration betweentwolocal municipal governmentswilling to share resources at one landfill site. Thislesson of optimizing economies ofscaleamong small municipalities can be the basis fora broader roll out of landfill and recyclingmanagementsystems and technologieselsewhere in the Adriatic Sea area and other regions.
P143940 | Flood Emergency Project | Western and Central Africa | Cameroon | Blend | FCS | Sustainable Development | Water | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/371911624993978741/text/Cameroon-Flood-Emergency-Project.txt | http://documents.worldbank.org/curated/en/371911624993978741/pdf/Cameroon-Flood-Emergency-Project.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. Projectsimplemented under challenging security conditions need to develop an alternative methodology for monitoring and datacollection.Given the problems of visiting the project area due to security issues, an alternative methodology wasdeveloped to monitor the project by carrying out activities such as: review of the press and social media in the area where theproject was reported; telephone contact with the communication media in the area to request information on the status of theproject; telephone contact with project beneficiaries, local authorities and others who can give testimony of the project statusand send photographs. In addition to these informalmechanisms, the ability to monitor the implementation of projects incontexts of restricted access orrisk conditions can benefit today from instruments such as Geo-Enabling for Monitoring andSupervision (GEMS)or remote sensing techniques with the satellite image utilization.2. To ensuresuccessful implementation of projects, the financial, technical, and institutional capacity of fragile and conflict-affectedcountries needs to be carefully assessed in an integrated manner, even if there is a base of technical capacity. Countriesin an FCV situation prioritize their resources based on emergencies or needs due to their situation, and the activities of aproject, no matter how important, can run the risk of taking a back seat, thereby jeopardizing their timely execution and delayingthe access of beneficiaries to project results. Thus, it is best to plan to pay for all critical project activities with loanfunds, including the RAP (and ESMP) costs, to avoid delays often generated by the late availability of counterpartfunds.3. To ensure thatcommunities take ownership of the differentrehabilitatedinfrastructures,project implementation needs touse inclusive participatory mechanisms.Cameroon isculturally and geographically a very diverse country. In the far north region, traditional and religious leaders play a key role inthe society and are as much respected as the governor or other key administrative leaders. Itis important to developstrategies to involve and include the local stakeholders in various ways, to take advantage of their knowledge and capacities. Theproject took this aspect into consideration andincluded those stakeholders to help the communities take ownership of thedifferent infrastructures that have been rehabilitated.
P143988 | Electric Power Project | East Asia and Pacific | Myanmar | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/156221617298683586/text/Myanmar-Myanmar-Electric-Power-Project.txt | http://documents.worldbank.org/curated/en/156221617298683586/pdf/Myanmar-Myanmar-Electric-Power-Project.pdf | IEG derives the following lessons drawn from the ICR:1. It is critical to build capacity of keysector stakeholders, to avoid delays taking place in procurement decisions, especially for countries affected by fragility,conflict and violence (FCV). To bridge the gap, introduction of skilled international technical experts to supportstaff of the implementing entity should be considered at an early stage of implementation. Since FCV countries can beexpected to have limited experience with large procurement packages and limited familiarity with the World Banks procurementframework, they can benefit from the Banks recently-introduced procurement hands-on extended implementation support (HEIS)for fragile countries, which could help reduce delays and would ensure the integrity of the procurementprocess.2. Effective risk mitigation and troubleshooting mechanisms need to be put in place and preferablybuilt into contract provisions, including for post-completion operation of assets. For complex projects and forclients with low capacity, World Bank teams can help by setting up mechanisms to identify and resolve contract implementationissues early on in the process. To further reduce risks, the inclusion of an OM contract in the projects costscan pay dividends by guaranteeing proper performance and efficiency of operation over the lifetime of the plant andequipment.3. Projects are more likely to succeed if greater focus is placed on critical policy reforms.The project was designed to respond to the Governments priority to increase access to electricity, and its TAactivities were intended to build a solid foundation for the policy reform needed to achieve the objective. With the focus onthe development of an NEP and improvements to the financial viability of sector, the project demonstrated high buy-in from theGovernment that had implications for all other project activities as well. The fact that Governments reform prioritieswere at the core of the operation sent a strong signal to stakeholders and ensured Governments support in solvingimplementation bottlenecks throughout the project.
P143993 | FIP - DECENTRALIZED FOREST AND WOODLAND MANAGEMENT PROJECT | Western and Central Africa | Burkina Faso | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099325006292220157/text/P1439930090a210850bfb50cbf9264b9b60.txt | http://documents.worldbank.org/curated/en/099325006292220157/pdf/P1439930090a210850bfb50cbf9264b9b60.pdf | The ICR provided four lessons. Some of them are summarized below because they may provide lessons of interests for otheroperations on Forest Investment Program (FIP).Citizen engagement at the most local level can lead to successfulimplementation of community-led Reducing Emissions from Deforestation and Forest Degradation (REDD+) projects. Forexample, local actors including different users of land and customary and administrative authorities at commune and village levelsengaged in a participatory land and social diagnostic (i.e., TerriStories) as a basis for identifying practical solutions to giveaccess rights to different user groups (ICR, para 37). Through active citizen engagements, the project mitigated the potential riskof underlying social tensions to induce conflict over land security and access to natural resources (ICR, para101).Burkina Fasos decentralization process was strengthened by the projects approach to useIntegrated Community Development Plan (PDIC) for REDD+. For example, the project reinforced the trust and dialogue betweenits targeted local municipalities and communities by integrating the results of the diagnostic activities into territorial planningtools (ICR, para 58). After project closing, the municipal institutions were expected to mobilize funds from the State budget tosupport natural resource management at the communal level (ICR, para 58), contributing to scale up the same approach for a broaderjurisdictional emission reduction investment program under a follow-on project (ICR, para 102).
P143995 | Bolivia: Improving Employability and Labor Income of Youth Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099850011292218973/text/P1439950c4934f08508c5707f2a5b15b8f6.txt | http://documents.worldbank.org/curated/en/099850011292218973/pdf/P1439950c4934f08508c5707f2a5b15b8f6.pdf | The following lessons are drawn from the ICR.In a complex context, opt for a straightforward projectdesign. While this project was well-grounded in country strategy, it nevertheless was challenged by a difficultinstitutional (and political) context: Two institutions, unfamiliar with the World Bank, were initially assigned to managing theproject, generating significant delays and uncertainties about implementation, and requiring a rationalization of projectdesign. A successful project needs the involvement of all key participating parties, including publicand private sector representatives. A constructive dialogue was developed between the Bank and the government,allowing agreement on two significant restructurings. However, insufficient attention was paid to involving private firms,which were a necessary ingredient in ensuring successful implementation. This would become a contributing factor to lowerproject targets.Applying available targeting tools can ensure adequate beneficiary targeting.The project used existing targeting tools, applied under the previous project effectively reaching the relevant population vulnerable youth from low-income families with low education levels.
P143996 | EC Manta Public Services Improvement Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099310003142219058/text/Ecuador000EC0M0rvices0Improvem0Proj.txt | http://documents.worldbank.org/curated/en/099310003142219058/pdf/Ecuador000EC0M0rvices0Improvem0Proj.pdf | The ICR (paras. 100 to 104) lists a number of lessons from which IEG derives the following lessons of broadrelevance andapplicability for similarprojects implemented in comparable environments.Establishment of a well-staffed andwell-equipped Project Implementation Unit prior to the start of implementation is crucial for ensuring efficientimplementation. The absence of a well-staffed and well-managed PIU was a critical factor resulting in significant delays,particularly in the years of implementation. In the case of the project, the PIU did not have prior experience in working withmulti-lateral development banks and wasunfamiliar with the World Banks safeguardsand fiduciary requirements.Appropriate technical assistance, including through specialized consultants, should be provided in the project preparation/earlyimplementation phases, to ensure that the requisite capacity is place to ensure timely implementation.Guidingprojects through political change and other external obstacles requires time, flexibility, and resilience. Changes inpolitical administration are oftentimes accompanied by shifts in leadership in key agencies which can result in shiftingpriorities. During the projects implementation, the city had three different mayors and four different PIU leaders. Theproject overcame these challenges through responsive restructurings while maintaining the focus on the originalobjectives.Cross-sectoral operations can offer an opportunity to amplify the development results. Theproject demonstrated the synergies and benefits of implementing cross-sectoral operations including optimization of constructionprocesses, and reduction in costs of materials, contracting, and labor than would havebeen possible if the WSS and transportcomponents had been under implemented under separate projects.Resistance to departing from nationalnorms can be overcome, where justified, through targeted training and agreements with the national government entitiesinvolved. In the case of the project, differences between the national norms and the Banks requirements in regard toland acquisition and procurementwere resolved by extensive discussions between the Bank supervision team and the relevantcounterparts. Provision of relevant training to the counterparts, early on in the implementation process, could help in avoidingsubsequent delays.
P144029 | The Power Recovery Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099145006132235690/text/P144029006c4850440b2d90d00503331e3e.txt | http://documents.worldbank.org/curated/en/099145006132235690/pdf/P144029006c4850440b2d90d00503331e3e.pdf | The ICR contains substantive lessons learned from the operation. The following suggestions are made to add to or elaborate onsome of the lessons that have already been identified:Investment Project financing may not be an appropriateinstrument for supporting complex projects comprising both infrastructure investments and substantive policy reforms. ThePower Recovery Project contained important policy reforms for development of a power market alongside investment in transmissionand distribution which made the operation complex. In the end the reform activities were taken over by other financiers. The WorldBank could have selected separate instruments for supporting the infrastructure investments and policy reforms or prioritizedbetween the two areas of engagement.Bringing about sustainable policy changes or supporting sector financialrecovery requires intensive engagement over time. The World Bank could have selected a programmatic approach, a DPL seriesfor policy reforms or a Program for Results either of which would have allowed phasing of activities to avoid the overload thatappear to have occurred with the Power Recovery Project.The capacity issues that arose with the PIUs could havebeen better managed by strengthening the capacity of the PMU not just for financial management, disbursements, and ME but alsoon procurement. The utilities PIUs could be made responsible for technical specifications while the PMU handles therest of the procurement functions with a capacity building plan for gradual devolution of functions to theutilities.Designing and implementing power sector financial recovery requires buy-in at high levels in Governmentbecause of the political economy issues related to electricity tariffs, governance, transparency, and accountability ofinstitutions. High level participation is key both at the design stage and during implementation is critical. At atechnical level it is important to formulate plans comprising both operational and financial restructuring measures and metrics.In the context of the World Bank operations, getting formal commitment to the whole package for example through DPL prioractions raises the profile of the required actions.
P144102 | Uganda Reproductive Health Voucher Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/594211621561305279/text/Uganda-UG-Reproductive-Health-Voucher-Project.txt | http://documents.worldbank.org/curated/en/594211621561305279/pdf/Uganda-UG-Reproductive-Health-Voucher-Project.pdf | Some of these lessons are drawn from the ICR, while others are drawn from IEGs review of the ICR.Lessonfrom IEGs review of ICR:Shortcomings in the selection of outcome indicators -- combined with lack offollow-up to address those shortcomings by improving the ME framework during implementation -- hinder the ability to showachievement of a projects development objective. This projects development objective specified a particulartarget group. However, the ICR (and the ME results framework it relied upon) did not sufficiently document the extent towhich the intended target group poor women living in project areas was effectively reached. An MEsystem, which would have tracked and assessed the breakdown of actual beneficiaries by poor/non-poor, region, and targetingmethodology, would have provided a fuller assessment of PDO achievement.The projects stated intention (PAD p. 8)to undertake systematic monitoring and assessment of the projects targeting methods, in terms of its accuracy andcost-effectiveness in reaching the poor, was not reported on in the ICR. Future projects of this nature may benefit from thereview and triangulation of project data with other available and relevant data sources to assess the poor/non-poor breakdown ofbeneficiaries (e.g., data from the Office of Auditor Generals Audit of the project, and Ugandas Bureau of Statisticssub-district poverty maps, 2018, among others).Lessons from ICR:Enhanced ownership,coordination and stewardship of the MoH are critical to sustain and build on the innovations and achievementsmade under anyproject, especially those piloting innovations. A similar project would benefit from a Steering Committee led by a senior MoHofficial, along with a MoH focal point whowould work directly with and monitor the voucher program and foster more regulardiscussions and field visits at the ministry level.Efforts to increase demand need to bematched with efforts toincrease service delivery capacity to meet that demand. Supply-side challenges in Uganda constrained the delivery system torespond effectively to the demand generated. Among these constraints were: some essential medical equipment and supplies; andstaffing constraints at the referral level.Referral system strengthening is key and requires longer-term investments inthe health sector and other sectors, particularly the transport sector and investments in rural road infrastructure.
P144103 | MD Second Competitiveness Enhancement Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099042123184518941/text/P1441030d63ce40150a0710b303de239e48.txt | http://documents.worldbank.org/curated/en/099042123184518941/pdf/P1441030d63ce40150a0710b303de239e48.pdf | The first three lessons are drawn from the ICR, with adaptation. The fourth is added by this ICRReview.Long-termpolicy dialogue with a government can help solidify the political and public commitment to astructural or policy reform. This project benefitted from extended policy dialogue conducted by the World Bank andother development partners with the Government of Moldova in over two decades of program, project, technical assistance, andadvisory service workfocused on private sector development. The policy dialogue helped achieve a broad consensus among thegovernment, private enterprise, and other stakeholders on the importance of enhancing the countrys competitiveness includingthrough regulatory reforms, SME development, and access to medium- and long-term finance for enterprises. The policy dialoguewas conducted with successive administrations, with competitiveness recognized by the political leadershipas vital to thecountrys drive for membership in, and economic integration with, the European Union.A flexible lending formatcan raise the chances of success of a financial intermediaryoperation. In this project, the line of credit wasallowed to provide sub-loans to enterprises in wide ranges of economic sectors and geographic locations. The line of creditcould provide loans for fixed investment and for working capital. The line of credit could also lend in Moldovan leu, inEuros, or in U.S. dollars. The First Competitiveness Enhancement Project had drawn thissame lesson. This project,which adopted a flexible and inclusive lending format as recommended, faced a robustdemand for medium- and long-term creditand fully disbursed the loan funds for the line of credit a year ahead of the project closing date.Impactevaluations usingrandomized control trials can help illuminate the economic impact of project interventions.In this project, three impact evaluations used the randomized control design to assess the impact of matchinggrantson new export sales and new job creation by beneficiary enterprises. Grant recipients were randomly assigned to acontrol group (for which the grants were approved later than for the treatment groups) and to two treatment groups (one providedfor regular monitoring, and the other, closer monitoring)that allowed for the quantification of the effectof the grantsand monitoring mechanisms on export sales and jobs. Byensuring that the groups were highly comparable (the onlyexpected difference between the control and experimental groups were theoutcome variables under study), the impactevaluations were able to separate the impact of the matching grantsfrom the impactof other observed and unobservedfactors on new exports and new jobs. The impact evaluations were conducted by independent experts, using amethodologyagreed with the Bank and made part of the Matching Grants Manual, with the Bank conducting field visits to firmsin the sample.Explicit definitions of concepts underlying project development objectives canhelp enhance therelevance of project results frameworks. In this project, the lack of a precise definition of export competitivenesshampered the design of the ME framework and the choice of relevant results indicators. While the three key outcomeindicators selected for the objective to increase the export competitiveness reflected the extent to which constraints to firmexport performance eased following the fulfillment of the prior actions, the indicators did not directly measure the achievement ofexport competitiveness itself, for lack of a concrete definition of the underlying concept.
P144134 | Strengthening micro-entrepreneurship for disadvantaged youth | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | RETF | IPF | 2013 | 2020 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/237431593553361316/text/Morocco-DTF-MA-Youth-Micro-Entrepreneurship.txt | http://documents.worldbank.org/curated/en/237431593553361316/pdf/Morocco-DTF-MA-Youth-Micro-Entrepreneurship.pdf | The following lessons were extracted from the ICR: Financial support is important toenable youth to establish their micro-enterprise. For example, youth cited lack of financial funds as the primaryreason that they did not launch a small business. Even though the project established partnerships with lending sources, the vastmajority of youth used personal funds to start their business (ICR, para 56). Barriers to access also included cost oftransportation, in particular for female youth (ICR, para. 38). The ICR reflected that future projects need to take into accountthe barriers that exist for youth to gain access to start-up capital. Results-based payment mayhelp a project maintain expected deadlines, but excessive pressure to achieve results may result in quality being compromised.For example, implementing partners rushed the recruitment process and did not vet participants to ensure that they had thecompetences necessary to become entrepreneurs (ICR, para. 56). This may have been because payments were made against the deliveryof agreed results. This system put pressure on NGOs to deliver according to agreed schedules and deliverables (ICR, para. 30). Monitoring systems need to be systematically designed to capture quality of program implementation, inaddition to project outcomes. For example, the monitoring system failed to capture important implementationweaknesses in the project activities, in particular the fact that (i) courses were taught in French as opposed to Arabic and (ii)courses were too academic. Similarly, the project could have benefited from a verification process to ensure that theimplementing partners were applying consistent selection criteria when enrolling the beneficiaries (ICR, para. 32). A basicmonitoring system can pick up these weaknesses and adjust in real-time to ensure quality program implementation.
P144139 | Statistical Capacity Building Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/799391623070186227/text/South-Sudan-Statistical-Capacity-Building-Project.txt | http://documents.worldbank.org/curated/en/799391623070186227/pdf/South-Sudan-Statistical-Capacity-Building-Project.pdf | The ICR (pp. 28-31) provides numerous detailed lessons emerging from each stage of the projects life cycle. Theyinclude:Successful implementation of development projects in fragile contexts depends not only on addressing developmentgaps, but alsoon consideration ofspecific fragility and conflict dynamics. In this case, delays in projectrestructuring revealed lack of flexibility in adjusting to evolving realities, capacity/resource constraints, and risks on theground.In fragile settings, the need may arise to incentivize project staff to overcome salary and staffing limitations.In this case, there was high turnover because NBS staff were not paid enough by the government to complete implementation ofproject-financed activities, a situation that grew worse as the macro-fiscal state of the country deteriorated. When outcomes areat risk due to deterioration of the security and/or fiscal context in a project that is otherwise performing well, the Bank couldconsider working with the client to find ways for key government staff to continue to receive adequate salaries.Carefulsequencing of activities is an important element of project design. In this case, prioritizing human capacity development duringthe projects initial phases fostered the development of ownership among statistical staff at the NBS and MDAs statisticalunits; despite later challenges, this early strengthening enabled continuation of statistical productioneven in the faceofongoing conflict.
P144183 | Mauritania Sustainable Landscape Management Project under the SAWAP | Western and Central Africa | Mauritania | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099620001052246088/text/Mauritania000S0e0Management0Project.txt | http://documents.worldbank.org/curated/en/099620001052246088/pdf/Mauritania000S0e0Management0Project.pdf | The ICR provided six lessons. Some of them are summarized below because they may beof interestfor other SLMprojects.The implementation period of aproject needs to be aligned with the time it expected to take toachieve the projects objective. Although gum Arabic trees needed at least five years before starting gumproduction, the SLM investment activities including plantations ofgum Arabic tress were implemented for only three yearsunder the project. It was not feasible to observe the results of the newly introduced SLM investment activities in the gum Arabicbelt.Established water supply systems are important in reforestation including for acacia trees in aridregions. Under the project, abundant watering was needed because the survival of the acacia seedlingsdepends heavilyon regular watering. To provide water to the tree nurseries and seedlings in the ground for the first year after plantation, theproject used various types of water tanks drawing water from wells constructed primarilyfor market gardens.This ICRReview adds the following lesson.In remote arid regions such as rural Mauritania, where men earn incomes fromoff-farmactivities leaving women to take care of agricultural/pastoral activities (PAD, para 18), a more gender-focusedapproach to supportwomen as participants in pastoral development is needed. In this projectcapacitybuilding operations were less likely to reach women if specific actions to benefit women were not designed. While theprojectexperience implied that the income-generating activities had positive effects for women, the effects were not measuredby gender-disaggregated indicators. A gender action plan is therefore essentialto finance andsupporttheinvolvement of women in all aspects of projects aimed at pastoral development in remote areas such as theSahel.
P144185 | MA-Second Skills and Employment DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2015 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | Lessons learned are derived from the ICR:While preparing Prior Actions and developingtargets, the institutional capacity of relevant ministries to implement reforms needs to be well assessed to the extentpossible. In particular, a number of PDO indicators formulated during project design were too optimistic whereby they did nottake into account unanticipated macroeconomic changes. This was particularly relevant for setting target results for programs thatinvolve the participation and take-up of the private sector.Collaboration with other developmentagencies can be a positive enabler for the success of labor market reforms. For SEDPL2, for instance, the financial andtechnical assistance of the French Development Agency (Agence Franaise de Dveloppement) and the German DevelopmentAgency/German Society for International Cooperation (Deutsche Gesellschaft fr Internationale Zusammenarbeit) helped toaccelerate the implementation of some reforms that would otherwise have taken longer toimplement.A more active involvement of the private sector (federations,training providers, and NGOs) is a promising model to increase the quality and relevance of programs as well as to reach vulnerablesegments of the population, especially at the local level.
P144269 | PROMOTING SUSTAINABLE CBNRM AND INSTITUTIONAL DEVELOPMENT | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099121823204519148/text/P14426908d2e6b00e0a1170d50660913724.txt | http://documents.worldbank.org/curated/en/099121823204519148/pdf/P14426908d2e6b00e0a1170d50660913724.pdf | The ICR draws lessons and provides several recommendations (p. 30-31) related to project design, procurement, financing, localchampions, project implementation, monitoring, and environmental safeguards.Based on this review, IEG draws the followingoverarching lessons:If institutional arrangements are too complex, there is a risk that project performance isadversely affected. The project did not fully account for ambiguous relationships between central and localgovernments, the limited capability of project staff, and readiness for implementation. The inability to effectively coordinateacross implementing agencies and establish essential support systems (notably supporting units for the FMUs) during the initialproject phase, negatively impacted activity implementation of the FMUs, particularly activities under the community empowermentcomponent. Contributing to the project challenges and initial low disbursement were a lack of clarity around roles andresponsibilities.If local champions are empowered to engage with communities and facilitate activities to improveforest-based livelihoods, this may create buy-in and commitment for sustainably managing forest resources. Local championsproved pivotal to the success of the small grants program benefitting forest farmer groups. The skills, adaptability, and approachof interpreting community needs and addressing emerging challenges were critical for achieving project objectives. Emerging womenlocal champions that were supported by the project encouraged other women to actively participate in the establishment ofcommunity-based forestry businesses, and to take a key role in the forest management activities.If long-termgovernment commitment and high-level support are in place, this may increase the potential for positive change towards sustainablymanaging forest resources. The Indonesian government faced significant challenges in addressing the underlying causes ofdeforestation and forest degradation andbetter managing its forest resources. While the project set out ambitious goals atappraisaland contributed to enhancing the enabling policy environment and empowering local communities in some FMUs, earlyprogress towards the PDO was slow given leadership challenges of the projects initial Executive Agency. A high-leveldecision to adjust implementing arrangements helped the project improve in its later years. In light of this, high-level governmentcommitmentas well as additional technical support and long-term financing are critical to address underlying challenges ofpoor forest governance and management and move towards sustainably managing forest resources in Indonesia.If arobust theory of change with appropriate outcome indicators is not in place, there is a risk that progress towards projectobjectives cannot be adequately measured. In this case, there were limited outcome indicators for monitoring performancewith respect to the objective to strengthen institutional and local capacity for decentralized forest management and generateimproved forest-based livelihoods (see discussion on Efficacy). Given the short time frame of the project interventions and theprojects primary focus on technical assistance and capacity building for institutional change, the links to outcomes weresomewhat tenuous.
P144270 | China Economic Transformation and Institutional Capacity Building | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024231025116/text/P1442701cbd45b0481aee81655b1b4d47c6.txt | http://documents.worldbank.org/curated/en/099053024231025116/pdf/P1442701cbd45b0481aee81655b1b4d47c6.pdf | The following lessons have emerged from the review of the ICR:Project objectives and ambition should bepreciseand focused, informed by key diagnostics such as Capacity Needs Assessments. This approach would enable projects of thisnature to more adequatelyidentify outcome-oriented indicators and narrow the number of indicators to a manageable level.According to the ICR, the PDOs were intentionally general to afford flexibility to accommodate a wide range of prioritysub-projects (p.12). However, outcomes that are too broad are usually difficult to measure, as evidenced by this operation.Therefore, given that indicators should adequately capture the expected outcomes defined in the PDO statement, the project qualitycould be significantly improved if Bank teams clearly define and limit the problems that an operation is trying to solve to a smallnumber of areas or sectors. A smaller and more focused scope improves the ability to identify measurable outputs and outcomes thatare required to bridge the gap between challenges prior to the project intervention and the desired results after theproject.Implementation support from the task team should not substitute the technical assistance activities that arerequired to achieve the project development outcomes. The Bank supervision budget was objectively very limited. However, while amulti-sectoral project requires a multi-sectoral task team to support the borrower, the primary objective of a task team is toproactively identify and resolve threats to the achievement of relevant development outcomes. Therefore, the IPF should haveadequately budgeted for international and local consultants, based on identified needs, to provide technical assistance to thegovernment and the beneficiaries to achieve project development outcomes. Nevertheless, given the governments need fordedicated technical support from the Bank, this operation could have benefited from a Bank executed grant to enable the taskteam to provide additional technical support to local governments.
P144305 | EGYPT Energy/Social Safety Nets Sector Reforms Technical Assistance | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/852001568744391347/text/Egypt-Arab-Republic-of-DTF-EG-Energy-Social-Sectors-Reform-TF.txt | http://documents.worldbank.org/curated/en/852001568744391347/pdf/Egypt-Arab-Republic-of-DTF-EG-Energy-Social-Sectors-Reform-TF.pdf | The following lessons were derived from the projects implementation experience (with some paraphrasing byIEG):Ways need to be identifiedpartly through the Banks convening powerto simplify thecoordination of complex projects. The projects complex set of activities and its institutional management weredaunting but might have been simplified. Five ministries, several state-owned companies, six consulting firms, and 41 separateconsultancies were involved. Coordinating and ensuring the cooperation of each of these entities was a major task. The WorldBanks convening power was helpful. Complexity was hard to avoid since the various ministries and state-owned companiesneeded to be kept aware of what was going on and what they needed to do. However, it might have been possible to hire an Egyptianconsulting firm to handle the 41 individual consultancies. The Project Management Team (PMT) could have selected them and thenturned them over to the apex consulting firm to arrange the terms of service and manage the separate consulting contracts. Thisapproach might have been easier compared to the PMT having handled all the consultants itself.Flexibility toaccommodate a dynamic environment is essential. Although the PAD identified some of the implementing agencies at theoutset, all the responsible agencies changed several times. The World Bank worked flexibly and engaged proactively with therequired agencies in a dynamic environment without requiring project restructuring to take place. This prevented further delays andbuilt effective partnerships with the relevant ministries, which enabled the achievement of better results that initiallyexpected.The coordination required by a project could help break silos both in the Government and in the WorldBank, while facilitating reforms. To reform energy sector subsidies and to free up funds that could be used for moretargeted social protection cash transfers, teams from the World Banks energy and social protection sectors collaborated onthe project, as did energy and social protection agencies in the Government and the Administrative Control Authority. Breaking ofsilos and cross-collaboration enabled the success of the project. Partnerships with a similar approach are being replicated inother World Bank-financed projects in Tunisia, Jordan, and Algeria.
P144336 | NATIONAL WATER RESOURCES MANAGEMENT PROJECT | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2014 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Integrated Water Resource Management (IWRM) reforms are inherently complex, and development partners need to able tosupport clients with best-fit solutions rather than best practice allowing the human and social systems involved in IWRM reforms togradually adapt to new realities. Because reforms and changes to social systems are conservative, development partnersneed to adopt realistic expectations about what can be achieved within specific timeframes. The Banks sustained engagementin the sector over the last 20 years, use of a mix of lending and grant-financed technical assistance, and a willingness to shiftfrom best practice to fit-for-purpose interventions enabled the government to make changes at a rate acceptable to stakeholders.Whereas the predecessor project (WMIP) failed to achieve certain institutional reforms that mirrored best practice in IWRM such ashaving an independent state water authority, this project took a more incremental approach and focused on functionrather than form, and worked to embed the functions of a state water authority into existing institutionalarrangements.Projects implemented on a national scale with activities scattered across the country canbenefit from a specialized ME firm to support ME systems. While the projects ME system was effectivein measuring results and overall success, a dedicated ME firm could be engaged for future projects to extend the clientscapacity and bring in good practices to manage the complexity of dispersed project activities and ensure effective and efficientprogress monitoring. (ICR, p 23)Effective donor coordination between the World Bank and bilateral organizationscan leverage financial and technical resources benefiting government clients. This project demonstrated that solidcoordination, knowledge sharing, and trust between the World Bank task team and bilateral donors such as SCD can maximize bothfinancial and technical resources. The World Bank had deep experience in the country and was able to draw on its global experiencein the sector, bringing that knowledge to the client with financial and technical support from SCD. The partnership and trust thatwas developed enabled the project task teams to adequately support the client when project implementation slowed and facilitatedthe additional grant financing. (ICRR interview)To improve the sustainability of training activities, projectscould consider strategic partnerships with local universities and vocational colleges to integrate project training materials intotheir curricula. This ensures that the knowledge is passed on to future generations and remains relevant and accessible.Projects could also work with local government bodies or sectoral agencies to institutionalize the training programs within theirregular operations as well as encourage organizations involved in the training to develop succession plans that include knowledgetransfer to new members or employees. (ICR, p 24)
P144377 | Samoa Development Policy Operation | East Asia and Pacific | Samoa | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/766641496936291010/text/ICRR-Disclosable-P144377-06-08-2017-1496936285272.txt | http://documents.worldbank.org/curated/en/766641496936291010/pdf/ICRR-Disclosable-P144377-06-08-2017-1496936285272.pdf | The ICR (pp. 26-28) offers several useful lessons, including:There are important distinctions betweensupport for measures to introduce changes to regulations and law as opposed to the introduction of the regulations orlaws themselves. In this case, particularly for a stand-alone development policy operation, it was not sufficient to settlefor measures to introduce changes on establishment of regulated vehicle weight limits. The Land TransportAuthoritys decision to combine this activity with other longer-term processes, in addition to high staff turnover, meant thatthose weight limits still have not been implemented.Coordinated financial and technical support fromdevelopment partners is a key element of the response to natural disasters in Pacific Island countries. In this case,collaboration among partners contributed to quick recovery from Cyclone Evan and investments in sustainable risk mitigation whilereducing the potential for overlaps and inefficiencies.There is a potential mismatch between therequirements of the DPO instrument and the need to deliver funding rapidly after a natural disaster. While a DPO is anappropriate instrument for quick-disbursing financing in the wake of a disaster, combining a two-pronged approach of short- andlong-term measures can detract from its intent to respond rapidly to urgent needs. In this case, the DPO was unable torespond rapidly due to the two-pronged approach.It would have been more appropriate to address the more urgent needsgiven limited country capacity, and a focus of the policy actions on more urgent recovery needs might have led to more efficientallocation of government attention and resources.
P144442 | Mali Reconstruction and Economic Recovery | Western and Central Africa | Mali | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099090624032518175/text/P144442-9238b018-2490-4f90-b1e6-f992f61c90ca.txt | https://documents.worldbank.org/curated/en/099090624032518175/pdf/P144442-9238b018-2490-4f90-b1e6-f992f61c90ca.pdf | The ICR offered four lessons from the operations (ICR, paragraphs 51-54) slightly modified below: Inmulti-sector local development projects, anintegrated intervention may generate larger impacts.This projectused an area development approachto generate a broad impact for beneficiaries. Communities prepared local development plansto identifypriority infrastructure investments and productive activities to be restored. Thismix of investments inpublic (infrastructure) and private goods (income-generating activities) in a post-conflict contextfacilitated an integratedresponse to the different development needs of the beneficiaries. Engaging local governments in subprojectimplementationcontributedto buildingcapacity and restoringlocal institutions. Increasing insecurity infragile countries may benefit from using third-party agentsto monitor implementation. In this project, flexibilitymeantquickly adapting to challenging circumstances. This adaptiveproject management style facilitated just-in-timedecisions to seize opportunities. Thiswas the case in adding Konna and Taoudeni target areas. Contracting MOD agencies asthird parties to implement selected activitiescontributed to the flexible design.The MODs were experienced withinfrastructure works in fragile areas. However, usingMODsalso led to operational constraints as procuring theirservices was delayed, and they were notpresentin some of the targeted areas. A candid assessment of the operationalcapacity of third parties and addingneeded staffmay mitigate these challenges. Hiring local NGOs andconstruction firms as third-party monitoring agents may address rising insecurity.In thisproject,NGOs and local enterprises were hired as third-party monitoring agents even as risks and longercompletion times were noted. Closer supervision, active monitoring of the security situation, sound community engagement, andenhanced ME mechanisms were added. Well-established local NGOs and firmsfacilitated the implementation of sub-projects.The NGOs hadknowledge of the local context. They systematically mapped vulnerable groups as part of the participatoryprioritization exercise. This effortincreased inclusivetargeting. In addition, procurementwas adaptedtolocal conditions. Contract sizes were adjusted.Firms were encouraged to join larger, nationalfirms. Prioritizing investments from local development plansraisespublic awareness of processes andacceptance of projects in target areas. The PIU used PDESC as an entry point into project areas in this project. Each ofthe 149 municipalities prepared or revised these plans over4 to 6 months. Inclusive consultationsinvolved electedofficials, state technical services, local development committees, andcivil society, including vulnerable groups (InternallyDisplaced Persons (IDPs), migrants, and pastoralists). They considered the priority needs of all groups in the target communities,particularlythose of women and youth. This consultative processinformed the public about the project especiallythrough organized public debates and legitimizedthe project to beneficiaries.
P144447 | India: Elementary Education III | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/278521546609915766/text/India-IN-SSA-III.txt | http://documents.worldbank.org/curated/en/278521546609915766/pdf/India-IN-SSA-III.pdf | Lessons drawn from the ICR and adapted by IEG: The Sector-Wide Approach (SWAp) canbe an effective instrument for early sector reform efforts, given theconvergence with national government programs and thebroad-based reach of the reforms; however, a more results-based approach can come into play once the early reforms have beenachieved and more targeted, specific initiatives are needed. In the case of this project, the SWAphelped to bring aboutincreased access through widespread teacher training and early childhood initiatives. However, improving quality required amore state-by-state approach in order to address specific challenges in each state, which the project began to support throughstate-level performance assessments and the use of state annual work program processes. Thedevelopment ofgrade-level, subject-specific learning standards, which are thendirectly linkedtostudent assessments and remedialactions by teachers, can have an immediate impact on education outcomes. In the case of this project, results fromgrade-level assessments alongside teacher training (including in evaluation of student performance) contributed to improvedretention and transition rates.
P144454 | Global Partnership for Education - Balochistan Education Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099400011022231236/text/P14445403aa5ac0370859302f767cc4560a.txt | http://documents.worldbank.org/curated/en/099400011022231236/pdf/P14445403aa5ac0370859302f767cc4560a.pdf | Lessons drawn from the ICR: Real-time monitoring systems, based on simple and accessible technologies, can beinstrumental in difficult, geographically dispersed environments thatcannot be accessed due to security reasons.In thecase of this project,using a real-time school monitoring mechanism (an Android application from the field to a customizedmanagement information system dashboard, inputted by local school management committee members) to monitor implementation progressremotely helped identify and address implementation bottlenecks in inaccessible areas. Rehabilitation/upgrading ofexisting schools can be a more effective approach than constructing new schoolsin areas where access is low, the state ofexisting infrastructure is poor, and student-teacher ratios are high. In the case of this project, the shift in focus at the timeof project restructuringto rehabilitating existing schools led to achievement of project objectives (and meeting enrollmenttargets) when the cost of new construction increased significantly.Additionally,decisions on new constructionespecially in previously underserved areas can bring new issues (e.g., distance, transportation, safety) that may impact theachievement of objectives.In addition, Precision in the selection of key project indicators cancapture project achievements more clearly and convincingly.In the case of this project, there was overlap in reporting onproject beneficiaries (those who benefitted from any project intervention) and newly enrolled/retained students, andalso in reporting on girls vs. boys (increased retention).More clearly disaggregated data would have given more clarity tothe level of achievement ofobjectives.
P144489 | Quito Metro Line One | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099120524174559204/text/P144489-0e08c087-7e1e-4208-9d42-518d79eb7ada.txt | https://documents.worldbank.org/curated/en/099120524174559204/pdf/P144489-0e08c087-7e1e-4208-9d42-518d79eb7ada.pdf | If a project has multiple co-financiers, the availability of a well-defined framework with their clear responsibilitiesand commitments from the start may contribute to effective coordination between co-financiers and reduce the risk of implementationdelays due to possible disagreements on key issues. This Quito Metro project had several financiers who, together with theQuito Municipality and GoE, co-signed the Principles of Coordination (PoC) at the launch of this project, while each of thesefinanciers signed separate financing agreements with the Municipality. The PoC laid out a clear framework for the fiduciary andsafeguards implementation arrangements, as well as integrity and conflict resolution mechanisms. It was the first project where theWB agreed to use another MDBs procurement guidelines (IDBs in this case), while the other MDB agreed to waive itsprocurement provision that only firms from member countries could participate in the bidding process and accepting the WBsapproach to an open international bidding. Close and effective coordination between the financiers was critical in theimplementation of this mega project.If a TA to identify a business operator model and select a metro operator isnot defined upfront to help the Borrower which has never implemented a similar metro project, the project risks delaying the launchof the metro services and achievement of the expected outcomes. Because such a TA was included only during the firstrestructuring in 2018 and implemented later during 2020-2022, the metro services could not be launched due to the absence of ametro operator. Hence, the project required three more extensions of the closing date after the first restructuring, until themetro started its operation and the expected benefits could be realized.Well-prepared safeguards assessmentsmay minimize implementation delay risks. Because not only feasibility studies and detailed designs, but also safeguardsassessments underwent independent reviews, that allowed carefully selecting the alignment that minimized social impacts and avoidedphysical resettlements. As no large-scale resettlements were needed, the construction works started on time and, in general, wentthrough any If the projects expected outcome is dependent on complimentary investment activities tobe financed/implemented outside the project scope, there is a high risk of that outcome may not be achieved due to lack of theprojects direct control of those activities. Restructuring of metro feeder routes and the integration of entire busfleet operating under the unified fare collection system are important to increase metro ridership. However, these activities weresupposed to be executed by the Municipality outside this projects scope and eventually did not happen, which negativelyaffected the achievement of several dependent outputs and increase in the daily ridership outcome. The end targets of relevantoutcome and interim indicators shall be set realistic and not dependent on the delivery of activities outside the projectsscope.
P144497 | Tanzania: Expanding Rice Production | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099245005192234752/text/P1444970bb2c4f09d0911b0eab00e2a75c0.txt | http://documents.worldbank.org/curated/en/099245005192234752/pdf/P1444970bb2c4f09d0911b0eab00e2a75c0.pdf | The ICR identified various lessons, most relevant ones are summarized as follows:Combining investments onhardware (irrigation infrastructure) with software (improved agricultural technology) leads to more benefits in terms of higheragricultural yields and production. The project provided a combination of improved seeds and good agronomic practices(including SRIs), which created a strong foundation for impactful irrigation infrastructure investments. A self-standing irrigationinvestment would not have added much value without complementarity software investments.To increaseincomes of farmers improvements to productivity are not sufficient catalysts for creating impact unless marketing and valueaddition are included in the program. The end of project review confirmed that incomes and revenues increase more whenfarmers are also supported with market linkages and value addition. For example, warehouses help farmers to improve storage anddefer sales to when prices are high, while mobilizing farmers in groups and linking them to off takers provides an opportunity forbargaining prices.A long-term approach to irrigation and agriculture development is key to ensure developmentalimpact. This project s experience showed that development of irrigation infrastructure and long-term viabilityof intermediate outcomesneed adequate time, and more than 5 years, to achieve developmental impact. Thus, sustained effortsare needed to institutionalize intermediate outcomes, sustain operationand maintenance for irrigation schemes as well as,linkifarmers to markets, and createa sustainable seed production system.
P144531 | Climate Smart Staple Crop Production | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/982891632315957357/text/China-Climate-Smart-Staple-Crop-Production.txt | http://documents.worldbank.org/curated/en/982891632315957357/pdf/China-Climate-Smart-Staple-Crop-Production.pdf | The following lessons in the ICR stood out as important and relevant to other projects onclimate smart staple cropdevelopment, and are presented here with some editing.1. A sound project monitoring and evaluation system with asolid baseline survey can support efficient project implementation. Under this project, the ME system design had aclear Results Framework and adequate indicators, with a technically sound baseline survey done at project preparation on thecropping system, farm type, and soil type, laying a solid foundation for measuring, demonstrating and reporting on results,performances, and the cost-effectiveness of various CSA technical options. Further, ME data were collected and analyzed by aprofessional third-party agency responsible for each province, ensuring the independence of the ME process and dataquality.2. The CSA interventions of a public good nature can benefit from support by a government payment forecosystem service (PES) or similar program. The compensations provided to the farmers under the project were well foundedand were effective means to achieving valuable climate benefits. As demonstrated in the economic analysis (ICR, Annex 4), in termsof the cost benefit ratio, the subsidies for farmers could generate far more climate benefits. The public good delivery by farmersshould be fully recognized and compensated fairly, as the beneficial externalities generated by a farmer cannot be internalized. Assuch, it would be desirable if compensation for CSA technologies could be covered in the PES program. Moreover, the project showedthat different technical interventions generated divergent financial returns for farmers and economic returns for society as awhole. Given this, the magnitude and level of CSA compensations can be based on specific implementation results to enable efficientand effective use of public financing.
P144601 | First Economic Reform Support Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/432851530222270683/text/Tonga-First-Economic-Reform-Support-Operation.txt | http://documents.worldbank.org/curated/en/432851530222270683/pdf/Tonga-First-Economic-Reform-Support-Operation.pdf | The following lessons are from theICR (p 26-77):Sufficient time should be allowed forreforms to be introduced when governments have a low institutional capacity.A medium-term perspective with athree or four-yeartimeframe would ensure thatsufficient preparatory work can beundertaken.A diagnostic ofgovernment implementationcapacity is essential, together withan assessment of technical assistance necessary to provide support, wheneverlow capacity is identified.Consideration of these aspects could then determine the timing and sequencing of reforms. Reforms should be prioritized andsequenced to reflect the stage of knowledge and capacity. In addition, some attention to risks posed by those who stood to gain orlose from reforms could help in managing risks of delayed implementation.Donor coordinationiscritical to the optimum allocation of TA support to the government andalso helps with the monitoring andsupervision of the operation.Joint missions alsohelp alleviate some of the burden on governmentcapacity.Identification of a series of potential reforms in the joint budget support matrix canfacilitate the choice of actions to use in adjusting the program. However, these changes should not undermine the logicallink between actions and targeted results. Care should be taken to ensure any changes in prior actions and triggers still follow alogical sequence which can be attributed to achieved outcomes.Strong government commitment to andownershipof reforms ensurescontinuedprogress even inin a low capacity context,characterized by frequent staff turnover. This also highlights the importance of civil service reform to help mitigate therisks arising from frequent staff turnover. The inclusive growth series in Tonga contains measures to strengthen remuneration inthe civil service, which could facilitate staff retention, but, more direct and targeted civil service technical assistance andreform may also be needed. In this regard, it will be important to consult and engage the key service sectors to ensure servicedelivery is not compromised in the process. Engaging these sectors in the Joint Budget Support Committeewill also helppromote their ownership.
P144602 | Kiribati Economic Reform Operation | East Asia and Pacific | Kiribati | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/435941489413504274/text/Kiribati-Kiribati-Economic-Reform-Operation.txt | http://documents.worldbank.org/curated/en/435941489413504274/pdf/Kiribati-Kiribati-Economic-Reform-Operation.pdf | This review restates two of the lessons drawn in the ICR and adds two more:1. The Bank can improve policy performanceparticularly in small states with thin capacity. The Kiribati DPOs provide an example of how the Bank can deploy itseconomies of scale in knowledge to assist small countries with a small civil service that is limited in its capacity todevelop policies in some areas.2. Bank project-level engagements can be springboards for policy reform. This was the caseof the telecommunications sector, where the Bank leveraged its project-level engagement to support the sector policyreforms.3. An unstable revenue source, such as fishing licenses, can derail macroeconomic policy. During the decade priorto the program, volatile fishing fees and weak tax revenues resulted in a sharp decline (ICR para 3) in per-capita RERF assets andincreased non-concessional debt. During program implementation increased fishing revenues allowed for some recovery of thoseassets, but also encouraged a pace of spending increases that does not look sustainable over the long term.4. Whereobjectives are too broad, narrow outcome indicators will impede adequate ME, This was the case with the third objective(expand private sector opportunities), which should either have been formulated more specifically (e.g., improve telecommunicationservices) or, alternatively, should have been underpinned by a broader set of actions aimed at addressing the key conditions thatinhibit private sector development.
P144612 | BURUNDI - ECONOMIC REFORM SUPPORT GRANT VII | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | In addition to the lessons presented in the ICR, IEG draws four main lessons from the experience of designing and implementingthisseries: Effective ownership of the program by sector ministries and agencies requires systematic capacitybuilding. In this case, the risks attached to Ministry of Finance control and ownership of the design, implementation andmonitoring of the reform program were recognized, and attempts were made from the outset to involve the sector agencies in thediscussion. Later they were assisted by specialists who designed medium term expenditure programs for the sector agencies. However,little use was made of these instruments, since the staff of the sector agencies had neither the relevant expertise norinstitutional incentives to adopt the instruments as their own. For reforms involving privatization,extensive and in-depth consultation with all major stakeholders can help design a program that is acceptable to, and consistentwith the ambitions of, affected parties. In this case, the previously successful privatization of a number of coffeewashing stations led to the assumption that the privatization of the remainder would also succeed. This, however, did not takeaccount of the changing perceptions and developing ambitions of the coffee growers. Pursuit of reformsthat do not have the necessary degree of political backing is unlikely to be successful. Although the series supported thedevelopment of a new Mining Code and the establishment of a commission to guide the country towards membership of the EITI, thelack of progress in negotiations with the international body, together with the fact that not one of nine benchmarks for membershipwas achieved, suggests that political buy-in for the necessary degree of transparency in the mining sector was not strongenough. A modest and incremental approach towards assisting the very poor and vulnerable can paydividends, especially in a fragile country context. Careful data building efforts, combined with flexibility in terms ofthe institutional framework and attention to local voices, can result in an important increase in the percentage of the very poorcovered by at least one social safety net.
P144614 | Cultural Heritage Preservation and Tourism Sector Support Project | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099062823135529322/text/P14461403b113a00f08ced05f46942627f2.txt | http://documents.worldbank.org/curated/en/099062823135529322/pdf/P14461403b113a00f08ced05f46942627f2.pdf | The ICR (p. 33-35) provided several lessons learned, which were adapted by IEG: Assessing cooperationdynamics between local agencies may allow for better project implementation and sustainability. The project design of thisproject included the cooperation of three different agencies, UTE, ISPAN, and UNESCO. Due to the project choosing UTE asimplementing agency, ISPAN and UNESCO were unwilling to corporate initially. Also, UTE lacked the necessary technical capacity andfiduciary experience to successfully implement the project. As a result of these two issues, the project experienced significantimplementation bottlenecks and delays. Equipping a PIU with the necessary capacity before the projectbecomes effective and ensuring that it has a presence in the implementation area as well as decision power can positively impactproject implementation. In this project, the PIU was based in the capital while the project was implemented in the North,not allowing a strong presence in the project area. Also, the PIU was not allowed to approve all operational transactions, whichhad to go through the government, resulting in substantial delays. Using Trust Funds to provideTechnical Assistance can be a useful tool to conduct the necessary technical studies. This project was not able to startthe actual works on the monuments due to most time being spent on procuring and conducting the required architectural, topographic,and geotechnical studies.A lesson learned added by IEG: Assessing local circumstances whendesigning a project to increase revenues from tourists, as local circumstances can positively impact project outcomes.This project was based on the assumption that tourists would leave their cruise ship and travel about six hours by land to visithistoric sites. This assumption was unrealistic and would have benefitted from being assessed into more detail.
P144637 | Community Development Program Support Project-Phase III | Western and Central Africa | Cameroon | Blend | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR (p. 32-34) included several lessons learned which were adapted by IEG with some modification oflanguage: The absence of government endorsement for an exit strategy may negatively impact thesustainability of project outcomes. Under this project, even though the exit strategy was prepared to ensure that thecommunes would continue to receive technical and financial support for managing local public finances after the project closed, itwas not endorsed by the government, possibly due to limited political prioritization. As a result, the sustainability of projectoutcomes are at risk. Building local capacity throughout the life of the project can positively impact projectoutcomes as well as their sustainability. While this project built some local capacity, it is not clear if the capacitybuilt will be sustainable if e.g. CFOs, who were trained under the project, leave their positions. Developing aResults Framework for World Bank operations aiming to support refugees and/or internally displaced people (IDP) that monitorsoutcomes and satisfaction particularly for refugees and IDP can ensure that they benefit from the project. In thisproject, the standard indicator number of beneficiaries was measured while it would have been better to assess morespecifically the impacts of investments on refugees and IDP as well as their satisfaction with project activities and their abilityto participate within the communes.
P144675 | Vietnam Power Sector Reform DPO3 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial |  |  | Five lessons are drawn from the ICR (pages 57-60), with some adaptation.One, the implementation of a complexmulti-part, multi-period, multi-operation, sector reform DPO requires a singular attention to the end-program goals and objectives.Delays in one period must be compensated for by accelerated action in another to keep the reform momentum going. Shortfalls in onereform area must be remedied by compensatory effort in another to keep the program goals within reach. Considering that a delay indivesting from power generation may have dulled private investor interest, Vietnam must now considerother meanstoincrease investment in new generation capacity in the light of rising demand for electricity.Two, technical progresswith a reform effort must be matched by political action --- that is, progress with the political steps needed to secure the reformoutcomes. The development of generation market rules, the installation of an information technology system, and the conduct ofactual trading in electricity made for robust technical progress with creation of a competitive market for power generation. But,the technical gains would have been hollow without a willingness by the Government to cede complete political control over thetariff setting and adjustment system to a rule-based mechanism.Three, a sector reform program must always berealistic, both with the scope and scale of the reformsas with the timeline. The realism of prior actions and expectedoutcomes must be rigorously scrutinized both during appraisal and implementation, including with regard to the macro-economicenvironment and the political setting in which the reform plan is to be pursued. The pressure to disburse the loan proceeds,for budget support purposes in a DPO like the PSRDPO, is ever present, but the option remains that the budget support can be scaledback to match the measure of progress made with the reform program.Four, a market reform program entails more thanjust transparency in the operation of the market, it also invokes transparency in theenactment of policy and institutionalreforms. Transparency of the Governments decisions is vital to gaining the confidence of stakeholders that the reforms aregeared to the public interest. It was important in the implementation of the PSRDPO that the prior actions required of theGovernment and that the results of various reform initiatives were disclosed and disseminated to market participants and to thepublic.Five, an energy sector reform program requires substantial technical assistance, which the Bank and theborrower must commit to provide, including on an ongoing basis. The PSRDPO benefitted from technical assistance provided duringprogram preparation, in the implementation of various technical aspects of the reform program, and for the design of the next stepin the long-term plan --- the creation of a competitive wholesale market. The Bank successfully mobilized grant funding for some ofthese requirements and supplied its own technical expertise for many other activities. The Government should financially supportother technical assistance requirements.
P144715 | Cambodia Global Partnership for Education Second Education Support Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2014 | 2018 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/124781530283826325/text/Cambodia-Cambodia-GPE-Education-Support-Project.txt | http://documents.worldbank.org/curated/en/124781530283826325/pdf/Cambodia-Cambodia-GPE-Education-Support-Project.pdf | The ICR presented a number of valuable lessons and recommendations thatare summarized here: the sense (particularly in thecontext of a project with a short timeframe)in building on the foundations and achievements of past efforts to facilitateimplementation readiness and deliverresults;the advantage in ensuring client /implementing agencyownershiptoincrease the sustainability andcohesiveness of interventions;and theneed to ensureaccuracy, consistency,and agreement on the wording of indicators,baselines, andtargets during projectpreparation.IEG notes the above and emphasizes the following:In the absence ofreliable baselines and targets, the value of even well chosen indicators is compromised. In this case, there was confusionregarding the definition of certain baseline and target values that led, eventually,to a restructuring. In addition,someof the targets were set with reference to a subset of eventual beneficiaries such that certain of the results suggestspectacular performance which, in fact, is not the case.A mid-term review (MTR) provides an opportunity totake stock, and to identify and mitigaterisks and challenges. In thiscase, there was no MTR, possiblybecauseofthe short project life-span of three years; however, a formal MTRmay have resulted in an earlier restructuring (andpossibly eased some of the bureaucratic hurdles encountered) and in more accuratereporting over a longer timeperiod.When seeking to address the quality of education and secure learning outcomes, it is important toaddress relevant demand and supply side constraints. This project adopted a multi-factored approach that involved, forexample,construction, training, community involvement, standardized testing etc. In so doing, the project built on availablelearning that suggests a one-sidedapproach is less likely to deliver results in a developmentcontext.
P144726 | National Cyclone Risk Mitigation Project-II | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2023 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | The project operations offered the following lessons: If standardized templates are customized for eachparticipating target state, this may contribute to attributing how the risk from cyclones and other hydro-meteorological hazardsare reduced in each state.In this project, project investments highlighted the effective response to Cyclones Amphanand Yaas. The investments adhered to standardized disaster resilient design principles. Quality construction complied with thelatest codes and World Bank guidelines. The MPCS design created standardized templates that allowed customization to meet specificneeds of each state. The designs of these investments underwent rigorous quality audits. High quality components formed part of thefinal structures. If planning for OM, realistic expectations are importantconsiderations. In this project, community institutions, such as the CSMMC fostered ownership and encouragedvigilant maintenance and repair of the infrastructure. Adequate budgeting would fund long-term maintenance and provide for arisingunexpected repair costs following extreme weather events. Shelters used for other purposes benefitthecommunity. In this project, the shelters were used for other functions after disasters. Communities embraced its usebeyond during emergency, to serve as hubs for community gatherings, educational programs, and delivering community healthservices. A formal knowledge exchange platform may facilitate the spread of best practices and innovativesolutions to reduce vulnerabilities.In this project, all agencies including SPIUs, the supervision consultant, andPMU began collaborating during the inception stage. However, the national, state, and local agencies did not formalizechannels where they could share knowledge and best practices among the states.Regular workshops, webinars, and collaborativeplatforms could help facilitate the exchange of information, share experiences of what works, and replicate innovative solutionssuch as conducting periodic mock drills and awareness campaigns,visual aids and translation during training. These aids couldfacilitate timely response, overcome language barriers, and promote better understanding in reducingvulnerabilities. A programmatic approach for DRM projects may facilitate progressive achievement of DRM relatedobjectives. In this project, design was built on the outcomes achieved under the first phase, acknowledging the knowledgeaccumulated from the preceding phase. Enhancing institutional capabilities demonstrated the continuing benefits of utilizingexisting frameworks. For example, as NCRMP I implementation was ending, this phase was starting. Conducting combined Phases I andII PSC meetings because of the programmatic nature of the approach to DRM facilitated knowledge sharing and strengthenedinstitutional relationships. Newly participating states benefited from the more experienced ones on complying with the policies ofWorld Bank-financed projects. The longer-term engagement fostered by a programmatic approach lends to a realistic achievement ofDRM related objectives.
P144774 | Connectivity Development Policy Loan 2 | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2014 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/762731467998766625/text/ICRR14703-P124006-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/762731467998766625/pdf/ICRR14703-P124006-Box393183B-PUBLIC.pdf | This evaluation highlights three lessons drawn by the ICR:Although an operation supporting reform in broad widely cross-cutting areas may have a stronger transformative impact, it also may bear a higher risk of achieving only a fraction of its objectives.A wide cross-cutting DPL does not automatically elicit the coordination efforts that engaging multiple agencies requires, so that inadequate coordination may impede the achievements sought.Electoral cycles may slow down the momentum of reform, particularly with the bureaucratic, administrative, and legal impediments that may arise during those periods.
P144775 | Institutional, Tax Administration, Social and Investment (INSTANSI) DPL 2 | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2014 | 2014 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/213471468178157482/text/ICRR14693-P126162-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/213471468178157482/pdf/ICRR14693-P126162-Box393183B-PUBLIC.pdf | IEG draws the following lessons from the experience of preparing and implementing this DPO series:It is important to have consistent, clear and specific objectives (as noted in the section 2.a, this was not the case). This was further exacerbated by the fact that the ICR had a different interpretation of the objectives. Careful consideration to the internal coherence of a program supported by a DPL series and ensuring the appropriate number of operations is envisaged from the outset would help achieve significant reforms. In this case, in practice, there was limited synergy between the two pillars, one of which was heavily diluted at the time of the second operation. Furthermore, reforms being supported may need to be sustained over a longer period than that covered by the series. In such cases, a series of individual DPLs may be more appropriate than a programmatic series. Otherwise, programmatic lending may not be the best instrument when there is significant uncertainty surrounding policy options of the Government and stand-alone DPLs may provide greater flexibility and lead to better results.Systematic formal supervisory reporting can assist monitoring when there are significant modifications to the program. There were such changes in design between the first and second operation, and the cancelation of the third DPL had implications in terms of results and policy dialogue that could profitably have been brought to management attention in a timely manner. The date when an indicator is measured would need to be consistent with the operationâ€™s implementation period. In this case, results were to be measured some 12 months after the closing date, and there was uncertainty over whether there would be a third operation. This could have been removed by extending the period of formal supervision (and hence the closing date) for a year later.
P144832 | NATIONAL UNIFIED REGISTRY AND OUTREACH WORKER PROGRAM | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/368601602882565893/text/Jordan-National-Unified-Registry-and-Outreach.txt | http://documents.worldbank.org/curated/en/368601602882565893/pdf/Jordan-National-Unified-Registry-and-Outreach.pdf | The following main lessons are drawn from the ICR (pp. 40-41):High-level government support canbe critical for project implementation.The cash compensation initiative depended on the implementation ofpoliticallysensitive energy subsidy reforms, which quickly lost traction as oil prices fell. On the other hand, the decision tobuild the NUR by anchoring it on NAFs cash transfer program enabled its development, because this was an establishedprogram. The subsequent high-level endorsement by the Government of Jordan to build the NUR platform was critical for establishingdata access.Complex implementation arrangements can influence coordination andownership.The project had a complex implementation structure with critical responsibilities resting with differentgovernment institutions.This arrangement necessitated lengthy negotiations to clarify responsibilities and coordinateactivities during project preparation, restructuring, and handover. Simpler implementation arrangements at project design, withclear lines of responsibility and accountability, would likely have expedited implementation significantly.
P144856 | Improving Pre-primary and General Secondary Education Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/144051605558789011/text/Uzbekistan-Improving-General-Sec-Pre-School-Edu.txt | http://documents.worldbank.org/curated/en/144051605558789011/pdf/Uzbekistan-Improving-General-Sec-Pre-School-Edu.pdf | The ICR (pp. 30-31) offered several lessons, including the following lessons restated byIEG:Teachers and school directors appreciate the objectivity of performance assessment tools andmonitoring of pedagogical practices as a formative and non-threatening approach to support their work. Teachers hadno such standardized tools prior to the project, and once they understood that such tools could be used to incorporate feedback andadjust methodologies into their daily routine, there was substantial interest to apply them.Theprovision of storybooks broadens the scope of early learning at home. Under the project, the provision of qualitystorybooks created several channels of positive impact, including the engagement of both mothers and fathers in the earlyliteracy of their children, supporting the development of reading skills in children who were too young to attend center-basedpreschool, and providing a link between the home and preschool environments.The placement of storybooks at home and inpreschool lending libraries contributed to a broad approach in creating opportunities for early stimulation andlearning.The alignment and sequencing of hard and soft investments facilitate the attainmentof desired results. Under ECCE, investments in materials and equipment were well tied to teacher training andcommunication interventions.However, the blend of investments was less optimal under general secondary education, wheretraining on ICT was insufficient to adequately address teachers skills gaps.Misalignment ofproject preparation cycles between the Bank and the government can create cumulative implementation delays. Earlystart of preparatory work, including a project feasibility studyrequired for government approval and drawing up of biddingdocuments during project preparation,is animportant determinant of project implementationreadiness.
P144871 | Improving Quality and Efficiency of Health Services Program for Results | Europe and Central Asia | Croatia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | PforR | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/503461606924731394/text/Croatia-Improving-Quality-and-Efficiency-of-Heal.txt | http://documents.worldbank.org/curated/en/503461606924731394/pdf/Croatia-Improving-Quality-and-Efficiency-of-Heal.pdf | The ICR (pp. 30-31) presented a series of insightful lessons that should prove useful to the preparation and implementation ofother PforR operations, including:Priority areas selected for PforR will underperform if not matched to proposedfinancing, with adequate financial incentives for achieving expected results. In this case, the support provided throughthe PforR amounted to less than ten percent of the total cost of the National Health Care Strategy while supporting five of itseight priorities. Spreading the financing so thin limited the financial incentives to reach ambitioustargets.Political economy analysis that assesses potential changes in the political arena and crafts flexiblemitigation strategies is an important element of project preparation. In this case, unanticipated changes in MOHleadership produced shifts in policy that undermined attempts to establish a hospital accreditation system and address a backlog ofhospital arrears.
P144892 | Moldova Health Transformation Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | PforR | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR (pp. 30-31) offers insightful lessons emerging from the operation, some of which are adapted here:ThePforR instrument can be effective both operationally and institutionally even in a challenging country context. In thiscase, the PforR reinforced the health sectors results-oriented culture, bringing the MoHSLP and CNAM together to findsolutions to common problems and leverage one anothers comparative advantages even in a situation of sustained politicalvolatility.Intensivesupport facilitates effective implementation ofa PforR and can maximizedevelopment impact. In this case, intensive supervision and capacity building efforts from the Bank team were needed toremove implementation bottlenecks and respond proactively to contextual challenges. The TA component provided critical technicalsupport and capacity building.Putting in place a strong monitoring and evaluation framework prior to launch of aPforR can facilitate smooth implementation. In this case, some indicators lacked clarity or data sources, and targets werenot clear, necessitating consultations with counterparts and program restructurings. The ICR (p. 31) notes that these disruptionscould have been avoided with more clarity upstreamin definition of indicators, data sources, measurement methodologies, andverification measures.
P144933 | Second Private Sector Competitiveness and Economic Diversification Prj | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099082823120014174/text/P1449330ab8af801d0b0300de3cd6560c4d.txt | http://documents.worldbank.org/curated/en/099082823120014174/pdf/P1449330ab8af801d0b0300de3cd6560c4d.pdf | Two lessons are drawn from the ICR, with some adaptation.Although enacting new laws and creating newinstitutions take considerable time and effort, governments must nonetheless persevere with legal and institutional reform if theyare to develop the enabling environment for private business activity and private sector development. In thisproject, The Government was able to establish the Credit Information Bureau in the first year of project implementation in 2014,but only after the International Monetary Fund and the multi-donor Financial Sector Reform and Strengthening Initiative had helpedthe Central Bank of Lesotho with preparatory work in creating a credit bureau starting before the preceding Lesotho Private SectorCompetitiveness and Economic Diversification Project was approved in 2007. After the creation of the Credit InformationBureau, it would take another six to seven years to enact theSecurity Interest in Movable Property Law in 2020 and establishthe associatedLesotho Electronic Registry of Movable Assets in 2021. The two sets of reforms were vital to improvingaccess to finance in Lesotho, where it been historically limited.Programs to diversify an economy and its exportstructure require a discerning search for, and a rigorous assessment of, those sectors and industries in which the economy enjoyscomparative advantage. In this project, commercial horticulture, handicraftmanufacturing for export, andtourism, offered viable opportunities to diversify the economy away from an excessive reliance on textile and apparel and roughdiamonds. Commercial deciduous fruit farming was 150 times more productive than smallholder subsistence wheatcultivation. Handicraftscouldleverage robust foreign interest in the countrys Basotho culture. Tourismoffered opportunities to exploit the countrys natural landscape and wildlife,rich history and culture, and colorfulfestivalsfor business advantage over competing destinations. Select strategic interventions would help nudge thedevelopment of these sectors as new sources of growth in the long term.
P144952 | Modernization of Public Finance Management | East Asia and Pacific | Myanmar | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2021 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099142503062331284/text/P1449520e5f9590590b87b0fdaa4f9ba67b.txt | http://documents.worldbank.org/curated/en/099142503062331284/pdf/P1449520e5f9590590b87b0fdaa4f9ba67b.pdf | The ICR presents a series of lessons and recommendations emerging from the projects experience. IEG summarizes themost persuasive lessons below:High-level political commitment and policy dialogue is criticalthroughout the project cycle. In the case of this operation, leadership and ownership were necessary to ensure theimplementation of the main PEFA findings andto support the planning of the subsequent phases and the continuity of theproject. The project was led by a single ministry (MoPF) and was placed under the Deputy Minister. The projectsSteering Committee was his management team which ensured full ownership as well as high-level commitment. Furthermore, the retreatsthat were organized with the government, the World Bank, and development partners helped build and foster trust which is necessaryfor sustained policy reforms.It is important to strike a balance between an ambitious scope, existing capacity,and FCV context. In the case of this operation, while it was important to align the projects design with theGovernments comprehensive and ambitious PFM reform strategy, the technical and management capacity of the staff of the eightIAs was a limiting factor, along with the FCV context. There is a need to better address these limitations with simpler andmore streamlined implementation arrangements to ensure greater efficiencies and decrease the risk ofduplication.There are benefits of anchoring the technical design and activities on strong analyticalwork. In this case, the first PEFA assessment (2012) helped in establishing a baseline measure of PFM strengths andweaknesses, which guided the design of activities. The 2020 PEFA assessment helped to determine the extent of progressmade.
P145040 | Supporting Sustainable Wastewater Management | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/444911630075683987/text/Georgia-Sustainable-Wastewater-Management.txt | http://documents.worldbank.org/curated/en/444911630075683987/pdf/Georgia-Sustainable-Wastewater-Management.pdf | IEG usesthree main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Institutional capacity building and technical assistance are crucial for project implementation in aweak capacity environment.Comprehensive training programs, relevant study tours on international best practices andimplementation support by the Bank areessential for project implementation. This was especially the case for Georgia wherethe wastewater sector was underdeveloped at appraisal. The lesson from this project is that enhanced capacity building to ensurethe functionality of the rehabilitated Wastewater Treatment Plantsis especially important in medium-size cities wherecapacity may be even more limited than in capital or larger cities.2. It is important to be realistic about thelevel of ambition for sector reforms. This was the first Bank project in the wastewater sector, yet the level of ambitionfor the sector reforms was relatively high, leading to non-achievement of some of the intended results (such as increasing costrecovery ratio, supporting water demand management). Amore gradual and phased approach aimed at sector reforms would be moreappropriate, based on a realistic assessment of the willingness and capacity of key stakeholders duringpreparation.3.The engagement of all stakeholders from the early stages of project preparation is necessaryfor facilitating projectimplementation. In this project, several of the key stakeholders, such as the GeorgianNational Energy and Water Supply Regulatory Commission or the relevant technical staff of the municipalities who oversawconstruction permits, environmental approvals and other important procedures were notidentified as one of the keystakeholders at the preparation stage of the project. This contributed to delays during implementation and rather limited resultswith sector reforms.
P145048 | WEST BALKANS DRINA RIVER BASIN MANAGEMENT | Europe and Central Asia | Western Balkans |  |  | Sustainable Development | Water | GEF | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099145003152234715/text/Western0Balkan0ina0River0Basin0Mgmt.txt | http://documents.worldbank.org/curated/en/099145003152234715/pdf/Western0Balkan0ina0River0Basin0Mgmt.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1.Establishing transboundary cooperation andstrengthening institutional capacities need to be part of long-term developmentstrategies. Building trust among institutions of different riparian countries, establishing mechanisms for closecollaboration, strengthening the capacities for this purpose, and formalizing the cooperation is a lengthy process requiringcontinuous external support over many years, if not decades. This cannot be fully achieved within a single project despite theprogress made. While this project made important contributions for the transboundary management of the Drina River Basin, itsresults will only be sustainable if further support to each country is provided. In the case of this Project, this will be providedthrough the new Sava and Drina Rivers Corridors Integrated Development Program (SDIP, P168862), and the Sava River BasinCommission.2. To ensure accurate assessment ofachievements, ME design for projects focusing ondeveloping institutional capacities need to include specific capacity assessments and evaluations to accurately assessachievements. To better assess the results of activities to strengthen capacities or create awareness, an ME systemshould include specific capacity assessments and evaluations, for example, based on polls and surveys. This is essential fordetermining whetherprojects effectively deliver on capacity building and contribute to long-term outcomes.3.To ensure successful management of transboundary projects, adequate financial resources need to be earmarkedtomanagerial/supervision requirements. Despitean experienced PIU in each country, the projectstillrequired substantial managerial and administrative support. Elevated transactions costs and close supervision through countryoffices must be anticipated and adequately resourced. Engaging the local staff at country offices and recognizing their undisputedrole for smooth project implementation is a key to success, especially in the complex projects that involve many countries anddifferent stakeholders who need continuous supervision and support.
P145055 | Sustainable Agriculture Transformation Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2022 | 2024 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099102023111514489/text/P14505508f0bf6012083a80425fb16de86d.txt | http://documents.worldbank.org/curated/en/099102023111514489/pdf/P14505508f0bf6012083a80425fb16de86d.pdf | The ICR included five lessons, out of which this review has highlighted (with some adaptation in language) the following fourlessons that had broad applicability to Bank operations. One additional lesson is also noted based on the research (Tuan et al.2021) that was highlighted in the report which was relevant based on the projects experience. Aprojects direct link to a national program brings strong ownership and commitment from the Government. The projectwas well-aligned with the Agriculture Restructuring Plan (ARP) and new MARD Sustainable Agriculture and Rural Development Strategyfor 2021-2030. The project activities contributed and supported the implementation of the Governments plans and strategieswith a renewed focus on sustainable and low carbon agriculture. A projectsinterventionon promoting low carbon technologies that is profitable to farmers encourages adoption.The project focused on building the capacity and knowledge of farmers on low-carbon cultivation technologies throughtraining, technical assistance, as well as supported them with access to credit, infrastructure development, and improved servicedelivery etc. These comprehensive set of interventions of the project led to reduced production costs and higher profits forfarmers, which were key factors encouraging the adoption of low carbon technologies. A focus on a few key valuechains in contiguous areasconnected farmers to markets and resulted in efficiency gains for the project.The project focused on two key crops rice and coffee and implemented a clustered approach in implementingproject activities. This approach allowed the project to develop infrastructures related to processing and logistics for therelevant value chains in key project areas, which not only helped improve farmers linkages to markets but also broughtefficiencies to project investments. A wholesale banking model for access to finance helped mobilize privatesector financing. The projects wholesale bank (BIDV) was not only able to manage and coordinate credit lines, butthis arrangement also helped bring additional financial resources from private banks and end-borrowers. This apexinstitution played a key role in helping the Government understand the market for credit which then enabled the Government tointroduce relevant policy adjustments. The fifth lesson which the ICR noted in paragraph 34 is the followingbased on independent research in the project area:5. ??????Factors that determine technology adoption go beyondfarm characteristics or previous experiences of farmers.As per the study (Tuan et al 2021) in project areas, thereare several other drivers of adoption such as educational status of farmers, farm size, adopter categories (innovators, earlyadopters, early majority etc.), interests, and other motivations. Due to thesediverse factors or drivers of technologyadoption, there is a need to be open to undertaking a differentiated approach in disseminating technologies based on theirlocations and socioeconomic context (ICR, paragraph 34)
P145057 | Pacific Aviation Safety Office Reform Project | East Asia and Pacific | Pacific Islands |  |  | Infrastructure | Transport | IDA | IPF | 2014 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099103123192014919/text/P1450570dbfb8a0dd0abd90c907772f141c.txt | http://documents.worldbank.org/curated/en/099103123192014919/pdf/P1450570dbfb8a0dd0abd90c907772f141c.pdf | The ICR developed several lessons, the most relevant ones are presented as follows: Projects aimed atsetting up or reforming regional institutions can effectively address bottlenecks by incorporating flexible designs and allowingfor longer implementation periods. The project experience showed that greater flexibility in project designs is necessaryfor course corrections to be made during implementation and to support changing needs in complex regional environments.Furthermore, strengthening the capacity of member states in governance and enhancing stakeholders abilities in implementationis crucial. For instance, empowering PASO Council members with skills in governance, strategy, finance, and leadership was vitalfor decision-making in aviation safety and security. Creation of regional approaches with a phased approach, whensmall states face challenges to deliver certain services independently could be valuable. Many Pacific states facechallenges to independently deliver their own internationally compliant aviation oversight and resolve aviation safetydeficiencies. These common challenges highlighted the need for a regional organization to provide a collective approach to aviationsafety oversight. When collaborating with regional organizations, its advisable to adopt a phased approach to preventoverambitious program objectives and ensure realistic outcomes achievable within the project timeframe. Additionally, coordinatingwith prominent donors in the sector can maximize project investments, bolster organizational capacity, and support continuousservice delivery. Other projects by other donors such as the World Bank funded, which ensured construction of critical aviationinfrastructure and strengthening the policy and regulatory environment in participating countries in the region, also contributedto successful achievement of project results.
P145101 | Uganda: Albertine Region Sustainable Development Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099110623184036424/text/P145101009a7b10050943503e198cbccaec.txt | http://documents.worldbank.org/curated/en/099110623184036424/pdf/P145101009a7b10050943503e198cbccaec.pdf | The following lessons were derived from the ICR (ICR, pages 32-33):1. Adopting a holistic approach to addressingregional development could delivergood results. The Project adopted a holistic approach that included addressing regionalconnectivity by improving the main road connecting the region and the entire country; regional urban and rural planning; localaccess to ensure year-round, uninterrupted access; access to markets; and developing skills relevant for the evolving needs of theregional economy. Such a holistic/systemic approach proved to be supportive of the multi-faceted development needs of the region,linking the investment in the infrastructure assets with economic development and poverty reduction goals and creating support fromvarious stakeholders.2. Appraisal stage project preparation should include feasibility studies, designs, obtainingpermits, and other necessary preparatory work. Feasibility studies were not done for Component 2 during preparation, resulting inthe need to restructure the component during implementation. Component 1 was suspended for 18 months, partly because the right ofway was not obtained at preparation. Designs were not completed during preparation for Components 2 and 3, and funds allocated tothem turned out to be insufficient once the designs were completed during implementation. For Component 3, the identification ofthe twinning institutions was delayed for nearly 2 years, and therefore the implementation of the entire component could notproceed. Also, the government did not provide RAP funding to Component 2, which caused challenges during implementation, and someactivities had to be dropped. The lesson is that the allocation of funding for investment activities should be based on diligentcountry-specific analysis, and the necessary preparatory activities should be conducted during appraisal and be a conditionfor project approval.3. A concerted effort must be made to address environmental and social (ES) risks. There wereproblems with gender-based violence (GBV), violence against children (VAC), and occupational health and safety. These challengeswere addressed through concerted efforts of all stakeholders. The Bank provided a GVB specialist and conducted hands-on training;the client ensured that a memorandum of understanding was signed with the Ministry of Gender, Labor, and Social Development toaddress GBV, VAC, and labor concerns and procured services of nominated service providers and a nongovernmental organization toaddress these problems. The lesson is that when social problems occur during project implementation, a judicious andmulti-stakeholder coordinated effort might be necessary to achieve a timely resolution.
P145114 | Quality of Decentralized Service Delivery Support Development Policy Operation | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2013 | 2014 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/205981467999705062/text/ICRR14789-P145114-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/205981467999705062/pdf/ICRR14789-P145114-Box393191B-PUBLIC.pdf | The ICR highlighted a number of lessons, such as importance of "thinking outside the box" in difficult circumstances; understanding political economy context; and government's commitment and leadership.In addition, this review suggests the following three lessons:Although extraordinary budget support by the Bank at the time of a shock can draw on ongoing sector reforms, lack of reflection of the key motivation of its engagement may affect program's relevance . For example, proper reflection of this in program objective and design would allow supporting the client's policy response to the shock, and engage in quality policy dialogue during program implementationAlthough drawing on strong reform momentum is important for the success of budget support operations, but, at the same time, it is critical that Bank's operation provide value-added to the reform program by facilitating the reforms and improving their quality through supporting critical actions during preparation and through policy dialogue during program implementationShortcutting the process of DPO preparation can speed up the provision of much needed resources to help alleviate a fiscal shortfall; however, this could result in design weaknesses that may affect the quality of the results chain, and reduce an operationâ€™s value in enabling key policy reforms.
P145114 | Quality of Decentralized Service Delivery Support Development Policy Operation | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2013 | 2014 | 2019 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/707991539617526286/text/126893-PPAR-P165171-P145114-PUBLIC.txt | http://documents.worldbank.org/curated/en/707991539617526286/pdf/126893-PPAR-P165171-P145114-PUBLIC.pdf | 6. Lessons 6.1 The following lessons are drawn from the design and implementation of the program\. 6.2 Strong government ownership and leadership of the reform agenda are important drivers of successful development policy financing. Although this appears self-evident, it bears repetition because development policy financing is sometimes used to attempt to leverage reforms even in cases where ownership is unclear. In Rwanda, the reform agenda supported by the QDS DPO derived directly from the government's own well-defined decentralization strategy, the preparation of which was participatory and supported by several development partners, including the World Bank. Implementation of the strategy underwent regular, structured, and in-depth monitoring with the World Bank and other development partners under government leadership, using the government's own M&E framework. This combination of government ownership and leadership, including its homegrown Imihigo culture of performance and results, is likely to have been decisive in securing progress in the reform agenda, which has been sustained since the QDS DPO closed. 6.3 Rollout of an IFMIS at the local government level can serve as a useful catalyst and vehicle for enhancing local capacity. In Rwanda, the structured training programs that accompanied the rollout of the IFMIS to the district and sector levelsâ€”with the support of the QDS DPO and other World Bank instrumentsâ€”served as a rallying point for improving PFM capacity and practices, notably on financial reporting. Successful implementation of the IFMIS helped local governments more efficiently budget, execute, account for, and report on a rapidly growing volume of fiscal transfers to them. 6.4 Flexibility, agility, and strategic acumen on the World Bank's part can play a valuable role in resolving a financing impasse that threatens to jeopardize development gains. In response to the 2012 ODA cutbacks, the World Bank undertook intensive consultations with its key shareholders and other stakeholders on acceptable modalities for rapidly restoring support to minimize reversals in Rwanda's development gains. Once a consensus was reached that development policy financing focused on decentralization was an acceptable way forward, the World Bank took the initiative to prepare the QDS DPO in record time. Stakeholders widely credit the operation not only with having mitigated the adverse effect of the ODA cutbacks but also with helping to restore normality in financing flows, including external financing and transfers to local authorities, while helping to secure continued momentum in a critical area of the country's reform program. 6.5 In designing a DPO, there may be a trade-off between speed and agility of response and value-added in terms of leveraging reforms, and additionality in securing reforms. In designing the QDS DPO, the choice of instrument and policy content reflected the need to provide quick financial support that could secure the backing of key World Bank shareholders. This meant that many of the measures supported by the operation were ones that the government had already been planning, and in some cases had already initiated, before the design of the QDS DPO was finalized. However, though the measures would likely have been taken even in the absence of the QDS DPO, nevertheless the operation likely facilitated implementation of the government's program, which would have been slower and more difficult in the continued absence of external financing.
P145162 | Pasture and Livestock Management Improvement Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/331561584107100782/text/Kyrgyz-Republic-Pasture-Management-Improvement-Project.txt | http://documents.worldbank.org/curated/en/331561584107100782/pdf/Kyrgyz-Republic-Pasture-Management-Improvement-Project.pdf | The ICR included five lessons. Four of these lessons were project-specific reflecting on the implementation experience of thisproject. One lesson was of broader applicability to similar projects and isemphasized with some adaptation oflanguage: To ensure the sustainability of the development outcome, climate change risk needs to be addressedat the design stage. Initial pasture monitoring results in this project showed that climate change is becomingincreasingly important innatural resources management and may pose a significant risk to development outcomes.Incorporatingresearch into the effects of climate changeandeducation of communities on climate change in projectdesign willhelp communities to prepare better for environmental changes due to climate change.
P145171 | Social Protection System Modernization Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2015 | 2018 | 2019 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/901901538347959716/text/Croatia-SOCIAL-PROTECTION-SYSTEM-MODERNIZATION.txt | http://documents.worldbank.org/curated/en/901901538347959716/pdf/Croatia-SOCIAL-PROTECTION-SYSTEM-MODERNIZATION.pdf | The following lessons from the project are based on the ICR (p.22): Regarding the instrument chosen, successful implementation requiresthat policy changes be linked firmlytocarefully consideredprerequisites. A results-based approach based ondisbursement-linked indicators(DLIs)needs to stipulate straightforward and concrete steps for DLIs. In the future, project designs with a strong reformcomponent should be based on changes initiated before the start of project implementation. Projectsentailing reforms with complex networks of stakeholdersare dependent onappropriate mechanisms to address institutionalsetup and mitigate possible communication and subordination issues that may affect project implementation. This operationincludedfive ministries and several agencies under those ministries, and given the history of weak coordination, it waslikely that some parts of the administration could oppose the proposed changes. Political risk analysis can bea powerful tool for assessing political readiness and the power of stakeholders that are responsible for pushing through policyreforms, as well as setting mechanisms to mitigate risks. In this case, the negotiating government was politically in exitmode at appraisal, and the new administrations commitment to some of the policy reforms dropped, leading to projectcancellation. Policy reformsneed a clear institutional champion and sufficient political backupacross various parts ofthe political spectrum (both the government in power and the opposition).
P145234 | Kenya Petroleum Technical Assistance Project (KEPTAP) | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099145003082323918/text/P1452340bcbc9b00c0aff205205033399b1.txt | http://documents.worldbank.org/curated/en/099145003082323918/pdf/P1452340bcbc9b00c0aff205205033399b1.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A flexible design in the ever-evolving oil and gas sector has a better potential for addressingunforeseen circumstances during implementation.In this project, many project activities associated with sustainablemanagement of petroleum wealth were underminedby the delays that occurred in oil exploration. A more targeted, strategic andphased approach would have been more appropriate, instead of trying to meet the immediate and future needs at the same time.The lesson arising is that a flexible design thatprioritizesinterventions, rather than addressing all thepossible impacts, is likely to havea greaterimpact in petroleum projects.2. Streamlined projectimplementation arrangements can help in minimizing delays during implementation. The design of this project originallyincluded in addition to a project steering committee responsible for project oversight, three implementing agencies. Having threeimplementing agencies proved to be cumbersome and contributed to delays during implementation. Eventually this arrangement waschanged with only one implementing agency following the recommendations of the Mid-Term Review. The experience of this projectfurther demonstratesthat the scope of the Project Steering Committee in multi-disciplinary projects is better limited toinforming and engaging beneficiaries, facilitating networking and collaboration and identifying cross-cutting issues, rather thancovering all aspects of project implementation.3. Multiple beneficiary TA projects may requireintensive and time-consuming Bank supervision,especially in countries with limited implementation capacities. Bankteams may also be required to identify if/when restructurings are needed,given the realities on the ground.Given that astandard supervision budget allocation may not be sufficient for such intensive supervision, it would help if Bank team supervisingsuch projects are involved in more than one activity in the country in order to spread costs for travel and other costs acrossmultiple activities.
P145251 | Third Shared Growth Credit | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | There are three key lessons of general applicability that may be drawn from the preparation and implementation of these threeoperations:Especially in a difficult country context, it is advisable to limit the programs scope and objectives soas to involve the minimum necessary number of sectors, ministries and agencies. In this case, the wide range of reform measures andcorrespondingly large number of concerned agencies stretched weak governmental coordinating capacity beyond its limits. A relatedlesson is that, where coordination is required, the Ministry chiefly responsible for program implementation should have theauthority, experience and connections to carry out its task effectively.While it is acknowledged that the impact of mostDPOs would only be felt in the medium term after the closure of the program, ME design can nonetheless advantageously includeintermediate indicators of progress in meeting objectives that can be more closely related and attributable to the prior actionsand other measures supported by the program.Exclusive reliance on prior actions alone may lead to an erroneous impressionof the programs achievements. In many cases, sustained follow-up is required to make the reforms effective, and it isimportant that program monitoring take this fully into account and implement remedial action where necessary. Examples from thisprogram include the need to survey enterprises regarding visits by taxation officials, and to carry out physical inspections ofimportant procurement contracts.
P145254 | TZ-Second Power and Gas Sector DPO | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial |  |  | The first three lessons are drawn from the ICR (paragraphs 94-96, pages 39-40), with some adaptation; the fourthisdrawn by IEG.Power sector reform programs that advance the electricity access agenda, among otherobjectives, need to incorporate the access effort in program design more explicitly. The DPO recognized the Governmentsobjective to expand access to electricity but failed to explicitly model the initiative in the programs results framework.Consequently, the DPO did not anticipate the increase in TANESCOs arrears despite over-achieving its income targetsasthe electricity company tripled its new connections in three years.Engaging the Tanzanian government on a policyframework for the development of the natural gas industry was worth the effort, notwithstanding the poortally on the programresults indicators. The steep decline in global oil and gas prices in 2014-16 slowed down the gas sector reform momentum inTanzania during the program period. However, theGovernment succeeded in developing thelegal framework for the upstreamgas industry, setting the development agenda for the entirety of the countrys energy supply chain that would be vital to thecountrys future economic prospects.Initiatives to expand the participation of the private sector in energysupply need to be informed by politicaleconomy analysis. A small number of controversial and poorly executed PPP contractscast a long shadow on the outlook for PPPs in Tanzanias power sector. A new Bank document, Rethinking Power SectorReform, lays out an agenda for more closely integrating political economy considerations in power sector reform programs.Astrong link between prior actions and reform implementationincreases the chance of DPOs achievingtheir objectives. The program missed mandating a timeline for the execution of policy and institutional reform plans adoptedby the Government in fulfillment of the prior actions, leaving elements of the reform program exposed to reversal and stalling asnew developments muted the urgency of the reforms, a new government assumed office, and political preferences shifted.
P145261 | Niger - Public Sector Capacity and Performance for Service Delivery Project | Western and Central Africa | Niger | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099041823083035717/text/P1452610548d5f05b0a1ab0d4679d54ccf8.txt | http://documents.worldbank.org/curated/en/099041823083035717/pdf/P1452610548d5f05b0a1ab0d4679d54ccf8.pdf | Twolessons are drawn from the ICR, with some adaptation.Weak institutional capacity undermines the impactof investment project financing operations with performance-based conditions. In this project, the Government wasunable to meet the 13 original performance-based conditions that would have advanced the implementation of 12 eligible expenditureprograms under the National Economic andSocial Development Plan. The original project suffered from a mismatch ofscopeandcapacity: (a) the project development objectives and project activities were overly ambitious; (b) theperformance-based conditions were too numerous; (c) project implementation required considerable central coordination; (d) theimplementing agencies did not completely understand the project, and (e) the information system was ill-equipped to measureperformance against plans. A restructuring of the project, with the project development objectives and activities revised andthe original 13 performance-based conditions scaled down to four, did not materially improvethe results with the Governmentdelivering on only two of the performance-based conditions.Where technical skills are lacking toimplement information and communication technology projects, considerable preparatory work and directimplementation supportare needed. The restructuring of this project recast the original ICT project activities (ICT solutions for customs,public investment management, human resource management, statistics, and monitoring and evaluation) into a revised set of ICTproject activities (public investment management, procurement management information system, human resource management informationsystem, and monitoring and evaluation). However, even the revised ICT sub-projects were not operational at project closing(after seven years of project implementation). According to the ICR, the hurdles included: (a) the lack of technical skillsin the country; (b) the ill preparedness of the government agencies to plan and implement major ICT programs; and (c)political resistance to transparency and accountability objectives that are embedded in ICT programs. Preparatorycapacity-building initiatives wouldhave helped, including project preparation advances and non-lending technicalassistance. Moreover, extensiveimplementation assistance would have been beneficial, including direct implementationsupport to facilitate the procurement process and ensure adequate contract management.
P145263 | CG Rep. LISUNGI Safety Nets System Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICRR confirms the series of lessons and recommendations emerging from the projects experience (ICR, pp. 26-27). TheICRR summarizes the most relevant lessons below:Better risk assessment during design allows for putting in placemitigation measures. The risk of substantial government counterpart funding falling through was not identified as such. Asa result, mitigation measures were not foreseen ahead of time resulting in project delays.In limited capacitycontexts, a simpler design for calculating cash benefits and monitoring of conditionalities is better than a more complexone. A relatively simple design allows for ease in communicating entitlements to beneficiaries and improves projectefficiency.Social safety net programs are more effective when they address both demand side as well as supply sidechallenges. SSN tend to focus more on the demand side (eligibility, selection criteria, CCTs/UCTs setting up systems todeliver transfers). However, it is equally important to strengthen linkages with the health and education sectors to overcomesupply side challenges and to ensure outcome level results for CCTs.Combining CCTs and IGAs allows for smootherconsumption patterns since poor households do not need to use the IGA transfers to meet their food needs when they arefaced with external shocks (e.g., illness, death of a family member) which undermines their ability to make productiveinvestments.The lesson regarding the inclusion of both refugees and host communities in social protection programsand its impact on peace-building is not supported by any analysis. The information provided is limited to better access tosocial services and poverty reduction for both refugees and host communities (ICR, p. 25).Additional Note: The ICRmissed an opportunity to draw lessons regarding some important aspects of the project such as (1) implementationdifficulties faced in rural versus urban areas and how they were addressed; (2) challenges with working with other Bank-financedprograms to improve supply side aspects (ICR, p. 13) (what worked, what did not, if there were challenges with sequencing,geographical overlap, etc.); (3) implementation challenges due to its multisectoral nature (education, health, social protection)(ICR, p. 16); (4) difficulties in identifying productive opportunities given the indigenous populations nomadic lifestyles (ICR, p.14); (5) the importance of ensuring minimum capacity (by running functional literacy and numeracy sessions in the Likouala region)to improve indigenous peoples understanding of their rights under the project (ICR, p. 12); (6) integrating refugees andhost communities in SSN programs; and (7) targeting predominantly women for IGAs and whether this had any unintendedpositive/negative outcomes.
P145268 | Niger Disaster Risk Management and Urban Development Project | Western and Central Africa | Niger | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099101723111515514/text/P1452680b1bd1d0fe0942001170519115a2.txt | http://documents.worldbank.org/curated/en/099101723111515514/pdf/P1452680b1bd1d0fe0942001170519115a2.pdf | The ICR (p. 30-32) included the following lessons learned, which were adapted by IEG: Improving urbanresilience may require a multi-sectoral approach. This project implemented activities related to flood risk management,drainage, land restoration, water management, urban development, and early warning, preparedness, and response. Also, combiningstructural investments with nonstructural activities such as flood risk mapping and communication, as well as land use planning andearly warning positively may positively impact the sustainability of project outcomes. Including mitigationmeasures that allow for project supervision in FCV environments may be beneficial for achieving positive project outcomes.This project used digital solutions such as GEMS for stronger territorial presence and remote supervision when there was asecurity risk. Hiring project staff, also for regional PIUs, during project preparation allows for a swiftproject implementation start. In this project, implementation experienced several delays due to the lack of regional PIUs.Once the regional PIUs were staffed, implementation took off.
P145275 | Mali - First Recovery and Governance Reform Support Credit (RGRSC-1) | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2015 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/190991525885288349/text/Mali-ML-First-Recovery-Gov-Ref-Sup-Cr.txt | http://documents.worldbank.org/curated/en/190991525885288349/pdf/Mali-ML-First-Recovery-Gov-Ref-Sup-Cr.pdf | The ICR presents the following lessons: To ensure greater impact of a program of reform, DPOs needto be selective and provide a stable and predictable level of support for the reforms and the budget. When tariffadjustments in the electricity sector face political difficulties for their implementation, a strategy to inform the public aboutthe problem and to communicate the importance and reasons for the reform can pave the way for subsequent and more difficultstructural reforms. In post conflict environments, the need for budget support is compatible with meaningful, long-termreforms.This review draws the following lesson: The experience of the programindicates reforms that improve processes (e.g., audit accounts, publishing of EITI reports) are likely to produce the expectedresults. On the other hand, actions affecting special interests are likely to be incomplete (e.g., auditing the payroll system),weakened during program design (e.g., the budget constraint for electricity subsidies) or reversed (e.g., illicit enrichment); insuch cases, the program is likely to fall short of achieving its objectives unless there is a strong political will to carry itthrough. A related lesson is that the design of hard-to-implement reforms is likely to benefit from a deep knowledge of thecountrys political economy.
P145309 | SKILLS DEVELOPMENT PROJECT | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099112123190065658/text/P14530903c5ae30f80b3c406c54e1077f1a.txt | http://documents.worldbank.org/curated/en/099112123190065658/pdf/P14530903c5ae30f80b3c406c54e1077f1a.pdf | The following lessons are a subset of the six lessons presented in the ICR, slightly reworded by IEG to be moresuccinct: Supporting a paradigm shift in the TVET sector from a supply-driven to a demand-drivensystem requires a holistic and transformational project design that is relevant to the countrys context and developmentgoals. In this case,project design included all the needed components and activities to help reshape andtransform the TVET system in Uganda, including: the creation of an autonomous body (TVET Council) with strong private sectorparticipation to inform policies within the sub-sector; SSCs to ensure relevant training for industrial sectors; creation of modelCoEs that could be replicated within the system; and a robust SDF that could provide support for quality trainingon whichenterprises could rely. Strengthening structured linkages between skills development and industry isessential for ensuring labor market relevance for trainees and employers. The success of the SDF and thedevelopment of high-quality training programs were directly linked to the real demands of the labor market.This was achievedthrough the inclusion of a robust communications campaign that provided information on the SDF so that enterprises and employeesknew the SDF was available.Additionally, the short courses, delivered by newly trained trainers and based on competency-basedcourses developed under the project, were developed with strong industry/enterprise input andcollaboration. Close engagement of relevant government structures in project implementation isimportant for ensuring alignment of project activities with the day-to-day government business and priorities in skillsdevelopment.The projects involvement of key relevant directorates and departments in the day-to-dayimplementation of the operation helped build capacity of civil services, enhanced ownership, ensured timely decision-making linkedto key interventions, and facilitated the sustainability of results through the gradual mainstreaming of key activities in planningand budgeting. Communication and marketing of skills development training and its potential for improvingemployment prospects are critical for influencing the public in general, and youth specifically, on the value of technical andvocational education. The project developed a new and robust communication and marketing strategy thatinformed young people of the new competency-based curricula and the opportunities for certification within the TVETsubsector.This strategy succeeded in reaching and attracting young people to access skills development training under theproject and will be expanded under the follow-on project.
P145316 | Dedicated Grant Mechanism for Local Communities Project | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2017 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099203002132326294/text/P14531609153e606f0a86e012ac3d1e656b.txt | http://documents.worldbank.org/curated/en/099203002132326294/pdf/P14531609153e606f0a86e012ac3d1e656b.pdf | The ICR (paras 95-100) presented six lessons. The three notable lessons are included below with rephrasing because these maybenefit future projects related to engaging local communities to enhance sustainable forest management and the REDD+process.Ensuring information is shared with appropriate targeted communities on a timely basis and by the mosteffective means is essential for awareness raising and the engagement with local communities to adopt sustainable practices toaddress deforestation and forest degradation and climate change. The project developed a detailed communication strategywith a multifaceted approach to communicate with and provide training to local communities, including delivering programs throughlocal radio stations, involving a climate change ambassador, using outdoor classes, designing a specific training program forwomen, and using local languages and pictures through training modules (ICR, para 96) through strong collaboration with keyinstitutions at national, regional, and district levels (ICR, para 98). Translating the complex concept of REDD+ and climate changeinto simple messages with pictures of daily actions and real-life examples ensured an inclusion of illiterate people intothe awareness raising and engagement activities (ICR, para 96).Establishing a good information management systemat project initiation can improve efficiency and effectiveness, especially for projects which involve multiple stakeholders withlimited monitoring experience. Insufficient disaggregation of targets for the target population (women, migrants, youth,and people with disabilities) resulted in limited depth in the analysis of thevulnerable stakeholders in project reporting(ICR, para 99). Data on beneficiary satisfaction needs to be disaggregated based on beneficiary groups (different levels oftrainees and grantees) (ICR, para 99). Moreover, the project benefitted from utilizing georeferenced data collection toolsincluding the Open Data Kit software and an interactive voice response platform for ME activities under the COVID-19restrictions (ICR, para 78). The ME system could have been further improved by increasing a flexibility to upload documents,an alignment with the ME criteria for subprojects, and a compatibility with an offline application under limited internetconnection (ICR, para 99).Limited additional financing from the Climate Investment Fund to the countries whichpiloted the Dedicated Grant Mechanism (DGM) projects can affect sustainability of development outcomes. The DGM programdesign document mentioned that the available resource envelope was limited given the complexity of issues and the broadness of thegeography covered (ICR, para 100). Only one out of 12 DGM projects was able to secure additional financing from the ClimateInvestment Fund (ICR, para 100). Given the intensive effort and resources invested in establishing the governance and fundmanagement structures for the project and the potential of the DGM to engage the indigenous people and local communities, it wouldbe a missed opportunity for the structures to be left unused after project closing (ICR, para 100).
P145317 | Maldives: PFM Systems Strengthening Project | South Asia | Maldives | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The lessons are drawn from the ICR. Alignment with government priorities is essential.Successful project design hinges on careful consideration of changing government priorities. In the Maldives,project formulation occurred in an environment of frequent policy changes. Still, it was successfully pursued, aspotentially sensitive PFM reforms were agreed upon early on during project formulation. This was facilitated witha newly elected government in place, a high-level steering committee that included external and government stakeholders; a focus oncommunications and change management; a straightforward design; and long-term on-site technicalsupport. Strategic communications between stakeholders, including the World Bank, is key to change ina PFM reform context. Project activities were most effective in inter-departmental working committee meetings, wheredepartment heads could reach out to stakeholders beyond the Ministry of Finance. The World Bank, in turn, had the opportunityto quickly (and informally), through timely technical advice, influence decision-making
P145335 | Health Services Improvement Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2021 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/099256212232236817/text/P14533509193700c309bff038afc3e01740.txt | http://documents.worldbank.org/curated/en/099256212232236817/pdf/P14533509193700c309bff038afc3e01740.pdf | The ICR (pp. 35-36) offered several lessons and recommendations, including the following lessonsre-stated by IEGReview:Thorough preparation facilitates the introduction of new DLI approaches and optimization of theirbenefits. While incentivizing results through DLIs was lauded, the actual use of DLI mechanisms was unclear to theClients representatives during the early years of the project. This lesson generated an ICR recommendation for a phasedapproach by introducing only a small number of DLIs and developing a well-funded and robust action plan embedding heightenedmanagement focus that may help in building capacity for subsequent scale-up and institutionalization of the newmechanisms.Working with community-based influencers is essential to addressing cultural obstaclesthatinterferewith the goals of improving maternal, neonatal, and child health and nutrition. Many humandevelopment operations have been previously hampered by the lack of appreciation of effective strategies to address socio-culturalissues affecting care-seeking behavior, particularly for maternal services. The project sought to alleviate such issues at thecommunity level by tackling cultural norms thatmight undermine routine child health services, early antenatal care, andattended deliveries, and by strengthening linkages with traditional and religious leaders for addressing socio-cultural issuesaffecting maternal health.Broad ownership by the Client, extending beyond individual counterparts, facilitatessustained commitment and effective implementation. At entry, it was assumed that the enthusiastic engagement of keyindividual sector leaders was a sufficient reflection of country ownership. However, technical leadershipwasnot asengaged, contributing to implementation inertia. Propagating the fact that the project supported Vision 2030 and the Sixth NationalDevelopment Plan may have helped in engaging many additional stakeholders to develop sufficiently wide stakeholder ownership withinand beyond the sector.
P145347 | Trans-Hindukush Road Connectivity Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2016 | 2025 | 2023 | ICRR | >=100 million | Highly Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099062823162527162/text/P145347036607407c095a606ad9b080c08d.txt | http://documents.worldbank.org/curated/en/099062823162527162/pdf/P145347036607407c095a606ad9b080c08d.pdf | The ICR draws the following three lessons from the experience of implementing this project, with some adaptation oflanguage.1. In Fragile, Conflict, and Violent (FCV) situation, complex infrastructure projects involving designand construction are more likely to succeed, if implemented through a series of projects or a multi-phased approach. Thisproject showed that challenges in FCV conditions are much higher when design and construction are packaged under a single project,as it was not possible to determine the costs and logistical needs prior to the detailed design. This necessitated re-engineeringand delays in initiating works.2. Long term Bank engagement is necessary for rebuildinginstitutions inFCV countries. While this project made considerable efforts in strengthening contract administration and the technicalcapacities of the Ministry of Public Works (MPW), the combination of political upheavals, securityand personnel safety risksoutweighed the Banks efforts.3. Adapting Banksprocurementapproaches would help in the FCVcontext. The Banks approach to the procurement of project works in this project did not adequately take into accountthe challenges of delivering works in the Afghanistan context. This resulted in larger packages and pre-qualification requirementsthat precluded most Afghan firms from bidding. The awarded contracts proved unviable as the international firms were unable tooperate effectively in the environment and the project was unable to verify the qualifications of the Afghan sub-contractors.
P145391 | Studies for Sustainable Flood Management | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Water | RETF | IPF | 2015 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/962251565725611587/text/Philippines-Studies-for-Sustainable-Flood-Mgmt.txt | http://documents.worldbank.org/curated/en/962251565725611587/pdf/Philippines-Studies-for-Sustainable-Flood-Mgmt.pdf | The ICR (pages 19-20) draws the following main lessons from the experience of implementing this project, withsome adaptation of language.(1) Capacity building activities should start as early as possibleduring implementation for the Bank team to play a significant role in assistingthe implementing agency. Thisis particularly so when a government agency starts to implement a Bank-financed grant for the first time. Although the Departmentof Public Works and Highways had implemented Bank-financed projects, the managing unit for this study had no experience withBank-funded projects and grants and it took time for the managing agency to become familiar with the financial, procurement anddisbursement arrangements of the Bank.(2)Continuity in Bank leadership can aid in long-termengagement with the clients. This project was prepared by the same Bank team thatassisted in the preparation of thegovernments Master plan. This continuity allowed the team to have a precise understanding of the countryand the sectorcontext for this project.
P145488 | Tuvalu Development Policy Operation | East Asia and Pacific | Tuvalu | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/590911529091090400/text/Tuvalu-Tuvalu-Development-Policy-Operation.txt | http://documents.worldbank.org/curated/en/590911529091090400/pdf/Tuvalu-Tuvalu-Development-Policy-Operation.pdf | IEG agrees with the ICR (para.75) that although limited capacity was factored into the design, it did not consider to theextent necessary the implementation capabilities of the Government. In very limited capacity environments, program design shouldstart with an evaluation of the capacity of country counterparts. The complexity of prior actions and the degree of coordinationneeded between Government departments should be a critical input in determining reform programs. The ICR suggests thatactivities of other development partners need to be fully accounted for in program design. The accounting should incorporate notonly the complementarity of development partner programs, but also the extent to which they utilize scarce Government capacity toimplement their programs. IEG agrees with the ICR that flexibility should be built into the design of DPOs ifcircumstances change, as they did when Tuvalus revenue stream increased because of fishing license fees. IEGsuggests that the continued lack of information on which to monitor progress should have triggered efforts to address the gapsearly in the DPO, rather than later, as evidenced by the ICR indicating that the information that it contains could beunreliable.
P145502 | Technology Center Systems Project (TCSP) | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2014 | 2021 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099051423165536803/text/P145502046aa4e0660b83f0aa2643e9542e.txt | http://documents.worldbank.org/curated/en/099051423165536803/pdf/P145502046aa4e0660b83f0aa2643e9542e.pdf | This ICR endorses three lessons identified in the ICR, which are rephrased below:(i) Projectimplementation readiness matters and needs to be assessed carefully before effectiveness. Thereadiness filters andcriteria instrument need to be used systematically to ensure that each project design matchesthe country and institutionalcontext. Accelerated preparation which does not meetthe country readiness conditions can set the project for failure orundesirable results.(ii) Strong risk assessment and adequate mitigation measures are key to settingtheproject ready to addressimplementing challenges. Underestimating risks during preparation can unfavorably affectproject implementation and outcomes due to insufficient measures put in place to mitigate such risks.A realistic assessmentof risks and putting in place mitigation measures to address these risks will facilitate projectimplementation.(iii)Hard infrastructure and soft outcome arising from TechnicalAssistanceand reformsare key to development and needsequalattention.The Borrowers representativesoften prefer to focus on the hard infrastructure components ofprojects, which they view as more tangible, and may not fully appreciate the importance of technical assistancecomponents. The Bank team needs to ensure that technical assistance componentsare as important as otherinfrastructure components of the project.
P145529 | MA-Rural Water Supply | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099021524164018142/text/P1455291a167e1049193ee1d0c76fed451a.txt | http://documents.worldbank.org/curated/en/099021524164018142/pdf/P1455291a167e1049193ee1d0c76fed451a.pdf | A strong citizen engagement strategy is needed to increase the clients ability to achieve the developmentoutcomes. A lesson learned from the previous BIRD II project was that a strong citizen engagement strategy was needed inthe pre-construction phase to assess the demands of the population related to service levels (standpipe or household connections).This Project applied that lesson, which allowed for citizen feedback and selection of the type of service demanded by thepopulation. Moreover, the engagement processes under this Project helped ONEE deal with land acquisition issues that were needed toinstall the bulk and distribution infrastructure. (ICR, page 26). Replicating processes or interventions from one country toanother just because it worked does not mean it will work in another context. That said, rural water and sanitation projectsworldwide suffer from not having an adequate citizen engagement strategy. This project offers a learning laboratory for otherclients to learn about the key elements of why this approach worked well in the Moroccan context. (ICCRauthor) The OM model based on Gardien Grants offers a potential model for piloting and replicationin other projects. There are certain characteristics unique to the Moroccan context for why the GardienGrants (GGs) model may be working. The water systems serving the rural populations are not decentralized systems butcentralized and managed by a large provider with technical capacity (ONEE). The agreement between ONEE and the localauthority is that the local authority will select a GG that will be responsive to the population. This agreement between these twoentities and the GG strengthens the compact between a central provider, a local government authority, the GG, and the population.Each standpipe is metered and if the GG does not pay their water bill to ONEE, ONEE will shut off the supply. (Interview with ICRauthor). This institutional commitment by ONEE to enforce its billing and collection increases the accountability of the GG tooperate and maintain the standpipe and in turn charge for their services. Sustainability of rural water systems worldwide has vexedgovernments and financing institutions for decades. The GG model in Morocco offers an opportunity for others to learn what elementsmay be applicable to other contexts. (ICRR author) The hiring of a technical assistance firm to support theproject implementing agency could benefit supervision, operation and maintenance, and participatory approaches throughoutimplementation. ONEE has high technical capacity to design and build infrastructure but is less adept with managingsocial processes in rural areas. (Interview with TTL.) The decision to hire a technical assistance firm with qualified staff tohelp with pre-investment processes, construction and post-construction OM processes was a key factor in ONEE achieving thedevelopment objectives. When client technical counterparts lack the skills on these social elements, this project can serve as alearning laboratory for Bank TTLs who are looking for potential ways to strengthen their clients capacity. (ICRRauthor) The Banks long-term engagement with the client in a specific sector could enhance prospects for implementation success. Previous projects such as BIRD II were not successful, but the Bank looked at whatdidnt work and made explicit changes to the approaches and incorporated those into the design of this project. The GG modelscaled up under this project was originally piloted under a predecessor project BIRD I. Although BIRD II was not successful, BIRDIV built on previous lessons from BIRD I and II and scaled them up. Without the learning from previous experiences in the Moroccancontext, BIRD IV would not have benefited from the previous successes and failures in the Moroccan context.
P145533 | China Contaminated Site Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099111124125029548/text/P145533-b1b7b21d-474f-464e-a477-fa6291acbc3e.txt | https://documents.worldbank.org/curated/en/099111124125029548/pdf/P145533-b1b7b21d-474f-464e-a477-fa6291acbc3e.pdf | The following lessons have been drawn from IEG:When indicators to measure behavioral changes and increasedperformance of public officials are lacking it is not possible to measure to what degree performance is changing, in order toassess the improved management capacity of the institutions. In this project, indicators in the RF measured the productionand availability of guidelines, policies and training materials, but failed to measure the changes in behavior (the applied newskills) that would better show the changes in the capacity among officials and other stakeholders, regarding the approach ofrisk-based analysis for site remediation.When target values are lacking in the Results Framework, it is notpossible to assess project success as the degree of project achievement cannot be compared to target values. In thisproject, relevant target values for output indicators were not set and neither updated during implementation. This made it notpossible to assess project achievement against targets.The following lessons from the ICR (rephrased) are consideredparticularly relevant:Balancing technical, economic, and social dimensions of the project can increase theprobability of success of remediation approaches. The remediation of contaminated sites is a complex environmental issuethat requires the consideration of the trade-offs. The implementation of stakeholder engagement appeared essential to ensure timelyremediation and build trust within the population toward the remediation plan. Similarly, the ESMP has proven an efficientinstrument to effectively avoid or mitigate potential social conflicts.Ongoing audits and controls during theremediation process cancontributeto building a demonstration effect. It was in the pilot nature of thisproject to allow for flexibility and changes in the technical approaches selected for site remediation. Due to the controls on thecounterpart side the inspections revealed important data (on levels of contamination, for instance) that allowed for reconsideringthe approaches and to learn from the process.
P145534 | MM: Telecommunications Sector Reform | East Asia and Pacific | Myanmar | IDA | FCS | Digital | Digital Development | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/099121323185020629/text/P145534070bfe50a7081d6083da3608d793.txt | http://documents.worldbank.org/curated/en/099121323185020629/pdf/P145534070bfe50a7081d6083da3608d793.pdf | The ICR draws the following two lessons from the experience of implementing this project, with some adaptation oflanguage.1. Designing project components that are aligned with the implementation capacity is especially importantin fragile settings.The experience of this project is that project implementation may be undermined by limitedpersonnel and excessively bureaucratic government systems. The lesson is that task team working in fragile settings need to have aclear understanding of the possible constraints that can significantly influence the outcome.2. Given thedifficulties of measuring the effectiveness of a policy reform, it may help to have a conceptual framework or a composite index tomonitor the outcomes. Moreover the targetsmay have to be frequently reassessed in a fragile setting wherecircumstances can rapidly change.
P145544 | Early Childhood Education Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Human Development | Education | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099621304262225878/text/P14554402675f70d60a3c40cc6abc65ac18.txt | http://documents.worldbank.org/curated/en/099621304262225878/pdf/P14554402675f70d60a3c40cc6abc65ac18.pdf | The ICR (pp. 37-38) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:The introduction of new concepts in development projects requires time to be understood bystakeholders. Under the project, the concept of Community Child Development Groups and Multi-Age Teaching took time to beadequately appreciated by key stakeholders in both the public sector and the community. Related delays necessitated a totalimplementation period of seven years and indicated the need for more realistic timetables to implement unfamiliarconcepts.Scholarships constitute important incentives to teacher-trainees from hard-to-reach areas to becomepre-primary schoolteachers and to be deployed in remote schools. The project trained 200 ethnic girls as pre-primaryschoolteachers through both short- and long-term scholarships.Early childhood education has multi-sectoraldimensions. Coordination and collaboration among sectors, stakeholders, and communities facilitated progress made in earlychildhood education in the country.Teams of the Department of Education and Sports collaborated with their peers in othersectors, notably the Ministry of Health, the Department of Finance, and the community. The project also benefited from internalcollaboration among departments of the Ministry of Education and Sports: District Education and Sports Bureau, Department ofInspection, Department of Planning, Department of Pre-Primary and Primary Education, and Department of Teacher TrainingEducation.
P145545 | Enhanced Road Access Project | East Asia and Pacific | Samoa | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099092923183023944/text/P14554508c0c010c40aacb0c1ec55d08395.txt | http://documents.worldbank.org/curated/en/099092923183023944/pdf/P14554508c0c010c40aacb0c1ec55d08395.pdf | The following main lessons can be drawn from the experience of implementing this project. In smaller and highlyexposed economies, using a thematically structured yet flexible project design like ERAPs PDO could be more effective inaccommodating potential changes. A relatively broad PDO can offer flexibility to address emerging needs that could come up duringimplementation. Having such flexibility in this project, allowed for the addition of various infrastructure components to ERAP,such as the Maliolio Bridge and access road, three water crossings on Upolu, and WCR Lot 2b during itsimplementation. This was possible as the PDO for ERAP was not too restrictive by focusing on critical roads and bridges inSamoa. A design-phase road safety audit can help avoid extra cost and time for resolving road safety issues thatmay be identified after construction. A post-construction audit in March 2021 identified high-risk safety concerns with culvertdriveways on WCR, leading to an extension of the project closing date to rectify and address this issue. While this contributed toimproving road safety on WCR, it resulted in both rectification costs of US$0.49 million and an 18-monthextension. Intensive implementation support and sufficient budget allocation may be required for enhance the success ofemergency operations. While the World Banks prior engagement in Samoas transport sector helped put in place thefoundations for quick preparation of the emergency ERAP project, challenges including slow design progress, performance issues withthe PMC, and staff changes led to a 45-month timeline from Board approval in October 2013 to the opening of Leone Bridge in July2017. Large infrastructure projects, particularly emergency projects such as the ERAP, are often developed within tight timeframes.In such cases, certain project details may need to be refined during implementation, underscoring the need for robustimplementation support and adequate funding.
P145554 | DRC:Financial Infrastructure and Markets | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/319841637289330774/text/Congo-Democratic-Republic-of-DRC-Financial-Infrastructure-and-Markets.txt | http://documents.worldbank.org/curated/en/319841637289330774/pdf/Congo-Democratic-Republic-of-DRC-Financial-Infrastructure-and-Markets.pdf | Three lessons are drawn from the Implementation Completion Report (page 21), with some adaptation.Dollarization presents an opportunity to leverage Bank fundstomobilizeprivate capital for lending tomicro, small and medium enterprise. In this project, the USdollar line of credit was highly valuable to banksand other financial institutions in the Democratic Republic of Congo, where the US dollaris the primary currency used insettling financial transactions. The Bank could have used this opportunity to require co-financing by the participatingfinancial institutions in theline of credit operationthat aimed to provide term financing to micro, small and mediumenterprises. The strategy would have been feasible, according to the Implementation Completion Report, because of the highlevel of dollarization of the economy. This project, however, did not require co-financing by the participating financialinstitutions which could have mobilized savings in the economy, including US dollar savings,for term lending to micro, smalland medium enterprises..Adherence to international Anti-Money Laundering/Combating the Financing ofTerrorismstandards isvital to the successful operation of national payments systems, particularlypayments systems that process multiple currencies. In this project, the Banque Central du Congohalted thesettlement of USdollar transactions in the real-time gross settlement systemand the automated clearinghouse system uponthe request of the U.S. Department of the Treasury. The mutual evaluation report prepared by the Groupe dAction Contrele Blanchiment dArgent en Afrique Centrale, based on a mission in August 2018, found theDemocratic Republic ofCongoto be non-compliant with 15 of 40 Financial Action Task Forcerecommendations.According to thereport,the countrysAnti-Money Laundering/Combating the Financing of Terrorismsystem remained relativelyineffective, despite the commitment of the political authoritiestherewere notable shortcomings in theimplementation of key mechanisms including national coordination, the definition of a supervision policy emphasizing the risk-basedapproach, and the supervision of financial institutions and designated non-financial businesses and professions. Futurefulfillment of the Financial Action Task Forcerecommendations couldhelp unlock the real-time gross settlement andautomated clearinghousesystems to US dollar transactions settlement.The costs of complex informationtechnology systems for a national payments infrastructure can be easily under-estimated and must be rigorously calculatedandevaluated. In this project, the cost of theNational Payments Card Retail Switch was far higher than originallyestimated. The number of institutions that had to be connected to the system and their willingness and capacity to conductthe system integration activities were easily overlooked. The much larger scope of the customization that was required raisedthe cost of developing and deploying the information technologyinfrastructure.
P145578 | MX Oaxaca WSS Sector Modernization | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Water | IBRD | PforR | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/099430006142227582/text/P145578048c3cc06e092320cd62e8f8fccc.txt | http://documents.worldbank.org/curated/en/099430006142227582/pdf/P145578048c3cc06e092320cd62e8f8fccc.pdf | The ICR (pgs. 29 to 30) lists a number of lessons from which IEG derives the following lessons that are relevantforsimilar projects implemented in comparable environments:1. Program design needs to be closely alignedwith the clients implementation capacity and readiness: This was the first PforR to be implemented inMexico, and only the third in the Latin America (LAC) region. Given the capacity level available to implement such aninstrument at the subnational level, as well as the inherent complexity of the institutional arrangements needed to coordinate thefiduciary and financial mechanisms at State and financial levels, the Program would have benefited from a more thorough financialand fiduciary viability assessment to ensure that FM mechanisms and institutional frameworks were in place at appraisal. Thekey lesson arising is that, for PforR operations, the Bank needs to conduct a more rigorous due diligence process for operationswhere State-level capacity is uncertain or limited, and secondly, to ensure that on-lending arrangements and policy frameworks areconducive to the proposed instrument, confirmed by appraisal and possibly through a requirement framed as a condition ofeffectiveness.2. In countries and/or States with limited implementation capacity, inclusion of a TechnicalAssistance component can play an instrumental role in ensuring the success of the PforR: The multi-annual TAcomponent originally included in the Oaxaca WSS PforR was important to ensuring strategic and oversight support. Thecancellation of the component impacted the achievement of the Programs objectives, especially for those activities designedto support capacity-building and knowledge transfer within beneficiary institutions, such as the Rural WSS Strategy and the WSSPublic Expenditure Review.3. For PforR Programs, hiring of an IVA Verification Agent should be aneffectiveness condition: The hiring of the IVA Verification Agent was delayed by two years, on account of theinitial delays in signing of operational documents and the need for amendments of the Subsidiary Agreement and the OperationalManual. This impacted the disbursement rate of the Program as no disbursement was able to process without going through averification cycle by the IVA. Given that disbursements under PforRs are normally linked to the achievement of specificresults, which call for independent verification, it would make sense to ensure that the hiring of an independent agent for thistask is made an effectiveness condition, so that delays in disbursement do not take place on this account.4.A strong commitment of the State and Federal agencies is critical for the successful implementation of a subnational PforRoperation. In the case of the Oaxaca WSS PforR operation, the GoO was able to mobilize some funds to meet a portionof the requirements of the cancelled TA component. Likewise, CONAGUA worked closely with the GoO to co-finance sub-projects andinfrastructure investments, and to provide critical technical support. Despite facing the negative impacts of naturalemergencies, such as earthquakes and the Covid-19 pandemic, the GoO and CONAGUA demonstrated a solid commitment to expediteimplementation and meet the DLI targets on time.
P145585 | SENEGAL - Skills for jobs and competitiveness | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099435002142217129/text/Senegal000Skills0development0TVET.txt | http://documents.worldbank.org/curated/en/099435002142217129/pdf/Senegal000Skills0development0TVET.pdf | The ICR (pp. 36-37) provided several key lessons, some of which are elaborated here:Strong public-privatecollaboration lies at the core of development and maintenance of relevant skills training programs. In this project, theinvolvement of the private sector in Boards of Directors, delivery of skills training, and financing the 3FPT contributed to designand implementation of interventions that were responsive to the needs of the economy for skilledmanpower.Performance-based contracts can be an important mechanism to improve dialogue, transparency,and monitoring of TVET institutions. The use of PBCs in this project facilitated negotiation of annual budgets of TVETinstitutions based on targets and results, shifting the management culture of these institutions from an input-based orientation toone focusing on outcomes.Tracer studies are essential for understanding the effectiveness of activities andpolicies. This projects design included tracer studies that produced valuable information on student activitiesfollowing completion of short-term skills training. The data revealed challenges with insertion rates that helped inform areas forimprovement moving forward.IEG adds one additional lesson:Confronting sensitive politicaleconomy issues up front can avert potentially costly issues and delays during implementation. In this case, identificationand resolutionof possible stumbling blocks such as textbook selection, as well as deliberateconsultation with multiplestakeholdersduring project preparation, allowed the project to escape some risks that were identified at appraisal.
P145586 | China Partnership for Market Readiness | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2014 | 2021 | 2021 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/634041624539875107/text/China-China-Partnership-for-Market-Readiness.txt | http://documents.worldbank.org/curated/en/634041624539875107/pdf/China-China-Partnership-for-Market-Readiness.pdf | The following two lessons in the ICR stood out as important and relevant to other projects on carbon emissions trading scheme(ETS) and are presented here with some editing. A clear political mandate and legal basis was the key toensuring aneffective ETS design. The Governments commitment to develop the national ETS was expressedstronger in the 13th Five-Year Plan (FYP, 2016-2020) compared to the preceding FYP, as it provided a detailed ETS plan andindicated the need for the rules and regulation to manage trading. The projects data collection and analysis supportednational GHG control targets in the 13th FYP to be disaggregated for the provinces. The Government also included the development ofthe national ETS as a target in the Nationally Determined Contribution. The fact that the national ETS was referenced as a policypriority in those top-level policy planning documents signaled the strong political commitment, which enhanced inter-ministerialcollaboration and buy-in from stakeholders. The project also facilitated high-level policy dialogue in the United Nations FrameworkConvention on Climate Change, that built momentum and traction for the national ETS development. High-level meetings between theBank and the Ministry of Ecology and Environment further confirmed the strategic importance of this project in supporting the ETSdesign. Widespread stakeholder engagement and capacity building was critical for confidence building, datacollection, and policy design. Relevant ministries, industry associations, and enterprises were engaged throughout theproject duration to raise awareness on the functions of an ETS. Capacity building at the local level ensured effectiveparticipation in the ETS design, especially for regions that were not covered by the pilot ETSs. There was a wide range ofcomplementary initiatives on capacity building led by other development partners such as the European Commission, the German Agencyfor International Cooperation, and the Asian Development Bank, as described in detail in the ICR (Annex 8, page 52-57). The projectensuredclose coordination with them to avoid overlapping in development initiatives and maximize impact of theproject.
P145605 | CO: Enhancing Fiscal Capacity to Promote Shared Prosperity DPL | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | DPF | 2014 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/695451473934841290/text/ICRR14949-P145605-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/695451473934841290/pdf/ICRR14949-P145605-Box396299B-PUBLIC.pdf | The ICR draws a familiar conclusion about the importance of respecting the borrower's priorities to ensure ownership and commitment. At the same time, the Bank has helped shape Colombia's approach to equity and poverty issues through analytical work and policy dialogue, not least through a high level workshop building consensus for the DPL's program.When the opportunity arose, the Bank was able to respond quickly because of its multisectoral capacity and a deep well of country specific knowledge. However, where the reform agenda exceeds the scope of a single operation, the Bank must be prepared to sustain an engagement over the longer term.Finally, the ICR notes an important synergy in the operation between governance reforms (access, transparency) and structural objectives (poverty reduction, equity).
P145610 | Peru Lima Metro Line 2 Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2020 | 2021 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/493971624280043388/text/Peru-PE-Lima-Metro-Line-2-Project.txt | http://documents.worldbank.org/curated/en/493971624280043388/pdf/Peru-PE-Lima-Metro-Line-2-Project.pdf | Following lessons are adapted from the ICR: Entering a project that has already been structured,procured, and awarded can significantly constrain theBanks ability to influence the initial design and risk mitigationmeasures to support implementation. In the case ofMetro Line 2, the project design was approved by the Government ofPeru andthe Concession Agreement was awarded, and other IFIs had approvedloans prior to the Bank concluding itsappraisal. As a result, the Banks ability to influence key project design decisions wasseverely limited and theprimary risk mitigation measures remaining were legal covenants and loan conditions. Thisimpacted key areas of projectimplementation from the development of final engineering designs to the implementationof the Banks safeguardpolicies. Complex projects that involve private concessions or public-private partnerships requiregreater institutionalcapacity and coordination from Government. Deficiencies in the Borrowers legal andtechnical capacity to proactivelymanage concession agreements can negatively impact project implementation. For example,in the case of Metro Line 2, theBorrower procured the works and assigned the concession using a semi-detailedsocial and environmentalassessment and required that specific management plans be developed by the Concessionaire andapproved in phasesonce detailed engineering designs would be finalized. The Bank considered the Project as a CategoryA under itssafeguard policies and required the Borrower to supplement and/or implement (or cause the Concessionairetoimplement) the Projects safeguard instruments accordingly. However, the Concession Agreement was not abletoresolve differing interpretations between the Borrower and Concessionaire in the implementation oftheserequirements. It isimportant to have a defined organizational structuretocoordinatebetween multiple international financial institutions (IFIs) during project implementation. TheMetro Line 2 Project was co-financed byseveral international financial institutions (IBRD, IDB, CAF, andKfW). Theco-financiers joined the project at differenttimes (in the case of the World Bank, after the Concession Agreement wasawarded) and did not have the opportunityto formalize acooperation agreement or designate a lead Bank, as was done inthe Quito Metro Project with the IADBand other co-financiers. A defined organizational structure for the coordination of thelenders would have beenbeneficial for project implementation and could have allowed for more leverage for the implementationof IFIsrequirements and project supervision on socio-environmental safeguards.
P145617 | PK Sindh Public Sector Management Reform Project | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099755106092222136/text/P1456170f54cb00dd08f7b0e931f3f33a40.txt | http://documents.worldbank.org/curated/en/099755106092222136/pdf/P1456170f54cb00dd08f7b0e931f3f33a40.pdf | The following lessons are drawn from the ICR.Understanding the political context risks and potentialmitigating measures is as important at sub-national as national levels. Difficulties that arose duringimplementation of the Sindh project notably ones related to meeting targets could not all have been forestalled,but some might have been alleviated with a better understanding of the regional governments mandate: when it comes toadopting measures to enhance tax revenue mobilization, strengthen the performance of PFM systems, the management of the developmentportfolio, and the strengthening of the public procurement system, an understanding of the limits of sub-national autonomy iscritical. In the case of the Sindh project, the realism of at least some of the targets set for the project might have beenbetter achieved with a more thorough understanding of the constraints in the political economy.Early projectrestructuring can turn around an initially non-performing project.Bank teams often wait until the mid-term review tocomprehensively assess project performance when an earlier restructuring might avoid implementation difficulties and delays.It may not salvage non- or weakly performing components, but it might nevertheless be meaningful in salvaging and allowing arefocus on other better-performing components.
P145618 | MEXICO Sustainable Energy Technologies Development for Climate Change | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/639611634917667521/text/Mexico-MX-GEF-Sustainable-Energy-Technologies.txt | http://documents.worldbank.org/curated/en/639611634917667521/pdf/Mexico-MX-GEF-Sustainable-Energy-Technologies.pdf | This review has drawn two lessons incorporating material in section 5. Lessons and Recommendations of theICR.Lack of local governments commitment to a project can adversely affect the achievement of projectobjectives if projects implementation depends on the endorsement of the same local governments. Through technicalassistance, the project successfully completed the RNAs and CERIPs. The 32 autonomous states were to implement these CERIPs.However, at appraisal, SENERs limitations in obtaining local governments commitment to the project and theimplementation of CERIPs was not adequately assessed. During project implementation SENER could not obtain the autonomousgovernments endorsement; hence, the subprojects identified in the CERIPs could not be implemented, and the project objectiveto improve the institutional capacity of ACE technology institutions, both private and public, could not beachieved.A reduction in the project scope without a revision of the project objectives can create gaps in thetheory of change resulting in project activities not supporting the achievement of the project objectives. When theproject scope was decreased from publication and implementation of CERIPs to only the publication of CERIPs, this weakened theprojects theory of change and created gaps in the result chain that did not support the achievement of the project objectiveto improve the institutional capacity of ACE technology institutions both public and private. The implementation of the investmentsand strategic actions identified in CERIPs was to boost human capital in science and technology and entrepreneurial disciplinescritical to commercialize ACE technologies. Since the project scope was reduced to the publication of CERIPs, the projectsintervention could not support the achievement of the project objectives, which depended on the implementation of investments andstrategic actions.
P145621 | Sustainable Production Systems and Conservation of Biodiversity | Latin America and Caribbean | Panama | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/174991619105540871/text/Panama-PA-Sustainable-Production-Systems.txt | http://documents.worldbank.org/curated/en/174991619105540871/pdf/Panama-PA-Sustainable-Production-Systems.pdf | The ICR (p. 26-27) provided several useful lessons learned, which were adapted by IEG, and are likely to be relevant to othersimilar projects: Seed financing by donors for a conservation financing mechanism can be leveraged togenerate a much larger fund if the government is supportive. In this project the Endowment Fund (EF) increased from US$1.5million to more than US$20.3 million within the projects implementation period. The project team was able to demonstrate therelevance of biodiversity and natural resources and build trust to establish ongoing revenue streams for conservation financing.Also, diversifying financing sources for the EF provides flexibility in case one financing contribution doesnotmaterialize. In this project, one company did notend up making its financial contribution. However,since the project had identified several, diverse financing sources, the loss of one financing source did not have a detrimentalimpact on project outcomes. Private investment can generate sustainable biodiversity benefits. In thisproject, the Coffee Route (a public-private eco-tourism partnership between local coffee producers and the Local Tourism AuthorityNational Network of Private Reserves Project) demonstrated to MIAMBIENTE and MIDA that private individuals are interested ininvesting their own financial resources in biodiversity conservation when the investments result in livelihoodbenefits.
P145634 | Second Phase of the Central Asia Road Links Program | Europe and Central Asia | Central Asia |  |  | Infrastructure | Transport | IDA | IPF | 2015 | 2021 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/948781623290014878/text/Central-Asia-Central-Asia-Road-Links-Phase-2.txt | http://documents.worldbank.org/curated/en/948781623290014878/pdf/Central-Asia-Central-Asia-Road-Links-Phase-2.pdf | The ICR (pages 26 -27) draws the following main lessons from the experience of implementing this project, presented with someadaptation of language.1. When implementing projects with a new client and in the context of the weakimplementation capacity, the project design needs to be simple. The design of this project was simple and straightforwardto be implemented by the Ministry of Transport and the Project Implementation Group.2. In the face of morefrequent and intense climatic events occurring in the region, the design should include climate resilient infrastructure tominimize vulnerability of the physical assets. While this project was being implemented,glacial melting along withprolonged and heavy rains caused mudslides and flooding throughout Tajikistan. The cross-coordinated work on the climate resilientinfrastructure by the Ministry of Transport, Ministry of Emergency and other bodies was key in responding to these climaticevents.3. A road investments impact on economic growthoften depends on a variety of factors external tothe road investment, making the theory of change complex and challenging to validate through an evaluation. The lessonfrom this project is that in addition to the improvement of physical connectivity, important institutional reforms on trade andtransport facilitations through cross-border measures are required to complement the physical connectivityissues.4.The long term impact of road safety measures could be undermined due to lack of enforcement of roadsafety regulations. Although road safety measures were incorporated into the design of the roads underthis project,theresults of the beneficiary surveyidentified road safety as a major concern. This highlights the need for enforcingroad safety strategy and mechanisms for enforcing road safety regulations in road sector projects.
P145686 | AR Flood Risk Management Support Project for the City of Buenos Aires | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2016 | 2024 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061724181536730/text/P145686-e1838413-ce56-49d9-92ab-ad664a09a45a.txt | https://documents.worldbank.org/curated/en/099061724181536730/pdf/P145686-e1838413-ce56-49d9-92ab-ad664a09a45a.pdf | The Banks long-term engagement with the client can enhance prospects for implementation success.This project built on previous Bank engagement and adjusted the design by incorporating lessons learned from previousin-country experiences. Notably, the project moved beyond building infrastructure to also investing in flood warning systems,education programs, and capacity building at the community level for emergency response. The comprehensive approach andlong-term relationship demonstrate that the thinking of the client and Bank evolves over time to address challenges that willimprove sustainability and resilience. The Banks Multiphase Approach (MAP) can serve as an appropriate mechanism whendealing with development problems and reforms that span multiple project cycles. Limited Bank staff turnoverduring implementation can allow trust to be built with the client and can have a positive impact on implementation success.The Bank team had one local TTL be part of the design, implementation, and completion, which can allow for trust todevelop between the Bank team and client. Difficult implementation challenges and the need to make quick course corrections can beinfluenced by the level of trust and quality of relationships between the Bank and the client. These relationships go beyondone project cycle. As this project showed, the thinking by the Bank team and the client evolved over time and took a morecomprehensive approach to ensure sustainability and resilience. There was limited Bank staff turnover among the extended teamas well such as the environmental and social specialists which proved important for the success of a large scale, high risk, andcomplex project. A strong citizen engagement strategy is needed to increase the clients ability to achievedevelopment outcomes. This project demonstrated the impact of having a strong citizen engagement and education program aspart of the design. This is particularly important in flood mitigation projects that rely on the communities input notonly for planning, but also for participation in risk reduction activities including early flood warningsystems. Combining green and grey infrastructure can provide a holistic and resilient approach to floodmitigation infrastructure investments. Historically flood mitigation has depended on grey infrastructure to improvedrainage and increase basin flow capacity to evacuate excess runoff. This strategy is an essential part of flood mitigation, butthis project demonstrated that incorporating green infrastructure can be equally as important. Repurposing public lands suchgreen areas or parks to allow for runoff retention can reduce peak flows, improve ground water availability, and provide cheaperand cost-effective solutions for city-wide flood management and climate strategies.
P145699 | Strengthening Social Safety Net Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2015 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | https://documents.worldbank.org/curated/en/099093024143511513/text/P145699-cc9bf63f-35a3-4f77-9189-68d12ef4855a.txt | https://documents.worldbank.org/curated/en/099093024143511513/pdf/P145699-cc9bf63f-35a3-4f77-9189-68d12ef4855a.pdf | The ICR (p. 42-44) provided several lessons, a selection of which are restated below.A strong technicalassistance program contributes to solid design of a project. Prior to this project, the World Bank had an extensivetrust-funded technical assistance (TA) program (Energy/Social Safety Nets Sector Reforms Technical Assistance Project, P144305).This TA supported the social safety net reforms, as well as the design and launching of the UNR and of the TKP. This allowed theproject to start implementation early on, as opposed to spending the initial period creating the necessary instruments to moveforward with a cash transfer program. In addition, the TA established a dialogue with counterparts, facilitating the relationshipwith the client.Cash transfer programs contribute to human capital development as long as quality health andeducation services are available. This project built on global experience that showed that cash transfer programscontribute to improvements in health, nutrition, and education outcomes by stimulating demand for these services. This projectfaced significant constraints in terms of the quality, cost, and proximity of services, as well as shortcomings in the availabilityof data from schools and public health facilities. As a result, enforcement of conditionalities was a majorchallenge.The introduction of an economic opportunities program can sustain the impact on poverty of cash transferprograms. As part of the additional financing, the Forsa program was included as a pilot. The focus was on providing wageand self-employment opportunities to TKP beneficiaries who were about to graduate from the conditional cash transfer program. Thepartnership with NGOs and private companies facilitated implementation of the pilot, as the MoSS did not have the capacity toprovide the necessary services to beneficiaries.The use of a results-based disbursement mechanism cancontributeto the achievement of outcomes. As designed under this project, DLIs focused on specific outputs along theimplementation processes of the PMT, MIS, TKP and Forsa. This motivated the client to focus on achieving outputs to accessdisbursement.The DLIs also provided an additional layer of monitoring progress towards the PDOs.Improvementsin technology can facilitate the implementation of cash transfer programs. As the project progressed, severaltechnological improvements were made to facilitate implementation, monitoring, and communications. For example, originally thenumber of days in which funds would be available in beneficiaries accounts, after payment due date, was 10 days. Thanks tothe implementation of the debit card, access to funds was immediate. The MIS enabled automated end-to-end business processes,reducing manual work and human error. Linking the Unified National Social Protection Registry to the UNR enhanced dataverification, targeting, and transparency. The use of social media and UNICEFs RapidPro app facilitated two-waycommunication with beneficiaries and the public, as well as program monitoring.
P145741 | Ghana Secondary Education Improvement Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099140002222311308/text/P1457410276d560470ae3702a97efa81157.txt | http://documents.worldbank.org/curated/en/099140002222311308/pdf/P1457410276d560470ae3702a97efa81157.pdf | The following lessons are a subset of lessons presented in the ICR, slightly reworded by IEG to be moresuccinct: The RBF approach supports a results focus, and can also incentivize Borrowers to adoptefficient implementation practices and offer flexibility to respond to new challenges. RBF kept discussions withgovernmentcounterparts focused on results rather thaninputs.Process-related DLRs helped improve implementation ofcivil works activities, including adherence to needs-based district and school selection processes and to pre-constructionrequirements.RBF design allowed flexibility to leverage financing for a more robust rollout of iCampus to provide a distancelearning option for SHS students during COVID. Given the governments commitment to steering morestudents into science, technology, engineering, and mathematics (STEM) fields, the hiring of more and higher quality math andscience teachers, especially females, and their equitable distribution and effective use are key. Project studies onmath and science teaching and learning point to the need to: reassess the syllabi for these subjects; strengthen teaching andlearning at the basic level to improve student preparedness entering SHS; carry out more group and practical work learningactivities in the classroom; and develop and implement a national policy on teaching at the SHS level, with follow-up teachertraining for ongoing improvement. More attention to consultation, capacity building, and communication in thedesign and implementation of initiatives is likely to enhance actors and stakeholders understanding anduptake.The beneficiary survey revealed that many teachers reported that they were not part of the SPP planningprocess and pointed to the need to be more inclusive in the development process, including the presentation of SPPs to teachers fortheir input before finalization.The 2021 fiduciary review identified specific areas for capacity development, includingbookkeeping training for head teachers and the conduct of monthly inspection reviews of school records.Most beneficiarysurvey respondents were unaware of the school digest or the school mapping portal, andsimilarly, the uptake of the iBox couldhave been improved through greater communication. Scholarships and bursaries for secondary education can serve asa useful policy tool to improve social outcomes, particularly for girls and women.Recent experimental evidence fromGhana on the impact of secondary school scholarships on education, health, and employment outcomes make a strong case forcontinuing to use this tool to support vulnerable students and reveals that scholarshipsdo incentivize girls with the abilityto succeed academically to choose to go to SHS.IEGs review offers an additionallesson: Gaps in a projects theory of change expand the risks of missed opportunities to incorporatecritical assumptions, interventions, outputs, and intermediate outcomes and indicators that enhance prospects for the success andsustainability of investments. Criticalgaps in this projects theory of change for improving education accessand quality were the absence of any contribution fromteacher recruitment to accommodate the significant increment in newstudent places (and the financing source); trends on classroom size and student-to-teacher ratios; and non-financial obstacles togirls access to secondary education (see Section 4).
P145747 | DRC: Strengthening PFM and Accountability | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099131502082328385/text/P145747025b2750bf0837500b135cdb3adf.txt | http://documents.worldbank.org/curated/en/099131502082328385/pdf/P145747025b2750bf0837500b135cdb3adf.pdf | Staying the course.. Objectives need to be realistic, and the Bank needs to stay committed over thelong term. In this case, PFM and governance were critical Bank priorities over two CPF periods, despite unevenprogress. While IGF was initially slow in responding to Bank support, it then gained political support and IGF became highlyeffective.Reliance on PEFAs to monitor and measure results can sometimes not be appropriate and isrisky. In this project, the Bank set PEFA indicators at too high a level to accurately trackproject results.They were replaced by indicators that could be more directly attributed to project activities and allowed continuedmonitoring for real-time course corrections. Without upfront assurances that subsequent PEFAs will be undertaken, they arenot useful for monitoring or to inform course correction.Sensitive reforms may be facilitated through acombination of policy and investment lending.Changing reform areas such as revenue management can be difficultto address with investment operations alone. In this project, authorities made little progress in procurement reform withoutappropriate regulation.
P145764 | Zambia:-Health Results Based Financing Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2011 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/860431468141564936/text/ICRR-Disclosable-P145764-06-22-2016-1466613291484.txt | http://documents.worldbank.org/curated/en/860431468141564936/pdf/ICRR-Disclosable-P145764-06-22-2016-1466613291484.pdf | These lessons are drawn from the ICR.Behavior change interventions and community involvementcan persuadehouseholds to actually use ITNs, and to know when to seek care and actually access care when needed, but more work isneeded to know how best to design and implement interventions to achieve thedesired behaviors. The MIS and DHS assessed theextent to which ITNs were actually used by household members, and found significant gaps between net ownership and use.Distribution of nets is not enough, and it makes sense to include a demand-side intervention, such as the community grantmechanism, to elicitappropriate behaviors. However, more thought needs to go into design, implementation andmonitoring.Interventionsare most successfullyimplemented by people who understand theirpurpose and have a vested interest in the outcome or have some other incentive to perform well and appropriatelymonitor and assess impact. The initial decision to have the AIDS team administer the small grants was logical. They had therelevant experience, procedures, and infrastructure (transport, etc.),and it would have been costly and inefficient totryto set up duplicate capacity in the NMCC. However, the AIDS team lacked motivation and understanding to ensure that themalaria grants were as effective as the HIV grants.Results-based financing is complex todesign and implement well, and so it makes a lot of sense to proceed in careful stages, and learn and adjust along the way. Thisproject is a good example of a staged approach. Itbegan with a pre-pilot in one district, then a full pilot thatincluded a limited set of outcomes and facilities and careful evaluation that could offer experience to use for a decision onwhether to adopt the approach widely.
P145765 | Ghana Climate Innovation Center | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/803131629717241563/text/Ghana-Ghana-Climate-Innovation-Center-RE-P1457.txt | http://documents.worldbank.org/curated/en/803131629717241563/pdf/Ghana-Ghana-Climate-Innovation-Center-RE-P1457.pdf | The ICR (p. 26-28) provided several lessons learned which were adapted by IEG: Business incubation andsupport is costly, challenging and takes time until results show. In this project, capacity staff for GCIC and GCVF had tobe recruited and trained, which was a lengthy process and resulted in delays. Planning for sufficient implementation time iscritical for achieving the desired outcomes. Collaborating and active communication with the private sectoris critical for improving the business environment and supporting entrepreneurs in climate technology sectors. Thisproject collaborated with several different stakeholders including development partners, ministries, and implementing institutionswhich resulted in broad public impact. Ensuring flexible and responsive project implementation is critical forovercoming implementation bottlenecks. The Bank team restructured the project to change the implementation arrangementsand closing date to support improved project implementation. However, the project would have also benefitted from a restructuringwhen it did not make sufficient progress in regard to an improved regulatory framework, therefore resulting in not achieving thetarget for policy reform.
P145766 | Second Programmatic Productive & Sustainable Cities Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2015 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The first two lessons are drawn from the ICR (pages 20-21), with some adaptation, and the third by IEG.One,political commitment to DPL reform programs can often be strengthened by a governments active participation in analyticalwork that support the reform objectives, extensive consultations with public and private stakeholders, and a deliberate effort tointegrate the DPL reform programs into national development plans. Colombias inter-ministerial Misin para elFortalicimiento de las Ciudades prepared 17 papers that provided a solid technical foundation to the institutional and policyreforms. The commission held at least 12 consultations with diverse stakeholders. In addition, the Government held at least oneconsultative event for each of the nine DPLI and eight DPLII prior actions. Importantly, the reform objectives wereembedded in the National Development Plans for 2010-14 and 2014-18.Two, DPL operations involving local governmentsshould deliberately make allowances for differences in institutional capacity, governance structures, and political setting betweennational and local agencies. In thisDPL, local governments were responsible for implementing many reform measures. Localunits needed more time to build consensus and to allocate resources to support reform objectives. They also needed greater effortto gain technical knowledge and to strengthen their capacity to implement reform measures. Moreover, they had to contend with localpolitical cycles --- the local government elections of 2015 ushered in many new local administrations, new local councils, and newlocal staff that had to be introduced to the objectives and content of the reform effort.Three, DPL operations needas much careful fiscal resource planning and programming as they do policy reform planning and sequencing. The central Governmenttook two years to commit budgetary resources to the Road Safety Agency (ASV) which was created in 2013. The Transport Planning Unit(TPU) and the Transport Regulatory Commission (TRC), also created in 2013, had yet to start operations in end-2015 due to lack ofbudgetary support. The ICR also reports that local governments took a longer time to allocate resources to DPL activities. It mighthave been that the imperatives of fiscal restraint in 2013-15 were more compelling than the need to promptly start the newagencies. Still, with expenditure reallocations being always available as an alternative funding option (according to the IMFArticle 2017 Article IV), these episodes illustrate that more careful fiscal planning is needed to support planned DPLoperations.
P145766 | Second Programmatic Productive & Sustainable Cities Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2015 | 2016 | 2020 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/426591583968971309/text/Colombia-Programmatic-Productive-and-Sustainable-Cities-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/426591583968971309/pdf/Colombia-Programmatic-Productive-and-Sustainable-Cities-Development-Policy-Loans.pdf | 6. Lessons 6.1 Several lessons emerged from this assessment of the Colombian DPL series. 6.2 Tacit assumptions that additional fiscal outlays will be forthcoming to support prior actions in DPOs can create risks to the sustainability of policy reforms. Risks to sustainability were detected in components that required additional fiscal resources, such as the extension of subsidies (for example, the PVG), matching grants (for example, the CP), or the creation of new entities (for example, the creation of a transport regulation commission and a planning unit). Their implementation was dynamic at times of adequate fiscal resources (2012â€“14) but lost momentum when the fiscal space tightened (2014â€“18). During periods of fiscal stress, the government can reduce budget allocations to flexible budget items, such as those involved in the DPLs. 6.3 When designing prior actions that require local-level implementation, it is important to consider municipal capacity and the time required to enact local-level reforms. In the case of the Colombia urbanization DPLs series, delays occurred because of low technical and institutional capacity at the local level; in some cases, only the largest cities were able to make progress. The Colombian decentralization model that provides full local autonomy presents difficulties in the implementation of policy reforms at the local level. Although the government has enabled local interventions in national laws and decrees, municipalities can autonomously decide when to implement certain enacted policies depending on the balance with other priorities and resource availability. 6.4 In designing multisectoral DPOs with many prior actions across sectors, which include local implementation requirements, municipal capacity building may be required. Central government agencies, the World Bank, or other international financial institutions can deliver the support. As an instrument, a DPL is designed to support the central government budget without earmarking financing to sector ministries that are part of the operation. Parties responsible for overseeing implementation indicated that their willingness to work on this operation depended on securing complementary support. The DNP and line ministries must do most of the design work and are responsible for implementing policies and complying with targets. In fact, for complying with their commitments, in some cases, they needed to source other finance from development partners to make sure the policy measures were achieved. 6.5 In the context of multisector DPOs, it is critical that prior actions be directly linked to results indicators so a clear line of sight and envisioned impact is identified ex ante, thus supporting a strong design at entry. In these DPLs, the results were expected to trigger policy and institutional change in support of more productive, sustainable, and inclusive cities in Colombia. Some results were defined more in terms of outputs broadly attributable to specific reforms, and in some cases, these were processes and actions rather than results. For example, structuring the NDP 2014â€“18 with a territorial or regional approach that takes into account the SoC framework is an action, and the number of conceptual design or feasibility studies supporting travel demand management policies is a process. In these instances, it is difficult to discuss the causal links between actions and results that should be indicative of having triggered changes that signal the achievement of the development objectives. 1Since the late 1960s, subnational governments have been enabled to constitute associations, for example, through the creation of metropolitan areas in the case of municipalities. However, these association mechanisms are voluntary. The institutional arrangement does not mandate functions or provide governmental resources to associations as the Constitution does for departments and municipalities to deliver the delegated services. 2An analysis on the impact of the Contratos Plan highlighted the need to introduce the following adjustments\. (i) build the capacity to monitor the content and commitments agreed to in the CP; (ii) strengthen the organization of the teams involved in the implementation of the CP through a detailed definition of roles and responsibilities; (iii) address the issue of the responsibilities and commitments attributed to the sectors in the CP (it was not possible to demand compliance to the sectors at any territorial level); (iv) define other and additional sources of funds for the CPs; and (v) enable a horizontal articulation among regions. 3The 1968 Constitutional Amendment granted legal status to metropolitan areas. In 1979, Decree No. 3104 introduced specific requirements and operational regulations for metropolitan areas, and in 1994, Law N. 128 added specific provisions related to their administrative responsibilities and financing sources. Under that regulatory setup, the decision to create a metropolitan area was at the departmental assembly level, and municipalities had little influence in this decision. The governance plan did not require all municipalities to participate; only the presence of the core municipality and two additional ones are required in a metropolitan area's governing board. 4Valle de Aburra (Medellin and its surrounding municipalities), created in 1980, is the metropolitan area with the most development prospects. According to interviews held during the evaluation mission, authorities mentioned that its success has been mainly the result of the shared view of the necessity of municipal cooperation for regional development, the long-term planning approach, and the availability of resources to operate and execute their plans. Medellin has contributed significant resources to the metropolitan area. Additionally, the metropolitan area could possibly raise its own resources from the environmental surcharge, pollution fee, and the service provision fee. The main elements of the metropolitan area of Valle de Aburra's metropolitan planning are included in the Metropolitan Development Plan prepared for 2008â€“20. Authorities commented that they are working on a new one with a 10-year horizon. In addition, their actions are guided by the Metropolitan Land Use Guidelines, the Basin Management Plan, the Integrated Solid Waste Management Plan, the Metropolitan Mobility Master Plan, the Plan for the Territory Occupation, the Land Management Standards, and the Metropolitan Strategic Housing and Habitat. 5 See the INRIX 2018 Global Traffic Scorecard at http\.//inrix.com/scorecard/. 6 Colombian housing policy gained new momentum at the beginning of the current decadeâ€”in 2011, the National Development Plan 2010â€“14 (Prosperidad para Todos) chose the home building sector as one of the five engines of growth, and in 2012, the Santos administration created the Ministry of Housing, Cities, and Territories (Ministerio de Vivienda, Ciudad y Territorio; MVCT). The ministry emerges from splitting the Ministry of Housing and Environment into two entities\. the MVCT and the Ministry of Environment. The new policy design introduced a segmentation among the poor households and set up a financial instrument to assist each segment according to its saving capacity. The policy's primary purpose was to reach the poorest families. Because of low or no saving capacity, the poorest and most vulnerable families, in practice, had been excluded from previously implemented financing arrangements, accumulating a high quantitative deficit of affordable housing in this segment of the population. 7 Under the previous system, although the policy differentiated between public housing for lowincome families and public housing for the poorest households, based on housing unit costs, there were no distinctions within the second heterogenous segment, where some households may have some mortgage-paying capacity. Originally, the designed subsidy program was similar for both public housing for low-income families and the poorest households. The subsidy was extended to families to facilitate access to credit from financial institutions, that is, to achieve the financial closure for extremely low-income households. However, the financial closure was not achieved in many cases because of the low saving capacity of poorest households and the prudent attitude of the Colombian banking sector, meaning that a substantial percentage of budgeted resources for housing subsidies was not executed. Also, the participation of the private sector in the construction phase was not conducted under clear rules. Corrupt practices have been identified, the quality of construction was often inadequate, and many projects never came to fruition (Herrera 2019). Law N. 1537 of 2012 included other important principles intended to make the participation of the private sector more efficient. For example, the law establishes that payments to private developers are made at the end of the project against delivery of finished housing and requires minimum technical construction standards. To avoid geographical concentration, the new policy enabled subnational governments with land availability to participate in the program (Herrera 2019). 8 The new government is planning to suspend the program because of its high fiscal cost. 9Families began to live in condominiums with multiple neighbors and social interactions, while in fact, numerous benefited families had previously lived in houses in the countryside or on the outskirts of the city, relatively isolated from each other. As a result, families were not familiar with rules governing the vertical property, such as administration fees and garbage management. In other cases, numerous families used to obtain their subsistence from activities or businesses developed inside their home, which is impossible under condominium rules. Large families started to live in housing with better conditions but of smaller size, which caused overcrowding. 10Territorial entities and the government of Colombia were forced to develop social support programs. The MVCT has worked in four action lines (community organization, rights and duties, security and communal harmony, and productive development) through alliances with nongovernmental organizations and based on workshops and cooperative activities under the National System of Social Accompaniment and Social Infrastructure to the Free Housing Program. Actions taken at the local level have reinforced these efforts. In the case of Medellin, for example, the Housing and Habitat Social Housing Institute of Medellin (Instituto Social de Vivienda y Habitat de Medellin), which is in charge of managing the municipality of Medellin's housing programs, deployed measures of social support successfully. The mission found that these programs' success at the local level varies according to the city's institutional capacity.
P145778 | Mizoram State Roads II- Regional Transport Connectivity Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099455001122214035/text/India000Mizora0II00Reg0Connectivity.txt | http://documents.worldbank.org/curated/en/099455001122214035/pdf/India000Mizora0II00Reg0Connectivity.pdf | IEG supports the following main lessons that the ICR draws from the experience of implementing this project, with someadaptation of language.1. Bioengineering solutions can help in protecting against landslides and enhanceresilience in hilly regions. One of this projects main achievements was the successful piloting work on the hillyareas of Mizoram for side slope stabilization to prevent landslides in a cost-effective and environmentally-friendlyway.2. Trade facilitation interventions at the borders can help in enhancing efficienthandling of movingfreight along corridors. Truck stops built along regional corridors near the border can enhance the physicalmovement of freight by reducing traffic congestion at the border.3. A careful market study of contractorcapacity during preparation is needed to reduce procurement delays during implementation in remote areas.The remotelocation of Mizoram resulted in procurement delays as the project found it difficult attractingqualified contractorstowork in the difficult terrain.The IEG draws the following additional lesson.Regional connectivity projects needto be comprehensive in their coverage. For regional connectivity projects, particularly thosepartly funded by a regional IDAgrant, it is necessary for the projects objectivetoinclude cross-border activities, given thattrade-related transactions costs (cost and time associated with moving goods across borderscontribute tonontariff barriers), are identified in the trade facilitation literature as a significant impediment to trading across borders inregional corridors.
P145782 | ACCESS WITH QUALITY TO HIGHER EDUCATION PROJECT-ACCES II -SOP PHASE 2 | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2014 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/817941585594620211/text/Colombia-CO-Access-with-Quality-to-Higher-Educa.txt | http://documents.worldbank.org/curated/en/817941585594620211/pdf/Colombia-CO-Access-with-Quality-to-Higher-Educa.pdf | The following lessons are drawn from the ICR.Demand-driven higher-education financing mechanisms such as theACCESstudent loan program in Colombia can lead to positive development outcomes. Emphasizing information outreach(presence on the ground) can reduce the knowledge gap and encourage participation by economically and geographically disadvantagedstudents.Enhancing financial literacy among loan recipients can help students manage their financial obligationsunder student-loan programs such as ACCES. The majority of individuals receiving student loans lack financial literacy andmay face critical debt burdens over time, indicating that remedial courses in personal finance can be crucial for the success of aprogram such as ACCES.The very poorest and students from remote areas may need more specific or moreintensive attention. While ICETEX has meaningfully helped improve education opportunities for vulnerable students, thevery poorest ones or those from remote areas have made relatively few gains. These students need more robust and strategicinterventions, such as remedial academic programs and coaching, incentives towards graduation, targeted financial products, andsupport to regional institutions for accreditation.
P145792 | Ghana - Maternal, Child Health and Nutrition Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/330721623857458233/text/Ghana-GH-Maternal-Child-Hlth-Nutr-FY14.txt | http://documents.worldbank.org/curated/en/330721623857458233/pdf/Ghana-GH-Maternal-Child-Hlth-Nutr-FY14.pdf | Lessons drawn from the ICR (pages 28-29), adapted by IEG: Holistic investmentin the lowest tier of thehealth system can lead to increased service utilization of basichealth services. In the case of this project, theproject increased autonomy of community- and district-level decision making and improved fund flows from central to districtagencies.These investments led to increased coverage of maternal and child health and nutrition services, although theimpact on health outcomes (i.e. maternal mortality) remained unclear given that the project did not include interventions in thecontinuum of care above the primary health care level. For ahighly decentralized implementation approach,monitoring arrangements that arerobust and well-considered can ensure quality of data and thus contribute to achievement ofoutcomes. In the case of this project, the monitoring plan made use of existing electronic routine service data collectionsystems, along with manual service registries. In addition, the project implementation unit was staffed with full-timeME experts and the Bank team provided extensive ME support. These all contributed to the quality and timeliness ofdata reporting. Flexibility in fund utilization can facilitate response to emergencies. In the case of thisproject, unallocated funds as well as reallocations from other components were well-utilized to aid thegovernments response to the Ebola outbreak and the COVID pandemic, without jeopardizing achievement of projectobjectives.
P145799 | NATURAL RESOURCES MANAGEMENT IN A CHANGING CLIMATE IN MALI | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2014 | 2020 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/552521593537256212/text/Mali-Mali-NRM-Changing-Climate-PSG.txt | http://documents.worldbank.org/curated/en/552521593537256212/pdf/Mali-Mali-NRM-Changing-Climate-PSG.pdf | The ICR included three lessons. The following are emphasized with some adaptation of language: Addressingland tenure issues is criticalto ensure a successful outcome for land restoration projects.The projectexperience showed that without addressing the underlying land tenure insecurity, land degradation outcomes will not materialize,and they will not be sustainable. It is also important to build in short-term incentives, while the longer-term benefits of landrestoration materialize. Implementing a project without a dedicated PIU ispossible with a properincentive structure in place.The project relied on a core team of staff appointed within the implementing agency tocoordinate the daily management and monitoring of tasks. Staff incentives were addressed through a national incentive framework,using counterpart funding. Thisallowed for bonuses and other benefits to align public officials responsibility withproject implementation.This also ensures that public officials would not be pulled into competing priorities of theimplementing agency.The following lesson isemphasized by IEG: Restructuring ofprojects needs to be timely and comprehensive to maximize the benefits of the restructuring process.The projectexperienced a relatively late restructuring process. This left limited time for benefits to materialize by completion. Also, therestructuring needs to be comprehensive and involve the revision of the PDO especially when critical activities are scaledback.
P145813 | PK Sindh Irrigated Agriculture Productivity Enhancement Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099083024181063200/text/P145813-2fa11bc4-cfe0-421d-a001-3a8a076982f6.txt | https://documents.worldbank.org/curated/en/099083024181063200/pdf/P145813-2fa11bc4-cfe0-421d-a001-3a8a076982f6.pdf | The ICR included four lessons. the following three are emphasized with some adaptation of language:1. Toeffectively address issues related to the water-agriculture nexus, a more holistic approachthat incorporates cross-cuttinginterventions combining technical, institutional, and capacity-building activities, is required. SIAPEP focused oninfrastructure improvement and supply, and capacity-building for beneficiaries. A stronger emphasis on institutional aspects andinterventions targeting agricultural productivity (which naturally complements improved irrigation water availability and is itsintended outcome) could have enhanced project outcomes. This requires the Bank to emphasize more collaboration and/or cross-supportin project design between the Agriculture and Water GPs.2. To ensure comprehensive assessment of outcomes,projects need aclear ToC combined with astrong ME design that informs adjustments to strategy and strengthensoutcomes, and provides rich evidence for future operations. Key data on project activities that extends beyond indicatorresults or activity lists, based on a thorough understanding of causal relationships within the project, can be used to analyze andadjust project processes. While the project collected data on numerous parameters, a number of indicators (which would havebenefitted project assessment) were not measured or monitored including: the operation and capacity of WCAs, HEIS operationalcosts, the effect of HEIS on input savings (water, fertilizer and labor), crop diversification, use and upkeep of laser landleveling (LL) and deep ripping (DR) equipment, the effects of LL and DR on water savings, the delivery of tents and nets, and theactivity of the Project Supervision Implementation Assistance Consultants (PSIACs). Also, data on adoption of practices andtechnologies promoted by the project beyond its direct beneficiarieswould have been useful to verify and assess spill-overeffect.3. To maximize benefits and strengthenthe sustainability of production, irrigation project needtoincorporate elements of agribusiness and agricultural marketing. Field interactions indicated that there isroom to encourage entrepreneurship among project beneficiaries/farmers and foster a culture of calculated risk-taking forproductive investments, rather than relying on subsidies. Capacity building, collective marketing schemes and improved marketlinkages could bolster irrigation and agriculture projects. Within the project cycle, timeliness of interventions beyond improvingirrigation water management is also crucial. For instance, activities such as the farmer field schoolsimplemented in thisproject should be conducted early in the implementation cyclerather than towards its end, since they require time andencouragement for adoption. Similarly, activities related to marketing through producer organizations need to be implementedshortly after project implementation begins to allow enough time to establish the relevant marketing links.The followinglesson is emphasized by IEG:4. To ensure successful implementation of activities targeting women in asocietythat exhibits a conservativesocio-cultural behavior, women activities need to be tailored to fit the cultural norms, andtargets need to be realistically set at appraisal.The project experience demonstrated that featuring activitiesgeared towards women did not automatically mean that women would participate as envisioned. Project design needs to include acomprehensive social analysis to clearly understand the role of women within the society and design relevant activities that wouldensure womenparticipation.
P145848 | Second Urban Poverty Reduction Project (PREPUD II) | Middle East and North Africa | Djibouti | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/321411606844655910/text/Djibouti-2nd-Urban-Poverty-Reduction-Pj-PREPUD-II.txt | http://documents.worldbank.org/curated/en/321411606844655910/pdf/Djibouti-2nd-Urban-Poverty-Reduction-Pj-PREPUD-II.pdf | The following two lessons in the ICR stood out as important and relevant to other projects in Djibouti with infrastructurecomponents and are presented here with some editing.The Banks two consecutive operations in Q7 (PREPUDand PREPUD II) prove that the Bank needs to ensure the development and enforcement of an operations and maintenance program priorto launch of implementation. Without such effort, there would be challenges to sustainability of the project assets,as described in Section 7. Additional consultations at the design stage with the responsible parties about the future of each suchasset would be essential. Utilizing its convening power, the Bank may be able to also support the Government to develop an actionplan for providing systematic maintenance of existing investment. Moreover, a need for an integrated approach to address themaintenance issue needs to be well communicated to the active donors in the country.Key project activitiesneed to be designed to be within the area of influence of the implementing agencies to ensure their capacities to resolve anypotential issues with stakeholders, especially when a faith-based organization is involved. The project encounteredthe implementation delays due to the claimed ownership on the land allocated to the Square and the construction of a temporarymosque. The ADDS had to seek higher-level support to resolve the issue, as such issue was outside of its scope of responsibilitiesand control.
P145861 | MALI - Skills Development and Youth Employment Project | Western and Central Africa | Mali | IDA | FCS | Human Development | Education | IDA | IPF | 2014 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099605010142229802/text/P1458610334e0c011096510139136604515.txt | http://documents.worldbank.org/curated/en/099605010142229802/pdf/P1458610334e0c011096510139136604515.pdf | The ICR (pp. 34-350 identified several important lessons, including the following lessons partially re-stated byIEG:Skills development interventions can be remarkably successful in fragile settings when the design includesdecentralized and flexible short-term training that can reach the maximum number of young people in rural areas. Theproject accommodated the countrys immediate needs of providing employment for unemployed and underemployed youth in ruralareas by providing skills training in a decentralized manner with certification upon completion and with opportunities forapprenticeships. Flexible skills training arrangements helped in accommodating the life situations of young rural beneficiaries.Decentralized short-term training provided training closer to where families liveand has likely contributed to alleviatingsome of the barriers to the participation of young women.In value chain domains, effective selection ofbeneficiaries, entrepreneurship training, and the provision of seed funds are critical for new entrepreneurs to begin and sustaintheir businesses. The project provided entrepreneurship training that included the preparation of business plans as wellas seed funds for beneficiaries selected to start Micro, Small and Medium Enterprises. This lesson also generated a recommendationto organize continuing education and training with mentoring and technical support to enhance continued viability of new Small andMedium Enterprises.The creation of an effective labor market observatory facilitates the monitoring of labormarket supply and demand. The project supported the establishment of a labor market observatory that provided valuableinformation to government, training institutions, and businesses for improving TVET operations.Dual apprenticeshipprograms can be an effective approach to fostering job market integration and/or self-employment. Under the project, dualapprenticeship programs in urban localities (combining formal training to confer cognitive and technical skills for one-third ofthe time and apprenticeship for two-thirds of the time) were found to be effective. Associated apprenticeship reforms also resultedin system improvements, including flexibility and duration, equitable access, and strengthening partnerships with the participationof professional organizations.Strong private sector engagement is essential for promoting the relevance of skillstraining programs. The project placed considerable emphasis on engaging the private sector through private sector-led jobcreation strategies to improve employment opportunities for youth. In doing so, the project supported entrepreneurship programs foryouth, scaled up established enterprises, and strengthened private TVET institutions to expand and improve their technical andvocational programs. The project included business leaders within the TVET governance structures. This engagement helped to instillprivate sector confidence in the training programs.
P145865 | Mitigate the Impact of Syrian Displacement on Jordan | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2014 | 2015 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/661411468184740901/text/ICRR14734-P145865-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/661411468184740901/pdf/ICRR14734-P145865-Box393183B-PUBLIC.pdf | The ICR provides several lessons (ICR pp. 24-25) that have been synthesized by IEG as follows:Utilizing existing delivery mechanisms and services allows quick preparation, implementation, and response, but technical assistance is also required. In this case, project preparation minimized time-intensive financial management and procurement reviews and relied on country systems already assessed by the Bank. A positive list of drugs and vaccines minimized the number of transactions and documents to be audited, thus reducing transaction costs. Strong ex-post audits ensured compliance with project requirements. Retroactive financing provided immediate fiscal relief. However, technical assistance related to fiduciary management was also needed for successful project implementation.Temporary time-bound support in emergency situations can help mitigate social instability. The universal subsidies played a role in maintaining social stability in the country, despite being burdened by a large refugee population (with no end in sight). A strong relationship between the Bank and the government facilitates rapid response. The Bank was able to provide rapid preparation and intensive implementation support drawing on the multi-sectoral staff in the region. This may not have been possible without the working relationship that existed between the Bank and the government.
P145897 | GEF Mainstreaming Integrated Water and Environment Management | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | GEF | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099700012272237364/text/P1458970c39fbc03c0b4f90fcb140b39e67.txt | http://documents.worldbank.org/curated/en/099700012272237364/pdf/P1458970c39fbc03c0b4f90fcb140b39e67.pdf | (Reference ICR paras. 70 to 74).The ICR lists a number of lessons drawn from the Project experience which haverelevance for similar projects carried out in comparable environments. From these, IEG derives the followinglessons:Adoption of innovative IWEM approachesneeds to take into accountspecific country and sectorcontexts: While the Project successfully demonstrated and mainstreamed various innovative IWEM approaches, adoptingthese approaches in other countries needs to consider contextual differences. For example, adopting water rights trading andpollution emission trading requires that a basic water rights system and emissions permit system is in place. Irrigation watertariff reform is an essential requirement for achieving the targeted improvements in increasing water productivity and reducinggroundwater overdraft.Applying an adaptive learning by doing approach can help reduce potential risksand help effectively scale-up activities: The Project activities were sequentially arranged as: Studying -Piloting and Demonstration - Scaling-Up and Mainstreaming - Incorporating into Policy. The innovative IWEM approaches were firststudied to identify challenges and solutions, and then piloted and demonstrated at a small scale. The lessons learned from thepilots were used to guide scaling-up and mainstreaming at larger scales. Based on the experience, key recommendations wereincorporatedin policies and regulations to guide IWEM in the country.A coordination mechanismcovering the water and environment sectors is a key requirement for implementing IWEM: In the case of theProject, awell-organized coordinated implementation arrangement was put into place to ensure cross-sectoral coordination atthe national, regional and local government levels. This included the establishment of Cooperation Agreements at various governmentlevels that facilitated timely and productive coordination meetings during the implementation period.
P145938 | Samoa Agriculture & Fisheries Cyclone Response Project | East Asia and Pacific | Samoa | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/644961517349226065/text/Samoa-Agriculture-Fisheries-Cyclone-Response.txt | http://documents.worldbank.org/curated/en/644961517349226065/pdf/Samoa-Agriculture-Fisheries-Cyclone-Response.pdf | The following lessons were summarized from the ICR (Section 6): While ultimately moreefficient and transparent, the initial set-up of e-voucher systems can be time-intensive, requiring multiple steps from multipleactors. In the Samoan context, set-up and roll-out took about 12 months and required: appropriate legislative provisionsand financial regulations, configuration of merchant operating systems, and on-the-ground assistance for beneficiaries andsuppliers who had never before used the system. Because these efforts were not properly accounted for at the time of projectdesign, distribution of vouchers was delayed. This is especially important to consider in an emergencycontext. Secondary costs and logistical challenges associated with the redemption ofvouchers can create obstacles in realizing vouchers intended benefits. Some subsistence farmers were unable to redeemtheir vouchers as they lacked the means for transporting assets from the relatively few merchant locations to their homes. Inaddition, there were challenges related to selected merchants due to their location, limited inventory, and staffinglevels. Implementing agencies lacking experience in managing donor-financed projectscould benefit from close collaboration with more experienced agencies, but overlooking the time necessary to learn can causeproject delays. Close collaboration between the MAF PMU and the PMU associated with another World Bank project enabledlearning. However, the learning curve was not sufficiently accounted for in the project timeline, and delays occurred as aresult.IEG adds the following lesson: When external shockslike natural disasters wipe out production, there is an opportunity to re-orient production to more sustainable and profitablecrops. In the case of Samoa, a negative average annual growth rate in the agricultural sector for the decade preceding theproject is clear evidence that a return to the status quo may not be desirable (PAD, p.1). Indeed, commercial farmers pushed theproject to increase its flexibility and allow them to invest in new activities that were more economically sustainable rather thanbe forced to invest in the recovery of less viable pre-disaster activities.
P145965 | DRC Human Development Systems Strengthening | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/468451637098486982/text/Congo-Democratic-Republic-of-Human-Development-Systems-Strengthening.txt | http://documents.worldbank.org/curated/en/468451637098486982/pdf/Congo-Democratic-Republic-of-Human-Development-Systems-Strengthening.pdf | The following lessons are a subset of the lessons presented in the ICR, reworded by IEG to be moresuccinct: A multisectoral project aimed at improved systems, capacity, and transparency risks being underminedby stakeholders with conflicting stakes and interests, especially if these were not assessed at the design stage.Inretrospect, a political economy analysis would have enabled the anticipation, mitigation, and better management of incidents oflack of support and interference thatarose during the project, especially regarding CVRS reform and the increased autonomy ofessential medicines acquisition. Failure to conduct a careful and systematic assessment of the various lendinginstruments and their relative strengths and drawbacks during the design phase can be a missed opportunity for choosing the rightinstrument that will produce optimal results.This is especially true for a multisectoral operation, focused on institutionbuilding in a fragile, low-capacity environment.In retrospect, instruments that may have better supported the projectsobjectives included disbursement-linked indicators, development policy lending, and Identity for Development (ID4D). Theproper range and mix of staff expertise required for a complex, multisectoral operation, as well as their in-country location, arecritical for quality Bank support to project design, implementation, and the achievement of results, especially in a low-capacitycountry.High staff turnover, an imbalance or underrepresentation of requisite technical skills, and changes in TTLs (and intheir expertise) all can undermine dialogue, problem-solving, and results. It is possible to support the continuity andresilience of a project supporting reforms and institution building, but only if necessary proactive measures are taken.Thiswas demonstrated by other projects and tasks thatwere able to continue meetings, including new project preparation.Thisproject, however, could have done more to consolidate important results, even under COVID-19 restrictions, especially the greateruse ofinformation technologyfor monitoring, validation of deliverables, building of stakeholder ownership, and onlinetraining. Information technologyholds great potential for facilitating survey work.The under-exploitation ofthis potential can undermine the timeliness, efficiency, and quality of survey results. The paper-based data collection method usedfor the SDI survey caused significant delays thatultimately cut short analysis, report writing, and use of survey results forservices improvement.Electronic methods (for example, Computer-Assisted Personal Interview) could have accelerated recordingof data and analysis.IEGs review offersone additional lesson: Attention tosustainability is critical during project design and throughout implementation.This involves the continued tailoring andprioritizing of interventions to fit the governments interest and commitment and its ability to finance incrementalrecurrent costs post-project.It also involves advocacy work to raise the interest, appreciation, and commitment of governmentand stakeholders to project activities and results and recognition of their contributions to national goals.Such dialogue,advocacy, and demonstration effects may take more time than the life of one project and would thus require continued effort forseveral years post-project.
P145995 | Jamaica DPL | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2014 | 2016 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/759141467996680347/text/ICRR14850-P145995-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/759141467996680347/pdf/ICRR14850-P145995-Box394823B-PUBLIC.pdf | The following lessons are taken from the ICR (p. 28) with some adaptation of language:Close coordination with other multilaterals in the course of project preparation and supervision enhances the impact of Bank operations. It also reduces transaction costs associated with donor assistance to the client governments, which is especially important at the time of major economic crisis.In cases where the Bankâ€™s supported reform programs have considerable overlap with the programs supported by other multilaterals, specific contribution (additionality) of the Bank operation becomes difficult to establish. Utilization of various Bank instruments (DPL, investment lending, and non-lending technical assistance) delivered as a well-coordinated package represents an effective strategy for advancing ambitious structural reforms, especially in the areas that require sufficient capabilities within the core government agencies, such as e.g. public sector reform.
P145995 | Jamaica DPL | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2014 | 2020 | PPAR | >=100 million | Satisfactory |  |  | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/336231570467350966/text/Jamaica-Economic-Stabilization-and-Foundations-for-GrowthDevelopment-Policy-Loan-DPL.txt | http://documents.worldbank.org/curated/en/336231570467350966/pdf/Jamaica-Economic-Stabilization-and-Foundations-for-GrowthDevelopment-Policy-Loan-DPL.pdf | 5. Lessons 5.1 The PPAR suggests the following three main lessons\. â€¢ Building and maintaining strong political and social consensus through explicit social forums and mechanisms such as the EPOC can be a critical element in gauging and bolstering government and societal ownership and commitment to complex stabilization and reform programs, promoting their chances of success. â€¢ Even high-risk reform programs implemented in times of crisis can succeed when accompanied by strong government ownership and commitment, social consensus, front-loaded adjustment, and well-coordinated support from international financial institutions and other external partners. â€¢ In designing and sequencing major reform programs, it is important to recognize that some may be implemented relatively quickly (for example, fiscal consolidation), giving quick and important wins, while others (such as investment climate and pension reform) require more time to build consensus and to prepare and implement legal reforms. Endnotes 1In February 2013, the government and financial institutions implemented a voluntary domestic national debt exchange to reduce government debt service and provide support to fiscal consolidation. The operation helped the government reduce public debt from 147 percent of gross domestic product in 2013 to 140 percent a year later (IMF 2014a). At the same time, the operation resulted in a reduction in the value and change in maturities of the government bonds held by domestic commercial banks, which resulted in significant liquidity pressure and the freezing of the domestic bond markets. The Bank of Jamaica, in response, introduced repo operations, which over time helped alleviate liquidity pressures. 2This agenda is based on the government's national council on competitiveness, which identified priority business climate reforms based on the World Bank's Doing Business indicators assessments and the council's own assessment of key constraints, which included business registration and development permits. For more information, see http\.//www.jamaicatradeandinvest.org/sites/default/files/resources/JAMPRO_NCCRoundtable_2 014.pdf. 3 The Implementation Completion and Results Report Review expressed concern that some of the policy agenda supported by the development policy loan overlapped with the policy agendas of the International Monetary Fund and the Inter-American Development Bank, which raises the question of the World Bank's additionality (World Bank 2015a). However, detailed comparison of prior actions under this DPL and the IMF Extended Financing Facility as well as interviews with IMF, World Bank, and IDB staff have shown that there was a clear division of labor in which the IMF and IDB focused on fiscal consolidation and tax reform while the World Bank focused on the structural fiscal and investment climate reforms. For example, key to fiscal consolidation was the short-term control of the wage bill (which was part of the IMF program); but sustainability depended on the full accounting of the public sector personnel and rationalization of government organizations (part of the World Bank 's program). There was thematic overlap with the EFF prior actions in only two out of nine prior actions under the DPL (regarding tax reform and small and medium enterprises), but specific DPL actions differed and were, in fact, complementary to those of the EFF. For example, the World Bank program targeted improvement in the government's policy toward micro, small, and medium enterprise (MSMEs) while the IMF's EFF program aimed to ease financing to MSMEs and to roll out the use of mobile money to underserved entities (including MSMEs) in a phased way. Another example is that the World Bank program supported improvement in budget institutions and systems through, for example, adoption and adherence to a transparent budget calendar and the Treasury Management Information System, while the IMF supported the adoption of a fiscal rule to frame the future conduct of fiscal policy. 4By the time of the DPL approval in December 2013, the government had previously agreed with the IMF and the World Bank on the 2013 budget, and budget execution was on track. The government completed all the prior actions, as required, and the IMF completed the second review of the EFF program. 5The trade unions are the Jamaica Confederation of Trade Unions, Bustamante Industrial Trade Unions, and the National Workers' Union. 6Fiscal responsibility legislation was adopted in 2010 and amended in 2014. Furthermore, in 2018, the government launched the preparation for the establishment of a new fiscal institution, Fiscal Council, following good international practice (see Clarke 2018). 7The application management and data automation is an online system used to track land development permits and licenses, and support planning and subdivision decisions regarding housing, manufacturing, and a variety of commercial activities. The original system was under development since 2005, but it was extended online and into all parishes during the program period. 8One area where there was disagreement with the authorities was the amount of budget support. The government argued forcefully for more support in the short term. The World Bank's decision on the size was driven by the size of the estimated external financing gap and the coordinated dialogue with the IMF and IDB, its own country exposure constraints, and concerns with debt sustainability. 9For more information, see the government's white paper on pension sector reformhttps\.//jis.gov.jm/white-paper-public-sector-pension-reform-tabled/. 10The white paper acknowledges in several places the support the World Bank provided in various stages of the pension reform (Government of Jamaica 2018). 11Hotels and resorts are an important part of the tourism industry and a major beneficiary of incentives. For more details on government's tax incentives, see\. https\.//www.jamaicatax.gov.jm/fiscal-incentives. 12MyHR+ is an integrated pensions and payroll system. Since January 2018, it was transformed into the Public Employees' Pension Administration System, leading to improvement in transaction costs and processing of payrolls and pensions. For more details on myhr, see https\.//mof.gov.jm/pepas/271-hrm-transformation/2459-hcmes-is-now-myhr.html. 13The public financial management reforms that are currently being supported are a public investment management information system, external audit strengthening for the Auditor General's department, rationalization of public bodies, design, and so on (World Bank, 2014e). 14For example, some key results indicators were achieved such as the rollout of the application management and data automation software in all 14 parishes of the country, providing citizens and clients of local governments with a single point of access to view the status of applications for subdivision applications, a vast improvement over the previous manually managed process. Also, the target on the key indicator (below 125 percent of gross domestic product) on the public debt was overachieved in 2017 and sustained.
P146007 | EG: Household Natural Gas Connection Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2015 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099091823160510750/text/P14600707a11650e2086a30f9bb957d262f.txt | http://documents.worldbank.org/curated/en/099091823160510750/pdf/P14600707a11650e2086a30f9bb957d262f.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1. Hiring aspecialized consulting firmcan be an effective way to ensure dedicated and specialized supervision of projectactivities.EGAS utilized the services of a specialized local consulting firm to monitor, supervise, and report backon the ESHS compliance of the implementing agencies and their contractors. The project experience demonstrated that this was aneffective way to supportthe PMU in monitoring compliance and preparation of monitoring reports.2. To avoidimplementation delays, projects with multiple financiers might better considerparallel financing arrangements where eachfinancier finances specific contract(s), preferably not interdependent on each other.Parallel financing arrangementswould help reduce the need for frequent adjustments to co-financing percentages in the Loan Agreement due to changes in exchangerates and nonsynchronous effectiveness of various financing agreements, which may delay implementation.It is important tocoordinate closely, especially on the effectiveness dates of respective financing agreements and the co-financing solutions. Theproject experienced showed that specifications of co-financing percentages for the entire scope of Component 1 worked well in theearly days of the project, but variations in exchange rates among the different currencies (for example, EUR and USD) and thedifferent closing dates complicated the prorating of financing sources for Component 1.3. To ensure smoothimplementation and timely disbursements, it is important to comprehensively assess the capacity of the implementing agency atappraisal to identify areas that need further support. The project experience showed that EGAS could have benefitedfromearly-stage focus on strengthening itsbudgeting and financial planning capacity. The project administration wouldhave benefited from that and may have allowed meeting the disbursement targets in a timelier manner.The following Lessonsare emphasized by IEG:4. To ensure an accurate assessment of achievements, the formulation of the PDO needs toreflect the core activities supported with a clear connection to Results framework (RF). This project supported sectorreform and private sector participation however, those two aspects were not reflected in the PDO and not comprehensively capturedby the RF.5.5. It is important to have a realistic ex ante cost estimate through conducting reliable feasibilitystudies as part of the appraisal process. This project had to cancel 40% of the IBRD loan (about US$200 million), whichsuggests a gross overestimation of costs at the appraisal stage. An accurate assessment of costs can allow the Bank to allocateadequate funding to a specific project and at the same time have the flexibility to fund other operations in the samecountry.
P146015 | Non-Formal Approach to Training Education and Jobs in Afghanistan Project | South Asia | Afghanistan | IDA | FCS | Human Development | Education | RETF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/683321568662278347/text/Afghanistan-Nonformal-Appr-Training-Edu-Jobs-in-Afg.txt | http://documents.worldbank.org/curated/en/683321568662278347/pdf/Afghanistan-Nonformal-Appr-Training-Edu-Jobs-in-Afg.pdf | The ICR presented a significant number of lessons and recommendations. Some referred to the particular context and recommended,for example, the prioritization of ongoing skills development, and continued capacity building within MOLSAMD to enhance itsprojectmanagement capabilities as well as the continuation of the business grants scheme. The ICR also noted that concerns of allstakeholder ministries should be explicitly addressed during the preparation process, to ensure there is broad government ownershipat the outset and to avoid down-the-line implementation delays. The value of cooperation between development partners within anoverall strategic contextwas highlighted in the ICR; had the restructuring recommended at the MTR been implemented, greatercoordination of effort among the partners operating in thetechnical and vocationaleducational and trainingsector the Bank, the German Agency for Technical Cooperation, and IADC would have been possible. The ICR also noted thatthe uncertainty around project direction, particularly post MTR, hampered staff morale and did not alleviate implementationbottlenecks. As such, the ICR recommended that project partners should take advantage of World Bank guidelines to change coursewhen it becomes clear that some project design aspects need to be modified and that, within the Bank itself, there needs to be amore clearly consistent position articulated between the Global Practice and Country Management Unit (CMU) ininteractions with the client. Finally, the ICR noted that the results framework failed to include indicators that adequatelycaptured the PDOs and suggested that greater care is needed during the concept, preparation, and appraisal stages to ensuringgreater accuracy in that regard.IEG emphasizes the ICRs lesson regarding the need for the articulationof a more coherent corporate perspective in dealing with the client. In this case, the ICR reported a lack of agreement between theGlobal Practice and CMU that resulted in mixed messages to the client and likely contributed to the long, post-MTR indecisionregarding whether or not the project should be closed.
P146095 | Economic Management Competitiveness Credit 2 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The following lessons are drawn from the ICR:Care should be exercised in designing multi-sectorprograms. A focused program, addressing a limited number of sectors or issues, may achieve more coherentoutcomes. The EMCC series may not have been unduly broad in its sectoral focus, but it addressed numerouspublic sector, financial sector, and private business themes all important but in drawing in several stakeholderswith at least partly dissimilar agendas, it risked uneven implementation, as happened in EMCC.Aprogrammatic operation introduces flexibility. Programmatic, multi-year programs sometimes need to adjust theirpolicies and their indicators to changing circumstances, or to better understanding of the issues as implementation advances.The EMCC went through a few transformations of PDO, of indicators, even of policy objectives all of them based onlearning by doing, i.e. during program implementation.Design and implementation of a programmaticoperationideally draws on inputs from many sources. Where local stakeholders and development partners areactive, and technical assistance and analytical work abound, an operation should engage such sources. The EMCC series is anexample. Inaddition to the direct relationship with the Borrower, the series also actively engaged other stakeholders,both local and external, and drew on ongoing research.
P146143 | Emergency Employment Investment Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2014 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/563331545342070522/text/Egypt-Arab-Republic-of-Emergency-Employment-Investment-Project.txt | http://documents.worldbank.org/curated/en/563331545342070522/pdf/Egypt-Arab-Republic-of-Emergency-Employment-Investment-Project.pdf | The ICR stated several lessons and recommendations that are not repeated verbatim here.Instead a broad lesson can be offered. Labor intensive public works proved to be a viable mechanism for generatingshort-term employment work in the emergency/crisis setting at the time this project was designed. However, the results of theproject were made possible thanks to the SFDs existing capacity and prior relationship with and experience with World Bankprocedures. Using an experienced implementing entity, with capacity built during several earlier projects, helped the projectachieve its goals. The lesson may not transfer to contexts of weaker capacity.
P146152 | Gabon - Skills Development and Employability Project | Western and Central Africa | Gabon | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061824163083728/text/P146152-9c7a23a3-0420-405b-be01-ca83965642df.txt | https://documents.worldbank.org/curated/en/099061824163083728/pdf/P146152-9c7a23a3-0420-405b-be01-ca83965642df.pdf | IEG highlights the following key lessons identified in the ICR: Effective communications campaigns can keepstakeholders informed and engaged in project implementation. This was particularly important in this project given that itconstituted the first Bank-financed education and skilling project in Gabon since 1974. Further, this was important given thenumerous challenges with project implementation, which included, changes in implementingagency leadership, design changes,high staff turnover, a reduction in financing amount and scale of project activities, and interruptions due to the COVID-19pandemic. The ICR reports that the project did not have a dedicated communications specialist or a communications plan, leading tounnecessary confusion among stakeholders; A multi-phased programmatic approach rather than a single project might beappropriate in low-capacity country contexts where the Bank is engaging ina sector for the first time to allow time forpolicy dialogue and reforms. The ICR admits that much remains to be done in order to solidify the initial gains made in thisproject; and Dedicated World Bank staff on the ground arenecessary in low-capacity country contexts where the Bankis engaging for the first time. This proximity allows for real-time communication, relationship building, and a betterunderstanding of technical and operational challenges to better address them. The ICR indicates that there was an observableimprovement in communication once dedicated staff were placed full-time in the country.
P146184 | Higher Education Development Project | South Asia | Afghanistan | IDA | FCS | Human Development | Education | RETF | IPF | 2016 | 2025 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099060823135521032/text/P1461840f380450bd0876e0358d643ce1c1.txt | http://documents.worldbank.org/curated/en/099060823135521032/pdf/P1461840f380450bd0876e0358d643ce1c1.pdf | The following five insightful and relevant lessons are drawn from the ICR. Results-based financing can bean effective mechanism for delivering development outcomes and fostering innovation and efficiency. Although it wasthe first project in Afghanistan to include an RBF approach, this projects smooth implementation by MoHE and the Ministry ofFinance was due in significant part to the Banks strong support and coaching. RBF propelled a shift from inputs andactivities to results and provided MoHE flexibility in the use of the projects budget to fund essential and innovativeactivities, among which were a number of activities to increase female enrollment. RBF limited the Banks involvement inprocurement and other administrative activities, improving project efficiency. Affirmative action policies toincrease the representation of women in higher education can be highly effective. Reserving seats for femalestudents in Afghanistans national university entrance exam in priority degree programs, together with coordinated supportservices, contributed substantially to increases in female enrollment in a context of deep-rooted inequalities in Afghan society.These actions demonstrated MoHEs strong commitment to gender equity. Especially in an FCV context, acompetent Operations and Monitoring Support Team (OMST), with staff working full-time on the project, can be pivotal to projectsuccess. The Banks presence in the field was limited due to prevailing security situations in Afghanistan.The strong and competent OMST at MoHE was highly effective in compensating for this shortcoming. OMST ensured coordinationbetween MoHEs leadership and the Bank, solving many implementation problems that arose, and providing regular monitoringreports to the Bank. Proactive risk management is crucial for safeguarding and securing implementation andresults in a fragile context. The project encountered formidable issues during implementation, including workdisruptions caused by periodic bombing and explosions in Kabul and the COVID-19 pandemic. OMST, with Bank support, continuedproject activities working through digital means when necessary, including during the COVID-19 pandemic. Moreover, the 2020project restructuring provided support to the higher education system to strengthen its response to thepandemic. In retrospect, a closer engagement with United Nations partner agencies and nongovernmentalorganizations, especially in a context of conflict and political instability, may have enhanced sustainability of reformimplementation and results. While not fully anticipated during project design or implementation, the abrupt andsweeping changes following the August 15, 2021 Taliban takeover, and their severe threats to sustainability, point to theimportance of closely engaging with relevant UN and NGO partners who would be equipped to serve as facilitators or third-partyimplementing agencies in order to carry forward selected activities initiated and supported under the project. This approach is akey consideration for the design and implementation of future operations in Afghanistan and other FCV countries.
P146194 | Belarus Biomass District Heating Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2014 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041823140032574/text/P1461940b122d105d09bdd089d6dba15e99.txt | http://documents.worldbank.org/curated/en/099041823140032574/pdf/P1461940b122d105d09bdd089d6dba15e99.pdf | The ICR identified several lessons and recommendations, but this review has retained two of them, which are rephasedbelow:(i) Fuel switching from gas and oil to wood biomass is highly sustainableand economicallysound. This project wastransformational as itfinanced primarily fuel switching from gas and oil to sustainablewood biomass.Moreover, biomass-fired district heating not only creates markets for wood resources, but also increases themarket price of biomass due to growing demand. From the countrys perspective, this is positive for local economicdevelopment, job creation and fiscal revenues.TA to the government andthe regulator to create an attractivelegal, regulatory, and institutional environment for biomass trading could significantly help the scale up ofbiomass-firedheat and power generation.(ii) Political economy factors canhinder improvementin financialviability andneed to be addressed duringpolicy dialogue among key stakeholders. The project impacton thefinancial health of DH companies has been smaller than expected.The average cost recovery rate increased from 15% to 25%instead of the target 80%.The Government willingness to move the heating sector towards cost-recovery has been slow, and theheat tariffs were not raised as quickly as expected for political reasons. The difference between the costs and the tariffs iscovered by subsidies, and heat supply represents only a part of the utilities business.Heat tariff reforms couldhave been more successful if a broad communication campaign and dialogue at different policy-making levels were organized, but thiswas not part of the project.
P146243 | Resiliance and Growth Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/878801528388897248/text/Poland-PL-DPL-Resiliance-and-Growth.txt | http://documents.worldbank.org/curated/en/878801528388897248/pdf/Poland-PL-DPL-Resiliance-and-Growth.pdf | Lessons are drawn from the ICR with some adaptation of language.Development Policy Lending (DPL) can helpmitigate global economic and financial shocks and protect vulnerable groups. The main benefit of the DPL was not thecost-efficiency of Bank financing at the time of crisis, but strengtheninglonger-term reforms for inclusive growth. The DPLseries was appropriate at the time as an important market signal after the financial sector crisis and to reinforce the credibilityofthe authorities commitment to reform; and to provide technical solutions for design and implementation of theirreforms. The DPLs created space for policy dialogue and enabled conducting innovative analytical and advisorywork.The DPL program responded well and in a timely manner to the Governments ownpriorities.. Facing a weak external environment, the government focused on adopting short- andmedium-term growth-supporting measures, while maintaining a fiscally prudent stance. To sustain the recovery, the authoritiesprioritized actions to strengthen public finances and financial sector oversight. These were followed by reforms aimed atbolstering the economys long-term competitiveness (such as enhancing labor market flexibility,raising participationrates, and improving the business environment especially through the promotionofinnovation.)The Bank focused its support in areas where it has a solid knowledgebase and which were strategic. The DPLs not only created space for policy dialogue but also enabled innovative analyticaland advisory work, including on a reimbursable basis. DPL engagement in a relatively high-income country must be based on astrong foundation of shared priorities, and high quality and cutting-edge analytic work (including just-in-time TA, impactevaluations, customized analytic notes). The DPLs played a key role in terms of the embedded knowledge transfer on how to tacklecomplex long-term structural priorities and restore fiscal buffers. An excellent example is the permanent expenditure rule,sophisticated and, at the same time, a relatively apolitical instrument to achieve and maintain fiscal prudence over the businesscycle and assure long-term sustainability of public finances.
P146243 | Resiliance and Growth Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2019 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/340071559242287976/text/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/340071559242287976/pdf/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.pdf | Lessons 8.2 The Independent Evaluation Group draws the following lessons\. â€¢ Development policy lending can help mitigate global economic and financial shocks and protect vulnerable groups in high-income countries when accompanied with timely, high-quality, and responsive technical assistance that supports the reforms. The series were appropriate to reinforce the credibility of the authorities' commitment to reform, while providing technical solutions for the reform program's design and implementation. The DPLs enabled dialogue on important reforms the government was undertaking based on its analytical and advisory work. â€¢ Where a high-income country is required to implement constitutional provisions, or agreed reforms with a regional body, providing support for the implementation of such reforms is likely to enhance the likelihood of success. In the case of Poland, policies limiting fiscal deficits and overall debt levels were required both by EU agreements and constitutional provisions. Though these policies were complex, the government committed to implementing them because of the importance of EU accession agenda to Poland's economy. However, policies not so required by the EU were more easily reversed, for example, the increase in the retirement age. â€¢ RAS are a promising tool for engaging governments in high-income countries when Bank Group staff demonstrate the capacity to produce timely and highquality analytical products in response to government requests. In the case of Poland, the government appreciated the quality and responsiveness of World Bank staff to their analytical needs. However, World Bank adjustment to the different business model could have been better managed. Staff had the (sometimes difficult) task of explaining to the government why the World Bank needed to charge high-income clients for services, while still requiring sole source procurement and retaining intellectual property rights. The World Bank and government are now working together to make RAS mutually beneficial and a new tool for engagement. â€¢ Coordinating with other partners in situations where the World Bank is not the largest stakeholder is important for successful implementation of reforms. In the case of Poland, the EC and the IMF are the dominant development partners providing more funds or guaranteed resources to the government. â€¢ Analyzing the political cost of implementing proposed reform measures is an important part of policy lending. Such an analysis would have been particularly useful in relation to the pension and labor market reforms these two series attempted to support. It is notable that Ministry of Finance staff requested such advice in the future to guide the implementation of new reforms.
P146244 | Promoting Innovation for Inclusive Financial Access | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2014 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/745001609405636869/text/Egypt-Arab-Republic-of-Promoting-Innovation-for-Inclusive-FA.txt | http://documents.worldbank.org/curated/en/745001609405636869/pdf/Egypt-Arab-Republic-of-Promoting-Innovation-for-Inclusive-FA.pdf | The first two lessons are drawn from the ICR (pages 34-35), with some adaptation; the third is offered by this ICR Review.Technical assistance is especially valuable in SME finance projects, where the focus is on financial innovationand non-bank financial institutions. This project benefitted from the provision of technical assistance from theBanks and the International Finance Corporations Middle East and North America MSME Technical Assistance Facility as wellas from South-South collaboration withIndia (theSmall Industries Development Bank) and Malaysia (the MSECorporation Malaysia, among others). The government enacted Law No. 176 in 2018 regulating financial leasing and factoringactivities, replacing Law No. 95 of 1995 on financial leasingand Ministerial Decree No. 446 of 2003 onfactoringactivities. The lesson is that availing of expert advisory services, the MSMEDAestablished a specializedInvestment and Venture Capital Departmentin 2015 and launched the Venture Capital Program to pilot venture capitalactivities.Having a capable and experienced apex institution for a line of credit operation facilitates theexpansion of the operations scope and scale. The MSMEDA (thenthe SFD)was the implementing agencyfor the Egypt Enhancing Access to Finance for Micro and Small Enterprises Project from 2010 to 2015. Thatproject aimedtocontribute to a sustainable improvement in inclusive access to finance for MSEs on a commercial basis andprovidedUS$300 million for MSE financing by banks and microfinance institutions. Thisproject expanded the scopeof the predecessor operation, embracing the participation of non-bank finance institutions, introducing leasing, factoring, andventure capital products, and focusing on women-owned and youth-owned MSEs and MSEs in lagging regions of the country. Thelesson is that MSMEDAs previous experience and record as an apex institution for an MSE line of credit, including itsfamiliarity with Bank standards and operations, helped with the design and implementation of this project.This reviewsuggest the following additional lesson.Providing MSE financing on a commercial basis, even as thetargets are the riskier segments of the market, remains vital to keep MSE financing sustainable. Thisoperation placed a special focus on women-owned MSEs, youth-owned MSE, and MSEs in lagging regions of the country. In lendingprograms with social impact dimensions, it remainsvital that financing be provided on a commercial basis and avoidintroducing market distortions or promoting entitlement programs. This project successfully used commercial banks,microfinance institutions, leasing and factoring companies, and venture capital companies as financial intermediaries. TheBank also prescribed the use of participation agreements, sub-financing agreements, and a Project Operations Manual that emphasizedsub-project appraisals as well as lending and investment decisions that were in accordance with market principles.
P146247 | Mali Obsolete Pesticides Disposal and Prevention Project | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2016 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/910871602539474353/text/Mali-Mali-Obsolete-Pesticides-Project.txt | http://documents.worldbank.org/curated/en/910871602539474353/pdf/Mali-Mali-Obsolete-Pesticides-Project.pdf | The ICR (p. 29-30) included several lessons learned which were adapted by IEG: Mainstreaming pesticidemanagement across agriculture projects and emergency projects, which procure large quantities of pesticides, might have a positiveimpact on the governments capacity to manage pesticides. Also, supporting governments in adopting thevoluntary International Code of Conduct on pesticide management and complying with its key articles will have a positive long-termimpact. Ensuring sustainable financing for pesticide management is essential to avoid any re-accumulation of newOP stocks. In Mali, it was critical that the government continue to financially support the CNGP to ensure the completionof two studies which were to define the characteristics relating to the long-term structure of pest management and sustainablemanagement and funding methods.
P146248 | Deposit Insurance Strengthening Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2014 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/776481537371621228/text/Serbia-Deposit-Insurance-Strengthening-Project.txt | http://documents.worldbank.org/curated/en/776481537371621228/pdf/Serbia-Deposit-Insurance-Strengthening-Project.pdf | The following are the main lessons that can be derived from the projects implementation experience (derived from the ICR,pages 18-19, with some paraphrasing):Combining results-based financing and technical assistance canbe effective for implementing reforms and building capacity in a sustainable manner. In this project, thedisbursement-linked indicators (DLIs) provided the impetus and financial incentive to implement reforms, while the specificallytailored technical assistance activities proved to beuseful in supporting the implementing agency, the Deposit InsuranceAgency (DIA), in achieving the targetsof each of the DLIs.Corporate governance reforms areessential for addressing the depletion of deposit insurance funds.Corporate governance challenges in threestate-owned banks that failed were largely responsible for the depletion of the Deposit Insurance Fund (DIF) in Serbia. The DIAitself had suffered from corporate governance problems in the past.As a result of this project, the DIA cites the followingas its most important achievements: (i) the appointment of independent board members to the DIAs Managing Board; (ii)the appointment of an Executive Director; and (iii) the creation of a Board of Directors with delineatedresponsibilities.World Bank operations can be instrumental in capitalizing deposit insurancefunds. The project was the first World Bank operation that re-capitalized a depleted deposit insurance fund,thusdemonstrating a novel way of engaging in the financial sector and responding to crises. This was achieved byextending OP 10s requirements on productive use to include an expenditure into a fund as an eligibleexpenditure. While three other World Bank operations have built on this projects success and have been approved (i.e.,the Bulgaria-Deposit Insurance strengthening Project; Bosnia and Herzegovina-Banking Sector Strengthening Project; and Serbia-StateOwned Financial Institutions Strengthening Project), further guidance is required on whether such operations should always bedesigned with Disbursement-Linked Indicators.The close and strong collaboration between the WorldBank, the International Monetary Fund, and the European Bank for Reconstruction and Development proved instrumental in ensuringthat substantialbut difficultreforms were indeed being implemented. The project was part of a broader reviewof bank resolution and deposit insurance that involved the World Bank, the IMF and EBRD. This joint effort included a broaderregulatory reform of the set of financial laws that were passed by the Parliament in February 2015 and are being applied as ofApril 1, 2015. The World Bank, IMF and EBRD ensured that the programs were closely aligned and coordinated and oftenconducted missions jointly.
P146250 | Djibouti: Governance for Private Sector Development and Finance Project | Middle East and North Africa | Djibouti | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2014 | 2021 | 2023 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061923140513334/text/P1462500437a3701b0ba050807cb53debd9.txt | http://documents.worldbank.org/curated/en/099061923140513334/pdf/P1462500437a3701b0ba050807cb53debd9.pdf | The ICR listed eight findings, lessons and recommendations, from which this review selected two lessons of particularimportanceto project implementation as rephrased to some extent below.i) A project implementation unit(PIU) needs competent leadership and staffing. As for most World Bank operations in this project a PIU was tobe used to implement this project. The establishment of the PIU and its staffing was a condition of effectiveness. A PIU waschosen and staffed but its performance fell short of expectations because oflack of appropriate skills and motivation. Afterrestructuring, with the leadership of the Ministry of Finance and close technical assistance of WB experts, the project team wasable to reorganize, improve staffing and deliver the reform action plan through sectoral andtechnical workgroups.The lesson is that PIU selection needs tobe underpinned bya sound and thorough review of therequired capacities to run a specific project, and then allocate the requiredhuman, financial, andtechnicalresourcesto support a projects activities throughout allphases. Without attention to such details projectimplementation will almost inevitably be hampered.(ii) StrongBank management and local staffing are key tosuccessful implementation asthey provideproximitysupport to the client and mitigate crisis situations.When the COVID-19 pandemic hit with the associated travel restrictions, the presence of a dedicated expert in the Banks fieldoffice was crucial for the projects successful implementation. Moreover, theBank staff played a key role in supportingproject implementation in difficult contexts. The Bank also worked with the Government, the National Agency for the Promotion ofInvestments (ANPI), and the PIU to find practical solutions for the various project management challenges in order to ensureon-time delivery.
P146280 | AL Financial Sector DPL | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2014 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/973461468010219908/text/ICRR-Disclosable-P146280-06-10-2016-1465565684659.txt | http://documents.worldbank.org/curated/en/973461468010219908/pdf/ICRR-Disclosable-P146280-06-10-2016-1465565684659.pdf | IEG agrees with the following three lessons identified by the ICR and rephrased below:(i)It isimportant for the Bank tomaintain a continuous engagement with its clients even whenthe lending portfolio is small orinexistent. As theBankcontinued to supportknowledge sharing activities (the 2013 FSAP, technicalassistancewith the bank of Albania), itwas able to react quickly to the pressing needs in the financial sector duringthe preparation phase of this operation, and the team succeeded to build sufficient ownership of the many policy and regulatorychanges. Continuous engagement put the Bank in a positiontoadapt and respond raipidly to the clients needs andeconomic realities.(ii) Having key stakeholders on boardfacilitatesthe DPOimplementation.Thispoints to the need to carefullyidentify and recognize in advance the ability of groups ofstakeholdersto lobby with authorities (government and parliament) and factor their interestsin the scope of the reformagenda. This allowsthe authorities and the WB to discuss freely the issues affecting theinterest groupsand, if nocommon understanding is reached with them, raise adequate safeguards and understanding with the decision makers to push the reformagenda forward. Alignment of key policy makers and a high level commitment to the reform agenda by all stakeholders are key to thecompletion of relatively ambitious prior actions, and should be considered carefully at the designphase.(iii)Regular coordination with otherdonors and partnerspositivelyimpactsthe expected outcomes.The Banks consultation with other international agencies (IMF, USAID, and EU) provedessential to the performance of the operation, given the extensive technical assistance that needed to be aligned with thecountrys and sectors priorities. In particular, this operationbenefited extensivelyfrom IMFssupportto knowledgesharing activitiesand the three-year EFF program. This program has ensured the adequacyof the macroeconomic framework by helping Albania to meet its external financing needs, while providing the necessary support tostrengthen fiscal and debt sustainability.
P146294 | TOGO - Education and Institutional Strengthening Project 2 | Western and Central Africa | Togo | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/840881621612182820/text/Togo-Global-Partnership-For-Education-Program.txt | http://documents.worldbank.org/curated/en/840881621612182820/pdf/Togo-Global-Partnership-For-Education-Program.pdf | A realistic understanding of capacity on the ground and the launching of mitigation measures at an early stage arecritical for yielding results. As pointed out in the ICR, issues that contributed to delays in the procurement oftextbooks and teacher guidescould have beenfactored into the timelines formation, and a more streamlinedprocurement approach wouldhave spedup the process. Similarly, early training of project staff on World Bank procurementrules and procedures would also have removed obstacles.Capacity building requires ongoing attention and continuousefforts. The ICRnoted that the one-time training on the use ofelectronic tablets provided to inspectors wasnot sufficient for utilizing the benefits from thetechnology. On the other hand, findings from inspectors classroomobservations helped identify difficulties confronted by teachers, who also benefited from follow-upsupport.Local communities can play a positive role when engaged and enabled. The ICR found that thecommunity-based approach contributed to the quality and efficiency of school construction. Training provided to COGEP membersallowed the COGEPs to play a significant role in supervising and monitoring at the school level.
P146314 | Climate Resilience Improvement Project (CRIP) | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099205005232226921/text/P14631407241140f708bcf017ace64fd2a2.txt | http://documents.worldbank.org/curated/en/099205005232226921/pdf/P14631407241140f708bcf017ace64fd2a2.pdf | The following lessons have been derived and summarized from the ICR, with minor additions by IEG after discussions with the Banktask team:The production of communication and learning materials as integral part of thedevelopment of complex technical modelling tools for disaster risk managementmay help in the understandinganduptakeof the highly technical modelling outputs. This projectdevelopedcomplexand often interlinked models necessary to implement the basin investment plans jointly with comprehensive communication andlearning materials. Theseincluded, for instance manuals, specialist training, and guidance onhow to use and updatedatabases.These materials aimed at simplifying the understanding around these complex tools and ensuring that they are usedin decision making by a wider audience who would benefit from the outputs.Inadequate attention to capacitybuilding of institutions in charge of post-project management of investments and not involved in project implementation canendanger thesustainability of project outcomes. In this project, for instance, the school landslide mitigationmeasures were carried out byNational Building Research Organization and then handed over to the provincial educationdepartments, whichis responsible for school infrastructure. The education departments were not involved in projectimplementation and only receiveda maintenance manualfor slope protection, but no training to provideadequatemaintenance. According to what the Bank task team mentioned to IEG, initially this was because they were not IAs and later alsobecause Covid19 did not allow to carry out training activities.This resulted in inadequate maintenance of the newinfrastructure.Insufficient attention to weatherevents in civil works contract conditions andimplementation might cause project delays and cost increases. The project did not adequately adoptand strictlyenforceclimate risk-informed work planning because it did not sufficiently factorin rainfall seasonalityand waterissuance in civil work implementation. This interruptedthe civil works several times a year,causing implementationdelays. The absence of technical experts to procure and supervise the high-value and technicallycomplexbasin investment plans contracts from the beginning may cause project implementation delays. This projectinsufficiently factored in the need for adequate technical capacity from the outset to procure andmanage thehigh-valueand technically complexbasin investment plan contracts. The technical capacity required toprepare terms of referenceand bidding documents, evaluateproposals for such contracts requiredexperienced procurement specialists, PMU staff, andtechnical evaluation committee members, which initially did not exist. In addition, the project initially also did not havesufficient capacity in the PMU to manage this complex work and ensure quality control. All this caused delays in projectimplementation.Having a central PMU with experienced staff to take care of Bank requirements andsupportmultiple IAs in a multisector project may enhancecoordination and facilitate smooth project implementation.Theimplementation arrangements of this projectincluded a central PMU with a project director and fiduciary, safeguards, andME staff and different IAs with deputy project directors. The PMUworkedtogether with thestaff intherespective IAs. While coordination among the different IAs, as in all multisector projects,waschallenging,thisarrangement helped overcome the challenges and ensured efficient coordination, ownership, and smoothproject implementation.
P146319 | Development Finance Project | Western and Central Africa | Nigeria | Blend | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2015 | 2023 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111124130531406/text/P146319-f099c304-1167-4d42-9260-6b8d8dafb5f4.txt | https://documents.worldbank.org/curated/en/099111124130531406/pdf/P146319-f099c304-1167-4d42-9260-6b8d8dafb5f4.pdf | The ICR identified a number of relevant lessons. Some of the key lessons are rephrased in the paragraphsbelow.Establishing a wholesale DFI that does not directly engage in retail lending or take on credit risk cancontribute to promoting MSME finance without crowding out private sector lenders. Overall, the DBN providedliquidityand promoted the development of a robust MSME finance ecosystem without directly competing with private lenders. The DBN focused onproviding wholesale financing to PFIs for on-lending to MSMEs, allowing the PFIs to take on these credit risks. By adopting thisapproach, the DBN played a catalytic role in promoting MSME finance without crowding out private sector lenders. The DBN avoidedthe practicesof distorting the market through subsidized or quasi-fiscal support and operated a flexiblemodel thatoperates on market terms.Strong and independent corporate governance and controls can contribute tofostering a DFIs ability to increase outreach and additionality. The DBNs founding by-laws underscoreditsfocus on MSMEs, financial sustainability objectives, and independent corporate governance, despite the Governmentbeing the largest shareholder. Board and executive management positions were appointed through acompetitive selection processbased on professionalexperience, and independent non-executive directors were always the majority to ensure that decisionsrely ontheir expertise. This framework ensured that the DBN remainfocused on channeling wholesale funds to eligiblePFIs for on-lending to MSMEs. The DBNs example underscores that strong governance structures and operational controls areindispensable for DFIs to effectively carry out theirmandate.Sustained support from the Government and itsentities can contribute to ensure the success of a DFI wholesale lending operations, including an efficient pricingstrategy. Since its inception, the DBN received invaluable support from the Nigerian Government, including the assistancewith hedging funds and mitigating exchange rate volatilities. Continuity of such support wascrucial for the de-riskingoperations and amplifying impact, especially among underserved market segments. From a regulatory standpoint, the project enjoyedcommendable support, highlighting the significance of a conducive regulatory environment.Â Furthermore, experience has shown theneed to revisit the pricing philosophy of lending above the inflation rate. In a high-inflation macroeconomic context where MSMEsoperate, adhering to a pricing principle that exceeds the prevailing inflation rate can make the DBNs facilitiesunattractive to PFIs. Consequently, a reassessment of the pricing strategy is warranted to align with market realities and enhancethe attractiveness of the DBNs offerings to PFIs, and ultimately, MSMEs.
P146322 | Turkey Sustaining Shared Growth DPL | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2015 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/679961529969453804/text/Turkey-Turkey-Sustaining-Shared-Growth-DPL.txt | http://documents.worldbank.org/curated/en/679961529969453804/pdf/Turkey-Turkey-Sustaining-Shared-Growth-DPL.pdf | The following lessons arefrom the ICR (p. 21-22): ADPO engagement in an uppermiddle-income country like Turkey needs to be based on shared priorities and high quality analytical work. The valueproposition for the Government was less about the Banks financial resources and more about the programming process,associated analytical support (including just-in-time technical assistance, evaluations, analytical notes etc.), and the overallsignaling effect. A programmatic structure helps to anchor policy actions to theoverarching development priorities and ensure continuity through different operations. Based on the experience of theoperation, two factors appear to be of particular importancein ensuring successful implementation of a programmatic series:(1) Identifying risks that might materialize over a longer time horizon relative to a standalone operation with well-developedmitigating measures; and (2) careful balancing of policy actions across successive operations with room for flexibility, avoidingbeing overly ambitious from the start. Establishing clear linkages between the policyactions and indicators is essential to assess the performance of an operation. To this end, the indicator, target impactand the observation period should be carefully selected to make the attribution of the observed impact to policy actions possible.For instance, in labor informality, a very high-level indicator was defined with only marginal intended impact over a shortobservation period, which made attribution difficult. In programmatic developmentpolicy financing operations, regular monitoring of implementation status and performance would support and enhance the finalreporting, particularly when the implementation period for the entire series is long and teams change. In this case, therewas not enough evidenceof systematic monitoring of program-level progress. Even though the team was required to submitimplementation status and results reports on a 12-month cycle and before the first operation was closed, none waspreparedduring the life of the operation.
P146328 | Pap-Angren Railway | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/331221619195606129/text/Uzbekistan-Pap-Angren-Railway.txt | http://documents.worldbank.org/curated/en/331221619195606129/pdf/Uzbekistan-Pap-Angren-Railway.pdf | IEG uses the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The difficulties associated with Bankengagement in project activities, where it has limitedfinancial leverage, needto be carefully assessed at appraisal.The leverage of the Bank in this project waslimited, in view of its relatively low contribution to project activities. The lesson from this project is that, while the Bankmust take some risks in order to enter new areas of engagement, it should assess the institutional and sectoral engagement moreattentively at appraisal.2. Sufficient time to train stakeholders in therequired Bank instruments suchas Resettlement Policy Frameworkand Resettlement Action Planis especially required insituations, where theapplication of safeguards is complex. In this project, the implementation of resettlement depended on a governmentapproach that was disjointed, inadequately funded, and hampered by weak capacity. The Banks resettlement rules wereretroactively applied to a major rail line that had beenmostly completed. This did not leave sufficient time to train thestakeholders in the Banks resettlement policies and procedures.3. Post impact evaluations couldbeespecially of high valuefor projects of a large financial, geographic, and socio-economic magnitude. In thisproject, while an evaluation was conducted at appraisal, there was no ex-post evaluation once the new rail line became operational.This precluded the extent to which the project contributed to socio-economic benefits and alleviating poverty.
P146332 | Myanmar Decentralizing Funding to Schools | East Asia and Pacific | Myanmar | IDA | FCS | Human Development | Education | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040424110023367/text/P1463321f8dbf10ed18dcc18eafe207e454.txt | http://documents.worldbank.org/curated/en/099040424110023367/pdf/P1463321f8dbf10ed18dcc18eafe207e454.pdf | TheICR (pp. 35-36) offered lessons and recommendations, including the following lessons re-stated by IEGReview: The projects support for decentralizing funds was, among other things, a tool to promotepeace and inclusion. In 2017, conflicts in Rakhine state broke out but did not stop project implementation. The ICR notedthat local authorities in Northern Rakhine state were cooperative and used national funding to reach their townships, promotingdialogue between the central and local authorities and bringing local groups together. The project benefitedgreatly from its simple design in the context of unknown or low institutional capacity. The projects decision tosupport the already established framework and system that the MOE had for the school grants and student stipend programs played akey role in fast execution and smooth implementation. The MOE was familiar with the implementation structure and benefited fromadditional financial resources and technical assistance to increase the projects scope andscale. One uniform ME framework among development partners, MOE, and the World Bank strengthened datacollection and utilization. This uniformity facilitated a practical approach for addressing bi-annual ME WorkingGroup meetings and the Technical Working Group meetings where all concerned partners participated to confront arising issues andoperational challenges.
P146344 | Nepal: Grid Solar and Energy Efficiency | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099032624180041467/text/P14634415a56c806319fd41dbee512ba51d.txt | http://documents.worldbank.org/curated/en/099032624180041467/pdf/P14634415a56c806319fd41dbee512ba51d.pdf | This review draws two lessons based on the information in the ICR.Future projects on loss reduction shouldfocus on developing capacity for measuring loss reduction. Ensuring that the implementing agency has the technical abilityto accurately measure distribution losses is critical for tracking the impact of investments targeted at reducing system losses.Although the investments and distribution centers prioritized by the DMP and DLRMP turned out to be valid for loss reduction, theabsence of appropriate tools and systems for data collection on losses in those areas resulted in an inability to assess the impactof the project on loss reduction in the selected areas. Hence, future project teams should establish that the capacity to assessloss reduction is put in place prior to undertaking further investments.Like the GSEEP, projects in fragilecountry settings should pay attention to land access issues. In fragile countries like Nepal, property rights are oftenpoorly defined or weakly enforced. For this reason, project implementation involving land acquisition from private landowners areat risk of delay or derailment if ownership rights for such lands are disputed or if implementing agencies face difficultnegotiations with private landowners. To avoid these issues, project teams should consider limiting project activities to publiclyowned lands. However, the process of securing approval from public authorities for the use of public land can be lengthy. Hence,the process to obtain government approval should begin well in advance to avoid delays in land acquisition andproject implementation.
P146398 | Second Climate Change DPO | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2015 | 2015 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following three lessons learned which had general applicability beyond this project were, with some editing,derivedfrom the ICR:1. Progress on climate change-related policy and institutional reforms requireseffective inter-sectoral coordination and dialogue because climate change affects many sectors. For example, inMozambique, building upon the coordination functions of Ministry of Planning and Development and Ministry of Environmental Affairs,the preparation of the National Strategy for Adaptation and Mitigation to Climate Change strategy marked a significant shift andprovided the initial platform for inter ministerial collaboration (ICR, para 84).2. Highlevel engagement with the government, supported by strategic and targeted technical assistance, is essential to achieving reformson climate change. While the World Bank had given technical assistance to various sectors in Mozambique, engaging with theMinistry of Planning and Development and the Council of Ministers ensured that climate change policy reforms was a prioritydevelopment issue (ICR, para 85). Moreover, having a coordinating body helped ensure that sector-level climate changepriorities were discussed and resolved by the Council of Ministers (Bank task team).3. Toensure sustainability of reforms climate resilience needs to be mainstreamed into sector strategies and be reflected in actualbudget. For example, policy actions strengthening the extension service to promote the uptake by farmers of conservationagriculture. This led to a new risk management capacity within the crop production department, and the opening of the extensionservice to the private sector for services, related to conservation agriculture (ICR, para 88)
P146451 | Sindh Global Partnership For Education Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2018 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/972381565011723288/text/Pakistan-Sindh-GPE.txt | http://documents.worldbank.org/curated/en/972381565011723288/pdf/Pakistan-Sindh-GPE.pdf | Defining a solid theory of change with valid and measurable indicators is key to assessing a projectsoutcome. In this project, it was difficult to measure achievement of PDO 3 without a proper indicator. The data on someindicators were also problematic given inconsistencies in definition andlack of clarity inmeasurement. Furthermore, thelack of an explicit results chain linking specific inputs and outputs to corresponding outcomes made itchallenging toattribute outcomes to inputs. For examples, education sector salary expenditure and non-salary expenditure were regarded asintermediate outcome indicators without a specific explanation of what specific project activitieswere envisioned toleadto anincrease in salary expenditure.Proper institutional arrangements and cooperation amongrelevant government agencies is critical for enabling and maintaining results.This projects delay indeveloping the B-HRMIS was partially caused by reassigning responsibility to a new unit. Due to legal issues that emerged duringimplementation, the Reform Support Unit was replaced by a newly established Directorate on Human Resources and Training.Cooperation among agencies was sometimes weak, which hindered achievement of results in some cases. The B-HRMIS relies on dataregularly provided by the Accountant General Controller, but a reliable system for regular provision of datahas not yet beendeveloped.Client commitments and ownership matter greatly in delivering and sustainingresults.Alack of stable and committed leadership at the Directorate on Human Resources and Training hasimposed risk on continuing operations of systems developed by the project. Moreover, the performance-based mechanism promoted bythe project has received resistance from those with vested interests (those who are reluctant to have their performance measured,and those who benefit from resource allocation inefficiencies). Confronting such resistance will require strong leadership from thegovernment as well as a sense of ownership felt by schools and local communities.
P146452 | Rwanda Third Support to the Social Protection System (SSPS-3) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following lessons learned are derived from the ICR:Coordinated efforts across developmentpartners well aligned with Government priorities provide important support to reforms. Although always the driver of thereform effort, the GoR counted upon needed financial and TA supportfrom its development partners,all under awell-coordinated and functioning donor-government group, the SWG, using regular backward- and forward-looking JSRs to ensurecollaboration in monitoring progress and in implementing well-coordinated policies and programs.Aprogrammatic DPL can provide a powerful instrument in establishing an efficient integrated safety net, responding flexiblyto support its evolution. Several factors facilitated the success of the programmatic DPL: The sectoral policyreforms were central to the World Banks CPS, complementary to and well-coordinated with other World Bank-financed operationsand non-lending services, and accompanied by critical TA needs. Effective development partner coordination, throughpolicy support to the Government, implementation support, technical support, and external consultants, provided mostly by the donorpartners, was achieved under the framework of the SWG. Implementation of the SSPS Program was characterized by acontinuous process of implementing, monitoring, evaluating where possible, analyzing, and adjusting based on lessonslearnedthe programmatic nature of the DPL allowed the flexibility to constantly refine, adjust, and adapt the program toimplementation experience and newly identified priorities and challenges.Development of consolidated MISrequires several iterative steps and takes time. Programs and projects that support this type of activity shouldfactor this into implementation schedules. A corollary lesson is that if broad, ambitious visions are developed, these need to beaccompanied by clear, achievable implementation plans based on a thorough understanding of needs, use cases, and institutionalcapacity.IEG observation:A programmatic DPL can provide the continuity that isnecessary to put in place and develop a comprehensive safety net that aims at promotion as well as protection. This isespecially the case when building a system from scratch in an environment of constrained resources. It offers the security ofpiloting and gradual expansion of a program; and the gradual introduction and harmonization of multiple programs. It may beparticularly useful in allowing the build-up of targeting systems and registries over a period of time, explore delivery methods,and develop links with sector ministries and agencies that affect both supply and demand.
P146460 | Jamaica Integrated Community Development Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099905003312278414/text/P146460062e741098092cd08f052d41d9cc.txt | http://documents.worldbank.org/curated/en/099905003312278414/pdf/P146460062e741098092cd08f052d41d9cc.pdf | The ICR presented 5 lessons that other teams may benefit from when designing projectsthat transform vulnerablecommunities. These lessons are presented below with slight modificationin language. Volatilecommunities may be transformed by using an integrated multi-sector model of violence prevention. In this project,infrastructure investments and serviceswere improved in under-serviced and volatile communities. These community prioritieswere accompanied by social interventions directed at the family, youth, schools, and community levels to build human capital andpromote public safety. At the same time, the project enhanced the capacityof institutions in preventing violence in thesecommunities. Design flexibility allowed residents to participatein identifying and prioritizing these infrastructureinvestments and services. Implementation proved challenging because of the numerous stakeholders, multiple small-scaleprocurements, and resulting demands on the implementing entity. At MTR, priorities were refocused to make the remaining activitiesconsistentwith the socioecological model of violence prevention. That reprioritization exercise helped achieving some outputtargets. Future interventions may benefit from integrating strategic psychosocial support at the designstage, and separately tracking its impact. In this project,social interventions accompaniedphysicalinvestmentstoincrease public safety. Activities evolved asdemand for psychosocial needs were identified. Forexample, alternative livelihood skills training for youth, positive parenting training, and capacity building support for schoolsto strengthen critical incident management were reconfigured as needs were expressed.The project did nottrack thebehavior changes adopted bythe beneficiaries receiving psychosocial support that couldinformfuture similarinterventions. Transparency, community engagement, and buy-in form part of an effectiveproject design.In this project,consistent and inclusive community engagement started at design stage andthroughoutimplementation. Engagement allowed design to better understandand validate community concerns.Residentsprioritized investments at project entry. Targets were adjusted as cost overruns were realized while the communityremained engaged throughvarious project communication mechanisms and participatory channels (SDCs, CDCs, and CBOs). When implementing community development projects with multiplecomponents,sequencinginvestmentsallowsproject beneficiaries to see early results. This sequencingbuildstrustand public buy-in. In this project,foundational work under the community outreach and social inclusionpackage of interventions designed to contributeto public safety. By mid-term, visible results in the solid waste agendaincluded i) operational institutional arrangements, ii) solid waste-related infrastructure in place, and iii) communities reportedto have adopted cleanliness practices (albeit without supporting evidence). Sustainability of project resultsrequire commitment and collaboration among various stakeholders. In this project,the following stakeholderscollaborated to achieveresults:the implementation agency (JSIF), CBOs, the local governments, and the multipleministries, departments, and other agencies (MDAs) directly linked to sectors (such as planning, SWM, water and sanitation serviceprovision, and public lighting). Engaging the MDA stakeholders was critical to manage expectations, reachagreements,addressissues that arise,especially regarding OM needs. A few incentives and institutional arrangements were inplace, such as the RBF scheme for SWM that involved communities, CBOs, and the NSWMA. Successvariedbased on capacities,agendas, and timelines. The incentives were designed match the institutional complexities. Improvements ingovernanceand coordination relied on strengthening partnerships across government and non-government actors..
P146469 | Senegal Tourism and Enterprise Development Project | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099081123172042218/text/P146469007cb5305b082e00779164e9641f.txt | http://documents.worldbank.org/curated/en/099081123172042218/pdf/P146469007cb5305b082e00779164e9641f.pdf | Three lessons are drawn from the ICR, with some adaptation.Consultation with stakeholders in project localitiesearly during the project design process can produce major benefits for the stakeholders. In this project, earlyconsultation and collaboration with the beneficiaries of the Saly beach restoration and protection hotels and fishingvillages led to the redesign of the original approach of quarrying for sand onshorein favor of sourcing sandoffshore. The decision led to less disruption of economic activity in the project areas, less air and noise pollution, lowercompensation cost for affected property owners, and higher beneficiary satisfaction.When the capacity andreadiness of project implementing agencies arethoroughly assessed prior to project approval, interventions can be designed toaddress their institutional shortcomings. In this project, the quality and pace of project implementation wassignificantly affected by deficiencies with the implementing agencies. The capacity of the Ministry of Tourism and AirTransport to manage some project activities and to coordinate with Senegal Coastal and Tourism Zones Development Agency and theSenegalese Tourism Promotion Agency was overestimated. The Agency for the Promotion of Investment and Major Works lackedstaff for procurement and financial management. Corrective actions were eventually taken during project implementation, butsignificant delays with project activities affected the achievement of the project developmentobjectives.Supporting enterprise creation is feasible but requires more than financial assistance to start-upentrepreneurs, including careful assessment of entrepreneurs, provision of flexible advisory services, and continuous monitoring ofenterprises. In this project, the Business Plan Competition awarded equity grants to 146 winners of the firstcompetition, 69 percent of which survived two years after receiving their grant awards. The project experience showed thatnew entrepreneurs need to be evaluated carefully prior to selection, provided professional advisory services, and monitored closelyduring their operating lives. They also need flexible business development services and enterprise support systems thatrecognize their status as start-ups and the complex risks in enterprise creation. The Bank should design simplifiedprocedures, while recognizing that a sizable number of new enterprises will not survive. The competition should speed up theprocess of paying out the grantawards (equity seed funds) to improve the likelihood of enterprise success. A focus ontechnical assistance (project resources were reallocated to technical assistance at restructuring) was vital.
P146474 | Guinea - Stepping Up Skills Project | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040524194541566/text/P146474134157302019a8813cf938710e44.txt | http://documents.worldbank.org/curated/en/099040524194541566/pdf/P146474134157302019a8813cf938710e44.pdf | The ICR provided several lessons (p. 35) which have been adapted by IEG: Complex implementationarrangements require a sound communication strategy to ensure smooth implementation. This project experiencedimplementation delays due to its complex design that involved three ministries and a high turnover at senior management andcomponents including crossover functions that involved different ministerial departments. Strengtheningthe link between skills development and the industry allows for ensuring labor market relevance of trainees. In thisproject the Competitive Fund and the short-term training programs under the E2E programs were directly linked to the demands of thelabor market. Also, the training programs were developed with inputs from the industry/enterprises to ensure relevance. However,gaining a better understanding of how to track this alignment is essential for effectively implementing thisapproach. Communicating and marketing the value of technical and vocational education to targeted youths and thepublic might positively impact the demand for such skills development interventions. This project developed acommunication and marketing strategy to inform the public of the competitive fund, internships as well as available certificationswhich allowed to attract targeted youth.
P146482 | Ayeyarwady Integrated River Basin Management Project | East Asia and Pacific | Myanmar | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2015 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099112823093012662/text/P146482087fdee04b08ec700229cd8613fa.txt | http://documents.worldbank.org/curated/en/099112823093012662/pdf/P146482087fdee04b08ec700229cd8613fa.pdf | The ICR lists a number of relevant lessons drawn from the Projects experience. From these, IEG derives the followinglessons that are relevantfor similar projects implemented in comparable environments.Transitioning to a moresustainable and cost-effective river management strategy requires sufficient time for implementation of a step-by-step approach,including piloting new approaches and creating institutions. The Project assisted DWIR in shifting from investments inmore expensive rigid structures that do not offer any flexibility when morphological and hydraulic conditions in the river change,to an approach that is based on measurements and offers a mix of soft structures, where possible, and hard structures, wherenecessary. In addition, creating robust institutions that can sustainably maintain themselves in an FCV context may require alonger implementation period than the conventional period for a project. (ICR paras.97aand97b).Implementation risks can be mitigated through phased implementation and flexibility. In regardto the installation of river buoys on the Ayeyarwady River, experience from the installation of the first set of buoys fed intomaking design improvements in the subsequent batches of buoys, helping to optimize the operation and maintenance (OM)protocols at the onset of the wet season. (ICR para 97c).Investments in appropriate analytical tools can reducethe investment costs of river works. Development of 2D hydro-morphological models and utilizing them for simulationshelped DWIR in making informed decision-making on the most cost-effective approachto stabilize river channels and protectriparian communities against riverbank erosion. (ICR para. 97d).Effective hydro-climatic risk management requiresclose collaboration between Integrated Water Resources Management and Disaster Risk Management institutions at alllevels.The project successfully adopted the IWRM-DRM nexus as a central tenet in project design resulting inpositive impacts on both agencies, DWIR and DMH, and the NWRC as inter-ministerial water resources authority. Creating an IWRMframework was effective in sustainably managingMyanmars abundant water resources with impacts on economic growth andpoverty reduction. (ICR para. 97e).Utilizing the immediate response mechanism as a supplementary source forfunding procurement of equipment (in addition to that allocated under the Project) can create problems for seamless integration ofthe separately procured equipment into the overall systems utilized by the agencies (e.g the hydro-met system used byDMH). The Projects experience showed that it was not optimal to use the IRM to acquire some of the hydro-met systems that werealready planned under the Project. The IRM should have been useddifferently to support complementary activities.
P146512 | APEI Regional DPO (RI) | Other | Africa |  |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/986401562879086473/text/Africa-APEI-Regional-DPO-RI.txt | http://documents.worldbank.org/curated/en/986401562879086473/pdf/Africa-APEI-Regional-DPO-RI.pdf | The following lessons are drawn from the ICR:Alternative design optionsfor regional tradeoperationsshould be carefully reviewed. Alternative modalities should be carefully reviewed, and the reasonsfor the one selected carefully thought through, along with the reasons for rejecting alternatives. In the APEI operation, theconditions relating to country participation, notably their readiness in terms of macroeconomic adequacy, would come to The EU hasbeen facing this challenge for years, and inequality between APEI members, notably both cyclical and structural differences,reduced the scope of the operation, and ultimately led to cancellation of the planned follow-up operation. In the meantime,many of the potential gains that a strong economy such as Mauritius might have reaped from a one-country DPL, was lost, as noted inthe modest achievements of the operation.
P146520 | Income Support Program for the Poorest | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061323090589446/text/P1465200b7d18507108df50c74081082700.txt | http://documents.worldbank.org/curated/en/099061323090589446/pdf/P1465200b7d18507108df50c74081082700.pdf | The ICR (pp. 19-20) offered insightful lessons, including some re-stated here by IEG: Global experience showsthat the matching of conditionalities and cash transfers is a successful mechanism to achieve impact on human capitalindicators.The experience ofthis project shows that they can be decoupled. Demand for health servicescould still be substantial apart from the incentive created by cash transfers, if promotion activities are actively undertaken andquality facilities are available. Attention to quality of services is important to ensure impact in projectimplementation. While project design needs to be realistic, considering country capacity, outcomes need to include somemeasurement of quality.In the case of this project, the collection of data on child weight and height could have contributedboth to monitoring of services and to evaluation ofproject impact. Support forthe development ofcountry systems is critical for the long-term sustainability of social programs. The project contributed to the creationof an MIS that allowed for monitoring indicators on beneficiary access to services.In a similar manner, support fordevelopment of an information system to record maternal and child health indicators could have contributed to capacity to measureimpact and promote program sustainability. The demonstration effect of pilots can be an important tool tomotivate stakeholders to scale up programs that contribute to country strategic objectives.In this case, theShombhob pilot demonstrated that financing demand, while ensuring availability of quality services, could lead tosignificant results.This hands-on experience not only helped in the scaling up of the program, but also in generating aconsensus that such a program could be viable in the country. Simplicity of institutional arrangements canfacilitate successful project implementation.A program addressing child nutrition and cognitivedevelopmentwill inevitably require involvement of multiple stakeholders.However, project design can easily become toocomplex, making implementation difficult. Striving for simple institutional arrangements is therefore vital.
P146537 | Tenth Poverty Reduction Support Credit (PRSC X) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2015 | 2018 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible |  |  | It is easy to be beguiled by strong country economic performance and assume that policy integrity exists where it mightnot. Extensive in-depth analysis of political economy issues should be an integral part of DPL program design. Caution iscalled for before basing program design and policy actions on the doing business indicators. In this case, reforms to promoteprivate sector development should have focused on the misuse of Mozambiques capital stock by its SOEs, not on the number ofdays to start a business. A comprehensive private sector assessment should be the basis on which private sector development reformprograms should be based. Implementation capacity constraints should be meticulously evaluated and incorporated into DPOprogram design (ICR, 38-9).
P146567 | Sustainability and Competitiveness DPL 3 | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | IEG concurs with the main findings and lessons in the ICR, inter alia:(i) Small island settings areparticularly challenging for information technology enabled reforms. In the case of Seychelles, capacity and connectivity gapsdelayed and made difficult system development and adoption.(ii) The quality of the Banks overallengagement is crucial, including how various instruments such as analytical work, policy-based lending, technical assistance andinvestment operations, along with the work of other partners, reinforce and complement each other.(iii)Progress is possible in small countries with limited capacity using cross-sectoral DPL series, as long as care is given in definingappropriately scaled targets.
P146619 | Poverty Reduction Support Credit II | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  |  |  | This review broadly concurs with the 4 lessons from ICR, and offers additional suggestions:Lesson 1: Importanceof sustained measures for good fiduciary practices to be ingrained in government operations, which also underscores the needfor a thorough and systematic ex ante risk assessment of risks to achieving development objectives and articulation ofmitigation measures. Excessively overburdening the fragile and low capacity system with complex technical reforms (IPSAS-basedreporting, introduction of ASYCUDA and IFMIS, payroll reform, etc.) is fraught with major risks to sustainability and thecredibility of reforms in the long term, once there is no direct donor support and hand-holding.Lesson 2: Need forgood communication with all stakeholders from the start to avoid preparation and implementation delays. At the beginning of theseries Parliament was not fully informed that the budget support was in the form of an IDA credit and not an IDA grant and neededadditional assistance on how to ratify such agreements, which took additional 11 months between the Board approval anddisbursement. In addition, an extended and sizable program such as this series would have benefited from a better upfrontunderstanding of the political economy risks and scenarios.Lesson 3: Need to keep the range of policy areasflexible, to better respond to exogenous shocks such as the Ebola crisis, which occurred after the start of the series andhighlighted the weaknesses in Liberias health caredelivery system.Lesson 4: Capacity for reform incountries like Liberia, requires heavy TA to support a successful reform program. The TA also encouraged stronger governmentcommitment and willingness to reform. The key TA support was particularly helpful in the areas of PFM, land reform and inelectricity sector reforms. At the same time, ongoing TA support for implementation (absolutely critical in an environment likeLiberia) also needs to be accompanied by strong and clearly targeted capacity building measures and indicators to ensuresustainability of achievements.
P146640 | BF - DPO - Growth and Compet. Credit 3 | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest |  |  | This review draws the following three lessons (with the first two from the ICR):1. Inadequate consultation with allrelevant stakeholders increases the risks that draft legislation submitted as a prior action will not pass opportunely to achievethe expected effects. The draft mining code and anticorruption legislation suffered from inadequate vetting, resulted in lateapproval, and had no impact during the program.2. In low capacity environments, objectives to buildcapacity may be more appropriate than objectives to achieve the long-term welfare goals of added capacity. Capacity building mayhave been what the less ambitious DPO4 program objectives (to enhance the governments ability in three areas) aimed for.However, such enhancements need to be measured. For example, enhanced government ability to reduce costs in agriculturerequires evidence to link reforms to cost reductions. Implementing reforms (by capitalizing the input fund) alone is not evidenceof the expected outcome.3. Mitigation of risksis unlikely tobenefit from mitigation measureswith impacts that are dependent of the risks that the measures aim to mitigate. For example, reforms to expand cotton productionwill hardly qualify as a mitigation measure for the risk of unanticipated production and/or price shocks on cotton production.
P146640 | BF - DPO - Growth and Compet. Credit 3 | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2014 | 2018 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/494031533935601565/text/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.txt | http://documents.worldbank.org/curated/en/494031533935601565/pdf/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.pdf | 6. Lessons â€¢ When political risks are high and capacity is strained, design is better focused on a few key priorities. This series covered too many areas, and some key binding constraints were not addressed. The series might have been more successful with a sharper focus on more realistic objectives accompanied by a simpler design. â€¢ The success of budgetary support depends on the suitability of the instrument to the country environment. In a context of political turbulence and uncertainties about the government's ability to undertake long term reforms, the World Bank could have ended the programmatic series after the third operation and made the fourth operation a stand-alone. Alternatively, the World Bank could have implemented a series of stand-alone operations after the second programmatic series when it became apparent that the political and policy environment was rapidly changing. â€¢ Lack of clarity on the respective roles and responsibilities of central and local governments and of the private sector undermines policy actions. It is important to ensure that there is a shared vision and that the need for reform is recognized and accepted by all parties. In this case, there was a lack of clarity among different stakeholders during implementation of the reforms on decentralization and fertilizer distribution. â€¢ When M&E is not adequately resourced or implemented, there can be delays in the identification of problems and the application of remedies. M&E weaknesses can be compensated by leveraging information available elsewhere, or through specific impact assessments and perceptions surveys. â€¢ There may be a trade-off between the promise of continuous and predictable financing, urgently needed in times of crisis, and the strength of the reform program. In Burkina Faso the emphasis was on continuous financing even when reform performance was waning. â€¢ The lack of broad consultations with stakeholders when the World Bank is designing a complex reform program could lead to unsatisfactory results. In this case, the lack of consultations with an important stakeholder association (the Confederation Paysanne du Faso) on fertilizer distribution affected the achievement of results of one of the first objectives. Also, some development partners and civil society organizations had limited knowledge of the reforms pursued in the G&C series. â€¢ Consultation with all important stakeholders is critical to inform program design. In this case, development partners, civil society organization, and academia complained to the PPAR mission about inadequate consultation by the World Bank. â€¢ Inadequately resourced implementing agencies will likely be unable to carry out agreed reforms. Under-resourcing may be an indication of low government commitment, which needs to be addressed through policy dialogue. It is also important to ensure that agencies have appropriate technical capacity and systems in place, and that potential political obstacles at the local level are being addressed.
P146653 | Uttarakhand Disaster Recovery Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2024 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062324233529003/text/P146653-0ffa24a9-cc4f-429d-8dd1-9c6448fd3910.txt | https://documents.worldbank.org/curated/en/099062324233529003/pdf/P146653-0ffa24a9-cc4f-429d-8dd1-9c6448fd3910.pdf | The operations offered the following lessons: If relevant indicators to measure expected outcomes arelacking, a project misses the opportunity to demonstrate, measure, and report on positive achievements at outcome level.In this project, reconstruction of housing units was used to provide evidence of community resilience. Indicatorssupported the physical infrastructure investments that were completed to show recovery and resilience of communities.However,indicators or benchmarks for the other dimensions of resilience were lacking. Communities could have used thesebenchmarks to track progress and suggest areas for improvement. Surveys, geospatial data to map and predict communityvulnerabilities,community feedback mechanisms could also inform theassessment of community resilience. Some of thesedata were available, but not captured. Projects focusing on increasing resilience of communities may benefit from usingbothquantitative and qualitative assessments fora morecomplete view of a communitys capacity to prepare, respond,and recover from disasters. Training end users in line departments in the use of sophisticated analyticalstudies, tools, and technologies may lead to more effective useof such tools.In this project, adopting the MISwas a significant step in strengthening institutional ME capacity. However, end users were not given sufficienttrainingto build capacity tooptimize the potential uses of suchtools. Training end users inline departments, may lead tomore effective use of these tools or lead to discovery of other uses to enhance the capacity of line agencies inearly warningand hydro-met systems. Projects that introduceadvanced tools and systems, may benefit from involving the staff ofthedepartment that will use the technology and facilitatetheir effective use, through user feedback and last-mileconnectivity in the use ofearly warning system. This may also fosterinter-agency collaboration fortimely andinformed decision-making because comprehensive data is now available to allstakeholders. A holisticapproach to resilience that considers the interconnected infrastructure elements can effectively address system-widevulnerabilities and enhance overall durability. In this project,infrastructure investments consisted ofinterconnected parts where each element was expected to contribute tooverall resilience. For roads, the project integratedresilient materials. Adequate drainage systems prevented waterlogging and damage. For bridges, the approach roads and surroundingareas play a significant role in overall functionality and resilience of the structure itself. This broader vision ensures thatvulnerabilities are not overlooked. The World Banks involvement added value in improved design standards. Updated guidelinesand safety measures are now adopted for other roads in the state. Innovative approaches, such asgender-focused homeownership, and resilient construction techniques, can facilitate more sustainable building practices andoperational efficiency in disaster management. In this project, the owner-driven, gender-focused housing constructionapproach demonstrated tangible benefits. For example, beneficiaries received funds in joint accounts to promote equitabledecision-making. Anotherexample was the design of the technically advanced USDMA building to be earthquake-proof with seismicbearings (called base isolators) and a strong commitment to environmental sustainability by receiving a Green Rating for IntegratedHabitat Assessment (GRIHA) 4-star green building rating. This GRIHA rating is derived from receiving 51 to 60 percent of applicablepoints in energy efficiency, waste management, and sustainable material use. The SDRF training center is the biggest search andrescue training center in North India. The project also introduced innovative bridge construction techniques, markingthedebut of the prefabricated modular steel bridge in the state. The project conducted bioengineering pilots that had the potentialfor wider adoption.
P146665 | Tenth Poverty Reduction Support Credit | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Unsatisfactory |  |  |  | The ICR (pp. 30-31) highlights several useful lessons with which IEG concurs,including:Political economy considerations are essential to the timing, sequencing, and level ofambition of reform. In this case, there was inadequate consideration of internal resistance and vested interests inopposition to governance and cotton sector reforms. Better consideration of these political concerns may have led to a moregradual approach, keeping in mind the need to construct a legislative, institutional, and regulatoryenvironment conducive toreform. It is also important to note that the process of policy dialogue around governance and broad political economy issuescan have longer-term impact, outside the results framework of a single operation or series ofoperations.Political cycles often create risks of deteriorating macroeconomicframeworks. In this case, the 2016 election involved electorally timed interventions in fiscal policy and somereversal of structural reform. Timing the implementation of reform measures to align with political cycles can mitigateagainst reversals and keep authorities engaged in agreed reform processes.IEG adds the followinglesson:Attribution of observed results can be ensured only through carefully designed prioractions. In this case, particularlyin relationto PPPs and agricultural diversification, the prioractions were inadequately specified to lead to intended outcomes.
P146665 | Tenth Poverty Reduction Support Credit | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2022 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/746991630422633137/text/Benin-Ninth-and-Tenth-Poverty-Reduction-Support-Credit.txt | http://documents.worldbank.org/curated/en/746991630422633137/pdf/Benin-Ninth-and-Tenth-Poverty-Reduction-Support-Credit.pdf | 3. Lessons 3.1 Relevant lessons from previous operations need to be taken on board in the design of new DPF operations. The design of this PRSC series appears to have not taken on board several important lessons identified by World Bank staff from previous operations. Some of them include (i) the importance of a targeted reform agenda, where the development objectives are clearly defined and the results indicators are well specified; (ii) the need for a realistic understanding of political economy and the associated risks related to high resistance to change within the government and by vested interests; and (iii) the importance of limiting the scope of the program, given limitations in administrative capacity. 3.2 Prior actions need to be substantive, that is, be critical to reforms with value added. Prior actions under PRSC-9 were quite soft, meaning that they could not credibly be associated with significant contributions to the objectives, and several triggers (for approval of PRSC-10) on governance and cotton sector reforms were either revised or moved to subsequent operations and later dropped altogether. 3.3 The World Bank should design projects with a clear understanding of the likely winners and losers; failure to do this raises the probability that projects are not implemented as planned or sustained over time. An understanding of political economy must encompass the private sector and other informal centers of power. If internal decision makers are to take informed risks, the World Bank should be candid in its ex ante assessment of the fundamental forces with direct involvement or interests in the reforms supported. 3.4 Distributional impact analysis from DPF-supported reforms should inform the design of operations. There is a lack of evidence on whether the DPF-supported reforms were pro-poor ex ante and ex post because the series did not conduct distributional impact analysis.
P146666 | Competitiveness for Tourism Development | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099060123091513455/text/P146666010870002e0ace60ec8693bafeee.txt | http://documents.worldbank.org/curated/en/099060123091513455/pdf/P146666010870002e0ace60ec8693bafeee.pdf | The following are lessons learned from the ICR with some paraphrasing: In small projects a simple projectdesign can help improve theimplementation and the achievement of projects results. In the case of thisproject, the project included many small activities and several beneficiaries, which added complexity and transaction costs. TheICR reports that during the early phase of project implementation, the implementing agency struggled with coordinating thesediverse activities with the various beneficiaries who were new to World Bank policies and procedures. Ensuringsufficient level of procurement capacity of the project implementation units and beneficiary institutions contributes to successfulproject implementation. In the case of Cabo Verdes project, both the implementing agency and the beneficiaryinstitutions lacked the technical capacity to develop relevant procurement documents and to conduct relevant procurementactivities. If foreseen at project design stage, some technical assistance could have supported these institutions in developingprojects complex terms of references as well as evaluating offers. Projects with diverse set of activitiesand large number of beneficiaries can benefit from a technical committee, which would coordinate and monitor projectactivities. The CTD project has a steering committee, but a technical committee could have helped overcoming technical andprocurement capacity problems delaying the implementation of the project.
P146688 | Jamaica Strategic Public Sector Transformation | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099173502172341232/text/P1466880b97aba0c20a8140803ecc7bf756.txt | http://documents.worldbank.org/curated/en/099173502172341232/pdf/P1466880b97aba0c20a8140803ecc7bf756.pdf | This Reviewconcurs with the key lessons identified in the ICR (pp. 23-24), which included: Awell-resourcedPIU is essential for project performance and efficiency. Thisproject incurred significant initialprocurement and contracting delays due to poorly defined terms of reference for the PIMIS, weak coordination across projectactivities, and ME shortcomings. An adequately staffed PIU during the initial stages of project implementation can help avoidthese kinds of hurdles; streamlining can take place once projectimplementation is under way and PIU procedures and systemsare well established. Awareness of information technologysoftware applicationmarket offerings isessential prior to the start of a tendering process. The ICR reports that the first PIMIS procurement failed in part due to thegovernments lack of understanding about market offerings and what a commercial-off-the-shelfsystem can potentiallyoffer. This issue was addressed during the second procurement attempt, where knowledge exchanges of the technical staff at the PIUallowed for a successful process. Similar projects would benefit from market consultations regarding the process of system designprior to the start of the procurement process.In addition to these lessons, the IEG finds that it is criticalthat the Bank avoid over ambitiousness. Furthermore, Bank should formulate a Results Framework with clearly defined indicatorswhich allow for the measurement of outcomes.
P146696 | Power Sector Recovery Project | Western and Central Africa | Guinea | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2022 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099091223152023422/text/P1466960b8dbaf0bc0ad7502292157e451b.txt | http://documents.worldbank.org/curated/en/099091223152023422/pdf/P1466960b8dbaf0bc0ad7502292157e451b.pdf | IEG derives the following lessons drawn from the ICR:1. Successful reforms of the electricity sector callfor Government commitment. Earlier World Bank projects had attempted to reform the electricity sector and utilitiesin Guinea and other countries, with limited success. The project in question was able to achieve some success towardimprovingthe technical and operational capacity of the utility because the Government had been fully engaged in the reform.For instance, the competitive hiring of EDGs Director General, and other directors and department heads helped bring instronger management to run the utility, and is a case in point. Conversely, after the military coup in 2021, the commitmentof the authorities declined, and was accompanied by a halt in the implementation of the reforms to the detriment of theperformance of the sector (and utility). 2. A PPP approach to the implementation of a managementservices contract (MSC) is often an effective practice in building technical skills and institutional capacity. Forthe project in question, multiple private firms were hired to diagnose EDGs operational situation, select the firm to takeup a performance contract with the Government, and to audit the performance of the contract. The MSC was successful indiagnosingweaknesses in the utility and inexecuting several measures to address to improve its overall effectivenessand efficiency. The private auditing firm played an important role in enforcing accountability and in assessing the actualachievements in the context ofthe MSC. 3. The project and the reforms it supportedexemplified the importance of shifting away from a culture of non-payment of energy bills through increased service quality andactive communication with clients. The increase in EDGs formal clients, and hence to its ability to collectrevenue, was linked to efforts to regularize informal electricity connections and improve the performance of the overallelectricity network, whilst actively educating the client through deployment of an external communication plan.
P146726 | Sierra Leone - Emergency Economic and Fiscal Support Operation | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422921528124311907/text/Sierra-Leone-SL-Emergency-Econ-and-Fiscal-Support-Op.txt | http://documents.worldbank.org/curated/en/422921528124311907/pdf/Sierra-Leone-SL-Emergency-Econ-and-Fiscal-Support-Op.pdf | The ICR (pp. 23-24) notes several lessons, with which IEG concurs: Even in the case of a nationalemergency, it is possible to make progress in government fiscal management reform. It is important to have a centralcommand with strong authority to coordinate the many actors coming together to fight an epidemic. A fiduciary agent canplay a critical implementation role in emergency contexts. In emergency situations, it is vital to consider practicalproject management issues such as payment of workers. The existence of widespread mobile phone use offers an opportunityto convey funds to workers in an emergency situation. Results indicators should not rely just on completed actions, butshould attempt, to the extent possible, to capture the outcomes of completed actions of theproject.The first lesson merits highlighting and augmenting: not only was it feasible to carry outfinancial management actions that would put the government in a better position to implement the next generation of sector reforms,it achieved important synergies by marrying budget and transparency imperatives of the Ebola crisis with longer-term financialmanagement and transparency concerns. Another key lesson is that development policy operations benefit from the quality ofthe Banks overall engagement, including how various instruments such as analytical work, and both country-based and regionalinvestment operations, along with the work of other development partners, reinforce and complement each other.
P146740 | BiH DPL | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/730981495479059190/text/ICRR-Disclosable-P146740-05-22-2017-1495479051771.txt | http://documents.worldbank.org/curated/en/730981495479059190/pdf/ICRR-Disclosable-P146740-05-22-2017-1495479051771.pdf | Four lessons are drawn from the ICR (pages 20-21), with some adaptation.One, ownership is crucial to the successof an institutional and policy reform program. Commitment to the BEDPL was secured at all levels of government in Bosnia andHerzegovinas complex system of government. The objectives and elements of the reform program have since been embeddedin the new medium-term Reform Agenda for Bosnia and Herzegovina, 2015-18, approved by the new political leadership in2015. Business environment reforms could be broadened in a new Business Environment Strengthening Project being prepared forFY2018 for Bank financing. In all cases, strong government ownership of the reform objectives is propelling the programforward.Two, political pragmatism and flexibility helps a reform program survive implementationchallenges. The Government turned its focus on business environment and investment climate reforms after efforts at a fiscalexpenditure reform initiative fell out of political favor. The BEPDL was subsequently developed in lieu of the cancelledPublic Expenditure DPL series. A fiscal policy reform package, originally included in the BEDPL, was dropped for similarreasons --- a lack of political support for the program component. The DPL survived as a US$50 million rather than a US$100million operation. Finally, the operation was scaled down to a stand-alone DPL in view of the difficult political environmentprevailing at the time of program preparation. Political pragmatism kept the reform programintact.Three, complementary technical assistance is often essential to the success of adevelopment operation. The provision by the Bank and the IFC of technical assistance to the state and entitygovernments helped substantively with the design and implementation of the BEDPL. The Bank provided technical assistance onbusiness registration law and business inspections law. The IFC provided technical assistance on trade facilitation,construction sector regulations, the new company law, and the decree on notary fees. The technical assistance packages, providedunder separate projects and financed with grants (see Section 1.d), were doubly essential, considering Bosnia andHerzegovinas previous poor track record in implementing structural reforms.Four, more nuanced institutional analysis is necessary for development programs that straddle various levels ofgovernment. Reforms in the business inspections system could be better designed if the role of the canton governments in theFederation of Bosnia and Herzegovina are more thoughtfully considered, in addition to those of the Government of the FBiH.Similarly, reforms in the construction permit system could be better implemented if gaps in the operational capacities of some municipal governments in Republika Srpska are directly addressed. The roles of various levels of government, particularly ofcantonal and municipal governments, are often not systematically analyzed in process reform initiatives.
P146797 | Kenya GPE Primary Education Development Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099000010202219782/text/P1467970679e930ea0bc1d09e5eff9ea3c1.txt | http://documents.worldbank.org/curated/en/099000010202219782/pdf/P1467970679e930ea0bc1d09e5eff9ea3c1.pdf | Lessons drawn from the ICR (pages 35-36), adapted by IEG: Project designs that include pilots as demonstrationmodels can be an immediatecatalyst for system-level change, if lessons are widely shared in a timely manner.In the caseof this project, the school management activities were initially implemented in 4,000 schools, but the timely feedback (duetodata generated bythe monitoring system, the learning assessments, and the evaluations) led to immediate scaling up ofactivities, by way of both the government budget and GPE Additional Financing. Improving learning outcomescan be an achievable project objective if accompanied by a strong ME framework and monitoring arrangements.In the caseof this project,the project was able to establish a robust ME system capable of systematically tracking progress, andproject activities included relevant assessments and studies thatinfluenced decision making and policy development. Forexample, the regular assessment data collection allowed for an evidence-basedcorrection at the time of project restructuring,when assessments indicated that learning levels had decreased. Remedial action was taken, by introducing more targeted teacherpedagogical skills training and peer-to-peer learning to complement ongoing activities. School-based teacher supportsystems are a critical ingredient for ensuring on-going quality improvements in schools.In the case of this project, ongoingsupport incontent and pedagogical practices was provided by teacher advisory tutors/curriculum supportofficers.Teachers also received timely feedback on teaching approaches.Peer-to-peer collaboration also enabled teachersto work together, share experiences, and find solutions to challenges. Equally important was the feedback loop developed with theNational Assessment Councilto ensure teachers were familiar with learning gaps, particularly after the COVID-19 schoolclosures. All of these were important for helping to motivate teachers and necessary for improving the quality ofteaching.
P146804 | Mauritania Public Sector Governance Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099122123163561938/text/P14680416b4e9205b18324180d35fb85e53.txt | http://documents.worldbank.org/curated/en/099122123163561938/pdf/P14680416b4e9205b18324180d35fb85e53.pdf | Small but targeted investments in strategic planning capacity in the executive branch can support the broader goals ofgovernance operations. A comparatively small investment of US$ 500,000 was a catalyst for the operationalization of thenewly created CSEPS. Based on the encouraging achievements described in Section 2.d, additional support for CSEPS could further PFMreform in Mauritania, focusing on improved public sector project monitoring and coordination. This support could include (i)building capacity through peer-to-peer exchanges in the region and beyond, (ii) encouraging CSEPS to prioritize further theprojects it monitors (highlighting 3-5 projects with high visibility and impact, creating synergies with the other components, and(iii)helping to strengthen communication and citizen engagement around these critical projects given strengthening the socialcontract.Complex ICT procurements should be carefully planned at appraisal, with sufficient due diligence beforeinitiating the procurement process. Due to protracted issues encountered during the procurement process, acquiring a newTreasury accounting system (from Oracle South Africa) was eventually abandoned in 2021 at the signature stage. The GoM subsequentlydecided that these funds (US$ 4.3 million) be reallocated to several replacement activities. Some of these activities requiredadditional ICT procurements, which were also not successful. Procurement planning and due diligence would have addressed some ofthese challenges. These types of procurements should dedicate sufficient resources to ensure completion, testing, interfacing, andbuilt-in provisions to ensure maintenance and sustainability.To effectively monitor implementation and assess theimpact of governance projects, the RF should be fully aligned with the PDO from effectiveness to closure, capturing outputs andoutcomes throughout implementation. The RF was extensively revised during the AF/First Restructuring and, to a lesserextent, the Second Restructuring, making it difficult to track progress and impact. The addition of a new component with theAF/First Restructuring (strengthening national statistical capacity, medium-term programming, and annual budget processes) andadding a new subcomponent (supporting the operationalization of the CSEPS) during the Second Restructuring were not clearly linkedwith the PDO (which was also revised during the AF/Second Restructuring), making it difficult to monitor progress and assess impactover time. In addition, the project did not have an indicator that tracked revenue collection, a fundamental data source for themobilization of public resources.
P146827 | Liberia Youth Opportunities Project | Western and Central Africa | Liberia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099355011282293068/text/P1468270e1665807b08f84090d47a1e2a72.txt | http://documents.worldbank.org/curated/en/099355011282293068/pdf/P1468270e1665807b08f84090d47a1e2a72.pdf | The ICR (p. 34-35) included several lessons learned, which were adapted by IEG: Engaging with localcommunities ensures continuous project support and community ownership. This project used various communication tools,including text messaging, and radio talk shows to involve local communities resulting in community members understanding theirroles and providing free land for youth groups to cultivate. Using direct payments of grants to beneficiariesthrough mobile money for procurement of farm inputs allows for greater local ownership. In this project, the PMTtransferred the full beneficiary amount to targeted youth groups who carried out purchases of farm inputs with the support ofcommunity facilitators. This procurement method also created a market for local community members and supported the provision ofmaterials of adequate quality to project communities.
P146831 | Support to the National Education Pact Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2016 | 2023 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099072324125513598/text/P146831-610c6707-e635-427e-95d0-63f8ac17cd0e.txt | https://documents.worldbank.org/curated/en/099072324125513598/pdf/P146831-610c6707-e635-427e-95d0-63f8ac17cd0e.pdf | The ICR (pp. 29-30) offered several insightful lessons, adapted here:Aligning a project with medium orlong-term sectoral policies provides a solid foundation that ensures continuity, though continued efforts and political economyanalysis are necessary to sustain momentum through periods of political transition. In this case, the project fullysupported the 2014 National Education Pact, and the broad support for that strategy enabled continued progress through a turbulentchange of government in 2020. That turbulence, however, caused efforts as securing Additional Financing ultimately tofail.Empowering decentralized entities with financial decision-making authority can lead to more efficient andrelevant allocation of resources, but that autonomy must be accompanied by efforts to ensure financial integrity andtransparency. in this case, School Management Committees were provided with comprehensive training on financial practicesand the use of Annual Operations Plans to ensure that they had the toolsto allocatefunds toward the schools bestinterests.The use of DLIs can incentivize important regulatory reforms when they are well aligned with governmentobjectives and priorities. In this case, the Ministry of Education had support (and pressure) for reform from othergovernment ministries, including the Ministry of Finance, facilitating regulatory changes and their implementation.
P146877 | STP- Quality Education for All Project | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/537771593538124582/text/Sao-Tome-and-Principe-STP-Quality-Education-for-All-Project.txt | http://documents.worldbank.org/curated/en/537771593538124582/pdf/Sao-Tome-and-Principe-STP-Quality-Education-for-All-Project.pdf | The ICR (p. 33-35) offered several useful lessons, including the following adapted by IEG:In projects withseveral different implementing agencies, the precise definition of roles helps to reduce tensions.In this case,theMinistry of Education needed to rely on an outside agency to manage project fundsbecause it did not have thenecessary financial management systems. The AFAPs role was clearly defined to only overseeing fiduciary aspects, while alltechnical leadership was the responsibility of the Ministry; however, some tensions arose during project implementation. Tomitigate this situation, it was necessary to clearly define each agencys roles and competencies.Havingdedicated personnel withina projects main ministryis critical for smooth implementation and coordination amongallagencies and entities involved ina project. There was no one dedicated to work full-time on thisproject, andthe resultinglack of coordination between different agencies was a significant barrier to implementationeffectiveness. After the mid-term review, a Project Coordinator from within the Ministry of Education was appointed, but this staffmember had many other responsibilities.Technology is a powerful tool to improve education quality, but risksrelated to limited capacity ininformation technologyand weak infrastructure need to be accounted for in projectdesign. This project included several initiatives that introduced information technology to make improvements in theeducation sector. The costs associated with purchasing the equipment to set up these programs and recurrent costs are notinsignificant.The Ministry of Education needs more staff withinformation technologybackgrounds to support themaintenance and implementation of these activities.Merit-based selection brings sustainability toaproject. In the case, many of the positions across the entire education system are politically appointed, includingMinistry of Educationleaders, department heads, school directors, school supervisors, etc. This poses significant risks tosustainability when there is a turnover in government. After the elections in 2018, and during the final six months ofimplementation, nearly every person in these positions changed, which compromised investments made in capacity-building andinstitutional strengthening.
P146883 | ET Productive Safety Nets Project 4 (PSNP 4) | Eastern and Southern Africa | Ethiopia | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2022 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099080924180551291/text/P146883-985968a3-e1ee-4c80-b4c9-719a0dd80e3e.txt | https://documents.worldbank.org/curated/en/099080924180551291/pdf/P146883-985968a3-e1ee-4c80-b4c9-719a0dd80e3e.pdf | Lessons from the ICR:Pronounced differences between regions may substantially affect outcomes where adifferentiated approach is not taken to administering social safety nets. Public works and other social safety netprojects should achieve clarity on salient differences between regions at appraisal. This may include insights on how to enhancethe appropriateness and effectiveness of public works and adapt the livelihoods program for pastoral areas, including aroundlivestock development and off-farm and wage employment pathways.Optimal higher level outcome measures are likelyto vary between safety net programs. For example, during PSNP 4 it was found that the focus on the extreme poor forsocial safety netsupport, rather than food insecure households, would be more effective in reducing poverty andvulnerability. Furthermore, progress was made against poverty, gender and resilience. Given these priority areas, measures ofpoverty reduction, gender and resilience might have better reflected program goals and achievements than the chosen outcome-levelmeasures of food security and nutrition.Social safety net projects in fragile and conflict-affectedsituations are likely to encounter unanticipated challenges that necessitatemid-course program adaptation. Theextent of challenges that arose over the course of PSNP 4 highlighted the need to continuously reassess assumptions and respond tocontextual risks. The projects planned ambitious systems-building agenda was superseded by the challenging contextwhich overstretched technical and budgetary capacities of implementing structures. While this shift was fully justified, itwould have been useful had there been established mechanisms to assess and communicate risks and challenges as they aroseandto correctly adjust the results framework in response.Where financing is uncertain, lack of flexibilityinresults targets may result in unrealistic objectives. Where project achievements are partially dependent onunpredictable streams of donor financing, financing gaps need to be reassessed regularly, based on a common understanding thatprogram goals and features may change over time as challenges arise and resources become available. Where this does not occur,there is a danger of misalignment between project resources and targeted results.
P146890 | P146890 - Georgia Competitiveness and Growth DPO3 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | IEG draws the following four lessons from the experience of this series:1. Incomplete results chains will undermineefficacy assessments. In this Program, the first objective was materially equivalent to the reforms that underpinned it.Trade-related reforms (e.g., on food/feed safety, competition) comprised the stronger legislation sought under theobjective. In this case achievement of the reforms (enactment and implementation) is equivalent to achievement of the objective andthus there is no meaningful efficacy assessment exercise.2. Monitoring indicators that do not accuratelyreflect objectives will also undermine evaluation. An example in the Georgia Program is the indicator used to reflect generaleducation quality, which was defined as the share of teachers that attended training on learning processes. While this indicatormay be related to actual learning, it does not measure it directly. The point of an evaluation in this case is to assess whethersuch training actually was effective in raising student test scores. Another example is the indicator for accessibility of healthservices, which was defined as the percent of theoretical coverage (Decree introducing Universal Health Coverage). The latter doesnot reflect actual health attention to the covered population.3. Attention to the more specific risks of anoperation (in addition to the broad political, macroeconomic, and capacity risks) will better anticipate implementation problems.The Georgia program suffered delays on a number of reforms (e.g., international standards, trade facilitation, and power) thatmight have been anticipated with a more detailed articulation of risks.4. An unfocused set of objectiveswill detract efficacy as it does not allow for synergies across objectives. In the Georgia DPO, areas such as customs efficiency,targeted social programs, and power sector reliability were mutually unrelated and thus unlikely to support each other.
P146930 | MZ Second Agriculture Development Policy Operation AgDPO-2 | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | Summary of lessons learned: DPO series objective should beconcrete and measurable, linked to toimplementation. Achievements stemming from prior actions should be strongly focused on the PDO and well-measurable. Dataavailability and instrument should be well planned in advance. It is important to ensure that any risks related to dataavailability are identified and accounted for upfront before concluding project preparation, and inform the Results Framework (ICR,para 80). Technical assistance facilitates the positive results of a DPL. The team rightly identified the need to buildboth administrative and technical capacity of institutions that implemented reforms and was instrumental in shortening the learningcurve (ICR, para 81) The design of a programmatic series should account for the risk of cancellation, particularly if itis a common occurrence in the region. The termination of the third operation in the series could have been mitigated by bettersequencing. (ICR, para 83).
P146933 | Urban Development and Poor Neighborhood Upgrading Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons were derived from the ICR (ICR, pages 31-32):1. The sustainability of developmentoutcomes is enhanced when the World Bank maintains its strategic and operational engagement over time, especially when social,political, and institutional risks are high. The World Bank has supported the developmental goals of the RoC since 2002,and the Project was designed based on a long-term Banks involvement in the country. The urban sector is facing manychallenges, including a large infrastructure deficit, increasing impact of climate change (including risks of flooding anderosion), and inadequate institutional capacity of key stakeholders. In this situation, World Banks continued engagement inmunicipal planning, management, finance, and service delivery would be important for the sustainability of the Projectsinvestments.2. Balancing the complexity of projects design with the countrys regulatory advancementand institutional capacity is important. Given the countrys fragility, the Project had overcomplex design,combining investment in assets in several sectors with regulatory and institutional support. The city-level institution building(Sub-component 2.4) was particularly ambitious, introducing advanced concepts (e.g., municipal asset management) while even basicOM arrangements were not yet established. The lesson learned is to balance the design complexity with the countrysinstitutional capacity at project preparation stage.3. When a project is to be co-financed by the counterpart, areview of the Borrowers financing capacity can be beneficial. The Project had to be downsized mainly due to thecancelation of the counterparts co-financing, and the risk of such event could have been evaluated prior to Projectsapproval, and mitigation measures could have been put together. Such measures could have included a Project design supportive ofthe operations re-scaling, which would be based on the pace of activities and/or on the number of targeted neighborhoods.The lesson is that complexity of projects design exacerbates the risk of delays and low project performance in cases whencounterpart co-funding cannot be provided.4. The selection of a projectimplementation agency is critical notonly for a projects implementation, but also for sustainable institutional development.The Projectsexperience showed that if the implementation were to be entrusted to a more relevant government institution, it would have been abetter venue for building sustainable institutional capacity (including for fiduciary control), accumulating knowledge andexperience, improving coordination and collaboration with key stakeholders, and delivering other infrastructure assets whileuniformly applying the same implementation arrangements for all investments independent of financing sources. It is thereforehelpful when implementation arrangements are made with more relevant government institutions and also when temporary PIUs in lessrelevant institutions are avoided.
P146936 | Uttar Pradesh Pro-Poor Tourism Development Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR (p. 19) included several lessons learned which were adapted by IEG: Working closely with localcommunities and key stakeholders during project preparation and implementation can positively impact the projects ownershipand sustainability but keeping implementation time in mind is key to ensure efficiency. This project had a highlyparticipatory approach with local communities and key agencies. However, this process prolonged preparation and reducedimplementation time due to a lacking clear commitment to a timeframe for each phase. Pro-poor tourism may workwell when the location attracts a large number of tourists. In this project, Agra the Braj region and Sarnath were wellestablished destinations where a large number of tourists came to visit. Identifying opportunities of products and services thatlocal social enterprises could provide to tourists was easier than in Kushinagar which did not have as many touristsvisiting. Decentralization of decision-making can make project implementation smoother. This projectsupported state authorities to decentralize power which allowed to address institutional risks like frequent changes in leadership,slow decision-making, and lengthy approval processes.
P146942 | PA Third Programmatic Development Policy | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2017 | ICRR | >=100 million | Satisfactory |  |  | Moderately Satisfactory |  |  |  | IEG concurs with the ICR lesson (pp. 25-26) with some minor adaptations:Strong Governmentownership of the reform agenda, based in the Government strategy, is essential to ensure the implementation and sustainability ofDPL programs. In the case of this DPL series, the Government engaged in the project implementation and continued to support thePDOs beyond the closing of the project.A simple design, based on the learning from previousoperations in the country, establishes an appropriate pace for reform implementation. In the case of this DPL series, it isconcentrated in four specific objectives clearly aligned with the Governments quinquennial Strategic Plan, instead ofcovering an extensive array of areas.Flexibility to account for rapid responses to changingcircumstances in the implementation of the projects is critical for ensuring effective delivery, especially in the case ofunexpected shocks. IEG would add that changes in the program need to be reflected in the results framework. In the case of this DPLseries, the procurement-related actions needed to be adjusted due to unforeseencircumstances.Strong analytical groundwork and complementary technical assistance are essentialto ensure adequate program implementation. This DPL series focused on areas of strategic relevance where the Bank had previouslyestablished a record of strong technical capacity and had cross-country experience.A fifth lesson should beadded:A solid fiscal basis along with excellent tax collection management are needed toguarantee the long term the sustainability of extensive social policies. In the case of this DPL series, so far the advancements inthe former areas are not enough, although the Government is engaged in supporting the PDOs beyond the DPL series.
P146981 | Piaui Productive and Social Inclusion DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2016 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/800771544713096072/text/Brazil-BR-Piaui-Productive-and-Social-Inclusion.txt | http://documents.worldbank.org/curated/en/800771544713096072/pdf/Brazil-BR-Piaui-Productive-and-Social-Inclusion.pdf | The most important lessons drawn by the ICR (1-3) to which IEG adds a fourth are:1. Robust analytical work andparticipatory processes during preparation are essential for designing successful policies. This was reportedly especiallythe case with respect to the two areas -- gender mainstreaming and citizen engagement -- that were not part of the original policymatrix.2. Capacity building activities and knowledge sharing are essential for ensuring improvements in the public sector.Program preparation and Bank support permitted state officials in key Secretariats (i.e., Planning, Environment, and RuralDevelopment) to learn from positive experiences in other Brazilian states and the parallel investment loan includes considerableresources to further strengthen public sector capacity.3. The combination of policy and investment operations, includingtechnical assistance, is important, especially in countries or states with low institutional capacity. In addition, an importantfactor not mentioned by the ICR, the parallel investment and/or technical assistance operations also provide an incentive forsectoral agencies to undertake policy and/or institutional reforms, which might otherwise meet resistance in the face of thetransfer of resources for general budget support though a DPL alone.4. The Banks engagement in key sectors, includingeducation, health, and rural development, over the longer term rather than through intermittent one-offinterventions,canbuild important on-going partnerships (in the present case with a state government)thatallowsthe Bankto develop and maintain abroad productive relationship and continuing policydialogueincluding sustainedtechnical and financial support to institutional stakeholders at thestrategic (i.e.,planning and finance) and sector-specific levels.
P146997 | BELARUS PUBLIC FINANCIAL MANAGEMENT MODERNIZATION PROJECT | Europe and Central Asia | Belarus | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099120008142212553/text/P146997043d6d20f608a690c4adf1a046db.txt | http://documents.worldbank.org/curated/en/099120008142212553/pdf/P146997043d6d20f608a690c4adf1a046db.pdf | The ICR (p. 19-21) presents a series of lessons and recommendations emerging from the projects experience. IEG summarizesthe most persuasive lessons below:Documenting actual behavioral changes originated by an operation in areas such as budgettransparency and accountability can enhance learning, especially in highly centralized countries. In the case of the Belarus PublicFinancial Management Modernization Project (P146997), regular documentation and reporting of progress in improving budgettransparency through online reporting of the citizens budget resonated strongly within a highly centralized government as wellas with the public. The projects achievement in launching a Fiscal Transparency Portal and publishing online monthly thecitizens budget generated momentum at all tiers of government. The central government continued enhancing budget transparencywith the innovation of an interactive fiscal database for the public as well as enabling users to download historical data onprogram-level expenditures. The regional (oblast) subnational governments and several districts (rayon)followed the example by publishing their own citizens budgets. Full coverage is expected by 2023. There were similar learningspillovers from the projects achievements relatedto TSA consolidation and state program budgeting.IFMISimplementation is often hampered by lack of clarity regarding system requirements, frequent change orders, and shortcomings inprocurement and contract arrangements. To ameliorate these risks and following the lesson from IFMIS implementation on howsuccessful operations require adequate preparation before the approval of the project (realistic functional and technicalrequirements, cost/time estimates, and procurement/disbursement plans), the Belarus Public Financial Management ModernizationProject (P146997) focused only on the inputs (i.e., regulatory reforms and business process reengineering) that were required forthe design of the IFMIS during the project time-frame, relegating the implementation of the IFMIS to a follow-on project.
P147006 | NI Sustainable Rural Water Supply and Sanitation Sector Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/303401605808117292/text/Nicaragua-NI-Sustainable-Rural-WSS-Sector-Project.txt | http://documents.worldbank.org/curated/en/303401605808117292/pdf/Nicaragua-NI-Sustainable-Rural-WSS-Sector-Project.pdf | The ICR lists a number of lessons which are relevant for similar projects implemented in comparable environments.(1) Toreach rural poor areas, strengthening institutional capacity at all levels of government is essential for sustainable WSSservices. This requires the establishment of a decentralized organizational structure with clearly defined roles,responsibilities and procedures. The project showed that each level in the structure needs to have the required capacity toaddress issues corresponding to its level of influence, to escalate issues that require a deeper level of support to the nextlevel, as well as sustained funding for infrastructure maintenance and employment of skilled technicians (ICR para 90).(2)Community-based implementation through a Community-Driven Development (CDD) Modality can be an agile and cost-efficient option forimplementation of non-complex works. It can result in increased ownership of the project at the community level. Thisproject showed that a CDD model was appropriate because technical solutions need to be carefully considered with due regard to thelocal and cultural context of communitities, including O M needs, costs, and adequacy of water supplies. However, theCDD modality needs to be supported by a technical and organizational support structure at the municipal and central governmentlevels as appropriate (ICR paras 89 and 92).(3) Sustainability of WSS infrastructure requires sound technical assessmentsparticularly related to water demand and its supply and quality. Poor quality of studies related to water resources was arecurrent problem under the project. In particular, WSS interventions would benefit from mainstreaming of watershedmanagement and planning approaches, as for example, piloted under the PACCAS project (ICR para 91).(4) Rigorous impactevaluation studies should be included in the financing of comparable WSS projects. In this project, the preparation of animpact evaluation was critical to fully capturing efficacy and efficiency aspects of the projects interventions (ICRpara 93).
P147010 | Higher Education Reforms Project | South Asia | Nepal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099855012092142272/text/Nepal000Higher0Education0Reforms0Project.txt | http://documents.worldbank.org/curated/en/099855012092142272/pdf/Nepal000Higher0Education0Reforms0Project.pdf | The ICR (p. 23-24) included several keylessons, adapted here by IEG: Performance Based Funding bythe government to HEIs provides an effective approach to promote consistent reforms. This project achieved criticalresults through reform grants and formula-based funding to HEIs against performance indicators that wereclustered in criticalareas such as governance, quality, relevance, resource generation, and planning. Emergencies can provide uniqueopportunities to address immediate needs but also build capacity to respond to future emergencies effectively. As a resultof the Covid-19 pandemic, the project was restructured to support the governments efforts to expand remote, internet-basedlearning, which was limited before the pandemic. Given the positive experience and increased demand, the new NurturingExcellence in Higher Education project will support the UGC and HEIs in the digitalization of learning materials andprograms. Strong leadership and timely implementation support can navigate a project successfully throughpolitical instability, disasters, and other unexpected events. In this project, strong leadership by the UGC and TUPIO aswell as timely implementation support allowed for positive outcomes and only a six-month closing date extension despite theaftermath of political turmoil, natural disasters, and a pandemic.
P147015 | Cape Verde Ninth Poverty Reduction Support Credit | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR appropriately draws the lesson that in countries with low capacity, design of budget support operations must berealistic, selective and focused on a limited number of areas of high impact, taking into account the time horizon for the reformimplementation. Excessive ambition can affect implementation.IEG addsthree furtherlessons:First, the results framework as an operational toolis weakened unless they show clear links from objectivesto reform areas, prior actions and target indicators. Absent such clear articulation of linkages, it is very difficult to attributethe Bank supported activities to the program objectives and measure and assess their contribution.Second, the relevanceand criticality of prior actions may be diminished if they consist only or largely of legislative actions and not measures thatdemonstrate enforcement and a strong will to implement reforms.Third, in the absence of an IMF program during aBanks budget support series, the Bank would be well advised to consider public debt related monitoring and target indicatorsto help achieve macro-fiscal stability.
P147147 | URBAN DEVELOPMENT SUPPORT PROJECT | South Asia | Afghanistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2017 | 2020 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/518831626860304871/text/Afghanistan-URBAN-DEVELOPMENT-SUPPORT-PROJECT.txt | http://documents.worldbank.org/curated/en/518831626860304871/pdf/Afghanistan-URBAN-DEVELOPMENT-SUPPORT-PROJECT.pdf | Following lessons are adapted from the ICR: The strength of client ownership, and client - World Bankrelationships, is central to the effectiveness of Technical Assistance (TA). The project was aligned to support thegovernments own program and the World Bank fostered a strong relationship with the policy-makers (up to the highest level).Senior, respected, well-networked, local consultants also strengthened theengagement. High-level coordination and ownership can mitigate against fragility and is key for theurban sector. Effective urban planning and management requires coordination across multiple sectors and tiers ofgovernment such as Ministry Level and President or Prime Ministers Office, particularly so in fragile, evolvinginstitutional environments. The project experience shows strong benefit from close collaboration with institutions with ahigh-level mandate for coordination such as Afghanistans High Council for Urban Development(HCUD). A clear logical link between outputs and outcomes at project design can critically affect theachievement of project outcome. The design needs to support validation and implementation-readiness, after initial outputsare delivered. A programmatic approach or Series of Projects can enhance sustainability.
P147152 | Grenada First Programmatic Resilience Building DPC | Latin America and Caribbean | Grenada | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/220751565013786731/text/Grenada-1st-Programmatic-Resilience-Building-DPC.txt | http://documents.worldbank.org/curated/en/220751565013786731/pdf/Grenada-1st-Programmatic-Resilience-Building-DPC.pdf | The following two lessons are taken from the ICR with some adaptation of language: When designinga programmatic series, it is important at the outset to be realistic about what can be accomplished, taking into account capacityofgovernment counterparts. Excessive optimism or complexity, such as that involved in the design of some components of thisprogrammatic series, results in having to adjust subsequent operations to reflect the reality on the ground. Political economyfactors in small countries, such as Grenada, may be of an order of magnitude different from those in large economies. For example,downsizing government departments must take account of scarce alternative opportunities; only a limited pool of potential investorsmight be interested in investing in PPP projects in a small economy; and skills and capacity may be scarcer.Creation of new administrative agencies can lead to mission overlap and higher fixed costs. This series required the creation ofnumerous new units and agencies, where assigning responsibilities to dedicated staff in existing units might well havesufficed.IEG draws the following three additional lessons: Adequaterecognition at the design stage for technical assistance (TA) requirements can assist the successful development and implementationof a reform program. In this case, relying on regular support from the World Bank team, and other external partnersproved insufficient. More could have been done to mobilize resources for targeted TA for certain particularly complex initiatives,and through leverage of the investment lending portfolio. While including legislation, new regulations, and otherpieces of paper within prior actions is appropriate, a program that does more to ensure practical application on theground stands a greater chance of success. Here, much new legislation was approved, but in several cases the capacity or politicalwill to apply the modified legal and regulatory framework was not manifest. Particularly in small economies withlimited implementation and coordination capacity, a relatively simple reform program focused on a few key areas stands a greaterchance of success than a wider-ranging initiative. In this case, the relative lack of success was due in no small part to anover-ambitious design involving ten sectors and thirteen agencies.
P147157 | BRAZIL BAHIA SUSTAINABLE RURAL DEVELOPMENT PROJECT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2014 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024215524537/text/P1471571d76ff209c19ff8194b7fbf07c0d.txt | http://documents.worldbank.org/curated/en/099053024215524537/pdf/P1471571d76ff209c19ff8194b7fbf07c0d.pdf | The ICR included five lessons, out of which this review has highlighted with some adaptation in language the following threelessons that has broader applicability.It is important to recognize that not all family farmers have the potentialto participate in market integration. In such instances, grant financing could support collaborations between mature and lessmature institutions (e.g., POs). Project experience showed that more mature POs had higher revenues. On the other hand,small-scale, less organized, and newer POs had difficulty selling their products and integrating into markets. In suchcircumstances, Call for Proposals and Business Plans should be open in seeking applications from a collaboration between mature andweaker POs, enabling the weaker POs to gain knowledge and benefit from the experience of the more experiencedPOs.In Productive Alliance type of projects, developing partnerships with key research and extension agencies, andproviders of financial services can enhance POs growth and promote innovations. Research and extension agencies playimportant roles in technology generation and adoption. POs should tap their services, to be complemented by linking to providers offinancial services and technical assistance. Such linkages can be essential in sustaining the growth ofPOs.Productive Alliance type ofprojects require strong ME design with appropriate technical staff thathave adequate knowledge of productive and market activities in a particular sector. For PA projects, project preparationshould include design of a strong ME system consisting of a combination of staff who have quantitative, technical andextension skills. Ex-ante preparation would allow such projects to effectively design early project activities such as Call forProposals which will create the platform for smoother project implementation. In this project, given that there were weaknesses ofquality at entry, particularly with the ME system, the project faced considerable delays during the early stages.
P147166 | HRF Grant for Strengthening Governance in Education and Water Sectors | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | DPF | 2014 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/322841498832900914/text/ICRR-Disclosable-P147166-06-30-2017-1498832896643.txt | http://documents.worldbank.org/curated/en/322841498832900914/pdf/ICRR-Disclosable-P147166-06-30-2017-1498832896643.pdf | This review suggests three lessons:1. A stand-alone DPO supporting only initial and partial prioractions is unlikely to succeed in a country characterized by a weak programming capacity. Haitis eighteen-month operationsupported prior actions that were incipient in nature (e.g., a regulation requiring ministries to submit expenditure forecasts) andthat required time to be implemented as well as complementary measures (e.g., accurate commitment data). This made it unrealisticto expect improvements (e.g., better cash management) within the operations time horizon.2. A stand-alone DPO mayprovide only weak implementation incentives. The operation by itself did not encourage ministries to implement the PFM, educationor water reforms. Those in charge of implementation need to own the reforms and be supported by strong leadership andfunding.3. Monitoring indicators reflecting only outputs will not allow an adequate assessment of a reform program. TheHaiti DPOs indicators (e.g., whether arrears were measured or not) did not allow an adequate assessment of the outcome(e.g., whether arrears declined or not).
P147183 | Innovative Access to Finance | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2015 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/132111580140758055/text/Turkey-Innovative-Access-to-Finance.txt | http://documents.worldbank.org/curated/en/132111580140758055/pdf/Turkey-Innovative-Access-to-Finance.pdf | This reviewagrees with thefollowingthree lessons identified in the ICRand rephrased belowregardingthedesign and supervision of a line of credit operation: To warrant long term sustainability of theline of credits outcome, commercial and financial viability needs to be at the core of the criteria of allocatingloansto final beneficiaries. Using theline of credits eligibility criteria of PFIs, sub-borrowers andsub-projects, as well as the terms and conditions of subsidiary and sub-loans, allocation of credits to final projectbeneficiarieswere based on financialand commercial viability oftheir undertakings.Theprojectslegal covenants helped to ensure sustained application of the criteria and the terms and conditions throughout projectimplementation. Toward capturing thedevelopment impactofthe Banks lineof credit operation, there is a need toincorporate in the operation design a better approach ofassessing the economicand financial efficiency of the operation. The assessment on development grounds ofa line of credit should not stopat pumping longer-term funding into apex banks and PFIs, it should ensure that there is a rigorous assessment of the economic andfinancial costs and benefits accruing to the key involved stakeholders. Previous similar projects and this onehave overlookedthis aspect, and this has led to the weakening of the projects results chain andits efficiencyassessment. For a credit line to respond to the borrowers needs, its supervision mustincorporatea regularmonitoring system of the developments affecting the countrys and international financialmarkets. Both nationaland international financial markets tend to be continuouslyvolatile.Thesupervision ofaline of creditneeds to monitor market developments, the financial health and eligibility of PFIs,and the quality of Bank-funded portfolios and the resulting impact on end-borrowers, in order to take timely responses when needed.This requires follow-up meetings with PFIs and field visits of end borrowers, as well astimely reporting of the main issuesfound and their resolutions for better management information.
P147185 | Mexico School Based Management Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2015 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/782981569599360238/text/Mexico-MX-School-Based-Management-Project.txt | http://documents.worldbank.org/curated/en/782981569599360238/pdf/Mexico-MX-School-Based-Management-Project.pdf | The ICR (p. 28-29) contained a narrative that IEG synthesized into the following lessons:School-basedmanagement requires both direct resources to schools and capacity-building activities to school supervisors, directors andparents. School director capacity is correlated with student learning (ICR p. 28). Instructional leaders and parentsneed training in how to effectively use financial resources (and local resources) and improve education services to improve studentlearning. The training was not just about managerial capacity, but instructional leadership skills. The ICR also noted thatdelayed resources to schools negatively impacted the activities in the school improvement plans, as these resources helped schoolsovercome challenges.Restructuring should ensure internal consistency and project teams shouldconsider including measurement of student learning. The objective and indicators in the results framework must alignwith each other. While the project restructuring corrected some weaknesses in the Results Framework, it missed theopportunity to add an indicator to measure learning (an aspect covered by the impact evaluation) and reduce the number of projectbeneficiaries from reduced resources.It also missed the opportunity to more effectively capture intermediate changes thatcould be expected from the project interventions. The restructuring continued to use indicators that measured drop-out, failure andrepetition rates, which may not have been good measures of the project activities. The ICR proposed more ambitious measuresto include student learning outcomes, as advanced by the Banks 2018 World DevelopmentReport.Additional benefits are attained when projects use analytical knowledge and data. Inthis operation, the Bank supported the government design and implementation of the impact evaluation and helped identifyinstruments to measure complex aspects such as managerial capacity or parental participation. Data from the impact evaluationand survey instruments were utilized not just for project monitoring and evaluation, but other purposes.However, more nuancedand revealing use of this resource can be illustrative of where disaggregated information can be applied to changes and approachesin one region over another. Results from the surveys were shared with school directors who participated in the impact evaluationand received a personalized diagnostic to understand shortcomings in managerial capacity. Data from the WMS and AGE surveys wereused by SEP to help inform school autonomy policies and the Banks policy dialogue with the government.
P147212 | Mexico Social Protection System Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099335003182215696/text/P14721206d85f70010ab040d2018f09f3bf.txt | http://documents.worldbank.org/curated/en/099335003182215696/pdf/P14721206d85f70010ab040d2018f09f3bf.pdf | The ICR (pp. 28-29) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:Supporting a long-term evaluation of a large social protection program enriches global knowledge. Therole of the project in supporting a long-run evaluation of PROSPERA resulted in valuable global knowledge. Long-run evaluations ofsocial programs are rare, even among OECD countries. The feasibility of such an evaluation for PROSPERA depended on sustainedcommitment by the government to a robust measurement of impact at the outset. Project financing of the final survey,resource-intensive organization of multiple rounds of surveys, and the ability of the World Bank to mobilize additional resourcesfor the analysis were instrumental in completing the evaluation cycle. Given the growth of conditional support programsinternationally, the results are expected to inform such operations.Promoting access of conditional supportbeneficiaries to other social and productive programs can be further facilitated by a legal framework and by budgetary resources tothese programs.Although access of PROSPERA beneficiaries to social and productive programs was quantitativelyattained, achieving linkages waschallenging. Preferential access was not binding. Budgets were not tagged forPROSPERA beneficiaries, and programs could opt to privilege their original clients. Opportunities and expectations to accessproductive programs were moderated by financial constraints.The broad framing of the objective to developinstruments for an integrated social protection system facilitated the ability of the project to respond to changes in governmentstrategies. Under the project, the government territorial-based strategy changed twice, but the PDO remained valid as thefocus on an integrated social information system was maintained.
P147213 | INTEGRATED SOCIAL PROTECTION AND PROMOTION PROJECT | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099100423173035920/text/P14721305134d90fa0ab930ed93c86de7e3.txt | http://documents.worldbank.org/curated/en/099100423173035920/pdf/P14721305134d90fa0ab930ed93c86de7e3.pdf | The ICR (pp. 28-29) presented insightful lessons, some of which are summarized here:Successful design ofprojects prioritizing the extreme poor will take into account their particular circumstances of poverty. In this case, thechallenges of reaching and serving the extreme poor, including lack of documentation and scarcity of salaried employment, were notfully considered in project design. Furthermore, the projects approach did not consider differences in the geographic contextof the poor; it lacked specific interventions or adjustments in operations or services for densely populated urban areas versusrural areas with high population dispersion.Interoperability efforts cover individual institutions with their ownnorms and laws that may not be compatible. In this case, the projects focus on integration of databases andinformation technology missed the need also to harmonize regulations, data sharing protocols, and actual use of integratedinformation. Integration is intrinsically a management and coordination challengethat needs to be supportedthrough specific mechanisms, arrangements, and measurement tools.
P147226 | Albania - Public Finance DPL | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2016 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/763241520260730108/text/Albania-Public-Finance-DPL.txt | http://documents.worldbank.org/curated/en/763241520260730108/pdf/Albania-Public-Finance-DPL.pdf | This review supports the lessons cited in the ICR, especially: (i) the need for the Bank to move quickly when windows ofopportunity present themselves; (ii) the need to leverage IBRD resources to help countries to de-risk; (iii) the need for the Bankto work with governments to have a proactive and well-conceived public communication plan on potentially controversial reforms; and(iv) close collaboration among development partners and governments on reforms could be productive.Otherlessons cited in the ICR with adaptation in language are thefollowing:1. Producing relevant analytical work that addresses critical challenges facing member countries, within the context of a difficultnon-receptive government could pay off at the end and enable the Bank to influence change. In the case of Albania, the Bank reliedon its analytical work to ignite its dialogue with the newly elected government. 2. Flexibility inadjusting envisaged instruments allowed the Bank to have more influence. The switch from a DPL to a PBG enabled the government togain the resources required to clear the outstanding arrears and restructure its domestic debt. 3.Working closing with other development partners helped to sustain critical reforms. In the case of Albania, the IMF introduced aconditionality to support the Banks results indicator on the non-accumulation of new arrears.4. Identifying and working with senior members of government who are champions of the Bank- supportedreforms is critical to successful implementation of programs. In the case of Albania, the Strategic Planning Committee, chaired bythe Prime Minister, provided a mechanism for holding ministers accountable and addressing bottlenecks in a timelymanner.
P147244 | Third Upper Secondary Education Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The following lessons are selected from the ICR:The DPL Programmatic Series was the most suitable Banklending instrument to provide general budgetary support while accompanying a reform program. The DPL Series allowed adjustment tothe pace in which policies were implemented and was also helpful for policy continuity despite changes in the administration andruling party in December 2012.In countries with strong technical capacity such as Mexico, DPLs canusefullyfocus on those elements of the reforms that will benefit most from Bank engagement. In this operation, the Bank triedto respond to the clients technical demands while being selective in choosing in which areas to support the Government basedon team composition and availability of resources.Complementary technical assistance can help to inform theGovernment reform and achieve the DPL Series objectives. In this operation, the technical collaboration between the Bank and theGovernment helped shape the policies introduced by the upper secondary education reforms based on evidence and international bestpractices. The provision of just-in-time technical assistance helped overcome the main obstacles faced during implementation of thereformAligning DPL Program indicators to official indicators helps decrease the ME burden of the Program for theGovernment and allows the team to obtain more reliable and timely information. When the Bank team aligned its indicators to theofficial indicators in DPL 3, ME was greatly improved because the implementing agency had more pressure to periodicallycollect and report data on official indicators.Introducing school accreditation processes requires taking intoaccount schools starting conditions and their ability to improve the education services they provide. Gaining fullaccreditation to enter the upper secondary education system proved to be challenging for most schools in Mexico. In many instances,schools found it difficult to comply with the full accreditation criteria and many lacked the necessary resources to complete theaccreditation process. To tackle these issues, as in the Mexican case, policies might consider allowing schools to gain temporaryaccreditation if they comply with a set of minimum criteria of quality and commit to specific quality improvements over a certainperiod of time.
P147257 | MA Capital Market Development & SME Finance DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2014 | 2015 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/945831582041717659/text/Morocco-MA-Capital-Market-Develop-SME-Finance.txt | http://documents.worldbank.org/curated/en/945831582041717659/pdf/Morocco-MA-Capital-Market-Develop-SME-Finance.pdf | Two lessons are drawn from the ICR (pages 38-39), with some adaptation, and a third is added by this ICR Review.Government commitment to reform objectives are crucial to the success of structural reform programs. Inthis programmatic development policy operation, the government of Morocco went beyond completing the 18 prior actions for theseries to proactively plan for,as well asto undertake, more measures that would advance its reform objectives.The government had a long history of commitment to the development of its financial sector dating back to the creation ofthecredit guarantee agencyin1949andthe financial market regulator in 1993. Following this DPF series,the governmenthas continued to engage FIRST with technical assistance projects, the IFC with a capital market developmentprogram, and the Bank with a financial inclusion DPL.Policy and structural reform programs in the financialsector can benefit from the provision of technical assistance both for program design and program implementation.The implementation of this programmatic development policy operation was supported by 25advisory services andanalytics activities under 9 technical assistance projectssupported by FIRST, in areas including: MSME finance; capitalmarket laws, rules,and regulations; credit information systems; financial inclusion, and financial stabilityframeworks. The advisory services and analytics supplied valuable technical inputs to the reform measures,including knowledge about international standards and practices. Moreover, according to the ICR, the technical assistance,whichwas well integrated into the operation, helped ensureits successby: supporting the implementation of theprior actions, and strengthening the capacity of the implementing ministries and agencies.In designingME plans, it is important for governments and the Bank to ensure that public or private information systems can supply thedata required for reporting on results indicators. In this programmatic development policy operation, the privatecredit bureaus information systemdid not report the size of enterprises --- large, medium, small and micro enterprises--- that requested and received credit reports. Thus, the attainment of the target to have 40,000 MSMEs covered by creditreports could not be ascertained. Similarly, the credit guarantee agencys information systemdid not report on theage of enterprises --- newor young --- covered by its guarantee and co-financing operations. Thus, the attainment ofthe target to raise the number of newor young enterprises from 1,572 to 3,000 could not be ascertained either.
P147272 | BAHIA ROAD REHABILITATION AND MAINTENANCE PROJECT - 2ND PHASE | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099042423155541912/text/P1472720e4e9200e60ab700f6eba0a88e43.txt | http://documents.worldbank.org/curated/en/099042423155541912/pdf/P1472720e4e9200e60ab700f6eba0a88e43.pdf | The ICR (43-55) included several lessons learned which were adapted by IEG: Providing a World Bankguarantee that would cover any delay in payment from the government to the private sector would make projects like this moreattractive and feasible for private sector engagement. In this project, the concessionaire faced difficulties in closingthe commercial loan necessary for contractual investments due to the difficult fiscal situation Brazil is in, which resulted indoubts as to whether the state would be able to pay the concessionaire over 20 years. However, such guarantees come at a cost whichhas to be weighed against the risks. Ensuring that ES requirements for contractors, andenvironmental specialists are clearly specified and included in contracts is critical for compliance with the Bankssafeguard policies. In this project, the construction companies did not follow the specifications of the Environmental andSocial Specifications as this was not explicitly stated as a payment item. Also, the responsibilities of environmental specialistswere not clearly defined at several work sites resulting in limited inspections only at the beginning and the end of interventionswhen many activities had already been completed. Combining a citizen engagement approach with atechnical review to identify targeted feeder roads is critical for ensuring the sustainability of project outputs. In thisproject, feeder roads were only identified by members of the community resulting in them being dispersed across the stateand making road maintenance for the consortia challenging.
P147277 | Distribution Grid Modernization and Loss Reduction Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099111723171524849/text/P147277029412d0ae08f390da5ae9641607.txt | http://documents.worldbank.org/curated/en/099111723171524849/pdf/P147277029412d0ae08f390da5ae9641607.pdf | IEG derives the following lessons drawn from the ICR:1. Achieving sustainability in distribution systemscharacterized by long-standing issues of high energy losses calls for a multidisciplinary effort: As illustrated bythe project, the vicious circle of no service, no payment culture needs to be broken, requiring a continuouscommercial and social management effort, combined with technical monitoring, and with the active and coordinated participation ofthe distribution utilities and the affected communities. In areas where clients will be formalized, it is essential tomonitor developments closely in order to avoid the influence/pressure of new or returning fraudulent initiatives. TheGovernments political will plays an especially important role. Loss reduction projects require sustained support overthe medium term, and a continued effort in strengthening institutions.2. Managing a large number ofsimultaneous contracts within a single project requires effective monitoring practices and tools: As illustrated bythe project, these included adequate institutional arrangements (including staff capacity and quick access to information), abilityto monitor contracts effectively, and the use of software to monitor all contract activities in the field in an integrated andcomprehensive manner, so as to strengthen controls and achieve more efficient technical and administrative processes. Inaddition, a close working relationship between the Borrower and the World Bank is helpful in identifying problems early. Themaintenance of rigorous construction records is essential in monitoring progress of works (and to help resolve any conflictsbetween contractors and utilities). Finally, it is a good idea for contracts to incorporate strong efficiency incentives,especially in their payment schedules.3. Adequate and timely procurement support by the World Bank (interms of capacity and expertise) can be critical during initial stages of implementation: This is especiallyimportant when, as in the case of the project, a significant part of the projects procurement relies on a single mainpackage. The early preparation and approval of high quality and timely set of bidding documents, and the contribution of theBanks relevant specialized staff, can help determine the eventual success of the project.
P147342 | Peru: Enhancement of Environmental Quality Services | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099091323121033190/text/P1473420ad626b09a0a72b0b9cd9e6c4172.txt | http://documents.worldbank.org/curated/en/099091323121033190/pdf/P1473420ad626b09a0a72b0b9cd9e6c4172.pdf | The following lessons are adapted from the ICR with some modifications of language:Requiring one approach toprocurement without first understanding the countrys operational context can lead to lengthy delays in projectimplementation. The main contract of the project, the environmental analytical laboratory, comprises goods and civilworks having unique technical features. Although the Bank initially recommended that the Borrower procure the laboratorysgoods and civil works separately, an approach commonly used in similar Bank investments in other countries, the Bank accepted theimplementation agencys proposal of a single-contract approach under the projects specific operational context, whichincluded the COVID-19 pandemic, frequent administration changes, the remaining implementation period, and slow and complicateddomestic review procedures.Pollution control projects that finance improvements in environmental monitoring,analytical infrastructure, and information sharing and disclosure without corresponding improvements in regulatory compliance andenforcement may fail to establish the incentive or urgency to complete the investment. During project preparation,the Bank team presented alternative project designs, based on successful global experience that would have includedimprovements in environmental enforcement and compliance to create a demand for environmental monitoring and information disclosureand ultimately demonstrate actual improvements in environmental quality. However, the GoP chose only to focus on environmentalmonitoring and disclosure in the project with the expectationthat future operations would consider support to enforcement.Such a design failed to create an urgency for completing the project-financed upgrading of environmental monitoring and analyticalinfrastructure. This design also failed to achieve the PDO or have any significant development impact.Projects innew sectors that do not have a flexible design may struggle to adjust to unexpected events during projectimplementation. In the case of his project, the Bank had introduced a project in a new sector in the country and didnot allow sufficient time for completing feasibility studies and other national requirements (including processing for domesticapprovals) as part of project implementation. Further, the main project instruments (for example, PAD and Operations Manual) alsolacked flexible designs and clear processes for coping with unexpected implementation challenges that were beyond the control ofthe implementing agencies and the World Bank. When the initial country risk assessment showed high political, institutional,and macroeconomic stability levels, the project design should have built-in flexibility to cope with potentially lengthydelays.An overly optimistic loan repayment period can undermine the completion of a project and the achievement ofproject objectives. The Governments insistence on repaying the loan five-and-a-half months after project closuremeant that the project could not be extended to allow the Bank support to continue to finance the remaining activities untilcompletion and to provide the needed technical support for implementing the most important environmental sector actions recommendedby the OECD. The project closed at a time when most of the main procurement documents were still being finalized.
P147343 | Public Financial Management Reform Program Phase I | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/976361593460396998/text/Zambia-ZM-Public-Fin-Mgt-Reform-Program-Phase-1.txt | http://documents.worldbank.org/curated/en/976361593460396998/pdf/Zambia-ZM-Public-Fin-Mgt-Reform-Program-Phase-1.pdf | The main lesson from this ICR relates to the usage of PEFA scores as PDO indicators. PEFA scores are not straightforward andthey are challenging to measure. Meticulously described PEFA scores with an emphasis on actions that need to be undertaken for anupgrade/downgrade would help strategize better in achieving targets.
P147348 | Transmission Grid Strengthening Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2014 | 2023 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099092424082044229/text/P147348-47412b8b-ff47-4888-aabf-1bae3e5aa649.txt | https://documents.worldbank.org/curated/en/099092424082044229/pdf/P147348-47412b8b-ff47-4888-aabf-1bae3e5aa649.pdf | IEG derives the following lessons from the ICR:1. The transition from a merit order-based regulatedsystem to a market-based system for providing stable low-cost power to the consumer needs to take into account the level ofdevelopment of the system: As demonstrated by the project, the degree of volatility identified by the market openingstudy and the initial lack of consensus on an appropriate market structure suggested that careful consideration needed to be givento the structuring of the wholesale market in terms of its institutions and regulatory framework, to provide assurance of a stablerevenue stream for new entrants. Secondly,the regulatory environment for such a market needed to provide assurancesearly on of prevention of market abuse. Thirdly, the relative fiscal costs of the safety net under market-based pricing (asagainst a regulated tariff) needsto be carefully considered in designing the structure of themarket.2. The form of contract for power transmission or large projects with potential ES impacts needsto separate activities by responsibility, for more efficient execution: Specifically, for power transmissionprojects, route planning and the related ESIA need to provide for a waiting phase during which the Government would complete allnecessary processes for registering lands and properties, complete any RAP compensations, and issue all necessary permits.Under this scenario, the contractor would remain in standby during this permitting period without incurring anycosts, until this phase is completed. This approach was utilized for ESRFRP-funded contracts for the Jvari-Tskaltubo 500 kVtransmission line construction, as well as for the KfW-funded transmission line, and appeared to be successfully avoiding thetypical complications that could arise.3. While quality and cost considerations are important, it isimportant not to lose sight of the fact that contractor capabilities constitute an important criterion: This isespecially true with respect to ES issues and also with respect to supervision contracts needing more careful consideration ofprocurement which would apply to most large transmission projects. In this regard, adherence to pre-qualificationunder the Banks procurement guidelines is a key factor to consider for large transmission projects.
P147356 | Ethiopia Statistics for Results Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | RETF | IPF | 2014 | 2020 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/516891592860374124/text/Ethiopia-Ethiopia-Statistics-for-Results-Project.txt | http://documents.worldbank.org/curated/en/516891592860374124/pdf/Ethiopia-Ethiopia-Statistics-for-Results-Project.pdf | The lessons in the ICR (pp. 26-27) are deemed appropriate and precise.a) Having client commitment, ownership, andaccountability around a strengthened NSS is key for the achievement of results. The CSA has demonstrated a high level of commitmentto statistical development. In this case, there was: (a) a continued understanding of project objectives and support for itssuccess, related decision making, and management of the project; (b) a clear understanding of how the project was helping indevelopment of the institution; and (c) a deeper knowledge of the broad sector reform process.b) Without properfollow-up and oversight of achieved project results, there is risk to their sustainability. Risks might be a consequence ofinsufficient government funding after the project completion, lack of facility maintenance, inadequate or no professional trainingfor staff, etc.In addition, IEG lists these closely related lessons:a) Having a significant presence of the WorldBank team in the country in which a project is being implemented greatly contributes to the success of a project.b) Thecapabilities and experience of any institution responsible for the implementation or organization of some activity need to beassessed beforehand in order to avoid any issues that might hinder the achievement of objectives. In this case, the PIUhad insufficient experience in managing procurement processes.c) If any project outcome targets or objectives depend onthe quality of internet connection, this needs to be taken into account, and measures should be taken to either increase internetquality or find a way to work around the issue. In this case, the poor internet connection greatly affected staff training andslowed down procurement processes. The issue of internet speed and reliability is of particular importance for projects indeveloping countries.
P147367 | Xinjiang Technical and Vocational Education and Training Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2015 | 2020 | 2024 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099121923091514551/text/P1473671ae8f980cc18ed612fa04cea9d7e.txt | http://documents.worldbank.org/curated/en/099121923091514551/pdf/P1473671ae8f980cc18ed612fa04cea9d7e.pdf | Lessons drawn from the ICR (pages 30-31) and adapted by IEG: In the context of complex social dynamics and highsocial risks, more intensive preparation and supervision can inform the Banks engagement on the operation. In the caseof this project, a more in-depthsocial assessment, robust risk monitoring mechanisms and candor in project supervisionratings, dialogue with Bank specialists and/or outside organizations, could have identified the key social risks more clearly andapplied mitigation measures more effectively. For projects with highly diverse implementing institutions,theME framework can more effectively measure results by disaggregating the indicators. In the case of this project, the keyproject indicators only provided an average figure, which was an aggregate of the results from the five project schools.However, given the very different baselines for each of the schools, these aggregate figures could not distinguish the variedperformance by school and made attribution to the projects interventions challenging.
P147381 | Zhuzhou Brownfield Remediation Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2016 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099120523143011604/text/P147381048dedd09d0ad650e962a58e8952.txt | http://documents.worldbank.org/curated/en/099120523143011604/pdf/P147381048dedd09d0ad650e962a58e8952.pdf | Linking brownfield remediation projects to local land use plans can increase the chances for project success.In the case of the Zhuzhou Brownfield Remediation Project, future land-use had a strong bearing on the required levels ofdecontamination. The redevelopment interests of the leadership of Zhuzhou also exerted time pressure on the project during theearly stages of land remediation. Thus, from the early stages of project preparation, the World Bank stayed in close communicationwith the leadership of Zhuzhou to inform them of progress made on the project and to seek coordination. Because senior officialsfrom the municipal government and the Development and Reform Commission as the development planner were strategically engaged tohead the PMO, the project was on the local governments radar, which allowed the linking of remediation work with urbanspatial planning, redevelopment, and financing. This high-level involvement was also instrumental in facilitatinginter-departmental coordination on remediation and redevelopment matters. As such, the project contributed to theoverall remediation and redevelopment of QIZ.Flexibility in project design may allow land decontamination andrestoration projects to proceed in the context of a highly dynamic planning environment. To adjust to the changingdemands in the project area, the design included a menu of remediation measures that could be used according to site specificcircumstances, contamination levels, time available for restoration, and future land-use. The project design had the flexibility toaccommodate third parties to take over site remediation in parts of the project area, as long as their remediation activities wouldbe implemented according to the same standards for land cleanup and managing potential social and environmentalimpacts.High quality contaminated site investigations and risk assessment can lead to designoptimization. The project feasibility study investigated the restoration and redevelopment needs within the originalproject area of 8.48 km2. The study also identified the different types of plots in the project area that were in various phases ofdevelopment and had varying needs for interventions. The plots included those where industries had already been relocated andredevelopment was in process, land plots where remediation and redevelopment were planned in line with the anticipated time spanfor project implementation, and plots where redevelopment was expected only after 2020. The most suitable site remediationapproaches were determined on the basis of three main parameters: (a) soil and groundwater contamination levels, (b) current landuse and the presence of people and structures, and (c) future land use based on the strategic plans. The project area was thendivided into 100+ plots, where each of the three main parameters was homogeneous, and the most suitable remediation approach amongfive to ten different technologies was selected for each plot. This approach ensured the tailoring of remediation to site-specificcharacteristics, while maintaining the flexibility to change from one approach to another in case the use of a land plot was tochange in the future.World Bank risk management applied to third party remediation works may ensure that bothBank-financed and third-party remediation investments within an appraised project area meet the same technical, environmental, andsocial standards. In the Zhuzhou Brownfield Remediation Project, the World Bank ensured that the following mitigationmeasures were in place for the site remediation in the parts of the project area that came under the Zhuzhou MunicipalGovernments PPP agreements: (a) priority should be given to World Bank-financed activities through carefulplanning, phasing, interfacing and coordination with third-party activities; (b) third-party work plans and redevelopment progressshould be communicated to the World Bank in a timely manner; (c) as stipulated in the project legal agreement, all remediation andredevelopment activities in the project area shall adhere to the same technical, environmental, and social standards applied to theproject; (d) the PMO/PIU was to carry out due diligence on third-party remediation activities and provide a report to the WorldBank; (e) the PIU would have designated staff for monitoring and monthly reporting on the status of third-party remediation to theWorld Bank; and (f) the PIU would solicit verification by the municipal environmental authority for all completed third-partyremediation works in the project area.
P147438 | Mongolia Export Development Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099101624224542438/text/P147438-ff21e34d-7a28-4f8d-bb60-a74f743219d4.txt | https://documents.worldbank.org/curated/en/099101624224542438/pdf/P147438-ff21e34d-7a28-4f8d-bb60-a74f743219d4.pdf | Three lessons are drawn from the ICR, with some adaptation.Export development and SME development require morethan interventions at the enterprise level and would benefit from an enabling business environment buttressed by policyreform.This project focused onmicro-level activities like quality assurance and export insurance, which, whileimportant, would bemore effective in the context of a competitivebusiness environment that supported private sectordevelopment. This project also added two activities at the second restructuring --trade and export policy enhancement andinternational market competitiveness enhancement-- although their outcomes and targets were not explicitly defined andmeasured. Policy and business regulatory reforms in critical areas, including trade facilitation, access to finance, and skillsupgrading, would be relevant to export development and SME development.Export development projects need toconsider the role of private enterprises and organizations in the export drive. In this project, the Government and theWorld Bank made a strategic decision at restructuring to shift the provision of export credit insurance to SME exporters from aproposed new SOE, Export Insurance Subsidiary at Ag Re, to private insurance companies instead, with the SOE, Mongolia Re,providing reinsurance, following similar models in East Asia. Elsewhere, this project focused on the provision of ProductivePartnership Scheme grants by the Project Implementation Unit at the MOFALI and quality assurance services by the Research andDevelopment Center also at MOFALI. Many project interventions in an export development project can be provided by the privatesector, including business development services by private management consultants (e.g., business development service providersemployed by development partner SME programs in the country), quality assurance services by private testing laboratories andcertification services, and trade finance products by private banks and non-banks.Export developmentprojects would benefit from the careful design, scoping, and piloting of planned interventions. In this project, thecluster approach to SME development, while based on the sound concept of business collaboration, was not readily adopted bySMEs,as only 10 of atarget 20 clusters of interconnected SMEs benefitted from the Productive Partnership Scheme. Thecluster approachshould have been tested well before implementation. In the same manner, the World Bank and governments shouldcarefully study and scope proposed interventions and their alternatives, including whether export development should focus on SMEsor large enterprises, a selected set or a broad range of industries, government agencies and SOEs or private service providers andfinancial intermediaries, andgovernment funding or co-financing by the private sector.
P147454 | CATASTROPHE DEFERRED DRAWDOWN OPTION (DPL with DDO) | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2014 | 2017 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/648591537796001024/text/Sri-Lanka-CATASTROPHE-DEFERRED-DRAWDOWN-OPTION.txt | http://documents.worldbank.org/curated/en/648591537796001024/pdf/Sri-Lanka-CATASTROPHE-DEFERRED-DRAWDOWN-OPTION.pdf | Five lessons were drawn from the ICR: (paragraphs 80-84) Arational government policy on disaster resiliencethat identifies actionable measures could be used to reinforce resilience by bringing together a variety of financing instruments.For example, this operation called on the budgetary support froma DPL to help push the Governments disaster resiliencepolicy reform by making available budget support during recovery operations, providing less strain on government coffers. Second, adeferred drawdown option could provide a multi-year window combined with rapid release after triggering an agreed upon condition.Third, an IPF could show examples of how to implement resilient infrastructure design, in this case road design.Fourth,complementary TA grants such as the Open DRI, could help launch an open platform to amplify its benefits. Adrawback in combining instruments was relying on disparate ME designs of individual instruments to monitor DPL outcomeindicators. There was a need to synchronize timelines to meet project requirements. In this case, 3 of the 9 PDO indicators werenot monitored well because these were implemented outside the Bank financed TA. Moreover, targets under a 5-year IPF implementationperiod may be met in Year 4 but remain unmet under a 3-year DPL program. A DPL with a Cat DDOinstrument could induce DRM policy making. In this case, along prepared National Disaster Management Plan and long discussedNational Spatial Data Infrastructure concept were pushed along as prior actions under the project. After the prior actions wereachieved, TAs supported policy implementation of the plan and the spatial data infrastructure. A DPL with a Cat DDOshould adopt some flexibility, such as what-if scenarios, to respond in a timely manner to changes during implementation includingunexpected shifts in government priorities, difficulties in enforcing conditions, or improved practices introduced by the project.At present the DPL with Cat DDO does not allow practical ways for both clients and task teams to reflect changes in targets andpolicy shifts leading to the achievement of the PDO. For example, in this operation, the Government reasonably prioritized twocritically important basins rather than meet the original target of nine basin plans but such change resulted in partially achievedtargets. Another example was the Governments decision to replace a national circular and instead require local governmentsto adopt standard by-laws that recognize their important role as first responders and primary actors in implementing DRM measures.There was no restructuring option, for example, that could favorably adjust the results framework. Another what if scenario couldbe alternative triggering actions for the drawdown option since the government had never issued a disaster declaration even thoughit had the 2005 Disaster Management Act in place. A DPL with a Cat DDO could showcase effective coordination of DRMrelated policy actions between government financial and planning authorities. This coordination could be reflected in timely andappropriate budget allocations during the post-disaster emergency and recovery periods. For example, in this case, MoF and MNPEAelevated the DRM agenda by clarifying roles in strengthening financial resilience and coordinating the overall DRM agenda. Withenhanced capacity, the NPD lead the PDNA and recovery planning process together with the Ministry of Disaster Management,facilitating the timely budget allocation for emergency and recovery works.
P147486 | TZ Education Program for Results | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | PforR | 2015 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061824182072908/text/P147486-1b6e9cd3-4826-4a8b-af73-837cf6ed2f3c.txt | https://documents.worldbank.org/curated/en/099061824182072908/pdf/P147486-1b6e9cd3-4826-4a8b-af73-837cf6ed2f3c.pdf | The ICR (pp. 43-47) offereda wide range of lessons in the areas of governmentownership and development partnerharmonization, program design and implementation, application of the split rating methodology, and designing outcomes andobjectives. IEG restates some of the key lessons here:A PforR instrument can support continued government focus onprioritizing results even during shifts in implementation context. In this case, the continuous dialogue between thegovernment and the Bank (and other development partners) regarding progress on activities and achievements incentivized by theprograms DLIs helped maintain focus on education quality and learning outcomes,even withthe addition of fee-freebasic education and added priority of expanding access,Disbursement-linked incentives are most effective when theyare aligned to institutions at the government or implementing agency level that can best influence the desired results. Inthis case, separate DLIs were well constructed to target schools, local government authorities, and institutions at the nationallevel.Learning outcomes can serve as effective outcome indicators, but only if the indicators carefully takecontextual dynamics into account when specifying how learning is measured. In this case, the significant expansion ofstudent enrollment during program implementation meant that more students from disadvantaged backgrounds were included in theoverall student population, and therefore the learning measures used at the beginning of the program were not necessarilyappropriate later. New types of indicators, including learning-adjusted years of schooling and learning poverty, can provide moremeaningful measures of progress in these kinds of situations.
P147489 | AFR RI- Great Lakes Emergency Sexual and Gender Based Violence & Women's Health Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/577281636641142625/text/Africa-Great-Lakes-Emergency-Womens-Health-Pr.txt | http://documents.worldbank.org/curated/en/577281636641142625/pdf/Africa-Great-Lakes-Emergency-Womens-Health-Pr.pdf | The ICR (pp. 47-49) offered many lessons and recommendations, including the following lessons restated byIEG:This project illustrates the importance ofmaking adequate provisions for evaluation whentesting newinterventions, evenin FCV settings. The project contributed to the evidence-base on interventionsto prevent and mitigate the effects of GBV in low income and fragile settings. Project funds supported the evaluation of twoinnovative approaches to improve mental health of survivors (through NET)and prevent intimate partner violence(throughits Agents of Change program that trained couples). The IE of NETin DRC and the IE of couples training in Rwanda bothshowed promising results that will undoubtedly inform future interventions as already shown by the government of Rwandas useofthe evidence of the couples training program to inform the decision of whether to scale up the interventionnationwide.Partnering with experienced local NGOs and leveraging existing capabilities achievesgreater results, especially in low income and fragile settings. Centers of Excellence provided specialized care andcomprehensive services to GVB survivors, that were otherwise not available in DRC Eastern provinces. This effort aimed atcomplementing and improving existing services. The specific expertise of Centers of Excellence contributed to train publicproviders and increased community outreach, while filling service gapsthrough, for example, mobile clinics. This strategyultimately contributed to increase the quality and availability of GBV specialized services and reproductive, sexual and maternalhealth services in public facilities and it was then replicated in Burundi and Rwanda. While the ICR reported issuesinreferral systems between Centers of Excellence and public facilities, the importance of investing inexisting NGOsresources and strengthening links with publiclyrun facilities in fragile and low-income setting should not be undervalued,given the limited capacity and resources in those settings.Working with existing local leadersandcommunity-basedorganizations enlarges project outreach. The outreach of the projects was larger whenservices were delivered with community-based organizations. The project worked with local leaders to change norms and practices,decrease stigma around GBV, and raise awareness about available services. The project also partnered with CBOs to conduct communitytherapy sessions and deliver services. This approach helped broaden awareness which resulted in more people searching forindividualized servicesin DRC and Burundi.Reducing social and cultural barriers for SGBV survivors toaccess services takes time and should be internalized in project ambitions at the design stage.While the projectrecognized this issue in its design, it didnot fully incorporate it in its PDO and intermediate indicators until very late inimplementation. The greater than anticipated difficulties in identifying SGBV survivors within communities and linking them tohealth services observed in Burundi and DRC were noticed after the Mid-Term Review. Had the reasons for not accessing services beenexplored earlier, this would have resulted in more accurate targets and less changes near the end of project implementation.
P147499 | Sustainable Croatian Railways in Europe | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2024 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099061324080523976/text/P147499-c777c811-16bf-402f-90d8-63abd31e6c36.txt | https://documents.worldbank.org/curated/en/099061324080523976/pdf/P147499-c777c811-16bf-402f-90d8-63abd31e6c36.pdf | The following lessons were derived from the ICR (ICR, pages 28-29):1. The Projects experiencehighlighted the WBs convening power to leverage EU funding to support reforms and infrastructure investments that lay outthe basis for sector modernization and competitiveness. Critical to the success of the supported reforms was a broad-basedcommitment by government and stakeholders, as well as the capacity for reform implementation. A good assessment of the level ofcommitment and capacity can provide critical information for project design, including the timing, scope, and sequencing ofreforms, as well as for risk mitigation. However, there can be external factors and unforeseen circumstances, which, in case of thereviewed Project, included COVID-19, supply chain disruption, and a spike in inflation. The lesson learned from the reviewedProject is that in such operating environment, a flexible project design could help with the necessary adjustment to the changingcircumstances and support the utilization of new opportunities when planned activities turn out to be no longerfeasible.2. The Project was negatively affected by the deficiencies of its ME framework, specificallyoverambitious targets and indicators that were not fully attributable to the Project. More generally, in largeinfrastructure projects, often standard, industry-wide performance indicators are included in the RF without considering if theyare within the project scope and control. In measuring the outcomes of institutional reform, often RFs rely heavily on output levelindicators that do not necessarily measure the envisioned change in the relevant sector institutions. The Projects MEframework was restructured multiple times but still contained inadequate and inappropriate results indicators, making it hard toassess progress toward the achievement of the PDO. The Project would have benefited from a presence of experienced MEspecialists on the team and/or in the implementing agency, especially during key implementation points, such as appraisal, mid-termreview, and evaluation. The lesson learned is that when RF has significant deficiencies, its adjustment through restructurings canbe challenging and if significant changes are made to the RF during implementation, it can impair the RFs capacity tocontinuously monitor project performance.
P147514 | Madagascar Emergency Food Security and Social Protection Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/107141557329581171/text/Madagascar-Emergency-Food-Security-Social-Prot.txt | http://documents.worldbank.org/curated/en/107141557329581171/pdf/Madagascar-Emergency-Food-Security-Social-Prot.pdf | The ICR included five lessons. The following two are emphasized with adaptation oflanguage: Projects attempting to promote rice intensification need toaddressimproving irrigation infrastructure in order to achieve the desired outcomes. The availability of adequate amounts ofirrigation water stabilizes rice yields. Without rehabilitation and maintenance of the irrigation infrastructure, water lossesincrease, leading to areduction in yields. Limited availability of irrigation water results in stressed plants that do notrespond tointensification activitiessuch as improved inputs andgrowing practices, among others, andeventuallyfail to produce the desired yield. Emergency operations can indeed launch IEs tomeasure the impacts of the activities. In general, emergency operations are not required to have evaluations, let aloneIEs, to show results. This project has shown that it is indeed possible to launch evaluations on time and in a scientific way tomeasure the results of project outcomes.
P147557 | PK Fiscally Sustainable and Inclusive Growth DPC | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/859611529356283059/text/Pakistan-Fiscally-Sustainable-Inclusive-Growth.txt | http://documents.worldbank.org/curated/en/859611529356283059/pdf/Pakistan-Fiscally-Sustainable-Inclusive-Growth.pdf | The first three lessons are drawn from the ICR (pages 31-33), with some adaptation. When engaging a newgovernment in a reform program, a gradual and measured approach to program design and implementationis desirable. Thestrength and durability of the political commitment to reforms is often uncertain, as is the institutional capacity of the newgovernment to execute difficult measures or even to absorb advisory services and technical assistance. The gradual approachallows a development partner and the new government to cultivate a level of mutual trust, and the new government toassimilateexternal knowledge and to developits institutional capacity,both of which are necessary for thesustainedimplementation of structural reforms. A morecomprehensive and integrated approach to privatizationthan simply focusing on the number ofequity saletransactions in any given year is likely to strengthen the reformprogram. Strategic privatizations are better set within the context of wider development agenda. A government shouldalso calibrate the scope and scale of its privatization program to its ability to plan and execute transactions, to the capacity ofprivate investors and the capital markets to purchase and to fund the purchase of state assets, and to the willingness of variousconstituencies to support SOE privatization efforts. When constructing an operationsresultsframework andits associated ME indicators and targets, it is best to set an output or an outcome for a program component, in addition todefining or describing the modality by which an objective is achieved. The creation of an OSS for business registration isreputedly a best practice modality for facilitating business registrations. But a results framework and ME plan mustspecify an output or outcome for an OSS, in terms, for instance, of the number of steps or the number of days to complete abusiness registration application. There is a need to involve implementing agencies at the planning stage of a DPO toensure they have the technical and financial resources to implement their part of the program.Planning the details ofthe OSS project with the SECP, EPBI and FRBwould have enabled the Bank and the Government to determine the ability of theimplementing agencies to execute a technology project. There is also a need to undertake active and in-depth consultationwith stakeholders to identify and mitigate political economy risks. Consultations with the constituency of various SOEs wouldhave allowed the Bank and the Government to gauge the extent of public support or opposition to the privatizationprogram.
P147557 | PK Fiscally Sustainable and Inclusive Growth DPC | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2020 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/623411595443109723/text/Pakistan-First-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project-and-Second-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project.txt | http://documents.worldbank.org/curated/en/623411595443109723/pdf/Pakistan-First-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project-and-Second-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project.pdf | 5. Lessons â€¢ In Pakistan, the World Bank reengagement with development policy lending after a long break benefited from a longer-term strategy (or program) that provides for several interrelated DPCs, a large and relevant technical assistance program, and close cooperation with the IMF. Progress made under the FSIG program in such a sensitive and capacity-demanding area as public revenue management was much more significant when compared with the World Bank's previous intervention, which was centered on self-standing investment lending. The development impact of the DPCs would have been much weaker without a long-term adaptable technical assistance package provided by DFID, and technical assistance alone would have scarcely made a dent in tax policy reform in Pakistan. Cooperation with the IMF's EFF program was a critical precondition of success in raising tax collection. â€¢ Dividing important sectoral issues among separate operations could be an effective strategy when the government is facing multiple reform challenges. In Pakistan, splitting the DPC program into two parallel DPC series helped mitigate the risks, including those related to political economy and implementation constraints; ensure more focused design of the individual series; and strengthen accountability of core government counterparts. â€¢ Political economy analysis and communication support related to politically sensitive reforms were insufficient. The privatization effort under the FSIG program was affected by an overly technical approach to the implementation of the agreed transactions, which did not consider many sensitive aspects of this process (unions, unemployment, and so on). The World Bank did not fully appreciate the influence of the stakeholders who opposed privatization and did not offer any significant communication support to the government of Pakistan to clarify the privatization process for stakeholders and explain its potential benefits.
P147629 | Agricultural Development Support Project | East Asia and Pacific | Myanmar | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099052824164517559/text/P147629197f2010ea18f7217e8b0465bcdb.txt | http://documents.worldbank.org/curated/en/099052824164517559/pdf/P147629197f2010ea18f7217e8b0465bcdb.pdf | The ICR included six lessons. The following three are emphasized with some adaptation oflanguage:1.Building mutual trust and respect betweenthe Government and the Bank is a critical firststep to re-engagea country experiencing fragility, conflict, and violence. Building rapport helps overcome initialdoubts and the lack of understanding or appreciation among the government, the Bank, and key stakeholders. It was valuable tomaintain regular contact and communication, take extra steps and time to understand the perspective and concerns of thegovernment and stakeholders, identify the common ground, point out areas and issues that require further discussion to proceed,explain the rationale and basis of the Bank policies and requirements, and offer the Banks help and support to findsolutions and build national capacity. The ICR confirmed that the Bank established a cordial working relationship with MOALI,implementing departments, and key stakeholders associated with this project.2. Irrigation projects involving dams,need to carefully but quickly assess dam safety, and ensure the implementation of all required precautionary and mitigation stepsto avoid serious accidents during implementation. During ADSP preparation, the Bank team assessed the candidate irrigationand drainage schemes. The Bank pointed out dam safety issues and remedial steps to MOALI and recommended hiring international TA.Such specialists would undertake further analyses, assessments, preparation, and implementation of dam safety plans for all dams asa priority. The procurement process for international TA and preparation of dam safety plans were considerably delayed. The SwaChaung Dam spillway collapsed in August 2018 before the dam safety plans were implementedand raised serious safety concernsabout all existing dams.3. Projects inFCV countries require a realistic ME designthatinvolvesmultiple data sources to verify results.FCV countries are usually not data-richenvironments. Baseline and impact data and other information about demographics and sector technical issues areeither notavailable or not reliable and therefore need to be generated. This can delay preparation, implementation, and closure processes orlead to inaccurate estimates of the impact of a project. In FCV countries, Bank teams can provide funding to addressthedifficulties of data access and the level of confidence in the data available. The ICR also demonstratedthatanecdotalinformation should be encouraged to back up a weak data story.
P147638 | Population and Health Support Project | Western and Central Africa | Niger | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2022 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099032524102032929/text/P147638168031208d18a0512b94ddd55bad.txt | http://documents.worldbank.org/curated/en/099032524102032929/pdf/P147638168031208d18a0512b94ddd55bad.pdf | The following lessons selected are the most relevant presented in the ICR: The lack of formalevidence-based feedback from the lower levels of healthcare and financial dependency of the lower levels of healthcare arehindrances to the transfer of performance-based financing beyond central government. Underpinning DLIswith atimed and monitored implementation plan, such as the RRI process, helps ensure results. The RRI approach focused on structuring theteams, which are composed of health staff and community members (doctors, midwives, women leaders, religious leaders, etc.). TheRRI process created a teamwork dynamic that was missing in most cases before the project. The project did not have aPIUbut relied on the countrys system to manage the operation. Indirect control over budget allocation and processesoffered gains in capacity building but made it challenging to implement timely adjustments. It isimportantto involveall actors to ensure their collaboration. The projectinvolved keeping girls in school.However, the teachers, principals, and Ministry of Education were not formally involved. Many of them were not informed aboutthe project and, therefore, did not collaborate in identifying girls and recording their attendance.
P147674 | Regional Sahel Pastoralism Support Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099510301092321302/text/P14767403a35880fa092c00cc627c208f90.txt | http://documents.worldbank.org/curated/en/099510301092321302/pdf/P14767403a35880fa092c00cc627c208f90.pdf | The ICR correctly highlights that the projects/PRAPS results are work in progress, being followed upby PRAPS Phase II. Accordingly, the six lessons highlighted in the ICR correctly focus on the more significant positive andnegative lessons learned from the Projects design and implementation experience, taking into account regional andcountry-level evidence, and the on-going challenges and risks to scaling up and sustainability of the projects results.Below is a summary of these 4 lessons presented in the ICR (with further details in paras. 65 - 71), with some addedclarifications.Lesson 1: Since pastoral activities cut across countries in similar agro-climatic zones,addressing the regional dimensions of pastoralism is vital; the division of responsibilities between the regional and the nationallevels should adhere to the principle of subsidiarity. The regional dimension of pastoralism over the entire Sahel isclear. Under the subsidiarity principle, regional activities should consist only in the residual set of activities required on theregional scene that cannot be performed at the national level. Appropriate mechanisms are needed to ensure effective regionalcoordination, including financial and procurement aspects, while promoting country-level roles and results, and sharing of relevantcross-country lessons.Lesson 2: Effective mechanisms for promoting social engagementis a critical action in fostering ownership, mitigating conflicts and ensuring adequate delivery of services and implementation ofinfrastructure, attuned to the needs of beneficiaries. PRAPS consistently and correctly stressed the importance of socialengagement and appropriate mechanisms in providing adequate and effective services and facilities.Lesson 3:Strengthening inclusion to get at the root-cause of conflicts should remain embedded in all projects targetingpastoralists. If this inclusion is not possible, projects should seek to work closely with other programs, specificallyaddressing the most relevant problem(s). Strategic inclusion activities, or the lack of them, have a key role in propellingconflicts in the Sahel as well as in forestalling and resolving them. Accordingly, the key lesson from PRAPS implementation is thatstrengthening basic social services and ensuring inclusion are core features that complement any program geared to foster strongergovernance and ownership at both regional and national levels. , with respect to: (i) managing landscapes, productive assets,or infrastructure; (ii) protecting and securing access to critical natural resources; and (iii) enhancing freedom of movement,within and across countries.Lesson 4: Diversification out of pastoral livestock activities to providealternative livelihoods will become increasingly important in a context of growing risks and uncertainty faced bypastoralists. While there is a need to support core pastoral life and production systems involving large number ofpastoralists and their families, it is important to recognize the need to also diversify out of pastoralism into viable activitiesthat may be less strenuous, less prone to risks, more remunerative, and provide a buffer to pastoral communities to betterwithstand and recover more quickly from shocks (e.g., extreme climatic events, political decisions affecting cross bordermovements, insecurity).
P147687 | Palestinian National Development Plan - Sixth Development Policy | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2014 | 2015 | 2017 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/535151483049927574/text/ICRR-Disclosable-P147687-12-29-2016-1483049918863.txt | http://documents.worldbank.org/curated/en/535151483049927574/pdf/ICRR-Disclosable-P147687-12-29-2016-1483049918863.pdf | The following lessons are taken from the ICR with some adaptation oflanguage: Designing and implementing a sequence of inter-related single-tranche operations brings considerable benefits in a highlyuncertain country environment. Such a lending strategy could serve as a robust platform for the reform dialogue and supportcontinuity of reforms, while helping to preserve flexibility. The governments commitmentto a reform process in a fragile political and institutional environment cannot be assumed to remain robust. The risk of weakeningthe clients ownership under such circumstances is usually high, which requires a development of relevant mitigationmeasures, including inter alia an adequate public communication strategy. Undertaking apolitical economy analysis to inform the design of reforms that affect vested interests could be a critical input to the programdesign, especially in the cases of reforms that in the past proved to be difficult to implement due to strong domestic politicalopposition. A proposed major reform in public procurement could be a good candidate for such a political economy study.
P147695 | Enhancing Public Management for Service Delivery in Rio de Janeiro | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/294641498764069730/text/ICRR-Disclosable-P147695-06-29-2017-1498764063170.txt | http://documents.worldbank.org/curated/en/294641498764069730/pdf/ICRR-Disclosable-P147695-06-29-2017-1498764063170.pdf | The following lessons are adapted from the ICR (paras 81- 86): When the full extent of reformscannot be achieved upfront, it is important to include in the operation sequential disbursements based on the gradual achievementof pre-conditions, which could provide continuous incentives to maintain government commitment. In afragmented implementation scenario where a number of diverse agencies are involved, a strong and committed leading and coordinatingagency with sufficient authority over the implementing agencies is needed. Also, it is important to provide incentives for eachagency to maintain commitment throughout project implementation.
P147705 | SME Competitiveness Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099210502152352730/text/P147705094a96f0ad0b44b056729bc1cd55.txt | http://documents.worldbank.org/curated/en/099210502152352730/pdf/P147705094a96f0ad0b44b056729bc1cd55.pdf | The following are lessons learned from the ICR (paragraphs 115 and 118 to 120) with someparaphrasing: Maintaining a balance between volume of technical assistance and value of direct financialsupport to SMEs can increase attractiveness of project participation for many SMEs and individual government agencies andaccordingly can increase impact of the program. Elimination of the Line of Credit resulted in a bias towards technicalassistance in the project design. The lack of developmental subsidies, such as matching grants or credit guarantees, was the mostapparent in the cluster subcomponents design. The lack of government co-financing reduced the investment potential ofparticipating SMEs and limited the pace of cluster formation. Engaging regional administrations in projectimplementation can increase the success of an SME support project particularly in large countries like Kazakhstan.Involvement of subnational administrations is valuable in SME support projects. This aspect was not considered in the case of thisproject, leaving regional administrations disengaged. The MNE does not have any representation at the subnational level and did nottry much to mobilize regional stakeholders. This limited the pace of project implementation, especially in the case of clustersubcomponent. Necessary arrangements and explicit agreements reached with potential project beneficiaries on thedisclosure of key operational results and performance data within the ME design can strengthen ME system of the projectand ensure collection of necessary evidence to capture the results of the project. As a system for collection ofperformance data from the SMEs was not part of the ME framework and was not obligatory for the SMEs to provide data,projects impact on the competitiveness of the SMEs could not be tracked and necessary evidence could not becollected. The targets in the results framework which are reviewed at each stage of project restructuring and, ifnecessary, adjusted in line with changes in project scope, can lead to better assessment of the project results. In thecase of this project, at the first restructuring, although the projects PDO remained unchanged, the activities were revisedsignificantly. Some of the indicators were also revised accordingly to reflect these changes, However, the team did not downshiftthe main project targets. In particular, the target for the number SMEs obtaining accreditations remained unchanged despite theremoval of the second stage of the SDP program from the project. This, while creating a disconnect between the project scope andproject target, also impeded the quality of ME framework. Streamlined implementation and involving limitednumber of ministry-level government agencies can improve operational and administrative efficiency in project settings with weakinter-agency coordination and institutional fragmentation. Implementation arrangements for smaller projects built aroundthe single counterpart agency or splitting responsibility for project implementation (two implementing agencies with two PIUs, eachwith its own TORs) can help management efficiency. In the case of this project, splitting the implementation responsibilitiesbetween the MNE and MIID would transfer responsibilities for implementing the better performing subcomponents, which demonstratedbetter ownership would improve project achievements.
P147740 | Health Systems Strengthening and Ebola Preparedness Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/591491607135604502/text/Cote-dIvoire-Health-Systems-Strengthen-Ebola-Prep.txt | http://documents.worldbank.org/curated/en/591491607135604502/pdf/Cote-dIvoire-Health-Systems-Strengthen-Ebola-Prep.pdf | The ICR (pp. 36-39) offered several lessons, including the following lessons restated by IEG:Pursuing asequenced implementation strategy for performance-based financing among regionscan help in facilitatingimplementation. District sequencing allowed additional time for setting up institutional arrangements, introductionof procedures, and training while learning from challenges faced by the initial group of districts.Staff movements andcollaboration among districts contributed to the dissemination of PBF processes and resultsorientation.Defining roles and responsibilities of institutional actors facilitates effectivecollaboration. Under the project, collaboration between the National Technical Committee for PBF and the ProjectImplementation Unit was deficient and could have been more effective if their roles and responsibilities were adequately detailedwith a clear description of functions.Mastering operational PBF procedures takes time. Underthe project, there was a steep learning curve, as PBF required a change in mentality in health service delivery along withadministrative and operational transformations.Time was required to set up the necessary arrangements at the central anddecentralized levels, including at the provider level. In addition, IEG identified the followinglesson:PBF can contributeto decentralization efforts. Under the project, capacityenhancements in planning, general management, and financial management contributed to the transformation of health facilities anddistricts into more proactive actors with a degree of autonomy, including for receiving and managing financial resources andbudgets.
P147758 | GN PRIMARY HEALTH SERVICES IMPROVEMENT PROJECT | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/749001637265472025/text/Guinea-GN-PRIMARY-HEALTH-SERVICES-IMPROVEMENT.txt | http://documents.worldbank.org/curated/en/749001637265472025/pdf/Guinea-GN-PRIMARY-HEALTH-SERVICES-IMPROVEMENT.pdf | The ICR (p. 25-26) offered several valuable lessons, including the following adapted by IEG: In lowcapacity and weak health system contexts, the direct supply of drugs and consumables to health facilities effectively reducesstockouts.In a post-crisis period, such as Guinea after Ebola, it was essential to use rapidmechanisms to make drugs and inputs available to reduce stockouts at health facilities in the areas affected by thecrisis. Involving the ministry in charge of local communities facilitates the implementation of healthprojects focused on primary health. This project involved the Ministry of Economy and Finance, the Ministry of TerritorialAdministration and Decentralization, and the Ministry of Social Action, which enabled sensitization of the population toparticipate actively in implementing the project. The involvement of these ministries also improved information sharing anddialogue between government agencies. Keeping a project localized in a specific geographic area simplifies itsimplementation and contributes to success. This project covered only two administrative regions out of eight in thecountry, making it easier to focus on the targets and achieve better results. The use of a specialized surveyagency ensures adequate identification of target populations.This project worked with the NationalInstitute of Statistics in collaboration with the World Banks Social Protection team to identify the populations consideredindigent, facilitating readjustment of the number of indigents considered likely to use project-supported health services duringthe restructuring of the project.In addition, the IEG review identifies the followinglesson: Setting outcome indicators, baselines, and targets at appraisal facilitates the projectsmonitoring and evaluation and avoids delays in implementation. In this case, the scarcity of information and capacityconstraints led to a lack of reliable data regarding project beneficiaries during the first three years of the projectslifetime, instability in outcome targets, and uncertainty about baselines. Consequently, there were delays in projectimplementation, a balance of funds to be reallocated, and difficulties in assessing overall projectachievement.
P147760 | Forestry Development Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041823094519136/text/P14776008b08240860b03d0368ea8b9071c.txt | http://documents.worldbank.org/curated/en/099041823094519136/pdf/P14776008b08240860b03d0368ea8b9071c.pdf | The ICR (p. 31-32) included several lessons, which are included here with minor revisions: SustainableForest Management (SFM) can have a positive impact on climate change goals as well as promote a circular economy and result in aneconomic boost for the forest sector. In this project, the intensified thinning regimes invigorated the forest stands,increased the volume of production by recovering timber from routine removal through thinning and increasedthe proportion ofhigh value logs. These interventions had climate resilience benefits in addition to the economicimprovements. Investments in new technologies requireadvanced training for the intendedusers. This project provided training to the users before the large-scale equipment was procured allowing for little timeto be lost once the new equipment came online. Investments to enhance private sector performance in thetimber industrycan significantly amplify the benefits of improved public forest management. In this project, theinvestments in modern machines increased the economic viability of SFEs which is likely toresult in their transformation tofully commercial state enterprises like those based in EU countries.
P147803 | Third Philippines Development Policy Loan | East Asia and Pacific | Philippines | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR distills the following main lessons: A programmatic multi-year DPL can provide an effectiveplatform to support reforms and institutional development. Complementary knowledge and technical assistance, as well asclose coordination among different teams and partners are vital for results. ME frameworks need to take into accountdata gathering constraints. When supportingenhanced fiscal management, acareful balance needs to bestruckbetween the risks and criticality of supporting legislative reforms, and between revenue and expenditure in budgetmanagement reforms.IEG concurs with these lessons, which are grounded in the experience of this operation. Inparticular, given the complex political economy in the Philippines,they underscore the importance of broad consultation andconsensus building thatneeds toinvolve the legislature from the outset in the discussion ofcritical policyreforms, when these depend on legislative endorsement.
P147806 | BT: 2nd DPC Series | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/356771578679845746/text/Bhutan-BT-2nd-DPC-Series.txt | http://documents.worldbank.org/curated/en/356771578679845746/pdf/Bhutan-BT-2nd-DPC-Series.pdf | The ICR has five lessons with which the review agrees. Three of the lessons are summarized below asexamples. Focusing on enacting legislative reforms rather than endorsing them for submission toParliamentwould support implementation better, and lead to achieving results; Strengthening the governments technicalcapacity would support reform implementation. Therefore, the WBG needs to focus on institutional strengthening and tailor futureoperations to existing capacity; Focusing on few key areas of reforms would help achieve better results giventhe governments weak implementation capacity.The review adds the followinglessons: Strengthening capacity alone will not solve the problems nor will better agency coordination. To designbetter programs and correct ones that do not function well,the WBG and the government must know what went wrong, why and howto improve program performance. A mismatch between means (e.g., implementation) and ends (e.g., objectives and results)calls into question the adequacy of policy design and of implementation arrangements. Because implementation is the only source ofexperience that can guide managers to test and improve programs, policy design and implementation must be looked atsimultaneously.
P147806 | BT: 2nd DPC Series | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2023 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/099435101022316985/text/SECBOS05feb09208708a9e01d5f77bd5025.txt | http://documents.worldbank.org/curated/en/099435101022316985/pdf/SECBOS05feb09208708a9e01d5f77bd5025.pdf | 3. Lessons 3.1 Overall, this Project Performance Assessment Report suggests that DPCs in Bhutan should be more selective, be sequenced to address critical constraints, have stronger risk assessment and mitigation, be complemented by support to overcome capacity constraints for implementation and coordination, and be informed by broader diagnostics. The DPC-supported reforms that were implemented successfully had complementary implementation support (from the IMF, ADB, or the Bank Group), and did not require complex legislative reform. â€¢ DPCs should be more selective, focusing on fewer and better-sequenced reforms. Selectivity filters should include reforms that address critical constraints to economic growth and stability, those that have government and parliamentary support, and those for which complementary implementation supportâ€” including to address concerns of Parliamentâ€”is available. â€¢ DPCs in Bhutan should have more thorough assessments of technical capacity and implementation risks and pay more attention to risk mitigation. Future 25 DPCs should be accompanied by plans to provide support to implementation. The existence of complementary support was key in each of the policy areas that worked well in this DPC. Capacity constraints limited the implementation of several reforms. The World Bank correctly identified capacity as a risk in Program Documents, but mitigating measures were insufficient and did not cover all aspects that required them, did not extend long enough beyond the time frame of the operation to ensure sustained implementation, or both. A more selective set of reforms (as per the lesson above) can also help focus scarce implementation support resources. â€¢ Greater attention is needed to foster coordination across ministries and agencies. For this purpose, investment project financing with results-based (disbursement- linked) indicators or Programs-for-Results may be more efficacious instruments to support the achievement of objectives. These can more easily incorporate support for knowledge sharing, capacity building, and institutional strengthening over a longer period than can development policy financing. Other development partners can also be encouraged to provide such complementary support, as was the case in this series with the IMF (on fiscal issues) and ADB (on the electronic tax filing and payment system). â€¢ DPCs in Bhutan that aim to address economic growth should be informed by a more rigorous assessment of major constraints to private sector development. The analytics used to inform investment climate prior actions of this DPC series focused on Doing Business indicators, which precluded identification and prioritization of major constraints to private sector development. These would have included the stateâ€™s role in the economy and the incipient nature of the institutions supporting the business environment. The 2020 SCD provided such a broader picture of constraints to private sector growth (World Bank 2020c); however, the assessment of the regulatory environment was limited by its reliance on aspects measured by Doing Business. â€¢ Bank Group management should consider what steps are feasible when legislation supported by development policy financing prior actions is not enacted. The programmatic approach in this case was insufficient to guarantee that prior actions requiring submission of bills to Parliament or their approval by Cabinet would lead to adoption and implementation of the DPC-supported legislation. The implications for future DPCs and other engagements with the government should be considered. 3.2 These lessons have particular importance given the role of DPCs in World Bank lending to Bhutan. During the FY15â€“19 Country Partnership Strategy period, the Fiscal 26 Sustainability and Investment Climate DPC series represented two out of the World Bankâ€™s four new lending operations in Bhutan and 42 percent of total lending by value. The additional two operations were also a DPC series (Strengthening Fiscal Management and Private Sector Employment Opportunities DPC series, approved in FY18 and FY19). The weak results in enterprise access to finance and the investment climate from the Fiscal Sustainability and Investment Climate DPC series reduced the overall effectiveness of the World Bankâ€“supported program in the country. Although it is understood that the authorities did not request other forms of World Bank lending, reliance on the development policy operation instrument alone proved inadequate to make meaningful progress toward development objectives. 1Extreme poverty is measured at $1.90 per day (2011 purchasing power parity), World Development Indicators. 2Since 2016, Bhutanâ€™s exports to India in US dollar terms have ranged between 77.7 percent and 90.9 percent of total exports, and imports from India have ranged from 77.1 percent and 83.9 percent of total imports (Bhutan 2013, 2016, 2018b, 2020b). 3World Development Indicators, Current account balance (percentage of gross domestic product); https://data.worldbank.org/indicator/BN.CAB.XOKA.GD.ZS?locations=BT. 4Access to finance (23.8 percent of respondents) and labor regulations (22.6 percent of respondents) are cited as the top business environment obstacles, per the Enterprise Survey undertaken in 2015 (IFC 2015). 5 Foreign direct investment was permitted only from 2002, in specific sectors, and there were limits on foreign ownership, a minimum investment size and debt-to-equity ratio, and restrictions on the use of foreign labor. 6The amendments also broadened the scope of business arrangements and made the Companies Act consistent with related legislation, although these aspects were not among the development policy credit (DPC) prior actions. 7Based on a World Bank Macroeconomic and Public Finance Policy Note for the government of Bhutan in November 2015 and other work (Boyreau and Rama 2015). 8Due to their bulky nature and discontinuities associated with their commissioning, hydropower projects can generate large macroeconomic fluctuations with disruptive effects. 9In its Bhutan Tax Rationalization technical assistance, the World Bank supported revisions to both general incentives (such as sales tax and customs duty exemptions for imports of plant and machinery) and sector-specific incentives (such as tax holidays). 10 As per the table of analytical underpinnings mapped to the prior actions in the Program Document (World Bank 2016b). 27 11By 2017â€“18, in the latest Global Competitiveness Report featuring Bhutan, its average score on these indicators had improved to 3.8 and its ranking had improved to 77th out of 137 economies on business sophistication (Schwab 2017). 12The scope of the task Improving Bhutan Investment Climate (P153221) was broader, but the work completed in time to inform the DPC series was limited to those areas covered by the Doing Business report, as stated in that taskâ€™s Completion Report (World Bank 2017). 13 This is similar to the International Monetary Fundâ€™s estimate of 33 percent in FY20â€“21. 14World Development Indicators, Domestic Credit to Private Sector (percentage of gross domestic product); https://data.worldbank.org/indicator/FS.AST.PRVT.GD.ZS?locations=BT. 15 However, see limitations on its implementation, discussed in the What Didnâ€™t Work section. 16The Implementation Completion and Results Report Review for this DPC noted that the Central Registry for Secured Transactions had played a role in increasing access to finance. However, this was based on assumptions regarding the share of micro, small, and medium enterprises in loans reported in the Central Registry for Secured Transactions because data on the size of borrowers was collected only beginning in 2018. 17As of 2017, the International Monetary Fund began working with the government on adjusting the framework for lending rates, advising on a Liquidity Forecasting and Management Framework that includes, among other things, a framework for guiding the lending rates of commercial banks (IMF 2019). However, the World Bankâ€™s 2020 Systematic Country Diagnostic refers to the â€œcontrolled interest rate regime, restricting competition, the supply of financial products and services, and financial innovationâ€ (World Bank 2020c, 26), and the International Monetary Fundâ€™s 2022 Article IV Consultation report does not mention any progress in this area. Therefore, there is no evidence that the interest rate regime has been addressed or improved. 18According to the World Development Indicators, in 2014, credit to the private sector in Bhutan as a percentage of gross domestic product was 45 percent. By the same measure, credit to the private sector has risen continuously since then, and in 2020, credit to the private sector in Bhutan as a percentage of gross domestic product touched 68.9 percent. However, this does not necessarily represent borrowing by firms that could not previously access financing, which was the aim of the DPC series. This could represent more borrowing by the large incumbent firms. Additional data that could help identify a link to the DPC series include, for instance, individuals in the Credit Information Bureau obtaining loans for business purposes; growth in the number of enterprises accessing finance; growth in loan volumes per enterprise; growth in loan volumes to micro, small, and medium companies; and so on. 19World Development Indicators, Foreign direct investment, net inflows (balance of payments, current US$); https://data.worldbank.org/indicator/BX.KLT.DINV.CD.WD?locations=BT 20Measured through the World Economic Forumâ€™s Executive Opinion Survey: â€œIn your country, how restrictive are rules and regulations on foreign direct investment? â€ (1 = extremely restrictive; 7 = not restrictive at all). 28 21 The prior action required submission to Parliament. 22The prior action required only approval by Cabinet, but implementation of the Licensing Policy required parliamentary approval. 23Bhutanâ€™s score on the strength of minority investor protection index fell from 5.0 (out of 10) in Doing Business 2015 to 4.7 (out of 10) in Doing Business 2016, without an explanation. In Doing Business 2017, the methodology changed, and Bhutan scored 6 (out of 10) on the extent of shareholder rights index. Its performance on this index then deteriorated to 4 (out of 10) in Doing Business 2018 and 2019, and 3 (out of 10) in Doing Business 2020. The deterioration in 2018 is described as follows: â€œBhutan strengthened minority investor protections by clarifying ownership and control structures but weakened minority investor protections by reducing shareholder rightsâ€ (Doing Business, https://archive.doingbusiness.org/en/reforms/overview/economy/bhutan). 24Other amendments to the Companies Act passed at the same time established the Office of the Registrar of Companies (Registrar) as an autonomous authority for the regulation of businesses and clarifying and expanding its functions. The Registrar is now responsible for registration of all businesses; issuing regulations appliable to businesses and capital markets; making provisions for commercial dispute resolution and establishing a dispute resolution body; implementing corporate social responsibility policies; and adopting a Corporate Governance Code, among other roles. (See description of the Registrarâ€™s role and its evolution here: https://www.cra.gov.bt/, section â€œAbout Us.â€) It is also responsible for corporate accounting and auditing standards and regulations on mergers and acquisitions. 29
P147839 | Pacific Resilience Program | East Asia and Pacific | Pacific Islands |  |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2024 | 2025 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099100924075029176/text/P147839-7833df28-f989-43de-9a19-ebe90658735c.txt | https://documents.worldbank.org/curated/en/099100924075029176/pdf/P147839-7833df28-f989-43de-9a19-ebe90658735c.pdf | The project included several useful lessons learned, which were adapted by IEG: If it is not ensured thata project, which is part of an SOP or a multiphase program approach, has its own PDO and Results Framework with PDO indicatorsreflecting the projects scope and outcomes, it may jeopardize the ability to measure the projects achievement.This project adopted the broader PREP PDO, and the original PDO included an outcome (financial protection) that theproject did not support. Also, the Results Framework did not include a PDO indicator to measure the second aspect of the PDO(resilient investments). Allowing resilience projects some flexibility in terms of design and implementation canensure their relevance. This projects original design was overly fragmented across too many activities, increasingthe risk of project activities overlapping with other donor-funded projects. However, the flexibility of the World Bank and SPCduring implementation allowed for an early restructuring to relocate funds to new opportunities such as LiDAR andORNSET. Providing DRM trainings in an environment with high staff turnover requires a careful consideration interms of delivery mode. This project was aware of the high staff turnover and as a result provided online training to alarge number of staff and costly face-to-face trainings to selected number of staff.
P147913 | Acre: Strengthening Public Policies DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/868321496689502491/text/ICRR-Disclosable-P147913-06-05-2017-1496689496280.txt | http://documents.worldbank.org/curated/en/868321496689502491/pdf/ICRR-Disclosable-P147913-06-05-2017-1496689496280.pdf | This review rephrases two of the lessons in the ICR and adds one more:1. A limited number of specificDPL areas will help achieve implementation for reforms. The Acre DPL focused on a few well-defined areas (results based planning,procurement, student testing and teacher incentives, and specialized services to women). This selectivity helps explain the timelyimplementation of reforms in three of the four areas.2. Similarly, close Bank supervision may have apositive bearing on reform implementation. The Bank dedicated 42 staff weeks to supervision (including the ICR). Such supervisionincluded important technical assistance inputs, for example, on procurement norms and regulations, where the Bank has considerableexperience.3. Levels of activity in public administration processes do not adequately measure publicadministration efficiency. The DPL focused on levels of activity (e.g. coverage of specialized services to women) that do notreflect the efficiency (cost effectiveness, value for money, or technical efficiency) with which those services are beingdischarged (e.g., the cost effectiveness of those services). By way of example, on public administration, the savings effectivelyobtained by moving from physical to electronic auctions or by aggregating small purchases into larger procurement contracts couldbetter measure the efficiency gains under the first objective than public resources management system or single source coverage. Oneducation, some measure of outcomes achieved (e.g., coverage and average standardized test scores) for a given level of resourceswould be appropriate.
P147921 | OMVS - TRANSMISSION EXPANSION PROJECT | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099121923083512943/text/P14792100f54930360a04907c970888f89b.txt | http://documents.worldbank.org/curated/en/099121923083512943/pdf/P14792100f54930360a04907c970888f89b.pdf | This review has drawn three lessons based on the information in the ICR.The construction of transboundaryelectricity transmission lines under one contract and hiring of a single owners engineer for the project can be critical inthe successful completion of the infrastructure investment. This project procured one contract for the construction of thehigh voltage transmission line between Kayes (Mali) and Tambacounda (Senegal). This was critical in preventing any constructiondelays that could have occurred if the construction of the transmission line had been contracted under two contracts, one for theMali portion and the other for the Senegal portion. Similarly, one owners engineer designing the project and supervising thecivil works was also critical in avoiding any implementation delays because coordination issues. In this project, SOGEM being thesingle project implementation entity facilitated the procurement and management of one contract and working with the ownersengineer. However, other similar transboundary electricity transmission projects implemented by two national utilities with onecontract for the construction of the transmission lines also proved to be a more efficient method compared to two separatecontracts, such as the Bolgatanga (Ghana)-Zagtouli (Burkina Faso) transmission line implemented by two national power utilitiesunder one contract with one owners engineer.Lack of procurement capacity of the PIU and insufficientpreparedness for the implementation of the safeguards policies can adversely affect the project implementation and decrease theprojects efficiency in achieving the project objectives. At appraisal, the project could not complete aResettlement Action Plan (RAP) because the exact route of the transmission line had not been decided. The RAP was to be preparedalong with the design of the transmission line. The PIU had insufficient procurement capacity, which resulted in significant delaysin the hiring of the owners engineer (responsible for the design of the transmission line) and the consultants for thepreparation of the RAP. It took about two years for the PIU to finalize the RAP after which the civil works could start on thetransmission line right-of-way where land acquisition was required. The Kayes-Tambacounda transmission line was fully commissionedon December 9, 2022, only a couple of weeks before project closing. Despite the project teams close supervision of theprocurement activities, the insufficient procurement capacity of the PIU continued through to project closing. As a result, someproject outputs could not be completed before project closing such as the commissioning of the two 20 MVA transformers on theKayes-Dagana transmission line.Weaknesses in the results framework can make it difficult to test the links in theresults chain and establish attribution between the projects intervention and the outcomes achieved. The projectwas designed on a simple and straightforward theory of change where the causal links from the project activities and outputs tooutcomes were direct and valid, and the achievement of the outcomes could be attributed to the project. However, the monitoring andevaluation (ME) design had significant shortcomings in adequately capturing the project outcomes and establishing attributionbetween the projects intervention and the outcomes achieved. The indicators measured the increase in the amount ofelectricity transmitted from Mali to Senegal and Mali at the system level. The results framework did not include indicators thatwould provide evidence for what has occurred as a result of the projects interventionattribution. The projectsresults framework was not sufficient to provide evidence of the achievement of the project outcomes that could be attributed to theproject.
P147924 | Guyana Secondary Education Improvement | Latin America and Caribbean | Guyana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062724185539053/text/P147924-cb3c45dc-3496-411b-aac8-680d4fe1f9a7.txt | https://documents.worldbank.org/curated/en/099062724185539053/pdf/P147924-cb3c45dc-3496-411b-aac8-680d4fe1f9a7.pdf | The ICR (pp. 28-30) offered several lessons and recommendations, including the following lessons restated by this ICRReview: Project implementation that is guided by a clearly defined theory of change and measurable PDO levelindicators and intermediate results indicators can support progress toward the achievement of objectives. Projectimplementation can be supported by the various stakeholders agreeing on project requirements prior to project effectiveness. Inthis project, delays in approving revisions to training modules and revisions to school designs led to delays in the initial stagesof implementation; and Close collaboration between the Bank and client countries on addressing challenges pertaining tocivil works can allow implementation challenges to be resolved expeditiously such that the implementation calendar is respected. Inthis project, construction delays led to significant cost overruns, which limited the amount of financing available.
P147979 | BR Amazonas DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/773831498054207949/text/ICRR-Disclosable-P147979-06-21-2017-1498054199807.txt | http://documents.worldbank.org/curated/en/773831498054207949/pdf/ICRR-Disclosable-P147979-06-21-2017-1498054199807.pdf | Among the useful lessons in the ICR, the following are highlighted: Program experience demonstrates theimportance of good collaboration between the Bank and other external partners. The partnership with the IDB, including theconstant sharing of information and the use of the same program implementation unit facilitated the implementation of a broadreform process. The Banks swift action to fill a financing gap was essential to advance reforms. Theusefulness of an ME system is augmented if targets are under the control of the implementing agency. In this case,some targets were set, the achievement of which depended on factors beyond the control of the stategovernment. In this and in other operations, the Bank is accumulating important knowledge on the securitysector. The risk assessment on the sector carried out for this operation was a crucial input to program design andimplementation. Given the likelihood of more frequent Bank interventions in this area, it would be useful to document citizensecurity experience in a systematic manner beyond that reported in ICRs or risk assessments. Electoral cycles andassociated campaigning periods can impact negatively on program results. Disruption may be reduced, or even avoidedaltogether (as in this case) by careful planning at the preparation stage, and through the inclusion of relevantmitigation measures.
P147984 | BR Bahia DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/585521498488000098/text/ICRR-Disclosable-P147984-06-26-2017-1498487994211.txt | http://documents.worldbank.org/curated/en/585521498488000098/pdf/ICRR-Disclosable-P147984-06-26-2017-1498487994211.pdf | Thisreview supports the ICR lessons on the importance of reform ownership for a strong implementation, the benefits of learning fromprevious operations, and the long-term nature of reforms aimed at changing social norms. On the ICR lesson regarding the role ofnew institutional arrangements, this review would note that, given the short time elapsed since the new arrangements wereestablished, it is too soon to draw a lesson on the role they played, especially on sustaining the progress of the reformprogram. This review offers one additional lesson: Programs supporting multi-step and multi sectorpolicies that are complex and require longer gestation period may be better supported by a programmatic rather than stand-aloneapproach. In these cases, a programmatic approach could allow for a better sequencing and pacing of the policy actions. It couldalso take better account of the authorities implementation capabilities and increase reforms implementation prospects, andultimately sustainability, by identifying appropriate prior actions and triggers between series and mobilizing more adequateresources
P148013 | JM Youth Employment in Digital and Animation Industries | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099051023105522638/text/P148013026021c0d80936b0439c1b9318a4.txt | http://documents.worldbank.org/curated/en/099051023105522638/pdf/P148013026021c0d80936b0439c1b9318a4.pdf | IEG draws the following lessons:Strong appraisal in innovative operations is key for success of the projects.This is always important, but most essential when the nature of the operation is highly complex and innovative for boththe country and for the WB.In this project, strong appraisal involves sound technical analysis, deep insight into thecountrys institutional framework and capacity in order to adequately assess risks,and to propose ME and procurementthat is adapted to the existing country capacity and to the projects needs. Highly innovativeactivities call for adapted intervention tools. In this project, apilot approach would have ring-fenced thepotential risks. Apilot operation with a more restricted scope (such as one sub-sector, a manageable group ofinstitutions, a specific geographical area, etc.), would have allowed the learning experience in a monitored way, on howinvestments and training can lead towards jobs thanks to a multi-partner participation.The followinglessons from the ICR is particularly relevant as well:When setting the foundations of an ecosystem for a newindustry it is critical to have an enabling policy framework (with identification of institutional roles andresponsibilities that best support the sectors growth needs) and a clear comprehension of the roles and dynamics of theprivate and public sectors. In this project a pre-existing platform of private and public institutions from the animation anddigital industries would have allowed for the private sector to build a pipeline, and for the Government to move forward theenabling environment actions that help (and do not interfere with) the private sector dynamics (setting policies, frameworks andinstitutional arrangements).Fiscal planning of governments can impact implementation, regardless of the existenceof a borrowers contribution.In this project there was no contribution from the borrower, but the fiscal spacestill needed to be planned for disbursements to happen. The constraints Jamaica faced in its fiscal planning hindered the pace ofproject implementation.
P148017 | MA-Health Sector Support | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | PforR | 2015 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099745012052236909/text/P14801704e55290110897c00c5bff62b556.txt | http://documents.worldbank.org/curated/en/099745012052236909/pdf/P14801704e55290110897c00c5bff62b556.pdf | These lessons are drawn from the ICR (with editing). When PforR funding is channeled as budget support to theMinistry of Finance, achievement of DLI targets is facilitated byprogram design and government budgetary mechanisms (orcoordination with development partners) thatensure that the Ministry of Health has sufficient budget, capacity, and incentiveto make every effort to do so. In this Program, initial shortfalls in MoH budget, buy-in, and motivation, coupledwithinadequate support and attention from the World Bank team, resulted in a slow start. Support forthedevelopment of a national health information system requiresattention to ensuring that data are available and used fordecision making. In this case, delays in availability of the data needed to measure and verify DLI targets delayed PforRdisbursement and inhibited implementation. The PforR instrument can be a useful motivator and vehicle for actions to improve sectorinformation systems. Timely and reliable data are needed for a PforR, but even more importantly, the instrument can encourage theirroutine use and dissemination to improve health system accountability, responsiveness, and outcomes. The ICR offered the example ofMoroccos National Initiative for Human Development (INDH), which routinely collects and uses data on the performance of itsearly childhood development programs, and noted that the ongoing PforR operation on early childhood development had contributed tostrengthening this culture in the INDH. Facilities can achieve significant improvements in service quality and develop aculture of quality enhancement through periodic self-evaluations using a detailed and thoughtful quality checklist, with audit andfeedback, announcement of results, and support for following through on action plans that address areas that need strengthening.The quality competition in Morocco used a comprehensive checklist that covered most aspects of quality of care (ICR, p. 24). Thiswas the first time that health service quality was measured in Morocco. Staff at participating facilities and peer reviewers wereasked for suggestions for improving the instrument for successive rounds. Most facilities that participated in two rounds of thecompetition achieved significant performance improvements between rounds, and best practices were shared across regions andfacilities. When falling birth rates, urbanization, or other causes of population migrationare changing populationnumbers in program areas,it is inadvisable to set service targets for maternal services as absolute numbers. Although it ismuch easier to collect data on absolute numbers, these data can easily miss changes in coverage rates that are a much bettermeasure of access, coverage, and utilization of services.
P148023 | National and Regional Roads Rehabilitation | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/931161596640224215/text/North-Macedonia-Road-Rehabilitation.txt | http://documents.worldbank.org/curated/en/931161596640224215/pdf/North-Macedonia-Road-Rehabilitation.pdf | The following two lessons in the ICR stood out as important and relevant to other projects in the road sector and are presentedhere with some editing.1. Output and performance-based contracting could be introduced successfully afteradequate implementation and internalization of the Road Asset Management System (RAMS); this would provide the road agencies withthe means to collect data needed to carry out such contracts. Under the project, the decision to introduceoutput-based contracting only after adequate implementation and internalization of RAMS by PESR allowed it to use a fullyfunctional RAMS to obtain accurate data on the road network to avoid any seriousdelays in procurement and the project failingto achieve its objectives due to a premature introduction of output-based contracting.2. The RAMS can help aroad agency make strategic decisions to improve financial sustainability of the road sector and fiscal management, under closecollaboration among key government agencies. The adoption of the RAMS concurrently happened with the time when thegovernment sought for innovative financing measures which might not be fully financially feasible. PESR used the RAMS torationalize the investments in road safety and climate resilience with close collaboration and exchange of data among keygovernment agencies. Strategic decision making in a sector level supported by the RAMS further benefits the whole economy, bycontributing to an improved fiscal management..
P148048 | Third Secondary and Local Roads Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099645212222267005/text/P1480480ea8e480e409ba10bd7da3bb1d04.txt | http://documents.worldbank.org/curated/en/099645212222267005/pdf/P1480480ea8e480e409ba10bd7da3bb1d04.pdf | This review has drawn three lessons based on the information in the ICR.Absence of a well-thought theory ofchange for technical assistance activities can prevent a proper assessment of the achievement of the expected outcomes; hence, theachievement of project objectives. The project financed technical assistance activities to improve the sustainability ofroad asset management. The project activities were partially defined. The expected outputs were some training and piloting of amicro-enterprise contract for road maintenance. The expected outcomes from project activities and outputs were not defined. Duringproject implementation, in accordance with the shift towards Output and Performance Results Based Contracts (OPRC) for roadmaintenance, micro-enterprise model was abandoned. Some activities could not be implemented because of COVID-19 restrictions ontravel. Overall, the theory of change was insufficient to fully assess how limited technical assistance activities, i.e., trainingsto the municipalities and the preparation of an OPRC in Guria regiona non-project regionwould lead to the achievementof the project objective to improve the sustainability of road asset management.Project-financed activities thatdo not support the achievement of project objectives can adversely affect projects efficiency. Under the thirdcomponent, the project financed road safety measures on non-project-rehabilitated roads. The results indicator included anindicator that captured the implementation or non-implementation of these activities. The outcomes from these activities were notproperly defined nor did the project objective formulation capture the effect of these activities on road safety measurement. Suchactivities can weaken the projects efficiency because the socio-economic benefits from their implementation are not includedin the economic analysis. A solution would be to make sure that the project formulation captures all the outcomes expected from theimplementation of project activities and the achievement of project outputs.Insufficient risk mitigation measurescan lead to sustained delays in project implementation. At appraisal, the risk stemming from potential land acquisitionand resettlement because of the Gurjaani bypass constructionthe only project activity that could lead to landacquisitionwas identified, and it was rated moderate. However, the mitigation measures proved to be insufficient. Because ofthe change in thedesign of the first two kilometers of the bypass, the addendum to the Resettlement Action Plancouldnot be prepared for more than two years. This was partly because of the uncertainty whether anaddendum would be neededwithout deciding on the new designand partly because of the time required to confirm that project-affected people would befairly compensated at the replacement value of their households.Together with the adverse impacts of COVID-19 pandemics, thisled to a project closing date extension by an additional 18 months.
P148052 | Mother and Child Health Services Strengthening Project | Western and Central Africa | Chad | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/859441623418721272/text/Chad-TD-Mother-Child-Health-Services-Strengt.txt | http://documents.worldbank.org/curated/en/859441623418721272/pdf/Chad-TD-Mother-Child-Health-Services-Strengt.pdf | The ICR (pp. 46-49) identified a few lessons and provided relevant recommendations, including the following lessons re-stated byIEG:Increasing financial autonomy of health facilities contributes to improvements in the quality ofservices. Under the project, and in addition to the use of service quality checklists, a large number of health facilitiesused PBF funds to mobilize additional human resources, provide bonuses that motivated staff to enhance performance, purchase drugsthat were out of-stock in the mainstream system, facilitate mobility for outreach services, and undertake infrastructurerepairs.Putting in place basic implementation arrangements to promote project readiness is equally importantto the development of substantive technical designs. Under the project, preparation revolved around technical design, andrelatively less on routine implementation arrangements and processes. Funds could not adequately flow until basic implementationarrangements were in place. A 4-year delay in recruiting an independent verification agency hindered PBF rollout and could havebeen curtailed with certain preparatory steps, such as drawing up and validating terms of reference, assessing of local andinternational markets for verificationservice providers, and engaging senior government decision-makers on the importance ofa timely process for approvals and contracting.
P148071 | Guizhou Tongren Rural Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099225005232217898/text/P14807108e194009a0a63700fca8afa874e.txt | http://documents.worldbank.org/curated/en/099225005232217898/pdf/P14807108e194009a0a63700fca8afa874e.pdf | The ICR (p. 18-19) provided several lessons learned, which were adapted by IEG: Adequate and targetedtraining in critical areas such as Bank procurement, financial management, and safeguards compliance is critical especially forfirst time clients during the early stage of project implementation. In this project, it was the first time for themunicipal and county governments in Tongren to implement a Bank project. While the Bank provided some training to government staffduring project preparation, lack of knowledge of Bank procurement and financial management policies resulted in implementationdelays. Identifying adequate levels of co-financing during project preparation is important for avoiding delaysin counterpart funding. In this project, a detailed fiscal analysis was conducted during project preparation which showedthat the debt levels for both counties were very high. In order to avoid a shortage of counterpart funding, the Bank team ensuredthat the counterpart funding requirements did not exceed one to two percent of the projected local governments fiscalrevenue. Designing a simple project with a straightforward Results Framework that allows for flexibility isbeneficial when the counterpart is new to Bank projects and has limited capacity. In this project, the objective andResults Framework were clear and simple, resulting in an achievable project objective reflecting the available funding resourcesand capacity.
P148083 | RS: Strengthening Fiscal and Water Resources Management DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2016 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/529361498502046574/text/ICRR-Disclosable-P148083-06-26-2017-1498502039955.txt | http://documents.worldbank.org/curated/en/529361498502046574/pdf/ICRR-Disclosable-P148083-06-26-2017-1498502039955.pdf | The following two lessons are taken from the ICR with some adaptation of language: Delivering developmentpolicy operations close to elections involves high risk. In this case, delaying the operation until after the electioncould have provided the conditions for a more ambitious reform program addressing the short and medium-term issues moreforcefully. National legislation may prevent or constrain a state government from undertaking key structuralreforms. In this case, there several examples of this. Where this occurs, the goals of the DPO are more likelyto beachieved if parallel efforts are made to address the federal level constraints.IEG adds a thirdlesson: A serious disconnect, as in this case, between the reform measures supported by the operation andthe program development objectives, is likely to undermine the outcome of the operation and reduce its credibility as a catalystfor change. If only limited reforms can, for political or other reasons, realistically be attained, and it is not possibleto change the timing of the operation, then the objectives may be adjusted to reflect these realities.
P148099 | Governance and Competitiveness Programmatic DPO | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/411441558707216780/text/Kyrgyz-Republic-Governance-and-Competitiveness-DPO.txt | http://documents.worldbank.org/curated/en/411441558707216780/pdf/Kyrgyz-Republic-Governance-and-Competitiveness-DPO.pdf | The ICR (pp. 35-36) presented several insightful and valuable lessons, including:When planningpolitically sensitive reforms, itis challenging to distinguish between genuine commitment by relevant authorities and merelip service. Realistic, in-depth political economy analysis can help identify the key players and agencieslikely topromote or resistreforms as well as potentially effective arguments and incentives to bring them on board. In thiscase, there was no clear, empowered champion for the overall reform process, leaving missed opportunities for forward movement inkey sectors.In a weak, uncertain reform context, success is likely to follow concentration of effort on ahighly parsimonious set of prior actions and follow-up triggers. In this case, priority was spread over too many areas,leading to coordination challenges and lack of accountability in a weak-capacity environment.Front-loadingmore politically sensitive reforms may help reduce stagnation and delay, flag areas where prompt intervention is required,andmitigate risks of cancelling subsequent operations. In this case, the more difficult reforms were framed in terms ofsubmissions or instructions to be issued, putting off more specific implementation-oriented actions and allowing resistance to setin.
P148110 | Mongolia Education Quality Reform Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061824183033949/text/P148110-3ee9b417-1d5c-453e-aa5b-cb4ec08f5048.txt | https://documents.worldbank.org/curated/en/099061824183033949/pdf/P148110-3ee9b417-1d5c-453e-aa5b-cb4ec08f5048.pdf | These lessons are drawn from the ICR (with editing).Cash transfers to families can provide important welfarebenefits for children in mitigation of income shocks.The cash support provided to families through theChildrens Welfare Fund had a positive impact. Parents and community representatives emphasized that this financial supportplayed an important role in meeting the basic needs of children, such as food, health, school supplies, and electroniccommunication needed to continue schooling remotely.Teachers and students need adequate computers and computingskills to enable productive use of technology for education. During the COVID-related school closures, teachers andstudents had to rely fully on e-learning and teaching. The experience demonstrated the potential of information technology tosupport childrens self-directed learning and teacher training, using on-line interactive lessons and other resources, andself-paced learning options. However, some teachers and families did not have computers with high enough performance quality, oradequate connectivity, or computer skills.Online teaching and learning resources need to be developed and storedin a well-structured and user-friendly way. Teachers frequently saved the original versions of interactive lessons theydeveloped on their personal computers or Facebook groups, becauseschools lacked a centralized system for securely storingsuch materials. This increased the risk of losing workand reduced opportunities for wide sharing. Also, security ofelectronic data and resources created by teachers need to be managed and enhanced at the schoollevel.A local support team with a specific focus worked well as a way of supporting teachers tolearn, adopt, and improve new teaching methodologies. Local early-grade mathematics assessmentsupport teamsthat monitored and consulted with teachers to provide constructive feedback proved effective. The teams made regular visits toschools, during which they observed teaching practices and provided immediate consultation, advice, and support.
P148114 | Guinea Agricultural Support Project | Western and Central Africa | Guinea | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2019 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/977311595883472101/text/Guinea-Guinea-National-Agricultural.txt | http://documents.worldbank.org/curated/en/977311595883472101/pdf/Guinea-Guinea-National-Agricultural.pdf | The ICR provided several lessons. The most important one follows with some modification of language:In thecontext of low institutional capacity environments, a stand-alone capacity building project can be very important to support thegovernment to implement sector-wide programs and reforms. The project supported the improvement of agriculture sectorknowledge and increase the government capacity to plan and mobilize funding in the sector. The project also served as the basis forincreased investments in the sector and helped structure and gradually ramp up the World Banks engagement in the agriculturesector in Guinea.The ICR Review formulated the following lesson:For institutional capacity buildingprojects, a relevant Results Framework with clear definition of institutional capacity building outcomes and relevant outcome levelindicators to measure the objective and linking project activities (training events and studies) to expected outcomes in arealistic manner are key to adequately monitor the results of a project. The projects theory of change should bevery clear from the beginning and the behavior change that can be achieved by the project activities need to be specified andappropriate and realistic indicators to measure these results should be designed. This was not the case under the project. Theprojects outcome indicators were not relevant to measure the PDO, as they were beyond the control and influence of theproject. The revised indicators did not resolve this issue as well. Thus, the project could not display the projects resultsand achievements.
P148127 | GUINEA - Pooled-Fund for Basic Education | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2016 | 2020 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/478211592408231309/text/Guinea-GPE-Guinea.txt | http://documents.worldbank.org/curated/en/478211592408231309/pdf/Guinea-GPE-Guinea.pdf | The ICR (pp. 34-36) included several insightful lessons, including:Awareness raising andcapacity building of local communities, including school management committee members, can be key features in promoting inclusiveand responsive institutions for service delivery. The introduction of awareness campaigns as well as basic managementtraining gave communities a stronger voice in monitoring and supporting school activities.Goodinstitutional capacity can be key to smooth implementation, results, and sustainability of interventions. Improvedproject capacity was key to sustainable project interventions. However, going forward will require additional support to build onthe projects achievements, inter alia, decentralized management and strong systems for planning, monitoring andevaluation.Pooled funds and a multi-sectoral approach provide a workable platform to tackle acrisis like Ebola. Under the project, members of the donor community combined their education sector resources in apooled fund to support national efforts to get children back into school after the crisis. The pooled fund ensured donorcooperation and a more rapid achievement of project goals than might otherwise have been the case, in particular in providingcoordinated and timely support for hygiene improvements in schools in the short term (hand-washing) and the longer term (latrinesand water points).
P148129 | China: Tianjin Urban Transport Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099111323192529075/text/P1481290e2871a0530a8160ed50bf0aa989.txt | http://documents.worldbank.org/curated/en/099111323192529075/pdf/P1481290e2871a0530a8160ed50bf0aa989.pdf | The ICR included four lessons. The following three are emphasized with some adaptation oflanguage:1.Shifting the dominant urban planning paradigm from car-centric to green mobility-prioritizingdevelopment requires buy-in from stakeholders and enough time to materialize. There was a lot of resistance from projectstakeholders to changing the urban planning and design status quo, which was the main factor leading to the delays experienced inthe first few years of the project. Five years is too short a project time frame to create innovative streetscape designs for largesections of the core urban area, get consensus on these designs and permits to construct from the relevantstakeholders, getthe works built and handed over, and establish new policies and procedures for operations and maintenance. Projects of thistype should also have a powerful steering committee, including heads of all relevant organizations, led by the MayorsOffice. The steering committee should meet frequently throughout the whole project lifecycle to adequately address anyimplementation issues.2. To ensure the success of active mobility infrastructure improvements, strict parkingmanagement measures need to be simultaneously enforced. Without strict parking management, motor vehicle parking willinevitably increasingly encroach on active mobility infrastructure and reduce the usage rates and safety of this infrastructure.World Bank should include motor vehicle parking management reform, led by the city mayor or head of the municipal transportdepartment, as a standard feature in projects seeking to increase walking and biking.3.Projects seeking tomake cities more friendly for active mobility should take a holistic, sociotechnical systems thinking-based approach rather thanfocusing overwhelmingly on infrastructure provision. Quality infrastructure is a necessary but insufficient preconditionto a city being a place where most people regularly engage in active mobility. While the activities supported underthisproject significantly improved the friendliness of the city infrastructure,the project only did analytical workwith no direct impact on the other indicators of friendliness in terms of the extent to which city management,services, andcultureare friendly towards active mobility. TheWorld Bank should take a holistic approach to future projectsglobally.
P148238 | P4: Pacific Regional ICT Regulatory Development Project | East Asia and Pacific | Pacific Islands |  |  | Digital | Digital Development | IDA | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/498371618867357440/text/Pacific-Islands-Pacific-Reg-ICT-Regulatory-Dev-Project.txt | http://documents.worldbank.org/curated/en/498371618867357440/pdf/Pacific-Islands-Pacific-Reg-ICT-Regulatory-Dev-Project.pdf | The ICR draws the following lessons from the experience of implementing this project, which are presented below with someadaptation of language.1. Technical leadershipiscritical for regional activities. Thisproject demonstrated the importance of regional championship and ownership of theagenda. A lack of technical leadership ontheagenda limits the ability of the institution to coordinate the necessary expertise and inputs to effectively implementprojects in that field.While the University of South Pacific was given the mandate for ICT development in this project, itwas not aligned with its core function as a tertiary education institution and lacked the necessary technical capacity to execute aBank-financed project.2. Multi-stakeholder projects requireclearly defined roles and responsibilities forstakeholder coordination.This entails a greater level of engagement, consultation, and stakeholder coordinationduring project preparation. Documents such as the project operation manual and implementation agreements between participatingstakeholders need to be prepared early on and stakeholders sensitized ahead of project effectiveness to reduce stakeholdercoordination risk and to avoid potential misunderstandings that may lead to downstream challenges.3. Procurementcapacity building should be complemented with technical assistance, if need be throughsupportfirms.While procurement is central to any projects implementation, the experience from this projecthighlights the criticality of the processes around the execution of procurement itself. This includes many areas that require muchmore subject matter expertise than procurement process familiarity, such as designing terms of reference, conducting marketanalysis, carrying out technical evaluation of proposals/bids, and contract management, among others. The lesson from this projectis that in technical assistance projects such as those pertaining to ICT, the availability of adequate technical capacitybecomesmore critical. In this project, the University of South Pacific did not clearly have the capacity to addressprocurement issues.4. Developing regional approaches requires long-term engagement.Regionalapproaches to economic development has advantages, particularly for small-states. The regional IDA Grant was potentially the onlyBank financing instrument to continue this long-term engagement. The lesson from this project is that the Banks existingfinancial instruments may not be best suited to respond to such needs, particularly in low-capacity regions where long-termengagement require sustained technical assistance, technical and implementation capacity building, and grant financing to continueoperations till long-term sustainability options are realized.
P148259 | HT Strengthening Hydro-Met Services | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2015 | 2021 | 2021 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/809851624670498455/text/Haiti-HT-Strengthening-Hydro-Met-Services.txt | http://documents.worldbank.org/curated/en/809851624670498455/pdf/Haiti-HT-Strengthening-Hydro-Met-Services.pdf | The ICR offered sixlessonsto be considered by teams in preparing future similar operations (ICR, paragraphs 64-69).Three of these, slightly edited, are noted below: A small size stand-alone grant may notattractpolitical commitment needed to achieve development outcome.This project was meagercompared to themagnitude of the problem being addressed. The targets were overly optimistic considering the capacity needs that it was designed tosimultaneously strengthen. The project experience shows that close monitoring and strong World Bank technical support to the PIUwere needed to compensate for the low technical and contract management capacity. FCV countriesmay be best served by aseparate implementation unit that could then be woven into strengthened institutions to sustainoutcome. This project aimed to strengthen a weak institution in an effort to gain ownership withproject designsupporting the effort with capacity support. The PIU was belatedly activated and constant support provided but the measure was notundertaken in time to help address implementation delays. Considering the volatility of conditions in FCVcountries,consistency in implementation may be offered by a PIU separated from an implementing institution that may undergoleadership changes or nascent ones that would still be establishing afoothold and negotiating support for itsremit. The sustainability of a centralized hydromet entity such as UHM in a country prone toextreme meteorological eventscaused by climate change requires long-term commitmentfrom all partners. Anefficient hydro-met system is an essential building block of a disaster risk management strategy. This requires time andresources.Anchoring an effective hydromet system in the appropriate institution requires careful assessment of needs andavailable resources. For example, the newly created UHM under MARNDR requires long-term strengthening and support. In thisproject,UHMlacked the necessary government buy-in to support its function as the countrys focal point forhydro-met services. Itsfinancial sustainability depended onbudgetary appropriations. Grants from development partnerssupplemented this. Introducinga fee-based hydromet services would help addressits financial needs. By aiming to sustaina viable UHM providesthe agency with the incentives to deliver accurateearly warnings against impending disasters andfosters resilience in a fragile conflict, and violence (FCV) afflicted country highly vulnerable to natural hazards.
P148291 | HIGHER EDUCATION PROJECT | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099012324141534914/text/P14829114a958f01f1be2919cbf336902f2.txt | http://documents.worldbank.org/curated/en/099012324141534914/pdf/P14829114a958f01f1be2919cbf336902f2.pdf | Lessons drawn from the ICR (pages 31-32), adapted by IEG: Major sector reforms, while unlikely to be fullycompleted within one project cycle, can still be significantly moved forward through project support. In the case of thisproject, quality assurance and higher education financing reforms required a lengthy and wide consultation process among keystakeholders to achieve consensus. However, building onprior analytic work and project preparation grant support, theproject was still able to contribute to sector reforms through the production of guidelines, assessments, and recommendations,which can be implemented and scaled up with follow up support. Deferring the measurement of project impact to the finalphase of the project period can lead to delays in recognizing that a project is off-track to achieve targets; therefore, otherintermediate measurements are necessary. In the case of this project, measuring improved quality of higher education couldonly realistically take place at the end of the project period given the need to implement all project activities before seeingimprovements. Therefore, the projects ME design included percentage of grants that are peer reviewed for qualityand relevance, and percentage of HEIs conducting graduate tracer studies. This ensured that other measurements of intendedoutcomes could be tracked throughout project implementation.
P148428 | Somalia Recurrent Cost & Reform Financing Facility | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2015 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/898101467317207623/text/ICRR-Disclosable-P148428-06-30-2016-1467319929701.txt | http://documents.worldbank.org/curated/en/898101467317207623/pdf/ICRR-Disclosable-P148428-06-30-2016-1467319929701.pdf | This review concurs with thelessons identified in the ICR, especially those related to (i) the importance ofstrengthening technical capacity of post-conflict clients,with a view ofusing country systems as soon as possible, (ii)the Banks innovation by using a simplified supervisoryMA, and (iii) the sustained focus on core governance andanti-corruptionreforms. IEG identified twoadditional lessons asfollows:(i) In special circumstances, temporary Banks support through the payment of salariesfor civil servants might be what is needed to prime the pump of reengagement with apost-conflict client.The State of Somalia had beenexceptionally weakened following decades in failed state status, andstrifeamong communities and regions. The economy was decimated and fiscal revenue vanished, and the country did not have the neededresources to run a government. Joiningeffortswith the international community, the Bankused grant resources topaycivil servants salaries, and this contributed substantially to stabilizing the country, which ismakingprogresstoward a stable situation.(ii)To operate in unsecurepost-conflict environments, the Bank has to be innovativethrough establishing well-identifiedpartnerships.This review concurs with thelessons identified in the ICR, especially those related to (i) theimportance of strengthening technical capacity of post-conflict clients,with a view ofusing country systems as soon aspossible, (ii) the Banks innovation by using a simplified supervisoryMA, and (iii) the sustained focus on coregovernance and anti-corruptionreforms.
P148499 | Saweto Dedicated Grant Mechanism in Peru | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2021 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099400111142227753/text/P1484990e9cd940b10b4b70604b88ccd584.txt | http://documents.worldbank.org/curated/en/099400111142227753/pdf/P1484990e9cd940b10b4b70604b88ccd584.pdf | The ICR (paras 98-101) presented four lessons. Three of them are included below with rephrasing because these may benefit futureprojects related to sustainable forest management through engaging indigenous people and nativecommunities.Working through indigenous peoples organizations is an effective approach to engage indigenouspeople and native communities to improve land titling and conduct other sustainable forest management activities. Adequatetechnical and financial support for institutional capacity strengthening is essential to engage them in the climate dialogue anddecision-making. A more structured, permanent governance framework for the indigenous peoples organizations to participatein the Forest Investment Plan, Reducing Emissions from Deforestation and Forest Degradation, and other relevant initiatives isrecommended by the National SteeringCommittee. Physical visits and training sessions specifically targeted for women would benecessary to increase women-led projects and their participation in decision making processes. Alliances between indigenousenterprises and the Centers for Productive Innovation and Technology Transfer as well as with other related public entities forcompetitiveness incubation were key for the generation of products and services with an added value and for the targeting of newand larger markets. Such alliances could be useful for boosting additional women-led projects.Missing adigitalized system to monitor progress of project implementation in terms of technical, financial, and environmental and socialaspects in an agency responsible for project implementation can negatively affect effective project implementation and MEquality. Securing budgets for developing a new system or strengthening an existing system should be strategically plannedin the local context during preparation, in order to operationalize the system; but this was not done by the project.Triangulation of reported data by the World Bank through a technical audit could have also been effective to identify datadiscrepancies in earlier stages to remedy the situation(ICR, para 94). The use of a comprehensive, automated, and georeferencedinformation system is required for sustainable community forest management projects to track community requests, approvalprocesses, physical and financial progress, efficiency and to adequately track deforestation. Considering limited internetconnection in the field, the system should be compatible with an offline application to collect the data in digital format and thentransfer it the online system.Strong political commitments and resources of government agencies at the local levelresponsible for approving land titles are essential to expedite titling processes. Although the project promotedagreements with regional governments by supporting them to acquire equipment and hire consultants, these measures were not enoughtofully expedite the titling processes because the Regional Agricultural Office had a limited number of specialists to review theconsultants products to formally approve titling documentations. The project identified the average time and cost of eachstage in the recognition and land titling processes per region, which can be utilized to ensure commitments from public budgets tosupply the necessary financial and human resources.In addition, IEG formulated the following lesson:Theprojects two-pronged approach, which combined land titling and productive investments to generate income, is an effective wayto support forest communities to carry out sustainable forest management practices. The project provided technical andfinancial assistance to native communities to strengthen governance and capacities to increase land titling activities andcommunity-based productive initiatives, that was a combination of interventions that directly contributed to their efforts ofimproving sustainable forest management practices (ICR, para 53). These activities were envisioned to contribute to long termincome generation, which would incentivize communities to protect their forests. However, to ensure a success of this approach, itis important to clearly define sustainable forest management, to strengthen local capacity of public institutions and communities,and to establish a good ME system.
P148523 | Hubei Jingzhou Historic Town Conservation Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099102023130528240/text/P14852307fa87508809fdc00b1aa1814937.txt | http://documents.worldbank.org/curated/en/099102023130528240/pdf/P14852307fa87508809fdc00b1aa1814937.pdf | The ICR (p. 29) included lessons learned which were adapted by IEG: Integrating cultural heritageconservation with tourism development and urban regeneration activities can broaden the projects impact. In thisproject, activities to improve the environment of heritage sites and the citys services for visiting tourists benefittedresidents regarding their living environment. Infrastructure projects in China might benefit from considering thepotential for overpricing when following government price standards. In this project, the borrower followed governmentprice standards to estimate the cost of planned civil works, which were approximately 30 to 40 percent higher than thecontracts actual costs. This resulted in the project being restructured and introducing additional activities in line withthe projects objective. Ensuring the approval of cultural conservation plans during project preparationcan avoid delays during implementation. In this project, even though most of the sites conservation plans hadalready been prepared and were approved when the project was appraised, their final approval took much longer than expected andresulted in implementation delays.
P148527 | Urumqi Urban Transport Project II | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099600001192320526/text/P1485270aa27e00950bd16021d939564724.txt | http://documents.worldbank.org/curated/en/099600001192320526/pdf/P1485270aa27e00950bd16021d939564724.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A robust technical analysis can help in designing an effective BRT system that are tailored to theneeds of the country. This project adopted a closed BRT system with segregated, median bus lanes and stations, pedestriancrossings with footbridges and underpasses, BRT priority signals and overtaking lanes at locations where space was available tomitigate queueing at BRT stations. These designs were determined based on detailed surveys andtraffic modelling.2. Urban transport interventions can benefit from engaging with citizens.This project entailed extensive public participation and consultation both during preparation and during implementation. The publictransport surveys helped in identifying the key issues faced by travelers.3. Effective inter-agency collaborationand coordination help in ensuring success of an urban transport project. Urban transport project requires closecollaboration between multiple agencies in planning, construction, public transport regulations and operation and trafficmanagement. This project was set up by a Project Leading Group (PLG) led by the Executive Vice Mayor to coordinate the localagencies during preparation and implementation. PLGs role was particularly important when the project faced challenges due tothe evolving circumstances such as new metro opening and the outbreak of the COVID - 19 pandemic.
P148560 | Energy Sector Development Project | East Asia and Pacific | Micronesia, Federated States of | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2014 | 2020 | 2020 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/447251593461280352/text/Micronesia-Federated-States-of-ESDP.txt | http://documents.worldbank.org/curated/en/447251593461280352/pdf/Micronesia-Federated-States-of-ESDP.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage:1. A targeted holistic package of support can be beneficial in small island contexts.Theconcept note of this project identified issues in the power sector in FSM, which seemed to be common to small islandstates such ashigh cost of imported fuel, tariffs not reflective of costs, and inadequate technical and managerial capacity.The lesson is that providing support for purchase of critical equipment linked to improving efficiency of electric supply andcapacity building for key institutions, can be useful in small island states.2. A centralized implementation unitfor addressing fiduciary and safeguards issues,can be useful in countries with limited capacityfor implementingBank-financed projects. A centralizedunit set up during implementation ofthis projectaided in workingeffectively to address such issues.3. Demand-side issues need to be included for an effective sustainableenergy strategy. The activities in this project addressed supply side and institutional strengthening issues, given theweak implementation capacity. Asthe first energy sector project in FSM, a lesson is that future projects should also considerincorporating demand-side issues in the energy sector.
P148604 | Accelerating Universal Access to Early and Effective Tuberculosis Care | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2014 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/835431548254354951/text/India-Accelerating-Universal-Access-to-TB-Care.txt | http://documents.worldbank.org/curated/en/835431548254354951/pdf/India-Accelerating-Universal-Access-to-TB-Care.pdf | The ICR (pp. 33-34) offered several lessons and recommendations, including the following lessons restated byIEG:Joint monitoring missions with key stakeholders provide an opportunity for the government anddevelopment partners to identify implementation challenges and corrective directions in a harmonized manner. Thejoint monitoring missions provided a platform for partners and the RNTCP to be further aligned with the National Strategic Plan,and the recommendations of the joint missions providedthe basis forrestructuring theproject.Focusing on results through the use of disbursement-linked indicators provides an incentiveto augment implementation performance. The project benefited from a clear set of targets that triggereddisbursements.Verification of results can be effectively performed by UN agencies presenceon the ground. Rather than facing delays in identifying and contracting a third-party agency, WHO stepped in tofulfil the verification role at no extra cost to the project, while concurrently bringing added credibility and technical depth tothe monitoring process.
P148616 | Agro-Processing, Productivity Enhancement and Livelihood Improvement Support Project | Western and Central Africa | Nigeria | Blend | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2017 | 2024 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062024203542265/text/P148616-1aa044dd-4867-47ea-b032-c37e9d7a797d.txt | https://documents.worldbank.org/curated/en/099062024203542265/pdf/P148616-1aa044dd-4867-47ea-b032-c37e9d7a797d.pdf | The ICR presented three lessons. Two that are likely to be widely applicable are presented below with someediting.Allocating resources through a competitive process among several units, such as states,implementing a project could expedite disbursements by channeling funds where they are better utilized. TheAgro-processing, Productivity Enhancement and Livelihood Support project allocated an initial sum to each of the participatingstates; additional allocation to them was contingent on timely and efficient implementation of project activities. This approachfostered a sense of ownership and accountability. The state that implemented most effectively received allocations twice as largeas the least effective state. There was full disbursement before the scheduled project closure, without any pending workor problems with fiduciary and safeguard issues.Early and continued engagement with the State Governments on WorldBank policies and regulations can help reduce delays. Some of the states that received funds from the project as a loanfelt that they should be allowed to implement the project as they found appropriate; they wanted to implement activities that wouldhave been unallowable, resulting in considerable delays. Communicating at the project appraisal itself that regardless of whetherthe funds go to them as grants or loans, bank policies regarding fiduciary responsibilities and safeguards apply could have avoidedthe delays.
P148642 | MA-Solid Waste Sector DPL4 | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2015 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/700731500904650697/text/ICRR-Disclosable-P148642-07-24-2017-1500904641929.txt | http://documents.worldbank.org/curated/en/700731500904650697/pdf/ICRR-Disclosable-P148642-07-24-2017-1500904641929.pdf | The Lessons are derived from the ICR document with some modification of language.1 . Sector reform takes time:reforms should start simple and gradually get more complex. There is a greater chance to succeed with more complex reformsif tangible results from simpler reforms are present first.2 . Focusing on improving systems rather thanjust training is more effective in achieving long-term results. Capacity building and training should bedesigned to improve the performance of a system and not only of individual skills.3 . WorldBank-supported reforms should be fully aligned with Government priorities for greater success.4 . In theright context, the use of DPL in sector reforms can be a very effective instrument. The DPL instrument can offer analysis,a reform planning framework, implementation support, and convening power by the World Bank while maintaining full governmentleadership and ownership of the reforms themselves.5 . Providing Local Governments with responsibility over theentire Municipal Solid Waste chain at the local level is a key lesson for success. Responsibilities for collection anddisposal of solid waste are often fragmented across several administrative boundaries.The experiencesuggeststhatgreater success can be achievedwhen responsibility of the entire system at the local level (collection, streetcleaning, disposal, recycling, etc.) is concentrated under one entity.
P148647 | Mekong Integrated Water Resources Management Project- Phase III | East Asia and Pacific | Cambodia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060823130526162/text/P1486470ce89840cb0b48d0f172ac82a853.txt | http://documents.worldbank.org/curated/en/099060823130526162/pdf/P1486470ce89840cb0b48d0f172ac82a853.pdf | (Reference ICR paras. 86 to 90).The ICR (paras. 86 to 90) lists a number of lessons derivedfrom the Projects experience. Based thereon, IEG derives the following lessons relevant for similar projects carried out incomparable environments.Early and adequate attention to institutional strengthening,capacity building, and aclear demarcation of responsibilities betweenthe key agencies is essential for effective water resources management(WRM). Experience under the Project showed thatthe lack of clarity regardingimplementation responsibilitiesamong MOWRAMs line agencies affected the first few years of implementation due to technical capacity gaps resulting from thelack of engagement from some agencies. Weaknesses in technical capacity and resources for WRM at a provincial level and the need toimprove cross-agency collaboration between the key agencies were evident in the early years of implementation. More thoroughassessments at the appraisal or early stages of implementation would have helped in early identification of these weaknesses andhelped prevent delays in implementation. (ICR para. 86).Several synchronized country projects interlinked by aregional component can contribute to advancing transboundary dialogue, but, for any individual country andproject, theproject development objectives need to be realistically formulated to limit objectives to those that are withinthe purview of the country concerned.The Project was designed to be implemented in parallel with other projects inthe Mekong IWRM Program. By doing so, the Project contributed to building the foundation of important aspects of IWRM in thecountry to better equip it for transboundary dialogue and collaboration. However, transboundary actions, by definition,requirethe implementation to be carried out by both the countries involved. In the case of the Project, the PDOindicatorconcerning transboundary exchange of WRM data and analysis with Vietnam could only be partially achieved becauseestablishment of the implementation arrangements needed concurrence andexecution by both countries which was beyond thepurview of Cambodia alone.Strong collaboration and leadership involving stakeholders at several levels cansignificantly enhance the achievement of objectives and the mitigation of impacts from external shocks. This wasparticularly evident under Component 1 (Fisheries Management) of the Project. A collaborative approach was proposed during projectdesign. Communities were engaged and consulted in all decision-making processes. A combination of bottom-up and top-down processeswas used in defining and implementing activities to be financed under the Project. Transparent beneficiary selection methodsweredeveloped, and small infrastructure needs prioritized, based on local development plans. The commitment from thestakeholders involved was demonstrated during the period of the COVID pandemic where engagement and support remainedstrong.(ICR para. 88).In-built sustainability measures developed during project design andimplementation are key for ensuring operational effectiveness of the project investments after project completion. Toensure sustainability of the project benefits, the clients need to establish operational structures and allocate financialresources to enable sustainable operations after the completion of the Project. These aspects need to be built in during theproject design. This was particularly evident from the experience under the hatchery subproject.
P148809 | NI Caribbean Coast Food Security Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/409991616512210514/text/Nicaragua-NI-Caribbean-Coast-Food-Security-Project.txt | http://documents.worldbank.org/curated/en/409991616512210514/pdf/Nicaragua-NI-Caribbean-Coast-Food-Security-Project.pdf | The ICR presents 6lessons (ICR, paras. 80-85). The aspects of the lessons that have broader application thanthis project have been summarized below. IEG suggestsone additional lesson.(1) Flexible andCustomized Targeted Interventions: The ICR referred to the importance of following flexible implementationarrangements for a project targeting a culturally diverse population. The ICR adds that most of the projects targetingand implementation instruments had been developed and agreed prior toproject launching. The lesson is that therearebenefits in having clear and agreedselection criteria for community and beneficiary participation prior to theprojects effectiveness, which enabled the implementation agency/MEFCCA and its 3 regional delegations to carry out anefficientand successful project, by targeting the expected benefits to the targeted beneficiaries.Accordingly, anadditional aspect of this lesson involves customizing the projects interventions to the priority needs of the targetedcommunities and direct beneficiaries (e.g., contributing to the enhancement of nutritional security of children in poor communitiesof the Caribbean Coast region).(2) Efficiency Benefits of Sound and Strengthened Implementation Roles andArrangements: The ICR correctly highlights the importance of clear institutional roles and arrangements, includingME system, for implementing the projects integrated approach, especially through MEFCCAs three regionaloffices/delegations. Moreover,these arrangements enabled a strengthened regional multi-agency participation and coordination,including customizing the design, implementation, sustainability and scaling up IDPs (including cost sharing arrangements),according to the different types of beneficiaries and their priority needs and capacities. The specific lesson is that thesearrangements, coupled with institutioncapacity building of key entities and implementation processes, contributed to bothfiscal and implementation efficiencies in generating, scaling up and sustaining the projectresults.(3) Effective Collaboration is a Key to Project Success: The ICR highlightedsomeessential conditions and elements for successful projects. This project was successful because of the strongcommitment at all levels of responsibility from: (a) committed and decisive Government leadership, at both central and regionallevels, which was further enabled by formal cooperative agreements between MEFCCA and relevant public service entities (ICR, Annex7); (b) effective collaborationwith and participation of the Autonomous Regional Authorities andindigenous communal governments, consistent with Government legislation;(c) sound ME system; and (d) the continuity ofthe Bank and Government technical teams. The lesson is that collaboration between various implementing institutions throughtransparent communication, clear allocation of responsibilities and participation, consistent with Government legislation of roles,formal cooperation agreements amongst key entities and a functional ME system can result in successful project outcomes.(4) Explicit and Measurable Integrated Strategy to Enhanced and Sustained Food and Nutrition Security:The ICR emphasized the projects integrated strategy and supporting interventions which promoted enhanced foodand nutrition security, as evidenced partially by various complementary outcome measures outlined in Annexes 1 and 6 of the ICR.The main lesson is that a focus on food productivity increases and qualitative indicators are not sufficient to achieve and sustainrobust and measurable improvements in food and nutrition security for the target population (which included landless, laborers,urban poor);IEG suggests oneadditional lessonwhich may have application to similar otherprojects.It is vital for the projects designto accurately and rigorously define key concepts embeddedin project objectives. The projects objective was to enhance food and nutritional security.The ICR defined food security in a multitude of ways. Without providing an explicit rationale, it was assumed thatinterventions which would increase food productivity/production would lead to increased food and nutritional security of targetedhouseholds. In practice, increased and diversified food production does not automatically lead to improved access tofood and nutrition by all persons in the target population. Given the structural poverty in areas like the Caribbean Coast,the project ICR did not providerelevant and robust evidence on the extent to which food and nutrition security for the targetgroup (including landless and laborers) was achieved, and yet the ICR claimed (without evidence) that food security had beenfully achieved because food production and its diversification had increased. The lesson is that, in the absenceof a cogent and precise definition of a projects objective, and the indicators with which results are measured,it isnot possible to conclude the extent to which the objective is achieved.
P148839 | Niger Investment Climate Support | Western and Central Africa | Niger | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2021 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099810010112241954/text/P148839076cdc20a908f1b0d9a1275b3c94.txt | http://documents.worldbank.org/curated/en/099810010112241954/pdf/P148839076cdc20a908f1b0d9a1275b3c94.pdf | The ICR contains the following lessons which IEG presents with some modification:Low quality preliminaryanalytical studies can decrease project implementation efficiency. In this project, low quality of the preliminary/technical studies for small-scale marketplace infrastructures and roads for the Zinder trade corridor delayed the construction.The cost of technical studies and works for the market infrastructure under Component 2 were higher than originally estimated. Toovercome these issues, the project team took proactive remedial measures that increased administrative and technical costs of theproject. This resulted in a low administrative and operational efficiency.When introducing a matching grantsprogram (or a financial support program of same sort), particularly in an FCV context, determining an appropriate rate ofbeneficiary contribution and complementing finance with a support component can increase success of the program. In thecase of Niger, beneficiary contribution between 20to 60% proved to be too high and had a negative impact on theimplementation. In addition, lack of a technical support component of matching grants program which would facilitate loanapplications for the borrowers adversely affected utilizations from the program.When collaborating with donors,where the Bank acts as the implementing agency, being informed about restrictions and limitations imposed by the donor at theinitial stage can help overcoming difficulties at the stage of implementation. In the case of the Niger project,implementing team were not informed about all restrictions and limitations, as most of them were coming up during projectimplementation. The design constraints did not allow the Bank to operate major changes as to better align activities to thedevelopments in the field, as this would have required going through donors complex approvalprocedures.Establishing adequate institutional arrangements and platforms can facilitate communication amongrelevant stakeholders for better identification and implementation of reforms in a country. In the case of Niger, theaccomplishments regarding the modernization of business environment are good examples of the adequate institutional and operationalarrangements facilitating the implementation of climate investment reforms. The project brought together different stakeholdersfrom public and private sector, like government agencies, private sector associations, business operators, providing the platformto communicate, engage, and identify priority reforms and support their implementation.
P148861 | Disaster Risk Management Development Policy Loan with CAT DDO | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/099220112102132039/text/Seychelles000SC0DPL0with0a0Cat0DDO.txt | http://documents.worldbank.org/curated/en/099220112102132039/pdf/Seychelles000SC0DPL0with0a0Cat0DDO.pdf | The following lessons are adapted from the ICR:A strong institutional champion is key to advancingcross-sectoral policy dialogue. The Department for Disaster and Risk Management as the implementing agency played acentral role in improving inter-agency collaboration between national and subnational entities involved in Disaster Risk Management(DRM) by establishing or reinforcing incident management procedures and communication. The Ministry of Finance, Economic Planning Trade, with its strong and central position also provided important impetus.Given the cross-cutting natureof DRM, a strong technical assistance program can be effective in building capacity in small island states. Due to theirsize and characteristics, small island states have limited capacities (e.g., few individuals or entities need to cover a broaderrange of government activities and responsibilities, limited resources for building local expertise, etc.) and the government oftenneeds to fulfill both local and national functions at the same time. In this operation, a strong TA program and close Banksupervision proved to be an effective strategy to strengthen institutional capacities and DRM outcomes.The CAT DDOis a multifaceted instrument that can be adapted efficiently and speedily to finance instant liquidity in a crisis. Inresponse to COVID-19 health emergency, the CAT DDO funds were the first source of external financing accessible to Seychelles andprovided a lifeline to people and economy. CAT DDO can include both natural disasters and health emergency.
P148868 | Odisha Disaster Recovery Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2020 | 2022 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099335006202213791/text/P148868080b0c7037097150667cad105ce9.txt | http://documents.worldbank.org/curated/en/099335006202213791/pdf/P148868080b0c7037097150667cad105ce9.pdf | The ICR (p. 30-32) included several lessons learned, which were adapted by IEG: Collaborating at thecommunity levelin DRM initiatives may help ensure sustainability. This projectworked withNGOs andbeneficiaries at the local level which resulted in theresolution of most grievances, and community-friendly design ofreconstructed houses. Failure to linkprojects to other development programs/projects beforeimplementation may undermineefficiency and lead todelays. In this project, during the design state thegovernment of Odisha had to coordinate with other central- and state-sponsored schemes to develop a list of beneficiaries. Whenbeneficiaries changed from the governments housing scheme to the projects scheme, significant delays occurred.Especially the district PIU in Puri faced considerable challenges in finalizing the beneficiary list resulting in most houses notbeing completed when the project closed.A lesson learned added by IEG: When working withcounterparts that have no prior experience in the implementation of Bank projects, continuous Bank supervision iscritical to ensure a successful project implementation. In this project, the Bank did not conduct regular supervisionmissions and reported findings with delay despite several implementation challenges such as natural disasters occurring. As aresult of lackingBank supervision, implementation progress was not tracked effectively.
P148886 | Second Emergency Food Security Support Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2015 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/822441473086793898/text/Guinea-Bissau-Second-Emergency-Food-Security-Support-P.txt | http://documents.worldbank.org/curated/en/822441473086793898/pdf/Guinea-Bissau-Second-Emergency-Food-Security-Support-P.pdf | The ICR included five lessons. IEG selected the following three that are or particular importance with some adaptation oflanguage: Collaboration among implementing agencies is key to successful implementation ofprojects, particularlyunder ashortened implementation period.Effective collaboration andcoordination among the multiple stakeholders and implementing entities involved, and World Bank teams,is critical to achievea successful outcome. In the absence of this effective teamwork, it would be difficult to successfully implementprojectswitha shortened implementation period. Adjusting the implementation time frame within the scope of theplanned intervention is critical to successfully achieve the desired outcome. The mismatch between thePDO, and the nature and scope of the planned activities and the duration of the implementation period negatively affected theachievements of the project. The implementation period was too short to improve the food security of vulnerable population groups.Also, the type of procurement work involved increased the implementation risks given the duration of theproject. Asound ME system and accountability for results is a critical tool for projectmanagement. A robust results framework should include all building blocks that ensure the efficient allocation andmanagement of the project resources (inputs) to generate the outputs necessary for achieving the expected development outcome ofthe project. An ME system that articulates clearly this result chain and the underlying cause-effect linkages is at the coreofa robust results framework. This ME system must be described clearly in the project documents (PAD and implementationmanuals). Leaving it to the project implementation units to design and implement the ME system is likely to result in anineffective and failed result framework. This would make it difficult to develop a coherent and strong story line documenting theachievements of the project, as well as not providing useful evidence as a management tool necessary for making mid-coursecorrections in the project.
P148896 | Local Governance and Services Improvement Program | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | PforR | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099240001122315964/text/P1488960983ca605a0881602f81fe283784.txt | http://documents.worldbank.org/curated/en/099240001122315964/pdf/P1488960983ca605a0881602f81fe283784.pdf | The program offered nine lessons and recommendations following the program operation (ICR, paragraphs 98-106). Five arepresented below with slight modifications: Development outcomes in the local government sectorareenhanced whensucceedingprojects builduponand expandon achievements of prior operations. Inthis program, theproposed local governance reform featured a historical, long-term engagementby the Bank and otherdonors. This approach firmed up donor coordination. Initial efforts graduallystrengthened municipal governance capacity.Municipalities wereslowly establishingcreditworthiness toaccess market resourcesfor municipalinfrastructure. Service delivery processes gradually improved over time.The PforRbuilton achievements of themulti-phased MDP. The well-defined sector andprogram goals led toeffective benchmarking of incrementalimprovements in management and service delivery. Reform may benefit from a long-term engagement in thesector and closecollaboration with donors.In this program, the Banks long-term engagement, itsleveraging of other donor partners interest in the sector, and the numerousanalytical work and background studies all servedtoinforma comprehensive local government sector reform.The program design not onlybuilton lessons andsuccess of previous similar interventions but also introduced innovations in optimal financing of importantinvestments. Accompanying institutional reforms with performance incentivefinancingstrengthensownership and spurs drive for institutional reforms. In this program,local administration staff who were trainedprovidedeffective accountability inresponding to its constituents. The program introduced a new performance incentivemechanism through which VCs strengthened their financing system. This mechanism enhanced ownership and commitmenttoaccountability.However, sustaining the reforms to better functioning VCs introduced by the program need to besustained. The continued application of the allocation formula after the program closes would ensure that LGUs receive funding ontime to deliver and sustain local services and be empowered to perform as fully functional entities accountable to the citizens.Delivery improvements can provide incentives for reform not only at the local government level, but also nationalsystems. A well-designed PforR may benefit from modest financing. In this program US$18 million achievedthe objectives in improving local government.Local government financing wasenhanced with predictable and more equitableallocation of resources to VCs.Capacity was built, not only at the local level but also at the central government level. VCsprepared annual plans, prioritized these with citizen participation, and secured funding for identified infrastructureneeds.Modest services were delivered such as solar energy generation and distribution that reduced electricity bills for thecustomers, prepaid water meters that improved water distribution fee collection. Some schoolsshared by clusters of VCs wereimproved implemented by Joint Service Councils. Joint projects may provide bigger impact on communities andbeneficiaries. In this program, VCs prepared small sub-projects with considerabletransaction costs. Future localgovernment investments may findeconomies of scale in larger, higher impactjoint sub-projectstobenefitsmaller VCs. Annual capital allocations to VCs may also need to be raised to discourage the proliferation ofmicro-projects and many equipment purchases, which led tonumerous contracts (more than 500). Each sub-project requiredcomplex supervision and monitoring of financial transactions. Micro-VC projects and bulk procurement of equipment may bemorebeneficial if these were consolidated or combined to reducetransaction costs. In addition, the rather tiny annual allocationsare deemed suboptimal in relation to the effort of preparing ACIPs and size of sub-projects to make significant impact. Lumpingallocations into fewer releases in West Bank context would encourage prioritization of sub-projects of scale that can betterimprove local service delivery.
P148927 | Transformation of Agriculture Sector Program Phase 3 PforR | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | PforR | 2015 | 2019 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/564821621628672335/text/Rwanda-RW-Transform-of-Agric-Sect-Prg-Phase3.txt | http://documents.worldbank.org/curated/en/564821621628672335/pdf/Rwanda-RW-Transform-of-Agric-Sect-Prg-Phase3.pdf | The following lessons are drawn from the ICR with some adjustments in language:A phased approach from a set ofIPF projects to a PforR program can allow for country systems to adapt more effectively and ensure effective ME.Moving from the IPF to the PforR instrument also challenges the capacity of client countries and raises the bar on what is expectedin a set of interventions over time. Hence, a geographically or thematically narrower and less complex scope for the initialPforR would allow institutions and systems to adapt over time and strengthen the preparation for highly relevantPforR-related processes, such as the ME system and DLI verification process. A phased PforR approach could acknowledgeincreased capacities and gradually expand coverage over time.PforR programs should identify and focus on thoseactivities within typically complex government programs that can incentivize reform. PforR operations often horizontallysupport large and complex government programs and attributing outcomes to specific PforR-supported activities is difficult. Hence,designing a clear PDO and logical Theory of Change is key to understand which activities were the triggers for reform processesoriented towards PDO achievement. Or else, the PforR risks going unnoticed in the government program without clearmeans to steer the direction towards its PDO.The ME system and DLI verification requires a transparent androbust criteria-based process. The DLI verification is a key aspect of PforR programs, both for disbursementsand credibility of the instrument. It allows for improving the accountability and transparency of the government. To ensure that,the process could: involve a verifying entity which has the mandate, capacity and experience to conduct verificationof development programs be transparent by detailing the methodology for the reported status of theDLIs recognize and incorporate qualitative material in telling the performance story allocate adequate stafftime and financial resources.PforR programs can be a catalyst for donor coordination in supportinggovernment programs. The generally larger PforR programs can facilitate better coordination among development partners todevelop a common approach in alignment with government priorities. Such harmonization of donor support towards a government programcan be a welcome and efficiently approach for client countries.
P148927 | Transformation of Agriculture Sector Program Phase 3 PforR | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | PforR | 2015 | 2019 | 2023 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099626002242316672/text/SECBOS1c5615f961655514c621b42c1e04a235f7960.txt | http://documents.worldbank.org/curated/en/099626002242316672/pdf/SECBOS1c5615f961655514c621b42c1e04a235f7960.pdf | 5. Lessons 5.1 PforRs should start with relatively mature and ready-to-implement activities, in this case including soil erosion control and enhanced technological innovation, which led to early results in land husbandry and increased agricultural productivity. It is important to start with a program with a geographically or thematically narrow and simple scope, which would allow institutions and systems to adapt over time and strengthen the preparation for highly relevant PforR-related processes, such as the monitoring and evaluation system and the DLI verification process. An intervention involving a multisector or multilevel approach covering several geographic regions is difficult to implement, particularly with many indicators and PAPs to be managed through interagency collaboration. Designs initially should be kept simple for eventual scale-up and include close coordination among the central-, district-, and sector-level authorities so that learning opportunities are used to attain stronger institutional and managerial capacity for similar operations. A PforR operation trying to address at once 22 almost all constraints for commercialization of farmers (production intensification, research and technology transfer, private sectorâ€“led value chain development, market- oriented infrastructure, agricultural finance, institutional strengthening) may not achieve substantial results in all areas. 5.2 Incentivizing institutional reforms is an added value of the PforR instrument that needs to be internalized by all stakeholders across sectors and at both national and subnational levels. PforR operations often horizontally support large and complex government programs. In a sector that faces challenges at different levels, there may be parallel projects by development partners that aim to contribute to the same envisioned outcome of the government program. When compared with the World Bankâ€™s two investment project financing projects implemented at almost the same time, the strength of the PforR instrument is its potential to contribute to institutional strengthening and reforms. It is important to ensure that stakeholders across sectors and administrative levels are aware of the current systems or their common practices and behaviors and are willing to change them. Explicitly including an institutional strengthening objective in a PDO statement and preparing a solid TOC can highlight key activities that are expected to trigger reform processes. 5.3 Any gaps in capacity and eligibility to request and execute budgets need to be addressed first to ensure the effective functioning of the fund disbursement mechanismâ€”based on DLI achievementsâ€”from the central treasury to the line ministry and affiliated institutions. The evaluation team received comments from multiple sources that indicated limited human resources, especially at the technical level, were associated with the Ministry of Agriculture and Animal Resourcesâ€™ challenges in securing sufficient allocation and timely disbursement of funds from the Ministry of Finance and Economic Planning (interview). Stakeholders in the implementing agencies considered implementation of the PforR instrument more labor intensive than other World Bank financing instruments. Allocating adequate staff time and financial resources to implement and report activities and coordinate with cross-sectoral stakeholders is important for the success of PforR operations. In addition, the centralized fund disbursement mechanism in public channels might not directly incentivize private financial institutions to increase agricultural lending to farmers, affecting the discontinuation of DLI 5 after additional financing. Fund disbursement mechanisms and DLIs must be carefully designed to provide adequate incentives to key drivers to achieve the envisioned results. 1 World Bank Data (database; accessed June 10, 2022), https://data.worldbank.org/indicator. 23 2The population projections are based on the Fourth Population and Housing Census 2012, which is the latest population and housing census. 9Although the baseline of disbursement-linked indicator 4 (key performance indicator 5) was set as five technologies, the Program Appraisal Document of Program for Results 1 included six crops in a footnote to the baseline: â€œMaize, beans, cassava, rice, wheat, and soybeanâ€ (World Bank 2014d, 56n41). 10Technology innovations refer to improved or new methods or practices of production (internationally or nationally generated), including more efficient input usage that led to increased productivity (for example, new or improved varieties of crops introduced and released, improved breeds of livestock, improved input usage such as improved seed varieties and fertilizers; World Bank 2014e). 11Adoption rate refers to farmers who adopt these improved or new innovations and those introduced two years previously to account for the lag in adoption rates (World Bank 2014e). 12 Detailed descriptions of the 20 technologies were not provided in available documents. 13The methodology for measuring program development objective indicator 1 was modified during implementation as described in the aide-mÃ©moire of the third Implementation Support Mission from March 2016. First, concerning the categories of technologies considered, irrigation and soil erosion control measures were included (in addition to improved seeds, fertilizer, and mechanization) and differential weights were used to arrive at a composite index. Second, the percentage of agricultural land covered by these technologies was used as opposed to their adoption by percentage of farm families. 14 The actual and target values for fiscal years 2016â€“17 were not provided. 15African Union Development Agency (website; accessed August 4, 2022), https://www.nepad.org/caadp/countries/rwanda. 16Through the Land Husbandry, Water Harvesting and Hillside Irrigation Project (P114931 2009â€“ 18), which included component C: implementation through the ministerial sectorwide approach structure. 17Rwanda Development Partners (website; accessed June 9, 2022), http://www.devpartners.gov.rw/index.php?id=19. 18 Through the Rural Community Support Project (2011â€“19). 19Rwanda Cooperative Agency (website; accessed January 10, 2023), https://www.rca.gov.rw/cooperatives/about-saccos. 20The country profile for Rwanda on the website of the Agricultural Science and Technology Indicators facilitated by the International Food Policy Research Institute (accessed July 15, 2022), https://www.asti.cgiar.org/rwanda. 21In the Agriculture Sector Investment Plan, the investment areas were expected to cover agriculture and animal resource intensification, research and technology transfer, value chain development, and private sector investment (World Bank 2014d). 24
P148957 | First Fiscal Effectiveness and Growth Development Policy Loan | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2016 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/761161588950880653/text/Romania-Programmatic-DPL-1.txt | http://documents.worldbank.org/curated/en/761161588950880653/pdf/Romania-Programmatic-DPL-1.pdf | This review concurs with the following key lessons presented in the ICR, (the lessons are summarized below, with some additionalaspects added): 1 . Successfuldevelopment policy financing requires sustained ownership of reforms and strong borrower leadership throughout preparation andimplementation of the policy agenda, which typically starts long before preparation of the operation or series and extends beyondits closing. In the case of this series, the risk of weakening political commitment was recognized from the start; and although theseries adopted numerous mitigating actions, that risk materialized, and mitigating actions could not preserve fully the achievementof results. demonstrating that the original risk rating of substantial was correct.2. A prior action (under a DPL) should not require a decision of Parliament. Instead, consultation andcollaboration with Parliament should be part of DPL preparation, through the provision of adequate information and inclusion of keyparliamentarians and advisors in capacity building programs. Resorting to government actions, such as emergency orders, as asubstitute for Parliamentary action and in the interest of achieving DPL results, contributes over the medium-term to underminingof good governance and the legitimacy of government institutions.3 . Availability oftechnical assistance and advisory activities as needed during design and implementation of a program can improve quality andbolster government commitment. The RAS program was critical for design and implementation of the FEG series. Because theseactivities were funded by the EU, the government could overcome its reluctance to accept technical assistance, and the policydiagnostics and advice provided by the RAS should have ongoing usefulness to future pro-reformgovernments.4 . Good local coordination between the implementing agency and theBanks Country Office is crucial for achieving DPL results. In this case, effective coordination between MoPF and the Bankwas key for the effective monitoring of progress, allowing the responsible authorities and Bank management to intervene effectivelyat key moments during reform implementation.
P148970 | Haiti Sustainable Rural and Small Towns Water and Sanitation Project | Latin America and Caribbean | Haiti | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099020624084019926/text/P14897010fb9d83a140411493f19c201883cc4daae9f.txt | http://documents.worldbank.org/curated/en/099020624084019926/pdf/P14897010fb9d83a140411493f19c201883cc4daae9f.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1. Projectsimplementedin fragile environmentsmust thoroughly and candidly assess the expected implementation challenges to ensurerealistic technical solutions and institutional arrangements that are identified and adopted. The project financed a largenumber of activities in eight out of the 10 administrative regionsunder challenging implementation conditions combined withweak capacity. While most activities were of small size, accessing implementation areas was difficult.Also, implementationarrangements involved numerous entities with weak capacity, which exacerbated implementation difficulties and required moreactivities to help them fulfill their roles.Such challenges needed to be carefully assessed at the preparation stage toensure smooth implementation and a successfuloutcome.2.Sustainability of WSS investments requiresimplementation of intense and multifaceted activities before, during and after conclusion of the works. These activitieswere part of the project implementation strategy and were partially implemented; however, as difficulties in meeting deadlinesincreased, a focus on concluding the works prevailed. As a result, although the project concluded most of the investments in waterand sanitation systems and facilities, there was limited evidence to indicate sustainability. It is therefore recommended thatimplementation arrangements of similar projects clearly demonstrate that the full range of activities required to supportsustainability is assured.3.To successfully and effectively tacklecrises that need rapid responses onvarious fronts,strengthening collaboration of joint World Banks practicescombined with design flexibility isnecessary to ensure coordinated andinnovative support. The project benefited from joint work of WB practices primarily water and health, but also education and energy, especially during crises that needed rapid responses on various fronts.Early in the project, ajoint response to cholera outbreaks was replicated in a project in Yemen. During implementation, theWB water team worked with the education team on the design of school latrines. In the last months of the project, a health projectincorporated WSS activities due to a new cholera outbreak. Flexibility in design is conducive to innovative practices, especiallyduring a crisis response.
P149005 | Kosovo Education System Improvement Project | Europe and Central Asia | Kosovo | IDA | FCS | Human Development | Education | IDA | IPF | 2016 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099350106282221493/text/P14900508f80ea0460ab7807695db27d9fd.txt | http://documents.worldbank.org/curated/en/099350106282221493/pdf/P14900508f80ea0460ab7807695db27d9fd.pdf | The following lessons are derived from thosepresented in the ICR, reworded by IEG: A projectsupporting multiple, complex, system-wide reformsin a politically fragile, low-capacity environment is not likely to succeedwithout undertaking, and factoring into the design, rigorous assessments of: the political economy of those reforms among keystakeholders; the commitment and ownership of the highest levels of government to reforms; the technical, managerial, andinstitutional capacity to implement them; and the availability of resources to ensure their proper financing andsustainability.Because these assessments were not systematically undertaken during project preparation, theinitial design, scope, and outcome targetsof the project were far too complex and ambitious for the countrycontext. Especially in the context of a constantly changing political environment with high turnover of sectorleadership and key technical positions, a stable, adequately staffed PCU with low turnover is critical for ensuring smoothimplementation, the achievement of results, and capacity building of ministry staff.Prior to restructuring, frequentrotation of PCU staff, including the Project Coordinator, undermined institutional capacity and memory and the pace of projectimplementation.Bank efforts to maintain implementation momentum during periods of government transition and to strengthen PCUstaffing helped bring stability and enhance capacity, contributing to a positive turnaround in the projectsperformancepost-restructuring. A timely, rigorous, candid, and evidence-based mid-termevaluation can be an effective tool for major restructuring of a non-performing project and for enabling its ultimatesuccess.In the case of this project, the restructuring resulted in a simpler, more focused design, with fewercritical activities, much better suited to the complex, fragile environmentand limited institutional capacity inKosovo.IEGs review offers an additional lesson: In a country where issues of stronginequities prevail, there are multiple opportunities to address these issues both directly and indirectly. Among the240 schools selected to benefit from SDGs, 140 were selected for their rural locations and for their service to disadvantagedpopulations.During the June 1, 2022 meeting with IEG, the TTLprovided additional information and insight on how theproject also factored equity concerns into the capacity and systems strengthening activities.Disadvantaged schools benefitedfrom school-level management capacity building and, disproportionately so, from the school report card pilot, which enabledcomparison to other schools in the municipality and nationally.The in-depth report on PISA 2018 addressed the special themeof learning equity across the country.The technical assistance exploring school financing formulas factored in the need forincreased financing for disabled students and disadvantaged schools.Had equity been included as a higher-order objective, andits tracking and measurement taken into account in the choice of intermediate results and/or outcome indicators (in other words,had equity been more systematically reflected in the various components of the projects results chain), the projectscontribution to equity may have been more fully assessed and developed.
P149049 | Forest Dependent Communities Support Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2023 | 2025 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099102924145077497/text/P149049-c278567f-8697-4396-8fdd-a1cc4694ca01.txt | https://documents.worldbank.org/curated/en/099102924145077497/pdf/P149049-c278567f-8697-4396-8fdd-a1cc4694ca01.pdf | In addition to the lessons highlighted in the ICR, this review has drawn three lessons based on the information in theICR:Adequate fiduciary capacity of implementing agencies is critical for continuation of communitydevelopment and capacity development efforts.The projects experience highlights that a lack of financialmanagement and procurement capacity can significantly undermine transparency and stakeholder confidence. As a pioneering effort inDRCengaging IPLC in land and forest management governance, the project addressed a key development challenge. However, itunderestimated the challenges associated with fiduciary and financial management capacity, which could impede the sustainability ofsuch initiatives in the future.Digital monitoring platforms and third-party monitoring can overcome both capacityand accessibility challenges for project teams.The ICR mentioned that community groups indicated the need fordigital tracking tools to facilitate their monitoring efforts. Theuse of third-party monitoring, particularly for conductingsocial audits, could have provided an additional layer of oversight and accountability. This approach might be especiallybeneficial in contexts where local capacity is still developing and where independent verification of project outcomes isnecessary.Extended preparation time and project preparation grants can support smoother implementation withpartners that are newly engaged. Engaging new partners with low capacity requires longer preparation times to establisheffective communication and implementation protocols. The project would have benefited from project preparation grants, which couldhave facilitated the necessary groundwork, including capacity building and the establishment of clear operational frameworks amongpartners. This preparation could have mitigated the capacity challenges encountered during implementation and ensured a smootherexecution of the project.
P149091 | Lusaka Sanitation Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2015 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR includes three lessons which are emphasized below with some adaptation of language:1. Implementing asuccessful citywide inclusive sanitation approach requires timely and targetedsanitation marketing combined with improvedcustomer services. During the first four years, Lusaka Sanitation Project relied on enforcement for connecting householdsto sewers, while the connection costs, as well as those of the OSS facilities, were not affordable for the peri-urban targetedpopulation. The project needed to change its approach with door-to-door communication instead of community-level engagementonly.Also,adding subsidiesfor both types of infrastructures and improving FSM services through a transitionalperformance-based subsidy associated with the coaching of private operators, a new call center, and an FSM unit among other,dedicated to sanitation customers.2.In countries with power supply challenges, it is crucial for projectssupporting sanitation systems that require power for their operation to secure affordable backup or alternative powersources. Despite have beenfully paid from the beginning, the national electricity companyfailed for over ayear to connect 10 out of the 20 pumping stations installed as part of this project. As a result, LWSC has been forced to operatethese stations at a minimum capacity and using backup generators, incurring additional fuel costs. Starting mid-March 2024, ZESCOimplemented gradual load shedding due to drought, resulting in more than 20 hours of announced power interruptions per day. Despitethe recent connection of the pumping station sites, LWSC is still required to operate the stations sparingly usinggenerators.3.The sustainability of water and sanitation utilities require regular tariff adjustmentstomaintain the sanitation chain functionally. Despite a good revenue collection efficiency (92%for 2023), LWSCscapacity to cover essential OM costs could be negatively affected due to low tariffs, which have not yet been adjusted since2019. Operational improvements provide leverage for the utilities to make a case with the government and thecustomers of water services that tariffs need to be increased. Increasingtariff is a criticalstepfor the sectors financial equilibrium and the sustainability of services. The longer the decision is deferred, thewider the financial gap, the higher the probability of the water and sanitation system collapsing, and the higher the next tariffadjustments would need tobe.
P149095 | Rwanda Public Sector Governance Program-For-Results | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | PforR | 2015 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/487701593443169107/text/Rwanda-RW-Public-Sector-Governance-P4R.txt | http://documents.worldbank.org/curated/en/487701593443169107/pdf/Rwanda-RW-Public-Sector-Governance-P4R.pdf | The following are the key lessons from the ICR (pp.28-30) with some adjustment in language:The prerequisite forthe success of the PforR instrument is a well-developed reform program that has been defined and is fully owned by thegovernment. The national program shaped the Programs design by identifying areas in need of additional support withthe World Banks value-added engagement. The existence of a clear national program of work clearly delineated the Programboundary.The involvement of the Supreme Audit Institution in the verification protocol of DLIs can increaseaccountability of the Program as long as the Supreme Audit Institution is independent and the strong commitment to results isshared at the highest level of the government. For Rwanda, the Office of the Auditor General conducted verification of allDLIs except for one, which was related to an unqualified audit opinion. A dedicated team within the Office of the Auditor Generalwas established and conducted verification for the entire Program implementation period. This team had sufficient competence,institutional and behavioral independence in relation to the executing agencies to carry out independent verification of DLIresults. Learning by doing served to strengthen ownership of Program results, provided added clarity in the accountabilityfor achieving results, and built institutional capacity.PDO results indicators need to be closely connectedto intermediate indicators and DLIs through a robust Theory of Change. A well-structured results chain based on a set oflogical and achievable steps reflecting the PDO indicators and DLIs is essential to the success of the PforR. Clear linkagesbetween the PDO indicators, intermediate indicators, supporting DLIs, operation interventions should be established andincorporated into the Programs results framework as well as operation interventions.The success of theProgram requires close and frequent monitoring and engagement and greater supervision by the task team. The nature of thePforR enabled the Government of Rwanda and World Bank to focus on technical issues rather than ICT procurement processes, whichtypically consumes supervision of Investment Project Financing. The Program required enhanced supervision in terms of the depth oftechnical expertise and the rigor of monitoring to support achievement of the DLIs and PAPs.
P149129 | Kenya Devolution Support Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | PforR | 2016 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099550111182239543/text/P14912902f845e07f08e7102c5f1e3db14f.txt | http://documents.worldbank.org/curated/en/099550111182239543/pdf/P14912902f845e07f08e7102c5f1e3db14f.pdf | Several lessons are drawn from the ICR:- Ownership of the PforR reforms by national and subnational governmentsis vital for its success. The PforRwas designed based on the government program of devolution and on theidentification of the main areas where support was sought by the government. This ensured the PforRs strong collaboration onimplementation and expectations for sustainability.- PforR coordination needs to be sufficiently incentivized inits design. The PforR appraisal dedicated no resources to support the lead ministry to coordinate all involved agencies,negatively affecting the PforR implementation. At MTR, a correction was made, and a separate sub-DLI was created for that purpose.This is a lesson for the future: PforR coordination needs to be sufficiently financed.- Annual performanceassessment capacity within the government needs to be developed. While the PforR chose to hire a private firm forperformance assessments, it is critical to build government capacity for the monitoring of government performance after the PforRclosure. Future PforRs could start with an outsourced ACPA arrangement, but then transition to a government-led performanceassessments before project closure.- National level agencies mandated with environmental and social safeguardsneed to be identified and supported to implement capacity building and oversight. The PforR involved extensiveinfrastructure investments requiring a safeguards capacity at county level. However, at appraisal, two government institutions(NEMA and CAJ), mandated with safeguards, were not included in the PforR capacity building activities. That shortcoming wascorrected during implementation. Future PforRs involving infrastructure investments may need to include sustained capacity buildingof such institutions.
P149130 | Second Global Partnership for Education | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099152503222310555/text/P1491300f29b020eb0a1ef01a5c71885d72.txt | http://documents.worldbank.org/curated/en/099152503222310555/pdf/P1491300f29b020eb0a1ef01a5c71885d72.pdf | The following lessons were presented in the ICR, slightly reworded by IEG to be more succinct: Failure to explorethe innovative use of information technologycan be a missed opportunity to overcome monitoring challenges in the context of apandemic.Regular school inspections and monitoring visits were not carried out due to travel restrictions, leaving theproject with considerable difficulty in obtainingmonitoring data. The use of smart phone-based Open Data Kit (ODK) or KoboCollect Apps could have helped the implementers obtain school-level data, and would be useful to consider in futureinterventions. The opening of school bank accounts for school-based grantimplementation enables transparent flow offunds and budget execution at the school level.The project was able to mainstream this practice into the national system,complemented with financial management training for school principals.The school bank accounts were capable of receivingother financial resources in addition to the funding under the project, a practice that might be applied to other school fundingprojects in the region. In the event that pilot projects are not ready, by an operations completion, to providefirm evidence upon which to recommend revisions and/or scaling up, the continuation of those pilots, rather than their termination,could be a way to ensure the collection of needed evidence to ensure sound decisions about whether or not to scaleup. Delays in reaching consensus by development partners and the government on the approach to school-based managementand financing (and related training materials) can cause implementation delays and alack of coordination of various sourcesof support. The clear articulation of the Grant Agents role can ensure that it is in a position to make technicaldecisions independently.IEGs review offers an additional lesson: Failure to establish clearoutcome indicators (and supporting output and intermediate indicators) for all dimensions of a PDO statement can lead to theinability to assess unequivocally the achievement of all of the projects intended outcomes.In the case of thisproject, achievement of the objective to improve pre-primary education quality, through the provision of school-based grants andaccompanying capacity building to manage and use these resources effectively, could not be fully assessed.
P149176 | Strengthening Institutional Capacity for Government Effectiveness Project | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099210503032312097/text/P149176046ffea0f109bf205849bec01a05.txt | http://documents.worldbank.org/curated/en/099210503032312097/pdf/P149176046ffea0f109bf205849bec01a05.pdf | With some revisions by IEG, the ICR presents the following lessons,: Addressing governance and public financialmanagement problems in contexts with low capacity and an environment of fragility, conflict, and violence (FCV) requires long-termcommitments by the national authorities and the donor community. It also requires a thorough analysis of the countryspolitical economy and risk analysis of the political conditions to be ready to redesign the project to tackle these events andmakes it possible to achieve the assistances goals. A government is more likely to capture and maintainthe gains in capacity building if the PIU is staffed with civil servants rather than consultants local or foreign whotend to disperse after the project ends.
P149182 | Citizen Access to Responsive Services Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2021 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099123201312317320/text/P1491820ad0d610220b9c50dcc407368235.txt | http://documents.worldbank.org/curated/en/099123201312317320/pdf/P1491820ad0d610220b9c50dcc407368235.pdf | The ICR (pp. 22-23) presents a range of insightful lessons, twoof which are summarized and expanded on here:Newmodelsof service delivery canfundamentally changethe culture of governance and the relationship between the stateand citizens. While the PDO for this project focused on increasing access to PSGA services, the process of achievingtheseobjectives included business process reengineering, changes in institutional mandates, and re-imagined structures,leadingto fundamental strengthening of transparency and accountability in the provision of services. The interface betweencitizens and service providers grew toarms length, reducing opportunities for rent-seeking behaviors as businessprocess reengineering and the removal of various stages of approval meant less red tape and greateraccountability.Relianceon countries own systems when they are strong enough is rightly a central feature of theaid effectiveness agenda. The procurement issues in thisproject were largely related to the government being contractuallyobliged to follow Bank procurement regulations, while the governments own procurement systems might have been adequate toguarantee fiduciary compliance. Setting up parallel systems hasbeen found to create duplication and increase transactioncosts, hamper alignment with country priorities and ownership, and constrain efforts to strengthen national capacity. On the otherhand, using recipient country procurement systems can provide incentives and momentumto strengthen domestic capacity andsystems, and to enhance domestic accountability processes.
P149242 | Emergency National Poverty Targeting Program Project | Middle East and North Africa | Lebanon | IBRD | FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099400004042277803/text/P1492420fd711a0010b95a00f70e9ed331c.txt | http://documents.worldbank.org/curated/en/099400004042277803/pdf/P1492420fd711a0010b95a00f70e9ed331c.pdf | The ICR (pp. 37-39) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:When a development project uses national institutions for its implementation in FCV settings, the project canconcurrently contributeto the preservation of those institutions and to the enhancement of their capacities. Theproject maintained and strengthened the capacities of the Ministry of Social Affairs, the Presidency of the Council of Ministers,and the administration of the National Poverty Targeting Program to provide critical support to poor and vulnerable householdsduring a highly fragile and volatile period. The project also strengthened the building blocks of a national social safety netsystemand contributed to helping Lebanon to weather the compounding effects of successive crises, that it continues toface.Collaborating with international organizations with comparative advantages and leveraging their capacitiesand expertise can expedite project activities and lead to more significant impact. The project benefited from itspartnership with the World Food Programme, its experience, delivery mechanisms, and ME systems, resulting ineffective implementation of the electronic food voucher program.Project coordination, ownership, andimplementation can be negatively affected by complex implementation arrangements. The implementation structureencompassing the Ministry of Social Affairs, the Presidency of the Council of Ministers, and the Fiduciary Operations Team wascomplex and negatively impacted implementation. Critical responsibilities rested with different government institutions, andnecessitated clarification of responsibilities and coordination of activities throughout the cycle of implementation and projectrestructurings. Simpler lines of responsibility and accountability would likely have expedited procurement activities and overallimplementation, particularly for the graduation activities.
P149282 | Solomon Islands Rural Development Program II | East Asia and Pacific | Solomon Islands | IDA | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099062023091535011/text/P14928204834bf00f092170446b93be28c0.txt | http://documents.worldbank.org/curated/en/099062023091535011/pdf/P14928204834bf00f092170446b93be28c0.pdf | The ICR included lessons learned (p. 36) which were adapted by IEG: Encouraging cash crop production atthe expense of sustenance crops can lead to food insecurity. The government prioritizes cash crops in the SolomonIslandsfor exports and taxation. Also, in this project, cash crops were grown at the expense of sustenance crops in a fewinstances. While in most parts of the world, people are rich and land/resource-poor, there is a link between cash and substance,and nutrition is determined by earnings; this is not the case in most of the Solomon Islands and other Pacific island countries,where home gardens provide most calories consumed by rural households. Lack of relevant in-depth market researchat appraisal may lead to a mis-targeting of beneficiaries. In this project, a smaller number of agribusiness thanestimated at appraisal and low capacity in existing agribusinesses resulted in a largely unutilized ASEF grant component.Furthermore, the demand for commercialization support for farmer groups exceeded the projects delivery capacity. Marketresearch during project appraisal could have identified these issues and opportunities. Supporting basicinfrastructure and services that engage and empower the lowest government and community level is critical for sustainability.In this project, engagement with wards positively contributed to achieving outcomes. However, there is a concern that thisengagement at the Solomon Islands lowest government level, ward level, initiatives will end after projectclosure.
P149286 | Uganda Multisectoral Food Security and Nutrition Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2015 | 2024 | 2025 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | https://documents.worldbank.org/curated/en/099120524174032347/text/P149286-a55c5c22-b66c-449f-bcee-9757cd07e6a6.txt | https://documents.worldbank.org/curated/en/099120524174032347/pdf/P149286-a55c5c22-b66c-449f-bcee-9757cd07e6a6.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1. Amulti-sectoral nutrition approach combinedwith a robust supra-ministerial coordination is critical to achieveaneffective institutional structure for improved nutrition outcomes. The project experience emphasized the importance ofmulti-sectoral approach and coordination.Future nutrition initiatives should leverage and strengthen the national nutritioncoordination structures under the leadership of the supra-ministerial coordination structuresto achieve better coordinationand greater impact. In the case of this project, the coordination anchor wasnationally mandated to overseethecountrys nutrition strategy, which was vital in the success of the approach.2.Successfulimplementation of multi-sectoral nutrition projects requires constant learning from implementation experience and evaluationoutcomes. Nutrition projects tend to have a complex nature and exhibit locational variability.Therefore,anational-level policy dialogue and widespread dissemination of project learnings are essential for obtaining the desiredcommitment from the highest levels of government to maintain project gains.3. ME design need to reflectadequate implementation arrangements and relevant indicators to comprehensively assess the project outcomes.Theproject experience demonstrated that theadoption of Geo-enabled ME technology, capacity building of relevant staff, andproper utilization of ME outputs can all help to significantly improve the MEquality, speed, and due diligence.Reliable ME dataallows for effective decision making and course-correction to fully achieve the planned outcomes. Inaddition, careful selection of nutrition related indicators and setting of realistic targets is critical to achieve the desiredresults. Nutrition outcomes, by their nature, take time to fully manifest as behavioral change is a time-consuming endeavor thatprogressively takes root. As such, project teams need to be realistic in setting targets that reflective of such progression.
P149322 | Road Sector Development Project | Europe and Central Asia | Ukraine | IBRD | FCS | Infrastructure | Transport | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099021524123010112/text/P1493221e07aac07218fce15ee63299a1b3.txt | http://documents.worldbank.org/curated/en/099021524123010112/pdf/P1493221e07aac07218fce15ee63299a1b3.pdf | The following lessons were derived from the ICR (ICR, pages 32-33):Ambition requiresflexibility. Implementing a transformational and impactful project in a volatile environment requires a constant dialoguewith the Government and innovative solutions to make timely adjustments to the design of the project, balancing the ambition andthe level of risk. The Project benefited from the support of the World Bank to escalate issues to the highest political level andto advocate for Project implementation flexibility and adjustments (including restructurings). The lesson is that whether mistakesare made with project design or external circumstances require projects adjustment, active engagement in project adaptationand a flexible approach to implementation (including restructurings if necessary) can be critical for a projectssatisfactory outcome.An adequate allocation of World Bank resources and time to meet supervision program needs iscritical. Short preparation timelines negatively affect development outcomes and often lead to restructurings to correctinadequate design. Supervision of projects with such deficiencies requires a reinforced monitoring system, through longer and moreinvolved missions and increased attention to red flags and early warning signs. In such circumstances, it is essential that properWorld Bank supervision budget be allocated to cover related expenses. The Projects experience was that it was essential tobe able to spend enough time in the field to (i) tailor interventions based on specific criteria (particularly, costing within thebudget); (ii) find key partners for the project, and (iii) address the cost evaluation difficulties.Securityconstraints require innovation in monitoring and supervision, as well as during the design stage. When supervision isdifficult due to security issues, and conducting field visits is not possible, teams operating in fragile settings could consider:(i) innovations such as the World Banks Geo-Enabling Initiative for Monitoring and Supervision (GEMS) and Third-PartyMonitoring Agents (TPMAs), and (i) integrating remote supervision capacities into the ME framework.
P149410 | CASA-1000 Community Support Program (P149410) | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Social Sustainability and Inclusion | RETF | IPF | 2014 | 2025 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The following lessons are based on the ICR, with minor adjustments. They can be used in the FCV context beyondAfghanistan.- Community driven development (CDD) operations can help alleviate the risk of conflict, and the CDDapproach of benefit sharing can be an effective mechanist of conflict prevention. By building on the lessons learned from CDD inFragility, Conflict, and Violence (FCV) settings, the Project implemented the benefit sharing approach successfully. This lead notonly to the support from the communities to the construction of the transmission line, but also mobilized communities to be theactive agents of development. The approach of benefit sharing is to treat local communities as active stakeholders who seekopportunities provided by the projects. Similarly, this approach was relevant in supporting COVID-19 response within the Projectand helped vulnerable households through assistance with basic needs and through small local infrastructure projects that providedjobs.- The Projects experience showed the benefits of structuring it as a standalone CDD project, designed inparallel with the parent CASA-1000 project, as opposed to being a subcomponent of the CASA-1000 project. Such design significantlyhelped in the implementation of benefit sharing. It allowed specialized Bank staff to be on the Project teams, working withgovernment agencies with dedicated experience in community development. Such design is a good practice.- CDDprojects linked to major infrastructure projects can benefit them for multiple reasons. The Project helped the CASA-1000transmission line project during implementation. Communities in the COI helped the CASA-1000 contractors in the identification ofthe locations for the tower, negotiations and granting access to contested or Taliban-controlled areas. Communities alsofacilitated land acquisition and resolving disputes in the CoI. Also, the Project helped communities understand the importance ofthe CASA-1000 project and how it was beneficial for corridor communities and Afghanistan at large in the long run. In addition, theProject managed to mobilize, train and elect new Community Development Councils (CDCs) along the CoI, and therefore strengthenedcommunity development in Afghanistan. Such interlinked CDD and infrastructure projects can be used in other FCV settings and alsoin non-FCV development context.
P149485 | Ningbo Sustainable Urbanization Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2024 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062624114023284/text/P149485-c1a61176-764e-410c-836d-7d3536c750a6.txt | https://documents.worldbank.org/curated/en/099062624114023284/pdf/P149485-c1a61176-764e-410c-836d-7d3536c750a6.pdf | The project identified the following lessons: When design uses a framework approach to facilitatepreparation and allow flexibility at implementation, the accuracy of ME targets and project costs may suffer.In this project, the framework approach meant that subproject investments were appraised in various stages andindicators and costs were allocated according to the initially identified subprojects. While the framework approached gave theproject flexibility and timeliness to respond to priority changes in local development plans, required a strong project managementcapacity. Significant efforts were needed to appraise investments in different batches following consistent principles andcriteria. However, this approach also meant changes in subproject components as subproject appraisals were conducted in phases.These resulted in changes to the pipeline and pointed to inefficiencies in resource use (time andfinancing Strong government commitment and high-quality technical assistance may improve implementation andincrease knowledge sharing. In this project, the Ningbo Development and Reform Commission was the mostimportant planning entity of the municipal government and housed the Ningbo PMO. The commission proactively proposed studies toexplore solutions for priority urban development and planning strategic issues beyond the project indicating its commitment toexploit the available TA. The choice of Ningbo as the project city was a crucial strategy to demonstrate climate-induced floodingin a typical Chinese coastal city.Towards the end of the project implementation, Ningbo PMO published two analytical paperson Resilient cities construction and management under climate change an example from Ningbo andThoughts on Managing the Government Financed Projects in the China Investment Magazine and the Zhejiang EconomyJournal respectively, two high level and influential publications in China and Zhejiang Province. Implementationdelays may be avoided if sector policies and requirements are adequately considered. In this project, regenerationsubprojects in the areas around Jiangs Ancestral Hall experienced significant delays. The Hall was listed in the culturalheritage assets managed by the National Cultural Heritage Protection Administration. This meant that any changes to and around theHall required their approval. The PIP did not include this as a requirement at implementation and the project was delayed for twoyears awaiting approval of the design. Early and frequent communication with different levels of administration entities and abetter understanding of approval requirements may avoid implementation delays.
P149512 | CAR Emergency Food Crisis Response and Agriculture Relaunch Project | Western and Central Africa | Central African Republic | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/115371487168582386/text/ICRR-Disclosable-P149512-02-15-2017-1487168569296.txt | http://documents.worldbank.org/curated/en/115371487168582386/pdf/ICRR-Disclosable-P149512-02-15-2017-1487168569296.pdf | The ICR included five lessons. The following are emphasized with some adaptation of language: Adequateimplementation budget/support iscritical for emergency operationsparticularly in fragile states.Simplified financial management and procurement procedures combined with the flexibility in preparing emergency operationsfacilitate rapid approval, effectiveness, and initial disbursement. However,the quality of implementation and achievement ofresults may be seriously compromised if adequate supervision resources are not provided. Outsourcing projectimplementation to well-established international institutions is not necessarily an effective strategy in fragile states, unlessthey have proven country-level institutional capacity and functioning procedures on the ground. WFPsexperience and know-how in developing and deploying school feeding program and food distribution were key in achieving theobjectives under Component 1.However, FAOs implementation performance was weak and the absence of a functioningME and related reporting system should have been noted during project preparation. Phasedpayments to international implementing agencies rather than a singletranche helps to ensure that the total amount of moneypaid to carry out an activity is fully used to do it. If using specialized UN Agencies is appropriate to implement someprojects in certain situations, payments should be phased.This would provide better incentives to implementers and make themdo a better job while respecting contractual agreements.
P149512 | CAR Emergency Food Crisis Response and Agriculture Relaunch Project | Western and Central Africa | Central African Republic | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2016 | 2018 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/516941531419159046/text/127422-PPAR-P149512-P165993-PUBLIC.txt | http://documents.worldbank.org/curated/en/516941531419159046/pdf/127422-PPAR-P149512-P165993-PUBLIC.pdf | 10. Lessons 10.1 Standard agreements between World Bank clients and UN executing agencies can facilitate success if they include a common vision about intended objectives, a clear and achievable results framework and related outcome indicators, and a clear articulation of how risks to the environment and social framework will be monitored, reported on, and managed. In the Central African Republic, the World Bank over-relied on UN reporting mechanisms after the humanitarian crisis, and did not fulfill its supervision responsibility, undermining opportunities to address ongoing project implementation challenges. 10.2 Efficient seed procurement for conflict-affected countries is complex because trading networks and normal supply and demand signals are disrupted, and hence the recruitment and funding of a technical team needs to be a prior condition of project effectiveness. The experience in the Central African Republic shows that procuring the correct seeds for specific geographic locations and their associated soil and agro-climatic conditions is technically demanding and time consuming. It also requires deep local and regional knowledge of supply and demand. Upstream diagnostic work on effective seed procurement (quality and realistic timeframe for procurement), including the availability and quality of technical support, is needed. This should involve a candid review of the World Bank's existing partnerships and ways of doing business (e.g. FAO execution) but also finegrained institutional analysis and mapping of capable government technical services and partners in the NGO community (some NGOs are much more capable than others and they need to be identified before crisis hits). The few dispersed agricultural technical services that remained after the crisis, including many well-trained and capable agents, should have been better incorporated into the emergency response. 10.3 Emergency food security operations do not necessarily require food agency coupling (such as WFP and FAO). Depending on the stage of recovery, emergency operations may be better served by pairing a food agency with a social agency (such as UNICEF or the Red Cross) to achieve more effective targeting and service delivery for the most vulnerable populations. 10.4 Post-conflict emergency assistance in highly agrarian economies should try to maximize synergies across sectoral operations to optimize the delivery of food aid while laying a foundation for growth of the agricultural sector. In the Central African Republic, interviews with UN relief agencies and development actors revealed that opportunities were missed after the 2012 coup to link humanitarian interventions with wider development aims, for example, by identifying transport interventions that could have increased market access while achieving stabilization aims. To achieve more effective harmonization, lessons from the Central African Republic suggest that aid could have been better coordinated through a multidonor strategy and funding tool designed to support the recovery while bridging the humanitarian reliefâ€“development divide.
P149521 | Technical Assistance Project for the Development Carbon Capture and Storage in the Republic of South Africa | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2017 | 2024 | 2025 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons were derived from the ICR (ICR, pages 25-26):1. Engaging and supporting clients inpiloting new technologies involves significant risks, but such activities bring considerable benefits in generating knowledge anddeveloping capacity, thus building a foundation for technology adoption. The Project did not achieve a full implementationof the pilot carbon storage facility component due to delays and thesubsequent cancellation of the construction and operationphases. However, the completion of its first phase - comprising geotechnical investigations, site selection, and CO2 storagefacility design -has provided insights intothe potential of the countrys geological formations to store CO2 emissions,forming a strong foundation for the next phases: construction, operation, and monitoring of the storagefacility.2. Changing project implementation arrangements mid-stream requires careful consideration to ensurethat the project management systems are either retained or replaced by adequate systems, and that the new implementing agency isbrought up the learning curve and provided with resources. In the Project, the risk of limited institutional capacity forProject implementation and sustainability wasmitigated at appraisal, including by using international advisory committees andimplementation consultants. However, the transfer of the Project to CGS did not include sufficient capacity building. As a result,CGS used its own internal processes for approvals.Shortcomings in procurement processes and financial management - includingdifficulties in preparing interim financial reports (IFRs) andawarding contracts -led to significant delays and thescale-down of Component 1.3. The design of CCS projects would benefit from considering a range of sectors,including industry, rather than focusing oncoal and the public sector. The management of CO2 capture and storage hasincreasingly shifted to industry globally. Hence, in the future, South Africa could benefit from consultations withindustrialemitters whenselectingsites for CO2 injection. Additionally, the country could explore the conditionsand incentives that would increase the uptake of CO2 management activities by a range of sectors.
P149526 | Sahel Malaria and Neglected Tropical Diseases | Western and Central Africa | Western and Central Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099255104112270450/text/P14952607292c70b00b145025688b3a43ca.txt | http://documents.worldbank.org/curated/en/099255104112270450/pdf/P14952607292c70b00b145025688b3a43ca.pdf | The ICR (pp. 31-32) offered several valuable lessons, including the following adapted by IEG:Collective andsynchronized actions can improve project effectiveness.Joint work plans and joint supervision between countries wasa learning-enhancing experience across the three countries. The joint approach allowed stakeholders on both sides of the border toengage in fruitful collaboration. It was the first time for the three countries to plan and implement a WHO strategy in acoordinated regional manner.Micro-planning of disease control campaigns can significantly contribute to betterresults.Health ministries empowered the local levels to consider and incorporate the needs of individual districts.This entailed micro-planning activities through workshops that supported and trained actors at all levels. The inclusive approachstrengthened ownership, built trust, and facilitated information dissemination.Partnering with other institutionsand development partnerscan contribute to supporting long-term national and regional policies. The project sought topromote a long-term regional approach and the countries were able to secure country-specific support from international developmentpartners to tackle malaria and NTDs.The engagement and support of community leaders and key local actorssuch as teachers can be crucial to the effectiveness of information and education campaigns to influence population behavior.The participation of community leaders in micro-planning activities contributed to their close engagement in publiceducation efforts and in gaining the populations trust. Teachers were key to providing awareness, education, and distributionof information in view of their status and credibility at the community level.Long-term procurementcontracts for drugs can contribute to cost-containment and can reduce the time-lapse for delivery. Long-term contractsbrought more leverage to negotiate prices and improve contract terms. CAMEG emphasized the importance of negotiating multi-yearcontracts for the pooled acquisition of drugs, although it also pointed out that the need to negotiate contracts every yeardiminished the room for lowering drug prices.
P149553 | Bangladesh NATP-2: National Agricultural Technology Program - Phase II Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061424175539184/text/P149553-e4ed3c2e-0f68-4181-bae5-3d10cbe9c929.txt | https://documents.worldbank.org/curated/en/099061424175539184/pdf/P149553-e4ed3c2e-0f68-4181-bae5-3d10cbe9c929.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. To ensuretimely dissemination of technologies, investments in research need to be also supported with adequatefinancial anddissemination tools and activities. A typical research lifecycle is longer than the standard period of a projectfinanced by the World Bank. While this project successfully generated 40 scalable technologies it required more time forthese technologies to be adopted at scale and to contribute to productivity increase.This emphasizes the relevance of asupport program like NATP in which technologies generated under NATP-Iweredisseminated underNATP-II.2.To improve market access and value chain development for smallholders,robust technicalassistance for a significant period of time is needed to ensure the achievement of sustainable outcomes. Given thecommercial nature of agriculture, public sector capacity requires significant technical assistance from specialists to facilitateliaisonwith market actors, to develop value chains and enable a transparent, equitable and efficient businessenvironment. NATP-II identified external technical assistance to provide such professional services for three sub-sectors, butcould not maintain this support throughout the project period. After the departure of the external technical assistance, localfield-level support for POs and market actors did not emerge thus jeopardizing sustainability.3. The publicdemand-driven decentralized agricultural extension system that was welcomed by beneficiaries earned support for it to be sustained.The project experience showed that the bottom-up approach for extension planning enabled the institutions to introducedemand-driven extension planning region by region. While it took a long time to set up Farmers Information and Advice Center (FIAC)facilities and popularize them amongst farmers, local extension service stations at the Upazila level were welcomed by smallholdersaccording to a beneficiary survey at project closing. The MoA decided to expand the FIAC network, but ministries responsible forlivestock and fisheries had at project closing not allocated any resources to support a decentralized extension system throughFIACs or a similar approach for livestock and fisheries.The following lesson is emphasized byIEG:4. Projects featuring research and extension activities could benefit from a coordination mechanism to maximize benefits. According to the ICRNATP-II suffered from weak coordination between research andextension components (paragraph 69). There could have been better coordination among research and extension components and the PIUsto develop regular channels to share information from the research sector and provide feedback from the field and along the valuechain.
P149555 | Moldova - DPO2 | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest |  |  | The most important lesson in the ICR is the following (with some adaptation of language):(1)Development policy objectives that are broad in terms of thematic and sector coverage are likely to encounter implementation andcoordination difficulties, particularly in countries with weak administrative capacity.This is confirmed byexperience from these operations, where attempting to address several diverse policy areas at the same time stretchesimplementation capacity and complicates the monitoring of impact.IEG draws the followinglessons:Unless political economy dimensions are carefully considered at the design stage,achievement of a DPOs objectives is likely to be jeopardized. In thiscase, the timing of the operation was less than optimal, since implementation suffered frompolitical turmoilfollowing parliamentary elections. Also, more account should have been taken of the influence of powerful oligarchs over reformprograms, especially in the financial and agricultural sectors, and an analysis made of how this might havebeenmitigated.Sectors presenting especially difficult challenges may be more appropriatelyaddressed by separate, dedicated operations. Here the issues in the financial sector were of such magnitude and complexityas to affect Moldovas macroeconomic stability as well as general confidence in the economy. Under such circumstances,including financial sector reform as one of six distinct policy areas overstretched the countrys limited implementationcapacity. Still more importantly, the reforms that were attempted were sufficient in both number, depth and scope to go to theheart of the problems facing the sector.
P149599 | Power Grid Improvement Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099000102152217858/text/Lao0People0s0D00Improvement0Project.txt | http://documents.worldbank.org/curated/en/099000102152217858/pdf/Lao0People0s0D00Improvement0Project.pdf | IEG derives the following lessons drawn from the ICR:1. The Project illustrates the importance ofstructuring operations on the basis of sound and well-targeted technical design, supported by adequate institutional capacitybuilding. The design of the project was relatively straight-forward and well-contained, and supported by adequategovernance structures. The selected district had the highest level of distribution losses in the country, making it anobvious candidate for project selection. Though improvements could have been made in sector regulation, thiswould nothaveaffected the viability or progress of the operation. The experience gained from the project could subsequently bescaled up and replicated in other load areas with high losses.2. The long delay in setting baselines forsome key indicators was a reminder that good project preparation can sometimes take a long time. There can be atension between the need to deploy IDA resources quickly and the need to take the time to undertake the up-front work needed toprepare the project thoroughly. Key ME issues also need to be flagged to counterparts early during appraisal tofacilitate planned operations.3. Though it is tempting for multilateral financing institutions to introduceambitious financial covenants wth a view to improving the condition of large state-owned utilities, these can often bechallenging to implement in the course of a single investment operation. Sustained progress is most likely to happenin the context of an on-going and future involvement, allowing supportive policies sufficient time in which to evolve.
P149605 | Nuton Jibon Livelihood Improvement Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2021 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099042523135022884/text/P149605004a78805f0ae69066f65d85cea8.txt | http://documents.worldbank.org/curated/en/099042523135022884/pdf/P149605004a78805f0ae69066f65d85cea8.pdf | The ICR included eight lessons. The following three are emphasized with some adaptation of language:1. Theinclusion of climate resilience building practices can help mitigate the impacts of climate-induced events. The projectarea suffered from climate-induced events, which are expected to repeat and aggravate communities in the future. Future projectsneed to place a stronger emphasis on innovative and tested climate-smart and nutrition-smart agriculture practices andtechnologies. A climate and disaster risk assessment mustbe considered for all IGAs, and themandatory inclusion of riskmitigation and resilience building measures should be adopted. Beneficiaries can also benefit from trainings for strengtheningawareness ofclimate change, its impact on their livelihoods, and above all strategies (provided by the project and otherrelevant actors) to reduce the risks.2.Supporting non-farm enterprisescan enable beneficiaries toshift their household income away from insecure and low-paid wage employment towards greater self-employment, creating a pathwayout of poverty.The projects experience emphasized that beneficiaries managed to shift from wage employment,such as casual day labor in both agriculture and non-agriculture sectors, to self-employment, through non-farm enterprises andlivestock rearing, which constitutes an important pathway out of poverty. Household income did not only increase but was alsomade more robust.3.Developing and strengthening community institutions is key for empowerment of ruralwomen. A remarkably high share of women participated in project activities. The project mobilized ahigh share ofwomen beneficiaries into community groups. This was achieved by targeting both men and women in mobilization campaigns. Since menusually work outside while women stay at home for household chores, eventually men encouraged women to participate incommunity-level project activities. Poor and extreme poor community members were involved in planning, managing and implementingvillage-level activities and decision making. Savings kept by the community were used as internal lending funds among thebeneficiaries and as a safety net. The revolvingfund and loan provision of the project is the prime source for thebeneficiaries to obtain loans and initiate livelihood enterprises.
P149606 | ROAD SAFETY SUPPORT PROJECT | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Transport | RETF | IPF | 2015 | 2018 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/550731519146561753/text/Nepal-Road-Safety-Activity-under-on-RSDP-roads.txt | http://documents.worldbank.org/curated/en/550731519146561753/pdf/Nepal-Road-Safety-Activity-under-on-RSDP-roads.pdf | The ICR (pages 19-21) draws the following main lessons from the experience of implementing this project, with some modificationof language.(1) A simple designcan be useful for executing projects in countries with relatively weakcapacity.In this project, the design was simple and based on a proper assessment of the capacity oftheProjects stakeholders.(2) The implementation agencys capacity and ownership can be key tosuccessful operations. In the case of this project, the Department of Roads (DOR) and the Ministry of PhysicalInfrastructure and Transport (MOPIT) had prior experience in executing Bank-financedprojects and were familiar with theBanks requirements. This in conjunction with strong ownership of the implementing agency aided in completing the project andin completing the civil works on site.(3) For a road safety operation, soft components may be as important asthe hard components and both components may be required for sustaining the overall objective of improving road safety. Theexperience with this road safety project showed that investments in road safety operation can provideleverage to influenceand drive policy and regulatory reforms later.(4) Stand-alone road safety operations can havea chance ofsuccess in improving road safety compared with having a component or subcomponent focused onroad safety under aroadproject. Despite a relatively small investment, this project attracted the attention of the authorities in theimplementing agency and this was demonstrated by the commitment to project ownership within the governmentbodies.(5) A Road Safety Audit before project preparation can help in achieving positive results. Therecommendations of the audit in this project before project preparation helped the team to better align the project activities andhave a focused mitigation plan. However, atpreparation, arrangements could have been made for abetter MEframework.(6)The project timelines need to be realistic and allow time not only for completingproject activities but also allow time for evaluating the results of intervention. Thelimited time frame in thisproject left little time for a proper evaluation of results.
P149609 | CO First Programmatic Sustained Growth and Income Convergence DPL | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2017 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/929831546885397405/text/Colombia-Sust-Growth-and-Income-Convergence-DPL.txt | http://documents.worldbank.org/curated/en/929831546885397405/pdf/Colombia-Sust-Growth-and-Income-Convergence-DPL.pdf | The following lessons are taken from the ICR with some adaptation of language: The design and preparation ofthis DPO series benefitted from continuity with respect to Task Team Leaders and core team members, both with respect to knowledgeof the issues and the economy and in regard to relationships with country counterparts; The reform experience inColombia underlines the need for intensive dissemination and implementation to bring about changes in behavior when institutionalreform involves new laws or regulations. The use of the secured transactions reform to extend credit access is a case in point,where the initial use was primarily for financing of motor vehicles. More dissemination could have broadened itsuse IEG draws the following two lessons: Design of development policy operations canbenefit from international experience and research. In this case, expected financing of SMEs and other sub-prime borrowers throughissuing instruments such as bonds did not materialize since the risks associated with such instruments were perceived to be toohigh. Sufficient study of international experience would have illustrated the likelihood of such anoutcome. Political economy issues can often undermine reform objectives. Two examples were the difficultiesassociated with the attempted consolidation of the Committee for Competitiveness with the System for Science, Technology andInnovation, and the restructuring of the National Tax and Customs Administration, both of which undermined the achievement of thethird pillar of the program. Intensive consultation, dissemination of the advantages of the reforms, and ensuring that allparticipants support the reform are necessary to reduce the risks of non-achievement of objectives.
P149620 | Moz Agriculture and Natural Resources Landscape Management Project | Eastern and Southern Africa | Mozambique | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099121124181048220/text/P149620-ce3054a7-596f-4753-97d3-a8adf414646c.txt | https://documents.worldbank.org/curated/en/099121124181048220/pdf/P149620-ce3054a7-596f-4753-97d3-a8adf414646c.pdf | The ICR presented five lessons. Two of them that are likely to be widely applicable are presented below with edits. In addition,IEG notes an additional lesson illustrative of the shortcomings inthe project design.A network ofsmall emerging commercial farmers and small or medium agricultural enterprises can be potentially utilized to deliver support tosmallholders to enable them to integrate into existing value chains. Although the performance of the model needs to beevaluated in depth, in this project, it was effective in delivering services to small-scale farmers, and the farmersorganizations found it to be an effective platform for interactions to obtain information necessary to improve productivity andgain access to markets for their surplus production.Although matching grant mechanisms are useful instruments forfinancing farmers purchase of equipment and other modern inputs, the incentive mechanisms built into a project to encouragefinancial institutions to provide credit to small-scale agricultural enterprises need to be carefully negotiated. In thisproject, only one financial institution provided support to small and emerging commercial farmers at the beginning of the project,at a subsidized interest rate of 5 percent. Most commercial banks did not participate in a co-financing mechanism because of theirperception of the risks associated with small-to-medium scale farming despite the establishment in this project of a partial riskguarantee mechanism. All the projects financial resources allocated to the partial risk guarantee were used insupporting only 5 SMEs. The small-scale emerging commercial farmers also found the usual interest rates offered by commercialbanks (over 27 percent) to be too high to be viable for their enterprises. The lesson is that a solution needs to be found toreduce the costs and risks for commercial banks of lending to remote small-scale borrowers, negotiate the solution with the banksduring project appraisal, and incorporate the solution in the projects design.In addition to the above, IEG alsonotes that without objectives that sufficiently engage with the expected transformation expected in householdstransitioning into more commercial opportunities, the tracking of success becomes too heavily aligned to participation.Productivity improvement is a useful proxy for farmers utilizing project support, but it does not effectively illustrate the degreeto which theyve increased household incomes or transitioned to an amplified value chain model.
P149629 | Enhancing Spatial Data for Flood Risk Management Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2014 | 2017 | 2018 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/248471505920735742/text/ICRR-Disclosable-P149629-09-20-2017-1505920727451.txt | http://documents.worldbank.org/curated/en/248471505920735742/pdf/ICRR-Disclosable-P149629-09-20-2017-1505920727451.pdf | The ICR draws the following main lessons fromimplementing this project, with some adaptation oflanguage.(1) A careful assessment ofindicators and targets forproject activities isimportant for effective monitoring. This project included indicators that were dependent on existence of tools underdevelopment in other projects, or would require external actions beyond the capacity of implementing and beneficiary institutions.This contributed to cancellation of project activities and indicators and the projects poor performance.(2)Project designneeds to adequately address the capacity building needs of the relevant government agencies. Theactivities in thisproject onlyaddressed the capacity building needs of the primary implementing agency -the NationalDirectorate for Water Resources Management (DNGRH) and did notaddress the capacity needs of theNational Centerfor Cartography and Remote Sensing (CENACARTA) -the main institution for thestorage of Lidar data. As implementationprogressed, it was observed thatlack of technical capacity within CENACARTA was a constraint in providing remote sensing datafor all potential users.This necessitated capacity building activities for CENACARTA during implementation.IEG addsthefollowing lesson: The deletion of a core PDO indicator can make the PDO redundant and hence change the PDO. In thecase of this project, deletion ofthecore indicator for the PDOjust months before closure without a replacementeffectively changed the PDO which should have received Board approval.
P149670 | Central America & Caribbean Catastrophe Risk Insurance Project | Latin America and Caribbean | Latin America and Caribbean |  |  | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099083201312349957/text/P14967004a2eeb0e0094e60e8eb3e5ba311.txt | http://documents.worldbank.org/curated/en/099083201312349957/pdf/P14967004a2eeb0e0094e60e8eb3e5ba311.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Early consultations with decision makers and provision of technical assistance are useful for ensuringownership of complex regional initiatives. These factors helped in drawing new Central American countries to the CCRIF SPCin this project.2. While donor commitment and financing are essential in establishing a facility, it would help tohave a follow-on project and an exit strategy. Donor support for the initial operating expenses and claims payout made itpossible for the CCRIF SPC to build its own reserves at an accelerated pace. While the results in Central America weresatisfactory, there continued to be a need for donor financing. The ICR (paragraph 85) noted that there is an ongoing second CCRIFSPC project and that this project will help in developing an exit strategy.3. The design needs to take intoaccount country-specific features to avoid delays during implementation. In this project, the Bank and the CCRIF SPCassumed that the process for cultivating CARICOM countries could be replicated for COSEFIN countries. However, Caribbean countrieslargely follow the common law by precedent, while the civil law system in Central American is based on rules and ordinances. Thefailure to take this into account at design led to project delays as the CCRIF SPC had to adjust to the demands of the COSEFINcountries.
P149697 | Transit Corridor Improvement Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099052623181026407/text/P1496970e607530cc0a36202ba000c4032e.txt | http://documents.worldbank.org/curated/en/099052623181026407/pdf/P1496970e607530cc0a36202ba000c4032e.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. An assessment of the technical capacity of domestic contractors could help in facilitatingprocurement. In this project, all the local contractors awarded the major civil engineering worksperformed well despite not having international joint venture partners. The successful engagement with domestic contractors,besides helping to reduce costs, also strengthened the sector by providing the experience needed for the firms to competecompetitively abroad.2. An agreement with stakeholders on project activities,objectives and technicalscope would help prevent implementation delays. In this project, the delays associated with the establishment of theTraffic and Road Safety Coordination Center proved to be challenging because of the differing priorities of the multiple governmentstakeholders.3. Not having targets or a methodology before entrycould hinder monitoring project activities.The project design did not have targets for some indicators or at least an explicitmethodology for monitoring someindicators in the results framework, with the intention being that targets would be set during implementation based on laterproject-supported surveys. This approach introduced a risk that the results outcomes would be inadequately monitoredshouldone or more planned surveys be poorly implemented or not done.
P149714 | Niger River Basin Management Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | RETF | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/470581608754142992/text/Western-Africa-Niger-River-Basin-Management-Project.txt | http://documents.worldbank.org/curated/en/470581608754142992/pdf/Western-Africa-Niger-River-Basin-Management-Project.pdf | IEG derives the following lessons drawn from the ICR:1. An autonomous financial mechanism for aRiver Basin Organization (RBO) has a better chance of being approved if all Member States perceive tangiblebenefits: The case of the hydropower levy and the concerns expressed by some states (Guinea and Nigeria) about thepotential for negative impacts on the business environment and the cost of electricity illustrates that the likelihood ofendorsement by member states is dependent upon their perceived assessment of relative costs and benefits. The likelihood ofmember states providing regular financing contributions is higher if they perceive that being part of an RBO provides themwith tangible benefits, such as being able to mobilize financing for investments; the fact that an RBO merely carries out aregulatory function may not be enough,2. Transboundary programs need to be cognizant and realistic about thepolitical economy of the transboundary space: Such programs face challenges in achieving political buy-in, sinceseveral countries need to collaborate. This calls for long-term engagement to achieve results. Project durations also need tobe commensurate with the basin structure and complexity of the project which could mean being open to extensions of closingdate. This also calls for a clear and coherent World Bank strategy, aimed at building trust with the client and facilitatingproject implementation.3. It is essential for RBOs to have strong organizational and institutional capacity,to be able to carry out their mandate in a timely and effective manner: A strong Project Management and CoordinationUnit, with well-trained staff especially one that is familiar with implementation of World Bank projects - is key for thesuccess of such Bank-funded operations. Regional programs involving RBOs must include a strong component on continuous learning andcapacity building, capitalizing on previous training programs. Evidence-based, multicriteria decision-making needs to becomeembedded in the modus operandi of NBOs, based on the decision-making experience around Fomi.4. A clear andcoherent World Bank Group engagement strategy with an RBO builds trust with clients, which facilitates successful projectimplementation: Towards this end, it is essential for Bank management to give a clear signal of support, once it isengaged in the project, and to provide a consistent set of priorities to Bank teams working with the same RBO, and to ensure promptand transparent communication in case changes are necessary. The engagement of Bank management is essential also to ensurethat governance challenges are properly addressed.
P149718 | Kenya Statistics Program for Results | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | PforR | 2016 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099910002212215578/text/Kenya000Kenya000Program0for0Results.txt | http://documents.worldbank.org/curated/en/099910002212215578/pdf/Kenya000Kenya000Program0for0Results.pdf | (1) A PforR instrument can be a game-changer in a problematic country context if it strategically supports the nationalgovernments policy priorities. The conditions for the Statistics PforR were challenging from the outset: publicsector governance was weak, most official statistics were outdated or unusable, the last poverty measurements were a decade old,and the recently closed statistical capacity-building project with similar objectives did not achieve them. The PforRopportunistically supported the national governments policy priorities [refer to Vision 2030, Second and Third Medium TermPlans, and the KNBSs Strategic Plan 2013-2017] by focusing selectively on a subset of the governments own programwith a clear results orientation. The PforR objective was to strengthen the capacity of the KNBS to generate betterand more accessible data to inform policymaking. The government recognized the need for adequate statistics and demonstrated itscommitment by pledging over 60% of the total program costs in a multi-year budget plan. While KNBS had good technical capacity,there were areas where it needed support. The task team collaborated with the IMF and SIDA to ensure a regular flow of technicalhelp to the KNBS to achieve DLI targets on time. By addressing strategic data gaps, improving data quality, and improvingdissemination practices, the PforR facilitated Kenyas access to international capital markets and reduced borrowingcosts. Kenya had just attained a lower-middle-income status and needed financing.(2)Twinning arrangementswith development partners can be critical for the success of a statistics PforR with many technically complex DLIs. At theoutset, KNBSs data was outdated, of poor quality, and had many gaps. While the KNBS had substantial technical staffresources, they were inadequate to meet the DLI targets. Capacity building was not a PforR component. The task team twinned withthe IMF and Statistics Sweden (SIDA), which was already assisting the KNBS. This made it possible for the three partners to findthe best way to jointly support KNBS and create leverage with the US$3 million TA provided by SIDA to help the realization of theDLIs under the Bank-supported program. The integration of capacity building ensured KNBS staff had the requisite skills and thelatest software to produce high-quality and timely outputs. For microeconomic survey activities and poverty indicators, the WorldBank assisted the KNBS. Through the East AFRITAC (Regional Technical Assistance Center), the IMF helped KNBS rebase CPI andmacroeconomic statistics. The IMF advised and provided TA on critical SDDS related aspects of the program. Statistics Swedenassisted with producing the updated business register and the rebased PPI. It also assigned two long-term resident statisticaladvisors in the KNBS.
P149724 | Lebanon Municipal Services Emergency Project | Middle East and North Africa | Lebanon | IBRD | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2014 | 2018 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/544381564092955893/text/Lebanon-LB-Municipal-Services-Emergency-Project.txt | http://documents.worldbank.org/curated/en/544381564092955893/pdf/Lebanon-LB-Municipal-Services-Emergency-Project.pdf | The ICR provided a series of lessons. The most important are the following:For a successful intervention foreffective emergency response, it is critical to intervene at the local/municipal levels. Local authorities are on thefrontlines of emergency responses. The local authorities play the main role in managing the increased demand for services, jobs andthe rise of social tensions due to the rapid influx of refugees. The project worked closely with local governments through CDR inidentifying and responding to local needs. Through this process, the project also built the capacity of the local governments inestablishing an inclusive decision-making mechanism, as well as in implementing community-level sub-projects.Aconsultative decision making system and framework approach, rather than relying on a centralized plan of pre-defined solutions, maywork well in implementing local solutions in emergency situations. The combination of a consultative decision-makingsystem and a framework approach adopted by the project was critical in identifying the needs of communities and in responding tothese needs in a rapidly changing context. The decentralized, participatory approach also resulted in high ownership andsatisfaction from beneficiaries, though sufficient time needed to be allocated for an effective consultative process. Defining thescope of the project clearly and allowing for flexibility facilitated the successful achievement of results.Bothquick wins and mid-/long-term improvements are necessary to restore trust and the social contract. In an emergencycontext, where there is mounting pressure and perceived competition over resources and services, quick, visible improvementsin municipal services were critical for building trust in local authorities. On the other hand, mid-size, developmental solutions,though taking longer time to prepare, provided larger, more lasting impacts. The two-pronged approach adopted by the project was ameaningful model, as evidenced by high beneficiary satisfaction.But it is important these intentions and approaches aresuitably captured in the PDO for the project.
P149747 | Morocco Inclusive Green Growth DPL2 | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2016 | 2017 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | Several lessons highlighted in the ICR are important andare consistent with thosein IEGs own recent assessmentof environmental DPLs:1. Government ownership at all levels is essential to ensure effective implementationof policy reforms for green growth. As the ICR (para. 122, pg. 30) stated, this is demonstrated by the DPL thatincluded the concerted effort of several agencies including the MEF, MAGG, MAPM, MEMDD (Ministry of Energy, Mines, and SustainableDevelopment) as well as national agencies, such as the Moroccan Agency for Tourism Development; National Aquaculture DevelopmentAgency (ANDA), and Oum Er Rbia River Basin Agency (ABHOER).2. In-depth knowledge of the country and sectorsis a key factor for ensuring adequate design of an operation and its successful implementation.The ICR (para. 124,pg. 30) adds in this regard that the ongoing dialogue that the World Bank already had in Morocco, coupled with the extensiveupstream and sectoral analytical work have contributed towards adequate design in terms of the selection of prior actions; outcomeindicators and targets....; and for issues that need attention from high-level decision makers, especially in finance and planningministries.3. Supporting the DPL with Advisory Services and Analytics (ASA) and investment project financingcontributes to successful implementation of policy and sectoral reforms and achievement of outcomes. The ICR (para. 125,pp. 30-31) observes, more specifically, that this DPL series has been well supported directly and indirectly...through ASAand investments, including grants, for example, a Multi-donor Trust Fund (MDTF) grant for ASA and support dialogue; MDTF support tothe ABHOER; GEF grant for integrated coastal zone management (ICZM); Partnership for Market Readiness (PMR) ASA on energyefficiency in buildings; and a grant from the EU Climate Change MDTF to support technical assistance activities onagro-meteorology, green taxes, groundwater governance component, and ICZM.To these can be added:4.Effective DPLsinvolvingactions in various sectors require a strong coordinating mechanism as well as adequate ownershipof the policy reforms and actions by the participating sector institutions. This too was an important lesson drawn fromIEGs recent review of environmental DPLs which clearly applies to this programmatic series as well.
P149750 | Second Programmatic State Owned Enterprises Reform DPL | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR draws a number of lessons, of which two are of particular interest and restated asfollows:Structural SOE reforms require a long period of engagement and implementation before achievingexpected outcomes. In the case of Serbia, the ICR reports that it took five years from the first identification to completionin 2016 and yet some of the impact of the new laws passed are yet to be realized. Maintaining the policy dialogue and the provisionof critical support over the medium term is essential for realizing the full impact of the series.Secondly,when a DPL series has not completely addressed challenges related to structural SOEs reforms, continuing the series with otherprogrammatic operations with follow-up actions or technical assistance may be appropriate. Serbia has a relatively large SOE sectorwith large fiscal costs that could potentially affect real sector growth. In this case, the series tackled short term reformswithout sufficient time and attention to achieving longer term results. The management of the fiscal costs of SOEs still requiressupport. After implementation of the series, Serbias SOE governance still shows significant gaps against OECD bestpractices, with room to improve SOE governance frameworks across all dimensions (IMF, 2019:58). There is room for moretransparency, assessment, and reporting to improve the governance and performance of SOEs, and the Bank is continuing to supportSOE reforms with a follow-on DPL series.
P149768 | Bosnia and Herzegovina: Public Finances DPL | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/901791561580087130/text/Bosnia-and-Herzegovina-Public-Finances-DPL.txt | http://documents.worldbank.org/curated/en/901791561580087130/pdf/Bosnia-and-Herzegovina-Public-Finances-DPL.pdf | The following lessons are drawn from the ICR and edited:Technical assistance can have asignificant impact on the quality ofan operation. Where implementation capacity ina country is low,focused technical assistance can provide that capacity and, working closely with government entities, build local ownership.ThePFDPL implemented technical assistance that was working directly with the government authorities, helping them engage inthe consideration ofappropriate policyand institutional changes.Political context isimportant in choosingbetween a stand-alone and programmatic approach. Teams need to understand the politicalcontext and the dynamics between local entities in deciding on the approach: is the context stable, or is it likely to havedisagreement or conflict? The stand-alone model was suitable for the complex BiH context with two entities in BiH (FBiH andRS) and the BiH institutionsin one federation. It allowed a short-to medium-term focus on consensus issues that mighthave deteriorated over a longer period of time.Single-tranche reforms should have effectivefollow-up. When contemplating a single-tranche development policy operation, teams may need a follow-up strategy forthe implementation of legal and regulatory changes introduced as prior actions under the operation. The stand-alone DPL inBiH introduced well-targeted interventions supported by technical assistance, and included a medium-term framework that providedthe longer-term perspective needed to undertake affordable annual budgeting.
P149770 | Samoa First Fiscal & Economic Reform Operation | East Asia and Pacific | Samoa | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/278471578926216505/text/Samoa-First-Fiscal-Economic-Reform-Operation.txt | http://documents.worldbank.org/curated/en/278471578926216505/pdf/Samoa-First-Fiscal-Economic-Reform-Operation.pdf | The ICR distills five lessons: the usefulness of using DPO engagement to elevate policy issues, the need to consider carefullywhether a DPO is the right instrument, the difficulty of aligning modalities and timelines of different Bank instruments, optionsfor timelier and more systematic follow-up of past actions, and the benefits of more regular consultation with the private sector.It also offers several suggestions to address some of the issues identified. This review concurs with these lessons andsuggestions, which are grounded in the experience of this operation.This review wishes to underscore theimportance of establishing a strong logical chain, in each support area, that links the Bank-supported policy actions to theexpected development outcomes, with the key underlying assumptions clearly identified. This helps to assess the adequacy of theactions for achieving the outcomes, as well as the risks that must be managed to ensure success.
P149776 | 2nd Fiscal Effectiveness and Growth DPL | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | This review concurs with the following key lessons presented in the ICR, (the lessons are summarized below, with some additionalaspects added): 1 . Successfuldevelopment policy financing requires sustained ownership of reforms and strong borrower leadership throughout preparation andimplementation of the policy agenda, which typically starts long before preparation of the operation or series and extends beyondits closing. In the case of this series, the risk of weakening political commitment was recognized from the start; and although theseries adopted numerous mitigating actions, that risk materialized, and mitigating actions could not preserve fully the achievementof results. demonstrating that the original risk rating of substantial was correct.2. A prior action (under a DPL) should not require a decision of Parliament. Instead, consultation andcollaboration with Parliament should be part of DPL preparation, through the provision of adequate information and inclusion of keyparliamentarians and advisors in capacity building programs. Resorting to government actions, such as emergency orders, as asubstitute for Parliamentary action and in the interest of achieving DPL results, contributes over the medium-term to underminingof good governance and the legitimacy of government institutions.3 . Availability oftechnical assistance and advisory activities as needed during design and implementation of a program can improve quality andbolster government commitment. The RAS program was critical for design and implementation of the FEG series. Because theseactivities were funded by the EU, the government could overcome its reluctance to accept technical assistance, and the policydiagnostics and advice provided by the RAS should have ongoing usefulness to future pro-reformgovernments.4 . Good local coordination between the implementing agency and theBanks Country Office is crucial for achieving DPL results. In this case, effective coordination between MoPF and the Bankwas key for the effective monitoring of progress, allowing the responsible authorities and Bank management to intervene effectivelyat key moments during reform implementation.
P149781 | Poland Growth and Resilience DPL2 | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Lessons are drawn from the ICR with some adaptation of language.Development Policy Lending (DPL) can helpmitigate global economic and financial shocks and protect vulnerable groups. The main benefit of the DPL was not thecost-efficiency of Bank financing at the time of crisis, but strengtheninglonger-term reforms for inclusive growth. The DPLseries was appropriate at the time as an important market signal after the financial sector crisis and to reinforce the credibilityofthe authorities commitment to reform; and to provide technical solutions for design and implementation of theirreforms. The DPLs created space for policy dialogue and enabled conducting innovative analytical and advisorywork.The DPL program responded well and in a timely manner to the Governments ownpriorities.. Facing a weak external environment, the government focused on adopting short- andmedium-term growth-supporting measures, while maintaining a fiscally prudent stance. To sustain the recovery, the authoritiesprioritized actions to strengthen public finances and financial sector oversight. These were followed by reforms aimed atbolstering the economys long-term competitiveness (such as enhancing labor market flexibility,raising participationrates, and improving the business environment especially through the promotionofinnovation.)The Bank focused its support in areas where it has a solid knowledgebase and which were strategic. The DPLs not only created space for policy dialogue but also enabled innovative analyticaland advisory work, including on a reimbursable basis. DPL engagement in a relatively high-income country must be based on astrong foundation of shared priorities, and high quality and cutting-edge analytic work (including just-in-time TA, impactevaluations, customized analytic notes). The DPLs played a key role in terms of the embedded knowledge transfer on how to tacklecomplex long-term structural priorities and restore fiscal buffers. An excellent example is the permanent expenditure rule,sophisticated and, at the same time, a relatively apolitical instrument to achieve and maintain fiscal prudence over the businesscycle and assure long-term sustainability of public finances.
P149781 | Poland Growth and Resilience DPL2 | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2019 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/340071559242287976/text/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.txt | http://documents.worldbank.org/curated/en/340071559242287976/pdf/Poland-Public-Finance-Resilience-and-Growth-Development-Policy-Loans.pdf | Lessons 8.2 The Independent Evaluation Group draws the following lessons\. â€¢ Development policy lending can help mitigate global economic and financial shocks and protect vulnerable groups in high-income countries when accompanied with timely, high-quality, and responsive technical assistance that supports the reforms. The series were appropriate to reinforce the credibility of the authorities' commitment to reform, while providing technical solutions for the reform program's design and implementation. The DPLs enabled dialogue on important reforms the government was undertaking based on its analytical and advisory work. â€¢ Where a high-income country is required to implement constitutional provisions, or agreed reforms with a regional body, providing support for the implementation of such reforms is likely to enhance the likelihood of success. In the case of Poland, policies limiting fiscal deficits and overall debt levels were required both by EU agreements and constitutional provisions. Though these policies were complex, the government committed to implementing them because of the importance of EU accession agenda to Poland's economy. However, policies not so required by the EU were more easily reversed, for example, the increase in the retirement age. â€¢ RAS are a promising tool for engaging governments in high-income countries when Bank Group staff demonstrate the capacity to produce timely and highquality analytical products in response to government requests. In the case of Poland, the government appreciated the quality and responsiveness of World Bank staff to their analytical needs. However, World Bank adjustment to the different business model could have been better managed. Staff had the (sometimes difficult) task of explaining to the government why the World Bank needed to charge high-income clients for services, while still requiring sole source procurement and retaining intellectual property rights. The World Bank and government are now working together to make RAS mutually beneficial and a new tool for engagement. â€¢ Coordinating with other partners in situations where the World Bank is not the largest stakeholder is important for successful implementation of reforms. In the case of Poland, the EC and the IMF are the dominant development partners providing more funds or guaranteed resources to the government. â€¢ Analyzing the political cost of implementing proposed reform measures is an important part of policy lending. Such an analysis would have been particularly useful in relation to the pension and labor market reforms these two series attempted to support. It is notable that Ministry of Finance staff requested such advice in the future to guide the implementation of new reforms.
P149831 | PERU SECOND DPL WITH A CAT DDO | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2015 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/218991556933212394/text/Peru-PE-CAT-DDO-II.txt | http://documents.worldbank.org/curated/en/218991556933212394/pdf/Peru-PE-CAT-DDO-II.pdf | The ICR identified four lessons and three are presented below thatmay be useful to other similar operations(with some paraphrasing): The impacts from El Nio Costero highlighted the need tointegrate risk reduction in the development and planning processes, particularly for entities at the sector and subnational levelsthat are tasked with managing vulnerable infrastructure. In the case ofPeru, strengthening the subnational governmentstechnical and financial capacity was critical to ensure that risk reduction criteria were integrated into investments and thatthere was local capacity to implement continuity plans followinga natural disaster. Thedesign of a rapid disbursing CAT DDO operation and pursuing policy reforms to promote a strong DRM program require asoundunderstanding of the institutions, challenges, and development priorities of the country. Good dialogue is paramount in shaping thedialogue with the country and helping define the metrics that would monitor progress within the three-year timeframe of theoperation. These metrics should tap into the governments ongoing efforts and programs. In the case of Peru, the dialogue andinclusion of the education, housing, and water sectors,ensured that reforms could be translated into concrete actions in riskreduction investments and interventions. Introducing new indicatorsrequire careful assessment of local capacity toevaluateits progress and may require additional support during implementation. The useof CAT DDOs may be an effective entry point to engage with key sectors to further advance the DRM agenda in a country and promoteinvestments in risk reduction. In the case of Peru, technical assistance activities in the education sector that covered seismicrisk assessment of school facilities resulted in the approval and adoption of the first National School Infrastructure Plan in2017, currently under implementation.
P149858 | Mexico Reducing Inequality of Educational Opportunity Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2015 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/952881588945255926/text/Mexico-MX-Reducing-Inequality-of-Educat-Opp.txt | http://documents.worldbank.org/curated/en/952881588945255926/pdf/Mexico-MX-Reducing-Inequality-of-Educat-Opp.pdf | The ICR (pp. 27-28) suggested several useful lessons,two of which are adapted here:Thenegative impact of high personnel turnover can be minimized through proactive measures. In this case, turnover of ECDpersonnel negatively impacted implementation and measurement of results; by contrast, SIIINAFE maintained information andapplication materials for qualified candidates for positions, allowing for quick response when staffdeparted.The inclusion of fluency inindigenous languages as a criterion for hiring projectimplementersincreases the likelihood that measures targeted to indigenous communities will translate into meaningfuloutcomes. In this case, the project shifted from listing language skills as an added benefit to a requirementfor selection and assignment of APIs, increasing the achieved outcomes of the API intervention.
P149872 | Energy Efficiency in Public Facilities Project (PRESEMEH) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2016 | 2024 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062724112090607/text/P149872-7cd2f755-2768-42ec-aeda-819d7c6c007b.txt | https://documents.worldbank.org/curated/en/099062724112090607/pdf/P149872-7cd2f755-2768-42ec-aeda-819d7c6c007b.pdf | The ICR (paras 97-101) provided five recommendations. Three of them are presented here withrephrasing.Considering the gaps in the level and quality of pre-project (baseline) energy services, it may help toadequately assess the actual success and relevance of EE subprojects in municipalities and public institutions facing poverty andvulnerability. The idea behind EE investments is that they can be repaid with energy savings from replacing inefficientequipment with efficient alternatives. However, a balance is needed between maximizing actual energy savings and the need forinfrastructure investments to ensure sustainability and minimum levels and quality of services. Throughout the projectsexecution, the implementing team noticed that there were several instances where energy services were lacking or did not complywith relevant national regulations (ICR, para 6, annex 5, page 48).An Energy Efficiency (EE) revolving fundmechanism may enhance the impact and sustainability of publicly financed EE projects, though it may demand considerable effort andtime. During implementation, this project observed that putting in place all elements to operationalize the new financialmodel of the revolving fund and gaining the trust of stakeholders took longer than expected, but investing in this effort wascritical as the budget constraints severely limit municipalities and health institutions capacity to allocate financialresources toward EE investments (ICR, para 70). The ICR (para 98) recommended that effective early communication to highlight theprojects benefits, such as energy savings and improved service quality, would be crucial to the planningprocess.Implementing a project across multiple municipalities and government levels is complex, though it maybring benefits. The project involved different institutions at different levels of government and in multiplemunicipalities, which inherently brought complexity to the projects implementation and resulted in a slow pace ofdisbursement in the early years of implementation (ICR, para 61 and footnote 49, page 22). Despite the challenges, the projectestablished the EE revolving fund that would work across the country beyond the projects timeframe and ensured paymentdiscipline by the beneficiaries (ICR, para 35). The ICR (para 99) recommended that designing and planning of EE operations should:(i) account for local capacities, resources, decision-making processes, and the political landscape; and (ii) leverage existingstructures and balance the trade-off between quick, large investments in fewer, larger municipalities and broader, inclusiveinvestments across many smaller municipalities.
P149884 | CF-EMERGENCY PUBLIC SERVICES RESPONSE PROJECT | Western and Central Africa | Central African Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2014 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/460311541086052944/text/Central-African-Republic-CF-Emergency-Public-Services-Resp-Proj.txt | http://documents.worldbank.org/curated/en/460311541086052944/pdf/Central-African-Republic-CF-Emergency-Public-Services-Resp-Proj.pdf | Lessons adapted from the ICR (pp. 30-31) include:Institution building in fragile environments isunlikely to be sustained in the absence of a clear exit strategy. While, in this case, outsourcing was an effectivetransition strategy, there was insufficient attention to transfer of capacity away from in-house assistance and toward independentaction by national authorities (see Section 7).Rebuilding of institutions in fragile contexts takestime. One project lifetime is rarely enough. While this lesson applies across the board, it is particularly importantfor revenue mobilization, due to risks of fiscal imbalance between low/volatile revenues and growingexpenditures.In fragile and conflict contexts, taking informed risks can be preferable todisengagement. In this case, although the security situation remained unpredictable while the project was being prepared, atransition road map and United Nations security-building interventions were underway. With these prerequisites, the Bank tookthe risk of engaging in fast preparation of an emergency program on public administrationrebuilding.The Bank plays a key convening role in ensuring donor coordination under fragile,emergency contexts. In this case, Bank collaboration with UNDP provided essential sequencing of activities that enabled rapid rollout.
P149886 | Solomon Islands Recovery Financing Development Policy Operation | East Asia and Pacific | Solomon Islands | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/913051522940133258/text/Solomon-Islands-Solomon-Islands-Recovery-DPO.txt | http://documents.worldbank.org/curated/en/913051522940133258/pdf/Solomon-Islands-Solomon-Islands-Recovery-DPO.pdf | The ICR didnt propose specific lessons learnt from this operation but discussed findings related to the challenge ofpreparing operations in the context of a recent natural disaster andin small states with limited capacity.But theICR summarized key lessons from other programmatic series of DPOs that informed the design of this operation such as the importanceof: (i) integrating budget support within an aid package that includes evidence-based policy dialogue, analytical work, TA andcapacity building activities, (ii) establishing close working level relationship with key government counterparts to ensure ongoingimplementation, (iii) proposing a modest reform agenda of uncomplicated and politically feasible reforms for gradual reforms tocreate momentum for future change, (iv) effective coordination among donors in small states with limited capacity and (v)complementing policy actions with TA both for design and implementation of policy actions.A lesson that IEG addsis,the importance of defining relevant intermediary outcome measures to enable achievement of reform targets at projectclosing. In the case of this operation, the full impact of reforms concerning land and extractive industries will only be visibleover time.
P149888 | Second Economic Reform Development Policy Operation | East Asia and Pacific | Kiribati | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | This review restates two of the lessons drawn in the ICR and adds two more:1. The Bank can improve policy performanceparticularly in small states with thin capacity. The Kiribati DPOs provide an example of how the Bank can deploy itseconomies of scale in knowledge to assist small countries with a small civil service that is limited in its capacity todevelop policies in some areas.2. Bank project-level engagements can be springboards for policy reform. This was the caseof the telecommunications sector, where the Bank leveraged its project-level engagement to support the sector policyreforms.3. An unstable revenue source, such as fishing licenses, can derail macroeconomic policy. During the decade priorto the program, volatile fishing fees and weak tax revenues resulted in a sharp decline (ICR para 3) in per-capita RERF assets andincreased non-concessional debt. During program implementation increased fishing revenues allowed for some recovery of thoseassets, but also encouraged a pace of spending increases that does not look sustainable over the long term.4. Whereobjectives are too broad, narrow outcome indicators will impede adequate ME, This was the case with the third objective(expand private sector opportunities), which should either have been formulated more specifically (e.g., improve telecommunicationservices) or, alternatively, should have been underpinned by a broader set of actions aimed at addressing the key conditions thatinhibit private sector development.
P149895 | Nicaragua Catastrophe Risk Insurance Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099225105232240341/text/P149895016e70b0a70a1f903e2c5e136407.txt | http://documents.worldbank.org/curated/en/099225105232240341/pdf/P149895016e70b0a70a1f903e2c5e136407.pdf | The reviewdraws the following main lessons of implementing this project, with some adaptation oflanguage.1. Catastrophe multi-risk pooling at the regional level can be a cost-efficient solution to enablecountries to access quick liquidity following a disaster event. Insurance mobilizes additional capital from outside thecountry and contributes to the overall reduction of the gap between a governments contingent liability to catastrophic eventsand the amount of readily available resources that can be mobilized. The lesson from this project is that effectively transferringpart of their disaster risk to capital and reinsurance market can help in solving a significant portion of the countriesimmediate liquidity needs in the aftermath of a disaster.2. Capacity building to countries is key to continueaccess to risk insurance and develop own financial protection strategies. Knowledge on exposure stemming from anunderstanding or risk profiles presented by the CCRIFSPC aided theNicaragua in making other risk-based decisions. Thecapacity building activities provided under this project helped Nicaragua in taking essential steps to incorporate disaster riskmanagement and climate adaptation in its urban and sector development policies.3.Tailored capacitybuilding and analytical supportby the Bankcan help in facilitating country participation in risk-poolinginsurance. Honduras decision to withdrawearly in the implementation in this project was rooted on institutionalbarriers, including inadequateunderstanding of the products, and hesitation to use IDA resources for premiumpayment.Since then, the disaster risk financing agenda in Honduras hadevolved, and Honduras has developed and adopted adisaster risk financing operational plan(2021). The ICR notes that this plan is framing Honduras current engagement withthe CCRIF SPC.The IEG draws the following lesson from this project.Use of national and regional IDAresources can help countries test and access new insurance instruments. Throughthis project, which had funding fromnational and regional IDA sources, Nicaragua was able to obtain insurance for disasters associated with tropical cyclones,earthquakes and excessive rainfall at lower premiums, due to its participation in a regional insurance pool, rather than obtaininginsurance individually.
P149913 | Third Public Sector Modernization Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest |  |  | The ICR offers some insightful lessons on project design. Key specific lessons include: Ideally, Bank financingfor information systems should only be committed when the authorities have approved the strategy, defined the specifications forthe information system needed to support the strategy, and agreed on the procurement and implementation of the system. This allowsimplementation to start immediately following project effectiveness. Results frameworks for institutional reforms shouldinclude milestones for the implementation steps needed to achieve the intended results. The results framework should show how theproposed activities will lead to expected results/outcomes. Dated milestones can help focus attention and instill a sense ofurgency in decision-making. Information on the implementation steps can facilitate dialogue with stakeholders to ensure that theyhave the same understanding of the implementation progress, challenges, and impacts on activities and expectedoutcomes.The ICRR offers the following additional lesson: PDO indicators should measure all aspectsof the stated result. Especially when the PDO is to improve access to services, the results framework may need multiple indicatorsto capture the services targeted with improved access. Effective use of ISRs is crucial for reporting project challengesand communicating the impact of delays on achieving project objectives. Low ratings on progress toward achievement of PDO andoverall implementation progress should be reported when critical components are not making real progress. Candid and accuratereporting can prompt stakeholders to take necessary actions and prioritize efforts towards overcoming obstacles.
P149963 | Tonga - Second Economic Reform Support Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons are from theICR (p 26-77):Sufficient time should be allowed forreforms to be introduced when governments have a low institutional capacity.A medium-term perspective with athree or four-yeartimeframe would ensure thatsufficient preparatory work can beundertaken.A diagnostic ofgovernment implementationcapacity is essential, together withan assessment of technical assistance necessary to provide support, wheneverlow capacity is identified.Consideration of these aspects could then determine the timing and sequencing of reforms. Reforms should be prioritized andsequenced to reflect the stage of knowledge and capacity. In addition, some attention to risks posed by those who stood to gain orlose from reforms could help in managing risks of delayed implementation.Donor coordinationiscritical to the optimum allocation of TA support to the government andalso helps with the monitoring andsupervision of the operation.Joint missions alsohelp alleviate some of the burden on governmentcapacity.Identification of a series of potential reforms in the joint budget support matrix canfacilitate the choice of actions to use in adjusting the program. However, these changes should not undermine the logicallink between actions and targeted results. Care should be taken to ensure any changes in prior actions and triggers still follow alogical sequence which can be attributed to achieved outcomes.Strong government commitment to andownershipof reforms ensurescontinuedprogress even inin a low capacity context,characterized by frequent staff turnover. This also highlights the importance of civil service reform to help mitigate therisks arising from frequent staff turnover. The inclusive growth series in Tonga contains measures to strengthen remuneration inthe civil service, which could facilitate staff retention, but, more direct and targeted civil service technical assistance andreform may also be needed. In this regard, it will be important to consult and engage the key service sectors to ensure servicedelivery is not compromised in the process. Engaging these sectors in the Joint Budget Support Committeewill also helppromote their ownership.
P149965 | Third Northern Uganda Social Action Fund (NUSAF 3) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099631504262231669/text/P14996501d9e4c0810b434056ed2a16c5b3.txt | http://documents.worldbank.org/curated/en/099631504262231669/pdf/P14996501d9e4c0810b434056ed2a16c5b3.pdf | Lessons drawn from the ICR (pages 29-30), adapted by IEG: The identification of a clear trigger mechanism fordisaster-relief financial disbursements, agreedupon in advance, can ensure rapid response and flow of funds to beneficiariesonce a shock occurs. In the case of this project, the overall strategy was in place, with readily available financing anddisbursement mechanisms, in addition to the identification of independent data sources such as satellite-based observations ofground vegetation and food security indices that allowed for rapid and transparent targeting of needyparticipants. Community-level revolving funds can be an effective intervention to ensure sustainability oflivelihoodsonce project support ends. In the case of this project, the village revolving funds provided continued access tofinance and sustained development of community institutions. Operations and maintenance of community assets are morelikely to be sustained by taking into account the constraints of local communities.In the case of this project, despitestrong ownership by communities, robust operation and maintenance plans with intensive follow-up by the project team were needed,including understanding the constraints in leadership, financial management, workload, and other factors faced by those localcommunities to follow through on maintenance plans.
P149969 | Volta River Basin Strategic Action Programme Implementation | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | GEF | IPF | 2015 | 2020 | 2020 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/131751593460268099/text/Western-Africa-Volta-Basin-SAP-Implementation.txt | http://documents.worldbank.org/curated/en/131751593460268099/pdf/Western-Africa-Volta-Basin-SAP-Implementation.pdf | The ICR (p. 32-35) included several lessons learned which were adapted by IEG: The preparation of complexprojects involving multiple countries needs to be given adequate time to identify project sites, design and implement feasibilitystudies, and mobilize the required technical and financial resources. In this project, the VBA lacked capacity andexperience for implementing a Bank project, due to the lack of ME, and social and environmental safeguard specialists withinthe agency. Also, the budget to recruit an environmental specialist and an ME specialist was limited. All these shortcomingsresulted in implementation delays and the cancellation of the implementation of activities under component3. Results are more likely to be achieved by setting tangible milestones within a realistic implementation timeperiod that allows for capacity development as well as complex collaborations and processes to reach consensus. For thisproject, the four year implementation period was ambitious and resulted in the cancellation of severalactivities. Successful project implementation relies on having the right mix of expertise in the Bank team,especially when the counterpart lacks capacity and requires intensive support. Also, effective capacity-building depends onTTL continuity and adequate transition arrangements when changes. In this project the Bank team did not have aforestry and irrigation specialist, which resulted in delays in providing support and no objections for Terms ofReference.
P149971 | Somalia Capacity Injection | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099020824094078974/text/P14997119712a20bf1b17710b234a0e85ec.txt | http://documents.worldbank.org/curated/en/099020824094078974/pdf/P14997119712a20bf1b17710b234a0e85ec.pdf | Front-load tough reform areas to build momentum. At appraisal, the project envisaged the capacity to design andthen implement both PG and pension policy within the lifetime of the project, which proved unrealistic. As one of theICR lessons rightly underlines, such long-term, and inherently difficult reforms face multiple veto players, opposed coalitions,and entrenched interests set against change. In the presence of government commitment to reform, they should be introduced at thevery early stages of any reform drive. This will convince reform beneficiaries (who, in the case of pension reform, are many butdispersed and hardly speak as a pressure or interest group) that the developmental impact of the reform will be positive and thusenlarge the pro-change constituency. The same lesson applies to staffing core Government: the RF envisaged gradual hiring of staffthrough the CIM, and this proved unrealistic. IEG concurs with the ICR that frontloading such hiring under conducive budgetaryconditions would have allowed for other reform priorities to follow.By the same token, and given the country context, itwould have been important to consider a focus on merit-based recruitment in the civil service and focus on a system that goesbeyond dividing civil service jobs according to clan and minority group status, instead of emphasizing pay and pensionpolicyaspects.Consider the administrative implications of duplicating tasks in a federal system. The ICRrightly draws attention to PCU cost. The setup of two PCUs in FGS and PSS reduced efficiency and run-up costs to a disproportionateextent, not allowing for a cost reduction after the fourth restructuring reduced the project scope. In federal systems, it isimperative to rely on one PCU for both fiscal and administrative reasons, and it is best to incorporate this into project designfrom the outset. The ICR rightly emphasizes the need for additional resource commitment to FCV states duringimplementation. The project led to substantial gains in development pertaining to institutional capacity building, and oneof the main reasons was the devotion of substantial WB resources to supervision and oversight. This is a precondition for successin FCV contexts where instability is endemic and a light-touch approach unlikely to work. Future FCV operations could well drawinspiration from the hiring and utilization of country experts to assist implementation.
P149991 | First Programmatic Inclusive Growth Development Policy Operation | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/390491586812684284/text/Georgia-Inclusive-Growth-DPO.txt | http://documents.worldbank.org/curated/en/390491586812684284/pdf/Georgia-Inclusive-Growth-DPO.pdf | IEG takes the following lessons from the ICR, with some modification of language: Even if aprogram goes off track because of adverse fiscal developments, it is important to continue a dialogue with the government so thatif the fiscal issue is solved, the program can continue. In the case of Georgia, the World Bank continued to have dialogue with thegovernment, with the result that even though the third operation was canceled, most of the triggers were met. Resultsindicators should be directed at outcomes rather than inputs. In the case of Georgia, a number of indicators measured inputs, whichhampered assessment of the overall impact of the program.IEG offers the following additionallessons: It is important to distinguish between development objectives what the program istrying to achieve, and the pillars how the objectives will be achieved. In the case of the Georgia DPO series these areconflated, which makes the impact of the program and the clarity of the results chain difficult to assess. Politicalresistance can be overcome by extensive outreach and simplification of processes. In the case of Georgia, making budget processeseasier to navigate overcame the resistance of local entities to the reforms, as did outreach. Eliminating an operation ina series if prior firm undertakings the government with respect to fiscal discipline are broken sends a clear signal to countriesthat these commitments are important. In the case of Georgia, the delay in processing DPO-2 and the cancellation of DPO-3 wereappropriate responses to the lack of fiscal discipline that led to the deterioration of the macroeconomicsituation.
P149998 | Private Sector Competitiveness DPO1 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/667891578692263384/text/Georgia-Private-Sector-Competitiveness-DPO1.txt | http://documents.worldbank.org/curated/en/667891578692263384/pdf/Georgia-Private-Sector-Competitiveness-DPO1.pdf | A DPO series that is well supported by the country dialogue and well coordinated with development partner programs islikely to be able to correctly gauge the governments willingness to pursue long-range, high-impact reforms. Becausethe PSC series had the right mix of reforms and was correctly timed for government commitment and capacity, it was able to achievea broad range of high-impact reforms.Banking reform is likely to be more successful when thebanking sector is relatively sound.In Georgia, deposit insurance that requires regular contributions from banks mayhave been more difficult to introduce into a banking system in crisis; in Georgia, banks were solvent and financially solid.
P150008 | Land Bank Financial Intermediation Project | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099051523155022383/text/P15000806a6eaf0dc0944f033f1ce719cd1.txt | http://documents.worldbank.org/curated/en/099051523155022383/pdf/P15000806a6eaf0dc0944f033f1ce719cd1.pdf | The following are lessons learned from the ICR (paragraphs 62 to 67) with some paraphrasing: Projectswith line of credits would benefit from having components that cover technical assistance and operating expenses to supportimplementation of new products offered by the credit line as well as the implementation of the project. In the case of theproject, no resources were allocated to support the implementation of Land Banks new strategy and products, although the WBoffered to include such funding in the project. This would have helped help with better implementation of the project. These fundswould have also supported the capacity building in the field of ESMS systems in the PFIs. For projects thatsupport DFIs, addressing the legal and institutional shortcomings associated with DFI supervision before project approval, can helpmitigating key risks during implementation. The project preparation team identified supervision weakness for Land Bank,however the project commenced before addressing these gaps. If the necessary measures were introduced such as, oversight ofnational DFIs by the National Treasurys financial sector policy division in the short term and in the medium-term the SouthAfrican Reserve Bank taking on the role of prudential supervision of these entities, the financial problems that the Land Bank hadencountered could have been diagnosed in advance. Replacing subsidized lending instruments with full costrecovery ones requires a through market analysis at project design to help assess the real demand for these productswithoutsubsidy and to include effective financing structures for other associated advisory services. In the case ofthe project, when the Land Bank decided to replace the subsidized lending product with the one on commercial terms, it facedchallenges in generating sufficient demand from financial intermediaries. The subsidized lending was indirectly financing the costof providing agricultural advisory and market access services via using a grant from the Department of Agriculture, Forestry andFisheries. However, it was not considered how these services would be provided if there was no subsidy. At appraisal a thoroughanalysis, which would assess the consequences of such change in the lending structure, could improve projectdesign. Design and implementation of credit lines focusing on specific sectors can be improved by involving TTLsfrom both the relevant sector as well as Finance, Competitiveness and Innovation GP. During the design stage, having aco-TTL from the Agriculture GP may have helped avoid some of the shortcomings that negatively impacted the project implementation.The ICR comments that a similar approach on the Borrowers side by involving the Department of Agriculture, Forestry andFisheries in the project implementation arrangements and benefitting from its guidance may also have helped address some of thechallenges the project faced in scaling up financing, particularly under the wholesale window.
P150009 | Tanzania Business Environment and Competitiveness for Jobs DPO | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/800941558366940221/text/Tanzania-TZ-Business-Env-Competitivenes-fr-Jobs.txt | http://documents.worldbank.org/curated/en/800941558366940221/pdf/Tanzania-TZ-Business-Env-Competitivenes-fr-Jobs.pdf | Lessons are drawn from the ICR with some adaptation of language.Implementationarrangements. Teams should attempt to agree on arrangements for implementation and implementation monitoring with thegovernment in advance, especially the central coordinating function, where the DPO-supported program aims to advance across-sectoral and cross-ministerial reform agenda. In Tanzania, such a role is conventionally played by the Ministry ofFinance, but administrative authority appearsto have been insufficient. This may have contributed to uncertaintiesregarding the absence of evidence of impact insome cases.In a country contextcharacterized by weak implementation and coordination capacity, rigorous selectivity in program design increases the chances ofsuccess.The team should emphasize simple designs and focus on fewer reforms when risks to program ownershipare high. Under such circumstances, it might be justifiable to limit future DPO series to just two operations to reduce therisk of back-loading. A simpler ME system with fewer indicators and clearly described responsibilities is animportant element of more selective program design.Consideration of the overall administrativeburden faced by a government can contribute to a more realistic assessment of government ownershipandcapacity.In designing DPOs, the temptation to be aspirational rather than realistic isbest avoided.In this case, the Authorities were faced with the need to implement fourparallel sector-specificDPOs, as well as shouldering the already onerous burden of coordinating multiple sources of external assistance.Astronger ex ante assessment of risks and eventual mitigation measures might have avoided many of the challenges theproject would face.
P150009 | Tanzania Business Environment and Competitiveness for Jobs DPO | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2022 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/099142306092213522/text/IDU07740978502d42046a40aaa100bc420a6a7d8.txt | http://documents.worldbank.org/curated/en/099142306092213522/pdf/IDU07740978502d42046a40aaa100bc420a6a7d8.pdf | 3. Lessons 3.1 This assessment offers the following lessons: 3.2 Informed risks: Although risk taking is a feature of PDOs that incorporate difficult reforms, these risks need to be informed. In Tanzania, the associated risks of the BEFJ DPOs were not clearly acknowledged or were downplayed. Future initiatives should include a more thorough and substantial discussion of ex ante risks and mitigating measures, and a more in-depth appreciation of the political economy that might arise from ongoing consultations with politicians to build strong ownership for Bank GroupÃ¢â‚¬â€œsupported reforms. The outcome of the program suggests that preparing DPO series with complicated reforms in the shadow of an upcoming election is ill- advised. Delaying such programs until a new government has taken office would ensure buy-in and ownership of the reforms that were included in the DPO. 3.3 Lessons from past experience: The BEFJ was a continuation of a long series of DPOs that provided budget support to Tanzania and contained business environmentÃ¢â‚¬â€œ related reforms. The achievements from the previous DPOs were disappointing. This series could have been better informed by a more in-depth and systematic review of experience with past DPOs and the lessons learned from them. 3.4 Complexity and coordination: In Tanzania, complex operations that span several ministries may strain the capacity of government counterparts. More focused operations that require less coordination could well be more effective. 3.5 Limitations to Doing Business indicators: More in-depth reform in certain areas will have a more significant impact in Tanzania. Using the Doing Business indicators to identify reforms resulted in some of the most important priorities being overlooked, as evidenced by the introduction of an electronic registry without accompanying changes in the legal and regulatory framework. Much more focused and in-depth analysis on which to base private sectorÃ¢â‚¬â€œoriented reforms could have been obtained through private sector assessments or investment climate analysis. 24
P150058 | Renovation of General Education Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099650001262233926/text/Vietnam000Reno0al0Education0Project.txt | http://documents.worldbank.org/curated/en/099650001262233926/pdf/Vietnam000Reno0al0Education0Project.pdf | Lessons drawn from the ICR (page 38) and adapted by IEG: The lack of an effective communications plan to gohand-in-hand with a complex reform process can undermine decision-making and collaboration among key stakeholders and lead todiminished outcomes.In the case of this project, there was no well-defined communication strategy nor was the staffing ofcritical communications specialists ensuredearly in the project period.Given the multiplicity of stakeholders in thecurriculum reform process, changes in policies and interference from divergent interests caused significant delays and disruptionsto project implementation. Ensuring that there is an institutional mechanism to promote coordination among variousstakeholders can mitigate risks such asunforeseen shifts in government policies.In the case of this project, thesignificant shift intextbook development and distribution policiesmeant adjustments inimplementation arrangements,new roles for private textbook publishers and authors, and new expectations for schools andparents, all of which leadto delays and disruptions toprojectimplementation.Also, APDOoutcome that is too far removed in the results chain from the direct project interventions can make measurement and attribution challenging. In the case of this project, therewere multiple key steps in the results chain (curriculum revision, textbook development, teacher training, learning assessmentsbased on the revised curriculum,establishment of learning and research centers) that made it less likely that improvedstudent learning outcomes would be realized (and measurable) during the tight project time frame. ME design thatdevelops a comprehensive assessment system as part project design but then relies on that system to measure project outcomes can beproblematic. In the case of this project, the learning assessment system was to be constructed as part of project activities butneeded to waitfor curriculum revisions and design of the new learning assessments.The baseline assessment was thereforeconducted late in the project period, and an endline assessment was never carried out.
P150060 | Vietnam Enhancing Teacher Education Program | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | PforR | 2016 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050823172528988/text/P15006007008840d60b6340c28a8edfc968.txt | http://documents.worldbank.org/curated/en/099050823172528988/pdf/P15006007008840d60b6340c28a8edfc968.pdf | The following lessons, slightly reworded by IEG, are a subset of the six relevant and insightful lessons presented in theICR: The PforR design can provide education sector authorities with an opportunity to think throughcomprehensive reform and alignment of the system. The project, together with the Bank-financed Renovation of GeneralEducation Project, aligned the new general education competency-based curriculum with the teacher and principal CPD andtraining.This involved: (i) moving from a centralized model to a continuing, online and blended model (combining in-personand online training); building LTTUs capacity to participate effectively in the reform; (iii) preparing training modules andrecording of participation and linking it to incentives; (iv) creating a cadre of core teachers and principal advisors to supportand coach teachers and principals on the job; and (v) linking financing to program results.The project has shown thatresults-based financing can indeed lead to enhanced accountability, systemic change, and a paradigm shift in service delivery andserves as a model, influencing the governmentsgradual transition to a performance-based state budgetallocation. The creation of communities of practices (COPs) linking LTTUs with schools, other stakeholders, andthe provincial and district levels can create an important feedback loop throughout the system, which is well poised to improveteacher training relevance and effectiveness. Teacher-learner communities and COPs provided LTTUs with importantlinks to teachers and principals at the school level and critical insights into the classroom, which served to enhance LTTUsin-service and pre-service teacher education.These connections were strengthened during project implementation andinstitutionalized.This feedback mechanism has helped both in-service and pre-service providers gain a better understanding ofthe challenges that teachers face in the classroom, which is essential for improving the quality of thesystem. Inclusion of specific gender and ethnic minority criteria for participation can enhance equality ofaccess to Program benefits. The project focused specifically on the participation of women and ethnic minorities indisadvantaged areas.Consultation workshops organized with women and ethnic minorities on the development and implementationof the CPD program and an awareness-raising communications strategy targeting women and ethnic minorities led to activeparticipation of women and minorities as core teachers and principal advisors and to the fuller participation of these groups inall aspects of the CPD program.As a result, women made up to 60 percent and ethnic minorities comprised approximately 10percent of the core teachers and principal advisors.TEMIS reports also provide gender- and minority-disaggregated data sothat provincial DoETs can continue to track and address the CPDneeds of women and ethnicminorities. Appropriate institutional implementation arrangements and coordination across institutions arecritical for ensuring the implementation of a broad reform agenda. Given that this operation was supporting partof a broader reform, having MoET fully manage the activities was an appropriate design element, essential for smoothimplementation.At the projects outset, institutional implementation arrangements were weak and fragmented,withroles and responsibilities ill-defined for LTTUs and provincial DoETs.Once MoET clearly defined the roles of theimplementation units, performance agreementsspecified accountabilities and partnerships between LTTUs and MoET, and ICTcapacities facilitated communication and collaboration with all 63 provinces, there was considerable improvement inimplementation.In addition, MoET, PMU, and LTTUs began to use technical assistance in strategic areas that brought in theneeded expertise to support international best practices for the CPD modules.MoETsundertaking of the substantiveeducational work enabled the relevant connections to the broader reform as well as strong system-wide capacitydevelopment.
P150066 | Nepal: Power Sector Reform and Sustainable Hydropower Development (PSRSHD) | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099112723151015967/text/P15006602331cb0150b01206d887f16ec3f.txt | http://documents.worldbank.org/curated/en/099112723151015967/pdf/P15006602331cb0150b01206d887f16ec3f.pdf | (Reference ICR paras. 66 to 70).The ICR (paras. 66 to 70) lists a number of lessons derived fromtheexperience under the Project. From these, IEG derives the following lessons that are relevant for similar projectsimplemented in comparable environments.Efficient preparation and execution of a policy agenda affecting more thanone sector and involving agencies in different sectors, as in the case of the Project, can be adversely affected by weaknesses inthe coordination between the key institutions and agencies involved. Itis essential to have the proper mechanisms inplace to ensure strong inter-agency coordination arrangements to facilitate smooth and successful implementation. The Project wouldhave benefited from the oversight provided by a well-constituted and empowered Project SteeringCommittee.During implementation, shifts in the clients priorities and emphasisin regard toproject content, as in the case of the Project, can be accommodatedby re-aligning the project to the new priorities.In the case of the Project, there was a subtle evolution of the Projects focus from the institutional and sector reform agendato infrastructure project preparation. Specifically, the significant increase in the supported hydropower capacity requiredsubstantially more attention to project preparation capacity while the parallel DPC operations exclusively focused on the reformagenda. In the case of the Project, the targeted institutional and sector reform actions were achieved. However, for futureoperations, depending upon the degree and significance of the changes, the need for a formal restructuring should be examined aswell.Training, targeted technical assistance and on-the-job training can enhance the capacity of the implementingagencies, but the gains can be constrained in the absence of adequate institutional-level human capital development plans.These plans should ensure that an adequate number of people are trained, people with adequate skills and experience are hired, andtalent is retained, including embedding highly skilled staff in the organizational structure to support decision-making andstimulate institutional learning.Inadequate specification of the specific modalities to be followed under newlyplaced World Bank policies and requirements can adversely affect implementation by causing uncertainty and implementationdelays. In the case of the Project, the Banks ESF did not fully specify how to carry out specific measures, andimplementation of the FPIC process was complex and difficult. Conducting small pilots before mandating the application of complexpolicy requirements can reduce uncertainty and provide for a smoother project-levelimplementationprocess.
P150113 | Tonga Cyclone Ian Reconstruction and Climate Resilience Project | East Asia and Pacific | Tonga | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/147051566927989374/text/Tonga-Tonga-Cyclone-Reconstruction.txt | http://documents.worldbank.org/curated/en/147051566927989374/pdf/Tonga-Tonga-Cyclone-Reconstruction.pdf | The ICR draws the following four lessons from the experience of implementing this project, with some adaptation oflanguage.(1)Reconstruction of housing infrastructure is necessary but not sufficient for building resilienceto natural disasters. This project contributed to constructing houses that are more resistant to cyclones and hence lesslikely to be destroyed or damaged. The project however affected only a small portion of at-risk assets and hence had limited impacton the overall vulnerability of Tonga to natural disasters.(2) Government provision of direct reconstruction ofhouses can establish expectations that have long term consequences. The project illustrated the political and fiscalimplications of the government having previously assumed too much responsibility for risk management in the housing sector, withpublic expectations that the government would directly reconstruct houses destroyed by a natural disaster. This make itdifficult to get government commitment for housing supply models that differed than this historic expectation. This impliesthe need for the Bank to be prepared to explain and persuade government of the long-term consequences of various housing recoveryproject designs and to seek to rebalance risks between households and the government. It also highlights the need for developingconsensus around a housing strategy prior to an emergency, as it is difficult to do so after a disaster.(3)A careful consideration of country-specific conditions (including cognizance of cultural norms and sensitivities) is required forsocial acceptance. This project contributed toconstruction of two roomhouses for 200vulnerablehouseholds and given the scarcity of resources,one room houses for 350 households whose needs were deemed to belessvulnerable.This decision created social and political challenges, as the one room houses were perceived astoo small andundignified.(4) The risks/challenges associated with reconstruction in remote locations can beanticipated and proper mitigation measures can be applied. Project efforts to facilitate access to trained labor andmaterials would be an important precondition for self-supported or owner-driven reconstruction efforts.
P150116 | Public Sector Performance Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099071023112536868/text/P15011605fc8a50e60ac3d0caa946a8cca0.txt | http://documents.worldbank.org/curated/en/099071023112536868/pdf/P15011605fc8a50e60ac3d0caa946a8cca0.pdf | Building on the lessons outlined in the ICR, IEG the following lessons were learned from theproject: PBCs may be less effective if financial incentives do not align with or are not invested in theagency or institution responsible for carrying out reforms. The ICR attributed the declining motivation of the tax and customsadministration to continue with reforms to process improvements and performance contracts to it not receiving an additionalinvestment budget. While this may or may not be related to incentives, the agency in question was asked to change or improveits practices without more resources. If indicators are not clearly defined, they will be difficult (or impossible)to measure. The ICR points out various weaknesses related to the selection of project indicators, which hampered their measurement.For example, the original RF included an intermediate results indicator, Project beneficiaries, a percentage of which arewomen, which posed a challenge since the project did not specify who is considered a project beneficiary. As the ICRnoted, the scope of the project yields multiple direct and indirect beneficiaries dispersed nationwide (p. 26). TheBank recognized the issue and replaced the indicator with one clearly defined and more easily measurable (the number of womenparticipating in public debates). Adequate attention needs to be paid to the ME system to ensureitfunctions as intended and contributes to accountability and lessons. The PIU appears to have largely neglected its MEfunction, relying on the IVA and Court of Accounts for reporting. As a result, ME reporting was sub-optimal. The Bank alsocould have done more to monitor the ME activities during supervision. Stronger ME implementation could have uncoveredissues with indicators earlier. The ICR notes that the weak ME element contributed to the need for projectrestructuring.
P150148 | DRC-Statistics Development Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2016 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099530003012222457/text/Congo00Democra00Development0Project.txt | http://documents.worldbank.org/curated/en/099530003012222457/pdf/Congo00Democra00Development0Project.pdf | The ICR offers the following lessons, with which IEG agrees, with adaptation: When supervision reports overrateoutcomes and underrate fiduciary, management, and implementation risks, the odds are low for correcting the problems promptly andhigh for achieving unsatisfactory results. Therefore, supervision missions should identify and flag risks early and rate projectsfairly. When the government uses differential salaries and bonuses to reward staff with the same qualifications in theimplementing agencies, the odds are high that the project will experience implementation problems. To prevent failure ina context where there is low capacity and high statistical needs, the WBG needs to: (a) assess what needs can realistically besatisfied with existing capacity, and (b) ensure that, soon after grant or credit approval,key positions are filled and thestaff in charge of managing the project receive proper training in basic management skills and Bank procedures (e.g., fiduciary,procurement, etc.). When in a country like DRC the project design pays insufficient attention to implementationrequirements, the project is likely to deliver unsatisfactory results. Therefore, to raise the odds of success, the design mustconsider imposing more rigorous implementation requirements, such as hiring key personnel and ensuring funds are set aside to paythe members of the project steering committee.
P150158 | Eastern Dedicated Freight Corridor-3 | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2015 | 2022 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062024190023346/text/P150158-b008bfc3-5fdf-4cd1-b565-656c5873e970.txt | https://documents.worldbank.org/curated/en/099062024190023346/pdf/P150158-b008bfc3-5fdf-4cd1-b565-656c5873e970.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The Banks long-term strategic support may raise the potential for success in enabling State OwnedEnterprises (SOEs) harness commercial financial markets and introducing fundamental changes in a countrys railsector. The time frame for large-scale, long-term reforms in a countrys rail sector are typically long. Thesestrategic reforms require the SOEs to evolve from a traditional government-funded organization to a commercial, market-focused andoperationally efficient entity. Likewise, long-term engagement by the Bank can enable the Bank to facilitate adoption of soundsocial, environmental and fiduciary policies.The lesson is that Banks long-term support may be necessary to facilitatesuch reforms.2. Careful planning for managing and coordination of land acquisition may be required, in countrieswhere subnational entities are involved in land acquisition. In India, national-level projects rely on state governmentsfor the complex process of land acquisition. The process in this project required intensive coordination between the DedicatedFreight Corridor Corporation Limited (DFCCIL), the state government land offices, the contractors and local governments. Over time,as land acquisition delays impeded construction, DFCCIL became much more systematic in coordinating land acquisition as it came torealize that coordination with local authorities was in the interest of timely project completion.3. A carefulassessment of the World Banks capacity and the contractors capacity may be required when new contracting structures areintroduced for the first time. This project conceptualized the Design-Build lump sum contract to ensure equitable risksharing between DFCCIL and the contractors. However, the project failed to foresee the time required for Banks internalapprovals, financial challenges faced by contractors and delays in land acquisition by DFCCIL. This contributed to the delays inthe initial years.
P150183 | KZ SKILLS AND JOBS PROJECT | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2015 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest |  |  | The project provided several lessons learned which were adapted by IEG: The Bank provides value-addedbeyond its financial assistance through technical assistance. This project was effective in supporting the establishmentof a system to improve skills that would benefit labor market outcomes. Even though the Bank did not end up financing the training,it ensured that delivered outputs related to design and standards were applied to the training supported under a governmentprogram, that was developed to replicate the design of this Bank-supported project. It is critical for aprojects Results Framework to be balanced and to measure all outcomes evenly. In this project, the ResultsFramework heavily focused on the first aspect of the PDO (measured through six PDO indicators) and included only one PDO indicatorto measure the second aspect of the PDO. Country-specific procedures need to be taken into account when designinga project since they can influence project implementation. In Kazakhstan, ratification of loans and adjustments of PDOsrequire lengthy and cumbersome parliamentary approvals. As a result, in this project the PDO was not modified to avoid thisprocess.
P150194 | Tuvalu Second Development Policy Operation | East Asia and Pacific | Tuvalu | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Negligible |  |  | IEG agrees with the ICR (para.75) that although limited capacity was factored into the design, it did not consider to theextent necessary the implementation capabilities of the Government. In very limited capacity environments, program design shouldstart with an evaluation of the capacity of country counterparts. The complexity of prior actions and the degree of coordinationneeded between Government departments should be a critical input in determining reform programs. The ICR suggests thatactivities of other development partners need to be fully accounted for in program design. The accounting should incorporate notonly the complementarity of development partner programs, but also the extent to which they utilize scarce Government capacity toimplement their programs. IEG agrees with the ICR that flexibility should be built into the design of DPOs ifcircumstances change, as they did when Tuvalus revenue stream increased because of fishing license fees. IEGsuggests that the continued lack of information on which to monitor progress should have triggered efforts to address the gapsearly in the DPO, rather than later, as evidenced by the ICR indicating that the information that it contains could beunreliable.
P150308 | Assam Citizen-Centric Service Delivery Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061224214542301/text/P150308-c85488aa-0e08-4a04-bcea-a1e89988e107.txt | https://documents.worldbank.org/curated/en/099061224214542301/pdf/P150308-c85488aa-0e08-4a04-bcea-a1e89988e107.pdf | The ICR identifies several lessons, with which this review adopts. The key lessons are extractedbelow: Comprehensive Citizen-Centric Approach: The Project demonstrated the effectiveness ofengaging communities and leveraging technology to enhance service delivery. By involving stakeholders through targeted efforts andcommunity consultations, the project aligned government services with traditional community systems, fostering mutual trust betweencitizens and the state. Additionally, the implementation of multi-channel service delivery, including human-assisted and directdigital channels, facilitated ease of access for citizens. Policy reforms and institutional arrangements further strengthenedaccountability and responsiveness in service delivery. Integration of Technology and Human Interaction:While technology played a pivotal role in streamlining processes and expanding access to services, the project recognizedthe continued importance of human interaction, especially through physical access points like PFCs. These centers providedessential support for individuals requiring in-person assistance, complementing digital service delivery efforts. Moreover, theinvolvement of trusted intermediaries, similar to the Tax Return Preparer model, offered opportunities for ruralentrepreneurship and improved service accessibility, particularly in remote areas. Streamlining ProcurementProcesses: The projects experience highlighted the importance of finalizing procurement strategies early on,particularly for major procurements. Delays in procurement strategy formulation, especially for PFC service providers and ITservices, led to project delays. However, once these contracts were awarded, momentum increased, reflecting the critical role ofstreamlined procurement processes in project implementation. This underscores the need for proactive planning and efficientexecution of procurement activities to ensure timely project delivery.In summary, the Project provides valuablelessons for replicable models in other regions facing similar challenges. These lessons underscore the significance of communityengagement, technological innovation, policy reform, and streamlined procurement processes in achieving efficient, accountable, andcitizen-responsive governance.This review adds the following: Proactive stakeholder engagement fortimely project implementation: The projects initial delays in developing and integrating the ARTPS portal highlightthe critical need for proactive stakeholder engagement. Early involvement of the Government of Assam and key stakeholders couldhave facilitated consensus-building on the portals development approach and integration with existing systems. Comprehensivefeasibility studies and risk assessments should be conducted early to anticipate and mitigate potentialchallenges. Ensuring inclusive service delivery through Indigenous community engagement: Theprojects success in tribal-dominated areas underscores the importance of engaging tribal communities in the service deliveryprocess. Meaningful consultations with tribal leaders and traditional village councils facilitated the development of tailoredinterventions aligned with community needs and cultural sensitivities. The translation and dissemination of service information inlocal languages enhanced accessibility and participation among tribal populations. Moreover, initiatives such as the TribalDevelopment Plan (TDP) addressed specific challenges faced by tribal communities, fostering trust and accountability in governance.This highlights the necessity of adopting culturally sensitive approaches and actively involving marginalized communities to ensureequitable and inclusive service delivery outcomes.
P150313 | Development Policy Loan 1 | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2014 | 2015 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/466421520260473365/text/Ukraine-DPL-1.txt | http://documents.worldbank.org/curated/en/466421520260473365/pdf/Ukraine-DPL-1.pdf | A number of useful lessons are highlighted in the ICR. First, significant government commitment is paramount in achievingimportant reform outcomes. Second, the need to coordinate closely among development partners is critical in moving forward thereform agenda. Third, strong analytical work and deep engagement with government counterparts are important for successful policylending. Fourth, flexibility in programmatic design allows the Authorities and the Bank to adapt the program to changingcircumstances. IEG adds two further lessons. First, patience enabled the Bank to seize a unique window ofopportunity to support critical and far reaching reforms, after having refrained from policy lending when the timing was not right.Prior to the operations, the Bank maintained an open policy dialogue and produced significant analytical work, both of which wereinstrumental in enabling the program to be designed in a short time span. Second, deep-rooted reforms that go against vestedinterests are difficult to sustain once the reform momentum wanes. A thorough political economy analysis during or prior topreparation can provide useful insights in this respect.
P150351 | Senegal Urban Water and Sanitation Project | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099300312232295107/text/P15035103f2aa20210b1640fdd3f9832cef.txt | http://documents.worldbank.org/curated/en/099300312232295107/pdf/P15035103f2aa20210b1640fdd3f9832cef.pdf | This review has drawn two lessons based on the information in the ICR.Close policy dialogue with theauthorities can be critical in achieving project objectives. The project team were located in Senegal and CotedIvoire. In addition to the 12 formal supervision missions, this proximity allowed frequent dialogue with the Senegaleseauthorities to solve issues related to project implementation and resulted in a productive dialogue about water and sanitationservices sector reforms. As a result, the government adjusted tariffs twice during project implementation that had a direct impacton improving the financial viability of the utilities in the short and medium-terms and conclusion of a performance agreement witha private operator.Without a robust results framework, outcomes in water and sanitation service delivery aspectscannot be adequately captured. The projects results framework was designed to capture the increases in the numberof water and sewerage connections. These indicators were sufficient to capture the results expected from the projectsintervention as formulated in the project objectives. However, water and sanitation projects require a higher level of achievementthat should encompass improvements in service delivery aspects, such as availability, reliability, quality, and affordability;especially so, in countries with low access rates like Senegal. The projects framework lacked these indicators. This canbe extended to the coverage of projects impact on socio-economic welfare of the project beneficiaries, with a special focuson women and girls.
P150357 | Local Roads Improvement Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2016 | 2024 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051724153068702/text/P1503571d0c3510861a31f1676fd83baccd.txt | http://documents.worldbank.org/curated/en/099051724153068702/pdf/P1503571d0c3510861a31f1676fd83baccd.pdf | This review has drawn three lessons based on the information in the ICR.An insufficient assessment of thedesign and technical capacity of the local contracting industry when novel road rehabilitation techniques are introduced can leadto significant project implementation bottlenecks resulting in limited progress. The project introduced a new techniquefor the rehabilitation of the local roads, and the tender documents were prepared based on the preliminary designs rather thandetailed designs. The lack of local design and contracting capacity was not adequately assessed during appraisal. The final designsprepared by the local companies included significant discrepancies. Local contractors did not have the appropriate equipment forthe proposed technical solutions for rehabilitation or upgrading of local roads, nor did they have the capacity to implementmultiple projects at the same time. These resulted in significant project implementation delays and cancellation of contracts. Thisissue was addressed by adopting a road rehabilitation technique with which the local companies were familiar. However, thisresulted in an increase per kilometer cost of construction and, hence, the narrowing of the projectscope.Continuous and proactive dialogue with the authorities when there are frequent changes at the seniormanagement of the project related public entities can be effective in ensuring the implementation of sector capacity strengtheningtechnical assistance activities including policy reforms. There were frequent senior management changes at the Ministry ofInfrastructure and Regional Development and the SRA during project implementation, which affected the decision-making process. Theproject team, benefiting from the presence of the Task Team Leader and other project team members in Moldova, proactively engagedwith the authorities to update them about the current status of the project implementation, especially with respect to thetechnical assistance activities for local road management capacity strengthening. Although these helped maintain the course of theimplementation of the technical assistance activities, and the project delivered the technical assistance results closer to theproject closing date, as the ICR reports (p.33), the likelihood of the adoption of the policies could be increased by a higherpolicy dialogue supported through development policy operations.A Mid-term Review conducted adequately andaccording to schedule can lead to a substantive restructuring of a stalled project and improve project implementation efficiencyresulting in the achievement of the project objectives. Because of the various project implementation issues related totechnical design, contracting capacity, and procurement, the project had achieved minimal progress by the Mid-term Review anddisbursed only around US$5.4 million. The project was at the high risk of not achieving its objectives. Based on the discussionsheld during the Mid-Term Review conducted in 2018, the project was substantively restructured in January 2019 to address thebottlenecks to project implementation. This restructuring resulted in a reduction of the length of the local roads to berehabilitated or upgraded by half but ensured the successful achievement of the project outputs and outcomes, and hence the projectobjectives.
P150374 | Somali Urban Investment Planning | Eastern and Southern Africa | Somalia | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099140110122211861/text/P1503740a4f2390990873207658684eebb8.txt | http://documents.worldbank.org/curated/en/099140110122211861/pdf/P1503740a4f2390990873207658684eebb8.pdf | The ICR (p. 25-26) provided several lessons learned, which were adapted by IEG: While working withmunicipal governments can result in strong levels of ownership within the municipalities it can also lead to coordinationchallenges.In this project, working through municipal governments reduced political interference and empowered themunicipalities. However, without a clear apex institution linking the municipalities, the project faced implementation challenges,which were addressed by hiring a program coordinator and establishing a Project Coordination Unit (PCU) under theSURP. Engaging international third-party expertise in the implementation of a project in a countrywith limited capacity while at the same time building capacity within the government can positively impact projectimplementation. In this project, project management capacity was enhanced by engaging UNOPS, which used in-house capacityrather than managing external consultants or firms, to deliver better quality assurance in a low capacity-environment while beingengaged locally. Ensuring a participatory approach by engaging with local communities during projectpreparation can positively impact implementation.During the preparation of this project local communities wereinvolved little, presenting a lost opportunity. However, throughout implementation the needs of vulnerable groups including womenand internally displaced persons (IDPs) became a priority resulting in participatory planningprocesses. World Bank executed components can be useful in a FCV context with limitedgovernment capacity and challenging monitoring. In this project, the World Bank executed several project activities suchas the institutional and socio-economic assessment on behalf of the government due to limited capacity. This allowed for a betterunderstanding of institutional capacity and existing dynamics that needed to be considered for calibrating the projectsimplementation approach.
P150394 | MP Higher Education Quality Improvement Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099081523142730864/text/P1503940561f8a0bd0b641082498fa64536.txt | http://documents.worldbank.org/curated/en/099081523142730864/pdf/P1503940561f8a0bd0b641082498fa64536.pdf | The ICR (pp. 24-25) offered several lessons and recommendations, including the following lessons, slightly re-stated byIEGs Review:Implementation of a reform agenda requires the cooperation of multiple stakeholders and anadequate level of human resourcesand expertise. Under the project, management capabilities were built throughout thesystem to implement reforms that have multiple stakeholders and that require a wide set of expertise. Also, the Department ofHigher Education expanded its capacities by hiring a professional organization to act as a Project Management Consultant and byhiring other consultants with special expertise.Adequate sequencing of context-specific activities facilitatestimely implementation. Prior steps and adequate sequencing, supported by buy-in efforts, were needed to promote governanceand HEIautonomy aspects. The project lost valuable time in 2015 and 2016 in the selection process forHEIs, and startingthis process during preparation would have reduced delays in related activities at the level of HEIs.Carefuldesign can avoid holding implementing agencies accountable for tasks and results beyond their control. Under the project,DHE committed to increasingthe number of faculty according to Government HEI norms. The approval of new positions was theresponsibility of the Public Service Commission and not DHE. The shortfall in faculty holdingregular positions was alleviatedby hiring contract faculty and guest faculty.A strong ME system is an integral part of the backbone for asuccessful reform agenda. The project provided due attention to ME and strengthened related capacities whileconverting manual processes to online operations that allowed the Department of Higher Education to carry out effective planningand to exercise due diligence in reporting.
P150395 | Tamil Nadu Sustainable Urban Development Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099021924192025443/text/P15039515d0f680111be911529ce8de32b5.txt | http://documents.worldbank.org/curated/en/099021924192025443/pdf/P15039515d0f680111be911529ce8de32b5.pdf | The following five lessons emerged from the operation (ICR, paragraph 77-81): Political commitment,policy reform, and provision of incentives are useful to improvethe financial sustainability of water services. Inthis project, water tariff in Tamil Naduwaslow and not based on consumption. Data from the Supervisory Control and DataAcquisition System (SCADA) in Namakkal showed that water consumption level was similar between households covered by the 24/7 pilotand households receiving intermittent supply. ULBs need incentives to approve bylawsfor volumetric billings toraisetariffs and increase collection. Metering could be piloted in selected areas wherehighlevels of services andhigh-water consumption are expected.Proper systems could be in place to monitor consumers usage and addresscomplaints. Data can then be generated to inform ULBs decision-making and counter public misconception onvolumetricbilling. Information, education, and communication activities instill behavioral changestosustaindesired levels of services. In this project, residentswere encouraged to participateinOM planning of municipal assets. However, there was no comprehensive communication strategy for the duration of the project.This could have been usedto engage local communities, raise awareness, and enhance ownership of project investments.Consumers could be provided a reliable schedule of water supply and be educated on benefits of volumetric billing to encouragereducing wasting water. Overall, citizen participation could be further explored, including mechanisms for people to contribute interms of timeand labor. The municipal development fund model may facilitate access toprivate marketresources.In this project, TNUDF provided loans and grants of over US$3.2 billion in urban investments. ULBsregistered 100 percent loan repayments. Future projects can support TNUDF to resume its pooled municipal bond program to increaseULBs access to financial markets, with the funds raised giving priority to green projects such as sustainable watermanagement, climate change adaptation, and energy efficiency. Results-based performance grants help promote urbangovernance reform in ULBs. In this project, the pilot Model Cities componentdemonstrated the effectiveness oflinking fund allocation to support improved urban governance and citizen engagement, strengthening staffing and technicalexpertise, mobilization of own resources, and enhancing accountability in delivering services to cityresidents. Institutional strengthening and capacity building of ULBs require sustained support.ULBs have benefited from the various TA, training, and capacity support activities under the project. However, dedicated funding,staffing, and collaboration with training institutions are required to continue developing and delivering structured capacitybuilding programs to strengthen institutional capacities of ULBs.
P150430 | Mauritania Social Safety Net System | Western and Central Africa | Mauritania | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/384801629220055019/text/Mauritania-Mauritania-Social-Safety-Net-System.txt | http://documents.worldbank.org/curated/en/384801629220055019/pdf/Mauritania-Mauritania-Social-Safety-Net-System.pdf | The following lessons are drawn from the ICR (pages 37-40):Close supervision and a focus on capacity buildingand analytical work can remove constraints posed by limited capacity environments. The Bank overcame limited countryknowledge and local administrative constraints to developing a safety net by continuous intensive interaction with the client,combined with field surveys and limited pilots, resulting in an operational platform being developed that supported an adequatelytargeted safety net program.Working through existing government institutions rather than adopting a conventionalproject-specific implementation unit can strengthen ownership and institutional sustainability. The project wasimplemented through existing government agencies that received necessary resources and technical assistance to subsequentlyadminister the programs and institutions created under the project.This integration of project institutions into governmentsystems facilitated ownership and increased the likelihood of them remaining viable.Government counterpartfinancing can increase the likelihood of institutions remaining sustainable beyond the project period. Safety netprograms require a steady flow of resources long after the project has closed in order to remain viable. The Mauritania safety netproject had been implemented with significant counterpart financing that contributed some 30 percent of the projectbudget.This not only showed the governments commitment to the project, but its willingness and, more importantly, itsability to maintain a safety net beyond World Bank financing.
P150475 | Programmatic Development Policy Loan for Sustainable Development | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2016 | 2017 | 2020 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/219221593208993150/text/Colombia-Colombia-DPL-for-Sustainable-Development.txt | http://documents.worldbank.org/curated/en/219221593208993150/pdf/Colombia-Colombia-DPL-for-Sustainable-Development.pdf | The ICR draws the following three lessons from the experience of implementing this operation, with some adaptation oflanguage.1. National reform efforts whose success depends to a considerable extent on subnational level structuresneed to account for the political, financial and technical risks at thoselevels. The activities associated withpromoting non-motorized transport modes in this operation faced obstacles at the subnational level. The lesson from this operationis that, where compliance at the subnational level is required for realizing the national objectives, they should not only beidentified, but also mitigated through measures embedded in the design of an operation and supported by prior actions, if need be,aimed at ensuring the compliance of subnational agencies.2. Thedesign of a reform program should be informedby extensive analytical work. The sound analytical underpinnings, including work conducted by the Bank, allowed the teamaided the team to design solid operations.3. Broad reforms as those supported by the series should be anchored ina widely accepted framework. This operation was aligned with elements of Colombias National Development Plan for2014-2018, prepared with comprehensive stakeholder engagement. This ensured the governments commitment to formulating coherentpolicies and pursuing their achievement supported by this series.
P150481 | Health System Resiliency Strengthening Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Health, Nutrition & Population | SPF | IPF | 2015 | 2022 | 2024 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099072723203021657/text/P1504810975eb301a0ac23033b9d4b280f2.txt | http://documents.worldbank.org/curated/en/099072723203021657/pdf/P1504810975eb301a0ac23033b9d4b280f2.pdf | The following lessons are a subset of the six relevant and insightful lessons presented in the ICR, slightly reworded byIEG.In FCV settingslike WBG, it is prudent to keep project design and technical components as simpleand flexible as possible. The projects success was due in part to its simple and flexible design.Theemergency support under the project not only helped address the acute needs of healthcare services in Gaza, but also enabled aquick response to the COVID-19 pandemic, without the need for restructuring.The direct contracting with WHO in support ofComponent 3 (building blocks for UHC), introduced during implementation to simplify Component 3, facilitated the provision oftimely inputs and technical expertise.Project support of evidence-based health sector reform is a complexundertaking, especially in an FCV setting, requiring due attention to contextual factors, including political economy, limitedcapacity, stakeholder involvement, and the need for a phased approach, aligned with country readiness to fully articulate, adoptand implement. Experience under this project has revealed the wisdom of: (i) ensuring a robust understanding ofcountry context and dynamics; (ii) providing adequate funding and a roadmap for capacity building; (iii) remaining flexible torespond to a dynamic situation; (iv) focusing on harmonization of donors work on governance and reform; and (v)understanding the critical path and dynamics of health system strengthening.Starting with relatively straightforwardmanagement systems and reforms and postponing the introduction of more complex systems to a later phase allows the rollout ofreforms incrementally at a pace that permits institutions to absorb and integrate new systems, before moving on to subsequentphases.It is feasible and desirable for an emergency operation to address acutehealthcaredelivery needs in times of crisis, while at the same time supporting critical components of health sector development, even in anFCV context. This project succeeded in achieving both its emergency objective (continuity of healthcare services)and its development objective (strengthening sector resilience through rationalizing OMR, improving equity of referralexpenditures, and building systems and capacities for moving toward affordable UHC through primary health care).Indeed, theCOVID-19 pandemic, unforeseen at the time of project design, has validated the projects focus on strengthening health systemresilience, especially: (i) addressing health financing challenges and reducing unsustainable health expenditures; (ii) building afoundation for strong primary health care; (iii) increasing domestic investment in the health system; and (iv) addressinginequities in healthcare access and health outcomes of marginalized populations.Supporting health reformsrequires a combination of consistent financing, technical assistance, and a whole-of-government approach. The WorldBank, through its in-country and HQ-based staff, along with external consultants, provided consistent technical support throughoutproject implementation. The project also engaged partners, donors and NGOs during design and implementation. Experienceunder this project has pointed to the desirability of engaging stakeholders from the wider government, beyond MoH, to ensurebroader political support. In retrospect, the fuller engagement of Ministry of Finance and the Prime Ministers officemay have broadened and strengthened political support for sector reform. Sharing theprojects achievements to a wider range of actors and stakeholders might be an effective way of expanding reform buy-in, demonstrating how seemingly intractablechallenges can be addressed, even in difficult contexts.
P150503 | MG-Reengagement DPO | Eastern and Southern Africa | Madagascar | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/653761497536078827/text/ICRR-Disclosable-P150503-06-15-2017-1497536071293.txt | http://documents.worldbank.org/curated/en/653761497536078827/pdf/ICRR-Disclosable-P150503-06-15-2017-1497536071293.pdf | The following lessons are taken from the ICR with some adaptation oflanguage: Strong coordination of budget support operation with Bank investment projects may be beneficial for policy reforms supportedunder a DPO. Despite various changes in the government at the political level, the Banks ongoing investment projects inMadagascar helped to keep continuity of the policy dialogue largely intact because of well-established line of communication at thetechnical level. In a low capacity environment program monitoring will benefit from additionaltechnical assistance on ME provided to the Government at both the preparation and implementation stages. The Madagascar DPOcould have included TA on data gathering and reporting, as well as ME administration (coordination of ME effort acrossvarious governmentagencies).The following lesson is additionally suggested by theIEG: Given that in a fragile policy environment institutional changes require more time for consolidation andhaving an impact, the evaluation of DPO outcomes will benefit from extended project cycles, including a later closing dateand additional supervision missions. This would allow for collection of additional ME data and for more accurate assessment ofboth actual program outcomes and theirsustainability.
P150520 | Punjab Rural Water and Sanitation Sector Improvement Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062524160537792/text/P150520-30e79ec4-4c4e-4c82-8058-73f10de063ec.txt | https://documents.worldbank.org/curated/en/099062524160537792/pdf/P150520-30e79ec4-4c4e-4c82-8058-73f10de063ec.pdf | Strong citizen engagement and behavior change communication activities are critical to changing behaviors inwater and sanitation projects. The premise of the project was to change behaviors around sanitation and hygiene habits,particularly reducing open defecation. This entailed massive social mobilization efforts at the village level, coordinated withother behavior change communication efforts through different media platforms. The Project demonstrated through its randomizedcontrol evaluation that the behavior change communication efforts in program had an effect on reducing opendefection. CDD interventions can be impactful when institutionalized in governments approachand programming. The CDD approach in the state of Punjab appears to have strengthened service delivery arrangements at thecommunity level due to their level of engagement and ownership over the installed infrastructure. This project demonstrated thelink between strengthened capacity of GPWSCs and improved access, reliability, and efficiency of water services. TheProjects investments in social outreach through well-structured IEC activities and dedicated staff were critical in buildingthe GPWSCs capacity and thus in achieving project outcomes as evidenced by the endline survey results. (ICR, p.20) Measuring service delivery outcomes at the Department and village levels was critical to shiftfrom a focus on construction towards service delivery. Similar to the paradigm shift in sanitation, there was a shift forwater supply as well. The project was measured in terms of access and quality of water services delivered, and not on the number ofphysical assets created (connections or length of pipes installed). This shift in focus from asset creation to performance andreliability is important for long-term sustainability. Strengthening the district functions to support community management throughGPWSCs empowered communities to operate and manage this infrastructure with technical backstopping from government. The focus onmonitoring and evaluation increased and accountability and was central in shifting the focus of the DWSS from a civil works agencyto that of a service delivery agency, and beneficiaries had the ability to drive local decision making on water availability. (ICR,p. 20) Beneficiary led construction of IHHL assets contributed to greater ownership, use and improvedmaintenance of assets created. Historically, the government of India had taken a supply driven approach to toiletconstruction, which went unused by households. As a result, a change in paradigm shifted from supply driven to demand driven, whichwas embodied by the SBM national program and implemented through this project. A demand driven approach with BCC interventions andcoupled with financial support and household led construction were key factors in high achievement of sanitation outcomes asbeneficiaries were able to choose location, design, and construct the IHHLs in a manner that was suitable to each household. Theircontribution either in the form of cash or labor in construction resulted in a strong sense of ownership and establishment ofsatisfied services in terms of utilization, good quality, and continued infrastructure asset maintenance over a long period. (ICR,p. 20)
P150576 | Tejaswini: Socioeconomic Empowerment of Adolescent Girls & Young Women | South Asia | India | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | Lessons from ICR (p.14)AGYW clubs and/or safe spaces can serve as effective platforms to deliver variousinterventions, when their financial and operational sustainability is considered upfront. The project successfullyachieved results at the community level by setting up 12,839 Tejaswini Clubs where over 1.19 million AGYW gathered and took part inmultiple activities. These clubs had strong demand and acted as means towards delivery of demand and supply-side interventions.However, at project closing, these clubs were not maintained as, although discussed, no clear exit strategy was developed. A clearlesson that was drawn from this is that, at scale, while these platforms can be effective for service delivery, relying on existingstructures instead of building platforms from scratch would help their sustainability in the future.Whereimplementation capacity is weak, overly complex project design can lead to failure.Implementation challenges arisingin Tejaswini were partly due to the complex design of multicomponent interventions. Given the multiple constraints AGYW face, therationale for flexible combination of multiple interventions was justified, particularly when the goal was not only to achieveeconomic outcomes but also to empower them. However, in practice, this gave rise to various difficulties during implementation,including the need to establish a continuum of activities that would have to flow down from community-type of interventions firstand then to institutional-type of interventions, essentially setting up several choke points in theproject.Agood design, close supervision, or restructurings cannot substitute for low political andbureaucratic commitment. During preparation, the state showed a high level of commitment to the empowerment of AGYW. Withthe approval of the Project and the development of inter-departmental strategy for convergent action, the Department set up thebuilding blocks for political ownership and support to the AGYW agenda. After the change in State leadership, that political willfizzled despite the PIU efforts. This resulted not only in implementation delays at project start, but with every change of PD,project momentum, clearances, approvals, and activities were further delayed, affecting in parallel the PIU morale. The Projectcould have better guided DWCDSS management throughout project implementation, to establish an enduring sense of ownership
P150631 | KH-Land Allocation for Social and Economic Development Project II | East Asia and Pacific | Cambodia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051723144045083/text/P1506310e554ac03b08c8c008c118e76b59.txt | http://documents.worldbank.org/curated/en/099051723144045083/pdf/P1506310e554ac03b08c8c008c118e76b59.pdf | The ICR presents eight lessons (ICR, paras. 107 114). The section below consolidates key aspects of these lessons intofour lessons which potentially have broader application than Cambodia.:(a) Lesson 1: Ensuringadequate political commitment and an enabling policy environment are vital for the successful implementation of a project:This projectwas based on a clear and approved legal framework for land titling which was championed by the mostsenior Government official in the Ministry of Land Management, Urban Planning and Construction (MLMUPC), the main implementingentity). This enabling policy environment, supported by strong proactive leadership at a high level, were vital elementssupportingthis projects successful implementation.(b) Lesson 2: Sound, responsiveand flexible planning at various stages of the project cycle help ensure project success: During this projectsdesign and implementation, the project exhibited the following positive traits, while addressing the relevant challenges:sound planning approaches, including clear criteria for selection of beneficiaries; participatory planning aspects andrealistic timelines, although there were some challenges in setting realistic and ambitious targets: land useplanning involved relevant community stakeholders and leaders; there was application of scenario planning approaches to identifyinterdependence of activities and determine the best sequence of delivery (e.g., especially with respect to start-up activities,such as settling-in assistance, provision of infrastructure and social services).(c) Lesson 3:Sound integrated, implementation, coordination and communication approaches and mechanismshelp ensure efficient/effectiveimplementation and results: These features, which were exhibited by the project, will help avoid siloed implementation andleverage comparative strengths at various levels (e.g., access to quality extension services and capacity-building to enable smoothtransition of agricultural workers into settled farmers; collaboration between communication and infrastructure experts onbehavioral change campaigns; mitigation of unintended project effects involving irrigation reservoirs on drinking water).(d) Lesson 4: A Sound Exit and Sustainability Strategy Requires TimelyPlanning. It is vital to carry out proactive planning for a projects closure during the last year of implementationthrough formulating and implementing a sound Exit andSustainability Strategy. Sound strategies, as in this project,included strong accountability mechanisms and engagement processes with relevant stakeholders. The sustainability strategymay also support a follow-up phase and/or prioritized activities. In the case of this project, the Exit andSustainability Strategyprovidedan effective bridge to LASED Phase III. Also, LASED III is monitoring andfollowing up on the implementation of the Sustainability Strategy for LASED II, which is an added positive lesson for projects withfollow-up phases.
P150634 | Rwanda Electricity Sector Strengthening Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099101223172517792/text/P150634089a8a80e10a03e0ce1f44d73a40.txt | http://documents.worldbank.org/curated/en/099101223172517792/pdf/P150634089a8a80e10a03e0ce1f44d73a40.pdf | The following lessons were derived from the ICR (ICR, pages 35-38):1. The Governments ownership and commitmentto sector reforms are essential for the achievement of project objectives. During Project implementation, the Government showed astrong commitment toinstitutional strengthening of the electricity sector. The REG and its subsidiaries, EUCL and EDCL, weresupported by a new legal framework, giving them autonomy to make decisions in key areas such as organization structure,recruitment, attraction and retention of staff, procurement, and expenditure approval, which contributed to a turnaround in theperformance of the sector. The REG and its subsidiaries were encouraged and empowered to apply good corporate governance practicesand adopt best-in-class business processes, which were fundamental for making the project successful. The lesson isthat government commitment is essential and can lead to projects success even when the objectives are ambitious.2.The World Banks early involvement in the design of sector reforms is important in ensuring proper design of the follow-upinvestment operations. The Bank had been atthe forefront in supporting Rwandas power sector reforms and providingtechnical assistance on policy, institutional, organizational, and regulatory aspects of the reforms for a long time. The projectdesign reflected the World Banks experience and lessons learned from similar activities in other countries and embeddedthree core elements for developing an efficient and accountable performance culture in the utility during the change process: (a)an appropriate organizational structure with a clear vision, (b) a skilled workforce, and (c) tools and systems to support staffperformance and inform decision-making. The lesson is that investment operations benefit when based on a long-term involvement inthe sector reforms in acountry and when in-depth analytical work and operational experience have been prioritized.3.Developing and implementing good utility management information systems (MIS) can modernize and transform utilitysoperations. The design, supply, installation, and operationalization (including staff training) of the IBMS played a transformativerole in improving efficiency, transparency, accuracy, and accountability of the utilitys business processes, which had aprofound impact on the utilitys operation. The lesson is that making investments in such systems a high priority iscritical. This lesson is consistent with the finding by the World Bank 2021 reportUtility Performance and Behavior inAfrica Today (UPBEAT) that utilities with goodMISs and sound performance management reporting and disclosure tend tohave better financial performance.
P150677 | Programmatic Financial Sector DPL 1 | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2015 | 2015 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/778861516292756356/text/Ukraine-Programmatic-Financial-Sector-DPL-1.txt | http://documents.worldbank.org/curated/en/778861516292756356/pdf/Ukraine-Programmatic-Financial-Sector-DPL-1.pdf | Three lessons, drawn from the ICR (pages 34-36) with some adaptation, are as follows:Governmentownership of reforms is crucial to the successful implementation of a DPL operation. The political, economic andsecuritycrisis of 2014-15 dictated thenecessity and the urgencyof the banking reforms under FSDPL1 andFSDPL2. However, economic necessity alone may not have been sufficient to complete two politically-difficultheadlineactions --- the submission by the banks of related party lending unwinding plans and the nationalization ofPrivatbank, following the latters failure to complete its recapitalization program.Strong political commitment by theUkrainian Government to financial reform was vital to complete the nationalization of Privatbank, consideringthe bankspolitical connectedness, and the submission by banks of related party lending unwinding plans, considering the vested intereststhat bank owners and managerswould have held with related party loans.A reform program would benefitfrom a flexible design in crisis situations. The two-part programmatic structure of FSDPL1 and FSDPL2 allowedthe Bank and the Government to adjust the policy matrix as the financial and economic crisis evolved in Ukraine over 2014-15.In this manner, the reforms were made relevant to changed conditions and responsive to evolving problems. For example, therising number of banks failures as the crisis deepened required a faster pace of deposit payoffs. In response, Enablingthe DGF to increase the speed of reimbursing insured depositors was added as a prior action to FSDPL2. Similarly,whereas FSDPL1 required diagnostic studies of the 35 largest banks, FSDPL2 required the certification by the National Bank ofUkraine (NBU) that 13 of the 35 banks were able to recapitalize in the amounts indicated by the diagnostic studies.Financial sector development and reform programs are always long-term efforts, for which structural and institutionalreforms are of paramount importance. Although FSDPL1 and FSDPL2 enabled the resolution of insolvent banks andthe nationalization of the largest private bank toaddress the immediate threats to financialstability,safeguardingbanking and financial stability is never aone-time operationbut is rather an ongoingeffort. In which case, theemphasis should be on structural and institutional reforms.The DPLs thereforefocusedon strengthening the financing of the Deposit Guarantee Fund (DGF) to enable it to meet the demandfor depositinsurance and bank resolution into the future. And, the DPLs aimed tostrengthen bank capitalto maintain publicconfidence in the banking system and to improve the banks capacityto meet the demand for credit in the Ukrainianeconomy.
P150677 | Programmatic Financial Sector DPL 1 | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2015 | 2015 | 2020 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/477561579113645942/text/Ukraine-First-and-Second-Programmatic-Financial-Sector-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/477561579113645942/pdf/Ukraine-First-and-Second-Programmatic-Financial-Sector-Development-Policy-Loan.pdf | 6. Lessons 6.1 Close coordination among donors is critical for DPLs to maximize the effectiveness of a jointly designed reform program. In this DPL series, close donor coordination ensured the reform program's consistency and the uniformity of advice regarding policy measures. 6.2 The design of DPLs needs to focus on all relevant issues, potential weaknesses, and gaps in reform measures. There were shortcomings in dealing with state-owned banks and the contracting framework in the DPL series. Although these omissions were understandable given the need to focus on the immediate crisis response (which overshadowed these medium-term concerns), the sustainability of outcomes in the long term relies on a continued focus on such reforms in follow-up operations. 6.3 The presence of task teams in the field can be a critical factor in promoting financial sector reform. Country-based task team leaders can have local knowledge and the ability to engage closely with counterparts. This is an important element in planning succession. 6.4 Weak public understanding of financial sector reforms indicates a need to expand outreach efforts to enhance political sustainability. 6.5 Sustainable reform is difficult to achieve in countries that have corrupt power structures and court systems. Under such circumstances, it is an open question whether World Bank assistance risks providing additional resources for rent seeking rather than support for reforms. 1For selected indicators regarding exchange rates, see the International Monetary Fund website at http\.//data.imf.org/regular.aspx?key=61545850. 2The Country Assistance Strategy for fiscal years 2012â€“16 reported that the general government deficit in 2010 was targeted at the equivalent of 5 percent of gross domestic product but was missed because of the deficit of Naftogaz, illustrating the connection between fiscal discipline, the losses of state-owned enterprises, and financial sector stability. 3The 2012 Household Budget Survey estimated that 19 percent of poor households and 16 percent of the bottom 40 percent had savings in financial institutions. 4 This is a temporary bank established to acquire the assets and liabilities of a failed bank. 5Between early 2015 and the end of 2016, the Deposit Guarantee Fund's staff increased from 200 to 399, and its budget doubled. Furthermore, most of the new staff was employed in the Department of Consolidated Sales and Asset Management, which had been created specifically to address problem bank resolution. 6The level of corruption in Ukraine is exceptionally high. This can severely undermine economic growth prospects, particularly by hindering private investment. Therefore, reducing corruption is essential to speed up the process of economic convergence with the rest of Europe (IMF 2017, 3).
P150751 | Bolivia Disaster Risk Managment DPC and DPL | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2015 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/761161510608562987/text/ICRR-Disclosable-P150751-11-13-2017-1510608555640.txt | http://documents.worldbank.org/curated/en/761161510608562987/pdf/ICRR-Disclosable-P150751-11-13-2017-1510608555640.pdf | The ICR provides the following key lessons (with some paraphrasing):The use of a single-tranche DevelopmentPolicy Operation (DPO) instrument to support the DRM agenda can lead to limited results during implementation. The use ofa single-tranche instrument was helpful to begin discussions on key national policy reforms; however, it was insufficient, giventhe time it is taking to implement these reforms. The Technical Assistance work helped to lay the foundation and create momentumfor this DPO and the programmatic engagement that was initially envisaged to support the countrys DRM agenda. Despite thisinitial strategy, the follow-on DPO and IPF operations did not materialize. In Bolivias case, the lack of familiarity withthe DPO instrument, the limited implementation time frame, and frequent changes in key Government personnel limited even furtherthe impact this instrument could have achieved and the use of programmatic financing strategy may have yielded moreresults.The time frame to achieve both medium-term program outcomes and results underthe DPO needs to consider external factors that may affect the pace of implementation. A Governmentprogram supported by a World Bank DPO, specifically if it is single tranche, can face many challenges given that the aim is tosupport policy reforms that take time to operationalize and implement. In addition, the preparation of this type of lendingoperation prior to elections faces the risk of likely post-election changes in key staff and shifting priorities during theimplementation phase that can affect project outcomes. An implementation time frame of 12-16 months provides limited time to adjustand address potential delays and negative impacts. Taking this into account, mitigation measures have to be discussed and agreedwith the Client during preparation. For example, during preparation of a DPO with a focus on DRM, the teams could considerpreparing a results matrix that (a) differentiates results that may realistically be attributed to the DPO within its timeframe;and (b) outlines program results over the medium term that can be attributable to the DPO, but need time for proper measurement, orfor full roll-out of detailed implementation measures such as local capacity building.Understandingthe institutional arrangements and expectations is key to supporting the implementation of policymeasures. During DPO design, it is important to understand the roles and responsibilities of different levels ofgovernment in policy design, approval, and implementation. In the case of this DPO, the local level was responsible for theimplementation of measures in several areas, but was not familiar with the financing instrument. As such, once institutionsunderstood that resources would not be channeled for specific interventions, the level of commitment and effort was reduced, withthe consequence that processes took longer than expected. In this context, a programmatic engagement benefiting from an IPF couldpotentially keep the reform momentum and support capital investments towards disaster risk reduction. In addition,inter-institutional coordination during implementation is key to push forward the DRM policy reforms and achieve results within thepolicy matrix. Therefore, it is important to have a strong ministry in charge of leading this inter-institutional coordination,which has the power and the authority to push the sectors and institutions involved in order to move forward the reformagenda.
P150754 | Comoros Social Safety Net Project | Eastern and Southern Africa | Comoros | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2015 | 2023 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099091224152033201/text/P150754-a8bbfd25-9ae4-42c8-9aa1-2996b51d005a.txt | https://documents.worldbank.org/curated/en/099091224152033201/pdf/P150754-a8bbfd25-9ae4-42c8-9aa1-2996b51d005a.pdf | The ICRR confirms the series of lessons and recommendations emerging from the projects experience (ICR, pp. 26-27). TheICRR summarizes the most relevant lessons below:Financial as well as technical support can increase theeffectiveness and sustainability of Income-Generating Activities. In particular in rural areas, where IGAs are related tothe agriculture sector, partnering with government (e.g., Ministry of Production) and/or Non-Governmental Organizations who havetechnical expertise can increase the chances of IGAs being successful and sustainable.Rehabilitating communityinfrastructure is an opportunity to improve not only the economic and social resilience at the community level, but also to improveresilience to future climate shocks. In particular, in countries that are vulnerable to climate change, cash-for-workprograms can be used to build more resilient infrastructure that can be managed and maintained by thecommunity.Balancing the introduction of digitalization with capacity building and technical support improves theefficiency of implementation while ensures thegreater inclusion of vulnerablepopulation. Training on the useof digital means and ensuring internetconnectivity allowed the project to reach a larger number of beneficiaries, especiallyin urban areas where internet connectivitywas available.The complexity in implementing at thedecentralized level with varying levels of capacities among the different islands requires a varied approach to technical supportand capacity building. In addition to different capacities, remote and difficult to access locations have additionallogistical challenges, in particular if the project is supporting the rehabilitation of infrastructure.Effectivecommunication between the central and regional authorities ensures bothsmooth implementation and ownership at all levels, inparticular when approaches are being implemented for the first time in a low-capacity context.AdditionalNote: The ICR missed an opportunity to draw lessons regarding some important aspects of the project such as (1)implementation challenges in rural versus urban areas and how they were addressed; (2) the different outcomes reached throughunconditional cash transfers versus IGA activities versus cash transfers with accompanying measures; and (3) the complexity ofadding an infrastructure rehabilitation component in a social protection program.
P150827 | Guinea-Bissau Public Sector Strengthening Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/577081634049860544/text/Guinea-Bissau-Public-Sector-Strengthening-Project.txt | http://documents.worldbank.org/curated/en/577081634049860544/pdf/Guinea-Bissau-Public-Sector-Strengthening-Project.pdf | The following lessons were drawn from the ICR and adopted by IEG:Theresults framework should have targetsattributable to the project and at a level of ambition feasible for the country context. In this case, the PDOsrelevance was reduced by selecting indicators that were not clearly attributable to the project and targets that were too ambitiousfor the country context.Success with PFM reform projects is critically dependent oncontext and the operating environment in a fragile situation such as in Guinea Bissau. The project aimed at coveringa range of PFM challenges from the revenue and expenditure side. While all were important, a broad approach was too taxingfor the authorities, translating into scattered and partial outcomes; rather, a more selective approach might have achieved andmore sustainable better results. One strategy for dealing with fragility challenges is to start with moderately ambitiousgoals and then refocus on those for which there is adequate support. This would respondto the difficulty of knowing inadvance which potential reforms are achievable.PFM reforms need to focus on behavior and policychanges as well as technical solutions. While reforms targeted by the project were directly linked to and integratedinto the governments reform agenda, volatility in government commitment proved to be a key challenge, where policy anchoringand sensitization could have helped to push forward lagging activities
P150844 | Rwanda Urban Development Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099605108112293045/text/P1508440b6cf9d09d0ad800efeef05d31c7.txt | http://documents.worldbank.org/curated/en/099605108112293045/pdf/P1508440b6cf9d09d0ad800efeef05d31c7.pdf | The ICR presented eight lessons for task teams to consider in designing future similar projects. Some of these arebelow,slightly modified: Consistent application of urban upgrading principles optimizes impact.Inthis project, the upgrading of the unplanned settlements in Agatare was to be a model for other urban upgrading inRwanda.Living conditionswereimproved with minimal resettlement or disruption in services.The followingupgradingprinciples were showcased: (i) onsiteupgrading with minimal relocation; (ii) communityinputs toinvestment decisions; (iii) use of flexible functional standards; (iv)standardizing costguidelines tooptimizelimited resources, such as establishing floors or ceilings forcost per hectare or cost per household; and (v)using area-based packaging of network infrastructurefor optimal impact. These principles were incorporated inthe design of the follow-on RUDP 2. Community participation in the project cycle - from start to implementation -fosterssustainability.In this project, the community participated only at preparation.In thefollow-onRUDP 2, each of the settlements created community upgrading committees toparticipate in the planning, design,implementation, and project oversight of upgrading activities. Forming dedicated focus groups consisting of women and othervulnerable groupsfacilitates institutional mechanisms forgender-inclusive and equitable investments and helpscoordinatesocial safety net responses. Making government resourcesavailable as soon asProjectAffected Persons(PAP) are identified helps avoid implementation delays.In this project, compensating PAPs wasidentified as a critical bottleneck in implementing works in Agatare settlement. Establishing compensation budgets and releasingpayments to PAPs slowed down the handover of construction sites to contractors. The use of flexible infrastructure standards helpedminimizeresettlement, and although still substantial, limited the size ofcompensation packages.In the follow-onRUDP 2, the government allocated US$15 million in the annual budgets of the implementing agencies to finance resettlement andcompensation costs. Integratingflood risk management in upgrading enhances resilience andmitigatesthe impacts of climate change.In this project, urban upgradingfinanced the construction of roads and drainage.Storm water runoff and erosion downstream could intensify without a drainage system in place, increasingflood risk andwetland deterioration. Household in the citys hilly terrain residing in the unplanned settlements are vulnerable to theimpacts of urban flooding. Flood managementwould increase infiltration capacity, retain storm water, and reduce the speed ofstorm water runoff. Flood management couldintegrategray infrastructure with nature-based solutions or greeninfrastructure. These green infrastructure interventions could provide social, recreational, economic, and environmental benefitsto residents(see ICR, Section II E Other Outcomes and Impacts). Clarifying functions of implementingagencies helpsenhancecoordination. In this project, MININFRA had the overall project coordination role. TheLODA SPIU carried out the day to day function butLODA did not report to and was not accountable to MININFRA. The lack ofclarity in the roles and responsibilities between the MININFRA PCU and LODA SPIU were reflected in the poor quality of earlyprojectmonitoring reportsPersistentproject management capacity gaps also showed this unclear roles carried out by theMININFRA PCU and the LODA SPIU. Future operations will benefit from assigningclearfunctions to each participatingagency. Attracting and retaining quality staff are hallmarks of successful implementation. In thisproject,factors that contributed to delayed hiring and retaining staffwere: (i) staff were hired with fixed-termcontract using cumbersomegovernment procedures; (ii) they startafter a project was approved or made effective; (iii)the governmentover assignsstaff duties; (iv) a limited pool of talent with the requisite technical skills and projectmanagement experience; and (v) qualified candidates are not attracted to short term (one year) contracts. Future urban operationsmay consider various measures such asthree-yearcontractswith an initial 612 monthprobationaryperiod;improving remuneration benefits;and collaborating with local schools and universities in training programs toincrease the talentpool.
P150922 | Ethiopia PFM Project | Eastern and Southern Africa | Ethiopia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099041823083512348/text/P150922037b5eb0b10b71c057f033f98d51.txt | http://documents.worldbank.org/curated/en/099041823083512348/pdf/P150922037b5eb0b10b71c057f033f98d51.pdf | When a government assigns procurement responsibilities to multiple agencies, it is critical to ensure close coordination (forexample, with secondment arrangements across agencies) and to set up a clear dispute-resolution mechanism to avoid delays. In thisproject, OFAG had technical responsibility for procurement, and MOFEC had selection responsibility. Lack of coordination amongthese agencies and political economy factors generated delays in procurement.To improve disbursement in the early yearsand improve project performance, the project should frontload some activities during design, such as ToR design. In this project,limitations in ToR and a weak follow-up of the OFAG contributed to the failed contract.To avoid or limit the impact ofturnover in senior leadership on project implementation, it is advisable to delegate project responsibilities to more juniorgovernment officials. In this project, there was significant senior leadership turnover in the first two years, which significantlyimpacted the projects pace of implementation.
P150924 | Comoros Second Economic Governance Reform Grant | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest |  |  | The ICR presents important lessons on the positive role of technical assistance activities on DPO performance, theconstraints placed by difficult relations between the central and island governments, and the additional Bank supervision that alow capacity context requires. IEG adds the following two lessons:1. 1. In low capacity settings,objectives on economic management and governance are likely to materialize slowly. In such settings, programs in those areas needto be designed with longer term horizons, where initial outputs (e.g., gradual consolidation of government accounts) lead to longerterm outcomes (e.g., efficiency gains in cash management) at the conclusion of the program.2. The privatesector can help overcome low capacity constraints. The award of a license to a private telecom operator in Comoros contributedsignificantly to expand access. The built in capacity of a private operator can help overcome Government limitations. The telecomreforms contrast with power sector reforms, where low operational and financial capacity makes progress more difficult andlongerto achieve.
P150929 | Burundi- Infrastructure Resilience Emergency Project | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2015 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/865261586789315844/text/Burundi-BI-Infrastructure-Resilience-Emergency.txt | http://documents.worldbank.org/curated/en/865261586789315844/pdf/Burundi-BI-Infrastructure-Resilience-Emergency.pdf | The ICR (p. 41-42) provided useful lessons learned which were adapted by IEG: Embedding a maintenanceprogram in the design of a climate-resilient infrastructure project is critical for ensuring the sustainability of past and futureinvestments. This project did not include a maintenance program and among the risks to its development outcomes are thelack of financing for the maintenance of urban infrastructure and roads. Building capacity for climate-resilientroad asset management at the national and local level allows to move away from a reactive decision-making process to a risk-basedapproach. In this project, an investment program was combined with road asset and DRM activities to build localcapacity. Using the local market for labor-intensive works ensures to build local capacity and communityownership. This project procured certain activities such as spots improvement and drainage structure construction from thelocal market which allowed for the hiring of local women and youth.
P150930 | MA-Large Scale Irrigation Modernization Project | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099120623121069562/text/P15093004932fa09f0af740be968275c8d2.txt | http://documents.worldbank.org/curated/en/099120623121069562/pdf/P15093004932fa09f0af740be968275c8d2.pdf | The ICR included six lessons. the following three are emphasized with some adaptation of language:1.Waterefficiency in agriculture can be effectively supported not only via infrastructure investments but alsobyinvolving technical assistance, digital innovations, and agricultural advisory services tofarmers. The project experience showed thatdigital solutions, including precise irrigation using irrigationsensors, need to be embedded in the design of an irrigation modernization project toenablethe most efficient andeconomical way of watering crops. Also, modernization in irrigation shouldbe complemented by strengthening the capacities ofthe agricultural advisory services to farmers. Furthermore, flexible management of water allocations for farmers (such as providingfarmers with water quotas information at the beginning of the season and allowing for the exchange of quotas) as well as the jointmanagement of groundwater and surface water resources, given the high interrelation between the two areneeded.2.To alleviate climate risks related to water scarcity, it is important that irrigationprojectscomprise a climate-informed design.The project experience showed that when irrigation modernizationprojects are impacted by the drought their technical and economic benefits can be jeopardized. These operations would be moreefficient if their designs were more climate informed. Proper water accounting should also be embedded in the investment studies.In addition, ensuring intersectoral water allocation management is key to secure water supplies for irrigated agriculture toeffectively execute the desired cropping patterns.3. Establishing a collaborative leadership for the developmentapproach is key to achievingan efficient results-oriented implementation process.The project experience showedthatinvolving all parties in the planning and execution stages, namely the Directorate of Irrigation and Rural Infrastructure(DIAEA) and the Regional Agricultural Development Offices (ORMVAs) as well as the Water Users Associations (WUAs), theproject-built consensus, enhanced coordination, and ensured the ownership on the part of the actors. Also, effective collaborationbetween central and regional actors helped to prevent implementation lags. This also ensured compliance with Environmentalsafeguards; the involvement of the Regional Project Management Unit (RPMU) members; sharing of work schedules with the environmentfocal points (EFPs), support to the EFPs in the resolution of the non-conformities, and involvement of the EFPs at the temporaryand final approvals of the works.4. A participatory process that includes farmer beneficiaries, as well asinstitutional stakeholders from the beginning of irrigation projects is more likely to ensure ownership for improved irrigationtechnologies. The project experience showed that irrigation modernization projects remain highly dependent on thecommitment of farmers to sustain the momentum by investing in on-farm equipment. However, in many cases, projects start theengagement with the farmers only after the commencement or even completion of construction. As noted in the beneficiary survey, theneed for a proactive and early involvement of farmers in the process is a key requirement for ensuring ownership of the irrigationtechnologies. The users involvement needs to start from the beginning, to enable participatory discussions on agribusinessmodels, irrigation demand, service agreements and beneficiaries responsibilities, and to inform irrigation system planning,design, construction, and OM. In addition to the farmers, it is essential for an irrigation modernization project to alsoengage institutional water management stakeholders, particularly River Basin Organizations, at an early stage.
P150938 | Financial Sector Support Project | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099015106302226366/text/P150938000e0290700ae7b0a9efcd764f4d.txt | http://documents.worldbank.org/curated/en/099015106302226366/pdf/P150938000e0290700ae7b0a9efcd764f4d.pdf | Three lessons are drawn from the ICR (pages 27-30), with some adaptation.States can improve their financialmarket infrastructure and strengthen their banking system by actively responding to recurring cyber threats against paymentssystems.The Bangladesh Bank cyber heist, committed half-a-year after this project started in February 2016,exemplifiesthe serious challenges continually faced by the authorities to keep payments systems safe and secure.Hackers, ostensibly aided by insiders, exploited weaknesses in the central banks access to the Society for Worldwide InterbankFinancial Telecommunication (SWIFT) global payment network to illegally transfer US$121 million and attempt to divert anotherUS$850 million fromthe central banks account at the Federal Reserve Bank of New York to fraudulent accounts in Sri Lankaandthe Philippines. In the context of this and similar projects, investments in cyber security would tend to be vitalpartsofprogramsto upgrade the financial market infrastructure. Additionally, measures to improve corporategovernance and foster ethical behavior among a financial institutions staff would strengthenefforts toreformbanking regulation and supervision.Strengthening banking regulation and supervision can help statesrestore financial soundness after an economic crisis, when economic distress would have invited temporary regulatoryrelief. The outbreak of the COVID-19pandemic in 2020, into the fifth year of this project,promptedmacro-financial policy responses that made it difficult, at least temporarily, to install a stricter bankingregulation and supervision regime. In addition to liquidity support programs and interest rates cuts, Bangladesh Bankembarked on a series of regulatory relief measure to help ease financial conditions at a time of economic distress thecentral bank delayed non-performing loan classifications, relaxed loan rescheduling policies, waived credit card fees, suspendedloan interest payments, relaxed credit risk rating rules for banks, extended the tenures of trade instruments, and allowedshort-term farm loan rescheduling. In actionsthat negatively affected this project, theauthorities delayedthepassage of the amendment to the Bank Company Act and the issuance of the prompt corrective action circular by BangladeshBank. While the regulatory relief responses were sufficiently justified, the Bangladesh Bank has since started working onaregulatory relaxation exit strategy that aims to strengthen the bankingregulatory and supervisory frameworkandreducefinancial sector vulnerabilities.In line of credit operations, streamlining complicated loanapproval processes can contribute to operationalefficiency gains. In this project, the readydisbursement of LTFF sub-loans for sub-projects was derailed by the absence of state budget allocations from the Ministry ofFinance, and when prepared, even these budget allocations had to be cleared by the Department of Planning. Meanwhile,participating financial institutions that signed loan agreements with sub-borrowers had to submit project documents to BangladeshBank, which reviewed eachsub-loan for compliance with project requirements, including that the sub-loan disbursement wascovered by a state budget allocation. Line of credit operations that utilize state bodies as apex institutionsmust invariably followgovernmental spendingprocessesand disbursement procedures, which, however, can turn out tobe overly complicated and needlesslybureaucratic. To address this issue, project planners might design streamlinedsub-loan approval processes at appraisal and embed these as covenants in loanagreements, or alternatively explore using asapex institutions other intermediariesthat were subject to minimal state bureaucraticprocesses.
P150941 | Eight Economic Reform Support Grant 8 | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | In addition to the lessons presented in the ICR, IEG draws four main lessons from the experience of designing and implementingthisseries: Effective ownership of the program by sector ministries and agencies requires systematic capacitybuilding. In this case, the risks attached to Ministry of Finance control and ownership of the design, implementation andmonitoring of the reform program were recognized, and attempts were made from the outset to involve the sector agencies in thediscussion. Later they were assisted by specialists who designed medium term expenditure programs for the sector agencies. However,little use was made of these instruments, since the staff of the sector agencies had neither the relevant expertise norinstitutional incentives to adopt the instruments as their own. For reforms involving privatization,extensive and in-depth consultation with all major stakeholders can help design a program that is acceptable to, and consistentwith the ambitions of, affected parties. In this case, the previously successful privatization of a number of coffeewashing stations led to the assumption that the privatization of the remainder would also succeed. This, however, did not takeaccount of the changing perceptions and developing ambitions of the coffee growers. Pursuit of reformsthat do not have the necessary degree of political backing is unlikely to be successful. Although the series supported thedevelopment of a new Mining Code and the establishment of a commission to guide the country towards membership of the EITI, thelack of progress in negotiations with the international body, together with the fact that not one of nine benchmarks for membershipwas achieved, suggests that political buy-in for the necessary degree of transparency in the mining sector was not strongenough. A modest and incremental approach towards assisting the very poor and vulnerable can paydividends, especially in a fragile country context. Careful data building efforts, combined with flexibility in terms ofthe institutional framework and attention to local voices, can result in an important increase in the percentage of the very poorcovered by at least one social safety net.
P150950 | Tunisia: Third Governance, Opportunities, and Jobs DPL | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons are drawn by IEG:A complex transition requires careful considerationof trade-offs between ambition and feasibility in project design. In Tunisia, political pressures and economic challengescalled for broad multi-sectoral interventions, but success might have been greater with a more careful assessment of institutionalcapacity in key reform areas.Reforms are especially prone to being undermined by their weakestlink. In Tunisia, employment reforms were affected by the lack of ownership of the employment agency. In such instances,other actors, for example non-governmental organizations, can be helpful through outsourcing.
P150976 | Senegal-Third Governance and Growth Support Credit | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons are drawn from the ICR:Budget support series should pay attention toabsorptive capacity. While budget support provides the opportunity for ambitious coverage and tacklingmanyissues, absorptive capacity in government agencies will often be the limiting factor; it needs to be carefully weighed againstpotential overreach in program design. The GGSC series was ambitious, increasing the burden on both Bank staff and theadministration, and placing the quality of reforms at risk.Prior actions need to be followedup. The passage of laws and regulations the usual contents of prior actions is a first step inreform; once passed, they also need to be put into practice, and this requires the necessary skills and, often, access to companiontechnical assistanceto build up those skills. Significant delays were experiencedin a number of instances in thisprogram, notably the application of financial regimes for universities experienced significant delays due to a lack of follow-up inthe Ministry of Finance that was in charge of the setting the budget nomenclature.
P150991 | GZ-Integrated Cities and Urban Development Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099120723163022660/text/P1509910a1525a0c10a42c083b1126b0ccc.txt | http://documents.worldbank.org/curated/en/099120723163022660/pdf/P1509910a1525a0c10a42c083b1126b0ccc.pdf | Some of the key lessons highlighted in the ICR include the following:Joint intra-urban spatial and capitalinfrastructure planning can contribute to sustainable urban growth planning and help strengthen municipal roles andaccountabilities.In the Palestinian context, intra-urban coordination was an effective instrument to plan acrossLGU boundaries to achieve sustainable urban area scale land use planning, as well as coordinated infrastructure provision and basicservice coverage. It demonstrated the strategic benefits of coordinated planning at the urban area scale. This supported addressingboth land use and zoning, alongside the detailed consideration of infrastructure development and services provision, to supportprogramming future investments. With implications for LGUs role and budgets, this work also help aid local transparencythrough, for example, this disclosure of baseline reports conducted. This further helped to strengthen municipal accountability,enhancing the link between communities and local government.Taking a flexible and responsivedemand-driven approach to capacity development mayprovide beneficial flexibility in an FCVcontext.The ability to provide flexible training and capacity building activities in response to emerging demandsand a changing context (such as the near blockade and conflict in Gaza as well as the outbreak of COVID-19), enabled opportunitiesand challenges to be addressed swiftly to support municipalities. Frontloading capacity building and training at the beginning ofplanned activities enabled municipal staff to better engage with the project activities. It also provided flexible forward-lookingsupport to municipalities aimed at service-continuity and resilience over the long-term.If politicalengagement and senior governmental commitment to capacity building is not forthcoming, learning may not be absorbed to embedvalue.Achieving greater local government level policy and planning consistency, coordination and connectivity ina fragile environment facing the challenges of geographic separation, movement restrictions and conflict with neighboringareas is a difficult undertaking. Capacity building initiatives that generate new co-ordination potential where littlepreviously existed, require strong governance commitment to ensure the uptake of opportunities for ongoing development. A stagedlong-run approach is necessary to achieve results beyond a relatively short-term technical capacity grant. Technically focused,planning-oriented work remains one element to drive coordination and shared outcome buildinginitiatives.Demonstrating the benefits of coordinated intra-urban planning and joint investment throughsmall-scale pilot projects may assist in building long-term benefits.Creating a big constructivevision while doing small tangible interventions to get results and build capacity and political capital on theground, can help to accelerate engagement, joint LGU commitments and momentum for positive progress. The approach tourban planning introduced for the first time in the Palestinian territories was a long-term goal of MoLG and required significantchanges to existing working arrangements at a municipal and ministerial level. This presented several challenges and necessitatedsignificant political leadership and required a shared sense of ownership and buy-in to be developed during project implementation.However, future large-scale vision and investment will be required to prove the long-term benefits of coordinated jointplanning.
P151007 | Enhancing Fiscal Management, Social Protection and Financial Inclusion | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2018 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/959051575910357655/text/Paraguay-PY-DPL-DDO.txt | http://documents.worldbank.org/curated/en/959051575910357655/pdf/Paraguay-PY-DPL-DDO.pdf | The following lessons are drawn from the ICR:Strong government commitment increases opportunity forreform. Strong Government commitment, for instance as reflected in broad stakeholder commitment to a reform agenda islikely to lead to successful outcomes. In Paraguay, the countrys long-term reform program had been developed with theparticipation of a large number of stakeholders, facilitating implementation.Strong analytical workunderlies successful substantive reform. Program design should be underpinned by strong analytical work andtechnical assistance. The DPL was based on prior strong research, which, in turn, provided the necessary rationale for selection ofpolicy and program reform areas.IEG adds the following lesson:Clearlyformulatedprior actions, with a robust causal chain to the intended results, are important for the success of developmentpolicy operations. In this case, the prior actions related to the substantially achieved first objective were mostlyprecise, relevant andmeasurable. Those for the second and third objectives, where outcome was much weaker, were few in numberand were not formulated with the appropriate degree of precision and detail.
P151058 | Nouadhibou Eco-Seafood Cluster Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099195002062336698/text/P15105802b396b0f50a905076e25fc58987.txt | http://documents.worldbank.org/curated/en/099195002062336698/pdf/P15105802b396b0f50a905076e25fc58987.pdf | The ICR draws the following main lessons from implementing this project, with some adaptation of language.1. Acareful assessment of the political economy considerations at design can help in reducing implementation delays. TheProject Implementation Unit (PIU) in this project was located outside the central government agencies. It was located in theNouadhibou Free Trade Authority (ANZF), a newly established entity with limited management experience and an unclearmandate.The strained relationships between the central government and ANZF contributed to implementationdelays.2. Adding a component weakly linked to project performance can increase project complexity and affectperformance. In this project, activities covering PPP and investment climate were added to this project with AF toavoid the time for preparing an entirely new project. The added activities had a national scope and loosely linked to the originalactivities in the fisheries sector. This increased the projects complexity and contributed to the projects lowrating.3. The design needs to be realistic about the time for implementing new activities. The time spanfor the AF project was approximately two years, from September 2019 to November 2021. This time frame was ambitious, given therange of activities supported by the AF project.4. A clear understanding of the priorities of the private sectorwould help projects seeking to target private sector participation in a sector. Although a Public-Private Dialogue (PPD)forum was created under this project, the private sector was not able to participate in the forum, as its basic priorities (such asbasic service needs) were given little consideration. This undermined private sector participation in the sector.
P151075 | Pakistan Community Support Project (CASA-1000) | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | RETF | IPF | 2020 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100724160042591/text/P151075-b26238f0-865f-4605-ba7b-3fef0e041364.txt | https://documents.worldbank.org/curated/en/099100724160042591/pdf/P151075-b26238f0-865f-4605-ba7b-3fef0e041364.pdf | Implementing standalone projects can be highly effective in delivering local infrastructure and services. TheCDD model used by the project was able to efficiently and equitably develop village-level infrastructure, providing public goodsthat were acceptable to most villagers. The endline survey respondents showed high satisfaction with the quality of infrastructure.The involvement of various sub-committees brought diverse perspectives and expertise. A standalone project allowed for specializedteams with expertise in community-driven approaches, which might not have been possible if benefit-sharing activities had been asubcomponent of the CASA-1000 project. It also enabled strategic engagement with the Government of KP on the development of theMerged Areas, supported by the $200 million KP Rural Investment and Institutional Support Project (effective September 2023).However, a drawback of implementing a standalone project was the misalignment between benefit-sharing activities and the CASA-1000construction timeline, highlighting the need for better synchronization with larger initiatives.A well-designedproject GRM can significantly enhance citizen-state trust, especially in regions with weaker state capacity and less empoweredcitizens. The project benefitted from the established a robust GRM not just for project specific feedback and complaints,but also to coordinate with the GRM of the CASA-1000 project. Collaboration with the CASA-1000 Projects GRM at NationalTransmission and Dispatch Company (NTDC) was crucial in resolving issues, requiring coordination between federal, provincial, andlocal entities to an extent that was new to the region. In addition, the GRMs toll-free Interactive voice response (IVR)system regularly surveyed community members and gathered feedback.Involving youth and women in project design cansignificantly enhance social sustainability. The Project was able to strengthen womens inclusion in developmentactivities in the region, which was challenging given the traditional norms in the tribal, patriarchal culture of the projectvillages. The PMU created Women Sub-Committees (WSCs) which helped to fulfill the minimum requirements for womens inclusion inthe development planning process and also conducted women-centric activities. To avoid tokenization, CDC members needed atwo-thirds majority endorsement from WSC members for approval of resolution and endorsement from 20% women in the WSC for releaseof installments. The project also engaged the Youth Development Committees (YDCs) to support CDCs in sub-project implementationusing digital skills, such as disseminating project information and conducting audits. These trained youth would be valuable assetsfor future community development. However, endline surveys indicated that women struggled to stay involved in the implementation ofschemes post-approval.Establishing and empowering village-level institutions such as CDCs can significantlyenhance local contribution and accountability. However, their long-term sustainability will depend on factors such as continuedsupport and integration with evolving local governance structures. The project was able to officially register CDCs andestablish bank accounts, creating a direct funds flow mechanism to the community level. Community contributions to localinfrastructure exceeded expectations, averaging over US$ 4000 per scheme. The principles of community funding and beneficiaryresponsibility require responsive and accountable intermediary institutions. As local government structures evolve and take on moreresponsibilities, practices from the project, such as needs analysis and participatory budgeting, may help establish more inclusivedevelopment processes. However, the long-term sustainability of the CDCs and the infrastructure they manage remains uncertain,though as of March 2024, 28 CDCs were actively maintaining important public infrastructure.
P151086 | Vietnam Energy Efficiency for Industrial Enterprises(VEEIE) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2017 | 2023 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062923142175287/text/P151086040ac2a02d085610da37080d03ff.txt | http://documents.worldbank.org/curated/en/099062923142175287/pdf/P151086040ac2a02d085610da37080d03ff.pdf | The following lessons were derived from the ICR with somemodifications by IEG (ICR, pages 35-36):1. The Projecthas been recognized by the Government and private sector for demonstrating economic, financial, and environmental benefits of EEinvestments and for creating an on-lending mechanism, which was effective in mobilizing remarkable private capital funding. Thecredit line supported by the Project had a significant leveraging effect, mobilizing a sizable private financing for EE in theamount of US$87 million, from PFIs and IEs, and turned out to support a scale-up. Such an important outcome would not be possibleif the Project did not address such EE financing barriers as the lack of incentives, insufficient liquidity, and short-termmaturity of the loans. It did so by using the KGGTF grant funding and by utilizing TA support from other Bank and IFC projects. Thelesson is that in countries with economic and political incentives to implement EE and a strong Government ownership in relation toEE projects, a parallel development of a financial mechanism for EE and capacity building for EE can be a most effective andefficient approach to EE mainstreaming.2. Selection of strong PFIs with dedicated project teams was vital for thesuccess of the EE credit line created by the Project. The Project benefited from a sound commitment of the PFIs managementto the EE lending strategy and their dedicated project teams. The Project also benefited from a wide PFI participation, whichenhanced the IE client base, covering a range of industrial clients and increasing the opportunities for EE lending. The lesson isthat during the preparation stage, a careful selection of strong PFIs with dedicated project staff is critical for a successfulcreation of an EE financing mechanism.3. The Project relied too much on the risk tolerance of the PFIs and credit ratingsof the IEs, which explains why it was not successful in attracting the expected number of subprojects and a variety of EEtechnology types. The Project suffered from risk aversion of some PFIs (in particular, to lending to steel and cement IEs), andmany perspective EE subprojects were not financed because the PFIs considered the IEs credit ratings to be too low. Thelesson is that to avoid such experience: (i) a more intensive, well-financed, and well-supervised TA to the PFI would be a goodmitigating mechanism; and (ii) a wider range of EE technologies and additional financial instruments could be considered.Specifically, the follow-up Vietnam Scaling up Energy Efficiency Project (P164938, approved in 2019) used a US$8.3 million grantfor TA and focused on the development of a risk sharing facility to provide partial credit guarantees to the PFIs.
P151089 | West Bank and Gaza: Finance for Jobs | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050523193524895/text/P15108907471870a10b3d8072e76b1ee068.txt | http://documents.worldbank.org/curated/en/099050523193524895/pdf/P15108907471870a10b3d8072e76b1ee068.pdf | Twolessons are drawn from the ICR, with some adaptation.The series of projects (SOP) can be anappropriate instrument when innovative solutions are being introduced and in FCS settings where institutionalcapacityisfledgling. In this operation, the Bank and the authorities sought to test three innovativefinancial solutions to mobilize private sector financing for job creation initiatives the matching grant facility forbusiness development services, the investment co-financing facility for jobs-based projects, and the development impact bond.The SOP instrument was an appropriate choice because the projects activities had to be carefullyphased over time, substantialeffort was needed to build knowledge and consensus among stakeholders, and the financial instruments being tested requiredstagingand adjustmentas experience with their deploymentevolved.Integrating socialbenefits in the assessment and choice of private sector projects can resultin a project poolwith greater developmentalimpact. In this project, the Bank developeda social rate of return methodology to analyzeand rankjob-creation projects proposed by the private sector for financing by the ICF. Seven of nine project proposals subjected tothefeasibility assessment managed by the PIA graduated to the pipeline by closing. The projects drew capitalcommitments of about US$35 million from private investors. Importantly, for the job-creation goals of the F4JSOP, theseprojects could generate about 2,112 jobs.
P151102 | Integrated Forest Ecosystem Management | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099100923101540081/text/P151102019a6800c509bb10ef8cd4841c2e.txt | http://documents.worldbank.org/curated/en/099100923101540081/pdf/P151102019a6800c509bb10ef8cd4841c2e.pdf | The following lessons are derived from the ICR with some adaptation of language:1.Candid ratings onproject progress during implementation may allow proactivityin addressing key implementation issues at an early stage.The project faced considerable delays and challenges, e.g., in procurement, which were affecting implementation progressin its first few years. However, ratings remained Moderately Satisfactory. While downgrading ratings is a significant decision withimplications for both the project and the broader message from the Bank in the country, a timely downgrade could have initiatedcorrective actions to be put in place. Noting that downgrading is not always an easy decision, project management should beprepared to take a calculated risk to downgrade project progress in similar circumstances.2. Developingaforest management information system not only generatesimportant benefits for forestry operations and policy butalsohelps to improve forest ecosystem management and governance. In the context of limited capacity and experience,the phased roll-out of theForest Management Information System(FMIS) allowed for a gradual introduction to new softwarethat was adopted by all 41 leskhozes, not just the pilots. With the measures taken by the Forest Service (FS), the FMIS is alreadycontributing to increased operational efficiency and the supply of better information, thereby helping to improve forest ecosystemmanagement and governance.For the FMIS tobe effective and serve as a strategic tool for economic growth withwider benefits in terms of transparency and participation, it is important to be adequately resourced and receive ongoinginstitutional support. Future operations can take note of the value of a phased approach to information systems and the need toprovide enabling institutional and financial frameworks to ensure wider benefits.3. While targeted institutionalreforms are an effective and efficient use of resources, they could also steerimportant yet complex policy and institutionalreforms in the forest sector. The project used a flexible, non-prescriptive approach to identifying strategic directionsand interventions, e.g., a sector functional analysis and a consultative Forest Code revision. These activities were carried outwith relatively small levels of financing but, nonetheless, are critical in steering important yet complex policy and institutionalreforms in the forest sector. Projects would benefit from taking similar flexible approaches to identifying interventions that canhave far-reaching impacts.
P151155 | CAMEROON - Strengthening Public Sector Effectiveness and Statistical Capacity Project | Western and Central Africa | Cameroon | Blend | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2018 | 2024 | 2025 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099121324175013245/text/P151155-737b785f-f4f5-4466-87b0-175a67287a51.txt | https://documents.worldbank.org/curated/en/099121324175013245/pdf/P151155-737b785f-f4f5-4466-87b0-175a67287a51.pdf | The ICRR agrees with the lessons from the ICR but would like to highlight the following:Ina countryfacing instability, such asCameroon, project designshould be simple and focus on a few keyareas.Cameroon was added to the FCV list in 2018, after the project was approved. However, the political situationhad been deteriorating. Despite many needs and requests from the government and other stakeholders, it is important to chooseclear, manageable objectives from the start. This helps overcome capacity constraints and challenges in coordinating with multiplestakeholders.ME should be a key part of a projects operations and managed effectively to provide timelydata for project management. It is important for the PCU to develop and use an ME manual even if not required, and toensure that ME specialists have the necessary skills. The WBteam should also actively address ME issues, includingduring project restructuring.
P151157 | BiH Floods Emergency Recovery Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2014 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/952401584389793453/text/Bosnia-and-Herzegovina-BiH-Floods-Emergency-Recovery-Project.txt | http://documents.worldbank.org/curated/en/952401584389793453/pdf/Bosnia-and-Herzegovina-BiH-Floods-Emergency-Recovery-Project.pdf | The ICR presented 12 lessons and recommendations from the projectoperations. IEG has selected the following lessons thatmay benefit other task teams designing similar projects: A task team with strong in-country experience andseasoned in rapid response project preparationshould benefit from usingstreamlined procedures. In thisproject, a strong task team was well versed in the countrys policy environment and governance and administrative structures.The team included technical experts on flood management, landslides and rehabilitation of infrastructure to help identify qualityissues in specific sub-projects and support the implementation units in addressing issues as these arise. The lesson from thisproject was that a project may benefit having a strong task team familiar with the country policy environmentandknowledgeable in rapid response project preparation. Using a positive list and allowing for retroactivefinancing may be an effective way to implement emergency response projects. In this project, a positive listidentifieditems eligible for retroactive financing. Reimbursement was applied to goods purchased during the emergency phase,goods that the government intended to purchase as part of its continuing response to the emergency, and goods to replenish stocksdepleted during the emergency. Agreement was reached that the RNA would serve as the basis for identifying items that would beretroactively financed. Simplified procurement procedures during the early phase of implementation, carried out by PIUs familiarwith World Bank procedures,also contributed to quick delivery of emergency response goods to the large number ofbeneficiaries.A framework approach and robust eligibility criteria with evidence-based prioritization, facilitated therehabilitation of infrastructure essential for public services and economic recovery. Decentralizedimplementation of an emergency response project empowers participating municipal authorities to build on their proximity withrecipient beneficiaries to build local DRM capacity. In this project, local authorities supported by dedicated personalimplemented andcommunicated with beneficiaries. Communication with local beneficiaries was effectivebecause oftheproximity between the places where decisions on sub-projects were made (municipal assemblies) and project beneficiaries. Inaddition, local experienced staff directly reached out to the project beneficiaries explaining the project objectives anddecisions. These factorsfostered beneficiary engagement and positively contributed to ademand-basedprioritizationof investments. Procurement procedures in emergency response and recovery projects may include cut-off dates totrigger re-allocation of funds when there are significant delays. In this project, restructuring followed the MidTerm Review and determined that the allocated funds for the first component exceeded need. The amount reduced was reallocated tothe component that dealt with local and regional infrastructure reconstruction and rehabilitation. This action served to keepfocused on achieving the desired project outcomes. Adopting a build back better strategy foremergency response operations may improve the resilience of rehabilitated infrastructure. In this project, improvingresilience in the affected areas was not a primary project outcome. Nevertheless, the flood protection works financed by theproject improved resilience of infrastructure in those areas (flood protection works were designed for a 100-year return periodflood while pre-disaster flood protection works were typically designed for shorter return periods). In a March 2019consultation,project beneficiaries agreed that public infrastructure financed under the project was more resilient than itscondition prior to the May 2014 floods. Accountability and municipal co-financing are effective mechanisms toreach a larger number of beneficiaries and contribute to efficient projectimplementation.In thisproject,accountability by local governments was evident in their promotion of stakeholder participation, fostered buy-in, andownership in project decision. Local governments also co-financed rehabilitation works, selected sub-projects, communicated withbeneficiaries, and implemented works. In this project,municipalities financed the preparation of feasibility studies anddetailed designs for priority infrastructure. This strategy led to executing a larger number of infrastructureinvestments,expanded project coverage, and reached more beneficiaries. Since only viable works werefinanced, projectimplementation was accelerated.Promoting accountability at the local level was critical in this post-disaster situation whendecisions had to be made rapidly and enforced just as quickly.
P151215 | Emergency Food and Livestock Crisis Response Project | Western and Central Africa | Chad | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/697831621627791705/text/Chad-Emergency-Food-and-Livestock-Crisis-Resp.txt | http://documents.worldbank.org/curated/en/697831621627791705/pdf/Chad-Emergency-Food-and-Livestock-Crisis-Resp.pdf | The ICR presents 6lessons which are based on project implementation experience and supporting evidence, considering bothpositive and mixed performance (ICR, paras. 104 - 108). The relevant aspects of the lessons that havebroader application beyond this project are summarized below. IEG suggests one additional lesson, which provides a furtherelaboration of the sixth lesson.(1) Ownership and Strategies: Country ownership, including strongalignment of the project with national policies and strategies, coupled with clear, timebound and sound implementation andsustainability action plan, especially for an emergency type of project, is crucial to lay a strong foundation for securingtangible and sustainable results; (2) Attainable Objectives: Practical and attainable objectives, coupledwith coherent components and prioritized interventions are vital to generate tangible and sustainable results, especially in thecontext of a short-term emergency project, taking into account the available timeframe and resources;(3) Mixture ofOutput and Outcome Performance Measures: Emergency-type of projects should endeavor to include an appropriate mix of output andoutcome performance measures, especially during an expanded phase of financial support, which can contribute to laying a soundfoundation for developmental-type of approaches to sustainable development;(4) Practical Approach to EmergencyOperations: There are strong practical advantages for an emergency-type of project to utilize, finance, build-on and expand,and strengthen agencies and activities which are already in place and operational, while making the relevant adjustments to achieveand sustain the project objectives. This approach also balances the need to ensure implementation readiness, adequacy offiduciary arrangements and the strengthening of local capacities, especially to enable the transition from emergency support todevelopmental support;(5) Role of Partner Agencies: Emergency-type of operations merit reliance on utilizingpartner development agencies which demonstrate a comparative advantage for helping to meet the project objectives, which ensuringthey carryout appropriate actions to strengthen relevant local entities to enable the transition to more sustainable developmentalapproaches and results; (6) Strategic Nexus: There is a strong nexus between emergency situations andsustainable socioeconomic development, accompanied by the appropriate type of project interventions. Short-term emergencyoperations which are aimed at improving food security of populations in time of crisis are best accompanied by an operationalmedium to long-term plan of activities aimed at strengthening national capacities, resilience, combatting poverty, improving locallivelihoods, creating jobs and generating increased incomes of the target populations. Accordingly, this nexus is enabled and bestachieved when an emergency-type of project devises and operationalizes relevant action plan and outcome indicators and measures topromote and assess progress toward meeting the projects follow up phase, especially with respect to developmentalobjectives.An additional lesson arising from this ICRR is that results-focused emergency projects include explicit actionplans, measures and arrangementsfor helping to scale-up and sustain relevant emergency and sustainable interventions,especially to ensure tangible pathwaysto achieving the above-mentioned nexus between emergency operations and sustainablesocio-economic development.
P151275 | BF - DPO - Growth and Compet. Credit 4 | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest |  |  | This review draws the following three lessons (with the first two from the ICR):1. Inadequate consultation with allrelevant stakeholders increases the risks that draft legislation submitted as a prior action will not pass opportunely to achievethe expected effects. The draft mining code and anticorruption legislation suffered from inadequate vetting, resulted in lateapproval, and had no impact during the program.2. In low capacity environments, objectives to buildcapacity may be more appropriate than objectives to achieve the long-term welfare goals of added capacity. Capacity building mayhave been what the less ambitious DPO4 program objectives (to enhance the governments ability in three areas) aimed for.However, such enhancements need to be measured. For example, enhanced government ability to reduce costs in agriculturerequires evidence to link reforms to cost reductions. Implementing reforms (by capitalizing the input fund) alone is not evidenceof the expected outcome.3. Mitigation of risksis unlikely tobenefit from mitigation measureswith impacts that are dependent of the risks that the measures aim to mitigate. For example, reforms to expand cotton productionwill hardly qualify as a mitigation measure for the risk of unanticipated production and/or price shocks on cotton production.
P151275 | BF - DPO - Growth and Compet. Credit 4 | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/494031533935601565/text/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.txt | http://documents.worldbank.org/curated/en/494031533935601565/pdf/127424-PPAR-P126207-P132210-P146640-P151275-PUBLIC-on-8-13-18-PPAR-Burkina-Faso-Growth-and-Competitiveness.pdf | 6. Lessons â€¢ When political risks are high and capacity is strained, design is better focused on a few key priorities. This series covered too many areas, and some key binding constraints were not addressed. The series might have been more successful with a sharper focus on more realistic objectives accompanied by a simpler design. â€¢ The success of budgetary support depends on the suitability of the instrument to the country environment. In a context of political turbulence and uncertainties about the government's ability to undertake long term reforms, the World Bank could have ended the programmatic series after the third operation and made the fourth operation a stand-alone. Alternatively, the World Bank could have implemented a series of stand-alone operations after the second programmatic series when it became apparent that the political and policy environment was rapidly changing. â€¢ Lack of clarity on the respective roles and responsibilities of central and local governments and of the private sector undermines policy actions. It is important to ensure that there is a shared vision and that the need for reform is recognized and accepted by all parties. In this case, there was a lack of clarity among different stakeholders during implementation of the reforms on decentralization and fertilizer distribution. â€¢ When M&E is not adequately resourced or implemented, there can be delays in the identification of problems and the application of remedies. M&E weaknesses can be compensated by leveraging information available elsewhere, or through specific impact assessments and perceptions surveys. â€¢ There may be a trade-off between the promise of continuous and predictable financing, urgently needed in times of crisis, and the strength of the reform program. In Burkina Faso the emphasis was on continuous financing even when reform performance was waning. â€¢ The lack of broad consultations with stakeholders when the World Bank is designing a complex reform program could lead to unsatisfactory results. In this case, the lack of consultations with an important stakeholder association (the Confederation Paysanne du Faso) on fertilizer distribution affected the achievement of results of one of the first objectives. Also, some development partners and civil society organizations had limited knowledge of the reforms pursued in the G&C series. â€¢ Consultation with all important stakeholders is critical to inform program design. In this case, development partners, civil society organization, and academia complained to the PPAR mission about inadequate consultation by the World Bank. â€¢ Inadequately resourced implementing agencies will likely be unable to carry out agreed reforms. Under-resourcing may be an indication of low government commitment, which needs to be addressed through policy dialogue. It is also important to ensure that agencies have appropriate technical capacity and systems in place, and that potential political obstacles at the local level are being addressed.
P151279 | Social Protection System Support | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2015 | 2016 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/697921558632133742/text/Rwanda-Social-Protection-System-Support.txt | http://documents.worldbank.org/curated/en/697921558632133742/pdf/Rwanda-Social-Protection-System-Support.pdf | The lessons are drawn from the ICR.National vision can be an overridingfactor for success. Teams need to be alert to government commitment in recommending reforms. In Rwanda, thegovernments sustained policies and financial commitment to social protection has facilitated dialogue with the Bank anddevelopment partners and created government-led policies that have facilitated ambitious forwardmovement.Early action on accountability and transparency can enhance the credibility ofpublic programs. Broad support is often necessary if a social protection initiative is to be successful. InRwanda, the introduction of an appeals and complaints mechanism, and subsequently broader accountability initiatives (socialaccountability, citizens engagement tools) helped ensure that beneficiary and other stakeholder views were mainstreamed intoproject planning and implementation.
P151281 | Capacity Strengthening for Implementation of Minamata Convention on Mercury Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099102023134036841/text/P1512810b2b6ef02a0a1c40d12c3266c91a.txt | http://documents.worldbank.org/curated/en/099102023134036841/pdf/P1512810b2b6ef02a0a1c40d12c3266c91a.pdf | The ICR developed several lessons, the most relevant ones are presented as follows: Future projects onpollution issues in China or elsewhere could consider provincial pilots and subsequent integration into national-level monitoringsystems. Piloting the MIS in the project provinces proved to be a successful first step toward national operationalizationand the integration of the MIS into the NSBs existing information system, and an effective approach to ensure efficiency andsustainability. Piloting of the MIS in high mercury use provinces proved to be a successful method to showcase local governmentprogress and generate national interest in mercury flow monitoring and reporting. After the initial provincial pilot, the processof operationalizing the MIS at the national level and its integration into the NSB statistical system was lengthy and requiredcross-sectoral coordination, but these extra efforts were critical to ensure a sustainable and national impact and increasedefficiency. Implementation agreements with local governments, rather than full project management units at theprovincial level, can be an effective and efficient implementation modality for decentralizing project activities. Theimplementation modality of having the Foreign Economic Cooperation Office working closely with the provincial and municipalDepartment of Ecology and Environments on pilot activities based on implementation agreements proved to be very effective andefficient. Cost efficiency was achieved by allocating a relatively small percentage of the grant funding to the provincial andmunicipal environmental authorities to help coordinate and implement the relevant pilot activities. It also helped build capacityat the provincial level. Similar technical assistance projects with local pilot activities should consider using implementationagreements to ensure streamlined and effective participation by local governments. Mercury recycling can be acost-effective way to reduce the use of mercury in some industrial processes and recycling technologies and practices could bepiloted at the enterprise level to validate their technical and financial viability for scaling up to the entire industry.The assessments of mercury recycling technologies conducted under the project indicate that recycling is a cost-effective way toreduce use othe f mercury in some industries, such as non-ferrous metal smelting industry, especially in terms of reducing the useof primary mercury. In future investment operations, mercury recycling technologies and practices could be piloted at theenterprise level to validate their technical and financial viability for scaling up to the entire industry. It will alsopromotea circular economy, energy savings, and reduction of greenhouse gas emissions. The findings of the assessments laid agood foundation for follow-on projects.
P151318 | Mali - Higher Education Support Project | Western and Central Africa | Mali | IDA | FCS | Human Development | Education | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099632004262220803/text/P15131804c41ac0ad0b68e0d8b1d733b690.txt | http://documents.worldbank.org/curated/en/099632004262220803/pdf/P15131804c41ac0ad0b68e0d8b1d733b690.pdf | The following lessons, drawn from the ICR and slightly consolidated by IEG, are well-grounded in the ICRs storyline andrelevant to other countries undertaking higher education reform.Establishing a solid governance system andstrong ownership are critical for ensuring implementation, institutionalization, and sustainability of reforms.Inthe case of Mali, the project helped support the establishment of the Directorate General for Higher Education and ScientificResearch, responsible for overseeing and guiding the development and reform of the higher education sector and the implementationof performance-based contracts. Instrumental in achieving this outcomewas the commitment of the actors who facilitated reformimplementation, leading to the autonomy of the project-supported higher education institutions. Realization of thegovernments intention to adopt the draft higher education regulatory framework will be important for institutionalizingautonomy for HEIs.The establishment of a strong and viable ME system enables the full documentation andanalysis of program achievements and challenges, which, in turn, enable decision-makers and implementers to learn and enhance theireffectiveness and impact. The project successfully established a sound ME system and supported numerous studies andevaluations thatwere undertaken during the projects life and proved to be essential for informing policy decisions inthe higher education sector.Effective accreditation mechanisms are essential for ensuring quality of highereducation programs and institutions.In the case of Mali, the establishment of two complementary quality assuranceentities has substantially strengthened capacity on this front.The Malian Agency for Quality Assurance of Higher Educationand Scientific Research has evolved into an effective regulation and accreditation body.In addition, quality assurance units,established in higher education institutions, are essential for the preparation of their self-evaluations (which are linked toperformance-based contracts) and quality criteria.Performance-based contracts can be an important vehicle forstrengthening dialogue, transparency, monitoring, and increased autonomy of higher education institutions.The use ofperformance-based contracts at the HEI level has helped HEIs negotiate annual programs and budgets based on targets and resultsrather than on inputs.The Ministry of Economy and Financehas recognized these contracts as best practice and recommendsexpanding this approach to improve the oversight and efficiency of other HEIs. Senior management of the HEIs have supported thereforms enthusiastically and restructured internal processes in keeping with the spirit of these reforms.They have also beenstrong proponents of the continued use and expansion of the reform system-wide.Government strategic thinkingand agility on the use of information technology can lead to a more expansive use of the technology than originally designed orenvisioned.Project investments in an HEI information system allowed for considerable connectivity with otherteaching and research institutions.These initial investments ininformation technologyenabledthe Ministry ofHigher Education and Scientific Researchand universities to adapt quickly to COVID-19 pandemic-related school closures bylaunching online courses, not only at the HEI level, but also at the primary and secondary levels, when and wherepossible.This led to much broader use of the information systems and technology than originally envisioned and enhancespotential for the creation of a future virtual university.
P151324 | CI-Infrastructure for Urban Development and Competitiveness of second cities | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR identified thoughtful lessons and recommendations arising from the implementation of this project, and this reviewhighlights three lessons, which are summarized below:When aproject covers multiple sectors, achievingthe best desired outcome requires enhancedpreparation and supervision, notably throughalarger programapproach.The Project was multisectoral and aimed atregional competitiveness. This multisectoral approachwas a key strength, aimed atboosting economic activity outside the capital. However, the complexity of coordinatinginterventions across multiple domains, such as infrastructure and private sector support, highlighted the importance of aligningambitions with local implementation capacity and strengthening inter-agency coordination. Theadequacy of a multisectoraldesign under a single IPF operation needs to be carefully considered with respect to whether implementation synergies aresufficiently strong. Aseries of sequenced interventionsplanned as an integrated urban development and economic growthprogram could be considered.The importance of continued local and national buy-in, including citizen engagement iskey to implementing multisector projects. Project implementation relied on both national authorities and localstakeholders, which were essential for overcoming projectcomplexity. Close collaboration with local governments inBouak and San Pedro and the participatory approach to infrastructure planning fostered client ownership, althoughtheProject had difficulties sustaining local ownership over time.The strong focus on citizen engagement in thedevelopment of urban masterplans contributed to community buy-in, whichpartly mitigated implementationchallenges.New financing instruments supporting MSMEs requireexpertise and time toachieve the desiredoutcome. The matching grant scheme faced difficulties, as many MSMEs were unable to provide their financial contribution,resulting in dropped sub-projects. Future interventions should better screen firms for financial capacity during selection andtailor matching requirements to the firms capabilities. Furthermore, the introduction of the Partial Credit Guarantee Fund(PPCG) was an important innovation in creating sustainable access to finance for MSMEs in Cte dIvoire. By redirectingIDA resources into capitalizing a mechanism that was designed following international best practices and coupled with strongcapacity-building, the Project was able to revert stalled implementation of some activities while promoting sustainability andscaling that is expected to endure long after project closing. These two financing instruments generated results, but achieving thedesired outcome still required expertise to ensure oversight and achieve results.
P151409 | ML- Second Recovery & Governance Reform Support Credit (RGRSC-2) | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest |  |  | The ICR presents the following lessons: To ensure greater impact of a program of reform, DPOs needto be selective and provide a stable and predictable level of support for the reforms and the budget. When tariffadjustments in the electricity sector face political difficulties for their implementation, a strategy to inform the public aboutthe problem and to communicate the importance and reasons for the reform can pave the way for subsequent and more difficultstructural reforms. In post conflict environments, the need for budget support is compatible with meaningful, long-termreforms.This review draws the following lesson: The experience of the programindicates reforms that improve processes (e.g., audit accounts, publishing of EITI reports) are likely to produce the expectedresults. On the other hand, actions affecting special interests are likely to be incomplete (e.g., auditing the payroll system),weakened during program design (e.g., the budget constraint for electricity subsidies) or reversed (e.g., illicit enrichment); insuch cases, the program is likely to fall short of achieving its objectives unless there is a strong political will to carry itthrough. A related lesson is that the design of hard-to-implement reforms is likely to benefit from a deep knowledge of thecountrys political economy.
P151416 | Urban Development Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099805008092242859/text/P1514160c6ea970830b335062b90fb45942.txt | http://documents.worldbank.org/curated/en/099805008092242859/pdf/P1514160c6ea970830b335062b90fb45942.pdf | The following lessons were mostly derived from the ICR with some modifications by IEG (ICR, paragraphs94-98): Institutional capacity building, knowledge sharing, and development of local expertise arecritical for the sustainability of investments in physical infrastructure. The reviewed project involvedsoft activities comprehensive training for government staff, development of manuals and guidance materials,and study tours aimed at developing capacity to operate the newly delivered assets in a sustainable manner. Local technicalspecialists and experts were part of these activities, thus local expertise was supported, and the connection between localconsultants and government agencies established or strengthened. This was especially useful for energy efficiency and seismicresilience activities in the project, which were new for the country. In addition, involvement of local experts was critical duringCOVID-19, when travel was restricted, and international experts could not be present. Clarity andsimplicity of the project implementation plan, as well as clarity regarding project risks, are key for successful projectimplementation. A clear and comprehensive work program, highlighting the interlinkages between activities, resources to bemobilized, and risks and constraints to be addressed would help proactively address implementation issues early on and therebyreduce implementation risks, including those related to project delays. The project experienced some delays in the first half ofits implementation due to insufficient attention to these mattersbut was able to make improvements once they wereaddressed. When retrofitting or rehabilitating schools or kindergartens, where temporarily relocationof students is needed, having a flexible relocation plan is critical. The project benefited from having such a plan whenthe works started slower than expected due to the contractors limited knowledge of retrofitting practices and when thecounterpart fundingbecame an issue due to the impact of the COVID-19 pandemic. As a result, the students needed temporaryarrangements for an extended period of time, which was made possible.
P151425 | Lao PDR Health Governance and Nutrition Development Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099745111152236175/text/P1514250016a750550a89c03f3e84b6912c.txt | http://documents.worldbank.org/curated/en/099745111152236175/pdf/P1514250016a750550a89c03f3e84b6912c.pdf | The ICR (pp. 36-38) offered several lessons, including the following lessons restated by IEGReview:Performance-based financing operations provide an opportunity to strengthen acountrys healthmanagement information system. Under thisproject, several preconditions were in place, including strong governmentownership and alignment of the operation and its ME with national plans that facilitated project support to the expansion ofDHIS2. The latter evolved to become the backbone of MOHs monitoring and reporting system. In addition, the incentivizationof data accuracy and timeliness through DLIs heightened overall attention to the importance of improving data quality. The projectoffered close hands-on support and extensive capacity building for strengthening the information system. Meeting the needs forcomprehensive technical support at the outset can be considered when planning similar futureprojects.Performance-based approaches using DLIs are effective modalities both to enhance focus on results and tochannel funds to the frontline service level. The use of DLIs with 80 percent of funds directly channeled to theimplementing level provided a first-hand understanding and appreciation of the concept of results-oriented management. The positiveexperience of thisproject contributed to agovernmentdecision to continue the use of this financing modality inits follow-on operation.Intersectoral collaboration at the local level allows effective responses toundernutrition. Thisproject promoted nutrition-specific interventions and nutrition-sensitive interventions toachieve results in changing behaviors, improveknowledge of mothers and caregivers, and improveenvironmental health andsanitation. The project established village-level platforms for providing community-level preventive and promotive health messages,actions, and intersectoral collaboration. Further, village facilitators trained by the project expanded the scope of theirnutrition efforts by contributing to the pandemic response at the community level, as they played an important in providing correctinformation about COVID-19 prevention and in promoting COVID-19 vaccinations in the villages.
P151442 | Social Assistance Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099445003022210103/text/Lesotho000LS0Social0Assistance0Project.txt | http://documents.worldbank.org/curated/en/099445003022210103/pdf/Lesotho000LS0Social0Assistance0Project.pdf | The ICR (pp. 47-49) contained several insightful lessons emerging from the projects experience,including: While decisions to scale up social protection programs can be taken in direct response tospecific events, it is more effective and efficient to front-load procedures and processes prior to an actual emergency.The Additional Financing for this project capitalized on ongoing project interventions to respond to the 2016 and 2019 droughtemergencies. To make the program more responsive, theMinistry of Social Developmentis developing standard operatingprocedures for expanding and contracting the Child Grant Program during future droughts and other potentialshocks. Achievement of disbursement-linked indicators mayrequire associated operational funding.In this case, other than expansion and capacity building of NISSA, the projectdid not earmarkinvestment projectfinancing to help implement the DLIs apart from the actual disbursement incentive; this meant that supplementary budget from thegovernment or other donors was required to complete the activities that were to produce the DLI results, and sometimes that fundingwas difficult to obtain.
P151447 | Ghana: Public Financial Management Reform Project | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2015 | 2022 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099071323132026742/text/P1514470f411d60720964402ca7dc13a01b.txt | http://documents.worldbank.org/curated/en/099071323132026742/pdf/P1514470f411d60720964402ca7dc13a01b.pdf | The ICR offers the following pertinent lessons: The implementation of multiple IT solutions requires awell-thought-through integration plan. During project implementation, IT solutions needed to be integrated to ensure thatall systems were fully linked. For example, the budget preparation solution (Hyperion) and the human resource management solution(HRMIS) became fully integrated parts of the GIFMIS. However, some IT solutions of the government remain standalonesystems. Projects that involve a wide range of technical areas and many actors/implementing agencies require astrong and motivated coordination and dedicated ME unit. The Project Steering Committee and PMU were critical inensuring coordination among implementing entities across the PFM value chain.IEG adds thefollowing: In order to effectively introduce reform measures and minimize resistance, it is crucial toincorporate culturally sensitive participatory approaches that prioritize change management. The challenges associatedwith past PFM reforms highlight the significance of addressing cultural resistance. To ensure successful reform implementation anddesired outcomes, deliberate change management strategies must be employed, emphasizing both cultural and institutional ownershipof the reform projects. Therefore, it is essential to include targeted interventions that specifically integrate change managementprinciples into the reform process.
P151448 | First Competitiveness and Fiscal Management Programmatic DPL | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/368181593006092833/text/Jamaica-First-Comp-and-Fiscal-Mgmt-Prog-DPL.txt | http://documents.worldbank.org/curated/en/368181593006092833/pdf/Jamaica-First-Comp-and-Fiscal-Mgmt-Prog-DPL.pdf | IEG concurs with the three general lessons of the ICR:1. Effective coordination with other multilaterals/partners canenhance the impact of a Bank-supported operation, at all stages, from preparation, design to supervision. In Jamaica, therewas a high level of cooperation between the Bank, the IMF, the IDB and DFID which enhanced the effectiveness of theoperation.2. Multilateral efforts can achieve higher level results that go significantly beyond the achievement of resultsindicators targeted by Bank operations alone. In particular, in Jamaica, these efforts led to an exceptional reduction in the debtburden that exceeded the target.3. Technical assistance and/or investment lending to bolster capacity and accompanyimplementation of a DPL can be essential for achieving development objectives. This was an important component of the Jamaicaseries.To these lessons, IEG adds the following:4.In preparing programmatic DPL operations that may extendbeyond a single government administration, obtaining clear indications of continued political commitment, increases the probabilityof policy continuity. In Jamaica, the Economic Programme Oversight Committee contributed strongly to the continuity of the programfollowing a change in government.5. In designing prior actions and triggers for policy frameworks, fewer but criticalactions are better than larger number of actions of varying criticality. In the Jamaica DPL series, initial twelve triggers wereexcessive but were appropriately streamlined in the second operation.
P151449 | Mali Support to Agroindustrial Competitiveness Project | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest |  |  | The following are lessons taken from the ICR with some paraphrasing: A realistic assessment of thefeasibility of management mechanisms during appraisal can ensure full operationalization and efficient use of public agribusinessfacilities and platforms built by projects. In the case of the SACP, the mango platforms for storage and conditioning werebuilt but were not being used by mango value chain exporters and processors by the end of the Project. That was mainly because theproject was unable to put in place a private management mechanism based on fees for usage as the business opportunity was notsufficient. Also, a public management mechanism was not feasible, or not entertained. This could have been avoided if themanagement arrangements be clearly articulated and resolved during project preparation, or specific options explored and modeledduring the appraisal of the project. When possible, collaboration among World Bank Global Practicescan help better management of key elements of the project and increase achievement of project objectives. The Project teamwas led by co-task team leaders from the Finance, Competitiveness and Innovation, Transport and Agriculture Global Practices. Thisarrangement resulted in a constructive collaboration melting different approaches and visions of the World Bank teams in onesuccessful design and supervision of of the project. A thorough analysis of risks associated withdependance on one anchor business while developing productive alliance, can help better and transparent management of thesealliances. In the case of SACP, project relied on Laham Industries for building productive alliances since it waslikely the only viable anchor. This involved certain risks such as such as perceived bias in the selection of beneficiaries,inability to influence the anchors commercial policy, and market distortions. A thorough analysis of these risks can help tounderstand how to better apportion costs and benefits to value chain participants in Bank-funded alliance development activities.Also, to include specific obligations in agreements between the Bank and beneficiary anchor businesses with respect to businessdecisions can improve the performance of the project.
P151479 | Ukraine - DPL 2 | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2016 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest |  |  | A number of useful lessons are highlighted in the ICR. First, significant government commitment is paramount in achievingimportant reform outcomes. Second, the need to coordinate closely among development partners is critical in moving forward thereform agenda. Third, strong analytical work and deep engagement with government counterparts are important for successful policylending. Fourth, flexibility in programmatic design allows the Authorities and the Bank to adapt the program to changingcircumstances. IEG adds two further lessons. First, patience enabled the Bank to seize a unique window ofopportunity to support critical and far reaching reforms, after having refrained from policy lending when the timing was not right.Prior to the operations, the Bank maintained an open policy dialogue and produced significant analytical work, both of which wereinstrumental in enabling the program to be designed in a short time span. Second, deep-rooted reforms that go against vestedinterests are difficult to sustain once the reform momentum wanes. A thorough political economy analysis during or prior topreparation can provide useful insights in this respect.
P151480 | Nigeria Edo State Fiscal Improvement and Service Delivery Operation | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/150081529101644486/text/Nigeria-NG-Edo-State-FISDO.txt | http://documents.worldbank.org/curated/en/150081529101644486/pdf/Nigeria-NG-Edo-State-FISDO.pdf | The lessons are drawn from the ICR with some adaptation:While a DPO program canincentivize reforms, reform orientation of the recipient is important to ensure sustainability and scale of reforms. Insome of the ESFISDO policy areas, Edo State has been able to achieve or exceed the targets set for the program of two operations,even though the second operation did not materialize. In the areas where the State did not achieve the targets (e.g. for the TVETreforms and the land transaction rates), the state has maintained the reform momentum and, as in the case with the TVET reforms, isimplementing the reforms in a more robust way than was anticipated by the DPO program. This suggests that the State itself isreform-oriented.Political transitions can cause significant delays in implementation of aDPO. Two political transitions took place during the program period, both of which caused long delays ineffectiveness and program implementation, which necessitated rescheduling the first operation. It is important to ensure mitigatingany potential delays arising from political transitions in a DPO program.If possible, specificmechanisms to ensure completion of a programmatic series of DPOs should be put in place, especially in high political riskenvironments. The operation was affected by a delay in parliamentary approval of the external borrowing plan, as well as apolitical transition. A mitigating mechanism could, for example, seek to ensure that initial parliamentary approval of anentire DPO serieswould suffice, without the need for subsequent approvals of the individual operations.
P151487 | First Public Investment Reform Sppt Cr. | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/110251560193272949/text/Niger-First-Pub-Inv-Reform-Sppt.txt | http://documents.worldbank.org/curated/en/110251560193272949/pdf/Niger-First-Pub-Inv-Reform-Sppt.pdf | The ICR draws a number of lessons, of which the following two are of particular interest (with some adaptation oflanguage):Overly ambitious reforms in relation to a countryscapacity can cause delays, and even undermine a program. Capacity constraints have a substantial impact on the likelihoodof successful implementation and need to be taken into account in some detail at the design stage. In this case, implementing amedium-term expenditure framework in a number of ministries posed challenges, as did multi-year budgeting and carry-overcommitments for multi-year projects. In the irrigation sector, key issues such as preparation of an appropriate legal framework andmanagement of an important dam, were not carried out as planned.In strengthening an irrigationauthority, the deployment of experts who have knowledge in similar contexts enhances the likelihood of successfulimplementation. In this case, the participation of irrigation experts with experience in other West African countriesassisted improvements in ONAHA. In addition, IWUAs began to receive funding against agreed targets rather than through randombudget availability.IEG draws the following lesson:Where changes inlegislation are key to a programs success, it is advisable to make the enactment of suchchanges early prior actions. This takes account of the limited influence of the Executive in securing legislativemodifications and reduces the possibility that lack of an adequate legal framework would blunt the impact of other reforms.
P151488 | National Social Safety Nets Project | Western and Central Africa | Nigeria | Blend | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099012624183017071/text/P1514881e50fcd0261bd211ca45ab33dadc.txt | http://documents.worldbank.org/curated/en/099012624183017071/pdf/P1514881e50fcd0261bd211ca45ab33dadc.pdf | Key lessons cited by the ICR (p.33) include:Utilization of restituted funds under the ARF can supporttheeffective and efficient use of the restituted funds and enhance social safety net program impacts. This approachcontributed to building strong fiduciary and social accountability mechanisms, with the involvement of a network of national CSOnetwork that ensured the use of funds. Another element of this approach was the decision to allocate the resources only to cashtransfers for beneficiaries, with IDA playing a fiduciary role, which contributed to build trust andaccountability.Securing the buy-in of all levels of government involved in social safety net systems in keyfor success. Among the drivers of buy-in and participation are: clear communication of project goals and modalities,well-targeted incentives and maintenance of ongoing dialogue; a clear institutional architecture, including clearmandates for stewardship, policy guidance and coordination and implementation mandates.Third party monitoring canenhance transparency and accountability of digital paymentsystems for cash transfers. In any cashtransferprogram, it is key to ensure that targeted beneficiaries receive the cash transfers in the amounts intended on time.Third party monitoring can provide critical evidence that beneficiaries received their payments in the due amounts, as well asproviding useful information on issues requiring attention.Close and rigorous follow-up and monitoring, includingchecks for quality and accuracy and the use of technology to reduce human error and ensure consistency, can contribute to enhancedtargeting of the poorest and most vulnerable households.The project used numerous feedback mechanisms,including TPM and beneficiary surveys to identify shortcomings in the pro-poor targeting of cash transfers. This enabled theproject to introduce a suite of policy changes mid-term with the result that, by November 2018,poor households were morelikely to benefit from the targeted cash transfers than they were during the initial project period. Community ranking wasintroduced, to ensure that the poorest communities were targeted by the intervention rather than those who weremore centrallylocated.A checklist was developed to improve the quality of implementation of community-based targetingandaproxy means testwas introduced. Finally, a protocol for backchecks was introduced as well: a sample of households werere-interviewed and data was compared to see if there were discrepancies between reported data and actual moniesreceived.Geographical targeting has an important role to play in reaching the poorest households, andnew technologies can refine the approach. Poverty in Nigeria is highly concentrated in certain areas, so geographicaltargeting has a key role to play in selecting beneficiaries of social safety net programs. Self-learning algorithms have been usedsuccessfully to identify geographical pockets of poverty using satellite images.In some cases, it may be advisable to includein the National Social Registry all households living in the very poorest areas to reduce the extent to which the pooresthouseholds are missed out.
P151492 | Second Public Financial Management Capacity Strengthening Project | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024214015397/text/P15149218cd23008d1bd2a11e5530e050c4.txt | http://documents.worldbank.org/curated/en/099053024214015397/pdf/P15149218cd23008d1bd2a11e5530e050c4.pdf | Design project sequencing by setting realistic targets in FCV contexts. The Somalia Second PFM CapacityStrengthening Project suggests that quick wins envisaged at appraisal should be implemented in the early stages ofthe project to carry forward a positive momentum and expand beneficiaries over time. Although its risk assessment analysis departedfrom sounds observations regarding the inherent risks in implementation in the country context, project design did not anticipatethe possibility of implementation delays that could undermine overall delivery. Front-load tough reformareas to build momentum. The Somalia Second PFM Capacity Strengthening Project demonstrates that it is useful to implementtough reforms early to enhance the chances of implementation by closure. One of the projects major objectives was to fullyimplement ITAS at closure. Such an inherently difficult reform typically faces multiple veto players, opposed coalitions andentrenched interests set against change. In the presence of government commitment to reform, such a reform should have beenintroduced at the very early stages of Somalias PFM reform drive. This may have convinced reform beneficiaries thatthe developmental impact ofthe reform would be positive and thus enlarged the pro-change constituency. In practice, importantDRM progress was made through the project, but even after two extensions, ITAS implementation was not achieved by closure.
P151502 | POVERTY REDUCTION SUPPORT CREDIT III | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  |  |  | This review broadly concurs with the 4 lessons from ICR, and offers additional suggestions:Lesson 1: Importanceof sustained measures for good fiduciary practices to be ingrained in government operations, which also underscores the needfor a thorough and systematic ex ante risk assessment of risks to achieving development objectives and articulation ofmitigation measures. Excessively overburdening the fragile and low capacity system with complex technical reforms (IPSAS-basedreporting, introduction of ASYCUDA and IFMIS, payroll reform, etc.) is fraught with major risks to sustainability and thecredibility of reforms in the long term, once there is no direct donor support and hand-holding.Lesson 2: Need forgood communication with all stakeholders from the start to avoid preparation and implementation delays. At the beginning of theseries Parliament was not fully informed that the budget support was in the form of an IDA credit and not an IDA grant and neededadditional assistance on how to ratify such agreements, which took additional 11 months between the Board approval anddisbursement. In addition, an extended and sizable program such as this series would have benefited from a better upfrontunderstanding of the political economy risks and scenarios.Lesson 3: Need to keep the range of policy areasflexible, to better respond to exogenous shocks such as the Ebola crisis, which occurred after the start of the series andhighlighted the weaknesses in Liberias health caredelivery system.Lesson 4: Capacity for reform incountries like Liberia, requires heavy TA to support a successful reform program. The TA also encouraged stronger governmentcommitment and willingness to reform. The key TA support was particularly helpful in the areas of PFM, land reform and inelectricity sector reforms. At the same time, ongoing TA support for implementation (absolutely critical in an environment likeLiberia) also needs to be accompanied by strong and clearly targeted capacity building measures and indicators to ensuresustainability of achievements.
P151544 | MSME Growth Innovation and Inclusive Finance Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2015 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/329191580741398788/text/India-MSME-Innovation-and-Inclusion-Project.txt | http://documents.worldbank.org/curated/en/329191580741398788/pdf/India-MSME-Innovation-and-Inclusion-Project.pdf | This review supports the four lessons filtered from the experience of the project implementation, which are rephrasedbelow:(i) The potential for declining competitiveness of IBRDs credit linesneeds to be discussed atproject appraisal, and risk mitigation measures should be identified andactivatedin case of riskmaterialization.The cost of the IBRD credit line became uncompetitive for SIDBI due to the Governmentsguarantee fee and the foreign exchange rate movements, which were further compounded by the introduction of domestic concessionalfunding sources. Thecost of the IBRD credit line was inclusive of the hedging cost and the sovereign guarantee feeandturned unattractive to institutions like SIDBI, and prompted the cancelation of the undisbursed creditline.(ii) Using improved data analyticsand innovative lending methodscan help overcome thebottlenecksin expanding lending to MSMEs.MSMEs in different sectors and countriessuffer fromcommon types of market failures. Using common lending methods including fintech solutions and improvement in data analyticscanhelp reduce transaction costs andovercome information asymmetries in order to improve access to finance for MSMEsacross different sectors and countries. This project targeted MSMEs in both manufacturing and service sectors from early to growthstage and effectively leveraged complementarities in serving the MSMEs across different sectors, building oncommon lendingmethods including the fintech and digital lending platforms.(iii) When designing a project, the design of theresults framework needs to better articulateintermediate outcomesand thePDO indicators. In designing theprojects results framework, the PDO results indicators focused narrowly on SIDBIs direct lending business.Tofully capture the projects impact in terms ofimproving the MSME financing ecosystem, thePDO indicators thatmeasureperformancerelated to the crowding in of private sector financing should have been identified atappraisal.Focusing the results indicators too much on a development of financial institutions direct lendingbusinesswas inadequate when designing a project with an intended impact of crowding in the privatesector.(iv) Synergy between the debt market and equity investment is key to the scaling-up of lending toMSMEs: The strategy and blueprint to revive lending towards the startup sector provided under this project pointed outthat the development of the venture debt market requires a vibrant ecosystem of venture equity investment. Strong synergy existsbetween the development of the venture debt market and a vibrant ecosystem of equity investment.
P151620 | PK Fiscally Sustainable and Inclusive Growth DPCII | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The first three lessons are drawn from the ICR (pages 31-33), with some adaptation. When engaging a newgovernment in a reform program, a gradual and measured approach to program design and implementationis desirable. Thestrength and durability of the political commitment to reforms is often uncertain, as is the institutional capacity of the newgovernment to execute difficult measures or even to absorb advisory services and technical assistance. The gradual approachallows a development partner and the new government to cultivate a level of mutual trust, and the new government toassimilateexternal knowledge and to developits institutional capacity,both of which are necessary for thesustainedimplementation of structural reforms. A morecomprehensive and integrated approach to privatizationthan simply focusing on the number ofequity saletransactions in any given year is likely to strengthen the reformprogram. Strategic privatizations are better set within the context of wider development agenda. A government shouldalso calibrate the scope and scale of its privatization program to its ability to plan and execute transactions, to the capacity ofprivate investors and the capital markets to purchase and to fund the purchase of state assets, and to the willingness of variousconstituencies to support SOE privatization efforts. When constructing an operationsresultsframework andits associated ME indicators and targets, it is best to set an output or an outcome for a program component, in addition todefining or describing the modality by which an objective is achieved. The creation of an OSS for business registration isreputedly a best practice modality for facilitating business registrations. But a results framework and ME plan mustspecify an output or outcome for an OSS, in terms, for instance, of the number of steps or the number of days to complete abusiness registration application. There is a need to involve implementing agencies at the planning stage of a DPO toensure they have the technical and financial resources to implement their part of the program.Planning the details ofthe OSS project with the SECP, EPBI and FRBwould have enabled the Bank and the Government to determine the ability of theimplementing agencies to execute a technology project. There is also a need to undertake active and in-depth consultationwith stakeholders to identify and mitigate political economy risks. Consultations with the constituency of various SOEs wouldhave allowed the Bank and the Government to gauge the extent of public support or opposition to the privatizationprogram.
P151620 | PK Fiscally Sustainable and Inclusive Growth DPCII | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2020 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/623411595443109723/text/Pakistan-First-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project-and-Second-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project.txt | http://documents.worldbank.org/curated/en/623411595443109723/pdf/Pakistan-First-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project-and-Second-Programmatic-Fiscally-Sustainable-and-Inclusive-Growth-Project.pdf | 5. Lessons â€¢ In Pakistan, the World Bank reengagement with development policy lending after a long break benefited from a longer-term strategy (or program) that provides for several interrelated DPCs, a large and relevant technical assistance program, and close cooperation with the IMF. Progress made under the FSIG program in such a sensitive and capacity-demanding area as public revenue management was much more significant when compared with the World Bank's previous intervention, which was centered on self-standing investment lending. The development impact of the DPCs would have been much weaker without a long-term adaptable technical assistance package provided by DFID, and technical assistance alone would have scarcely made a dent in tax policy reform in Pakistan. Cooperation with the IMF's EFF program was a critical precondition of success in raising tax collection. â€¢ Dividing important sectoral issues among separate operations could be an effective strategy when the government is facing multiple reform challenges. In Pakistan, splitting the DPC program into two parallel DPC series helped mitigate the risks, including those related to political economy and implementation constraints; ensure more focused design of the individual series; and strengthen accountability of core government counterparts. â€¢ Political economy analysis and communication support related to politically sensitive reforms were insufficient. The privatization effort under the FSIG program was affected by an overly technical approach to the implementation of the agreed transactions, which did not consider many sensitive aspects of this process (unions, unemployment, and so on). The World Bank did not fully appreciate the influence of the stakeholders who opposed privatization and did not offer any significant communication support to the government of Pakistan to clarify the privatization process for stakeholders and explain its potential benefits.
P151712 | Urban Productive Safety Net Project (UPSNP) | Eastern and Southern Africa | Ethiopia | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099101623190021681/text/P1517120286a28067099a90be9989b54fad.txt | http://documents.worldbank.org/curated/en/099101623190021681/pdf/P1517120286a28067099a90be9989b54fad.pdf | Lessons drawn from the ICR (pages 34-25), adapted by IEG: Flexibility built intothe social protectionmechanisms can allow for quick response to shocks. In the case of this project, the internal conflict led to millions ofdisplaced persons who were in need of social protection support. The government set up temporary coordination mechanisms atthe federal and regional levels in response to the crisis, and adapted implementation mechanisms (blanket registration vs.poverty-based targeting, temporary bank locations) to quickly provide access to cash transfers for those inneed. Targeting can be effectively and efficiently carried out in an urban context to ensure the poorest households arereached. In the case of this project, a combination of geographic (selected areas in eleven cities) and community-basedtargeting was able to identify the poorest households such that 73% of project beneficiaries were living below the povertyline.
P151746 | Modernization of Real Property Registration and Cadastre | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2024 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062424000042083/text/P151746-234dad60-3591-4533-a8c1-3a50164b2207.txt | https://documents.worldbank.org/curated/en/099062424000042083/pdf/P151746-234dad60-3591-4533-a8c1-3a50164b2207.pdf | The following lessons were derived from the ICR (based on ICR, pages 20-21):1. Havingsufficient information about the quality and completeness of the existing cadastre data during project preparation can be criticalfor developing an adequate project design and avoiding project restructurings in projects aimed at modernizing real propertyregistration and cadastre. This information is needed to assess risks, outline mitigation measures at project designstage, and either include these measures in project activities or address them outside of the project using such tools as technicalassistance (TA), Advisory Services and Analytics (ASAs), and Development Policy Operations (DPOs). The Project experiencedemonstrated that it would have been highly beneficial if both the World Bank and the Client were better informed about the issueswith data and had agreed-on plans on how to address them, including through: (i) conducting studies and piloting; (ii) mobilizinghuman and technical resources for property surveys; (iii) improving the legal framework; (iv) endorsing guidelines for a range oftechnical tasks to be conducted by cadastral agents and at higher levels. 2. While designing the RF,especially for projects of an innovative nature, selecting indicators that are not manageable for the Client (such as too complexor overly technical indicators) might create complications and lead to a significant RF adjustment during restructurings.In Projects experience, existing data availability and data collection and reporting capacity of the Client would have beenimportant to consider, as well as making sure that the definitions of indicators and data collection methodologies were explicitand clear to the Client.3. When multiple donor and government-funded activities are implemented in parallel,coordinating them and facilitating technical discussions and, whenever possible, supporting joint development of the technicalaspects of projects can enable synergies. From 2013 to 2018, the Korean Eximbank was supporting the Government inestablishing the NGIS, and a pilot to develop IISRPRC was a part of that operation. However, the pilot did not align with thecriteria determined in the Bank Project reviewed here. Due to this misalignment, the Project had to allocate significant time andresources for the operationalization of the NGIS and its integration with the IISRPRC.4. Advocating for policysolutions identified during project implementation can be beneficial for the sustainability of project outcomes and for laying outa foundation for continued reforms. During the Projects execution, the needed sectoral legislative changes wereidentified, and 13 key legislative measures were introduced, aimed at improving the following: registration processes, safety andaccessibility of cartographic and geodetic materials, geodetic and cartographic activities for spatial data management, landrecords and state cadastre maintenance. Furthermore, they introduced measures to protect property rights, increase thecapitalization of private property, ensure transparency in property rights registration, and promote the management of spatialinformation. Due to these efforts, the Project served as a platform for advocating policy solutions, which added value to thesustainability of Project outcomes.
P151754 | Pacific Islands Regional Oceanscape Program - Federated States of Micronesia | East Asia and Pacific | Micronesia, Federated States of | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099063023163027714/text/P1517540bdcd990ad0a94502267f1c0adb0.txt | http://documents.worldbank.org/curated/en/099063023163027714/pdf/P1517540bdcd990ad0a94502267f1c0adb0.pdf | This review reiterates the lessons provided in the ICR (paragraphs119-128), with some minor additions andnorecommendations are provided.1. Long-term engagement. Pacific Islands Regional Oceanscape Program(PROP) andimplementation in RMIneed to be considered as a long-term multiphase process and engagement. While the originalintentions of the program were and continue to be relevant, they need to be realistically stretched across multiple phases ofsuccessive projects under the program. This review would also add that they need to be grounded first in a diagnostic of countryissues rather than overall regional issues.2.PROP was the World Banks first engagement in PacificIslands oceanic and coastal fisheries. Participating countries and institutions had little to no experience managing WorldBank-financed projects. Region-specific challenges, in part due to the fragile institutional contextthere arecapacity constraints, significant hands-on support needed, and the overall challenges of reaching stakeholders beyond capitalcities due to the dispersed nature of the countries, must also be considered at design.3.The theory ofchangewas overly complex and not well articulated in design. It employed a hub-and-spoke regional model where a country-ledapproach could have avoided the need for restructuring in 2018. The programs theory of change was demanding, complex, andambitious given the client countrys institutional capacity, time, political, geographical, and financial constraints. The ideaof leveraging regional institutional capacities (from the FFA, SPC, and others) to effectively implement national project resultschains was weakly developed, poorly understood, and owned by countries and thus operationalized sub-optimally. The underlyingassumptions of the ToC were not communicated among partners, and collaboration opportunities were missed with other developmentpartners.4. There was minimal consideration of gender equality in the project design, which is a critical dimension whenimplementing effective coastal fisheries management. Continued support to coastal fisheries management and project can be informedby consultation with SPCs Pacific Framework for Action on Scaling up Community-based Fisheries Management:20212025,to assess how to best engage in either direct community-based fisheries management or/and its enablingwork; and (c) recent analytical work about gender inequalities in access to productive resources, assets, services, andopportunities, such as the Country Gender Assessment of Agriculture and the Rural Sector in Solomon Islands, conducted by the Foodand Agriculture Organization (FAO) and SPC in 2019.25.Financing the Situation Analysis Reportand leaving itsimplementation to additional, non-identified financing, did not yield any tangible outcomes in the coastal fisheriessector.During the design, the FSM Government was not able to fully commit to coastal fisheries development outcomes with thehelp of PROP financing. This was a missed opportunity and a loss of valuable time.
P151760 | Pacific Islands Regional Oceanscape Program - Republic of the Marshall Islands | East Asia and Pacific | Marshall Islands | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099062023091537194/text/P15176000171530d30a00e0c89acb8f6908.txt | http://documents.worldbank.org/curated/en/099062023091537194/pdf/P15176000171530d30a00e0c89acb8f6908.pdf | This review reiterates the lessons provided in the ICR (paragraphs120-126), with some minor additions though norecommendations are provided.1. Long-term engagement. Pacific Islands Regional Oceanscape Program(PROP) andimplementation in RMIneed to be considered as a long-term multiphase process and engagement. While the originalintentions of the program were and continue to be relevant, they need to be realistically stretched across multiple phases ofsuccessive projects under the program. This review would also add that they need to be grounded first in a diagnostic of countryissues rather than overall regional issues. Where this project in the Marshall Islandsmade the most advances, it connected toissues where there was a local demand, such as monitoring, compliance, and surveillance.2.PROP was the WorldBanks first engagement in Pacific Islands oceanic and coastal fisheries. Participating countries and institutions hadlittle to no experience managing World Bank-financed projects. Region-specific challenges, in part due to the fragile institutionalcontextthere are capacity constraints, significant hands-on support needed, and the overall challenges of reachingstakeholders beyond capital cities due to the dispersed nature of the countries, must also be considered atdesign.3.The theory of changewas overly complex and not well articulated in design. It employed ahub-and-spoke regional model where a country-led approach could have avoided the need for restructuring in 2018. Theprograms theory of change was demanding, complex, and ambitious given the client countrys institutional capacity, time,political, geographical, and financial constraints. The idea of leveraging regional institutional capacities (from the FFA, SPC,and others) to effectively implement national project results chains was weakly developed, poorly understood, and owned bycountries and thus operationalized sub-optimally. The underlying assumptions of the ToC were not communicated among partners, andcollaboration opportunities were missed with other development partners.4. There was minimal consideration of genderequality in the project design, which is a critical dimension when implementing effective CBRM. Continued financing of the CBRMprocess through the MFMR and project can be informed by (a) new research and lessons learned about the adoption of CBRM in theregion; (b) consultation with SPCs Pacific Framework for Action on Scaling up Community-based Fisheries Management:20212025,to assess how to best engage in either direct community-based fisheries management or/and its enablingwork; and (c) recent analytical work about gender inequalities in access to productive resources, assets, services, andopportunities, such as the Country Gender Assessment of Agriculture and the Rural Sector in Solomon Islands, conducted by the Foodand Agriculture Organization (FAO) and SPC in 2019.25.Consensus building in coastal fisheries management needs timeand requires continued support. Engaging communities and local government on fishery resource management and conservation issuesand building a trusted relationship with MIMRA teams require investment in time and resources due to the remoteness of the atollsand related transportation needs and travel time.
P151777 | Pacific Islands Regional Oceanscape Program - Solomon Islands | East Asia and Pacific | Solomon Islands | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099062323172025020/text/P1517770a7723a0e909c360e3ab040dcc65.txt | http://documents.worldbank.org/curated/en/099062323172025020/pdf/P1517770a7723a0e909c360e3ab040dcc65.pdf | This review reiterates the lessons provided in the ICR (paragraphs120-126), with some minor additions1. Long-termengagement. Pacific Islands Regional Oceanscape Program needs to be considered as a long-term multiphase process and engagement.From this ICRR we noted that regional projects can benefit from being grounded first in a diagnostic of country issues rather thanoverall regional issues. Where this project in the Solomon Islandsmade the most advances is where itconnected to issueswhere there was a local demand, such as, monitoring, compliance and surveillance.2. Region-specific challenges andimplementation readiness. PROP was the World Banks first engagement in Pacific Islands oceanic and coastal fisheries.Participating countries and institutions had little to no experience with managing World Bank-financed projects. Region-specificchallenges, in part due to the fragile institutional contextthere are capacity constraints, significant hands-on-supportneeded, and the overall challenges of reaching stakeholders beyond capital cities due to the dispersed nature of the countries mustalso be considered at design.3. The theory of changewas overly complex, not well articulated at design andemployed a hub and spoke regional model where a country led approach could have avoided the need for restructuring in 2018. Theprograms theory of change was demanding, complex, and ambitious given the institutional capacity, time, political,geographical, and financial constraints by the client country. The idea of leveraging regional institutional capacities (from theFFA, SPC, and others) for effective implementation of national project results chains was weakly developed, poorlyunderstood, and/or owned by countries and thus operationalized suboptimally.4. The adoption of CBRM as the nationalstrategy to conserve coastal fishery resources, including coral reefs, requires a lot of investment both in time and resources.While empowering and training communities to effectively manage coastal fisheries through development of CFMPs will improve andmaintain the productivity of coastal resources in the medium term, communities are more likely to support management andconservation goals when these are supported by income generating activities that materialize in the short term, including fromlocal value chain investments and diversification of livelihood opportunities.5. There very limited consideration ofgender equality in the project design, which is a critical dimension when implementing effective CBRM. Continued financing of theCBRM process through the MFMR and project can be informed by (a) new research and lessons learned about the adoption of CBRM in theregion; (b) consultation with SPCs Pacific Framework for Action on Scaling up Community-based Fisheries Management:20212025,to assess how to best engage in either direct community-based fisheries management or/and its enablingwork; and (c) recent analytical work about gender inequalities in access to productive resources, assets, services, andopportunities, such as the Country Gender Assessment of Agriculture and the Rural Sector in Solomon Islands, conducted by the Foodand Agriculture Organization (FAO) and SPC in 2019.26. Foster improved project management. The PMU had challenges meetingreporting requirements. In a new project phase, improved project performance management and oversight systems can be incorporatedearly on and agreed rules and procedures consistently applied. These issues could be addressed by (a) supporting the MFMR instrengthening its performance management, (b) aligning future results targets with the MFMRs institutional results targets,and (c) strengthening fiduciary capacity within the MFMR.
P151780 | Pacific Islands Regional Oceanscape Program - Tuvalu | East Asia and Pacific | Tuvalu | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2015 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | This review highlights three of the lessons provided in the ICR (paragraphs111-119), with some minor additions andprovides no recommendations.1. Long-term engagement. The Pacific Islands Regional Oceanscape Program(PROP) andimplementation in Tuvalu need to be considered as a long-term multiphase process and engagement. While the original intentions ofthe program were and continue to be relevant, they need to be realistically stretched across multiple phases of successive projectsunder the program. This review would also add that they need to be grounded first in a diagnostic of country issues rather thanoverall regional issues.2.PROP was the World Banks first engagement in Pacific Islands oceanic andcoastal fisheries. Participating countries and institutions had little to no experience managing World Bank-financed projects.Region-specific challenges, in part due to the fragile institutional contextthere are capacity constraints, significanthands-on support needed, and the overall challenges of reaching stakeholders beyond capital cities due to the dispersed nature ofthe countries, must also be considered at design.3.The theory of changewas overly complex and not wellarticulated in the projects design. It employed a hub-and-spoke regional model where a country-led approach could haveavoided the need for restructuring. The programs theory of change was demanding, complex, and ambitious given the clientcountrys institutional capacity, time, political, geographical, and financial constraints. The idea of leveraging regionalinstitutional capacities (from the FFA, SPC, and others) to effectively implement national project results chains was weaklydeveloped, poorly understood, and owned by countries and thus operationalized sub-optimally. The underlying assumptions of the ToCwere not communicated among partners, and collaboration opportunities were missed with other development partners.4. Therewas minimal consideration of gender equality in the project design, which is a critical dimension of the Country PartnershipFramework.
P151785 | MG-Electricity Sec Operations & Governance Improvement Project(ESOGIP) | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The following three lessons are from the ICR with some adaptation of language: While implementingprojects that support strategic sector reforms, preparing detailed analysis and phasing the implementation can help avoidingbottlenecks and lead to better achievement of results. In the case of Madagascar, the ESOGIP project supported tariffreform for which the preparation of a detailed analysis on tariffs was crucial to guide discussions and the strategies to be put inplace. This reform was divided into several phases: the first involving tariff optimization, notably simplifying tariff structures,adjusting the targeting of subsidies to focus on vulnerable households and SMEs, and the second involving indexation and automaticadjustment. Established jointly by an external auditing firm and utility, and assessed periodically, AssetManagement Plans can ensure that the allocated project resources are used effectively and efficiently. In the case ofESOGIP, the issues encountered during the implementation in relation to fixed asset management caused delays inproject implementation. Asset management audits had to be conducted while diagnosing irregularities. Systematic and closermonitoring with a robust ME implementation with dedicated specialized personnel could have helped avoid emergence of some ofthese issues. An asset management plan which involves the procedures for managing fixed assets, clarifying the responsibilities ofstaff/direction within the utility for each stage of the plan can be of significant help to implementingagencies. Clarifying decision-making powers of the PIUs at appraisal stage Is essential to ensure effectivecoordination and management across the levels of project implementation. The PIUs of the project did not in fact havesubstantial decision-making authorities particularly the one in JIRAMA. This resulted in inefficient project execution. Thedecisions in relation to the project had to undergo several layers of approval in the organizational structure. In practice, thismulti-layered approval process delayed approval of procurement files, payments to contractors, and approval of invoices.Establishing clear boundaries regarding the authority of all PIUs at appraisal can help prevent encountering such bureaucraticchallenges during implementation.
P151794 | Emergency Macroeconomic and Fiscal Support Grant | Western and Central Africa | Guinea | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/449011475086357147/text/ICRR-Disclosable-P151794-09-28-2016-1475086347213.txt | http://documents.worldbank.org/curated/en/449011475086357147/pdf/ICRR-Disclosable-P151794-09-28-2016-1475086347213.pdf | The following lessons are taken from the ICR with some adaptation of language: An emergency budget supportoperation could be an effective tool for re-engagement with the client under difficult circumstances. It is an appropriateinstrument to exploit additional opportunities that a major crisis would bring and it could be used to achieve three objectivessimultaneously: provide incremental funding to alleviate the impact of severe crisis, send a signal to international communityabout broader assistance needs of the affected country, and initiate critical longer-term reforms. Strongdonor coordination and information sharing could be a major driver for effective utilization of funds available to alleviate thecrisis as it helps to improve prioritization and strengthen accountability. To make the donor coordination more efficient, theGovernment has to be strongly committed to it at the very top by allocating sufficient human resources and politicalcapital.
P151803 | Honduras Fiscal Sustainability and Enhanced Social Protection DPC | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/465331498832926892/text/ICRR-Disclosable-P151803-06-30-2017-1498832921174.txt | http://documents.worldbank.org/curated/en/465331498832926892/pdf/ICRR-Disclosable-P151803-06-30-2017-1498832921174.pdf | IEG concurs with thefour lesson distilled on the success of the DPC,including the importance of dedicated technicalassistance for reforms in a difficult environment, government commitment and timing of engagement, coordination with developmentpartners, and complementarity of World Bank instruments.In addition, the DPC underscores the importance ofsetting realistic objectives. The World Bank supported a broad reform agenda in Honduras. However, the countryhada poortrack record in maintaining fiscal discipline. Several recently evaluated World Bankinvestment projects in the DPC policyareas was also unsuccessful -the Power Sector Efficiency Enhancement (P104034) was rated moderately unsatisfactoryand the Improving Public Sector Performance (P110050) was rated unsatisfactory. In this context, the scope of the DPC wasappropriately modest even though the ICR states that the DPC tackled an ambitious set of reforms. Suchrealismappear tohave been a key factor in the programs success in achieving the expected outcomes.
P151804 | FIRST PROGRAMMATIC SHARED PROSPERITY DEVELOPMENT POLICY LOAN | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2016 | 2022 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/572281626085623641/text/Panama-PA-First-Prog-Shared-Prosp-DPL.txt | http://documents.worldbank.org/curated/en/572281626085623641/pdf/Panama-PA-First-Prog-Shared-Prosp-DPL.pdf | The ICRR concurs with key lessons that are articulated in the ICR.Strong government ownership of thereform agenda is essential to ensure the implementation and sustainability of a DPO series. Selecting program objectives andreforms that had wide public support as well as political backing helped to ensure that the necessary legislation would be passedand implemented. It was important that the legal and regulatory framework underpinning the reform program was initiated anddeveloped by the Government, with technical inputs from the WB and other development partners (ICR, p. 49). TheGovernment continued to support the PDO beyond the closing of the DPL series, in particular through a new DPO series tocarry forward actions that were originally intended for a fourth Shared Prosperity DPO but were considered too complex to beimplemented within the time frame.Simple design based on strong analytical underpinnings and technicalsupport are important for effective design and implementation of appropriate interventions. The series focused on threemain objectives that were closely aligned with the Governments Strategic Plan and priorities (as well as the BanksCPF) and had strong analytical underpinnings, rather than trying to cover an extensive array of measures (ICR,p. 50).Readiness to adapt to changing circumstances is important to ensure that the program remainsrelevant and addresses emerging challenges. The most obvious example was the inclusion of new actions (within an existingobjective) to address the challenges to Panamas international financial standing as a result of leaked documents. Targetshad to be adjusted periodically in response to monitoring the progress of implementation, sometimes to be more realistic andsometimes more ambitious.Continuing engagement beyond the series is important to sustain results byfollowing through on implementation and mitigating risks. In this case, a planned fourth DPO was instead rolled into a new DPOseries, enabling continued dialogue and actions focused on complex issues in order to deepen the reforms initiated under this DPOseries (which in turn was carrying forward some reforms initiated in previous operations).A further lesson is theimportance of technical assistance that is timely and well-targeted to addressing technical issues that arise ormay impede implementation. Reforms to address tax transparency and fiscal integrity introduced after the series had begun likely would not have been implemented so effectively without bringing in expertise from the WBG and other developmentpartners in these areas.
P151816 | Financial Sector Support Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062923195539811/text/P15181604374a006e0917c0d7d1ca2b911f.txt | http://documents.worldbank.org/curated/en/099062923195539811/pdf/P15181604374a006e0917c0d7d1ca2b911f.pdf | The following are lessons learned from the ICR with some paraphrasing: When designing and implementingprojects which include improvement of digital financial services, having IT and cybersecurity experts in the project team canincrease projects achievements. The FSSP project involved all of the regulatory and supervisory entities and theirupgrading of IT frameworks. This required management of technology related risks and good understanding of cybersecurity. Theproject team could have benefitted from such expertise within the team to assist with the design, and making necessary adjustmentsto the project activities. As digital financial services and the need to manage technology related risks is quickly gainingimportance, having strong expertise on IT and cybersecurity on the project teams can improve design and implementation of similarfinancial services projects in the future. Bringing all supervisory /financial sectorstakeholders together under one project can create synergies between the actions and can improve implementation as well increaseoutcomes of the project. Such schemes may increase coordination and communication among the relevant institutions. In thecase of FSSP, supporting both PDMO and CBK together contributed to a better coordination of the M-Akiba issuance. In addition, theprovision of support to both CMA and NT under the project facilitated the approval of a new capital marketsregulation. Having a flexible project design and participatory approach can contribute to increasingachievement of project development objectives. This projects flexible design allowed to address thegovernments emerging needs in relation to the changing economic and financial conditions in Kenya. It was possible to adjustactivities, through restructuring the project to provide support and set up of KDIC during the time of bank failures.
P151821 | Second Programmatic Resilience Building Development Policy Credit | Latin America and Caribbean | Grenada | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest |  |  | The following two lessons are taken from the ICR with some adaptation of language: When designinga programmatic series, it is important at the outset to be realistic about what can be accomplished, taking into account capacityofgovernment counterparts. Excessive optimism or complexity, such as that involved in the design of some components of thisprogrammatic series, results in having to adjust subsequent operations to reflect the reality on the ground. Political economyfactors in small countries, such as Grenada, may be of an order of magnitude different from those in large economies. For example,downsizing government departments must take account of scarce alternative opportunities; only a limited pool of potential investorsmight be interested in investing in PPP projects in a small economy; and skills and capacity may be scarcer.Creation of new administrative agencies can lead to mission overlap and higher fixed costs. This series required the creation ofnumerous new units and agencies, where assigning responsibilities to dedicated staff in existing units might well havesufficed.IEG draws the following three additional lessons: Adequaterecognition at the design stage for technical assistance (TA) requirements can assist the successful development and implementationof a reform program. In this case, relying on regular support from the World Bank team, and other external partnersproved insufficient. More could have been done to mobilize resources for targeted TA for certain particularly complex initiatives,and through leverage of the investment lending portfolio. While including legislation, new regulations, and otherpieces of paper within prior actions is appropriate, a program that does more to ensure practical application on theground stands a greater chance of success. Here, much new legislation was approved, but in several cases the capacity or politicalwill to apply the modified legal and regulatory framework was not manifest. Particularly in small economies withlimited implementation and coordination capacity, a relatively simple reform program focused on a few key areas stands a greaterchance of success than a wider-ranging initiative. In this case, the relative lack of success was due in no small part to anover-ambitious design involving ten sectors and thirteen agencies.
P151831 | Kenya Youth Employment and Opportunities Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | High | https://documents.worldbank.org/curated/en/099090624180510874/text/P151831-4b10944e-48fc-4b44-8100-1057c751578f.txt | https://documents.worldbank.org/curated/en/099090624180510874/pdf/P151831-4b10944e-48fc-4b44-8100-1057c751578f.pdf | Lessons drawn from the ICR (pages 32-33): Self-employment and entrepreneurship can provide critical employmentgrowth opportunities in a dominantly informal economy.In the case of this project, given the context of limited formal jobsgrowth, the clear focus on supportingself-employment with skill building and work experience through apprenticeships,combined with a comprehensive package of support for young entrepreneurs, played a key role in achieving short-term employmentoutcomes. Participation of private sector employers, not just training providers, can be acritical elementofemployment accessibility for vulnerable youth.In the case of this project, job placement was a key bottleneck underComponent 1 on employability. Although the projects original model for engaging private sector employers was not followed, theprojects arrangementsaddressedthe job placement challenge through including apprenticeships in the informalsector, using results-based financing models with private employers in the formal sector, andhiring specialized serviceproviders for training and linkage/placement with employers. Evidence-based decision making and knowledge buildingcan inform and strengthen operational implementation. In the case of this project, a strong monitoring and evaluationsystemsupported implementation effectively and transparently. Results of impact evaluations helped to direct overall funds allocationbased on the relative effectiveness of individual interventions and to adopt corrective measures.
P151832 | Transport and Urban Infrastructure Development Project | Western and Central Africa | Burkina Faso | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099040523082038242/text/P15183201417ce0b709d010e074f6be502a.txt | http://documents.worldbank.org/curated/en/099040523082038242/pdf/P15183201417ce0b709d010e074f6be502a.pdf | The operations identified four lessons (ICR, paragraphs 80-83). These arepresented below with slightediting. Covenants in legal agreements may be useful in synchronizingall components that would supportreadiness to implement.In this project, the simplified project design focused onactivities that were ready tobe implemented. Counterpart financing was secured bya covenant in the financing agreement. This completed supporting studiesfor activities under the first component. However, acovenant or agreement with the local governments similar to howcounterpart financing was secured for preparatory studies was notused.As a result of these shortcomings,targetswere underachieved, and some activities werecancelled because these could not be completed on time or transferred to otherBank-financed projects in the country for completion. Future similar projects may consider covenants in legal agreements tosynchronize all componentsreadiness to implement. Early planning of safeguardsmay help identifyrisks that may be mitigated by including correctivemeasures incontracts. In this project, contractors werehiredbefore the environmental and social (ES) safeguards studies were completed. Implementation revealed several ESnon-compliance.Good practice calls foridentifying safeguards risks, proposing mitigation measures and instrumentsfollowingthe preparation of technical studies before firms are contracted ESclauses may then be included such asstipulating the timely recruitment of safeguards specialists to monitor compliance. In this project, the social safeguardspecialist was absent for four years. This contributed todelays in implementing the RAPsandconstructionwork.An early assessment of Gender-Based Violence (GBV) risks may also outline an implementable GRM applicable to allactivities. Including periodic minimum performance standards/measures in construction contracts maybeuseful incentives in an FCV environment. In this project, corrective measures in the first three years of theproject(or halfway through project period) did not improve implementation. One road had a 46 percent completion rateonemonth away from the initial deadline, investment contractsunder component B had notstarted, and component C activitieswere not ready for implementation. The task team recognized the institutional instability within an FCV context brought by a largeinflux of internally displaced personsandthe constant demand to restorepeace and security.Action plans wereadopted to expedite project implementation by including clauses in construction contracts requiring a company to reach a minimummonthly progress rate under penalty of (recoverable) deductions. Bonuses rewarded exceeding performance targets.As a result,construction contracts met revised targets. A change in implementing agencies also facilitated implementation. Future operations inthe country may benefit from adopting a similar clause inconstructioncontracts. Multisectorprojects may require separate executing agencies tofoster ownership ofactivities implemented by eachagency.In this project, the Ministry of Infrastructurewas the home of a single Project Implementation Unit(PIU) with the Ministry of Transport(MOT) and the Ministry of Urban Planning and Housing (MUH) as members. Thisimplementation arrangement did not encourage ownership by the line agencies of their respective activities (see Section 5 Efficiency above).One PIUin each line Ministrymay encourage ownership and foster leadership in each executingagency.Acoordinator devoted to the project in each PIU may be hired usingperformance-based contracts. Includingperformance measures in personnel contracts (e.g., standards to be metfor completing specific tasks (preparing TORs, awardingcontracts, recruiting staff, reporting to donors, addressing grievances), including regular coordination with key stakeholders andrating the quality of reports)may address challenges objectively based onevidence. Future operations may hireatechnical coordinator exclusively committed to the project under the supervision of a strategic coordinator overseeing allactivitiesto increaseresponsiveness and leadership.
P151835 | BI-Social Safety Nets (Merankabandi) | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099080323130577510/text/P151835072e55a09409033025dd633ca67c.txt | http://documents.worldbank.org/curated/en/099080323130577510/pdf/P151835072e55a09409033025dd633ca67c.pdf | The ICR (pp. 29- 30) identified lessons or insights that emerged from the experience of this project. A few ofthese are echoed here. Pilots are useful for effectively scaling up targeted interventions to largerportfolios. Regular cash transfers work well with complementary behavior change activities/support to promote investmentin households human capital and productive inclusion. Providing cash transfers to women under the social safetynet program helps in empowering them and in addressing childrens needs and nutrition. However, appropriate efforts need tobe taken to mitigate any risks associated with going against existing gender norms. Participatory approaches can workwell in complex environments, especially when the project is first of its kind in the country as it helps in ensuring differentdevelopment partners are working in tandem towards in building the countrys social safety net.
P151851 | Integrated Water Resources Management in Ten Basins | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2017 | 2024 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | IEG derives the following lessons from the ICR: The Banks long-term engagement with the client isessential to enhance prospects for implementation success in dealing with complex institutional, legal, and socialreforms.This project built on previous Bank engagement and adjusted the design by incorporating lessons learned from theprevious experience as well as drawing on global experience. Notably, the predecessor project laid the groundwork for theinstitutional and legal reforms, but their full realization went beyond one project cycle. A comprehensive approach to reforms anda long-term relationship between the client and the Bank evolves over time as challenges emerge. As noted in the PAD of thepredecessor project, IWRM reforms take 10-15 years in developed economy contexts; therefore, in such contexts where the Bank issupporting a series of reforms that extend beyond one project cycle, the Banks Multiphase Approach (MAP) is as anappropriate mechanism when dealing with development problems and reforms that span multiple projectcycles. Measuring the user satisfaction of the services offered by the implementing entity is one way to capturewhether capacity building efforts have been successful. It can be hard to measure and quantify the impact of capacitybuilding projects in the short term when there is no large-scale infrastructure that will dramatically improve the production ordelivery of a service (e.g., reservoir, drainage systems, irrigation systems, etc.). The efforts of this project to strengthen IWRMcapacity at national and subnational level modifying human behavior - will ideally lead to benefits of improved droughtmanagement, increased water productivity, losses avoided from mitigating water conflict, averted losses from avoiding a damfailure, and improved disaster risk management. These outcomes often need to be modelled to capture the economic benefits of aproject. To measure the impact of capacity building projects one way is to assess the satisfaction of the clients who receive theservices from the institution. For example, farmers receiving real-time information on water availability for irrigation, surfacewater flows during climatic events to inform local authorities that flooding will occur, and ground water levels can informabstraction from aquifers. The information or training received by stakeholders ideally will translate into modified behaviors thatadd value to the stakeholder and society at large. Capturing stakeholder perceptions and behaviors can be one way to measurewhether a capacity building project is having its intended impact rather than just reporting on outputs generated or organizationalunits established. Listening to stakeholders who benefit from the service can be a proxy for whether the quality of that servicehas improved or not, which can also serve as a feedback loop to the implementing entity. (ICR author) Ahigh-level steering committee is an essential instrumental in ensuring continuity in project management, particularly when there ispolitical turmoil. The political crisis in Peru in recent years resulted in frequent changes in government and in theleadership of institutions which affected the implementation of this project. In this context, the Project established amulti-sectorial Project Steering Committee to provide high-level guidance and oversight around project management which proved tobe of upmost importance to the overall continuity of project implementation. The committee was chaired by the Ministry ofAgriculture and consisted of the head of ANA, representatives from the Ministry of Economy and Finance as well as agrarian andnon-agrarian water users, with the World Bank acting as an observer. The committee reviewed and approved decisions on the hiring ofkey experts, provided advice on strategic and operational aspects to incoming decision-makers, and allowed for coordination amongdifferent stakeholders where needed during times of transition. A strong citizen engagement strategy is needed toincrease the clients ability to achieve development outcomes. This project is another example in the water sectorthat demonstrated the impact of having a strong citizen engagement and education program as part of the design for water resourcemanagement. Engaging and organizing local communities was a key aspect to help ANA safeguard the investments in the technology andmonitoring at the basin level, and at the same time show local populations how information generated by the technology can be usedin managing water for agriculture.
P151861 | Mozambique - Financial Sector DPO II | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2016 | 2016 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | Two lessons are drawn from the ICR (pages 29-30), with some adaptation, anda third is added by this ICR Review.Solid analytical grounding, close donor coordination, and extensive technical assistance are important in thepreparationand implementation of structural reforms in the financial sector, particularly where institutional capacity isweak. Challenges to the stability and development of the financial sector in Mozambique weredaunting, but thecountrys capacity toplan and implement sector reformprograms was weak. The Bank, the IMF and otherdonorsextended TA to the government to help upgrade the implementation capacity of the BDM andBDMcapably issuedregulations to improve risk management in banks. However, the BDM faced capacity constraints proceeding to the next set ofreform measures and was delayed in raising the minimum capital requirements for banks and in establishing a crisis managementcommittee, two measures that were designated as triggers to FSDPO II but instead delayed as triggers to FSDPO III.Governments mustmake mid-term assessments of a programmatic series and be flexible to adjust course ifnecessary. The moderate accomplishment of the third objective suggests thatthe government could have carefullyassessed progress with the implementation of the reform plan before the closing of FSDPO II in mid-2016 to determinewhetherthe program had not made enough progress with the third objective to develop the long-term financial markets,beforeproceeding withplans for the FSDPO III. Following the cancellation of FSDPO III, the government returned tofocus on a more elementary concern associated with the first objective to reinforce financial stability by securing approval forthe Bank Resolution and Deposit Insurance Strengthening Project financed by FIRST. The focus on banking stabilitywouldturn out to beappropriate considering that two banksfailed in 2016 --- Moza Banco, the countrys fourth largestbank,in September, and O Nosso Banco, a small bank about 77 percent-owned by the ISSM, in November.Good governance in both the public and private sectors are essential in a reform program. In viewof the heavy damageinflicted on the economyby the governments failure to correctly report on its public debt, itis imperative that development programs in Mozambique, including this financial sector reform program, continue to emphasize goodgovernance principles and practices in both the public and private sectors. The imperative becomes even more urgentconsidering reports that the undisclosed loans were not only concealed, but also misused (indictments were handed out in January2019 against several government officials, bankers and private persons). Issuance of new bank NPL and risk managementstandards and passage of the AML/CFT law and rules under FSDPO I were a good start at promoting good governance inbanks.
P151869 | Burundi Coffee Sector Competitiveness Project | Eastern and Southern Africa | Burundi | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2016 | 2021 | 2023 | ICRR | >=25 million & <50 million | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099152002212328581/text/P15186904b377e047092f203e195ccf8a90.txt | http://documents.worldbank.org/curated/en/099152002212328581/pdf/P15186904b377e047092f203e195ccf8a90.pdf | The ICR included five lessons. The following three are emphasized with some adaptation oflanguage:1.In a FCV context, having more flexible procedures to transfer funds across the World Bankcountry portfolio in an emergency can increase disbursement rates.The absence of a flexible procedure to transferfunds under this project resulted in cancelling US$19.2 million, about a third of the grant funding.2. Settingfarm level prices at a sufficiently high level can incentivize producersto invest more of their resources and effortsinto cropproduction. Enhancing farmer incentives through better pricing can result in higher yields and improvedcoffee quality. Higher volumes of quality, fully washed coffee can, in turn, lead to lower per unit processing costs and to morestable and higher payments by off-takers. Thus, higher prices can contribute to more generous margins across the board, enabling arenewed cycle of investments. This can contribute to a steady growth of Burundis coffeesector3.Improving rural roads can be indispensable for coffee farmers to reduce time and cost oftransporting fresh primary production to processing points and markets. Coffee cherries need to be brought to CWSs within6 hours after harvest to avoid a drastic decline in quality. While distances are short in Burundi, rural roads are poor and hardlypassable during the rainy season. The project experience showed that producers were particularly satisfied with the 33 km (out ofthe planned 60 km) of roads constructed/rehabilitated under the project.
P151916 | Early Childhood Development Project | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099053024212041236/text/P15191617b19690951938b1323b2b3bbb02.txt | http://documents.worldbank.org/curated/en/099053024212041236/pdf/P15191617b19690951938b1323b2b3bbb02.pdf | IEG concurs with the ICRs lessons, notably: Substantial capacity buildingthroughoutimplementationis required for first-time clientsto promote client ownership,address high staffturnover, and sustain development outcomes. In this case, trust-funded activities allowed the Bank to organize study toursto Japan and China for senior SMCA leadership to enhance technical capacity and identify possible solutions contextualized to theSri Lankan context. Instituting beneficiary feedback mechanisms and regular follow-up throughoutaprojects lifecycle allows for course corrections to be implemented on a timely basis. The transmission ofinformation from the field to the PMU was delayed in this particular project, leading to delays in identifying real-time solutionsto ongoing challenges faced by the ECD centers, teachers, and communities. This was further exacerbated by the COVID-19-inducedlockdowns, resulting insignificant delays with gathering beneficiary feedback. The PMU found that while regular meetingbetween the PMU and PSC were beneficial, a similar downstream effort with the divisional and provincial officers would also haveworked to provide in-time support to address the challenges. The identification of indicators measuringimprovements in ECD quality can support progress toward the provision of quality ECD services.There is a growingbody of evidence published in the last decade suggesting that structural quality in the absence of procedural quality will havelimited and superficial impact on ECD quality. The project would have benefited from incorporating this nuanced understanding initsimplementation efforts, especially during restructuring, when the indicators were revised and added, to track progress inprocedural indicators of quality.
P151934 | EU/IPA Energy Sector Technical Assistance Program - Phase 2 Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2015 | 2021 | 2022 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099005106182231715/text/P15193405261340e00834004478f48112eb.txt | http://documents.worldbank.org/curated/en/099005106182231715/pdf/P15193405261340e00834004478f48112eb.pdf | The ICR had identified several good lessons of experience that can be drawn from this project. The ICRR suggests the followingadditional perspectives:Simple project designs with few stakeholders and components are easier to implement andhave a better chance of success than those involving multiple stakeholders and components, however when a complex project design isdeemed more suitable for achieving project objectives a conscious decision must be made whether to front load World Bank resourcesin project preparation or to shift more resources to the implementation phase. The project had an extensive list ofactivities involving many stakeholders (MENR, EUS, TEIAS, ESPIA, EMRA, BOTAS, including in some cases multiple units within thesame stakeholder entity). The level of ownership and capacity was uneven such that the World Bank had to devote considerable effortinteracting with stakeholders to ensure that there was adequate capacity (e.g., PIU) and ownership (e.g., EUAS) during theimplementation phase. The approach was risky as it appears the issue of ownership was not adequately addressed at preparation stagealthough the implementation risk was well understood. There was no conscious decision to delay the World Banks support onownership issues to the implementation phase, but the choice of the supervision staff team including a large part of it in theAnkara Office facilitated the constant attention that was needed on these aspects.Reforms typically requireinstitutional capacity to implement and maintain, but capacity is subject to the risk of erosion due to staffing changes unlesslong range plans are put in place for continual training and recruitment of suitable personnel. Long term engagementof the World Bank and EU would help to keep the focus on safeguarding the achievements of the project, especially through laterphases of the EU/IPA technical assistance program to the energy sector.The use of analternativemechanismfor implementing EU/IPA technicalassistance from that used for other activities in the samesector program provided an opportunity for learning lessons and improving coordination with the EU.Other activitieshad been supported withthe Central Financing and Contracting Unit of the Ministry of Treasury and Finance(CFCU)handling procurement and financial management.The implementation arrangement under thisprojectinvolvedproject coordination within MENR and channeling of financing through a World Bank administered grant,thusprovidingan opportunity for capacity building within the sector while also enabling cross learning both within thesector and with the CFCU.
P151941 | SECOND PROGRAMMATIC FINANCIAL SECTOR DEVELOPMENT POLICY LOAN | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2016 | 2016 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest |  |  | Three lessons, drawn from the ICR (pages 34-36) with some adaptation, are as follows:Governmentownership of reforms is crucial to the successful implementation of a DPL operation. The political, economic andsecuritycrisis of 2014-15 dictated thenecessity and the urgencyof the banking reforms under FSDPL1 andFSDPL2. However, economic necessity alone may not have been sufficient to complete two politically-difficultheadlineactions --- the submission by the banks of related party lending unwinding plans and the nationalization ofPrivatbank, following the latters failure to complete its recapitalization program.Strong political commitment by theUkrainian Government to financial reform was vital to complete the nationalization of Privatbank, consideringthe bankspolitical connectedness, and the submission by banks of related party lending unwinding plans, considering the vested intereststhat bank owners and managerswould have held with related party loans.A reform program would benefitfrom a flexible design in crisis situations. The two-part programmatic structure of FSDPL1 and FSDPL2 allowedthe Bank and the Government to adjust the policy matrix as the financial and economic crisis evolved in Ukraine over 2014-15.In this manner, the reforms were made relevant to changed conditions and responsive to evolving problems. For example, therising number of banks failures as the crisis deepened required a faster pace of deposit payoffs. In response, Enablingthe DGF to increase the speed of reimbursing insured depositors was added as a prior action to FSDPL2. Similarly,whereas FSDPL1 required diagnostic studies of the 35 largest banks, FSDPL2 required the certification by the National Bank ofUkraine (NBU) that 13 of the 35 banks were able to recapitalize in the amounts indicated by the diagnostic studies.Financial sector development and reform programs are always long-term efforts, for which structural and institutionalreforms are of paramount importance. Although FSDPL1 and FSDPL2 enabled the resolution of insolvent banks andthe nationalization of the largest private bank toaddress the immediate threats to financialstability,safeguardingbanking and financial stability is never aone-time operationbut is rather an ongoingeffort. In which case, theemphasis should be on structural and institutional reforms.The DPLs thereforefocusedon strengthening the financing of the Deposit Guarantee Fund (DGF) to enable it to meet the demandfor depositinsurance and bank resolution into the future. And, the DPLs aimed tostrengthen bank capitalto maintain publicconfidence in the banking system and to improve the banks capacityto meet the demand for credit in the Ukrainianeconomy.
P151941 | SECOND PROGRAMMATIC FINANCIAL SECTOR DEVELOPMENT POLICY LOAN | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2016 | 2016 | 2020 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/477561579113645942/text/Ukraine-First-and-Second-Programmatic-Financial-Sector-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/477561579113645942/pdf/Ukraine-First-and-Second-Programmatic-Financial-Sector-Development-Policy-Loan.pdf | 6. Lessons 6.1 Close coordination among donors is critical for DPLs to maximize the effectiveness of a jointly designed reform program. In this DPL series, close donor coordination ensured the reform program's consistency and the uniformity of advice regarding policy measures. 6.2 The design of DPLs needs to focus on all relevant issues, potential weaknesses, and gaps in reform measures. There were shortcomings in dealing with state-owned banks and the contracting framework in the DPL series. Although these omissions were understandable given the need to focus on the immediate crisis response (which overshadowed these medium-term concerns), the sustainability of outcomes in the long term relies on a continued focus on such reforms in follow-up operations. 6.3 The presence of task teams in the field can be a critical factor in promoting financial sector reform. Country-based task team leaders can have local knowledge and the ability to engage closely with counterparts. This is an important element in planning succession. 6.4 Weak public understanding of financial sector reforms indicates a need to expand outreach efforts to enhance political sustainability. 6.5 Sustainable reform is difficult to achieve in countries that have corrupt power structures and court systems. Under such circumstances, it is an open question whether World Bank assistance risks providing additional resources for rent seeking rather than support for reforms. 1For selected indicators regarding exchange rates, see the International Monetary Fund website at http\.//data.imf.org/regular.aspx?key=61545850. 2The Country Assistance Strategy for fiscal years 2012â€“16 reported that the general government deficit in 2010 was targeted at the equivalent of 5 percent of gross domestic product but was missed because of the deficit of Naftogaz, illustrating the connection between fiscal discipline, the losses of state-owned enterprises, and financial sector stability. 3The 2012 Household Budget Survey estimated that 19 percent of poor households and 16 percent of the bottom 40 percent had savings in financial institutions. 4 This is a temporary bank established to acquire the assets and liabilities of a failed bank. 5Between early 2015 and the end of 2016, the Deposit Guarantee Fund's staff increased from 200 to 399, and its budget doubled. Furthermore, most of the new staff was employed in the Department of Consolidated Sales and Asset Management, which had been created specifically to address problem bank resolution. 6The level of corruption in Ukraine is exceptionally high. This can severely undermine economic growth prospects, particularly by hindering private investment. Therefore, reducing corruption is essential to speed up the process of economic convergence with the rest of Europe (IMF 2017, 3).
P151947 | Third Lagos State Development Policy Operation | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2015 | 2017 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial |  |  | Three lessons are drawn from the ICR (page 29), with some adaptation. The predecessor to this programmatic series,the stand-alone FLSDPO, drew similar lessons.Sub-national operations should carefully consider the degrees ofdependence of the sub-national government on the central government and define prior actions and results targets that do not undulypenalize the sub-national government for actions not under its control. The fulfillment by Lagos of the programsstate-level fiscal balance and debt ratio targets depended on thestatus of inter-governmental revenue transfers.Sub-national operations should consider the institutional capacity of sub-national agencies to implement reform plans. Insome cases, technical assistance may help upgrade the capacity of state agencies.The state government agencies met theprogram targets for audit and for financial management but missed the outputs for procurement reform.Theprogrammatic approach can help sustain the momentum of a medium-term reform program during changes in political leadership to theextent that they commit the government to a multi-year reform path and keep the policy dialogue active. The programmaticapproach to SLSDPO and TLSDPO, and the close linkbetween the two operations and the FLSDPO, helped ensure that the Banksengagement and dialogue with the state government was ongoing and continuous even as the stateheld its gubernatorial electionin March 2015,prior tothe completion ofSLSDPO and before the approval of TLSDPO. The continuity of thereform program could have been compromised without the programmatic approach, which had securedthe states commitment tothe medium-term initiative before the new electoral cycle.
P151963 | Ecuador - Sustainable Family Farming Modernization Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2016 | 2024 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061724214519367/text/P151963-dbb35b0a-71b6-4e76-94a5-00e907056908.txt | https://documents.worldbank.org/curated/en/099061724214519367/pdf/P151963-dbb35b0a-71b6-4e76-94a5-00e907056908.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1. To ensuresmooth implementation of project activities,appropriate institutional arrangements are required to be in place.Implementation of the project was significantly affected by two institutional factors: a cumbersome institutional decision-makingprocess; and the fact that the project was designed as part of a broader Government program, which would finance certain activitiesneeded for the project to achieve its objective. While a number of legal provisions were introduced early on in the project tofacilitate implementation, the PIU was not provided with sufficient decision-making power.Also,the complementaryactivities of other programs (especially delivery of agri-environmental innovations) ended up being taken on by the project itself(through a restructuring). Further, the assignment of the project implementation to a sub-secretary under MAG resulted in weekinstitutional leverage and ownership.Future projects should be enabled with sufficient decision-making autonomy; bestrategically placed at a level that guarantees full institutional ownership; and encompass all the elements needed to ensure thatthe agreed objective can be achieved without depending on other programs or other initiatives beyond the projectscontrol.2. Projects involving multiple activities need a smart procurement approach to ensure smooth flow ofprocurement activities.The sub-project cycle involving three main groups of activities (i.e., works, capacitybuilding, input delivery) triggered a cumbersome procurement approach in which multiple activities were split in large numbers ofsmall consultant and work contracts, resulting in low participation of bidders, high volume of low-cost activities, largegeographic dispersion, and frequent contract extensions.To reduce transaction costs and foster economies of scale futureprojects could adopt packaging contracts in larger lots to improve procurement efficiency.3. The project designneed to reflectrelevantME arrangements combined with adequate capacity in the PIU to ensureproper andverifiable project impact evaluation. The validation of the projects ME system dataexperiencedshortcomings that include data collection and transmission errors, and incorrect interpretation and calculation ofresults indicators. Futureoperations need to include in the PIU an ME specialist with sufficient statistical knowledgeand programming capabilities to enable the replicability of survey results.The following lesson is emphasized by IEG basedon input from the project team:4. To ensure timely implementation of projects in countries with limitedimplementation capacity, the Bank needs to ensure timely flow of funds, stability of the PMU, coordinating with other developmentpartners (like FAO), and better synchronization of activities.Given Ecuadors extremely slow, bureaucratic andcumbersome internal approval processes (including procurement and financial processes), channeling the Bank loan funds through asecond-tier bank (e.g. CONAFIPS, a government-owned but enjoys a great deal of independence) should be considered. This likelywould have avoided a substantial portion of the delays suffered by the project. Also,the Bank from the very beginning onwardsshould agree with the Borrower on a stable PIU which would not be affected by any change in government, ministers, vice-ministers,and Secretaries of Irrigation. Further, the Bank should explore the possibility of engaging an implementation support agency (suchas FAO e.g.) to support the PIU. Finally, more attention should be givento the synchronization of the three main elements ofthe project, i.e. building of irrigation infrastructure, training capacity building of prospective users (farmers), andsupply of complementary inputs.
P151972 | Citizen-Centric Service Delivery Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2016 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099450012272134141/text/Albania000Citi0ered0public0services.txt | http://documents.worldbank.org/curated/en/099450012272134141/pdf/Albania000Citi0ered0public0services.pdf | The ICR offers the following lessons with which IEG agrees: The experience with the project demonstrates that aclear vision and purpose must underpin the digitalization efforts of a government which seeks to deliver better services to thecountrys citizens. For reforms to succeed, selecting the correct delivery model is fundamental. For Albania, thecreation of high-quality physical access points, alongside efforts for the service to be more citizen-centric (via feedback andservice standards), created a new culture, which raised citizens expectations and increased the demand for more complexinstitutional service delivery reforms. Building CSCs produced quick gains and visible changes, creating the space for moreambitious institutional reforms. The customer-orientation of the CSCs and their professionalism changed the service deliveryculture in the country. Selecting appropriate results indicators must constitute a central point of project design, sincethe information and communications technology inputs (ICT) alone are insufficient to ensure that the project delivers services andbenefits citizens. Sustained and informative dialogue with the client regarding the instrument is critical to ensure thatthere is strong alignment between the incentives it provides and the incentives of the relevant implementingagencies.The results of the project illustrate the continued relevance and importance of physical channels ofservice delivery, especially for the vulnerable groups. In other instances, further financing and investment should be encouragedto support scaling up e-service ambitions to ensure more resilient, citizen centric and transparent service delivery. To strike theright balance, it is important to take into account the local context, the characteristics of service users and thecharacteristics of the services provided.
P152018 | Floods Emergency Recovery Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2015 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/661811596831459432/text/Serbia-Floods-Emergency-Recovery-Project.txt | http://documents.worldbank.org/curated/en/661811596831459432/pdf/Serbia-Floods-Emergency-Recovery-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptationof language.1. Flexible procurement packages and provisions for retroactive financing are important tools foremergency situations.In this project, a significant set of technical designs existed that could be utilized quicklyfor implementing reconstruction activities. This, in conjunction with provisions for retroactive financing,enabled launchingprocurement activities even before the Bank approved the project.2. Preparation of the Contingent EmergencyResponse Componentneeds to be treated as a priority. In this project, the precise responsibility for preparing CERCProject Operation Manual (POM) was not clearly specified,and no deadline was fixed for the completion of the POM. Though theCERC was a new instrument atappraisal, this project offers a concrete example of why teams should regard producing a POM forCERC, either during implementation or even during preparation, as a priority.3. Supply and installation ofequipment should not be separated during contracting. The rehabilitation of fixed substations in this project was animportant activity, and the intention at design, had been to procure the needed goods and installation services in integratedcontracts. However, the procurement of equipment was separated from the installation services during implementation, on groundsthat there were qualified local firms to execute installation of the procured equipment. This activity was not completed and thesubstations not installed.
P152021 | Power Sector Reform: Second Development Policy Credit | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2016 | 2017 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Fivelessons are drawn from the ICR (pages 22-24), with some adaptation of language.1) A dedicated sectorenergy reform operation (as opposed to inserting a limited number of prior actions in a multi-sector or general macro-economicsupport operation) can be more useful in countries facing severe energy sector challenges. The DPOs allowed for themodification of indicators and targets that could better reflect changing circumstances and evolvingpolicy dialogue. Forinstance, the targets for reducing subsidies were revised in the face of governments commitment to maintaining subsidies forpolitical economy considerations. Likewise, the government was able introduce, as complementary measures, a mechanism based ontariff surcharges and a Tariff Rationalization Fund to maintain nationally uniform tariffs in the face of windfall gains producedalongside falling oil prices during the operation period.(2). The governments ownership of reform isnecessary for the success of a development policy operation.In this operation, the governments ownership andinvolvement in the reform of the power sector was focusedduring preparation. The government issued notifications regardingreducing subsidies, increasing tariffs substantially and setting a cap on circular debt.When these priorities were no longerpresent, the leverage of the Ministry of Finance (MoF) over the Ministry of Water and Power (MWP) diminished and MWP no longer wasascommitted tosector reforms as it was during preparation. This contributed to the limited efforts at sector reformsduring DPO2.(3) A balanced approach among instruments targeting federal and sectoral levels can help bring aboutmore sustained results. Federal DPOs have supported IMFs programs to stabilize the macroeconomy byproviding budgetary support for reforms aimed at improving energy sector sustainability and private sector growth. A morestrategically balanced mix of budget support with other Bank instruments could help leveraging more sustainableresults.(4) Close collaboration with the International Monetary Fund can benefit a DPO program. Closelyaligned positions among donors could help in pushing through difficult reforms. Collaboration with the IMF could have played a rolein effective completion of the IMF program.(5) In the context of a DPO operation, it can be difficult to implementreforms, even when a requisite prior action has been taken. To help improve the collection rates and reduce distributionlosses of Discos, one prior action in DPO 1 had required the outsourcing of collections of Discos. Even though the prior action wasmet, only two distribution companies proceeded with the outsourcing of the collection of feeders with losses of 50% or above.
P152039 | Geothermal Exploratory Drilling Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2015 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/472641593015670736/text/Armenia-Geothermal-Exploratory-Drilling-Project.txt | http://documents.worldbank.org/curated/en/472641593015670736/pdf/Armenia-Geothermal-Exploratory-Drilling-Project.pdf | EG derives the following lessons drawn from the ICR:1. The projects phased approachwasappropriate forgeothermalenergy investments in sites with high resource uncertainty. In suchprojects, public funds could be used to cover the risky upstream exploration stages, so that private sector interest and funds canbe leveraged for downstream investments. The assessment determined that a power plant would not have been economically viable, evenif geothermal flow had been found. This allowed for the preservation of the remaining SREP grant funds, which could bereallocated to other priority projects in the SREP pipeline (including projects in Armenia funded by other donors, or even projectsin other countries).2. A comprehensive and open outreach effort to private geothermal developers proves tobean effective way to unequivocally determine the commercial viability of further resource development after explorationdrilling: During the project, after test well results established that the temperature of the geothermal resourcefell in a grey area between temperatures suitable for a flash cycle plant and the minimum needed for a binary powerplant, the use of market soundings provided a clear indication to the Government that there was no real private sector interest indeveloping the resource.
P152064 | Albania Financial Sector DPL | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/120091562777268548/text/Albania-AL-Financial-Sector-DPL.txt | http://documents.worldbank.org/curated/en/120091562777268548/pdf/Albania-AL-Financial-Sector-DPL.pdf | The ICR draws the following two lessons from the experience of implementing this operation, with some adaptation oflanguage.(1) A quick and comprehensive response to a crisis can lead to sustainable improvements infinancial stability. This operation was in response to the crisis due to the high NPLs. The urgency created by the crisisfacilitated in the passing of complex pieces of legislation.(2) Continuous engagement with theauthorities during the program design and implementation phase and a strong on the ground support can help in programimplementation. In this operation, this aided in providing timely support to react to problems (such as thebailiffreform setbacks during implementation).
P152096 | Supporting Education Reform in Targeted Circuits | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099031824073527007/text/P15209611828980cf18d8f19b5661bf74f5.txt | http://documents.worldbank.org/curated/en/099031824073527007/pdf/P15209611828980cf18d8f19b5661bf74f5.pdf | The ICR (pp. 30-31) offered several lessons and recommendations, and the following lessons were re-stated by this ICRReview:Working closely with project implementing agencies to ensure understanding of the World Bankspolicies and procedures facilitates the World Bank re-engagement with the country in development lending. The project wasone of the first operations approved when the World Bank began reengaging with Ecuador after a lending hiatus. Although thepreparation team considered lessons from similar projects in other countries, it had limited country experience, and the Clientalso had limited familiarity with World Bank policies and procedures. Hence, the project required adjustments and closeimplementation support to pursue its objectives.A thorough identification and anticipation of macroeconomic andpolitical risks at the preparation stage can help in ensuring a simple project design. Ecuadors economy ishighly dependent on oil revenues. At the time the loan was approved, oil prices started plummeting, going from US$106 per barrel inJuly 2014 to US$30 per barrel in January 2016, and the GDP stagnated. This led to partial loan cancellations to assist thecountrys stabilization efforts. Also, the project was prepared at a time when Ecuador had witnessed relative continuity inpolicy priorities and staffing under the previous administration that lasted 10 years. Elections were scheduled for 2017, andchanges were likely. While little could be done to mitigate these risks that are beyond the control of the project, they shouldhave suggested greater caution and simplicity in the initial project design.Market research that identifies thebest approach for managing civil works and the use of unit prices instead of lump sums can facilitate the implementation ofprojects with a large number of contracts related to infrastructure rehabilitation. In the specific context of thisoperation, helping the implementing agency to manage infrastructure rehabilitation instead of hiring a third party was found to bean effective option. Hands-On Expanded Implementation Support wasprovided to the implementing agency to speedup the launch and award of procurement processes. The project significantly improved civil works execution once MINEDUC became theonly executing agency for infrastructure development.
P152104 | Serbia Competitiveness and Jobs | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2016 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099825006232284890/text/P1521040f8a8950240b4200f523068af30c.txt | http://documents.worldbank.org/curated/en/099825006232284890/pdf/P1521040f8a8950240b4200f523068af30c.pdf | Composite and suboptimal number of DLIs introduced at project design can complicate project management and becomeadministratively cumbersome for the World Bank and implementing agencies.Project design involved 9 DLIsandmost of them were composite (ex. DLIs regarding the innovation component).Although, detailed verificationprotocols were defined to assist the World Bank and implementing entities, they were difficult to manage and required intensivework. Broad consultations with all relevant counterparts in a structured manner can help addressing some ofthe implementation issues. As reported in the ICR, some of the counterparts were not fully on board with the proposedactivities and felt that additional consultations to further narrow down the priorities were needed, creating complications duringimplementation.At the same time, for activities (Component #3 on Innovation) where existing dialogue was betterdeveloped, including through engagement from previous projects, priorities were more clearly developed and ownership from thecounterparts stronger.Technical assistance provided to Borrowers agencies at various implementationcapacities can complement and improve achievements of investment operations.According to the ICR,team membersacknowledged that it was key to have a TA embedded in the project, which was also funded by trust funds (about EUR 2.3 million, oralmost 40% of the total TA provided). In addition, line ministries and agencies confirmed that the main benefit of the CJproject was the technical assistance received, as the capacity of the counterparts was uneven (i.e., the PPS showed high technicalcapacity whereas the capacity of the MOESTD was weaker).
P152136 | Nicaragua Strengthening the Public Health Care System | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2015 | 2021 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/618911624021706418/text/Nicaragua-Strengthening-the-Public-Health-Care-Sys.txt | http://documents.worldbank.org/curated/en/618911624021706418/pdf/Nicaragua-Strengthening-the-Public-Health-Care-Sys.pdf | The ICR (pp. 24-25, and the Borrowers comments, p. 48) offered useful lessons restated byIEG:Results-based financial incentives, complemented by a quality assurance framework, can inducepositive behavioral changes among institutional actors. In the context of the project, annual performance agreementsand Quality Health Care Plans, along with effective ME systems, proved to be useful tools to promote a results-orientedculture and accountability that guided the management of decentralized health services at the municipal level. Capitation paymentslinked to municipal performance resulted in closer alignment with the Ministry of Health, including in homogenizing standards ofcare and reporting.The implementation of a project within the sectors organizationalstructurei.e., without an added executing unit-- contributes to optimizing resources and allows the development of in-housemanagement capacity,as was observed under the project. The projects reliance on national-level technical andadministrative directorates to provide leadership helped in fostering commitment to strengthening both central and peripheralcapacities in the sector.A sustained sectoral engagement with the Bank can produce long-lastingdevelopment impact and can facilitate sectoral efforts to embark on new strategic directions. This operation was part of asequence of four operations spanning over two decades that provided support to decentralization and incremental strengthening ofNicaraguas public health care system. As such, the project benefited from previous progress made in the sector, capacitiesthat were built, and lessons learned from preceding operations, thus setting the foundations for further improvements and forstrategic shifts to address evolving disease priorities,as was observed under the project.Incountries that are vulnerable to natural disasters that are known to contribute to population displacement and infectious diseaseoutbreaks, flexible financial arrangements in project design can help the initiation of timely sectoral responses to communicabledisease threats. Pre-planning, activation, and disbursement procedures that were applied by the project allowed promptresponses to public health threats arising from the spread of Dengue, Zika and Chikungunyaviruses.
P152171 | Economic Management Strengthening | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099122523195518498/text/P1521711ae3d5600e1927c1bc923e272adb.txt | http://documents.worldbank.org/curated/en/099122523195518498/pdf/P1521711ae3d5600e1927c1bc923e272adb.pdf | The ICR (pp. 21-22) offers several lessons and this ICRR would like to emphasize several ofthem:Inter-departmental collaboration in project design enhances thedelivery of outcomes. Anyproject requiring collection of data or connecting systems, as in this case, requires extensive communication and stakeholderengagement. Projects of this nature need to undertake an in-depth scoping before designs are presented. The procurementof the DWI/BI required more time than initially planned due to the changes to the departments within GRA with theresponsibility for the management of DW/BWI, which in turn required additional inter-departmental collaboration. Task teams mayalso consider internalizing this during project design and ensure the procuring entity and the beneficiary entities are on the samepage.During restructurings, the level of ambition needs to be carefully calibrated. The government andBank team were understandably cautious about the pandemics uncertainties and focused on achieving the original PDO. They mayhave missed opportunities to respond to changing dynamics/circumstances and new information. At the first restructuring, due inpart to delays (2020), there was evidence that the challenges faced by Ghana were increasing. Fiscal challenges hadincreased, with an increasing fiscal burden from SOEs, high rollover and solvency risks, the reforms around debt management couldhave been re-designed to address the unfolding situation.
P152230 | Kazakhstan: Southeast Europe and Central Asia Catastrophe Risk Insurance Facility | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | GEF | IPF | 2016 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/769071607368827989/text/Kazakhstan-KZ-SEECA-CRIF.txt | http://documents.worldbank.org/curated/en/769071607368827989/pdf/Kazakhstan-KZ-SEECA-CRIF.pdf | The ICR identified a few lessons, which are summarized and rephrased below: For growing economies exposedtocatastrophe risks, a sustainable solution is to promote a private catastrophe insurance marketin combination withfinancial resilience:Kazakhstan faced both a harsh climate, elevated earthquake risk, and someweaknesses inits economic structure. This project showed how thiscountry mitigated catastrophic consequences by transferring financialrisks to the private risk markets. For catastrophe insurance to be effective, the insurancecoverageneeds tobe imbedded into a lenders underwriting process. In the context of this project,ascaled down catastropheinsurance market and infrastructure project were developed.The achievedoutcomewould only grow deeper rootsonly when a compulsory catastrophe insurance will be legislated to create a goodenvironment of insurance market expansion. Forthe catastrophe insurance to reach a high level ofpenetration, itneeds to be made compulsory or to be bundled with something that people want, like loans or subsidies. If bundled with a loan,catastrophe insurance becomes a part of the production costs for the insured.Hence, catastrophe insurance needs to become anintegral part of the lending process. The presence of an implementing agency that already has adeveloped expertise is central to implement a project in a difficult context. The Kazakhstan context wasnotideal for the successful completion of this project, which achieved tangible results.This was possible because aprofessionally managed reinsurance company like Europa RE had the expertise for implementing a technically complex catastropheinsurance project. Itsoutstanding expertise in developing catastrophe insurance marketsand its reinsurancecapacity at minimum cost were central to the performance of the project.
P152232 | Vietnam HCFC Phaseout Project Stage II | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2019 | 2024 | 2025 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111124130022313/text/P152232-4eedb651-e763-46dc-9b16-3b1068eba53e.txt | https://documents.worldbank.org/curated/en/099111124130022313/pdf/P152232-4eedb651-e763-46dc-9b16-3b1068eba53e.pdf | The ICR included several useful lessons learned, which were adapted by IEG: If the governmentrequires a long time for processing the project and signing the legal agreement there is a risk that the market/shareholderanalyses are no longerrelevant once the project becomes effective and might have to be updated. In this project, theprocess with the government started in 2016 and lasted several years. Once the project became effective in 2019, the market hadchanged completely resulting in implementation issues such as limited progress in the identification, preparation, and approval ofsubprojects and conversion activities and SMEs lack of capacity and willingness to prepare individual subprojects. Thesechallenges resulted in disbursement delays and the need to reduce the projects scope. A project designinvolving the private sector that is sufficiently flexible to be adapted to unforeseen market changes can ensure that the projectmeets the objective within the boundaries of donor conditions. In this project, the heavy reliance on the subprojectapproach became difficult in the refrigeration sector due to market shifts and an initial misunderstanding of the make-up of thesector as well as restrictions imposed on alternatives by the MLF Executive Committee. As a result, it was not possible to modifythe design of project activities for the refrigeration sector leading to a significant return and partial reallocation offunds. Providing continuous training and capacity activities for project beneficiaries and partner agenciescan positively impact the sustainability of outcomes beyond the project. In this project, while some enterprises did notqualify for MLF assistance, enterprise capacity was further strengthened through workshops and awareness raising sessions held forenterprises in the AC, foam, and refrigeration sectors, to ensure that these enterprises were ready for HCFC phaseout on their ownonce the bans became effective.
P152241 | Somali Core Economic Institutions and Opportunities Program (SCORE) | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2021 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/839761624646059771/text/Somalia-Somali-Core-Economic-Institutions-SCORE.txt | http://documents.worldbank.org/curated/en/839761624646059771/pdf/Somalia-Somali-Core-Economic-Institutions-SCORE.pdf | Three lessons are drawn from the ICR (pages 42-42), with some adaptation.Structuringcomplex andlong-term reform programs asa series of gradual and carefully sequenced operations raises their chances of success in FCVsettings. In Somalia, SOMPREP1 (which aimed to strengthen public-private dialogue and buildpublic sectorcapacityfor private and financial sector development), SOMPREP2 (which aimed to improvethe investment climateinthe fisheries and gums and resins value chainsand in seaport and solid waste infrastructure),this SCORE-Phase 1Project, which aimed to improve the enabling environment for private and financial sector developmentand catalyzeprivate investment and job creation,and SCALED-UP (which aimed to provide access to digital financial and government servicestargeting entrepreneurship and employment) comprised a series of structural reform operations to develop public institutions andencourage private activity. The parsing out of structural reform plans into manageable operations helps address constraintsto program implementation inFCV settings, as in Somalia, where securityrisk ishigh, political commitmenttoreform can be fragile, the macroeconomic environment is volatile, institutional capacity is weak, and reform implementation can beupended by any number of unexpected shocks.A multi-faceted approach to stakeholder engagement helps securepolitical commitment to reform measures. This project employed confidential discussions and inclusive forums toconduct policy dialogue and to obtain the commitment of stakeholders to the reforms measures. According to the ICR, thismulti-faceted approach to stakeholder engagement was instrumental inimproving decision-making and facilitatingthe completion ofproject activities related to the development of selected Somali ports. Specifically, theconsultations and negotiations involved the FGS authorities, the Ministry of Transport and Ports, the Mogadishu Port Authority, andthe Federal Governance Committee, the hybrid Somali-international bodyestablished in 2014 bythe FGS, donors, andinternational financial institutions to provide a forum for dialogue on strategic financial governance issues. With FederalGovernance Committee providing political and diplomatic oversight, the consultations paved the way forthe FGS to sign arevised 14-year agreement to manage the port with the same concessionaire inOctober 2020Leveragingpubic grants to mobilize private financinghelp enhance the sustainability of private sector developmentefforts. In this project, the SBCF grant matching scheme mobilized US$6.5 million in investments from beneficiarySMEs andUS$2.1 million from families and friends of the SME owners, as well asUS$1 million from domestic financialinstitutions, raising US$9.6 million in private sector resourceson an 1.8X leveraging of US$5.3 million in public grantsextended by the SBCF to some 101 beneficiary firms. Private financing (or financing that doesnt come fromaninstitutional source, whether a public agencyor a private sector bank)by grant beneficiaries and their familiesand their friends are important sources of enterprise funding in many business settings and help align private incentives with thepublic purpose of matching grant schemes.
P152276 | Belarus MSME Access to Finance Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2018 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099082123133040428/text/P1522761c663aca41c6f014bbe19ffb1dc94d632f8b5.txt | http://documents.worldbank.org/curated/en/099082123133040428/pdf/P1522761c663aca41c6f014bbe19ffb1dc94d632f8b5.pdf | The following three lessons are taken from the ICR with some adaptation of language: Implementing an LOCproject as part of a broader structural reform agenda can yield more significant and sustainable results. The design oftheLoC was informed by sound analytical work, including FSAP, and implementation results reflected increasing access to finance bythe MSMEs. A more significant impact and sustainable results could have been achieved if the LoC were carried out in tandem withbroader structural reforms in the country. When implementing a LoC, an established and smooth relationshipbetween the implementing agency and the PFIs can contribute to a more successful project implementation and achieving results.The operation was implemented on the existing relationship between the DBRB and the PFIs, which helped close cooperationon and monitoring the LoC. The bottlenecks were addressed promptly, and necessary adjustments were made to the terms and conditionsof the LoC. A flexible LoC design that accommodates changes promptly and efficiently can help improve theimplementation. In the case of the project, while taking feedback from the PFIs and the beneficiaries, the PIU and theWorld Bank team adjusted the terms and conditions of the LoC. This was possible due to the flexible design, which did not require along procedural process, helped address barriers, and expedited disbursements.
P152347 | Bosnia and Herzegovina Employment Support Program | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041023164033302/text/P15234703a53300c70827a0437da9de4bfd.txt | http://documents.worldbank.org/curated/en/099041023164033302/pdf/P15234703a53300c70827a0437da9de4bfd.pdf | The ICR (pp. 33-35) offers a series of insightful lessons stemming from project experience, including thefollowing:A comprehensive approach to labor market policies, addressing both supply- and demand-side factors, canallow for flexibility in times of crisis. One of the projects approachesto increasing formal private sectoremployment among targeted groups of registered job seekers was through wage subsidies, an intervention that is by nature flexibleand responsive to labor market needs and to employers constraints (high labor costs). This proved to be particularly valuableduring the COVID-19 emergency, when other types of interventions (such as training) might have increased labor supply productivitybut not addressed labor market needs.Targeting specifically vulnerable populations and redesigning policiesto meet their needs is important for achieving higher-level policy objectives. In this case, defining eligibility forspecific vulnerable groups rather than allowing universal eligibility guaranteed access for populations who were less likely tohave obtained employment on their own. Project impact evaluations also showed that these groups remained employed longer, and thatsatisfaction was increased among both job seekers and employers.Cultivating a culture of continuous monitoring andimpact evaluation can encourage effective feedback loops, improving the design of interventions and achievement of outcomes.For example, in the RS, an annual impact evaluation showed that the employment program was most effective for job seekersbetween the ages of 25 and 30, people with lower qualifications, and the long-term unemployed, prompting the program to focus onand increasetargets for those groups in 2021.
P152358 | ICT Sector Support in Somalia Phase II | Eastern and Southern Africa | Somalia | IDA | FCS | Digital | Digital Development | RETF | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/412571624656637814/text/Somalia-SO-ICT-Sector-Support-Phase-II.txt | http://documents.worldbank.org/curated/en/412571624656637814/pdf/Somalia-SO-ICT-Sector-Support-Phase-II.pdf | The ICR draws the following main lessons from the experience of implementing this project, which are presented here with someadaptation of language.1. The project design needs to besimple andadaptable,especially in aFragile, Conflict and Violence (FCA) context. This project had a limited number of components and interdependentactivities. Many ofthe project activities were dependent on the passing of the Communications Law, but were designed in a waythat allowed for flexibility and adaptability, given that it was still uncertain whether the Act would beapproved by theparliament.2. Standard interventions need significant adaptation.The choice to supporta Communications Act and the National Communications Authority in this project was informed by telecom development across manycountries (including FCV countries),and by the first phase of this project. While these interventions are fundamentalbuilding blocks forthe evolution of the sector, looking forward, when developing this type of core sector interventions, itwould beuseful to incorporate features such as private sector incentives, understandingfragility drivers and developingadequate risk mitigation strategies and engaging stakeholders who can provide insight on what is needed to ensuresustainability.3. Reform drivers can help in expediting implementation. This project helped in thepassage of the communication law and establishing the ICT regulator. A success factor was the ability to link the expected reformsunder this project to the government goals of achieving High Indebted Poor Country (HIPC) status, enabling critical debtrelease.This was critical in a FCV context where policy reforms are needed to counteract power dynamics.4.Even if thehybridmodalityis necessary in a FCV context, they are not always efficient, and hence steps tomitigate the effect of these inefficiencies are required. The lesson from this project is that, while this modality canbesuccessful in kick-starting implementation, it adds to administrative complexities, and the uncertainty over theavailability of donor funding adds to the complication of project management.5. Local anchoring is particularlyimportant in a low security environment. This project demonstrated the importance of employing local language speakingstaff, and with an understanding of the local context, sensitivities and relationships. This project eventually did this through aSomali speaking consultant, and this proved to be essential in supporting the supervision team.
P152394 | Transforming Health Systems for Universal Care | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100824143538560/text/P152394-d8d03f1b-82d5-42aa-9e66-ac49dad27bb0.txt | https://documents.worldbank.org/curated/en/099100824143538560/pdf/P152394-d8d03f1b-82d5-42aa-9e66-ac49dad27bb0.pdf | The ICR (P. 32) provided lessons thatare summarized below:Data availability is critical to ensureadequate monitoring of project implementation.The project faced challenges in measuring indicators, particularlythose related to reproductive health. This was due to the design of the indicator, which relied on measuring frequency of visits tohealth facilities to obtain family planning care. This indicator was designed assuming demand would be mainly for short-term familyplanning methods. In reality, preferences transitioned to longer-term methods thatdid not require frequent visits tofacilities. In addition, local health facilities still used paper-based systems that did not facilitate the reportingprocess.Implementation of projects in a devolved context raises the level of complexity for projectimplementation. The results-based mechanism facilitated project implementation, as it adjusted to the variouspriorities at the local level. However, challenges remained due to delays in the transfer of funds to counties, as well as weakinstitutional capacity at the local level to carry out procurement and financial management and to comply with safeguardresponsibilities. Staffing in the PMT was not sufficient to support and supervise 47 counties, which had frequent staffturnover.
P152398 | Public Sector Modernisation Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099725011072236099/text/P152398008303a0ce08d080f1123f58d3a0.txt | http://documents.worldbank.org/curated/en/099725011072236099/pdf/P152398008303a0ce08d080f1123f58d3a0.pdf | The following lessons were identified: In a context where multiple government departments and entities areinvolved, the sequencing of activities is crucial to foster and strengthen collaboration. Under this project, the sequencing ofactivities under the Strengthening of HRM activities helped build a common understanding and ownership of the reforms leading toeffective collaboration among involved stakeholders. High-level PEFA indicators are often ill suited for measuring morefocused objectives.
P152406 | Federation Road Sector Modernization Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2017 | 2024 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR draws the following two lessons from the experience of implementing this project, with some adaptation oflanguage.1. Integrating climate resilience in the investment planning process can help the road agency providetimely interventions. A key activity of this project was conducting a vulnerability assessment of the network. Data fromthis assessment was incorporated into an upgraded Road Asset Management System (RAMS) to help short-term maintenance programs andlong-term reconstruction plans. This project demonstrated the validity of integrating climate change resilience into infrastructuremanagement systems rather than creating a parallel management system.2. Commencing land acquisition activitiesbefore project effectiveness can help in reducing delays during implementation. Given that land acquisition, compensationand resettlement are complex and can take years to complete, especially in countries with burdensome administrative procedures. Thelesson from this project is that sufficient time provided for land acquisition, can help in reducing delays duringimplementation.
P152440 | Energy Sector Development Policy Operation | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2015 | 2016 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/553061529696445101/text/Kyrgyz-Republic-Energy-Sector-DPO.txt | http://documents.worldbank.org/curated/en/553061529696445101/pdf/Kyrgyz-Republic-Energy-Sector-DPO.pdf | The main lessons, taken from the ICR are:(a) Sustained engagement in a sector, over a period of time, is necessary inorder to generate a momentum for reform and to maintain commitment to the reform process. In the case of the Kyrgyz Republic, themain impetus to reform the energy sector arose out of an anticipated supply crisis in the winter season 2014-15. The lessening ofthis urgency after the heating season, combined with a change in government, led to a backtracking of earlier-agreed reforms inpolitically sensitive residential sector, for fear of an anticipated public backlash. By shifting the burden on commercial andindustrial consumers allowed the targets in the results indicators nominally to be met, the failure to address the issue ofbelow-cost recovery tariffs for a household sector that accounted for more than half of total electricity consumption could onlyundermine the sustainability of the sector over the medium term.(b) Communication about the facts of the sector andoutreach to the general public can play a vital role in explaining and expanding the publics understanding of the need forreform. The communication campaign launched by the Government under the project in regards to the energy sector led to someincrease in public awareness about the reforms, though public interest in the topic waned somewhat after the critical winter seasonof 2014-15. However, had a strategy of pubic outreach been launched well prior to the project, it may have been useful in promotinga greater understanding of the precarious nature of the energy sectors finances and the need for tariff increases all round,to achieve cost recovery.
P152441 | Georgia National Innovation Ecosystem (GENIE) Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099031324183549071/text/P15244112932060bc1bfef13dfd1240d067.txt | http://documents.worldbank.org/curated/en/099031324183549071/pdf/P15244112932060bc1bfef13dfd1240d067.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. For newly established implementing agencies working in the innovation sphere, where substantialcapacity building is required, obtaining complementary technical assistance and advisory services from development partners can betransformative in building such capacities. During project preparation, the Bank identified the Georgian Innovation andTechnology Agencys limited institutional capacity as a potential implementation risk. Recognizing the Georgian Innovation andTechnology Agencys (GITA) capacity constraints, the European Union (EU) agreed to fund a technical assistance project that wasdirectly linked to the objectives of this project. This complementary intervention facilitated the delivery of an intensive andfocused program of technical assistance, advisory, and training services to GITA. This boost in technical assistance contributed tothe turnaround in project implementation.2. Embedding pilots for new types of interventions in project design canhelp project implementation. The lesson from this project is that innovation interventions that might be new to thecountry could be initiated at a small scale and tested with rigorous pilots and impact evaluation. Gradual building up would allowfor capacity building tailored to the needs of the country.3. Acceleration and business development services cancomplement innovation financing programs. This project showed that the strong performance of firms that received grantsthrough the project-supported program (notably mobilization of US$105.00 million in private capital) was largely due tothe business development support the firms received through the grant-winner training programs.
P152625 | Social Health Insurance Project: Improving Access, Quality, Efficiency and Financial Protection | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2016 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099110723211519273/text/P152625017a8140620978e0a5d4b4b1a052.txt | http://documents.worldbank.org/curated/en/099110723211519273/pdf/P152625017a8140620978e0a5d4b4b1a052.pdf | The ICR (pp. 33-35) provided a large number of insightful observations, lessons, and recommendations,including:Bank support for the strengthening of key institutions can help shape government policy decisions onhealth sector reform. In this case, project activities related to the MSHI were instrumental for SHIF to build capacityand to manage funds, which informed the governments decisions on reforming the purchasing of healthservices.Projects focusing on sectoral reform, particularly if that reform is politically challenging,maybenefit from use of the Program for Results (PforR) instrument. In this case, a PforR may have more efficientlyincentivized the Ministry of Finance to push for health financing reforms.In situations where fundamental changein policies and processes is being supported, analysis and reports developed within the scope of a project will be useful andsustainable only if they are accompanied by close implementation support and actionable tools. Without a real-lifeperspective, deliverables can lose their relevance and importance over time.IEG adds one additionallesson:Interventions intended to protect people and households from catastrophic medical expenses are mosteffective if they contain elements specifically targeted to groups most likely to experience such expenses, and/or to thepoor. In this case, broader reforms of health care financing, in the absence of such targeting, did not produce results inprotecting the most vulnerable.
P152646 | Emergency Primary Healthcare Restoration Project | Middle East and North Africa | Lebanon | IBRD | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/222671623849017380/text/Lebanon-Emergency-Primary-Healthcare-Restoration.txt | http://documents.worldbank.org/curated/en/222671623849017380/pdf/Lebanon-Emergency-Primary-Healthcare-Restoration.pdf | The first two lessonspresented here aredrawn from the ICR, pp. 32-33, and restated by IEG. The other two emergedfrom the information in the ICR. In emergency situations, temporary support to meet essential health needsthrough integrated, pro-poor interventions can mitigate the potential for social instability. Improving access for a hostpopulation by increasing the supply of services and reducing their cost to achieve a better situation than before the refugeesarrived can decrease grievances against the refugees, reduce problems with social cohesion, and increase trust in the government.This impact is enhanced if the program improves government accountability and citizenengagement, in addition to the primarybenefits of improving health care andhealth outcomes and reducing out-of-pocket burdens, as in thisproject. Building on existing initiatives and delivery mechanisms can facilitate quick preparation andimplementation. Reliance on existing programs, structures, and tested implementation approaches can helpfacilitaterapid and effective disbursement and response to a crisis. The MOPH built on its experience in contracting with PHCCs and improvedthe contract specifications, monitoring, and verification under the project. The project used the existing MOSA mechanism foridentifying the poor, and worked with the MOSA to rapidly develop a supplementary list of eligible potential beneficiaries when theexisting list was found to be incomplete and to contain inaccuracies. Early meaningfulengagement with beneficiaries can provide important input into the design of a package of essential health care services.Engagement with beneficiaries can help ensure that a limited package of essential health care services does not haveimportant omissions that undermine its efficacy and make it unresponsive to the health needs of the target population. Althoughthis early engagement did not happen in the project, beneficiary engagement during the project provided this important input forthe design of care packages in the successor project. Outreach and communication activities are important tostimulate demand when trying to shift health care seeking behavior to include more prevention. The need for and value ofpreventive services (like screening for hypertension, diabetes, and cancers) may not be evident to the intended beneficiaries, soeducation and skillful social marketing can increase uptake. The successor project has given more emphasis to outreach,communication, and explanation of the value and benefits of prevention.
P152653 | Regional Sustainable Energy Industry Development Project | East Asia and Pacific | Pacific Islands |  |  | Infrastructure | Energy & Extractives | RETF | IPF | 2016 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099032724145016546/text/P1526531bcb3780c0199a1126c64f548943.txt | http://documents.worldbank.org/curated/en/099032724145016546/pdf/P1526531bcb3780c0199a1126c64f548943.pdf | The ICR included three lessons which are emphasized below with some adaptation of language:1. If regionaltechnical assistance projects are well-designed andsupported by adequate follow-on support to embed and enhance the progressin utility capacity building, it is likely thatutility capacity will be enhanced in a cost-effective way. Theproject succeeded in enhancing capacity of some utilities, informing the design of donor-funded projects, and leveraging follow-onsupport. Despite limited funding, ambitious objectives, inadequate indicator target values, and implementation challenges,SEIDP-funded trainings and data collection activities showed that a regional approach saves costs compared to individual countytraining programs, fosters peer learning (through sharing of challenges and implemented solutions), and can yield positiveoutcomes.Key SEIDP success factors included the selection of a trusted regional champion as an implementing agency,identification of relevant trainings based on good assessment of utility capacity building needs, selection of a dedicatedpartner organization with strong links to the RE industry, andinclusion of utility performance benchmarking which driveshealthy competition that leads to tangible improvements.2. If adifferentiated approach that addressesvarious capacity baseline levels is adopted, it is likely that impacts of capacity building activities within a regional projectwill be maximized. The efficacy assessment of the SEIDP highlighted outcomes mostly from relatively high to medium sizepower utilities, while fewersubstantial outcomes emerged from small utilities. These small power utilities have weakercapacity than the medium to high size ones, as some of them do not even have an electrical engineer.To address thedifferentiated capacity baseline levels,additional one-on-one follow-on assistance in some areas such as DigSilent PowerFactory training, energy resilience enhancement tools training, and benchmarking reporting could be provided. The World Bank plansto help remedy this by providing Bank-executed assistance that targets small utilities.3. If additionalprovisions to ensure adoptionby sector ministries and policy makers are in place, it is likely thatchanges in countrypolicies will be institutionalized. Power utilitiesoften do not have the mandate to develop and enforce countrypolicies and regulations, so reaching out to critical policy makers and regulators is key to institutionalize orsustainoutputs from regional technical assistance activities. Development agencies are encouraged to include support,collaboration, or other mechanisms to facilitate adoption and/or enforcement of project outputs by government officials. In thecontext of this project, greater impacts could be achieved if some of the outputssuch as technical guidelines/grid codes,solar and wind resource data, recommendations from VRE assessmentare adopted and enforced/promoted by Pacific IslandsCountry ministries in charge of the energy sector, as in the case of Vanuatu, where the technical guidelines were adopted andenforced by the Government, not the utilities.
P152659 | Gambia Electricity Support Project | Western and Central Africa | Gambia, The | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/591861614787529923/text/Gambia-The-Gambia-Electricity-Support-Project.txt | http://documents.worldbank.org/curated/en/591861614787529923/pdf/Gambia-The-Gambia-Electricity-Support-Project.pdf | The ICR identified several lessons and recommendations arising from the experience of project implementation, and themostsalient lessons are paraphrased below:(i)Simplicity inproject design and flexibility inimplementationarenecessary to operate effectively in an FCV context. The PDO and the projectcomponentswere simple, and this enabled the Bank team and the Borrowertointegrate emergencydevelopments in thesectorand in the country context,and tobuild better the needed trust and capacity to pave the way for morecomplexoperationsand reforms in the future.(ii) Effectiveness in an FCV contextrequires significantresources and dedication from theBanks and Borrowers teams.Exceptionally,the Banks team was dedicated to this operation, as there was limited rotation of TTLs despite theFCV context throughout the four-year period of project implementation. Two senior staff shepherded successively the designandimplementation of the project from the outset until its closure,including increasedbudget resources forintensive supervision. Their dedication enabled sustained support to the capacity building and advice to the implementing agencies,which contributedsignificantly to achieved outcomes.(iii) In an FCV context, the Banks teamneeds to earmark enough resourcestoensure compliance with keyaspects ofproject implementation (procurementand ES safeguards notably). In the context of this project,technical capacity in the areas of procurementand ESwas generally weak, and implementation could not proceed if these aspects were not handledcorrectly.Procurement involved complex procedures and contracts and ES safeguards had to deal with sludgemanagementissues andhaving in place afunctional grievance redress mechanism. The above tasks wereaddressedthrough sustained capacity building and training, and the hiring of adequate internationalexpertise.
P152693 | Results-based Scaling Up Rural Sanitation and Water Supply Program | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | PforR | 2016 | 2024 | 2025 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099080224110051326/text/P152693-c9eee273-a76d-4fc5-9f31-a50223b46500.txt | https://documents.worldbank.org/curated/en/099080224110051326/pdf/P152693-c9eee273-a76d-4fc5-9f31-a50223b46500.pdf | The ICR (paras. 93 to 97) lists a number of lessons from which IEG derives the following lessons that are relevantforsimilar projects implemented in comparable environments:1. Alignment with existing government strategies andwell-organized implementation arrangements can make it easier to achieve strong governmental ownership of a Program:The Program had many cross-sectoral implementation arrangements and ownership at both central (e.g. MARD, NCERWASS,MoH-VIHEMA AND CEMA) and provincial/commune levels (PPC and commune representatives), which allowed good practices from the Programto be scaled up by GoV. Examples include the BCC approach, which was applied nationwide since 2019, with the goal ofdeveloping BCC plans in all communes and provinces of the country: to date, some 50 provinces had developed and approved such aplan. Looking ahead, the country could well benefit from the integration of the lessons from the Program, such as theimportance of including sustainability criteria in development and operation of water schemes, and the demonstrated effect ofinter-sectoral collaboration between different implementing agencies.This lesson is consistent with the key lessonemerging from the Project Performance Assessment Report (PPAR) for a similar Results-Based Rural Water Supply and SanitationProgram (P127435).2. Developing standardized and adaptable training modules for clients on the PforRmechanism could be useful for future operations: The provincial agencies reported difficulties they encountered inthe early years of the Program in understanding the PforR mechanism. For the success of the Program, it was important foractors at the province, district and commune levels to understand the mechanism fully. This problem has also proved relevantfor other PforR operations. Though the detailed mechanism would be context-specific, the lesson is that the World Bank needs todevelop a common set of training materials and modules for government counterparts, which could be tailored to country and projectcontext.3. While the PforR can be an effective mechanism, compatibility with the clientsinternal budget allocation and financing procedures needs to be carefully analyzed during the design stage: ThePrograms requirements turned out to be not fully compatible with the GoVs annual budget allocation process, especiallyat the provincial level. The PforRs requirements, such as the prefinancing of investments and counterpart fundsallocation, proved to be challenging as GoVs budget allocation was not results-based, and led to a delay in Programimplementation during the initial two years. A key lesson is that for the World Bank, future projects should analyze thecompatibility between the PforR approach and government procedures to set agreed guidelines in the Financing Agreement and ProgramAction Plan.
P152736 | Strengthening Primary Health Care for Results | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | PforR | 2015 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099000105252237232/text/P1527360e9e55a0f90921c02db0a96f912b.txt | http://documents.worldbank.org/curated/en/099000105252237232/pdf/P1527360e9e55a0f90921c02db0a96f912b.pdf | The ICR (pp. 31-33) offered several lessons and recommendations, and the following lessons were partially re-stated by IEGReview:The PforR operation fostered an increased focus on results and coordination between governmentagencies and development partners. The operation motivated stakeholders to focus on resultsand facilitated thecoordination of donor assistance through its results-oriented framework.There are tradeoffs between aprograms scope and its sustainability. The demands imposed on the system by an ambitious Star Rating accreditationinitiative in terms of technical capacity and financial resources proved to be difficult to achieve and sustain, indicating that aless resource-intensive approach may be more appropriate in the future.Nutrition support can be effectivelyintegrated into broader maternal and child health care development efforts. In the past, support tonutritionservices in Tanzania tended to be compartmentalized. Under the PforR operation, the nutrition agenda benefited from (i) astrengthened primary health care system that is essential for the delivery of nutrition interventions; and from (ii) improvementsin maternal and child care that synergistically contribute to progress in the nutrition agenda.Financialsustainability of results-based financing is vulnerable to changes in government commitment to the payment of financial incentivesto health workers. The lack of reliable financial flows to RBF, exacerbated by the turnover of senior governmentofficials, slowed down Program implementation during the last years of the operation and negatively impacted Program sustainabilityand the trust of stakeholders who were previously motivated by noteworthy RBF results that were observed during the preceding yearsof the Program.
P152799 | Health System Strengthening and Support Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR (p. 26) offered several lessons and recommendations, including the following lessons, restated by IEGReview:Abottom-up approach to project design enhances ownership, but it may also lead to fragmentation ofproject activities and responsibilities. Under this project, various MOH Directorates submitted more than 50 sub-projectproposals at the design stage, resulting in a degree of fragmentation. The lesson was supplemented by a recommendation noting thata unifying framework with strong justifications for activities can ensure full coherence and complementarity of design under futuresimilar operations.The ability to mount an effective response to unforeseen emergencies is facilitated by theflexibility of the project and the adaptability of its management. This was demonstrated by the projects ability toquickly reallocate resources, adjust priorities, and launch new interventions in response to the COVID-19 pandemic and theearthquake.Continuity of health care and resilience to emergencies are facilitated by a strong focus on primaryhealth care. Under the project, a patient-centered primary health care was instrumental for delivering responses toCOVID-19 and earthquake emergencies and for restoring access to essential services while concurrently contributing to theresilience of the health system.
P152810 | Tanzania Education and Skills for Productive Jobs Program (ESPJ) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | PforR | 2016 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099020124130517937/text/P1528101ab304f0231b87713d8638cf253a.txt | http://documents.worldbank.org/curated/en/099020124130517937/pdf/P1528101ab304f0231b87713d8638cf253a.pdf | An effective results-based program design will consider the trade-offs betweena holistic strategy anda partial andmeasured approach. This is particularly important for those new programs that intend to promote major reforms that are launched ina low-capacity environment.In this case, the program supported essentially the whole NSDS, which implied the engagement ofmultiple sectors and stakeholders.Although the DLIs provided incentives for the reforms, they were not sufficient.Forexample, the creation of the NSC was accompanied by a specific DLI, but the political context did not facilitate the intendedreform actions. In addition, the responsible institution for its design and implementation, the Prime Ministers office, wasnot a recipient of funds under the program. In the case of the Fit for Business seal of approval, one of the areas that wassupported by the program, there was no DLI, and no achievement thereof.The assessment of institutional capacity toimplement a results-based program can contributein the design process to determiningwhether a robust technicalassistance component is needed.In the context of this program, implementation capacity was limited, such that financialincentives were not sufficient to achieve the ambitious objectives set out in the program design. The ICR describes severalexamples where entities had difficulty understanding the program design and implementation procedures. In addition, monitoring andevaluation systems needed to be fully developed from scratch, while implementing agencies lacked the appropriate skills for thisendeavor. Collaboration between public and private institutions is particularly important in the TVETsector.Industry has a role in defining the skills needed, designing the curricula, and validating programs, as well as inoffering training. The public sector needs to regulate, oversee implementation, and provide financial incentives to ensure thatpoor youth benefit from training programs.The efficient implementation of these roles and responsibilities needs to becarried out in an environment that allows for dialogue and collaboration.
P152821 | AFR RI-GLR: Displaced Persons & Border Communities | Other | Africa |  |  | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2016 | 2019 | 2020 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/496861593036672417/text/Africa-GLR-Displaced-Persons-and-Border-Comm.txt | http://documents.worldbank.org/curated/en/496861593036672417/pdf/Africa-GLR-Displaced-Persons-and-Border-Comm.pdf | The following two lessons were extracted from the ICR: Institutional rigidity and internaladministrative objectives can be harmful to implementing regional projects. For example, to havethis projectapproved it needed to go through several administrative processes and waivers to avoid having a stand-alone project. When theparent project was closed, theassociated IDA grant was prematurely closed. Throughout the application process, agileprinciples were not applied (ICR, para. 77) Political EconomyAnalysisis necessary to understand client countries and mitigate risks. For example, forced displacement isinherently a political issue. Prior to beginning a project, the World Bank would do well to assess and fully understandpolitical actors motivations and interests. When it came to the parent project for this operation both Zambia andTanzania withdrew due to changes in the political alignments of their newly elected governments. A strong politicaleconomy analysis could have signaled the different priorities of political parties, and provided the World Bank an opportunity toaddress all actors interests in the projects design. The following lesson was extracted byIEG: Regional forums are able to bring together key stakeholders to discuss politicallysensitive topics. For example, while the project was only able to implement one workshop of stakeholders, preliminary dataindicate that there was some use and uptake of information shared at the workshops. Furthermore, therehas always beenaregional commitment to discuss and share emerging best practices among neighboring countries in the Great Lakesregion.
P152822 | Development Response to Displacement Impacts Project in the HoA | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following lessons were derived from the ICR (based on ICR, pages 18-19):1. While addressing forceddisplacement is most effectively done at the local and community levels, consolidating enabling policy and institutional reforms atthe regional level creates essential synergy and enables action on the ground. Through regional policy engagement, peerlearning, and a common approach, the Project offered participating countries greater opportunities to take concrete actions. TheProject established the HoAs Regional Secretariat on Forced Displacement and Mixed Migration (RSFDMM), under theIntergovernmental Authority on Development (IGAD), to facilitate cross-country approach and knowledge. This supported thedesign of progressive policies by the IGAD-led Nairobi Process (a series of initiatives to address forced displacement,treating it as a development challenge rather than a humanitarian crisis), which provided a platform for discussing previouslymuted sensitive issues, setting goals, and defining monitoring processes, thus enabling action. Additionally, IGAD-coordinatedresearch and learning enabled countries to share experiences and inspire each other.2. An integrated approach toservice delivery in both host and refugee communities builds a critical social foundation for addressing forced displacement.Initially, the Project focused on host communities, based on the understanding that they were underserved, while refugeesettlements received international assistance for basic services. However, an analysis of legal and policy framework for refugeeintegration, conducted during the additional financing for Uganda (April 2019), revealed challenges refugees faced in securinglivelihoods and accessing social services, including limited land access and employment opportunities, and language barriers.(Source: AF Restructuring Paper, page 26). Building on this assessment and leveraging the positive attitudes in theProject-supported host communities towards including refugees as beneficiaries, the Project introduced an integrated approach topromote long-term refugee inclusion and host-refugee coherence.3. Community procurement enhances speed and costeffectiveness. During Project implementation, procurement for subprojects in Ethiopia and Uganda was managed bycommunities as part of the CDD approach, in line with World Banks procurement guidelines. Community procurement proved to befaster, more cost effective and, according to multiple stakeholders, less susceptible to elite capture compared to standard publicprocurement methods. It was widely regarded as a key element of the Projects success. In Uganda, strong and consistentpositive feedback was received at the subnational level from District Chairs and Chief Administrative Officers. Incorporatingcommunity procurement into country systems would further support this approach in the future.
P152860 | Yunnan Early Childhood Education Innovation Project (YECEIP) | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099320009272220766/text/P15286005da6b103c09dde02a8b8286d757.txt | http://documents.worldbank.org/curated/en/099320009272220766/pdf/P15286005da6b103c09dde02a8b8286d757.pdf | The ICR (pp. 32-33) includes several well developed lessons, including: Keeping institutionalarrangements simple, in a complex project, can help implementation. In this case, even though there were multiple ProjectImplementation Units (seven at the county level, and three at the university level), their standardized structure and coordinationby an experiencedProvincial Project Management Office facilitated smooth operations. The participation andexpertise of relevant universities can build capacity to support early childhood education outcomes. In this case, theinclusion of three key universities in the ECE field helped maintain and increase the supply of ECE teachers, establish modelkindergartens that served as exemplars and laboratories for innovation, and developimportant analytical and diagnostictools. Community engagement is central to development of effective andinclusiveECE in ruralsettings.In this case, staffing of rural ECE centers placed priority on village-based candidates with strong ties tothe community, increasing teacher retention and supporting engagement with local communities and parents. Non-governmentalorganizations provided systematic professional development programs to ensure adequate staff competencies.
P152881 | KOSOVO: COMPETITIVENESS AND EXPORT READINESS PROJECT | Europe and Central Asia | Kosovo | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2024 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062724105078714/text/P152881-48bab262-48fb-4375-90c0-1c656fc78e9a.txt | https://documents.worldbank.org/curated/en/099062724105078714/pdf/P152881-48bab262-48fb-4375-90c0-1c656fc78e9a.pdf | Three lessons are drawn from the ICR, with some adaptation.Because enactment of laws by legislative bodies is acomplex process over which implementing agencies have little control, the Bank may alternatively consider treating legislation as aprior actionin a development policy operation or embedding it in a programmatic investment project financingoperation. In this operation, the passage of the new Law on Inspections tookfour years to accomplishfromproject approval in 2017, with the enactment ofLaw No. 08/L-067 in 2021. The Law on Inspections was necessary to reformthe regulatory frameworkfor business inspections, establish the Office of Inspector General, and enable the adoption ofmodern inspectionmethods including risk-based inspections. The delayed passage of the legislation left little time toaccomplish some operationalmeasures to implement reforms, including purchasing an e-inspection system, which also ran intoprocurement problems. Linking legislative reforms to prior actions under complementary development policy operations may helpaddress political challenges.Micro, small, and medium enterprises could benefit from more flexible matching grantterms at a time of economic crisis. In this operation, the Bank and the Government liberalized the conditions forthe extension of matching grants to MSMEs in response to the pandemic to include a reduction in the contribution of beneficiariesfrom 40 percent to 10 percent of total certification costs, the treatment of equipment purchases as an eligible expenditure, andthe differential in the contributions by MSMEs to capital expenditures from 50 percent for medium sized enterprises to30percent for micro and small enterprises. These innovations enabled the beneficiary firms to expand their productofferings, improve their product quality, and obtain product certifications even at a time of economic distress. Meanwhile,incentives for women-owned and women-managed firms yielded positive outcomes including in less developed regions. Theoutsourcing of the operation of the matching grants program to a private provider facilitated the implementation and thetransparent management of the support scheme but may have come at the cost of neglectingto fosterinstitutional capacitybuilding at a competing government agency.Although comparisons between treatment and control groups representthegold standard for impact evaluations, projects must recognize the limitations of these methods. In thesecond round of the matching grants program supported by this operation, not enough time had lapsed between thetreatment (theextension of matching grants to MSMEs) and the effect (a rise in exports by matching grant recipients, relative to the controlgroup). The sample size was also small and data availability was a constraint. The ICR suggests using intermediateindicators, including trade exhibitions in foreign markets, commercial contacts with new buyers, and signed export contracts, butthe use ofthese proxies would fail to measure the intended effect of the intervention. The method could still be used,however, but at a time after project closing when the interventions would have had sufficienttime to claim results.
P152898 | Emergency Education System Stabilization | Middle East and North Africa | Lebanon | IBRD | FCS | Human Development | Education | RETF | IPF | 2015 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/252041574177978100/text/Lebanon-Emergency-Education-System-Stabilization.txt | http://documents.worldbank.org/curated/en/252041574177978100/pdf/Lebanon-Emergency-Education-System-Stabilization.pdf | Lessons drawn from the ICR (pages 31-32), adapted by IEG: In an emergency education system stabilizationoperation, flexibility coupled with intensive supervision support by the Bankcan help ensure project effectiveness.Inthe case of this project, timely restructuring, reallocation of project funds, and the use of direct payment mechanisms wereexamples of flexible and timely Bank responses to implementation bottlenecks. Even in an emergency situation that demandsimmediate and short-term support, the Bank can provide additional value through analytic work and research to support longer-termoutcomes. In the case of this project, the Research for Results (R4R) program was linked to the project to generate evidence on theeducation sector, and the projects analytic work helped inform institutional strengtheningactivities.
P152903 | DRC Reinsertion and Reintegration Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/181861618233967849/text/Congo-Democratic-Republic-of-Reinsertion-and-Reintegration-Project.txt | http://documents.worldbank.org/curated/en/181861618233967849/pdf/Congo-Democratic-Republic-of-Reinsertion-and-Reintegration-Project.pdf | The ICR provides excellent lessons, reflective of both successes and difficulties of theproject. Principal among these are: Eligibility criteria for participation in DDR projectsmust account for local realities and communities to ensure broad engagement. The project design clearly took acomprehensive view of the communities of people it needed to support in order for reinsertion and reintegration to be successful.It also notes though, that eligibility criteria should have been less specifically tied to e.g. weapons, because that meant veryfew women (who did not often have weapons) approached the project (ICR para 71). Broader criteria could have allowed broaderparticipation. For DDR programs to be effective in reducing armed violence, they must be must be linked tobroader social and economic reforms. Without explicit alignment with broader social, justice and economicdevelopment strategies, including regional and cross-border strategies, DDR programs alone cannot sustain reductions in armedviolence. This project exemplified third generation DDR approaches (ICR para 71) and was aligned with these broadergovernment and partner strategies. DDR programs are contingent on partnerships, which need to formalizedthrough clear agreements on divisions of responsibilities. Explicit expressions of responsibilities between partnerorganizations at project outset would have helped manage both coordination and political challenges that arose when MONUSCOwithdrew its support of the program and possibly avoided early project closure. Politically sensitive DDRprograms often require more time and a combination of analytical, technical and political skills than the Banks businessmodel allows. At the internal Bank project management level, the complexity of DDR programs often requires full timeattention to manage sensitivities and many moving parts but project managers are regularly expected to be managing multipleprojects. This raises the likelihood of often significant safety or security risks manifesting, as well as operational andreputational risks. At the broader political level, the ICR suggests that quicker and higher-level political engagement by the Bankcould have changed the trajectory of the project away from early closure. Additional lesson fromIEG The viability of economic reintegration activities is contingent on favorable local economic andsecurity conditions. The Borrowers Comments (ICR Annex 5) highlight that the violence and permanent insecurity inthe regions where the CPRs were located; large regularly moving populations; and very limited economic opportunity for both XCs andlocal communities made the economic integration aims of the project essentially unviable. While the PAD assesses macroeconomicrisk as moderate, despite clear recognition of the volatile security situation, it does not address in detail the viability ofthe local economic activities and targets in relation tothis known context. Consequently, the preparation offered by theproject for developing economic opportunities was not able to be widely applied and targets fell farshort.
P152910 | Congo - Education Sector Support Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Human Development | Education | IDA | IPF | 2016 | 2023 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099080824095540987/text/P152910-4fa7c8b0-251f-4935-8fa7-36b35311fa30.txt | https://documents.worldbank.org/curated/en/099080824095540987/pdf/P152910-4fa7c8b0-251f-4935-8fa7-36b35311fa30.pdf | The ICR (pp. 31-32) provided insightful lessons, some of which are restated below.Teacher buy-in on curricularreforms is essential to ensure successful implementation.Teacher training under the project demonstrated that thenewcurriculum would require a shorter time to prepare classes and would allow for greater student participation in class. Teacherswelcomed these changes, particularly because of the greater student participation and interaction. The ICR recognized that theprocess was still in its initial stages, and that further training was planned under the new TRESOR project by expanding on contentknowledge and pedagogical practices.Continuous capacity assessment is necessary to ensure satisfactoryimplementation. At appraisal, implementation capacity risk was correctly assessed as Substantial due to thecountrys historically weak implementation capacity and persistent challenges in the use of country systems.Fiduciarymissions were carried out systematically;however, towards the end of the project implementation period, both procurement andfinancial management ratings weredowngraded to Moderately Unsatisfactorybecause of deficient financial management andprocurement processes detected as a result of in-depth reviews.Good quality data is essential for projectpreparation, monitoring, and evaluation. The PAD rated the technical design risk of the project as Substantialmainly because of the lack of reliable data on the school-age population as well as onteachers working in the system eitheras civil servants or bnvoles.Consequently, the project included activities that intended to createan EMIS and a personnel management system, thus addressing both these challenges.At closing, some progress had been achievedon both counts, but further work was needed to fully implement both systems.
P152932 | Public Financial Management Enhancement Project | Eastern and Southern Africa | Zimbabwe | Blend | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2016 | 2021 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Highly Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099955010202235258/text/P1529320f78e0b0170a205056d7423dd063.txt | http://documents.worldbank.org/curated/en/099955010202235258/pdf/P1529320f78e0b0170a205056d7423dd063.pdf | Lessons identified in the ICR are helpful, such as (i) the need for the Bank to be more realistic in assessing capacityconstraints -recognizing that addressing capacity issues during implementation may delay project implementation (141) - and to bemore realistic in assessing initial ownership to ensure that reforms are indeed not only feasible but also doable given theparticular country context(144), (ii) In addition to one-off training, its important to implement a series of actions(training champions to roll the training over, conducting refresher training, impact assessment at the end of the year to check ifthe knowledge acquired was being applied, leveraging peer learning, and study tours) to ensure the sustainability of reformprocess. (146); (iii) the need to correctly time PFM reforms (147); and (iv) obtain assurances of financing from theauthorities before proceeding with the design of the project.
P152936 | National Electrification Project | East Asia and Pacific | Myanmar | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2016 | 2022 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099100623155540300/text/P15293605ec1d407809cf7087f87de2d8f4.txt | http://documents.worldbank.org/curated/en/099100623155540300/pdf/P15293605ec1d407809cf7087f87de2d8f4.pdf | The projects implementation experience generated several lessons, which are summarized below:The IDAImmediate Response Mechanism (IRM) deployment required capacity building for the government and task team, and IRM proceduresshould be improved for future projects. The GoM and task teams needed training and preparation support for IRM activationand implementation, especially in procurement, safeguards, and fiduciary matters. World Bank procedures limited the IRM to aspecific disaster, thus hindering its use for broader disaster prevention and preparedness. In fragile contexts like Myanmar, IDAshould consider project-specific Crisis and Emergency Risk Communication (CERC). Improving the procedures would enable moreflexible deployment of IRMs for enhanced disaster prevention and preparedness.Making grid connection fees andinternal wiring more affordable increased the adoption of grid connection. Households and Village ElectrificationCommittee (VECs) bear the costs of low-voltage infrastructure and household connections. With IDA support, alleviating some of theburden on VECs to secure their own financing could expand the main grids reach into lower-income communities. Connection costsremained a significant barrier for low-income households even in electrified villages. Establishing mechanisms to support internalwiring and finance connection costs over time (e.g., grid connection subsidy) accelerated the adoption of main grid electricity bylower-income households and SMEs.To ensure successful mini grid development at scale, a holistic approach iscrucial, including a suitable business model, enabling environment, planning, finance, Productive Use of Energy (PUE), andgovernment and developer capacity building. Under NEP, the private sector selected sites for development, which provedattractive for private sector mini grid developers. The project focused on creating an enabling environment and regulatoryframework to attract private investors. It emphasized the importance of productive uses of electricity for mini grid economicviability. Future mini grid programs should explicitly support enabling environments and promote financial viability.Moreover, strengthening local manufacturing capacity for key materials in grid extension, such as electric poles and transformers,improved the sustainability of grid expansion and reduced costs. International consultants and workshops helped local manufacturerslearn global standards and efficient operation modalities.Combining public and private-led approaches involvinggrid, mini grid, and off-grid technologies can effectively accelerate energy access in fragile countries. Myanmarsexperience shows that a hybrid approach requires well-defined scope, close coordination between private and public entities, andcoordination between different technologies. Leveraging all three technologies and public sector-led approaches can target remote,less accessible unelectrified villages in border or fragile states and areas with high poverty incidence and low electrificationrates where the private sector is less interested. Collaboration among the World Bank, IFC, and MIGA enhances the success ofenergy projects. The Joint Implementation Plan facilitated comprehensive electricity tariff reform and private sector involvementin power generation. Sharing information and resources between the WB and IFC led to innovative off-grid solutions. MIGAs riskmitigation increased sector attractiveness to foreign investors, contributing to universal electricity access inMyanmar.Close partnership and coordination among donors under the NEP are critical for achieving scalableresults. Partners supporting energy access in Myanmar include the Asian Development Bank, Government of Italy, GIZ, KfW,AFD, JICA, and GEAPP. Design and implementation of future energy access projects should be coordinate among these partners. NEPplayed a pivotal role in supporting this coordination, despite and limited resources.More broadly, the project identifiedtechnical-level best practices and lessons learned that can benefit the design offuture energy access projects in Myanmar.These include early onboarding of an independent verification agent, designing calls for proposals to balance speed and localprivate sector growth, capacity building for participants and evaluators, updating tripartite agreements for effective governanceof mini grids, and improving modular mini grid designs. The testing of public and private sector approaches for off-grid solarrequired coordination, public-private partnerships, commitment to quality standards, and consideration of social inclusion aspects,which should be carried forwardinto future projects.
P153064 | Health Service Delivery & System Support Project | Western and Central Africa | Sierra Leone | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR (p. 32-34) included several lessons learned which were adapted by IEG: Political leadership,ownership and commitment can positively impact project implementation and sustainability. While the governmentsleadership and commitment were commendable during the Ebola outbreak, the flagship programs and key building blocks of the healthsector would have benefit from greater ownership. For example, the handover of the National Emergency Medical Services (NEMS) waschallenging due to a lack of government ownership and financing to sustain the NEMS. Technical support and closeengagement with the Ministry of Public Works to ensure quality, efficiency, and adequate project management facilitate theimplementation of health projects with large infrastructure components. In this project, the MOHS lacked capacity andexpertise to manage the construction of the Jojoima health facility and the Bank did not provide adequate supervision resulting inimplementation delays. Building ME capacity within the Project Implementation Units (PIUs), developing andoperationalizing an ME plan, defining clear lines of communication, roles, and responsibilities during project preparation canpositively impact the projects ability to measure results. In this project, the IHPAU did not have sufficientcapacity, and lackedcoordination resulting in poor data quality, inconsistencies, and challenges to monitor projectachievements.
P153084 | MG - Resilience DPO | Eastern and Southern Africa | Madagascar | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory |  | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/735711528388515356/text/Madagascar-MG-Resilience-DPO.txt | http://documents.worldbank.org/curated/en/735711528388515356/pdf/Madagascar-MG-Resilience-DPO.pdf | IEG draws the following two lessons: 1. IDA impact from stand-alone DPOs will benefit from consistency withlong term goals. In one area (JIRAMA, the power company), Madagascars first four DPOs, including that covered by thisreview, sequentially addressed various issues (control of leakages, statistics, procurement, and power generation contracts). Yetthe long term result sought (a well-managed company) remains elusive. A more integral approach would diagnose thevarious sources of losses and support those measures with significant loss reduction impacts. Timely parallel support throughInvestment Project Financing operations and Non-lending Technical Assistance remains critical, particularly in low capacitysettings. 2. A program that relies on multiple government agencies and stakeholders is likely to run higherrisks. This operation targeted actions by MFB, MCS, JIRAMA and three other agencies. As a result performance varied, with someagencies (e.g. MFB, the coordinating agency) achieving better results than others (e.g., MCS). Stronger leadership and incentives(e.g., providing budgetary compensation for undertaking costly reforms) may help address those risks.
P153085 | DRC - Goma Airport Safety Improvement Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099925010112228202/text/P153085088a7f90130813d0729b0dd7178a.txt | http://documents.worldbank.org/curated/en/099925010112228202/pdf/P153085088a7f90130813d0729b0dd7178a.pdf | The ICR draws the following main lessons from the experience of implementing this project, which are reported with someadaptation of language.1. A flexible design and contingency funds for unplanned activities can be useful forprojects in fragile and conflict affected environment. In this project, some activities (such as changing from a mobilecontrol tower to a permanent tower and drainage works from the airport to Lake Kivu) weremodified at government request. Theflexible design and contingency funds for unplanned activities enabled the project to adapt to the changing situation on theground.2.The project activities need to be aligned with the project development objective for properattribution of results. In this project, the key indicator - regulatory certification of the safety and security standardsof the airport - was unrealistic as none of the project activities supported the certificationprocess.3. A decentralized approach to project management can help in implementation on theground. In this project, relocating the Project Implementation Unit from Kinshasa to Goma allowed:(i) tosubstantially improve the implementation of the project; (ii) improve the dialogue between the local and the central governmentthat helped to incorporate inputs from the stakeholders; and (iii) secure acceptance of the project by the localcommunities.
P153115 | Hunan Integrated Management of Agricultural Land Pollution Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR extracted several lessons from implementing the project. Three that are likely to be widely applicable are presentedbelow with some edits:A risk-based approach, in which the remediation measures are targeted toaddress the nature of assessed risks, has the potential to be effective in controlling heavy metal pollution (ICR, para 96).The approach entailed conducting spatial mapping of sources (for example, mining, industries, and so on) and typesof heavy metals (for example, cadmium, arsenic, lead, and mercury); classifying the intensity of these heavy metals on farmland(for example, high, medium, and low risk based on safety thresholds); and implementing targeted remediation measures (for example,closing heavily polluting mines and industries, converting contaminated farmland into estates/industrial parks, and applyingfarmland passivation measuresadding chemicals, especially liming of polluted soilsto change heavy metals from activeforms to stable forms). The projects risk-based approach successfully mitigated heavy metal pollution in the soils of HunanProvince.Adopting a learning-based model of work that continually reworks the approach to reducing environmentaldamage based on observed outcomes, can potentially lead to the development of robust models for scaling up the approach (ICR, para99). This unique approach was a game changer in managing agriculture and the environment in this project. Through fiveyears of continuous implementation, exploration, summarizing, and synthesizing, the project established a comprehensive managementmodel for farmland heavy metal pollution mitigation.The science-enterprise-society technology modelof expert decision-making, enterprise support, and cooperative implementation with farming communities has the potential tomobilize grassroots enthusiasm and improve farmers participation in projects (ICR, para 100). Demonstrations ofimproved practices empowered rural communities. Participating counties were organized and guided by the project to conductexperiments on agronomic measures, rice varieties, and remediation products. The outreach to farmers and policymakers via shortdocumentary films and easily accessible rural websites catalyzed societys understanding of the critical challenges andopportunities to participate and contribute to finding solutions. The project built the capacity of local researchers, extensionworkers, and farmer cooperative representatives to develop and maintain early warning systems. The experiences of projectstakeholders are potentially useful for developing robust and effective decision-support tools that can be used even in areas thatlack research and extension expertise.
P153203 | BR Manaus Service Delivery and Fiscal Management DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2016 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/867711542810640371/text/BR-Manaus-Service-Delivery-and-Fiscal-Mgm-P153203-ICRR.txt | http://documents.worldbank.org/curated/en/867711542810640371/pdf/BR-Manaus-Service-Delivery-and-Fiscal-Mgm-P153203-ICRR.pdf | The ICR (pp. 31-32) presented a number of insightful lessons, including:Changemanagement processes require buy-in from both the leadership and technical staff of organizations centrallyinvolved. In this case, all key stakeholders were involved in the design of reforms, allowing buy-in and flexiblyshaping decisions to accommodate resistance.Reforms wereintroduced gradually and in a low-profile manner, withrewards for performance clearly and fairly explained, allowing managers to check progress, identify obstacles, and solveproblems.Leadership is key. In this case, senior municipal government officialsshowed strong leadership and engaged in continual communications within and acrossorganizations.The incorporation of management-for-results in schools can improve studentperformance. In this case, SEMED implemented an on-line monitoring system with clear, school-level targets andpathways for finding solutions when school-specific issues were identified. Management contracts, signed between the schooldirectors and SEMED, and based on school-specific indicators and bimonthly student assessments,enhanced monitoring andaccountability.
P153234 | Third Development Policy Operation | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The following lessons are taken from the ICR with some modification of language by IEG.A series of 4 DPOs can often beexcessive. Changing conditions could necessitate significant changes to the program, which complicates design, implementation andevaluation. In Armenia, by the time the fourth DPO commenced circumstances had changed substantially compared with the first DPO.Armenian authorities indicated that two DPO series that each had 2 programs could have improved performance.Excessively broad PDOs complicate design, greatly increase the difficulty of effective implementation, complicate monitoring andmakes effective evaluation highly problematic. In the case of Armenia, the numerous changes the failure to translate triggers in apreceding DPO into prior actions in subsequent DPOs complicated achieving the targets of the program.Pressuresto disperse can compromise the effective implementation of a programmatic series. Furthermore, it can also lead to shortcuts beingtaken to comply with prior actions. This results in less effective or delayed reforms. In the case of Armenia, the pressure todisperse resulted in a tax law that contains many weaknesses, and laws and regulations in the mining sector that were not fullyeffective.IEG adds the following lessons.Undertaking numerous changes to results indicatorsand modifying targets greatly complicates both program implementation and evaluation. In the case of Armenia, widespread changes inresults indicators made the effective monitoring and evaluation of the program extremely difficult.Whendesigning a Monitoring and Evaluation Framework, it is important to ensure that the indicators relate to outcomes and not toinputs. In the case of the Armenia DPO series, numerous indicators measured inputs.If a DPO series has an overarchingobjective, including indicators that provide information on whether it is being achieved strengthens the evaluation of its success.In the case of Armenia, job creation was the overarching objective, but there were no indicators containing employment data
P153243 | AO-Fiscal Management Programmatic DPL | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2015 | 2017 | 2019 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/278511549921690776/text/Angola-AO-Fiscal-Management-Programmatic-DPL.txt | http://documents.worldbank.org/curated/en/278511549921690776/pdf/Angola-AO-Fiscal-Management-Programmatic-DPL.pdf | The ICR (pp. 21-22) offered a number of general lessons and recommendations, although some of them pertaining topolitical commitment overlapped. The most important conclusions from the ICR were:Targets fordevelopment outcomes should not be overly optimistic, and the time frame for achieving results should be realistic. Manyparts of the program were based on the assumption that results that were unachievable, could be achieved. This arose from pressureto design a high-profile program that would garner strong international buy-in. The program did not sufficiently take into accountthe political and institutional realities in Angola.In a complex operation with multiple pillars,the project team needs to be satisfied that political support is strong and will be maintained through the life of the program.This manifested itself in insufficient resources being provided to fulfill many parts of the program, in particular thecash transfer program.In preparing and supervising a program such as this, strong buy-in andcommitment from counterpart agencies is essential. The commitment of the MoF was strong in the areas of its directinterest, such as the subsidy and tax portions. It was much less so in other areas.IEGaddstwo additional lessons. IEG evaluations have revealed that a common issuerelated to DPOs is the over-estimation of the capacity of counterparts to implement the program. Design should always take thisinto account. It is better to have relatively modest goals that can be achieved, rather than an overly ambitious programthat fails.At the first indication that Government commitment to the program appears to be waning,intensive consultations are necessary to decide on the programs future. The ICR noted that as the macroeconomicsituation deteriorated, and the Governments policy measures departed from World Bank recommendations, the intensity ofsupervision declined. IEG suggests that this should have triggered more intensive consultations and coordination with otherdevelopment partners in an attempteither toreverse unsuitable policies or cancel the operation at an earlier date.
P153251 | IN Swachh Bharat Mission Support Operation | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | PforR | 2016 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099091523140562778/text/P15325104d51050080b0620ff05fe21c20f.txt | http://documents.worldbank.org/curated/en/099091523140562778/pdf/P15325104d51050080b0620ff05fe21c20f.pdf | (Reference ICR paras. 76 to 80).The ICRlists a number of lessons from which IEG derives the followinglessons thatare relevant for similar projects carried out in comparable environments.Strong leadership and awhole-of-government approach may enablesuccessful programimplementation: Proactive political andadministrative leadership was a distinctive feature of SBM-G and were critical to align the country behind a common goal andsustain momentum for a large and complex program with ambitious and time-bound targets.Strong institutionalcapacity and systems at all levels may increase the potential for successful program delivery: The SBM-G experiencerevealed that while proactive central leadership was critical for implementation at scale, weak institutional capacity and systemsat the local level adversely impacted delivery of the facilities and services. Absence of robust data systems and MEcapabilities at the local level posed challenges to correctly identifying beneficiaries and setting targets at the start of theSBM-G Program. A lack of adequate integration of the PFMS across different levels of the government led to delays in allocation andtransfer of funds and delayed payments to the beneficiaries. Future national government programs need to carefully assess theinstitutional and system capacities at local levels prior to program implementation and take necessary measures to addressweaknesses.ODF sustainability requires sustained efforts to promote and maintain behavior change:Behavior change promotion was a significant aspect under the SBM-G. While arange of BCC interventions were deployed, thosefound to be led by communities or those that involved inter-personal communication such as door-to-door campaigns were found to bemost effective in mobilizing communities to construct and use toilets. However, behavior change is a long-term process and requiresa long-term strategy to ensure its sustainability. Without supportfrom the government, the burden of repairing andmaintaining toilets and sanitation facilities falls on households which can influence their behavioral patterns on usage.Appropriate policy and clarity in institutional responsibilitiesfor infrastructure upkeep areneeded. The SBM-Gmonitoring systems need to track toilet use and infrastructure quality in a reliable manner and on aregularbasis.
P153268 | Access to Sustainable Energy Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2016 | 2024 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062024184517145/text/P153268-a8141b2b-5e43-4743-877e-c1dcf485ccc2.txt | https://documents.worldbank.org/curated/en/099062024184517145/pdf/P153268-a8141b2b-5e43-4743-877e-c1dcf485ccc2.pdf | Simplification of project design based on past experience can lead to a more effective approach. According tothe project documents, simplification of project design is one of the important lessons to be learnt from the project. The effortsto mainstream photovoltaicwere further bolstered by an approved regulatory framework with a simple yet effectivedesignfixed monthly tariffs to customers, sustainable revenue flow to service providers for operational support and a designfocus on the provision of services which ranges from efficient appliances to radios and fanswhich is derived from globalexperience through the World Bank. Some of these elements of project design are visible in the ASEP project but they are componentspecific and does not necessarily diffuse into all areas of the project. As such, greater simplification of project design based onpast WBG experiences could be a very key asset for the project per se.Implementation of a fee-for-service deliverymodel for household solar systems can be critical in achieving off-grid electrification outcomes and ensuringsustainability. The successful demonstration of the fee-for-service delivery model by electric cooperatives showed thatthe sustainability of the solar home systems will be more likely compared to households covering the initial capital costand maintenance cost of the systems. The mainstreaming of the fee-for-service delivery model within Philippines is evidenced by theadoption of this model for the full off-grid electrification in remote areas by the host government. According to the ICR (page37), the model ensured strong ownership from the electric cooperatives, adequate subsidies and tariffs along with pre-installedPPMs to ensure periodic cash flow. It also incentivized the ECs to use SHS for their off-grid electrification projects withprovision of grants for initial capital costs and maintenance of SHS in key areas. These interventions helped to ensure successfulmainstreaming of the fee-for service delivery model.Insufficient assessment of legal frameworks can adverselyaffect the achievement of project results. The pre-paid metering component of the project was dropped due to regulatoryand ownership constraints. The possibility that the households could switch back to post-paid meters after a six-month trial of thepre-paid meters (allowed by law) was not identified at appraisal. The installation of the pre-paid meters was expected tocontribute to the financial viability of the electric cooperatives that would have expected to provide them funds to adequatelyoperate and maintain the on-grid and off-grid electricity infrastructure.
P153269 | Sustaining Reforms for Inclusive Growth | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/308981527259048992/text/Seychelles-Sustaining-Reforms-for-Inclusive-Growth.txt | http://documents.worldbank.org/curated/en/308981527259048992/pdf/Seychelles-Sustaining-Reforms-for-Inclusive-Growth.pdf | The ICR offers both operation-specific and general lessons. IEG adds the following: Theeffectiveness and sustainability of a reform program can be significantly affected by the electoral cycle, and it is important totake political events into consideration in both the design and the timing of the program. Especially in the context of politicaluncertainty, a careful political economy analysis, including in-depth consultations with the political opposition duringpreparation, can facilitate program implementation and sustainability. Clear explanations ofthe reasoning behind the choice of policy areas, prior actions and outcome targets can reinforce the internal logic and coherenceof the reform program supported by a DPO.
P153277 | TZ-Zanzibar Improving Student Prospects Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051724151027879/text/P153277141002b0ce18d011f2a0024e622a.txt | http://documents.worldbank.org/curated/en/099051724151027879/pdf/P153277141002b0ce18d011f2a0024e622a.pdf | The ICR (pp. 27-29) presents several important lessons, some of which are restated below:A clear PDO incombination with measurable and realistic indicators contributes tosuccessful achievement of project objectives.Thisproject had clear objectives, and indicators were defined at the correct outcome level.The projects design wasinformed by lessons learned from other education projects in the country and globally. A previous project in Zanzibar had faceddifficulties with respect to indicators that were difficult to measure or where attribution to the project was not clear. Theproject also focused on a segment of the education cycle and on specific areas (math, science, and English) therein.Thishelped simplifyproject design and aided in targeting of resources.Retraining teachers is a viable means toincrease the supply of teachers in subjects where there is a shortage.Thisproject supported the retraining ofarts and language teachers through a two-year program to increase the number of math and science teachers.This strategy ledto an improvement in the balance of teachers among subjects, resolving the oversupply of arts and language teachers and reducingthe shortage ofmath and science teachers.The impact at the fiscal level was limited to the increase in salary of MSEteachers, a smaller fiscal impact when compared to the alternative of mass recruitment of new teachers. In order to ensure thatthis process was successful, the retraining program was rigorous, and it was achieved through a pairing of international technicalassistance and local expertise of the State University of Zanzibars School of Education.The provision ofdirect financing to schools, through School Improvement Grants, contributes to increasing school autonomy and reducingparents out-of-pocket expenditures.Under thisproject, school grants covered expenses that parents wouldotherwise have had to pay.They also financed learning materials, textbooks, mock examinations, motivational activities forstudents, remedial lessons, female hygiene products for students, and sporting events.
P153338 | MX: Expanding Rural Finance | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2016 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/999331636394303629/text/Mexico-MX-Expanding-Rural-Finance.txt | http://documents.worldbank.org/curated/en/999331636394303629/pdf/Mexico-MX-Expanding-Rural-Finance.pdf | The first twolessons are drawn from the ICR (page 28), with some adaptation. The third lesson is added by this ICRReview.Partnering with an apexinstitution with a proven history, expertise, and knowledge of workingwithlending institutions in the ruralsector increasesthe probability of successfully expanding financing to ruralMSMEs. In this project, the FNDhad builta competitive advantage in rural finance with a broad network ofparticipating financial institutions, both regulated and unregulated by supervisors, that servedthe rural and agriculturalmarket. The participating financial institutions themselves were knowledgeable oftheir rural MSME clients, helpingreduce the transactions costs normally associated with asymmetric information in finance and with credit risk. Leveraging thestrengths of the FND for this operation servedto effectively expand productive lending to rural MSMEs in Mexico, both usingthe project funds and the FNDs own resources.A monitoring and evaluation design thatsystematically tracks classes of beneficiaries helps maintain a projects operationalfocus on target groups.In this project, the ME design called for periodically tracking the number and percentage of sub-loan beneficiariesby gender (women), location (marginalized areas), population group (indigenous peoples), and economic sector (first-time borrowersfrom formal financial institutions). According to the ICR, this monitoring design helped the FND and the participationfinancial institutions to maintain their focus on meeting lending targets for these groups of borrowers. The project exceededor nearly achievedall of the results targets for the percentage of women beneficiaries, the proportion of borrowers frommarginalized communities, and the percentage of first-time borrowers among the project beneficiaries.Requiring counterpart financing in a financial intermediary lending operation crowds in investment from the privatesector and strengthens the financial intermediaries commitment to project objectives. In this project,theFNDs credit policy which requiredthat a fraction of the sub-loan approved to a final borrower must befinanced by theparticipating financial institutionwith its own funds the average requirement was 20percent resulted in the participating financialinstitutions contributing around US$80 million of their ownresources to rural lending to match the US$318.8 million drawn from the Bank loan. In the second round of rural lending, theparticipating financial institutions contributed around US$63 million oftheir own resources to match the US$254 million lentby the FND from itsown resources (repayments from the credit lines extended by the FND to participating financialinstitutions). Altogether, some US$143 million of private sector investment was mobilized by the project.
P153370 | Second South West Indian Ocean Fisheries Governance and Shared Growth Project - Madagascar | Eastern and Southern Africa | Southern Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099090424065014009/text/P153370-7a7693e7-c505-4527-95dd-013e31b563c4.txt | https://documents.worldbank.org/curated/en/099090424065014009/pdf/P153370-7a7693e7-c505-4527-95dd-013e31b563c4.pdf | The ICR (p. 26) included several lessons learned which were adapted by IEG: Partnering with NGOs whichare locally engaged and experienced can support local government entities especially with limited implementing capacity.In his project, three international but locally invested NGOs worked with local communities to improve their capacity to organizeand co-manage. This allowed the regional branches of the fisheries department to focus on other activities that could not bedelegated such as enforcement and registrations. Failure to ensure long-term political commitment may jeaopardizethe achievement of sustainable outcomes. In this project, changing priorities of successive ministries and ministersnegatively impacted project implementation since complex fisheries reform processes require continued government commitment overtime. Performance-based financing instruments and sequencing of activities might help to secure long-term commitment by thegovernment. Fisheries reform processes can be lengthy and require continuous World Bank support. AMultiphase Programmatic Approach could help achieve such continuous support. Also, requiring critical readiness conditions, such asthe effectiveness of Monitoring, Control and Surveillance (MCS) or addressing the open access nature of the fisheries, and allowingsufficient time for countries to meet these conditions might positively impact the implementation and sustainability oftheproject.
P153420 | Climate Smart Agriculture Support Project | Western and Central Africa | Niger | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099083123203039124/text/P153420046c5ac0c20818f08a45f7fe6787.txt | http://documents.worldbank.org/curated/en/099083123203039124/pdf/P153420046c5ac0c20818f08a45f7fe6787.pdf | The ICR included four lessons. The following three are emphasized with some adaptation oflanguage:1.Acollaborative effort of relevantinstitutions can contribute to a successful climatechange adaptation program. In this case, the project drew on the skills of highly experienced institutions in criticalareas by entering into strategic partnerships with such institutions as AGRHYMET in areas of weather forecasting and climate changemitigation measures; INRAN and ICRISAT in promoting climate smart technologies, especially in restoring bio-degraded lands; FAO inpromoting agro-pastoral field schools; RECA on multi-modal information systems; and the Faculty of Agronomy of the University ofNiamey on bourgou production on saline soils. Such institutions need to be brought on board as early aspossible.2. To ensure a successful outcome for projects in fragile environments, several factors need toconsidered including:working with local stakeholders;harnessing digital technology; and intensifiedimplementationsupport.The project experience demonstrated thatit is vital to work with local stakeholders including localadministration and civil society in project implementation. Also,harnessing digital technology, including using GEMS and Kobotoolbox, facilitates real time monitoring, thus aiding in quick decision making in a rapidly changing environment. Finally,implementation support must be intensified including through a high degree of informality to facilitate rapid decisionmaking.3. Delivering agricultural input subsidies to the poor could be effectively achieved through an e-vouchersystem.The project helped with the successful establishment and operationalization of an e-voucher agriculturalinput subsidy platform. Its use demonstrated agility in facilitating the poors access to inputs while promoting the privatesectors growth in this domain. When such a program is acting as a replacement to a system of physical delivery of subsidizedinputs, institutional inertia and resistance from vested interests can be a significant challenge. A clear understanding of thepolitical economy surrounding prevailing input subsidy programs and enlisting the support of farmers organizations and otherchampions is critical in countering such resistance.
P153487 | Equal Access and Simplified Environment for Investment (EASE) in Egypt | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041823140023062/text/P1534870b9af2d0860a91e020e97f757e1e.txt | http://documents.worldbank.org/curated/en/099041823140023062/pdf/P1534870b9af2d0860a91e020e97f757e1e.pdf | The following are lessons learnt from the ICR (paragraph 82) with some paraphrasing: Projects even withsmall budgets can make a significant impact on improving government to business services through well designed digitalinvestments. The project delivered a new licensing services digital delivery model that is flexible for growth andcan be adopted as a model for effective digital services transformation. This way, the project contributed to simplifying one ofthe most complicated steps in starting up a business in Egypt, as well as created a large impact toward facilitating evidence-basedpolicymaking, transparent policy implementation and support Egyptian authorities for better decision-making. Success was achievedby making relevant agencies own these systems to guarantee the sustainability of project results. Donorcollaboration can help to create the momentum for reform. In the case of the project the donor coordination facilitatedthrough the Transition Fund where, the WB and the OECD were implementing partners worked in collaboration for the achievement of acombined PDO: To improve the regulatory environment for investors through simplified industrial licensing and transparentland allocation processes and to support the Government of Egypt in designing a new investment policy and legal framework, and instrengthening its international investment regime. Such collaboration provided a firmer, stronger support forthe realization of reforms in the country. Reform on land allocation can be performed moreeffectively via close cooperation among involved entities, clearly defined roles, and availability of established systems of landinformation and classification. Implementing land allocation reform in Egypt was particularly challenging as theresponsibilities of relevant institutions on land allocation were unclear in general and the authority for industrial lands wasdisbursed among several entities. This complex situation was resolved through the project support that achieved close coordinationamong entities with clearly defined roles and responsibilities and a digitalized system set up for land information andclassification. Sustainability of results on digitalized /automated systems can be ensured by building technicalskills and capacities in the beneficiary institutions. Increased technical skills and capacities would enable beneficiaryinstitutions adapt and amend systems in line with changing needs. Enhanced skills also contribute to increased ownership at thebeneficiary institutions. In the case of the project, through TA and trainings provided, the GAFI was able to undertake severalreforms for the OSSs that were not funded by the EASE project and pursued efforts to improvement of businessenvironment.
P153541 | Shaanxi Poor Rural Areas Community Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099040424174040202/text/P15354111f5b070bd1b5d817187c030f5df.txt | http://documents.worldbank.org/curated/en/099040424174040202/pdf/P15354111f5b070bd1b5d817187c030f5df.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1. To ensurethe success of farmers cooperatives, projects need to investin complementary infrastructure in combination with investmentsin human capital. The project supported investments in human capital development includingtraining and capacitybuilding,technical assistanceto strengthen cooperativesfinancial management and community procurement, businessplan preparation, and management of sub-projects. In addition, the projects investments in cooperative productiveassets (for example, cold storage, markets, and processing equipment) and public investments (for example, rural andproduction/farm roads, irrigation and drainage) greatly contributed to the success of farmerscooperatives.2. Projects that includepublic funding for private enterprises need to clearlyarticulatethe public benefits from such partnerships with the private sector to ensure smooth implementation ofactivities.The projects experience showed thatmatching grants to agro-enterprises caused delays inproject implementation. To ensure smooth implementation, itis important to clearly articulate the public benefits from suchpartnerships with the private sector,and the need for maintaining strong communication with the governmenttofamiliarize new staffwith the rationale and benefits to avoid any impediments to implementation.The project highlightedthe poverty reduction dimensions, especially the gain for the poor and the Government, and the ability to leverage private sectorcapital to rural and remote areas that would otherwise not be considered attractive investment destinations. There is also need forextensive consultations among prospective agro-enterprises to ensure that their own benefits from this arrangement are clearlyunderstood.3. Project design needs to accurately assess the timeframe needed to bring framers cooperatives toprofitability to ensure realistic achievements over the implementation duration.The project experience showed thatbringingfarmers cooperatives to profitability is a lengthy process that entails restructuring existing or establishing newfarmer cooperatives, including setting up the governance organs, administrative systems, accounting systems and software, andtraining. In addition todeveloping business plans; and carrying out physical investments and sometimes planting crops thathave long maturity periods (for example, up to three years in perennial crops) before harvest begins. In view of this lengthyprocess and based on this projects experience, ensuring significant progress toward profitability requires earlyidentification, mobilization and training of beneficiary farmer cooperatives. Also, a strong ME system is needed forperformance evaluation and constant feedback loop to guide tailored and continuous technical and administrative capacitybuildingthe presence of both a third-party ME service provider and a financial auditor for farmer cooperatives can behelpful in this regard.
P153548 | Lushan Earthquake Reconstruction and Risk Reduction Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111124132042570/text/P153548-5f1b7ef1-ce27-4d42-8b21-4870e21711cd.txt | https://documents.worldbank.org/curated/en/099111124132042570/pdf/P153548-5f1b7ef1-ce27-4d42-8b21-4870e21711cd.pdf | The project offered the following lessons from the operation: When projects support disaster resilientinfrastructure,it is important to broadly define outcomes and relevantindicators to capture broader economic impact andlivelihoods for a more comprehensive assessment of the project. In this project, design focused on reducing physical riskwith solutions beyond physical infrastructure design solutions.The PDO was achieved. However, the outcomes suggest otheraspects of resilience could form part of design. For example, the project showed that resilient infrastructure could spur economicgrowth. Regions with flood protection standards experienced an influx of commercial and residential investments. Public open spacesaround emergency shelters have enhanced the communitys daily experience. Landscaped grounds of the emergency shelterscontributed to improved daily life. Future disaster resilience initiatives highlight envisioning resilient infrastructure not onlyas a means of risk reduction but also as a driver of broader community benefits, contributing to safe and vibrant communities. Thelink between outputs and its broader economic impact, for example, on real estate development and waterfront rehabilitation, couldbe strengthened. A strengthened DRM system causes effective disaster response and benefits resilience. Improved preparedness couldbe reflected in activities such as conducting periodic drills. Risk reduction then fosters livable habitats for residents ofdisaster-prone areas. Indicators of a more comprehensive economic impact assessment may broaden the outcomes of riskreductionand Building Back Better. If including the construction of emergencyshelters to strengthen disaster resilience, it is important to havedetailed design specifications suitable toaddressemergencies and guidelines for their non-emergency use.In this project, emergency shelters werecompleted in time. These were utilized in crises such as the COVID outbreak, earthquakes, and floods. However, certain technicaldesign shortcomings were discovered after completion. For example, the underground parking areas were to be overflow shelter areasand/or storage for emergency equipment when not in use. Ceiling heights in most were restricted to 2.2 m, which impeded the use byemergency vehicles. Emergency supplies required transfers to smaller vehicles, affecting time-sensitive emergency responses.Another observed shortcoming was the visibility of connections for septic tank to mobile toilets, or water supply to tanks. Thesetechnical design flaws, while minor, underscore the importance of ensuring that detailed specifications match the needs to delivereffective and efficient emergency response. When not in use as shelters these structures may serve as public open spaces, withpotential for social and leisure activities, especially in land-scarce regions. Preparing guidelines for non-emergency use ofshelters could optimize its utility for the community. If standards for disaster resilient infrastructureincorporated community concerns to design these standards, adherence may be better implemented. In this project, countygovernment prioritized community concerns over adherence to disaster resilient design guidelines. For example, the county agreed toconcerns raised by merchants and residents to reduce the heights of street curbs in commercial areas, to avoid impeding commercialoperations. This design concession adjusted the drainage capacity standards, but heightened pedestrian safety concerns and riskthat urban flash floods may affect adjacent structures. In Mingshan, residents expressed hygiene concerns while county officialsexpressed image issues because the shelter was near the Mengdingshan Scenic Resort entrance. As a result, mobile toilet connectionswere excluded from emergency shelters in Mingshan. While the Government and implementing agencies are to be commended for theirattentiveness to community input, a more concerted effort to gain resident support for design standards might have been beneficial.Alternatively, a more creative design solution that meets both safety objectives and community preferences could be furtherexplored. These instances highlight the need for a balanced approach where the community is enjoined to express their preferenceswhile not compromising safety and project goals.
P153591 | KH - Livelihood Enhancement and Association of the Poor Project (LEAP) | East Asia and Pacific | Cambodia | IDA | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099090524065037063/text/P153591-e1e19b9c-952f-4175-bd22-8c271ee3c83a.txt | https://documents.worldbank.org/curated/en/099090524065037063/pdf/P153591-e1e19b9c-952f-4175-bd22-8c271ee3c83a.pdf | The operation offered the following lessons: If capacity building is combined with small livelihoodgrants, these may empower poor households. In this project, economic development was to be delivered topoor households by enhancing soft skills, building technical capacities using participatory means, and using these asincentivesto access financial resources for livelihood opportunities. Participating beneficiaries gained skills and resourcesto sustain livelihoods and jobs, as reflected in its Teach the community how to fish motto. FormingSHGs may deliver income-generating opportunities to impoverished and vulnerable communities. In this project, a systematicapproach was initiated by building institutional capacity, establishing, and strengthening SHGs to become sustainable communityinstitutions. This approach requires time and optimal use of resources. One way was to collaborate with service providers and NGOsspecializing in community engagement to boost SHG capacity. This collaboration is vital when faced with a limited governmentcapacity to deliver such support. A customized, flexible, and inclusive community participatory approach may bebeneficialwhen working with marginalized communities todesign, implement, and monitor local investmentprojects. This projects inclusive approach meant fostering social capital while contributing to local economicdevelopment. Women and vulnerable populations were actively involved. Beneficiaries were informed about objectives, approaches, andactivities. They were made aware of their participations short- and long-term social and economic benefits. Beneficiariesbegan to trust local authorities because of their flexibility and responsiveness. Community members gained a sense of ownershipfrom these participatory engagements. This approach heightened participation in project training, in forming savings groups, and inengaging in community meetings. Such participation maximized the projects impact and asense of ownership thatcontributes to the sustainability of project outcomes. Using resourcesto raise awareness, training, andmentoring of women beneficiariesmay strengthen womens participation and boost their economic position. In thisproject, financial assistance was used to foster womens confidence, amplify their voices, and empower them to assert agency.The project facilitated an inclusive environment for women to participate and optimize benefits from project activities. Othersimilar projects may engage traditional male leaderswhile nurturing womens leadership skills and making availablerelevant networking opportunities. These strategies may further enhance gender equality and empower women to contribute to moresustainable and impactful development outcomes.
P153603 | MA-Second Capital Market Development and SME Finance DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | Two lessons are drawn from the ICR (pages 38-39), with some adaptation, and a third is added by this ICR Review.Government commitment to reform objectives are crucial to the success of structural reform programs. Inthis programmatic development policy operation, the government of Morocco went beyond completing the 18 prior actions for theseries to proactively plan for,as well asto undertake, more measures that would advance its reform objectives.The government had a long history of commitment to the development of its financial sector dating back to the creation ofthecredit guarantee agencyin1949andthe financial market regulator in 1993. Following this DPF series,the governmenthas continued to engage FIRST with technical assistance projects, the IFC with a capital market developmentprogram, and the Bank with a financial inclusion DPL.Policy and structural reform programs in the financialsector can benefit from the provision of technical assistance both for program design and program implementation.The implementation of this programmatic development policy operation was supported by 25advisory services andanalytics activities under 9 technical assistance projectssupported by FIRST, in areas including: MSME finance; capitalmarket laws, rules,and regulations; credit information systems; financial inclusion, and financial stabilityframeworks. The advisory services and analytics supplied valuable technical inputs to the reform measures,including knowledge about international standards and practices. Moreover, according to the ICR, the technical assistance,whichwas well integrated into the operation, helped ensureits successby: supporting the implementation of theprior actions, and strengthening the capacity of the implementing ministries and agencies.In designingME plans, it is important for governments and the Bank to ensure that public or private information systems can supply thedata required for reporting on results indicators. In this programmatic development policy operation, the privatecredit bureaus information systemdid not report the size of enterprises --- large, medium, small and micro enterprises--- that requested and received credit reports. Thus, the attainment of the target to have 40,000 MSMEs covered by creditreports could not be ascertained. Similarly, the credit guarantee agencys information systemdid not report on theage of enterprises --- newor young --- covered by its guarantee and co-financing operations. Thus, the attainment ofthe target to raise the number of newor young enterprises from 1,572 to 3,000 could not be ascertained either.
P153604 | Poyang Lake Basin Town Water Environment Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099102323141561230/text/P1536040cc292603608de201554a9160777.txt | http://documents.worldbank.org/curated/en/099102323141561230/pdf/P1536040cc292603608de201554a9160777.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1. Anintegrated approach can be an effective and practical to effectively address water pollution in lakes.The projectcombined physical works with non-infrastructure measures. This includedfrequent consultations with the communities duringproject preparation and implementation. As aresult of the high quality of consultations, communities have adopted theapproach and were active in the implementation of the Lake Management Platform (LMP).2.A participatoryapproach with adequate inclusion of women is critical to implementing sustainable lake basin management and enhanceawarenessof the lake and river environment protection through practical procedures to change beneficiaries behavior.The project conducted timely and frequent consultation with beneficiaries and encouragedfemale participation. Thesewere essential elements for the establishment and implementation of diversified and long-term Public Participatory Management (PPM)mechanisms. For example, community members in Poyang County following the participatory approach and ownership at the local levelhave initiated a monetary contribution from the household at a level of US$1.5 per month to support the sustainability of the lakeand river environment protection.3.The application of disruptive technologies, such as the pipeline cleanrobots and smart dustbin systems for solid waste recycling, smart systemcancontributeto the wastewater and solidwaste reduction and digitized waste management. The use of the disruptive technologies helped achieve the costeffectiveness of the entire system. This approach can be adapted across the country and globally based on thorough system diagnosisand analysis.
P153613 | Livestock Sector Development Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099061423080039333/text/P153613097289e052087e60485c8666b785.txt | http://documents.worldbank.org/curated/en/099061423080039333/pdf/P153613097289e052087e60485c8666b785.pdf | The ICR highlights two major lessons. They are sound and supported by the projects implementation experience andpresumably, have beentaken into account during the recent formulation and approvalof Phase 2Project.Lesson 1: If activities targeted explicitly to smallholder farmers are not in place, theymight lose out in the competition with larger and more commercial farmers and agribusinesses. The LSD project, through itsvalue chain modernization component (credit line and matching grants), aimed at improving access to finance and improvedtechnologies of livestock farmers, including dehkans. However, most beneficiaries of the LSD project were large-scale commercialfarmers and agribusinesses. The number of dehkans who benefited from LSD project interventions, including from credit lineinvestments and VCD grants, fell short of expectations as larger and medium-sized farmers had an advantage in terms of betteraccess to information and extension services and had a greater ability to mobilize resources and provide collateral. The follow-onproject took this lesson into account. It included a separate component and a special credit line window to work exclusively withsmallholder farmers by developing criteria and a set of actions to target better and encourage the participation of and directbenefits to smallholders.Lesson 2: Public livestock support services, including veterinary and animalhealth, research, extension, and advisory services, may contribute to the pickup and sustainability of livestockproductivity. Although the LSD project extensively included capacity-building activities into the project design andinitial activities in developing the livestock sector strategy and a livestock traceability system were completed, these areas, aswell as marketing and value addition infrastructures, remained underinvested. Learning from this project, the follow-on projectaims to cover these gaps adequately; the project is applying the lesson of the importance ofinvesting in livestock publicsupport services and market and value addition infrastructure, which arevital support interventionsto achieve a realand sustainable transformation of the livestock sector.
P153702 | REGIONAL PROGRAM TO HARMONIZE AND MODERNIZE LIVING CONDITIONS SURVEYS | Western and Central Africa | Western and Central Africa |  |  | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | https://documents.worldbank.org/curated/en/099100424133599456/text/P153702-40de1053-31f6-49c1-8d94-d0a0ff250a4e.txt | https://documents.worldbank.org/curated/en/099100424133599456/pdf/P153702-40de1053-31f6-49c1-8d94-d0a0ff250a4e.pdf | The ICR offersimportant lessons with which IEG concurs. They are: The regional designresulted inpositive impacts that could not have been achieved through eight individual projects. Some of the main benefits were: (i) theregional capacity-building workshops were an effective way to introduce new concepts and approaches to household surveys andsocio-economic indicators. (ii) the harmonization of living conditions surveys was more easily achieved in a group context inWAEMU. (iii) The existence of regional institutions (WAEMU Commission) with credibility among its member countries facilitated theadoption of politically sensitive steps such as public access to data. (iv) Cooperation with a regional institution (WAEMUCommission) did not mean that all aspects of a project needed to go through that institutionthe World Bank could retaincertain responsibilities (e.g., design and methodology of the surveys). (v) A regional project had a strong demonstration effectthat led to other countries in Sub-Saharan Africa adopting harmonized living conditions surveys including the initiation of moreregional projects in Africa. Regional projects in member countries that have diverse implementation capacity needdisproportionately larger TA budgets to succeed. The regional design required a significantly larger technical assistance budget tosucceed. First, the supervision budget was insufficient to cover the cost of supervising the activities and providing necessaryimplementation support to one regional institution and eight countries with diverse levels of client (NSO) capacity. Second, giventhe low-capacity environment in several of the WAEMU countries, the support implementation missions, and regional workshops did notprovide enough technical assistance for these countries to consistently achieve the desired level of quality in outputs.Consequently, budgets from other WB Analytical and Advisorytasks had to be diverted to this project.
P153744 | Philippines Social Welfare Development and Reform Project II | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099003003222313912/text/P153744036ac420aa0ac0e0a992391ce75a.txt | http://documents.worldbank.org/curated/en/099003003222313912/pdf/P153744036ac420aa0ac0e0a992391ce75a.pdf | The ICR (pp. 25-27) offered several lessons and recommendations, including the following lessons re-stated by IEGReview:Flexibility in CCT conditionalities allows uninterrupted grant support for children from poor households.Under normal circumstances, it is understood that CCT beneficiaries would need to comply with specified conditions toreceive cash grants. However, during the COVID-19 pandemic, it was difficult for beneficiaries to attend schools or to participatein Family Development sessions and visit health facilities for checkup and immunizations. DSWD suspended CCT conditions in 2020,and, in 2021, it introduced new flexible conditions, including remote learning modalities to maintain a regular flow of granttransfers.Maintaining the accuracy of social protection targeting systems can promote the inclusion of vulnerablepopulation groups and can contribute to a stronger impact on poverty reduction and human capital accumulation. Under theproject, targeting accuracy progressively diminished as the share of poor beneficiaries belonging to the bottom two quintilesdeclined because of limited replacement of exit beneficiaries. Program coverage of pregnant women and young children declined ashealth grants were provided without varying by the number of eligible children, thus providing little incentive to report newpregnancies, and contributing to a decreasing coverage of new pregnancies and young children. This lesson led to a pertinent ICRrecommendation for investing in a dynamic social registry that can receive frequent updates from various sources, and for designingeffective incentives that would promote the inclusion of pregnancies and newborns in programmonitoring.Strengthening social protection delivery systems beyond 4Ps CCT can make systems more adaptive toshocks. Under the project, the response to the COVID-19 pandemic highlighted the need to further strengthen deliverysystems. The project helped the government early response to the pandemic through timely emergency support for 4Ps CCTbeneficiaries, but support to additional beneficiaries (e.g., new poor) encountered difficulties, as there was no accurate andupdated social registry. Application forms were manual and payments were made mostly in cash. This experience raised another ICRrecommendation to make the system more adaptive to shocks, including for natural disasters, by further investing in DSWDscapacity, social registries, information technology and payment mechanisms that can facilitate timely inclusion of eligiblepopulations not covered in regular social protection programs like 4Ps. Such investments, including the expansion of digitalpayments, can provide added attention to the least financially-included areas through collaboration with the private sector andfinancial service providers.
P153753 | Malawi Agricultural Support and Fiscal Management DPO | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2022 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/562501637168642031/text/Malawi-Agricultural-Support-And-Fiscal-Management-DPO.txt | http://documents.worldbank.org/curated/en/562501637168642031/pdf/Malawi-Agricultural-Support-And-Fiscal-Management-DPO.pdf | IEG concurs with the general lessons of the ICR (p. 28):Lesson 1: Careful matching of prioractions and results indicators to the political and institutional context is a prerequisite to successful outcome of a DPO. In thisoperation, several of the prior actions were designed to create legislative frameworks (SGR law, COGA, WRA, ADMARC) andinstitutional reforms. However, in Malawi, these kinds of actions are undermined by weak capacity and governance problems. Futureoperations could consider more strongly linking prior actions and triggers to implementation of reforms. Similarly, whenpossible, results indicators should be easier to track and more closelylinked to outcomes (see the discussion in Section4).Lesson 2: Strengthening linkages with Bank TA and investment lending operations can supportimplementation and supervision of DPOs. One of the strengths of this DPO was that it was linked closely to a set of Bank TA andinvestment lending operations. However, an even closer link between the actions tracked in the TA operations and the prior actionsand RIs of the DPO would have further supported implementation and supervision of the DPO.Lesson 3: DPOseries need to adequately account for lengthy processes of legislative change. The analysis in the ICR indicates that in Malawi ittakes a long time to implement legislative change. Developing and implementing laws is time consuming, unpredictable, and not fullyunder the control of the executive. In this DPO, there were delays in putting in place laws for ADMARC, the COGA, the WRA and theAudit Reform act, which should be taken into account for future operations.To these lessons, IEG adds thefollowing:Lesson 4: It is important for projects with potential impact specifically on women to trackcarefully and report those impacts. In this case, the ICR states that some prior actions targeted women, but reporting or analysisof any benefits that accrued is missing.
P153863 | Senegal River Basin Integrated Water Resources Management Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | RETF | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099825001092319855/text/P15386300174b905e096200ca47d988ec1f.txt | http://documents.worldbank.org/curated/en/099825001092319855/pdf/P15386300174b905e096200ca47d988ec1f.pdf | IEG derives the following lessons drawn from the ICR:1. Long term support to regional organizationsis key to advancing water security: Long term support to regional organizations is key to implementing integratedwater resources management measures (e.g. introduction of sustainable land management), which can help mitigate and adapt toclimate change. Because the impact of such measures is basin-wide, regional organizations are well placed to coordinate theirimplementation, so as to maximize benefits for all riparian countries involved, and to avoid some of the effects of politicalinstability that might otherwise prevail.2. Control of invasive aquatic species necessitates goingbeyond mechanical removal: The persistent challenge posed by invasive aquatic species calls for a sequencedapproach, from needs assessment to implementation, supported by monitoring frameworks, in lieu of ad hoc approaches based onmechanical removal. Use of comprehensive and innovative approaches to prevention and eradication, e.g. through changes inirrigation and drainage infrastructure design, including resizing of canals to increase flow velocities, can be more effective inthe long run.3. Institutional strengthening activities for water resources and typha management need tocapitalize on existing governance arrangements. The project promoted community-level engagement and participation,to ensure the long-term sustainability of measures for removal of typha, and to build awareness of risks associated withinvasive aquatic species and required responses. WUAs are not present in all riparian countries - for instance Mauritania,where agricultural cooperatives were tasked with canal operation and maintenance. The initial focus of the project being onWUAs, meant that Mauritanias cooperatives were not identified as key actors involved in the management of typha something that was addressed only after the 2018 restructuring, which recognized the diversity of existing governancearrangements.
P154036 | Disaster and Climate Resilience Improvement Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099900009302210599/text/P154036049e8aa0340b0810ae9f3d19a294.txt | http://documents.worldbank.org/curated/en/099900009302210599/pdf/P154036049e8aa0340b0810ae9f3d19a294.pdf | The ICR provided five lessons from the operations (ICR, paragraphs 92-96). These are presented below with slightmodifications: A broadly formulatedobjective facilitates a flexible response to evolvingneeds.In this project, the objective covered disasters in a broad sense, which managed to include the COVID19pandemic. The project reallocated resources for the PIUs to support the subnational governments, the disaster managementauthorities, and other departments in Punjab and the State to address the growing health crisis. The reallocated fundsfinanced activities that contributed to enhancing local disaster management capacity. Specifying sites forpossible subprojects prior to project start may enhance readiness of a project usinga framework approach.Inthis project, appraisal was completed in five months because this was prepared as an emergency response. Adopting a frameworkapproach meant that the government had a list of priority investments. However, infrastructurework sites were approved onlyas implementation was underway. Delays were experienced because some complex infrastructure works required extended preparation.The 2018 national elections and postponed procurement and contracting decisions also contributed to delays. identifying work sitesfor proposed civil works may help spur implementation readiness and avoid delays. Sectors with enhancedcapacities may have room to absorb the implementation needs of additional investments financed by cost savings. In thisproject, substantial cost savings were generated by the exchange rate gainswhen the PKR continued to decline against the USDduring the life of the project. This led to substantial differences in estimated and actual costs of subprojects. A change inpriorities led the governmentto cancel some activities without changing the level of ambition of the project objectives.These resources were then used to finance additional critical subprojects to achieve disaster resilience, and in some cases, exceedtarget outcome indicators. Building the capacity of the PIUs in financial management and planning prepared them to absorb andimplement the added investments. Strengthened district-level entities may become effective frontline respondersto emergencies. In this project, design focused on enhancing the capacities of disaster management authorities at thegrassroots level. In Punjab, this focus translated to adopting district level and community-based disaster management planning;establishing district level emergency operations centers; and village emergency reporting and facilitation centers. In the State,the Disaster Management Agency developed district level disaster riskmanagement plans and participated in procurement. Theseefforts led to fostering outreach, coordination, andresponse capacities of local disaster management entities in Punjab andthe State. Enhanced capacities were demonstrated in their response to the 2019 floods, generating smog alerts, mapping locustinfestation, predicting geographical areas to be affected by heatwaves, and reducing the spread ofCOVID19. StandardizingPost Disaster Needs Assessments (PDNAs) may help establish baselinesformonitoring and evaluating emergency projects. Inthis project, lack of baselines for the projectinterventions led to setting initial targets in percentages. This proved difficult to monitor. Exact targets were established atthe mid-term. The framework approach in project design allowed the adjustment of targets during implementation as governmentpriorities evolved. Standardizing baselines, in both methods and minimum targets, may be further refined with ICT tools such asremote sensing, community-based monitoring, or application-based surveys for improved data collection, supervision, andtransparency. These tools may helpwhen access to physical sites is limited.
P154041 | MA: Transparency and Accountability DPL2 (Hakama II) | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | Three lessons are drawn from the ICR (pages 22-24), with some adaptation. There is valueto frontloading areform program when aclearly identifiableopportunity for transformative change emerges. The ArabSpring of 2010-11 and the ratification of a new Constitution in 2011 createdsuch anopportunity for economic andgovernance-related reforms in Morocco. The Hakama I and Hakama II development policy operations, whichaimed to promoteaccountability and transparency in the management of public resources and to foster open governance,loaded many legal,policyand institutional initiatives upfront in the program timeline to catch thereform wave goingforward. Sustained policy dialogue serves to nurture a reform process. Continuous dialogue amongdevelopment partners, governments and stakeholders keeps the focus on the policy agenda andmotivates progresswithreform actions. The Banks country dialogue with Morocco on accountability, transparency, and governancehelpedto encourage theAuthorities, albeit with some delay,to appoint members of the procurement body CNCP,enact the ATI Law,and move forward with the petitions system. Harmonization of operational demands on borrowers bydevelopment partners supporting multi-donor programs assists in the successful implementation of such programs. The Bank, EUand AFDB took a unified approach to their public-sector governance reform programs in Morocco and assumed the burden not only ofpolicy, and but also of operational, coordination. The Government did not have to comply with the separate operationalrequirements of three different external agencies.
P154041 | MA: Transparency and Accountability DPL2 (Hakama II) | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2016 | 2017 | 2020 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/824781581458449816/text/Morocco-First-and-Second-Transparency-and-Accountability-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/824781581458449816/pdf/Morocco-First-and-Second-Transparency-and-Accountability-Development-Policy-Loan.pdf | 6. Lessons 6.1 Better use of knowledge and improved knowledge management contribute to the quality of operations. This assessment noted several areas where the design and implementation of World Bank operations could have been improved\. â€¢ Poor overall public expenditure outcomes for improving shared prosperity reflect inadequate intraand intersectoral allocations. The former is being managed through outcome-oriented budgeting. The latter has not been a focus because of a lack of basic diagnostic studies. Recent studies of the public investment program undertaken by the World Bank and the IMF partly addressed this issue. However, a comprehensive PER was last performed more than two decades ago. A new one should be a priority, especially given the number of DPFs being pursued in Morocco. â€¢ Lessons from experience received pro forma treatment. It is not enough to cite a lesson; its effect on the operation design should be explained. â€¢ It is important to preserve key information to maintain institutional knowledge that can inform future operations and policy dialogue. 6.2 Monitoring and evaluation require greater attention during design and implementation. â€¢ Inadequacies in reporting requirements and information conservation undermined the ability of the World Bank and its management to monitor progress. More frequent aide-memoire are needed, especially after each mission and when there is a significant gap between operations within a DPF series (in this case, two years). â€¢ The indicators selected should be aligned with the time segment of the longerterm program from which they are derived. In this case, some indicators were not fully attributable to or were misaligned with (more ambitious than) the project development objectives or what could be achieved and measured during implementation (approximately three years). â€¢ Implicit assumptions that the reform will eventually improve intersector allocations and service should be validated. This can be accomplished with parallel assessments (in this case, through technical assistance). 6.3 Greater transparency and better information management are needed to sustain dialogue as World Bank teams and counterparts change. â€¢ Key elements of the dialogue need to be recorded, per World Bank requirements, and periodic reporting by the borrower should be envisaged as part of the project design and in the financing agreement. The World Bank team should prepare more frequent progress reports when warranted (for example, after a supervision mission) and when there is a significant delay between operations in a series. â€¢ It is important to ensure a smoother transition when task teams change, especially when the program that is part of the policy dialogue is implemented over lengthy periods. 6.4 It would be helpful to assess a cluster of mutually reinforcing World Bank operations jointly. Including an assessment of the economic growth DPF series might be considered (World Bank 2013a). In this case, other potentially relevant operations would have included the parallel technical assistance provided by the World Bank and other donors (for example, assessing how complementary financing enhanced DPFs) as well as other donor support to Hakamaâ€”notably the EU's support based on the collaborative approach already developed elsewhere (World Bank and European Commission 2015). 1 Referred to as the Organic Budget Law in World Bank documents. However, Organic Finance Law represents a more accurate translation of the original name in French (loi organique relative a la loi de finances). See\. http\.//lof.finances.gov.ma/sites/default/files/loi_organique_130-30_fr18.pdf. 2 https\.//pefa.org/sites/default/files/assessments/reports/MA-May09-PFMPR-Public.pdf https\.//pefa.org/sites/default/files/assessments/reports/MA-Sep16-PFMPR-Public-with-PEFACheck.pdf 3 Even though the Public Expenditure and Financial Accountability review was completed in 2016, it was only made public in 2018 and does not capture the expected favorable effects of the Hakama reforms on public financial management systems. 4The elements of the reforms were as follows\. deepening national identity and social cohesion; the rule of law, regionalization, and governance; job creation and economic development; national sovereignty and social development; and strengthening social services. (See World Bank 2018c.) 5A recent World Bank blog on Asia explained that Reforming the public sector is a constant process to address emerging challenges stemming from an increase in economic sophistication and expanded citizens' expectation....Typically, significant challenges emerge from the enormous scale and complexity of the reform tasks to be undertaken. This requires levels of commitment, coordination and collaboration that may be without precedent for those involved even when the circumstances are most favorable. https\.//blogs.worldbank.org/governance/addressingchallenges-public-financial-management-and-public-sector-reform-east-asia. 6The hiatus was due in part to uncertainty and limitations on International Bank for Reconstruction and Development allocation for Morocco before the World Bank's capital increase. 7The European Union also supported Hakama through budget support. Its analysis also concluded that a sound basis for lending through budget support was present (European Commission 2012). 8The blog post is available at https\.//www.cabri-sbo.org/en/blog/2018/programme-basedbudgeting-reform-in-morocco-challenges-and-lessons-learned. 9 https\.//www.finances.gov.ma/fr/Pages/plf2019.aspx. 10https\.//www.huffpostmaghreb.com/entry/plf-2019-adoption-en-commission-de-la-premierepartie-du-projet-de-loi-de-finances_mg_5be94545e4b0769d24cf0a2a. https\.//www.medias24.com/MAROC/ECONOMIE/ECONOMIE/187409-PLF-2019-un-budgettout-sauf-social-selon-l-opposition.html. 11The World Bank Group's 2018 Strategic Country Diagnostic for Morocco provides additional information\. The potential of the existing PPP framework has not been fully exploited . . . 55 percent of the total volume of infrastructure projects involving private sector participation were PPP, the rest consisted of other forms of private sector participation using merchant and partial contracts (World Bank 2018c). 12The following list of relevant audits pertaining to reforms under Hakama are publicly available at http\.//www.courdescomptes.ma/fr/Page-27/publications (portal), which includes http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-annuel/rapport-annuel-de-lacour-des-comptes-au-titre-des-annees-2016-et-2017/1-215 (annual report); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-annuel/rapport-preliminairesur-lexecution-du-budget-de-letat-pour-lannee-2016/1-203 (2016); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-thematique/rapport-surlevaluation-du-systeme-de-la-fonction-publique/2-200 (public finance system); http\.//www.courdescomptes.ma/fr/Page-27/publications/rapport-thematique/synthese--secteurdes-etablissements-et-entreprises-publics-au-maroc/2-146. 13According to a World Bank study, Citizen engagement in the Hakama DPL stands out in two ways\. First, the DPL itself is based on extensive public consultations in the framework of the National Dialogue on citizens' new constitutional rights, government consultations on different aspects of reform as well as online consultations and a nano survey to gather citizens' feedback on the reform agenda. Second, the reforms supported through the DPL directly enable increased citizen engagement in Moroccan public space. Citizens are given the opportunity to access and comment on draft laws, submit petitions, voice their concerns and priorities in public consultations, and benefit from e-government services. http\.//pubdocs.worldbank.org/en/977051497970145435/Case-3-Morocco-Rebuilding-Trustbetween-Citizens-and-Government.pdf. For more information about Morocco joining the Open Government Partnership, see the U.S.- Middle East Partnership Initiative website at https\.//mepi.state.gov/morocco-ogp. 15To view the Open Budget Survey 2017 for Morocco, see the International Budget Partnership website at https\.//www.internationalbudget.org/open-budget-survey/results-by-country/countryinfo/?country=ma. 16For example, the petitions regarding French in schools and women's inheritance rights\. https\.//www.moroccoworldnews.com/2019/04/269557/morocco-intellectuals-petition-french and https\.//www.moroccoworldnews.com/2018/03/242922/moroccan-public-personalities-signpetition-womens-inheritance-rights. 17For more information, see the legal analysis of the Second Draft Law on the Right of Access to Information\. https\.//www.article19.org/data/files/medialibrary/37263/Morocco-analysis-RTI-lawdraft-two-final-version.pdf. 18See the Rule of Law Indexes for 2012â€“13 and 2019\. https\.//worldjusticeproject.org/sites/default/files/documents/WJP-ROLI-2019- Single%20Page%20View-Reduced_0.pdf and https\.//worldjusticeproject.org/sites/default/files/documents/WJP_Index_Report_2012.pdf. 19 The platform is at https\.//www.eparticipation.ma/fr. 20The mission was provided with a full list of e-government services (approximately 80) now available online. 21See http\.//www.unpan.org/Library/MajorPublications/UNEGovernmentSurvey/PublicEGovernanceS urveyintheNews/tabid/651/mctl/ArticleView/ModuleId/1555/articleId/58649/Default.aspx. 22The Country Partnership Framework for fiscal years 2019â€“24 proposed an Advisory Services and Analytics program that includes a new Public Expenditure Review (World Bank 2019, 66). 23
P154114 | Liberia Forest Sector Project | Western and Central Africa | Liberia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099050324085012327/text/P1541141ba68b501e19a8518acf6c03418d.txt | http://documents.worldbank.org/curated/en/099050324085012327/pdf/P1541141ba68b501e19a8518acf6c03418d.pdf | The ICR included six lessons, the following three are emphasized with some adaptation of language:1.Incomplex, politically sensitive, risky implementation environments, proactive and adaptive management is criticalforproject success.The project ownership and political commitment of the FDA during LFSP preparation differedsignificantly from the political landscape during implementation. The project transitioned from a planned 9-step process to acluster approach for enhanced CFM. Responding to community demand with small-scale social infrastructure investments, coupled withongoing awareness and PLUP activities, resulted in substantial post-MTR improvements. This shift not only promoted better sharingof benefits but also increased the chances of sustainable CFM. Engaging multiple stakeholders, including various governmentagencies in the region, broadens ownership at different levels, reducing the risk of unintended deviations. It became evident that,even when government agencies aim to lead, additional technical support through TA or project resources is essential while buildinggovernment technical capacity. In all, a realistic assessment of implementation timeframes, including the possible impact ofchanges in institutional, administrative, and political circumstances, is always needed.2.Designing a clearRF and substantivelymodifying the RF following the MTR ensures that the RF accurately reflects the evolving nature of theproject and aligns with the achievements identified during the MTR or other critical project milestones. The sharp andabrupt decline in the Governments interest in transitioning from concessional forestry to CFM was impossible to foresee andreflect in thefirst restructuring.However, if adequate intermediate results indicators were introduced at the designstage, the RF would have captured project progress and achievements better. The absence of a second substantive restructuring basedon the MTR prevented the World Bank from fully adjusting the projects RF to capture the eventual achievements of the revisedapproach. Future interventions should prioritize timely and thorough revisions of the RF, particularly after significant changes inproject strategy or approach.3. Forest projects need to investin adaptive technology and accommodatechanges in management trends to enhancethe effectiveness ofimplementation.The global attention on thevalue of forest carbon stock has changed the interest of governments in the traditional forest concession.Whilenotanticipated during the projectdesign as well as in MTR,LFSP piloted the use of technologies such as drones,Geo-enabling initiative for Monitoring and Supervision (GEMS) and Kobo Toolbox software for forest inventory and better real-timemonitoring of the implementation of project activities. The use of such technologiesproved to beuseful in the contextof limited transport access and during the COVID-19 restrictions. The project also conducted a major concession review with a listof policy recommendations that considered the global trend in forest management as well as Liberias local political context.Forestry projects design and implementation arrangements need to accommodate the changing landscape of forest management toenhancethe effectiveness of the implementation.
P154149 | Vanuatu Aviation Investment Project | East Asia and Pacific | Vanuatu | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2015 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/846371601519784742/text/Vanuatu-Vanuatu-Aviation-Investment-Project.txt | http://documents.worldbank.org/curated/en/846371601519784742/pdf/Vanuatu-Vanuatu-Aviation-Investment-Project.pdf | The following three lessons are used from the experience of implementing this project, with some adaptation oflanguage:1. The regional approach could be an ideal option for countries with limited IDA allocation and an urgentneed for developing complex large scale investments. As part of an IDA regional program, this project provided additionalfunding from regional IDA sources. This aided Vanuatu in accessing additional resources and support from the Pacific AviationInvestment Program (PAIP) aided in preparing the project in an expedited manner. Further, a regional procurement approach can behelpful in enabling the participating countries to standardize their practice.2. While maintaining the benefit ofusing harmonized solutions across participating countries, regional programs need to allow a certain flexibility in tailoring thedesign to reflect country context. In this project, the regional requirements on results indicatorslimited theprojects option to offset some shortcomings in the ME framework by making it more relevant tothe countrycontext.3. Remoteness needs to be factored into project budgeting, especially when there are limited benchmarksfor certain sectors. Given that this was a first of its kind financingin thesector, cost estimates proved tobe challenging. The lesson is that higher cost contingencies need to be factored into the project design at appraisal, and theseestimates need to be updated continuously based on the latest data available data during implementation.
P154185 | Malawi Education Sector Improvement Project (MESIP) | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2017 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099005110202229654/text/P15418502555bb034095e902dc398236a64.txt | http://documents.worldbank.org/curated/en/099005110202229654/pdf/P15418502555bb034095e902dc398236a64.pdf | The following lessons are drawn from some of the six lessons presented in the ICR, slightly reworded by IEG to be moresuccinct: Low-cost construction is an efficient means of improving school infrastructure, throughalliances between schools and communities, especially in low capacity contexts. School- and community-ledconstruction under the project effectively addressed the severe shortages of classrooms, achieved at a low cost and with highquality.Training received by communities, together with the classroom construction experience gained under the project, haveequipped those communitiesto raise their own funds, build their own shelters, and pave the way for more community-basedconstruction. Seeing the evidence of the capacity of communities to produce high-quality classrooms at low cost, thegovernmenthas now agreed to a significant scale-up of this approach. Malawis National Education Sector Investment Plan(2020-30) adopts community construction as the standard approach and targets construction of 44,000 such classrooms by2030.The ongoing Education Reform Program currently being supported by the Bank targets the construction of 10,900 low-costclassrooms (at a cost of$7,000 each), targeted to schools with pupil-to-classroom ratios above90. Communities can be highly effective in supporting changes in attitudes and practices that favor schoolattendance and retention of vulnerable, disadvantaged students. With project support: mothers groups haveadvocated for girls and disabled children to go to school and for the retention of teenage girls in Standards 6 to 8; communitychiefs have pledged to discourage early marriage, which deters girls from attending school; girls haves been encouraged to reportany abuse, which triggered an increase in the number of incidences reported and in cases actually being addressed by the court, anindication of communities willingness to take these incidences of abuse seriously and addressthem. The effectiveness and efficiency of results-based financing approaches can be significantly enhancedwith (i) the utilization of annual (versus one-time) targets; and (ii) the upstream consultation of potential independentverification entities and their methodologies.The projects transition from one-time end-of-project DLItargets to annual DLI targets improved motivation and progress, demonstrating its potential to effectively ensure that all DLIs areachieved.Challenges experienced with the verification of Year 4 DLIs were theresult of weak methodology underpinningthe verification exercise, resulting in a loss of confidence of the Local Education Groupin the validity of theresults. This points to the need for a more careful selection of the independent verifiermoving forward, with the closeinvolvement of the LEG inapproving the Terms of Reference, selecting the best candidate, and reviewing the proposedvalidation methodology.IEGs review offers an additional lesson: Equity objectives aremost effectively assessed by tracking and comparing the progress of disadvantaged districts and disadvantaged students with theirbetter-off, better performing counterparts who do not suffer from the same constraints and disadvantages. A numberof equity indicators and targets under this project tracked improvements in the disadvantaged districts over their baselines, butdid not systematically measure the extent to which gaps in key performance and outcome indicatorsbetween the disadvantageddistricts/vulnerable populations and their better-off counterparts were reduced or closed.
P154213 | CL Social Inclusion for Shared Prosperity DPL | Latin America and Caribbean | Chile | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/610141515630428206/text/ICRR-Disclosable-P154213-01-10-2018-1515630422362.txt | http://documents.worldbank.org/curated/en/610141515630428206/pdf/ICRR-Disclosable-P154213-01-10-2018-1515630422362.pdf | The ICR (pp. 37-38) provides several useful and insightful lessons, including:Deliberateconsensus-building can be key, even for seemingly less controversial reforms. In this case, a careful process ofbringing stakeholders together in dialogue across the ideological spectrum built support for the full scholarship program, and alsofacilitated agreement on implementation details.The Bank can add important value in high-incomecountries. In this case, sustained analytic work brought the Banks vast expertise on poverty, vulnerability,and equity measurement to bear on a long-term reform agenda.IEG adds the followinglesson:Although improvement in learning outcomes cannot reasonably be expected in the time frame ofa development policy operation, improved learning can still be acknowledged as a longer-term outcome, with a plan for addressing itwith targets. In this case, the results chain linking outputs to increases in quality of education to the implicitgoal of improved learning outcomes was not clear.
P154219 | Deposit Insurance Strengthening Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2016 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/671471600459696037/text/Bulgaria-Deposit-Insurance-Strengthening-Project.txt | http://documents.worldbank.org/curated/en/671471600459696037/pdf/Bulgaria-Deposit-Insurance-Strengthening-Project.pdf | The ICR offers the following lessons with some modification of language by IEG:Results based financing,particularly when combined with an effective results framework that involves unambiguous success criteria can be a powerfulinstrument to achieve PDOs. In Bulgaria, project design ensured that disbursements occurred upon achievement of clearly specifiedcriteria that were independently verified. Although funds were used to bolster the financial position of the BDIF, they alsoresulted in the financial strengthening of the institution as well as enhancing its institutional capabilities. This could be avaluable lesson for World Bank operations directed at supporting deposit insuranceschemes.In the design of projects in which disbursement depends on achieving DLIs, it isimportant to consider the implications of indicators, the achievement of which are beyond the direct control of the borrower. InBulgaria, the process of bankruptcy of KTB had to go through the courts, which led to delays in its liquidation and recovery ofassets. This is an issue that needs to be considered at the preparation stage of the project.IEGoffers an additional lesson:The importance of continuity in project teams is often overlooked. Continuityensures that confidence is engendered and that unforeseen issues that inevitably arise during the course of a project can beresolved in a timely manner. In Bulgaria, continuity of the project team contributed substantially to the successful completion ofthe project.
P154253 | Human Development Service Delivery Project | Latin America and Caribbean | St. Vincent and the Grenadines | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2024 | 2025 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099110824132515498/text/P154253-14d27634-ee9d-4bc0-b62b-7bc395248fac.txt | https://documents.worldbank.org/curated/en/099110824132515498/pdf/P154253-14d27634-ee9d-4bc0-b62b-7bc395248fac.pdf | The ICR provided important lessons and recommendations, including the following lessons restated by IEGReview:Multisector operations face difficulties due to the complexities associated with working with severalimplementation agencies. In the case of small countries, multisector projects are often necessary in order to achieve economies ofscale. However, this type of design brings challenges linked to having several agencies, each of which requires dedicated focalpoints who can ensure adequate implementation of project activities and can coordinate with a central project unit. Sectoralownership of project activities, clear and specific terms of reference, and a well-prepared operations manual can contribute tomitigate these issues.Well-designed indicators are critical in the assessment of project objectives. In the case ofthis project, indicators were not realistic as they depended on the implementation of a number of activities that were not ready atthe time of project launching. This is the case of the CLASS assessment tool for objective 1, and the dependence on the eCPAtargeting tool for Objective 2. In addition, a baseline could not be prepared and indicators did not rely on existing institutionaldatabases.Institutional development contributes to sustainability, but reforms associated with changes in the frameworkmay be difficult to achieve through an investment operation. This project supported important reforms in the Social Protection andLabor sectors, including the PAP Act, the Disability Act, the Elderly Act, and the Protection of Employment Act, as well as theLabor Relations Bill, aiming that they be reviewed by Cabinet and/or be tabled in Parliament. Although development of legaldocuments is technical and can be supported by a project, approval processes are usually political and, therefore, beyond the scopeof the project.
P154263 | Local and Regional Competitiveness Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099040323135030953/text/P1542630e058e604b0b7ff0181021313f67.txt | http://documents.worldbank.org/curated/en/099040323135030953/pdf/P1542630e058e604b0b7ff0181021313f67.pdf | Three lessons are drawn from the ICR (pages 29-30), with some adaptation.Complex project design withinter-dependent project activities, diverse infrastructure types, and numerous implementing entities with varying capacities maymake project implementation difficult. The design of this project was overly complicated. Many projectactivities were finely interlinked- some activities could not be initiated without other activities being completed, somecould not even bepreciselydefined without the products and results of other activities being delivered. Inparticular, the activities under the second project component were dependent on activities under the first project component.Many activities required collaboration between the government and various sets of private stakeholders, but consensus-buildingtypically takes time and effort. Infrastructure sub-projects could be proposed by regional development centers,municipalities, and other public entities. Tourism services and linkage and innovation sub-projects could be submitted bybusiness associations, training and educational service providers, civil society organizations, destination managementorganizations, and micro and small private enterprises. The sub-project beneficiaries had limited capacities in variousaspects of project design, implementation, and supervision. Clearly defined and streamlined project activities, focusedinvestments, and selectivesub-project beneficiaries would have made fora projectthat was easier to implement andcomplete.The choice of a political body rather than a line ministry or a sector agency may complicateproject implementation and may not create institutional development gains via the project experience.In thisproject, the Cabinet of the Deputy Minister for Economic Affairs was selectedas the implementing agency by the Government andthe Bank. The performance of the implementing agency was cramped by several challengesowing to the politicalfocusof the Cabinet, according to the ICR. There were four Deputy Prime Ministers for Economic Affairs over the six-year life ofthe project. Each election cycle (there was a presidential election in 2019 and parliamentary elections in 2016 and 2020)stalled project activities. The staff was limited as well, causing delays in decision-making. Overall, clearancesrequired for project activities were delayed. While the ICR admits that the project experience was valuable totheCabinet of the Deputy Minister for Economic Affairs, greater institutional development gains would have been realized withthe selection of a line ministry or sectoral agency as the project implementing agency.Tourisminfrastructure sub-projects designed for local sites, requiring regulatory clearances and permits, and involving local agencies ofvarying capacities would require a longer time periodto implement.The original four-year implementationtimeline was not sufficient for the class of sub-projects planned for this operation. Infrastructure sub-projects in selectedtourism destinations would take time to design, contract for, and construct. Moreover, it would take time to secure permitsfor sub-projects in cultural heritage sites, considering both the nature of cultural tourism and the cumbersome processes that tiedup the regulatory system.In practice, for several cases, it took more than a year toobtain permits forsub-projectsin cultural heritage sites. Disruptions caused by the COVID-19 pandemic would aggravate the problem oncethe sub-projects slipped into 2020. The ICR also faults the restructurings for the short time periodsby which theproject was extended at each restructuring.
P154291 | Indonesia Energy Sector DPL | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2016 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099310012082213133/text/P154291078fc0c0ca0b66f09a3ffceb7617.txt | http://documents.worldbank.org/curated/en/099310012082213133/pdf/P154291078fc0c0ca0b66f09a3ffceb7617.pdf | The design of DPL series should recognize risks arising for political cycles that could result in changes in priorities aselections approach. In the case of Indonesia, the change in priorities in mid-2016 compromised the successful completion of theseries. Under circumstances when political priorities might change, the prospects for sustainability could be increased by briefingParliamentary committees on the reforms. Alternatively, a less ambitious reform program or one spread out over a longer period oftime could increase chances for successIn large middle-income countries that have access to internationalcapital markets, leverage associated with conditionality in a DPL series may not be strong. The size of a DPL relative to thegovernment budget is relatively small and alternative financing is available so that the incentive to reform in order to obtain theloan is not as great as it is in smaller countries. It is therefore incumbent upon DPL teams to ensure to the extent possible thatthere are clear prospects for completing the reform program. In Indonesia, reform enthusiasm was initially strong but waned asreforms proceeded because of political issues and inter-ministerial rivalries.When designing programs thatrequire complex implementation, a clear line of responsibility is highly desirable. The complex implementation arrangement inIndonesia, where two ministries were responsible for the overall program, while a third was responsible for technicalimplementation hampered overall achievements.When prospective reforms require substantial changes toexisting arrangements and responsibilities, which might be strongly opposed by vested interests, a longer time horizon for reformmight be desirable. In Indonesia, the program was confronted by opposition to a number of components of the program, particularlywith respect to implementing a performance based regulatory system for PLN.
P154299 | First Programmatic Energy and Water Sector Reforms DPL | Middle East and North Africa | Jordan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2016 | 2017 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/532471561641076061/text/Jordan-JO-Energy-Water-Sector-Reforms-DPL.txt | http://documents.worldbank.org/curated/en/532471561641076061/pdf/Jordan-JO-Energy-Water-Sector-Reforms-DPL.pdf | The ICR derives the following key lessons from the DPLs preparation and implementation experience (withsome paraphrasing by IEG):Debt and cost recovery need to be monitored in both the energy and watersectors when these are interdependent. Persistent deficits could become debt and beshifted around institutions (in the case of Jordan, from NEPCO to WAJ, and from WAJ to MOF). This deficit accumulation andconsequent debt shifting needs to be monitored carefully across all the institutions engaged in reform processes to understand howreforms in one sector impact on the reforms on other sectors and adjustaccordingly.Automatic policy correction mechanisms can help avoid future financialgaps. The First DPL helped achieve financial sustainability in the electricity sector through tariff increases, import ofcheaper LNG fuel, and the fall in global crude oil prices. Without the automatic electricity tariff adjustment mechanism (AETAM),the rapid increase in global crude prices in 2018 could have adversely affected the financial viability of the sector. The AETAMautomatically triggered the regulators monthly tariff review, resulting in a fuel price increase in the consumer tariffs.This fuel price adjustment clause helped NEPCO collect an additional JD 257 million during 2018, thus helping the country absorbthe shock of oil prices increasing from under US$50 per barrel when the Second DPL was approved in December 2016 to almost US$85 inOctober 2018.There is a need to ensure that tariff adjustments in the electricity sector flowthrough to water sector tariffs in small increments. None of the pressure of higher electricity tariffs has been passed onto water consumers. Consequently, the municipal water services are now in a difficult position leading not only toincreased indebtedness of WAJ but also the necessity of a very large water tariff increase to return WAJ to financial equilibrium.Passing on the energy tariff increases through an automatic tariff adjustment mechanism in the water sector would have helped keepincremental tariff increases small. Achieving financial sustainability in water services will require a combination of centralgovernment borrowing to pay down WAJs more expensive debt and small but steady water tariffincreases.While weaning the water sector from subsidies in the medium-term, efficiency measuresneeded to reduce the water sectors energy intensity and non-revenue water. Good starts for reducing energy costswould be to replace old inefficient pumps and introduce renewable energy into the water sector. The water and energy sectors needto identify further synergies such as: (i) directly connecting water pumping stations and other heavy power loads to the grid; (ii)time-of-day pricing for water pumping; and (iii) increasing water storage to reduce the need for 24/7 pumping. To harness thesesynergies, detailed technical analysis and planning required based on improved data on water sector energy use. Technical expertsare needed to facilitate this cross-sectoral dialogue and generate a series of projects that could be outsourced as performancecontacts. At the same time, there is a need to ensure that efforts to address subsidies do not actually led to the rise ofcross-subsidies.To address financial sustainability gaps, cost reductions in the energy sector needto complement tariff increases. The financial sustainability of Jordans electricity sector was achieved through acombination of tariff increases and cost reduction efforts. To ensure that costs do not rise again, it is essential to continuefocusing on minimizing costs through least-cost investment plans, allowing competitive pressures, giving proper economic signals toproducers as well as consumers to manage demand, and diversifying supply sources for energysecurity.Policy reforms in the electricity and water sectors are lengthy processes spanning severalyears and requiring multiple policy interventions. The DPL series built upon the earlier reforms in the energy sector tounbundle the vertically integrated sector, set up the regulator, promote private sector participation in generation anddistribution, and enable renewable energy generation.This DPL series was followed in June 2018 by the First EquitableGrowth and Jobs Creation DPL, which aimed at policy reforms to address high cross-subsidies in the electricity sector. TheGovernment and the Bank are finalizing a five-year reform matrix which, in the energy sector,would continue toaddress the high cross-subsidies, and meet the need for (i) open access to the grid network given the rapidly falling global costof renewable energy, (ii) strengthening regulatory practices, and (iii) enhancing energy security. In summary, a multi-stage policyreform process across multiple operations is characteristic of improving basic service sectors such as energy and water.
P154387 | Vietnam: Project for Improved Land Governance and Databases (VILG) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099061224122518009/text/P154387-eecdb9cd-dc55-45b1-9d46-a6af2a2ac466.txt | https://documents.worldbank.org/curated/en/099061224122518009/pdf/P154387-eecdb9cd-dc55-45b1-9d46-a6af2a2ac466.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Land administration is not the sole factor driving land markets. Although accurate,integrated and unified land information can assist land administration officials in processing requests and resolving landdisputes, the lesson from this project is that improved land administration is not the sole factor driving land markets and thatincreases in land transactions and related land markets are dependent on multiple factors, including trends in the economy and thereal estate market.2. A longer term evaluation covering both project and non-project areas, may help in measuringthe efficiency aspects of land administration projects. In this project, the MPLIS only became functional in 2022. Thismade it difficult to measure the efficiency aspects of the project.3. A careful assessment of the sub-nationalentities may raise the potential for success in projects.In decentralized structures, with different capacities,finances, strengths and weaknesses, different modes of engagement may be required. The lesson from this project is that differenttechnical assistance and lending arrangements may be required in projects entailing sub-national entities, taking into accounttheir experience and capacity.
P154389 | Myanmar Financial Sector Development Project | East Asia and Pacific | Myanmar | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099112123191023930/text/P15438905213e60b60bfb804c00b3728bc6.txt | http://documents.worldbank.org/curated/en/099112123191023930/pdf/P15438905213e60b60bfb804c00b3728bc6.pdf | The following are lessons learned from the ICR with some paraphrasing: Up-front incentives can ensure aconsistent and timely disbursement of funds by the Borrower. The ICR reports that in the case of the project thedisbursements lagged due to two reasons (apart from the from the mismatch of fiscal year endings and the MOPF financial rules).First the commitment charge to be paid by the Borrower calculated on the undisbursed amount was reduced to zero. This guaranteed nocost for the Borrower for not withdrawing the funds until they are needed. Second, the service charge was determined equal tothree-fourths of one percent per annum which was represented a higher cost for the Borrower than the option of not withdrawingfunds and relying on its own resources. For these reasons, the measures adopted through the restructuring (expanding EEPs andextending implementation period) did not help the lag in disbursements. Discussing these issues during the project preparation inadvance can help adapting the project and improve project results. Monitoring financial access in terms oftraditional and mobile/digital finance via separate indicators can help better understand the sources of enhanced financialinclusion. In the case of Myanmar project, the PDO indicators were formalized in a way to cover trend in financial accessstemming from both traditional and mobile banking improvements. Monitoring the parallel development in financial access throughtraditional and digital banks can provide a clearer picture of the vulnerability of the current trend of financial access as wellas the contributors to the change.
P154422 | Mozambique Eleventh Poverty Reduction Support Credit | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2018 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible |  |  | It is easy to be beguiled by strong country economic performance and assume that policy integrity exists where it mightnot. Extensive in-depth analysis of political economy issues should be an integral part of DPL program design. Caution iscalled for before basing program design and policy actions on the doing business indicators. In this case, reforms to promoteprivate sector development should have focused on the misuse of Mozambiques capital stock by its SOEs, not on the number ofdays to start a business. A comprehensive private sector assessment should be the basis on which private sector development reformprograms should be based. Implementation capacity constraints should be meticulously evaluated and incorporated into DPOprogram design (ICR, 38-9).
P154447 | Smallholder Agriculture Development and Commercialization Project | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099102723090012476/text/P154447024ca9d0db08fca01f73a0c304a2.txt | http://documents.worldbank.org/curated/en/099102723090012476/pdf/P154447024ca9d0db08fca01f73a0c304a2.pdf | The following lessons are derived from the ICR with some modification of language.Several lessons emerged from theexperience of organizing Farmer Field Schools. Calibrating training to build on participants knowledgeby assessing what they already know can help in more effective use of training resources. During the early post-war years,Angolan farmers had limited skills. Therefore, the training dealt with the basics andwas sufficiently long. However, as theknowledge of basics became more widespread among farmers, the FFS training wasnt suitably modified and shortened to enablemany more farmers to complete basic training to graduate to advanced issues. Paying attention to buildingin-house capabilities while using a third party to provide training can increase the chances of sustaining training activitiesbeyond the life of a project. FAO provided technical support for organizing FFS, which included training the trainers inthe ministry. IEG was informed by the Bank team (09.13.23)that the government staff established 600 FFS on their own as partof the training. As a result, the government can now organize FFS in the follow-up project without the support ofFAO. Complementing training of farmers in improved agricultural practices with interventions that help themgain access to inputs can improve their chances of adopting the practices they have learned about. The farmerswho benefited from only training raised their yields by about 40 percent. But those that received support harvested nearly 80percent higher yields.In low-capacity environments where the absence of required skills is anticipated, anupfront investment to address them can reduce or eliminate the risks of implementation delays. In this project, delayswere expected because of a shortage of specific skills, but a decision was made to address them as they arose. The strategy failed.An upfront investment, which might have proven unnecessary, would have paid off through the timely execution of project activitiesand compliance with the needed safeguards.Where technical capacity within institutions is weak, implementingsmall-scale, low-tech options, if available, is superior to embarking on more extensive, complex options that demand institutionalcapacity. Supporting small-scale irrigation investments such as in pedal pumps that farmers managed individually workedfine. Building larger systems requiring data analytical capacity and involving contracts to build and maintain was lesssuccessful.
P154464 | Second Municipal Services Improvement Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099112423170518938/text/P15446403660cb09e096fa04376e8dc58c8.txt | http://documents.worldbank.org/curated/en/099112423170518938/pdf/P15446403660cb09e096fa04376e8dc58c8.pdf | The ICR (p. 26-27) included several lessons learned which were adapted by IEG: A demand-driven designallows for flexibility and limits the possibility to define indicator targets during project preparation. Therefore,ensuring that the Results Framework is being revised once the targets are known is important for being able to monitor progresstowards achieving the projects objective. Making grants available to municipalities which do not accesssub-loans allows to provide financing to poorer municipalities with lower borrowing capacity. This project made an effortto include poorer and vulnerable communities by requiring grant-financed investments to focus on their needs. In general, similarprojects might benefit from also making grants available to municipalities with lower borrowing capacity if they meet some criteriasuch as, for example, capacity to cover subsequent operation and maintenance costs. Carefully assessing politicaland governance-related inherent and residual risks on the national as well as the local level might positively impact projectimplementation. In this project, unplanned parliamentary elections and an extended period of political instability andclear leadership in the central government resulted in the Bank deciding to postpone the projects effectiveness resulted ina slowing down of the implementation pace and the need for an extension of the closing date.
P154523 | Technical Education Quality Improvement Project III | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050009102210463/text/P1545230ea50e907d08a030852c0808c081.txt | http://documents.worldbank.org/curated/en/099050009102210463/pdf/P1545230ea50e907d08a030852c0808c081.pdf | The ICR (pp. 26-27) highlights a number of useful lessons, some of which are summarized here:Feasibilitystudies and technical assistance, together with convening support and favorable political economy conditions, can facilitate reformin challenging areas such as faculty hiringin higher education. In this case, project support for a detailedexamination of the current status of faculty shortages, drivers of faculty vacancies, implications of faculty shortages for qualityof education, and solutions for addressing faculty vacancies provided a sound foundation for developing a menu of options topresent to states.Demonstrated positive outcomes in previous projects can be used decisively to generatereceptivity and momentum for further innovations and reform. In each successive phase of TEQIP, new innovations built onsuccesses of the previous phase. TEQIP III built on progress in improving quality in participating institutes (accreditation andautonomy) to reinforce the need for clear accountability and reliable data, leading to the introduction of a student learningassessment system.
P154524 | Pakistan: Third Punjab Education Sector Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IBRD | IPF | 2016 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099081023103038905/text/P1545240cff99709b08ea301e8d6818ee81.txt | http://documents.worldbank.org/curated/en/099081023103038905/pdf/P1545240cff99709b08ea301e8d6818ee81.pdf | Long-term engagement with a client can secure results in a sector such as education.Investments in education are long-termendeavors and, as such, require substantial commitment and availability of resources.This project came after a DPF series andtwo investment projects, allowing the client and the World Bank to build on prior interventions and learn from priorexperience. Results-based lending allows teams to focus on outcomes instead of processes, but it requiresrobust information and fiduciary systems. This operations model relies on government systems to procure, contract, and delivergoods and services. Management and information systems must therefore be in place and operate under clear accountabilitymechanisms.Private schools provide a means to increase access in an environment of substantial population growth, butaccountability is important. As observed in this project, low-cost private schools tend to cater to poor children,performwell, and serve vulnerable groups (such as girls).However, these schools need to be accountable to authorities by allowingregular monitoring and student performance assessments.This is not always the case. As reported for this project,private schools do not always allow government authorities to enter premises.
P154577 | College Education Development Project | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099110524175022574/text/P154577-3e182eed-2e85-4a79-ad25-fd727e25e2c2.txt | https://documents.worldbank.org/curated/en/099110524175022574/pdf/P154577-3e182eed-2e85-4a79-ad25-fd727e25e2c2.pdf | The ICR provided insightful lessons including those below:When engaging for the first time in a subsector,simple and realistic project design can enable smooth implementation. As a first operation in the college subsector,project design incorporated targeted interventions for system and institutional capacity building at the national and collegesubsector levels. Sufficient time needs to be built into a project to allow for engagement and consultations among manystakeholders undertaking new strategic-level and management activities to achieve project objectives.Establishingproject leadership and the PMU in a timely manner enables implementation readiness. During preparation, the riskassessment for institutional capacity for implementation and identification of mitigation measures can help ensure readiness.Dialogue with the Government on implementation readiness could include, for example, consideration of assignment of a projectleader from the Government before approval. This can enable timely staffing of the PMU with the requisite technical expertise andcommencement of project activities.Continuous hands-on support for capacity building can enable successfulimplementation of new activities. The Institutional Development Grants provided to 120 colleges supported newactivities including goal setting, planning, implementation and reporting. When there is a lack of experience for implementation,scalable on-the-ground capacity building, training, and rapid response are essential throughout project duration for institutionaldevelopment and successful implementation.
P154621 | China: Guangdong Compulsory Education Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial |  |  | Lessons drawn from the ICR (page 22) and adapted by IEG: Equipping classrooms with ICT can be aneffective intervention to improve teaching if the technology enables teachers to better execute their daily tasks and provides themwithadditional resources to engage students. Teachers also need to be trained in the use of the technology to ensureutilization in their classroom environments. Also, technology that is available in the local market helps improve sustainabilityand ensures availability oflocal technical support. Evaluations of critical project activities need to bewell considered during the appraisal stage to ensure opportunities to gather robust baseline data and proper evaluationdesign.In the case of this project, the different types of teacher training (i.e BBT vs. backbone teachers) requiredevaluating different dimensions of teacher practices. Also, piloting of the instrument in the local context would have helpedunderstand the baseline distribution ofpedagogical practices and set meaningful targets. Lastly, the key pilot activities onequity were not clearly delineated and therefore were not carried out effectively.
P154623 | China: Gansu Technical and Vocational Education and Training Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2017 | 2023 | 2025 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | https://documents.worldbank.org/curated/en/099083024163534769/text/P154623-d0eeb436-a5f2-425e-9cc2-9be37444ce08.txt | https://documents.worldbank.org/curated/en/099083024163534769/pdf/P154623-d0eeb436-a5f2-425e-9cc2-9be37444ce08.pdf | The ICR (pp. 31-32) offered several lessons and recommendations, including the following lessons restated by IEGReview:The establishment of a Skills Council, includingtechnical experts fromindustry and key teachersfrom universities, can beinstrumental in improving the correlation between the skills demanded by enterprises and thoseprovided by TVET schools, and in advancing the shift from a supply-driven approach to demand-driven delivery. Underthisproject, the Skills Council promoted TVET coordination and management for pursuing the above directions, and it conductedanalytical and research studies on current needs of enterprises to guide schools in adjusting their courses and in optimizing theirtraining programs. The Council provided guidance to project schools in responding rapidly to new skills demands fromenterprises.The designation of a focal point to provide continuous technical support, expertise, and promptadvicefacilitates the implementation of school reform activities, as was undertaken by thisproject through thecontracting of anexperienced school reform consultant.The collective experience of the series of TVETprojects in China can provide valuable guidance to the design and implementation of future TVET projects. The projectpreparation team visited locations of similar projects in Yunnan and Guangdong Provinces to observe first-hand, learn, andinternalize lessons, including on close school-industry linkages. The cross-fertilization in the design and implementation ofprojects across provinces provided a virtuous cycle of learning from experience while adapting project design to local conditionsand introducing innovations.This IEG ICR Review also identified the following lesson:Institutionalizingsustainability planning in TVET schools can contribute to reducing the risk to development outcome. The project providedtechnical assistance to support the preparation of Sustainable Development Strategies by each of the project schools. Four workinggroups of 15 members each were established to identify opportunities and challenges faced to achieve sustainable development and todesign corresponding responses at the institutional and policy levels through a consultative process. The project was the firstWorld Bank-assisted TVET project in China to plan for sustaining the impact of its outcomes. Sustainable Development Strategiesintegrated institutional, organizational, and operational arrangements, and aimed to ensure that capacities to developcompetency-based curricula, reforming teaching methods to be student-centered, performance assessments, and project outcomes aresustained and expanded.
P154669 | Innovative Financing for Air Pollution Control in Jing-Jin-Ji | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | PforR | 2016 | 2022 | 2023 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099052923141042820/text/P15466902b23a90e509b8c08d28e570617f.txt | http://documents.worldbank.org/curated/en/099052923141042820/pdf/P15466902b23a90e509b8c08d28e570617f.pdf | The ICR (pages37 to 38) lists several lessons from which IEG derives the following lessons that are relevantforsimilar projects implemented in comparable environments:1. Success of the PforR Programrested upon the Governments strong commitment and effective action plans: The mitigation of air pollutionon such a large geographical scale necessitated strong commitment from the government which maintained the responsibilityfor identifying priority areas and issuing policies and regulations. The sustainability of the commitment was alsocritical. The PforR financed a time slice of the governments program (APPCAP), its design being conceived during thefirst phase and its implementation period coinciding with the second phase of that program, with a third phase extending wellbeyond the time horizon of the PforR. The government program provided a stable policy environment for RE, EE and airpollution abatement projects in China, as well as for the PforR itself. The governments action plan on air pollutionprevention/control set clear targets which were helpful to achieving effective reduction of GHG emissions under theProgram.2. PforRs can be effective instruments for supporting the short-term financingneeds of government programs as well for strengthening the institutional capacity needed to assure their longer-termsustainability. PforRs can balance the twin dimensions of financing investments and supporting policies and reforms, whichwould otherwise need to be handled separately through IPF and DPO instruments. PforRs link funds disbursement to resultsachieved, and the DLIs can be designed to take into account both short-term results and longer-term institutional reform. Inthis way, the Program supported strengthening of HXBs capacity to design and deploy innovative green financing products,with a view to mainstreaming green finance in HXBs portfolio. This allowed the impact of the Program to be enlargedsubstantially.
P154672 | Hebei Air Pollution Prevention and Control Program | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | PforR | 2016 | 2020 | 2021 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/314981613570798833/text/China-Hebei-Air-Pollution-Prevention.txt | http://documents.worldbank.org/curated/en/314981613570798833/pdf/China-Hebei-Air-Pollution-Prevention.pdf | The ICR draws the following three lessons from the experience of implementing this PforR operation.1. A robustresults framework and robust mechanisms for monitoring are key to realizing results in a PforR operation. The PforR wasapplied for the first time in Hebei for managing air pollution in cooperation with government agencies. Linking results toindicators that were verified by external third parties enhanced the effectiveness of fiscal spending, besides increasingtransparency and accountability.2. Solid analytical underpinnings based on scientific knowledge can ensure successof the PforR instrument. Manydisbursement-linked indicators in this operation were based on thesource apportionment study that identified the sources of ambient air pollution and quantified their contribution to air pollution.This provided the scientific basis for choosing the relevant disbursement linked indicators.3. Capacity buildingforpreparing the Terms of Reference to the government counterparts prior to the start of implementation can help in avoidingdelays during implementationfor a PforR operation. In this operation, while the governments program progressedas planned, issues associated with Bank disbursements were mainly due to issues associated with third party verification ofresults.
P154702 | Kazakhstan Programmatic Development Policy Financing | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/212611528407090438/text/Kazakhstan-Kazakhstan-Programmatic-DPO.txt | http://documents.worldbank.org/curated/en/212611528407090438/pdf/Kazakhstan-Kazakhstan-Programmatic-DPO.pdf | IEG draws the following lessons.First, a successful DPO strikes acautious balance between plugging afinancial gap and advancing a quality reform program. Some elements of the adjustment plan may not have securedfirmpolitical commitment from the Government, as evidenced by the deferral by the Government of VAT reform, and the backtracking by theNBK on capital hikes and consolidated financial reporting by banks. The social protection objective lacked a prior action.Second, the design of a successful DPO series anticipates roadblocks that may derail the preparation and approval ofsubsequent operations in a programmatic series and tries to ensure that the commitment to continue with future stages remainsstrong. Notwithstanding the cancellation of the second operation, the Governmentpursued a number of measures related tothe NFRK that would contribute to a reduced non-oil fiscal deficit in the future. Similarly, the NBK made progress withmeasures planned under the proposed second operation to improve the central banks open market operations and strengthen themonetary policy transmission mechanism.Third, political economy dimensions need to be fully considered when designinga reform program. In this case, for example, vested interests effectively blocked several dimensions of the banking sectorreform. To address this, it is often useful to conduct a political economy analysis at the preparation stage and to consultextensively with affected parties regarding the content of the reform program.
P154782 | Indonesia National Slum Upgrading Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061224141512330/text/P154782-59b8b95f-438b-4f2d-9716-53af5b38d5ba.txt | https://documents.worldbank.org/curated/en/099061224141512330/pdf/P154782-59b8b95f-438b-4f2d-9716-53af5b38d5ba.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Effective planning tools and technical capacity on the ground may raise the potential for success ofcomplex integrated infrastructure projects. This project aimed at slum upgrading operations with national coverage. Theactivities required a network of community facilitators with technical skills and planning tools.The project benefitted fromthe earlier urban programs in Indonesia, which left a legacy of tested project architecture, an effective Management InformationSystem (MIS) and a network of skilled field-based facilitators.2. The sustainability of slum alleviation agendamay require a long-term incremental and adaptive approach. The project achieved its objectives by gradually shifting theresponsibilities to local governments. The lesson from this project is that while the central government still has a critical rolein sector policy, strategy and monitoring, assigning the responsibilities to local governments may raise the potential forsustainable outcomes.3. Community participation can help in enhancing ownership. This project employed aparticipatory approach, by allowing communities to engage actively in the decision-making process during planning, designing andconstructing infrastructure in slums. This inclusive approach ensured that the diverse needs of the community wereaddressed.
P154784 | Kenya Climate Smart Agriculture Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100324130020547/text/P154784-b6f6a484-afb7-4184-9e99-35e6daf20935.txt | https://documents.worldbank.org/curated/en/099100324130020547/pdf/P154784-b6f6a484-afb7-4184-9e99-35e6daf20935.pdf | The ICR included six lessons. The following three are emphasized with some adaptation oflanguage:1.Creating successful connections between the community and national levels is a critical elementof project designto ensure its success and longer-term impact.An important feature of the KCSAP design was thecombination of the community level component (component 1) and the components serving the development of a national level ecosystem(component 2 and 3). This approach not only allowed for an effective diffusion of nationally generated knowledge though local levelnetworks, but also to reach beneficiaries beyond the selected ward and counties and the national strategy overall. It also createdsome foundational infrastructure at the national level which now feature in the continuing National Agricultural andRural Inclusive Growth Project and the Food Systems Resilience Program and which enable a more rapid scale up of the activitiesalready initiated under KCSAP. This includes the big data platform and the farmer registry.2. An MEdesign with a comprehensive set of indicators is key tobetter assess the multidimensionality of resilience building andincrease understanding of impact pathways.While the ME was based on large number of intermediate indicatorswhich enabled the tracking of the progress of the implementation of the project, more attention could have been given to resilienceindicators. The PDO outcome indicators rely on some core assumptions regarding the impact of adoption of TIMPs on resilience. Itwould have been useful to more thoroughly articulate the causality between the adoption of TIMPs and increase in resilience, and toexplore if other proxy measures for resilience could usefully have been adopted. While an increase in productivity is one indicatorof increased resilience, the project could have identified others to include so that there could be a more multidimensionalapproach to resilience building to help strengthen the monitoring/assessment of resilience.3. A flexible andadaptable project design allows an adequate response in a changing implementation environment and increases the efficacy ofimplementation. The experience of KCSAP demonstrated thatsome small changes in the way the project was implementedallowed it to vastly increase its reach and disbursement efficiency. Increasing the project reach benefited from the training oflead farmers, which was a key feature adopted during project implementation. Also, to address disbursement constraints in thecontext of the multiple layers created by the devolved nature of the government,the World Bank team created a flow of fundframework. This approach is applied in other World Bank projects not only in agriculture but also in othersectors. Similarapproaches could also be relevant in other countries with devolved governments.
P154803 | Malawi Floods Emergency Recovery | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099725012232121349/text/Malawi000Malawi0Floods0ERL.txt | http://documents.worldbank.org/curated/en/099725012232121349/pdf/Malawi000Malawi0Floods0ERL.pdf | The ICR (paragraphs 85-99) provides a number of lessons learned from the projects experience. The following lessons areemphasized with some adaptation of language: Design of emergency operations may benefit from being informedby a Post Disaster Needs Assessment (PDNA). In this project, the PDNA provided a sound technical basis forpriorities that focused on livelihood supportand the medium- and longer-term recovery needs. In addition, project designincorporated time-bound aspects in implementingthe livelihood support activities (Input for Asset (IFA) program), and otherimmediate/short term interventions to facilitate the management of supervision resources, better structure delivery mechanisms, andminimize the risk thatresources may not reach its intended beneficiaries on time. AninheritedProjectImplementation Unit (PIU) may benefit from a reassessment of needs of an emergencyproject.While an established PIU is beneficial during early implementation, it is critical to conduct capacityassessment of the PIU to ensure efficiency in implementation. This includes:(i) assessingneeds against available staff andresources toidentifygaps orexcess capacity; (ii) developing staff performance evaluation protocols; and (iii)establishing a system of competitive rehiring after a year of implementation similar to establishinga newPIU. Establishing a safeguards steering committee may be useful to oversee large sector or high riskprojects to strengthen safeguards compliance. A safeguards steering committee could provideoversight,establishaccountability and mechanisms for redress, bolster ownership, and facilitate adequate resourcing of correctivemeasures, when needed. Specific lessons to address Gender Based Violence (GBV) in labor-intensive constructionworks: Indesigning livelihood programs (such as Input for Assets (IFA) used in this project)usingeconomic and entrepreneurial interventions that empowerwomen and communities may be useful. Targetingfemale participationmayreduce exploitative relationships that tend to develop when there is aninflux of both menand womenin labor intensive construction works. In this project, GBV service providers engaged and trained mothers in thecommunity on GBV issues to buildtrust. Empoweredcommunities may better understand rightsand opportunities forservices and redress. Use of technology may supportconfidentiality and reducethe stigma ofreporting GBV incidents. In this project, survivors showed more confidence and appreciated the convenience of reportingincidents using cell phones publicized by GBV providers or virtual meetings.Technology may reduce the riskfromdouble-punishment faced bywomen who report incidents. Women who reported GBV incidentswereostracized for causingwork stoppages,loss of income for workers (both men and women). The Grievance Redress Mechanismwas not trusted. Greater vulnerability and risk for GBV incidents prevailed. Othermeasuresmay needto address GBVreporting and safeguards compliance to avoidan incentive to remain silent, individually and asacommunity. Fostering community engagement and GBV awareness early and often. In thisproject, reported GBV incidents were correctedthrough measures directed at contractors (e.g.,translatedanddisseminated improved codes of conduct).Engaging the community at project preparation mayprovidea good understanding of the rights of individuals and the communityinpreventing GBV in the work place byidentifying tools and services available to victims and the community, andeffective use of the grievanceredressmechanism. Periodic reminding ofrights, services, and options to communities may foster trust in these tools and servicessuch as assigningfemale volunteers and leadersto signal that women have a role in the community not only inparticipating inlivelihood interventions, but also in monitoring,and resolvingincidents.
P154805 | Power Distribution Development Program-for-Results | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | PforR | 2016 | 2020 | 2022 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/415611630075756217/text/Indonesia-Power-Distribution-Development.txt | http://documents.worldbank.org/curated/en/415611630075756217/pdf/Indonesia-Power-Distribution-Development.pdf | This was the first PforR program in Indonesia. IEG derives the following lessons drawn from the ICR:1.A clearly defined scope and program boundary are important to the achievement of the programs outcomes.When a PforR supports a portion of a larger government program byselecting a sub-program, it is important for programdesign to clearly define its period of support and outline the boundaries and geographical focus. The ability of the currentProgram to define areas of intervention and activities that could realistically be achieved given the implementationcapacity of the client - was key to its success. Clearly defined Program boundaries and results areas, and identification ofkey activities linked to disbursement incentives, established a clear operational logic, which was an important factor guidingProgram implementation.2.Key prerequisites for the success of a PforR operationare strongleadership and alignment of Program design with the clients internal organization. Strong leadership wouldensure a streamlined decision-making process on strategic aspects during Program design and on any issues arising duringimplementation. If Program components can be designed so as to be aligned with the clientsorganizational structure, this could additionally benefit from a faster decision-making process throughout programimplementation.3. An important feature of the PforR instrument is that it incentivizes removal of criticalroadblocks to improving Program effectiveness, efficiency and sustainability. DLIs were carefully selected toaddress implementation challenges and institutional capacity constraints, with required improvement measures included in thePAP. By linking public investments with outcomes and results involving institutional reforms, the Program made it easier forthe World Bank to get involved in sensitive and politicized areas budget planning and personnel management than would have beenpossible under traditional IPF operations.4. The success of the Program called for the close engagement ofthe Bank team and close monitoring, which necessitated greater supervision. Close monitoring and technical expertisewere required to verify the achievement of DLIs and PAPs, as well as for proper verification protocols. Duringimplementation, most supervision of the Program was country office-based, which significantly facilitated coordination with theclient, other donors and the IVA, and allowed the team to provide timely feedback to PLN through the Program period. Thisallowed fiduciary aspects to be closely monitored, training to be provided to strengthen capacity of PLN staff, and safeguardssupervision to be ramped up when needed. Close and proactive engagement by the team through the Programs restructuringensured the achievement of outcomes and maximized the disbursement from each DLI.
P154807 | Regional Disease Surveillance Systems Enhancement (REDISSE) | Western and Central Africa | Western and Central Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099101824102020324/text/P154807-49b213e3-99af-4f31-b8ba-fa189d8ae49c.txt | https://documents.worldbank.org/curated/en/099101824102020324/pdf/P154807-49b213e3-99af-4f31-b8ba-fa189d8ae49c.pdf | The ICR (pp. 44-45) offered several important lessons and recommendations, including the following lessons restated by IEGReview:Health security is borderless and can be bolstered by regional and global approaches for capacitydevelopment in preparedness and response rather than unilateral actions. Under the project, collective national actionsand regional coordination to confront the COVID-19 pandemic contributed to the ability of participating countries to cope with thepandemic, supported by the projects regional platform that facilitated joint planning and harmonization, preparedness andresponse measures, and mutualization of limited resources.The One Health approach encompassing human health,animal health and environmental aspects requires time and an enabling environment. Under REDISSE, an operational paradigmshift was needed to progressively foster collaborative work among sectors. Clarifying the roles of key institutions, encouragingcooperative learning, and opting for a phased approach of change management appeared to be better options rather than a big bangapproach to the modus operandi that each sector was following. In this context, the advancement of One Health was found to beeasier to implement at the sub-national level where governors had the authority to direct resources across sectors and to promotejoint work.Health security requires investment tradeoffs between regional and national levels, betweensectors, and between sub-national regions. Under the project,the national yearly planning exercise often became acontentious period mainly where sectoral budget contests required further reviews to prioritize annual activities, delaying thestart of implementation cycles.
P154819 | Panama Second Shared Prosperity Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2019 | 2022 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  |  |  | The ICRR concurs with key lessons that are articulated in the ICR.Strong government ownership of thereform agenda is essential to ensure the implementation and sustainability of a DPO series. Selecting program objectives andreforms that had wide public support as well as political backing helped to ensure that the necessary legislation would be passedand implemented. It was important that the legal and regulatory framework underpinning the reform program was initiated anddeveloped by the Government, with technical inputs from the WB and other development partners (ICR, p. 49). TheGovernment continued to support the PDO beyond the closing of the DPL series, in particular through a new DPO series tocarry forward actions that were originally intended for a fourth Shared Prosperity DPO but were considered too complex to beimplemented within the time frame.Simple design based on strong analytical underpinnings and technicalsupport are important for effective design and implementation of appropriate interventions. The series focused on threemain objectives that were closely aligned with the Governments Strategic Plan and priorities (as well as the BanksCPF) and had strong analytical underpinnings, rather than trying to cover an extensive array of measures (ICR,p. 50).Readiness to adapt to changing circumstances is important to ensure that the program remainsrelevant and addresses emerging challenges. The most obvious example was the inclusion of new actions (within an existingobjective) to address the challenges to Panamas international financial standing as a result of leaked documents. Targetshad to be adjusted periodically in response to monitoring the progress of implementation, sometimes to be more realistic andsometimes more ambitious.Continuing engagement beyond the series is important to sustain results byfollowing through on implementation and mitigating risks. In this case, a planned fourth DPO was instead rolled into a new DPOseries, enabling continued dialogue and actions focused on complex issues in order to deepen the reforms initiated under this DPOseries (which in turn was carrying forward some reforms initiated in previous operations).A further lesson is theimportance of technical assistance that is timely and well-targeted to addressing technical issues that arise ormay impede implementation. Reforms to address tax transparency and fiscal integrity introduced after the series had begun likely would not have been implemented so effectively without bringing in expertise from the WBG and other developmentpartners in these areas.
P154821 | CO Second Programmatic Sustained Growth and Income Convergence DPL | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons are taken from the ICR with some adaptation of language: The design and preparation ofthis DPO series benefitted from continuity with respect to Task Team Leaders and core team members, both with respect to knowledgeof the issues and the economy and in regard to relationships with country counterparts; The reform experience inColombia underlines the need for intensive dissemination and implementation to bring about changes in behavior when institutionalreform involves new laws or regulations. The use of the secured transactions reform to extend credit access is a case in point,where the initial use was primarily for financing of motor vehicles. More dissemination could have broadened itsuse IEG draws the following two lessons: Design of development policy operations canbenefit from international experience and research. In this case, expected financing of SMEs and other sub-prime borrowers throughissuing instruments such as bonds did not materialize since the risks associated with such instruments were perceived to be toohigh. Sufficient study of international experience would have illustrated the likelihood of such anoutcome. Political economy issues can often undermine reform objectives. Two examples were the difficultiesassociated with the attempted consolidation of the Committee for Competitiveness with the System for Science, Technology andInnovation, and the restructuring of the National Tax and Customs Administration, both of which undermined the achievement of thethird pillar of the program. Intensive consultation, dissemination of the advantages of the reforms, and ensuring that allparticipants support the reform are necessary to reduce the risks of non-achievement of objectives.
P154847 | Andhra Pradesh Disaster Recovery Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2022 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099041823171549255/text/P15484709f93e0053094e102487a307c801.txt | http://documents.worldbank.org/curated/en/099041823171549255/pdf/P15484709f93e0053094e102487a307c801.pdf | The ICR (p. 34-35) provided several lessons learned, which were adapted by IEG: If the projectsimplementing unit is also the entity for emergency response, then the likelihood of insufficient capacity to implement the projectwhile at the same time be able to respond to emergencies increases. During the implementation of this project, the statefaced cyclones and other emergencies resulting in lack of capacity for project implementation resulting in implementation delaysand cancellation of activities. Expanding the risk spectrum analysis during preparation allows toalso develop mitigation measures for low risks. In this project, several unexpected risks materialized such as thegovernment of Andhra Pradesh having funds flow issues, the nation-wide launch of the goods and services tax (GST), and the COVID-19pandemic, all resulting in major implementation bottlenecks. For projects with a large number ofcontracts, comprehensive and strategic procurement planning allows for timely supply of goods and services that are essential forproject implementation. In this project, the target for rural roads had to be decreased due to higher than initiallyexpected construction costs. Also, the project faced thechallenge of attracting contractors for small and geographicallydispersed works in remote areas.
P154861 | Zimbabwe National Water Project | Eastern and Southern Africa | Zimbabwe | Blend | FCS | Sustainable Development | Water | RETF | IPF | 2016 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/274211623791855169/text/Zimbabwe-Zimbabwe-National-Water-Project.txt | http://documents.worldbank.org/curated/en/274211623791855169/pdf/Zimbabwe-Zimbabwe-National-Water-Project.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. Securingadequate project financing is a key factor to enable implementing the project activities according to the appraiseddesign.Designing a project that requires financing beyond the amount approved in the projects grant or legaldocument presents considerable reputational and outcome risks. The project experience showed thatphasing the project to allowtwo distinct phases would have been a better option to achieve the projects outcomes. Also, an earlier, proactiverestructuring to align the work program with the actual financing would have allowed the team to realign the project objectives andresults at an earlier stage.2. In fragile countries, engaging directly with government institutions mayensurebuilding local capacity.Under this project, the benefits for the Zimbabwe National Water Authority(ZINWA ) went far beyond the physical investments in the growth centers. Substantial capacity was gained on procurement,connections and payment systems, social safeguards, ME, and general project management. Moreover, contrary to the perceptionof weak performance on projects that utilize country systems, the overall performance of the ZINWA staff assigned to the PIU wasnotable.3. Training the local team on the Banks operational policies is critical toidentify andavoid any violations to the these policies. It is important that the PIU has adequate awareness of the Banksoperational policies to identify and/or avoid any policy violation. Training on Bank Safeguards should be held at the outset ofprojects. Under this project, a social safeguards specialist should have been hired, even on a part-time basis, to support the PIUin the identification of potential issues.
P154875 | Somalia Recurrent Cost & Reform Financing Project - Phase 2 | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2015 | 2022 | 2024 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099111423123574481/text/P1548750451f6f0f7096dc00c2406fe7551.txt | http://documents.worldbank.org/curated/en/099111423123574481/pdf/P1548750451f6f0f7096dc00c2406fe7551.pdf | Successful state-building in fragile contexts requires a long-term, multi-phased approach that fully engages thegovernment. Full government engagement in project design led to strong ownership and alignment with the Federal Governmentof Somalias (FGS) strategies, allowing for flexibility in resource allocation and enabling the project to build capabilitieswhere the government was prepared to act. This engagement was complemented by a focus on strengthening core Human ResourceManagement (HRM) and Public Financial Management (PFM) systems, which proved fundamental for the sustainability of developmentinterventions. The use of country systems not only built institutional capacity but also served as a testing ground for otherprojects, thereby paving the way for future operations like RCRF III and sectoral projects in health and education. Recognizingthat state-building is a long-term endeavor, the project wisely adopted a multi-phased approach, allowing for significant progresseven within a five-year timeframe. This approach underscored the need for sustained, long-term support from development partners asthe government continues to rely on external funding for some recurrent costs, emphasizing the necessity for a longer-termcommitment from development partners for ongoing reforms and state-building. The use of focused DLIs witheligibility criteria can be a powerful combination to ensure ownership and incentivize reforms, but coordinated technicalassistance is needed. DLIs and eligibility criteria allowed the government to make progress at a realistic pace whilemaintaining pressure for reform. However, consistent technical assistance was required. Some DLIs were intended to incentivizereforms supported by other projects. In such cases, stronger Bank internal coordination and with different government counterpartswould be essential to facilitate the achievement of such DLIs. The use of a Monitoring Agent is an innovativeapproach to buttress credibility in country systems while building institutional capacity. The monitoring agent createdtrust in nascent fiduciary systems. The frequency of communication between the Monitoring Agent and the government helped buildstate capability and explain how to work with partners like the Bank. The Monitoring Agent also provided regular strategic andoptions papers, which benefited the CMU and development partners alike. This approach could be beneficial in other fragile andconflict-affected settings to ensure credibility and facilitate state-building efforts. Coordination amongstWorld Bank projects and with donor projects can increase impact. In Somalia, donors provide financing and support indifferent regions and different sectors, and the governments capacity to coordinate these interventions was low. Therefore,the World Bank can play a proactive role in coordinating with and informing donors of implementation progress and risks, ensuringsynergy in project design. Bank Communication and coordination with subnational governments isessential. In a conventional IPF, the World Bank engages mostly with the center and relies on the national government tocoordinate with their subnational counterparts. In a context where there is a lack of trust between the national and subnationalgovernments and an unstable security situation, this could worsen intergovernmental relationships or result in frequent delays.Therefore, the World Bank should maintain close engagement with state or subnational governments and include them in discussions and decision-making whenever possible. A communication and change management plan could further theseefforts. Intensive implementation support in FCV projects in Somalia should be adequately supported by both humanand financial resources. Due to the security challenges and the huge need for technical assistance, which is not easy toacquire, RCRF II required a supervision budget much higher than thatof a typical IPF. The resources provided by the SMPF werekey to ensuring that the Bank could carry out regular supervision missions and dedicate sufficient time and talent to provideintensive implementation support. For a project with such a broad scope and high complexity as RCRF II, it could have benefitedfrom additional staff members to support operational tasks, ME, and training.
P154908 | Livestock Development Project | Western and Central Africa | Cameroon | Blend | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099041724113520739/text/P15490813adb0a08519952177b21f38259f.txt | http://documents.worldbank.org/curated/en/099041724113520739/pdf/P15490813adb0a08519952177b21f38259f.pdf | Two of the lessons from the ICR restated with editing are as follows: Inclusion of or consultationswith, wherever feasible and appropriate, various actors whose involvement is essential to the project, has the potential to enhancetheir participation and success of the relevant components. Producer organizations struggled to obtain the 10 percentfinancing from local financial institutions required to benefit from matching grants. It was partly because the local financialinstitutions did not understand how the matching grants worked, and they were reluctant to co-finance because they felt that thetransaction cost of doing their own due diligence would be high. Following the midterm review, the problem was addressed byincluding the financial institutions in the evaluation and selection of business proposals seeking matching grants. This proved tobe effective as the process became transparent to local financial institutions and, having signed off on the proposals, they wereable to streamline the process for cofinancing.Delegating complex administrative processes to communities andproducer organizations while empowering them may nevertheless challenge their capacities to perform the necessary tasks, requiringsignificant efforts to build their capacity. The model of supporting local councils and producer organizations withmatching grants was designed to bring together stakeholders such as local financial institutions and off-takers. The beneficiarieswere required to procure their requirements using the World Bank guidelines, but many of them who were smallholders were unfamiliarwith formal processes. The financial institutions had limited engagement in the livestock sector in the regions where the Projectwas implemented. The requirement caused considerable implementation delays.
P154947 | Regional Infrastructure Development Fund | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099020624134578316/text/P1549471a7e97e0431bde01b7784d3fb165.txt | http://documents.worldbank.org/curated/en/099020624134578316/pdf/P1549471a7e97e0431bde01b7784d3fb165.pdf | The following are lessons taken from the ICR with some paraphrasing: Complementary financing terms acrossinstruments of the financing program can help quick adaptation to emergency situations such as the COVID-19 pandemic.During the implementation, PT SMI offered ERRC and PEN loans under the same fund-based profit margin mechanism, leading to directcompetition between the two programs. The PEN loan program, offering a zero interest rate, had more favorable terms compared to theERRC and was preferred by the SNGs. The ERRC could have been positioned differently and offered fee-based, with the profitmargin calculated as a fixed-sum service fee rather than as interest on the loan amount. As ICR reports, this could have addressedthe negative stigma often associated with lending and interest rates, which are culturally sensitive topics to the Indonesianpublic. If designed with modest goals, framework projects can successfully deliver proof of concept, achievetheir targets, and provide subnational governments the opportunity to think about their long-term goals. Although the RIDFproject was initially designed as a two-phase project, targets were ambitious compared to the limited implementation period,capacity constraints, and required approval procedures. This first phase project could have been framed as a pilotwith moderate goals, aiming to deliver proof of concept and encourage new borrowers. The moderate targets would have also increasedthe projects likelihood of success, as failure at this stage risked discouraging potential borrowers from considering thesubnational loan instrument. Matching the implementation period with the projects ambition level can helpimprove the projects achievements. RIDF had a short implementation period compared to projects of a similar nature.In addition, MoHAs requirement of a five-year loan tenor for SNGs based on election cycles and a lengthy internal approvalprocess severely curtailed SNGs interest in RIDF. These limitations narrowed the sectoral scope of the subprojects down tolargely revenue-generating hospitals, markets, and roads.
P154948 | National Affordable Housing Program | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099020524134012247/text/P1549481ef75c20c5197951c9f46a54f6bf.txt | http://documents.worldbank.org/curated/en/099020524134012247/pdf/P1549481ef75c20c5197951c9f46a54f6bf.pdf | Lessons in the ICR are mostly focused around the quality aspects of the housing support provided by the project (pages 28-29)and synthesized as follows:If the interests of different stakeholders are not fully considered, there is a riskthat complex housing subsidy reform goals are not achieved. The housing subsidy program piloted under the project pursuedmultiple goals including improved economic efficiency and optimized targeting of housing subsidy instruments. While the projectdemonstrated that there is a role for diversified housing subsidy instruments in Indonesia, uptake of the new program was limitedgiven the value of the existing subsidy program to different Indonesian stakeholders. For transformative housing reform goals to beachieved, a phased approach that considers the political economy may be more suitable.If a construction qualitysystem is in place, home improvement is an effective and low-cost measure to improve housing conditions for the poor. Eventhough support by the World Bank focused on a large existing home-improvement program (BSPS), the projects push for aquality assurance and quality control system during implementation was adopted as technical guidelines for the entire BSPS program,which changed the programs trajectory toward better efficiency and sustainability.If housing-qualitystandards and associated monitoring systems are in place, this may increase the potential for climate resilient andenergy-efficient housing delivery outcomes. The project aimed to build climate and disaster resilience at appraisal butlacked the monitoring system to enforce and measure progress. As part of the restructuring, the project included a focus onconstruction quality and structural integrity standards, as well as improved resilience of upgraded and/or reconstructed housingunits. This allowed for monitoring of progress towards housing quality-related goals.In addition, IEG draws the followinglesson:If effective targeting is in place, this may increase the potential that limited government subsidies areextended to the needed beneficiaries to enable shared prosperity. The projects eligibility criteria under the homeacquisition program (BP2BT) stimulated targeting reform for all other Government housing finance subsidy programs, whicheffectively extended the reach of the program to those in most need. Specifically, it allowsbeneficiaries up to the 95thincome percentile and the working member with the lowest income of the household to apply for government subsidies and benefit fromthe housing finance programs.
P154981 | Public Expenditure and Fiscal Risk Management DPF-DDO | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2016 | 2021 | 2024 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099082223092035396/text/P1549810f3dbad05e0a557084d4d6636b3f.txt | http://documents.worldbank.org/curated/en/099082223092035396/pdf/P1549810f3dbad05e0a557084d4d6636b3f.pdf | A DDO can help reduce the potential for backtracking on reforms over a longer time frame than traditional DPFs.In this case, attempts to reverse the public-private partnershipreforms did not proceed partly because of the riskof loss of the buffer to shocks afforded by the operation.This safeguard may be particularly relevant in a context ofpolitical volatility in which commitment to some reforms may be reversed.Civil service reforms can be politicallychallenging and require significant investmentsin change management among key stakeholders.In this case,insufficient analytic work was conducted prior to the operation to identify likely additional costs to subnational governments andsources of resistance.A single results indicatorcan measure the contribution of more than one prior actionto achievement of an objective, but care must be taken not to situatesuch an indicator so far down the results chain that itcan also be significantly affected by factors outside the scope of an operation. In this case, the results indicator onsubnational governments compliance with fiscal rules effectively captured the combined impact of PAs 1-3, but it also wentbeyond what the PAs alone could achieve, complicating assessment of attribution.
P155024 | Second Social Protection System DPO (SPS-2) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2016 | 2017 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The lessons are drawn from the ICR.National vision can be an overridingfactor for success. Teams need to be alert to government commitment in recommending reforms. In Rwanda, thegovernments sustained policies and financial commitment to social protection has facilitated dialogue with the Bank anddevelopment partners and created government-led policies that have facilitated ambitious forwardmovement.Early action on accountability and transparency can enhance the credibility ofpublic programs. Broad support is often necessary if a social protection initiative is to be successful. InRwanda, the introduction of an appeals and complaints mechanism, and subsequently broader accountability initiatives (socialaccountability, citizens engagement tools) helped ensure that beneficiary and other stakeholder views were mainstreamed intoproject planning and implementation.
P155038 | Andhra Pradesh 24X7 Power for All | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2017 | 2022 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | (Reference ICR paras. 67 to 72).The ICR lists a number of lessons drawn from the Projects experience thatare relevant for similar projects undertaken in comparable environments. From these, IEG (with some adaptation) derives thefollowing lessons:The Projects experience showed that, where the World Bank-financed projectispart of a larger government program, it is difficult to attribute the achievement of outcomes to the Project unless the relevantindicators are tailored appropriately. Results indicators should be precise, attributable and measurable as a specificcontribution of the Project separately from other investments carried out in the sector.Lacking a clearlydefined theory of change embedded in the Projects design, the ME system did not track the outputs of important activitiessupported under Component 2 (smart grid development in urban areas). This created a missing link between the activitiessupported and anticipated outcomes, and resulted in a missed opportunity for the Bank to be proactive when it became apparent thatthese activities would not be implemented. ME design should require the embedding of a clear theory of change with causallinks and a results chain identifying all significant outputs and intermediate results.A change in the governmentin Andhra Pradesh led to a shift in focus and new strategic goals that impacted on the ability of the Project to achieve itsobjectives. In the case of the Project, the Bank team was not successful in getting the agreement of the new GoAP topursue the original objectives. In such cases, the Bank should consider following a pragmatic approach and consider options such asscaling down the Project.The Project was Indias first WB-AIIB co-financed operation and provided anopportunity for assessing how the collaboration was carried outand how it could be improvedin future. In such cases, project completion reportingshould include a discussion of the main features of, andexperience from, the inter-agency collaboration, as this could inform replication of the collaboration in other projects.
P155066 | Third Development Policy Operation | East Asia and Pacific | Tuvalu | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099540207272246435/text/P1550660537b5a0900aad2036fdf0f97a1a.txt | http://documents.worldbank.org/curated/en/099540207272246435/pdf/P1550660537b5a0900aad2036fdf0f97a1a.pdf | In microstates characterized by high institutional and social fragility, limited capacity and resources in the public sector,and given the volatility in the Pacific Islands both economically and climatically, DPO series would benefit from narrowing in ononly the most critical issues. In the case of Tuvalu, this included, for example, ensuring that future fiscal needs will besafeguarded by revenue flows from the TTF and implementing a more realistic solution to the imminent problems and long-term issuesin the financial sector. Social sector policies could be pursued through more targeted and tailored IPFs.Rethinkingthe approach to reforming some of the highly specialized state institutions in microstates is another important lesson. A financialsector consisting of two banks and no central bank does not sustain, for example, the setting up of a fully-fledged bankingcommission and regional or subregional bodies looking into banking regulation and supervision would be more realistic. As noted inthe ICR, other Pacific Island Countries such as Kiribati and Nauru have a comparable need to strengthen banking supervision.Regional strategies have also supported supreme audit institutions in the PacificExcises on products associated with NCDscan produce a double dividend in that they can contribute towards positive health outcomes and increased domestic revenuemobilization at the same time. The flip side is that they can have negative equity impacts as the tax is regressive.Poverty-related mitigation in the short term could focus on building incentives and financing support programs for affected groups.This could also be combined with effective information campaigns about the link between the higher price of the products andassociated opportunities for support and a healthier lifestyle.In severely capacity constrained contexts like Tuvalu, theBank could undertake its own research on the impact on sales of targeted harmful products and initiate monitoring of the prevalenceof smoking, obesity, and associated NDCs. Similarly, the Bank could collect statistics for sugary beverages and other food productswith a high sugar content when these are absent and limiting the ability to measure the extent to which indicators weremet.The most recent data on poverty incidence dates back to 2010. More recent data will be needed to guide policies andmonitor progress.There is an unusual gender gap in the much higher enrolment of girls than boys in secondary education inTuvalu, which suggests that boys may be at a gender disadvantage. However, the ICR articulates gender issues as only related towomen. For example, it argues that removing secondary education school fees is likely to benefit women as there are more girls thanboys enrolled in secondary education and does not address the underlying reasons for the underrepresentation of boys in secondaryeducation.
P155086 | Local Road Asset Management Program | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | PforR | 2016 | 2023 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | If the PforR is complemented by an IPF TA, the latter may help build the capacity in the gap areas. Theimplementation of both Bridge and Road PforRs in this operation benefited from the implementation of the TA which supportedtrainings and capacity building of government agencies in the use of asset management systems, preparation of MTEPs and engagementof communities in routine road maintenance. These TA activities were essential for the achievement of the targets set in theresults framework.If trainings in the use of asset management systems are complemented by the expertstechnical guidance on the ground, this may contribute to better understanding of government officers in the practical applicationof these systems. Including targets for the use of these systems in the results framework or DLIs is not sufficient forthe achievement of those targets. This experience of this operation demonstrated that the implementing agencies benefited from theactual guidance of the technical expert provided by the Bank under one of the TF-funded TAs to help them use those systems andprepare quality MTEPs.If local communities are directly involved in the routine maintenance of local road network,this may help increase their ownership of and commitment to the roads that they use daily. This operation supportedboth the training of communities in routine maintenance and provided them with jobs through involvement of road maintenanceservices. Bceause of this, they learn to appreciate the local road network. This operation has built the communitiessense of local road network ownership and importance of road routine maintenance, which is necessary for the provision of continuedadequate routine maintenance to slow down the premature deterioration of the created or rehabilitated roadassets.If climate change risks are not properly assessed and adequate mitigation measures integrated in theoperation design, the operation may risk losing a share of the investments. An operation implemented in a climatevulnerable country is always at a risk of having its infrastructure assets tested by the climate change impacts at some point ofits implementation. While a contingency emergency response component (CERC) was not included in the operation design, the designsfor local roads and bridges were prepared as per the current national standards with Vietnamese climate guidance, meaning based onthe historic data of the past flood events. That approach minimized the scale and extent of the damages from a series of naturaldisasters in 2020, which were subsequently addressed before the closing date of this operation. But if these disasters had occurreda year or less before the closing date, the operation may have ended up with either extension to support the restoration efforts orclosing without the restoration of the damaged infrastructure that had been created under this operation. In future, eitherinclusion of a CERC and/or preparation of designs based on the modeling of future climate change impacts should be considered ininfrastructure operations climate vulnerable countries to minimize the risk of losing the benefits.
P155097 | Strengthening Social Protection and Inclusion System | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099193003142313829/text/P1550970ff58d90f60a17c007ad5c990122.txt | http://documents.worldbank.org/curated/en/099193003142313829/pdf/P1550970ff58d90f60a17c007ad5c990122.pdf | At the appraisal stage, realistic assessment of the size of the project in line with the countrys annualbudget allocationcan avoid critical implementation challenges. It is important to ensure active involvement of theMEF during project preparation to identify realistic budget allocation projections within the timeframe of the project and thebudget cycle process. Despite full commitment, project implementation was practically stalled for almostfour full years dueto lack of financial support from the government. Adequate consideration of overall portfolio challenges at theproject design stage can improve implementation. Cumbersome fiduciary procedures under Panamas nationalConstitution and frequent staff turnover, even at the technical and fiduciary levels, affected implementation severely. Thesefeatures are intrinsic to Panamas country systems and outside the control of the project. At the preparation stage, it iscritical to ensure that other financial instruments are considered, such investment projects with disbursement against results,that may reduce the burden of fiduciary procedures. Additional support from the Bank can helpachievepositive results when implementation capacity is limited. In the case of this operation, provisionofsupport for the design and implementation of the impact evaluation of the Cohesin Socialprogramyielded significant positive results.
P155118 | Second Fiscal and Economic Reform Operation | East Asia and Pacific | Samoa | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR distills five lessons: the usefulness of using DPO engagement to elevate policy issues, the need to consider carefullywhether a DPO is the right instrument, the difficulty of aligning modalities and timelines of different Bank instruments, optionsfor timelier and more systematic follow-up of past actions, and the benefits of more regular consultation with the private sector.It also offers several suggestions to address some of the issues identified. This review concurs with these lessons andsuggestions, which are grounded in the experience of this operation.This review wishes to underscore theimportance of establishing a strong logical chain, in each support area, that links the Bank-supported policy actions to theexpected development outcomes, with the key underlying assumptions clearly identified. This helps to assess the adequacy of theactions for achieving the outcomes, as well as the risks that must be managed to ensure success.
P155121 | Burkina Faso Economic Governance, GovTech and Citizen Engagement Project | Western and Central Africa | Burkina Faso | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2016 | 2022 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099081423115537685/text/P155121019e6fd0350ac060bba9aac690f4.txt | http://documents.worldbank.org/curated/en/099081423115537685/pdf/P155121019e6fd0350ac060bba9aac690f4.pdf | IEG offers the following lessons, some derived from the ICR with modifications: Focusing ontechnology and management-induced change is likely to increase the chance of success of credits/projects that support acquiring andadopting information technology and communications. To assess the results correctly the project design must ensurethat the results indicators are appropriate to measure the achievement of objectives.
P155123 | Somaliland Civil Service Strengthening Project | Eastern and Southern Africa | Somalia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2016 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099020924180518114/text/P1551231698d8a0d619df91237f837425f1.txt | http://documents.worldbank.org/curated/en/099020924180518114/pdf/P1551231698d8a0d619df91237f837425f1.pdf | Operating in environment like Somaliland requires patience, time, and resources as well as continuity.Institutional reforms in Somaliland require timelines well beyond that of a typical project, especially those that callfor legislative or executive actions. Adaptability is a virtue in such environments. Institutional reforms require continuousadaptability to changing circumstances and challenges. Extensive World Bank implementation support significantly improved thequality of project activities, their outputs, and their impacts. Limited experience and expertise in implementing agencies withlarge and/or complex procurements (for example, design and procurement of complex IT systems) resulted in multiple iterations from preparation of terms of references and evaluation of proposals to contracting vendors. Lack of continuityand predictable (in terms of timing and funding) long-term support to reform efforts significantly affected not only theimplementation of specific reforms but also their sustainability.Donor-financed salary enhancements should beintroduced with an agreed exit strategy. The CSSP facilitated salary enhancements for TMP staff. While higher salariessucceeded in attracting and retaining needed talent and motivation, they demoralized regular civil servants in similar positionsand reduced knowledge transfer to regular civil servants because of that. Donors should have worked through the tradeoffs posed bysuch salary enhancements and adopted a well-defined, enforceable exit strategy from funding higher salaries before launching theTMP-style mechanism. Clear milestones would have ensured that the government took responsibility for financing the higher salaries,including TMP recruits, under a new pay regime. Finally, the project should have ensured all staff recruited were aware at the timeof their recruitment of the exit strategy. This could have helped defuse pressure from staff to retain their higher salaries in thepost-salary reform/post-project environment.The operation would have benefitted from more time for learning.The shortened project preparation cycle meant that bringing counterparts (both PCU staff and government counterparts) upto speed on World Bank requirements and procedures occurred largely during project implementation rather than during projectpreparation. This particularly impacted the preparation of terms of reference and bidding documents, as well as in preparing bidevaluation reports, particularly for more complex procurements. For instance, the procurement process for the assessment and designof HRMIS development took multiple iterations. By the close of CSSP, the second stage contract (for the design anddevelopment of HRMIS specifications) was only being launched. Given the Somaliland environment and worldwide experience with thedesign and implementation of such electronic systems, it is likely that procurement and implementation of HRMIS will require thewhole CSSP II project implementation period and, in the case of PMIS, probably even more time. Moreover, as the project neared itsclose, turnover among the ranks of the PSRSC spiked as changes in political leadership occurred, which slowed key projectactivities, pension reform in particular. Calculating in additional time for learning in the design stage would have beenbeneficial.Future similar engagements will require stronger mitigation of low government capacity. Itshould not have been surprising that limited human resource and financial capacities would cause challenges. It hampered progresson pension reform mostly because the government was unwilling to assign dedicated, full-time staff to work on the pension reforms,opting instead to assign it to staff who continued to shoulder their prior responsibilities. Moving forward on such demandingreforms requires full-time, dedicated civil servants. The Pension Policy and Pension Law have both been through multiple drafts andremained works in progress as the CSSP closed. The Cabinet eventually approved the Law and Policy on September 21, 2023. However,considerable work remains on the design and implementation of a civil service pension system even after the follow-on CSSP IIproject.Strengthening public sector training institutes needs to focus on building capacity to design and delivera small number of courses rather than on developing many courses. A more promising approach would be to limit the numberof courses developed under such a contract to, for example, three or four courses and to deeply involve the beneficiaryentitys faculty (CSI faculty in this case) in the curriculum development process for each of those limited number ofcourses.It is important and feasible to monitor institutional reform impacts. Due to the limitationsof the results framework, this ICRR can draw only limited conclusions about the projects impacts. Annex 7 of the ICR providesa set of readily monitored indicators to assess the extent to which a typical core set of HRM reform objectives is being achieved.These can be monitored with or without an electronic HRMIS, though it is considerably easier with such a system up andrunning.
P155133 | Tonga First Inclusive Growth Development Policy Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099045005312217028/text/P15513306505440e009efd0ddf52adaf91b.txt | http://documents.worldbank.org/curated/en/099045005312217028/pdf/P15513306505440e009efd0ddf52adaf91b.pdf | The lessons are drawn from the ICR.Institutional capacity and political support should be continuouslymonitored. In a dynamic institutional and political environment, frequent changes in key counterparts and ministershighlight the importance of working with a broad set of stakeholders. In this series, this was addressed by requiring allparticipating ministries to appoint working level staff to support coordination and continuity, as well as introducing regularmeetings with the Cabinet and/or the Finance Minister, to maintain political support for the reform.Politicallysensitive reforms should be well-grounded in client ownership. Success in the wage bill management reform was grounded inanalysis undertaken by the government (with development partner assistance). The reform process started with a review ofremuneration to ensure a common reference base, followed by extensive consultation and awareness raising about performance-basedpay, including extensive training to support implementation, and regular consultations and adjustments to improveimplementation.While PAs may be highly relevant to achieving Program objectives, they need to be consistent withcapacity constraints and efforts to build capacity. This series underlined the importance of having a stable team orbeing able to adjust the reform program (including triggers) to ensure its continued relevance. That was a particular concernin attempting to improve accountability in government, as Tonga struggled to address capacity constraints in trying to implementnew procurement regulations, better budget reporting and audit recommendations.,
P155148 | Capacity Building in Public Financial Management 2 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2018 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest |  |  | To avoid pursuing overly ambitious reforms in relation to the level of existing capacity, the Bank should adhere to findingsfrom diagnostics such as Capacity Needs Assessments as well as lessons from predecessor projects. In the case of thisProject, Bank staff carried out such an assessment in 2019 that should have been used to calibrate the level of complexity, forexample, of the revenue forecasting tools that were developed.Projects should avoid using composite indicators.However, internationally recognized standards and indexes can be consulted and unpacked to determine critical areas the Bankcan monitor independently. This Project could have used the detailed breakdown of the Kyrgyz Republics performance interms of budget transparency provided by the International Budget Partnership to assess improving budget transparency andparticipation.
P155172 | PforR on Modernization and Optimization of Public Administration | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | PforR | 2016 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/127921620307444530/text/Serbia-PforR-on-Modernization-of-Pub-Admin.txt | http://documents.worldbank.org/curated/en/127921620307444530/pdf/Serbia-PforR-on-Modernization-of-Pub-Admin.pdf | The following are some of the key lessons from the ICR (pp.35-38) with some adjustment in language:Effectivesupport can benefit from leveraging the World BankIMF relationship and harnessing different World Bank instruments.The Bank and the IMF coordinated closely to push critical reforms forward, with the IMF primarily focusing on the wage bill, andthe Bank focused on how efficiency could be strengthened at the disaggregate level. Given the complex nature of the reforms inSerbia complexity of single spine pay systems and large-scale retrenchment of public employees a concertedmulti-faceted approach (using the PforR as well as Bank-administered trust funds and DPLs to incentivize reforms along withcomplementary support from other development partners) was warranted, and it greatly improved the prospects of achieving thedevelopment outcome under the PforR. Without the full package of distinct but related approaches, the PforR may not have achievedas much as it did in a relatively difficult reform context.Institutional capacity can be improved through thenecessary cooperation in the monitoring and reporting of DLIs. Despite the initial challenges, the need forinter-ministerial and institutional coordination improved the capacity of individual institutions to collect, collate and integratedata. Furthermore, the process helped to shine a light on specific aspects that needed to be addressed to strengthen existingdatabases and/or create new ones. The significant institutional improvements made with support from the Program as well as thetechnical assistance provided by development partners are likely to last beyond the Program.The client and theBank should view mid-term reviews as an opportunity to make strategic adjustments to the program.Mid-term reviewsare an important step in the program cycle. They give both the Bank and the client a moment to step back and conduct an objectiveand holistic assessment of how the program is performing. If a program is experiencing challenges, it is an opportunity totroubleshoot and catalyze change. In this case, the Mid-Term Review was a missed opportunity to address implementation problems andmake strategic adjustments to the program to fully achieve the PDO. Specifically, there were significant challenges and subsequentdelays with the verification process for DLI 8, while this ultimately did not affect the achievement of the PDO. The mid-termreview report mentions that the definition of some DLIs could have been refined, especially with regards to their targets and datacollection requirements.Given the complexity of public wage system, it is important to address the fiscal costsexplicitly when designing reforms. This PforR did not explicitly address the fiscal costs of the reforms that wereenvisaged under the Program, and to some extent this impacted the implementation of the wage system reforms. In addition, the lackof data analytics and fiscal forecasts of the impact of the reforms made it difficult for the Government to make a clear decisionabout the full implementation of the reforms. This could have been avoided by ensuring that the fiscal impacts and costs wereexplicitly discussed, understood, and built into the Program.The following is an additional lesson from thisreview:Results frameworks for core institutional reforms should provide a clear line of sight from operationalsupport incentivized by DLIs through to IRI and PDO targets, and ultimately achievement of improved public services.PDO targets should seek to reflect results at the outcome level, and go beyond the outputs incentivized by DLIs. Thetheory of change should provide an analytical basis to justify why particular interventions were selected and sequenced, and whatimpact in what timeframe they were expected to have on specific, longer-term fiscal consolidation and service delivery outcomesexpected to occur, even if beyond the Programs closing.
P155186 | Uganda Reproductive, Maternal and Child Health Services Improvement Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099110624154533426/text/P155186-7de7b6fa-dfa9-4d1e-9feb-329ca0eaaf04.txt | https://documents.worldbank.org/curated/en/099110624154533426/pdf/P155186-7de7b6fa-dfa9-4d1e-9feb-329ca0eaaf04.pdf | Lessons drawn from the ICR (pages 35-37): adapted by IEG: Multi-sectoral involvement of other relevant agenciescan facilitate vital statistics registration. In the case of this project, while NIRA had the mandate to register births anddeaths, other sectoral agencies were tapped to facilitate the collection of registrations. The health sector, where mostbirths and many deaths take place, played a role in developing tools for death certification and training of vital statisticsstaff; the education sector was a focal point for mobile vital statistics registration. Nationwide scale-up of the RBFprogram can be effectively carried out with strong supportive actions. In the case of this project, development of aharmonized national RBF framework helped to communicate clear standards and expectations (as well as facilitated monitoring andevaluation) and training of trainers in RBF helped to ensure readiness to launch.
P155191 | Providing an Education of Quality in Haiti (PEQH) | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099010424102026004/text/P1551911f624b10981b2e01e94ab18e488e.txt | http://documents.worldbank.org/curated/en/099010424102026004/pdf/P1551911f624b10981b2e01e94ab18e488e.pdf | The ICR (pp. 28-29) offered lessons and recommendations, including the following lessons re-stated by IEGsreview:In a fragile context, putting in place foundational elements prior to launching anoperation greatly facilitates implementation. During the initial phase of preparation, a Non-Lending Technical Assistancebrought technical expertise, fostered dialogue, and delivered analyses and technical products that served as the foundation for thedevelopment of the Quality Assurance System. The technical assistance also facilitated the introduction of new financing modelstopromote student enrollment. Continued reinforcement of a Project Implementation Unit, beyondthe arrangements made at entry, allows a project to expand its scope in an effective manner. During implementation, theproject enhanced the capacities of the Project Implementation Unit in fiduciary and technical aspects, and in supervision at thelocal level, thus allowing the project to maintain critical functions in varying circumstances and to take on new activities withsufficient capacity. Examples included the establishment of an internal control unit and infrastructure unit, and the timelyengagement of supplementary administrative and technical expertise.Coordinationamong development partnerspromotes synergy and system-wide impact.Coordination with development partners facilitated the alignment ofinterventions around government priorities while promoting the ownership of relevant government units. The development of theEducation Management Information System, whichwas associated with the application of the Quality Assurance System in primaryeducation, considered not only the information needs of development partners, but the needs of the system as a whole.
P155229 | Lesotho Transport Infrastructure and Connectivity Project (LTIC) | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2018 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lessons have been derived and summarized from the ICR, with additions by the IEG after discussions with the Bankteam:If a CERC is incorporated in the project design in a country with high risk of natural disasters, it enablesthe Recipient to respond faster in the affected areas. The incorporation of the CERC in this project allowed itsactivationin less than six months (in June 2021) after the January 2021 flooding and before the approval of a formalrestructuring which took place in March 2022. That enabled the government to promptly start the needed preparatory activities priorto the CERC activation and launch the tenders right after the CERC activation. It eventually (and in this case with implementationdelays)helped the Recipient rehabilitate the damaged infrastructure and restore the transport connectivity for the affectedcommunities before the project closing date and without requesting an additional financing.When local communities,in addition to on-site experts, are actively engaged in overseeing the safeguards implementation, it allows for proactivemanagement of environmental and social safeguards. The Recipient ensured consistent safeguards staffing on thecontractors and the PIUs sides. The RD provided regular safeguards trainings to raise awareness of contractors,community-based micro-enterprises for road maintenance, and government staff members about safeguards requirements and relevantmitigation measures. All contractors were mandated to have CLOs to oversee compliance on the respective packages. However, it wasactive involvement of local communities besides the presence of the safeguards experts on the sitethat helped timely identifyemerging safeguards implementation issues and promptly addressing them.If new interventions are included inthe project during a restructuring without adequately reflecting this change in the ME system, this ME system may becomeinadequate to assess the impact of the new interventions and their contribution to the achievement of the relevantobjective.The 2022 restructuring reallocated the funds from Component 1 to the CERC. Despite the introduction of the two outputindicators during that restructuring, no specific targets were set, no outcome indicators were devised, and no monitoring of theoutput indicators took place throughout the implementation. Hence, the impact of those activities to achieve the relevant objectivecould not be objectively assessed.
P155235 | Caribbean Regional Communications Infrastructure Program (CARCIP) | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Digital | Digital Development | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099100923165036261/text/P1552350f8afeb0cd08da708c8a82a46f23.txt | http://documents.worldbank.org/curated/en/099100923165036261/pdf/P1552350f8afeb0cd08da708c8a82a46f23.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A long-term engagement may be required for projects with a regional dimension. While thisproject showed progress on the ground after six years of implementation,the IT/ITES sector continued to face challenges inNicaragua. While a regional approach can benefit small states, these engagements may require ongoing technical assistance,technical and implementation capacity building, and funding to continue operations for an extended length of time, particularly incountries with limited implementation capacities.2. A flexible approach to training courses, vendors, andschemes may increase the potential for success. The approach followed in this project for implementing the Training andCertification Program increased the coverage and impact. This was partly due to the mix of providers, local andinternational.3. Further research by the Bank can help in measuring the progress of the IT/ITES sector in thedigital economy. This project faced challenges when measuring the progress of the IT/ITES sector due to the absence ofIT/ITES data at the country level. The opted alternative, to measure the satisfaction rate expressed by the ICT companies, left outthe opinion of online freelancers and program graduates. Further Bank research could help develop different indicators for thesetypes of activities.
P155256 | Pacific Resilience Program | East Asia and Pacific | Vanuatu | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099335012202115604/text/Vanuatu000Pacific0Resilience0Program.txt | http://documents.worldbank.org/curated/en/099335012202115604/pdf/Vanuatu000Pacific0Resilience0Program.pdf | The ICR drew several lessons based on the project experience, including:1. Use of IDA resources can helpcountries test and access new insurance instruments. In this project, the Republic of Vanuatu (ROV)was able toobtain insurance for disasters associated with tropical cyclones and earthquakes at a lower premium, due to the countriesparticipating in an insurance pool, rather than obtaining insurance individually. In addition, the ROV was able to share itsexperience with and learn from other countries in a similar situation resulting in re-evaluating the suitability of availablecatastrophe insurance products.2. It is important to monitor and evaluate the extent to which a country improvesits understanding of post-disaster risk financing products to better measure efficacy. Projects supporting regionalcatastrophe risk insurance schemes could be not measured against their to payout for insured events; however they could measure thesuccess of capacity-building activities or an increase in percentage of counterpart funding of the insurancepremia.3. Over time, there is need for Pacific Island Countriesto develop their own, institutionalizedfinancial protection measures that do not rely from donors.Further engagement by the Bank is required in this area,and the Bank should continue to explore options for parametric insurance for governments which include reduced premia, and/orprovide coverage for a broad range of disaster events.IEG finds that:A traditional economic analysis isnot very effective for assessing the efficiency of instruments that offer financial protection. The Bank could investigatealternative metrics for demonstrating project efficiency.
P155257 | PACIFIC RESILIENCE PROJECT UNDER PACIFIC RESILIENCE PROGRAM | East Asia and Pacific | Marshall Islands | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/464791602540659075/text/Marshall-Islands-Pacific-Resilience-Program-RMI.txt | http://documents.worldbank.org/curated/en/464791602540659075/pdf/Marshall-Islands-Pacific-Resilience-Program-RMI.pdf | The ICR drewseveral lessons based on the project experience, including: Establishing a regionalcatastrophe insurance pool can have financial benefits and allows for knowledge exchange between countries. In thisproject, RMI was able to obtain insurance at a lower premium due to participating in an insurance pool rather than obtaininginsurance individually. In addition, RMI was able to share its experience with- and learn from- other countries in a similarsituation resulting in re-evaluating the suitability of available catastrophe insurance products. Itis difficult to assess the contribution of a project on disaster financing instruments without some system for capturing evidenceon this. In this project, capacity building goals were not captured well by either the results framework or otherqualitative evidence. IEG also finds that: Traditional economic analysis isnot very effective for assessing the efficiency of instruments that offer financial protection. The Bank could investigatealternative metrics for demonstrating project efficiency. Even after experience with the instrument,governments may conclude that disaster insurance is not the right mechanism for disaster financial risk management. TheRMI government was not willing to sustain support for the insurance mechanism, in part on the grounds that no disasteroccurred during the project period and no payout was made. But this is in conflict with the goal of catastrophic insurance,which is precisely to cover events that are low probability but high risk.
P155259 | CI -DPO-Poverty Reduct. Support Credit 3 | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2016 | 2018 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  |  |  | The following lessons are adapted from the ICR:When the disbursement objective of a DPOpredominates, program design should be less ambitious. The tradeoff between budget support and reform implementation inthis series led to instability in the triggers and the policy matrix. More importantly, it compromised some potential achievementsbecause of the failure to delay disbursement until key reforms were made (ICR, p. 32). In such contexts thereshould be explicit mention in the PD of the primacy of the disbursement objective.The effectiveimplementation of reform programs requires effective sequencing. The lesson from reform program in Cote dIvoireillustrates the need to allow adequate time for their completion. Politically sensitive reformscentral to the performance of the economy require the participation of Bank staff in their design. Outcomes in CotedIvoire demonstrate that if appropriate measures are not adopted by government authorities, the reforms should be excluded,and the viability of the entire program should be reviewed in depth. IEG adds the followinglesson:Reform programs with large numbers of prior actions are difficult to implement. TheCote dIvoire DPO series illustrates that reducing the number of prior actions would provide the program with more focus
P155293 | Liberia Social Safety Nets Project | Western and Central Africa | Liberia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2016 | 2023 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099091224203517005/text/P155293-31809c77-e9d1-4dee-92a2-cc62bc433a01.txt | https://documents.worldbank.org/curated/en/099091224203517005/pdf/P155293-31809c77-e9d1-4dee-92a2-cc62bc433a01.pdf | The ICRR confirms the series of lessons and recommendations emerging from the projects experience (ICR, pp. 22-24) The ICRR summarizes the most relevant lessons below:Maintaining a balance between hands-on implementation supportand building the capacity of government staff entails a trade-off between efficiency and effectiveness. Whereas, there isaneed to intensify implementation support during political transition periods in order not to slow down the project, it is equallyimportant that the Banks team support does not replace the need to build the capacity of government staff. Improvingefficiency should not take place at the expense of ensuring effectiveness and sustainability.Adopting a holisticapproach which includes policy dialogue as well as capacity building/training to accompany the technical aspects canensuregreater ownership and sustainability. Focusing on the technical aspect of building a SP system and on delivering the cashassistance is necessary; however, it is insufficient to ensure long term sustainability. Allocating a budget for institutionalizingthe SP and for ensuring buy-in through communication, policy dialogue and training is key to improveownership.Having a flexible design, especially in Fragile, Conflict and Violence (FCV) contexts helps limitdelays. The projects design did not condition the disbursement under one component before the other. This allowedthe project to deliver the cash assistance while building the SP systems.Exogenous shocks can provideopportunities to pilot innovative approaches which could later be scaled up. The COVID-19 pandemic allowed the project topilot two new aspects: (i) delivering cash assistance in urban areas which provided a proof of concept for universaltargeting in urban areas; and (ii) using mobile means to deliver the assistance which was replicated in the second phase of theproject in rural areas.Removing potential access barriers facilitatesthe successful transition to mobilepayment. Technical support (e.g., through the provision of mobile phones, assistance to obtain SIM cards, coordinationwith the mobile money operators, etc.) facilitated the introduction of mobile payments and ensured that beneficiaries had access tothe service. Additional Note: The ICR missed an opportunity to draw lessons regardingsome important aspects of the project such as (1) implementation challenges in rural versus urban areas and how theywere addressed; (2) the complexity in implementing the additional measures regarding nutrition and home-gardening and how theyshould be addressed in future similar operations; and (3) the reason why other non-Bank funded social safety net programs did notutilize the MIS, notwithstanding the issuance of the cabinet endorsement in 2020 for the LHSR to be used as the primary tool fortargeting SP programs (ICR, p. 10).
P155425 | Dominican Republic Strengthening Management of Public Finances DPL | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2016 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/910481541087033635/text/Dominican-Republic-DO-Strengthening-PFM-DPL.txt | http://documents.worldbank.org/curated/en/910481541087033635/pdf/Dominican-Republic-DO-Strengthening-PFM-DPL.pdf | IEG draws the following lessons:Government commitment is crucial The program was of directpractical relevance to the Government in creating fiscal space. This helped to maintain the focus on reforms evenwhen oversight responsibility for implementation was unclear (Credito Publico).Inadequate planningand resource allocation can undermine the Quality of Supervision.Broad collaboration across global practicesin the Bank is essential not only during project preparation but also during implementation, and sufficient resources need to beallocated to allow a rigorous supervision effort.Clear, well-designed and formalized oversight andmonitoringresponsibilities among the Borrowers institutions,defined at the outset, are important for smoothimplementation. With multiple agencis responsible for different aspects of implementation, inter-agency conflictsare likely to rise if overall responsibilities are not sufficiently well defined.DPLs canbenefitwhen accompanied by investment operations. While prior actions are essential milestones of reform,their implementation also needs to be planned and executed, often in situations where local capacities are limited. Here, theintroduction of investment operations or technical assistance was essential for putting the policy initiatives into place (Section3b)..
P155480 | Chad-DPO Fiscal Consolidation Program | Western and Central Africa | Chad | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/990871557422580730/text/Chad-Chad-DPO-Fiscal-Consolidation-Program.txt | http://documents.worldbank.org/curated/en/990871557422580730/pdf/Chad-Chad-DPO-Fiscal-Consolidation-Program.pdf | The following lessons are taken from the ICR (p. 26), with some adaption of language:Familiarity with Bankprocesses and procedures is an important component of the counterpart governments effective program implementation andshould not be assumed at appraisal. This lack of familiarity can lead to implementation delays in programs where there is an urgentneed for funds to be disbursed.Program design in an environment where capacity is limited and there is highstaff turnover requires PDOs and indicator design that take these factors into account. This is especially the case when otherdonors are actively involved and institutions such as the IMF are monitoring results. Coordinating the use of indicators adds todonor cooperation and can go some way towards offsetting the limited capacity of government counterparts.Ensuring that prior actions are directly linked to country circumstances increases the probability of successful reformmonitoring and raises reform impacts. Reflecting the issue of external shocks in program design can increase programeffectiveness.
P155522 | Bihar Rural Roads Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099111324152034071/text/P155522-2d4ce70c-53e5-48f1-b151-493c7ddceaa7.txt | https://documents.worldbank.org/curated/en/099111324152034071/pdf/P155522-2d4ce70c-53e5-48f1-b151-493c7ddceaa7.pdf | Strengthening institutions requires long term engagement and strong government commitment, and thus, a programmaticapproach may be better suited for such projects. The lack of strong commitment from the implementing agencies along withchanging political priorities can also hinder the process; this often leads to prioritizing infrastructure improvement, which aremore straightforward, over institutional improvements that can be time consuming to implement and often requires strong ownershipsand champions to execute. A programmatic approach, which goes beyond a typical project lifecycle, could help maintain continuousconsultations and engagement with the government agencies to sensitize them to the benefits of institutional improvements and tobuild strong commitment over time to implement them.Strong and flexible Bank support is required where theimplementing agency and the sector has significant capacity gaps. The flexibility in the level of Bank support in responseto emerging capacity shortfalls proves important for the successful implementation of Project activities. In instances wheresignificant capacity gaps are identified in the implementing agencies, such support can be built into the Project design at thebeginning and options such as Hands-on Expanded Implementation Support (HEIS) can be explored for both procurement and technicalsupport.Innovative road rehabilitation methods can bring benefits, but their sustainability need to be monitoredover time. In particular, they need to be supported by a comprehensive Assets Management System to ensure that localclimatic conditions are properly factored in lifecycle costs, including routine and periodic maintenance.Buildingtrust through close consultations with communities can improve efficiencies in project implementation. As demonstrated bythe experiences from the Janata Durbars initiative, it is clear that regular consultations with project communities play a key rolein fostering trust towards the project and the implementing agencies. Engaging community members in project activities, promptlyaddressing their feedback and concerns, and incorporating their suggestions are essential strategies that not only buildtrustbut also facilitate smoother and more efficient project implementation. Such participatory approaches can be integratedinto the design of future projects to enhance their effectiveness and community acceptance.The adequacy andappropriateness of technology should be assessed against the specific contexts and environments in which it is used. A keylesson from the Projects experience with the use of an app to record grievances is that when technology is used,particularly involving communities with poor literacy and inadequate access to technological devices, it is important to ensurethat (i) the technology used is tailored to address the specific requirements of the users, (ii) users are aware and educated inhow to use the technological solution, and (iii) the appropriateness of the use of technology is assessed in the specific context.As was evident from the Projects experience with Janta Darbars which promoted more person-person interaction, at times, morehuman-oriented solutions can create better results compared to technological solutions.
P155540 | Third Economic Reform Development Policy Operation | East Asia and Pacific | Kiribati | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/475551622122805649/text/Kiribati-Third-Economic-Reform-DPO.txt | http://documents.worldbank.org/curated/en/475551622122805649/pdf/Kiribati-Third-Economic-Reform-DPO.pdf | IEG draws the following two lessons from the evaluation of the DPOs:Small, geographically dispersed economiesmay require balancing relatively modest private sector development prospects with public spending. In Kiribati,government successfully oversaw the administration of SOEs and joint ventures while creating the infrastructure that could supportprivate business at a scale that was appropriate for Kiribati.Efficient management of publicassets is pivotal to fiscal sustainability. From a situation of weak oversight of asset managers, misalignment ofasset allocation with long-run investment objectives, and unrealistic investment targets, a proper sequencing of reforms better asset managers, revised custodial arrangements, and recruitment of accomplished custodians, contributed to better portfolioreturns and reduced management costs for RERF and, ultimately, strengthened public financial management in Kiribati byre-establishing RERF as a buffer against external economic shocks.
P155542 | Pacific Resilience Program | East Asia and Pacific | Pacific Islands |  |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099101723110032001/text/P155542023dbc90d60bae30b1bfd48ca45d.txt | http://documents.worldbank.org/curated/en/099101723110032001/pdf/P155542023dbc90d60bae30b1bfd48ca45d.pdf | The ICR provided five lessons, with three slightly edited below (ICR, paragraphs 103-107): Resultsframework for specific sub-projects of abroader program may helpattributeoutcomes.In this project,the PDO replicated the PDO of the broaderprogram. However, the scope was refocused away from disaster resilience bystrengthening appropriate financial instruments to only program coordination and knowledge sharing.Not all the inputs to thewider programsuch as early warning or resilient investments in participating PICs were addressed in the results framework andtheory of change.Including outcome indicators for PIFS-implemented regional activitieswithin the PREP results frameworkwould establish how the sub-projectcontributestothe PREP outcome. A regional endeavor with anexperienced staff may help engage member countries.In this project, the RCU was managedby awell-respectedcoordinator, supported byan experienced team. The PICs saw the PIFS as an external entity that did notnecessarily represent their interests. The RCU adeptly navigated thisdivide. The participating PICs willinglyparticipatedin regional PIFS-sponsored meetingswhere the new concept of disaster risk financing was sharedtoinfluence behavior that would reduce the shared risk from natural hazards. Peer-to-peer learning promoteslong-term engagement. In this project, the use of peer-to-peer learning took advantage of the regions tradition forface-to-face interactions as the preferred means of communications. PIFS initiated the practitioners forums, ProgramCoordination Meetings, and established the DRF Working Group to facilitate long term engagement.
P155553 | Private Sector Competitiveness DPO2 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2018 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | A DPO series that is well supported by the country dialogue and well coordinated with development partner programs islikely to be able to correctly gauge the governments willingness to pursue long-range, high-impact reforms. Becausethe PSC series had the right mix of reforms and was correctly timed for government commitment and capacity, it was able to achievea broad range of high-impact reforms.Banking reform is likely to be more successful when thebanking sector is relatively sound.In Georgia, deposit insurance that requires regular contributions from banks mayhave been more difficult to introduce into a banking system in crisis; in Georgia, banks were solvent and financially solid.
P155605 | Albania Competitiveness Development Policy Loan | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2017 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/580761561587964184/text/Albania-Albania-Competitiveness-DPL.txt | http://documents.worldbank.org/curated/en/580761561587964184/pdf/Albania-Albania-Competitiveness-DPL.pdf | The most important lessons in the ICR are the following (with some adaptation oflanguage).(1) Finding the right balance between supporting upstream and downstream activities isimportant for capturing the full benefits of reforms. In this operation, most of the supported reforms were on upstreamactivities (adopting by-laws and decisions). To fully capture the benefit of reforms, it is important to consider the impact ofdownstream activities, which require more time.(2) TheDoing BusinessDistance to Frontier (DTF) indicators for the results framework either needs to be refined or supplemented with other indicators toaddress attributional issues. In this operation, the DTF indicators were used mainly because they had large visibilityin the country and hence considered to be a good tool to motivate the authorities to push for reforms. Notwithstanding thisbenefit, it would have been useful to complement this indicator, with more granularity for addressing attributionalissues.(3) Supervision and dedicated technical assistance resources are required for supportingprogress on reforms, especially in areas of weak capacity. In this operation, the team prepared severaltechnicalnotes, and this aided in informing and advancing the policy dialogue.
P155605 | Albania Competitiveness Development Policy Loan | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2017 | 2018 | 2023 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/099446503102334407/text/SECBOS08dd9ccc020096430c65d030921dd.txt | http://documents.worldbank.org/curated/en/099446503102334407/pdf/SECBOS08dd9ccc020096430c65d030921dd.pdf | 3. Lessons 3.1 This assessment offers the following lessons: â€¢ It is crucial for prior actions to address the key binding constraints to achieving the stated objective of a DPL. This was not the case in this operation. The 2016 Regional Operations Committee review meeting raised the point that reforms in key areas where Albania was lagging at the time of preparationâ€”such as paying taxes, registering a property, and enforcing contractsâ€”deserved more attention than reforms in the DB areas, such as construction permits, to achieve the operationâ€™s overall objective of enhancing competitiveness. â€¢ The prior actions of this operation did not have a sufficient level of ambition to make a significant contribution to enhancing competitiveness. They had been designed as part of a two-stage process within the confines of a programmatic development policy operation. When the DPL series of two operations was reversed to a stand-alone operation, the credibility of the prior actions for the first operation should have been reassessed. â€¢ It is crucial for IFC to determine, at implementation, warning signals regarding inadequate client commitment and show flexibility and patience only to those clients that show proof of trust, ownership, and commitment. IFC advisory services projects can play an important role in complementing World Bank efforts on policy reforms. They can, however, consume a significant amount of IFC resources while not serving the intended purpose of contributing to the DPLâ€™s objectives, particularly in situations where there is a lack of client commitment during implementation. Despite IFCâ€™s continued efforts in supporting the government in areas such as investment policy framework, IGM, and trade facilitation, there was limited progress in implementation of reforms in these areas. â€¢ For progress in the uptake of LCPs or the AEO programs by businesses, it is crucial to have the following in place: (i) a clear communication and outreach strategy; (ii) a systematic approach to educating businesses and customs about the benefits of these programs; (iii) strong engagement of customs and other border agencies with the private sector; and (iv) a culture of trust between customs and the business community. However, these prerequisites were not in place at the time of preparation of this operation, resulting in low uptake of these programs by businesses in Albania. 23 â€¢ DB indicators as targets and metrics of reforms do not work very well, even if they are valid ways to point to a problem area. Because of the limited agenda they have, DB indicators cannot prioritize the range of private sector development constraints. Also, because of the limitations and lack of granularity of the DB indicators, they cannot track reforms very precisely. â€¢ Clear assignment of responsibility for the collection of particular data needs to be assigned at the outset. The expected outcome of reducing the cargo dwell time at the port of Durres could not be assessed because of limited information provided by stakeholders during the IEG virtual mission. This indicates a failure to have in place clear responsibility for data collection and reporting as part of the DPL. 1 Gross domestic product figure is from World Bank Data (database) â€œGDP per Capitaâ€” Albania,â€ World Bank, Washington, DC, https://data.worldbank.org/indicator/NY.GDP.PCAP.CD?locations=AL. The population figure is from World Bank Data (database) â€œPopulation, Totalâ€”Albania,â€ World Bank, Washington, DC, https://data.worldbank.org/indicator/SP.POP.TOTL?locations=AL. 2 A local clearance procedure enables traders to clear goods at their premises or other approved locations. 3An approved economic operator is a company that, by satisfying certain criteria, is considered to be trustworthy by customs and other border inspection authorities and therefore entitled to a number of simplified processes and procedures (or benefits) as a reward for its long-standing high compliance levels. 4Data are from the Worldwide Governance Indicators (database), World Bank, Washington, DC, https://info.worldbank.org/governance/wgi/Home/Reports. The Worldwide Governance Indicators is a research data set that summarizes views on the quality of governance provided by a large number of enterprise, citizen, and expert survey respondents in industrial and development countries. These data are gathered from a number of survey institutes, think tanks, nongovernmental organizations, international organizations, and private sector firms. The Worldwide Governance Indicators do not reflect the official views of the World Bank, its Executive Directors, or the countries they represent. The Worldwide Governance Indicators are not used by the World Bank Group to allocate resources. Percentile rank indicates the percentage of countries worldwide that rate below Benin. Higher values indicate better governance ratings. 5Currency conversion rate from euros to US dollars obtained from XE, https://www.xe.com/currencyconverter/convert/?Amount=1067083373&From=EUR&To=USD. 6These data were provided by the Albanian Investment Development Agency during the Independent Evaluation Group virtual mission in February 2021. 7Data are from the Worldwide Governance Indicators (database), World Bank, Washington, DC, http://info.worldbank.org/governance/wgi/Home/Reports. 8Distance to frontier is a Doing Business indicator that illustrates the distance of an economy to the â€œfrontier,â€ which represents the best performance observed on each Doing Business topic across all economies since 2005. An economyâ€™s distance to frontier is indicated on a scale from 0 to 100, where 0 represents the lowest performance and 100 the frontier. An improvement in score through time would indicate the economy is improving. 9 The logistics performance is the weighted average of a countryâ€™s scores on six key dimensions: (i) efficiency of the clearance process (that is, speed, simplicity, and predictability of formalities) by border control agencies, including customs; (ii) quality of trade- and transport-related infrastructure (for example, ports, railroads, roads, and information technology); (iii) ease of arranging competitively priced shipments; (iv) competence and quality of logistics services (for example, transport operators and customs brokers); (v) ability to track and trace consignments; and (vi) timeliness of shipments in reaching their destination within the scheduled or expected delivery time. 25
P155645 | Burkina-Faso eGovernment Project | Western and Central Africa | Burkina Faso | IDA | FCS | Digital | Digital Development | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The ICR review draws the following key lessons from the experience of implementing this project, with some languageadaptation.1. A simple design and agility to changing conditions may raise the potential for success in FCVsettings. A limited number of components and activities in this project helped handle implementation challenges. Further,the Bank supervision team was agile and proactive with two timely and relevant restructurings. This helped in completing theproject activities. However, the task team could have aimed to deploy fewer than seven digital platforms to better align the scopeof envisioned activities with the capacity level of the government agencies.2. Prioritizing womensparticipation in the digital economy would help minimize the gender gap in the ICT sector. In this project, only eightpercent of women versus 16% of men reported regular internet usage. The lesson is that the Bank team could prioritize this aspectby supporting the Government in defining policies, strategies, and programs for womens inclusion in the digital economy.
P155656 | Second Disaster Risk Management Development Policy Loan with a CAT-DDO | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2016 | 2020 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/363561623419063930/text/Philippines-Second-DRM-DPL-with-a-CAT-DDO.txt | http://documents.worldbank.org/curated/en/363561623419063930/pdf/Philippines-Second-DRM-DPL-with-a-CAT-DDO.pdf | The ICR derived the following lessons from theDPL programs experience, with some adaptation forbrevity:A strong institutional champion is key to advancing complex reform programs. As the implementingagency, the Department of Finance played a central role in ensuring inter-agency coordination of DRM-related policy actions whileadvancing new thinking on financial protection. It also convened the key DRM agencies to sustain buy-in and maximize responsive toGOPs priorities.Establishing clear rules of the game at preparation supports the effectiveness of the CatDDO instrument. A clear understanding of the procedures and responsibilities of GOP and the World Bank to trigger the CATDDO mechanism and process disbursement allowed the transfer of funds in only two days after the country was hit by Tropical CycloneMangkhut in September 2018. The steps include: (a) the declaration of a state of emergency, (b) the decision-making process toactivate the CAT DDO, (c) the necessary documentation to request Bank disbursement, and (d) the process to incorporate theresources in the national budget. The Bank teams close involvement and sustained dialogue on the DPLs financialaspects is crucial at all stages of the program.An effective reform program needs to be supported by a solidanalytical foundation. While the CAT DDO can provide timely liquidity following a disaster, it is also important toprovide support throughout the program to enhance the countrys capacity to implement its DRM program. In this case,the programmatic TA program was an effective supervision strategy to support and track policy reforms and also to compensate forthe drawdown of funds in September 2018, thereby continuing the strengthening of DRM institutional systems and sectoral agencycapacity until the closing of the program.IEG also adds the following lesson:A CAT DDO can be aneffective tool for supporting policy reform when it selects Prior Actions that are highly relevant and critical, and uses resultsindicators wisely to provide impetus for sustained reform progress.As indicated earlier, the Second DRMDPOs Prior Actions are highly relevant to achieving the PDO of strengthening the Government and Bank strategiesfordisaster risk management. Moreover, the results indicators are also substantially to highly relevant,astheyconsisted of actions that included adoption, implementation and mainstreaming of policies and instruments that werecausally linked to supporting the achievement of the PDO.
P155694 | Serbia Public Expenditure and Public Utilities DPL 1 | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2022 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/627581626707657263/text/Serbia-Public-Exp-and-Utilities-DPL1.txt | http://documents.worldbank.org/curated/en/627581626707657263/pdf/Serbia-Public-Exp-and-Utilities-DPL1.pdf | This Review concurs with the lessons from the ICR, which are summarized below. The fourth lesson is revised to include emphasison social protection mechanisms to counter the negative impact on the vulnerable. The Review adds lessons on results indicators andreform ambition. Development partner coordination, supportive technical assistance, complementary Bank operations, aprogrammatic approach, and strong analytic underpinnings were key factors in the success of this DPLseries. Incentivizing implementation of prior actions with DLIs from a parallel PforR did not ensure theimplementation of the new wage policy due to political sensitivities and the need for additional analysis. Strongpolitical will is decisive for advancing complex, politically sensitive reforms and for effectively negotiating with vestedinterests, as is government ownership and communication strategy towards stakeholders. In this case, two key ministers supportingthe design of the series left during implementation, creating a challenge for some reform components. Politicalsustainability of DPL supported structural reforms with negative social impact can be enhanced when reforms are accompanied bymitigation measures to cushion the impact on the vulnerable, be it through the compensation packages in the context of redundanciesor expanded social protection mechanism to cushion the impact of increases in social sensitive prices of publicutilities.
P155824 | Climate Change and Green Growth in Vietnam | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2016 | 2017 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/242261590174538440/text/Vietnam-Climate-Change-and-Green-Growth-in-VN.txt | http://documents.worldbank.org/curated/en/242261590174538440/pdf/Vietnam-Climate-Change-and-Green-Growth-in-VN.pdf | IEG concurred with the ICR Team on the lessons derived from the program with some additionalpoints.1 .Strong engagement at the sector level is essential to address climate change and green growth, as they can critically affectprogram outcomes. The governments change in strategy to prioritize the provinces over the sectors (i.e. ministries)for the envisaged expenditure reviews under this Program resulted in the modest achievements on the sector-level targets.Considering that the need for intersectoral coordination to address climate change had been pointed out since the preceding DPFseries, it would be essential to strengthen sector-level engagement and coordination.2 .Strengthening high-level engagement with the focus on outcomes and impacts of the policies would enhance the efficacy of theprogram. PDO indicators should be directly relevant to measuring outcomes that are attributable to project interventionsand need to be monitored accurately to generate adequate and robust evidence on efficacy. Focusing only on the delivery of tangibleoutputs would lower the level of achievements of development outcomes.3 . Good practice on coordination amongdevelopment partners is required to realize the benefit of their joint inputs. Parallel financing and joint supportmissions by the Japan International Cooperation Agency, the Agence Francaise de Development and the World Bank complemented eachother and provided integrated support to NDC implementation. However, the institutional capacity risk that was identified atappraisal was not adequately mitigated. The weakened engagement of stakeholders after the discontinuation of the direct technicalassistance to the PCU negatively affected the achievements of the outcomes.
P155842 | Modernization and restructuring of the road sector | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/099300312232216946/text/P155842089e29e06609082093f87b67ac30.txt | http://documents.worldbank.org/curated/en/099300312232216946/pdf/P155842089e29e06609082093f87b67ac30.pdf | This review has drawn two lessons based on the information in the ICR.Stand-alone technical assistance, withoutan investment lending component, can be insufficient to trigger major sector reforms. The project financed only technicalassistance activities to modernize and restructure the road sector in Croatia. The project was to deliver studies, reports, andbidding documents for the implementation of a road asset management system (RAMS) and a new automated tolling system. These twoactivities were key activities for the achievement of the sector reform through RAMS data feeding into the rolling plans toincrease the efficiency of the sector and new automated tolling system increasing the road sector companies revenues. Theproject did not finance the actual procurement of both systems, which was a shortcoming that may have ensured governmentssustained commitment to the reform process. Nevertheless, the project was partially successful in facilitating the mergers of theroad sector companies, financial restructuring of the system, and harmonization of a set of rules, such as accountingprinciples.Conditioning the use of guarantees on strict requirements can be counterproductive in achieving sectorreforms. The World Bank guarantee to be used for the optimization of the road sector companies debts wasconditional on the implementation of revenue and cost measures, and governance and transparency commitments. It was expected thatthe need to use the guarantee would lead to the implementation of these measures resulting in a sector reform. However, when thegovernment was able to restructure the debt of the road sector companies benefiting from the improvements in the European and localcapital markets, the necessity to implement the reform measures to benefit from the IBRD guarantee subsided, and the governmentcommitment to the sector reform weakened. The conditions tiedto the use of the guarantee did not lead to the expected sectorreforms.
P155876 | West Africa Regional Communications Infrastructure Project - SOP3 | Western and Central Africa | Western and Central Africa |  |  | Digital | Digital Development | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099100923101020035/text/P155876141744e7a15ba3142331ac271cc9270cce009.txt | http://documents.worldbank.org/curated/en/099100923101020035/pdf/P155876141744e7a15ba3142331ac271cc9270cce009.pdf | The ICR draws the following two main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Intense efforts by the Bank team may be required in implementing a PPP in an FCV environment.The project had a Project Preparation Advance (PPA), so the PPP framework was ready by project effectiveness. Despitethis, the Bank team had to make intense efforts to clarify the suitability of those agreements to mobilize private-sectorfinancing, given the frequent changes in government.2. A candid assessment of the project interventionswould help ensure the optimal use of the ME framework as a feedback mechanism. In this project, the intended outcomeswere either realized or exceeded, even though the main project activity was only completed two weeks before the project closed.Hence, the outcomes could not be attributed to the project interventions. The lesson is that it would help rectify the MEframework with a project restructuring and enhance candor during implementation in such cases.
P155885 | South Africa Partnership for Market Readiness | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2017 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099055011302120905/text/South0Africa000South0Africa0PMR.txt | http://documents.worldbank.org/curated/en/099055011302120905/pdf/South0Africa000South0Africa0PMR.pdf | The ICR (p. 30-31) included very useful lessons, which were adapted by IEG: A combination of a clearpolitical mandate, legal basis, and coordination among ministries is critical for the development and implementation of a carbonpricing instrument. The objective of this project was fully aligned with the governments climate priorities andcommitment to implement a carbon pricing instrument. The NT did not just collaborate with different ministries but also withnon-governmental stakeholders. This had a positive impact on the implementation. In addition, South Africa also shared lessonslearned with other countries in international forums. A countrys Ministry of Finance can be a key championfor climate change action as part of their responsibility of managing the national budgeting process. In this project NTtook on several roles that were critical for a successful implementation such as coordinating across different government entitiesas well as non-governmental stakeholders. In addition to successfully launching carbon pricing and policy design, it built supportfor carbon pricing within the government and industry to ensure coordination and efficiency. Allowing forflexibility in the calibration of carbon pricing instruments is critical. South Africas carbon pricing instrumentincluded measures to ensure its ongoing competitiveness and allow for adjustments in case of future competitiveness concerns. Forexample, introducing the taxes in phases, providing different allowances, not including the electricity sector in the first phase,and planning for a review of the tax after two years of implementation provide sufficient flexibility to adapt the instrument toSouth Africas national context when needed.
P155902 | National Program for Innovation in Fisheries and Aquaculture | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | The following lesson is drawn from IEGA grant mechanism that aims to involve vulnerable communities will havemore success if it comes with a set of technical assistance tools and incentives that facilitate their participation. Inthis project, the technical and administrative aspects of the grant mechanism were a challenge for the participation of vulnerablepopulations from the informal economy that lacked the technical capacity to apply for the subsidies. It was thanks to thedissemination and technical assistance efforts of the project, together with additional incentives in the competitive process thathelped overcome these constraints.Projects supporting sectoral innovation still need to have indicators thatassess the actual effectiveness of the underlying innovations at improving sector outcomes. In this project indicatorsfocused on sub-project completion, whereas important outcomes such as income improvement for producers, productivity increases invalue chains or improved sustainability of fisheries were not part of the RF.The following lessons are selected as mostrelevant, from the ICR (rephrased)The learning derived from the mechanism of demand-driven grants can lay thefoundation for key sectoral public policy. The important insights generated in the project into what innovations in thesector show the strongest potential and what are the incentives for stakeholder participation provide now guidance for elaboratingmore adapted and strategic programs in public policy that facilitate sector transformation.A politically neutralsteering committee and a stable and high performingtechnical team are factors that work towards the projects stabilityand its performance. Amid frequent leadership changes in national government and PRODUCE, the project was successful inretaining most key project staff. The steering committee, made up of stakeholders from institutions across the sector, was a sourceof technical and strategic support for the projects programming, and provided an important buttress against interference inthe program by political appointees. Expert members on the steering committee for strategic guidance and detailed protocols forhiring and replacement of key staff have proven essential to protect the neutrality and transparency, hence giving stability to theproject
P155920 | Honduras First Fiscal Sustainability and Enhanced Competitiveness DPF | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/381851556745502500/text/Honduras-Honduras-First-Fiscal-Sustainability-DPF.txt | http://documents.worldbank.org/curated/en/381851556745502500/pdf/Honduras-Honduras-First-Fiscal-Sustainability-DPF.pdf | The lessons are drawn from the ICR.A strong policy dialogue can continue even after a programmatic DPL istruncated. In this case, the dialogue was supported by other vehicles such as technical assistance, ongoinginvestment projects or knowledge products in areas supported, and by continued donorcoordination.Complex challenges require comprehensive solutions. Isolatedsector-level interventions may be undermined by exogenous factors, either in the domestic economy or the externalenvironment. The energy reforms supported by the FSECDPL provided only short-lived results, which were quickly undermined byexternal (oil price increases) and internal developments (weak governance, political economy aspects). Without tacklingthe challenges in the energy sector in a comprehensive manner, durable progress turned out to be difficult toachieve.Coordinated assistance bythe principal externalpartners helpssolidify and consolidate reforms. Teams should seek common ground and complementarity on reform with otherstakeholders. In Honduras, this allowed complementary TA to be linked into the operation while supporting jointobjectives.
P155962 | IRAQ EMERGENCY FISCAL STABILIZATION, ENERGY SUSTAINABILITY, & SOEs DPF | Middle East and North Africa | Iraq | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/771681553629077129/text/Iraq-Iraq-Emrgncy-Fiscal-Stabilization-Enrg.txt | http://documents.worldbank.org/curated/en/771681553629077129/pdf/Iraq-Iraq-Emrgncy-Fiscal-Stabilization-Enrg.pdf | Three lessons are drawn from the ICR (page 19), with some adaptation.Crisis lending can beconsistent with longer-term structural reform. The DPF combined emergency financing, inresponse tothe oil priceand ISIS insurgency shocks of mid-2014, with a program to improve expenditure management, energy supply sustainability, and SOEtransparency over the period 2015-17. The loan proceeds helped Iraq meet its financing needs as oil prices plunged andsecurity expenditures soared, while the reform program enabled the government to take measures that would begin tomeet thepopular demand for reliable basic public services in an FCV affected environment.A stand-aloneoperationstrains the effectiveness ofa medium-termpolicy and institutional reform dialogue, when the programmaticapproach is the optimal intervention. TheBank strove to maintain the medium-term character of the reform program bypicking interventions from the first year of the original three-part plan, by designing the results framework to focus onintermediate outputs, and by rapidly preparing a follow-on operation on the same three policy areas even as thegovernmentcontinued to implement the first operation. However, the stand-alone operation also constrained the implementation ofinstitutional capacity building initiatives which were better suited tothe longer timeframe of aprogrammatic series.Planning and systematic technical assistance are critical for embedding policies in institutions. The DPFhas had to confront weak institutions and poor governance in a countrydamaged by decades of armed conflict, politicalinstability, and economic sanctions. Careful planning of the structural reform program andtheconveyance ofsystematic long-term technical assistanceby multiple development partners aimed to ingrain the reform agendaingovernment operations in a manner that would be, hopefully, difficult to reverse.
P155963 | Pakistan Punjab Jobs and Competitiveness Program for Results | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | PforR | 2016 | 2022 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR draws the following main lessons from the experience of implementing this Program,with some adaptation oflanguage.1. Strong government ownership and involvement at the design stage may raise the potential for thesuccess of PforR operations. A key factor in this operation was that the design was based on policy proposals developedunder the Jobs and Competitiveness Non-Lending Technical Assistance (JC NLTA), which informed the Punjab Growth Strategy(PGS). The Banks hands-on support during design built a level of credibility and trust with the Government of Punjab that theteam nurtured throughout the operations lifetime.2. Internal collaboration withinthe World Bank Groupcan raisethe potential for success in programs with cross-cutting agendas. This operation combined thecompetitiveness and spatial development agendas of the GovPunjab. The Bank brought in people with wide-ranging expertise, not onlyfrom other units within the Bank, but also from the International Finance Corporation (IFC). The seamless collaboration between thetask team, theWorld Banks Urban and Environment Global Practices and IFC helped successfully link the competitivenessand spatial development agendas.3. An initial demand assessment to properly dimension the private sector appetitefor investing in Combined Effluent Treatment Plants (CETPs) could help design an appropriate set of incentives.Thisprogram was unable to attract private sector interest despite the attempts made by the Punjab Government to advertise theCETPs feasibilities. The lesson is that an initial demand assessment could have helped in designing the appropriate set ofincentives.4, Including an Investment Policy Financing (IPC) component in the Program for Results (PforR) can helpprovide incentives to steer reforms. This project had substantial technical assistance (TA) activities to help the variousimplementing agencies. In this operation, procurement by all the participating entities remained consistent with the stipulatedvalues under the PforR. However, the Bank was not able to have a deeper engagement with the implementing agenciesdue to theabsence of a TA component for implementation support.
P155969 | Earthquake Housing Reconstruction Project | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2015 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060524104533667/text/P15596914eb53308019b6412d2a0e727bb2.txt | http://documents.worldbank.org/curated/en/099060524104533667/pdf/P15596914eb53308019b6412d2a0e727bb2.pdf | The ICR formulated several useful lessons. The most relevant ones, with IEGs modification, are asfollows:Bank-to-bank fund transfers can be useful to ensure transparency, improve financial inclusion, and accessto banking services, including housing insurance. Under the project, the grant payments to beneficiaries were made throughthe banking system to reduce the possibility of corruption and ensure building code compliance. This decision contributed toincreasing the number of bank account holders from 52 to 70 percent. A district-wide analysis showed that banking coverage amongthe beneficiaries increased from 0 to 100 percent in some districts. Using the banking system also helped to unlock constrains inthe credit and savings market, promote payment system, bolster risk mitigation capacities, and enhance the capacity of locallybased financial service providers.149,000 households were brought to the banking network, thereby exposing them to savings andcredit facilities, which are crucial precursors for prosperity.When a project works with an agency with a limitedtenure, early planning is critical to ensure transition of institutional memory and capacities built by the project to permanentagencies for the country to be able to continue strengthening the related sectors. Under the project, successful housingreconstruction is attributed to the NRA, whose mandate was specific to the countrys reconstruction from the 2015 earthquake.NRAs closure before completion of housing reconstruction and incomplete tasks from the 2019 NRA overwhelmed the successoragency, NDRRMA. However, the overwhelming challenge to NDRRMA strengthened their capacity and helped them get acknowledged by othergovernment agencies at national, district, and local levels through project implementation, facilitation, and coordination.Adoption of an owner-driven approach, in terms of moving from building homes for people to supporting peopleto build safer homes by themselves not only ensures effective use of financial resources but also improves disasterresilience. Under the project, individual families used financial assistance to rebuild their houses. The grant wasdisbursed in tranches and with compliance to earthquake resistant building standards. The project provided technical, material,supervisory, training, and social facilitation. An owner-driven approach to reconstruction also meant using locally availablematerials and incorporating traditional construction methods and designsfound to be culturally relevant and environmentfriendly, in conjunction with special disaster-resisting features recommended by the relevant technical codes/guidelines, whichimproved disaster resilience.Projects that include housing reconstruction for low-income households could benefitfrom considering the affordability of these investments for such households. In this project, the housing reconstructiongrant provided about a third of the construction cost, and the participation by low-income households in the project led to theirincreased exposure to higher indebtedness, and some persons were reported to have resorted to selling assets to participate in theprogram.It is important to consider in project design that low-income households could afford their share of reconstructioncosts.
P156001 | Lesotho Education Quality for Equality Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024220527765/text/P1560011ebabbf0f21b1e11b4e5763c2575.txt | http://documents.worldbank.org/curated/en/099053024220527765/pdf/P1560011ebabbf0f21b1e11b4e5763c2575.pdf | The ICR Review included the following ICR lessons: Reliance on Community Construction Committees in remoteareas can support improved access to local school infrastructure if potential challenges are addressed. In this particular project,delays in salary payments and the provision of construction materials, which initiallyled to implementation delays, werelater resolved and allowed school constructions in remote areas to be completed on a timely basis; The introduction ofSIPs can promote a sense of community ownership, with the results of the SIP assessment indicating, among other things, thatcommunitieshad increased their level of awareness of what happens in schools, and their concern over protecting the schoolfacilities and materials; and Complex institutional arrangements necessitating interagency coordination within thecontext of high government staff turnover can impede implementation. In such instances, identifying a focal point for eachsub-component may prove beneficial.
P156012 | Health System Support Project (KIRA) | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2017 | 2023 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099070724235531540/text/P156012-1acfd1db-2ed5-4355-83ee-aaeef2ac0ab4.txt | https://documents.worldbank.org/curated/en/099070724235531540/pdf/P156012-1acfd1db-2ed5-4355-83ee-aaeef2ac0ab4.pdf | The ICR highlights a number of lessons derived from the project, notably: The development of a health financingstrategy can support the long-term financing of FHC-PBF in Burundi, reducing dependence on donor funding and supporting thesustainability of development outcomes. The introduction of a health insurance agency (CaissedAssurance Maladies Obligatoire, CAMO) which would pool resources of all the different health insurance programs andserve as the single financial management system to advance universal health care in Burundi can also support the sustainability ofdevelopment outcomes. In Burundi, approximately 75 percent of the financing of public health centers is derived from the PBFprogram and interruptions in the funding of the PBF would adversely affect the provision of primary healthcareservices. Reliance on community health workers to provide referral to health facilities, conduct sensitization sessionsfor behavior change, ensure healthcare provision at community level including retrieval of patients who have abandoned care, andstrengthen the collaboration between health facilities and the community can effectively support development outcomes by ensuringthat vulnerable segments of the population receive the healthcare services they require. For a PIU charged withoverseeing more than two projects: (i) an assessment of its capacity to take on additional projects can guide projectimplementation and facilitate the Bank to meet the financial management and procurement guidelines; (ii) consultations with PIUstaff can support the findings in this assessment; (iii) the review and update of all PIMs for all active projects when a newproject is adopted can help clarify the roles and responsibilities of staff and consultants at the PIU; and (iv) the introductionof internal controls; (v) the operations of the PIU can be strengthened by clearly laying out the responsibilities of civilservants and consultants.
P156021 | Ecosystem Conservation and Management | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099031524133522879/text/P156021112955d02f19f26130bb84931a8c.txt | http://documents.worldbank.org/curated/en/099031524133522879/pdf/P156021112955d02f19f26130bb84931a8c.pdf | The ICR identified several lessons. Two of them that stood out as potentially useful to other similar projects are restated herewith some editing as follows:Communicating with stakeholders proactively on the platforms in which they raiseissues a meeting where the issues emerge can diminish the chances of the issues escalating into major publicrelations challenges. The conservation community in Sri Lanka objected to three project activities (PERC at LunugamveheraNP, the Kudawa access road in Sinharaja WHS, and the pipelinein Yala NP). The Bank project team, addressing the issue throughconventional channels, such as consultation, news articles, and publicity material, failed to quickly assuage theconcerns.The chances of effectively making project activities demand-driven can be enhanced by buildingcapabilities for carrying out consultative processes in implementing organizations. Low institutional capacity was flaggedas a risk. Despite the support, officials from FD and DWC faced difficulties developing integrated proposals based on the needs anddemands of affected communities. They reverted to identifying investment activities from a list of needs in existing PA managementplans. Centralizing decision-making, they prioritized infrastructure development and mechanical interventions over softinterventions, such as grassland management and manual maintenance, that communities would have preferred.
P156056 | Social Safety Nets Project | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2023 | 2025 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099101024173523024/text/P156056-409d0dec-140b-40cc-8da1-3b8028bb85f6.txt | https://documents.worldbank.org/curated/en/099101024173523024/pdf/P156056-409d0dec-140b-40cc-8da1-3b8028bb85f6.pdf | The ICR (pp. 18-19) offered several lessons and recommendations, including the following lessons restated by thisICR Review: Institutional arrangements that provideimplementing agencies with the authority and thebudget to implement project-assigned responsibilities can support project implementation. In this particular project, delays in theapproval of the WBB Regulations and Selection Criteria by the Parliament resulted in the MOSEW lacking the resources and theauthority to recertify and enroll beneficiaries in the WBS, and to implement other Component 2 project activities which it wasresponsible for. This led the MOSEW to approve an expansion in the number of Samurdhi program beneficiaries, which werenot selected based on the targeting methods supported by this project. In an emergency, reliance onanexisting beneficiary roster can provide fasterassistance to alleviate the economic hardships on the most vulnerablesegments of the population. This project relied on the existing roster to provide social assistance benefits to households mostaffected by the repercussions of the COVID-19 pandemic. While reliance onthe existing beneficiary roster was not aligned withthe projects objectives, this was necessary nonetheless to prevent a significant portion of vulnerable households fromdrifting into poverty, which would carry with itlong-term socio-economic impacts. Adequate revisions to the resultsframework and the DLI matrix following revisions to project components are needed to support project implementation and progresstoward the achievement of objectives. In this project, the elimination of Component 2 activities at the first restructuring madethe achievement of Objective 1 (Contribute to the improved equity of Sri Lankas social safety net programs) difficult.Further, the first restructuring maintained a DLI linked to Component 2 activities which had been dropped. Finally, the firstrestructuring did not introduce either a PDO level or intermediate results indicator to monitor progress toward the achievement ofthe new project activities.
P156250 | Strengthening the Science, Technology and Innovation System in Peru | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092523173510389/text/P156250093cfe10fa086410ad8e2e08cfb2.txt | http://documents.worldbank.org/curated/en/099092523173510389/pdf/P156250093cfe10fa086410ad8e2e08cfb2.pdf | The ICR identified a list of useful lessons and recommendations arising from the implementation of this project presented in theparagraphs 90-98.This review highlightstwo lessons which are rephrased below.(i) A comprehensiveand coordinated approach when strengthening the STI system needs to focus on supply of innovation, demand of innovation, and anecosystem that limits misallocation of resources. Achievements from this project indicate the benefits of innovation mightoccur if a countrys innovation ecosystem has: 1) the necessary conditions for firms to demand innovation, 2) qualified humancapital to supply innovation, and 3) an efficient allocation and accumulation of knowledge capital. This projects differentcomponents addressed these three aspects, that were primarily focused on the demand side, and adding pilot programs that overallpromotePerus ability to foster long-term innovation-driven productivity growth.To ensure structural impact, theexperience in this project suggests that these interventions require a strong collaboration between all actors of the STIsystem.(ii) Strong and coordinated institutions are critical to (i)a more efficient allocation of knowledgecapital and investments within the innovation ecosystem and (ii)sustain policy in the innovation space long enough to achievetangible results.The impact of innovation policy is contingent upon the institutional strength and stabilityofthe governing body of the STI system, as these institutions are critical to ensuringthe sustainability of policyinterventions. All project interventions transferred the capacity to CONCYTEC to conduct theseactivities independently in thefuture. Through these activities, relevant institutions now have an improved set of tools to use for the effective and efficientdesign and implementation of innovation programs. Many of the activities need significant time to show their impacts.As thebenefits of innovation programs tend to materialize in the medium to long term, it is key that Governments design policy agendasthat are forward looking.
P156252 | Long Term Export Finance | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2017 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/192851634307674092/text/Turkey-Long-Term-Export-Finance.txt | http://documents.worldbank.org/curated/en/192851634307674092/pdf/Turkey-Long-Term-Export-Finance.pdf | The first two lessons are drawn from the ICR (paragraphs 52-53), with some adaptation, and the third is offered by this Review.which takes a different position to that proposed by the ICRTechnical assistance, capacity building, advisoryservices, policy dialogue, and structural reform programs would complement line of credit operations in expanding the supplyof,and access to, long-term finance. This project formspart of a long series of World Bank financialintermediary operations targeting the export and SME sectors in Turkey over about two decades. The continuing series has beenjustifiedas a bridge until financial infrastructure constraints are lifted and alternative sources of long-term financeare developed, which can be a long-term process. Within this framework, programmatic advisory services anddevelopment policy operations focused on bank and non-bank financial services and on capital markets will begin to addressstructural impediments to developing a long-term finance market for exports and other economic activities.Theco-financing of sub-loanswould strengthen the economic impact of line of credit operations. This project didnot require the intermediary, the Turk Eximbank, or the participating financial institutions to co-finance the first round ofsub-lendingto SMEand large enterprise exporters. Yet, a co-financing mandatewould have magnified theeconomic impact of this operation beyond the original US$300 millionproject fund.Even the utilization of thesub-loan reflows wassubject only to a best efforts clause for the Turk Eximbank use its bestefforts to utilize repayments to finance additional development projects to further the development ofexporters.The World Banks leverage to require participating financial institutions to report ontheir lending activities inline of credit operations needs to be exercised with caution and courtesy. In thisproject, the ME design required a load of data from participating financial institutions including employment,loan-by-loan information, and company data the value for evaluation of which turned out to be questionable after the WorldBank did not conduct an evaluation of the net benefits of long term finance to exporters using the data collected from thelenders. Approaches that the World Bank could use in collectingdata from private entities engaged in projects include:(a) an assurance to the private entities that the results of any analysis of the data will be made available to them.
P156257 | Special Financing Facility for Local Development | Eastern and Southern Africa | Somalia | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2016 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/739241617717344366/text/Somalia-Special-Financing-Facility-for-Local-Dev.txt | http://documents.worldbank.org/curated/en/739241617717344366/pdf/Somalia-Special-Financing-Facility-for-Local-Dev.pdf | The ICR presented a number of lessons and recommendations (ICR, paragraphs 105 - 115). A few are provided below with slightmodification in text: Engaging early in crises may remove the perceived divide between humanitarianand recovery assistance. In this project,early recovery support to the most vulnerablepeopleaffected by the disaster wascombinedwith project activities. This strategyhelped clientstransitiontoward medium-term and long-term resilience building activities and allowed for preparing the follow-onproject. In anFCV environment, a government-led NGO implemented service deliverymodel maybe effective.Somalialackeda government institution to leaddisaster and crisispreparedness, crisis management, recovery planning and implementation. Recognizing that the government was graduallybuildingits systems and structures, partneringwith experienced civil society and others like the onewiththe Building Resilient Communities in Somalia (BRCiS) consortium under the project - proved useful and effective. This approachproved helpful in accessing hard to reach or security restricted regions. The partnership, where the government maintained itsleadership but delegated implementation to the consortium, enabled the government to show its ability torespondtodisasters andcrisesthe country faced and begin tobuild trust betweencitizens and state, andunderpin the legitimacy of nascent government institutions. Piloting small scale innovativeapproaches in FCV remains relevant. In this project, the State and Peacebuilding Fund allocatedUS$2.8 million fordrought response. This commitmentled to test the useof the International Non-Governmental Organizations (INGO)consortia to deliver recovery services, expanding the reach of newly forming institutions that areemerging from or amidpersistentFCV environment. The government has endorsed thisinnovativeservice delivery modelfordeploymentin a much larger scale under the follow-on project. Usingathirdparty may extend the task teams ground presencein FCVstates.In this project, the third party agent,Abyrint, carried out project supervision when security challenges emerged. In addition to regular mission support,Abyrintassisted implementing entities in addressing capacity challenges on the ground. Budgeting for these services enabledearly and frequent technical support that implementing entities and other partners needed to monitor theproject, mitigaterisks from prolongeddelays,and deliver uninterrupted trainingsupport tocounterparts. Adopting country systems toimplementprojects fosters confidence and boostsownership of the project.In this project, theBank agreed to use the countrys own systems to implement theproject. At closing, government officials from multiple jurisdictions expressed a strongownership of the project,whilefamiliarizing themselves with their own systems. Theyindicated appreciation for the assets delivered by theproject. Such ownership may facilitate commitment to mitigaterisks inmaintaining these assets.
P156363 | Nai Manzil - Education and Skills Training for Minorities | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2016 | 2021 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099145009262237992/text/P156363078c42b03d089380e80f91a67113.txt | http://documents.worldbank.org/curated/en/099145009262237992/pdf/P156363078c42b03d089380e80f91a67113.pdf | A strong outreach recruitment effort is crucial in ensuring appropriate youth participation: The projectundertook an extensive outreach effort that was crucial for the recruitment of intended beneficiaries. The PIAs included a varietyof activities, including mobilization camps, door-to-door visits, and newspapers. The door-to-door campaigns were used to connectwith families and convince them of the safety of the program, especially for girls.Community engagement with keylocal influencers promotes minority youth participation: Engagement with local influencers such as religious leaders andsocial activists can have a profoundimpact on the recruitment of religious minorities and women. Religious leaders played acrucial role in enabling the participation of Muslim youth and women in the project.Addressing Financialconstraints is key to alleviating demand-side constraints for disadvantaged beneficiaries: Under the project,financial support was crucial for ensuring enrollment continuation of beneficiary participation. The targeted beneficiaries of theproject were severely disadvantaged, and the stipends provided by the project helped address demand-side constraints toparticipation such as transportation costs. Thorough Needs assessment is key to ensuring quality design andimplementation: For a first-generation project, needs assessmentsare crucial to informingthe design of theproject and ME systems. The project embedded needs assessments in the design of the project that helped tailor projectactivities to the needs of the minority communities. The implementation illustrated that PIAs that were able to deliver higherpositive resultswere the ones who could adopt stronger strategies to address the needs of the beneficiaries such as poorwriting skills.
P156410 | Governance and Policy Program for Khyber Pakhtunkhwa (KP) | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062824121091599/text/P156410-243cc953-589c-4ab3-874e-a58626994d3a.txt | https://documents.worldbank.org/curated/en/099062824121091599/pdf/P156410-243cc953-589c-4ab3-874e-a58626994d3a.pdf | The following lessons are informed by the ICR and project documents (ICR, p. 31-33).Political ownership is neededto sustain momentum in governance reforms and ensure successful implementation of project activities. A significant factor in KPGovernance and Policy Program project was its strong alignment with the governments strategy and the project teamsresponsiveness to the governance challenges that surfaced during project implementation. Implementing agencies in KP led theprojects design and supervision of project activities, fostering a sense of ownership and commitment to project outcomes.Project implementation benefited from political ownership of reforms. Leadership and reform commitment in the implementing agenciesand participating departments was in place and was encouraged by the performance orientation of top political leadership (e.g., bydirectly seeking citizens feedback through the portal).Incremental Operating Cost (IOC) expenditures should beclear, subject to review and approval, and included in the operations manual to prevent ineligible expenditures from being includedin the budget. Since IOC spending does not pass through WBGs procurement review process, it can provide room forineligible expenditures. The case of KP Governance and Policy Program project shows that problems such as staff hiring without dueprocess, excessive spending on repair and maintenance of assets and inclusion of expenditures which were otherwise procurable innature that led to delays could have been prevented had there been upfront training on IOC rules at the start of the project andgreater scrutiny throughout the project by the Banks financial management team.Dedicated effort andstrategies are needed upfront to develop gender-sensitive approaches to capacity-building to ensure the inclusion of and impact onwomen. The case of KP Governance and Policy Program project shows that female participation in capacity building activities in KPwas low (11% of total trainees) at the beginning and became a constraint in rolling out a gender-sensitive approach to capacitybuilding because special measures to improve womens participation were not taken at an early stage of the project. Examplesof government policies that could have increased female participation in KP are related with mobility issues which could have beensolved by offering women virtual participation or providing training closer to the place of duty/residence or by improvingtransportation. Introducing incentives in hiring departments (or hiring managers) to ensure higher female employee participation intrainings or making relevant training mandatory for promotion in certain job descriptions to ensure that they did not exclude womencould also have been addressed by improved government policies.ICT-based solutions can improve public servicedelivery, but their success also depends on strong political leadership and the governments ability to hire and retainquality ICT professionals. The case of KP Governance and Policy Program project shows that innovative technology using ICT-basedsolutions can go a long way in improving public service delivery in countries or provinces where governments overalladministrative capacity is low. In KP, the technologies that made an important contribution were the establishment of a KPsCitizens portal to collect feedback and monitor responses; geotagging of public investment assets and schemes for efficientmonitoring and policy decisions; implementation of e-procurement systems to enhance transparency and monitoring; virtual hearingsof cases in the Secretariat for District Judiciary; and an e-stamp system for taxpayers facilitation. The project unit hadstaff for key positions including an ICT specialist. In addition, the use of ICT technology transformed citizensengagement through the citizens portal for the accountability of public services.
P156411 | Governance and Policy Project for Balochistan | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062924000528250/text/P156411-fca7b81b-d890-4115-a279-56b187faad6d.txt | https://documents.worldbank.org/curated/en/099062924000528250/pdf/P156411-fca7b81b-d890-4115-a279-56b187faad6d.pdf | The ICR draws the following three main lessons from the experience of implementing this project (ICR, p.28-29).Ownership is needed to sustain momentum in governance reforms and ensure successful implementation ofproject activities. A significant factor contributing to the success of the Governance and Policy Project for Balochistanwas its strong alignment with the governments priority areas and reforms defined under the Balochistan ComprehensiveDevelopment Strategy 20132020 and its responsiveness to the governance challenges that appeared during projectimplementation.There is a need to enhance focus on gender issues. The Governance and Policy Project forBalochistan had limited focus on gender issues. Before restructuring, the Project had a PDO level indicator on womenofficers participation in trainings, and an intermediate indicator on women feedback providers on school and irrigationfacilities. After restructuring, the Project monitored womens participation in training, and supported trainings in genderresponsive budgeting, gender audit, and anti-harassment of women at workplace. But the Project did not monitor gender disaggregateddata for complaints resolved by the Balochistan Ombudsman, thereby missing an opportunity for insight on women beneficiaries ofgovernment services.
P156412 | Federally Administered Tribal Areas (FATA) Governance and Policy Program | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062924002540418/text/P156412-13c820f7-4838-4fd1-981a-1d3bfb0216eb.txt | https://documents.worldbank.org/curated/en/099062924002540418/pdf/P156412-13c820f7-4838-4fd1-981a-1d3bfb0216eb.pdf | The following lessons are some of the most relevant and informed by the projects ICR (p. 30).Toproperly implement governance reforms and related projects, political ownership is important. In Pakistans FATAGovernance and Policy project, the governments request to restructure the projects design and results framework tosupport the newly merged areas of FATA and KP was fundamental to the projects ownership. In addition, the projectsstrategy gave implementing agencies key decision-making competences in the projects design and implementation of activitiesto achieve the projects objectives. The fact that the Additional Chief Secretary of GovKP was chair of the projectsSteering Committee also contributed to strong political ownership of the project.For efficient servicedelivery and transparency, technological interventions should be made a part of the proposed solutions. PakistansFATA Governance and Policy project the use of innovative technology was supported by the project. Examples include regularreporting of budget execution by using IFMIS or geotagging public assets in merged areas through GIS and MIS technology. Inaddition, technology also supported continuous capacity building through virtual trainings and helped increase the projectscost-effectiveness. However, the projects experience shows that the success of technological interventions also depends ontheir institutionalization. Strong political leadership and the governments ability to hire and retain quality ICTprofessionals was fundamental to the efficient delivery of technological solutions.Improved governmentpolicies for gender inclusion and high-level monitoring of their implementation are needed for low-capacity and fragilecountry/provincial project settings such as FATA. Female participation was low in capacity building activities supportedby the project in the merged areas (13% of total trainees). There were several reasons for this outcome that could have beenaddressed by improved government policies. Mobility issues could have been solved by offering virtual participation or providingtraining closer to the place of duty/residence or by improving transportation. Introducing incentives in hiring departments (orhiring managers) to ensure higher female employee participation in trainings or making relevant training such as PFM,procurement,sectoral planning, and project management and ME, mandatory for promotion in certain job descriptions areother policies that can foster gender inclusion.
P156422 | Third Village Community Support Project | Western and Central Africa | Guinea | IDA | Non-FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2016 | 2021 | 2022 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/455331625761120129/text/Guinea-Third-Village-Community-Support-Project.txt | http://documents.worldbank.org/curated/en/455331625761120129/pdf/Guinea-Third-Village-Community-Support-Project.pdf | The following lessons in the ICR stood out as important and relevant to other projects on decentralization, and are presentedhere with some editing.1. Strengthened stakeholder ownership and accountability at all levels and capacitybuilding at the grassroots can be vital for the long-term sustainability of local government actions. This project showedthat it was important to involve the stakeholders at all levels in the participatory local planning and budgeting process, namely,the central ministry in charge of decentralization, line ministries, state decentralized services, technical and financialagencies, local authorities, and local communities. It has a potential to improve the quality of investments, strengthen thestakeholders sense of ownership and accountability, and facilitate the resource mobilization to local development plans,which would result in the long-term sustainability of local government actions. Moreover, the projects experience indicatedtheimportance of outsourcing some capacity building activities to local NGOs. For example, recruiting and training youth fromthe local communities to provide technical support on IT tools and software to local governments would support decentralizationprocess in the long-term.2. Bottom-up participatory planning and budgeting of government activities can beeffective for conducting strategic policy dialogue for decentralization. The local government plans were not sufficientlyreflected in the government planning and the public investment budgeting at the national level. To address this, the projectsupported government reforms by: (i) ensuring the social inclusion of vulnerable and disadvantaged groups, such as indigenouspeoples, returnees, women, and youth, and (ii) working in urban environments and fragile conflict-affected areas, with an aim forlaying the groundwork for improved local governance. To further enhance the effective management of community activities in aparticipatory manner, provision of basic infrastructure and equipment to local governments and promoting local indigenous solutionsin communities would be essential.3. Improved financial management systems for facilitation of fiscal transfer andmanagement of tax revenues and fees with support from commercial banking facilities would be key for effectivedecentralization. This project institutionalized the financing of local communities annual investment plans,through the permanent financial mechanism. This achievement enabled to systematically transfer 15% of mining revenues to localgovernments. Concurrently, the project supported local communities to collect revenues and fees from local resources by reinforcinglocal service delivery, implementing micro-projects that fulfilled their needs, and strengthening their IT capacities with tailoredsoftware. In the future, supporting the communities to access commercial bank financing to improve their financial capacity wouldfurther scale up local projects.
P156444 | Second Programmatic Inclusive Growth DPO | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | IEG takes the following lessons from the ICR, with some modification of language: Even if aprogram goes off track because of adverse fiscal developments, it is important to continue a dialogue with the government so thatif the fiscal issue is solved, the program can continue. In the case of Georgia, the World Bank continued to have dialogue with thegovernment, with the result that even though the third operation was canceled, most of the triggers were met. Resultsindicators should be directed at outcomes rather than inputs. In the case of Georgia, a number of indicators measured inputs, whichhampered assessment of the overall impact of the program.IEG offers the following additionallessons: It is important to distinguish between development objectives what the program istrying to achieve, and the pillars how the objectives will be achieved. In the case of the Georgia DPO series these areconflated, which makes the impact of the program and the clarity of the results chain difficult to assess. Politicalresistance can be overcome by extensive outreach and simplification of processes. In the case of Georgia, making budget processeseasier to navigate overcame the resistance of local entities to the reforms, as did outreach. Eliminating an operation ina series if prior firm undertakings the government with respect to fiscal discipline are broken sends a clear signal to countriesthat these commitments are important. In the case of Georgia, the delay in processing DPO-2 and the cancellation of DPO-3 wereappropriate responses to the lack of fiscal discipline that led to the deterioration of the macroeconomicsituation.
P156455 | SEE Catastrophe Risk Insurance Facility TA SECO | Europe and Central Asia | Western Balkans |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2016 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/362221624635003924/text/Western-Balkans-SEE-Catastrophe-Insurance-Facility-TA.txt | http://documents.worldbank.org/curated/en/362221624635003924/pdf/Western-Balkans-SEE-Catastrophe-Insurance-Facility-TA.pdf | Three lessons are drawn from the ICR (pages 36-37), with some adaptation.Mandatory catastrophe insurancepolicies are essential to maintaining the financial sustainability of a regional catastrophe reinsurance system. Inthis project, Europa Re had to alter its business strategy after the SEE states failed to mandate compulsory catastrophe riskinsurance in their national markets. As evidentin other regional insurance pools afterwhich the SEE CRIF waspatterned, a mandatory system helps to ensurethat an adequate volume of insurance premium is generatedand that theregional system remains commercially viable and achieves economies of scale. The lack of national mandates would beassociated with lower market demand for catastrophe insurance products.Unconditional government aid touninsured homeowners and farmers in the aftermath of a disaster dampens the incentive to secure catastropheinsurance. In this project, the government in Albania continued tocompensateuninsured homeowners andfarmers without mandating the purchase of catastrophe insurance after two earthquakes in 2019, and so did the governments in NorthMacedonia and Serbia after major floods in 2014 and 2016 respectively. Governments typically consider post-disaster aid as apolitically favorable approach, and refrain from mandating compulsory catastrophe insurance which are viewed by voters as atax. Yet, unfettered disaster aid imposes fiscal costs on governments and discourages the transfer of risks to insurers.Astrong reinsurance partneris essential in establishing and sustaining a disaster risk insuranceprogram. In this project, notwithstanding the lack of mandated compulsory catastrophe insurance, Europa Re played acrucial role not only in acting as a reinsurer to private insurance companies operating in national markets, but as an enablinginstitution that built theunderlying disaster insurance infrastructure in the SEE region. In particular, EuropaRedeveloped the underlyingautomated online underwriting, pricing, and sales platform;designed theclaimsmanagement system based on remote sensing technologies;and carried out the advanced risk mapping and modeling work thatunderpinned insuranceoperations. Europa Realso trained hundreds of insurance agents working for local insurancecompanies and worked withnational regulators to ensure that the products could be sold in the SEEcountries.
P156473 | Strengthening Rights and Economies of Adat and Local Communities | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099011024091524591/text/P1564731c43a7203518dcf1b7cdb611fb20.txt | http://documents.worldbank.org/curated/en/099011024091524591/pdf/P1564731c43a7203518dcf1b7cdb611fb20.pdf | The ICR (p. 25-27) included several lessons learned, of which three stood out and were adapted with some editing byIEG: Issues related to land tenure security and land rights in indigenous communities are usually complexand require an integrated approach. In this project, indigenous people faced several challenges related to land tenuresecurity and land rights, deforestation and environmental degradation, lack of representation and participation, discrimination,and legal/social marginalization as well as forced evictions and displacement, requiring an integrated approach such as legalreforms, participatory decision-making processes, capacity building as well as defining community measures to prevent and resolveland conflict. Sustainable land management practices have the potential to enhance livelihoods among indigenouscommunities as well as protect the environment. This project demonstrated the positive impact of engagement of indigenouscommunities in implementing sustainable land management on livelihood enhancing opportunities such as increased income, improvedfood security, and stronger community cohesion as well as environmental conservation. Engaging with indigenouscommunities during project appraisal to ensure their buy- in as well as use their centuries old knowledge and practices can resultin effective, sustainable land-use strategies that benefit both, the environment and local economies. This projectconducted intensive stakeholder consultations with different government entities as well as local communities ensuring adequate andsuccessful buy- in to project implementation.
P156475 | Oromia National Regional State Forested Landscape Program | Eastern and Southern Africa | Ethiopia | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099052824170529634/text/P15647514e0e420601b72b1cdc6dd672381.txt | http://documents.worldbank.org/curated/en/099052824170529634/pdf/P15647514e0e420601b72b1cdc6dd672381.pdf | The ICR (paras 104-115) presented eleven lessons. Three of them are presented below with rephrasing as these may inform thesimilar operations regarding the Emission Reductions Purchase Agreement (ERPA).Developing a solid understandingregarding the following key factors may support successful implementation of Emission Reduction (ER) and Emission Reduction Credit(ERC) payments: (i) identify the type and scale of interventions in forestry and agriculture that generate ER; (ii) assessthe importance of addressing fundamental issues and reforms related to land use and private sector business climate, includingaccess to financing; and (iii) analyze if and how a better interface between forestry and agriculture contribute to the intendedresults.Establishing the required Emission Reduction Payments instruments such as Monitoring, Reporting, andVerification systems and Benefit Sharing Plan may ensure adequate preparation resources. Along the same lines, the timelydesign and implementation of adequately funded complementary livelihood interventions to forest-dependent communities is essentialto generate community motivation, capacity building and engagement in the longer-term benefits pursued by theprogram.Providing regular and close monitoring and supervision at lower level (woreda level) may address the majorproblems created by staff turnover and lack of motivation. This project experienced a challenge of high staff turnover,particularly among woreda coordinators, which resulted in the limited technical support provided to A/R and PFM cooperatives insome project woredas and kebeles (ICR, para 81). Organizing training for woreda level staff and explaining the nature of theproject is also critical to addressing root causes of motivational issues.IEG adds the following lesson regardinglivelihoods based on the project documentation review.Measuring outcomes of livelihood support investments and towhat extent these contributed to incentivizing the communities to participate in the PFM system and the ER system may strengthenthe enabling environment for implementing the ER and the ERC payments in communities. Behavioral changes by communitiesand farmers largely depended on incentives from grant support for livelihoods, according to the testimonies provided by a group ofrepresentative beneficiary communities during the May 2023 ICR workshop (ICR, para 102). However, no evidence was providedregarding any outcomes related to incentivizing the communities to be involved in the PFM system and the ER system. The ICR (para81) noted that the projects livelihoods support investments did not fully achieve the expected benefits due to theinsufficient budget allocation and the limited business skills and experience among A/R and PFM cooperatives. The project task teamnoted that, if they were to repeat the project, the livelihoods of communities would take a higher priority during design to ensurealignment of incentives with the project objective, as well as grants to beneficiary communities, would start earlier in order toexpand and to allow more time to implement, support, and improve the support provided to households (Task Team Response).
P156479 | Chad Safety Nets Project | Western and Central Africa | Chad | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2020 | 2021 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/813861600205618109/text/Chad-Chad-Safety-Nets-Project.txt | http://documents.worldbank.org/curated/en/813861600205618109/pdf/Chad-Chad-Safety-Nets-Project.pdf | 1. If the objective of a project is to pilot interventions in a given country context, then the results framework needstobe tailored to this purpose. Particularly in a re-engagement project in a fragile country context, the RF for the project should gobeyond institutional accomplishment indicators and indicators of beneficiary reach and devise some indicators which shed light onfactors which contributed to success or challenges for the pilot, including delays. Then, when scale up is implemented, the designcan be based more accurately on actual experience and learning. In this project, the RF indicators for the pilot interventioncomponents focused almost exclusively on coverage and did not include enough IRIs to reap full lessons learned. The analysis ofcauses of delays and bottlenecks had to be mostly based on supervision observations, with little help from the RF (ICR, paragraph95).2. For projects thatrely on local implementing agencies and NGOs in addition to Government, often in a fragilecountry context, it is important to assess the availability and capacity of these local entities upfront,and not just focuson capacity assessment and institution-building for the Government. In this project, labor-intensive implementation ofsub-components (for CfW) (and its monitoring until the MIS was up and running) depended on local implementing agencies. Theircapacity was lower than expected. Thus, technical assistance provided for completion of the project had to be broadened to includethis non-Governmental sector, requiring more resources (ICR, paragraph 96).3. Cash for Work (CfW) activities aresignificantly more costly and difficult to roll out than simple cash transfers (CTs), particularly in a fragile country situation.In this project, US$1.00 yielded benefits of US$14.75 for CT beneficiaries, but only US$2.67 for CfW interventions. The latterfigure is comparable to costs of CfWs in other neighboring countries. In this project, although targeting and labor intensityindicators were high relative to other countries, factors increasing complexity and costs included delays in planning public worksactivities, lining up tools and protective equipment needed, and securing environmental approvals. While there still may be validreasons to choose cash for work over simpler CTs, the differences incost-benefit ratios are significant and likelygeneralizable across countries (ICR, p. 52, Annex 4, paragraph 2).4. In cash transfer programs, the use of communitycommittees for target validation and payment oversight has some advantages, but incentives also need to be considered. In thisproject, the use of such committees led to difficulties when some members who were not beneficiaries, (received no transfers)became discontent and did not fully fulfill their role, as observed under the project (ICR, paragraph 99).
P156505 | Vanuatu Infrastructure Reconstruction and Improvement Project | East Asia and Pacific | Vanuatu | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR (p. 23-24) included several useful lessons learned which were adapted by IEG: When World Bankprojects are being implemented in countries with limited capacity and staffing to manage key areas such as safeguards, financialmanagement and procurement, resources need to be made available to allow for training of government and Project Management Unitstaff. In this project, the government and PST faced challenges to complete and submit Interim Financial Reports andannual audits in a timely manner due to limited knowledge of requirements and despite training and support being provided afterproject effectiveness. The reasons were related to high staff turnover. This could have been addressed by appointing a seniorfinance staff from the payroll department to review and clear financial management reports. Strengthening thecapacity of local contractors might positively impact resilience and allow for a more effective and timely recovery immediatelyfollowing natural disasters. This project focused on working with island-based contractors/small-scale contractors insteadof identifying international contractors, even though it was more time-consuming. However, this might ensure a faster responsivetime in case of another disaster due to the local contractors understanding of local realities and being onsites. Strengthening construction supervision and quality control through using digital survey tools can bebeneficial for projects that are widely geographically spread. This project did not use such tools due to capacity,information and communication technology, and logistical constraints. However, the project could have benefitted from adopting suchdigital tools, especially for critical construction verification activities.
P156507 | GEF China Sustainable Cities Integrated Approach Pilot | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2018 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The following are key lessons extracted from the ICR with some amendments to the language by IEG:Interventionsregarding TOD strategies for cities are more likely to have success when they are adapted to the distinct stages of urbandevelopment of each city. The incorporation of TOD into city strategy is heavily influenced by the development stage ofthe rail transit system, which serves as a reflection of the citys overall planning and development level. In this project, inthe cities where the rail system was in its initial stages, the TOD strategy concentrated on leveraging new rail lines to optimizethe existing urban spatial structure. In cities with more advanced rail systems, the challenges shift toward maximizing theefficiency of new rail stations to alleviate existing transportation congestion and foster regeneration.Theintegration of TOD into long-term urban development is more likely to be achieved if the role of the private sector is encouraged,especially the real estate industry, which is a major source of investment. Many companies find themselves hesitant toinvest in TOD, given its higher demands on both human and capital resources compared to conventional investments. This reluctanceexists despite the governments implementation of numerous encouraging policies, and it limits the potential scope of TOD. Inthis project, the inclusion of private sector capital was identified as a critical need for financial sustainability in the case ofTianjins corridor-level TOD application- Rail Transit Financing research.Active, consistent engagement by anational ministry can significantly boost the impact and sustainability of cities good practices. Participatingcities developed separate approaches to mainstreaming TOD principles into local contexts. A central-level PMO can leverage theseapproaches and increase the possibility of incorporating them into national guidelines and leading the dissemination of goodpractices within the country. Under the project, the establishment of the National TOD Platform fostered a collaborativeenvironment where cities could mutually benefit from shared insights. Simultaneously, the distillation of lessons learned fromthese cities was valuable input for enhancing pertinent national-level policies.In addition, IEGdraws the followinglesson:Relevant indicators measuring actual change in behavior and practices are needed to measure the results ofa technical assistance project with significant expenditure. In this project, the indicators were at the output andintermediary outcome level and did not provide evidence of tangible results on the ground e.g. increase in use of public transport,especially given the significant expenditure on this TA project.
P156559 | MZ - Emergency Resilient Recovery Project | Eastern and Southern Africa | Mozambique | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2016 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099639312222223042/text/P156559-9338e71b-df1f-4976-a6af-a8a96ed03aed.txt | https://documents.worldbank.org/curated/en/099639312222223042/pdf/P156559-9338e71b-df1f-4976-a6af-a8a96ed03aed.pdf | The ICR included several lessons. The following three are emphasized with some adaptation of language: Toachieve acceptable levels of resilience, the recovery of infrastructure requires time, expertise and comprehensive technicalstudies. Due to the urgency of relaunching agricultural production in the Licungo River Basin, the initial rehabilitationof the Nante and Nicoadala dikes and the Intabo and Munda-Munda irrigation schemes under the project was done under emergencyconditions, using designs and feasibility studies already prepared by Government, development partners and existing WB projects.These infrastructures were further damaged by cyclone Idai in 2019, thus reflecting insufficient resilience in design. The secondrehabilitation of the Munda-Munda irrigation scheme, all water supply infrastructure and classrooms were preceded by either acomprehensive vulnerability analysis or feasibility and technical studies, and each infrastructure was designed to be resilient tothe prevalent flood, cyclone, and drought risks. This required significant time and effort from Government technical staff and theWB team to adequately conduct the necessary due diligence. As a result, all infrastructure recovered or built following therecommendations of technical studies and designs showed adequate resilience to all cyclone and flood events that occurred between2019 and early 2022. Appropriate coordination among all relevant stakeholders is critical to buildsynergies, alignment, and impact of recovery projects. The project established consultation, coordination and informationexchange mechanisms with relevant developments partners. Through these coordination mechanisms, overlaps and duplication of effortswas avoided and complementarity and impact on the ground was increased, including gradual up taking of outcomes and lessonsgenerated by the project.
P156629 | Macroeconomic & Fiscal Management Operation | Western and Central Africa | Guinea | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2017 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/687631593007540971/text/Guinea-GN-Macroeconomic-Fiscal-Mgmt-Operat.txt | http://documents.worldbank.org/curated/en/687631593007540971/pdf/Guinea-GN-Macroeconomic-Fiscal-Mgmt-Operat.pdf | Three lessons are drawn from the ICR (pages 34-35), with some adaptation.A reformprogramcould benefit from political economy assessments of difficult reform measures. In thisseries, the government reversed a prior action for the first operation, lowering the VAT rate back to 18 percent from a target 20percent after consumers and firms mounted large demonstrations against the VAT reform measures, a public response that was notflagged in discussions of risk at appraisal. The public also objected to the exclusion of flour and edible oils from the VATexemption list. Additionally, an original trigger to the second operation, increasing the participation of the private sectorin fertilizer importation, was dropped and replaced by a substitute prior action, improving the management of, and raising fundingfor, rural roads, after the original trigger gained little political support as DPF2 was prepared.Technical assistance to fragile countries with weak institutional capacity could make the difference between successor failure in implementing reform measures. In this series, the government performed better with reforms to the FNDLthan with reforms to the FODEL systems. The Third Village Community Support Project and the Support for Local GovernanceProject delivered crucial technical assistance inputs aimed at building the capacity ofmunicipalgovernmentstoaccess and utilize FNDL funds. No similar technical assistance or complementary investment project wasdelivered to help build the institutional capacity of prefecture or municipal governments to plan or manage FODEL projects.The technical assistance was even more crucial for the FODEL, as prefectures and municipalities had to prove compliance with EITIstandards to tap FODEL resources.Implementation timetables for reform plans have to be better aligned withelectoral schedules or have contingency plans if electoral schedules were disrupted. In this series, implementationof reforms to the FODEL system stalled after local government elections were delayed for more than a year. CAGF unitsrequired membership from local governments, and FODEL operations required the training of local government officials. Neitherstep could proceed until local elections were completed and new local governments were installed after a lengthy delay.
P156651 | Productivity and Transparency Support Credit | Western and Central Africa | Sierra Leone | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2019 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/099225011162242295/text/P1566510949ef0061092a10f90590884363.txt | http://documents.worldbank.org/curated/en/099225011162242295/pdf/P1566510949ef0061092a10f90590884363.pdf | Three lessons from the ICR are critical, with someadaptation.A firm commitment by the government to exitan industry in favor of the private sector can help encourage private enterprises to enter, invest, and do business in theindustry. In this series, the passage by Parliament of the Sierra Leone Seed Certification Act of 2017 and theissuance by the Ministry of Agriculture andForestryof the Seed Certification Agency Regulations of 2020 helped firm upa government decision to exit the agriculture inputs market and to promote the production, multiplication, and distribution ofseeds by the private sector instead. By the closing date, authorities licensed thirty-four private enterprises to operateasseed growers, processors, sellers, exporters, and importers. A similar strategy for fertilizers followed the adoptionby the Cabinet of a new fertilizer policy in 2017 to progressively reduce the public sectors role and encourage the privatesector to supply and distribute fertilizers instead. Only the slow organization of the NaFRA created by the NationalFertilizer Regulatory Agency Act of 2017 stalled the licensing of private fertilizer firms. However, at least 50privateenterprises had submitted expressions of interest.Reform measures can succeed better if they reflectthe implementing agencys institutional, technical, and financial capacity. In this series, systems losseswere not reduced to 28 percent as targeted butrose from 38 in the baseline to 39 percent at closing. The EDSA onlypartially implemented the NCOP using its available corporate resources and supplemental resources provided by the Bank. TheEDSA rehabilitated only 30 percent of medium-voltage and low-voltage networks in the electric power distribution system,handicapping the effort to reduce technical losses by about ten percentage points. Moreover, the EDSA could not procure andinstall bulk meters in time under a separate project toreducecommercial losses. This measure was not part of thisseries but would have helped reduce total systems losses. According to the ICR, the Bank overestimated the capacity of theEDSA to implement the reforms.Consistent and dedicated preparatory work on reform legislation can eventually payoff even if the initialpolitical environment was not conducive to the reform effort. In this series,theExtractive IndustriesRevenue Bill had been deadlocked in Parliament since2014, three years before the approvalof the first operationin 2017. However, the government bureaucracy persisted in arguing the merits of unifying thefiscal regime for the mineral sector, which suffered from inconsistency, lack of transparency, and poor efficacy in raising mineralrevenues to their estimated potential. The Bank included the bills passage as a prior action of the second series, andthe enactment by Parliament of the Extractive IndustriesRevenue Act of 2018 fulfilled the prior action. According tothe ICR, the dedicated work by the bureaucracy was instrumental in advancing the reform process untila new government,elected into office in the general election of 2018,was sufficiently convinced tosupportthe reform objective andthe proposed legislation.
P156655 | Indonesia Fiscal Reform DPL | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2022 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099630002032238414/text/P1566550ccf9b40520b6c00eebba5cfaf58.txt | http://documents.worldbank.org/curated/en/099630002032238414/pdf/P1566550ccf9b40520b6c00eebba5cfaf58.pdf | The ICR (p. 34) offered the following lessons appropriately drawn from experience with this DPL series, with some adaptation byIEG:DPLs should prudently consider political economy constraints, secure commitment at the highest levels, andconsider the election cycle. While there was generally a strong technical understanding of the underlying politicaleconomy constraints and agreement on the proposed reforms, governance-related risks were high and mitigating measures were unableto avert their materialization. Reforms often need cabinet support, thus requiring a coalition of stakeholders beyond theimplementing agency. Strong continuous buy-in from the Ministry of Finance and line ministries, including delineation theresponsibilities of each entity, also are key to facilitate the supervision and implementation of the operations, while reconcilingtheir sometimes conflicting objectives. Finally, the pace of reforms typically slows during pre-election periods, while politicaltransitions may also pose considerable risks for reversal of ongoing reforms. Although the government has retained its commitmentto tax reforms and resumed them after the elections, the pace was much more gradual [and] over a longer time horizon thaninitially expectedthe strength of sector interests was underestimated (TTL response).The design ofDPLs should rest on a vision and strategy that reflects high-impact priorities. Reforms that support existing governmentefforts with prior actions that are evidence-based are more likely to succeed. The policy actions included in thisprogrammatic DPL series drew on government plans and were supported by a strong body of analytical evidence. However, some actionsthat would have been important to move forward along the results chain were avoided or mitigated due to politicaland technical constraints (outside of the Banks control) (ICR, footnote 55). To minimize the impact of political andtechnical impediments, the design of a programmatic policy series should rest on high-impact priorities (in the short-run) andlonger-term investment in institutions or capabilities.The design of DPLs should also carefully consider the mostappropriate sequencing of reforms. For instance, tax administration capabilities had to be built up before tax policyreforms could be attempted successfully. A key lesson from this DPL series is that preparation should probably start after keylegislation is passed in Parliament, so that the operations can focus on implementation. Moreover, if prior actions are notfollowed up as intended and reforms are either delayed or dropped, it would be advisable to review the entire strategy, rather thanpostpone key actions (i.e. indicative triggers) to subsequent DPLs. Key reforms should not be backloaded, especially close to anelection since the latter often undermines strong prior actions. The most difficult reforms should be pursued in the firstoperations of a programmatic series, which can then be consolidated and deepened rather than trying to build momentum withweaker reforms.Some complex reforms may be better pursued with a results-based operation, rather than with a DPL.The DPL series enabled the Bank to support a wide range of key fiscal reforms, but it was sometimes challenging to definea clear result soon after the end of the DPL series. Some reforms, such as the introduction of a subnational chart of accounts,might better have been included in a results-based operation to reflect the complexity of the reform, with more and smaller reformsteps and a longer time period to achieve results.Building on these lessons, two further points can bemade: Be explicit on the results chain and implementation measures needed to carry forward reforms that havebeen initiated. Although the ICR (p. 34) states that some reforms that can no longer be pursued through the DPLseries have been subsequently supported through other instruments (e.g. TA engagement) with positive results, necessary nextsteps were often unclear, nor was it clear from the documentation whether and what mechanisms were in place or expected to supportimplementation of some measures that were introduced later in the series (e.g., with respect to disaster mitigation and climatechange). Consultations with domestic stakeholders: Failure to consult with domesticstakeholders in the course of design may have contributed to underestimation of the pushback from private interests and others that stalled Parliamentary passage of some of the key tax reforms.
P156679 | Health System Performance Reinforcement Project | Western and Central Africa | Cameroon | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099062724185039534/text/P156679-86d793b7-e9e8-41a0-a0b7-977157322c02.txt | https://documents.worldbank.org/curated/en/099062724185039534/pdf/P156679-86d793b7-e9e8-41a0-a0b7-977157322c02.pdf | The ICR (p. 28) offered several lessons and recommendations, including the following lessons, partially re-stated byIEG:Despite positive momentum, scaling up too quickly can limit the ability to adopt previous learning and buildfrom experience. The project seized momentum and government commitment to prioritizing the PBF model. However, the pace ofscaling up the project proved to be overly ambitious, given capacity constraints and the lack of PBF experience of the new nationalimplementation unit. A more sequential approach would have also helped to fully internalize the lessons from the previousoperations: the conclusions of the ICR and the impact evaluation of the PBF model of the previous operation were not shared untilwell into the implementation of this project, limiting the adoption of recommendations made.Alternative approachesfor PBF verification mechanisms, such as using representative samples, can offera more cost-effective solution, especially in resource-limited contexts. Verification mechanisms may entail trade-offsbetween effectiveness and efficiency when including all health facilities. While it potentially contributed to improved healthservices utilization and quality, findings from a recent impact evaluation suggest its effectiveness may not be significant. DeWalque et al. 2021 showed that outcome differences between the PBF (treatment group) and the increased financing group (controlgroup where no PBF verification mechanisms were included) were not statistically significant using data from the PBF pilot phase.The project incurred significant overrun costs for verification, with a large portion of the budget allocated to this process.Moreover, an audit of verification agencies revealed inefficiencies and a lack of transparency, further questioning the value ofsuch verification mechanism. Instead of implementing costly verification arrangements for all health facilities, the project couldhave opted for a more targeted approach, that strategically allocates resources to achieve effective oversight while minimizingcosts.Maintaining continuity within project teams and implementing sound handover arrangements are critical toensure effective project implementation and supervision. Implementation suffered from frequent team changes, notably TTLsfrom the Bank side and also the departure of the PBF expert in the CTN, resulting in a significant loss of expertise and continuityin PBF both within the World Bank team and the CTN, which seemed to have occurred with limited handover processes, and persisteduntil the projects conclusion.
P156687 | Himachal Pradesh Public Financial Management Capacity Building Program | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | PforR | 2017 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060524104534098/text/P1566871c2e6030731bc31168b22abb9330.txt | http://documents.worldbank.org/curated/en/099060524104534098/pdf/P1566871c2e6030731bc31168b22abb9330.pdf | The ICR presents seven lessons (p.28/29) based on the experience of this PFM capacity-building Program in HP, two of which areworth highlighting here. Both these lessons pertain to projects/programs thatare technology-intensive: Investments in process automation ensure business continuity in times ofcrisis. This Program was IT-intensive and involved multiple DLIs directed towards automation of GoHP business processes.These very investments turned out to be helpful in maintaining some level of business continuity during the COVID-19 pandemic whenlock-downs and social distancing made physical in-office presence challenging. When/if automation does not affect underlyingbusiness processes, the use of back-up paper files becomes imperative. However, where automation results in a thoroughreview and modification of the underlying business processes, there is a greater likelihood of success. CreatingIT capacities up-front is a fundamental requirement in technology-intensive programs. While software development andimplementation can be outsourced to solutions providers, in-house personnel with deep IT knowledge and project management skillsare needed to ensure (a) that the right solutions are being applied and (b) that the changes will besustainable.A third lesson that can be drawn from this Program has to do with the reformchampions. The GoHP PFM capacity building Program relied heavily on the championship of the designated nodal officer(Additional Director Treasuries), and on the Additional Chief Secretary (Finance), who served as chair of the steering committee.The lesson here is that it is best not to place all eggs in a single basket. The ICR notes that there was turnover of key personnelin the participating departments; however, the designated nodal officer provided continuity and leadership to the Program. Whatwould have happened in the absence of this nodal officer? Fortunately, the Additional ChiefSecretary (Finance) was also thereto provide leadership and continuity. The Program was very fortunate to have had both these seniorofficials throughout the implementation period.
P156761 | Third Programmatic Resilience Building Development Policy Credit | Latin America and Caribbean | Grenada | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest |  |  | The following two lessons are taken from the ICR with some adaptation of language: When designinga programmatic series, it is important at the outset to be realistic about what can be accomplished, taking into account capacityofgovernment counterparts. Excessive optimism or complexity, such as that involved in the design of some components of thisprogrammatic series, results in having to adjust subsequent operations to reflect the reality on the ground. Political economyfactors in small countries, such as Grenada, may be of an order of magnitude different from those in large economies. For example,downsizing government departments must take account of scarce alternative opportunities; only a limited pool of potential investorsmight be interested in investing in PPP projects in a small economy; and skills and capacity may be scarcer.Creation of new administrative agencies can lead to mission overlap and higher fixed costs. This series required the creation ofnumerous new units and agencies, where assigning responsibilities to dedicated staff in existing units might well havesufficed.IEG draws the following three additional lessons: Adequaterecognition at the design stage for technical assistance (TA) requirements can assist the successful development and implementationof a reform program. In this case, relying on regular support from the World Bank team, and other external partnersproved insufficient. More could have been done to mobilize resources for targeted TA for certain particularly complex initiatives,and through leverage of the investment lending portfolio. While including legislation, new regulations, and otherpieces of paper within prior actions is appropriate, a program that does more to ensure practical application on theground stands a greater chance of success. Here, much new legislation was approved, but in several cases the capacity or politicalwill to apply the modified legal and regulatory framework was not manifest. Particularly in small economies withlimited implementation and coordination capacity, a relatively simple reform program focused on a few key areas stands a greaterchance of success than a wider-ranging initiative. In this case, the relative lack of success was due in no small part to anover-ambitious design involving ten sectors and thirteen agencies.
P156766 | Access to Long Term Finance | Europe and Central Asia | Ukraine | IBRD | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099120524174542238/text/P156766-81a00190-3601-49e8-9c45-5f38a8540c3a.txt | https://documents.worldbank.org/curated/en/099120524174542238/pdf/P156766-81a00190-3601-49e8-9c45-5f38a8540c3a.pdf | The following three lessons are from the ICRwith some adaptation of language: If implemented inconjunction with reforms supporting the same objective, the credit lines to support SMEs access to finance can helpachieving development outcomes more effectively. In the case of ALTP, the country experienced significant shocks duringthe implementation period. It can be reasonably expected that, in the absence of a stable macroeconomic performance and effectivelegal framework, chances of developing sustainable long-term finance would be low. The development outcome could have been moresignificant if the implementation of other supporting reforms on facilitating development of long-term investors, such as pensionfunds, and enhancing capital markets had not stalled. Availability of foreign currency hedging instruments underthe credit line operations or providing loans in foreign currency can increase attractiveness of offered funds to beneficiary SMEsand PFIs. According to an NBU survey, about 80 percent of businesses in need of a loan would be seeking financing in localcurrency. In the case of Ukraine, SMEs typically do not have access to financial instruments such as currency swaps or forward rateagreements which impedes them to hedge against currency risks. The project did not prohibit UEB from providing sub-loans to SMEs inlocal currency, which suggested that PFIs would have to hedge against the currency risk or take the currency risk on its balancesheet within the prudential limit. Hedging against currency risks and more expensive pricing on the WB financing reduced itsattractiveness for the PFIs. In countries where WB engages in credit lines on a consistent basis, having aprovision for re-lending funds refunded by PFIs to the wholesale bank, can help continuity of operations. As mentioned inthe efficacy section, the low participation of small private PFIs in the project was due to difficulty in complying withthe eligibility criteria. As for larger banks it was due borrowing in foreign currency. In fact, most of thefunds that UEB disbursed to PFIs were pre-paid or returned. The project did not call for UEB to re-lend any funding reflows fromPFIs under similar terms. Under the ALTP, it is assumed that funds returned by PFIs were used by UEB to continue financing theircore clients, export-oriented SMEs. However, there is no record of such reflows in the project reporting within the lifetime of theproject
P156777 | Kenya Urban Support Program | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | PforR | 2018 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100724163522054/text/P156777-a1288e83-0aeb-4b92-86f1-cbcd9072c46e.txt | https://documents.worldbank.org/curated/en/099100724163522054/pdf/P156777-a1288e83-0aeb-4b92-86f1-cbcd9072c46e.pdf | The following lessons were reported in the ICR, here with some amended language:Comprehensive and continuouscapacity building in a hybrid PforR and timely monitoring can help reduce delays and improve the Programs results.For PforRs, it is key that the government has the resources to provide the needed capacity-building and program management support.In the context of Kenya, adding a national-level DLI would not have guaranteed that a sufficient budget was allocated, so the IPFmodality offered a solution. It also allowed the Bank to provide more hands-on support in implementing capacity building andTA.Including national-level agencies responsible for ES standards in Program design can mitigate ESS issuesby supporting oversight. KUSP supported extensive infrastructure investments at the urban areas level, which requiredconsiderable safeguards capacity building at the county and urban areas level. However, the Program suffered from numerous ESissues as described in previous sections. Close collaborative working arrangements with key regulatory agencies to i) ensure thatMunicipalities comply with environmental permit conditions and ii) provide capacity building to municipalities and counties tomanage environmental, health and safety risks based on national laws and regulations may enhancecompliance.Partnering with accurate stakeholders and providing hands-on support may contribute to thePrograms success. During implementation, the National Program Coordination Team (NPCT) engaged closely withrelevant national departments and agencies and had a pool of technical experts to provide hands-on training and capacity building.NPCT worked closely with Council of Governments to strengthen inter-governmental relations, coordinate capacity-building activitiesand policy and legislative review and development, and provide support for program coordination, including social risk managementand FM. The strong engagement with Council of Governments became an integral element of KUSP success by troubleshooting problemsand enhancing coordination and communication with Counties and Municipalities.A robust APA process may enhance thePrograms success. Several factors challenged the APA process in KUSP, such as lacking QAR documentation, MC and PSwaivers granted without proper documentation, the finance agreement not clearly linking the definition of the MCs and PSs to thePOM (and agreed changes not revised in the POM), and some political interference by the Program Steering Committee with the resultsof the APA. Keeping these challenges in mind for future project designs may enhance implementation and results.
P156778 | Belarus Health System Modernization Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2017 | 2024 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR (p. 23) included several lessons, adapted here by IEG: Planning for extra time for developing andimplementing complex solutions can avoid delays and the need to extend a projects implementation period. Forexample, in this project, e-health solutions took longer than envisioned given the complex procurement process and challengesrelated to coordinating with multiple stakeholders, resulting in implementation delays. When project activitiesextend beyond one sector, cross-sectoral cooperation is key for a successful project outcome. In thisproject, all decisions related to the development of the Central Health Information System were coordinated and agreed with theMinistry of Economy and Ministry of Communication as part of development and implementation of the national programDevelopment of Digital Information-based Economy and Society for the period 2016-2020. This collaboration includedthe development of ICT legislation and regulation, standardization of health care digital data anddata exchange protocols,etc. In addition, the RSPC MT and health authorities at the local level jointly worked on development and implementation plans fordigitalization and integration of local health facilities into the CHIS, specifying necessary investments in each facility andimproving capacity.
P156837 | State Owned Financial Institutions Strengthening Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2018 | 2023 | 2024 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040124151010372/text/P156837117149f06b1a79b1a04740e1c3d9.txt | http://documents.worldbank.org/curated/en/099040124151010372/pdf/P156837117149f06b1a79b1a04740e1c3d9.pdf | The following lessons are derived from the ICR (pp. 29 and 30):The continuous ownership and commitment of theborrower/implementing agency and continuity in the World Banks project team can be critical in achieving developmentoutcomes and ensuring the sustainability of the reforms in the financial sector. In the case of the SOFI Project,starting from the appraisal, GoS showed strong commitment and determination to implement the SOFI reforms. Despite challengingconditions imposed by the COVID-19 pandemic and other external developments like Russias invasion of Ukraine, higherinflation, higher energy prices, and interest rate hikes, the continuous commitment of the GoS to the reform process enabled theachievement of the project results. In addition, the project had the same Task Team leader from project preparation to projectclosing. This significantly contributed to staying on course and achieving the project objectives.Collaborationwith other donors particularly can improve and reinforce project implementation and the achievement of project results.During the implementation of the SOFI Project, the IMF Standby Arrangement (SBA) and Project Coordination Instrument (PCI)contained a clause that reinforced the importance of the IBRD SOFI loan results, elevating the importance of difficult reforms. Thetechnical merits of the reforms covered under the SOFI Project that were embedded in and contingent on the IMFs SBA and itsPCI proved to be a strong combination in ensuring the successful implementation of the project. The collaboration between theIMF and the World Bank teams was enhanced during the implementationwith regular joint missions to Serbia and meeting with theSerbian authorities.A relatively simple but focused project scope can significantly contribute to achieving reformobjectives in the financial sector. The ICR reports that a broad set of financial sector topics, such as capital markets,insurance, and other subsectors, were potentially considered as part of the project design during project preparation. However,considering that the SOFI alone was already a complex sector for reform, instead of having a wide breadth covering many financialsector segments, the Projects scope was simple and restricted to the SOFIs with a deep focus. This approach facilitated theachievement of project results.
P156849 | Support for Autonomous Higher Education Project (SAHEP) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2017 | 2023 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099121224023513320/text/P156849-5f39fe2e-a9cf-4511-8c28-da974ac3acce.txt | https://documents.worldbank.org/curated/en/099121224023513320/pdf/P156849-5f39fe2e-a9cf-4511-8c28-da974ac3acce.pdf | The ICR (pp. 32-34) contained a range of insightful lessons, including:It is possible to overlook key risks andpreparatory steps when approving a project as a country is transitioning from IDA to IBRD lending. In this case, rushingto take advantage of the countrys IDA allocation before graduation to IBRD meant that some essentialpreparatoryactivities, approvals, risk analyses, and feasibility studies were not ready by effectiveness.Decentralizingproject management responsibility to beneficiary implementing agencies can build ownership for results, but this is likely to bethe case only when there are relatively few implementers and capacity is already robust. In this case, university-levelimplementing agencies, under MOET coordination, were able to ramp up quickly and effectively respite lack of prior familiarity withBank procedures and requirements. Delegation of responsibility to them helped build their confidence and commitment to projectactivities and outcomes.Completion of land acquisition processes, or at minimum, identification of acceptablebackup plans in the event that acquisition falls through, is a prerequisite for approval of project financing. In thiscase, significant time and effort were expended on a university whose participation could not move forward in the absence of theseapprovals.Higher education institution accreditation requires not only capacity but incentivization. Inthis case, targets for institution-level accreditation were not reached because of cumbersome processes and lack of significantreward for having completed the process. Institutions need both the carrot (assistance and incentives) and stick (compliancemeasures) to encourage them to navigate complex, comprehensive assessment processes at the institution rather than just thedepartment or program level.
P156858 | BOOSTING HUMAN CAPITAL AND PRODUCTIVITY DEVELOPMENT POLICY FINANCING WITH A DEFERRED DRAWDOWN OPTION | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2021 | 2023 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099510007122221550/text/P15685805dc48706a0a1f108a9c48e1ae92.txt | http://documents.worldbank.org/curated/en/099510007122221550/pdf/P15685805dc48706a0a1f108a9c48e1ae92.pdf | Three lessonsare drawn from the ICR (pages 27-28), with some adaptation. The fourth is offered by this ICR Review,albeit in disagreement with another lesson cited by the ICR (paragraph 67).Using objective criteria for theaccreditation and licensing of schools can help counterpolitical challenges to reformsineducation.In this project, theSuperintendence of University Education and the GeneralDirectorate ofUniversity Education setobjective criteria for rating the quality of university programs and for issuingoperating licensesto universities. This technical methodfor licensing universities was easily understood andreadily supported by the public, according to the ICR. Moreover, it is expected to serve asan effective deterrent tofuture attempts to politicize the licensing process, a likelyreaction from vested interests that will be hurt by the strictimplementation of the quality assurance program.The private sector can makean important contribution toinfrastructure investment, but it takes time to mobilize private participation in infrastructure. Inthisoperation, targets for private participationin school infrastructure were set in terms of investment commitmentsrather than actual investment outlays, but even this diminished target was not achieved. Problems with the frameworkforpublic-private partnerships (PPP) and a past scandal with a PPP project derailed progresswith the goal. It is vitalthat the legal, regulatory, and operational frameworks for PPPsin infrastructure exist and are sound and that there are bothfirm political commitments toand robust public support for the private provisionofinfrastructure.The ability of government staff to publicly defendand communicate the merits ofreform measuresis vital to the success of a structural reform program.In this operation, the ICRmadea distinction between the success reaped by measures to reform secondary and tertiary education versus the lack ofprogress with actionsto reform the VAT withholding system. According to the ICR, education reform was facilitated bytheMINEDU having a cohort of resolute and capable young staff who were able to project the strength of the governmentscommitment to the reform measures to the rest of the bureaucracy and to the public. In contrast, there was a lack ofconviction about the necessity for, and benefits ofVAT reform.The deferred drawdownstructure mayofferthe Bank leverage over additionalreforms. In this operation, the DDO not only incentivizededucational policy and regulation of business and trade but provided a buffer against unforeseen shocks. In the end, the Bank fullydisbursed the DDO against two massive shocksthe infrastructure damage caused by El Nino and the economic effectsof the COVID-19 pandemic. Thus, the financing structure of the operation gave the Bank leverage in policy dialogue not only overthe original program development objectivebut over two additional, critical issues. In this case, it would seem thatthere was no tradeoff between sustaining already implemented reformsagainst policy reversalsversusreducing the options for new sets of reformsthe Bank and its member country got itall.
P156865 | WBG - DPG VII | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2016 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/824531509656543401/text/ICRR-Disclosable-P156865-11-02-2017-1509656531670.txt | http://documents.worldbank.org/curated/en/824531509656543401/pdf/ICRR-Disclosable-P156865-11-02-2017-1509656531670.pdf | The lessons offered by the ICR concern the importance of: Adopting long-term perspectives ofreform, because successful institutional reforms require continuity of effort over a number of years. Tackling difficultreforms on the basis of high quality political economy and technical analysis. Aiming atgreater fiscalconsolidationand adequate financing of budgets to reduce the risk of further accumulation of arrears. Leveraging additionaldonor support is key to this dimension. Focusingprior actions on critical policy areas. Conducting acandid assessment of the Authorities commitment to reform,and of the risks related to weak implementation capacity,withconcrete proposalsfor mitigation in both areas.While these lessons areunobjectionable, they are of a general nature, and lack practicality (for instance, how can commitment beensured?). Concrete examples fromthe experienceof designing and implementing the operation under review would have beenuseful (see Section 14 below for further discussion).
P156892 | BF-Transport Sector Modernization and Corridor Trade Facilitation Project | Western and Central Africa | Burkina Faso | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2017 | 2023 | 2025 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099121224024038786/text/P156892-ff4c194f-55e5-4f38-959b-948c1e3d40b6.txt | https://documents.worldbank.org/curated/en/099121224024038786/pdf/P156892-ff4c194f-55e5-4f38-959b-948c1e3d40b6.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Scaling up Investments in cross-border information systems can help in realizing greater efficiencygains in regional projects.This project aimed at simplifying customs clearance and border crossingprocesses.However, the interconnected technology at Niangolgo (Burkina Faso and Cote dIvoire land border) was not beingfully utilized by all transporters, many of whom still relied on paper-based processes. The lesson from this project is thatrefined and clearly articulated incentive structures, that can reduce the variance in clearance and crossing processes and times,such as the use of preferred lanes for known shippers according to their risks profiles, can help in realizing efficiency gainsfrom investments in cross-border information systems.2. A longer-term engagement may raise the potential forsuccess for implementing sectoral reform strategies. This project was implemented in the wake of a Development PolicyFinancing (DPF) Operation. The project aimed at providing technical assistance for implementing some of the prior actions of theDPF operation.The lesson is that a long-term engagement may be required for implementing sectoral reformstrategies.3. Feasibility studies that carefully take into account local conditions and risk factors can help inreducing implementation delays. The roll out of the truck renewal program was delayed, as project design implicitlyassumed that the design used in Abidjan truck fleet program could be replicated in Burkina Faso. However, Burkinabe banks were lessinclined to approve credit to informal freight transport companies and a first iterationof applications resulted in a highrejection rate.This necessitated extensive consultation with beneficiaries and commercial financial institutions duringimplementation to tailor appropriate solutions in the country context.
P156894 | Afghanistan Digital CASA Project | South Asia | Afghanistan | IDA | FCS | Digital | Digital Development | IDA | IPF | 2018 | 2025 | 2024 | ICRR | >=50 million & <100 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099092723115544537/text/P1568940bbc3ed0990ae4300e565edb5efd.txt | http://documents.worldbank.org/curated/en/099092723115544537/pdf/P1568940bbc3ed0990ae4300e565edb5efd.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A long term approach might be required for addressing the limited institutional capacity in fragilesettings.This project experienced delays in decision making on key activities due to the limited technical andoperational capacity. For example, lack of familiarity with global practices in procuring bulk international and domesticconnectivity through the Indefeasible rights of use contract (IRU) led to significant delays and ultimately the decision by thegovernment to not follow the method. This resulted in missed opportunity for efficiency and savings. The lesson is that buildingthe technical and operational capacity in fragile settings needs to begin during preparation to avoid delays duringimplementation.2. Combining regulatory reforms with stricter compliance enforcement can help in projects aimed toattract private sector investment in the ICT sector. This project sought to enable and mobilize private capital in ahigh-risk environment. While the projects legal agreements did have disbursement conditions(such as ensuring that anoptical fiber license was issued to at least one private operator and issuing right-of-way guidelines by the Afghanistan TelecomRegulatory Authority), these conditions were not sufficient for attracting private sector investment. The lesson is that along withdisbursement conditions, theBank could advise governments to complement these conditions with stricter enforcement such asthrough contractual obligations.3. Significant attention and investment could help in institutional coordinationwhen project activities encompass multiple ministries, departments and agencies. In this project activities aimed atcross-sector infrastructure sharing the telecommunications network and adoption of e-Government entailed institutional coordinationacross different agencies. The lesson is that for such projects involving institutional coordination the Bank could help indeveloping mechanisms through formal and informal means to encourage ministries, departments and agencies to work together.
P156900 | Transport Sector Modernization and Corridor Trade Facilitation Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2017 | 2022 | 2023 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099221503102333344/text/P156900023a2760350ac6b00f495b65243b.txt | http://documents.worldbank.org/curated/en/099221503102333344/pdf/P156900023a2760350ac6b00f495b65243b.pdf | The ICR draws the following two main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Having a solid and comprehensive roadmap with adequate time for preparation at appraisal can help tominimize implementation delays. The preparation of this project was expedited, and it was prepared in only five months.Additional time and effort were then required to complete key guiding principles, roadmaps and plans steering the implementation ofimportant activities.These factors contributed to the delays in the initial years. This indicates that the project would havebenefitted from an extended preparatory period.2. A careful assessment is necessary of furtherendeavors,such as developing a fleet renewal initiative in this project. The sustainability of efforts deployed inpursuing such fleet renewal scheme depends on complementary efforts by both Cote dIvoire and Burkina Faso to resolve thematter based on the experiences to date. The sustainability of such reforms needs to be ensured through appropriate budgets andcontinued training programs.
P156960 | Nepal Third Financial Sector Stability Credit DPC3 | South Asia | Nepal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2017 | 2018 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  |  |  | Three lessons are offered, including two adapted from the ICR (page 32).Close collaboration among majordonors is vital to the success of broad national reform programs, particularly where the institutional and technical capacity forprogram design and implementation needs augmenting. In this program, the Bank and the IMF jointly prepared theNepal FSAP of 2014 which informed the prior actionssupported by this program. The legal departments of bothorganizations also helped review the draft BAFIA and the draft NRB Amendment Act. DFID and FIRST provided significanttechnical assistance and advisory services through their staff and international consultants. According to the ICR, the closecollaboration between the Bank and DFID was exemplary, starting in 2012, and consisting of joint missions, employment of experts,capacity-building activities, and large resource contributions for program design and implementation.Reformchampions in a countrys bureaucracy are needed for the implementation of complex reform programs where the politicalenvironment is uncertain and potentially volatile. In this program, the Bank worked closely with reform champions inkey positions at the Ministry of Finance and the NRB who were knowledgeable about the financial sector, held strong convening powerover stakeholders, and made compelling arguments for policy and structural reform. These key executives kept theirorganizationswell informed of the program rationale,design, and implementation plan.Thereform-mindedbureaucracy at the Ministry of Finance and the NRB pressed on with the medium-term program notwithstanding the politicaluncertaintyfrom frequent changes in the national leadership and the civil disturbancerelated to the drafting ofthecountrys new federalist Constitution.Governments can successfully takeadvantage of theopportunities offered by crisis situations to motivate reform programs. In this program, the liquiditycrisisof 2011, the failure of many financial cooperatives in 2013-14, and the devastating earthquake in 2015 exposed the vulnerability ofNepals banking, cooperatives, and insurance sectors to macro-financial shocks and to natural disasters. In response, theauthorities committed to a comprehensivereform program to recapitalize and restructure the countrysfinancialinstitutions and to strengthen the legal and institutionalframeworkfor bank supervision, bank resolution, financialcrisis management, operational risk management, deposit insurance, payments and settlement, and transparency. The demand forpost-crisis recovery helped firm up broad political support for the reforms.
P156963 | Moldova Economic Governance DPO1 | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2019 | 2020 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099100003222339119/text/P1569630090ba1081081040bbab7cb544c2.txt | http://documents.worldbank.org/curated/en/099100003222339119/pdf/P1569630090ba1081081040bbab7cb544c2.pdf | This review concurs with the lessons drawn from the ICR (pp. 35-36). Future budget support operations in Moldovaneed to better reduce ex-ante the risk of policy reversals or partial implementation of the reforms. Future operations need torecognize that the sustainability of reforms may be fragile and political volatility high, especially in election years, thus it iscritical to assess reform sustainability, especially in highly sensitive areas subject to extreme political volatility. The 2016pension reform supported by EGDPO demonstrated how fragile sustained reform was as a result of the political cycle, with pensionindexation changes in 2017, 2018, 2019 and again 2020. This suggests the risks might have been better anticipated, and it would beprudent to consider additional ex-ante measures to reduce these risks, including strengthening accountability mechanisms, buildingstronger reform coalitions to ensure sustainability across different governments and designing prior actions to encompass more ofthe results chain. To the extent possible, operations should provide a deeper ex ante assessment of risks,especially those related to politics and governance and to institutional capacity. All the risks related to the 2018 elections thatwere identified, but underrated, in the PD were manifested at the implementation phase. Moreover, in the case of the assetdeclaration reform, the competent authority, NIA, was itself being restructured. This created an additional technical complicationbecause the IT system had to be transferred from one institution to another with implications for system testing and timelyfunctioning.Coordination with development partners through complementary actions is crucial during both design andimplementation of the reforms to reinforce reform progress and ensure sustainability. For the EGDPO in Moldova, (1) during itsdesign, prior actions were either complemented or supported by other donor programs (IMF, EU), and (2) during implementation,especially after release of the Fiscal Package, joint work and coordinated messages from the development partners community werecrucial to address, and in some cases reverse, new initiatives, such as the capital amnesty.
P157035 | Afghanistan Technical Assistance Facility | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2016 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/386661593006623305/text/Afghanistan-Technical-Assistance-Facility.txt | http://documents.worldbank.org/curated/en/386661593006623305/pdf/Afghanistan-Technical-Assistance-Facility.pdf | The ICR does not contain a Lessons Learned section, but several key lessons can be discerned fromthetext: Utility of Direct Funding without a PIU: One of the unique initiatives under theproject was that investment of project funds was made directly to the two implementing units the MFPD and the PolicyDepartment - without the need for a central PIU unit to oversee implementation. This way, the two units were more directlyaccountable for and took ownership over the project activities and the achievement of the objectives. In a larger context, itreflected the governments accountability and ownership of the projects implementation and outcomes. Concurrently, thisresulted in reduced costs. It could be a good model to follow fortechnical assistanceprojects. However, it must benoted that this initiative involved a fairly small investment over a short period of time, ideally conducive to a technicalassistance project, and probably is not ideal for projects with larger investments and complex frameworks to achieveobjectives. Need for Effective Capacity Building: Linked to the above,this modelassumes agenerally high degree of capacity and capability of both units to undertake the designated implementation activities. The ICR atvarious points states that there were delays caused because ofthe two units unfamiliarity with preparing and executingshort-term output-based consultancy contracts (ICR, para 45), as well as a dearth of in-house economists (civil servants) withexpertise in forecasting and fiscal planning that had been previously done by external consultants (ICR, para 50). The skillstransfer to civil servants caused initial delays in implementation and also points to the need for more capacity building inspecialized areas that ought to have been considered as a key component of the project. Importance of NPPs andBudgetary Allocations in Fiscal Planning: The other important outcome supported by the project was the development andadoption of NPPs that took priority consideration for budgetary planning. A particularly important initiative was the developmentof NPPs such as WEE and the Citizens Charter. Unfortunately, while important NPPs were developed and proposed, the requiredbudgetary allocations to support these NPPs were never undertaken. Therefore, while appropriate NPPs are extremely important toprepare and propose, there must be tangible budgetary allocations to support and sustain the implementation of theNPPs. Importance of a Practical and Effective ME Framework in Design ofTechnicalAssistanceProjects: It seems that the baseline PEFA ratings of D in the results framework (ICR, para66, Table 4 TAF Results Framework) for all three activities were artificial ratings and without a proper basis. That should havebeen avoided. It only provided for a situation where, unless the project totally collapsed, even the most marginal activitywould have to be scored above the low base rating. This is a design flaw that should be avoided because it gives a skewed view ofactual achievements.This important exercise was further compromised by agreeing to a FPIP self-assessment of activities thatbore completely inconsistent and totally confusing results. It is clear from the ICR that dependence on ME assessmentsbased entirely on inflexible and generic methodologies such as used by the FPIP ME framework can lead to inconsistent results(ICR, para 66). The World Bank must have a more influential role in designing ME methodologies that are tailored to assessproject characteristics to enable more accurate assessments. Early Termination: The project wasterminated prematurely after only 18 months upon the request of the government, with acknowledgment in the ICR that it had,however, laid a good foundation to achieve the main objective of fiscal management and budget planning.Integrationofall TA projects on fiscal performance improvements can have positive effects of consistency, coherence, transparency, andaccountability.
P157036 | Togo Employment Opportunities for Vulnerable Youth Project | Western and Central Africa | Togo | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099082323140527811/text/P1570360c8fe8c0a3089f6054bec62b8075.txt | http://documents.worldbank.org/curated/en/099082323140527811/pdf/P1570360c8fe8c0a3089f6054bec62b8075.pdf | Lessons drawn from the ICR (pages 32-33) and adapted by IEG: Youth employment programs that integrate multipleinterventions can have an increased impact compared to single-focus interventions. In the case of this project, interventionsaddressed both supply side (skills development for youth) and demand side (focus on self-employment opportunities, as well as softskills (promoting a culture ofsavings) and technical needs (local market assessment) were more responsive to the range ofconstraints to increased youth employment. Identifying synergies with existing operations and partners can generateefficiencies in project implementation. In the case of this project, the twinning of projects (with the parallel safety netsproject) enabled sharing of some project specialist staff and administrative support staff, and partnering with GIZ enabled use oftheir existing business skills training curriculum.Also, The tightly-linkedsequencing of keyproject interventions can also generate efficiencies in project implementation and monitoring. In the case of this project,the savings requirement from the first phase of the projecttriggered the matching grants and hence provided the seed capitalfor the second phase.
P157038 | Safety Nets and Basic Services Project | Western and Central Africa | Togo | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099102424140039295/text/P157038-8781f09e-ea59-4a0d-bbd1-e3d699e00992.txt | https://documents.worldbank.org/curated/en/099102424140039295/pdf/P157038-8781f09e-ea59-4a0d-bbd1-e3d699e00992.pdf | Lessons can be drawn to highlight the importance of strategic design, community involvement, digital innovation, flexibility,capacity building, and economic empowerment in the successful implementation of social protectionprojects:Lesson 1: Simplification and Targeting. Simplifying project design and focusing on coreactivities can significantly enhance implementation efficiency. Employing a multi-step targeting strategy that includes geographictargeting, PMT, and community validation can ensure that the most vulnerable populations are accurately identified and included.This approach can streamline operations and enhance the inclusivity and effectiveness of social protectionprograms.Lesson 2: Digital Innovations and Adaptability.Incorporating digital advancements inproject design can significantly improve the resilience and adaptability of social protection systems. Digital payment methods andplatforms, such as the Novissi platform used in Togo, can enhance the efficiency and reach of cash transfer programs, especially intimes of crisis. Prioritizing the development and integration of digital tools can ensure timely and effective servicedelivery.Lesson 3: Community Involvement and Local Governance.Engaging local communities andstrengthening local governance structures can be critical for the sustainability and success of social protection programs.Community involvement can enhance the relevance and acceptance of interventions and build local capacity and accountability. Futureprojects can benefit from prioritizing community-driven approaches and investing in capacity building initiatives for localauthorities.Lesson 4: Flexibility and Responsiveness. Flexibility and responsiveness can be essentialattributes for the successful implementation of social protection projects. Designing projects with built-in mechanisms for rapidadaptation to changing circumstances, such as economic shocks or health crises, can ensure that projects can pivot effectively inresponse to unforeseen challenges. This includes having contingency plans, flexible funding arrangements, and adaptive managementpractices.Lesson 5: Capacity Building and Institutional Strengthening. Investing in capacity building andinstitutional strengthening can be fundamental for the long-term success and scalability of social protection programs. Trainingand capacity building initiatives can equip implementing agencies with the necessary skills and knowledge, enhancing the immediateeffectiveness of the project and building a robust foundation for future social protection efforts.Lesson 6:Economic Inclusion and Empowerment.Combining cash assistance with economic empowerment activities can significantlyenhance the impact of social protection programs. Providing beneficiaries with the tools and support needed for entrepreneurshipandincome generation can help address employment barriers and build long-term resilience. Integrating economic inclusion componentscan complement direct cash transfers and promote sustainable livelihoods.
P157054 | Madhya Pradesh Rural Connectivity project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099112524122528046/text/P157054-340f71a7-59f8-469a-846b-f40842c40577.txt | https://documents.worldbank.org/curated/en/099112524122528046/pdf/P157054-340f71a7-59f8-469a-846b-f40842c40577.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Good Quality-at-Entry, based on the lessons from previous projects, may raisethe potential forsuccess of projects. This project built on previous rural connectivity programs at the national level and at the statelevel. This was supported by knowledge exchange workshops during implementation. Based on the experience from the national levelprogram, timely procurement for most project activities (with 30% of works contracts awarded prior negotiations) contributed toeffective and timely arrangements. These factors, coupled with appropriate implementation arrangements, contributed to the projectsuccess.2. Early involvement of relevant stakeholders can help in preventing delays during implementation.This project experienced delays in completion of road safety activities due to the lack of timely responsiveness of themany key stakeholders involved. The lesson from this project is that where implementation requires joint efforts, early involvementof the stakeholders can help in preventing delays during implementation.3. A combination of measures aimingat responding to the challenges on the ground (as opposed to one size fits all) may be required for designing climatemitigation measures. Given the state context, this project had various interventions to cater for both heavy rains andhigh temperature impacts (Bitumen treatment and plastic waste) that were selected to respond to the challenges of the ground.
P157055 | Cote d'Ivoire - Electricity Transmission and Access Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099091124134589711/text/P157055-5789c280-bd10-40c2-8bf3-065df4d85dbe.txt | https://documents.worldbank.org/curated/en/099091124134589711/pdf/P157055-5789c280-bd10-40c2-8bf3-065df4d85dbe.pdf | To ensure efficient project implementation, it is important tothoroughly assess technicalstudies, environmental and social considerations, procurement readiness, and Borrower capacity at the appraisal stage. Theproject faced initial delays in implementation due to incomplete studies and insufficient expertise, particularly on environmentaland social aspects. The implementing agency, CI-Energies, was overstretched due it its involvement in multiple in multiple domesticand donor funded energy projects, impacting supervision. This was later addressed with owners engineers, notably EDF playing apositive role in facilitating implementation, but future projects should prioritize readiness assessment, institutionalstrengthening, and enhancement of technical capacity during appraisal. For effective monitoring, it is crucial todesign indicators and targets that can accurately measure performance results and be directly attributed to the project.The ICR indicates that one of the challenges faced was measuring the system losses, which was difficult to attribute solely to theproject. Even though there was evidence of improvement, it was not easily measurable at the project level leading tomisunderstandings about its achievement. Effectiveresolution ofunexpected environmental challengesrequires a collaborative effort among all parties involved, particularly government authorities, engineers, and organizations likethe World Bank.During implementation, the unexpected discovery of pollution of water and land with hydrocarbons andPolychlorinated Biphenyls (PCB) led to the suspension of activities on the Bia Sud. Significant work had to be undertaken fordepolluting the site, which allowed activities to resume after an 18-month interruption. This incident demonstrated the WorldBanks comparative advantage in mobilizing financing and expertise from local and external partners to address unforeseensafeguard challenges. Stakeholders acknowledged that the high standards and thoroughness of the World Bank staff and theirenvironmental and social instruments were crucial in identifying and addressing such unforeseen issues. Similar incidents may arisein other World Bank project sites, so teams should remain vigilant for potential leaks from stored transformers or other pollutionwhen appraising and implementing electricity transmission and distributionprojects.
P157060 | BF - DPO series on Energy and PFM | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2019 | 2021 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/845021614105893722/text/Burkina-Faso-BF-DPO-series-on-Energy-and-PFM.txt | http://documents.worldbank.org/curated/en/845021614105893722/pdf/Burkina-Faso-BF-DPO-series-on-Energy-and-PFM.pdf | Three lessons are drawn from the ICR (pages 26-27), with some adaptation.Governments and the Bankmightconsider includinga contingency emergency response componentin FCV situations, when security shocks impair agovernments ability to maintain its fiscal obligations under a reform program. In this program, the escalationof Burkina Fasos spending for defense and security in 2018 impaired its ability to pay subsidies to SONABHY,raisingarrears in the energy sector a year after they were largely settled. The ICR (page 26) speculates that emergencyfunding, presumably from external sources, could have helped the Government meet its defense and security expenditures while at thesame time preserving the gains made earlier with the clearance of cross arrears in the energy sector. A heightened securityrisk is commonin many FCV settings. Anticipating the implications of these events for government obligations under areform program and planning for fiscal responses mightbe considered during program planning.Basic taxadministration reform measures can yield material contributions to revenue performance. While this program benefitedfrom changes to Burkina Fasos General Tax Code as well as from the introduction of new specific taxes, improvements in taxadministration possibly helped drive VAT and non-VAT revenue higher than in the baseline. These tax administration reformsincluded such basic improvements as giving clarity to tax invoices, facilitating payments by taxpayers,and cleaning-up taxdatabases, including by reconciling tax and customs datasets. According to the ICR (page 26), these improvements in taxadministration helped fostertax compliance and broadened the tax base in Burkina Faso.Resolving fuelpricing and electricity tariff distortions is needed to attract private equity financing for the power sector. Inthis program, the onrush of IPP projects is lending a sense of urgency toBurkina Faso resolving itsfuel pricing andelectricity tariff setting issues soon. Current reforms supported under this operation provided onlypartialpass-through of fuel costs and the adoption of fully-cost-reflective electricity tariffs. An inability to agreeon costs and tariffs will derail the countrys ability to obtain guaranteed equity financing (usually 30 percent of investmentcosts) and to cover additional investment costs for these IPP projects as they advance through the pipeline.
P157127 | Forest Sector Modernization and Coastal Resilience Enhancement Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | https://documents.worldbank.org/curated/en/099082824120031773/text/P157127-b3369799-708d-46b1-92d1-3ca2617a0290.txt | https://documents.worldbank.org/curated/en/099082824120031773/pdf/P157127-b3369799-708d-46b1-92d1-3ca2617a0290.pdf | The ICR presented five lessons. Three of them that are likely to be widely applicable are presented below with someediting.In designing activities that need to be appropriate for specific situations such as coastalafforestation plans consultations with local communities can improve the outcomes (ICR, para 90). Even with theshortened implementation period, the survival rate of coastal forest plantation and restoration was significantly higher under theForest Sector Modernization and Coastal Resilience Enhancement project (FMCR) than in similar projects implemented previously inViet Nam without incorporating local knowledge. In implementing FMCR, local experts assessed the sites before planting. The processconsumed time and required rejecting unsuitable areas, reducing the planted area, but it paid off in terms of high survival rates.The role played by local communities, particularly the planting and tending of trees by women, also contributed to thesuccess.Analyzing political economy and government decision-making processes as part of assessing risk can helpidentifythe mitigation measures needed to insulate the project from cumbersome decision making processes (ICR, para 91).Implementation of the project was challenged by cumbersome central and province-level internal approval procedures, whichaffected key results. Strengthened coordination between technical experts and decision-makers would have better alignedtechnical solutions with broader political and economic considerations.Collecting robust data that reflect theunique characteristics of each location can help in comparing options for their cost-effectiveness and choosing the interventionsthat align with ecological and economic goals of the project. Site-specific analyses can help in comparing mangroverestoration with alternative coastal protection measures to highlight cost-effectiveness; and the conditions for naturalregeneration versus planting need to be evaluated to choose the method that aligns with the ecological and economic goals of theproject.
P157136 | Modernization and Innovation for Better Public Services in Argentina | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099133503072354482/text/P15713600363ca004087aa020a6f6e040f2.txt | http://documents.worldbank.org/curated/en/099133503072354482/pdf/P15713600363ca004087aa020a6f6e040f2.pdf | The ICR identifies eight lessons, which it frames as Lessons and Recommendations. This review concurs with thelessons in the ICR. It focuses on the following lessons that can best inform projects with similar area focus (GovTech,e-government) or implementation modality (investment loans with RBF component).Successful, e-governmentreforms build on a government vision and strategy, and a central agency with the authority to drive the reform agenda. In thecase of this project, the positioning of the implementing agency within the Chief of Cabinet office provided the authority neededto align sector ministries with the reform. The implementing agencys shared vision and leadership authority greatlyfacilitated the design and implementation of digital solutions, with explicit political commitment during the implementationperiod.Adequate resources for change management activities are critical for e-government reforms, along withflexibility to adjust the specific services and range of supported institutions. Digital government reforms entail cultural,behavioral, and process changes that can be derailed by resistance from key stakeholders. In supporting this operation, thegovernment carried out multiple change management activities, including consultation, communication, awareness raising, andcapacity building during project implementation to accompany the reform process.Results-based financing incentivizesgovernments to make the difficult changes needed for e-government to succeed. In this operation, the RBF component helpedalign incentives and set a road map for advancing the Government reform program. Close monitoring of DLI targets and otherindicators sent a clear message to stakeholders on the importance of achieving results. The budget allocated for input-basedexpenditures decreased during implementation because of fiscal tightening, putting project implementation at risk. The projectmitigated this risk using RBF with DLIs, enabling full disbursement of the loan amount.GovTech reforms may require alonger period than a single Bank project can support. This project was the first GovTech project in Argentina to follow a wholeof government approach, with citizen-focus design and transparency as key principles. It did not address issues such as civilsociety co-design of public policies use of data analytics and machine learning techniques, with little attention to sub-nationalreforms. The recognition of further work needed in these aspects was one of the drivers of the new follow-up project on DigitalInclusion and Innovation in Public Services. Future projects should consider a phased approach that supports a sequence ofprojects.
P157206 | Cote d'Ivoire Land Policy Improvement and Implementation Project | Western and Central Africa | Cote d'Ivoire | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2018 | 2024 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Sustained high level commitment and support from the WB and the government may raise the potential forsuccess in land administration projects. This project was designed as the first in a series of projects to implement theGovernments reform agenda by concurrently establishing the institutional, capacity, legal, procedural and technologicalfoundation for nationwide land registration. The project benefitted greatly from consistent and high level backing from the WB andthe Government.2. Investment in Impact Evaluation analysis may help in demonstrating early results in landadministration projects. Broader impacts, such as increased investment, productivity and access to finance in landadministration projects, take time to materialize following land registration and may depend on complementary reforms. However, theadditional time, funding and coordination invested in implementing the Impact Evaluation may be worthwhile for demonstrating earlyresults.3. Digitization and streamlining of rural land registration procedures may raise the potential for successin land administration projects. A digital and systematic approach to land registration in this project, supported bycounterpart financing, allowed the Project to significantly accelerate delivery of land certificates.
P157207 | Pakistan Competitiveness and Growth Development Policy Credit | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2016 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/493141588012455268/text/Pakistan-Pakistan-Competitiveness-and-Growth-DPC.txt | http://documents.worldbank.org/curated/en/493141588012455268/pdf/Pakistan-Pakistan-Competitiveness-and-Growth-DPC.pdf | The ICRs principal lessons are summarized below: To raise largesums of money and obtain positive outcomes the borrower needs to plan and act ahead of its needs so that it can enter the marketwhen the market sentiment is in its favor. The benefits of a World Bank guarantee are likely to increase if the guaranteehas flexibility, the borrower considers multiple market segments, has a sufficient large number of banks to submit proposals andrequests proposals under a transparent and competitive process. When reforms take time to implement and to deliverresults, a standalone operation is less appropriate than a series of policy loans, where the initial operationcan befront-loadedwith the more difficult reforms, when the momentum for reform is likely to be stronger.
P157224 | First Programmatic Electricity Distribution Reform Development Policy Loan for Rajasthan | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2016 | 2017 | 2022 | ICRR | >=100 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/099500007072243964/text/P1572240f6536a01d0ab7e0be8329b2c18c.txt | http://documents.worldbank.org/curated/en/099500007072243964/pdf/P1572240f6536a01d0ab7e0be8329b2c18c.pdf | IEG derives the following lessons drawn from the ICR:1. Impactful World Bank-supported electricitydistribution sector reforms require long-term engagement. An important lesson from this DPL series is that aholistic package of policy, regulatory, operational and financial measures supported by a long-term engagement plan is critical fora distribution sector performance turnaround. Lessons learnt from previous reform efforts in India and elsewhereindicated that financial bailouts of distribution companies alone without deep reforms in other areas do not provide long-termsustainable solutions. Hence the design of this Program included fundamentals of sound distribution sector performance - costrecovery tariffs, good governance and management accountability and operational efficiency improvements. bare subject to politicaleconomy influences and, therefore, often require time to address effectively. Such deep and comprehensive reforms require externalsupport over an extended period of time and hence need long-term engagement plans involving the government and otherstakeholders.2. Options for reforms need to be synchronized to the country context. Anotherimportant lesson is that reforms may need to be incremental while relationshipsand consensusare built to create thenecessary conditions for progress on deeper and more difficult reforms. The Bank was sensitive to the countryssocio-political context in selecting pragmatic reform options. It thus emphasized operational efficiency improvements, improvinggovernance and performance management and accountability instead of tariff increases and private sector participation. Thisenabled the Bank to build relationships and trust attributes that paved the way for engaging constructively withstakeholders on exploring options for private sector participation in the electricity distribution sector and for strengthenedengagement on the electricity-water-agriculture nexus.3. Identifying windows of opportunity is critical forreforms to succeed. Another important lesson from this DPL series is the importance of choosing the right timing forreforms and fully capitalizing on the moment. The Bank chose to support the GoR in implementing reforms at an opportune timewhen there was a strong alignment between the GoI and the GoR on electricity distribution sector reform issues. The GoI and thestates/territories were preparing the UDAY program to address the electricity distribution sectors financial and operationalperformance problems. The GoR needed to resolve electricity sector constraints to its 2020 Vision economic growth strategy. TheBank moved quickly to prepare the DPL series at a time when the appetite for reforms was strong in Rajasthan and India.However, the Bank did not take full advantage of the propitious moment to lock in an engagement plan although it was fullyunderstood at that time that the reforms would need to be sustained through an engagement over time. Later when the Bankexplored complementing the DPL series with additional technical assistance after the 2018 state elections, there had been a changein priorities of the state government due to other emerging challenges, and this foreclosed the possibility of a third phase of theDPL series.
P157233 | Mali Reinsertion of Ex-combatants Project | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | https://documents.worldbank.org/curated/en/099111324152532280/text/P157233-42ab80ab-79b1-4dbe-ade5-53b6bd06455d.txt | https://documents.worldbank.org/curated/en/099111324152532280/pdf/P157233-42ab80ab-79b1-4dbe-ade5-53b6bd06455d.pdf | The following lessons were derived from the ICR (based on ICR, pages 23-24):1. In the FCScontext, Disarmament, Demobilization and Reinsertion canbe successful if designed and implemented within a widerpeacebuilding framework, including development programs that consider not only ex-combatants, but also communities and localownership. Community development was not included in the original design of the reviewed Project, and it turned out to bea shortcoming, creating difficulties for working in the Project areas. This aspectwas addressedat Restructuring 1 whensupport to socio-economic reinsertion (a short-lived operation) was strengthened by new activities targeting long-term communitydevelopment, thus promoting local ownership and sustainability of the Project outcomes.2. Embedding Disarmament,Demobilization and Reinsertion (DDR) programs Project Implementation Unit (PIU) in the government structures in charge ofthe DDR program, rather than establishing a separate PIU entity, is likely to work best, as it ameliorates project implementationand strengthens capacity of the government structures. The reviewed Projects PIU was fully embedded into theNational DDR Commission (CNDDR) (the implementing agency for the Project) within the Ministry of Reconciliation, Peace and SocialCohesion. The PIU Coordinator was the CNDDR National Coordinator and a high-level civil servant. This helped maintain close linkswith the Ministry, facilitating Project implementation. Also, the PIU was knowledgeable on DDR dynamics and adequately trained todeliver and sustain the reinsertion program. In addition, extensive capacity building was provided through the PIU to thestructures in charge of the DDR process, improving CNDDRs capacity to implement the national DDR program.3.Having an effective ME and MIS system prior to launching project activities is especially important when local capacity islimited. In the reviewed Project, procedures for data collection were not systematic, and information sharing amongimplementing partners and local authorities was limited. This resulted in reduced data availability and limited data analysis. Thereviewed Project would have benefited if, prior to the start of implementation, clear and practical data collection procedures,transparent and well-defined reporting requirements, and thorough data analysis processes were established. Additionally, theME system could have been combined with an efficient Management Information System (MIS) (beyond a dashboard), to track andconsolidate the relevant data. The reviewed Projects experience demonstrated that a pre-implementation agreement on acomprehensive ME and MIS framework is especially important when local capacity islimited.4. Focusing onsupport to the re-insertion of female ex-combatants can be a strategic decision that contributes to the peace process.While female ex-combatants are often excluded from socio-economic reinsertion activities, the reviewed Project focused onsupporting them, which was less controversial in the context of the stalled agreement on security sector reform, mainly due totheir lower rank as compared to the male ex-combatants. Also, women ex-combatants had a strong interest in reinsertion. Thegovernment and signatory movements agreed to focus on the female ex-combatants as a sign of good will and commitment toreinsertion. The Project applied a gender sensitive approach to ensure that differentiated needs of male and female ex-combatants are considered. The Project experience demonstrated the importance of including a gender specialist and train the staff on genderissues when working with female ex-combatants.
P157249 | Wildlife and human-elephant conflicts management in the South of Gabon | Western and Central Africa | Gabon | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099113023165020304/text/P15724909e8eba09b0b7590080b5b727ef2.txt | http://documents.worldbank.org/curated/en/099113023165020304/pdf/P15724909e8eba09b0b7590080b5b727ef2.pdf | The following are the IEG lessons:Planning the surveys and tracking tools early in the implementation may helpmeasure beneficiary satisfaction as a project outcome. In this project, the surveys to assess satisfaction took place toolate (towards the projects end), and no time was left to react, resulting in low results for womenssatisfaction.Pooling resources and finding synergies with other donors may contribute to the sustainabilityof outcomes. From the design phase, this project counted on ongoing projects that were synergetic in their interventions.The pooling of resources for the lab has proven successful in reaching sustainable outcomes and providing a platform for futurecooperation in the same area.The following are the most relevant lessons extracted from the ICR(rephrased):Clear delimitation of roles and responsibilities during the design phase may contribute to effectiveinter-agency cooperation during implementation. In this project, despite thechallenges of inter-agency cooperationand past difficulties, ANPN and DGFAP worked well together to ensure the implementation of activities in their respective zones ofresponsibility. From the outset, the project emphasized the full participation of both agencies, which improved overall projectownership and interventions.The use of a specific gender methodology during implementation may contribute toensuring the success of a project that has a strong gender focus and goals. The project did not meet its targetsregarding female beneficiaries satisfaction and had issues reaching them in remote areas.Further efforts and tools canhelp to engage with communities more deeply in remote areas. This can be done regularly by social specialists.Activitiescould be adapted to the challenges at play in these communities. Time, budget, and staffing needs for more challenging areas mustbe assessed carefully, and help from local NGOs could be sought to improve the adaptation of gender-focused interventions.
P157291 | Cambodia Health Equity and Quality Improvement Project (H-EQIP) | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2016 | 2023 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099102924172012196/text/P157291-e1710357-1726-4094-aeda-917aaba6ca66.txt | https://documents.worldbank.org/curated/en/099102924172012196/pdf/P157291-e1710357-1726-4094-aeda-917aaba6ca66.pdf | The ICR (pp. 28-29) and project team (in conversation with IEG) offered a series of insightfullessons:Long-standing engagement in a country and sector can allow lessons and learningfrom previous supportto beadapted and re-implemented. In this case, the Bankhad engagement in Cambodia that went beyond theproject. Its presence in the sector-widedialogue was strong and well-coordinated with an ample coalition of developmentpartnersand fluid conversations with the government.Building and strengthening capacity ultimately paysoff. Multiple examples of this lesson are evident across its design and implementation. Implementation through existinggovernment structures reduced overhead costswhile consolidating relevant official departments. The projectwas carefullydesigned to gradually transfer competencies (for example, HEF monitoring, previously outsourced to non-governmentalorganizations,to government structures), thus ensuring sustainability, while also closely supervising processes to guaranteetransparency and good governance. The establishment of the PCA was another success story, implemented with the support of bothMOHand the Ministry of Economy and Finance. The Bank team started these transitions early in project preparation and investedtime in learning from other experiences in the region through study visits. However, from the interview with the project team, ittranspires that, although there were more gains than losses in this approach, the Bankdoes lose some control over projectimplementation. It also means having to share government officials with other organizations implementing projects through thegovernment and, consequently, less dedicated bandwidth.There is a sometimes difficult balance between equity andquality in ahealth system. The project aimed to increase utilization of public health facilities by increasingquality (SDGs) and also reducing financial barriers to access (HEFs). However, upsurges in utilization rates may overwhelm thehealth system, distorting supply chains and over-stretching human resources, for example, thus deteriorating quality,paradoxically. Recognition of and planning for these potential negative externalitiesisneeded.Improvementsin health services quality do not translate automatically into higher utilization of thepublic health system. The project team shared that addressing rooted perceptions takes time, and there are elements thatare hard to address that play a fundamental role in demand. Waiting times and distances associated with public health facilitiescannot compete with the much larger network of the private and informal sector. In addition, inthe relatively unregulatedhealth sector of Cambodia, buying drugs over the counter without prescriptions saves time for clients.
P157324 | Ecuador Risk Mitigation and Emergency Recovery Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2016 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099200009192225244/text/P1573240546c650b70bd5e04544f38adb7c.txt | http://documents.worldbank.org/curated/en/099200009192225244/pdf/P1573240546c650b70bd5e04544f38adb7c.pdf | The ICR presented eight lessons and recommendationsbased on this emergency operation (ICR, paragraphs 80-87). The moreimportant ofthese are presented below withmodifications. In addition, IEG derived two additionallessons: Narrowly specifying the disaster risks to be addressed in the PDOslimits the flexibility of aframework approach in an emergency operation.In this project, the original PDO limited the flexibilityof thePDO to address thedisaster risks that emerged because the PDO directly referred to two potential disaster risks, i.e., the ElNino phenomenon and the eruption of the Cotopaxi volcano.As a result, the PDO had to be changed duringrestructuring tobroaden the scope of the objective rather than specifying the disasters beforehand. In addition, because one of thedisastersdid not materialize, the pre-identified preventive measures also had to be revised duringimplementation. Insufficient attention to a logicallyconsistent theory of change whenrestructuring a project might lead to unsatisfactory project outcome. The project had several revisions of projectactivities, indicators, and targets. In these revisions, the Bank task team did not sufficiently workthrougha logicallysound results chain that would have leadthe revised project activities to achieve the PDO. Therefore, when changing projectactivities, it is important to ensure that the theory of change remains valid and modify the PDOifneeded. Low quality technical designs and feasibility studies of preventive investments thatdo not comply with World Bank policies and standards may cause implementation delays. In this project, the governmentfinanced most of the designs and feasibility studies for the subprojects. The designs were of poor technical quality, did not meetthe countrys own standards, international best practices, or World Bank requirements. The World Bank team and the PIU hiredtwo engineers to review thedesigns but this plus any change to the approved designs caused implementation delays. Eventually,the government sought other financing for those subprojects to avoid further delays. Project funds may be used to finance designsand feasibility studies of subprojects to help ensure that quality standards are met even before the loan is madeeffective.IEG Lessons: Governments need favorable conditions to take advantage ofretroactive financing. In this project, the government did not useup to 40 percent of the loanproceedsretroactively because the government did not have the available fiscal space to procure the works before having thesereimbursed. In addition, designand studies for the works were not sufficiently advanced to be financedretroactively.Knowing these factors would give the government maneuverability to better planavailableresources. A strong agency with convening power needs to have the mandate and capacity to coordinatedifferent agencies.In this project, an institutionally strongMEF, with its convening power wasselectedto implement the project. However, the agency did nothave the implementation mandate related todisasters - frompreventionto recovery. Neither did it have the capacity to coordinate other agencies implementingsubprojects. Theoperation became even more complex after a disaster was declared asother co-executing agencies wereadded. Experiencedconsultants were hired to assist MEF. Training supplemented capacity gaps. The Bank team acknowledged thatoffering projectmanagement tools (such as the Hands-on Expanded Implementation Support) would also have been helpful.Selecting an agency withthe mandate for post disaster recovery, aided bytraining in capacity gaps, adopting project management tools,andin-country presence by task team could further simplifyimplementation arrangement.
P157343 | Second Macroeconomic Stability for competitiveness and Growth | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2018 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest |  |  | IEG draws three lessons from the series, which overlap those of the ICR.IEG concurs with theobservation in the ICR that a policy-based guarantee can be a useful instrument for debt restructuring. In the case of Ghana, therefinancing of the debt reduced pressure on the government and on the exchange rate that arose from the very short-term nature ofthe countrys debt.Close working relations between the government and the Bank strengthens not onlyspecific reforms incorporated into the series but can also enhance more generally a government reform program. In the case ofGhana, the extensive analytical foundation and continuing diagnostic work not only allowed the series to be prepared within a shorttime frame when the need arose as a result of the crisis, but also provided a foundation for the future preparation ofassistance.When elections overlap series operations, continuity risks can be reduced by briefing keyopposition politicians on the rationale for reforms, progress to date and expected results. An awareness of electoral cyclesis necessary in order to ensure that significant changes in government priorities do not compromise the final operations in aseries. In Ghana the change of government in 2016 and its changing priorities led to the cancellation of the thirdoperation.
P157404 | Chongqing-Dadukou Fiscal Sustainability DPO | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/530701576685868644/text/China-Chongqing-Dadukou-Fiscal-Sustainability.txt | http://documents.worldbank.org/curated/en/530701576685868644/pdf/China-Chongqing-Dadukou-Fiscal-Sustainability.pdf | Three lessons are drawn from the ICR (pages 32-34), with some adaptation. Because this DPF was intended by the centralgovernment as a pilot for a sub-provincial level fiscal reform program, the lessons drawn here are relevant to futuredistrict-level fiscal reform programs in China.First, development policy lending --- which aims to support policy andinstitutional reforms through budget financing --- can be an effective instrument in advancing subnational fiscal reforms.ThisDPF provided general budget support to the Dadukou District Government (the DPFproceeds wereon-lent by thecentral government to the Chongqing Municipal Government and, in turn, by the Chongqing Municipal Government to the DadukouDistrict Government). Thereform programobjectives were achievedthrough prior actions and time-bound outcometargets.Technical assistance, whichwas the mode for Bank engagement with China on budget reforms in thepast,coulddeliverknowledge, expertise, andtraining, but it couldnot require policy or structuralreform actions like a DPF could.Moreover, the Dadukou District Government has continued to engage the Bank in policydialogue about fiscal reform in 2018, after program closing in December 2017.Second, subnational fiscal reform inChinas districts and municipalities will require concurrent fiscal reform at the central government and provincial governmentlevels, given the complex nature of inter-governmental fiscal relations in China. The experience with this DPF showed thatfostering the sustainability of district finances is not straightforward because: (a) the central government continues to issueexpenditure mandates to subnational governments, and the mandates are commonly unfunded; (b) district governments havetosecure the approval of the municipal government to allow LGFVs to retain revenues in the district; (c) inter-governmental transfersare often volatile, complicating medium-term budget planning; and, (d) district governments are unabletocompletelyseparate the commercial from the government assets of LGFVs absent a central government national policy andguidance on the issue.Third, a simplified DSA framework would be better suited for future fiscal reform initiativesin other districts across China. The DPF prepared a customized DSA manual forthe Dadukou District Government that wasintended to be comprehensive in its accounting of local government debt. But even with the customization, the districtgovernment struggled to determine: the district governments off-budget liabilities;the LGFVs off-balance sheetliabilities; and, the district governments contingent liabilities. Hence, thelesson is to use a simplified DSAframework if subnational fiscal reforms are to be expanded to other districts across China following theexperienceinDadukou District. Toward this end, the Bank is reportedly working with the Fiscal Academy of the centralgovernments Ministry of Finance to develop a simplified DSA template that could be used by local governments to supportsubnational fiscal analysis and planning. The conduct of the DSA by provincial governments rather thanby districtgovernments, where technical capacity is less robust,is also being considered.
P157405 | Third Economic Management and Competitiveness Credit | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2016 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | The following lessons are drawn from the ICR:Care should be exercised in designing multi-sectorprograms. A focused program, addressing a limited number of sectors or issues, may achieve more coherentoutcomes. The EMCC series may not have been unduly broad in its sectoral focus, but it addressed numerouspublic sector, financial sector, and private business themes all important but in drawing in several stakeholderswith at least partly dissimilar agendas, it risked uneven implementation, as happened in EMCC.Aprogrammatic operation introduces flexibility. Programmatic, multi-year programs sometimes need to adjust theirpolicies and their indicators to changing circumstances, or to better understanding of the issues as implementation advances.The EMCC went through a few transformations of PDO, of indicators, even of policy objectives all of them based onlearning by doing, i.e. during program implementation.Design and implementation of a programmaticoperationideally draws on inputs from many sources. Where local stakeholders and development partners areactive, and technical assistance and analytical work abound, an operation should engage such sources. The EMCC series is anexample. Inaddition to the direct relationship with the Borrower, the series also actively engaged other stakeholders,both local and external, and drew on ongoing research.
P157406 | Hunan Fiscal Sustainability DPO | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/217161578438972681/text/China-Hunan-Fiscal-Sustainability-DPO.txt | http://documents.worldbank.org/curated/en/217161578438972681/pdf/China-Hunan-Fiscal-Sustainability-DPO.pdf | Three lessons are drawn from the ICR (pages 32-34), with some adaptation.Development policy lending ---which aims to support policy and institutional reforms through budget financing --- was an effective instrument in advancingsubnational fiscal reforms in Hunan Province in China. The DPF achieved results through prior actions and time-bound outcometargets,which technical assistance (the main modality for Bank engagement with China on budget reforms over several years),could not easily deliver. The single tranche nature of the operation did not detract from the requirement for multi-yearinstitutional reforms as the Bank engagedHunan Provincein extensive policy dialogue from concept review in December2015 to program approval in January 2017. Moreover, the Hunan Provincial Government continued to engage the Bank in policydialogue about fiscal reform though 2018, takinga continuinginterest in the DPF reform objectives.Subnational fiscal reform in Chinasprovinces will require concurrent fiscal reform at the central government level,given the complex nature of inter-governmental fiscal relations in China. The experience with this DPF showed that fosteringthe sustainability ofprovincial finances is not straightforward because: (a) the central government continues to issueexpenditure mandates to subnational governments, and the mandates are commonly unfunded; (b)inter-governmentaltransfers, including general and earmarked transfers from the central government,are often volatile, complicating medium-termbudget planning; and, (c) relationshipsbetween provincial governments and LGFVs, UDICs,and PBSOEs that finance publicinvestments and receive budget subsidies are complex. Even asLGFVs are phased out and replaced by commercial SOEs, thecontinued existence and operations of PBSOEs and the emergence of PPPs and SPVs will keep inter-governmental fiscal relationscomplex.Considering the difficulties encountered by theHunan ProvincialGovernmentin conducting acomprehensive DSA, a simplified DSA framework would be better suited for future fiscal reform initiatives in otherprovincesacross China. The provincial government struggled to determineits off-budget liabilities,contingent liabilities,andoff-balance sheet liabilities ofLGFVs, UDICs, andPBSOEs. The Bank is reportedly working with the FiscalAcademy of the central governments Ministry of Finance to develop a simplified DSA template that could be used at theprovincial level to support subnational fiscal analysis and planning.
P157416 | Trans-Anatolian Natural Gas Pipeline Project | Europe and Central Asia | Europe and Central Asia |  |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099040007262226913/text/P15741604fb2200610800d0ef9ac03444f9.txt | http://documents.worldbank.org/curated/en/099040007262226913/pdf/P15741604fb2200610800d0ef9ac03444f9.pdf | IEG derives the following lessons drawn from the ICR:1. The use of shareholder finance in lieu of projectfinance can sometimes be useful when project structures are complex. In the case of the TANAP project, the choice ofthe financing structure was justified in light of the complexity of the Southern Gas Corridor program project, the strategic natureof the project, and the possibility of minimizing implementation delays, which would have had substantial impacts on downstream gascustomers and consumers.2. For large infrastructure projects, it is important for institutional structuresfor implementation to be put into place prior to Board approval. The TANAP operation was implemented on time, underbudget, and with full fiduciary compliance, which was possible because it was appraised when the institutional structure forimplementation was fully ready, the main contracts had already been procured, and works had already begun.3.The World Banks involvement in transformative infrastructure projects can help deepen engagement with countries at a broaderlevel, thereby enabling wider contributions to country development agendas. The Banks involvement in theTANAP project led to the building up of trust which facilitated engagement in several other areas under the umbrella of the BankGroups Country Partnership Framework (CPF) for Azerbaijan FY16-20. It also demonstrated to the government andwider stakeholders in Azerbaijan how the Bank could engage and deliver on important projects, thereby paving the way for otherpartners to support the country.
P157425 | Transformation of the Tertiary Technical and Technological Institutes Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2017 | 2024 | 2025 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099112024134010188/text/P157425-2b64d7f7-e569-46de-b0cd-433bb5301870.txt | https://documents.worldbank.org/curated/en/099112024134010188/pdf/P157425-2b64d7f7-e569-46de-b0cd-433bb5301870.pdf | The ICR (pp. 30-31) provided insightful lessons, including the following:During preparation, recognition ofmacroeconomic conditions and political realities in project design and scope can mitigate known risks.While Bankteams have little control over a countrys economic and political context, project design can be well-targeted and the loanamount more modestly scaled to increase the likelihood of achievement of objectives.When reengaging with a countryafter a long hiatus, implementation arrangements that realistically account for institutional capacity can enable implementationreadiness and implementation efficiency.Large-scale civil works can be a complex undertaking, especially incountries with limited experience and knowledge of Bank policies on procurement and safeguards. Project components can besuccessfully implemented when capacity is accurately assessed during preparation.Monitoring of progress isimportant to verify achievement of project outcomes. A clear causal link between project-financed interventions andobjectives enables attribution of results to the project rather than external factors. Accurate monitoring and reporting areessential to assure accurate attribution.Implementation support can enable course corrections to right-size aproject.When a project is substantially downsized and multiple restructurings occur, Bank teams can providesubstantial implementation support while focusing on development outcomes and maintaining implementation efficiency.
P157469 | Development Policy Credit 2: Fiscal Sustainability&Investment Climate | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  |  |  | The ICR has five lessons with which the review agrees. Three of the lessons are summarized below asexamples. Focusing on enacting legislative reforms rather than endorsing them for submission toParliamentwould support implementation better, and lead to achieving results; Strengthening the governments technicalcapacity would support reform implementation. Therefore, the WBG needs to focus on institutional strengthening and tailor futureoperations to existing capacity; Focusing on few key areas of reforms would help achieve better results giventhe governments weak implementation capacity.The review adds the followinglessons: Strengthening capacity alone will not solve the problems nor will better agency coordination. To designbetter programs and correct ones that do not function well,the WBG and the government must know what went wrong, why and howto improve program performance. A mismatch between means (e.g., implementation) and ends (e.g., objectives and results)calls into question the adequacy of policy design and of implementation arrangements. Because implementation is the only source ofexperience that can guide managers to test and improve programs, policy design and implementation must be looked atsimultaneously.
P157473 | Gabon Statistical Development Project | Western and Central Africa | Gabon | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | IPF | 2017 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099101024161041095/text/P157473-9df929d4-748c-464c-8492-37a6aa23babf.txt | https://documents.worldbank.org/curated/en/099101024161041095/pdf/P157473-9df929d4-748c-464c-8492-37a6aa23babf.pdf | IEG agrees with the lessons set out in the ICR (pp. 29-31).IEG adds the following: Periodicalrevisions the RF are important for ensuring that all significant aspects of aprojects impact are assessed anddocumented. Revisions to the RF allowfor a more thorough evaluation of a projects effectiveness andcontribution to development goals. Revisions help projects to better reflect their impact and address any gaps that might exist inthe original RF. For example, in the Gabon project specifically, monitoring the number of scholarships provided would help assessthe enhancement of human resources capacity. Other indicators could have included the number of decrees and policies developed andimplemented, such as the establishment of the INSTAT and new regulations for the NSS. Additionally, tracking the time taken fromdata collection to publication for various surveys and censuses would have helped assess improvements in datadissemination. Strengthening the institutional capacity of statistical agencies is foundational forlong-term project success.Such programs should encompass technical training, management development, andinfrastructure improvement, tailored to meet the specific needs of the institution. Additionally, ongoing TA and mentorship shouldbe provided to support continuous development. By building a robust institutional framework, the project can sustain its benefits,allowinginstitutions to independently enhance theircapabilities. Investment in moderndatatechnologies for data collection, processing, and dissemination can significantly improve the accuracy, efficiency, andtimeliness of statistical outputs. The project incorporated some technological advancements like the CATI system for datacollection, which enhanced the capabilities of DGS staff. While constituting an initial investment that increases cost in theshort-term, advanced data technologies are in the long-term important for streamlining operations and providing real-time datainsights, which are inputs for timely decision-making and project adjustments.
P157490 | Indonesia's Infrastructure Finance Development (IIFD) - RE | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Other | Infrastructure, PPP's & Guarantees | RETF | IPF | 2016 | 2023 | 2024 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099112023182030889/text/P157490026140101408f0503ccca39262c9.txt | http://documents.worldbank.org/curated/en/099112023182030889/pdf/P157490026140101408f0503ccca39262c9.pdf | The ICR identified multiple lessons learned and recommendations in paragraphs 82-94, which are generally sound, but this reviewhas highlighted four of them as rephrased below: A more focused capacity building strategy isrequired. While good results in terms of general PPP training across ministries and agencies has been achieved, a focus ondeveloping specific skills in targeted sectors is now required. The development of a professional cadre of PPP practitionerssustainably deployed to key sectoral GCAs will enhance activities such as project identification, project preparation and contractmanagement. Stakeholders expressed that there is varied level of sophistication, andthere is need to customize trainingwith more relatable local case studies and converting currenttraining content into Bahasa Indonesia, as well as allowingparticipants to conduct the examination in Bahasa Indonesia. This would help in improving the understanding of the content andencourage wider participation. Toward sustainedinfrastructurefinance development,the role of the PPP Unit needs to be enhanced. Toward taking the Indonesia PPP Program to the next level, the PPP Unitneeds to play a proactive and complementary role. The Projecthas set in place critical building blocks, which require to beenhanced and promoted. For instance, there is a need to advocate for PPPs and actively engage with line ministriestohelp them address sector policy issues, especially those related to creating a viable and efficient business model for PPPs. Theyneed to galvanize political support to reduce the sector funding gaps, as well as provide flexible government support mechanismstailored to sector needs. To accelerate the roll out of PPPs, there is need to roll out sector programs for PPPs ratherthan taking a project-by-project approach and ramp up capacity building and project developmentassistance. Growth of infrastructure finance requiresthe creation ofa viablebusiness models in key sectors. Many sectors have traditionally been dominated by SOEs and other government entities fordelivery of infrastructure and associated services. These sectors have a combination of policy bottlenecks and reluctance forchanges in front-end service delivery by the private sector. For example, in the health sector thus far most PPP projects have beenstructured as infrastructure-only hospital PPPs, thus constraining the fiscal affordability and achieving the full potential forvalue-for-money. Besides hospitals, there could be potential for PPPs in diagnostics and specialty care segments. Therefore,the PPP Unit needs to have a proactive policy dialogue with relevant line ministries to move forward with PPPs in thesesectors. Achievementof sustainable resultsin infrastructure financedevelopmenthingeon reconcilingfiscal management andobligationsand the designof sustainable PPPsmodels. Completed infrastructure experiencehigh funding gaps, emanating from high capital expenditureneedsand/or poor cost-recovery from end customer tariffs, such as in water, municipal waste and healthcare. In these cases,there is a need to address the sector funding issues. The complexity and magnitude of required funding make it critical that thesector level funding issues are addressed squarelyto device sector and programmatic solutions. There is a need todeveloppragmatic PPP options that are not solely based onbudgetary sources, and where tangible cost efficiencies orrevenue enhancementscan be derivedthrough PPPs models. There could be multiple funding solutions, such as revenuesharing from operating assets, asset monetization, blended financing and green grants, that could be customized to meet the varyingneeds of sectors and projects.
P157507 | PFM and accountability to support service delivery PforR | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | PforR | 2018 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100724153511193/text/P157507-96a9e3a5-dccf-48b8-a16e-0c64870a9bad.txt | https://documents.worldbank.org/curated/en/099100724153511193/pdf/P157507-96a9e3a5-dccf-48b8-a16e-0c64870a9bad.pdf | This was the first PforR Program in Pakistan, in the South Asia region of the WB, and in the federal and provincial governmentadministration sectors. The ICR offers two lessons. IEG agreed with them but would like to add one on programcomplexity.Successful program implementation, especially in a first-of-its-kind PforR, can be compromised if theoriginal program design is not simple. The Pakistan PFM PforR Program had a complex, wide-ranging, two-level PDO that wasapplicable at the federal and four state-government levels with diverse capacity, and covered PFM for greater accountability inservice delivery as well as improvement in procurement systems. As the PforR was being used for the first time in Pakistan,government officials were tasked with simultaneously implementing the Program while also learning about it, and striving to meet alarge array of targets set by eight Disbursement-Linked Indicators, five PDO outcome indicators, and 16 IRIs. The Programexperienced a two-year implementation delay, resulting in a problem project status during its early stages. This delayunderscores the benefits of a simpler initial design. A simpler design from the outset can be useful in preempting initialdelays, fostering a more productive learning experience and enabling gradual and longer-lasting capacity building at the federaland state government levels. Complex reform programs need to plan for adequate implementation time to allowthe achievement of outcomes. The Pakistan PFM PforR Programs successful implementation was undermined by aninadequate timeframe at the design stage and the lack of a sequencing strategy. The original timeframe was insufficient for anambitious PDO and the largescale reforms that were aligned with the governments 15-year PFM Reform Strategy leading to theextension of the Programs closing date by two years. Building institutional capacity is a long-term process. TheICR(para 34) noted that the Program experienced delays, mainly due to its nature and scale of reforms requiring multi-stakeholdercoordination across federal and provincial levels, as well as a lack of dedicated HR capacity. At least five steering andmanagement committees were established but staff in the implementing entities struggled with daily management issues. The ICR alsonoted that the project period was insufficient to manifest tangible improvements in the health and education sector outcomes (para45), and that a sequencing strategy would have helped leverage the progress achieved.A first-of-its-kind PforR canbenefit significantly from a TA component. The Pakistan PFM PforR was the first in the country and the client andstakeholders had little knowledge of its approach, challenges and logistics. These collectively undermined the Programsimplementation as the client required time to understand the instrument. A TA component and training on the PforR instrument forthe client and other stakeholders would have been useful to avoid delays in implementation. The ICR (para 48) mentioned that theWBs substantial support was positively embraced by stakeholders, but a TA component would have more effectively builtinstitutional capacity, particularly in change management, ME, trainings, and impact evaluations.
P157571 | Power Sector Financial Recovery Program | Europe and Central Asia | Armenia | IBRD | FCS | Infrastructure | Energy & Extractives | IBRD | PforR | 2016 | 2022 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099105006232234913/text/P15757100606c9082084eb0aa1d39f3afc8.txt | http://documents.worldbank.org/curated/en/099105006232234913/pdf/P15757100606c9082084eb0aa1d39f3afc8.pdf | The ICR (paras. 101 to 106) lists a number of lessons derived from the experience during Program implementation from among whichIEG derives the following lessons relevant to Programs undertaken in similar environments.The PfR instrument canbe a suitable choice for tackling the long-term, structural nature of challenges leading to poor financial performance in theenergy and infrastructure sectors. The Program was among the first of several World bank operations utilizing the PfRinstrument to support the financial recovery of infrastructure sector utilities. Financial distress is common in client countrypower sectors and not just in state-owned enterprises. The successful use of the PfR instrument under the Program showed how asmaller operation targeting financial recovery actions can generate substantial reform impact through a granular and well-sequencedDLI approach.Success of PfR operations requires stakeholders buy-in and commitment through a combination ofactions. These include deep analytical engagement at the design stage; strong Government commitment to the Programobjectives; realistic theory of change with an achievable timetable for the DLIs; and DLIs, including those related to the privatesector, that are within the control of the Government and/or implementing agencies. Continuity in oversight and support from astable supervision team - in this case over a six-year period - was a major factor in ensuring he Programssuccess.Standard electricity reliability indicators may not be the most appropriate measures of projectoutcomes. The Program relied on system-average interruption frequency (SAIFI) as a PDO indicator even though thisindicator takes time to show any improvement; is relatively to measure adequately; and can be affected by many external factorsoutside the Programs control (e.g. weather variations). Future programs aiming to improve reliability should also considerusing indicators that can be more immediately linked to Program results.While private participation ininfrastructure provision is desirable on considerations of fiscal prudence,operational efficiency, and quality of serviceprovision,care needs to be taken to craft the right set of incentives for balancing public and private interests. Inthe case of the Program, while the private power distribution company benefited financially from the incentives provided under theProgram, the lack of a clear incentive and penalty structure in its license undermined the ability of the GoA to ensure that thePDO indicator target for reliability was met.Programs that include the closure of state-owned companies shouldinclude provisions for addressing labor issues, including retrenchment, that may occur as a direct and indirect consequence of theWorld Bank financed intervention. While PfRs rely on national systems and laws,any PfR that includes measuresresulting in retrenchment should review the appropriateness of the relevant provisions in the national systems and ensure theiraugmentation, if needed, in line with the principles in the Banks Environmental and Social Framework(ESF).
P157671 | Angola Statistics Project | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099102023103014003/text/P15767104a84410470a9dd0fc9b4eba5d73.txt | http://documents.worldbank.org/curated/en/099102023103014003/pdf/P15767104a84410470a9dd0fc9b4eba5d73.pdf | The ICR (pp. 21-23) offersa range of insightful lessons covering staffing needs for project implementation, management ofproject stakeholders, improving fiduciary performance in a low-capacity context, improving project monitoring and evaluation, andimproving outcomes for statistical capacity-building projects. Key specific lessons include: Even with additionalsupport from Bank specialists, implementation of a project without qualified specialists in fiduciary performance and monitoring evaluation can have significant negative impacts on a projects success. Achievement of outcomes requires a dedicated andmotivated Project Implementation Unit staffed with a project coordinator and specialists in fiduciary and ME. The hiring ofstaff with critical expertise may be considered as a condition for project effectiveness or significantdisbursement. Adequate planning and budget monitoring tools are required to keep adequate track of operational and unitcosts. In this case, cost overruns had adverse impacts on project timelines and results. While external audits can provideimportant ex ante lessons to underpinchanges at a future time, timely real-time tracking can serve as a dynamicdashboard to make immediate course corrections and save project costs.IEG offers the followingadditionallesson: Country context and country experience are important factors in project design, especially in situationswhere survey field work is anticipated.
P157691 | Micro, Small & Medium Enterprise and Large Enterprise Supply Chain Finance | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2016 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/346191593553462103/text/Turkey-MSME-LESCF-Project.txt | http://documents.worldbank.org/curated/en/346191593553462103/pdf/Turkey-MSME-LESCF-Project.pdf | This ICR Review draws the following lessons from this project.Having well-defined sub-loan and sub-projectcriteria, terms, and conditions facilitates the implementation of credit line operations. In this project, theeligibility criteria for MSME and large enterprise borrowers, the eligibility criteria for sub-projects, the terms and conditionsof sub-loans to MSMEs and large enterprises, and the approval procedures for sub-loans to MSMEs and large enterprises were clearlydefined in the PAD, incorporated as covenants in the Loan Agreement, and included in the project Operations Manual. Accordingto the ICR (pages 16-17), the project benefitted from having well-defined operational parameters that were agreed upon duringpreparation. Moreover, the clear design of the project enabled the utilization of future reflows, helpingsustain the project outcome.It is important for the Bank and a borrower to be highly responsive to theeffects of political and economic shockson the implementation of an operation. In this project, the coupattempt in 2016, the indictment by the U.S. of a former Halkbank officer in 2017, and the currency and debt crisis of 2018,required, at the very least, a discussion between the Bank and Halkbank of thepossibility of adjusting the project parametersto address changed conditions in the credit markets. In response to the indictment of the former Halkbank officer, the Bankbroadened the scope of project audits. And in response to the currency crisis, the Bank allowed working capital loans tolarge enterprises and waived the requirement to confine 15 percent of sub-lending to sub-projects in priority regions of thecountry.Credit line operations need to be placed in the larger context of banking, non-bank, and capitalmarket development in the long run. In this project, the PAD explicitly recognized that the Turkey Micro, Small andMedium Enterprise (MSME) and Large Enterprise Supply Chain Finance Project, like other MSME credit line operations inthecountry,was a bridge measure that was bothnecessary and beneficial until Turkey made greater stridesdeveloping long-term sources of finance for MSMEs in its banking system,non-bank sectors, and capital markets. In thisregard, concurrent efforts by the government and the private sector to reform the countrys collateral regime, improve thecredit information system, revise the bankruptcy law, as well as deepen the capital markets (including by introducingsecuritization, project bonds, and long-term Sukuks)are treated as complementary initiatives to MSME credit lineoperations.
P157704 | First Fiscal Consolidation, Sustainable Energy and Competitiveness DPF | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2016 | 2017 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/816741624540038239/text/Egypt-Arab-Republic-of-1st-Prog-DPL-on-Fisc-Sust-Energ-Comp.txt | http://documents.worldbank.org/curated/en/816741624540038239/pdf/Egypt-Arab-Republic-of-1st-Prog-DPL-on-Fisc-Sust-Energ-Comp.pdf | The ICR offers the following finding and lessons with which the review agrees: The most important reason for thesuccess of the DPF series was the Governments ownership of the reform program, which had been started before the DPFprogram. Leadership in monitoring and coordinating the program by one government agency, in this case the Ministry ofInvestment and International Cooperation, was fundamental to resolve blockages throughout theprogram. A complexprogram with potentially large redistributive effects requires a communication strategy to explain the reform program to thepublic. Such effort involves reaching a wide group of people (NGO, citizen groups, legislators) to explain the reforms and theirobjectives and build support for them. Doing so helps raise awareness about the distributional impact of maintaining the statusquo, where the main beneficiaries of the energy subsidies were the richest groups. In the short run it is difficult tooffset the full impact of an adjustment action like a large devaluation. The welfare effects of such actions and their impact onthe poor are likely to be offset over a longer period, in part by higher economic growth and job creation, and in part by targetedsocial protection measures. Reforms seeking to correct misalignment in the structure of prices of electricity and energyproducts must be accompanied by tax measures and the reduction of electricity and fuel subsidies with the creation of fiscal spaceto finance social protection programs to help the poorest groups. A good stock of knowledge can enhance the substance andthe quality of design and implementation of a reform program aimed at bringing deep structural changes in the power sector. Thatknowledge and background permitted the Bank to make a good case for the relevant actions, their impact on critical groups ofsociety and their link to the programs stated objectives. Early and sustained collaboration within the World BankGroup and a staffing model based on field-based task team leaders facilitated the exchange of information within the Group andhelped build a strong relationship with the client and keep program implementation on track.
P157801 | Sustainable Fisheries Resources Development Project (Fourth South West Indian Ocean Fisheries Governance and Shared Growth Project) | South Asia | Maldives | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099112123191015826/text/P1578010f099d70ab09bd601d6ccd87b262.txt | http://documents.worldbank.org/curated/en/099112123191015826/pdf/P1578010f099d70ab09bd601d6ccd87b262.pdf | The ICR (paras 86-88) provided three lessons. Additional lessons were provided during the IEGs meeting with the TTL. Fourof those lessons are presented here with rephrasing as these may be useful for the other projects on expanding fisheries andmariculture sector in the small island counties.The fisheries sector has the potential to emerge as a fallbacksector to absorb laid-off labor from the other sectors if the fisheries sector can be more diversified and modernized.Despite the initial anticipation at the outset of the pandemic, the fisheries sector achieved a rapid export turnaround. Evenduring 2020, which experienced a few months of lockdown, the export was 13 percent higher than in2019, and exports furtherincreased by 9 percent and 16 percent in 2021 and 2022 (ICR, para 87). However, the fisheries sector could not accommodate labormobility from the declined tourism sector even temporarily because the fisheries sector could not absorb additional labor andlacked modern infrastructure like cold storage and canning facilities.Combining knowledge/reform-orientedactivities and infrastructure investments can be beneficial when complementing each other. In this case, component A ofthe project focused on infrastructure installation, such as Vessel Locating Devices and electronic observer systems. However, itwas necessary also to implement regulatory reforms to ensure compliance with fishing protocols in the Maldives. The development andoperation of the complementary Fisheries Information System played a crucial role in utilizing the electronic observerseffectively.If the mariculture sectors growth isenhanced, it mayattract more privateinvestments. The project used a design-build-finance-operate-maintain and transfer (DBFOMT) concession to mobilize privatesector financing of US$8 million for the construction of the multispecies hatchery and an additional amount for operation andmaintenance of the facility at no cost to the government (ICR, para 55). However, despite the governments keen interests inprivatization, private entities generally have limited interests in mariculture due to the low expected growth rate of themariculture sector compared to the fisheries sector (TTL meeting). To build on the projects success in private capitalmobilization, more support for privatizing public investments and enhancing the mariculture sector would beneeded.If asound human resources development strategy for implementation agencies is in place, then there isa higher potential thatadequate technical expertise in the implementing agencies will be retained. Although theproject introduced an innovative private sector-led approach to mariculture development, the Ministry of Fisheries, MarineResources and Agriculture (MoFMRA) had no expertise and motivation to operationalize the private sector-led approach and facilitateprivate sector leadership (ICR, para 59). During preparation, the capacity assessment could have included a thorough analysis ofrisks to appropriate staffing, staff retention, and bureaucratic hurdles in the human resources development strategy. As ariskmitigation measure, adopting the right types of incentives to ensure staff motivation can reduce detrimental and frequentturnover and underperformance.
P157804 | Sri Lanka Competitiveness DPL | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2017 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/485741553530764606/text/Sri-Lanka-Sri-Lanka-Competitiveness-DPL.txt | http://documents.worldbank.org/curated/en/485741553530764606/pdf/Sri-Lanka-Sri-Lanka-Competitiveness-DPL.pdf | The ICR identified two lessons asrephrased below:(i) Economic and sectorwork (ESW) and technical assistance (TA) are the essential building blocks that pave the way for thedesign,implementation and performanceof a DPF operation.This operation becamepossiblebecausethere wassizable completed or ongoing ESW in the areas of reform. The reform agenda was able to be sustained dueto the TA provided by the Bank and external donors. In this case, theDFATtechnical assistance supported by theWorld Bank has been effective in maintaining the reform momentum under the Development Policy Financingoperation.(ii) When the conditionsfor a programmatic DPF are not met, it isworthidentifying windows of opportunities that can make a stand-alone and short-term DPF feasible .Thisstand-alone DPF operationcreated the space to achieve substantial results in the context of political uncertainties.TheWorld Banks operation was able to provide strategic support to the reform momentum generated by a coalition Government.Careful consideration is important to ensure that targets for progress indicators are achievable within the shorter implementationtime frame of the operation.
P157858 | Secondary Education Improvement Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2017 | 2023 | 2025 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | Three key lessons can be drawn from the projects interventions: Strong leadership and timelyimplementation support can lead aproject toachieve critical results needed to strengthen institutionalcapacity. In this project, strong leadership was exhibitedby the Secretary of State, who acted as the ProjectDirector, and the PMT,comprised of Directors and Director General of various departments under MOEYS to oversee theprojects activities and programs. As a result, monitoring was consistent and timely, and the project met its objectiveswithout a need for restructuring. Structuring project implementation and financial management system around agovernments existing management arrangements can strengthenimplementation and fosterownershipof aproject. In this case, the Department of Finance was responsible for the projects overall financialmanagement, which included the governments own provision of funding on scholarships, tuition, and stipends to teachers andschool management officials. This arrangement ensured governmentownership while building sustainability for future expansionof the program. A performance-based approach through DLIs can providegovernments witheffectivetools to promote fundamental change in improving service delivery. Thisproject achieved critical results through thereform of SBM, which led to qualifying targeted schools achievingthe minimum effective school standards. In addition,centering communities at the forefront of school management and planning systems fostered strong institutionbuilding andownership at the local level.
P157900 | Mali - Poverty DPO | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2022 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/981811636395475586/text/Mali-Mali-Poverty-DPO-Series.txt | http://documents.worldbank.org/curated/en/981811636395475586/pdf/Mali-Mali-Poverty-DPO-Series.pdf | The ICR provides the following lessons, with which the ICRR concurs with some modification of language. The scopeof the PDO should reflect the limited range of feasible PAs and the constraints of the implementation timeframe. In the PRISGOseries, PDOs are set at such a high level that is impossible to evaluate them against performance criteria. The PDO needed to bemore narrowly specified so that reforms underpinning them can be more closely linked to the objectives. Overambitioustriggers had to be downgraded in the PRISGO2 and ended up being input focused due to limited progress. In setting triggers,acknowledging capacity constraintsas well as political and security risks is essential . An explicit results chainprovides a focus for assessment of program design. As pointed out by the ICR, many reforms focus on inputs and activities and leavegaps detailing how these activities will contribute to the achievement of ultimate objectives such as land security and effectiveuse of agricultural inputs. A clearer results chain would have clarified each step (and associated risks) towards achievingoutcomes and objectives and how to measure progress. Results indicators need to track progress towards achieving theassociated objective. This requires avoiding RIs that focus on partial results, achieving inputs or simply measuring whetheractivities were completed. Technology can be leveraged to facilitate ME in conflict affected areas. The IBMphone survey was used to significant effect to evaluate the first pilot of the e-voucher scheme, and was used also for theoperation (e.g. on land commissions). Although those not covered by mobile network would not be accessible through this approach,the IBM survey provide a low cost and effective means to gather information, also at mid-term. Addressing complex policyareas such as the energy sector requires a robust political consensus. To aim to achieve meaningful progress over three years, inareas such as energy reform where progress has been stalled during many years prior, is unrealistic. DPOs may not be theappropriate instrument for achieving such reforms.
P157922 | DR Congo - Education Quality Improvement Project (EQUIP) | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Human Development | Education | RETF | IPF | 2017 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099030424171536235/text/P1579221cfac0c0081974d104132704af3b.txt | http://documents.worldbank.org/curated/en/099030424171536235/pdf/P1579221cfac0c0081974d104132704af3b.pdf | The ICR provided some important lessons learned, the most relevant of which are summarized below:Performancebased financing (PBF) can be an effective instrument to focus on results rather than inputs.This is particularlyrelevant for countries such as the DRC, as it shows that PBF strategies can be implemented in fragile and conflict-affectedsettings. Commitment from the MEPST and the government was key in the implementation of this policy.One particularlyimportant outcome was that, as a result of the incentives posed under the PBF, more female teachers were hired.Addressing sexual exploitation and harassment is a critical component of any effort to increaseenrollment and permanence of girls in schools. The project focused on communications campaigns to raise awareness,removed stereotyping in textbooks, included this topic in teacher and administrator training, and implemented aGRM.Subsequently, two projects will be addressing this cross-cutting area in order to sustain theseefforts.Effective training for teachersgoes beyond in-service teacher training. A teacherprofessional development system includes training at the pre-service and in-service levelsas well as continuous supportthrough classroom observation and feedback. Thisproject only provided a short-term training program through cascadetrainings.This limitation was recognized by the country and the Bank, and a wider scope of teacher development activitieswill be supported through the two new projects.Ensuring that textbooks arrive and are used in the classroom is acritical factor in achieving better learning conditions.The project supported a last-mile textbook distributionsystem to avoid a previously observed situation where textbooks would arrive at the district level but would not reach theclassroom.Logistics are particularly challenging in large countries with underdeveloped infrastructure, difficult climateconditions, and conflict situations.Defining a realistic results framework is fundamental to the processes ofevaluating outcomes and monitoring progress.The original project design had a very large set of indicators to bemonitored, with a particularly large number of them at the PDO level.While the restructuring reduced the number ofindicators, it was still large. A well-designed theory of change can contribute to the design of indicators, so as to selectivelytrace project activities and measure results and outcomes.
P157932 | Improving Access to Affordable Housing Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2017 | 2022 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099330006292229001/text/P15793200e0b870810932d06959e1e7b7ad.txt | http://documents.worldbank.org/curated/en/099330006292229001/pdf/P15793200e0b870810932d06959e1e7b7ad.pdf | The ICR presented 5 lessonsfrom the operations that task teams may consider whendesigning future similar projects inmiddle income countries like Mexico: (ICR, paragraphs 80 - 84). Four of these are below,slightlymodified: A clear definition of the value added offered by the World Banks assistance may helpcountries that have strong housing sector institutions.In this project, contributionsto the existinginstitutions and programs were (i) offering solutions to last-mile challenges facing disadvantaged populationgroupspreviously excluded from receiving housing assistance; and (ii) optimizing benefits toclimate, gender, and citizenengagement. The projectbuilton the countrys strong institutionsand took advantage ofthegovernments interestto do more for the target population. Thegovernment commitment gave theproject team thesignal to innovate and experiment for incorporatingenvironmentally-friendlyfeatures of affordable low incomehousing. High quality technical and analytical work maystrengthen a flexible design.In this project, existing housing sector institutions, an operational framework in place, and thegovernment commitment to lowincome housingfacilitatedimplementation. The Bank team complemented these advantagesbyconductingsubstantive analytical work before and during preparation to help CONAVI calibrate the design of its housing programto reach previously excluded groups. The analytical work informed the annual adjustment of the OperatingRulesof the CONAVI Social Housing Program, including before appraisal.Technical assistancealso providedstrategicnarratives to innovate on features of the low income housing interventions.Including housing designfeatures that promotedenergy efficiency, resilience, and sustainability in self-produced homes also increased thegovernments collection of useful features to strengthen sector programs such asthe National HousingProgram 20212024. Sector support where sophisticated housing markets arein placemay findadded value by targetinglow incomehousing needs.In this project. market-based housingfinance was available to most middle-income people.The poorer segment isusually characterized by a lack of access tobasic banking services, much less to mortgages or housing finance products. The project demonstrated that innovative interventionsmaybe tied to products of the formal housing finance markets to reachexcluded groups of low income households,including informal sector workers and those relying on self-production. The innovation may featureeasing the regulatoryenvironment to enjoin participation bylocal organizations, such as nongovernmental organizations, saving banks, andcooperatives in providing housing finance related services. Microloans and specialized technical assistance may be used tocomplementthe allocation of federal direct housing supports to increaseaccess to housing finance and ensuretheappropriate use of resources and housing quality. The building and housing sector projects maybenefit from incorporating climate change mitigation and adaptation features in housessupported by public programs.The building and housing sector contributes up to 40 percent of global Green House Gas (GHG) emissions and energyuse.In this project,homes were designed to maximize energy efficiency gains, reduceemissions, and resilienceto climate impacts and natural hazards. These features could significantly contributetolow-carbon, resilient future. Climate change poses threats to poor people living in precarious, overcrowded homes, builtwith inadequate materials. This segment of the population usuallylack technical expertise, and furtherexposethemto adverse climate and health impactscaused by water leaks, poor ventilation, overheating, and dirt floors. Theproject showed that incorporating sustainability measures in housing design and constructionreduced energy consumption andemissions, reducedelectricity bills, and ledto greater indoor temperature comfort. The TA in this project helped buildtechnical capacities to apply sustainable housingsolutionsfor self-builders (under Component 2) and provideddatato measure impact.
P157987 | National Strategy for Development of Statistics Implementation Support | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2018 | 2024 | 2025 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial |  |  | As a lesson, the ICR highlights that to prevent delays in implementation, the costs of a PIU must be properly budgeted, and thePIU should be granted the authority needed to approve activities. This can be accomplished by strategically positioning the PIUwithin the national statistics office and establishing an internal prior approval mechanism based on agreed workplans andbudget.IEG adds that establishing an enabling environment through legal and regulatory frameworks for the production anddissemination of core official statistics is critical to developing and sustaining statistical capacity for evidence-basedpolicymaking. The enabling environment should align with international standards and support the independent production and use ofofficial statistics.
P158078 | Togo Economic Governance Project | Western and Central Africa | Togo | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2018 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099031424172095629/text/P158078167dbeb03518faa1f53f94ea2fe2.txt | http://documents.worldbank.org/curated/en/099031424172095629/pdf/P158078167dbeb03518faa1f53f94ea2fe2.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. A well-defined project design, driven by robust analytical underpinnings,and understandingof political dynamics may raise the potential for success even in fragileenvironments. The project design reflectedthe Governments priorities. The analytical underpinnings formed the basis for establishing clear andmeasurable goals.This ensured Government commitment and cooperation with other development stakeholders.2. Proper sequencingof reforms in Public Financial Management (PFM) initiatives may help in addressing downstream complexities in fragilesettingswith low initial benchmarks. The project prioritized laying the groundwork for PFM enhancementseffectively, recognizing Togos low initial benchmarks and its status as a fragile country atappraisal.3. Achieving and attributing service delivery improvements within the timeframes of individualGovernance operations can be challenging. Although the project supported activities with solid rationale, their discretenature hindered establishing a direct link to enhancing service delivery.
P158111 | Tunisia Business Environment and Entrepreneurship DPF | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2019 | 2021 | ICRR | >=100 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/376871607987900947/text/Tunisia-TN-Business-Environment-Entrepreneurship.txt | http://documents.worldbank.org/curated/en/376871607987900947/pdf/Tunisia-TN-Business-Environment-Entrepreneurship.pdf | The ICR offers several lessons, with which IEG agrees. When there is a strong expectation of rapiddisbursement,a standalone DPL operation might not be suited for deep and longer-term reform. When this operation wasapproved the Bank was approaching its exposure limit to Tunisia; therefore, the opportunity cost of approving a large loan is highif its implementation risks are high. To capture the impact of reforms, the results framework must have resultsindicators that measure the operations impact over its time horizon. With a strong ME system in place it is unlikelythat prior actions 5 and 6 would have been adopted, and it would have been evident that the impact of reforms supported by prioractions 4 and 7 would take more time than the duration of the DPL. More effective arrangements are necessary tofacilitate coordination,monitoring and follow-up ofreforms implemented. Leadership and coordination of politicallysensitive reforms requires a powerful and capable entity with the authority to supervise other ministries and agencies and quicklyaddress bottlenecks and issues with commitment to reform. This role was played by the MDICI which, post-revolution, had lost partof its mandate and its capacity to coordinate reform implementation by other ministries. To enhance the impact on resultsit is necessary to (a) allocate more resources fortechnical assistance to support implementation and (b) redress the balanceof the Banks internal incentives from preparing new operations to monitoring the impact of subsequentoperations.
P158138 | Youth Economic Inclusion Project | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest |  |  | The ICR (pp. 22-24) presents several lessons generated through this project:It is essential that institutionalarrangements are based on a thorough analysis of institutions technical, operational, and convening capabilities. Theprojects chosen arrangement aimed to improve the MFPEs capacity and authority over the MFPEs implementationagency (ANETI). However, issues like limited internal capacity, lack of experience with World Bank-financed projects, procurementchallenges, and recruitment rules affecting government staffwere known during project design and should have been consideredduring decision-making at the time, along with issues related to mandates, funding, legal responsibilities, and politicalrisk.To avoid delays that can affect project outcomes, it is important to ensure early on that PIUs andimplementing agencies have the capacity to manage procurement processes effectively. Public procurement in Tunisia isregulated by multiple institutions, including the Public Procurement Authority, Market Control Commissions, Evaluation Committees,and Opening Committees. All procurement activities for World Bank-financed projects must pass through these entities beforecontracts can be signed. Obtaining clearances from each institution is time-consuming and requires expertise from PIUsandimplementing agencies. This suggests that, in order to avoid delays that could jeopardize project outcomes, it is crucial to ensurethat PIUs and implementing agencies have the necessary capacity and readiness to manage and expedite procurement processeseffectively.Strong innovation or system-strengthening project outcomes cannot be effectively captured if theseobjectives are not included in the projects RF. In this case, the projects objectives were not clearlyreflected in its RF, limiting the ability of the Bank and the government to track progress and provide timelyoversight.Simplifying project design and focusing on core activities that are better aligned with the vision andmandate of the implementing agency can increase implementation efficiency. The project required numerous preliminaryactions, including setting up aMIS, data systems, and VCD analyses, before beneficiaries could be processed and fundsdisbursed, suggesting that the range of innovations might have been better implemented through a phased approach over a longer timehorizon, potentially across several projects (including TA or capacity-building-focused programs). In this regard, theprojects entrepreneurship component showed promising results, with the straightforward design under the second restructuringbeing effective in supporting entrepreneurs during its implementation over 12 months. By streamlining and refocusing on coreactivities, the project could efficiently solicit, process, and select many entrepreneurial projects for funding. While this shiftmeant that some important innovative and system-strengthening elements were lost, the simpler design better matched theMFPEs vision and mandate, resulting in accelerating the implementation of the remaining activities.
P158140 | DPL to reform the Indonesian maritime logistics sector | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/567201591623930709/text/Indonesia-Indonesia-Maritime-Logistics-DPL.txt | http://documents.worldbank.org/curated/en/567201591623930709/pdf/Indonesia-Indonesia-Maritime-Logistics-DPL.pdf | These lessons are drawn from the ICR:Sector-specific programmatic designs enhance the impact ofreforms. When the choice is between a broad multi-sector approach to reform and a focused one, in this case thelatter was successful in generating intended in-depth policy reforms that might not have been possible to the same extent had theengagement involved a broader set of complex themes.Complementary instruments to address risk can facilitatethe implementation of reforms. In this case, capacity and institutional risks were identified at appraisal, andmitigating measures technical assistance and advisory services were introduced, drawing line ministries closer intothe reform process. However, longer term sustainability is still at risk due to capacity challenges among some keypartners.A good implementation agency is vital for success. In this case, the project faced aparticular challenge of coordinating with other partners that had differing views about strategies for implementing logisticsreform, along with capacity weaknesses. Here, CMEA had a strong mandate from the President to coordinate theoperation,in that way serving as a strong conduit for the Bank in assisting line ministries and agencies to fulfill theirroles.In addition, IEG suggests the following lesson:The time horizon for reform should be considered intandem with the length of the PDO. In this case, a specific target had not been set in consideration of challengesof attribution; instead, other arrangements had been put into place to maintain momentum, notably World Bank TA and bilateral donorsupport, underpinned by strong government commitment.
P158194 | Myanmar Flood and Landslide Emergency Recovery Project | East Asia and Pacific | Myanmar | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099102723185512026/text/P158194003e0e20b90bd2f0335be3fc04ed.txt | http://documents.worldbank.org/curated/en/099102723185512026/pdf/P158194003e0e20b90bd2f0335be3fc04ed.pdf | The ICR (p. 28-29) included several useful lessons learned, which were adapted by IEG: In the case of anemergency, countries benefit from simple Bank procedures that allow the Bank to respond quickly. In this project, the IRMmechanism was too complex to be implemented effectively. Slow procurement resulted in goods and equipment being procured for 18months, not allowing to provide support for the 2015 flood response. Communicating with other developmentpartners about the Banks safeguard policies is critical to ensure compliance and avoid implementation delays. Inthis project, the national road to be rehabilitated as fast as possible in Chin Statewas critical for residents. As a result,the government used other donor financing to start the rehabilitation. However, theBank determined that the rehabilitationwas linked to the planned project-financed works and was subject to the Banks safeguard policies, resulting in significantimplementation delays since corrective action plans needed to be developed before implementation couldcontinue. When FCV tools within the Bank are not available to the project team, providing adequate resources toenable third-party execution to facilitate implementation can be positive for project implementation. In this project, theteam could not benefit from certain Bank tools such as the Hands-on Expanded Implementation Support (HEIS) and FCV advisers, whichmight have benefitted project implementation.A lesson added by IEG: An insufficientlyoutcome-oriented objective can contribute to failing to choose outcome-oriented indicators that allow for measuring outcomesachieved. In this project, the very output-oriented objective contributed to the difficulty of indicators not measuringoutcomes since the objective did not signal that those outcomes were important.
P158298 | Strengthening Critical Infrastructure against Natural Hazards | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2018 | 2024 | 2025 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR(p. 21-22) included several lessons learned that were adapted by IEG: Designing DRM projectsaround the key DRM pillars can allow for comprehensive strengthening against natural hazards. This project design focusedon disaster risk identification, preparedness and response as well as financial protection against disasters and improving theresilience of critical infrastructure allowing a simultaneous strengthening of the DRM pillars and therefore allowing for acomprehensive approach that strengthens the countrys overall DRM capacity. Having financing resourcesavailable to allow for essential preparatory activities during project preparation can positively impact project implementation.In this project, the Project Preparation Advance (PPA) financed the conducting of feasibility studies, designing bridgerehabilitation and river embankment reconstruction in detail, preparing Terms of Reference as well as environmental and socialsafeguard documents during project preparation allowing for a smooth implementation start. Citizen engagement canensure support from local communities and beneficiaries and positively impact the sustainability of project outcomes. Thisproject conducted outreach activities during project preparation and implementation to ensure the engagement of local communitiesin project related decision making. Also, the project was able to achieve high local labor force participation in therehabilitation/construction of bridges and flood protection infrastructure, which also fostered local ownership.
P158333 | Second Regional Trade Facilitation Competitivess Credit | Western and Central Africa | Western and Central Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2017 | 2018 | 2019 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR has the following lessons with which this review agrees. Regional programs in which twocountries are involved in reforms are more likely to succeed if the two countries have more similar economic strengths or attachequal importance to the proposed reform agenda. For example, transit trade is more important for Togo than for CtedIvoire, andTogos economic relationship with Burkina Faso is more equal; Policy operations like the tworeviewed usually need technical assistance for carrying out many of the changes the operations support. Accompanying technicalassistance is essential for implementing the reforms; Difficult reforms require more than two years to work through thevarious stages to ensure implementation; Greater attention needs to be paid to prior analysis when designing a program.Both the poverty and social impact analysis and the political economy study identified potential losers and the risk of vestedinterests obstructing the reforms. These studies do not seem to have been adequately taken into consideration; Greatercarein definingresults indicators and targets eases program monitoring and assessment ofresults.IEG adds the following lesson, related to the penultimate bullet pointabove:Reforms carry with them changes in incentives. For reforms to succeed, it is necessary that theimplicit incentives the reforms create are aligned with the true incentives that are required to generate the expected results ofthe program.
P158463 | CI-DPO on Fiscal Management, Education and Energy Reforms | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2019 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099920005182241545/text/P1584630d8c5a101b0afd302103c9f567f3.txt | http://documents.worldbank.org/curated/en/099920005182241545/pdf/P1584630d8c5a101b0afd302103c9f567f3.pdf | Three lessons are drawn from the ICR, with some adaptation.Enhancing transparency is a vital first step indesigning and advancing structural reform programs. In this series, the institutional, technical, and financialaudits of the PVAM, the Reserve Fund, and the CCC-managed development funds were vital to understanding structural and operationalproblems in the governance and management of the cocoa industry.Regular and systematic conduct of independent audits wouldcontinue to be necessary moving forward to help design reforms that would address issues and questions raisedby the collapsein international cocoa prices in 2017: the viability of the government-set farmgate prices, the adequacy of the Reserve Fund toprotect producers from price drops, the utility of the development funds to support productivity initiatives, and the overallgovernance of the industry marketing, pricing, and support systems.Electricity tariffs remain a naggingissuein electricity service reform. In this series, the range of measures to improve the operational andfinancial performance of the electricity sector included improving collections of electricity bills, reducing and settling arrearsandrestructuring debt with utility companies, and reducing technical and non-technical losses in transmission anddistribution.A decree was issued adopting a methodology to set electricity tariff rates closer to operating costs, but theseries never required implementation of the adjustment.Aplan preceding this series to raise tariffs in 2016 wasrejected by customers, and a new plan to raise tariffs to cover operating costs atIPPs remains politicallycharged.However, the authorities must ultimately confront the issue if the scheme to attract private participation in energyprojectsis to succeed.Assembling a package of complementary support instruments can help strengthen theimpact of a development policy operation. In this series, the effort to improve the operational and financial performanceof the electricitysector was supported by related interventions includingan International Finance Corporationinvestment to expand the AZITO and CIPREL power plants, an IDA guarantee operation for the refinancing of short-term liabilities ofCI-ENERGIES, and a separate IDA investment project financing toreinforcethetransmission system, rehabilitate andextend thedistribution system, continue with rural electrification, and strengthen institutional capacity of the electricitysector. According to the ICR, these combined operations provideda critical mass of leverage toimplementdifficult reforms.
P158520 | Colombia Territorial Development Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2017 | 2018 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/260351584568282055/text/Colombia-CO-Territorial-Development-DPL.txt | http://documents.worldbank.org/curated/en/260351584568282055/pdf/Colombia-CO-Territorial-Development-DPL.pdf | The ICR provided nine lessons with the reflection of the operational experience that characterized the importance of ownershipand capacity of different levels of the government, Banks internal collaboration, long-term engagement, public awareness andactive participation to bring cadaster reform, and efficient and effective institutional coordination. The lessons were informativewhen implementing similar policy reforms in the area of territorial and financial management. The ICRs lessons are, however,limited to reflecting its operational expertise and lacked the critical assessment of the program design. The following lessonsthat IEG found are meant to inform the other DPFs in their program design.Clearly define objectivesof the pillars of a reform programThe program document was not explicit on what reform objectives of the policyareas/pillars expected and how these pillars contributed to the program objective. The program consisted of two pillars which were(i) strengthened institutions for land management and territorial planning and (ii) improved sub-national financial management andinvestment prioritization. The program document, however, did not present the objective or aim of the pillar and as a result, prioractions were simply a bundle of policy actions without a clear path to the objective. For instance, neither program document northe ICR explained the ambition or objective of Pillar 1 and simply listed the prior actions. As a result, the ICR was not able todemonstrate what consolidated outcome was achieved based on the group of prior actions. The lesson is that defining the objectivesof the pillars/policy areas enables the DPF to causally link prior actions through pillars/policy areas to the programobjective.Orienting prior actions and indicators to the outcomesWhile most prioractions in this program were oriented to the outcomes, some were limited to the process of the reform, leading to the limitedfulfillment of the policy reform. Such policies as multi-purpose cadaster, rural land administration and Contratos Plans clearlydefined the problem and thrust into the structural change of the policy area. Coupled with the criticality of the policy area, theoutcome of the prior actions was clearly presented. On the other hand, some prior actions such as financial reporting requirementsand standard project designs were the intermediate process to achieve the objective of the policy area. The indicators associatedwith the prior actions were also not designed to assess the outcome of the policy reform. As a result, the outcome of these prioractions did not capture the final outcome of the policy reform. The lesson is that when developing prior actions and indicators, itis essential to delineate the intended outcome of the reform, and prior actions and indicators need to be oriented to achievingit.
P158576 | Zarafshon Irrigation Rehabilitation and Management Improvement Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2018 | 2021 | 2023 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099525009202231119/text/P15857603a880b0d00a97f00b55b7caf1e6.txt | http://documents.worldbank.org/curated/en/099525009202231119/pdf/P15857603a880b0d00a97f00b55b7caf1e6.pdf | The ICR provided several lessons, two of which are summarized as follows:Long-term support through a series ofoperations is crucial for countries to reform their irrigation sectors and transition to basin-based management systems.There has been long-term cooperation between the Tajik Government and the World Bank in the agriculture sector dating backto 2006. The cooperation started with emergency projects focusing on irrigation expansion for rural livelihoods under FVWRMP andthen PAMP and PAMP II. This project focused more on institutional strengthening and sector reforms. The follow-on project isneeded, as the Government still needs support for adequate institutional arrangements to fully implement the National Water Code.Further support will also be required to ensure sustained success of the newly established SDLRI. Also, the technical and financialcapacity of the River Basin Organizations (RBOs), which are not yet fully independent from the ALRI, needs to be increased. WUAsalso need further support in terms of technical and financial capacity. Additionally, further work will be required on watermeasurement/and volumetric-based payment for irrigation water delivery, which was introduced in the river basin to ensurecontinuous success of this component. During this period, the PMU improved its capacity through the World Bank projects and thecore people who were involved in previous projects remained available for preparation and implementation of this project. It willbe important for the World Bank and the client to ensure that the same team will continue to prepare and implement thenext project.It is key for projects focused on irrigation infrastructure improvement and management to designirrigation efficiency and service delivery indicators that adequately measure project outcomes. Although yield increase iswidely used as an outcome indicator for irrigation projects, attributing crop yield increases only to improved irrigation servicesis not logical as it is prone to several external factors including climate, quality of soil, seeds, fertilizers, and otheressential agricultural inputs. Under the project the issue of agricultural data integrity also remained a challenge for theyield indicator. A robust impact evaluation, including collection of data from non-project areas, needs to beconducted at the beginning and closure of future projects. Future project designs should consider the impact of measurement systems(for example, volumetric measurement) on overall water management and define indicators that are measurable and attributable toproject activities (such as irrigation efficiency, adequacy and reliability of irrigation water). The Project also experiencedchallenges related to reliability of official data for evaluation of investments in the irrigation sector, indicating the need fora much more robust ME system not only at the project level but also at the national level.
P158643 | Pakistan: National Social Protection Program | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | PforR | 2017 | 2022 | 2023 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099052423145513313/text/P1586430a40f550ca0b611063165adaae39.txt | http://documents.worldbank.org/curated/en/099052423145513313/pdf/P1586430a40f550ca0b611063165adaae39.pdf | The ICR (pp. 24-25) cited a range of lessons and recommendations, some of which are restated here:Developingand sustaining an effective social safety net can contribute to timely and effective shock response. In this case, thedigital capabilities and safety net systems that were developed as part of the BISP agenda were efficiently and effectivelydeployed during the COVID-19 crisis and 2022 floods.Ownership and leadership at both the central and local levelsof a comprehensive social safety nets program are critical to success. In this case, creation of beneficiary communitycommittee groups facilitated engagement with key local stakeholders.Combining the Program for Results instrumentwith technical assistance can promote smooth and timely implementation. In this case, the well-defined programmaticframework ensured consistent focus on results, promoted in-depth sectoral dialogue, built capacity when and where it was mostneeded, and both catalyzed and harmonized additional sources of funding.Transparency can promote dialogue andidentify emerging issues. In this case, making program administrative data available on an external website allowed forfull transparency and the use of data for studies by external groups.
P158698 | Third Social Protection System Support (SPS-3) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2017 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The lessons are drawn from the ICR.National vision can be an overridingfactor for success. Teams need to be alert to government commitment in recommending reforms. In Rwanda, thegovernments sustained policies and financial commitment to social protection has facilitated dialogue with the Bank anddevelopment partners and created government-led policies that have facilitated ambitious forwardmovement.Early action on accountability and transparency can enhance the credibility ofpublic programs. Broad support is often necessary if a social protection initiative is to be successful. InRwanda, the introduction of an appeals and complaints mechanism, and subsequently broader accountability initiatives (socialaccountability, citizens engagement tools) helped ensure that beneficiary and other stakeholder views were mainstreamed intoproject planning and implementation.
P158717 | China: Hubei Inland Waterway Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2018 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099111424150530076/text/P158717-6d3163fd-7e15-41ba-a86e-53aebc25f98f.txt | https://documents.worldbank.org/curated/en/099111424150530076/pdf/P158717-6d3163fd-7e15-41ba-a86e-53aebc25f98f.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Capturing outcomes that are within the control of the project raises the potential for achieving theintended outcomes. In this project, the expected outcome of one results indicator was forecasted on assumed completion ofall three remaining complexes. Given that two complexes were not directly under the control of this project as these activitieswere not financed by the project, the expected outcome could not be achieved.2. A holistic approach may be raisethe potential for promoting IWT projects. This project addressed the constraint of low standard of the navigation channeland the low water level in the four month dry season, but there are still a number of challenges in promoting IWT along the HanRiver, such as development of ports along the Han River with good hinterland connectivity.
P158733 | Anhui Rural Road Resilience Program for Results | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | PforR | 2019 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR draws the following main results from the experience of implementing this PforR program, with some adaptation oflanguage.1. Designing a PforR program incorporating the priorities identified in the Government strategy, mayraise the potential for success of such operations. The design of this rural road operation was aligned with thepriorities identified in Anhui Provinces 13th Five-Year Plan. This ensured steadfast commitment by theprovince.2. The PforR design for flow of funds can help in incentivizing timely implementation of programactivities by local governments. Inthis operation, the Anhui Provinces Plan was to be financed through (i) subsidiesfrom national and the provincial government; (ii) counties general budget funds; and (iii) the IBRD loan. These funds flowedthrough the government treasury system managed by the finance bureaus at provincial and county level.Local governments weretherefore incentivized to carry out the Program activities with the innovation requirements on a timely basis to benefit from PforRfinancing.3. Having a consistent country-based co-team leader can help in facilitating seamlesstransition.Although there were four task-team leaders (TTLs) during the lifetime of this operation, seamlesstransition was facilitated by the co-TTL who remained on the team from project preparation until project closure.
P158739 | Colombia Fiscal and Growth DPL 1 | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2017 | 2018 | 2023 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/099355307212218984/text/P1587390a0249e09008b980481ddda1d99d.txt | http://documents.worldbank.org/curated/en/099355307212218984/pdf/P1587390a0249e09008b980481ddda1d99d.pdf | Flexibility of programmatic DPF enables timely adjustment to emerging policy challenges, such as a surge in migration(ICR, para. 76). The DPF series was adapted to address the major challenge to services and labor markets from a surge inmigration from Venezuela that required urgent policy action. Although seeking grant funding for this purpose came at the cost ofsome delay in the second operation, the supplementary funds enabled effective implementation, building on actions and institutionsalready being supported.Strong government commitment is crucial for effective implementation of criticallegislation and institutional reforms, based on clear objectives established in coordination with the World Bank. Stronggovernment ownership, based on strong coordination between the World Bank and the Government of Colombia in establishingobjectives and defining the RIs (ICR, para. 77) yielded timely passage of legislation underpinning many of the actions,enabling substantial overachievement of many targets that were set in the less certain environment before enabling laws had takeneffect. Conversely, the ICR (para. 74) indicated some uncertainty as to whether the momentum [on competitiveness] will be asstrong under the new administration taking office in August 2022 while expressing optimism that the policies recentlyapproved and instruments implemented would be sufficient to maintain momentum on competitivenessunder a newadministration.
P158768 | Public-Private Partnerships and Public Investment Advisory Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2018 | 2025 | 2024 | ICRR | Less than 10 million | Highly Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Twolessons are drawn from the ICR, with some adaptation.Building a strong legal and governance frameworkfor public investment and public private partnerships is vital to developing viable infrastructure projects. Thisoperation placed a strong emphasis on settingthe legal, regulatory, and institutional framework for infrastructure projectpreparation and appraisal. Although the Government failed to take a project to tendering and could only manage to completeand approve one feasibility study, the elements of thelegal, regulatory, and institutional framework were wellconsidered. Hence, the transfer by the Government of corePPP functions from the Ministry of Finance to theAdministrative Office of the President with the amendment to the Public Private Partnership Law in 2020 merited a projectsuspension since the policy reversal fractured what would have otherwise been a robust framework for infrastructure projectdevelopment.Nurturing of the institutional and technical capacity for project appraisal, preparation, andtendering is equally vital for infrastructure project development particularly in the medium to long-term. Thisproject provided for the creation of a high-level inter-ministerial Project Evaluation Committee to provide overall projectoversight, facilitate coordination, and institutionalize a harmonized upstream process for technical appraisal and prioritizationof both publicand PPP project proposals. It also supported the training and professional certification of staff at theGovernment and the Central Partnership Authority. Meanwhile,resident advisers wouldbe embedded within and workclosely with the Central Partnership Authorityand line ministries and would be funded by the Government. Because theproject would also help prepare potential future projects private, public, orPPP projects, whichimplementation wasexcluded from the project, but whichfeasibility study, tender documents, andsafeguard documentswouldhave been prepared under the project the focus on institutional and technical capacity building was doublyimportant.
P158769 | Sindh-Multi-Sectoral Action for Nutrition (MSAN) | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Water | RETF | IPF | 2018 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099950002252222942/text/Pakistan000Sindh0MSAN.txt | http://documents.worldbank.org/curated/en/099950002252222942/pdf/Pakistan000Sindh0MSAN.pdf | The following lesson isadapted from the ICR:Small Grants incur high transaction costs and are morechallenging to implement.The project experience shows thatsmall grants attract similar procedural requirementsas larger financing, and thereby have high transaction costs, requiring a high level of attention, staff time and political supportto navigate efficiently. The limited funding itself made it more difficult to obtain political and administrative attention andsupport, thus aggravating delays. Moreover, procedural delays are a particular risk for projects of short duration as a slowstart-up period consumes a relatively larger part of the total time available for implementation. Therefore, in evaluating futuresmall-grants, the Bank needs to carefully consider the relatively high transaction costs, insist on realistic project timelines andproceed only if there is a particularly high level of client support and expected impacts relative to the small projectsize.
P158791 | Children and Youth Protection Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099122223102544658/text/P1587911897e890661a9fe15583d113eff8.txt | http://documents.worldbank.org/curated/en/099122223102544658/pdf/P1587911897e890661a9fe15583d113eff8.pdf | Lessons drawn from the ICR (page36), adapted byIEG: Focusing on the operational aspects of awell-designed policy program can significantly increase its effectiveness and efficiency. In the case of thisproject, interventions focused on removing technical barriers to access for vulnerable households, increasing the accuracy ofdatabases that identify beneficiaries, improving information exchangeamong agencies, and implementing community outreach andhousehold verification, all worked together to improve coverage of the existing safety net programs. Resultsindicators that are too broad or incorrectly framedcan be unduly affected by external factors and fall shortinmeasuring true impact. In the case of this project, several key indicators and disbursement-linked indicators wereframed according to denominators that were outside of the projects control. Therefore, numerous revisions had to beundertaken to more carefully measure project progress and results.
P158958 | OECS Regional Agriculture Competitiveness Project | Latin America and Caribbean | OECS Countries |  |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 2017 | 2024 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099061924222029498/text/P158958-b53a6926-38bc-4272-9d21-a9e6a174e2a7.txt | https://documents.worldbank.org/curated/en/099061924222029498/pdf/P158958-b53a6926-38bc-4272-9d21-a9e6a174e2a7.pdf | Three lessons articulated in the ICR are restated below with some modification by IEG.Involving keystakeholders in the project design itself thus leading to opportunities to understand how they are likely to respond toproject components can reduce delays in project implementation and improve the chances of project success (ICR, para 87).Aggregators and agro-processors faced difficulties in securing loans from banks, which required them to offercollateral and have legal status. Collaborating with financial institutions could have eased these difficulties by streamliningprocesses with suitable assistance to aggregators and agro-processors. Similarly, engaging input suppliers in the early stagescould have prevented the supply issues that emerged when farmers and fishers went to them with the vouchers, they received topurchase inputs.If project design entails several government institutions to coordinate their activities toimplement a project, clarifying their role in the implementation arrangements can avoid delays starting the project (ICR, para 88)The initial delays experienced by the Project in Saint Vincent and the Grenadines was largely attributed to unclearleadership roles among the ministries. Additionally in Grenada, the project implementation units engagement in concurrenttasks within the Ministry diluted its focus and commitment, leading to Project delays.One-size-fits-all approachto supporting productive alliances may limit project benefits (ICR, para 89). Productive alliances exhibited a wide rangeof needs. Emerging PAs needed support for basics, such as bylaw establishment, training for financial management training, andstrategies to access markets, whereas more mature productive alliances could have benefitted from more advanced technical supportfor assessing infrastructure investments and market expansion. While the training provided to them helped them achieve theobjectives, tailoring support aligned with their needs could have been more effective.
P158982 | Trade and Logistics Services Competitiveness Project | Western and Central Africa | Togo | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2024 | 2024 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099062724190052785/text/P158982-86e8ae39-289e-48a5-8784-a797d7f5cd69.txt | https://documents.worldbank.org/curated/en/099062724190052785/pdf/P158982-86e8ae39-289e-48a5-8784-a797d7f5cd69.pdf | Three lessons are drawn from the ICR, with some adaptation.An inclusive participatory process and a strongemphasis on capacity building involving private stakeholders (and not just government agencies) are vital to the success of areform program. In this project, it was recognized at the outset that the rationalization of theroad transportservice industry underthe proposed Transport Orientation Lawwould produce winners and losers. The Governmentlaunchedan early and extensiveconsultation with stakeholders, most importantlytruck driverunionsandcarrierassociations, to more transparentlycommunicate the net benefits of the project to the stakeholders andto effectively build consensus around the reformmeasures. To address stakeholder concerns, the project included acomprehensive reskillingprogram for transport and logistics workers who would be displaced by the reform measures. Thereskilling conveyed the Governments commitment to address and mitigatethe costs of the project to affectedstakeholders.Complex projects in low-capacity environments may need to draw on the expertise of specializedpartners to efficiently implement select project activities. This operation selected the International Road Union(IRU) -- the international association of non-profit organizations in the road and transport sector -- to act as the technicalassistance partnerfor capacity building in the trucking industry. The IRU Academy recommendedimprovementstothe legal and regulatoryframework for the transport sector, designed the certification system and the trainingcurriculum, ran the capacity-building program, supportedthe training center, and helpeddesign and implementtheindustry formalization plan.This operation also selected theInternational Motor Vehicle Inspection Committee(CITA) -- theinternational association of vehicle inspection companies -- to serveas the technical assistance partnerfor the capacity building activities for vehicle inspection instruments. The CITA collaborated with the Bank-managed GlobalRoad Safety Fund to assess the countrysregulatoryframework for vehicle inspections, worked withthe MinistryofTransport during the start-up phase of the project, ran thecapacity-building program, and supported the designandimplementation of vehicle inspection schemes and mechanisms. Additionally, theProject CoordinationUnitenlisted the support of United Nations Office of Project Services (UNOPS) to manage the procurementof a largelotof equipment for the project. The participation of the UNOPS enabled the completion of much-delayed projectactivities before the closing date.Maintaining a constant policy dialogue with country authorities overseveralyears is critical for ramping-up investment in trade and logistics services. This project, which aimedto improve the efficiency of trade logistics services in Togo, pavedtheway for the more ambitiousLom-Ouagadougou-Niamey Corridor Project for Burkina Faso, Niger, and Togo, which aimedto improve regionalconnectivity andinfrastructure along the corridor between the capital cities of Togo, Burkina Faso, Niger, and Togo.The preparation, approval, and implementation of this three-country , five-componentregional investment in a most vitaltransit corridor for the three nations would not have been feasible without the long-running policy dialogue conducted by the Bankwith Togo to reform trade and logistics services in the country.
P159010 | STP Strengthening Growth and Fiscal Policy DPO | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2018 | 2023 | ICRR | Less than 10 million | Moderately Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099140502222338667/text/P15901006867d507b0ad6709e3d97f84886.txt | http://documents.worldbank.org/curated/en/099140502222338667/pdf/P15901006867d507b0ad6709e3d97f84886.pdf | This review broadly concurs with the lessons from ICR and offers additional suggestions for some of them:Morefocused reform agenda. Excessively spreading sectoral coverage of a DPF in a low-capacity environment like STP is fraught withrisks to efficacy, sustainability, and the credibility of reforms in the long term.Capacity strengthening.Designing a DPF series in STP required more emphasis on capacity analytics, including better guidance from ongoing sectorinvestment and TA projectson the capacity needed to implement the new laws and regulations supported by prior actions. Bankteams need to be realistic in estimating the technical needs to implement politically sensitive and technical systems such as newVAT in a low-capacity context such as STP, where it was relatively easy to pass laws to meet PAs. Still, additional measures wereneeded to ensure implementation.Results measurement. Results indicators and targets should reflect the existingcountry systems and limited government capacity for implementing new systems. Several indicators did not adequately consider thesechallenges.Advantages of DPF series. Success in STP (land registry) shows the advantages of a series of DPFs insupport of seemingly straightforward reforms. It makes adjustments based on lessons learned and changing country circumstanceswhich is more difficult for one-off reform measures, even when supported by abundant TA and analytics.Ownership andimplementation: Performance in the electricity sector shows the importance of a realistic ex-ante assessment of counterpartcapacity, ownership, and commitment to implementation. The electric utility in STP faced significant issues, and the attempt toresolve them all at once failed.
P159023 | Senegal Structural Reform Development Policy Operation Series | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2019 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099020224090521478/text/P15902316463290cb1ae821fed2ee5ceefb.txt | http://documents.worldbank.org/curated/en/099020224090521478/pdf/P15902316463290cb1ae821fed2ee5ceefb.pdf | Two lessons are drawn from the ICR, with some adaptation.Understanding and accounting for the politics and thepolitical economy of reforms is essential to designing and implementing meaningful prior actions that advance the reformagenda. In this program, the dominant telecommunications operator held a monopoly or near-monopoly position in manysegments of the telecommunications and broadband markets. In allocating frequencies for the next generation 4G services, theindustry regulator issues frequencies only to the dominant operator following less than transparent negotiations. Given thispolitical economy context, it was necessary for the Government to articulate a national policy of infrastructure sharing betweenthe dominant and non-dominant players and enshrine the policy in legislation. It was also necessary for the Government toalter the governance framework for the industry regulation and create a joint commission to negotiate the technicalandfinancial terms of licenses granted to newentrants. The reform measures aimed to break the monopoly power of thedominant operator and steer the regulator toward greater market competition.Structural reform programs take timeand may require support from other operations beyond the scope of a programmatic development policy financingseries.In this program, prior actions over three operations could only require the submission of draft laws tothe National Assemblyand not the enactment of the draft laws by the legislature, much less the issuance of implementationdecrees by the President or the promulgation of regulatory decisions by the electricity regulator or the telecommunicationsregulator. It would take support from a related programmatic development policy operation, theFirst andSecondSenegal Equitable and Resilient Recovery Development Policy Financing, to complete the legislative enactment and theexecutive-branch implementation of the legal and regulatory reforms introduced by Senegal Multi-Sectoral Structural ReformsDevelopment Policy Financing. The multi-sector orientation of both Bank series allowed for the inclusion of follow-up reformmeasures in the second series.
P159040 | Regional Disease Surveillance Systems Enhancement (REDISSE) Phase II | Western and Central Africa | Western and Central Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2017 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099110824113536747/text/P159040-4251755b-48c6-49db-99d3-3273f663ccbc.txt | https://documents.worldbank.org/curated/en/099110824113536747/pdf/P159040-4251755b-48c6-49db-99d3-3273f663ccbc.pdf | The ICR (pp. 40-41) offered several lessons and recommendations, including the following lessons slightly restated by IEGReview:Regional approaches maximize the benefits of projects promoting health security. Under thisregional operation, participating countries followed common standards and approaches for preparedness and response to healthemergencies, and the ensuing cohesive and collaborative approach for responding to COVID-19 pandemic helped countries to implementmutually agreed best approaches and to follow defined standards developed through a participative effort, thus contributing to agreater buy-in and adoption of standardized approaches. This lesson illustrates the merits of a regional approach for futureoperations supporting health security, and it corroborates previous IEG findings (World Bank. 2022. The World Banks EarlySupport to Addressing COVID-19: Health and Social Response. An Early-Stage Evaluation. Independent Evaluation Group. Washington,DC: World Bank) indicating that Regional projects facilitated knowledge sharing and were particularly helpful forcountries with limited capacity to respond independently to COVID-19. Regional projects supported technical cooperation betweenministries and public health institutes, encouraged leadership, developed human capacity, and coordinated technical sharing andfinancing for COVID-19 responses in countries. Longer-running regional projects had more established networks, which hadsuccessfully built some preparedness before the pandemic to support COVID-19 responses, although even newer regional projects addedvalue, mainly through convening and technical and learning support.Despite the large cancelation of funds, theregional approach enabled the project to achieve its outcomes substantially, providing for efficientimplementation.Adopting globally accepted indicators can provide an objective assessment of preparednesscapacities. Under the project, the adoption of the Joint External Evaluation tool facilitated alignment of stakeholdersand development partners in support of compliance aspects with IHR requirements and reduced the ME burden on countries.Nevertheless, there is a downside to such an adoption, as WHOs updates to the Joint External Evaluation indicators andbenchmarks became increasingly stringent.Projects that support the establishment of One Health approach requiretime and extensive planning during preparation and early implementation. REDISSE sought to establish One Health incountries where the concept was novel, and where implementation required major structural and behavioral changes. Under theproject, all four countries experienced challenges and delays in implementation, and there was competition among the health,animal, and environmental sectors to get financing for their sectoral priorities. The level of efforts required for promoting OneHealth was underestimated.
P159053 | Yemen Emergency Crisis Response Project | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2022 | 2024 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099082923164015722/text/P159053154192c08f1a9281213e9202e4c1.txt | http://documents.worldbank.org/curated/en/099082923164015722/pdf/P159053154192c08f1a9281213e9202e4c1.pdf | Lessons drawn from the ICR (p.45):1. The World Bank can be an important actorin FCV contexts, even where it lacks field presence. The project was highly innovative in its approach, both as onlythe second Bank project invoking the FPA and as a reflection of the World Banks emerging understanding of its value added inhumanitarian contexts. Partnership with the UN organizations proved to be a pragmatic and effective way of leveraging thecomplementarities between humanitarian and development agencies and delivering effective interventions in the midst of a conflict.The Bank brought its technical expertise in delivering innovative social protection and short-term job opportunities in FCV,while the UN agencies capitalized on their country-wide presence, high risk tolerance, large humanitarian and political network,and service providers on the ground. In this partnership, the Bank contributed financing as well as technical and operationalexpertise, and the UN agencies carried out on-the-ground project implementation by engaging national institutions and providedsupervision of project implementation. Through this groundbreaking and successful collaboration, the ECRP restored basic servicesand supported the resilience of the conflict-affected population. This innovative partnership also helped to preserve localinstitutional capacity for rapid program scale-up during potential post-recovery and reconstruction.2.In the FCV context, the multi-layered monitoring model at all levels of implementation using an array of technologyensures rapid identification of emerging issues and their timely resolution. Project design put a strongemphasis on both ongoing monitoring and on community engagement for selecting infrastructure projects, both of which made itpossible for the project to tailor interventions to divergent needs of various localities and to be responsive to the changingsecurity situation on the ground. In an FCV context, the security situation is highly volatile, with crises often emergingand compounding the existing vulnerable situation. In order to ensure that the project remained fully aware of andresponsive to shifting circumstances, the project benefitted from multiple layers of feedback, including regular monitoring by theUN partners and SFD and PWP, independent TPM, community monitoring and feedback and remote monitoring using mobile and cloud-basedapplication, phones, GPS-enabled devices, geotagging of project sites, and social media and technology. These modalities enabledtwo-way communication with beneficiaries and service providers, helped to identify implementation issues, get real time updates onconflicts on the ground, manage grievances, monitor non-compliance/fraud by service providers,etc.3 Partnership with local, politically neutral, andwell-respected institutions with strong local knowledge improves implementation efficiency amidst civil conflict and supportspost-conflict reconstruction through institutional preservation. This approach was supported through the engagementof the SFD and PWP, with long established reputations for political neutrality, credibility and objectivity for effective targetingand program delivery. They played a critical role on technical aspects, such as coordinating with local stakeholders, targetingbeneficiaries, and supporting communities in identification and prioritization of investments, and were instrumental for achievingrapid results for emergency response. Their well-established networks with government officials, civil society and NGOs helpedgarner political buy-in, mitigate political interference, threats and insecurity on the ground. This approach allowed the projectto have an efficient and effective implementation model, highlighting the importance of tapping into existing local resources andpartnerships to maximize the development impact, and were key to the projects success during the activeconflict.4. Donor funding is critical for preserving keynational service delivery institutions during conflict. Over the years, the World Bank played a key role in providinga platform for donor coordination and for the advancement of policy and institutional reforms; economic and social development; andbuilding national capacity in Yemen. The World Banks continued engagement during the conflict and continued dialogue withdonors has served to mobilize resources beyond humanitarian funding and contributed to better coordination and alignment ofinterventions within the sector. SFD and PWP have been kept operational during the conflict by external aid from a consortium ofdonors that is providing approximately 80-85 percent of its financial resources, including the World Bank. Such support enablesthese local institutions to deliver services during conflict and ensures their readiness for scaling up implementation during therecovery and reconstruction phase.Additional Lesson:Even under the FPA, under which the Bankdelegates safeguards responsibility to UN and UN safeguards apply, the quicker reporting of issues by the UN and a more active roleby the Bank in monitoring safeguards applicationmay have reduced the work-related deaths and injuries, which occurred underthe project, and prompted a quicker response to gaps in UN safeguards and safeguards compliance.The project did not achieve a minimally acceptable standard of workplace safety until 2019, with the Bank task teamonly learning about project related deaths after a significant time delay as part of implementation support missions. Whenquestioned about this by IEG, the task team noted that, Application of the Banks safeguards policy and later the ESFallowed the Bank to provide better oversight, monitoring and capacity building in the areas of Occupational Health and Safety,gender, among others. Through the systematic preparation of Environmental and Social Management Plans (ESMPs) the Bank wasin a better position to apply its mitigation measures to ensure that worker safety is ensured. As a result, the Banktask team concluded that application of the Banks ESF policies is an important aspect to consider particularly in anFCV environment.
P159215 | Mongolia Employment Support Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | The ICR (pp. 38-39) defines the following lessons generated through this project: Exogenous shocks offer anopportunity to pilot and improve programs, contributing to a countrys preparedness to respond to futurecrises. Maintaining a focus on results and close implementation support helps in avoiding adverse effects on aprojects implementation that are due to more competitive projects that run in parallel. For example, the introduced by theGovernment parallel micro-loan program with better terms than the project-financed micro-loans reduced demand for the latter, andso the Bank decided to reallocate the unused amount for micro-loans to where it was more needed by financing social insurancecontributions and thus addressing the Governments pressing needs during the pandemic. Informationsystem development can be challenging in a low-capacity environment, but, as demonstrated by this project, risks can be mitigatedthrough close monitoring, customized technical support, timely decisions, and dedication from both the client and theBank. Taking into account the local capacity when designing a project can increase the likelihood for the projectssuccessful implementation. In the case of this project, for example, while the design of the Integrated Employment Program underSubcomponent 2.1 was innovative and relevant, it required strong local implementation capacity, which was lacking, leading toimplementation delays and eventually dropping the subcomponent. This was an important lesson that informed the design of the SkillsInnovation Program under the follow-up project MERESP. Working with multiple stakeholders and considering labor supplyand demand is crucial for successful employment promotion programs, as demonstrated by the successful demand-driven trainingsprovided under the project.
P159217 | Strengthening Hydro-Meteorological and Climate Services | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest |  |  | The ICR draws key lessons learned from the experience of implementing this project. Below is a summary of theselessons.Sector-specific operations are likely to produce better results than country-wide and multi-sectorinterventions. This can be better achieved through embedding hydro-met projects into sector-specific operations. Theapproach may also enhance political commitment and long-term capacities for meteorological agencies.Operations in key sectorsthat need hydro-met services, for example civil aviation, food security, and disaster management could strengthen sector-specificmeteorological services. This could help strike a balance between standalone operations and providing small grants withinestablished larger projects to reduce administrative costs and improve implementation.Considering benefits forprivate-sector use without compromising the provision of public resources can maximize socioeconomic benefits of hydro-metservices. The value of hydro-met data is higher when access is open as opposed to the price and revenue received whensold. Therefore, even though private sector use may generate more income, the primary purpose is to provide risk information andearly warnings to protect people and property from risks.Long-term engagement and partnerships in the hydro-metsector may enhance long-term results. The ICR highlights Nepal and Bhutan as examples of regional collaboration andpartnership. The nature of project activities, technical capacity building and equipment procurement require budget and supportbeyond six years of project implementation.
P159258 | GZ-Third Municipal Development Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2018 | 2024 | 2025 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | https://documents.worldbank.org/curated/en/099082724091016674/text/P159258-f76c1ced-6181-4da0-b8d0-b8caf08e14e0.txt | https://documents.worldbank.org/curated/en/099082724091016674/pdf/P159258-f76c1ced-6181-4da0-b8d0-b8caf08e14e0.pdf | The operation identified the following lessons: Local governments in an FCV (Fragile, Conflict, andViolence) environment may benefit from incremental assistance. In this project, the implementation agencyhas a track record of delivering quality operations in a complicated and FCV environment. By continuing to use the sameimplementing agency, its capacity to institutionalize systems and procedures from lessons offered by completing prior projectsallowed them to increase the technical ambition of subsequent projects. This proven implementation arrangement may serve as aprototype to achieve results in building local government capacity. Formulating impactful grants that followinternational best practices may benefit the response to local needs. In this project, allocatinggrants used international best practices. For example, this project adopted a high share of capital grant funding relative to otherfunding sources. This project was the only source of municipal funds for infrastructure. A substantial grant size was betweenUS$11-15 per capita rather than the global convention of over $5-10 per capita. The grant allocation formula responded to localconditions by allowing the use of funds for operational expenses, acknowledged financial sustainability needs, and by addingsubstantial needs-based focus. Financing larger investments may lead to more transformationalresults. In this project, as MDP moved from 1, 2, to 3, proposed investments in West Bank municipalitiesevolved into fewer and larger investments. This signified increasing ambition as municipal capacity improved over time. Encouragingsuch flexibility boosts municipalities confidence to focus on larger investments. Future operations in FCV environments mayconsider such progressive flexibility and support for intermunicipal cooperation to facilitate transformationalresults. Committing to counterpart financing may better promote local ownership of completed investmentprojects. In this project, the MDLF and the MOLG implemented the various projects to show ownershipof these activities. However, counterpart contributions earlier committed to facilitate the sustainability of these completedinvestments did not materialize. To mitigate the volatility of the source of counterpart funds (aid from the international donorpartners), future operations in FCV countries may design creative commitments to make available counterpart financing to reflectownership and sustainability of project investments. Customized technical support may further enhance thecapacity of municipalities. In this project, the capacity-building needs of municipalities were designed asopportunities to be addressed as these arose. For example, local technical consultants and TA were customized to solve procurement,safeguards, technical designs, etc. issues and met key performance indicators to achieve results in municipal finance projects.Other areas were identified that required additional attention - cost accounting systems, IFMIS implementation, green spacesinvestment, and budget execution and were added as interventions to enhance capacity.
P159262 | Tonga Second Inclusive Growth Development Policy Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2017 | 2019 | 2022 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  |  |  | The lessons are drawn from the ICR.Institutional capacity and political support should be continuouslymonitored. In a dynamic institutional and political environment, frequent changes in key counterparts and ministershighlight the importance of working with a broad set of stakeholders. In this series, this was addressed by requiring allparticipating ministries to appoint working level staff to support coordination and continuity, as well as introducing regularmeetings with the Cabinet and/or the Finance Minister, to maintain political support for the reform.Politicallysensitive reforms should be well-grounded in client ownership. Success in the wage bill management reform was grounded inanalysis undertaken by the government (with development partner assistance). The reform process started with a review ofremuneration to ensure a common reference base, followed by extensive consultation and awareness raising about performance-basedpay, including extensive training to support implementation, and regular consultations and adjustments to improveimplementation.While PAs may be highly relevant to achieving Program objectives, they need to be consistent withcapacity constraints and efforts to build capacity. This series underlined the importance of having a stable team orbeing able to adjust the reform program (including triggers) to ensure its continued relevance. That was a particular concernin attempting to improve accountability in government, as Tonga struggled to address capacity constraints in trying to implementnew procurement regulations, better budget reporting and audit recommendations.,
P159263 | Tonga Third Inclusive Growth Development Policy Operation | East Asia and Pacific | Tonga | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2019 | 2021 | 2022 | ICRR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  |  |  | The lessons are drawn from the ICR.Institutional capacity and political support should be continuouslymonitored. In a dynamic institutional and political environment, frequent changes in key counterparts and ministershighlight the importance of working with a broad set of stakeholders. In this series, this was addressed by requiring allparticipating ministries to appoint working level staff to support coordination and continuity, as well as introducing regularmeetings with the Cabinet and/or the Finance Minister, to maintain political support for the reform.Politicallysensitive reforms should be well-grounded in client ownership. Success in the wage bill management reform was grounded inanalysis undertaken by the government (with development partner assistance). The reform process started with a review ofremuneration to ensure a common reference base, followed by extensive consultation and awareness raising about performance-basedpay, including extensive training to support implementation, and regular consultations and adjustments to improveimplementation.While PAs may be highly relevant to achieving Program objectives, they need to be consistent withcapacity constraints and efforts to build capacity. This series underlined the importance of having a stable team orbeing able to adjust the reform program (including triggers) to ensure its continued relevance. That was a particular concernin attempting to improve accountability in government, as Tonga struggled to address capacity constraints in trying to implementnew procurement regulations, better budget reporting and audit recommendations.,
P159297 | P4: Pacific Regional Connectivity Program: Phase 3B, FJ Connectivity Project | East Asia and Pacific | Fiji | Blend | Non-FCS | Digital | Digital Development | IBRD | IPF | 2017 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099033123080528426/text/P1592970eebd800d60b5fa081bb1aca2223.txt | http://documents.worldbank.org/curated/en/099033123080528426/pdf/P1592970eebd800d60b5fa081bb1aca2223.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Complementing infrastructure investments and regulatory reforms can help in positively impacting theoutcomes in ICTprojects. Given that important previous lessons from reforms in the telecommunication sector fromaround the world showed that monopoly control of essential bottleneck infrastructure severely restricts the development of the ICTsector, the design of this project included open-access arrangements that were built into the contractual structure of the cable.This arrangement worked well in this project.2. The project duration needs to be well-aligned to the projectsactivities. This project was expected to complete its activities in the first half of the timeline and the second half wasto be used to monitor the project outcomes over time. The lesson for this project is that a closing date somewhat closer to thecompletion of the works might have been more appropriate and that this could have triggered a more rapid decision on the use of theproject savings in the later stages of the project.3. The recipient capacity needs to be carefully assessed atdesign, especially in countries with little experience in working with World Bank projects. Some of the operational andadministrative issues observed in this project, such as procurement and information processing, pointed to the need to payparticular attention to building such capacity.
P159303 | Sri Lanka Financial Sector Modernization Project | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2023 | 2024 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099050324083535771/text/P159303135873d05b19c3c165482259adb2.txt | http://documents.worldbank.org/curated/en/099050324083535771/pdf/P159303135873d05b19c3c165482259adb2.pdf | Three lessons are drawn from the ICR, with some adaptation.Selecting the appropriate financinginstrumentis critical to the success of a financial sector development program. Many of the mid-levelpolicy and even some technical-level reforms recommended by the Financial Sector Assessment Program and advancedby thisproject could have been better supported by a development policy operation, even a programmatic one. In this operation, thealignment of regulationby the Securities and Exchange Commission to the IOSCO Principles of Securities Regulationrequired the enactment of the Securities and Exchange Act. Similarly, improvements in the regulatory frameworkforthe insurance industry and the supervisory practices of the Insurance Regulatory Commission were premised onthepassage of the proposed Insurance Industry Act. However, none of this legislation was required as performance-basedconditions or disbursement-linked results for this project. They could have been designed as prior actions for a programmaticdevelopment policy operation, in which alignment with international standards (through issuances of the implementing rules) andupgrades of the related financial market infrastructures (through acquisition and operationalizationof the related ITsystems) could have constituted second and third generation actions.Extensive consultations with keystakeholdersare necessary to ensure firm commitment to and ownership of structural reforms by the Government and fosterimplementation readiness among implementing agencies. This project did not achieve the reforms to diversify theinvestment strategy of the Employees ProvidentFund andto restructurethe underwriting and reinsurance businessesof the National Insurance Trust Fund. The Bank should have more firmly secured the Governments commitment to thesereforms at appraisal, including those of all implementing agencies and coordinating bodies and at both the leadership andmiddle-management levels. It is vital, according to the ICR, that aGovernment realizes that implementing agencies, andnot the Bank, are fully and ultimately responsible for project implementation.A dedicated and systematic technicalassistance component may be needed in projects where implementing agencies have no experience with Bank processes and whereimplementation capacity is weak. In this project, only the Central Bank had previous experience implementing a Bankoperation the Sri Lanka Central Bank Strengthening Project which was implemented two decades agoin 2001-2005. Neither the Securities and Exchange Commission nor the Insurance Regulatory Commission wereknowledgeable aboutBank procurement, and yet the project involved the major acquisition of IT goods and services for theupgrading of decades-old financial market infrastructures. The Central Project Coordination Unit at the Ministry of Financewas weak in project coordination, let alone monitoring and evaluation. A substantivetechnical assistance componentinvolving the systematic training of Government project staff inall relevant facets of Bank operations and thefieldingof external experts in all stagesof project execution would have served the operation better than ad hocresponses to emergency requests to untangle procurement, financial management, and ME process bottlenecks as they arose.
P159378 | EQRA | South Asia | Afghanistan | IDA | FCS | Human Development | Education | IDA | IPF | 2019 | 2025 | 2024 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | https://documents.worldbank.org/curated/en/099062824085020097/text/P159378-e1446b21-9721-4b07-9382-1f5757bccb99.txt | https://documents.worldbank.org/curated/en/099062824085020097/pdf/P159378-e1446b21-9721-4b07-9382-1f5757bccb99.pdf | The ICR (pp. 31-32) presented a series of insightful lessons, including:In fragile and conflict environments,high needs and gaps in human development are generally accompanied by equally high implementation challenges. In thiscase, access to education, especially for girls, was a clear and urgent need, but the pathways toward meeting that need requiredwork in underserved rural areas and coordination among multiple levels of government entities with lowcapacity.In a low-capacity environment accompanied by conflict and violence, a deliberate focus on capacityand system building can help sustain momentum toward government ownership, but this approach may lead to delays in achievingresults.In this case, schedulingtasks that are usually completed during project preparation for theearly implementation stage resulted insignificant delays.In a fragile and low-capacity environment,the mix of results-based instruments and pure investment financing should be carefully considered. In this case, it was anongoing challenge to pre-finance activities with high price tags towards meeting DLIs that may not have been a necessary stimulusto drive the required reforms. Results-based financing, under these conditions, may be better suited forsoftactivities that are not costly but that are still difficult to achieve, such as policy reforms andimprovement in inter-ministerial collaboration.
P159427 | West Bengal Institutional Strengthening of Gram Panchayats Program II | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | PforR | 2017 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099121323191023853/text/P1594270bda5670220b34f00ac396c5abcd.txt | http://documents.worldbank.org/curated/en/099121323191023853/pdf/P1594270bda5670220b34f00ac396c5abcd.pdf | Some of the key lessons offered by the operation are the following: (ICR, paragraphs 77-81) A unifiedstatewide performance-based grant system may facilitate institutional and financial systems reform of GPs.In thisproject,untied grants from the state were distributed to GPs using a performance-based grant allocation system. Disbursementswere linked to the adoption of targeted reforms and the use of various systems to build GP capacity. The annual performanceassessments facilitated institutional reforms.GPs generatedown-source revenues (OSRs) and regularized administrativefunctions such as planning, budgeting,procurement,and improved service delivery. A programmaticapproach to follow reforms introduced under the first phase may ensurea readiness to implementandhelpachievedevelopment objectives.In this project, GPs were provided a preview ofthe expectedprogression of the institutional reform initiated underthe programsfirst phase. GPs were given a preview of thebenefits to be derived from the adoption ofinstitutional and financial reforms to benefit them. TheP4R mechanism servedas a platform where incentives were offered to rewardthe adoption of institutional reform. The P4R engagement allowedfor cascading operational and technical aspects of the reforms. The legacy systems adopted by the prior phaseensured theprograms readiness to be implemented. The state-level Program Management Unit (PMU) had sufficient capacity, with many staffcontinuing from the first phase. Usingestablished systems and trained stafffrom the predecessor project helpsensurecontinuity. Continuous community engagement may helpsustainprograminterventions. In this project, local communities were continuously engagedat the GP level. Para baithaks(community meetings) were organized where the local people could interact directly with GP officials and articulate theirdemands. Residents were consulted during the construction of subprojects (for example, road laying). Any grievancewasresolved through the GRMS within a specified period. The programincreased the participation of women in GramSabha and Sansad meetings.Local people saw the benefits ofa bottom-up planning process, whichhelpedthem register ownership of the program activities. Adopting a state-level digital dashboard that displays the public GP levelperformance noted aboveand the participatory experience facilitated by the program may encourage residents to continue theircivic participation andhelpdemand sustainingcapital assets. A detailed assessment of externalagenciesmay inform the design of program incentives that would minimize implementation delays. In this project, somekey program activities, such as the external audit of GPs that involved the engagement of external agencies (such as ELA), wereseverely delayed. Therefore, a thorough assessment of the external agencies, whichplay a key role in implementingtheprogram, needs to consider adding incentives for the timely completion of obligations. In addition, programs may establish asystematic coordination mechanism to engage with external agencies to help reduce implementation delays.
P159434 | Chad Statistical Development | Western and Central Africa | Chad | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2017 | 2023 | 2024 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099122223185010674/text/P1594341b825e60b118dc3178eb31a73c14.txt | http://documents.worldbank.org/curated/en/099122223185010674/pdf/P1594341b825e60b118dc3178eb31a73c14.pdf | The ICR offers several lessons with which IEG concurs. They are: The project was well designed as evidencedby the successful capacity development of INSEED. This was achieved through INSEEDs learning by doing, thatis, implementing, processing, producing and disseminating survey data. The project was designed to have INSEED implement andprocess consumption surveys with an agricultural module, make the CPI more representative by collecting rural data, rebase thenational accounts, carryout national accounts related surveys, and quarterly economic summaries, and disseminate data. Technicalassistance, assessments, and training were part of the package of statistical products. This lesson aligns with internationalexperience on building statistical capacity through data production. The project succeeded in collecting useful data andgenerating statistical products because of a comprehensive package of support provided to INSEED including TA, equipment and ICTimprovements, investments in human resource development within INSEED, and close collaboration with INSEED management and GoC, morebroadly. The combination of these multiple inputs speaks to the careful consideration given to the institutional, human resource,and technological input requirements as well as the importance of ownership of the project by INSEED.An additionallesson identified by IEG is: A strong ME system within INSEED, effective World Bank supervision, andresponsive in-country technical Bank consultants were key factors supporting the completion, processing, and dissemination ofsurvey data on time. This was despite the initial weak capacity and fragile country conditions. INSEED had detailed annual workplans and progress reports to monitor the status of the project implementation on a day-to-day basis. These reports highlightedimplementation challenges and provided updates on issues, recommendations, and progress on actions agreed with previous World Banksupervision missions. The World Banks local office in Chad maintained continuous dialogue with the authorities andprovided them with timely advice on challenges impeding project implementation.
P159437 | Comoros Statistics Project | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2017 | 2021 | 2022 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099105012252121964/text/Comoros000Comoros0Statistics0Project.txt | http://documents.worldbank.org/curated/en/099105012252121964/pdf/Comoros000Comoros0Statistics0Project.pdf | The Needs of the Implementing Agency MatterIncorporating the data production and dissemination needsof the implementing statistical agency directly in the projects design can contribute greatly towards smooth implementationofprojectactivities. The Comoros Statistics Project enjoyed a smooth and successful implementation experience becauseat the preparation stage, the project team consulted with and incorporated directly into the project design the statistical agendaof INSEED, the national statistical office (selected as the project implementing agency). This facilitated implementation at everystage of the project.Strategically Locating the Project Coordination Unit In Comoros where thecapacity of the national statistical agency is particularly weak, implementing an ambitious statistics project can be a challenge.Agency staff are not always willing to cooperate and learn from an externally appointed project manager. Establishing a projectcoordination team within the national statistical agency comprised of the latters technical staff (and consultants forfinancial management and procurement) can be an important way to overcome this barrier. Appointing a senior technical staff memberdirectly accountable to the Director General of the agency as the project manager can be a gamechanger in motivating staff tocooperate with one of their own to achieve the projects objectives and strengthen their technical capacity to producequality and timely statistics.
P159476 | Burkina Faso Livestock Sector Development Support Project | Western and Central Africa | Burkina Faso | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2018 | 2023 | 2024 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099082323102014792/text/P1594760a75b54052094a008e7fa9431d5f.txt | http://documents.worldbank.org/curated/en/099082323102014792/pdf/P1594760a75b54052094a008e7fa9431d5f.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language:1.Whendefining indicators for livestock herd improvement programs, it is important to critically account for all the elements along theentire chain to adequately calibrate the time needed for successful implementation. Herd improvement programs, especiallywhen starting from a very low infrastructural and human capacity base, require a lot of pre-requisites, including establishing theappropriate physical and logistical infrastructure (adequately equipping multiplication centers and decentralized handlingfacilities, acquiring high performance breeding stock and appropriate climate-controlled transportation mechanisms, etc.), andtraining staff at all levels. The gestation period of animals needs to be fully accounted for as well. All this helps set realisticexpectations of the productivity levels achievable during the projects implementation period.2.Establishing a flexible ME system that allows the revision ofoutcome indicators is importanttosharpen attribution and set realistic expectations. Recalibrating aspects of the project as soon as the need forcorrective measures is detected is more effective than waiting for the mid-term reviewto take action. Thiscan createmissed opportunities for timely intervention.3. To ensure a successful outcome for projects in fragileenvironments, it is important to work with local stakeholders, rely on digital technology, enhancemulti-sectoralcollaboration, and intensifyimplementation support. In a fragile environment, working with localstakeholders, including local administration and civil society, is vitalin project implementation. The project worked withthe Citizens Livestock Monitoring Network (RECiVEL) for situational and activity monitoring within a constant feedback loop.RECiVELs sustained presence on the ground and ability to undertake a rapid return when calm is restored allowed the project toexploitwindows of opportunity whenever such windows open up, thus facilitating a rapid rebound when the situation allows itto do so safely.Also, harnessing digital technology facilitated real-time monitoring, thus aiding in quick decision-making ina rapidly changing environment.Enhancingmulti-sectoral collaborationcreated incentives and facilitated theintroduction ofa policy measure on the Small Ruminant Plague (PPR) vaccination subsidy mechanisms and modalities fororganizing annual mass PPR vaccination campaigns. Finally, the Banks project implementation support team was in constanttouch with their government counterparts with a high degree of informality, facilitating rapid decision-making.
P159508 | GABON FISCAL CONSOLIDATION AND INCLUSIVE GROWTH OPERATION | Western and Central Africa | Gabon | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | DPF | 2018 | 2019 | 2024 | ICRR | >=100 million | Moderately Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/099080323122024237/text/P15950800df5200160abaf04cc115164071.txt | http://documents.worldbank.org/curated/en/099080323122024237/pdf/P15950800df5200160abaf04cc115164071.pdf | The ICR Review identifies three key lessons: The identification of PAs and RIs should be carefullyconsidered to ensure that they are relevant to the achievement and/or to the measurement of achievement of the operationsobjectives. The identification of PAs should be grounded in sound analytical underpinnings; The relevance of a PA thatleads to a fiscal impact should be supported by a rigorous ex ante and ex post analysis of the anticipatedadditional government revenues generated or the anticipated reduction in government expenditures; and Triggers,targets, and RIs should be appropriately adapted to lessons learned or changes in underlying conditions and risks.
P159512 | Guyana Payments System Project | Latin America and Caribbean | Guyana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2017 | 2022 | 2023 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/099061623180521644/text/P159512072cf500f508c0408721e5cc0e50.txt | http://documents.worldbank.org/curated/en/099061623180521644/pdf/P159512072cf500f508c0408721e5cc0e50.pdf | Two lessons are drawn from the ICR, with adaptation.A comprehensive set of interventions, starting with anational strategy that addresses the needs of the government and the private sector for clearing, settlement, and recording ofmonetary and financial transactions, helps to ensure the successful development and implementation of a modern national paymentssystem.The Governmentadopted aNational Payments System Strategyin 2018 to guide itsefforts tobuild a robust, safe, and efficientnational payments system.Parliament enacted theNationalPayments System Act 2018 to provide the enabling legal and regulatory framework for the creation, operation,andoversight of the new system. The project funded both the acquisition and installation of hardware and theprocurement and upgrading of software for the new infrastructure and extendedtechnical assistance and training to the centralbank to lead the development and operation of the new system. The project catered toboth the government and theprivate sector requirementsfor the system, serving not onlyinterbank payments and retail services but also agencypayment transactions and government securities trading. Finally, the project required observance of the internationalstandards for financial market infrastructures as a results target.The participation of all key governmentagencies in a project promotingelectronic payments strengthens the viability of a nationwideelectronic paymentinnovation.In this project, the Ministry of Finance, the Guyana Revenue Authority, and the National InsuranceFund were chosenas key participants and users of the modern payments system with targets set for the percentage of Governmentpayments processed through the real time gross settlement system and the automated clearinghouse. The three key agencies weredirectly connected to the new payments infrastructure, including to the systems virtual private network,and theirsoftware were upgraded to enable them to channel payments through the new infrastructure. An Inter-Participant Working Groupestablished by the Bank of Guyana served to coordinate the participation of these key agencies in the design and implementation ofthe project. In a complex systemundertaking of this nature, harnessing the participation of all stakeholders created acollaborative environment that proved critical to the success of the project.
P159515 | Access to Longer Term Finance for Micro, Small and Medium Enterprises Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2017 | 2023 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099062823112526459/text/P159515063425f0b50892e0070db72bc28d.txt | http://documents.worldbank.org/curated/en/099062823112526459/pdf/P159515063425f0b50892e0070db72bc28d.pdf | This ICR Review draws the following lessons from the ICR of this project (pages 24-25)-Flexibility of line ofcredit conditions can increase the projects capacity to adapt to changing environment in the country or globally during theimplementation. In the case of the project, the flexibility in the project design enabled the project team to adjust LoCterms and revise the project activities in line with the changing needs of the borrower. Without the option to disburse funds in USDollars, the LoC could not be utilized entirely in pesos in high inflation and interest rates.-Clear and simpleeligibility rules can facilitate application for an LoC. In the case of the project, one of the reasons for the delayedutilization of funds was the lack of clarity and complexity of the eligibility rules. Once clarified and coupled with simplifieddocumentation, the appetite for PFIs improved. With respect to the environmental and social requirements, compliance withthemand strengthened institutional capacity helped BICEaccess the credit lines of various internationalorganizations.-Technical assistance components in financial intermediary projects can have more impact than a lineof credit per se. The project experience showed that even small amounts of technical assistance components couldcontribute positively to reform processes by increasing institutional capacities, reducing information asymmetries,strengthening communication among stakeholders, and thus facilitating access to finance.The IEG also draws the followinglesson on monitoring the outcomes of access to finance projects, including LoCs:-Conducting independentassessments regarding the economic/financial impact of the LoC on the final borrowers can strengthen the evidence on impact as wellas provide additional input for the design of future LoC projects in other client countries. In addition, indicators suchas access to finance by women and indigenous communities and other excluded segments in the results framework can help assess theoutcomes of the LoC on social inclusion. The projects ME system was weak concerning these areas; some additionalinformation was collected in an ad hoc manner by the PIU.
P159547 | Nepal Fourth Financial Sector Stability Credit DPC4 | South Asia | Nepal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2019 | 2019 | 2021 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  |  |  | Three lessons are offered, including two adapted from the ICR (page 32).Close collaboration among majordonors is vital to the success of broad national reform programs, particularly where the institutional and technical capacity forprogram design and implementation needs augmenting. In this program, the Bank and the IMF jointly prepared theNepal FSAP of 2014 which informed the prior actionssupported by this program. The legal departments of bothorganizations also helped review the draft BAFIA and the draft NRB Amendment Act. DFID and FIRST provided significanttechnical assistance and advisory services through their staff and international consultants. According to the ICR, the closecollaboration between the Bank and DFID was exemplary, starting in 2012, and consisting of joint missions, employment of experts,capacity-building activities, and large resource contributions for program design and implementation.Reformchampions in a countrys bureaucracy are needed for the implementation of complex reform programs where the politicalenvironment is uncertain and potentially volatile. In this program, the Bank worked closely with reform champions inkey positions at the Ministry of Finance and the NRB who were knowledgeable about the financial sector, held strong convening powerover stakeholders, and made compelling arguments for policy and structural reform. These key executives kept theirorganizationswell informed of the program rationale,design, and implementation plan.Thereform-mindedbureaucracy at the Ministry of Finance and the NRB pressed on with the medium-term program notwithstanding the politicaluncertaintyfrom frequent changes in the national leadership and the civil disturbancerelated to the drafting ofthecountrys new federalist Constitution.Governments can successfully takeadvantage of theopportunities offered by crisis situations to motivate reform programs. In this program, the liquiditycrisisof 2011, the failure of many financial cooperatives in 2013-14, and the devastating earthquake in 2015 exposed the vulnerability ofNepals banking, cooperatives, and insurance sectors to macro-financial shocks and to natural disasters. In response, theauthorities committed to a comprehensivereform program to recapitalize and restructure the countrysfinancialinstitutions and to strengthen the legal and institutionalframeworkfor bank supervision, bank resolution, financialcrisis management, operational risk management, deposit insurance, payments and settlement, and transparency. The demand forpost-crisis recovery helped firm up broad political support for the reforms.
P159576 | Bihar Transformative Development Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2016 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099050224090031935/text/P1595761e0072a070186d71333b81a9d553.txt | http://documents.worldbank.org/curated/en/099050224090031935/pdf/P1595761e0072a070186d71333b81a9d553.pdf | The ICR identified several lessons. Three of them are restated with some editing as follows:Community basedorganizations can potentially complement traditional delivery institutions in the last mile delivery of services when faced byemergencies such as the COVID pandemic. The cluster-level federations organized by the project were able to deliverservices to rural communities to give them access to food, finance, and reliable health advice during COVID. Community trainedcadre complimented the outreach efforts of the departments of agriculture and health. Several village organizations operated PublicDistribution System (PDS) ration shops.Federating self-help groups offer an opportunity to build scaled-uporganizations capable of accessing and delivering services to poor households, but they require attention to their financialviability and capabilities beyond their core financial intermediary role. Timely recovery of loans and rapid rotation offunds among the SHGs is required to have enough earnings to meet the costs of their staff and cadre. Further transfer ofresponsibilities from the State Mission to the community institutions will challenge their capabilities.Partnering with organizations rather than contracting out implementation has the potential to ensure thepost-project sustainability of the interventions. The project partnered with several organizations that routed their fundsthrough the implementing organization and the community institutions to implement their programs better. The service-fee-basedpartnership model offers a way for the organizations to sustain themselves post-project.
P159653 | Caribbean Regional Oceanscape Project | Latin America and Caribbean | OECS Countries |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2018 | 2022 | 2023 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099164002012332121/text/P1596530ba27c402108ac900f84d6665678.txt | http://documents.worldbank.org/curated/en/099164002012332121/pdf/P1596530ba27c402108ac900f84d6665678.pdf | The ICR included nine lessons learned. The following two lessons are highlighted since they have broader application. Thelanguage has been adopted and some related lessons have been consolidated. Institutional buy-in is criticalto ensure the sustainability of the coastal marine spatial plans and other initiatives on blue economy and can be achieved with aneffective and targeted communication strategy. To obtain the right level of support, the institutions and decision makersmust have a clear vision and expected outcomes of project deliverables. Communication strategy plays a pivotal role in promotingblue economy concept and helps shape a common vision and goals of the project amongst all relevant target groups. And since theblue economy concept is relatively new to many stakeholders, developing a communication strategy early on could lessen the riskof leading to diverging interpretations and shape a collective vision from the beginning of the project. For example, concisesummaries of Coastal Master Plan and the Marine Spatial Plans would have been helpful for decision makers to capture the keyinformation, accompanied by in-depth analysis for technical staff. Achieving buy-in and endorsement of the coastal marine spatialplans and other initiatives of blue economy were critical factors in sustaining the project.Monitoring andEvaluation of these projects need to be thoughtful, pragmatic and focused on looking for where the project has added outcomeoriented change.There was the poor alignment in the results frameworks indicators and the intended outcomes ofthe project, resulting in a lack of evidence towards the achievement of the project as a whole. Focusing less on what can bemeasured and what needs to be measured is essential to better understanding what these diversified projects actually contribute tothe regions where they are being implemented.
P159655 | Fiscal Performance Improvement Support Project (FSP): | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2018 | 2025 | 2024 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099092023121514085/text/P1596550f9141c0990b3e6064cb138f03cf.txt | http://documents.worldbank.org/curated/en/099092023121514085/pdf/P1596550f9141c0990b3e6064cb138f03cf.pdf | TheICRR confirms the series of lessons and recommendations emerging from the projects experienceand presentedin the ICRR and proposes an additional one regarding the importance of high-level commitment to advance policy reforms. IEGsummarizes the most persuasive lessons below:Balancing ambition of objectives with pragmatism is especiallyimportant in FCV contexts. Projects design needs to carefully manage the trade-off between the ambition of PFMreforms and more pragmatic and necessary priorities of ensuring governments day-to-day operation with existing capacity andwith limited external support, in particular if donor financing is interrupted. As such, institutional reforms in such FCVenvironments need to have realistic objectives that can be sustained by the governments own resources. The ICRR would addthat a political economy analysis, mapping the winners/losers of such reforms would also help in guiding both the design andimplementation of such projects, and not only in FCV contexts.There is a need to address human resource capacitiesand incentives in a streamlined and coordinated fashion with other projects to ensure proper project implementation. Bysupporting NTAs through the FSP project, the World Bank undermined another project - TAGHIR which intended to transitionNTAs to Tashkeel (the ministrys organization structure). It would be preferable to concentrate all financing of externalstaff under a single instrument for proper streamlining with civil service reform program. Furthermore, and though in theory it ispreferable to rely on national systems for fiduciary arrangements, it may be more efficient and effective to use conventional PIUsto implement the project and to outsource the audit of projects to a reputable audit firm than to rely on the limited nationalcapacities.Carefully design digital approaches and business models to ensure efficiency aswell as sustainability. ICT solutions, in particular in FCV contexts, are associated with a set of implementation, qualityand sustainability risks. Considerations at the design stage should be taken to ensure that simple open-source solutions thatcombine flexibility on maintenance arrangements (including avoiding proprietary licensing) and affordable cost are chosen in orderto avoid fragmentation, inefficiencies and unsustainable ICT solutions. Selecting vendors solely on lowest price without takinginto consideration life-time costs of the system (including license fees), may not be the most efficient, effective or sustainablesolution in the long-run.Another lesson which is not included in the ICR but is alluded to under Key Factors DuringPreparation: is the importance of selecting the appropriate counterparts and engaging at the right level to ensurehigh-level ownership and commitmentfor advancingthe reform agenda. FSP partnered with three key stakeholders(MOF, NPA and SAO), which were critical for advancing the PFM reforms in the vulnerable and high-risk FCV context. All threeinstitutions served as implementing agencies and actively supported the reform. Furthermore, the Bank engaged closely with the keystakeholdersto prepare the projects budget in a participatory way. Closer engagement with Presidents office wasone of the untapped measures that could strengthen the reform focus and collaboration towards overall projecttargets.Finally, in Afghanistan, it was very useful to have a dedicated Gender and Social Development experton the Banks team to lead the dialogue on gender-related issues and to follow up on the gender-related activitiesimplemented by the project.
P159669 | Second Programmatic Electricity Distribution Reform DPL for Rajasthan | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2019 | 2020 | 2022 | ICRR | >=100 million | Moderately Satisfactory |  |  | Satisfactory |  |  |  | IEG derives the following lessons drawn from the ICR:1. Impactful World Bank-supported electricitydistribution sector reforms require long-term engagement. An important lesson from this DPL series is that aholistic package of policy, regulatory, operational and financial measures supported by a long-term engagement plan is critical fora distribution sector performance turnaround. Lessons learnt from previous reform efforts in India and elsewhereindicated that financial bailouts of distribution companies alone without deep reforms in other areas do not provide long-termsustainable solutions. Hence the design of this Program included fundamentals of sound distribution sector performance - costrecovery tariffs, good governance and management accountability and operational efficiency improvements. bare subject to politicaleconomy influences and, therefore, often require time to address effectively. Such deep and comprehensive reforms require externalsupport over an extended period of time and hence need long-term engagement plans involving the government and otherstakeholders.2. Options for reforms need to be synchronized to the country context. Anotherimportant lesson is that reforms may need to be incremental while relationshipsand consensusare built to create thenecessary conditions for progress on deeper and more difficult reforms. The Bank was sensitive to the countryssocio-political context in selecting pragmatic reform options. It thus emphasized operational efficiency improvements, improvinggovernance and performance management and accountability instead of tariff increases and private sector participation. Thisenabled the Bank to build relationships and trust attributes that paved the way for engaging constructively withstakeholders on exploring options for private sector participation in the electricity distribution sector and for strengthenedengagement on the electricity-water-agriculture nexus.3. Identifying windows of opportunity is critical forreforms to succeed. Another important lesson from this DPL series is the importance of choosing the right timing forreforms and fully capitalizing on the moment. The Bank chose to support the GoR in implementing reforms at an opportune timewhen there was a strong alignment between the GoI and the GoR on electricity distribution sector reform issues. The GoI and thestates/territories were preparing the UDAY program to address the electricity distribution sectors financial and operationalperformance problems. The GoR needed to resolve electricity sector constraints to its 2020 Vision economic growth strategy. TheBank moved quickly to prepare the DPL series at a time when the appetite for reforms was strong in Rajasthan and India.However, the Bank did not take full advantage of the propitious moment to lock in an engagement plan although it was fullyunderstood at that time that the reforms would need to be sustained through an engagement over time. Later when the Bankexplored complementing the DPL series with additional technical assistance after the 2018 state elections, there had been a changein priorities of the state government due to other emerging challenges, and this foreclosed the possibility of a third phase of theDPL series.