P009113 | AGRICULTURE SECAL | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | DPF | 1997 | 1999 | 1999 | ICRR | >=100 million | Moderately Satisfactory |  | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/382671474634711835/text/000020051-20140522081018.txt | http://documents.worldbank.org/curated/en/382671474634711835/pdf/000020051-20140522081018.pdf | (1) The process of reform is just as important, if not more important, than the actual substance of the reforms. Three aspects of the process were weak. First, it is not clear who was responsible for providing the political commitment and the political cover for the reforms -- the Prime Minister, the Deputy Prime Minister for Economic Reform, or the Minister of Agriculture. Second, it is not clear who or what unit was responsible for managing the reform process on a day-to-day basis. Third, some influential stakeholders did not support the reform process, since the Parliament blocked the implementation of several second tranche conditions. Together, the GOU and the Bank should have involved and managed the key stakeholders more effectively.(2) Conditionality has its limits. It is only possible to craft a set of necessary, but not sufficient conditions for the achievement of the project's reform objectives. Therefore, it is important for the Bank to assess the government's commitment, not only to the letter but also to the spirit of the reforms.(3) For an institutional reform project, the objectives were far too ambitious. It was unrealistic for the GOU to achieve all the immediate institutional outcomes (such as changes in legislation) during the short time-frame of the project, let alone the expected results of the project (such as the dissolution of 1000 collective agricultural enterprises).
P009113 | AGRICULTURE SECAL | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | DPF | 1997 | 1999 | 2000 | PPAR | >=100 million | Moderately Satisfactory |  | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/514261511188802515/text/multi-page.txt | http://documents.worldbank.org/curated/en/514261511188802515/pdf/multi-page.pdf | 7. Lessons The following are the principal lessons arising from this project\. (1) Where there is a limited political consensus for reform, as in Ukraine, there are limits to the effectiveness of sector adjustment loans, and their related conditionalities, in advancing the reform agenda. In addition to high-quality sector work, the Bank must broaden the range of partners and stakeholders involved during project preparation in order to enhance the domestic ownership of the reforms. While this will take more time during preparation, it will pay off during implementation and improve the outcome and sustainability of such projects. (2) The process ofpolicy and institutional reform is just as important as the substance of the reforms in achieving sustainable outcomes. A major problem between the first and second tranches was the lack of a credible, representative forum in which the key domestic stakeholders could reach a workable consensus on each step of the reform process. Eventually, the Inter-Ministerial Commission for Agrarian Reform came to play this role. Now reconstituted as the Presidential Commission on Agrarian Reform, it includes significant representation from nongovernmental stakeholders as well as all levels of government. (3) It is important to be realistic about the amount of time required to implement the institutional reforms that undergird the various policy reforms. Not only do institutional reforms require continuous consultation concerning the details of the reforms, with key stakeholders in credible and representative forums, they also require changes in laws, regulations, and procedures in order to become effective. (4) In order for the private sector to become the major supplier of agricultural inputs, the government needs to take explicit measures to demonstrate to the private sector a credible commitment to maintaining the policy reforms. This includes reducing the role and the size of the public sector from a direct participant to a market facilitator, clarifying the legal priority in the collection of farm debts, and actively resisting policy reversals such as the export taxes on agricultural commodities.
P009117 | Agricultural Seed Development Project | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/972011475100356067/text/000020051-20140602113836.txt | http://documents.worldbank.org/curated/en/972011475100356067/pdf/000020051-20140602113836.pdf | (a) Successful restructuring of government institutions requires clear government commitment to and ownership of these restructuring efforts. The Bank should not support such efforts without demonstrated commitment to such reforms.(b) The Bank and UAAS pre-selected the enterprises and managers to support under this project, because there were no viable commercial banks in Ukraine to do so at the time. This approach is fraught with uncertainties and should be avoided whenever possible.(c) Newly created enterprises operating in an uncertain market environment like that in the Ukraine require more than the usual learning period before they can reach full production and efficiency. The SAR's expectations in this regard were unrealistic.(d) Where sector policy reforms are necessary for the profitability of investment projects, as in this case, Bank management (both country and sector) must provide adequate support to the supervision team in this regard.
P009121 | Water Supply, Sanitation and Health Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2008 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/404941474853309610/text/000146597-20140619160341.txt | http://documents.worldbank.org/curated/en/404941474853309610/pdf/000146597-20140619160341.pdf | On first entry to a subsector it is better to have a simple project design than a complex one that may have low Borrower ownership and run into problems of implementation. In this case the Bank's desire for a comprehensive approach to WSS and health was too ambitious given the dire state of the country's basic infrastructure, its poor operation and maintenance and the political imperative to get things working. A phased approach would have worked more effectively as Borrower knowledge and confidence was built.Bank procurement rules can result in major cost savings providing local capacity and governance constraints are addressed. Unfamiliarity with the Bank's procurement rules initially resulted in significant delays in implementation that could have been avoided if governance challenges had been better understood and adequate resources had been allocated for procurement training and monitoring. Once this was addressed, however, application of the Bank's procurement rules led to cost savings that enabled the project to be more cost efficient than originally anticipated.Monitoring and Evaluation needs to be designed at appraisal, not during implementation. This project invested extensively in social assessments and pilot projects during preparation, but these efforts were not reflected in a reliable, evaluable, and comprehensive baseline indicators because detailed design of M&E was delayed for 3 years.
P009121 | Water Supply, Sanitation and Health Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2008 | 2015 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/222081468189534492/text/97564-PPAR-P009121-P049621SecM2015-0239-IDA-SecM2015-0153-Box391506B-OUO-9.txt | http://documents.worldbank.org/curated/en/222081468189534492/pdf/97564-PPAR-P009121-P049621SecM2015-0239-IDA-SecM2015-0153-Box391506B-OUO-9.pdf | 4. Lessons Learned 4.1 The key lessons derived, based on the findings of this PPAR, are the following\. Â· When designing infrastructure and service provision projects within the context of a regional environmental crisis it is essential to minimize objectives and keep them focused on interventions the borrower will support. In this case, driven by the Aral Sea crisis, the Water Supply, Sanitation and Health Project overly emphasized the need to mitigate a range of ill-defined public health problems when even provision of basic services like potable water supply was in jeopardy. Â· Adoption of community driven development models in a country where the culture of community self-help lacks prominence may require additional capacity-building efforts. In the case of Uzbekistan, the well-established community-driven model for implementing the sanitation, health, and hygiene components, based on the experience in Nepal, India, and Peru experienced difficulties. This was due to the insufficient attention paid to building the capacity in the local institutions responsible for project implementation, especially since the community centric culture did not exist in the country. The project however benefited from an extensive series of six social assessments, as these assessments clearly demonstrated that consulting communities in the design of pilot projects put pressure on authorities to give greater attention to the scale and cost of projects. Â· The practicality and realism of bringing about institutional strengthening of a developing country's main utilities through a performance-based management contract needs very careful appraisal. The Bank needs to adopt a flexible approach that can strengthen operating performance of the utility's business in key areas without imposing unacceptable foreign management. In the case of the Bukhara and Samarkand, the foreign Operator (with hindsight) did have a very positive impact on modernizing and providing a commercial orientation to the utilities. However, socio-political factors ignored at appraisal, and exacerbated by the imposed Court judgment beyond the control of the implementing agencies, clouded judgment during implementation and at closing about the effectiveness of this arrangement. This is because the private sector model antagonized the implementing agencies and had left a lingering resentment on the value-added by the private sector. This is particularly egregious given that the municipalityappointed utility staff, following capacity-building through the operator, has subsequently demonstrated their ability to manage the utilities effectively and sustainably. Â· Introduction of private sector or NGO participation in a new socio-political environment requires continuity of specialist Bank supervision and the right mix of skills. In the case of both projects the annual turnover of task team leaders led to a lack of proactivity on critical institutional issues that exacerbated delays and hindered the Bank's effectiveness and efficiency. Â· Proper tariff setting and demand management efforts are critical factors that lead to expansion in customer base and increased revenues for the utilities. In the case of Water Supply, Sanitation, and Health project, greater attention was paid to securing financial viability under the new decentralized arrangements. Activities included periodic water tariff increases proposed by the regional government for central government approval, and simplification of tariff structure. The project was also successful in demand management through physical actions to reduce water losses, creating and updating a water user database, metering, and financial incentives to conserve water. Once staff was trained, equipment procured and public awareness was raised, the demand management program was mainstreamed in all three utilities. As a result, the customer base was expanded and revenues were increased, leading to improvements in financial viability of the utilities. Â· Financial autonomy is important for long-term sustainability of water utilities. The Buhkara and Samarkand Water Supply Project managed to increase water metering significantly through various measures, leading to enhanced collection of revenues. However, due to lack of financial autonomy, the utility is experiencing difficulty collecting the arrears from government institutions. This is likely to adversely affect the utilities' commercial performance if the government does not address the utilities' autonomy issue soon.
P009122 | Cotton Sub-Sector Improvement Project | Europe and Central Asia | Uzbekistan | Blend |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1995 | 2002 | 2004 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/927381474632837469/text/000020051-20140612063514.txt | http://documents.worldbank.org/curated/en/927381474632837469/pdf/000020051-20140612063514.pdf | The main lesson is that the Bank should not make substantial investments in countries that have not embraced the reforms critical for transition to a market economy; at best, small pilot projects are justified. Sector-oriented investments do not have leverage needed to achieve the broader liberalization and privatization reforms that are required. The ICR does not derive these particular lessons; but it points to others that are equally pertinent to transition economies. "An improvement in international price received for Uzbek cotton did not translate into better farm gate prices nor did it lead to sector liberalization. Critical aspects of agricultural policy such as introduction of competition into the ginning industry, farm credit and input supply were not defined. Potential drivers of sector liberalization such as farm restructuring and land reform were omitted from sector liberalization scenarios". In other words, the Bank needs to give closer thought to the sequencing of policy-based loans and investment loans, and the sequencing of steps in the reform process.
P009123 | Institution Building Technical Assistance Project | Europe and Central Asia | Uzbekistan | Blend |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1994 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/103211474666546672/text/000020051-20140604052549.txt | http://documents.worldbank.org/curated/en/103211474666546672/pdf/000020051-20140604052549.pdf | A technical assistance loan, without strong linkage to policy-based lending, is unlikely to have significant development impactIn considering a TA loan, the Bank should make a realistic assessment of the Borrower's inclination to utilize grant funds, and the availability of those funds
P009125 | Health Project | Europe and Central Asia | Uzbekistan | Blend |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/307131474593293427/text/000020051-20140613063349.txt | http://documents.worldbank.org/curated/en/307131474593293427/pdf/000020051-20140613063349.pdf | Pilot approaches that are not well defined (operational/research questions to be tested, roles and responsibilities, timing and content of discrete phases) or underpinned by a good M&E framework will compromise opportunities for learning and replication.Project management functions that are not sufficiently mainstreamed into relevent line ministries will undermine efforts to build sustainable capacity and experience of the agencies with permanent responsibilities for sector management and oversight. Organizational weaknesses in the government apparatus and public administration can negatively impact project effectiveness and sustainability.
P009127 | Drainage, Irrigation & Wetlands Improvement Project - Phase 1 | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2003 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/221451475787453262/text/000180307-20150112091736.txt | http://documents.worldbank.org/curated/en/221451475787453262/pdf/000180307-20150112091736.pdf | The ICR offers a number of lessons of which the following three, with some adjustment of language, are the most important ones arising from the project experience:1. In the formation of WUAs in challenging situations where the state previously provided all services, there is a particular need during the transition for both parties to clearly understand their responsibilities and their mutual dependence, and to be regulated by laws governing both parties.2. The Bank should develop, at the appraisal stage, a good understanding with the borrower of contract and procurement clearance requirements and the likely constraints and, if necessary, agree to responsiveness standards at negotiations.3. A carefully designed Results Framework and M&E system is essential for measuring impact. Indicators should be specific, measurable, attributable, relevant and time-bound (SMART). There should also be a strong focus by the Bank supervision team on ensuring baseline and final impact surveys.
P009131 | Financial Institution Building Project | Europe and Central Asia | Uzbekistan | Blend |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/408061475110305859/text/000020051-20140612145759.txt | http://documents.worldbank.org/curated/en/408061475110305859/pdf/000020051-20140612145759.pdf | Before proceeding with a technical assistance loan, the Bank should question the wisdom and convenience of lending to a country unwilling to remove the constraints that prevent realizing the benefits of the proposed assistance.
P009285 | KOLUBARA B. THERMAL | Europe and Central Asia |  |  |  | Other | Other | IBRD | IPF | 1991 |  | 1998 | ICRR | >=100 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/987231474629397407/text/000020051-20140516154149.txt | http://documents.worldbank.org/curated/en/987231474629397407/pdf/000020051-20140516154149.pdf | The outbreak of the war could not have been anticipated at the time of project approval.
P009448 | GAS DEVELOPMENT II | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1985 |  | 2005 | PPAR | >=50 million & <100 million | Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/179831468743406781/text/29515.txt | http://documents.worldbank.org/curated/en/179831468743406781/pdf/29515.pdf | Lessons 68. Themainlessons that emerge from the assessment o fthese two projects are\. Indesigninginstitutionaldevelopment components ofprojects, the incentives for those directly concerned byproposed changes should be well alignedwith the project objectives. Inparticular, the staffing andremunerationimplications o f major institutional reorganizations (such as the creationo f GTCL), needto be well understood and explicitly addressedifreorganizations are to be successfully implemented; 0 Buildinga strong gas industry ofintemational standardrequires amajor IDeffort\. better management, greatly increasedtraining, betterremuneration andmore autonomy; 0 The Bank should take a less dogmatic approach to sector reforms andpractice greater sensitivityto local socio-political constraints, ifit i s to achieve collaborativedialog and succeed inobtaining Borrower 'buy-in' to its proposals. 0 Strong and continuing field office involvement insubstantive project work i s more effective than intermittent, long-distance involvement o f HQstaff. 0 Whenthe Bank finds it difficult to justify its support for aparticular sector due to policy differences, it should strategically weigh the benefits o fmaintaininga flexible form o f engagement against the consequences o f full withdrawal. Repeated sharp changes inthe Bank'sinvolvement could be damaging to its credibility and could constrain its ability to seek policy reforms.
P009454 | PRIVATE SEC IND'L CR | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1992 | 1998 | 1999 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/204301474508768050/text/000020051-20140519080530.txt | http://documents.worldbank.org/curated/en/204301474508768050/pdf/000020051-20140519080530.pdf | Bank appraisal should (a) establish realistic eligibility criteria for participation of financial intermediaries in a line of credit; and (b) review thoroughly, prior to loan negotiations, eligibility of potential participants, particularly when the financial intermediaries are subject to new prudential regulations. This avoids unpleasant surprises after the loan/credit is put in place, such as finding that no or few financial intermediaries are in fact eligible to participate in the line of credit.
P009459 | ROAD REHAB. & MAINTE | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1987 |  | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/804981511189041908/text/multi-page.txt | http://documents.worldbank.org/curated/en/804981511189041908/pdf/multi-page.pdf | 6. Lessons Learned and Recommendations 6.7 The following key lessons and recommendations emerge from this audit. 6.8 Examine the non-infrastructure impediments to poverty reduction. While the Bank's assistance in developing rural infrastructure has helped increase economic activity and improve quality of life, the rural population of Bangladesh remains, by and large, poor. Therefore, noninfrastructure interventions, such as improving rural institutions, are needed to maximize the impact of infrastructure investments on poverty reduction. Institutional interventions should be geared towards making the Union Councils more efficient, responsive, and accountable to the rural population. This will involve directly supporting Union Councils to increase their organizational capacities, and working with local communities to design institutional interventions to improve the rule of law in rural communities, and reduce the role of musclemen in political and economic activities. 6.9 Take a sector-program approach. The road sector in Bangladesh is nearing maturity and the Bank has accumulated extensive experience in the sector. It is now time, therefore, to move towards a programmatic and sector-wide investment approach. This would help facilitate the development of an institutional framework for long-term sector investment strategies and policy reforms for improved road management and financing. 6.10 Rationalize donor coordination. The current geographical division of donor activities in Bangladesh may not based on comparative advantage of the donors and may no longer be suitable with the opening of the Jamuna Bridge. The development and improvement of the road network may require a reorientation from the traditional north-south axis to one that best serves the new geographic configuration of economic activities. Therefore, the Bank needs to work with all donors and the government to ensure investment strategies are coordinated on the basis of rational and comparative advantage criteria.
P009461 | BWDB SYSTEM REHAB. | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1990 |  | 1998 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/948761474592297098/text/000020051-20140519064720.txt | http://documents.worldbank.org/curated/en/948761474592297098/pdf/000020051-20140519064720.pdf | * A sector-wide approach considering the comparative advantages of all institutions is required to design systematic reform of a dominant public sector agency resistant to change. * Participatory design, planning and O it cannot be imposed by outsiders.* A multiplicity of cofinanciers adds synergy to the policy debate and pressure for reform but requires enhanced attention to coordination and team planning with the Borrower.* Rehabilitation projects should mitigate original design defects.
P009465 | Second Road Rehabilitation & Maintenance | South Asia | Bangladesh | IDA |  | Infrastructure | Transport | IDA | IPF | 1994 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/631001474504360854/text/000020051-20140602110911.txt | http://documents.worldbank.org/curated/en/631001474504360854/pdf/000020051-20140602110911.pdf | Some of the lessons learned are scarcely new, even if they are very broadly applicable - "Careful supervision of contractor performance is needed to assure adequate quality of works, with payments tied to fulfilling the quality requirements" and "it is important for RHD to emphasize strict quality control, planning, scheduling and timely delivery of civil works with their contractors."
P009467 | URBAN DEV. I | South Asia | Bangladesh | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1988 | 1998 | 1999 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/346161475075465617/text/000020051-20140522103146.txt | http://documents.worldbank.org/curated/en/346161475075465617/pdf/000020051-20140522103146.pdf | Physical investments in the urban sector should be preceded by comprehensive institutional and financial review, and when necessary, policy reform;Where a project suffers a long history of non-performing status, a high level Bank official should intervene to ensure that the composition of field teams and the frequency of visits is adequate to address the problems;Project Implementation Units should be integrated within implementing agencies to retain skills and preserve institutional memory;In countries where natural disasters are common, projects should be designed to be flexible enough to permit fund reallocation for emergency assistance;the size and complexity of projects should be reduced to focus on specific sub-sectors with a limited number of components, that can be implemented by one agency.
P009468 | Fourth Fisheries | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2006 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/808481474549905740/text/000020051-20140617142702.txt | http://documents.worldbank.org/curated/en/808481474549905740/pdf/000020051-20140617142702.pdf | The ICR suggested a number of lessons, of which the following appear to be of general interest: (i) Clear user rights over common property resources (such as inland water bodies) are fundamental, if these resources are to be effectively and sustainably utilized. (ii) Simple cost-effective entry points are needed in inland open-water fisheries to avoid overtaxing newly formed community organizations. Satisfactory performance can lead to more ambitious programs. (iii) Community involvement in preparation through monitoring of construction works increases project quality. (iv) Political support is critical to sustaining nature conservation efforts.
P009470 | Forest Resources Management | South Asia | Bangladesh | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1992 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/189831475077770291/text/000020051-20140607154318.txt | http://documents.worldbank.org/curated/en/189831475077770291/pdf/000020051-20140607154318.pdf | (i) The Bank has valuable experience in forest sector management in several countries in different parts of the world and it can bring useful advice to the Government of Bangladesh to help improve the performance and contribution of the forest sector to the economy. Hence the importance of cross country learning; (ii) Protecting forest resources through beneficiary participation is a challenging task that requires the cooperative effort of all the stakeholders--the communities, research organizations, NGOs, various government departments/agencies and grass root village organizations. The building of this kind of participation requires time, resources and explicit attention to incentives for the stakeholders--costs that need to be explicitly recognized and built into a project. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured.
P009470 | Forest Resources Management | South Asia | Bangladesh | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1992 | 2002 | 2006 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/208921468205174549/text/36295010BD.txt | http://documents.worldbank.org/curated/en/208921468205174549/pdf/36295010BD.pdf | 6. Lessons and Considerations for Future Development 82. Four specificlessonsregardingthe pro-poor growth challenge, and a final lesson related to the Bank's strategyfor Bangladesh's rural sectorhave emergedfiom this review. The first four lessons are closelyinterlinked, and, together, provide two important observations. First, the projects illustratepracticalways to emphasizegrowth and social equityat the sametime, and even demonstratinghow improving equity can also improve productivity. Second,actions across the four areas canbe mutually reinforcing.Pro-poor and gender-inclusiveagriculturalgrowth canbe further stimulatedwhen more than one action area is tackled simultaneously. (1) Dedicated focus on enhancingproductivity pays off. Breakthroughsinproductivity canbe triggeredby making a quantum improvementin productivity a major goal and specifically addressing this in the project's design. Without designingthe project with this in mind, productivitybreakthroughs may not occur. 83. The SDPP and the HORTEXcomponent of the ASIRP placed their major focus on stepped up productivity, and achievedthe breakthroughsthey aimed for. The FRMF did not emphasizeproductivity enhancement, aid no major gains in the productivity of the forestry sectoroccurred. 84. The achievementsreflected the emphasisthat each project placed onproductivity. The very essence of SDPPwas to bring about a quantum leap in the silk sector's productivity to enableBangladeshto be more competitivein relation to the internationalmarket. Nearly all of the SDPP7smonitorable indicatorsmeasuredproductivity.Likewise, the major objective of the horticulturalexport component of ASIRP was to help Bangladeshiexporters to break through the barriers to entryinto the much higher-value international market, compared to the lower-value (and lower-productivity)of the domesticmarket. The FRMP was more in the mold of traditionalBank projects. Its design and impactwas on increasing the number of hectares ~mdercultivated forests, coastalprotection, environmental management and iiistitutionalimprovement. It also had a smallresearch component, as often found ill a Bank rural project. While the FRMP successfullyachievedits objectives, a major jump in productivitywas not its centralpurpose and was not achieved.33 85. The SDPP and HORTEX achieved their breakthroughsthrough a combinationof institutional as well as technologicalinnovations.The enhancement of silk sector productivitywas primarilythrough introducingtechnical improvements, but drivingthis was the new Silk Foundationand the NGO sector. The export breakthroughfor horticultural products involved substantialnew technologiesfor Bangladesh in growing, grading, packaging and transportingof produce,but it was pioneered and then catalyzedthrough an institution, HORTEX, designed and dedicated exclusivelyfor this purpose. - - 33. The reference to improve theproductivity in FRMP's developmentobjectivesreferredto the expansionof forestplantations, not to an improvementinproductivity per hectafe. 86. The SDPP and HORTEX successesmight, however, be exceptionsto the more typical situationfound in Bangladesh's agriculturalsector,where technical knowledge to enhanceproductivitymay be limited. The IEG mission was informed that research was a smallpart of government's expenditure in agriculture-only about 0.2percent of agricultural GDP.34A revolution in agriculturalproductivityis likelyto need a much strongertechnical base than Bangladesh's relatively small researchprogram can currently provide.35 (2) Sociallyinclusiverural developmentneed not constrain rapid agricultural growth. Project design featuresthat target benefits for the poor and women may even enhance agriculturalgrowth. 87. Over 80 percent of the SDPPparticipantswere poor women, and they showed greater interest and care in rearing andreeling-hence in adoptingsericulture and achieving higherproductivity-than wealthierhouseholds. Poor women were the primary target of the SDPP's NGO extensionservices.Under the FRMP's communityforestryprogram, higher productivity,sustainabilityand social inclusionwere found to be mutually complementaryto each other. Tree survivaland groundcover significantlyincreased and yields will likelybe higher, andpoor families and women were the primarybeneficiaries. The key factorleading to increased productivity and sustainabilitywas the switchto communitymanagement by the sociallydisadvantaged, who took greatercare of the plantations than governmentor villagers with higher incomes.. (3) Government-civil societypartnerships can enable large gains in development capacity, both for social inclusion andfor agricultural growth. 88. Bangladeshis known for particularly large inefficienciesin the public sector, and in governance generally.By contrast,the country is rich in its non-government sector, particularlyin its NGOs. Two of the projects reviewed, the SDPP and the ASIRP, indicate that partnerships between government and civil society canbe a major source of increased vitality and productivityin Bangladesh's rural sector. 89. Promotionof the silk sectoris based on a partnershipbetween the Silk Foundation (technical,promotionaland seed production) and the NGO sector, which does most of the extensionand field support,as well as seedproduction. The commercialprivate sectoris fast developing as an additional actor in reeling,weaving, and garment manufacture. The Silk Foundation's technical skillsare conlplementedby the NGO sector's far wider reach and greatercapacityto provide extensionservicesskilled in socialoutreach.Under the horticulturalexport component of ASIRP, horticultural exports were promoted through partner activitiesbetweenHORTEX and the private sector.36Under the DAE component of ASIRP, the partnershipsbetween DAE and NGOs at the upazila level became the centerpiece of the agriculturalextensionprogram. DAE emphasizedto the IEG mission that this 34. Source\.WB ReportNo. 34543-BD; Bangladesh\.Revitalizingthe Agricultural TechnologySystem, November 30,2005. 35 Globalevidence has indicatedthatreturns to research are higher than for any other investmentin agriculture. 36. The partnership for the first exportwas with an NGO. Sincethen, the commercialprivate sectorhas become the dominantsource of horticultural exports. approach could greatlyincrease the effectivenessof agriculturalextension-the DAE providing its technical skills, but others, especiallythe NGO sector, being better in field outreach. 90. By contrast, the FRMP projectwas implemented mostly by the Forestry Department,indicatingthat governmentimplemeiitationwithout partners can alsobe success~l,at least for forestry.However, the pilot activitiesin communityforestry all involve the FD working with small NGOs, the formermainly in technical areas and the latter in local-level social support.The initial experiencewith the FD-NGO partnerships appears promising. 37 (4) To enhancebenefiltsfor women andthe poor, project formulation needs the systematicintegrationof measuresto achieve this. Measures to achieve such social objectivesneed to be organicallyintegratedin the project\. i.e., specificallyfeaturedin the project's design, costing, institutional arrangements, staffing,management processes, the logical framework and monitoring. 91. All threeprojects took somepositive stepsto target women and the poor. These actions, which are typical of other Bank projects, arenoted immediatelybelow, but they were more in the nature of add-ons to project implementationrather than being systematically integratedinto the projects. A more systematicapproach could likely have achieved more. 92. With its labor-intensiveand cottage-based activities,the silk sector is pre-eminent in includingwomen and the poor. Silkrearing and reelingprovide regular income and can be donepart time and on marginal f m s or by the landless. The IEG mission also observed a high proportion of women employed in weaving and garmentmanufacture.Additionally, the NGO extension activities in the SDPPwere specificallytargeted to women and the poor. Based on mission discussions in the field, perhaps over 95percent of beneficiaries were poor, of which over 85percent were women. 93. Concerningthe ASIRP, DAE said that extensionworkers were asked to target women and poor liouseholds.The mission was also told that in choosing communitiesfor sub-project grants, the local (upazila) committeesfavored communitieswith a high proportion of women and the poor, but there is no datarelative to this. Assuming that the sub-projectsdid have some successin socialinclusion, this would have been importantin counteringthe natural societal tendency for minority groupsto be left behind. It is possible that the gender and poverty impact of the ASIRP would have been quitemodest without the project's efforts, sincethe mission visits found the usual tendency for men and wealthier individualsto have the primary influenceon village-level decisionmaking. 94. The FRMPprovided the most striking example of gender and poverty alleviation outcomesinfluencedby project actions. In the mission's visits to several communitymanaged plantations,the great majority of the beneficiarieswere women and the poor. As with the other two projects, the primary reason was that selectionof participants by the Forestry Departmentand local committees strongly emphasized gender and poverty criteria. 37. There is also positive global evidence where forestrydepartmentshave worked withNGOs.; for instance, in India and Nepal. This was appropriatesinceinternational experienceindicatesthat forestry development can have negative social impactsunless there are specificmeasures for social inclusion. The development of government-managedplantations commensuratelyreduces the number of hectares under traditional forests.Even when degraded, such lands provide for traditional forest-based activitiesimportant for the livelihoodsof women and the 95. However, none of the projects employed a systematicapproachto social inclusion, which would likelyhave enhanced gender and poverty alleviationoutcomes. The IEG mission noticed the followinggaps. First, the capacityto plan, implement and monitor the projects' gender and poverty aspectswas limited in both the government and Bank task teams. Themission did not encounterany social specialistsin the project agencies, and data in the ICRs indicatethat the Bank team for the FRMP onlyinvolved a social specialistin project preparation,and for the ASIRP, onlyin supervision.Second,none of the projects had a gender andpoverty alleviationplan, which should also have been integrated into the project's detailed design. Third, therewere no monitorableindicators on poverty and gender impactsin the log fiames, and project data on outcomes was limited. Hence the key features for systematicallyenhancingbenefits forwomen and alleviatingpoverty were largely absent.39 (5) The Bank's rural project portfolio in Bangladesh would merit scaling-up, prioritizing, a longer-termprogram approach, and a better strategicframework. 96. The Bank's lendingto Bangladesh's rural sectorhas declined significantly over the last 5-10 years. (See the completelistingof Bank projects to Bangladeshin Annex C.) Out of 25 ongoingprojects in the Bangladeshportfolio as of February2006, only oneproject is rural (2006 CAS, Annex B8). And only onerural project was approved during the last five years FYOl to FY0540-compared to 23 approvedprojects in the overallBangladesh lending program. None of the three projects reviewed in this PPAR had follow-onprojects. 97. This situationcontrasts sharplywith the messages expressedin Bank and Governmentpolicy documents. The government's 2005 PRSP sees agriculture as the key driver of pro-poor growth. The Bank has also emphasizedthe importanceof the rural sector and highlighted this in each of the last three CASs (1998,2001 and 2006). The 1998CAS comments that faster agriculturalgrowth and rural development are critical in a country where more than 90 percent of the poor live in rural areas. It also commentsthat several 38. Socialrisks alsoneed to be tackled in project.designand implementation. In missiondiscussionswith forestrycommunity groups,a vulnerabilityof the extremepoor to pressuresby locally influentialpersons (to sell forestrights at well below market value for instance) appearedto be a risk. Adaptationsto reduce this risk might be considered,such as strengtheningcommunity-levelinstitutions and making individualdecisions subjectto reviewby the whole community. 39. In this situation,even understanding the social impact of project activitiesis difficult, and making adjustments duringproject implementation has littlebasis on whlch to plan. In the appraisalreports and some government documents, there was also a tendencyto highlightthe expectedgender andpoverty alleviation impacts in the main text, but with limited further reference and implementationdetails in the annexes. 40. This was the Microfinanceproject (approved in FYO1)which is partly rural. Two otherprojects with impact on the rural sector in the FYOl to FY05 period were the Rural Electricity-Renewable Energy Development Project (FY02) and the Rural TransportImprovementProject (FY03). strategicprioritiesprovide the framework for our assistance, of which agriculturewas one. Sincethree of these priorities were macro or cross-cutting(macroeconomic management, private sectordevelopment, and public sectormanagement), agriculturewas one of onlytwo sectors, along with human development,that were singled out. The 2001 CAS considered rural development as one of three priorities for pro-poor growth. Whilethe 2006 CAS is less explicit in highlightingrural development,the first of the CAS's two pillars (improving the investment climate) includes agriculture-along with infrastructure,water resourcesmanagement and informationand communicationstechnology-in its listingof four sectors critical to pro-poor growth. Yet the priorityplaced on agriculture in these policy statementsdoes not appear to have been translated into the lendingprogram. This situationappears likelyto continue, sincethe 2006 CAS has only one rural development project -the proposed National Agricultural TechnologyProject -amongthe 24 projects listed in the proposed lendingprogram for 2006 to 2009 (2006 CAS, Annex B3). It should, however be noted that there are severalpast and proposed projects that supportrural developnlentmore broadly.41Whilethese projectshave potentially significantimpacts on the rural sector,none of theseprojects directlytackles the rural sector's need for a major shift in agriculturalproductivityand pro-poor growth. For this, additional direct engagement in agriculture,water and forestryis needed. 98. The IEG mission frequentlyheard the view that rural sectorlendingis more difficult and its resultsmore disappointingthan in other sectors. The threeprojects reviewed in this PPAR do not support this view. All three projectswere worthwhile, with outcomes at least moderately satisfactory. TheFRMP achieved all its physical objectives,helped improve institutional capacity, developed environmental management plans for Bangladesh's nature reserves,helped develop coastalmangrovesto improveprotection against storm surgesand started successfi~lpiloting of community-based forestry. The SDPP significantlyraised productivity in the silk sector, which had a positive impact on gender inclusion and poverty alleviation.The ASIRP pioneered and catalyzed a breakthroughin horticultural exports, and the agriculturalextensionpart of the project may alsohave had a significant impact. With sensibledesignsthat play to Bangladesh's strengths(such as the NGO sector),with the introductionof technological and institutionalinnovationsas needed, and with strong implementationsupport, ruralprojects in Bangladesh can succeed 99. In fact, the averageperformanceof the three PPAR projects is not substantially different from the aggregate situationacrossthe Bank's entireBangladesh portfolio. Excludingthe PPAR projects, nine of the 17projects completed between the beginningof 2000 and end of February 2006 had a satisfactoryoutcome, six were moderately satisfactory, onemoderatelyunsatisfactory, and one unsatisfactory. 100. The Bank should not downplay the importanceof relevance. If development of the rural sector is a strategicpriority, it does not make senseto neglect it. The question of why support for rural development has declined, is appropriateto pose across the board; not only 41. TheRural Departmentofthe Bank's SouthAsia Regionhas commentedonanearlier draftof the PPAR that it also envisages other operationsinrural livelihoods, water managenlent,fisheriesand landmanagement. The Rural Departmenthas also madereferenceto otherproposedor ongoingprojects supportingrural development suchas rural electrification,rural finance,andlocal governance. to the Bank, but also to other development agenciesand to the government.42It is better for the Bank to support a highlyrelevant development thrust, eachproject having a moderately successfL1o~~tcome,than to support areas of less relevancebecause these are easier.Not supportingrural development in Bangladesh is walking away from one of the country's highest priorities. 101. Bank lendingto the rural sectorhas also sufferedfrom a lack of continuityin recent years. Thiswas not so in the past. Both the FRMP and the ASIRP followed previous projects in their respective sectors,the Bank having supported two projects in forestryand three projects in agriculturalresearch and extensionprior to the FRMP and ASIRP. The ASIRP followedon almost immediatelyfrom the Agricultural Support ServicesProject, which had startedpioneering the new extensionapproaches and had provided initial supportto HORTEX.None of the threeprojects reviewed in this PPAR had follow-onBank support, even though two projects in particular-SDPP and ASIRP-supportedprograms which required a longertime period to become hlly established. 102. The lack of continuityin lendinghas been compoundedby uliduly shortproject durations\.The ASIRP had only a 3%year implementationperiod, and the SDPP 5%years, which included the establishmentof a new agency, the SF, to implementthe project. The 9% years implementationperiod for FRMP was more realistic and about right for the large program that the FRMP supported (thoughthis unusually long implementationperiod could have been broken down into two shorter projects). Thismore realistic time fiamehas probably contributed to the higher outcome and sustainabilityratings for the FRMP relative to the other two projects. 103. The IEG missionnoted the particular vulnerability of the ASIRP's agricultural extension component. In field discussions,it was encouraging to find, four years afterproject closure, enthusiasm still present amongDAE staff for the new extension approachintroduced under the ASIRP. However, as one district officer expressed it, we stillhave the partnerships,but, sincethere is no money, nothing for the partners to do. The ASIRP began a new extensionprogram, followingthe initial stepsthat were taken in the later years of the ASSP, but, inevitably, the program was far from fully establishedwhen the 3%year project ended. StoppingBank lendingat that stagewas unfortunate, since a strongresearch aid extensionprogram is a paramount need for acceleratedagriculturalgrowth in Bangladesh. The FRMP, SDPP and HORTEX programs, although lessurgently in need of continued nurturing,would also have benefited from continuedtechnical and financialsupport. 104. The sparse rural sectorwork in the last decademay have contributed to the Bank's limited attentionto Bangladesh's rural sector.The situationis better now; papers on the rural non-farm sectorand on agriculturaltechnology were issuedrespectively in 2004 and 2005, water management has alsobeen reviewed, and there arethree ongoing studies-on agribusiness, rural finance, and a public sector expenditurereview. Work on an agricultural masterplan has also been done, in partnership with the Government. However, this impressivearray of activityappearsto be pieces of a pie rather than a comprehensiverural 42. ResidentBank stafftoldthe IEG missionthat they hadobserveda decline inrural lendingby most of the donorcommunity.And the Governmentdoes not always apply sufficient funds to the areas it has prioritized;for instance, the muchreduced funding of the agriculturalextensionprogramafterASIRP closed. strategy.What still appears missing is a thorough sector analysiswith sufficient depth and breadth to prepare an overallrural sector strategy. This could also be used to engage the Government and the donor community in a strategic and broad-ranging dialogue on sector policy and lending.
P009482 | Fourth Dhaka Water Supply Project | South Asia | Bangladesh | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/772581474508208161/text/000020051-20140607173019.txt | http://documents.worldbank.org/curated/en/772581474508208161/pdf/000020051-20140607173019.pdf | Early supervision should either sort out the problems of adherence to covenants or cancel the project before major infrastructure contracts have been awarded.The absence of a main Project Director (there were different project directors for various project components) prevented efficient implementation of several works and consultancy contracts.
P009484 | Agriculture Research Management | South Asia | Bangladesh | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/669561474908366757/text/000020051-20140607153947.txt | http://documents.worldbank.org/curated/en/669561474908366757/pdf/000020051-20140607153947.pdf | The ICR offers four lessons which are appropriately drawn from the analysis and findings. They reflect earlier OED findings, and, with some modification, are reproduced here: 1. A neccessary condition for sustainability is the development of management skills and processes to allow efficient implementation of priority research. (The equivalent lesson in the ICR seems to suggest that this is also sufficient because it will allow efficient management within a reduced budget envelope, however OED argues that enhanced skills and processes can only make efficient a scale of operation that can be financed, it cannot alone ensure sustainability.) 2. The effectiveness of technical assistance and training can be increased if these programs are well coordinated and implemented early in the project to offer benefits during the project period. This may call for management of the training program by outsourcing. Outsourcing arrangements should be in place before credit effectiveness. 3. A realistic assessment at appraisal of procurement management capacity is particularly important for research organizations where procurement is not a core professional activity. Procurement Core Teams or outsourcing may help. 4. Project Implementation Units are neither necessary nor desirable because they isolate project activities from the institutional mainstream, may reduce high-level support, and are likely to be damaging to longer-term sustainability. In this case, it is very unlikely that a PIU would have achieved better implementation and transition to the operational phase and sustainability would almost certainly have been even more questionable.
P009484 | Agriculture Research Management | South Asia | Bangladesh | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1996 | 2002 | 2003 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/184781468741916030/text/multi0page.txt | http://documents.worldbank.org/curated/en/184781468741916030/pdf/multi0page.pdf | Lessons The following are the main lessons from the two projects\. 2.61 The lessons ofprevious projects and the diagnosis of constraints emerging during preparation should lead to a set of reforms identifying the minimum for an effective and efficient project which should be clearly articulated in the evolving Bank management documentation Any changes, whether the result of new knowledge or borrower concerns, should be justified with further analysis and be clearly documented. (In ARMP, expediency seems to have overtaken analysis, and rationales in the evolution of the design during preparation and appraisal were not adequately recorded towards the end as the pressure to lend built.) 2.62 Adoption of new unified national extension approaches should be based on evaluated costeffectiveness data It pays to maintain experimentation with a number of promising alternative approaches al different cost levels for a considerable period, if not permanently, since the target is costeffectiveness and since resources and technical challenges can be expected to change over time. 2.63 Cutting costs by institutional rationalization-generally calling for the closing of research stations and substations-is politically difficult, but too seldom faced by either the borrower or the Bank. It may hold as much potential for improving efficiency as increasing benefits and is a quicker route to financial sustainability. 2.64 Bank Project Appraisal Documents (PADs) should include\. a thorough analysis ofpast capital and operating cost allocation and donor support to the sector or subsector; a projection of a reasonable expectation offuture resources availablefrom borrower and donors; leading to a realistic assessment of the expected financial sustainability in the post-project period Too frequently the focus of appraisal documents is on counterpart funding during the project but not afterwards. 2.65 Startup workshops and intensive early supervision with a particular focus on procurement can reduce implementation delays, which can seriously damage the logical coherence and sequencing of a project A common misconception is that borrower institutions that have implemented Bank projects before have adequate procurement experience. With the high staff turnover of most government departments this is rarely the case. 2.66 7he level and rate of introduction of computerized management systems needs to be carefully matched to the current and realistically projected computer skills and technical support capacity. Future Directions 2.67 The following selected issues, a number of them long-standing ones from the past, are high priorities for improved research and extension efficiency in Bangladesh\. * The\. vision for agricultural research in the future should include in particular\. greater attention to the enabling framework and less to the financing of particular research; a central body with strong skills and authority over funding allocation (as for the University Grants Commission); incentives for research performance either through substantial independence from civil service rules or substantial civil service reform; a major rationalization including closure of institutes and substations; improved incentives for research/extension/farmer feedback coordination; and resolution of the financial sustainability issue.26 * A review of the adoption level and adoption rate of improved varieties of different release age to better understand the adoption lag and possible reasons, and to better understand the economic returns to breeding research. * Quick action on the outstanding issues of seeds policy and subsidies with the aim of sustainability. * A review of, and decisions on, the future of CERDI. * A review of the economic impact of ATI expenditure now and over the next 10 years to assess the extent to which that investment is impacting on agricultural production. * A continuation of experiments in extension methods with strong monitoring of cost-effectiveness (particularly farmer field schools if these are to be used more widely) with a focus on lowering costs perhaps through increased audiovisual and information technology means. 26. Probably through some form of government commitment to fund at a certain percentage of agriculture GDP associated with a phased program to increase the share of private, NGO, user fee, and commodity cess funding.
P009491 | RURAL ROADS & MARKET | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1988 |  | 1998 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/377661475097322918/text/000020051-20140516155901.txt | http://documents.worldbank.org/curated/en/377661475097322918/pdf/000020051-20140516155901.pdf | The key lessons from this project are (i) continuous local community participation at all stages of the project is essential for project success, and (ii) developing a sustainable local source of funding is a challenging undertaking and rarely achieved in the context of a project; it requires a broader intervention including changes in policy to increase the revenue base and decision making powers of local governments.
P009491 | RURAL ROADS & MARKET | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1988 |  | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/804981511189041908/text/multi-page.txt | http://documents.worldbank.org/curated/en/804981511189041908/pdf/multi-page.pdf | 6. Lessons Learned and Recommendations 6.7 The following key lessons and recommendations emerge from this audit. 6.8 Examine the non-infrastructure impediments to poverty reduction. While the Bank's assistance in developing rural infrastructure has helped increase economic activity and improve quality of life, the rural population of Bangladesh remains, by and large, poor. Therefore, noninfrastructure interventions, such as improving rural institutions, are needed to maximize the impact of infrastructure investments on poverty reduction. Institutional interventions should be geared towards making the Union Councils more efficient, responsive, and accountable to the rural population. This will involve directly supporting Union Councils to increase their organizational capacities, and working with local communities to design institutional interventions to improve the rule of law in rural communities, and reduce the role of musclemen in political and economic activities. 6.9 Take a sector-program approach. The road sector in Bangladesh is nearing maturity and the Bank has accumulated extensive experience in the sector. It is now time, therefore, to move towards a programmatic and sector-wide investment approach. This would help facilitate the development of an institutional framework for long-term sector investment strategies and policy reforms for improved road management and financing. 6.10 Rationalize donor coordination. The current geographical division of donor activities in Bangladesh may not based on comparative advantage of the donors and may no longer be suitable with the opening of the Jamuna Bridge. The development and improvement of the road network may require a reorientation from the traditional north-south axis to one that best serves the new geographic configuration of economic activities. Therefore, the Bank needs to work with all donors and the government to ensure investment strategies are coordinated on the basis of rational and comparative advantage criteria.
P009496 | Integrated Nutrition Project | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/446241474652951850/text/000020051-20140607170545.txt | http://documents.worldbank.org/curated/en/446241474652951850/pdf/000020051-20140607170545.pdf | 1. A well-conceived, well-proven, relatively simple and straightforward set of core nutrition interventionsâ€“â€“growth monitoring of young children, attention to nutritional status of pregnant women, preparation of food and micronutrient supplementationâ€“â€“can be quickly implemented and can have an impact on severe malnutrition in a relatively short period of time. 2. Using community-based and international NGOâ€™s as significant implementation partners is feasible and can be of great value in controlling costs, circumventing weak government capacity and enhancing sustainability.3. Action should be taken early to see that contracts with NGOs are not taxed by the Government.4. Good baseline data, representative indicators and the use of control as well as intervention areas enable a project to document its results in a meaningful and objectively compelling manner.5. Acting upon operations research findings to effect optimal programmatic change is feasible and useful.6. Intersectoral coordination/involvement in a sector-specific project is difficult, requires a great deal of continuing work, and may or may not be worth the effort; i.e., it is not automatically a desirable and efficacious thing.7. Careful timing of scaling-up of a successful project to a more ambitious program is key to achieving insitutionalization of activities and sustainability, and such successful initiatives should be well-consolidated so that premature expansion and diminished wider impact does not occur.
P009496 | Integrated Nutrition Project | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2002 | 2005 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/939391468206956357/text/32563.txt | http://documents.worldbank.org/curated/en/939391468206956357/pdf/32563.pdf | 6. Findings and Lessons 78. Therewere institutional problems inBINPwhich hampered implementation. The ICR suggeststhat the inter-sectoral component shouldnot havebeenincluded, allowing resources (including supervision) to focus on the core community component. However, it appearsthat the more integrated approach to the inter-sectoral programsbeingadopted underNNP isnow, unlikebefore, reachingthe target group. 79. The limited impact ofBINP onnutritional outcomes raises serious doubts as to thejustification for scaling theproject up to the nationallevel. To do so will prove very costly, with limited nutritional gain. Several lessons emerge from this analysis which shouldbe borne inmind\. Supplementary feedingfor children does have a positive impact, especially for the most malnourishedchildren. NNP has revised the eligibility criteria so that only growth faltering children with WAZ-2SDs receive feeding, as well all children with WAZ-4 SDs. The latter group constitutes a very smallpercentage o f children, so there appears to be scope for raising this thresholdto, say, -2.5 SDs, to capture more children amongwhom feeding seems most successful. There i s also some mis-targeting,which i s likelyto bebest addressedby further training for CNPs ininterpretinggrowth charts. Supplementary feeding for pregnant women appears likelyto be an ineffective approach on two grounds\. the pregnancy weight gain achieved by most women is too small to have a notable impact on birthweight (though there are sub-groups for which benefits are more substantial) and evidence from elsewhere suggests it i s anyhow pre-pregnancy weight which i s the more important determinant o f birth weight (Kramer, 1987). The programwould appear more successful ifit restricted its attention to the most malnourishedwomen, improvedtargeting to reduce Type I1error andtriedharder to discourage leakage and substitution. For both types o f feeding program, there i s evidence o f a greater impact inthe lean season. There are grounds for considering either increasingthe size o f the food supplement inthis period, restrictingit to those months, or adjustingthe eligibility criteria by time o f year. Discouragingwomen from eating down duringpregnancy has some benefit for birthweight. But all forms o fknowledgetransmitted bytheproject suffer from a knowledge-practice gap &e., not puttingknowledge into practice, though uptake o fbetter practices has increased inproject areas). Such gaps are common and have multiplecauses. However, paying attention to the causes o f the gap can help enhance project effectiveness. Inthe short-run the gap can also be alleviated through better targeting, although that maynot help those who are time constrained. 80. More general lessonscan also be drawn about the use o f the growth monitoring approach. This approach has proved successful elsewhere, notably inTI, so it cannot be arguedthat growthmonitoringwith counseling is an inherentlyflawed approach. Indeed, many studies show the role o fmother's knowledge inimproving child nutrition including OED's own impact study o fbasic education inGhana. There appear two main reasonswhy the approach hasbeen less successful inBangladesh\. (1) poor implementation, notably training o f CNPs; and (2) resource constraints on mothers. Consideration o f the context and attention to detail inimplementation are, rather needless to say, vital ingredients o fprogram success. 81. A positive lesson from BINP emerges withrespect to evaluation. There was a strong commitment to evaluationfrom the start. Crucially, funds were obtained to conduct the baseline prior to project effectiveness. This i s not usually done; inmany projects the plannedbaseline gets delayed given other problems encountered during project start-up. However, it would have beensensible to award a contract for all three studies at the outset, rather than change contractors for the survey duringthe course of the project.
P009506 | POWER DIST. (16 TOWN | South Asia | Bangladesh | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1989 | 1998 | 2000 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/276301474563680391/text/000020051-20140526224631.txt | http://documents.worldbank.org/curated/en/276301474563680391/pdf/000020051-20140526224631.pdf | Relevant lessons are: (i) need for proper coordination between project staff and commercial operations personnel; and (ii) adequate attention should be paid to improving the condition of consumer service drops and meters in order to achieve sustainable reduction in non-technical losses
P009509 | Jamuna Bridge | South Asia | Bangladesh | IDA |  | Infrastructure | Transport | IDA | IPF | 1994 | 2000 | 2001 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/219381474501074383/text/000020051-20140529071637.txt | http://documents.worldbank.org/curated/en/219381474501074383/pdf/000020051-20140529071637.pdf | The ICR identifies the following lessons of broad applicability:The Bank still has a comparative advantage in providing financial assistance for large infrastructure projects, especially in countries with poorly developed capital markets.Achieving "quality at entry" is dependent on the resources allocated for project preparation. The preparation and implementation of social and environmental components of large civil works projects need same attention as preparation and implementation of physical components.NGOs can play a significant role in facilitating the implementation of social and environmental components.
P009516 | AGRIC. SUPPORT SERVI | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1991 |  | 1999 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/997311474553684306/text/000020051-20140521040318.txt | http://documents.worldbank.org/curated/en/997311474553684306/pdf/000020051-20140521040318.pdf | 1. Policy change and true ownership are essential pre-requisites for a significant change in extension direction, they may be best achieved through a series of phased steps but with a clear longer-term goal; 2. Intensive supervision in the early years is required for innovative projects; 3. Consultants and TA can play a major role in developing strategies, and managerial and process solutions; 4. Close cofinancier involvement and coordination and cofinancier provided TA can contribute substantially to development effectiveness. 5. Targeting of extension at poorer farmers and women appears to be possible (although, in this case, further data will be needed). 6. High levels of supervision input can contribute to improving project performance.
P009516 | AGRIC. SUPPORT SERVI | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1991 |  | 2003 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/184781468741916030/text/multi0page.txt | http://documents.worldbank.org/curated/en/184781468741916030/pdf/multi0page.pdf | Lessons The following are the main lessons from the two projects\. 2.61 The lessons ofprevious projects and the diagnosis of constraints emerging during preparation should lead to a set of reforms identifying the minimum for an effective and efficient project which should be clearly articulated in the evolving Bank management documentation Any changes, whether the result of new knowledge or borrower concerns, should be justified with further analysis and be clearly documented. (In ARMP, expediency seems to have overtaken analysis, and rationales in the evolution of the design during preparation and appraisal were not adequately recorded towards the end as the pressure to lend built.) 2.62 Adoption of new unified national extension approaches should be based on evaluated costeffectiveness data It pays to maintain experimentation with a number of promising alternative approaches al different cost levels for a considerable period, if not permanently, since the target is costeffectiveness and since resources and technical challenges can be expected to change over time. 2.63 Cutting costs by institutional rationalization-generally calling for the closing of research stations and substations-is politically difficult, but too seldom faced by either the borrower or the Bank. It may hold as much potential for improving efficiency as increasing benefits and is a quicker route to financial sustainability. 2.64 Bank Project Appraisal Documents (PADs) should include\. a thorough analysis ofpast capital and operating cost allocation and donor support to the sector or subsector; a projection of a reasonable expectation offuture resources availablefrom borrower and donors; leading to a realistic assessment of the expected financial sustainability in the post-project period Too frequently the focus of appraisal documents is on counterpart funding during the project but not afterwards. 2.65 Startup workshops and intensive early supervision with a particular focus on procurement can reduce implementation delays, which can seriously damage the logical coherence and sequencing of a project A common misconception is that borrower institutions that have implemented Bank projects before have adequate procurement experience. With the high staff turnover of most government departments this is rarely the case. 2.66 7he level and rate of introduction of computerized management systems needs to be carefully matched to the current and realistically projected computer skills and technical support capacity. Future Directions 2.67 The following selected issues, a number of them long-standing ones from the past, are high priorities for improved research and extension efficiency in Bangladesh\. * The\. vision for agricultural research in the future should include in particular\. greater attention to the enabling framework and less to the financing of particular research; a central body with strong skills and authority over funding allocation (as for the University Grants Commission); incentives for research performance either through substantial independence from civil service rules or substantial civil service reform; a major rationalization including closure of institutes and substations; improved incentives for research/extension/farmer feedback coordination; and resolution of the financial sustainability issue.26 * A review of the adoption level and adoption rate of improved varieties of different release age to better understand the adoption lag and possible reasons, and to better understand the economic returns to breeding research. * Quick action on the outstanding issues of seeds policy and subsidies with the aim of sustainability. * A review of, and decisions on, the future of CERDI. * A review of the economic impact of ATI expenditure now and over the next 10 years to assess the extent to which that investment is impacting on agricultural production. * A continuation of experiments in extension methods with strong monitoring of cost-effectiveness (particularly farmer field schools if these are to be used more widely) with a focus on lowering costs perhaps through increased audiovisual and information technology means. 26. Probably through some form of government commitment to fund at a certain percentage of agriculture GDP associated with a phased program to increase the share of private, NGO, user fee, and commodity cess funding.
P009518 | Second Rural Roads & Markets Improvement | South Asia | Bangladesh | IDA |  | Infrastructure | Transport | IDA | IPF | 1997 | 2003 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/842201474895983875/text/000020051-20140607174045.txt | http://documents.worldbank.org/curated/en/842201474895983875/pdf/000020051-20140607174045.pdf | Large projects like this require a long time for preparation (more than 3 years) even though they follow-on from successful projects. This improves the smoothness of implementation but there are ways of reducing start up time such as appointing design staff before effectiveness, retaining the agency's earlier project team and starting land acquisition earlier.The number of contracts was overwhelmingly large; in future projects works in nearby areas should be packaged in one contract.To be effective a programmatic Sector Environmental Assessment requires detailed guidelines for planning, design and implementation.In Bangladesh the current land acquisition procedures are outdated, time consuming and provide opportunities for corruption.Regular monitoring systems (SEME) and socioeconomic impact studies should be synchronized through a common survey framework. The ToR for studies needs to be coordinated to draw synergies between the two activities and exploit comparative advantages.
P009524 | Dhaka Urban Transport | South Asia | Bangladesh | IDA |  | Infrastructure | Transport | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/444101475097102555/text/000020051-20140613081725.txt | http://documents.worldbank.org/curated/en/444101475097102555/pdf/000020051-20140613081725.pdf | Complex project designs should be avoided in a weak implementation environment.Borrower ownership and leadership are essential to ensure progress where significant policy and institutional reform is envisaged.Lines of authority for project management should be clearly defined.Where local administrative capacity is weak a highly experienced independent engineer should be appointed.Public relations and a comprehensive communication strategy are particularly important for urban transport projects.To support economic sustainability measurable actions should be included as part of the project design and monitored appropriately.
P009529 | POP. & HEALTH IV | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1991 | 1998 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/236581474748950785/text/000020051-20140526223200.txt | http://documents.worldbank.org/curated/en/236581474748950785/pdf/000020051-20140526223200.pdf | Borrower commitment to a project and its implementation, combined with long-term IDA commitment and effective management and oversight can result in a solid project, even one of great magnitude, such as this one. Policyissues need to be addressed, including financial aspects of sustainability, even in large, ongoing, credit-financed programs. Projectized approaches can be inefficient and undermine Government ownership and implementation. Pressures on poor governments to fund tertiary care facilities and curative care will continue to be strong, and must be resisted in order to have the greatest public health impact, i.e., to use the funds most efficiently and effectively. Greater involvement of NGOs in large government-run programs is to be encouraged.
P009529 | POP. & HEALTH IV | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1991 | 1998 | 2006 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/784711468002177460/text/36564010BD.txt | http://documents.worldbank.org/curated/en/784711468002177460/pdf/36564010BD.pdf | 5. LESSONS LEARNED 5.1 Aid-financed health infrastructure can work in improving health outcomes.. . provided other conditions are inplace\. this PPARhas produced additional evidence in support o f the main argument o f IEG's impact evaluation that the creation o f an extensive health and family planningsystem inBangladesh, with considerable assistance from external finance, has made a demonstrable improvement to the healthoutcomes o f Bangladeshis. However, this success was achieved through the balanced growth o f infrastructure and appropriately trained staff, The experience o fthe community clinics shows that services will not be usedifthey lack resources or the skills o fthe staff are inadequate for what i s expected o f them. 5.2 Public andprivate provision are complementsnot substitutes\.The health demands o f Bangladeshis are met bybothpublic and private providers. These suppliers do not work inparallel, but Co-exist through various symbiotic relationships. 5.3 A SWAP takes time to implement and is an evolutionaryprocess. InBangladesh it can be said it took 20 years ofdonor coordinationto beginthe process o fimplementing a SWAP. It i s not feasible tojump from a project approach to fully-fledged SWAP overnight. Rather institutionsneedto evolve from one to the other, though a series o f interiminstitutionalarrangements.Thechanging way inwhich donor funds havebeen handled under FPHP, HPSP andHNPSP i s an example o f this. 5.4 Wide stakeholderparticipation inpreparation helps ownership but can weaken design.The broadparticipatoryprocessmade it difficult to prioritize, notably with respect to ESP. A compromise needbe sought betweenparticipation andtechnical guidance to working $goups inorder to maintain satisfactory quality at entry. 5.5 Think through the implications of the new system. The move to a SWAP implies a change inhow things are done for bothDPs and government inways which are often not well understood. It i s imperative to think through how systemswill actuallywork, andmake sure that all involvedunderstandthis. This process will necessarily take time. 5.6 Draw on the appropriate skills mix. Many aspects o fthe design and implementationof a SWAP do not fall withinthe competence o fhealth specialists. Thus, theneedfor appropriate expertise should berecognized anddrawn on. Bank staff should seek to draw on the Bank's experience with similar issues inother countries, making sure that local staff, DPs and government can all benefit from this experience. 5.7 Failure to assessfully thepolitical economy of reform and toprepare both a proactiveplanfor addressing/mitigatingrisks and a contingencyplan will considerably diminishprospectsfor successful reform. Ina politicked environment policy reversals are the norm not the exception. DPs should beprepared to adapt their approach\. maybe renaminginstitutions will suffice, but it may not be so. 5.8 Too much donorBank intervention can undermine government capacity and ownership of a SWAP approach. Preparation o fthe SWAP startedwith a highdegree o f local ownership. But the extensive role playedby donors inthe review process, and the importance o f the tasks which eventually fell to HPSO, but would have beenbetter carried out by government, reduced local ownership. 5.9 Be realistic in'tackling major reform objectives. HPSP combined the move to a SWAP withtwo major sets ofreforms\. unification and decentralisation, as well as the introduction o f a new tier o f service delivery at community level. This was rather a lot to hope to achieve ina single project. A more phased approachmay have yielded more lasting results ina less acrimonious manner.
P009533 | Gas Infrastructure Development | South Asia | Bangladesh | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1995 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/955191475092543470/text/000020051-20140529205159.txt | http://documents.worldbank.org/curated/en/955191475092543470/pdf/000020051-20140529205159.pdf | Careful project preparation, including appropriate conditionalities, is necessary to gauge Government commitment to the project and to the reforms attached to the project. In order effectuate policy change, the Bank should not rely on other donors' conditionalities, but should take steps during project preparation to augment its own leverage through appropriate conditionalities and covenants. Objectives without concomitant components are almost certainly not going to be achieved.
P009533 | Gas Infrastructure Development | South Asia | Bangladesh | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1995 | 2000 | 2005 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/179831468743406781/text/29515.txt | http://documents.worldbank.org/curated/en/179831468743406781/pdf/29515.pdf | Lessons 68. Themainlessons that emerge from the assessment o fthese two projects are\. Indesigninginstitutionaldevelopment components ofprojects, the incentives for those directly concerned byproposed changes should be well alignedwith the project objectives. Inparticular, the staffing andremunerationimplications o f major institutional reorganizations (such as the creationo f GTCL), needto be well understood and explicitly addressedifreorganizations are to be successfully implemented; 0 Buildinga strong gas industry ofintemational standardrequires amajor IDeffort\. better management, greatly increasedtraining, betterremuneration andmore autonomy; 0 The Bank should take a less dogmatic approach to sector reforms andpractice greater sensitivityto local socio-political constraints, ifit i s to achieve collaborativedialog and succeed inobtaining Borrower 'buy-in' to its proposals. 0 Strong and continuing field office involvement insubstantive project work i s more effective than intermittent, long-distance involvement o f HQstaff. 0 Whenthe Bank finds it difficult to justify its support for aparticular sector due to policy differences, it should strategically weigh the benefits o fmaintaininga flexible form o f engagement against the consequences o f full withdrawal. Repeated sharp changes inthe Bank'sinvolvement could be damaging to its credibility and could constrain its ability to seek policy reforms.
P009540 | Third Inland Water Transport | South Asia | Bangladesh | IDA |  | Infrastructure | Transport | IDA | IPF | 1991 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/880071474853571691/text/000020051-20140607141736.txt | http://documents.worldbank.org/curated/en/880071474853571691/pdf/000020051-20140607141736.pdf | The five "lessons learned" are broadly applicable but hardly news - (i) The need for thorough planning and a participatory process; (ii) Continuity of personnel and close monitoring are needed; (iii) Empowerment of the Implementing Agency is necessary; (iv) An enhanced private sector role is required; and (v) Commitment to reform is essential.
P009542 | Third Rural Electrification | South Asia | Bangladesh | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1990 | 2000 | 2001 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/533671475100474886/text/000020051-20140529073735.txt | http://documents.worldbank.org/curated/en/533671475100474886/pdf/000020051-20140529073735.pdf | (a) Rural electricity cooperatives can function efficiently. Electric power distribution can be improved by shifting the responsibility for its implementation from public sector parastatals to private sector entities, even when these entities are cooperatives, and therefore not privately owned.(b) Local training programs established by a central body can create a cadre of competent technicians who can, in turn support a private sector led construction.
P009542 | Third Rural Electrification | South Asia | Bangladesh | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1990 | 2000 | 2001 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/464891511185765795/text/multi0page.txt | http://documents.worldbank.org/curated/en/464891511185765795/pdf/multi0page.pdf | LESSONS Four lessons emerge. First, the success of this project (and its two predecessors) must be attributed in part to the availability of a tried and tested model\. the master plan developed in 1978 was strengthened by technical assistance from the National Rural Electrification Cooperative Association, a U.S. agency with a performance record dating back to the 1930s. However, even with a sound master plan, the projects would not have succeeded in the absence of long-term commitment by government\. this is the second lesson. Third, the unique division of labor in the Bangladesh system of rural electrification is worthy of note\. the cooperatives handle consumer services and operational aspects; the (apex) Rural Electrification Board performs a quasiregulatory function, and provides finance, technical inputs and training; and the private sector carries out construction. This is a promising model, noteworthy for its transparency and the quality of performance monitoring. Fourth, the feasibility of serving poorer households needs to be more carefully researched. It is possible that, even in a densely populated country where the majority of the population lives in rural areas, there will be a tradeoff between coverage of the poorest households and the financial performance of the cooperatives supplying them with electricity. Also, poorer households that are capable of paying domestic electricity tariffs may, nevertheless, be cut off from grid supply because they cannot afford the upfront costs of connection and house wiring. There may be a case for providing a targeted subsidy to cover these one-time costs.
P009544 | NAT'L MINOR IRRIGATI | South Asia | Bangladesh | IDA |  | Other | Other | IDA | IPF | 1991 |  | 1999 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/174191474852942349/text/000020051-20140519065234.txt | http://documents.worldbank.org/curated/en/174191474852942349/pdf/000020051-20140519065234.pdf | (i) Implementation rates of projects that depend on farmer and community initiatives are difficult to predict, and hence a start is best made with flexible small scale initiatives which can be adapted and expanded according to demand; (ii) Social organizers are needed in projects that require beneficiaries to take new community initiatives to obtain project benefits; (iii) Appointment of key implementation staff should be a condition of board presentation or effectiveness to avoid the risk of long delays; and (iv) Where benefits depend greatly on technical innovations, adequate arrangements should be made for appropriate technical support.
P009545 | River Bank Protection | South Asia | Bangladesh | IDA |  | Sustainable Development | Water | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/519151474496576022/text/000020051-20140607151902.txt | http://documents.worldbank.org/curated/en/519151474496576022/pdf/000020051-20140607151902.pdf | The following lessons noted by the ICR are of broad applicability: Use of an Independent Panel of Experts (IPOE) (or similar body) will be effective only when the implementing agencies (IAs) and the IPOE clearly understand the TORs, and if the IAs adequately manage the panel's outputs. To ensure cost-effectiveness, Technical assistance (TA) must be pro-actively managed by the contracting project agency from the outset of the consultants' assignments. Without good management, TA inputs in the early days of the assignment tend to be squandered, often resulting in reduced and delayed delivery of TA outputs.
P009549 | Coastal Embankment Rehabilitation | South Asia | Bangladesh | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2003 | 2004 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/132421474561988913/text/000020051-20140612091718.txt | http://documents.worldbank.org/curated/en/132421474561988913/pdf/000020051-20140612091718.pdf | Coastal protection projects require a comprehensive approach which should include the following key elements: (i) a coastal protection plan; (ii) a network of safe havens, access roads and adequate drainage; and (iii) a modern disaster preparedness and response system. Sustainability of flood control and drainage schemes can be improved through community participation in operation and management (O&M), including contribution to O&M costs. However, institutional and implementation arrangements to introduce community participation are complex, difficult in practice and need significant time to implement fully. Also, it is important to ensure that the groups that exist do not wither away for lack of legal provision and resources.Donor policies and procedures must be agreed before project approval. Failure to do so disrupts the timely flow of funds and services during project implementation.
P009549 | Coastal Embankment Rehabilitation | South Asia | Bangladesh | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2003 | 2005 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/904761467996994427/text/31565.txt | http://documents.worldbank.org/curated/en/904761467996994427/pdf/31565.pdf | Lessons 60. Experiencewith this project confirms a number o f OED lessons\. There i s a need to pay continuous attention to implementation performance in disaster-related operations to ensure that such operations are practical anddo not sideline needed sector reforms. Issuesthat particularly require attention are ensuring that the Borrowerhas the institutionalcapacity to manage andmonitor social mobilizationandresettlement andi s conversant with the Bank's procurement procedures and guidelines (inthis operation, the Borrower's attention to social mobilization andresettlement languished once donor financing ceased). Technical and sociaVorganizationa1assistance essential for the introductionofnew innovationsor ways ofdoingbusiness must be fully funded for the duration o f a project. Failureto do so may cause serious implementation delays. This project also highlightedthe importance ofharmonizationo fpolicies among donors for subsectors inwhichthey sharecommonconcerns andinvestment. Ifdevelopment partnersare unwillingto commit to the durationo fthe project, then altemative ways offinancing technical assistance should be explored. Coastal defenses should be renovated to higher engineering standards inhomogenous units. This not only has greater sustainability thanisolatedrepairs of existing infrastructurebut it also provides amodelthat canbemonitoredto test the success o f the innovationanimportant design consideration. 21 Annex A
P009550 | Primary Education Development Project | South Asia | Bangladesh | IDA |  | Human Development | Education | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/723791474851654575/text/000020051-20140612141204.txt | http://documents.worldbank.org/curated/en/723791474851654575/pdf/000020051-20140612141204.pdf | A programmatic approach should ensure that there is sufficient political committment by the borrower to this modality and a clear agreement on development objectives. Likelihood of succes is enhanced when there is adequate institutional capacity, clear agreement among the development partners and between the government and development partners on objectives and intervention modalities, and a strong M&E system.Government commitment to systematic data collection and utilization of this data for timely policy and corrective intervention is fundamental to the success of any project.High transaction costs associated with coordination of many discrete but interdependent projects cannot be underestimated.
P009553 | JUTE SECTOR ADJ.CRED | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1994 | 1998 | 1998 | ICRR | >=50 million & <100 million | Highly Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/785311475101203112/text/000020051-20140519055954.txt | http://documents.worldbank.org/curated/en/785311475101203112/pdf/000020051-20140519055954.pdf | (1) Relying on the Ministry of Jute to deliver the program may have contributed to the negative outcome. When it became clear that the jute industry was likely to contract, Ministry-of-Jute zeal for its implementation may have dropped off. A greater implementation role for the Ministry of Finance may have been in order. It may have had greater power, legal competence and certainly incentives for carrying the program through to completion. (2) Once again the Bank was technocratic in a political arena. Attention to positions on jute privatization, and to liquidation of insolvent mills among the various actors (government players, farmers, mill owners, etc.) might have permitted the Bank to help put together a program with greater political support (It certainly would have permitted writing a better statement of risks and how to deal with them in the President's Report.) (3) There is little discussion in the President's Report about bankruptcy practice in Bangladesh. Nine public mills were to be declared bankrupt and liquidated. But whether the legislation/ regulations and procedures for this were in place is not addressed. If the reform program in effect requires bankruptcy proceedings, the constraints on such proceedings of a legal, customary, political nature etc. need to be thoroughly addressed during project preparation so as to facilitate liquidation "down the road."
P009555 | Female Secondary School Assistance | South Asia | Bangladesh | IDA |  | Human Development | Education | IDA | IPF | 1993 | 2001 | 2003 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/450391474504847857/text/000020051-20140607150204.txt | http://documents.worldbank.org/curated/en/450391474504847857/pdf/000020051-20140607150204.pdf | Â· The very poor may enroll children to school in response to food or money. However, parents may do the minimum necessary to get the desired benefit and not necessarily encourage childrenâ€™s attendance. Incentives must be tied to attendance, study, and passing of examinations.Â· Enrollment in school, although important, does not automatically bring about education and information acquisition. Access to education of low quality has dubious benefits. Governments and donors must provide the very poor with the means to help them attend classes regularly and learn the required material.Â· People may modify their social customs to obtain earnings and status, particularly if these customs have drawbacks. Award of stipends or possibly even simple cash transfers to families may be useful in postponing marriages for girls who did not attend or finish primary school, perhaps in the form of stipends for vocational training. The FSSAP experience may be useful in eradicating other undesirable customs (such as female â€œcircumcisionâ€ in Africa.)Â· Significant amounts of overstated data in a database may make it hard to assess project effects. Decisions based on incorrect data may hurt intended beneficiaries. To ensure the integrity and accuracy of data, therefore, projects should aim at establishing realistic parameters and criteria for inclusion in various programs.
P009555 | Female Secondary School Assistance | South Asia | Bangladesh | IDA |  | Human Development | Education | IDA | IPF | 1993 | 2001 | 2003 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/117381468768556580/text/262260BD0PPAR.txt | http://documents.worldbank.org/curated/en/117381468768556580/pdf/262260BD0PPAR.pdf | Lessons 1.65 Experience with the project confirms a number o f OED lessons from education projects\. The very poor may enroll children to school inresponse to food or money. However, parents may do the minimumnecessary to get the desired benefit and not necessarily encourage children's attendance. Incentives must be tied to attendance, study, and passing o f examinations. Enrollment in school, although important, does not automatically bringabout education and information acquisition. Access to education o flow quality has dubious benefits. Governments and donors must provide the very poor with the means to help them attend classes regularly and learnthe required material. 68. An ex-ante microeconomicmodelingexerciseshows that studentsbenefitingfrom the BrazilianBolsaEscolamight have improvedattendance,but the funds might have alimited impactonpovertyreductionor inequalitylevels (Bourguigon,F., F. Fereira, andP. Leite. (Ex-ante Evaluationof ConditionalCashTransfer Programs\. The Case of BolsaEscola. Seminarpresentedat the World Bank, October 22,2002). 0 People may modify their social customs to obtain earnings and status, particularly ifthese customs have drawbacks. Award o f stipends or possibly even simple cash transfers to families may be useful inpostponingmarriages for girls who didnot attend or finish primary school, perhaps inthe form o f stipends for vocational training. The FSSAP experience may be useful ineradicating undesirable customs inother countries. 0 Significant amounts o f overstated data ina database may make it hardto assess project effects. Decisions based on incorrect data may hurt intended beneficiaries. To ensure the integrity and accuracy o f data, therefore, projects should aim at establishing realistic parameters and criteria for inclusion invarious programs. 0 Programs that have much social appeal andpolitical support criterion-based provisions for reviews should be established early on. It may be harder to modify such projects if governments perceive that their political benefits will be reduced. 0 Successful pilot projects may be scaled up as full operations, but size may create unforeseen problems. Implementersmust carefully assess the benefits and risks o f scaling up.
P009559 | TECHNICAL ASSISTANCE 6 | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1992 | 1999 | 2001 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/398641474895417932/text/000020051-20140529065916.txt | http://documents.worldbank.org/curated/en/398641474895417932/pdf/000020051-20140529065916.pdf | 1. The idea of a 'one-stop' approach to providing PPF may have had value. However, an adequate and comprehensive framework for identification, appraisal, and implementation of sub-projects including an assessment of the capacity of implementing agencies would have considerably enhanced final outcomes. 2. Quality at entry is of critical importance for process projects, and the operational guidelines should be finalized before credit effectiveness.3. In such projects, which aim to finance a variety of specialized and complex sub-projects, the TTL cannot provide adequate support and must be supported by specialists in the area. Adequate supervision budgets must be provided.
P009560 | Non-Formal Education Project | South Asia | Bangladesh | IDA |  | Human Development | Education | IDA | IPF | 1996 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/859301475094450244/text/000020051-20140607141530.txt | http://documents.worldbank.org/curated/en/859301475094450244/pdf/000020051-20140607141530.pdf | Government commitment, vision, and a clear strategy increase the probability of carrying out complex and difficult projects. - A robust assessment of institutional capacity and a clear understanding of additional resources required increase the probability that a complex project will be carried out within the expected time frame. - Large, multi-member oversight councils may not be effective in meeting regularly and actually formulating policy. - Systematic monitoring and formative evaluation of non-formal education programs are essential. Where a project specifically targets female education, appropriate performance indicators should be incorporated to monitor progress towards this objective, e.g., training and hiring female teachers, and designing relevant curriculum.
P009568 | TRUST FUND FOR ENV. | South Asia | Bhutan | IDA |  | Infrastructure | Urban, Resilience and Land | GEF | IPF | 1992 | 1998 | 1998 | ICRR |  | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/351581474504692130/text/000020051-20140519060218.txt | http://documents.worldbank.org/curated/en/351581474504692130/pdf/000020051-20140519060218.pdf | Trust funds need a legal framework to institutionalize collaboration betwen the parties and define the role of the fund; A reliable source of funding is necessary during the period of establishment of the trust fund; and Design and appraisal teams should include expertise in financial asset management, and trust fund institutional and program development.
P009572 | EDUCATION | South Asia | Bhutan | IDA |  | Human Development | Education | IDA | IPF | 1988 | 1997 | 1999 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/132651475069818807/text/Bhutan-Primary-Education-Project.txt | http://documents.worldbank.org/curated/en/132651475069818807/pdf/000020051-20140519080305.pdf | Limited implementation capacity often generates implementation delays. Government commitment and project ownership are crucial to satisfactory implementationAccess to schools is often the biggest determinant of enrollment increases.
P009574 | EDUCATION II | South Asia | Bhutan | IDA | Non-FCS | Human Development | Education | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/666571475085580457/text/000020051-20140615094921.txt | http://documents.worldbank.org/curated/en/666571475085580457/pdf/000020051-20140615094921.pdf | Educational system reform towards improved student learning outcomes in Bhutan has been a "generational process," in which over the past 20 years -- since the launching of the "New Approach to Primary Education -- infrastructure, inputs and processes have been laid down. In the next ten years it is essential that the system become more outcomes oriented, both in assessing and improving what and how well students learn and in assessing and improving the performance of teacher and managers. End of cycle (e.g., 8th grade) examinations are generally not valid measures of student learning outcomes; the Project appropriately created new standardized achievement tests in math and English and the Ministry has done well to make these the indicators of learning outcomes in the follow-on Education Development Project.In a series of Bank supported projects, it is important that lessons from one project be used in improving performance in the next. In the project preceding the current one, construction delays were a serious problem and ways of overcoming were said to have been built into the current project design. However, the current project experience even more serious delays, and at the end its recommendation was once more that up-front planning measures should be taken to avert construction-related delays. Another lesson from the preceding project was the need for good built-in monitoring and evaluation processes in new Project, but many of those built into SEP were dysfunctional. Good practice would be to revise unworkable performance indicators early in the project rather than declaring them to be unusable at the end of the project. It is important that newly appointed component managers be adequately prepared for their responsibilities through a systematic process of handover and training. When financial managers fail to improve their performance even after intensive training and are ultimately replaced, it would be good for this to be done early in the project rather than late, since poor financial management can contribute to project delays and ineffectiveness.
P009582 | Third Forestry Development Project | South Asia | Bhutan | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1994 | 2002 | 2003 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/145671474908964242/text/000020051-20140612065307.txt | http://documents.worldbank.org/curated/en/145671474908964242/pdf/000020051-20140612065307.pdf | The ICR notes several important project level lessons two of which are repeated here: (i) land for reforestation is often subject to other uses by local communities and therefore plantations have proven unsustainable in the absence of meaningful involvement of current users; (ii) the training policy needs to ensure that staff trained in a particular skill remain employed in that area of training and that all training is consistent with an established training program. The ES adds the following:(i) In projects with a clear poverty alleviation objective alongside an objective of regenerating forest cover, development objectives should be framed at least partly in terms of poverty alleviation. This should be done in a way that is monitorable and should be backed up in design by a monitoring and evaluation system capable of measuring poverty impact. (ii) Policy issues such as seedling pricing and institutional issues like land tenure arrangements and linkages between forests and livestock grazing need to be identified and dealt with ex-ante. Solution to these issues requires commitment from various levels/departments of government. Hence, if they are not sorted out at the design stage, they may never get resolved and may dampen the implementation experience of the best of projects. (iii) Development of an efficient monitoring and evaluation system is crucial to the establishment of a community based forest protection and management system.This is so not only for assessing outcomes and impacts but for making efficient mid course corrections, as and when required. (iv) Staff continuity on the Bank side is as important as that on the side of the Borrower. In the Bhutan Third Forestry Development Project there were six Task Team Leaders over the life of the project with consequent negative impact on project performance.
P009843 | A.P. IRRIGATION II | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1986 |  | 2001 | PPAR | >=100 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/753481511185803149/text/multi0page.txt | http://documents.worldbank.org/curated/en/753481511185803149/pdf/multi0page.pdf | 4. Findings and Lessons The AP II Experience has Catalyzed Reform 4.1 The Bank provided a credit/loan package of $325 million for completion of the works under a third phase project, AP III, in 1997. During appraisal government resolved the water allocation issue which so dogged AP II. This revealed that some of the AP II irrigation works constructed at the tail-end of Sriramsagar are not viable with the water available and therefore a decision has been made to abandon them they remain as a monument to government's overambitious water engineering plans. Almost all the carry-over works in Sriramsagar have been completed, the last in May 2000 (Annex B). 4.2 In the hiatus between the projects, the state government initiated a large-scale and statewide reform program led by a new Chief Minister who was recently reelected for a second term. The irrigation sector has been a major beneficiary, and this has provided an opportunity for the Bank to reorient its assistance. The appointment of a Country Director has provided much needed leadership for the Bank's India operations and eliminated the communication problems that lay at the heart of much of the poor Bank management under AP II. From being an antagonist under AP II, the Bank has become a partner.24 Gradually, the Bank's irrigation subsector work and investment is being brought within state-wide public expenditure purview under the Bank's Andra Pradesh Economic Restructuring Package. To date, however, there has been little progress on unbundling the subsector to improve its governance, downsizing the state payroll and making it financially more accountable. 4.3 The Sriramsagar project has become operational with a marked growth in irrigated area that occurred shortly after AP II was closed and before AP III became effective, Figure 2. Government's efforts in promoting participatory irrigation management and simultaneously launching a program to reform the way the ICADD works with farmers was key to this new start. By 1998 GOAP had created and empowered through the electoral process, 10,292 water 24. Oblitas, Keith and Peter Raymond. 1999. Transferring Irrigation Management to Farmers in Andra Pradesh, India. World Bank Technical Paper No. 449. 25. Raymond, Peter 1999. Water Users Association in Andrah Pradesh. Forth National Confernce on Participatory Irrigation Management, National Institute for Rural Development, Hyderabad. users groups covering the entire state's Figure 2\. Growth of Irrigated Area in irrigated area of 4.8 million ha. The Bank Sriramsagar Project assisted GOAP's lead, initially as part of preparation activities for AP III and latterly r ea (00 in the preparation of the AP Economic ha( Restructuring Project with timely inputs by 3 the WBI and the Participatory Irrigation 1 L Management Network. The Irrigation and Command Area Development Department has devolved contracting to the new water user groups and this, in the main, is responsible for the completion of secondary and tertiary irrigation that led to expansion of irrigated area. 1992-93 1993-94 1994-95 1995-96 1996-97 1997-98 1998-99 1999-00 But Fundamental Problems Remain 4.4 Participatory management, however, is only part of the sustainability equation provision of adequate and timely funding for operation and maintenance continues to be a problem. Despite a three-fold increase in irrigation charges in 1997 and the formation of water users' groups, the share of cost recovery through users' fees has declined from 4% of total expenditures in 1994-95 to 1.8% in 1999-2000. Worse, a recent expenditure review of the irrigation sector shows that typically more than 80% of the AP's Non-Plan expenditures on Major and Medium Irrigation that is supposed to cover operation and maintenance expenditures is being spent on interest payments against borrowings to finance capital expenditures.26 And within the overall total expenditure, about 57% is spent of staff costs and interest payments, only 43% on works. Currently, ICADD has approximately 48,000 staff, comprising 8,300 engineers at all levels, 18,500 non-technical office staff and more than 21,000 lower-level staff. As the DFID report notes, the ICADD is in a debt trap. Despite this there is an ambitious program of 32 new medium schemes, 11 of which are under detailed investigation. In addition, 36 major, 42 medium and 636 minor irrigation projects are still under construction. 4.5 The current financial situation of the ICADD appears unsustainable. This could change if GOAP reduces the high overhead costs of the ICADD, curtails new commitments and implements proposals to make WIJGs financially autonomous (with the authority to collect irrigation fees and use them for operation and maintenance). Even though there has been impressive increases in the performance of the Sriramsagar project, and the pace of work to complete the Srisailem component has accelerated, their long term sustainability looks uncertain in the current budget setting. Lessons * Inadequate appraisal followed by unilateral design changes in mid-project risks conflict over unresolved issues and may lead to redundant investment. Most of the water allocation controversy that damaged the Bank's reputation for objectivity and jeopardized smooth implementation of the project could have been avoided. The key was realizing the 26. Aikman, Ian et al., 2001. Andhra Pradesh Impact and Expenditure Review Irrigation Sector Phase I Final Report to DFID. Babtie Group Ltd, Glasgow, UK for DFID. 27. Government of Andrah Pradesh. 1999. Swarna Andrah Pradesh Vision 2020. centrality of water allocation to project sustainability and resolving the issue with GOI and Government of Andrah Pradesh before the project started. * Consistent Bank management requires a balance between technical and country development aspects favoring one or the other creates problems. Good communications and timely, clear decision-making is a prerequisite. The poor Bank performance on AP II was eventually reversed with the appointment of a resident Country Director, the establishment of consistent Bank management of country programs, and the improvement of communications with GOI and state governments. * Large-scale water development projects need to be designed within a river basin framework considering all water users to ensure efficient and effective water allocation using appropriate public and private sector instruments. * Lack of sound operational plans, poor water management and inadequate feedback from monitoring and evaluation have large economic, financial and social costs.
P009860 | WTRSH PLAINS | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1990 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/292791475088097932/text/000020051-20140528121051.txt | http://documents.worldbank.org/curated/en/292791475088097932/pdf/000020051-20140528121051.pdf | (1) A watershed or sub-watershed is a very practical unit within which to plan and implement natural resource management projects in rainfed areas. Managing water -- the most basic natural resource in a watershed -- not only provides a practical framework for project implementation, but also a focus for the collective efforts of the village communities living in the watersheds.(2) Ownership of the project by beneficiaries is essential for a successful outcome and for long-term sustainability. To achieve ownership, the project must pro-actively provide training in participatory methodologies for both project staff and beneficiaries. (3) It is important for the services of different government departments (in this case, soil conservation, forestry, agriculture, horticulture, and animal husbandry) to be provided in an integrated way. For this to continue beyond the life of the project, this requires the development of new organizations (such as village development committees) and of permanent institutional arrangements among government departments, local governments, and the village development committees that create the incentives for this integration to continue.(4) In order to receive the beneficiaries' support for long-term conservation objectives, it is also important for the beneficiaries to realize some short-term benefits from the project's interventions.(5) During project implementation, it is very important to have feedback mechanisms, such as the midterm review, to effectively evaluate and reflect upon the progress of the project, and then to make the mid-course corrections that become necessary.
P009860 | WTRSH PLAINS | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1990 | 1999 | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/127781468750007616/text/multi-page.txt | http://documents.worldbank.org/curated/en/127781468750007616/pdf/multi-page.pdf | 7. Lessons The following are the principal lessons arising from these two projects\. (1) A watershed, or sub-watershed, is a very practical unit within which to plan and implement natural resource management projects in rainfed areas. Among the diversity of natural resources in a typical watershed, from forests to annual crops and pastures, water is the most basic natural resource upon which all other life depends. Managing water in a watershed not only provides a practical framework for project management, but also a focus for the collective efforts of the village communities living in the watersheds, since improvements in the availability of water have the most immediate impact on the quality of their lives. (2) Ownership of the project by the beneficiaries is essentialfor a successful outcome andfor long-term sustainability. This requires a change of perspective, particularly on the part of project staff, as well as training in participatory methodologies. Both project staff and beneficiaries need to view their working relationship as a collaborative partnership. Interventions need to be demand-driven by the beneficiaries within the supply framework provided by the project. (3) It is important for the services of the different government departments (in this case, soil conservation, forestry, agriculture, horticulture, and animal husbandry) to be provided in an integrated way. For this to continue beyond the life of the project (which in this case occurred within the context of project teams), this requires the development of new organizations (such as village development committees) and of permanent institutional arrangements among government departments, local governments, the village development committees, and individual farmers, that will not only facilitate but also create the incentives for this integration to continue. (4) In order to receive the beneficiaries' support for long-term conservation objectives, it is also important for the beneficiaries to realize some short-term benefits from the project's interventions. This means working closely with the beneficiaries in order to understand their varied sources of income and their most immediate needs, and then modifying the standard technical solutions, where necessary, to accommodate the long-term development objectives to these short-term needs. (5) During project implementation, it is very important to have feedback mechanisms such as the midterm review, to effectively evaluate and reflect upon the progress of the project, and then to make the midcourse corrections that become necessary. The midterm reviews were a crucial, soul-searching period for both the Hills and Plains projects. These led to major, project-saving changes in the implementation of both projects in order to enhance the demand-driven nature and increase the degree of local ownership of the project's investments.
P009869 | Nathpa Jhakri Power Project | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1989 | 2002 | 2003 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/132071474576793877/text/000020051-20140607164714.txt | http://documents.worldbank.org/curated/en/132071474576793877/pdf/000020051-20140607164714.pdf | 1) The project provides lessons on how not to design and implement a project. While there were efforts both from the Bank and from the government to resolve design deficiencies during implementation, the problems were too numerous to be surmountable. The government's inability to act decisively on major project issues, and by force majeures, worsened the problems. 2) Securing broad based commitment from key stakeholders in government is an important element in ensuring timely completion of projects. This process involves dialoguing and agreeing with government prior to appraisal on key institutional issues such as staff composition and recruitment, delegation of authority, and key accountabilities and responsibilities of various key agencies involved in the project. 3) To ensure satisfactory compliance to safeguards policies, the Bank needs to secure commitment from the Borrower at the early stage of project preparation, and provide technical support in undertaking social and environmental impact studies and in developing mitigating measures.
P009870 | CONTAINER TRANSPORT | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1994 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/857481474489207433/text/000020051-20140607151015.txt | http://documents.worldbank.org/curated/en/857481474489207433/pdf/000020051-20140607151015.pdf | Pilots to test new technologies are important, are key to modernizing operations, and must be carefully designed. Their preparation should not be overlooked because they are just 'pilots'Bidder qualification criteria need to be strict and specific to the conditions of the bid, especially when bid conditions are similar but not identical to previous bids. For example, IR/CONCOR used to provide bidders with engineering designs for the equipment, and therefore suppliers needed not have engineering capability. In bids under the project, suppliers were required to provide their own engineering designs, for which local suppliers were not prepared and yet were considered to be qualified.
P009872 | TAMIL NADU URBAN | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1988 | 1998 | 1998 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/652981475110324972/text/000020051-20140519063342.txt | http://documents.worldbank.org/curated/en/652981475110324972/pdf/000020051-20140519063342.pdf | The project's scope should be less ambitious and much simpler given the constraints on the borrower's institutional capacity and the Bank's resources. The continuity of the Bank's core project team during the project cycle (from preparation through supervision) contributed to the successful implementation of the project.
P009872 | TAMIL NADU URBAN | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1988 | 1998 | 2008 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/123341468260075752/text/39929.txt | http://documents.worldbank.org/curated/en/123341468260075752/pdf/39929.pdf | 5. Lessons The TNUDF model i s a viable and effective model for financing urban infrastructure investments, capable o f being replicated elsewhere in India. But as the model will have limited success in the absence o f ULB capacity, i t should be replicated w i t h the design features which were most successful in improving ULB capacity, namely the grant fund for project preparation, and encouraging the development o f close working relations between ULBs and Fund, especially as a source o f easily accessible technical expertise. Priority infrastructural needs o f the urban poor are often not the same as that o f the urban population as a whole. The financial intermediary approach will have limited success in addressing the basic infrastructure needs o f the poor unless the there i s a delinking between subproject financing method and the expected (monetary) returns. The experience o f these two projects shows that there are strengths and weaknesses in both the financial intermediary approach and the direct provision o f infrastructure approach. W h i l e the first i s clearly more efficient, the second i s often better able to meet the needs o f the poor. Efforts should be made to find the right balance o f these two approaches, o n the one hand by targeting grant funding mainly to meet the needs o f the poor and other market failure situations, and o n the other by encouraging financial discipline and a debt culture among ULBs. Cost recovery o f infrastructure investments from the poor should be w e l l thought out and implemented in a transparent manner. Attempting to recover the full cost o f infrastructure investments from the poor and strictly enforcing such cost recovery can have unintended negative impacts such as increasing their vulnerability to exploitation and abuse, for example by moneylenders. When such cost recovery mechanisms are implemented their design should include a dispute resolution mechanism that the poor can access. The Bank i s able to have a less costly but s t i l l relevant role in financing small city infrastructure needs when it i s able to hand over subproject supervision to an intermediary such as the TNUDF.,In such instances the Bank's role i s redefined as a provider o f policy advice through intellectual support and technical knowledge, a role which it performed w e l l in TNUDP-11. Projects need to develop meaningful M&E frameworks at design, which focus on the development impact, and with a definite baseline and targets to measure performance as well guide project implementation.
P009877 | DAM SAFETY | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1991 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/834271474419916130/text/000020051-20140528125830.txt | http://documents.worldbank.org/curated/en/834271474419916130/pdf/000020051-20140528125830.pdf | Future dam safety projects must aim at developing efficient investment allocation criteria that include benefit-cost analysis covering evaluation of population, economic assets and other resources potentially at risk.Dam safety projects must discriminate between investments needed to maintain structural integrity (i.e. deferred maintenance and the institutional issues that raises) and investments for new works to lower the environmental risk and improve flood forecasting and conveyance capacity.Innovative projects need thorough preparation, particularly of new institutions and organizations, and should be piloted first over 2-3 years before embarking on a major investment project.State's performance is only likely to improve when disbursement is linked to performance - this suggests that India may benefit from APL-type projects.Client satisfaction with Bank's performance does not mean that the Bank is effective in inducing sustainable reform, new institutions and higher levels of efficiencyIn-country ICR workshops provide invaluable feedback, information and raise awareness of development issues - they should be standard for all ICRs.
P009877 | DAM SAFETY | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1991 | 2000 | 2009 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/832621468267587078/text/486510PPAR0Ind1fficial0Use0Only1pdf.txt | http://documents.worldbank.org/curated/en/832621468267587078/pdf/486510PPAR0Ind1fficial0Use0Only1pdf.pdf | Lessons At its core, the project was aninstitutional developmentproject, even though 80% o fits cost went towards remedial works andbasic dam safety facilities. The key lessons from the project are\. Institution-building can be a longprocess when it involves organizations at multiple levels, establishing new work methods, and upgrading technical expertise. Insuch cases, the Bank should consider an extended commitment through a sequence o fprojects or through adaptable program lending. Institutionsthat carry out regulatory functions require technical expertise and adequate resources to be able to function ina capable and independent manner. Inthisproject, shortage o fexperiencedqualified staffandinadequate operating budgets contributedto the under-performanceo f the state dam safety organizations. When new monitoring andreportingprocedures are instituted, their purpose should bemade clear to all those involved, and appropriate and regular feedback should be given to those originating the data. Inthis project, there was little systematic analysis or feedback from higher levels on reporting emanating from the dam level, which may be affecting its quality andcompliance. New techniques and equipment should be tailored to the existing level o f capacity, facilities and funds for ongoing maintenance. A significant portion o f the relatively sophisticated instrumentationinstalled at dams under this project has deteriorated for lack o f maintenance or use.
P009882 | WTRSH HILLS | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1990 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/780681474419836800/text/000020051-20140528121001.txt | http://documents.worldbank.org/curated/en/780681474419836800/pdf/000020051-20140528121001.pdf | (1) A watershed or sub-watershed is a very practical unit within which to plan and implement natural resource management projects in rainfed areas. Managing water -- the most basic natural resource in a watershed -- not only provides a practical framework for project implementation, but also a focus for the collective efforts of the village communities living in the watersheds.(2) Ownership of the project by beneficiaries is essential for a successful outcome and for long-term sustainability. To achieve ownership, the project must pro-actively provide training in participatory methodologies for both project staff and beneficiaries. (3) It is important for the services of different government departments (in this case, soil conservation, forestry, agriculture, horticulture, and animal husbandry) to be provided in an integrated way. For this to continue beyond the life of the project, this requires the development of new organizations (such as village development committees) and of permanent institutional arrangements among government departments, local governments, and the village development committees that create the incentives for this integration to continue.(4) In order to receive the beneficiaries' support for long-term conservation objectives, it is also important for the beneficiaries to realize some short-term benefits from the project's interventions.(5) During project implementation, it is very important to have feedback mechanisms, such as the midterm review, to effectively evaluate and reflect upon the progress of the project, and then to make the mid-course corrections that become necessary.
P009882 | WTRSH HILLS | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1990 | 1999 | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/127781468750007616/text/multi-page.txt | http://documents.worldbank.org/curated/en/127781468750007616/pdf/multi-page.pdf | 7. Lessons The following are the principal lessons arising from these two projects\. (1) A watershed, or sub-watershed, is a very practical unit within which to plan and implement natural resource management projects in rainfed areas. Among the diversity of natural resources in a typical watershed, from forests to annual crops and pastures, water is the most basic natural resource upon which all other life depends. Managing water in a watershed not only provides a practical framework for project management, but also a focus for the collective efforts of the village communities living in the watersheds, since improvements in the availability of water have the most immediate impact on the quality of their lives. (2) Ownership of the project by the beneficiaries is essentialfor a successful outcome andfor long-term sustainability. This requires a change of perspective, particularly on the part of project staff, as well as training in participatory methodologies. Both project staff and beneficiaries need to view their working relationship as a collaborative partnership. Interventions need to be demand-driven by the beneficiaries within the supply framework provided by the project. (3) It is important for the services of the different government departments (in this case, soil conservation, forestry, agriculture, horticulture, and animal husbandry) to be provided in an integrated way. For this to continue beyond the life of the project (which in this case occurred within the context of project teams), this requires the development of new organizations (such as village development committees) and of permanent institutional arrangements among government departments, local governments, the village development committees, and individual farmers, that will not only facilitate but also create the incentives for this integration to continue. (4) In order to receive the beneficiaries' support for long-term conservation objectives, it is also important for the beneficiaries to realize some short-term benefits from the project's interventions. This means working closely with the beneficiaries in order to understand their varied sources of income and their most immediate needs, and then modifying the standard technical solutions, where necessary, to accommodate the long-term development objectives to these short-term needs. (5) During project implementation, it is very important to have feedback mechanisms such as the midterm review, to effectively evaluate and reflect upon the progress of the project, and then to make the midcourse corrections that become necessary. The midterm reviews were a crucial, soul-searching period for both the Hills and Plains projects. These led to major, project-saving changes in the implementation of both projects in order to enhance the demand-driven nature and increase the degree of local ownership of the project's investments.
P009885 | PETROCHEMICALS | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1991 |  | 1999 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/547171474665162222/text/000020051-20140519082559.txt | http://documents.worldbank.org/curated/en/547171474665162222/pdf/000020051-20140519082559.pdf | The major lessons are: a) subsector reforms are more likely to succeed when distortions of the economy are corrected; b) pricing covenants should always state the principles on which they are based and should provide for formal periodic reviews; c) all government approvals should become a condition for Board presentation; d) expansion investments should not be approved until the production in the existing plant has started; and, e) for expansion projects, direct contracting or possibly limited international bidding (LIB) procurement could be considered to accommodate the process licensors' recommendations and specific needs for standardization.
P009888 | POWER UTIL EFFIC IMP | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1992 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/190821474903397444/text/000020051-20140522102719.txt | http://documents.worldbank.org/curated/en/190821474903397444/pdf/000020051-20140522102719.pdf | Development outcome of Bank assistance to India's state power sector will likely be unsatisfactory unless sectoral issues on regulation, tariff, financial and reform are addressed through a full restructuring of the sector, which takes state governments out of the ownership of sector institutions, and includes privatization of distribution and establishment of independent generation companies. - Apex onlending institutions are a poor choice for supporting the state level sector reforms that are needed in the Indian power sector. These reform address a wide range of sector issues which can not be effectively handled through sub-loans from an apex lending institution. Bank lending activities in the power sector should focus directly on states which are in the process of implementing such reforms, and should not be used to support intermediaries which have proven to be ineffective in bringing about state reforms.- The focus on establishing acceptable financial rates of return, rather than income generating tariff adjustments, without taking into account its impact on broader issues of state resource generation and allocation is self-defeating. Without tariff adjustments, state resources are drawn from other important state development objectives, including education, health, and roads.
P009890 | HYDERABAD W/S | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1990 | 1998 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/993441474493053826/text/000020051-20140519083155.txt | http://documents.worldbank.org/curated/en/993441474493053826/pdf/000020051-20140519083155.pdf | The project provides a strong lesson on the importance of competent and committed senior management (including heads of various operational departments) supported by effective and timely staff training in the laying of a solid foundation for a newly established entity when at the same time a major investment program was being carried out.
P009895 | TECHNOLOGY DEVELOPME | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1990 |  | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/640601474945571500/text/000020051-20140519082346.txt | http://documents.worldbank.org/curated/en/640601474945571500/pdf/000020051-20140519082346.pdf | Timing is important; the project was implemented during a period of liberalization, when growing competition was forcing firms to improve their technologies and innovate. The project was a catalyst in accelerating the reform momentum.The strong, committed intermediaries were crucial to the success of this complex project.Flexibility in project design was important in allowing the project to respond to the changing economic environment.Strong financial incentives, along with consensus building and training, enabled technology institutions to change their attitudes and create new skills.The success of venture capital depends on the presence of a body of potential new entrepreneurs with advanced technological capabilities and experienced financiers, as well as a fairly efficient capital market.Private firms can be induced to enter technological collaboration with technical institutions through modest financial incentives if the scheme is administered by an intermediary with good business contacts and that understands technology; a private sector intermediary may be more effective than a government bureaucracy; universities offer enormous potential for technological collaboration.Continuity in Bank task management, including careful planning for a change in task manager, contributes substantially to successful implementation.
P009898 | UPPER KRISHNA PHASE | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1989 |  | 1999 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/664061475098717194/text/000020051-20140519074325.txt | http://documents.worldbank.org/curated/en/664061475098717194/pdf/000020051-20140519074325.pdf | The ICR lists a number of familiar lessons, especially in the context of this borrower, but the main lessons are: (a) the need for the Bank to restrict project designs to achieving realistic objectives to which there is real and substantial borrower commitment, rather than continue to approve operations which absorb large staff resources (48 SW p.a. in this case), and are costly in fees, as they struggle to an unsatisfactory conclusion. (b) the need for the Bank to adopt a basin-wide approach rather than supporting separate operations with competitive riparian authorities, and (c) on resettlement, income restoration is particularly difficult and takes much longer than relocation.
P009906 | INDUSTRIAL POLLUTION CONTROL | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1991 | 1999 | 2000 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/103691474895014969/text/000020051-20140528130936.txt | http://documents.worldbank.org/curated/en/103691474895014969/pdf/000020051-20140528130936.pdf | Lines of credit geared to environmentally related investment by private entities are likely to provide little assistance in achieving broader sectoral objectives.
P009906 | INDUSTRIAL POLLUTION CONTROL | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1991 | 1999 | 2007 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/371501468258578024/text/38472.txt | http://documents.worldbank.org/curated/en/371501468258578024/pdf/38472.pdf | 4. Lessons 4.1 The ICRsfor bothoperations contain a number of relevant findings and lessons, focusing on specific project design and implementation issues. The PPAR agrees with these observations, which will not be repeated here. Unfortunately, moreover, the ICR for PCP and MTRfor IPPPwere not carried out sooner, so that their lessons and recommendations could have been taken into account earlier inthe life of the follow-on operation. As a result, it experienced many o f the same design-related problems encountered by IPCP. This timing disconnect, while perhaps unavoidable given the Bank's (inretrospect, clearly premature) decision to press ahead quickly with the processing of IPPP, nevertheless suggests an important generic lesson\. theBank should not goforward with new (even complementaryfollow-on) projects that attemptto extendand/or replicatepreviously untesteddesign approaches when there has been insufficient opportunity to monitor, evaluateand learnfrom the implementation experienceand results of thefirst operation.Adequate monitoring and evaluation mechanismsare alsoparticularly important nder thesecircumstances. 1\. 4.2 A second lesson concerns the way the objectives of these projects were framed\. to support GO1efforts to prevent and alleviate industrialpollution and to promote cost-effective pollutionabatement from industrial sources. These are general objectives that focus on processes rather than concrete results interms of environmental q~ality.~'However, by expressing project objectives interms of support to processes rather than attainment of outcomes, there i s no incentive to buildin monitoring and evaluation mechanisms that focus on environmental results, without which it i s impossible to determine what the actual environmental impact of the actions taken has been. This was clearly the case with both IPCPand IPPP. To the extent possible, therefore, the objectivesof Bank-supportedenvironmentprojects should identifi upfront thespecific outcomes they seek to achieve in terns of improvements in environmentalquality. 4.3 Other general lessons which can be drawn from this experience refer to the approach to pollutionmanagement followed in IPCPand IPPP, which was clearly a partial one. While industrial pollutionwas an important contributing factor to overall air and water quality problems inIndia in the 1980s and OS, and the projects' focus on the most highly pollutingindustrial subsectors and establishments by targeting them and the states where they were primarily locatedwas not inappropriate, these efforts should have beenplaced in the context of more comprehensivenational and localpollution abatementstrategies, involving thefull range of contributing sectors (in all likelihood including urban sanitation, transport, energy and even agriculture, as well as industry) and suitableactions to address air, water?and land degradationproblems in a more spatiallyfocused way. 59. Many early Bank environment projects had similar objectives, so IPCP and IPPPare not unique inthis regard. 4.4 By not doing so, even though project environmental outcomes appear to have been positive, in that they did reduce emissions and effluent discharges by specific polluting industries, they may not have had a significant impact in terns of improving overall ambient air and water quality in the places where these industrialplants are situated!' This could havebeen the case either becausethe establishments involvedare spatially dispersed, becausenon-industrial sources of air and water pollution were not addressed at the same time at the same locations, or both. Inany event, no information was collected that would allow an assessment of these potentialimpacts on ambient environmental quality. 4.5 Inshort, these operations, with their exclusive focus on (in all likelihood, dispersed) industrial sources, may havebeen necessary, but not sufficient, to resolve broader air and waterpollutionproblems inIndia, even inthe specific localities where project-related investments were made. Nor i s information providedinany of the project documents (either ex-ante or ex-post) about the relative importance of industrialversus other sources of air and water pollution inthe specific localities where project interventions occurred. Hence, it is impossible to determinethe relativepriority of addressing industpial, as compared with other, sources of pollution at anyparticular locality, or more generally. Thisshould, infact, have been the startingpointfor Bank involvementin this regard. 4.6 By not taking an area-based approach to addressing pollution problems, the Bank missed an opportunity to implement one of its own specific recommendations following its assessment of GOI's EnvironmentAction Program in 1995. Why this disconnect occurred i s unclear, but it would appear that the staff assessingthe EAP and managing preparation of IPPPwere either not sufficiently in communication (or agreement) regarding how the Bank should approach pollution abatement in Indiaor that there was simply too much inertia inthe design o f TPCP that was carried over without much question into IPPP. 4.7 The approach to industrialpollution management through lPCP and IPPPwas also a partial one in that it did not incorporate thefull range of instruments which could have potentially been used to achieve pollution prevention and control objectives. The approach followed did involve a combination of carrot (i.e., effectively subsidized credit for industrialpollution abatement investments, grant financed Common Effluent Treatment Plants, demonstration projects, etc.) and stick (i.e., effluent charges, strengthening of SPCBs to enhance their capacity to enforce pollution control legislation and monitor industrial compliance). And the two acting together, particularly stronger enforcement on the part of environmental authorities, do generally appear to have had a positive result interms of reducingpollution inthe target industrialsubsectors, at least among the larger establishments. However, public disclosureof polluting industries, especially inthose cases where compliance problems persisted, could also have been used as a way of inducing offenders to adopt less pollutingand/or resource saving technologies and better waste management practices. This approach has proven highly 60. Or as the IEGICR review for IPCPput it lines of credit gearedto environmentaIIy related investment by private entities are likely to provide little assistance inachievingbroader sectoral objectives. cost-effective in other countries such as Indonesia and could also be particularly so in India given growing public awareness of the health and other costs associated with pollution, together with the increasingly proactive role of environmentalNGOs, the media ,and the court system. The associated lesson i s that Bankprojects seeking to improve the environment, whether in a single sector such as industry or more generally, should use all available means to achieve this objective. 4.8 Institutional strengthening of the State PollutionControl Boards was an important objective of both Bank operations. This i s apersisting need clearly recognized by the Boards themselves. More generally, institutional capacity buildingfor environmental management (as for many other purposes) tends to bea long-termprocess that requires continuous support. In this regard, the Bank missed an opportunity to be more helpfulto the SPCBs by not granting afurther extension at i! time when IPPP's implementation was clearly improving.62 This reportedly occurred becauseBank management was more concerned with removing an unsatisfactory project from its portfolio than continuing to support key client agencies when they were making increasingly good use of Bank assistance. The corresponding lesson is that inproject extension decisions, development effectiveness considerations should takeprecedence over internal Bank portfolio quality)' concerns. 4.9 Finally, inaddition to the need to approach pollution management challenges ina more holistic and spatially strategic way, a number ofprioritiesfor potential future Bank and/or other donor support were confirmedindiscussions with environmental authorities and other national stakeholders during the PPAR mission.63 These include\. Within the industrial sector, preventing and controllingpollutionfrom small and medium-scale establishmentsthrough better functioning CETPs and other means appears to be the principal on-going challenge, together with collection and disposal of hazardous waste.Both at the central and state government levels, GO1 recognizes the need to improve the design, implementation and operation of CEPTs, to focus more on smaller polluting industries, and to properly address hazardous waste issues from both bio-medical and industrial sources.
P009910 | FAMILY WELFARE TRG ( | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1989 |  | 1998 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/170071475089413639/text/000020051-20140519062336.txt | http://documents.worldbank.org/curated/en/170071475089413639/pdf/000020051-20140519062336.pdf | Where institutional capacity is weak, ambitious software components like development of a human resource strategy tend to be ignored. In such cases, an arrangement that allows for a longer term commitment with a series of smaller steps that have to be achieved before proceeding to the next step would be preferable. The recently approved Adaptable Program Loan would be a suitable vehicle. It also helps in such situations to make sure more conditions (e.g., adequate procurement and land acquisition mechanisms) are in place before negotiating the loan. But borrowers can help enormously by maintaining critical staff in position for the duration of the project so learning can take place and be applied. However, the project also showed that even weak administrations will improve when faced with the threat of losing funds.
P009921 | SHRIMP & FISH CULTUR | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1992 | 2001 | 2002 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/951211475100106294/text/000020051-20140602111838.txt | http://documents.worldbank.org/curated/en/951211475100106294/pdf/000020051-20140602111838.pdf | The ICR says that the three most important lessons were: (i) Government agencies should avoid direct involvement in commercial operations, focusing on regulatory aspects; (ii) The design complexity of projects should not exceed borrower institutions' and beneficiaries' management capacity; (iii) Aquaculture projects must be guided by appropriate policies and regulations, and supported by institutions capable of addressing the manifold social, technical and environmental problems they pose.
P009925 | TALCHER THERMAL | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1987 |  | 1998 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/772631475091534702/text/India-Talcher-Thermal-Power.txt | http://documents.worldbank.org/curated/en/772631475091534702/pdf/India-Talcher-Thermal-Power.pdf | (a) During Appraisal the Bank needs to make sure that demand projections are based on reasonable scenarios, to minimize the risks that new capacity will be utilized; (b) Contracts for coal supplies need to be designed on a arms-length commercial basis, and not dictated by central government institutions; (c) A complete survey of project affected persons in all areas to be acquired should have been implemented during the project design phase, and the resettlement schemes developed in consultation with the affected parties. The choice of the location for the resettlement colony should be integrated into the environmental assessment process; and (d) allowing oustees to chose their own land and location as a preference over relocation in resettlement colonies should be an option in public consultation and planning stages of resettlement programs.
P009932 | SECOND TN NUTRITION | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1990 | 1998 | 1998 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/844271475083700450/text/000020051-20140519063119.txt | http://documents.worldbank.org/curated/en/844271475083700450/pdf/000020051-20140519063119.pdf | The TINP model works to reduce severe malnutrition, but to make significant progress reducing moderate malnutrition it needs to be supplemented by a greater emphasis on improving home-based care and feeding of the youngest children, which requires more and better outreach, improved inter-personal communication skills, and community mobilization.The Bank needs to take a firm and timely stand in dealing with chronic and persistent problems that endanger the development objectives--for example the failure to undertake the mid-term evaluation survey in a timely way -- rather than wait in the hope that agreed actions will eventually be taken.
P009940 | POP. TRG (VII) | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1990 | 1998 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/828281474575170577/text/000020051-20140521041944.txt | http://documents.worldbank.org/curated/en/828281474575170577/pdf/000020051-20140521041944.pdf | Lessons of Broad Applicability.(a) Differences between statesâ€”in implementation capacity, governance, financial and human resources, and interest in the program must play a larger role in project design. (b) Monitoring, evaluation and feedback must be built into implementation proceedures. (c) Performance-based financing of recipient units (in India, states, which received funds for implementation of the national FW program) can be effective in improving implementation performance.
P009941 | MAHARASHTRA POWER | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1989 | 1999 | 2000 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/972011474484662483/text/000020051-20140522110058.txt | http://documents.worldbank.org/curated/en/972011474484662483/pdf/000020051-20140522110058.pdf | (a) Thorough preparation prior to appraisal, including a resettlement plan and the issuance of bidding documents are essential to avoid costly delays in project implementation;(b) A sustainable solution to the problems of the power sector at the state level requires action to address their root causes: - the politicization of decisions, high non-technical losses due to theft and the lack of a commercial culture. This can only be achieved by means of a fundamental restructuring of the sector rather than a revitalization of existing SEBs as previously attempted.
P009946 | NAT. HIGHWAYS II | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1992 | 2003 | 2002 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/826451474511932808/text/000020051-20140607145907.txt | http://documents.worldbank.org/curated/en/826451474511932808/pdf/000020051-20140607145907.pdf | Several important lessons are identified by the ICR. Three are repeated here: Readiness for implementation is crucial for completion of the project on schedule and achievement of its objectives. Actions that are critical for project implementation such as engineering designs/feasibility studies need to be completed before credit/loan effectiveness.Absence of Resettlement Action Plan prior to start of the project leads to poor implementation. A coordination committee consisting of members drawn from the project team, state, local authorities and project affected persons, might significantly contributes to the successful implementation of resettlement program.Multi-state projects with several implementing agencies result in high transaction costs and are very complex and require close coordination between national and state government agencies. Future transport projects should consider covering fewer states.The ES adds the following lesson - it is important to closely monitor the implementation of the resettlement program through the development of key monitoring indicators.
P009955 | UTTAR PRADESH BASIC EDUCATION | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1993 | 2001 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/186791474486568935/text/000020051-20140602103533.txt | http://documents.worldbank.org/curated/en/186791474486568935/pdf/000020051-20140602103533.pdf | Borrower ownership of a project is critical to successful implementation, particularly in cases of innovative and difficult projects. Continuity of competent staff is critical to the quality of implementation. - Educational research and monitoring helps schools improve, and projects should finance such activities at the level of local academic institutions. - The startup of complex investments takes time, and as much planning as possible should be done before funds start flowing. Often, projects are finished by the time quality-related inputs start becoming more visible in schools.
P009956 | ELECTRONICS | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1989 |  | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/682461511188983565/text/multi-page.txt | http://documents.worldbank.org/curated/en/682461511188983565/pdf/multi-page.pdf | 4. Lessons for Bank Interventions in TVET 4.1 The Bank's experience in India shows that it is possible to implement successful TVET projects. Contributing factors to the success are as follows\. * Government commitment, ownership, and attention to execution can make it possible to overcome the implementation obstacles of the very complex TVET projects. * In India, state-level execution authority and accountability proved more effective than national-level execution. Involvement of institution staff in a team approach would also increase effectiveness over a top-down order to implement. * Classroom delivery of TVET is often neglected in methodological terms, and structured textbooks may be hard to find. Projects must monitor instructional effectiveness rather than assume that it exists. * Training staff to maintain equipment is a viable and cost-effective means of maintenance provided parts are readily available and that staff have an incentive to carry out the work. * When multiple donors are involved in a sector, coordination becomes essential. Donor meetings should be held and expectations should be clarified. Disagreements among donors may adversely impact government programs.
P009958 | AGR.DEV.I (TN) | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1991 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977081474398394143/text/000020051-20140526223750.txt | http://documents.worldbank.org/curated/en/977081474398394143/pdf/000020051-20140526223750.pdf | (1) Achieving appropriate synergies between policy reforms, institutional development, and public investments is crucial for broad-based and sustainable rural development. In this case, a committed and determined state government provided both a coherent policy framework and decentralized execution to the lowest appropriate levels.(2) Economic and sector work, strategic planning, public expenditure reviews, and manpower reviews all provided a sound base for appropriate policy and project interventions. (3) For joint forest management involving both the state and local communities as equal partners, an appropriate legal framework is crucial. In this case, enabling legislation to operationalize the institutional arrangements for sharing of costs and benefits of community forest management was absent.(4) Eliminating the state's role in the marketing of plant protection chemicals removed a previous conflict of interest between the sale of pesticides and the promotion of biological pest controls, and has helped, along with effective agricultural extension, to institutionalize the IPM approach to plant protection.(5) The involvement of rural women in the operation and maintenance of handpumps has enhanced the sustainability of investments in rural water supply systems.(6) Undertaking baseline surveys and identifying monitorable performance indicators is crucial to measuring progress, or the lack of progress, in project implementation.
P009959 | RUBBER | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1993 | 2001 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/979021474627576107/text/000020051-20140602103720.txt | http://documents.worldbank.org/curated/en/979021474627576107/pdf/000020051-20140602103720.pdf | (a) Well functioning public institutions like the Rubber Board are an essential complement to (private sector) planters and processors, helping to create a business-friendly regulatory environment; (b) Preparation of projects involving credit lines should include careful investigation of the demand for credit, making allowance for adjustments to a progressively liberalizing financial environment; (c) Permanent crops such as rubber can provide major environmental benefits, by enhancing green cover, sequestering carbon, and reducing water runoff and soil erosion.
P009961 | UP SODIC LANDS RECLA | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1993 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/301151474849578123/text/000020051-20140604053618.txt | http://documents.worldbank.org/curated/en/301151474849578123/pdf/000020051-20140604053618.pdf | Several important lessons are identified by the ICR. Two are repeated here: (i) Project success is founded on a preparatory process that directly involves line departments and intended beneficiaries, allows ample time for preparatory studies, assimilates experience from similar operations, carries out pilot operations and allows for flexible implementation. (ii) Establishing a logical sequence of development activities is a key ingredient to success; in this case, the establishing of property rights and land titling provided the basis for assuring beneficiaries' involvement. Then, creating organizations of poor people followed by mechanisms for resolving technical problems and provisions of associated resources.The ES adds the following lesson: reclaiming sodic lands with sound land and water management policies through beneficiary participation is a challenging task that requires the cooperative effort of all the stakeholders--the communities, research organizations, NGOs, various government departments/agencies and grass root village organizations. The building of this kind of participation requires time, resources and explicit attention to incentives for the stakeholders--costs that need to be explicitly recognized and built into a project. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured.
P009961 | UP SODIC LANDS RECLA | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1993 | 2001 | 2004 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/877881468250246522/text/29124.txt | http://documents.worldbank.org/curated/en/877881468250246522/pdf/29124.pdf | Lessons 50. Four project-specific lessons are identified here. Lesson 1\.A holistic approach to sodicity requires not only remedial measures but also adequate attention to critical systemic issues. Failure to do so can undermine project sustainability. The focus o f the Up Sodic Lands Reclamation Project was on developing participatory models for large-scale landreclamation, and it didnot give adequate attention to critical systemic issues such as economic incentives for use and management o f water, resources for operation and maintenance o f drainage, tackling o f which call for policy reformmeasures. Adequate attention to these issues is critical to ensuring that need for large resources for remedial measures do not arise inthe future. This was also a serious shortcoming because the sustainability o f the reclaimed landis dependent on effective handling o f these systemic constraints. Lesson2\. It is important to plan and execute an evaluation of the pilot experience before a larger follow-on intervention is designed and approved. While this may lead to delays in the effectiveness of the larger project, it i s important to allow lessons of experience from the pilot to inform the design of larger interventions. Inthe caseofthe Sodic LandsReclamationProject, the pilot closed inMarch 2001 andthe follow-on was approved inDecember 1998 andbecame effective in March 1999. There was no time for the project team to step back and look at the experience o f the pilot and learn from it effectively. Lesson 3\. Ininnovative and complex operations like the Sodic Lands Reclamation project, where the long-run environment impact is not easy to forecast, its monitoring and evaluation should be given sufficiently high priority in project implementation. This requires not only identification of an appropriate systemas was done inthis intervention, but also a plan to ensure that observations are evaluated and feedback is effectively utilized. Though RSAC was strengthened, and a large amount o f data is being generated, it i s not being utilized effectively. Even ifRSAC was able to report changes in quality and quantity o f groundwater, the project didnot put inplace a plan o f action to deal with problems when they occur. Lesson 4\. Ittakes time to build a constituency for community participation, and project design must plan for it. The Bank's time bound approach to project implementation made it difficult for the relevant implementing agency to do justice to the critical process issues. Further, the socio-economic community context needs adequate attention as participatory processes can bring about complex and irreversible changes inthe social, economic and political fabric of society. Adequate attention needs to be given to incentives and returnsto farmers as individualsand as a group, bothduring implementationand inthe post-projectperiod. Eventhough the success ofthe Sodic LandsReclamationProject depended on adequate community participation, sufficient time andresources were not devoted to these issues inthe project preparation and implementationphase. Neither was M&Eofprocess issues giventhe attention it deserved. As aresult, community participation as actually implementeddifferedfrom what was envisagedby the project design. There are indicationsthat the approach to community participation as implementedinUP has created a sense o f dependency inthe beneficiary communities. Further,because the social conditions and the power relationsinthe village society were not given adequate attention, the gains to the poor were less thantheproject couldhavepromoted. The projectbenefitedthemeconomically, but gains to the richer sections o f village society interms o freinforcing their superior social position seem to have beensubstantial. Adequate attention to the heterogeneous nature o f village society and village power relations while promoting community participationwould have allowed the project to deal adequately with this issue. Only when farmers were assuredo f economic retums were they willing to devote their time andresourcesto projectactivities. Itisto thecredit oftheprojectteam that they recognizedthis early on and emphasizedsecuring landtitles for farmers before the reclamation efforts started. This created strong incentives for participationbyindividuals. However, the incentives for continued participationare not so clear inthe case o fvillage-level institutions created for project implementation. Memberso fWUGs and SICs had adequate incentives to function as a group while the project was ongoing. Onproject closure it i s not clear that the benefits o fcooperation are larger thanthe costs incurredinterms oftime spent in gettingtogether inregular meetings. Today, eventhough WUGs couldbe important to ensuringadequatemaintenance of linkand field drains, a large numbero f them have become dormant. The SICs similarlydo not have a well-definedrole to play onproject closure. Inthe case o fthe women's selfhelp groups, onthe other hand, the economic returns to the group memberswere substantial andthe benefits o f cooperation far outweigh the costs o f gettingtogether.
P009963 | POPULATION VIII | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1992 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/648731474576809757/text/000020051-20140607170845.txt | http://documents.worldbank.org/curated/en/648731474576809757/pdf/000020051-20140607170845.pdf | Effectiveness and sustainability of health projects targeted at urban poor will be enhanced by (among other things): Anticipating political and other events that could delay initiation and implementation, for example, by obtaining approvals and clearances before these events occur.Decentralization and involvement of local politicians.Involvement of female community volunteers and local leaders in planning and implementation.Involvement of private practitioners through use of incentives.Provision of client-friendly services at convenient locations and times.Use of user charges that take into accountability to pay. Collaboration and coordination with referral health services and other slum development programs.Careful attention to a focused set of interventions and messages based on sound communications research and identification of needs in order to generate demand.
P009964 | Haryana Water Resources Consolidation Project | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1994 | 2002 | 2003 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/414681475086967374/text/000020051-20140607152122.txt | http://documents.worldbank.org/curated/en/414681475086967374/pdf/000020051-20140607152122.pdf | Privatization of irrigation assets (through WUAs) can be successfully carried out even in South Asia, with its enormous inherited burden of inefficient government organizations and procedures; such WUAs may need continued nurturing after project closure.Borrower actions to improve water use efficiency, allocation between competing uses and management of water quality will only occurr under force major conditions.Where policy and/or institutional reform is a major project objective, the Bank should look for key actions to be taken prior to negotiations or Board approval rather than relying on a Letter of Development Policy; an APL might also be appropriate in such circumstances.
P009965 | PUNJAB IRR & DRAINAG | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1990 | 1999 | 2000 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/141201475079138585/text/000020051-20140522104946.txt | http://documents.worldbank.org/curated/en/141201475079138585/pdf/000020051-20140522104946.pdf | To attain satisfactory "quality at entry" the borrower must have a water resources management policy and strategy in place,as noted in ICR;When there is no strategy, more non-engineering inputs are needed during identification, preparation and supervision.Sustainable improvements in the productivity of irrigated agriculture require a participatory approach with farmers, the establishment of viable WUAs, and related measures for generating adequate and assured operation and maintenance funds from users.More effective interagency coordination (for instance obtaining prior Forestry Department authorization) will increase speed of implementation;Complementary agricultural inputs must be provided to maximize agricultural production.
P009972 | THIRD NATIONAL HIGHWAYS PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/402601475111954873/text/000020051-20140619091835.txt | http://documents.worldbank.org/curated/en/402601475111954873/pdf/000020051-20140619091835.pdf | In designing resettlement policies, it would be prudent at the outset, to try and harmonize the policies of the Bank and the Borrower. Introducing the Bankâ€™s resettlement compensation policy in India (which also has a national policy but provides different levels of compensation) may have introduced distortions that affected populations may perceive as unfair. The lack of clear, consistent contract management practices can lead to unnecessary delays in the implementation of physical works by the implementing agency.The project design should include measurable indicators for the institutional development to track the effectiveness of institutional development activities financed under the project. Transport projects involving central and state transport agencies require additional coordination and simpler implementation mechanisms to accelerate land acquisition, forestry clearance, tree cutting, utility relocation, etc. to avoid unnecessary delays. The Government and road sector institutions need to create incentives and facilities for systematic training to increase the number of qualified road engineers, and technicians. There is also a need for competent environmental officers, an important career track not yet widely recognized in the Indian roads sector. The current shortage of qualified manpower is out of phase with the enormous demand for large infrastructure projects. The lack of coordination among development partners can result in missed opportunities for meeting common objectives. Both the Bank and the Asian Development Bank apparently supported institutional strengthening of NHAI during the projectâ€™s implementation period but coordination of their efforts was not apparent in project supervision reports.
P009973 | STATE ROADS I | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1989 | 1998 | 1999 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/365121474596913153/text/000020051-20140522102210.txt | http://documents.worldbank.org/curated/en/365121474596913153/pdf/000020051-20140522102210.pdf | The ICR contains a good set of lessons, some of which are also noted below:- project readiness for civil works needs to be better assessed at appraisal, and should include explicit arrangements for land clearance and removal of obstructions from right of way-methods for allocating road maintenance funds (such as PMS) need to balance optimization aims with local capacity, the latter considering institutional, human resources, technology and availability of funding for financing recurrent activities.-introducing independent supervision requires concerted efforts by the borrower, that needs to accept the challenge to in-house supervision, the consultants, that need to anticipate and address problems and the Bank, that needs to follow the pilots closely and be flexible in resolving problems.
P009977 | ICDS II (BIHAR & MP) | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1993 | 2003 | 2004 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/645651474944588576/text/000020051-20140612064742.txt | http://documents.worldbank.org/curated/en/645651474944588576/pdf/000020051-20140612064742.pdf | Project preoccupation with quantity over quality prevents the redressing of structural problems (already identified from earlier nutrition projects and ICDS I) inherent in a large national program such as the ICDS. The settings, rules of the game and incentives for nutrition programs such as ICDS have to be changed to break the perpetuation of poor services at AWCs, i.e. de-emphasize food distribution/feeding; and emphasize comprehensive child growth and development through growth monitoring and effective counseling to mothers on feeding practices and prevention/treatment of childhood diseases.Shift ICDS program focus from inputs to outcomes, decision making and results; emphasize the need for and use of an effective M&E system to manage for results and assess outcomes.
P009979 | Coal Sector Rehabilitation Project | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2003 | 2003 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/258241474553461521/text/000020051-20140607150251.txt | http://documents.worldbank.org/curated/en/258241474553461521/pdf/000020051-20140607150251.pdf | Policy reforms that are complex and crucial to the success of a project must, at the least, be clearly defined in the SAR, and articulated in a formal Letter of Development Policy;Failure to complete necessary legislative actions ahead of loan effectiveness reduces the project's leverage, and undermines its chances of success;The Bank should not rely on studies and their expected implementation of their recommendations as part of conditionality; andDeveloping a consensus on contentious issues as part of large sector reform can be time consuming, and should not be underestimated.
P009981 | CEMENT INDUSTRY REST | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1990 |  | 1998 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/677941474484454991/text/000020051-20140519063425.txt | http://documents.worldbank.org/curated/en/677941474484454991/pdf/000020051-20140519063425.pdf | As indicated in para. 3 above, the project demonstrated the benefits of market liberalization for industrial growth and efficiency. The problem of power supply reliability that affected all companies furnishes further evidence that state-owned utilities, with inadequate rate structures impede industrial development.
P009982 | NORTHERN REGION TRANSMISSION PROJECT | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1990 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/766631475070197020/text/000020051-20140604042936.txt | http://documents.worldbank.org/curated/en/766631475070197020/pdf/000020051-20140604042936.pdf | The Bank should not support a loan to an inefficient public sector institution that is likely to have great difficulties in implementing the project. It should insist on institutional reform before it moves forward. At project appraisal, the Bank accepted the role the GOI wanted for NTPC -predecessor of POWERGRID- and found acceptable that project execution were assigned to NHPC and NRPC. Later on, when project implementation was stalled, the GOI had to restructure these institutions and create POWERGRID to get the project moving. This delayed process was detrimental to project implementation. The situation was reversed by transferring project execution to POWERGRID.
P009988 | Second Technician Education Project | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1991 | 2000 | 2001 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/601711474558404694/text/000020051-20140529070222.txt | http://documents.worldbank.org/curated/en/601711474558404694/pdf/000020051_20140529070222.pdf | Â· Government commitment, ownership, and attention to execution can make it possible to overcome the implementation obstacles of the very complex TVET projects.Â· In India, state-level execution authority and accountability proved more effective than national-level execution. Involvement of institution staff in a team approach would also increase effectiveness over a top-down order to implement.Â· Classroom delivery of TVET is often neglected in methodological terms, and structured textbooks may be hard to find. Projects must monitor instructional effectiveness rather than assume that it exists.
P009988 | Second Technician Education Project | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1991 | 2000 | 2000 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/682461511188983565/text/multi-page.txt | http://documents.worldbank.org/curated/en/682461511188983565/pdf/multi-page.pdf | 4. Lessons for Bank Interventions in TVET 4.1 The Bank's experience in India shows that it is possible to implement successful TVET projects. Contributing factors to the success are as follows\. * Government commitment, ownership, and attention to execution can make it possible to overcome the implementation obstacles of the very complex TVET projects. * In India, state-level execution authority and accountability proved more effective than national-level execution. Involvement of institution staff in a team approach would also increase effectiveness over a top-down order to implement. * Classroom delivery of TVET is often neglected in methodological terms, and structured textbooks may be hard to find. Projects must monitor instructional effectiveness rather than assume that it exists. * Training staff to maintain equipment is a viable and cost-effective means of maintenance provided parts are readily available and that staff have an incentive to carry out the work. * When multiple donors are involved in a sector, coordination becomes essential. Donor meetings should be held and expectations should be clarified. Disagreements among donors may adversely impact government programs.
P009989 | TECH EDUC I | South Asia | India | IBRD |  | Human Development | Education | IBRD | IPF | 1990 | 1999 | 1999 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/134411474594849942/text/000020051-20140522102043.txt | http://documents.worldbank.org/curated/en/134411474594849942/pdf/000020051-20140522102043.pdf | ICRIt is possible for even a very complex multi-state project to be successful with full ownership and commitment of the States along with policy support and critical technical assistance from the Center.With the current emphasis on decentralization, more Bank attention should be given to local implementers. Technical assistance should be provided by the Bank and the Borrower to these implementers at an early stage.
P009989 | TECH EDUC I | South Asia | India | IBRD |  | Human Development | Education | IBRD | IPF | 1990 | 1999 | 2000 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/682461511188983565/text/multi-page.txt | http://documents.worldbank.org/curated/en/682461511188983565/pdf/multi-page.pdf | 4. Lessons for Bank Interventions in TVET 4.1 The Bank's experience in India shows that it is possible to implement successful TVET projects. Contributing factors to the success are as follows\. * Government commitment, ownership, and attention to execution can make it possible to overcome the implementation obstacles of the very complex TVET projects. * In India, state-level execution authority and accountability proved more effective than national-level execution. Involvement of institution staff in a team approach would also increase effectiveness over a top-down order to implement. * Classroom delivery of TVET is often neglected in methodological terms, and structured textbooks may be hard to find. Projects must monitor instructional effectiveness rather than assume that it exists. * Training staff to maintain equipment is a viable and cost-effective means of maintenance provided parts are readily available and that staff have an incentive to carry out the work. * When multiple donors are involved in a sector, coordination becomes essential. Donor meetings should be held and expectations should be clarified. Disagreements among donors may adversely impact government programs.
P009990 | VOCATIONAL TRAINING | South Asia | India | IBRD |  | Human Development | Education | IBRD | IPF | 1989 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/672861475085028439/text/000020051-20140526220922.txt | http://documents.worldbank.org/curated/en/672861475085028439/pdf/000020051-20140526220922.pdf | Institutional capacity and authority must be carefully assessed during appraisal, particularly in areas of new lending, where agencies are unfamiliar with Bank regulations.Participatory approaches would have created training programs with greater local relevance. Beneficiary participation is very important, particularly when local labor markets are critical in project success.Preparatory work (such as land acquisition) should be completed before projects become effective.
P009990 | VOCATIONAL TRAINING | South Asia | India | IBRD |  | Human Development | Education | IBRD | IPF | 1989 | 1999 | 2000 | PPAR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/682461511188983565/text/multi-page.txt | http://documents.worldbank.org/curated/en/682461511188983565/pdf/multi-page.pdf | 4. Lessons for Bank Interventions in TVET 4.1 The Bank's experience in India shows that it is possible to implement successful TVET projects. Contributing factors to the success are as follows\. * Government commitment, ownership, and attention to execution can make it possible to overcome the implementation obstacles of the very complex TVET projects. * In India, state-level execution authority and accountability proved more effective than national-level execution. Involvement of institution staff in a team approach would also increase effectiveness over a top-down order to implement. * Classroom delivery of TVET is often neglected in methodological terms, and structured textbooks may be hard to find. Projects must monitor instructional effectiveness rather than assume that it exists. * Training staff to maintain equipment is a viable and cost-effective means of maintenance provided parts are readily available and that staff have an incentive to carry out the work. * When multiple donors are involved in a sector, coordination becomes essential. Donor meetings should be held and expectations should be clarified. Disagreements among donors may adversely impact government programs.
P009993 | PRIVATE POWER UTIL I | South Asia | India | IBRD |  | Other | Other | IBRD | IPF | 1991 |  | 2000 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/926011506446523541/text/multi-page.txt | http://documents.worldbank.org/curated/en/926011506446523541/pdf/multi-page.pdf | 5. Conclusions and Policy Lessons 5.1 The Bank did not object to the GOI proposal for switching the Dahanu plant from coal to natural gas when gas becomes available. But if this switch were to take place, the justification for supporting the investment would be destroyed, because the plant would no longer qualify as a least-cost generation option. The Bank needs to be sure that proposals for future actions that appear to be environmentally attractive are also realistic and economically viable. Bank appraisals should, therefore, include an economic evaluation of all proposed future changes in the way the project is to be operated. This evaluation would ensure that uneconomic options are not included in the project design just to make it appear more environmentally friendly than it actually is. The most economical solution for switching to imported gas would probably be to add gas turbine generators and convert the existing plant for use in a second-stage heat recovery boiler in a combined-cycle operation, and the Bank should encourage BSES to carry out a thorough feasibility study on this option. 5.2 The Bank's current policy of supervising projects only until the loan is fully disbursed and closed is inadequate to confirm compliance with the Bank's environmental guidelines. For projects where operating procedures can have a significant environmental impact, agreement should be reached during the appraisal process on the environmental monitoring data to be collected, verified by an independent environmental agency, and submitted to the Bank during the project's operational phase. The Bank should continue to review this data after loan closing, in the context of its country sector work program. Short, focused supervisions should be considered to verify the efficacy of the environmental agency's efforts. 5.3 The MPCB has failed to meet its obligations to supervise and report on the project's compliance with GOI environmental guidelines. The Bank should make implementation of environmental agreements a central issue in its ongoing dialogue with the national and local government, and should decline lending for any further environmentally sensitive projects where governments have not fulfilled their existing obligations. The Bank needs to be convinced that the GOM will comply with its environmental commitments before it agrees to any new projects in Maharashtra requiring similar environmental supervision and reporting commitments. 5.4 The social-action project component, which was intended to do something for the indigenous tribal population, lacked focus. Consequently, local expectations were raised, and then disappointed when nothing was accomplished. Social action programs should only be included in projects when there is an agreement on their specific objective. For the Bank, the primary objective should be to ensure that the standard of living of groups affected by the project would not decline. These groups need to be clearly identified, and an action program needs to be fully formulated before the project is presented to the Board.
P009995 | ANDHRA PRADESH STATE HIGHWAY PROJECT | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/435851474899130908/text/000020051-20140613030438.txt | http://documents.worldbank.org/curated/en/435851474899130908/pdf/000020051-20140613030438.pdf | Several important lessons are identified by the ICR. Five are repeated here for their broad applicability:Successful implementation of institutional reforms requires broader involvement of road agency staff and their acceptance of the reforms. The Borrower's commitment for the reforms should be carefully assessed and all crucial decisions should be ensured before a project starts. To ensure adequate focus on the reforms during project implementation, project funding could be divided into different phases, and each phase made contingent on progress with reforms/institutional development initiatives during project implementation, using measurable and agreed performance indicators.To ensure adequate enforcement of contract conditions by private sector consultants it is important to introduce a centralized system to share past performance (based on suitable rating criteria) of consultants and their staff amongst various road agencies.Capacity building for each contractor is critical. Training facilities for contractors staff, including construction workers and equipment operators should be established/strengthened. Also, training of contractors staff (preferably at the beginning of work) could be included as part of the contract. Progress milestones for road works should be fixed as percent road length completed or percent physical progress, instead of completion of a full road section if the same is unlikely to be fully handed over to contractor due to land acquisition and other problems.
P010001 | Private Farmer Support Project | Europe and Central Asia | North Macedonia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2003 | 2003 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/377721474556440261/text/000020051-20140612063039.txt | http://documents.worldbank.org/curated/en/377721474556440261/pdf/000020051-20140612063039.pdf | (1) It takes great skill to implement policy and institutional reforms where civil society institutions are weak and in the face of powerful minorities with vested interest in the old system. The project management team needs to be focused, flexible, and independent of day-to-day politics in order to do so.(2) The administration of competitive grants requires strong, independent supervision and regular auditing, since these are susceptible to inappropriate use, particularly in a society where academic, community, and institutional leadership is often traditional and inflexible.(3) Farmers' organizations must be built progressively upwards from the grass roots in a layered organizational structure -- from local to regional to national -- building leadership capacity along the way and avoiding elite capture at all points, particularly at the national level.
P010162 | MAHAWELI GANGA III | South Asia | Sri Lanka | IDA |  | Other | Other | IDA | IPF | 1981 |  | 2004 | PPAR | >=50 million & <100 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/227761468760785447/text/29489.txt | http://documents.worldbank.org/curated/en/227761468760785447/pdf/29489.pdf | 11. FindingsandLessons 11.1 Thayer Scudder and his associates intervieweda small sample o f Mahaweli settlers at repeated intervals between 1979 and 2001. As early as 1984, not long after Mahaweli 111beganto be implemented,they beganto have doubts that the program's potential would be realized\. At a time whenothers were emphasizing theproject's ongoing success, we were thefirst to inform the Minister that theAccelerated Mahaweli Program risked replicatingpoverty within the Mahaweli systems ...Ashis unoficial advisers we had to inform him of our belief that the settlement component of the country s largest ever project wasfailing. A shocked silencefollowed-the Minister's initial reaction being that ifsuch was the case he would have to resign. Since then our negative assessment intensijied and Vimaladharma and Wanigaratne 's recent survey hasfurther documentedsettler poverty and lack of multiplier effects.17 11.2 The reports by Scudder andhis associates were apparently not considered by OED's 1994 assessment, althoughthey are mentionedinOED's 1986reviewo f Bank assistance to Sri Lanka. The 2004 reassessment essentially reiterates findings that were made by Scudder and his Sri Lankan colleagues 20 years ago. To summarize, OED finds\. 17. Scudder, op. cit., 2003. Professor Scudder's colleague, Dr. Wanigaratne led OED's 2004 survey, using the same instrumentthey had employedpreviously. The development effectiveness ofthe Bank's overall support to the Mahaweli program-credits and loans approved between 1970 and 1998 totaling one-half o f US$l billion inreal terms-has beenextremely limited; The incomes o ffarm families settled inSystem C have declined inrealterms over the two decades or so since they were relocated; and the mean income level i s now below the absolute poverty line; partly for this reasonthere was muchlower than expected creation o f ancillary off-farm employment; The primary rationale for the program-rice import substitution-ceased to be tenable shortly after Mahaweli I11was approved (1981) owing to the halving o f world rice prices; restoring the economic viability of the Third Mahaweliproject hinged on diversifying out o f paddy-but neitherthe mindset ofthe MahaweliAuthority nor the broader policy environment were conducive to diversification, a circumstance that remains largely true today; and Although government sought to devolve part o f the responsibilityfor operation and maintenance on Farmer Organizations, these groups remain government clients and are not financially self-sustaining. 11.3 Many lessons may be drawn from the Bank's protracted involvement with the Mahaweli program. Many o f these lessons have beentaken into account inthe design o f more-recently prepared Bank projects. For example, there i s widespread recognition today that investmentsininfrastructure needto be accompanied by measuresto reform the policy environment andto strengthen institutions. Water needs to be pricedto reflect the growing (cross-sector) competitionfor supplies; and irrigationoperation and maintenance costs needto be recovered from users ifpublic schemes are not to be an excessive burden on the recurrent budget. 11.4 The following more specific lessonsmay be derivedfrom the ThirdMahaweli Project. First, rushing technical and economicfeasibility studies, or paying insufjcient attention to theJindings is likely to result in an unsatisfactoryproject outcome. Inthis case, the Bank felt pressuredto lend inorder to builda relationship with a promising new government. Consequently, not enough care was taken either to estimate or subsequently to contain the costs o f the proposed irrigation schemes. Important environmental considerations bearing on the preservation o f biodiversity and the management o f conflicts betweensettlers and wildlife were brushedunder the carpet. The long-term fiscal implications were downplayed and the inflationary impact o f project funding was not taken seriously enough. 11.5 Second, settlementprograms that do not select candidates withprevious farming experience and which do notprovide settlers withfull title to their land are not likely to prosper. This project, to date, has failed to deliver security o ftenure to farmers. Title was not given to the farmers out of apaternalistic concern that they would speculate withthe landratherthanfarm it.The importance ofsecureproperty rightswas less widely recognized in 1980when the project was appraisedthanit is now. Without title, farmers are not legally able to sell their plots and, ifthey sell illegally, are less likelyto recoup the value of investmentsthey have made. This discourages less successful farmers from selling upandimpedesconsolidation ofplots that are too small to beviable. 11.6 Third, using repeated interviews with a small number of households, supplemented by interviews with local leaders and community groups is an effective lowcost techniquefor tracking theperformance of rural developmentprojects. The work by Scudder and his Sri Lankancolleagues bear this out. Early on Scudder's approach was describedas controversial byBank evaluation expertsbecausethe small initial sample was opportunistic not random (based on who was available for interview-subject to certain screening criteria), and was maintained almost without rotation over several years. The Bank suggestedthat this approach was appropriate for highlighting problems to be further explored, butcould not beusedto draw reliable conclusions about anentire population. Itwas also suggestedthat the researchers' familiarity with the respondentsand the possibility that respondents would expect to receive help inexchange for information-might encourage respondentsto underreport their incomes.'* Nevertheless, at a cost o f only US$20,000-US$40,000 per survey Scudder and his colleagues were able to predict early on that the Mahaweli program would not fulfill its development objectives.
P010192 | FORESTRY II (TERAI) | South Asia | Nepal | IDA |  | Other | Other | IDA | IPF | 1984 |  | 2001 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/171801511185777228/text/multi0page.txt | http://documents.worldbank.org/curated/en/171801511185777228/pdf/multi0page.pdf | FINDINGS AND LESSONS Lesson 1 Achieving forest regeneration through community-driven development is only the first phase. An important second phase is to ensure equitable management and distribution of benefits. The Bank has been one of the largest donors in the forest sector in Nepal. Unlike most other donors, which have worked in a few districts at a time, it has been active in several districts at the same time. In addition, the Bank is active in several other sectors in Nepal. Hence, the Bank has a comparative advantage in addressing cross sectoral issues that affect the working of all departments. If benefits from community forestry are to go beyond simple forest regeneration and are to contribute to the development of Nepal, then it is essential that the country is provided support in dealing with the second phase challenges. Through its cross sectoral presence and the use of a combination of lending and non-lending instruments that it has at its disposal, the Bank could support the government's efforts in this direction. Lesson 2 Not all the challenges and problems in implementation of a program of community participation can be visualized upfront. Hence the importance ofan efficient monitoring and evaluation system to make mid course corrections as and when required. Timely diagnosis of problems can help countries resolve challenges more readily and efficiently. Failure to develop an efficient monitoring and evaluation system contributed to an inefficient use of resources in the Hill Community Forestry Project. Lesson 3 The dependence of the poor on forests is great and forest sector development should be a part of the Bank's poverty alleviation strategy in countries like Nepal. Hence, in addition to increasing/regenerating forest cover, development objectives should be framed at least partly in terms ofpoverty alleviation. Understandably, the substantial availability of grant resources from other donors has made HMGs' government reluctant to borrow Bank credit for the forest sector. However, given the importance of forest sector development to poverty alleviation, the Bank could 'push' for forest sector i;sues as a part of its overall poverty alleviation strategy.
P010209 | LEFT BANK OUTFALL DR | South Asia | Pakistan | Blend |  | Other | Other | IDA | IPF | 1985 |  | 1999 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977591474491261482/text/000020051-20140519065151.txt | http://documents.worldbank.org/curated/en/977591474491261482/pdf/000020051-20140519065151.pdf | (a) major multi-disciplinary schemes of this type and complexity require a higher order of preparation and detailed planning than either the Bank or borrower were accustomed to at the time; (b) in the interests of efficiency and cost containment the Bank needs to take early and determined action to resolve problems on slow moving projects; (c) complex engineering/social programs need careful analysis of institutional capabilities and risks as critical inputs to realistic scheduling, and some contingency time built into the program.
P010277 | HIGHWAYS IV | South Asia | Pakistan | Blend |  | Other | Other | IBRD | IPF | 1987 |  | 2000 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/590051509569084658/text/multi0page.txt | http://documents.worldbank.org/curated/en/590051509569084658/pdf/multi0page.pdf | 6. Lessons Learned and Recommendations Lessons Learned\. Technical Assistance 6.1 Approach to TA. When the implementing organization is competent and has freedom to act, a content-oriented approach to technical assistance can be effective on well-defined institutional issues. For example, institutional development took place in NHA, but the gains were limited to the problems tackled and important issues went ignored. When issues are complex, as they nearly always are, and even if the organization is competent, process consulting is indicated in TA because the relevant information, a correct diagnosis, and appropriate interventions can only be achieved if the client is fully involved. This was approximately the case with KPT. 'Doctor' consulting failed regardless of client capacity and is, therefore, rarely indicated. 6.2 Theory of technique. Looking at TA and country's development needs broadly, the Bank needs to evolve and codify a new way of working with the client in change process. This could be called 'theory of technique'. 21 The delays with the action plans, ineffectiveness of TA, or undesired effects and side-effects due to errors of omission and commission, are indicative of insufficient understanding of the client's problems (also by the client) or of conceiving them too narrowly. It is necessary to structure the Bank-client relationship-itself an intervention-in a way that involves the client in defining the problem, studying it, and developing interventions that are genuinely relevant to the client's needs.22 6.3 Project concept. Approaches to improving service delivery organizations as government departments do not work. The extensive efforts in this and predecessor projects, and numerous projects elsewhere, demonstrate that improving the performance of a parastatal organization needs to culminate in its privatization-the quicker the better.23 Sustainability is ensured only when there is competition, accountability, and incentives to go after, be responsible for and keep the benefits from productivity improvements. NHA, KPT, and PR are concrete examples. Recommendations 6.4 Roads are still unsatisfactory in Pakistan. NHA is a competent agency, but the institutional and policy framework (for definition see footnote 17) within which it operates prevents it from making good decisions. PR infrastructure, operations, services, and planning are affected by misaligned institutional incentive structures, unclear contractual relationships, lack of 21. In a recent Bank-sponsored seminar, Douglass North named learning about and understanding of the 'change process' to be at the cutting edge of development theory. 'Theory of technique' is a more appropriate term because it runs through all the activities from data collection to monitoring results and implies that change process is not only observable but also can be influenced. 22. It is suggested here that working with the client using correct theory of technique is the critical factor in development and change, and for scaling up. Quick fixes such as new instruments [from innovation market place I to eradicate poverty or cause behavior changes will not work alone. 23. The 'end game' would need to be different for individual sectors\. full privatization for railways; a landlord port role for Karachi and Qasim; and an autonomous NHA (and provincial road agencies) with private sector service delivery for most operations. managerial independence, and unfunded service obligations. Trade facilitation, including customs, excess labor, and private sector participation persist as concerns for KPT. The Bank should continue to work with the GOP in the road and port sectors and begin anew in rail and provincial and rural roads. Among the priority issues to be addressed in the transport sector are\. * Definition of the roles of the sectoral institutions. Several entities-MOC, NHC, NHA, MLG, C&WD, MOR, PR-have an important but overlapping roles, or cooperation between them is arranged through ministerial committees. The institutional responsibilities need to be thoroughly studied and intersectoral decisionmaking clarified. * Sectoral performance indicators. The paradox that projects are satisfactory but the program fails to achieve desired outcomes applies in Pakistan. It must be faced squarely. One important way to do so is to develop sectoral performance indicators, both quantitative and qualitative, that can be used to identify needs, evolve project concepts, and broadly gauge movement toward desirable ends. The indicators should have a view toward the sector's graduation, that is, to overcome dependency on aid and begin independent functioning. * Privatization and pruning ofPR, now. The matter has been studied sufficiently. Pro; --s consulting is indicated to involve the government, the private sector, PR, other affectea interests, and civil society to register and monitor their points of view and concerns so that a realistic privatization model and rail track abandonment can be pursued. * Development of a policy framework for roads, and progressive commercialization of road administrations'service delivery. There should be a management umbrella, with appropriate road-user representation, on the roads managed by the five organizations, MOC, NHC (if its existence is justified), NHA, C&WD, and MLG so that investment decisions are consistent. regionally fair, adequate resources are allocated to construction, maintenance and oper2tior and that intersectoral and equity considerations are taken into account. * Further commercialization ofKPT. KPT management should vigorously pursue the landlord port concept and adopt commercial management principles in all its operations and asset management-the container and bulk cargo ports, real estate assets, and so forth, and revalue assets continuously. With regard to labor, KPT should continue to improve its labor productivity without abandoning social responsibility. * Shared power. Current transport sector institutions lack sufficient communication with important sectoral actors. Increased partnering should be sought with the Ministry of Petroleum and with government and nongovernmental environment bodies on clean fuels and other environmental matters; with local universities and research institutes (e.g., in pollution control, traffic safety, management systems, data analysis, and training courses for these activities, etc.); with user groups (e.g., regular meetings and joint training activities with the trucking association, other road users, the shippers council, the police regarding enforcement and traffic safety, axle-load control, regulation, etc.); and with the private sector (land use, economic development, trade facilitation, contracting and consulting industry practices, etc.). 6.5 Four technical content issues require urgent attention\. * Development of data services and completing the management systems. The availability and application of compatible data and road management systems in NHA and C&DW is necessary. There also is a need to improve current data services, with regard to traffic counting, axle loads, road condition, and cost and price information. * Human resources development. NHA, KPT, and PR have capable professionals. These technical skills must be maintained and updated by continuous training and by creation of an institutional environment and practices that value and reward technical and professional excellence. A twinning partner would be highly desirable for NHA and KPT. Training of management at all levels is also important. This probably is best done in the context of eventual studies on sectoral organizations and the policy framework because the evolving partnerships and organizations require interpersonal skills and decisionmaking capability. * Environment and traffic safety. Comprehensive programs in environmental protection and pollution control, traffic safety, and axle-load control need to be developed in NHA and C&DW. * Functional and administrative classification of roads. Size of the network. The modernization and expansion of the NHS and of the provincial road network necessitates a review of the classification of the entire road network. The size of the network is also an important issue. Some suggest that Pakistan's road network length is adequate and focus should now be on maintenance. This claim should be examined carefully. Resolution of this issue has implications for funding of all the roads.
P010280 | PRIMARY EDUC. III | South Asia | Pakistan | Blend |  | Other | Other | IDA | IPF | 1987 |  | 2000 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/715011511188765513/text/multi-page.txt | http://documents.worldbank.org/curated/en/715011511188765513/pdf/multi-page.pdf | 5. Lessons 5.1 Several lessons are worthy of broad dissemination. The audit points to areas of Bank performance where changed behavior would help ensure that only those projects in social sectors that meet high standard of efficacy in advancing development objectives are selected. In cases similar to PEPIII, extremely difficult and complex issues in the country and in education systems challenge the Bank to exercise discrimination in deciding whether projects-however relevant 8. Pakistan Education\. Issues for a Divisional Strategy. January 31, 1996 (revised July 18, 1997). 5.2 and responsive-should receive IDA financing-and if they do, how performance issues should be addressed. * IDA financed the Pakistan Third Primary Education Project in FY87 in response to the Government of Punjab's request after the province had declined to participate in PEPII approved the previous year. Total estimated cost was US$233.91 million and the IDA credit was US$143.35 million. This audit was closed in FY96 after an extension of 30 months. Based on a single province, the project set the pattern for four similar operations in the 1990s. From 1994, the first Social Action Program Project (Cr. 2953), the pioneer of IDA-assisted programmatic operation in Pakistan, also supported primary education with policy, budgetary and management interventions. * Objectives were relevant to the Bank's mission to reduce poverty and to the goals of the federal and provincial governments to improve educational quality, access and equity, especially for girls and rural populations. The project supported activities to\. develop institutional capacities; develop and institutionalize policy; and introduce innovations that would influence demand, access, quality and costs. It supported a large school building and maintenance component; a large study program to advance national and provincial policy and innovation strategies; and new forms of curricula, assessments, in-service teacher training and more affordable textbooks. CIDA was to have financed textbook paper and community participation components but the agency withdrew following differences of view on changes in design and scope. * The Implementation Completion Report shows that implementation was slow and achievements were far below expectations. It attributes the project's failure to meet its objectives to the extremely challenging environment, weak borrower commitment and capacity, delays and problems with TA from non-IDA sources, deficient preparation, and the lack of flexible lending instruments. The ICR is thoughtful in its analysis of the issues but, while it comments on some deficiencies in Bank performance at appraisal, some important gaps in reporting bias the ICR's overall evaluation in the Bank's favor. * The weight the Region gave to relevance and responsiveness in justifying the project was disproportionate to implementation realities. The concerns voiced internallyconcerns about project size, complexity and risks-were overshadowed by the IDA strategy to support basic and girls education in a poor but strategically important country. OED concurs with the Region that weaknesses in borrower commitment, capacity and institutions (weaknesses identified in internal reviews) should have been more carefully appraised. The Bank's decision to go ahead is a concern because staff considered the project unready for implementation and of high risk. The ICR argues that the investment instrument was not a sufficiently flexible instrument to overcome problems but, in fact, during preparation, more flexible instruments were considered. Staff proposed tranching disbursements based on satisfactory borrower performance but (the proposal) did not go forward after internal review. Instead, in final form, the legal agreement signed by federal and provincial governments included annual reviews of a mandated action program that would allow the Bank and borrower to adjust implementation mechanisms as needed. However, the Bank compromised its capacity to supervise implementation from a position of strength by making concessions to the borrower's objections to legal conditions at appraisal, at negotiations and at credit effectiveness. Supervision was further compromised because of Bank staff turnover, lax monitoring of compliance with the legal agreement and patchy supervision of technical components. The ICR points out that the components chosen to achieve project objectives were insufficiently prepared and tested. An example is the phased approach to the policy studies program which proved ineffective. However, the ICR fails to question why the Bank had allowed these activities to continue so long without restructuring the component. The staff argued that the project's emphasis on policy became less important relative to the huge investment in school construction activities. But this does not justify the lack of proactivity in revamping a costly component and redefining project objectives. * The Bank failed to attend sufficiently to the incentives and linkages inherent in the education system. In introducing an innovation to employ low-cost assistant teachers, many of them women, the Bank took a risk to advance an important initiative but failed to address the lack of policy, institutional and cultural supports in this area. In establishing independent management of primary education, it ignored the tight structural links that bind primary education to more advanced levels and require coordination. In addressing challenges of project size and complexity, it decided that the assessment component was the most likely candidate to drop. Unfortunately, this was a key to incentive for teachers and students to adopt the new curriculum. In delinking issues of teacher employment and teacher pay at the borrower's request, the Bank side-stepped critical issues of teacher management and high recurrent budgets for teacher remuneration. * A fundamental flaw exacerbated these weaknesses-the absence of clear policies and procedures agreed between federal and provincial authorities to govern their authority and responsibilities. Punjab's vision of greater autonomy promoted local ownership and effort, which the Bank supported. But the province was limited by federal laws, policies, budgets and control of project funds. The lack of clarity and resulting tensions adversely affected project coordination and implementation. The project found itself entangled in a much broader issue for federal-provincial relations than it was able to handle. * The audit reaffirms the conclusions of OED's previous review of the Region's ICR. The main disagreement is on Bank performance which OED rates as unsatisfactory (ICR unsatisfactory only at appraisal). The Bank used poor judgement in recommending the project as ready for IDA assistance when it considered the risks insurmountable. During supervision the Bank failed to ensure that project resources were used efficiently or to take remedial action when they were not. OED agrees with most other ICR ratings. Outcomes are rated as unsatisfactory because many components were not implemented and those that were implemented did not achieve targets set or results intended. Institutional development is rated as negligible and borrower performance as unsatisfactory. OED rates sustainability as unlikely (ICR uncertain) because the government's plans for future project operation are unformed and under-funding of recurrent budgets continues. Perhaps the most positive result for the Bank from the project's serious shortcomings was that it reinforced the need for a new strategy for social sector development in Pakistan. Several lessons are worthy of broad dissemination\. * When a project proposal has serious flaws, the Bank should not proceed under the assumption that trouble-shooting action during implementation will be effective or without cost. If the view is that more preparation would be unlikely to improve implementation readiness, as in the PEP III case, the project should not go forward for Board approval. Experience shows that turnaround is difficult to achieve during implementation without major review and borrower commitment to restructuring. * Relevance, responsiveness and high levels of investment inputs do not ensure good progress and results. In the PEP III case, the project's relevance to the Bank's mission in poverty and basic education, and its responsiveness to the Punjab's request IDA assistance, were necessary but not sufficient conditions for success. * Rigorous appraisal of the borrower's statement of commitment and capacity are required to inform project design. Experience in Pakistan indicates that government habitually overpromises and underperforms. This is a Regional insight with which OED concurs. * OED supports the ICR's insight that policy is not advanced when the Bank provides financing for large investment activities before the borrower has begun to improve the enabling environment. When budgets are tight, institutions are weak, and ownership uncertain, investment activities such as the large school construction component in PEPIII, are likely to attract most attention, reducing the focus on policy and qualitative outcomes. * When the Bank favors a shift to decentralization of education, it should avoid championing the stakeholder who is the major beneficiary while failing to ensure that other stakeholders' concerns are adequately addressed. In retrospect, it is clear that the Bank's implicit strategy in favor of the province was ill-prepared, a consensus among stakeholders was absent, and the Bank found itself uncomfortably placed to advance the project. * Rigorous self-evaluation and disclosure helps foster confidence among stakeholders, partners and Bank staff that the institution is directing scarce IDA funds to interventions that have been carefully selected because they will directly benefit the poor. In the PEP III case, the Bank could have done better in balancing risks and benefits by additional high quality review of technical and institutional components prior to Board presentation. During implementation, Bank managers need to encourage staff and government officials to review all objectives and components realistically and candidly and not to hold back from advising on drastic remedial action when appropriate, even if that means restructuring or cancellation. In primary education which is localized, yet geographically dispersed, support to the many related local institutions with diverse specialized functions is critical but difficult to achieve. The Bank is now doing more to foster strong institutions at national level but it also needs to foster education sector institutions locally. While it may lack the capacity to do this directly, it is well positioned to achieve partnership with locally-based change-agents to help sector institutions learn by doing. Bank Response * The subsequent round of IDA-funded projects have remedied some of the deficiencies noted in the Audit Report and ICR, but some persist. Those that continue to negatively affect Pakistan education Projects include\. overly ambitious agendas that do not satisfactorily take into account deficiencies in the technical and institutional capacity of the client; the difficulties for maintaining a consistent policy dialogue in the face of frequent changes of government and key policy and technical staff; creation of enabling environments that are based on long-term government vision of sector reform and growth; and construction efforts still plagued by delays, poor quality and governance issues despite substantial efforts by Bank staff to remedy these problems. * However, the provincial projects formed in the wake of PEP III, including the 2nd Social Action Program Project, have profited from the PEP III experience. Specific actions and activities reflected in these projects include\. * Focus on province-based initiatives that are largely independent of federal regulatory frameworks and interference except where mandated by law (e.g. curriculum content); * Emphasis upon annual Operational Plans and budgets to ensure that government monitors its own progress against stated and agreed annual goals; * Broad consultation with stakeholders in project design, down to the school and village level; * Use of sector focus to ensure integration of instruction and infrastructure into a continuous cycle of schooling; * Insistence that the client initiate requests for development assistance and that the client take lead responsibility, with IDA technical support as required, in defining project elements and modalities; * Expanded network of stakeholders and institutions involved in project implementation including district level officials, community level organizations including PTAs and head teachers; * Decided shift away from large-scale projects with heavy emphasis on construction to policy and reform-based lending that is linked to specific outcomes such as enrollment increases, improvement in student performance, teacher attendance, and transparent adherence to governance criteria; * Creation of non-line agencies to implement projects only where no capacity exists or intractable problems in the use of available agencies; * Reform of IDA-funded in-service teacher training efforts, with heavy emphasis on reduction in number of transfers and inclusion of teacher assessment of materials in design and production.
P010305 | PUNJAB URBAN DEVELOP | South Asia | Pakistan | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1988 | 1998 | 1999 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/773461474586187038/text/000020051-20140521033815.txt | http://documents.worldbank.org/curated/en/773461474586187038/pdf/000020051-20140521033815.pdf | Agencies responsible for O&M should, at a minimum, be involved in the project planning stages. Future project operation--including especially the financial and human resources for O&M--should be secured before implementation completion. While over-complex projects are to be avoided, the minimum necessary conditions for project success need to be identified during appraisal and taken into account when components are being designed: if uncollected solid waste is likely to block sewers and drains, ensuring collection prevents costly damage to expensively constructed roads and other infrastructure. Spot-checks of procurement practices reduce corruption, as does increased transparency (disclosing more information to the general public).
P010308 | SMALLHOLDER RUBBER R | South Asia | Sri Lanka | IDA |  | Other | Other | IDA | IPF | 1988 |  | 1998 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/319821475084433597/text/000020051-20140516154740.txt | http://documents.worldbank.org/curated/en/319821475084433597/pdf/000020051-20140516154740.pdf | Assumptions at appraisal on the interest of producers in forming groups for production or marketing purposes should be more closely scrutinized. It may be desirable for some more direct test of interest (e.g. shown by a more formal survey) to be required.
P010310 | MAHAKALI IRRIG. II | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1988 | 1998 | 1999 | ICRR | >=25 million & <50 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/675741475112146983/text/000020051-20140519083411.txt | http://documents.worldbank.org/curated/en/675741475112146983/pdf/000020051-20140519083411.pdf | Successful projects should be given time to develop as local growth centers for agricultural innovation and to allow evolution of private sector initiative.When projects share common resources (water, a DOI management unit) project appraisal should ensure that project expansion does not jeopardize the feasibility of, or administratively overload, the parent project.Timely M&E would have helped identify redundancies in project design (caused by private sector irrigation development) and restructuring of the project.Building the whole system simultaneously from head-to-tail risks too little and too late attention to developing water management and water users' groups, agricultural linkages, and maintenance. If physically feasible, irrigation project should be completed sequentially, section-by-section from head to tail, to enable a gradual build up to full operation, provide models for institutional development, and generate early benefits. It would also allow efficient downsizing as needed.
P010313 | PRIVATE SECTOR ENERGY DEVELOPMENT | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1988 | 1999 | 2002 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/445701475098754135/text/000020051-20140602104733.txt | http://documents.worldbank.org/curated/en/445701475098754135/pdf/000020051-20140602104733.pdf | Sector Reforms and IPPs: Private investment does not substitute for reform, and should not be attempted without at least the basic reform elements in place. Benchmark Pricing vs. Competitive Bidding: Competitive bidding for IPPs combined with incentives for providing least cost power could have resulted in lower trariffs, prevented too many and suboptimal projects being developed, and promoted transparency.Important Issues in Managing Large IPPs : These include: tailoring public financial support and guarantees to facilitate an efficient investment program; having an efficient fuel supply policy; allowing IPPs to procure fuels in competitive markets, both foreign and domestic; creating capacity to manage IPP contracts; and ensuring efficient plant dispatch. An option for gaining valuable experience without much risk is to begin with a small IPP.Due Diligence by Other Lenders: Risk mitigation measures provided in the security package may not be sufficient when the underlying economics are compromised by an unsound macroeconomic situation in the country.Procurement: International competitive bidding -- for IPP concession on basis of price -- leads to greater transparency, reduces the risk of corruption, and allows more flexibility for Bank financing.Contingent Liabilities: Where contingent liabilities are likely to be an important issue, a monitoring system -- perhaps at the Central Bank -- ought to be put in place.Covenants: Material covenants that may be difficult to enforce through measures such as suspension of disbursements could be designed as conditions of loan effectiveness, or other remedies designed according to the needs of the situation. At the same time, threat of suspension is not practical when it is applied to a private sector transaction i.e. the Bank cannot penalize the private sector for inaction by the government on an unrelated matter. On another count, the Bank should not encourage essentially commercial provisions such return on equity as part of the covenants.Corruption Allegations: It is difficult for the Bank to maintain an "honest broker" role in a complex project when different parts of the Bank Group often play conflicting roles -- IFC as a lender to IPPs seeking to mitigate its reputational risk; the Bank's Project Finance Group trying to mitigate calls to the Partial Risk Guarantee; and the Bank's macroeconomic team advising on the macroeconomic agenda. In dealing with corruption, the Bank should encourage the government and its agencies to pursue matters strictly according to law and internationally recognized due process, while honoring contractual conditions.Renegotiations: Renegotiations (or indeed any negotiations) will more likely result in prompt and mutually acceptable solutions when they occur in a commercial atmosphere, free of coercion.Mitigating Foreign Exchange Exposure: Financial stresses generated due to currency mismatch between liabilities and ultimate source of revenue (in this case domestic consumers) can be mitigated if the ultimate revenue source is linked wherever possible to foreign currency such as for electricity sales to export-oriented industries.
P010325 | KARACHI WATER & SANI | South Asia | Pakistan | Blend |  | Sustainable Development | Water | IDA | IPF | 1989 | 1999 | 2001 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/485521474569181329/text/000020051-20140529164445.txt | http://documents.worldbank.org/curated/en/485521474569181329/pdf/000020051-20140529164445.pdf | (1) Without a fundamental legislative and regulatory reform, including changed incentives and contracting of a private operator, the project was doomed from the start;(2) Financial covenants are ineffective if the water supply and sewerage authority is not given the authority and means to comply with them. In the particular case of KWSB, excessive politicization of the tariff settings and of the management added to the difficulties; (3) The project design should have incorporated more of community participation and especially so under the sanitation component where Karachi had gained valuable experience from the Orangi sanitation works.
P010330 | CLOSED(T) HILL COMMUNITY FORES | South Asia | Nepal | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1989 | 1999 | 2000 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/925631474750246393/text/000020051-20140526225946.txt | http://documents.worldbank.org/curated/en/925631474750246393/pdf/000020051-20140526225946.pdf | The lessons identifed by the ICR are interesting and have important implications for the future management of Nepal's forests. Four lessons from the ICR are repeated here. (i) Reorientation of government institutions --the project has demonstrated that given a favorable policy and legal framework, a government department can evolve from one concerned primarily with policing to one working with communities in forest management; (ii) Restoration of forest ecosystems--Protection and management of natural regeneration has proven to be a more successful mechanism than plantation establishment to restore forest ecosystems; (iii) Sustainability and ownership--community empowerment cannot be accelerated at a pace beyond the capacity of the facilitating institution to manage expansion and the rate of learning and behavioral change required by forest users. (iv) Monitoring and evaluation--the weakness in M&E meant that ineffective strategies were supported for longer than they should have been with associated financial costs.The Evaluation Summary adds the following: (i) Establishment of a sound policy and legal foundation and clear benefit sharing arrangements are essential for the sustainability of a forest managment program based on community participation.(ii) Multiple donor involvement in the forest sector in Nepal was a reality before the project. In such situations caution needs to be exercised during project preparation to ensure that donor overload and/or coordination does not become a handicap in project implementation. (iii) Given the potential of forest development to impact the lives of the rural poor it is important to make forest sector development an essential part of the poverty alleviation strategy of the Bank in the country.
P010330 | CLOSED(T) HILL COMMUNITY FORES | South Asia | Nepal | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1989 | 1999 | 2001 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/171801511185777228/text/multi0page.txt | http://documents.worldbank.org/curated/en/171801511185777228/pdf/multi0page.pdf | FINDINGS AND LESSONS Lesson 1 Achieving forest regeneration through community-driven development is only the first phase. An important second phase is to ensure equitable management and distribution of benefits. The Bank has been one of the largest donors in the forest sector in Nepal. Unlike most other donors, which have worked in a few districts at a time, it has been active in several districts at the same time. In addition, the Bank is active in several other sectors in Nepal. Hence, the Bank has a comparative advantage in addressing cross sectoral issues that affect the working of all departments. If benefits from community forestry are to go beyond simple forest regeneration and are to contribute to the development of Nepal, then it is essential that the country is provided support in dealing with the second phase challenges. Through its cross sectoral presence and the use of a combination of lending and non-lending instruments that it has at its disposal, the Bank could support the government's efforts in this direction. Lesson 2 Not all the challenges and problems in implementation of a program of community participation can be visualized upfront. Hence the importance ofan efficient monitoring and evaluation system to make mid course corrections as and when required. Timely diagnosis of problems can help countries resolve challenges more readily and efficiently. Failure to develop an efficient monitoring and evaluation system contributed to an inefficient use of resources in the Hill Community Forestry Project. Lesson 3 The dependence of the poor on forests is great and forest sector development should be a part of the Bank's poverty alleviation strategy in countries like Nepal. Hence, in addition to increasing/regenerating forest cover, development objectives should be framed at least partly in terms ofpoverty alleviation. Understandably, the substantial availability of grant resources from other donors has made HMGs' government reluctant to borrow Bank credit for the forest sector. However, given the importance of forest sector development to poverty alleviation, the Bank could 'push' for forest sector i;sues as a part of its overall poverty alleviation strategy.
P010333 | ENGINEERING EDUCATION PROJECT | South Asia | Nepal | IDA |  | Human Development | Education | IDA | IPF | 1989 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/456711474650967982/text/000020051-20140529075600.txt | http://documents.worldbank.org/curated/en/456711474650967982/pdf/000020051-20140529075600.pdf | High borrower commitment and ownership supports implementation even in countries whose projects often have unsatisfactory outcomes. - Decentralization of managerial functions at the institution level and autonomy to manage school inputs and outcomes are important incentives to administrators and staff, which may facilitate project implementation. - Substantial cost recovery in a difficult environment demonstrates that such a reform is possible when there is a strong leadership, willingness to engage in serious negotiations with students and politicians, and good support from senior management.- It is important to assess the extent of sustainable in-house capacity to undertake procurement and availability of local technical assistance before insisting on foreign consultants or procurement agencies.
P010344 | RURAL ELECTRIFICATIO | South Asia | Pakistan | Blend |  | Other | Other | IBRD | IPF | 1990 |  | 1999 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/849751474504707310/text/000020051-20140519070227.txt | http://documents.worldbank.org/curated/en/849751474504707310/pdf/000020051-20140519070227.pdf | Given that it is unlikely for RE programs to be self-financing, before implementation RE programs require a financing plan which does not put an undue burden on the power utility. The financing plan should identify sources of financing for the capital costs of the program and, at a minimum, should require coverage of operating costs by rural consumers. Subsidies for electricity or other fuels for tubewells should be removed in order for farmers to base their selection of electric or diesel pumps on economic criteria.
P010344 | RURAL ELECTRIFICATIO | South Asia | Pakistan | Blend |  | Other | Other | IBRD | IPF | 1990 |  | 2001 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/236781511185674397/text/multi0page.txt | http://documents.worldbank.org/curated/en/236781511185674397/pdf/multi0page.pdf | LESSONS Three lessons emerge. First, as the completion report notes, thorough project preparation is essential. This project failed because, at appraisal, it was not feasible economically, financially or institutionally. Implementation will inevitably be unsatisfactory unless the required preparatory studies and reviews are carried out in advance, and unless implementation procedures and monitoring and coordination requirements are spelt out in appraisal reports, and agreed prior to startup. Second, a project will fail to meet targets if the incentives are wrong. It is not realistic to expect a utility to carry out activities for which it is not adequately compensated. WAPDA's tariffs are too low to cover the cost of rural electrification, and the need for explicit subsidy of the rural part of WAPDA's operation has not been effectively addressed by government. Third, tariff analysis is fundamental in public utility projects, with respect to the average level, the structure of the tariff schedule, and the level of subsidy. Subsidies to poor consumers are essential if they are to be able to afford connection and wiring charges-in this case, WAPDA's charges were prohibitive, shutting out the poor. In Pakistan, outreach to poor households would probably be enhanced if the balance of subsidy was shifted away from tariffs toward upfront charges.
P010346 | SINDH PRIMARY EDUCATION | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1990 | 1999 | 2000 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/348521474485303250/text/000020051-20140528121913.txt | http://documents.worldbank.org/curated/en/348521474485303250/pdf/000020051-20140528121913.pdf | Useful lessons infrequently identified in education sector ICRs: In planning school facilities, educators and architects/engineers need to work together so that special needs of pupils are taken into consideration in the design of school furniture, blackboard location, flexible space arrangements and sanitation facilities.Close coordination between the Bank's financial management and procurement staff is required in the review of audit reports.Willingness of boys to enroll cannot be taken for granted when all incentives are designed for girls. The ICR proposes that boys' access should also be given priority in planning.
P010348 | CLOSED(T) BHAIRAWA LUMBINI III | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1990 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/490961475073322281/text/Nepal-Second-Bhairawa-Lumbini-rehabilitation-project.txt | http://documents.worldbank.org/curated/en/490961475073322281/pdf/Nepal-Second-Bhairawa-Lumbini-rehabilitation-project.pdf | In countries were social and institutional capital are low, the Bank needs a long term plan of engagement (possibly over several project cycles) to allow sufficient time for these to develop and ensure sustainability.Engineering interventions (tubewells) need to be sized according to social manageability rather than to economies of scale.There has to be trade-off between hydrogeology and socially appropriate well construction - difficult drilling conditions (boulder beds) preclude the small-scale private sector groundwater development feasible in nearby Bangladesh that has almost identical agro-ecological and social conditions.
P010349 | AGRIC. RES. II | South Asia | Pakistan | Blend |  | Other | Other | IDA | IPF | 1990 |  | 1999 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/281161475075133913/text/000020051-20140521031253.txt | http://documents.worldbank.org/curated/en/281161475075133913/pdf/000020051-20140521031253.pdf | (i) Substantial and sustained consultation with a wide audience (e.g. participatory workshops) are needed both to obtain ownership and to explicitly assess the level and foci of ownership; (ii) the early emergence of problems in institutional, policy, or political areas should be reacted to swiftly and pro-actively if a project is to be revived given the inherently long lead time with reforms in these areas. (iii) Project design should be adapted to the level of ownership in different parts of the system.
P010352 | TRANSPORT SECT PROJE | South Asia | Pakistan | Blend |  | Infrastructure | Transport | IBRD | IPF | 1990 | 1998 | 2000 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/675361474496741989/text/000020051-20140522111431.txt | http://documents.worldbank.org/curated/en/675361474496741989/pdf/000020051-20140522111431.pdf | There are three lessons with broad applicability. First, improved contract administration with timely payments and good bidding documents and procedures both reduces claims against the employer and strengthens the local construction industry. Second, improvement in railway operations must consider the entire logistic chain and all the activities to move freight door-to-door in order provide the shippers satisfactory and competitive service. And third, the process of creating borrower ownership for ambitious restructuring need to be more than a legal (project) conditionality or requiring upfront changes. Appropriately, in this project, a long run view of the (railway) restructuring processes was adopted and that enabled the Bank to assist GOP to open access for private railway operators and pursue other railway privatization policies.
P010352 | TRANSPORT SECT PROJE | South Asia | Pakistan | Blend |  | Infrastructure | Transport | IBRD | IPF | 1990 | 1998 | 2000 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/590051509569084658/text/multi0page.txt | http://documents.worldbank.org/curated/en/590051509569084658/pdf/multi0page.pdf | 6. Lessons Learned and Recommendations Lessons Learned\. Technical Assistance 6.1 Approach to TA. When the implementing organization is competent and has freedom to act, a content-oriented approach to technical assistance can be effective on well-defined institutional issues. For example, institutional development took place in NHA, but the gains were limited to the problems tackled and important issues went ignored. When issues are complex, as they nearly always are, and even if the organization is competent, process consulting is indicated in TA because the relevant information, a correct diagnosis, and appropriate interventions can only be achieved if the client is fully involved. This was approximately the case with KPT. 'Doctor' consulting failed regardless of client capacity and is, therefore, rarely indicated. 6.2 Theory of technique. Looking at TA and country's development needs broadly, the Bank needs to evolve and codify a new way of working with the client in change process. This could be called 'theory of technique'. 21 The delays with the action plans, ineffectiveness of TA, or undesired effects and side-effects due to errors of omission and commission, are indicative of insufficient understanding of the client's problems (also by the client) or of conceiving them too narrowly. It is necessary to structure the Bank-client relationship-itself an intervention-in a way that involves the client in defining the problem, studying it, and developing interventions that are genuinely relevant to the client's needs.22 6.3 Project concept. Approaches to improving service delivery organizations as government departments do not work. The extensive efforts in this and predecessor projects, and numerous projects elsewhere, demonstrate that improving the performance of a parastatal organization needs to culminate in its privatization-the quicker the better.23 Sustainability is ensured only when there is competition, accountability, and incentives to go after, be responsible for and keep the benefits from productivity improvements. NHA, KPT, and PR are concrete examples. Recommendations 6.4 Roads are still unsatisfactory in Pakistan. NHA is a competent agency, but the institutional and policy framework (for definition see footnote 17) within which it operates prevents it from making good decisions. PR infrastructure, operations, services, and planning are affected by misaligned institutional incentive structures, unclear contractual relationships, lack of 21. In a recent Bank-sponsored seminar, Douglass North named learning about and understanding of the 'change process' to be at the cutting edge of development theory. 'Theory of technique' is a more appropriate term because it runs through all the activities from data collection to monitoring results and implies that change process is not only observable but also can be influenced. 22. It is suggested here that working with the client using correct theory of technique is the critical factor in development and change, and for scaling up. Quick fixes such as new instruments [from innovation market place I to eradicate poverty or cause behavior changes will not work alone. 23. The 'end game' would need to be different for individual sectors\. full privatization for railways; a landlord port role for Karachi and Qasim; and an autonomous NHA (and provincial road agencies) with private sector service delivery for most operations. managerial independence, and unfunded service obligations. Trade facilitation, including customs, excess labor, and private sector participation persist as concerns for KPT. The Bank should continue to work with the GOP in the road and port sectors and begin anew in rail and provincial and rural roads. Among the priority issues to be addressed in the transport sector are\. * Definition of the roles of the sectoral institutions. Several entities-MOC, NHC, NHA, MLG, C&WD, MOR, PR-have an important but overlapping roles, or cooperation between them is arranged through ministerial committees. The institutional responsibilities need to be thoroughly studied and intersectoral decisionmaking clarified. * Sectoral performance indicators. The paradox that projects are satisfactory but the program fails to achieve desired outcomes applies in Pakistan. It must be faced squarely. One important way to do so is to develop sectoral performance indicators, both quantitative and qualitative, that can be used to identify needs, evolve project concepts, and broadly gauge movement toward desirable ends. The indicators should have a view toward the sector's graduation, that is, to overcome dependency on aid and begin independent functioning. * Privatization and pruning ofPR, now. The matter has been studied sufficiently. Pro; --s consulting is indicated to involve the government, the private sector, PR, other affectea interests, and civil society to register and monitor their points of view and concerns so that a realistic privatization model and rail track abandonment can be pursued. * Development of a policy framework for roads, and progressive commercialization of road administrations'service delivery. There should be a management umbrella, with appropriate road-user representation, on the roads managed by the five organizations, MOC, NHC (if its existence is justified), NHA, C&WD, and MLG so that investment decisions are consistent. regionally fair, adequate resources are allocated to construction, maintenance and oper2tior and that intersectoral and equity considerations are taken into account. * Further commercialization ofKPT. KPT management should vigorously pursue the landlord port concept and adopt commercial management principles in all its operations and asset management-the container and bulk cargo ports, real estate assets, and so forth, and revalue assets continuously. With regard to labor, KPT should continue to improve its labor productivity without abandoning social responsibility. * Shared power. Current transport sector institutions lack sufficient communication with important sectoral actors. Increased partnering should be sought with the Ministry of Petroleum and with government and nongovernmental environment bodies on clean fuels and other environmental matters; with local universities and research institutes (e.g., in pollution control, traffic safety, management systems, data analysis, and training courses for these activities, etc.); with user groups (e.g., regular meetings and joint training activities with the trucking association, other road users, the shippers council, the police regarding enforcement and traffic safety, axle-load control, regulation, etc.); and with the private sector (land use, economic development, trade facilitation, contracting and consulting industry practices, etc.). 6.5 Four technical content issues require urgent attention\. * Development of data services and completing the management systems. The availability and application of compatible data and road management systems in NHA and C&DW is necessary. There also is a need to improve current data services, with regard to traffic counting, axle loads, road condition, and cost and price information. * Human resources development. NHA, KPT, and PR have capable professionals. These technical skills must be maintained and updated by continuous training and by creation of an institutional environment and practices that value and reward technical and professional excellence. A twinning partner would be highly desirable for NHA and KPT. Training of management at all levels is also important. This probably is best done in the context of eventual studies on sectoral organizations and the policy framework because the evolving partnerships and organizations require interpersonal skills and decisionmaking capability. * Environment and traffic safety. Comprehensive programs in environmental protection and pollution control, traffic safety, and axle-load control need to be developed in NHA and C&DW. * Functional and administrative classification of roads. Size of the network. The modernization and expansion of the NHS and of the provincial road network necessitates a review of the classification of the entire road network. The size of the network is also an important issue. Some suggest that Pakistan's road network length is adequate and focus should now be on maintenance. This claim should be examined carefully. Resolution of this issue has implications for funding of all the roads.
P010360 | CORP. RESTRUCT. & SY | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1991 | 1998 | 2000 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/739391474575516059/text/000020051-20140526221855.txt | http://documents.worldbank.org/curated/en/739391474575516059/pdf/000020051-20140526221855.pdf | Important sector reforms - such as a privatization program - should be prepared so as to ensure sustained commitment of the government and the borrower, taking into account the impact and attitude of major stakeholders.The privatization program for a major utility should be agreed prior to project inception, and should integrate appropriate regulatory reforms, pricing policies, measures to help ensure contractual stability, consideration of a possible need for strategic investors, and a realistic analysis of the capacity of the targeted capital markets.
P010361 | ICDS I (ORIS & ANDHR | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1991 | 1998 | 1998 | ICRR | >=50 million & <100 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/612131474574583736/text/000020051-20140519063206.txt | http://documents.worldbank.org/curated/en/612131474574583736/pdf/000020051-20140519063206.pdf | Implementation was focused on achieving certain numbers of children being fed and enrolled in the pre-school education program, but not on preventing malnutrition through behavior change among mothers. High quality, properly oriented and timely training is a sine qua non for high quality service delivery. The ICDS (Integrated Child Development Services) program supported by the project contained too many components and insufficient resources and manpower to undertake them all well.
P010363 | 3RD ROADS | South Asia | Sri Lanka | IDA |  | Infrastructure | Transport | IDA | IPF | 1991 | 1999 | 2000 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/197451474563248384/text/000020051-20140526220831.txt | http://documents.worldbank.org/curated/en/197451474563248384/pdf/000020051-20140526220831.pdf | Three key lessons emerge from this project:i) When a (road) agency is characterized by a traditional structure and little innovation, too narrow institutional objectives are inadequate and will help little to modernize and make the management of the (road) sector more efficient. ii) Greater participation in Bank-financed works is an important incentive to the local construction industry, but where it is a relatively infant industry it needs to be supported by measures oriented to improving their financial management (including securing adequate working capital) and to ensuring an adequate stream of on-going construction awarded through competitive contracting to provide the newly created industry with steady work opportunities.iii) Decentralization of the road network is a long-term process that requires (a) appropriate transfer of funds from the central authorities, (b) long-term support through setting standards, regulating, training and helping prepare local-level highway plans, and (c) a well designed monitoring system to assess the technical and financial performance of the decentralized agencies.
P010363 | 3RD ROADS | South Asia | Sri Lanka | IDA |  | Infrastructure | Transport | IDA | IPF | 1991 | 1999 | 2003 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/572281468763781674/text/261380LK0PPAR.txt | http://documents.worldbank.org/curated/en/572281468763781674/pdf/261380LK0PPAR.pdf | LESSONS 0 The performance o f a wide range o f projects-not only those inconflict zones-is vulnerable to the impact o f war, especially through unexpected conflict events duringproject implementation. Projects will not do so well duringconflict as inapeaceful situation. Spatial separation o fa project from active conflict zones does not guarantee that an operation will be free o f conflict constraints. 0 Project design should not be blindto conflict, and must cautiously but explicitly address the constraints imposed. War-weary governments are unlikely to have strong ownership o f reform unrelatedto the causes o fthe conflict. Decentralization may go against centralized conduct o f war. Conflict generates a poor business climate that private firms themselves are unwilling to invest in. 0 Itis importantto focus upona clear vision o fthe intendeddevelopment results of a project, and to remain focused on them through systematic monitoring and evaluation. Inother words, the baseline shouldbe measured, the counterfactual clearly understood, and M&E supported and implemented.
P010366 | RURAL WATER | South Asia | Pakistan | Blend |  | Sustainable Development | Water | IDA | IPF | 1991 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/320491474577325891/text/000020051-20140602103040.txt | http://documents.worldbank.org/curated/en/320491474577325891/pdf/000020051-20140602103040.pdf | (1) A demand-driven rural water supply and sanitation strategy based on strong community participation requires a longer time to take root than what is usually offered by one single project. The AJK component performed better than the Balochistan and Sindh components precisely because it enjoyed a centuries old tradition of community participation whereas the other two did not.(2) Changing the habits of excreta disposal implies a much greater effort than providing water supply. Symptomatically, the water supply investments performed much better than the latrine components. (3) Project objectives should be stated in terms that would allow quantitative monitoring of progress towards reaching them.
P010367 | MICRO-ENTERPRISES | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1991 | 1998 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/455221474849832009/text/000020051-20140522080504.txt | http://documents.worldbank.org/curated/en/455221474849832009/pdf/000020051-20140522080504.pdf | Financing of microenterprises is viable, with a satisfactory recovery rateThe role of women in microenterprises can be enhanced if credit is made available
P010368 | POVERTY ALLEVIATION | South Asia | Sri Lanka | IDA |  | Other | Other | IDA | IPF | 1991 |  | 1999 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/969371474586409784/text/000020051-20140519082130.txt | http://documents.worldbank.org/curated/en/969371474586409784/pdf/000020051-20140519082130.pdf | (i) Establishing a semi-autonomous agency to manage the flow of funds to NGOs and other service delivery organizations to ensure greater responsiveness and decentralization of service provision, is a logical response to the inherent weaknesses of a highly centralized and rigid government machinery. However, the managerial, administrative, technical and monitoring skills and competencies required to effectively operate such an agency are considerable. The availability of these skills cannot be taken for granted, especially in the context of a large national program. (ii) The governance structure of any semi-autonomous agency, the institutional framework linking the apex agency to partner organizations, as well as establishing minimum standards for accountability and transparency, need to be fully worked out before funds are disbursed. Participation and training are essential.(iii) Pilot projects, as a basis for testing strategies and approaches, can play a central role in facilitating overall project success. (iv) Effective monitoring and evaluation, together with research and beneficiary studies are essential to ensure efficient project implementation and the drive for development impact.
P010369 | MAHARASHTRA RURAL WS | South Asia | India | IBRD |  | Sustainable Development | Water | IDA | IPF | 1991 | 1998 | 1999 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/932521474664281508/text/000020051-20140521031430.txt | http://documents.worldbank.org/curated/en/932521474664281508/pdf/000020051-20140521031430.pdf | The ICR addresses some key deficiencies in project preparation which caused less than satisfactory outcome at the end. These are mainly in the areas of: (i) design of components to appropriately match project objectives; (ii) community participation; and (iii) institutional and financial reforms and arrangements. Furthermore, alternative technical solutions should have been evaluated so as to make new services better affordable to users. The lessons from this project should be carefully reviewed when preparing follow-on projects in Maharashtra and elsewhere in India.
P010370 | CLOSED(T) URB WATER & SAN REHAB | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1991 | 1999 | 2001 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/530131474596329196/text/000020051-20140529070048.txt | http://documents.worldbank.org/curated/en/530131474596329196/pdf/000020051-20140529070048.pdf | Most of the lessons are trite and have been known since the mid-1970s. Once again it should be recalled that:(1) In the face of general agreement of what had gone wrong in the past ( under three previous Bank-financed water supply projects) it was a fallacy to expect that half-measures that failed to radically change the legal/regulatory framework and the incentives would produce any better results than in the past; (2) Politicization of tariff increases, staff recruitment, and of other administrative and financial matters will destroy the best-intentioned project and the costs will ultimately be borne by the consumers in the form of poor and unsafe service;
P010371 | FAMILY HEALTH | South Asia | Pakistan | Blend |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1991 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/284301474482700782/text/000020051-20140529204503.txt | http://documents.worldbank.org/curated/en/284301474482700782/pdf/000020051-20140529204503.pdf | Â· Baseline performance indicators and interim quantitative benchmarks, in terms of both outputs and health outcomes, should be identified at appraisal and regularly tracked in supervision as well as used in final evaluation.Â· Project emphasis on human resource development is important and can pay off in terms of improved management and service outcomes.Â· Gender priorities in health projects are important to articulate in project design, can be met in project implementation and can result in increased MCH/FP service use.Â· Financial management issues need to be integral components of the Bankâ€™s continuous supervision.
P010373 | TELECOMS. II | South Asia | Sri Lanka | IDA |  | Infrastructure | Transport | IDA | IPF | 1991 | 1998 | 1999 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/516981475086853270/text/000020051-20140519084231.txt | http://documents.worldbank.org/curated/en/516981475086853270/pdf/000020051-20140519084231.pdf | In Telecommunications (TC), networks expansion, improvement of operations and sector reform towards liberalized and regulated statutory set-up is a complex process that takes time and involves major actors in government, society and economy, best supported by a sustained Bank involvement via multiple channels and instruments (incl. PSM loans and SALs if needed). Surplus credit funds due to cost savings and elimination of project items should be identified and canceled, or reallocated, early, e.g., at project mid-term review, to reduce commitment charges for the Borrower, or ensure that needed items, which would suffer delays, be also implemented.
P010374 | SMI IV | South Asia | Sri Lanka | IDA |  | Other | Other | IDA | IPF | 1991 |  | 1998 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/412811474590668647/text/000020051-20140516155528.txt | http://documents.worldbank.org/curated/en/412811474590668647/pdf/000020051-20140516155528.pdf | The importance of seeking financial viability and strenghtening the internal efficiency of participating credit institutions is difficult to exaggerate, and should be a component of credit lines such as this one. Well-functioning financial institutions can effectively and productively distribute Bank credits in productive ways. However, it is important that such loans focus on the sources of imperfection which prevent lenders from carrying out effective intermediation in the first place. In addition, Bank research on the need for a long-term commitment for fundamental financial reform is supported by the experience of this credit.
P010375 | KARACHI PORT MODERN. | South Asia | Pakistan | Blend |  | Infrastructure | Transport | IBRD | IPF | 1991 | 1998 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/156801474566843056/text/000020051-20140521032954.txt | http://documents.worldbank.org/curated/en/156801474566843056/pdf/000020051-20140521032954.pdf | There are two lessons. First, trade facilitation is an important factor in demand and in port productivity. To carry out trade facilitation measures requires participation of all the actors: the government policy makers, the port management, customs officials, and the users; it cannot be undertaken by the port alone, and neither is government sponsorship alone sufficient. Second, port productivity is composed of a complex array of factors in addition trade facilitation, these should include physical configuration and equipment at the port, staff training in all aspects of port operations, and elucidation of and agreements on clear targets with appropriate incentives, and especially privatization.
P010375 | KARACHI PORT MODERN. | South Asia | Pakistan | Blend |  | Infrastructure | Transport | IBRD | IPF | 1991 | 1998 | 2000 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/590051509569084658/text/multi0page.txt | http://documents.worldbank.org/curated/en/590051509569084658/pdf/multi0page.pdf | 6. Lessons Learned and Recommendations Lessons Learned\. Technical Assistance 6.1 Approach to TA. When the implementing organization is competent and has freedom to act, a content-oriented approach to technical assistance can be effective on well-defined institutional issues. For example, institutional development took place in NHA, but the gains were limited to the problems tackled and important issues went ignored. When issues are complex, as they nearly always are, and even if the organization is competent, process consulting is indicated in TA because the relevant information, a correct diagnosis, and appropriate interventions can only be achieved if the client is fully involved. This was approximately the case with KPT. 'Doctor' consulting failed regardless of client capacity and is, therefore, rarely indicated. 6.2 Theory of technique. Looking at TA and country's development needs broadly, the Bank needs to evolve and codify a new way of working with the client in change process. This could be called 'theory of technique'. 21 The delays with the action plans, ineffectiveness of TA, or undesired effects and side-effects due to errors of omission and commission, are indicative of insufficient understanding of the client's problems (also by the client) or of conceiving them too narrowly. It is necessary to structure the Bank-client relationship-itself an intervention-in a way that involves the client in defining the problem, studying it, and developing interventions that are genuinely relevant to the client's needs.22 6.3 Project concept. Approaches to improving service delivery organizations as government departments do not work. The extensive efforts in this and predecessor projects, and numerous projects elsewhere, demonstrate that improving the performance of a parastatal organization needs to culminate in its privatization-the quicker the better.23 Sustainability is ensured only when there is competition, accountability, and incentives to go after, be responsible for and keep the benefits from productivity improvements. NHA, KPT, and PR are concrete examples. Recommendations 6.4 Roads are still unsatisfactory in Pakistan. NHA is a competent agency, but the institutional and policy framework (for definition see footnote 17) within which it operates prevents it from making good decisions. PR infrastructure, operations, services, and planning are affected by misaligned institutional incentive structures, unclear contractual relationships, lack of 21. In a recent Bank-sponsored seminar, Douglass North named learning about and understanding of the 'change process' to be at the cutting edge of development theory. 'Theory of technique' is a more appropriate term because it runs through all the activities from data collection to monitoring results and implies that change process is not only observable but also can be influenced. 22. It is suggested here that working with the client using correct theory of technique is the critical factor in development and change, and for scaling up. Quick fixes such as new instruments [from innovation market place I to eradicate poverty or cause behavior changes will not work alone. 23. The 'end game' would need to be different for individual sectors\. full privatization for railways; a landlord port role for Karachi and Qasim; and an autonomous NHA (and provincial road agencies) with private sector service delivery for most operations. managerial independence, and unfunded service obligations. Trade facilitation, including customs, excess labor, and private sector participation persist as concerns for KPT. The Bank should continue to work with the GOP in the road and port sectors and begin anew in rail and provincial and rural roads. Among the priority issues to be addressed in the transport sector are\. * Definition of the roles of the sectoral institutions. Several entities-MOC, NHC, NHA, MLG, C&WD, MOR, PR-have an important but overlapping roles, or cooperation between them is arranged through ministerial committees. The institutional responsibilities need to be thoroughly studied and intersectoral decisionmaking clarified. * Sectoral performance indicators. The paradox that projects are satisfactory but the program fails to achieve desired outcomes applies in Pakistan. It must be faced squarely. One important way to do so is to develop sectoral performance indicators, both quantitative and qualitative, that can be used to identify needs, evolve project concepts, and broadly gauge movement toward desirable ends. The indicators should have a view toward the sector's graduation, that is, to overcome dependency on aid and begin independent functioning. * Privatization and pruning ofPR, now. The matter has been studied sufficiently. Pro; --s consulting is indicated to involve the government, the private sector, PR, other affectea interests, and civil society to register and monitor their points of view and concerns so that a realistic privatization model and rail track abandonment can be pursued. * Development of a policy framework for roads, and progressive commercialization of road administrations'service delivery. There should be a management umbrella, with appropriate road-user representation, on the roads managed by the five organizations, MOC, NHC (if its existence is justified), NHA, C&WD, and MLG so that investment decisions are consistent. regionally fair, adequate resources are allocated to construction, maintenance and oper2tior and that intersectoral and equity considerations are taken into account. * Further commercialization ofKPT. KPT management should vigorously pursue the landlord port concept and adopt commercial management principles in all its operations and asset management-the container and bulk cargo ports, real estate assets, and so forth, and revalue assets continuously. With regard to labor, KPT should continue to improve its labor productivity without abandoning social responsibility. * Shared power. Current transport sector institutions lack sufficient communication with important sectoral actors. Increased partnering should be sought with the Ministry of Petroleum and with government and nongovernmental environment bodies on clean fuels and other environmental matters; with local universities and research institutes (e.g., in pollution control, traffic safety, management systems, data analysis, and training courses for these activities, etc.); with user groups (e.g., regular meetings and joint training activities with the trucking association, other road users, the shippers council, the police regarding enforcement and traffic safety, axle-load control, regulation, etc.); and with the private sector (land use, economic development, trade facilitation, contracting and consulting industry practices, etc.). 6.5 Four technical content issues require urgent attention\. * Development of data services and completing the management systems. The availability and application of compatible data and road management systems in NHA and C&DW is necessary. There also is a need to improve current data services, with regard to traffic counting, axle loads, road condition, and cost and price information. * Human resources development. NHA, KPT, and PR have capable professionals. These technical skills must be maintained and updated by continuous training and by creation of an institutional environment and practices that value and reward technical and professional excellence. A twinning partner would be highly desirable for NHA and KPT. Training of management at all levels is also important. This probably is best done in the context of eventual studies on sectoral organizations and the policy framework because the evolving partnerships and organizations require interpersonal skills and decisionmaking capability. * Environment and traffic safety. Comprehensive programs in environmental protection and pollution control, traffic safety, and axle-load control need to be developed in NHA and C&DW. * Functional and administrative classification of roads. Size of the network. The modernization and expansion of the NHS and of the provincial road network necessitates a review of the classification of the entire road network. The size of the network is also an important issue. Some suggest that Pakistan's road network length is adequate and focus should now be on maintenance. This claim should be examined carefully. Resolution of this issue has implications for funding of all the roads.
P010377 | SCARP TRANS. II | South Asia | Pakistan | Blend |  | Other | Other | IDA | IPF | 1991 |  | 1999 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/508911475074165352/text/000020051-20140519075627.txt | http://documents.worldbank.org/curated/en/508911475074165352/pdf/000020051-20140519075627.pdf | (i) A social mobilization program and a multi-disciplinary approach to project implementation is essential for such irrigation projects; (ii) farmer training should be an integral part of project design; (iii) availability of micro-credit may lessen poor farmer reliance on other more affluent farmers and increase equity impact of such community-based projects; and (iv) monitoring and impact evaluation activities should run from the start of a project.
P010378 | IRRIG. REHAB. | South Asia | Sri Lanka | IDA |  | Sustainable Development | Water | IDA | IPF | 1991 | 1999 | 1999 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/231561474490775989/text/000020051-20140522102128.txt | http://documents.worldbank.org/curated/en/231561474490775989/pdf/000020051-20140522102128.pdf | Although some of the Lessons Learned were known widely at the time of appraisal the following are worthy of note:-1. Institutional and agricultural policy reforms must precede rehabilitation if the benefits are to be achieved.2. Low profitability and productivity in agriculture inhibit the development of farmer organizations.3. Farmer organizations must be established in advance of rehabilitation planning, design and implementation.4. Implementation management responsibility should be devolved to the provinces for effectiveness and efficiency5. A maintenance fund with actual support from farmers is a possible solution to project sustainability and should be pursued further.
P010381 | GAS FLARING REDUCTIO | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1991 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/756401474850255107/text/000020051-20140519083025.txt | http://documents.worldbank.org/curated/en/756401474850255107/pdf/000020051-20140519083025.pdf | Every effort should be made to ensure that co-financing agreements become effective in parallel with Bank loans, because delays can constrain project implementation performance, and thereby negatively affect the project's economic viability. Improving the legal and fiscal framework to promote private sector participation in petroleum exploration and development may not be enough to get desire results. The negotiation process also needs to be streamlined and strengthened.
P010386 | POWER DISTRIBUTION | South Asia | Sri Lanka | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1992 | 1998 | 2000 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/402871474596008298/text/000020051-20140526222224.txt | http://documents.worldbank.org/curated/en/402871474596008298/pdf/000020051-20140526222224.pdf | Areas of civil unrest risking difficult security situations should not be included as project component. Project management should be entrusted to competent and stable staff within a project implementation unit. Procurement issues should be addressed and resolved well before project approval by the Board.
P010386 | POWER DISTRIBUTION | South Asia | Sri Lanka | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1992 | 1998 | 2004 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/675471468760785805/text/29532.txt | http://documents.worldbank.org/curated/en/675471468760785805/pdf/29532.pdf | LESSONS LEARNED 41. The ESDP's unique design for implementation can serve as a model for other rural electrification initiatives with renewable energy and energy efficiency components. The ESDP lesson with potentially the broadest applicability is its demand-driven and commercially focused approach of enabling multiple stakeholders to overcome financial, institutional, and market barriers associated with small-scale renewable energy and the promotion of energy efficiency. Throughout implementation, this required a strong and consistent emphasis on establishing strategic and working partnerships between the central government, Provincial Councils, the Ceylon Electricity Board, commercial and development banks, a microfinancing institution, private developers, contractors and consultants, industry associations, equipment vendors, rural electricity cooperatives, and consumers. It also required a stable, competent, and highly proactive Administrative Unit with multi-disciplinary capabilities to manage project coordination and implementation, which proved to be a key element in successfully broad-scaling private investments to commercialize renewable energy technologies. 42. The ICR provides an excellent and detailed section on lessons learned, which benefited from a stakeholders' survey and a full-scale, independent report.' The lessons can be clustered around three main actions\. (i)Build the business andpolicy environment 43. The key barrier of access to capital must be addressed as a priority, be it for longer-term loans (sought by project developers), for credit assistance to improve affordability (required for village hydro and solar electricity consumers), or for working capital (needed by entrepreneurs). Sri Lanka has the advantage of having a long experience with minihydro dating back from the establishment of the tea estates (that is, good maps, existing roads, and good rainfall data), as well as financial institutions (such as DFCC Bank and National Development Bank that were already lending to small and medium enterprises, as well as to a variety of large infrastructure projects, before ESDP. Even before ESDP and the SPPA became realities, DFCC Bank had pioneered the financing (with debt and equity) of the country's first-ever private sector minihydro project that was set up to sell power exclusively to the CEB grid. Under ESDP, the two development banks DFCC and NDB, by virtue of their in-house engineering capabilities, spearheaded the financing of grid-connected minihydro, often syndicating their loans with other commercial banks that were PCIs. Today, commercial banks have gained sufficient confidence to lend to this sector by themselves. While prior experience is important, microfinance institutions can play a significant role in providing consumer financing for solar home systems and term loans to community-based organizations for developing small and medium off-grid renewable energy projects. Although microfinance institutions and rural development banks are in general more 9. International Resources Group. World Bank/Sri Lanka Energy Services Delivery Project\. Impact Assessment and Lessons Learned. Washington DC, March 2003. suited for financing rural energy services rather than larger commercial banks and main vendors of solar home systems, exceptions do exist, such as the continuing role played by Hatton National Bank and DFCC Bank as leaders in financing off-grid village hydro projects. 44. Unfavorable aspects of the overall investment environment must be addressed\. for small hydro developers, a transparent and standardized contracting and tariff arrangement (the SPPA) is essential; for dealers of solar home systems, high import costs and the lack of consumer financing needed to be resolved; and for village hydro developers, access to favorable credit terms and reliable manufacturers of turbines and induction generator controllers were required before they could enter rural areas and stimulate demand for a mini-grid among small communities. (ii)Scale-up the Market 45. In addition to the adoption of market-based principles, several measures need to be taken to foster continued growth in the renewables industry. First, a reliable after-sales service system needs to be established. In Sri Lanka, the solar industry responded very well and now has more than 100 sales and service outlets throughout the country, developed through foreign and local private investment. Second, information technology should be introduced in the operations of participating microfinance institutions, which in the case of ESDP reduced turnaround time of loan approvals for solar systems from more than 3 months to less than 30 days. Third, consumers should be trained properly in the operation, maintenance, and limitations of their systems, particularly to self-diagnose technical problems (such as loose wiring connections, shading over photovoltaic modules, tripping of village hydro distribution circuits, keeping distribution poles free of rot and termite attack) and avoid over-usage. This is especially important as systems grow older and components start failing. Solar systems need special watching and improvements, as complaints have increased (in absolute numbers, but not per capita) about system malfunctions. Some consumers indicate a preference and willingness-to-pay for grid connection if ever feasible for their remote area, since the 200 watts per household provided by microhydro or the subsistence-level electrification provided by solar home systems are limited and do not permit the addition of more appliances or leisure uses. 46. The stakeholders' survey indicated that rural consumers are willing to pay more for their energy use, as long as the supply is reliable, safe, and of a high quality as is demonstrated by hydro and solar energy compared to the use of kerosene, which poses health risks in addition to inconvenience of use. Community contributions (in cash and kind) to the implementation and management of off-grid village hydro is crucial to project success. In Sri Lanka, families contributed their time to civil works and construction of distribution lines, as well as the supply of poles, sand, and other materials in kind, which were assigned equivalent cash amounts and deducted from their actual required payments. These contributions brought a sense of project ownership and a desire to ensure successful implementation. (iii)Establish Robust Project and Financial Management Systems 47. Competent project management proved essential to ESDP's successful implementation, as were accounting, record-keeping and financial reporting systems that were timely and comprehensive. Particularly noteworthy is the performance of the Administrative Unit in\. (i) brokering partnerships among multiple stakeholders; (ii) quickly assimilating the underlying technologies; and (iii) setting up a financial management system for monitoring and disbursing against loan refinancing applications from PCIs, as well as verifying and releasing grant disbursements, including the tracking of over 20,000 solar home systems. In practice, these enabled the Bank and the borrower to be flexible in project design (for example, the certification of a microfinance institution to reverse the slow uptake of solar home systems in rural areas, and the relative ease in revising the Operating Guidelines to improve systems and procedures) and to introduce output-based aid approaches (such as the tying of project development consulting contracts to concrete deliverables).
P010390 | MAHARASHTRA FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1992 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/298241474571935978/text/000020051-20140529160452.txt | http://documents.worldbank.org/curated/en/298241474571935978/pdf/000020051-20140529160452.pdf | The lessons identifed by the ICR are interesting and have important implications for the future management of India's forests. Two important lessons from the ICR are repeated here. (i) The need for flexibility during project implementation so that forest management practices can be linked to site conditions. (ii) Government commitment to reform programs must be clearly established prior to project effectiveness. OED adds the following lessons. (i) It is essential that participatory forest sector development is made a part of the poverty alleviation strategy of the Bank in the country since community involvement in the management of forest resources has the potential to have a significant impact on rural poverty. (ii) In community forestry projects, alongside an objective of increasing forest cover, development objectives should be framed at least partly in terms of poverty alleviation. This should be done in a way that is monitorable. (iii) Continuity in top management is crucial for proper implementation of a complex operation like Maharashrta Forestry. Implementation under the current project was made more difficult by frequent changes at the Secretary level and amongst senior staff in the forestry department. (iv) While most forestry projects continue to set plantation targets in terms of area physically planted, it actually seems logical to judge achievements in terms of trees that have survived. Given the fact that projects are now required to have a functioning Monitoring and Evaluation system, assessing outcome in terms of survival rates may not be as impossible a task as it seemed some years ago.
P010391 | WEST BENGAL FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1992 | 1998 | 1999 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/822181475089184162/text/000020051-20140519064937.txt | http://documents.worldbank.org/curated/en/822181475089184162/pdf/000020051-20140519064937.pdf | Use of the logical framework, and critical path analysis (PERT) is recommended in project design, to connect project inputs to results. However, in partial contrast to this lesson, a process-oriented approach, rather than fixed blueprints is also recommended.Flexibility is required in micro planning, if village level Forest Protection Committees and local people are to buy-in to improving the productivity and protection of the forest. Bank staff need more guidance on the necessary degree of ex ante project ownership to justify proceeding, and how to enhance ownership during implementation. Need for improved communication (especially active listening) within the implementing agency and the Bank, and between the implenting agency and the Bank. Delegation of financial authority to field staff facilitates implementation.
P010392 | CLOSED(T) POWER EFF IMPROVEMEN | South Asia | Nepal | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1992 | 1999 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/622201474853084416/text/000020051-20140529165125.txt | http://documents.worldbank.org/curated/en/622201474853084416/pdf/000020051-20140529165125.pdf | Public consultations based on sound technical, economic, financial criteria and taking into account social and environmental concerns, as used in the screening and ranking exercise of the Medium Hydropower Study, should be made an integral part of the preparatory process to create a political consensus on proposed hydropower investments. It is an essential tool for mitigating social and environmental impacts as well as implementation risks.
P010393 | AIDS PREVENTION AND | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1992 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/761091474485798939/text/000020051-20140528130437.txt | http://documents.worldbank.org/curated/en/761091474485798939/pdf/000020051-20140528130437.pdf | Borrower commitment to a project, combined with effective management and oversight, can result in a well-conceived and implemented project. States and municipalities involved in decentralization of a national program should be involved from the start in order to maximize "buy-in". Monitoring must be routine, begin with appropriate indicators and adequate baseline data, and be used as a management as well as evaluation tool. NGOs can be very useful in reaching specialized, hard-to-reach populations. Specific AIDS-related lessons include the need to emphasize prevention, including communication for behavior change at the individual and community level and the need to have and use baseline epidemiological data. It is important to stay atop changing technical findings and approaches, such as the doubt of the general value of syndromic management of STDs. HIV/AIDS will continue to spread significantly, and thus donors and borrowers must enlarge their efforts. (Even though the % of seropositivity in India is "only" 1-5%, India is already home to 5 million infected individuals, the largest number of HIV-infected individuals in the world.)
P010393 | AIDS PREVENTION AND | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1992 | 1999 | 2004 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/645791468771642132/text/multi0page.txt | http://documents.worldbank.org/curated/en/645791468771642132/pdf/multi0page.pdf | Lessons 63. The first National HIV/AIDS Control Project was a critical start-up investment to put in place the mechanisms for the response. Project experiences suggest many lessons relevant to the HIV/AIDS response in India and elsewhere, of which OED highlights a few of the most prominent. Building robust institutions requires substantial innovation andflexibility. The original design of the project called for establishing a National AIDS Control Authority that would have functioned as an autonomous parastatal. However, as it became evident that Parliament would not approve such an arrangement, a compromise was struck that led to creation of NACO, a high-level semi-autonomous body under the MOHFW headed by a Director with the status of an Additional Secretary. Likewise, the eventual adoption of the society model for State AIDS 28. Reimbursements were suspended in Tamil Nadu briefly. control activities greatly reduced the administrative impediments to timely project implementation. * Epidemiological and behavioral surveillance provide key information to build support for the response in countries where denial is high and the epidemic is otherwise invisible. Epidemiological evidence to establish the potential scope of the epidemic in India was thin during most of the life of the project. The states with the strongest commitment and response were those where the number of AIDS cases was mounting (Maharashtra, Manipur, Tamil Nadu). The additional information provided by the first national round of HIV surveillance in the last year of the project was a catalyst and turning point for political commitment in some states where HIV had spread, but the number of AIDS deaths was small. Had these activities occurred earlier, political commitment might have developed earlier in several key states. They also would have provided a baseline for measuring the accomplishments of the project, demonstrated more clearly the feasibility of effective responses, and have enabled fine-tuning of project activities. * Projects that seek to enlist NGOs to implement HI V/AIDS interventions need to carefully assess NGO capacity in light of what is expected, and to ensure continuous training and technical support. The Bank, the government, and others in the international community overestimated local implementation capacity. While NGOs may in principle have a comparative advantage in spreading AIDS awareness or in reaching high-risk groups, their capacity for doing so may be weak. The mere existence of well-established development NGOs in the social welfare sector did not ensure the skills or capacity to quickly shift to HIV/AIDS interventions sometimes targeted to non-traditional groups. The lack of training and technical support to NGOs during project start-up delayed the implementation and expansion of project activities. While the project made major headway in terms of the selection and vetting of NGOs, capacity for monitoring and evaluation of NGO activities remains extremely weak. * When political commitment is heterogeneous in a decentralized system, channeling resources to effective programs in areas with the highest commitment can serve as a powerful demonstration of the localfeasibility of otherwise controversial programs. The project management's decision to channel funds to the states most able and willing to use them facilitated the development of indigenous models or pilots of key interventions, with lessons for states that lagged, as well as institutional models (like the Tamil Nadu society model) better suited to rapid implementation of the project. * Targeted awareness and interventions for high-risk groups can be successful only to the exctent that complementary efforts are launched to improve the environment for HIVprevention among these groups. The project focused on implementing specific IEC and technical interventions for high-risk groups. But in a number of cases NGOs reported that harassment by police made it difficult to work effectively and drove members of the beneficiary groups underground. Gradually, the states are coming to realize that law enforcement must be sensitized and informed of the public health benefits of the interventions for groups that are engaging in otherwise illegal activities, so that they cease counter-productive enforcement actions, the NGOs can do their jobs, and those at highest risk are enabled to engage in safer behavior. * Campaigns to increase awareness of HIV/AIDS and promote behgavior change must be informed by local research on behavior and attitudes in their design and implementation and in such as way as to reduce stigma ofpeople living with HIV/AIDS. * Where a majority of clients seek STD treatment in the private sector (as is often the case with se-xually transmitted diseases), engaging private and even traditional nonallopathic practitioners is likely to be necessary to ensure coverage and impact. Future Directions 64. While HIV/AIDS has likely spread less than it would have in the absence of the project, it nevertheless has continued to spread, albeit unevenly, throughout India. The results of the 2001 round of sentinel surveillance found six states in which HIV infection had reached high levels among STD patients and surpassed one percent of women attending antenatal clinics-Andhra Pradesh, Karnataka, Maharashtra, Manipur, Nagaland, and Tamil Nadu. In these states, where the epidemic started somewhat sooner, infection is mounting and so is the number of people living with HIV/AIDS in need of health care. In other states and union territories HIV has spread among high-risk groups, but not into the general population, while in a large number the epidemic has not yet taken off even among CSWs and IDUs, where it is likely to appear first. In 2001, roughly 75 percent of sex workers and their clients reported using condoms during their most recent sexual contact. But consistent condom use among CSWs and paying clients in the last month is lower about 50 percent and with non-paying partners lower still (21 percent) (NACO 2001c). 65. Certain priorities remain relevant for all states, irrespective of the stage of the epidemic\. * Expanding correct knowledge in the population concerning specific ways that HIV is spread and how to prevent it; * Building and sustaining government and NGO capacity to implement, monitor, and evaluate programs; * Refining the procedures for vetting and funding projects and improving the transparency of the process; * Improving the reliability of funding flows, reducing uncertainty of funding levels, and improving the timeliness of release of resources to SACS and NGOs; * Expanding the coverage of behavior change interventions to high-risk groups, while improving the quality of services; Investing in baseline surveys and analytic work that will help to design, evaluate, and improve the effectiveness and efficiency of programs, and disseminating results. 66. In the states with the most advanced epidemics and mounting numbers of AIDS patients, programs need to urgently improve the access of people living with HIV/AIDS (PWAs) to cost-effective medical care. Interviews with PWAs and visits to AIDS wards, together with data and reports from a variety of sources, indicated that many PWAs lack access to even the most basic health care and continue to be subject to discrimination and stigma by health care providers as well as family, Co-workers, and neighbors (Dube 2000; Hawkes and Santhya 2002; Jain 2002). These states will want to conduct surveys of public and private provider knowledge, attitudes, and practices toward treatment of AIDS patients, and of the type and quality of treatment that AIDS patients are receiving, as the basis for assessing what improvements are necessary. Thus, both care and reducing discrimination against people with AIDS are urgently needed. 67. The states that have not yet felt the brunt of the epidemic, where infection rates are still low, cannot be complacent. Experience globally and in India shows that HIV can and will spread wherever it can. These areas have an opportunity to act early, spread awareness, and enable those at high risk to adopt safer behavior, preventing a widespread epidemic. In these areas, expanding coverage of behavior change interventions is critical, as is continuous sensitization of policymakers to the urgency and priority of the task. 68. The Second National HIV/AIDS Control Project ($229.8 million) was approved in 1999, financed by an IDA credit of $191 million and a government contribution of $38.8 million, covering the period 1999-2004. The Second Project addresses many of these issues, by seeking to\. expand the coverage of targeted interventions to high-risk populations; increase access to voluntary counseling and testing centers and quality of IEC for the general population; improve access to low-cost care for people living with HIV/AIDS; enhance technical and managerial capacity; and promote multisectoral responses. The project design also calls for strengthening monitoring and evaluation. The Mid-term Review is scheduled for June 2003. Recommendations 69. In addition to the general priorities noted above, the OED evaluation recommends that the second project address a number of specific issues highlighted by this review of the first project\. * Improve the environment for behavior change among high-risk populations by sensitizing law enforcement to the need for HIV prevention; * Establish mechanisms to ensure that national and state-sponsored behavior change campaigns are based on rigorous research and are subject to regular monitoring and evaluation; * Reduce the discrimination faced by HIV-positive persons, starting with the medical profession, and ensure the involvement of PWAs in the policy dialogue; * Provide incentives to extend the tenure of Project Directors to at least 3 years, to reduce their turnover and improve effectiveness; * Improve the dissemination of the results of analytic work and ensure access of researchers to raw epidemiological and behavioral datasets (like the BSS) for additional analysis, to improve the effectiveness or targeting of programs; and * Put in place a results-based monitoring framework that will shift the focus from achieving output targets to monitoring progress toward agreed outcomes and to the quality of interventions.
P010394 | MIDDLE SCHOOLING | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1992 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/628861474630373315/text/000020051-20140529210601.txt | http://documents.worldbank.org/curated/en/628861474630373315/pdf/000020051-20140529210601.pdf | The size and scope of a project should be determined to be administratively feasible. Projects that demand more outputs that the borrower can produce are often restructured and down-sized later. However, the large project sizes and excessive appraisal expectations may make subsequent achievements look meager.The capabilities of implementing institutions should be carefully assessed, and their responsibilities clearly defined during project implementation. Overly high expectations of implementation capacity produces delays and disappointing outcomes.The Bank should act on financial control and audit problems early on to avoid large-scale irregularities.
P010395 | Basic and Primary Education Project | South Asia | Nepal | IDA |  | Human Development | Education | IDA | IPF | 1992 | 2000 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/711451474659818256/text/000020051-20140528130129.txt | http://documents.worldbank.org/curated/en/711451474659818256/pdf/000020051-20140528130129.pdf | Strategies targeting the neediest can increase their participation in education, particularly through interventions tailored to their needs (e.g. provision of books, scholarships, sanitary facilities for girls, literacy programs for women.- Parents and local communities must be closely involved in the delivery of educational services if the needs of diverse groups are to be met. Involvement is more likely if parents receive tangible incentives and see the fruit of their work.- Close donor coordination can effectively help overcome the obstacles of working in poor countries with limited accessibility. This means that donors must collaborate during appraisal and establish common financing and evaluative criteria.-The integration of project management structures into the regular education system is not possible unless there are clear reinforcing policies and a change in bureaucratic culture.
P010396 | CLOSED(T) TELECOMS. V | South Asia | Nepal | IDA |  | Infrastructure | Transport | IDA | IPF | 1992 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/587831475088132850/text/000020051-20140528130353.txt | http://documents.worldbank.org/curated/en/587831475088132850/pdf/000020051-20140528130353.pdf | Comprehensive sector reform takes time and continued involvement in a sector provides the Bank with the opportunity to support reforms step by step under various governments.The efficacy of a government corporation can be hampered by government salary scales, investment approvals, and procurement procedures. Only the establishment of a privately owned commercial company, operating under suitable regulation, provides the necessary autonomy to quickly expand service to meet demand and incentives to employees to become more consumer oriented and competitive.The successful private operation of value-added and other marginal telecommunications services creates new job opportunities and may reduce staff fears of privatization of the main operators. It may also encourage potential investors, as it provides a track record of commercial operations and demonstrates that the legal and regulatory framework is working satisfactorily.
P010398 | SECOND AGRIC.EXTENSI | South Asia | Sri Lanka | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1992 | 1998 | 1999 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/453231474588150126/text/000020051-20140521033733.txt | http://documents.worldbank.org/curated/en/453231474588150126/pdf/000020051-20140521033733.pdf | 1. Any radical change in the organizational structure (of extension services or any other public agency) should be preceded by a coherent national policy. Institutional change should be pursued within the framework of a well thought out strategy that recognizes the views of various stakeholders and potential non-public sector partners in service delivery.2. The adoption of new technology requires an appropriate enabling policy environment that allows farmers to reap the benefits of the new technology.3. New methods to deliver services such as agricultural extension need to be properly tested for their feasibility and effectiveness as a pilot program before they are expanded or scaled up. This is particularly true for approaches that are significantly different from the traditional system in place and call for a singnificant transformation of the behaviour and attitudes of many stakeholders. 4. Efforts to decentralize extension services must carefully consider the impact on the critical linkages with research, which often continue as a national program.5. Complex inter-institutional coordination activities may be beyond the scope of an individual project management unit, particularly when decision making is decentralized to local or provincial authorities.
P010398 | SECOND AGRIC.EXTENSI | South Asia | Sri Lanka | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1992 | 1998 | 2000 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/294161511188789495/text/multi-page.txt | http://documents.worldbank.org/curated/en/294161511188789495/pdf/multi-page.pdf | 6. Lessons Analytical foundations ofproject design\. An important lesson emerging from this project is the need for a proper assessment, either through economic and sector work or in-depth project preparation, of (a) the policy and other constraints to agricultural development; (b) the institutions and institutional framework for project implementation, including monitoring systems, staff capacity, and coordination mechanisms. Participation and ownership\. The lack of commitment of the various agencies suggests a much greater need for the participation of the agencies in project design and formal agreements among agencies to pursue a common objective. The importance of borrower ownership has been known for some time, but the experience of SAEP, implemented in a decentralized setting, demonstrates the importance of getting not only the central ministries, with which the Bank has traditionally had contacts, on board, but also to nurture ownership among the decentralized implementing agencies. Incentives and accountability\. Another old lesson is strongly reiterated by SAEP design. Even with an innovative, participatory, and farmer-centered methodological approach, to make the service delivery system truly demand-driven, it is critical to have incentive structures that hold service providers accountable to their clients, the farmers. The traditional bureaucratic setup, where performance is not linked to rewards or sanctions and accountability is primarily to superiors, will not yield an effective demand-driven system. Bank process\. As the Bank becomes increasingly decentralized, accountability and decisionmaking processes will become increasingly important. The Bank needs to resolve where the accountability for project outcomes will lie (with the task manager or country director). This has implications for decision making on important issues such as pre-mature closing of projects, and restructuring. As a development partner, the Bank also needs to be particularly aware of substantively involving the borrower in important decisions affecting investments, and to directly engage the borrower in negotiating options such as restructuring and closure.
P010399 | ENV. PROT. & RES. CO | South Asia | Pakistan | Blend |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1992 | 1999 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/421261474501668745/text/000020051-20140528125444.txt | http://documents.worldbank.org/curated/en/421261474501668745/pdf/000020051-20140528125444.pdf | Where technical assistance is a key element of a project, procurement arrangements should be completed before effectiveness.
P010400 | MAHARASHTRA POWER II | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1992 | 1998 | 2000 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/639961475075483111/text/000020051-20140522110141.txt | http://documents.worldbank.org/curated/en/639961475075483111/pdf/000020051-20140522110141.pdf | A sustainable solution to the problems of the power sector at the state level requires action to address their root causes: - the politicization of decisions, high non-technical losses due to theft and the lack of a commercial culture. This can only be achieved by means of a fundamental restructuring of the sector rather than a revitalization of existing SEBs as previously attempted.
P010401 | DOMESTIC ENERGY RESO | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1992 | 1998 | 1999 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/683481474501858460/text/000020051-20140522102637.txt | http://documents.worldbank.org/curated/en/683481474501858460/pdf/000020051-20140522102637.pdf | Nearly all of the ICR's lessons are of broad applicability, but on the other hand, they are mostly common-sense, standard international oil industry practices (e.g., account for uncertainty in reserves and variability of production rates; field-tested technology should be adopted; upsteam field development and investments in downstream facilities should be coordinated, etc.). If these were truly learned for the first time under this Project, then the Government of Pakistan's association with a Bank loan was indeed a very costly learning curve. If these are already well-known best practices in the petroleum industry, then they should not be presented in the ICR as lessons learned under the project.
P010405 | EAST.SADIQIA SO PHAS | South Asia | Pakistan | Blend |  | Sustainable Development | Water | IDA | IPF | 1993 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/568471474650342453/text/000020051-20140529210649.txt | http://documents.worldbank.org/curated/en/568471474650342453/pdf/000020051-20140529210649.pdf | Before considering investment in high cost sub-surface drainage, there should be preceding interventions in water conservation, surface drainage, improved water management and a program to identify residual subsurface drainage requirements.Field trials and investigations of drainage options should be completed before project appraisal.Farmers will participate in on farm drainage/irrigation improvements through use of their own equity - credit is not essential and equity ensures a strong stake in the success of implementation and subsequent operation.
P010406 | SUNSARI MORANG HEADW | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1993 | 1998 | 1998 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/435551474570229462/text/000020051-20140519064806.txt | http://documents.worldbank.org/curated/en/435551474570229462/pdf/000020051-20140519064806.pdf | * WUGs will not be sustainable unless government and project management uphold WUGs' authority to manage water and collect irrigation service fees.* The Bank must be more vigilant in imposing covenants regarding water user fees and their recovery. * Incentives to induce cost recovery apply to WUGs and project management, and it is essential these are fully explored and agreed at appraisal.
P010407 | ADP - RAJASTHAN | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1993 | 2001 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/591911474907436233/text/000020051-20140529204333.txt | http://documents.worldbank.org/curated/en/591911474907436233/pdf/000020051-20140529204333.pdf | Several important lessons are identified by the ICR. Two are repeated here. (i) Any hybrid policy reform cum multisectoral state wide investment project is bound to be a complex operation and in this case 12 departments of GOR were involved. This made Borrower coordination and monitoring and World Bank supervision difficult. Investments would have better been concentrated on fewer critical areas, that responded most directly to objectives, were technically robust and had a high chance of success. (ii) Under typically harsh field conditions of Rajasthan, especially when migratory practices are followed, animal breeding programs should avoid use of exotic stock and focus upgrading on selection within the locally adapted breeds.The ES expands on the above two lessons identified by the ICR. (a) In a situation where several policy reforms and investments are required in a sector, a two phased operation over a longer period of time could be planned. Attention could then be focused on the more critical policy reforms and investments that have wider impact in a first phase, followed by the others in a second phase. This would allow both the Bank and the Borrower to focus their energy on implementation issues in a few areas at one time. (b) Though animal breeding programs that use exotic stock have had tremendous success in some countries, the importance of adapting to local conditions cannot be under-estimated. Hence the importance of adequate technical studies during the project preparation stage to see what is likely to be successful in given socio-economic and climatic conditions.
P010407 | ADP - RAJASTHAN | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1993 | 2001 | 2006 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/766211468051260179/text/34578.txt | http://documents.worldbank.org/curated/en/766211468051260179/pdf/34578.pdf | 4. Lessons 4.1 The experience o fthe Rajasthan ADP project offers four lessons for future Banksupported state-wide multisectoralinterventions inthe agriculture sector inIndia and elsewhere. Lesson1\.When several policyreformsand investmentsare requiredin a sector, a multi-phaseoperationover a longerperiodmay bemoreappropriate.Early attention couldthen befocused on criticalpolicy reformsand the most crucial investmentsto createthe rightplatformfor subsequentinvestments.This would avoidthe simultaneous preoccupationwith meetingmultipletargets at the expense of a soundpolicyframework. The Rajasthan ADP was a hybridpolicy reform cum investmentproject. Infact the design began as a policy reform project and thenwas changed at a later stage into an investmentoperation. Itwas a complex state-wide operation that involved 12government departments. This made Borrower coordinationand monitoring andBank supervision very demanding. Boththe Government's coordinationunit andthe Bank supervision missions were caught up ingetting individual departments to meet their targets and gave less attention to how these achievements contributed together to supporting the Government's agricultural strategy, the realproject objective. Lesson2\. Monitoringand evaluationof outcomes shouldbeintegralto project design. Realistictargets and indicatorsneedto be linkedto objectives. Inthe RajasthanADP, M&Eoftheoutcome ofpolicyreform andtheinvestment components should have beenan integralpart o fthe project. The fact that it was not, resulted infocus on project outputs rather thanprogress on achievingoutcomes. Lesson3\. ComplexBankinterventionslikethe RajasthanADP requirestrongand constantBankmanagement oversightto ensurethe alignmentof implementation and designand strict adherenceto Bankproceduresandpolicies. The safeguard violation could have beenavoided hadthere beengreater vigilance exercised inapplying the Bank's Operational Directives. It i s well known that road construction, and even improvement, can potentiallyinvolve some measure o f land acquisition. Hence the Operational Directive on Involuntary Settlement should have been triggered andthe Bank should have worked with the borrower from the beginningto ensure that the Bank's safeguard policies were met. Lesson4\. Adequate understandingof the financialsituation of the government at the appraisalstage can helpensurethe financialhealthof a projectduring implementationandthe sustainabilityof activities supportedafter closure. Particularly after MTR, the tight fiscal situation o f the government adversely affected progress on a number o fproject activities. N o analysis was done at the project design stage to realistically assess government capacity to meet its financial commitment to a complex and demanding multi-sectoraloperation. Such an analysis would have allowed the Bank to be aware ofpossible financial constraints that the government could face and planupfront for such situations. IEG's Sector Lessons Note (World Bank2003) suggests that at the appraisal stage the following information should at least be compiled\. information on local fundingneeds for theproject period and at least five years beyond andincluding other significant incremental projects inthe sector; informationon the past five years o fbudget allocationto that sector and analysis o f any gap; supporting evidence o f changed government priorities for sectoral budgetary allocations ifbudget demandi s shown to be significantly beyondpast actuals.
P010408 | BIHAR PLATEAU | South Asia | India | IBRD |  | Infrastructure | Transport | IDA | IPF | 1993 | 2000 | 2001 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/277771475077049030/text/000020051-20140529203846.txt | http://documents.worldbank.org/curated/en/277771475077049030/pdf/000020051-20140529203846.pdf | The ICR identifies a number of important lessons, three lessons are repeated here:Readiness for implementation is crucial for completion of the project on schedule and achievement of its objectives. Actions that are critical for project implementation and need to be completed before credit/loan effectiveness should be carefully monitored.During project implementation adequate attention needs to be given to monitoring and evaluation and performance indicators to track project performance.Beneficiary groups need to be involved right from the project design stage for them to develop a sense of ownership and responsibility. The ES adds the following lesson - Projects that depend on grass root organizations for implementation need to realistically assess upfront whether adequate capacity is available. If such capacity is weak, then the project has to allow for adequate resources in terms of time and money to build this capacity.
P010409 | COMMUNITY WAT SUPP/S | South Asia | Sri Lanka | IDA |  | Sustainable Development | Water | IDA | IPF | 1993 | 1999 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/465391475079504167/text/000020051-20140526211336.txt | http://documents.worldbank.org/curated/en/465391475079504167/pdf/000020051-20140526211336.pdf | The ICR presents several important findings and lessons applicable to the project and useful for many future projects in Sri Lanka and elsewhere. One which should be further highlighted is the need for rigorous M&E during project implementation, the key for achieving sustained results. Similarly, the continued funding of TA activities is the key to critical institutional improvements.
P010410 | RENEWABLE RESOURCES | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1993 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/222541474485822080/text/000020051-20140607153647.txt | http://documents.worldbank.org/curated/en/222541474485822080/pdf/000020051-20140607153647.pdf | The ICR identifies some useful lessons. Ten lessons from the ICR are reproduced below.Adequate time must be allowed to develop innovative projects and the market for renewable energy. A specialized financial institution such as IREDA was essential at the beginning as new technologies were commercialized, but if market growth is to expand, broader participation by the financial sector is essential. Similar to rural electrification the world over, affordable financing accessible to rural consumers is essential for selling PV products in rural areas. Delivering rural PV services needs a partnership between key actors: rural financing institutions, product/service suppliers and preferably organized consumer groups. Assessment of land acquisition as well as payment of compensation should be completed prior to commencement of civil works to avoid delays in project implementation. The renewable energy program should be consistent with and embedded into the plan for power sector reform and restructuring.Supportive and predictable policies and regulatory framework are essential for market development. Tariffs and power sales rules should be fair to all parties for sustainable development of the sector. Careful attention should be paid to maximizing energy output rather than installed capacity. Regular review and rationalization of subsidy policy is necessary.
P010410 | RENEWABLE RESOURCES | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1993 | 2002 | 2004 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/365261468771275818/text/27076.txt | http://documents.worldbank.org/curated/en/365261468771275818/pdf/27076.pdf | Lessons Learned 58. The main lessons from this evaluation are as follows\. P Power sector reforms andrenewable energy commercializationshouldbepart o f an integrated strategy. P The Bankanditsclient countries shouldincorporateprovisionsto levelthe playing field between conventional andrenewable energy technologies while legallregulatory and other sector-level reforms are being designed and implemented. Relegating this to later fine-tuningposes serious risks to the commercialization o frenewable energy, as regulatory unpredictability andtariff uncertainties discourage local private investments. P Monitoring andevaluation systems shouldbedevelopedfor bothprojectand sector-level outcomes, which should distinguishbetween efficiency and equity indicators. This is essential insetting gridversus off-grid subsidies, designing output-based aid schemes, andpromoting investments as well as mitigating risks incapacityexpansionbasedonrenewables, since the sector indicatorswould send clearer signals to investors whether transparency and predictability inthe regulatory framework governing renewables are being achieved. b The GEF andother grant support operate inapower sector reformsetting, and thus should also be keyed to sector outcome indicators. Otherwise, focusing only on project inputs andprocesses (e.g., buyingdown the commercial interest rate) andoutput indicators (e.g., quantities o fsolar PVunits sold) fosters a culture o f dependence on grants and subsidies, which ironically works against the full commercialization o frenewables and hinders their ability to compete inthe market whenthese financial incentives are reduced or withdrawn. b Muchlearning-by-doing is involved innon-conventionalprojectssuchas renewable energy development and commercialization, which underlines once more the importance o fmonitoring and evaluation systems.
P010411 | JHARIA MINE FIRE CON | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1993 | 1998 | 1998 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/751001474496764528/text/000020051-20140519060610.txt | http://documents.worldbank.org/curated/en/751001474496764528/pdf/000020051-20140519060610.pdf | Nothing but the standard comments on the need to have realistic implementation schedules and to teaching the Borrower about Bank procurement procedures.
P010414 | FAMILY HEALTH II | South Asia | Pakistan | Blend |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1993 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/454131474501741380/text/000020051-20140529075727.txt | http://documents.worldbank.org/curated/en/454131474501741380/pdf/000020051-20140529075727.pdf | Both performance indicators and targets need to be agreed upon at appraisal and then used as a management as well as a monitoring and evaluation tool. An assessment of implementing agencies' capacities in both service delivery and management, especially financial management, should be part of project design. The integrity of the procurement process needs to be safeguarded at appraisal and throughout the life of the project. For multi-donor funded projects with parallel financing arrangements, a well-defined coordination mechanism for project effectiveness including targets and indicators, for timely and coordinated release of funds, and for joint monitoring and evaluation activities needs to be agreed upon at appraisal.
P010415 | 1992 FLOOD DAMAGE RE | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1993 | 1998 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/361611475083894313/text/000020051-20140519081917.txt | http://documents.worldbank.org/curated/en/361611475083894313/pdf/000020051-20140519081917.pdf | Simple, performance-based eligibility criteria can expedite selection of subprojects to be financed. In this case, projects with adverse environmental impact were excluded. Priority was given to irrigation and drainage repairs for which beneficiaries were willing to make supplementary contributions.
P010416 | POWERGRID SYSTEM DEVELOPMENT PROJECT | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1993 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/110301474665522850/text/000020051-20140604043021.txt | http://documents.worldbank.org/curated/en/110301474665522850/pdf/000020051-20140604043021.pdf | Three factors contributed to develop POWERGRID into a well-functioning and commercially viable transmission utility: (a) effective management with operational autonomy; (b) competent and experienced staff with a continuing human resource development program; and (c) adequate financial support.
P010417 | BALOCHISTAN PRIMARY | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1993 | 2000 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/469571474560534663/text/000020051-20140529073329.txt | http://documents.worldbank.org/curated/en/469571474560534663/pdf/000020051-20140529073329.pdf | Among the many lessons for the Pakistan context, several are of broad applicability and are not frequently mentioned in ICRs (OED's emphasis in italics).Lessons for EducationComplementing targeting priorities with appropriate targeting mechanisms have been shown to improve equity.Toward ensuring sustainability beyond completion, project processes and outcomes and, in particular, the implementation of agreed exit strategies should receive more attention from supervision missions from mid-term.Taking to scale successful interventions need to consider the time required to build additional capacity to ensure appropriate follow up and quality in the delivery of interventions. Too much too soon leads to serious operational drawbacks.Demand-driven interventions involving community participation in managing school-related issues have proved effective worldwide in reducing teacher absenteeism and in increasing access to schools---in this case, for girls, as well as boys.Needs-based teacher training activities involving periodic peer interaction and on-site follow up have proven effective to change teaching practices in the classroom.Ensure the involvement of qualified NGOs in the design and implementation of project-related interventions for which they have shown expertise.Among lessons learned for the Bank's management, the most important are that management should ensure that supervision missions avoid frequent changes in tactics, priorities and unwarranted design changes, and that they are backed appropriate budgets, sufficient time for field visits and adequate skills to address relevant issue. Among lessons learned by the Borrower, the most important are: planning should be undertaken at the start to ensure adequate financial resources for new structures and activities beyond the completion of the project; permanent staff should act as counterparts to technical experts to ensure that capacity-building remains within the DPE; the fees for experts should not be changed during implementation, local experts should used except in dire necessity, only qualified persons should be engaged, and TA costs should be controlled at 5% of total costs rather than the 10% in this project.
P010418 | KARNATAKA WS & ENV/S | South Asia | India | IBRD |  | Sustainable Development | Water | IDA | IPF | 1993 | 2001 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/584401475070530321/text/000020051-20140529211215.txt | http://documents.worldbank.org/curated/en/584401475070530321/pdf/000020051-20140529211215.pdf | (1) A sustained improvement in environmental health requires three ingredients: safe, potable water; sanitary excreta disposal; and health education;(2) Sustainable water supply and sanitation systems can best be assured by delegating the administration to the lowest, appropriate level which is to the village level through the establishment of village-based committees.(3) Financial sustainability requires user fees to be levied to pay for the costs of operations and maintenance. If, in addition, users are obliged to contribute something - in cash or in kind - towards the construction of the system they can be expected to care more for efficiency of investment and for the continued operations and upkeep of the facilities.
P010419 | PRIVATE FINANCE DEVELOPMENT PROJ (PFDP) | South Asia | Sri Lanka | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1993 | 1999 | 2000 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/671651474635236581/text/000020051-20140528120752.txt | http://documents.worldbank.org/curated/en/671651474635236581/pdf/000020051-20140528120752.pdf | IDA should support and encourage reforms when the government has a good diagnosis of the problems and a consistent policy framework to solve them. When the government lacks both the diagnosis and the framework, it tends to reform policies in an ad-hoc manner, without generating clear benefits to the country.Long lists of actions and studies cannot substitute for the solution of the main problem that plagues the development of the financial sector. In Sri Lanka, the fundamental problem in the financial sector was a public sector deficit of 10 percent of GDP, which the government financed with forced loans from the financial institutions at below market rates of interest. The deficit, thus, had to be reduced so that the financial institutions could offer more attractive interest rates and have more resources to lend to the private sector.Foreign loans granted to domestic institutions to onlend to entrepreneurs do not expand the supply of domestic savings if domestic policies discourage people and companies from savings, and discourage financial institutions from intermediating resources.
P010420 | Colombo Urban Transport | South Asia | Sri Lanka | IDA |  | Infrastructure | Transport | IDA | IPF | 1993 | 1999 | 2000 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/606871474659235827/text/000020051-20140526225815.txt | http://documents.worldbank.org/curated/en/606871474659235827/pdf/000020051-20140526225815.pdf | The ICR draws two broad lessons. First, that project objectives should be realistic and evolve during identification, preparation and appraisal. During that process sufficient institutional analyses should be undertaken to ensure that the means chosen would be implementable and likely to achieve the desired ends. The railways provides an example. A restructuring of a government service delivery department to achieve efficiency gains failed because it proved impossible. Restructuring a government department has thus, again, shown not to achieve the desired ends for efficiency, accountability, and improved service unless there is competition, that is, deregulation to allow private sector entry to market. Second, that it is difficult to provide effective supervision when there are many implementing agencies unless the projects are a part of the regular work program of established government entities with clear mandates within the project's scope. 'Ad hoc' project management units cannot solve fights over turf and do not contribute to the institutional strengthening of the implementing agencies.
P010420 | Colombo Urban Transport | South Asia | Sri Lanka | IDA |  | Infrastructure | Transport | IDA | IPF | 1993 | 1999 | 2003 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/572281468763781674/text/261380LK0PPAR.txt | http://documents.worldbank.org/curated/en/572281468763781674/pdf/261380LK0PPAR.pdf | LESSONS 0 The performance o f a wide range o f projects-not only those inconflict zones-is vulnerable to the impact o f war, especially through unexpected conflict events duringproject implementation. Projects will not do so well duringconflict as inapeaceful situation. Spatial separation o fa project from active conflict zones does not guarantee that an operation will be free o f conflict constraints. 0 Project design should not be blindto conflict, and must cautiously but explicitly address the constraints imposed. War-weary governments are unlikely to have strong ownership o f reform unrelatedto the causes o fthe conflict. Decentralization may go against centralized conduct o f war. Conflict generates a poor business climate that private firms themselves are unwilling to invest in. 0 Itis importantto focus upona clear vision o fthe intendeddevelopment results of a project, and to remain focused on them through systematic monitoring and evaluation. Inother words, the baseline shouldbe measured, the counterfactual clearly understood, and M&E supported and implemented.
P010421 | NORTHERN RESOURCE MANAGEMENT | South Asia | Pakistan | Blend |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1993 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/600801474396256551/text/000020051-20140528115838.txt | http://documents.worldbank.org/curated/en/600801474396256551/pdf/000020051-20140528115838.pdf | 1. With respect to the sustainability of community organizations: (i) keep to a manageable scale; (ii) plan for the post project period; (iii) develop NGO capacity to play an increasing role; (iv) use the Bank's new project instruments with longer commitments. 2. Community requested training programs on agricultural technologies, delivered within the village, can be a very effective technology transfer mechanism and may be appreciated more by beneficiaries than routine extension visits. 3. Thorough analysis of project and post-project local funds requirement should be carried out at appraisal. 4. Road construction, even road improvement, often involves some land acquisition and therefore falls under the Involuntary Resettlement OD calling for careful consideration of compensation arrangements.
P010421 | NORTHERN RESOURCE MANAGEMENT | South Asia | Pakistan | Blend |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1993 | 1999 | 2000 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/508241511188654165/text/multi-page.txt | http://documents.worldbank.org/curated/en/508241511188654165/pdf/multi-page.pdf | LESSONS 1 . Multiple component rural development projects can work if they focus on efficiency at the village level through community participation backed by efficiency of services through institutional reform and privatization. Complementarity between policy reform, investments at village level, and community institutions and processes should be reflected in the logical framework. 2. With respect to sustainability there are four main lessons\. (i) keep the community mobilization project element to a manageable scale this was done in this case; (ii) at least indicatively plan for the post-project period at appraisal with respect to both funding and operational design and prepare early for that transition this was not done1I; (iii) develop NGO capacity to play an increasing role partly done outside the project under the National Rural Support Program; and (iv) use the Bank's new project instruments with longer commitments -not available in this case at the time of appraisal. 2 3. Community-requested training programs on agricultural technologies, particularly those which enhance individuals skills to supplement household income and delivered within the village, can be a very effective technology transfer mechanism and may be appreciated more by beneficiaries than routine extension visits. For efficiency, a complementary combination should be sought. I. This reflects the borrowers comment no. 2, although it does not go as far as proposing a follow-on project which goes beyond OED's evaluative role. 2. The 1996 audit for the predecessor Integrated Hill Farming Development Project concluded similarly\. some time is likely to be required to build up effective relationships between communities and implementing agencies .oa longer implementing periodl.. is desirable. 4. Appraisal reports should analyze project and post-project local funds demand, compare these with recent budget allocations, and explicitly size the project against these findings. Where financial sustainability still remains an issue, they should outline a phased program of response, for example cost recovery, phased reduction in services, privatization, etc. 5. Road construction, even road improvement, frequently involves some measure of land acquisition and therefore falls under the Involuntary Resettlement Operational Directive, calling for careful consideration of the compensation arrangements. From the inception of project processing managers should invoke the Involuntary Resettlement Operational Directive and assist borrowers in ensuring that the Bank's safeguard policies are met. 6. The absence of a suitable credit line limits the options in community driven development and has implications for sustainability. This raises the importance of addressing credit delivery issues in a pragmatic way.
P010423 | NTPC POWER GENERATION | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1993 | 1999 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/808511474481662944/text/000020051-20140529070432.txt | http://documents.worldbank.org/curated/en/808511474481662944/pdf/000020051-20140529070432.pdf | (a) When Bank policies and standards to be agreed in a Bank project are more restrictive than those prevailing in the country, during project appraisal and negotiations or earlier during project preparation, all parties concerned in the country should be made aware of the implications entailed by such agreement. (b) An independent monitoring panel has proven to be an excellent instrument to help the Borrower and the Bank assess performance and likely outcomes of environmental, resettlement and rehabilitation programs. (c) The Bank should establish the principle that environmental studies that are included in projects financed by the Bank, are to be made readily available to concerned individuals and NGOs of the country; and (d) the increasing use of independent monitoring panels in Bank projects raises funding issues (in this project, the cost of the IMP was financed under the Bank's supervision budget --see below).
P010424 | NATIONAL LEPROSY ELIMINATION PROJECT | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1993 | 2001 | 2002 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/221161474587006428/text/000020051-20140602103809.txt | http://documents.worldbank.org/curated/en/221161474587006428/pdf/000020051-20140602103809.pdf | The ICR highlights some of the following lessons: 1)When disease burden is high, centralized vertical organizational structure is useful. When disease burden is low, integrated approach is more efficient. 2) Role of states in project implementation needs to be strengthened. 3) Strengthening of general health system capacity is necessary to address long-term issues of diagnosis and treatment. 4) Effective program management requires high quality, recent epidemiological and management information. 5) Effective targeted programs require high levels of coverage and saturation. It is difficult to identify, reach and cover hard to reach groups such as the urban poor, women and scheduled tribes/casts.
P010447 | PUBLIC SECTOR ADJUST | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1994 | 1996 | 2006 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/313441468065937476/text/34101.txt | http://documents.worldbank.org/curated/en/313441468065937476/pdf/34101.pdf | Lessons 0 A series o f one-tranche loans in a programmatic framework can be an effective instrument for support reforms o f a country with a poor track record. However, effectiveness o f a series o f one-tranche loans depends on a willingness to withhold lending until a critical mass o f previously-agreed prior actions have been undertaken. The delay between the SAL and the first SAC was particularly effective in this respect. 0 Complex or politically-difficult sector reforms are best supported through dedicated sector operations. A multi-sector operation can play only a secondary or facilitating role when dealing with institutional development (as in tax reform or civil service reform), deep-rooted reluctance to reform (as in power), need for specific funding to offset costs o f adjustment (as in banking), or weak service delivery (as in health and education). O f course, even a dedicated sector operation can succeed only if there i s commitment to reform.
P010448 | Forestry Research Education and Extension Project | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1994 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/783881474504834139/text/000020051-20140607152205.txt | http://documents.worldbank.org/curated/en/783881474504834139/pdf/000020051-20140607152205.pdf | The ICR identifies some important lessons. Two lessons from the ICR are repeated here. (i) Design of a project involving multiple implementing agencies should not rely upon overall coordination by a national ministry, unless that ministry has already demonstrated its capacity for such coordination; (ii) Sustainability considerations must be thought through right from the very beginning of the project. This includes sufficient care in the process of formation of groups/institutions, capacity building efforts and having a conscious strategy for external inputs (including NGOs). The ES adds another lesson: India has the largest number of poor in the world, a large percentage of whom are dependent directly or indirectly on forests for a living. There is need to strengthen the research input for forest activities that impact the poor, i.e those focused on improving productivity of non timber forest products, if future forest sector activities are to have a significant poverty reduction impact.
P010449 | ANDHRA PRADESH FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1994 | 2001 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/603751475092555759/text/000020051-20140529211259.txt | http://documents.worldbank.org/curated/en/603751475092555759/pdf/000020051-20140529211259.pdf | (i) In projects with a clear poverty alleviation objective alongside an objective of regenerating forest cover, development objectives should be framed at least partly in terms of poverty alleviation. This should be done in a way that is monitorable and should be backed up in design by a monitoring and evaluation system capable of measuring poverty impact. (ii) Policy issues such as seedling pricing, and coordination with other departments and agencies should be identified and dealt with ex-ante. Solution to these issues requires commitment from the State and often from the Central government. Hence, if they are not sorted out at the design stage, they may never get resolved and may dampen the implementation experience of the best of projects. (iii) In the early stages of implementation of a community forestry program, compensatory benefits play an important role in establishing a cooperative relationship between the community and the forest department. However, in the long run, returns from the forest should be sufficient for the community to have a vested interest in the protection of the resource. Hence sustainability issues need special attention right from the design stage of the project. (iv) Development of an efficient monitoring and evaluation system is crucial to the establishment of a community based forest protection and management system. This is so not only for assessing outcomes and impacts but for making efficient mid course corrections, as and when required. (v) In the past, social forestry efforts have met with limited success. However, there is need to re-focus attention on social forestry as tree plantations outside the forest area play a crucial role in meeting the diverse demands from the forest sector.
P010449 | ANDHRA PRADESH FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1994 | 2001 | 2003 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/373651468051855587/text/multi0page.txt | http://documents.worldbank.org/curated/en/373651468051855587/pdf/multi0page.pdf | LESSONS Several generic lessons from this project underscore findings elsewhere. 1. It is possible to tum around the strategy of a large public entity from command-and-control to community participation quite quickly given commitment at the top. It is a longer process to develop community skills and create incentives throughout the service. Therefore, sustained skills development for govemment staff especially at the lower levels and for other stakeholders in participatory processes over periods longer than a single project is necessary. 1. In Annex B the AP Forest Department dispute that there was any forced eviction. They also note that encroachment, being illegal, cannot be compensated. They argue that no VSS members complained of lost land. The mission, based on field observation, discussion with NGOs, and findings of the subsequent OED Tribal Study Survey, believes that some households, although an unknown number, did loose land-based income sources as a result of the project without explicit arrangements aimed at fully and sustainably replacing that income. As noted later in the report, the mission is aware of the complexity of this issue. Under the follow-on project it appears it is being addressed through a Ressettlement Plan. 2. In any tribal forest situation there is a high potential for triggering involuntary resettlement. During project review, within the new safeguard monitoring management formats, Bank management should carefully question claims in natural forest management projects that no involuntary resettlement issues are anticipated and focus on this issue should be sustained during supervision. 3. Even where a high percentage of the poor are forest dependent, it is much easier to manage forests for trees than for the poor. Equitable distribution of the benefits needs early attention through pro-poor policy, pro-poor government and community processes, and pro-poor resource management practices. 4. Economic analysis of community development interventions will usually be incomplete if it assesses only the net benefits associated with members themselves or their allocated area. First, because others may have previously utilized resources inside the boundary, and second, because members may have previously utilized resources outside the boundary. Whether the net costs and net benefits balance out is an empirical question requiring attention.
P010450 | PRIVATE SECTOR ENERGY DEVELOPMENT II | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1995 | 2000 | 2002 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/465961475100327594/text/000020051-20140602104817.txt | http://documents.worldbank.org/curated/en/465961475100327594/pdf/000020051-20140602104817.pdf | Sector Reforms and IPPs: Private investment does not substitute for reform, and should not be attempted without at least the basic reform elements in place. Benchmark Pricing vs. Competitive Bidding: Competitive bidding for IPPs combined with incentives for providing least cost power could have resulted in lower trariffs, prevented too many and suboptimal projects being developed, and promoted transparency.Important Issues in Managing Large IPPs : These include: tailoring public financial support and guarantees to facilitate an efficient investment program; having an efficient fuel supply policy; allowing IPPs to procure fuels in competitive markets, both foreign and domestic; creating capacity to manage IPP contracts; and ensuring efficient plant dispatch. An option for gaining valuable experience without much risk is to begin with a small IPP.Due Diligence by Other Lenders: Risk mitigation measures provided in the security package may not be sufficient when the underlying economics are compromised by an unsound macroeconomic situation in the country.Procurement: International competitive bidding -- for IPP concession on basis of price -- leads to greater transparency, reduces the risk of corruption, and allows more flexibility for Bank financing.Contingent Liabilities: Where contingent liabilities are likely to be an important issue, a monitoring system -- perhaps at the Central Bank -- ought to be put in place.Covenants: Material covenants that may be difficult to enforce through measures such as suspension of disbursements could be designed as conditions of loan effectiveness, or other remedies designed according to the needs of the situation. At the same time, threat of suspension is not practical when it is applied to a private sector transaction i.e. the Bank cannot penalize the private sector for inaction by the government on an unrelated matter. On another count, the Bank should not encourage essentially commercial provisions such return on equity as part of the covenants.Corruption Allegations: It is difficult for the Bank to maintain an "honest broker" role in a complex project when different parts of the Bank Group often play conflicting roles -- IFC as a lender to IPPs seeking to mitigate its reputational risk; the Bank's Project Finance Group trying to mitigate calls to the Partial Risk Guarantee; and the Bank's macroeconomic team advising on the macroeconomic agenda. In dealing with corruption, the Bank should encourage the government and its agencies to pursue matters strictly according to law and internationally recognized due process, while honoring contractual conditions.Renegotiations: Renegotiations (or indeed any negotiations) will more likely result in prompt and mutually acceptable solutions when they occur in a commercial atmosphere, free of coercion.Mitigating Foreign Exchange Exposure: Financial stresses generated due to currency mismatch between liabilities and ultimate source of revenue (in this case domestic consumers) can be mitigated if the ultimate revenue source is linked wherever possible to foreign currency such as for electricity sales to export-oriented industries.
P010452 | SINDH SPECIAL DEVELO | South Asia | Pakistan | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1994 | 1999 | 2001 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/164401474488713979/text/000020051-20140529065614.txt | http://documents.worldbank.org/curated/en/164401474488713979/pdf/000020051-20140529065614.pdf | (1) The project clearly lacked ownership, and is another unfortunate example of how lack of ownership dooms a project. A systemic approach should be taken whenever a large traffic management program is formulated. (2) Risk analysis should be taken seriously. This holds for the project as a whole, as well as many of its components. For example, better risk analysis might have averted proceeding to construct an overpass over railroad tracks which were only infrequently used at the time of project formulation and which ceased to be used even while the project was being implemented.
P010453 | BALOCHISTAN NRM PROJ. | South Asia | Pakistan | Blend |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1994 | 2000 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/181191475099333584/text/000020051-20140529210734.txt | http://documents.worldbank.org/curated/en/181191475099333584/pdf/000020051-20140529210734.pdf | Awareness of the importance of improved governance in natural resource management is crucial to build capacity in the relevant institutions;It is important to link the policy reforms and concrete investments proposed in a project. In this project, there was a great disconnect between the institutional and environmental rehabilitation activities of the project. This preempted an effective synergy between the two components of the project. For instance, EIA regulations were implemented but no enforcement activities were implemented by the project to monitor mitigations. As a result pollution continued unabated. Allowing flexibility in disbursement scheduling and avoiding frontloading at the beginning of the project could minimize misappropriations of funds.The pace at which activities have to be implemented has to be set according to the institution's capacity to absorb the new increase in activities and funding; The project experience shows that, particularly in sensitive arid/semi-arid ecosystems,community participatory land management systems are likely to be more successful.
P010454 | HIGHER EDUCATION PROJECT | South Asia | Nepal | IDA |  | Human Development | Education | IDA | IPF | 1994 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/842291474504862389/text/000020051-20140607152501.txt | http://documents.worldbank.org/curated/en/842291474504862389/pdf/000020051-20140607152501.pdf | (a) Higher education policy reform is a long-term process that needs continued support over a protracted period; reform requires patient discourse with and broad dialogue among all stakeholders; and incentives can make a significant difference(b) For cost recovery initiatives to produce sustainable improvements in education quality, they must be accompanied by a strong commitment for continued public support(c) Projects of high complexity -- such as university reform -- are unlikely to capture all intricacies or anticipate every eventuality, so project implementers and supervisors should be able to adjust project design with Government and IDA management support(d) In reform projects, achievement of development objectives must be measured by reform implementation, not by specific activities.(e) Stakeholder consensus up front greatly facilitates reforms, but a lack of consensus can sometimes be overcome later(f) Decentralization creates new incentives and stimulates new and productive thinking among(g) Runaway university enrollment expansion can be controlled, despite strong student protests, if the authorities are determined(h) Bank task team leader continuity is a strong positive for successful project implementation.
P010455 | BLINDNESS CONTROL | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1994 | 2002 | 2003 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/784041474656123315/text/000020051-20140612062051.txt | http://documents.worldbank.org/curated/en/784041474656123315/pdf/000020051-20140612062051.pdf | Effective partnerships. Ways were found to effectively involve NGOs and private providers which could usefully be emulated elsewhere. These efforts were cost-effective, expanded the reach of the program into peripheral areas and contributed to long-term sustainability.Monitoring and evaluation mechanisms utilizing tools such as the Rapid Assessment Survey can help steamline the program, identify problem areas and organize effective responses. Defining indicators of success in terms of outcomes can have a significant impact on how a project is managed.Context-specific packages of services need to be planned for remote and rural areas. Lack of eye carea facilities, poor transport and inadequate communication in these areas require different service packages than those used in more built-up areas.The introduction of best technical practices. The Bank utilized its comparitive advange to the fullest in this project, by providing technical assistance to introduce state-of-the art technology that would have taken vastly longer to disseminate.Attention to stakeholder and beneficiary needs and concerns. Despite the introduction of superior technology, the project could have failed had needs and concerns of stakeholders and potential beneficiaries not been adequately taken into account. Particulary in remote areas, gender disparaity, low literacy, poverty, lack of motivation, taboos and suspicions could have resulted in low demand. The way the project overcame these problems, through a participatory preparatory process, well-designed beneficiary assessment and KAP studies, and targeted IEC and communication programs should be studies for possible use elsewhere.
P010456 | SOCIAL ACTION PROGRA | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1994 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/991161474895145239/text/000020051-20140519082810.txt | http://documents.worldbank.org/curated/en/991161474895145239/pdf/000020051-20140519082810.pdf | The ICR identifed four pertinent lessons. The sector investment approach proved effective in establishing policy dialogue and influencing expenditure levels, but time and perserverance are required to establish innovations in the targeting of funds and the reform of service delivery. Improving governance and financial management are important prerequisites for success, including defining rules of behavior and monitoring compliance. To win and sustain ownership, early involvement of provincial authorities and stability of key staff are essential. Supervision of sector investment credits covering all social sectors is demanding and resource-intensive but pays off in terms of dialogue with government agencies at all levels and responsiveness to difficult issues arising---as long as, as the ICR emphasises, supervision staff have policy-based lending experience and broad-based sector skills. That the SAPP approach may inadvertently promote over-centralization is an important observation in the borrower's report and deserves further examination. It suggests that, before launching complex and untested initiatives, more modest approaches should be tried.
P010457 | Family Welfare Project | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1994 | 2002 | 2003 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/479491475077757884/text/000020051-20140607153435.txt | http://documents.worldbank.org/curated/en/479491475077757884/pdf/000020051-20140607153435.pdf | The units of government below the center that are responsible for project implementation need to be as much committed and involved in project design as is the center. Management structures and implementation arrangements must be tailored to the context and environment of the different implementing units, in this case, states; a single model is unlikely to be appropriate in all cases. An adequate assessment of the impact of training on quality of services requires more than an end-line survey asking trainees whether they benefited; it requires direct observations of service quality itself.Project outcomes appear to suggest that training of large numbers of para-medical staff requires in-house training capacity, while the implementation and management of a behavior change strategy may best be done by a private sector firm. This is an interesting hypothesis that should be tested elsewhere.If community involvement is a goal of a project, the communities should be involved in the design of the project--for example, in the selection of sites for health facilities and in deciding on ways to involve and utilize volunteers from the community.
P010458 | POWER SECT. DEV. PRO | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1994 | 2001 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/903771474650654739/text/000020051-20140607145615.txt | http://documents.worldbank.org/curated/en/903771474650654739/pdf/000020051-20140607145615.pdf | (a) A program to unbundle and restructure a large organization is not likely to succeed if implemented from within the organization. It would be advisable to undertake the reform program through a management team and agents who are at the same time committed to the reform and empowered by the Government with a full mandate and authority to carry out the restructuring and unbundling.(b) In the power sector, a privatization program should give initial priority to the privatization of the power distribution companies rather than the privatization of the power generation plants.(c) An active campaign of public awareness and dissemination of the power sector reform will help employees, customers, others stakeholders and public at large to understand the rationale and benefits/costs entailed by the reform program. Radio and TV media, the Internet, and seminars and workshops would be the appropriate instruments to carry out the campaign.
P010460 | POPULATION & HEALTH | South Asia | Nepal | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1994 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/792311474563977068/text/000020051-20140602114053.txt | http://documents.worldbank.org/curated/en/792311474563977068/pdf/000020051-20140602114053.pdf | Â§ Clarification of the role of the PIU vis-Ã -vis a MOHâ€™s implementation unit is important at the time of Project design as well as implementation, to reduce bureaucratic ambiguity and potential rivalry. Â§ Synergistic development of infrastructure and service/logistics capability can result in demonstrable improvements in coverage and utilization, even in very poor countries.Â§ In community-based interventions, early and steady involvement of community leaders and end-users results in better ownership, support, and use of facilities.Â§ In the absence of government commitment to donor coordination, the Bank should take the lead in advocating and advancing such coordination.
P010461 | MADRAS WATER SUPPLY II | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1995 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/210631475088604163/text/000020051-20140613025831.txt | http://documents.worldbank.org/curated/en/210631475088604163/pdf/000020051-20140613025831.pdf | Under conditions of acute water scarcity, high socioeconomic returns can be expected from leak detection and reduction programs;Future water projects must be preceded by a thorough risk analysis when there is reasonable doubt about the sufficiency of available water sources; the effective capacity of each project component is also critical;When there is an increase in the number of outsourced services, it is important that this be matched by an appropriate number of trained officials to monitor and control their activities;There should be an effective balance between domestic and commercial/industrial water consumers when tariffs are drawn up.
P010463 | INDUS POLLUTION PREVENTION | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1995 | 2003 | 2004 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/923341474492993520/text/000020051-20140612084720.txt | http://documents.worldbank.org/curated/en/923341474492993520/pdf/000020051-20140612084720.pdf | A line of credit targeted at pollution prevention requires a lot of upfront work on the screening and appraisal of sub-projects. There is a need to ensure that the financial intermediaries (FIs) have an adequate comprehension of the technical standards that will be enforced by the Bank as a condition for approving sub-loans.Loans to FIs need to be designed in the context of the impact of alternative sources of finance available from other donors and parallel Bank programs. Consideration should be given to more flexible project design, perhaps not making the FI loans effective until they are specifically requested. Distinguishing between financing "pollution control" and "pollution prevention" investments may be of less value than an integrated approach which considers cost-effectiveness and permits both kinds of investment. Credit resources should be focused on priority sites or zones where the marginal benefits are high and project investments can reinforce regulatory enforcement .
P010463 | INDUS POLLUTION PREVENTION | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1995 | 2003 | 2007 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/371501468258578024/text/38472.txt | http://documents.worldbank.org/curated/en/371501468258578024/pdf/38472.pdf | 4. Lessons 4.1 The ICRsfor bothoperations contain a number of relevant findings and lessons, focusing on specific project design and implementation issues. The PPAR agrees with these observations, which will not be repeated here. Unfortunately, moreover, the ICR for PCP and MTRfor IPPPwere not carried out sooner, so that their lessons and recommendations could have been taken into account earlier inthe life of the follow-on operation. As a result, it experienced many o f the same design-related problems encountered by IPCP. This timing disconnect, while perhaps unavoidable given the Bank's (inretrospect, clearly premature) decision to press ahead quickly with the processing of IPPP, nevertheless suggests an important generic lesson\. theBank should not goforward with new (even complementaryfollow-on) projects that attemptto extendand/or replicatepreviously untesteddesign approaches when there has been insufficient opportunity to monitor, evaluateand learnfrom the implementation experienceand results of thefirst operation.Adequate monitoring and evaluation mechanismsare alsoparticularly important nder thesecircumstances. 1\. 4.2 A second lesson concerns the way the objectives of these projects were framed\. to support GO1efforts to prevent and alleviate industrialpollution and to promote cost-effective pollutionabatement from industrial sources. These are general objectives that focus on processes rather than concrete results interms of environmental q~ality.~'However, by expressing project objectives interms of support to processes rather than attainment of outcomes, there i s no incentive to buildin monitoring and evaluation mechanisms that focus on environmental results, without which it i s impossible to determine what the actual environmental impact of the actions taken has been. This was clearly the case with both IPCPand IPPP. To the extent possible, therefore, the objectivesof Bank-supportedenvironmentprojects should identifi upfront thespecific outcomes they seek to achieve in terns of improvements in environmentalquality. 4.3 Other general lessons which can be drawn from this experience refer to the approach to pollutionmanagement followed in IPCPand IPPP, which was clearly a partial one. While industrial pollutionwas an important contributing factor to overall air and water quality problems inIndia in the 1980s and OS, and the projects' focus on the most highly pollutingindustrial subsectors and establishments by targeting them and the states where they were primarily locatedwas not inappropriate, these efforts should have beenplaced in the context of more comprehensivenational and localpollution abatementstrategies, involving thefull range of contributing sectors (in all likelihood including urban sanitation, transport, energy and even agriculture, as well as industry) and suitableactions to address air, water?and land degradationproblems in a more spatiallyfocused way. 59. Many early Bank environment projects had similar objectives, so IPCP and IPPPare not unique inthis regard. 4.4 By not doing so, even though project environmental outcomes appear to have been positive, in that they did reduce emissions and effluent discharges by specific polluting industries, they may not have had a significant impact in terns of improving overall ambient air and water quality in the places where these industrialplants are situated!' This could havebeen the case either becausethe establishments involvedare spatially dispersed, becausenon-industrial sources of air and water pollution were not addressed at the same time at the same locations, or both. Inany event, no information was collected that would allow an assessment of these potentialimpacts on ambient environmental quality. 4.5 Inshort, these operations, with their exclusive focus on (in all likelihood, dispersed) industrial sources, may havebeen necessary, but not sufficient, to resolve broader air and waterpollutionproblems inIndia, even inthe specific localities where project-related investments were made. Nor i s information providedinany of the project documents (either ex-ante or ex-post) about the relative importance of industrialversus other sources of air and water pollution inthe specific localities where project interventions occurred. Hence, it is impossible to determinethe relativepriority of addressing industpial, as compared with other, sources of pollution at anyparticular locality, or more generally. Thisshould, infact, have been the startingpointfor Bank involvementin this regard. 4.6 By not taking an area-based approach to addressing pollution problems, the Bank missed an opportunity to implement one of its own specific recommendations following its assessment of GOI's EnvironmentAction Program in 1995. Why this disconnect occurred i s unclear, but it would appear that the staff assessingthe EAP and managing preparation of IPPPwere either not sufficiently in communication (or agreement) regarding how the Bank should approach pollution abatement in Indiaor that there was simply too much inertia inthe design o f TPCP that was carried over without much question into IPPP. 4.7 The approach to industrialpollution management through lPCP and IPPPwas also a partial one in that it did not incorporate thefull range of instruments which could have potentially been used to achieve pollution prevention and control objectives. The approach followed did involve a combination of carrot (i.e., effectively subsidized credit for industrialpollution abatement investments, grant financed Common Effluent Treatment Plants, demonstration projects, etc.) and stick (i.e., effluent charges, strengthening of SPCBs to enhance their capacity to enforce pollution control legislation and monitor industrial compliance). And the two acting together, particularly stronger enforcement on the part of environmental authorities, do generally appear to have had a positive result interms of reducingpollution inthe target industrialsubsectors, at least among the larger establishments. However, public disclosureof polluting industries, especially inthose cases where compliance problems persisted, could also have been used as a way of inducing offenders to adopt less pollutingand/or resource saving technologies and better waste management practices. This approach has proven highly 60. Or as the IEGICR review for IPCPput it lines of credit gearedto environmentaIIy related investment by private entities are likely to provide little assistance inachievingbroader sectoral objectives. cost-effective in other countries such as Indonesia and could also be particularly so in India given growing public awareness of the health and other costs associated with pollution, together with the increasingly proactive role of environmentalNGOs, the media ,and the court system. The associated lesson i s that Bankprojects seeking to improve the environment, whether in a single sector such as industry or more generally, should use all available means to achieve this objective. 4.8 Institutional strengthening of the State PollutionControl Boards was an important objective of both Bank operations. This i s apersisting need clearly recognized by the Boards themselves. More generally, institutional capacity buildingfor environmental management (as for many other purposes) tends to bea long-termprocess that requires continuous support. In this regard, the Bank missed an opportunity to be more helpfulto the SPCBs by not granting afurther extension at i! time when IPPP's implementation was clearly improving.62 This reportedly occurred becauseBank management was more concerned with removing an unsatisfactory project from its portfolio than continuing to support key client agencies when they were making increasingly good use of Bank assistance. The corresponding lesson is that inproject extension decisions, development effectiveness considerations should takeprecedence over internal Bank portfolio quality)' concerns. 4.9 Finally, inaddition to the need to approach pollution management challenges ina more holistic and spatially strategic way, a number ofprioritiesfor potential future Bank and/or other donor support were confirmedindiscussions with environmental authorities and other national stakeholders during the PPAR mission.63 These include\. Within the industrial sector, preventing and controllingpollutionfrom small and medium-scale establishmentsthrough better functioning CETPs and other means appears to be the principal on-going challenge, together with collection and disposal of hazardous waste.Both at the central and state government levels, GO1 recognizes the need to improve the design, implementation and operation of CEPTs, to focus more on smaller polluting industries, and to properly address hazardous waste issues from both bio-medical and industrial sources.
P010464 | DISTRICT PRIMARY EDUCATION PROJECT | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1995 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/664661474849165807/text/000020051-20140612100015.txt | http://documents.worldbank.org/curated/en/664661474849165807/pdf/000020051-20140612100015.pdf | This Project made important contributions in showing: the power of strong government ownership of the various intervention strategies at all levels coupled with strong support from resident Bank professionals; the desirability of focusing on a few simple and measurable educational quality and access targets (results);the desirability of building local level institutions/channels to deliver services (block and cluster resource centers) supported professionally by existing entities at the district, state, and national levels;the positive impact of good analytical work during preparation coupled with the government's determination to foster change based on experience and field-based lessons; the decision to not to use international consultants, even when they might have helped in such things as improving data quality, reporting and use of outcomes, suggests that other ways beside the use of loan money should be explored as ways to make international expertise available to IDA supported projects.
P010467 | Colombo Environmental Improvement | South Asia | Sri Lanka | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2001 | 2002 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/656531474898903332/text/000020051-20140607143623.txt | http://documents.worldbank.org/curated/en/656531474898903332/pdf/000020051-20140607143623.pdf | In designing projects to undertake activities where there is little local experience, and where several agencies will be involved in implementation, either en extended preparation period is required to ensure that the activities or agencies are ready for implementation, or thew scope of the project should be reduced.Prequalification of contractors is important. In particular, emphasis should be placed on the international experience and previous performance of potential contractors, and it is important to verify this dataIn technically complex projects, in particular, the Bank should not allow lending/portfolio pressure to determine the timing of project approval.The Bank should avoid changing the Task Team Leader between appraisal and negotiations.
P010467 | Colombo Environmental Improvement | South Asia | Sri Lanka | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2001 | 2003 | PPAR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/572281468763781674/text/261380LK0PPAR.txt | http://documents.worldbank.org/curated/en/572281468763781674/pdf/261380LK0PPAR.pdf | LESSONS 0 The performance o f a wide range o f projects-not only those inconflict zones-is vulnerable to the impact o f war, especially through unexpected conflict events duringproject implementation. Projects will not do so well duringconflict as inapeaceful situation. Spatial separation o fa project from active conflict zones does not guarantee that an operation will be free o f conflict constraints. 0 Project design should not be blindto conflict, and must cautiously but explicitly address the constraints imposed. War-weary governments are unlikely to have strong ownership o f reform unrelatedto the causes o fthe conflict. Decentralization may go against centralized conduct o f war. Conflict generates a poor business climate that private firms themselves are unwilling to invest in. 0 Itis importantto focus upona clear vision o fthe intendeddevelopment results of a project, and to remain focused on them through systematic monitoring and evaluation. Inother words, the baseline shouldbe measured, the counterfactual clearly understood, and M&E supported and implemented.
P010470 | Financial Sector Deepening and Intermediation Project (FSDIP) | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1995 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/917881474565678576/text/000020051-20140607174341.txt | http://documents.worldbank.org/curated/en/917881474565678576/pdf/000020051-20140607174341.pdf | 1. Loans (credit lines) to banks are not an effective inducement to reform. The cancellation of the project's credit line and the privatization (supported by the subsequent BSAL) led to improvements that were vainly sought through the FSDIP and earlier projects.2. The limitations that TA could remedy, while undoubtedly prevalent, are often the excuse but rarely the impediment to policy reform, especially in countries like Pakistan which has excellent commercial bankers. Any skills that the central bank lacks could have been purchased domestically (with revenues from seigniorage). The ICR of the BSAL emphasized the importance of "political will" to reform, not technical capabilities.
P010473 | TUBERCULOSIS CONTROL | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/468921474555669129/text/000020051-20140615110734.txt | http://documents.worldbank.org/curated/en/468921474555669129/pdf/000020051-20140615110734.pdf | State ownership and management capacity and the articulation of clear objectives and management guidelines are critical for effective implementation of TB program activities at the decentralized levels. The TB program initially used a center-to-district model, which caused states to have inadequate involvement in program planning, management and oversight, and, as a consequence, limited ownership and effectiveness.Allowing local health providers and patients to choose community volunteers allowed the engagement of a broad range of persons of diverse background and the significant involvement of women, and resulted in improved response to the particular needs and situations of target groups at the local level. The involvement of private practitioners in the RNTCP was instrumental in widening the reach of DOTS services and in ensuring that TB patients of these providers receive quality DOTS. The RNTCP has also had promising experiences with many NGOs and voluntary self-help groups in tracking smear positive patients, providing treatment and following them up.Well developed monitoring and evaluation at all levels of a program encourages pro-activity in the identification and solution of problems. Intensive monitoring and supervision of all aspects of the program at every level has been essential to the success of the program. The program has been able to publish and distribute widely a quarterly and annual performance report, summarizing the comparative performances of each state and district, and the timely receipt of the quarterly reports has greatly facilitated this activity.Planning for program extension should include plans to enhance staff capacity, both qualitative and quantitative.A firm and consistent position on the part of the Bank when dealing with serious implementation problems can result in significant improvements in implementation performance. The Bank's insistence on contracting out procurement responsibilities resolved the issue of inadequate procurement capacity, which was slowing implementation considerably.
P010475 | Road Maintenance and Rehabilitation | South Asia | Nepal | IDA |  | Infrastructure | Transport | IDA | IPF | 1994 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/782501474852823267/text/000020051-20140526230306.txt | http://documents.worldbank.org/curated/en/782501474852823267/pdf/000020051-20140526230306.pdf | There are two broad lessons. First, a coordinated and coherent approach by multiple donors working together toward a well-focused and clearly articulated sectoral objective (e.g. improved road maintenance) yields results. This is particularly useful to the donors and the government, especially if there are periodic reviews and exchanges to ensure integration of experiences at the managerial levels. Second, project preparation and appraisal should focus on sector program preparedness rather than just the economic evaluation of individual projects. In Nepal, as in many other countries, road designs and cost estimates were out-of-date when implementation started. It would have helped and contributed to sustainability, if there had been a recurrent program preparation process supported by good cost, traffic and road condition information. In the current project, the introduction of 3-year rolling program was not achieved.
P010476 | Tamil Nadu WRCP | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1995 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/604181474649821377/text/000020051-20140613052041.txt | http://documents.worldbank.org/curated/en/604181474649821377/pdf/000020051-20140613052041.pdf | This innovative project has a number of lessons:(1) The long period of pre-project policy dialogue and the long, detailed project preparation established a strong strategic direction for the project. This helped sustain the project in the face of two changes of state governments in 1996 and 2001.(2) A dramatic paradigm shift in the government's approach to managing a key resource such as water requires extensive training of government staff, WUAs, farmers, and even of NGOs involved in delivering such training. Training needs are often underestimated and training capacities of NGOs to provide training often overestimated.(3) Irrigation projects should include an agricultural support services component at the outset in order to enhance their economic impact.(4) The separate component for land acquisition and economic rehabilitation worked well for acquiring land, but faced some limitations in rebuilding the livelihoods of those adversely affected by the project. (5) Revision of water rates involves not only political will but also assurances that revenues so raised will result in improved services.(6) Involving intended beneficiaries in planning, implementation, and monitoring can improve transparency, instill a sense of ownership, and reduce conflicts.(7) Covenants which have little direct relevance to project activities -- such as that to reduce subsidies to the Tamil Nadu Electricity Board -- should not be imposed on projects. These are difficult to enforce, and take considerable time and effort of both Bank and Borrower with negligible returns.
P010478 | Pakistan:NWFP Community Infrastsructure Project (CIP) | South Asia | Pakistan | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/103511474573182286/text/000020051-20140612102447.txt | http://documents.worldbank.org/curated/en/103511474573182286/pdf/000020051-20140612102447.pdf | Lessons in addition to those in the ICR are:1. Physical targets may be achieved in a short time period, but the qualitative aspects of a project especially those relating to community development and participation cannot be rushed. 2. Reporting data on some performance indicators or preparing evaluation reports are not enough. Without attention to quality and methodological soundness, their learning value is much reduced.
P010478 | Pakistan:NWFP Community Infrastsructure Project (CIP) | South Asia | Pakistan | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2003 | 2006 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/614111468287747416/text/33612.txt | http://documents.worldbank.org/curated/en/614111468287747416/pdf/33612.pdf | LESSONS LEARNED 0 Successful CDD depends inpriority on the understanding of and commitment to a CD modelby the local government authorities. 0 Theproject andthe community participationmodelmustbedesigned so as to permit maximumflexibility dependingonthe circumstances ofeachcommunity. 0 The design o fthe project should ensure that the social infiastructure, Le., the CD per se, interacts with the chosen physicalinfiastructure. Since CD is a longprocess, implementationplans must allow for this. 0 The selection o fhighquality CD and IDstaffis o f crucialimportance for CDD. They should be inplace fkom the beginningo fthe project andavailable for the periodo f the project. 0 The design o fthe project shouldpayparticular attentionto the active participationo f women inall phases o fthe project, not only as recipients o ftargeted packagesbut also as deliverers o f good practiceto members o fthe community. Sustainability o f any CDD project is largelydependent onwomen. 0 Investments costs o f CDD projects with active participation o fthe beneficiaries are likelyto be substantially lower thanwhen implementedbygovernment entities. 0 For any CDD projectbasedon cash contributions (whether for capital costs and/or O&M) fiom the LGandthe community, the design o fthe project must provide for verification o f effective payment and origin o f funds. 0 Any M&E system mustbe finalized, put inplace, andfblly functioning before start o f the project andthose responsible to operate anduse it recruited andtrained. Supervision and completionmissions must report systematically on the findings o f the system.
P010480 | BOMBAY SEWAGE DISPOSAL | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/432731474649407653/text/000020051-20140612134408.txt | http://documents.worldbank.org/curated/en/432731474649407653/pdf/000020051-20140612134408.pdf | The project experience shows that slum communities are willing to pay fees to operate and maintain community toilets sustainably, provided that they are involved from the beginning and are given the responsibility for managing the community toilets.There is the need to think of potable water supply, sanitary excreta disposal, and hygiene education as a package, on which the health improvements depend.There are limitations to fully turn around a poorly prepared project during supervision.
P010481 | PUNJAB FOREST SECTOR DEV. | South Asia | Pakistan | Blend |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1995 | 2002 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/590331474665753970/text/000020051-20140607150631.txt | http://documents.worldbank.org/curated/en/590331474665753970/pdf/000020051-20140607150631.pdf | The ICR offers many lessons - too many in fact - but a number confirm lessons from other projects. The following (with some adjustment in formulation from the ICR and one addition) are the most important: 1. An implementing institution managing a new project should be subject to a careful analysis of financial management capacity very early in preparation so that systems and skills can be developed and tested even before effectiveness. 2.Research components, due to the lag in impact, call for very early identification and completion of training needs so that the new skills can impact as early as possible. 3. Repeated interaction and good skills training backed up by positive stakeholder response can turn around authoritarian public service attitudes towards more participatory approaches quite quickly. 4. Establishing sustainable community-based resource management groups takes longer than a typical Bank project period. 5. Weakness in M&E is often due to the failure to design M&E during preparation, inappropriate institutional location of the M&E function, and lack of incentives to report.
P010482 | BALOCHISTAN COMMUNITY IRRIGATION AND AGRICULTURE PROJECT | South Asia | Pakistan | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/161481474565771306/text/000020051-20140607171316.txt | http://documents.worldbank.org/curated/en/161481474565771306/pdf/000020051-20140607171316.pdf | Greater emphasis should be laid on CAD, which is far more cost-effective at improving scheme efficiency than high-cost headworks.Technical criteria for pilot FISs should allow for the beneficial economic impact of increased groundwater recharge.Contracts for FO labour should be awarded at market rate (not 25% below contractor rates.) this would avoid unfair competition from contractors who are able to "front-load" costs not included in FO contracts, and hence put in lower bids on unit rates.There is a trade off between using a PMU and government departments. The PMU is usually more efficient, but the opportunity to improve government efficiency is lost.
P010484 | Uttar Pradesh & Uttaranchal Rural Water | South Asia | India | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/456521474502706436/text/000020051-20140612093103.txt | http://documents.worldbank.org/curated/en/456521474502706436/pdf/000020051-20140612093103.pdf | The main strength of the Swajal approach is transparency, from pre-feasibility stage to O (b) safety and adequacy of water sources; (c) reliability and cost of power supply; and (d) the dominance of male household members in financial decision-making. Using performance-based compensation systems and recruiting from NGOs, public and private sectors. helped to maintain high rates of retention of competent staff in the PMUs and DPMUs.
P010485 | HYDROLOGY PROJECT | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/713051474504198962/text/000020051-20140612133557.txt | http://documents.worldbank.org/curated/en/713051474504198962/pdf/000020051-20140612133557.pdf | The ICR draws some very narrow, project specific lessons from the review. A broader lesson might be that, in an operation such as this, where improving collaboration between institutionally disparate and geographically separate agencies, a third party with the level of visibility of the World Bank, can play an important role in raising the visibility of the program and, through it's periodic reviews and target setting, help establish and regularize the processes of inter-agency collaboration.
P010486 | NWFP Primary Education Project | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1995 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/104611474500918537/text/000020051-20140607143408.txt | http://documents.worldbank.org/curated/en/104611474500918537/pdf/000020051-20140607143408.pdf | An objective implementation capacity assessment is an imperative for large, complex projects, particularly in the areas of financial management and procurement.- Beneficiaries need to be involved in design and re-structuring to avoid the non- implementation of programmed activities.-Mechanisms to improve public-private partnership need to be established within a context of clear policy and an enabling environment, if they are to be effective. - Project design should provide clear benchmarks and performance indicators if project objectives are to operationalised and monitored.- Effective supervision entails a proactive approach which would enable the borrower to find solutions to problems rather than merely identifying them.
P010489 | AP 1ST REF. HEALTH S | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/427011475087944833/text/000020051-20140607171401.txt | http://documents.worldbank.org/curated/en/427011475087944833/pdf/000020051-20140607171401.pdf | (1) State level projects in a country as large and populous as India (given a committed State) are effective units of focus for development assistance, and are more likely to be able to effect meaningful institutional, policy, and health system reform. (2) Rigorous Bank procedures can translate into good governance. (3) Some aspects of health system strengthening, e.g., effective referral between levels of care, MIS, work force allocation, need to be carried out across all three institutional levels (primary, secondary and tertiary), even if a project is otherwise only focusing on lower levels within the health system. (4) Contracting out of non-clinical services (and even clinical services) to the private sector can work well. (5) A user fee system can be introduced in a poor country, exempt the poor, and still collect adequate resources. (6) The retention of user fees at the facility level is critical to their efficient use, and should be designed into projects that include a user fee component. (7) Patient satisfaction surveys are valuable for feedback and improvement of service delivery, but they are not sufficient in and of themselves to document improved quality. They should be coupled with independent analyses of service output and outcome (e.g., aspects of quality, accessibility and use), using appropriate indicators that have already been put in place in the design of the project.
P010492 | Population Welfare Program Project | South Asia | Pakistan | Blend |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2000 | 2001 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/742621474850591415/text/000020051-20140529074958.txt | http://documents.worldbank.org/curated/en/742621474850591415/pdf/000020051-20140529074958.pdf | Benchmark targets for project components are necessary in order to adequately monitor progress, manage the program, and document program accomplishments. Among these benchmark targets and indicators that need to be measured regularly are those that address quality and use of FP/RH services, adequacy of contraceptive supply, and degree of involvement of NGOs, communities, and other segments of the private sector. Decentralization of funding should accompany decentralized program administration and service provision; this condition should precede commitment of IDA funds. Similarly, a detailed appraisal of the financial management system should be carried out and necessary improvements be made prior to approval of the project.
P010496 | Orissa Health Systems | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/796811474632133113/text/000020051-20140617133207.txt | http://documents.worldbank.org/curated/en/796811474632133113/pdf/000020051-20140617133207.pdf | (i) Assess and address state and project management capacities: Despite having addressed the issue of project management and funds flow arrangements in the project design, these continued to be a problem in the early stages of the project. The capacity of the PMC to plan, execute and monitor various project activities, including civil works and procurement, was significantly affected due to the decision of the government not to contract a management agency post project effectiveness.(ii) Accountability also important for results: During field visits, it was observed that there were differences in implementation progress across the state despite the same incentives given to project managers. Hence, it is also recommended that issues of accountability and motivation are also studied and addressed during project preparation.(iii) Develop local capacities to use fees collected: The collection of user fees has increased the availability of incremental budgets for non-recurrent expenditure at the facility level, which is likely to positively affect the quality of services provided. However, there is a need to develop local structures like the RKSs at the facility levelthat should be able to use these funds for the local population and be accountable to them.(iv) "Software" should not wait for the "hardware": Software activities like IEC should be initiated in the early stages of the project irrespective of the status of the completion of civil works. This gives enough time for the project to implement these activities and generate awareness amongst the population to use these facilities. Innovative pilots too should be initiated in the early stages of the project to give sufficient time period toassess the impact of these interventions and put in place arrangements to scale up these interventions if the impact is positive.(v) HCWM is a behavioral change: Change in HCWM practices takes time and therefore constant training and monitoring is required by the project and the DHS to inculcate this behavior. This needs to be a continuous process and supply of HCWM consumable material should be continually provided or procured using district health committee funds.(vi) Prompt identification of problem status important for improvement: It was observed that execution of project activities and disbursements significantly improved after it was identified as a problem project in October 2003, despite the delay in identifying it as a problem project. This indicates that proactive identification of problem status and realistic ratings are important for successful project execution.(vii) District specific planning maybe more suitable: As the study on child mortality in Orissa notes, there are significant differences in health indicators between districts. Hence, district specific planning would seem to be more appropriate compared to a uniform set of activities being implemented across the state to improve health outcomes.(viii) Engage further the private sector. Given the growth of the private sector in Orissa, it is important to engage more actively with the private sector and go beyond the contracting out of just "hotel" functions. Though the commitment of GOO to strengthen the public sector is warranted given the large number of poor still accessing these facilities in the state, it is also important to engage the private sector in healthcare given its increased presence. The focus of the public-private partnerships should be on improving access to and quality of healthcare in remote and tribal areas where the public sector may have poor reach and contracting in of specialist services to provide comprehensive emergency obstetric and neonatal care.
P010498 | ENERGY SERVICES DLVY | South Asia | Sri Lanka | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2003 | ICRR | >=10 million & <25 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/105451475079577658/text/000020051-20140612065957.txt | http://documents.worldbank.org/curated/en/105451475079577658/pdf/000020051-20140612065957.pdf | 1. Overcoming the barriers to access to finance is crucial for renewable energy investments in general, but specifically those targeted at rural, remote and off-grid areas. For private entrepreneurs the need is often for longer term loans that better fit their respective risk profiles as well as the cash flow requirements of renewable energy investments (high initial costs, relatively long repayment periods). For rural households and villages, the need is for loans that make (renewable) energy systems more affordable.2. A conducive and credible policy and regulatory framework is paramount for the success and future commercialization of renewable energy investments, as well as off-grid and poverty-oriented energy service delivery systems more generally. 3. Allowing for flexibility, innovation and participation in project design and implementation (i.e. a consultative and iterative 'continuum of options' approach) is of great importance when attempting to overcome the range of problems associated with renewable energy and off-grid developments (access to finance, market development issues, servicing, monitoring, etc). A willingness to pursue a range of different alternatives (i.e. public, private, NGO involvement, retail-driven as well as community-driven approaches, commercial banks as well as MFIs) seems apt to fit the different needs and contexts of renewable energy demand in developing countries.
P010498 | ENERGY SERVICES DLVY | South Asia | Sri Lanka | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2004 | PPAR | >=10 million & <25 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/675471468760785805/text/29532.txt | http://documents.worldbank.org/curated/en/675471468760785805/pdf/29532.pdf | LESSONS LEARNED 41. The ESDP's unique design for implementation can serve as a model for other rural electrification initiatives with renewable energy and energy efficiency components. The ESDP lesson with potentially the broadest applicability is its demand-driven and commercially focused approach of enabling multiple stakeholders to overcome financial, institutional, and market barriers associated with small-scale renewable energy and the promotion of energy efficiency. Throughout implementation, this required a strong and consistent emphasis on establishing strategic and working partnerships between the central government, Provincial Councils, the Ceylon Electricity Board, commercial and development banks, a microfinancing institution, private developers, contractors and consultants, industry associations, equipment vendors, rural electricity cooperatives, and consumers. It also required a stable, competent, and highly proactive Administrative Unit with multi-disciplinary capabilities to manage project coordination and implementation, which proved to be a key element in successfully broad-scaling private investments to commercialize renewable energy technologies. 42. The ICR provides an excellent and detailed section on lessons learned, which benefited from a stakeholders' survey and a full-scale, independent report.' The lessons can be clustered around three main actions\. (i)Build the business andpolicy environment 43. The key barrier of access to capital must be addressed as a priority, be it for longer-term loans (sought by project developers), for credit assistance to improve affordability (required for village hydro and solar electricity consumers), or for working capital (needed by entrepreneurs). Sri Lanka has the advantage of having a long experience with minihydro dating back from the establishment of the tea estates (that is, good maps, existing roads, and good rainfall data), as well as financial institutions (such as DFCC Bank and National Development Bank that were already lending to small and medium enterprises, as well as to a variety of large infrastructure projects, before ESDP. Even before ESDP and the SPPA became realities, DFCC Bank had pioneered the financing (with debt and equity) of the country's first-ever private sector minihydro project that was set up to sell power exclusively to the CEB grid. Under ESDP, the two development banks DFCC and NDB, by virtue of their in-house engineering capabilities, spearheaded the financing of grid-connected minihydro, often syndicating their loans with other commercial banks that were PCIs. Today, commercial banks have gained sufficient confidence to lend to this sector by themselves. While prior experience is important, microfinance institutions can play a significant role in providing consumer financing for solar home systems and term loans to community-based organizations for developing small and medium off-grid renewable energy projects. Although microfinance institutions and rural development banks are in general more 9. International Resources Group. World Bank/Sri Lanka Energy Services Delivery Project\. Impact Assessment and Lessons Learned. Washington DC, March 2003. suited for financing rural energy services rather than larger commercial banks and main vendors of solar home systems, exceptions do exist, such as the continuing role played by Hatton National Bank and DFCC Bank as leaders in financing off-grid village hydro projects. 44. Unfavorable aspects of the overall investment environment must be addressed\. for small hydro developers, a transparent and standardized contracting and tariff arrangement (the SPPA) is essential; for dealers of solar home systems, high import costs and the lack of consumer financing needed to be resolved; and for village hydro developers, access to favorable credit terms and reliable manufacturers of turbines and induction generator controllers were required before they could enter rural areas and stimulate demand for a mini-grid among small communities. (ii)Scale-up the Market 45. In addition to the adoption of market-based principles, several measures need to be taken to foster continued growth in the renewables industry. First, a reliable after-sales service system needs to be established. In Sri Lanka, the solar industry responded very well and now has more than 100 sales and service outlets throughout the country, developed through foreign and local private investment. Second, information technology should be introduced in the operations of participating microfinance institutions, which in the case of ESDP reduced turnaround time of loan approvals for solar systems from more than 3 months to less than 30 days. Third, consumers should be trained properly in the operation, maintenance, and limitations of their systems, particularly to self-diagnose technical problems (such as loose wiring connections, shading over photovoltaic modules, tripping of village hydro distribution circuits, keeping distribution poles free of rot and termite attack) and avoid over-usage. This is especially important as systems grow older and components start failing. Solar systems need special watching and improvements, as complaints have increased (in absolute numbers, but not per capita) about system malfunctions. Some consumers indicate a preference and willingness-to-pay for grid connection if ever feasible for their remote area, since the 200 watts per household provided by microhydro or the subsistence-level electrification provided by solar home systems are limited and do not permit the addition of more appliances or leisure uses. 46. The stakeholders' survey indicated that rural consumers are willing to pay more for their energy use, as long as the supply is reliable, safe, and of a high quality as is demonstrated by hydro and solar energy compared to the use of kerosene, which poses health risks in addition to inconvenience of use. Community contributions (in cash and kind) to the implementation and management of off-grid village hydro is crucial to project success. In Sri Lanka, families contributed their time to civil works and construction of distribution lines, as well as the supply of poles, sand, and other materials in kind, which were assigned equivalent cash amounts and deducted from their actual required payments. These contributions brought a sense of project ownership and a desire to ensure successful implementation. (iii)Establish Robust Project and Financial Management Systems 47. Competent project management proved essential to ESDP's successful implementation, as were accounting, record-keeping and financial reporting systems that were timely and comprehensive. Particularly noteworthy is the performance of the Administrative Unit in\. (i) brokering partnerships among multiple stakeholders; (ii) quickly assimilating the underlying technologies; and (iii) setting up a financial management system for monitoring and disbursing against loan refinancing applications from PCIs, as well as verifying and releasing grant disbursements, including the tracking of over 20,000 solar home systems. In practice, these enabled the Bank and the borrower to be flexible in project design (for example, the certification of a microfinance institution to reverse the slow uptake of solar home systems in rural areas, and the relative ease in revising the Operating Guidelines to improve systems and procedures) and to introduce output-based aid approaches (such as the tying of project development consulting contracts to concrete deliverables).
P010500 | Natl Drainage Prog | South Asia | Pakistan | Blend |  | Sustainable Development | Water | IDA | IPF | 1998 | 2005 | 2008 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/366661474898800451/text/000146597-20140617163103.txt | http://documents.worldbank.org/curated/en/366661474898800451/pdf/000146597-20140617163103.pdf | The National Drainage Project affirms and highlights several lessons from the Bank's general experience : 1. Avoid overcomplexity: As designed, NDP had little chance of being effectively implemented. The project involved too much: four large provinces, with separate governments, a very broad-based reform agenda, and, for the most significant reform - devolving powers and responsibilities to independent provincial agencies and farmer organizations - a major change in stakeholder roles. Some of the reforms were perceived to be against vested interests and were strongly resisted. A more modest reform agenda, perhaps in only one state, might have achieved more, and established positive experience for further reforms and scaling up. 2. A reform agenda needs to give attention to incentives for change for the different stakeholders, and to the processes and sequential actions of the reform program: Participatory dialogue with farmers was limited. Government staff were apprehensive about the consequences of devolution for their employment. This mistrust continued, and towards the end of the project, the Irrigation and Drainage Departments were effectively taking back responsibilities for water charges collection and O reform champions can have major impact, but basing reform on a few champions is a vulnerable strategy: A few reform champions in central and provincial governments were key to setting up the reform agenda. Their number and influence diminished over time. There was not a broad base of stakeholders (such as in the provincial Irrigation and drainage departments, amongst civil society and, especially, the farming community) to keep driving the reforms forward. A transparent discussion process, clearly visible incentives and the fostering of stakeholder organizations might have created a demand for reform and organizational capacity to achieve the reforms. 4. At least the core features for launching a project should be in place at project entry: Not one intended civil works contract was ready, or had even reached detailed design at the time of Board presentation. The lack of at least a first year of contracted works contributed to the major delays and reduced achievement of the investment program; investments reached only about 24 percent of intentions. Additionally, there had been only limited discussion with communities, and preparation of the M&E program had not even begun.
P010501 | PVT SECTOR GROUND WA | South Asia | Pakistan | Blend |  | Sustainable Development | Water | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/767261474904051588/text/000020051-20140607150759.txt | http://documents.worldbank.org/curated/en/767261474904051588/pdf/000020051-20140607150759.pdf | Establishing a GRF requires coordination of a wide range of institutional changes, affecting the equity of water distribution, ownership by both communities and local government, alternative income sources to compensate for decreased reliance on groundwater, and poverty-targeting of "critical areas." A public awareness program and stakeholder participation must precede introduction of groundwater regulation. Users must be involved in groundwater monitoring and voluntary self-regulation.Women's Organizations can contribute to conflict resolution among members of FOs/CTWs and the optimal siting of TWs.To control salinity, non-engineering solutions, for example saline agriculture and biological drainage, may be effective in controlling groundwater salinity intrusion.
P010503 | AGRIC HUMAN RES DEVT | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/369121474564102641/text/000020051-20140607153603.txt | http://documents.worldbank.org/curated/en/369121474564102641/pdf/000020051-20140607153603.pdf | (i) Open ended objectives should be avoided in project designs as they weaken accountability and evaluation of outcomes. (ii) If open ended objectives are unavoidable, the project design should include a structured set of quantitative indicators tied to the objectives, for each component, and an M&E program which includes independent qualitative assessments of major outputs during implementation and on completion.
P010505 | RAJASTHAN DISTRICT POVERTY INITIATIVES PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/280611474595704811/text/000020051-20140619080835.txt | http://documents.worldbank.org/curated/en/280611474595704811/pdf/000020051-20140619080835.pdf | Livelihoods projects need to focus on clusters of activities, preferably organized around existing supply chains--the sub-project investments made under this project were too diffuse and therefore difficult to sustain.The institutional framework needs to be built around persons and agencies with experience of working with the poor; this project was weakened by the lack of people with the necessary skills, and the rapid turnover of personnel.A Management Information System needs to be established at the outset to allow for effective monitoring of sub-projects. In this project, there were separate datasets for physical and financial progress that could not easily be reconciled. (In the ICR Review Meeting with IEG the project team said the problem is not the lack of appropriate software--India is a world leader in MISs--but the difficulty of getting local agencies to use it).
P010506 | MP FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1995 | 2000 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/174331474488751548/text/000020051-20140529070825.txt | http://documents.worldbank.org/curated/en/174331474488751548/pdf/000020051-20140529070825.pdf | The lessons identifed by the ICR are interesting and have important implications for the future management of India's forests. Five important lessons from the ICR are repeated here. (i) Conflict management is a critical aspect of community based forest management and efforts to strengthen the skills of village leaders and local staff in coping with conflict and mediation should be planned from the outset. (ii) Establishing the linkage between forest users' rights and responsibilities is critcal to people's participation. (iii) The poverty alleviation impact of the project is considerable, forest benefit streams provide strong incentives to forest users and benefit sharing policy provides an effective self funding mechanism for regular forest maintenance. (iv) Effective engagement with a broad range of stakeholders including development NGOs, activist NGOs, academics, private sector entities, politicians, and the press would increase awareness and understanding of the transformation, policy positions, development programs and ensuing benefits. (v) Reform of a public forest institution and the establishment of collaborative forest management require long term commitment to become sustainable and institutionalized.The ES adds the following lessons, some of which strengthen the lessons coming out of the ICR. (i) India has the largest number of poor in the world, a large percentage of whom are dependent directly or indirectly on forests for a living. Hence it is essential that forest sector development is made a part of the poverty alleviation strategy of the Bank in the country. (ii) In projects with a clear poverty alleviation objective, even alongside an objective of increasing forest cover, development objectives should be framed at least partly in terms of poverty alleviation. This should be done in a way that is monitorable and should be backed up in design by a monitoring and evaluation system capable of measuring poverty impact. (iii) Limited domestic resources led India to seek financial assistance from the World Bank and other donor agencies to support programs that involve local communities in forest management. Given the long gestation period in realizing benefits from the forest sector (making the community participation efforts financially and institutionally self sustaining takes time) there is continued need for concessional finance for the forest sector on a long term basis. However there is also need to give greater attention to long term sustainability issues in Bank forest sector projects. (iv) International cooperation and coordination with other donors who have done major grass root level work in community participation (like DFID and the Ford Foundation) should be actively pursued. The Bank also has valuable experience in several countries in different parts of the world and it can bring useful advice to the Government of India to help improve the performance and contribution of the forest sector to the economy. Hence the importance of inter donor and cross country learning; (v) Establishment of a sound policy and legal foundation and clear benefit sharing arrangements are essential for the sustainability of a forest management program based on community participation.
P010506 | MP FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1995 | 2000 | 2005 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/905631468246645642/text/32246.txt | http://documents.worldbank.org/curated/en/905631468246645642/pdf/32246.pdf | 4. Lessons 4.1 The following lessons may be derived. First, to mobilize villager supportfor resource consewation a long term commitment is needed by the government and donor agencies. The JFM strategy involves increasing the stake o f communities (residing inthe neighborhood o f forests) inthe management and protection o f those forests. However, the regenerated forest area can be maintained only ifthe villagers get adequate retums from the forest. This requires a long term strategy o f forest protection and creating alternative economic opportunities for villagers at least until the forest regenerates and communities can depend on the forest for their livelihood. There are important implications here for the Bank's strategic approach to forest management. The appraisal document envisaged the need for a ten-year program o f Bank support and the low impact found bythis evaluation suggests that such an extended commitment may be warranted. Second,flaws in the legal and incentiveframework need to be addressed. An overarching strategy o f forest protection through community participation also requires attention to the legal andpolicy framework for forest management bearing on, among other things, forest user rights, relations between protection committees and village institutions, and issues related to the marketing o f non-timber forest products. Third, the Bank's involvement in theforest sector needs to be seen in the larger and longer term context ofpoverty reduction and thepoverty impact of such involvement should be monitored. A large percentage o f the poor inrural areas are found inand around forests and the Bank can make a substantial contribution to poverty reduction in 17. OED, 2000, op. cit., p. 46. India through a strategy that involves the poor inforest protection. However, this must be done in a way that i s monitorable and should be backedup indesignby a systematic monitoring and evaluation system capable o fmeasuringpoverty impact.
P010509 | MULTIMODAL TRANSIT | South Asia | Nepal | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2004 | 2004 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/369831474896969982/text/000020051-20140612104643.txt | http://documents.worldbank.org/curated/en/369831474896969982/pdf/000020051-20140612104643.pdf | Projects that depend on exogenous factors should be treated as high-risk projects and the Bank should have an exit strategy if enabling arrangements cannot be concluded within a reasonable time frame.Bilateral and regional initiatives, such as regional transit projects, require political commitment and consensus by all parties to succeed.Project Implementation Units can be effective, but there should be an absorption strategy once the project is completed, with a view to strengthening the Ministry concerned.
P010509 | MULTIMODAL TRANSIT | South Asia | Nepal | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2004 | 2008 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/368431468289202058/text/40141.txt | http://documents.worldbank.org/curated/en/368431468289202058/pdf/40141.pdf | 3. Lessons Learned from the Project 3.1 Inadditionto the identification oflessons learned the missionhas suggesteda possible future strategy that could be adopted; an approach that could leadto increased traffic through the facility and an improved financial position for the operator. Suggested Future Actions toAssist Transportin Nepal 3.2 It is recommendedthat a user conference beheldto improve the utilization o f Sirsiya I C D and that a user group be established. The GoN now has an I C D that i s underutilizedwith a fraction o f the imports andnone of exports movingthrough the facility; the country is not achieving the benefits projected. The best course o f actionnow i s to undertake specific steps that should have beentaken during the conception of the project. The IEGmission suggests that the GoN (through NITDB)hold a conference in Kathmandu, inviting major stakeholders inNepal's transport industry, including major importers, exporters, freight forwarders and representatives o f the IndianRailways and the TMC o fthe Sirsiya ICD. The focus o fthe conference would beto actively promote the use o fthe facility and to identifyspecific actions to be taken that would increase the ICDs usefulness inserving the foreign trade ofNepal. One o f the initial target markets for this conference would be exporters, who now do not currently use the ICD. 3.3 One result o fthe conference shouldbe the formation o f a Transport Working Group that would monitor service quality on the rail route betweenNepal and Kolkata, and the ICD, and continue to respond to problems encountered by existing users and to promote the route to non users. Some suggested agenda items at the conference include the introduction o f definition o f a trial period o f improved service on the rail route, via the ICD, to encourage more exports as well as imports, to use the facility. 3.4 Specific improvement suggestions duringthis trial period would come primarily from existing and potential users, but some suggestions include the operation o f a daily train service between Kolkata port and the ICD, regardless o f the number o f wagons loaded; this might decrease transit times and increase the service reliability, which have been common complaints amongmany users and potential users. IndianRailways now operates only full 35 wagon trains; it mightbe worthwhile for the GoN to offer to subsidize the IndianRailways (duringthis trail period) for the initial losses incurred in operating shorter rakes, for a limitedperiod o f time while reaction to the new service i s evaluated. It has also been alleged by some ex-users that not all shipmentsreceive equal treatment within the ICD; Le., some shipments are expedited while others are delayed unnecessarily. Fears o f such concerns inside the I C D need to be eliminated with a clear and transparent description ofthe organization and demonstrationo fprocedures followed within the ICD. Manynonusers o f the facility have such negativeperceptions (real or imagined) o f the I C D and only through open dialogue can these perceptions be alleviated. Inaddition to discussions, trips to the ICDto demonstrate the procedures mightproveto be helpful ingenerating user confidence. 3.5 It is possible to develop a smooth-running road and railmultimodal service for the benefit o f importers, exporters and the operators, while minimizingthe risk o f transport delay. However, this does not happen automatically by opening the doors o f the ICD; it mustbe actively promotedby assembling all stakeholders, engaging infrank discussions, and responding to the concerns o fpotential users. It i s important that this kindo f direct involvement o fpotential users o f a new service be included inthe formulation o f similar projects inthe future. 3.6 Itis generally acknowledgedthat customs officials at many o fNepal's borders are susceptible to corruption. Successful implementation o fnew procedures and systems should be reinforced with civil service reform o f compensation to reduce the likelihood o f corruption on the part o f customs officers. IEGrecommends this course o f action for considerationto accompany any further implementation o f ASYCUDA modules. A critical part o f the customs reform shouldbe the elimination o fmanual procedures, which put the customs officer personally inthe clearance procedure, increasingthe potential for corruption. Lessons TheBank should more critically reviewfeasibility studies that include diversion of trafflc from road to rail. Projects that depend onformal international cooperation agreements should not commence until such agreements areformalized, or there is at least a strong possibility of such agreements being brought to a timely conclusion. For projects that require cooperationfrom organizations within more than one country, all relevant stakeholders includingpotential users should be thoroughly consulted. Implementation of customs reforms should ifpossible be coupled with a civil service compensation review to reduce the likelihood of corruption.
P010511 | MALARIA CONTROL | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/265891474893860404/text/000020051-20140615110609.txt | http://documents.worldbank.org/curated/en/265891474893860404/pdf/000020051-20140615110609.pdf | Projects should be more realistic in setting development objectives and in defining the credit size based on a more rigorous analysis of the institutional and financial capacity of the Borrower.Future efforts should include much more extensive and realistic development of agreed-upon indicators and results monitoring arrangements that can be of greater use for both the Borrower and the Bank for recurrent program decision-making, backed up by the resources and commitment to make them work.In the context of a decentralized program, nurturing ownership of states and strengthening program management capacity at district and state levels is essential for program success.Future efforts should have a stronger focus on private sector both for service coverage and for more accurate surveillance.Surveillance for drug resistance could be substantially strengthened, and as resistance to CQ expands, GoI should accelerate expansions with ACTs. Action to ensure that effective treatments are made available in line with documented resistance and transmission patterns.Experience with state-level entities for disease control in India (e.g. for HIV/AIDS) might have been taken into account, along with malaria experiences in other countries. This might have accelerated the move towards state-level malaria societies that would reduce the bureaucracies of state-level institutions.
P010513 | ENVIRONMENTAL ACTION 1 PROJECT | South Asia | Sri Lanka | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/129871474506030653/text/000020051-20140612135524.txt | http://documents.worldbank.org/curated/en/129871474506030653/pdf/000020051-20140612135524.pdf | * Project supervision can greatly benefit from the continuity of the Task Team Management. The project was led from the country office and had the same Task Team Leader throughout the project, in sharp contrast to the Bank norm of 2.2 years, and this significantly contributed to the success of project supervision.* In countries where recruitment to public sector has to follow protracted procedures, technical staff vacancies should be filled as condition for project effectiveness in order to reduce the prospect of long delays.* To ensure vital ownership, institutional development projects should be managed by the implementing institutions rather than external Project Management Teams.
P010516 | RURAL WS& SANITATION | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/926331474504167244/text/000020051-20140612134834.txt | http://documents.worldbank.org/curated/en/926331474504167244/pdf/000020051-20140612134834.pdf | Based on the ICR the key lessons are: (i) The existence of parallel modes of service delivery, one demand-driven and another supply-driven, in the same sector can send a confusing signal and has implications not only for efficiency and effectiveness but also for sustainability of activities begun under the project. (ii) In a country where decentralization is an ongoing process, if local government institutions are bypassed in a Bank project that is setting up a system of decentralized service delivery, it could send a mixed signal to local government authorities and confuse the communities regarding the policy of decentralization and the devolution process. (iii) Coordination between donors is an issue which needs paramount attention. Other donors have been supporting local-level delivery mechanisms in the rural water supply and sanitation sector and it is important that the approaches followed by all in terms of community contribution requirements etc. are harmonized. Otherwise, it can send an inconsistent message to the communities.(iv) Project experience highlights the importance of having an effective and well functioning M&E system right from the beginning, results from which provide continuous feedback for the implementation of subsequent batches of sub-projects. (v) Given the high involvement of the support organizations in mobilizing and guiding the communities, their selection and training deserves special attention so that adequate steps to ensure the incorporation of marginalized groups in project activities can be taken.
P010516 | RURAL WS& SANITATION | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2004 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/983691468289202755/text/443680PPAR0P0105160Box327410B01PUBLIC1.txt | http://documents.worldbank.org/curated/en/983691468289202755/pdf/443680PPAR0P0105160Box327410B01PUBLIC1.pdf | 5. Findingsand Lessons 86. Access to rural water supply and sanitation has improved significantly since 1991 whenthe first reliableestimates of coverage becameavailable.58Nationalaccessto improved drinking water resourcesthen stood at 67 percent. This increased to 75 percent by 1995.Thereafter eight independent surveys each showed improvements, albeit with some variation. Average national access in2004 was estimated to be 89 percent based on the 2004 Living Standards Survey and the World Health Survey o f 2003.59 The incremental improvement of 14 percent i s equivalent to about 3 million people receiving improved access to water. The FB's RWSS contributed about a sixth o f the improved accessabout half a millionpeople a major achievement. The FB concept successfully challenged existinggovernmentpractice used toprovide RWSSin Nepal andprovides a replicable model 87. The strategy followed showed that a small organization can successfully implement a national demand-driven program to improve rural service provision. Specifically, confining itselfto a facilitating role reduced its overhead costs and staffing levels while at the same time enhancing the role and skills of local NGOs in service delivery. Adoption o f a comprehensive approach to RWSS that includes community-level institutions in service delivery and also addresses social concerns i s more successful than a purely technical approachthat provides only hardware. The focus on establishing community-level institutions, buildingtheir capacity and putting them inthe lead role in the planning, design and construction of community infrastructure worked well and reduced service provision costs significantly below those of government agencies. Quality control was enhancedthrough participatory M&Eof SOs by communities in responseto FB's questions. 88. There remains the question of how to fully integrate FB-financed andcommunityowned RWSS indistrict and regional planning. This i s a much discussed issue inNepal and regionally and several o fthe Bank's development partners questioned the Bank's approach for RWSSthat acted independently o f local and central 57. High staffturnover may also have beenthe result of the deterioratingsecurity situationand the excellentreputationofthe FBthat provided a launchingpad for better-paidemployment elsewhere. 58. HMG Ministryof Health. 1991. Survey conductedby the Family Planning, Maternal and Child Health Division. 59. WHOAJNICEF. 2006. Joint MonitoringProgrammefor Water Supply and Sanitation. Coverage EstimatesImprovedDrinking Water. UpdatedinJune 2006. 60. ADB. 2007. Servingthe Rural Poor\.A Review of Civil Society-LedInitiatives in Rural Water and sanitation.Discussionpaper.37 pp. July 2007. Communities also raised this interms of mitigatingthe impact of environmentalrisksthat were beyond their resources to manage. There is also the issue of reachingthe neediest; the FB's schemes tendedto benear roads, not indistant or poorly accessible villages. The Bank's SecondRWSSproject is responding to these challenges by adding the FB's schemes (sometimes retroactively) to the District Development Plans and ensuring a greater focus on remote and underserved areas. Incontrast, the ADB/DWSS Fourth RWSS actively developed District Profiles ofRWSSto aid strategic planning and interventionto the neediest areas although there is no formal mechanism to update these at present. 89. The FBproject provided sustainable service delivery that is fully owned by the communities and i s not reliant on government for routine operation and maintenance. A preconditioni s that communities must be unanimous intheir support for RWSS and make anupfront cash deposit. Ownership is enhancedwhenthe community has charge of procurement, the development i s an equal partnership among the lead agency, NGOs and the community, and the community makes its ownarrangements and employs its own staff for operation and maintenance ina transparent manner. Under these conditions communities are prepared to pay a substantial portion of the capital costs of RWSSmore than a third in cash and kindand make regular monthly payments to the village water users' committee for systemoperation and maintenance. 90. The project helpedwomen by significantly reducing the very onerous burdenof carrying water over long distances and saved more thenthree hours o f labor per household per day. The empowerment of rural women with the objective of enhancing their income generating potentialand status incommunities was substantially achieved through hygiene, literacy and skills training. With these enhanced skills women participated invillage water committees, filling the bulk of treasurer posts, and as village health workers. The more enterprising engaged in small-scale agriculture and husbandry utilizingmicro-creditprovided by the WTSS group seed fund and members' savings. In aggregate these skills and activities increased family welfare and its health status. Revealedpreferences in project schemes indicate satisfaction with improved RWSS service deliveiy and a demandfor other investments 91. Project communities' revealed preferences indicate satisfaction with the RWSS suppliedby the project (Figure 2).61Whenwater is inshort supply this is the highest priority but it was not that frequent (36 percent). However, inthe majority of project communities that had continuous water suppliesprovided by the Board they were satisfied with the service provided. Consequently the most frequent requests inthese villages were for roads that would connect them to hospitals and health centers and markets, more training o f women and upgradingo f village schools generally by adding 61. The datapresentedhere are derived .fromfocus group interviewsconductedby IEGDecember 3-10, 2007. Although 17 villages were visited, only the findings from villages with morethan 10 individualsin the group, includingat least4 women are reported.At the end of eachdiscussion participantswere askedto discuss and list their five top preferencesfor future assistance,Resultsfor all the interviews were then summarizedand fell into 11 categories. The frequency o fresponses was summed for each category and expressed as a percentofthe total (11). Each answer was scored for priority, first counted as 5; last as 1, andthe average priority for eachcategory was determined. two more grades above the primary level and additional teachers. Slightly under halfthe villages requested better access to communications technology for educational and marketingreasons. 92. While the RWSS project managedto successfully build results-orientated rural development, the arrangements for monitoringand evaluation need strengtheningto measure healthand social impacts. In particular\. Figure 2\. Revealed preferences 0 a standardized approach that Importance would allow longitudinal -_ - - comparison of project outcomes and impacts across the Batches. Water Id 0 an unbiased estimate o f project Rectric&ya sAgriculture impact on health given that Women's health and hygiene Heaths 19 Training Schools a Roads improvements were among the justification for the project. p a r r 8% Irrigalion 0 methods and application E Credit arrangements to track and evaluate changes inwomen's o tl r welfare and incomes resulting 0% 20% 40% 60% 80% 100% from project interventions. FrequencyHow often mentioned Source\. IEGfield survey 2008. The project experience confirms six IEGlessons\. Comprehensive approaches to development inwhich provision o f small-scale infrastructure i s accompanied by capacity-building to develop local institutions and ownership are more successful than infrastructure alone. When existing institutions fail and are unwilling to reform, careful design of new institutions can be a viable solution. The success o f this approach i s heavily conditionedon in-depthinstitutionalanalysis, close attention to the governance structure andthe willingness of the Bank to stand firm against vested interests for as long as it takes to be accepted. Even so, government does have a role and its interest mustbe internalizedinthe governance and regulatory structures of new organizations\. partnership is better than conflict. Small pilot projects to test new institutional approaches can be very successful providing they adopt a learning approach and give thoughtful attention to feedback from continuous monitoringto refine the development model. Itis important to understandthe incentive structures affecting adoptionofnew approaches to RWSS at the village level and that this will vary geographically and socially. Suchunderstandingtakes time to mature as communities and project sponsors internalize feedback to fine tune development models. Neither top-down blueprintnor rigorously time-tabled short-term approaches work successfully. The project experience demonstrates that small pilot projects unfettered by the expectations o f existing institutions can work well, as does an incremental approach that improves its relevance through sequenced feedback from well-designed monitoring and evaluation. Rural communities even if poor and barely literate can successfully implement, operate and maintain water supply and sanitation systems. This i s conditioned on unanimous community agreement on what they want to achieve and their willingness to make upfront financial commitments. It also requires well-designed and sequenced support packages that enable social inclusion, enhance the social and economic role of women, and emphasize self-reliance. Local NGOs can be successful interlocutors after appropriate orientation and skills enhancement. Ifimprovedhealthoutcomes are aproject objectivethen careful designofM&Eto linkproject interventions to improvements inhealthincomes is needed. This needs to be done from the outset o fthe project.
P010517 | PVT SECT INFRAS DEV | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2007 | 2004 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/247931474632995213/text/000020051-20140612101321.txt | http://documents.worldbank.org/curated/en/247931474632995213/pdf/000020051-20140612101321.pdf | The creation of an infrastructure fund is not a sufficient catalyst to promote private participation in infrastructure, in the absence of institutional capacity and an appropriate legal and regulatory framework.The pricing of credit in infrastructure funds needs to be linked to the riskiness of sub-projects.Local financial institutions should be closely involved from the outset, so that the objective of private participation in infrastructure is integrated with the objective of financial sector development.An unsatisfactory QAG review of quality at entry often should be the trigger for redesign of the project.
P010522 | Assam Rural Infra | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/716491474594593867/text/000020051-20140613033538.txt | http://documents.worldbank.org/curated/en/716491474594593867/pdf/000020051-20140613033538.pdf | Especially where the implementing agency has limited experience with using external financing, clearly defined procurement and implementation modalities, and first year activities, should be a part of project design and preparation. To promote growth of the rural economy, road networks need to be better planned with agricultural potential in mind, incorporating well placed farm-market roads, to ensure maximum convergence between project activities and impacts. Building a constituency for community participation takes time and project design must plan for this, ensuring adequate attention is given to incentives for participants, as individuals and as groups, during implementation and in the post project period.
P010525 | GENERAL EDUCATION II | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/584071474664556879/text/000020051-20140615102135.txt | http://documents.worldbank.org/curated/en/584071474664556879/pdf/000020051-20140615102135.pdf | #NAME?
P010526 | HEALTH SERVICES PROJECT | South Asia | Sri Lanka | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/944981474506760805/text/000020051-20140607171701.txt | http://documents.worldbank.org/curated/en/944981474506760805/pdf/000020051-20140607171701.pdf | The effective implementation of a project often depends on the satisfactory performance of the Project Coordinator. In circumstances where a country, and sector, have already demonstrated problems with effective Coordinators, recruitment of a satisfactory Project Coordinator can usefully be made a Condition of Effectiveness.
P010529 | Orissa WRCP | South Asia | India | IBRD |  | Sustainable Development | Water | IDA | IPF | 1996 | 2005 | 2005 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/460661474593121872/text/000020051-20140613044845.txt | http://documents.worldbank.org/curated/en/460661474593121872/pdf/000020051-20140613044845.pdf | (1) Water user associations require at least three to four years of support to be capable to operate, manage, and maintain minor and sub-minor canals. Farmer awareness and WUA formation should take place before scheme improvements commence in order to enhance ownership.(2) Complementary agricultural support services are required to maximize the benefits and sustainability of irrigation improvements. This should have been reflected in project allocations at the outset.(3) Water resources and agricultural staff should be trained together, not separately, for integrated management of water resources. (4) More efficient procurement organization and procedures are needed to avoid serious delays in project implementation.
P010530 | Irrig Sector Devt | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/392931474659517930/text/000020051-20140613044707.txt | http://documents.worldbank.org/curated/en/392931474659517930/pdf/000020051-20140613044707.pdf | Agricultural extension improvement should parallel irrigation improvements: Agricultural extension activities, including on-farm water management, were not included in the project. It was expected that the Bank financed Agricultural Research and Extension Project, prepared in parallel with the irrigation project, would provide these services. The extension project was unsuccessful and the extension services were not forthcoming. This failure was exogenous to the Irrigation Sector Project, and thus is not part of this evaluation. But the ICR highlights that this gap diminished yield increases. Parallel improvements in stakeholder participation and financing need to accompany infrastructure improvements: Performance in such "software" areas as stakeholder participation, irrigation management turnover, upgraded maintenance and cost recovery were project weaknesses. More focused attention to these areas, within a clear action program agreed with, and "owned" by, the stakeholders, would have improved sustainability.
P010530 | Irrig Sector Devt | South Asia | Nepal | IDA |  | Sustainable Development | Water | IDA | IPF | 1998 | 2004 | 2008 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/864011468053401392/text/444380PPAR0P011closed0August0702008.txt | http://documents.worldbank.org/curated/en/864011468053401392/pdf/444380PPAR0P011closed0August0702008.pdf | 5. Lessons 97. The ISP project demonstratesthat water is anecessary butnot sufficient input for increasingcrop yields and farmers' incomes. A more comprehensiveapproachis required. Agricultural extension efforts inthe project were modest, doing little to boost yields or crop diversification. How far this was a result of the Maoist insurgency is unclear. The recently closed (2002) Agricultural Research and Extension Project failed to improve the link betweenresearch, field application and strengthenedagricultural extension service.60 New technological improvements were not disseminatedto farmers; and governmentresearchremainedKathmandu-based. (And yet the preceding agricultural extension project [1985-951had satisfactorily developed a group-centered, participatory approachto replacethe ineffective training and visit system.) Currently JICA is supporting the AgriculturalTraining and Extension Improvement Project andthe Swiss Development Corporation is focusing on vegetable seed production amongpoor and disadvantagedfarmers inremote areas ofNepal. There are severalreports about the ineffectiveness of the public sector agricultural extension system; butno alternative systemhas emerged. The lack of a harmonized and sector-wide approachprecludes reform efforts that promote solutions which are more closely aligned to the highly variable agroclimates and soils of Nepal. 98. A similar problem exists for the irrigationsubsector. Inthe previous five years ADB, World Bank and USAIDhave each worked with DOL However, they operatedin isolation. Eachagency promoted its own model andthe models were sometimes incompatible-for example, there were conflictingproposals about how to get farmers to pay for irrigation. Financing projects without regardto anoverall strategy for the irrigation sector is not an effective way to press for changes ingovernment policy, institutions and individual behavior. Program lending has a potentially bigger impact on 60. World Bank. 1998.Nepal Agricultural Researchand ExtensionProject. Credit 2977-NEP. This project cost US$23.8million, hadan IDA credit of US$17.6million and was completed in2003. IEGrated outcome as unsatisfactory,institutional developmentas modestand sustainability as unlikely; Borrower performancewas ratedunsatisfactory. the ways sectorsare managedandonpolicies andregulations that affect economic incentives. It is particularly important for the agricultural andwater sector to seek a consensus among government agencies, donors, and concernedNGOs about what can be done, who will do it, andhow. This more comprehensiveapproachwould link irrigation and agricultural reformpolicies to higher level macro-economic instrumentsto improve agricultural sector performance. More attention is neededto targeting the poorest. 99. The Nepal RuralWater Supplyand Sanitation Project andthe Poverty Alleviation Funddemonstratethat the private sector andNGOs can offer an alternative to central government agenciesthat are unable or unwillingto reform. Project design failed to tackle DOI's ineffective businesspractices, relying too muchon technical assistance to introduce reformto farmers. The same approach was evident inother water sectors. Support to urbanwater supply and sanitation continued to center on ineffective centralized institutions. The Bank hadmore success with ruralwater supply and sanitation. It createdan autonomous FundBoard that worked through the private sector andNGOs. This approachhas succeeded butneeds futher strengthening, particularly mobilizationof local funding and linking itto district development planning. This model could be extendedto the irrigationsector. 100. Self-employment inagriculture andwage-employmentjointly account for more than halfthe income of the pooresthouseholds inNepal. Inthe absence of alternative livelihoods, effective measures to improve agriculture sector performance are vital for reducing poverty. Within agriculture, growth of staple crops has fallen behindthat of livestock, horticulture and fruit. Cereals still dominate and yields improve only slowly. 101. Given the Bank's mandateto alleviate poverty, was itjustified to spend so much on the SMIP project for sucha modest increaseinirrigated area?Higher levels of incremental agricultural production were achieved inthe FMIS at a quarter of the cost per ha. Project assistance to the SMIP was precededby three other Bank credits totaling $128 million inpresentprices. To date, the government has also investedUS$74 million inthis project. And yet there are still 800,000 hectares of rain-fed cultivable landinNepal, muchof it located inthe most poverty-stricken western and far westernregions. The productivity of rain-fed agriculture needs boosting and particular attention is neededto improve understandingof terrain and agro-climate and to assist farmers to adopt smallscale irrigation. There are many NGOs inNepalcapable of doing this work as demonstratedby the success of the farmer-managedirrigationsystems. 102. Finally, monitoringand evaluation of the agriculture sector needs strengthening. The partial privatization of agricultural input supply has left holes innational databases. Information, for example, on the use of fertilizer and groundwater is lacking. Comprehensivestatistical data is a significant public good that is essentialto inform sounddecision-making andpublic policy. Lessons 103. Experiencewith this project confirms five IEGlessons\. A more comprehensive approachis requiredto maximize benefits from improved agricultural water management.Water is only one input among many; institutional development and capacity building are equally important; as are agricultural inputs and marketing. Donors need to work together more effectively, with eachworking to their comparative advantage, the aim being to achieve a harmonized sector-wide approachthat avoids duplication and contradictions. InNepalthis assessment found while it made sense for donors' projects to be geographically differentiated this was at the expense of sector-wide coordination andmutual learning. Do not lose sight of project beneficiaries. Too muchattention to water resource policy and managementdeflected attention from the need to reformpublic sector managementof large-scaleirrigationprojects and improve service-delivery. As a result the longer-term sustainability of the public irrigation subsector and farmer's livelihoods dependent on it are at highrisk inNepal. Non-governmental organizations are generally better at working with farmers to increasethe productivity of small-scalefarmer-managedirrigation systems. The project clearly demonstratedthat partnershipwith NGOs inNepalenabled agricultural productivity improvements inremote locations where the poorest rural communities are located. Greater attention should be given to monitoring and evaluation to ensure informed policy-making and decision-making. InNepal the scope of data collection and storageof data on agricultural input and output performance information significantly contracted during the transition from public to private service provision.
P010531 | Reproductive and Child Health Project | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2005 | 2006 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/263351474502995709/text/000020051-20140613052212.txt | http://documents.worldbank.org/curated/en/263351474502995709/pdf/000020051-20140613052212.pdf | Policy reform at the national level must be accompanied by a plan for implementation of the policy at sub-national levels, particularly with regard to delegating appropriate responsibilities and building capacity for implementation. Special focus should be given to poor-performing states/districts.The challenge of implementing a national project dealing with sensitive issues on population and reproductive health should not be underestimated.Stronger emphasis should be placed on IEC programs to help implement policy changes.
P010556 | Highways Rehabilitation | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2004 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/500921474630701186/text/000020051-20140626122145.txt | http://documents.worldbank.org/curated/en/500921474630701186/pdf/000020051-20140626122145.pdf | Adapted from the ICR:Implementing a sector policy reform through in an investment operation is difficult. Under this project, the legal covenant regarding NHA's financial standing was waived and the governmentâ€™s resolution of NHAâ€™s debt remains outstanding. The time gap between the project preparation and implementation must be avoided to reduce the likelihood of financing gaps and bid prices. The engineer's estimates must be updated at the market value at the time of appraisal and adequate premium be allowed to cover for the procurement delays.Unanticipated price hikes due to market dynamics particularly in developing countries like Pakistan must be expected and adequate allocation for price contingencies must be built into the budget.
P010561 | Natl Agr Technology | South Asia | India | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1998 | 2005 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/170481475097116732/text/000020051-20140613082532.txt | http://documents.worldbank.org/curated/en/170481475097116732/pdf/000020051-20140613082532.pdf | The ICR has extracted a number of useful lessons from the experience with this project.Decentralizing control in a research organization can increase efficiency if it is accompanied by systems of accountability. Exchanging the principle of hierarchical control for the principle of accountability has unleashed an enormous amount of energy and creativity in an organization with large intellectual capacity.A clear communications strategy is needed to successfully implement organizational and management changes. A better communications strategy on the overall change process throughout the organization would have enabled staff to understand and respond to the changes in a better way.Fostering public-private partnerships in research and development requires not only an enabling environment, but also private sector participation in project design and implementation, and broad dissemination of success stories. Only a few such partnerships were established due to (a) inadequate investment in partnership building, and (b) lack of attention to the potential benefits of public-private partnerships. Cost recovery of extension services not only reduces the cost to government but also demonstrates to farmers that extension services have economic value. In the case of the extension programs organized under the ATMAs, most material technologies and services were sold to farmers on a cost-recovery basis, and farmers paid part of the cost of training programs. In the traditional system in non-project districts, the distribution of free inputs and services to farmers continues to create a dependency relationship on government so that many farmers look to extension for a â€œhand-outâ€ rather than as a reliable source of technology and information.
P010563 | FINANCIAL SECTOR DEV PROJ. (FSDP) | South Asia | India | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1995 | 2003 | 2003 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/687971474665731997/text/000020051-20140607154526.txt | http://documents.worldbank.org/curated/en/687971474665731997/pdf/000020051-20140607154526.pdf | An adjustment operation focused on broadly applicable policies is a more appropriate instrument (than an investment operation directed at indivdual banks) to foster market orientation, allocative efficiency, and competition in the financial sector.For an operation to be successful in achieving objectives such as those of FSDP, it must close the serious gaps in the legal and judicial framework, address corporate governance, and provide the right incentives for enhanced managerial autonomy and accountability, which in most cases requires a bolder move to privatize the public banks.Specific monitoring indicators and performance benchmarks must be part of the design of a project such as the FSDP
P010566 | GUJARAT STATE HIGHWAY PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/932391474664007436/text/000020051-20140619080655.txt | http://documents.worldbank.org/curated/en/932391474664007436/pdf/000020051-20140619080655.pdf | 1. Success of a project is rests on strong continued leadership and commitment of the top management. This project enjoyed strong leadership in the government, in the implementing entity, and in the Bank team. All three contributed to the project's success. 2. Stakeholder consultation process is part of the product. The Environmental Management Unit in the implementing entity was successful not only because of effective training, well planned impact mitigation, and recovery of roadside community and water supply facilities but, especially, because of continuous and enduring community consultation programs and processes to achieve community acceptance.3. Strong and cooperative contract management ensures good, cost-effective results. The Employer and the Consultant worked together toward the same objectives. Well-informed project management, supported by knowledgeable consultants, started at design, continued through procurement and control of cost and time schedule to completion. The Consultant was also able to transfer knowledge to the Borrower.
P010566 | GUJARAT STATE HIGHWAY PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2008 | 2012 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/608151468285010919/text/706780PPAR0P010IC0disclosed08030120.txt | http://documents.worldbank.org/curated/en/608151468285010919/pdf/706780PPAR0P010IC0disclosed08030120.pdf | 5. Lessons 5.1 The following main lessons are drawn from this report\. Â· The physical and financial sustainability of a road network hinges on the road agencyâ€Ÿs capacity to undertake needs-based and timely implementation of road improvement and maintenance works. This enables optimal use of available funds, and avoids greater costs of repair in the future. Beyond project completion, Gujarat has worked to consolidate its capacity for and progress in monitoring road condition data and prioritizing road works on that basis. Data from selected state highway segments indicate that road condition (roughness) has been kept within acceptable limits. Karnataka has more work to do in building similar capacity, and this is reflected in signs of distress that are noted in project roads, five to seven years after improvement. Failure to take timely remedial action will result in far greater rehabilitation costs in the future. Â· Institutional and administrative capacity-building should be carried out in step with the readiness of the target agency to internalize it. The ability to improve capacity on multiple fronts such as planning, procurement, contract management, and environmental and social safeguards may differ from one road agency to another, and may take more than one project cycle to materialize. In retrospect, institutional reforms in the Karnataka project could have been attempted in a phased and incremental manner, allowing time for them to be integrated with wider operations, and obtaining the support of key government departments and their leadership. Â· As road agencies evolve from being providers of roads services to â€žmanagersâ€Ÿ of increasingly outsourced functions, it is essential that core competencies are retained and strengthened to ensure sustainable management of the road network. The core competencies relating to planning, technical design, road management systems, procurement, contract management and environmental and social safeguards have been impacted to different extents in Gujarat and Karnataka due to outsourcing to consulting firms, staff turnover, staff depletion and lack of follow-up training. A credible mechanism for human resource management must be put in place to fill these gaps. Â· The roads agency should lead the way in creating a productive working relationship with other entities involved in the implementation of roads projects. A culture of partnership and cooperation was demonstrated in Gujarat between the Roads and Buildings Department, road works contractors and supervising engineers which minimized disputes and speeded up implementation. The Roads and Building Department worked to earn the confidence of other parties through responding in a credible and consistent manner to issues that arose during project activities. Â· Decentralization of the Bankâ€Ÿs project leadership and supervision does not appear to confer any significant advantage over the task leadership based at headquarters. Feedback from the road agencies in Gujarat and Karnataka suggests that the locus of Bank task management did not make a significant difference in terms of response time and attention span. In practice, both the Karnataka project, which was managed from the Bank's country office, and the Gujarat project, which was managed from the Bank headquarters, were able to conduct a similar number of supervision missions (KSHIP\. 15; GSHP\. 17). However, lending and supervision costs were significantly higher for the Gujarat project. Â· A knowledge product that seeks to cover a subject that has already been well studied must provide clear justification of its likely added value. The Road Transport Service Efficiency Study covered subject matter that had been covered by other prominent reports within India. The new study was justified by highlighting the added value from surveys and interviews of stakeholders and gathering the experience of comparator countries. The study served to renew policymakers' attention to politically challenging issues facing operators of freight trucks and passenger bus services, and the motor insurance sector.
P031829 | OZONE DEPLETING SUBSTANCES II | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1995 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/589111474653136938/text/000020051-20140613051723.txt | http://documents.worldbank.org/curated/en/589111474653136938/pdf/000020051-20140613051723.pdf | The establishment of regulations requiring private sector firms to abide by national environmental commitments is necessary if substantial benefits are to be achieved efficiently.Compensation to private-sector firms for subproject completion should be performance-based or be based on the achievement of agreed-upon milestones should the financial burden for completion be too heavy on firms. This would act as an incentive for the timely completion of subprojects.Even for an implementing agency that has had considerable experience and has partnered with the Bank in the past, it is important to ensure that the agency possesses the necessary capacity to fulfill its functions under the project in question, as new projects may entail different procedures and new knowledge requirements.
P033965 | Environmental Remediation Pilot Project | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/529441474856679259/text/000020051-20140612065516.txt | http://documents.worldbank.org/curated/en/529441474856679259/pdf/000020051-20140612065516.pdf | The project demonstrated the importance of: (a) securing government commitment to reform and clean up at the highest level; (b) having an effective communication strategy to win over the public; and (c) ensuring the continuity of a highly skilled and committed project management team throughout intervention. Based on the results of the beneficiary survey, the ICR contains a detailed list of lessons from the viewpoint of different partners in the process.
P033965 | Environmental Remediation Pilot Project | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2003 | 2009 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/602781468016206321/text/488100PPAR0P031C0Disclosed071301091.txt | http://documents.worldbank.org/curated/en/602781468016206321/pdf/488100PPAR0P031C0Disclosed071301091.pdf | 7. Lessons 7.1 The experience o fthe ERPP andEPSAL suggests the following lessons for future projects that attempt to address past environmental damage and improve environmental performance inthe process o fprivatization. e A development policy loan supportingprivatizationwith environmental remediation should include strong measures by the Government to monitor and rewardcompliance (or punishnon-compliance) to ensurethat remediationand compliance plans are completed on schedule. Inthe EPSAL, eventhough all o fthe policy conditions were met and the RPs and CPs were signed, the achievements in terms of implementation o fthe plans, along with their environmental results, were mixed. Over-reliance onthe goodwill o fthe enterprises themselves was a risky strategy, as changes inownership, management, and financial performance stalled progress on remediation and compliance. e Eveninwell-prepared EIAs,it is difficult to include sufficient detail inthe technical specifications o fremediation investments. Modifications indesign and re-negotiations duringimplementation should be anticipated, and possibly reflected inalongerproject implementationperiodandhigher thannormal contingency funds. e Evenwhenthe State assumes responsibility for remediatingpast environmental damages o f SOEs, setting a cap on the State's liability creates risk for potential investors and delays during re-negotiations. The possibility o f letting the State assume more o f the risk for additional remediation costs shouldbe considered. e Harmonizing country environmental legislationwith international best practice i s a necessary but not sufficient condition for improved environmental performance. In development policy lending for environmental protection, more attention needs to bepaidto improving the country's implementation practices, track record, and capacity inenvironmental regulation. This i s likely to require carefully targeted technical assistanceto buildthe capacity o f national and sub-national environmental authorities. A parallel technical assistance loan, or a wellcoordinated programof technical assistance fundedby other donors, should be considered. 7.2 Several findings o fthis PPAR are relevant to IEG's ongoing evaluation o fthe WBG's safeguard andsustainability policies. First, there were-difficultiesencountered in choosing an environmental classification for the EPSAL. Funds were not channeled through financial intermediaries, butthe fact that not all o f the participating firms had been identified at appraisal meant that the EIA requirements o f an classification could not be met. A modification o fthe classification criteria may be inorder. 7.3 Second, the PPAR was able to compare two projects with similar objectives but different financing instruments\. aninvestment loan and a DPL. Both projects supported the process o fremediating past environmental damage inthe process o fprivatization. While the DPL provided more flexibility thanthe investment loan in terms o fthe selection o fparticipating enterprises andthe preparationand implementation o f remediation and compliance plans, this flexibility came at the cost o f less control on the part o fthe Government and the Bank over the completion o fthese plans. Future DPLs inthis area needto build inbetter monitoring and enforcement mechanisms to compensate for less detailed Bank and Government control over safeguards and environmental compliance. 7.4 Finally, the EPSAL placedtoo little emphasis on the enforcement o f environmentalregulations compared to its focus on the passage o f legislation. A greater focus on institutional capacity, compliance monitoring, and sanctions for non-compliance would have improvedthe likelihood o f achieving environmental outcomes. This finding i s similar to one of the conclusions of IEG's 2008 evaluation of environmental sustainability, namelythat the achievement o f environmental outcomes i s more elusive thanthe achievement o fintermediate outcomes such as policyandinstitutionalreforms. This calls for a greater focus on environmentaloutcomes, along with a more diligent effort to develop andmonitor indicators to measure these results.
P034004 | Health Project | Middle East and North Africa | Lebanon | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1995 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/102611475078520590/text/000020051-20140612133510.txt | http://documents.worldbank.org/curated/en/102611475078520590/pdf/000020051-20140612133510.pdf | Bank teams preparing projects for major policy reform initiatives should undertake a thorough analysis of the prevailing governance structures in the concerned sector, including a review of the institutional absorptive capacity and decision-making process for major reforms.Supervision from in-country Bank staff can be particularly beneficial for projects that aim to undertake major policy reform.Integration of the project staff into the regular staffing structure of the relevant line ministry should be agreed as early as possible during project implementation.
P034035 | LB-ADMIN. REHAB. | Middle East and North Africa | Lebanon | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/173501474491058690/text/000020051-20140612101719.txt | http://documents.worldbank.org/curated/en/173501474491058690/pdf/000020051-20140612101719.pdf | 1. In post-conflict countries, close supervision is especially important. Changes in Government (there were five different governments during this period) made matters worse as regards taking decisions and tracking progress. Lack of continuity on the Bank side compounded matters. 2. Well qualified and well paid PIU staff need to be mainstreamed into the regular civil service. OMSAR tended to operate in an enclave manner. 3. The Annex 1 indicators are very general. In order to have a handle on tracking actual progress, specific indicators including on outcomes in addition to outputs, should have been included.
P034037 | LB: AGRI. INFRA. DEVEL. | Middle East and North Africa | Lebanon | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/804211474596663186/text/000020051-20140613051051.txt | http://documents.worldbank.org/curated/en/804211474596663186/pdf/000020051-20140613051051.pdf | The ICR contains a number of lessons, albeit not new, which are sustained by the evidence. With some modification, the most important are:(i) Approval and financial procedures for project sub-component investments should be established and tested for efficiency before project start-up.(ii) Early training in procurement is important especially where there is no prior experience with Bank procedures.(iii) A strong environmental unit is needed for infrastructure and should be put in place at the start.(iv) A strong M&E Unit is needed to function from the start of the project - the most often repeated OED lesson. This usually calls for either buidling on an existing M&E structure or initiating the establishment of a unit even before effectiveness.
P034038 | URBAN TRANSPORT DEVELOPMENT PROJECT | Middle East and North Africa | Lebanon | IBRD | FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/651831478614596275/text/ICRR-Disclosable-P034038-11-08-2016-1478614569988.txt | http://documents.worldbank.org/curated/en/651831478614596275/pdf/ICRR-Disclosable-P034038-11-08-2016-1478614569988.pdf | Several lessons are selected from the ICR with some adaptation of the language: Forprojects in countries with fragile politicalconditions and instability, a new project is preferable over additional financingfor the scale -up of activities. While additional financing can be used to cover for price increase and cost overruns inorder to facilitate completion of activities, a new project is better suited to carry out new activities or expand the scope, thusallowing more time for completion, if needed, through extensions. Political commitment andstrong technical support is essential to achieve results in improving urban transport in a fragile environment. Under thisproject, enforcement of the park meter scheme and an active role of the responsible agency in traffic management and enforcementhelped achieve the outcomes that are likely to be sustained. Finance of land expropriationspayments with loan proceeds provides certainty on the funds availability and the timeliness of transfer. Under thisproject, the lack and unreliability of government financial resources for the required land expropriations delayed the project anddid not permit its full disbursement as originally planned.
P034080 | BIODIVERSITY COLLECTIONS PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1994 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/693011474909160383/text/000020051-20140604053021.txt | http://documents.worldbank.org/curated/en/693011474909160383/pdf/000020051-20140604053021.pdf | The main lesson is that the Bank needs to be more selective in the projects that it undertakes. Even a project such as this one, with a very limited objective focussed on strengthening a single research center (with a staff of 335) with a very narrow role in the context of sectorial management and the country's public sector, required a substantial level of support, including 36% of grant funds and 11 supervision missions (with an average of four staff per mission), and achieved only moderately unsatisfactory results. In view of the project's experience, the Bank needs to carefully consider whether such exercises are consistent with its role.
P034081 | CN - XIAOLANGDI MULTI. II | East Asia and Pacific | China | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/456251474896951409/text/000020051-20140612145707.txt | http://documents.worldbank.org/curated/en/456251474896951409/pdf/000020051-20140612145707.pdf | Project success was greatly assisted by having in place the implementation organization with full decision-making authority, and accountability for implementation performance, prior to the start of the project.The use of an international panel of experts substantially reduced the time needed for resolving conflicts on technical issues. The panel on environmental management issues and the establishment of an office of the environmental supervising engineers ensured that contractors followed all environmental requirements and that early corrective actions were taken when needed. This is particularly important for projects that have significant environmental management risks. The use of a disputes review board to resolve claims issues proved to be extremely useful and resulted in most claims being expeditiously resolved.Training of staff in financial and business management and tariff negotiations prior to completion of the project added significantly to project sustainability.
P034081 | CN - XIAOLANGDI MULTI. II | East Asia and Pacific | China | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2004 | 2008 | PPAR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/812911468218977436/text/41122.txt | http://documents.worldbank.org/curated/en/812911468218977436/pdf/41122.pdf | CONCLUSIONS AND LESSONS 3.42 Duringthe Xiaolangdi andTarimBasinProjectsthe Bankwas able to work with national-level organizations o f water policy issues giventhe cross-cutting nature o fthese enterprises. For the first and only time the Bank was inthe privilegedposition o f assisting MWR with the integrated planning ofthe Yellow RiverandTarimRiverBasins. This was importantbecausethe incremental impact o fthe projects the Bank supported on water resourcesmanagement could be modeledat the river basin scale andfully integrated with China's large portfolio o fpotentialprojects. Inboth cases, this approach indicatedthat the Bankassistedprojects were better than project alternatives that were thus rejected. And in both cases the Bank-assisted projects put a large emphasis on saving water ina river basin context. 3.43 Reviewingthe post-1990 portfolio o fagriculturalwater projects supported bythe BankinNorthandWest Chinathere hasbeena clear trendfrom buildingnewirrigation that increasesbasin-wide water demand, to projects that seek to improve water use efficiency and conservation efforts. However, there have beensome strategic mistakes that should have beenavoided -the Guanghong IrrigationProject approved in 1999 effectively doubled water use for irrigation inthe mid-reaches o fthe Yellow River near Xian. At the same time the downstream Water Conservation Project approved in2001 was extremely effective inreducing overall water consumption and i s a prime example o fwhat the Bank should support. There are three lessons\. The Bankneedsto elevateitsengagement in China's water resources policy discussions above the provinciallevelto emphasizethe perverseincentivesthat are created by extensive agricultural water subsidies. Subsidiesfor irrigation and landmanagementjeopardize water conservation effort, longer term sustainability o f irrigation and landreclamationprojects and water availability for towns, cities, industryand environmental management. Despite more than two decades o fBank partnership and several state-of-the art projects piloting new approachesthese tendto be enclave projects. While Chinese senior planners and politicians at the center acknowledge that pricing should play a role inensuring more efficient and rational allocation anduse o f water this i s still as at an early stage o f applicationand far from politically acceptable inthe provinces. Without such a change inthe near future water shortages and environmental consequences o fresource mismanagement will continue to grow to crisis proportions; 0Monitoring and Evaluation requires capacity building and reorientation to measureoutcomes and impacts.There is little virtue inimplementing development models for reclaiming degraded lands or for river basin management if impacts on welfare, incomes andthe economy cannot be accurately measured. While this is less o f a problem for physical achievements it is a major problem for measurement o f socio-economic outcomes and impacts. Muchmore attention has to be givento understandingthe appropriate counterfactual and ensuringunbiased sampling. There i s also an issue around selection o fthe most effective M&Emodel considering the outcomes expected and the cost o f the projects. Appropriate training to redressthe problems found inM&Ei s clearly indicated. Inaddition, more attention should be givento fully utilizing existing Chinese resources. The Ministry o f Finance has indicatedthat it has a national network o f monitoring that include socio-economic indicators and that consideration should be givento working with themto triangulate evaluative findings; and 0 Muchgreater care is required in dealingwith issues of attribution when estimatingex-post economic rates of return. Specifically this means clearer definition o fthe project counterfactual and a systematic accounting o fthe effects o f exogenous actors and investmenton project impact. Without such attention to these exogenous factors there i s a danger that estimated ERRSgive a false impression o f project impacts. This, inturn, may leadto incorrect lessons on development effectiveness and the efficacy o fpolicy, institutionaland engineeringmeasures utilized to achieve development objectives.
P034082 | Public Sector Adjustment Loan (PSAL) | Europe and Central Asia | Hungary |  |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2001 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/187051474906480471/text/000020051-20140529074824.txt | http://documents.worldbank.org/curated/en/187051474906480471/pdf/000020051-20140529074824.pdf | Several important lessons emerge from this operation: (1) A voluntary pension system switching strategy is preferable to a forced switch as it avoids legal problems and builds broad support for the system; (2) The privately managed pension system must be backed by appropriate regulatory provisions to ensure good corporate governace; (3) Performance indicators are critical to assess implementation of pension reform; and (4) Effective operation of single tranche loans require fulfillment of major conditions prior to disbursement.
P034083 | Urban Transport Project | Europe and Central Asia | Turkmenistan | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2002 | 2002 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/763201475092971300/text/000020051-20140604055801.txt | http://documents.worldbank.org/curated/en/763201475092971300/pdf/000020051-20140604055801.pdf | Scope and depth of institutional reform and policy changes have to be well linked to the political environment in which it is to be implemented, and a better understanding of the political economy of the country is required.Mapping of project reform objectives to the loan /project agreement results in greater likelihood of their implementation and compliance. Bank practice of comprehensive economic and financial evaluation, as regards investments of vehicle replacement in financially constrained environments, encourages task managers to be more concerned with justifying the proposed investments using a nominally correct economic framework, even in the absence of reliable data. Simpler less comprehensive approaches used by the business world actually yield more practical information, such as the financial comparison of vehicle retirement vs rehabilitation and replacement in cost terms. A good practice would be a combination of narrower scope higher quality analyses nested within a larger conceptual framework with lower expectations.OED lessons also suggest that attempting reforms within the public sector through tripartite arrangements is difficult to enforce and brings limited returns. Without formal devolution of responsibility over urban/city transportation to the municipality, performance contracts are insufficient instruments for accountability. Further, there should be more effort to increasing competition within the main urban network through greater de-regulation of the sector.
P034091 | AR-Higher Education Reform Project | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/257461474631031048/text/000020051-20140613031356.txt | http://documents.worldbank.org/curated/en/257461474631031048/pdf/000020051-20140613031356.pdf | Crisis response can be more effective and rapid if built upon existing institutions and on-going projects. Donors must have flexible procedures so as to be able to move funding from various projects into priority areas, such as health activities.During reform activities, it is important to ensure ownership at all levels to keep operations on track in the face of adverse macro-economic circumstances. Even limited investment, distributed based on transparent and objective selection procedures, can go a long way toward stimulating a culture of change and quality improvement.
P034092 | Technical Assistance Project | Europe and Central Asia | Turkmenistan | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1995 | 2004 | 2005 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/523471474488880394/text/000020051-20140613030630.txt | http://documents.worldbank.org/curated/en/523471474488880394/pdf/000020051-20140613030630.pdf | 1) In cases of fraud, corruption or mis-procurement, the Bank should act quickly and decisively. The Turkmenistan case reflects badly on the Bank and on the policies it promotes. 2) TA projects for countries initiating a transition to a market economy should be designed with the borrower, be simple and well focused on a few priority areas.
P034093 | Public Sector Resource Management Adjustment Loan | Europe and Central Asia | Kazakhstan | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/557631474650931468/text/000020051-20140529073154.txt | http://documents.worldbank.org/curated/en/557631474650931468/pdf/000020051-20140529073154.pdf | Increasing the effectiveness of resource mobilization and improvements in the efficiency with which government resources are used require an IBRD strategy that focuses on the overall system of governance for the use of public resources. This system includes a legislature to oversee the use of public funds; an external auditor to attest to the propriety of public expenditures; a free press and participative civil society; and the development of domestic monitoring and evaluation systems to inform policy and enhanced public sector performance. The public sector reform management loan components were relevant but should have been conceived as a part of a broader strategy to improve institutions that ensure accountability to the public for effective use of public resources, and to develop government monitoring and evaluation systems.
P034095 | Financial Sector Adjustment Credit (FSAC) | Europe and Central Asia | Kyrgyz Republic | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1996 | 1998 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/996461474665264203/text/000020051-20140529075431.txt | http://documents.worldbank.org/curated/en/996461474665264203/pdf/000020051-20140529075431.pdf | This project confirms the importance of Government Commitment and ownership for the success of a project. Detailed monitoring of implementation is especially valuable in an operation such as this which addresses many aspects of a problem and involves a number of institutions, as may be typical of financial sector reform operations.
P034101 | PK-TELECOM REG & PRIVAT | South Asia | Pakistan | Blend |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/172101474482922657/text/000020051-20140612095014.txt | http://documents.worldbank.org/curated/en/172101474482922657/pdf/000020051-20140612095014.pdf | (a) The establishment of new regulatory agencies and the enabling of private sector participation takes considerable time and multidisciplinary resources, particularly legal and economic expertise. This project was very ambitious and it was necessary to extend its implementation by four years, two of which were needed to develop and implement deregulation measures. (b) A sector reform agenda is better implemented by a ministry having a limited sector portfolio. In Pakistan, when the responsibility of the telecommunications sector was transferred to the MOITT, the project took momentum and the GOP could then announce the progressive implementation of the telecommunication sector policies.(c) A training program for capacity building in new institutions should be designed and detailed implementation arrangements agreed to at an early stage of project preparation and appraisal. This is crucial to achieve institutional development.(d) The introduction of the Calling Party Pays regime and prepaid calling cards is a strong incentive to growth in the mobile telephone market.
P034106 | Urban Infrastructure and Pilot Decentralization | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/858991474634094914/text/000020051-20140607154653.txt | http://documents.worldbank.org/curated/en/858991474634094914/pdf/000020051-20140607154653.pdf | The delegation of contract management and reliance upon private consultants can be powerful and successful means of leveraging otherwise limited municipal capabilities.Both municipalities and the relevant central government department must have minimum core in-house capacity to use a project's management tools effectively.Enhancing the competitiveness of local construction and consultant firms requires a long-term sustained effort that goes well beyond the scope of the project.Even when responsibilities are delegated to an AGETIP-type agency, government involvement in institution and capacity building is essential for reform to succeed.More attention needs to be paid to the selection and definition of performance indicators and target to ensure that they truly measure the results of a project.
P034112 | OT - EMERGENCY REHAB. I | Middle East and North Africa | West Bank and Gaza |  |  | Infrastructure | Transport | SPF | IPF | 1994 | 1999 | 2000 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/239311474595946282/text/000020051-20140522110912.txt | http://documents.worldbank.org/curated/en/239311474595946282/pdf/000020051-20140522110912.pdf | The project provides several important and interdependent lessons whose generalizability should be investigated. Among the most important ones are the following: (i) the short time span in which local capacity can be developed when given the opportunity and responsibility (and good supervision); (ii) the importance of close on-the-ground supervision for learning, results, and timely completion -- even in difficult circumstances; (iii) 'ownership' and 'capacity' as dynamic developmental concepts that take time, patience, resources, an allowance for initial reduced quality, and good relationships with the mentors (re: the termination of the project's Management Consultant for the lack of responsiveness to the borrower's needs).
P034118 | ECON REFORM/DEVP LN. | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 1997 | 2001 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/366891511185568183/text/multi0page.txt | http://documents.worldbank.org/curated/en/366891511185568183/pdf/multi0page.pdf | 5. Lessons The main lessons from ESAL and ERDL 1-111 are\. * Changes in the incentive regime are necessary but not sufficient conditions for efficient and rapid economic growth. Linking rapid growth to these policy changes in a short Country Assistance Strategy period gives rise to expectations that may not be fulfilled. As a consequence, policy makers in borrower countries, and the policy reforms themselves, become politically vulnerable. That vulnerability could result in the government being voted out of office at the next elections. * Sequencing reforms to emphasize sectors with growth potential, such as exports, at the beginning would bolster belief in the benefits of the incentive changes and soften the blow of job loss when uncompetitive sectors begin to decline. It would also bolster private sector confidence and encourage investments that are internationally competitive. * A resident mission and timely and substantial technical assistance are crucial for the successful implementation of complex reforms involving several government agencies, new institutions and laws. The subsidiary lessons from ESAL and ERDL I-III are\. * Government ownership of reforms and political consensus for some sensitive reforms such as privatization are crucial for project success. It is advisable to assist in developing political consensus rather than pushing for early implementation. * In complex and wide-ranging policy programs that require substantial legal and institutional change, confining conditionality to core activities would increase the prospects for successful implementation. * Institutional change, especially when full consensus has not been reached, tends to take a long time, usually longer than expected by Bank staff. These delays should be factored into project design. * Series of single tranche operations that are disbursed after agreed reforms are implemented offer flexibility for reform programs with uncertain time lines.
P034154 | ER-Ports Rehab SIL (FY98) | Eastern and Southern Africa | Eritrea | IDA | FCS | Infrastructure | Transport | IDA | IPF | 1998 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/477901475096944023/text/000020051-20140626074824.txt | http://documents.worldbank.org/curated/en/477901475096944023/pdf/000020051-20140626074824.pdf | The ICR has identified a number of lessons, of which the most important are listed below:Restructuring a project in a timely manner to respond to changed circumstances is likely to increase the chances of achieving intended project results. However, the timing and relevance of injecting additional resources and introducing new activities towards the tail end of implementing a project should be assessed critically. They could complicate the institutional and implementation arrangements as well as imply injecting new skills in the project implementation team which may not be readily available.Pooling resources for a project from multiple donors reduces the transaction costs for the Recipient through streamlined procurement processing and implementation arrangements, but also increases the coordination and administration costs for the Bank project team. This is compounded by a situation where the Recipient is a new state, as it involves intensive supervision on the part of the Bank.Risk assessment and risk management/mitigation measures for projects in fragile states should not underestimate the political risks and include â€œpull-outâ€ options or alternative arrangements. Having an appropriately defined risk assessment with mitigation measures would assist project teams to recognize any events potentially impacting project implementation and respond quickly with appropriate actions.
P034161 | FINANCIAL SEC T.A. | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1995 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/460241474577976070/text/000020051-20140602111525.txt | http://documents.worldbank.org/curated/en/460241474577976070/pdf/000020051-20140602111525.pdf | 1. Supervision of technical assistance from the field can very productive, much more so than supervision from headquarters. In this case, supervision from the field allowed for tailoring technical assistance to the evolving needs of the agencies. 2. Technical assistance projects need to strike a balance between adequate definition of the project (to avoid a black box approach with lack of accountability) and over-specification which inhibits the Bank's capacity to adjust project formulation to changing needs and better information. 3. Regular monitoring, and proximity in terms of supervision from the field, are strong pluses for effective implementation which takes advantage of this balance in project formulation. 4. Financial sector reform takes time and careful nurturing by the country with flexible assistance from the Bank.
P034162 | MAHARASHTRA EARTHQUA | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1994 | 1999 | 2000 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/283721474573277692/text/000020051-20140522104255.txt | http://documents.worldbank.org/curated/en/283721474573277692/pdf/000020051-20140522104255.pdf | Key lessons learned through the experience of this project are:emergency rehabilitation projects should include longer-term assistance for disaster management planningdamage assessment criteria should be simple (a minimum of categories) yet still technically specific, widely publicized, and appropriate to local construction practices and conditions earthquake-resistant technical recommendations have to be persuasive--only if potential beneficiaries "own" project recommendations can there be sustainability economic rehabilitation and the strengthening of local social and organizational capacity is an integral part of the reconstruction process project management units can be very effective in the post-disaster context if they are committed to participatory principles and endowed with competent leadershipemergency projects should allow for a longer implementation period than three years so that vulnerability reducing activities and improved disaster management practices can take hold.
P034162 | MAHARASHTRA EARTHQUA | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1994 | 1999 | 2005 | PPAR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/473931468253190043/text/32515.txt | http://documents.worldbank.org/curated/en/473931468253190043/pdf/32515.pdf | Lessons Learned 51. The mission's field visits to disaster projects inGujarat andAndhra Pradeshwere extremely useful for highlightinggood practice inMaharashtra. Among the lessons suggested bythe project experience are the following\. 52. Careful poverty targeting and sensitiveproject design can lead to major poverty reduction impacts even under difficult post-disaster circumstances. The project provided better than adequate housing for beneficiaries at the bottom o f the social ladder, which shows the potential o f using the reconstruction periodto promote policies to effectively reduce the gap between rich and poor. Inthis sense, the project achievements are a lasting monument to the convictions o f the supervising officials. 53. Simplicity of message is essential to the adoption of disaster-resistant technologies. The project promoted simple earthquake-resistant features for non-engineered masonry construction that could be understood, adopted, and applied by the villagers. Their wide dissemination and use will benefit a much larger population than originally targeted, as these techniques would be used infuture house construction. Training 7,000 local artisans in earthquake-resistant techniques (facilitated greatly by the simplicity o f the message) was a major contributor to changing the construction practices inthe disaster-affected region. 54. Damage assessmentsneed to be simple, carefully tailored to local construction types, and they should lead to damage awards closely tied to the actual cost of what needs to be done. Although the damage assessment was undertaken ina professional manner, the original compensation system was too complicated. The experience o f using the criteria o fthe International Association o f Earthquake Engineering for damage assessment was painful for all concemed. The assessment criteria may work well for modem, engineered housing where what can be observed on the surface indicates what i s going on within the wall. But they were abysmal for classifying damage to mud-bonded stone structures. Many o f the people interviewed attributed the bulk o f implementation problems to early difficulties distinguishingbetween damage categories 1-3 inthe first two damage assessments. Specifically, informants noted that because the distinctions between categories were not intuitive, this led to a non-standardized assessment because o f observer error. 55. Future damage assessments that use the IAEEcriteria inareas where owner-built earthen houses are common need to carefully modify them so that they suit local conditions andbuildingpractices. Post-earthquake safety evaluations should determine ifbuildings are habitable and include some sort o f solution for the owners o f those that are not. 56. The OED study o f Natural Disaster lendingshould explore the ways used inother Bank-financed disaster projects have arrived at definitive beneficiary lists ina less contentious manner than the one used here. Pressures to include additional beneficiaries are inevitable and usually prove impossible to resist. Throughout the project period, the pressure to classify additional families as eligible beneficiaries continued unabated, and after project closing (even as late as the date o f the OED mission inSeptember 2004) the GOM was still negotiating with families denied benefits. There must be a better way. 57. Beneficiaries entitled to new housing need to make a significant contribution. Bank emergency reconstruction lending used to expect cost recovery at levels that could not feasibly take place, given all the disaster victims had lost andneeded to replace. A recent PPAR'O o f an earthquake project that targeted low-income families and expected full cost recovery found that over halfthe original beneficiaries hadbeen unable to pay and consequently had given up their homes. So the fact that MEERP provided finished houses for fiee i s a reaction to earlier lessons learned.'' But there i s probably a midpoint between full cost recovery and no cost recovery that does not create quite so much dependency and perpetually escalating expectations among beneficiaries. Because they are usedto receiving everything for free, and then havingthe govemment come back again and again (bathrooms, stone floors see para 25 and Box 2), the PPAR mission found that many beneficiaries innew villages are currently unwillingto pay user charges for urban services, and it even found one group that expectedthe government to paint and maintain their new houses inperpetuity. In contrast, families inthe villages that stayed inplace are continually improving their homes andcompounds usingtheir own funds. 58. In the aftermath o fnatural disasters an element o f grant funding is probably unavoidable, but official largesse should be limited so that beneficiaries contribute their own savings, or labor, or materials, or time for rehabilitation. Evenwhere people have no insurance and l o w incomes, full grant-based rehabilitation is socially pemicious. It i s also not economically sustainable. Expectations inIndiahave risen. Following the Gujarat earthquake, there was full awareness o f what hadbeen provided inMaharashtra, and that awareness constrained project design. 59. Problems were created by uneven rehabilitationheconstruction incentives. Villages litigated for the right to relocate even when it was technically contraindicated and likely to cause individual families great inconveniencebecause the benefits given to villages that only rehabilitated compared so unfavorably with what other groups obtained. 60. Owner-driven construction was more effective than the use of contractors. During project design it was believed that the only way to produce the huge number of new dwellings neededwas to bringinlarge contractors. The results were as desired. However, in the villages that were not relocated (where people were expected to repair their units but they actually built new ones) a much larger number o f (quite comparable) houses were built, and contractors were generally not involved. Inthose villages it was possible to use localpeople inconstruction, so employment was created for people from the disaster-affectedregion. (Contractors generally used imported labor because workers from outside the area were willing to work 12-14 hours a day inresponse to piecework incentives). Also, when homeowners were put incharge o f the process, houses are more adapted to each family's requirements -there was no one-size-fits-all approach necessary. What works inIndia, a large country with ample production o f buildingmaterials and a highlymobile work force 10.Report No. 28389 on the El Salvador Emergency Earthquake Reconstruction project (Loan 2873) 11.Inthe villages that were not relocated, the beneficiaries made contributions averaging 10to 20 percent o f the construction cost. may not work everywhere. But the reliance on owner-managed construction was even more widely usedfollowing the earthquake inGujarat, and the results were equally positive. 61. Supewisoy personnel do not always need higher education. Thejunior engineers that worked on the project were over-qualified for what they were expected to do, and this can be seen intheir concentration on their personal agenda o f furthering their careers by landing government posts. A number o fpeople interviewedinthe project area suggested that future projects working with post-disaster housing could more effectively and economically be supervised bybuilders and masons rather than engineers, at least as regards owner-built structures. 62. Grievanceproceduresneed to be inplacefrom the outset. The strikes, protests, and litigation that plagued this project were partly the result o f not having efficient and effective processes to redress grievance inplace. An ability to make decisions and communicate them speedily to the involvedparties is important. A dissemination capacity i s helpful, especially ifdecisions haveimplications for other beneficiaries. 63. Participation should only be encouraged when expressedpreferences will be taken into account. Community participation i s not apanacea, andmore participationi s not always better thanlessparticipation.Inthis project, participationwas extremely useful inthe design o fhouses and their layout. Insome o fthe villages visited, however, it created problems that were difficult to resolve duringthe construction process. This was partly a result o fnot decidingbeforehand what aspects o f contracted work homeowners should supervise and what the observers should do inthe event o f a grievance. Women's groups cited local supervision o f construction as being a triumph o fwomen's empowerment. Onthe other hand, the missionmet with representatives o f several construction firms that hadbeeninvolved in activities supervisedby community groups duringthe project. The interviewedcontractors (and several public officials) were critical o fwhat they classedas excessive community participation leadingto blackmail inthe housing component. Insome cases, homeowners triedto extract bribes from contractors before approvingthe work. Constructioncompanies attributed work stoppages inKillari (see Box 2) to frictions and misunderstandingsbetween builders andvillagers unfamiliar with the proper use o f steel reinforcements andconcrete. In their opinionbeneficiaries should beinvolvedinthe planningphaseandinhousingunit allocation. It seems clear that inthe villages visitedhaving individual owners supervise the construction o fjust their own house was counterproductive, although the use of construction committees for the same purpose worked better, inpart because the committees were able to benefitfrom training. 64. Participationmay have been even less useful where there were stark social divisions, and a majority may have beeninclinedto call for things that are unfair to the minority. Some villagers heldup construction starts, demandedbihcation o f villages or new relocation sites, triedto dictate buildingmaterialpreferences, delayed house allocationdecisions, and interferedwith the contractors' work. Reportedly community participationwas more problematic inlarger villages andthose where the political leadership had a clear agenda. Pressuring Village Level Committees to accept women members was a short-livedtriumph, as once the project closedwomen's participationwas discontinued. 65. Relocation of villages that consist mostly of one and two story buildings duringpostearthquake reconstruction is usually a mistake in the long-term. Although the GOM considers the relocatedvillages to be the project's greatest success, and a survey conducted at the end o f theproject showedthat 77 percent o frespondents thought that the new villages were better thanthey hadhadbefore, therewere no strongtechnicalreasons to support the decisionto relocate, andmany good reasons not to do so. The social interactionpattems that have built up insettlements that havebeenoccupiedfor alongtimearerarelyifeverpreservedinanew site. Inmost villages the modemstyle houses provided forgo the courtyards whichwere popular intraditional architecture. Many ethnic groups restrict women to the home compound. Since the new villages do not have walled courtyards, insome cases this results inthe day-to-day restriction o f women to a small room. Although most relocated families now own more land thanformerly, inmanycasesthey are farther fi-om their fields, family graves, andplaces o f worship thanthey were before. The designo f new villages, though similar to what prevails in the newerneighborhoodsinthe periphery o fMumbai, didnot fully consider the social, economic, and cultural needs o fthe villagers. Longer distances betweenhouses (and a lack o f courtyards) made it difficult for villagers to socialize.
P034180 | EARLY CHILDHOOD DEVELOPMENT | Eastern and Southern Africa | Kenya | Blend |  | Human Development | Education | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/300081475073735823/text/000020051-20140613032602.txt | http://documents.worldbank.org/curated/en/300081475073735823/pdf/000020051-20140613032602.pdf | Early childhood education projects are highly desirable and much needed to help poor children prepare for successful primary-school attendance. However, they often have complex arrangements, require extensive collaborative work among diverse stakeholders, and in low-income countries may be prone to failure. - It is possible to empower communities to carry out early childhood education. However, they need timely financial support as well as training and follow-up from the government. Simple project designs with simple fund-flow arrangements are needed when community involvement is required.- Preschool education teachers may be difficult to train and retain due to low remuneration and a limited educational background. To prevent attrition and wastage of training funds, better incentives,including better terms of employment, and non-monetary incentives should be implemented.
P034181 | Urban Works & Microenterprise Pilot Project | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 1999 | 2000 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/665251474650902980/text/000020051-20140528120403.txt | http://documents.worldbank.org/curated/en/665251474650902980/pdf/000020051-20140528120403.pdf | OED agrees with the lessons cited in the ICR, for example, early attention should be given to financial management and transparent financial procedures to ensure future sustainability.
P034212 | MAHAWELI RESTRUCTURI | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 1998 | 2006 | 2004 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/885521474553737897/text/000020051-20140612131640.txt | http://documents.worldbank.org/curated/en/885521474553737897/pdf/000020051-20140612131640.pdf | Before a project of this nature is approved it is necessary to make a detailed analysis of the legal and institutional requirements for satisfactory transformation of existing irrigation agencies; experience from other countries suggests that better results may be obtained by changing the incentive structure, particularly creating a competitive environment for finance. Measures could include results-based budget release and divestiture to the private sector. Setting up a new public agency is another option but should probably only be pursued as a last resort. The key institutional and policy reforms need to be implemented before a large investment loan is made; alternatively, a structural adjustment operation may be appropriate, backed up by a parallel technical assistance credit. Expert technical assistance is vital for the design of complex institutional restructuring. Institutional reform of this type presupposes a programmatic approach, with appropriate donor coordination; a single investment project funded by one donor agency is not an appropriate vehicle.
P034213 | General Cadastre and Land Registration Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/969681474502259746/text/000020051-20140617130521.txt | http://documents.worldbank.org/curated/en/969681474502259746/pdf/000020051-20140617130521.pdf | 1. Land cadastre and registration services are best combined under one agency. The overwhelming lesson from this project is the illustration it provides of implementation capacity under two different institutional structures: (i) implementation of land cadastre and registration through two separate agencies; or (ii) combined implementation under one agency. International experience suggests that the one agency model is significantly better. The Romania experience provides a comparison of the two approaches in the same project. Both the Bank staff and the Borrower leave little doubt as to their views: from the ICR - "The new agency has achieved in less than two years what the project was unable to achieve under the dual agency system in five years"; and from Romania's ICR - "There is no doubt that the Agency itself is the greatest achievement of the project.". The data comparing achievements before and after establishment of ANCPI appear to corroborate these views.2. A deferment of an intended institutional change at least needs advance planning and a clear transition plan for the institutional transformation. The ICR refers to awareness at appraisal (though this is not indicated in the PAD) that the single agency approach was better for the longer term. The apparent rationale for sticking with two agencies was that the project should not add further complications to already challenging new activities; hence, it would be better for staff to become familiar with the technical practices of cadastre and land registration before institutional change. However, If deferment was the best decision, a clear road map for transition to the single agency model could have been prepared. In effect, the transition could have been a built-in project activity, under a detailed (though flexible in implementation), time-framed. and costed Transition Plan. 3. Major institutional changes, even when made late in the project period, can pay off. The project illustrates that change to a better institutional model, even with the disruption that this may entail, can be better than continuing with a somewhat unsatisfactory institutional arrangement. The existing two-agency model, with all its faults was making some achievement. Yet the Government, with the Bank's support, decided to create a new combined agency some 6 years after project approval and already at the end of a 1.5 year extension (a further extension of 1 year was subsequently made). A lower risk and more comfortable stance might have been to stay with the existing institutional structure for the remaining months of the project. However, the risk paid off, with resultant major achievements over the last 2 years.4. Information technology needs greater attention and resources in the design and implementation of a land management project. The ICR reports that one of the most difficult aspects of the project was the development of a Joint Information System to provide records of all land mapping, registration and transactions. The JIS took four years to set in place, more than twice as long as planned. Recommendations made in the ICR include: (i) the hardware and software of the system should be procured under separate contracts to enable as much attention on the software as on the hardware (the project's combined procurement resulted in emphasis on hardware); (ii) a phased approach, starting with a simpler system, and upgrading it later may be best; and (iii) building into the project (and project preparation) adequate technical assistance to help the agency establish the system.
P034213 | General Cadastre and Land Registration Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/453991468005956033/text/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.txt | http://documents.worldbank.org/curated/en/453991468005956033/pdf/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.pdf | 6. Lessons (a) General Lessons 6.1 Given the large attitudinal shift involved in the agricultural transition, government officials and project staff needed substantial technical assistance and training before operations could be expected to succeed. Governments showed strong commitment to the preparation of the projects under review. Yet once the loans were approved, delays in declaring effectiveness were experienced for several of the loans, while during early implementation even staffs of the project units often did not fully understand how specific project activities linked to objectives. If this was true at the center, it was even truer in the localities where projects were implemented. Consultant services were not always used as effectively as they might have been (this was the case for credit operations in the Armenia ARSP and Georgia ADP). There was an attitudinal lag\. most government officials in the agricultural ministries still exhibited a command and control mentality with respect to agricultural development. 6.2 When the leadership of project implementation units was skilled and motivated and their staffs were well trained, project implementation generally proceeded smoothly once some experience with the Bank's procedures had been acquired. This was especially the case with project units for the Romania ASSP and Georgia ADP, whose performance improved rapidly once professionally adept managers were recruited to replace earlier political appointees. Similarly, the appointment of a technically trained person to manage a purely technical agency such as the Romania's ANCPI for the GCLR Project resulted in a rapid acceleration of project implementation. 6.3 In the complex and rapidly changing ECA environment, sound donor coordination was critical. The two Romania projects rebounded from a very poor start once the Bank and other members of the donor community began working together to help Romania meet the European Union accession requirements. Together they helped Romanians to take advantage of the grants-in-aid made available under the Community's special accession program for agriculture and rural development. 6.4 Where donor coordination was less sharp, progress was slow. Management of the land registration component of the Georgia ADP was, at times, complicated by conflicting donor expectations that proved hard to resolve. In Tajikistan, it took the Bank until 2003 to realize that if donors spoke with one voice to the government on land reform, it might create conditions more favorable for the farms that the project had restructured. (b) Lessons from the Sub-sectors Agricultural and agribusiness services 6.5 Farmers and rural business owners will respond enthusiastically to innovative technologies corresponding to their needs. Experience from the assessed projects showed that agricultural research and extension works best when it is consultative and demanddriven. In Romania, the competitive grant approach proved to be an excellent vehicle both for generating applied research findings and extending these to farmers. But, as Armenia showed, the competitive grant scheme can also lack the strategic focus needed to effect a comprehensive strengthening of agriculture research. To respond to farmers' needs, competitive research grants should be open to all applicants, including non-governmental organizations, universities, and government research institutes. For pure farm extension work, the financial sustainability of advisory services in a setting with many small, semisubsistence farmers can only be achieved if government acknowledges its responsibility to provide these citizens with appropriate and effective advice and information. This will probably entail some measure of subsidy given the low incomes of many of the clients; but that need not preclude use of private contractors to deliver the service. Land administration 6.6 The Bank's international experience with land policy issues has strengthened the design of projects in ECA; but there is no uniquely correct model for land administration or land reform and effectiveness depends on responsiveness to local conditions. Whether grounded in restitution (Romania), or in the granting of more or less equal allotments to agricultural workers and other rural residents (South Caucasus), or being limited to the transfer of usufruct rights only (Tajikistan), each program was designed to accommodate socio-political necessities in the aftermath of de-collectivization. In Tajikistan however the project design was overly ambitious and not tailored enough to the local circumstances. 6.7 It makes sense to adopt a unified approach to land administration. Cadastral and land recording/land registration services are both technology and information intensive. These two services need to be closely linked and preferably digitalized to increase efficiency and enhance access. The unified approach worked well in each of projects reviewed here that had a land administration component (Azerbaijan FPP and ADCP; Georgia ADP, and Tajikistan FPSP). Rural finance 6.8 With appropriate regulation, technical advice and staff training banks that lend to rural areas can operate sustainably. To realize the potential from scaling up commercial bank lending to rural areas, it is essential\. (a) to confirm that supervision and prudential regulation has been developed and can be effectively enforced; (b) to prequalify the banks deemed eligible to participate in tendering for loan proceeds, based on rigorous prudential examination; (c) to ensure rigorous monitoring of the credit program, with the assistance of international expertise if necessary; (d) to ensure that the terms, maturities and grace periods of loans are proportional to the expected returns and the estimated economic life of the investment; and (e) to allow intermediaries to administer credit reflows in accordance with their own terms and conditions. 6.9 The non-bank financial intermediaries have an important role to play in rural areas; but it is important to be realistic about their capabilities. There is a strong demand for locally-based credit facilities (such as credit unions) in rural villages, and for rural financial institutions that take credit. These institutions must be savings-driven and encouraged to diversify their loan portfolio rather than focus only on farm lending. Sustained, strong support in the form of training and supervision is required if they are to evolve into viable financial institutions. The volume of lending needs to keep step with the growth in management skills and savings mobilization among members (overly-rapid expansion in the Georgia ADP and ambitious targets in the Azerbaijan ADCP considerably stressed implementation of farmer credit programs in these two projects). In general, these projects have shown that small village-based credit cooperatives are not an appropriate mechanism for large-scale credit delivery.
P034301 | PHASE OUT OF ODS PRE | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1997 | 2007 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/803101475114055267/text/000020051-20140618080858.txt | http://documents.worldbank.org/curated/en/803101475114055267/pdf/000020051-20140618080858.pdf | 1. In dealing with an understandably reluctant private sector, full commitment of the government to the project objective is essential for timely implementation.2. Although GEF and MP projects are often rather small and use grant resources, they need to be subjected to the same rigorous standards for appraisal and supervision as the Bank's own portfolio, especially in assessing risks and in actions to address revealed problems.
P034489 | MALAWI RAILWAYS REST | Eastern and Southern Africa | Malawi | IDA |  | Infrastructure | Transport | IDA | IPF | 1995 | 2000 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/897591474482603012/text/000020051-20140529165214.txt | http://documents.worldbank.org/curated/en/897591474482603012/pdf/000020051-20140529165214.pdf | Investments by parastatals ahead of privatization are not always valued by the potential bidders and there is a real danger that many of the investments could be considerably devalued. All investments prior to concessioning, therefore, need to be subjected to a rigorous technical and financial evaluation. To the extent possible, all long-lived investments prior to concessioning should be avoided.Restructuring of railways while waiting for the completion of the concessioning process (which can take a number of years) can play an important role in helping the privatization process. During the interim period, restructuring can yield benefits such as retrenchment of surplus staff, reduction in operating costs, improved accountability, etc. which are critical for reducing losses and making the railways attractive to private sector.
P034489 | MALAWI RAILWAYS REST | Eastern and Southern Africa | Malawi | IDA |  | Infrastructure | Transport | IDA | IPF | 1995 | 2000 | 2001 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/277901511185742786/text/multi0page.txt | http://documents.worldbank.org/curated/en/277901511185742786/pdf/multi0page.pdf | 6. Lessons Learned 6.1 Railway reform in Malawi was one of the early efforts in Africa to restructure and concession railway operations to the private sector. The experience provides some useful lessons\. * Restructuring can make eventual privatization process more manageable, but significant performance improvement should not be expected in the interim. * Substantial investment in the interim should be avoided if possible since prospective concessionaires do not always put commensurate values on these investments. * It is important to separate the operation and downsizing functions during the restructuring exercise. The Malawi railway restructuring created two separate entities to manage the reorganized railway operation and to carry out the retrenchment of surplus staff and disposal of surplus assets. * There is a need to keep an intense policy dialogue with the government to maintain the focus on the privatization agenda. The project's conditionality to make substantial disbursement conditional on progress on the privatization agenda turned out to be a useful instrument to keep the focus on privatization. * Staff Retrenchment is a complex undertaking. It requires careful planning and rigorous economic and social assessment. An analysis on the distribution of costs and benefits should be included as part of cost-benefit analysis. * Establishing appropriate regulatory mechanism for the post-privatization period should not be overlooked.
P034490 | MX TECHNICAL EDUC/TRAINING | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Education | IBRD | IPF | 1995 | 2003 | 2005 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/569271474481784543/text/000020051-20140612154116.txt | http://documents.worldbank.org/curated/en/569271474481784543/pdf/000020051-20140612154116.pdf | For large and complex projects to be implemented satisfactorily, experienced staff must participate in the preparation process and the interest of important stakeholders must be ensured. High-cost projects need continuous political and private support to be implemented, and this support must be ensured during appraisal.- Certification of skilled workers may be less important than training. Employers are more likely to be interested in whether workers can actually carry out the required tasks than knowing whether, on paper, they have acquired a particular formal standard of competence or not. This is a particularly important issue when employers must pay for the certification process.- Studies and impact evaluations must be designed so as to obtain sufficiently clear answers to guide implementation and the direction of possible changes. When causality of results is unclear, the investments dependent on them may become less prioritarian.
P034491 | Power Transmission & Distribution Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/768141475072494933/text/Albania-Power-Transmission-Distribution.txt | http://documents.worldbank.org/curated/en/768141475072494933/pdf/000020051-20140612091629.pdf | 1. Government commitment and ownership of power reforms are paramount for the project to yield real benefits and for objectives to be successfully achieved.2. Careful balancing of "carrots and sticks" (i.e. constructive engagement and suspension of project) in Bank supervision is key, especially when Government commitment is lacking. 3. Appropriate monitoring and evaluation systems, that incorporate social and equity indicators alongside efficiency-related indicators, are important for highlighting the impact of Bank-supported power projects and reforms on the economy and on the poor, and help bring focus on role of efficient and equitable electricity and energy more generally as a means to sustainable development and poverty reduction. 4. Power projects that address the efficiency and reliability of transmission and distribution facilities should place an equal emphasis on demand-side management to improving the supply of electricity.5. Whilst voucher privatization can be a useful way to attempt to spread the potential benefits of privatization (as well as increase its social acceptance), minority privatization (i.e. keeping majority Government ownership) may not ensure the benefits which private ownership has the potential to bring about.
P034578 | BR RGS Highway MGT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/156321475075726664/text/000020051-20140615101332.txt | http://documents.worldbank.org/curated/en/156321475075726664/pdf/000020051-20140615101332.pdf | Political and fiscal uncertainties can be a potent combination in increasing project risk, and should be assessed with care, especially where the borrower has experienced these factors in the recent past.Results-based contracts for road maintenance and rehabilitaiton can be effective even within a fiscally-constrained environment.
P034579 | Land Reform Implementation Support Project (LARIS) | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1994 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/163281475097924738/text/000020051-20140612133927.txt | http://documents.worldbank.org/curated/en/163281475097924738/pdf/000020051-20140612133927.pdf | To reduce transaction costs a project should place responsibility for cadastral and registration functions in the hands of a single agency. In this project, training of counterparts exposed them to new ideas about international good practice so that, by project end, there was broad support for the single-agency idea; the follow-on project will build on this. Large investment loans should generally be deferred until the right legal framework is in place.Eligibility criteria for participation of sub-national governments need to spelled out before Board approval. Patience and flexibility is needed in addressing the very special needs of transition economies; it takes time to build a workable relationship with counterparts. Procurement of equipment for regional offices needs to be based on visits to check the needs of each office rather than blanket ordering of standard packages.
P034581 | HOUSING | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 1999 | 1998 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/419751474898462187/text/000020051-20140519064204.txt | http://documents.worldbank.org/curated/en/419751474898462187/pdf/000020051-20140519064204.pdf | The experience shows the difficulty of developing lending operations at the sub-national government level with a new borrower, which is not familiar with Bank operations and where the executive branch does not enjoy full co-operation with the legislature. The Ukrainian legislators did not give support to the project mainly because it would have benefited only three cities. The main lesson is that the Bank should better understand at the project preparation phase the political complexity and the decision making processes in the country that would affect the project approval and implementation.
P034583 | Structural Adjustment Credit | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1998 | 2000 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/158921474508654081/text/000020051-20140522103230.txt | http://documents.worldbank.org/curated/en/158921474508654081/pdf/000020051-20140522103230.pdf | This SAC reaffirms the importance of a high level counterpart to champion reforms. With this, the Letter of Development Policy can be a useful tool in implementing reforms. Continuity of Bank teams is extremely important. Mass privatization schemes depending on vouchers can be useful to accelerate privatization, but they do not guarantee wide participation in the assets being privatized because of resale at discounts.
P034583 | Structural Adjustment Credit | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1998 | 2004 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/746081468751804137/text/26439.txt | http://documents.worldbank.org/curated/en/746081468751804137/pdf/26439.pdf | 8. Lessons Learned 8.1 Georgia's weak governance severely limitsthe country's ability to create conditions conducive to economic development and the effective use of development assistance-The problems that limit growth inGeorgia transcend economic policy. The political and geographic fragmentation o f the country poses severe challenges to the executive. The inability o f the executive to overcome obstacles posed by the parliament and regional officials, establish a minimumlevel o f the rule o f law, and overcome a pervasive culture o f corruption severely limits the country's ability to establish sustained, broad-based growth with significant job creation. 8.2 For a country such as Georgia, which experienced economic collapse, it is incumbent that the Bank give high priority to prompt measures that can directly mitigate conditions for the poorest. 53This section is based on interviews with energy sector firms, govemment officials, and Bank staff. 8.3 Turnover on the country team limited program effectiveness-From 1994to 1998,there was one Country Economist for Georgia. Officials interviewed cited the benefits that they believe this continuitybrought. However, since 1998, there have been3 Country Economists, and an interval o f around6 months duringwhich the position was unfilled. While there werejust two Country Directors duringthe periodcoveredby this PPAR, and good continuity on the rest o fthe Country Team, the tumover diminished the continuity o f the program, andprobablyconstrained the ESW that was performed. 8.4 A more robust and timely ESW programwould have been beneficial to the design o f the reformprogram-The Country's first poverty studywas completed in 1999; the design o f the reform program would have benefited from earlier work inthis area. A study o fthe sources o fgrowth might also have beenbeneficialbyidentifyingsectors from which growth might be expected to flow, and then considering means by which to facilitate such growth. A Public Expenditure Review-a veryuseful analytical tool for a country with Georgia's perennially weak fiscal situation-was completed in 1996, and then not again until 2002. Fiduciary reports (CFAAs and CPARs) were completed infrequently. The rapid tumover inCountry Economists was probably part o fthe reason for the weak ESW. 8.5 Turnover among policy officials hinderedreform progress-During the seven years coveredby this PPAR, there were seven Prime Ministers and four Ministers of Finance. There was also substantial tumover among other officials concerned with implementingthe reform program. For an official contemplating a brieftenure, it i s more difficult to appreciate the benefits o f reform, and so this tumover made reform progress considerably more difficult.
P034584 | MUN SERVICES DEVT | Europe and Central Asia | Latvia |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/547751475084250776/text/000020051-20140607172511.txt | http://documents.worldbank.org/curated/en/547751475084250776/pdf/000020051-20140607172511.pdf | The ICR highlights the following:The project coordination role falls too much on the Bank's shoulders when there is no clear project coordination responsibility within the supervisory ministry.Technically meaningful and timely indicators are necessary to guide project management. Targets set should be realistic and attainable, and revised during a project's mid-term review if they are not.The national approach to utility regulation and supervision needs to be extended down to the purview of municipal utilities.In assisting municipalities, it is not a good idea to separate sub-project appraisals and approvals from the award and management of sub-loans, as was done under the MDF
P034605 | FIN SCTR & BUS ENV | Latin America and Caribbean | Guyana | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1995 | 1999 | 2001 | ICRR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/373991474589537350/text/000020051-20140529164319.txt | http://documents.worldbank.org/curated/en/373991474589537350/pdf/000020051-20140529164319.pdf | Broad government commitment to a project is critical for success. While this project benefited from commitment by some agencies, project implementation suffered from lack commitment, especially concerning privatization. However, the privatization program succeeded in spite of this because of the efficiency of the consultants engaged under this project. In privatization, open consideration of social and environmental issues are critical: labor continuity, severance arrangements and employee stock ownership options are aspects of privatization which can greatly enhance the effectiveness of privatization programs. Attracting and retaining qualified staff, with adequate compensation, is essential. Project design should be kept simple. This project comprised a number of components which might have been better handled in separate projects.
P034605 | FIN SCTR & BUS ENV | Latin America and Caribbean | Guyana | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1995 | 1999 | 2004 | PPAR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/671391468750034306/text/29334.txt | http://documents.worldbank.org/curated/en/671391468750034306/pdf/29334.pdf | 5. Lessons and Recommendations 5.1 Governanceproblems and distrust are the binding constraints to improving the investment climate and getting PSD going in Guyana.Unless realprogress is made on those fronts -and donors needto recognize their very limitedcapacities to help inthose areas donor-drivenprojects can expect to continue to have low rates o freturn, andmay evenbe harmful. 5.2 Every component of every donor project and everyproject process (such as consultations on project design, the hiringo fconsultants, procurement o f goods, selection o ftrainees, and choice o fregulatory options) should be assessed to seeing how theprojects andprocesses can avoid deepeningdistrust, and ifpossible, serve to build trust across the racial divide. Participatory approaches, as appliedinpreparation o f the PRSP, shouldbe applied inmonitoring andevaluation o f allprojects, bothbydonors andclients. 5.3 More diagnostic work is needed to identifi strategies and tacticsfor rationalizing incentives, building sustainable institutions, andfostering social capital. IfGuyana could build its social capital, it would have no lack o f financial capital or humancapital. New studies are not needed to undertake seriouspublic sector reforms, including civil service reforms, that have been postponedfor a decade or more. These reforms are a necessary preconditionto effective capacity buildingandthe sustainabilityof institutionsthat are currently overwhelmingly donor-dependent. 5.4 Closer donor coordination is needed to increase the eficiency and cost-effectiveness of technical assistanceprojects aimed at institutional development. Having multiple cooks (donors) inthe samekitchen(project component) preparingthe samemealsbutwithdifferent ingredients andtastes is neither efficient nor cost-effective. While inpolicy-basedoperations there maybe a case for some overlap, ininstitutional development TA projects there should be clearer division of responsibility among donors to avoid duplicationandoverlap. Agreements should be sought on lead donor andpooling arrangements reflecting donors' experiencein Guyanaand comparative/competitive advantages. 5.5 Donors and GOGalike need to strengthen ongoing and ex-post monitoring and evaluation of IDprojects to get prompt andtrue accounts not only o fprogress toward objectives but also o fthe quality, impact, andcost-effectiveness ofthe particularinstruments employed (in TA projects these include consultant advice, consultant-prepared studies, andvarious types o f training and equipment). 5.6 Donors need toface up to the labor market distortions and other downsidesfor the longer run being caused by their hiring and salary supplementationpractices. Donor policies on salary supplementation o fpublic servants (including consultants performing line positions in government) needto be rationalizedand harmonized with a view to promotingrather than postponingcivil service reform.
P034606 | FIN MRKTS & PENS REF | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 1999 | 2000 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/828941474570831710/text/000020051-20140526221726.txt | http://documents.worldbank.org/curated/en/828941474570831710/pdf/000020051-20140526221726.pdf | #NAME?
P034606 | FIN MRKTS & PENS REF | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 1999 | 2006 | PPAR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/985611468198871795/text/350650REV0pdf.txt | http://documents.worldbank.org/curated/en/985611468198871795/pdf/350650REV0pdf.pdf | 4. Conclusions and Lessons 4.1 The Bank's private sector development strategy has yielded mixed results. Attempts to reach international best practices in a relatively short period o f time from a weak foundation have encountered the following problems\. lack o f political support; continued government involvement; weak institutional capacity; and deeply entrenched governance issues, which are not conducive to an ambitious reform agenda. In the current highly fluid political environment, the Bank needs to narrow its focus to a few k e y areas. There were in each sector more options for privatization and/or private sector participation that could have been considered and that might have diffused some o f the opposition to the reform. Greater appreciation o f the political opposition to the Capitalization may have raised some questions about taking a less ambitious approach to the program such as more public participation earlier in the process or perhaps a phased approach. A broader public information campaign focusing o n the 'why' capitalization was needed m a y have been more effective in diffusing opposition to reform. O f course w e can only speculate as to whether the outcome might have been better. Nevertheless, there have been some winners'' in the process such as the telecommunications and the electric power sectors. In the case o f Hydrocarbons, perhaps other approaches to capitalization could have been considered based o n the experience o f other energy-producing countries. The frail regulatory environment 21The Government states that i t considers Borrower Performance with regard to P F M O I1to have been satisfactory. See Annex H. now needs to be safeguarded against further erosion through government interference. The Superintendencies o f Telecommunications and Electric Power need to be reinforced in order to sustain the good outcome in those sectors. 4.2 The pension reforms should have been designed with more safeguards to prevent the huge fiscal burden. Moving forward, every effort should be made to avoid the financing o f the cost o f pension reforms by transferring resources from the private pension system. 4.3 With respect to financial sector reforms, greater attention should have been paid to the frail condition o f the banking system prior to adopting new norms, such as those dealing with loan classifications, and to have provided a bail-out strategy early on accompanied by an exit strategy for non-viable institutions. 4.4 Support o f public sector reforms has run into similar obstacles\. weak institutional capacity, lack o f commitment to accountability, opposition to implement changes, shifting political environment marked by high staff turnover, and limited enforcement capacity. Perhaps a more important obstacle to successful reforms was the lack o f commitment to a hard budget constraint. Fiscal reforms were needed to create a favorable environment for a financial operations project. The Bank overlooked some o f these factors by pursuing an optimistic and ambitious strategy with projects that taxed the government's implementation capacity. 4.5 The Bank's view o f risks was perhaps somewhat optimistic. I n some cases as in the CPAC, the risk mitigation strategy perhaps did not pay as much attention to mounting opposition to capitalization. While these are helpful steps, risk assessment needs to be addressed more proactively in terms o f project design, with a direct relation between the level o f risk and complexity o f the project. 4.6 Lessons from the Bank's experience with the four projects\. 0 The political and social environments are fundamental factors behind the outcome o f reforms. Even the best designs can fall prey to the political process. In the case o f Capitalization, opposition to reform was underestimated. The design o f pension reforms could have analyzed the risk factors more carefully and have incorporated a more intensive Bank support during the critical transition phase. The P F M O I I was overdimensioned and did not take into account the ingrained culture o f discretionary spending for which a more directed approach to fiscal policy adjustment could have been considered. 0 When institutional weaknesses are prevalent, the Bank needs to limit the scope o f i t s operations, and be less ambitious in terms o f project objectives. The Implementation Completion Report for the Financial Markets and Pension Reforms underscored that Bolivia's pension reform went far beyond previous reform experiences and i s being widely observed by other reforming countries. Sometimes achieving this distinction could backfire in terms o f lack o f institutional capacity to implement the reforms. A country with weak institutional capacity such as Bolivia may need to go at a slower pace or implement a less complicated program in terms o f pension reforms. 0 Communicating to stakeholders and educating them about the reasons for the reforms can be just as important as the passage o f laws. Greater efforts could have been made in communicating the importance o f reforms to all political groups as w e l l as to the beneficiaries. SIRESE could have given greater priority to public relations particularly in educating consumers. Greater outreach to public service employees o n the benefits o f the new financial management system m a y have been an effective motivational factor. However, sometimes the benefits are evident as in the case o f the telecommunications sector where cell phones became an affordable commodity to many Bolivians. 0 Risk assessments o f projects need to identify specific loadproject components subject to risk and provide contingent plans to guard against adverse impact. Financial sector operations involving new regulatory standards need to b e accompanied by contingency plans in case the reforms result in systemic weakening, and in the design o f the program attention needs to b e paid to the financial and technical resources available to address those contingencies.
P034607 | HN PUB SEC MOD TAC | Latin America and Caribbean | Honduras | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2000 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/990181474895867374/text/000020051-20140607163433.txt | http://documents.worldbank.org/curated/en/990181474895867374/pdf/000020051-20140607163433.pdf | 1. Combining instruments, with a TA project complementing an adjustment credit was important for a successful design and implementation of the reform process. 2. The commitment of the Government was demonstrated throughout the process by high-level attention to the reform program, adoption of detailed implementation programs prior to credit effectiveness, proper staffing of counterparts, and a pro-active approach to privatization, including discussions with the private sector. In spite of this, however, the Government failed to follow through on some important reforms, including privatization and social security; cutting back administrative expenditures; and dealing with problems such as absenteeism and multiple employments of civil servants. Hurricane Mitch also played an important role in detracting Government's attention from the ambitious and complex reform program. Therefore, Government commitment is a necessary, but not sufficient condition for success of complex reforms.
P034607 | HN PUB SEC MOD TAC | Latin America and Caribbean | Honduras | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2000 | 2007 | PPAR | Less than 10 million | Unsatisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/333201468256481887/text/37126.txt | http://documents.worldbank.org/curated/en/333201468256481887/pdf/37126.pdf | lessons and moved away from this type o f lending in favor o f more modest singletranche programmatic lending. W h i l e government ownership was solid at the outset, IDA did not adequately ascertain the strength o f the many competing interest groups opposed to the operation. Assessing the broader political context for reform is important in assessing its likely implementation and sustainability. The market framework and strategy for reform in the energy sector should not focus solely on privatization and competition. While this model has worked well in many countries, the size and institutional features o f the market m a y necessitate an interim strategy o f partial privatization and regulation. The disbursement o f final tranches in structural adjustment operations should be tied to the desired outcomes, not inputs, and IDA should avoid granting waivers connected to these outcomes. This lesson also applies to one-tranche programmatic operations, which also should focus o n outcomes, not inputs.
P034609 | Private Sector Development 2 Project | Europe and Central Asia | North Macedonia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/173211474896263391/text/000020051-20140612085216.txt | http://documents.worldbank.org/curated/en/173211474896263391/pdf/000020051-20140612085216.pdf | The Bank should take fully into account the lessons of prior projects before initiation of new ones in the same areaAdequate TA is essential for a credit line project in a country that has a relatively underdeveloped banking system
P034617 | ML SELINGUE REHAB. | Western and Central Africa | Mali | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/170671474652928552/text/000020051-20140607171444.txt | http://documents.worldbank.org/curated/en/170671474652928552/pdf/000020051-20140607171444.pdf | (1) This project proves that the Bank can justify financing a project generated out of necessity even when the main implementing agency is an unstable institution, provided that country commitment is strong, and essential measures are put in place and promptly enforced.(2) This project also shows that a simple two-pronged lending operation involving both physical infrastructure and institutional development components can be handled successfully by giving adequate attention to both components as if they were separate, self standing projects. (3) IDA credits should include direct funding for carrying out environmental actions. In this project the cost of the Environmental Action Plan (EAP) â€“equivalent to about US$2.5 millionâ€“ was not included in the Credit. Lack of financing is a formidable barrier for the timely implementation of an EAP.
P034618 | Labor Market Development | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 1996 | 2006 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/240211474501198963/text/000020051-20140617131059.txt | http://documents.worldbank.org/curated/en/240211474501198963/pdf/000020051-20140617131059.pdf | The key lesson from this project is that a pilot can indeed be replicated. The LMIS was a functional system that achieved its purpose and was not beyond the capacity of the responsible agencies in other municipalities, so they were able to adopt the system.There are likely lessons to be learned from the delays, though the ICR is not sufficiently clear on the cause of the delays to draws out these lessons explicitly. It is likely that policy reforms need buy in from all important stakeholders before they can proceed, thus delaying the operation if it depends on these reforms.
P034622 | Ozone Depleting Substances (ODS) Phaseout GEF Project | Europe and Central Asia | Hungary |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1996 | 1999 | 2000 | ICRR |  | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/816981474573799775/text/000020051-20140526211148.txt | http://documents.worldbank.org/curated/en/816981474573799775/pdf/000020051-20140526211148.pdf | The official ban on ODS trade from 1996 has led to an upsurge in illegal trade in ODSs, both imports and exports, which undermine the objective of phasing out ODS use and the financial viability of the 3R scheme. As a consequence, the MOE is currently studying a project to train and equip customs officers to identify ODSs and effectively control their smuggling, which is believed to be a feasible task. Since this problem was also observed in connection with ODS Phaseout projects in other countries, and could potentially recur with similar future programs involving trade restrictions, (e.g., in connection with a proposed phaseout of persistent organic pollutants), it would seem desirable to include such enforcement components from the start, rather than waiting till the damage has begun.
P034755 | KH - Technical Assistance Project | East Asia and Pacific | Cambodia | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/297911475078776061/text/000020051-20140607163858.txt | http://documents.worldbank.org/curated/en/297911475078776061/pdf/000020051-20140607163858.pdf | 1. Technical assistance projects should not cover too many activities. The board range of components covered by this project made it difficult to focus on and support substantial improvements in most of the components. 2. New borrowers, as was Cambodia, with little capacity, need to be supported by realistic projects. Basic institutional capacity is essential in the preparation and implementation of a TA project, and this capacity was nonexistent in Cambodia. Countries with similar levels of development should be subject to careful evaluation of institutional capacity before assistance is extended. 3. As projects are developed, careful attention should be paid to avenues of communication with the government, and where these are inadequate, they should be recognized as a constraint and taken into account in project formulation.
P034891 | VILLAGE INFRASTRUCTU | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1995 | 1999 | 1999 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/175181474904196175/text/000020051-20140522080933.txt | http://documents.worldbank.org/curated/en/175181474904196175/pdf/000020051-20140522080933.pdf | The key lessons from this project are: (i) large projects can be used to address village level needs at considerable speed, and (ii) village participation improves resource allocation and enhances transparency. in particular,direct channeling of Bank funds to village level was highly effective and did not result in either loss of "control" or "waste" as predicted by Bank staff who advocated standard channeling through ministerial agencies.villagers voluntarily contributed land thus negating the legal department's intention to impose "standard involuntary resettlement and compensation guidelines" that would have delayed implementation and been contentious.
P034891 | VILLAGE INFRASTRUCTU | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1995 | 1999 | 2001 | PPAR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/278441511187359238/text/multi0page.txt | http://documents.worldbank.org/curated/en/278441511187359238/pdf/multi0page.pdf | 6. Findings and Lessons Based on questionnaire surveys applied to 197 people in 33 villages, this audit has sought to evaluate the likely poverty impact of three projects. It cannot pretend to be an impact evaluation\. there is no comparison of with project and without project scenarios and, for reasons indicated in Chapter 1, no attempt to stratify beneficiaries into poor and less poor groups. Nevertheless, the audit has hopefully demonstrated that project objectives were consistent with poverty reduction and, because these objectives were met, it is reasonable to infer that the poor benefited and that, in two of the three projects, these positive results will be sustained. The audit has found that the village midwife program is effective, that the roads built have in most cases been adequately designed and adequately maintained, and that in two projects there has been significant local capacity building. Project results do not appear to have been adversely affected by the 1997 East Asian financial crisis. Probably the crisis was felt more in the cities than in the countryside. In rural Central Java, at least, a separate Bank consultation found agreement among men, women and young people that. wellbeing had increased in the ten years up to 1999, with a 10-15 percent fall in the proportion of poor households.38 This is borne out by the audit survey, which found a majority of village chiefs and women reporting that most people were better off than they had been five years before (Table 3,
P035076 | ZM-Power Rehab SIL (FY98) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2006 | 2008 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/886691474591812187/text/000020051-20140615113843.txt | http://documents.worldbank.org/curated/en/886691474591812187/pdf/000020051-20140615113843.pdf | It is critical to establish the political viability of the reforms supported through extensive consultation with actual and potential political leaders. Critical policy issues must be addressed up front prior to effectiveness (prior to Board approval would be preferable).Unless the Authorities respect their undertakings, notably in the area of tariff adjustments, then this will lead, as in the case of ZESCO, to an unsustainable financial situation. This issue is also emphasized by the DBSA in its comments. Much stronger insistence by the Bank on such issues is required, including the threat to suspend disbursements.Large environmental subcomponents, such as the GTDP, require government commitment and adequate financing.It is mistaken to expect a power utility to have the capacity to implement effectively social projects such as agricultural extension schemes and feeder roads.Rehabilitation projects in the power sector tend to be much more complex than green field schemes.Commercialization and fair, soundly based and regulated transfer pricing mechanisms are minimum elements of power sector reform (these elements were not specifically addressed in the PAD).Governments should not use utilities to provide hidden subsidies to large industrial consumers.Senior managers in utilities need capacity in the financial and commercial, and not just the engineering sides of the business. ZESCO's staff, while displaying technical excellence, was weaker in other critical management areas.Cross conditions of effectiveness with parallel lenders need to be spelled out in the PAD and included in the risk analysis.Trying to address, in one single project, not only investment requirements but also a substantial range of policy issues accumulated during more than 20 years of absence from the sector (including policy dialogue), is likely to lead to an over-complex and unwieldy operation.Arguably this project should have been canceled when it became clear that there was no real Borrower commitment to the agreed reform agenda. However, this would have been difficult given the large number of agencies involved.
P035079 | WASTE DISPOSAL PROJECT | East Asia and Pacific | Korea, Republic of |  |  | Sustainable Development | Water | IBRD | IPF | 1995 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/531161474908447352/text/000020051-20140607160833.txt | http://documents.worldbank.org/curated/en/531161474908447352/pdf/000020051-20140607160833.pdf | Private operators of environmental facilities are less likely to be exposed to pressures from various local civic groups than the Government. Currently, in Korea there are about 130 incinerators for specified waste, but only Kunsan is owned by the Government. Thus far, only Kunsan has been exposed to systematic demands from local civic groups for various payments, with arguments pertaining to the protection of public health. This is likely because the Government is much more sensitive to negative exposure in the press or at staged meetings than are private operators.Future feasibility studies of wastewater systems should include a detailed assessment of land use plans and enforcement of respective regulations especially for mixed residential and industrial areas. Also, the feasibility studies should conduct a thorough assessment of the quality of wastewater that will be generated by the new industries that will be connected to the system.For efficient and better quality treatment, the legal-commercial aspects of the sewerage service, requiring a contract between the service provider and the beneficiary, including permission for the quantity and the quality of wastewater, should be pursued.
P035080 | NI INSTITUTIONAL DEV CR | Latin America and Caribbean | Nicaragua | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/517581474486036133/text/000020051-20140607163650.txt | http://documents.worldbank.org/curated/en/517581474486036133/pdf/000020051-20140607163650.pdf | 1. Agencies need to have inducements to engage in a system of performance contracts (the project's IRAs). One such inducement would be to make this a requirement for budget authority after a certain date. 2. Staffs of institutions targeted for reforms should be informed of the goals and methods to be used, to promote active participation and ensure consistency and common understanding of tasks.
P035081 | Ozone Depleting Substances (ODS) Phaseout GEF Project | Europe and Central Asia | Poland | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/623841474907856675/text/000020051-20140602112919.txt | http://documents.worldbank.org/curated/en/623841474907856675/pdf/000020051-20140602112919.pdf | The ICR offers a number of lessons, among them: a. The careful selection of enterprises requires appraisal of their financial viability and sustainability.b. Public awareness campaigns are essential for success and benefit by the use of well-known personalities as spokespersons.c. Environmental labeling and financial incentives are useful in the market.d. It is easy to underestimate the amount of technical assistance that may be required to prepare subprojects.Although not included among the lessons in the ICR, it is worth noting the utility of including a clause in the grant agreement that aims to encourage continued use of the financed equipment for purposes consistent with the objectives of the grant, even when enterprises go bankrupt. The ICR notes (p. 23) that such a clause has been a feature of several subsequent ODS phaseout projects.
P035082 | Municipal Finance Project | Europe and Central Asia | Poland | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2002 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/891081474510113961/text/000020051-20140607150928.txt | http://documents.worldbank.org/curated/en/891081474510113961/pdf/000020051-20140607150928.pdf | (i) A line of credit does not provide adequate leverage to require changes in commercial bank operations or procurement procedures. (ii) A more thorough examination of procurement procedures during project preparation might have prevented the delays encountered after project approval.
P035160 | HARYANA POWER APL-I | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/206051474555025454/text/000020051-20140604042800.txt | http://documents.worldbank.org/curated/en/206051474555025454/pdf/000020051-20140604042800.pdf | Political support for the reform, ownership, and reform "champions" are indispensable elements to start and sustain a reform process, and no practical purpose is served by taking "shortcuts";The APL proved to be a powerful lending instrument for dealing with a complex reform program with a long gestation period, within a highly sensitive and volatile environment. It is also an excellent instrument allowing adjustment as a result of lessons learned during the project in similar projects elsewhere;Both the client and the Bank should make a clear distinction between the means used to manage the reform process and the legal agreements and covenants upon which formal assessment of progress and outcome achievement would be made during supervision, especially for complex policy matters such as privatization of distribution;Country-based supervision was intensive and cost-effective (20 missions in 2 years) and enabled development of a productive partnership with the Bank's clients and development partners;Use of best international practice and consultants was key to the acceptability of the technical and institutional reforms;Distribution works are better performed on a "supply and erect" basis rather than procuring goods and having them erected through labor contractors;The format of the ICR for APLs could be revised to reflect the programmatic aspect of the APL, and by treating it as part of the documentation necessary for processing a subsequent operation.
P035163 | ENERGY EFFIC/HOUSING | Europe and Central Asia | Lithuania |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/811371474635145086/text/000020051-20140607143707.txt | http://documents.worldbank.org/curated/en/811371474635145086/pdf/000020051-20140607143707.pdf | Pilot projects are based on a limited amount of knowledge and experience -- they are an opportunity to confirm the efficacy of mechanisms, institutions and project assumptions. The strength of the monitoring and evaluation process is central to pilots' success or failure.Visible project success attracts participants-- and the higher the number of successful cases, the greater the willingness to contribute financially towards home improvements. At the outset, in the absence of financial incentives, i.e. tax benefits and grant elements, public outreach alone will be very slow to convince/motivate homeowners. This may change when project sponsored activities gain in acceptance and credibility.However well prepared they are, projects whose main purpose is to change people's behavior through new experiences will be slow to begin, and slow to disburse.Homeowners Associations are far more willing to take on debt to renovate common property if they are provided with institutional and technical support and financial incentives.Lack of alienable collateral is an important obstacle to private sector lending.
P035169 | UTTAR PRADESH FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1998 | 2004 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/368411474509385378/text/000020051-20140612103105.txt | http://documents.worldbank.org/curated/en/368411474509385378/pdf/000020051-20140612103105.pdf | Programs involving complex institutional change need assured long-term support;Effective communication is critical to ensure the success of community-led processes; andEvery attempt should be made to avoid creating parallel institutions at the local level.
P035170 | Orissa Power Sector Restructuring Project | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Moderately Unsatisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/879891474899177903/text/000020051-20140613035821.txt | http://documents.worldbank.org/curated/en/879891474899177903/pdf/000020051-20140613035821.pdf | Tariff reform needs to incorporate a mechanism for gradually transitioning from a situation of substantial subsidies to one of full cost recovery to achieve financial sustainability.It must be recognized that Government's continued political support will be necessary to withstand forces of resistance to the operation of an effective regulatory agency (one that will increase tariffs when necessary). The Bank should take strong action if the Government undermines regulatory institution by, for example, not appointing new commissioners as needed).Private investors will continue to support sector unbundling only if they believe that their investment of personnel and financial resources will generate a reasonable return. Policy decisions that eliminate the prospect of profitability will drive them from participating in the sector.Financial covenants for dedicated investments in power generation and evacuation transmission lines should include cross-indemnification against the risk of the other investment not being completed in a timely fashion.
P035172 | UTTAR PRADESH POWER SECTOR RESTRUCTURING PROJECT | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/404891475090764732/text/000020051-20140613051627.txt | http://documents.worldbank.org/curated/en/404891475090764732/pdf/000020051-20140613051627.pdf | Energy sector reform should always have the return of the sector to financial viability as a clearly defined primary objective. Most of the other objectives are means to reaching this primary objective. There is an inherent conflict between the objectives of sector reform, which are difficult and often contentious, and subject to the ebbs and flows of the commitment of changing governments, and the objectives of physical investment lending, which are straightforward and short term. The reform agenda often passes through periods of low popularity, but in the end is critical for the successful long term stability of the sector. This is an ongoing conflict, which the Bank must accept as it continues its efforts to encourage and support improved energy sector performance.
P035173 | Second Powergrid System Development Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/913811475094304479/text/000020051-20140617134618.txt | http://documents.worldbank.org/curated/en/913811475094304479/pdf/000020051-20140617134618.pdf | The main lessons which may be drawn from this successful operation are:1. The importance of a committed and technically proficient implementing agency (also the Borrower in this case) is clear from the experience of this project. 2. POWERGRIDâ€™s satisfactory financial and technical performance, as well as its environmental and social safeguards systems, resulted from ongoing practices which had been supported by previous Bank projects. This shows the value of a continual, long term relationship between Bank and implementing agency.3. The benefits of a strong Bank team during both preparation and supervision are evident.4. The presence of the TTL and other team members in the India country office undoubtedly contributed to the excellent working relationship with POWERGRID and to the satisfactory supervision of the project.5. For large utilities such as POWERGRID, with substantial investment needs, the time slice lending approach is appropriate, provided other preconditions â€“ such as technical and financial proficiency and familiarity with Bank practices -- are in place (as in this case).
P035312 | TT- BASIC EDUCATION | Latin America and Caribbean | Trinidad and Tobago | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/876251474502690861/text/000020051-20140612100653.txt | http://documents.worldbank.org/curated/en/876251474502690861/pdf/000020051-20140612100653.pdf | Project scope should be tailored closely to the implementation capacity of a country. Overly complex and ambitious projects, particularly in small countries, strain the capacity of the relatively few implementers available and may cause delays and cancellations of components.- Effective poverty targeting is not easy. The communities most in need may lack the means to participate or may have difficulty finding available land for civil works. Projects focused on poverty alleviation must foresee the obstacles and take measures early on to address them.- When funds are transferred to schools, a simple but effective accounts monitoring system is necessary. The implementation capacity at the local level must be strengthened to allow for close supervision of expenditures.
P035494 | DO- BASIC EDUCATION | Latin America and Caribbean | Dominican Republic | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/965531475091486705/text/000020051-20140612100603.txt | http://documents.worldbank.org/curated/en/965531475091486705/pdf/000020051-20140612100603.pdf | In-service teacher training programs do not necessarily improve teachers' classroom behaviors or improve student achievement. Offering monetary rewards for diplomas may encourage teacher participation in training, but training impact is unclear. There is a need to clearly define skills for which scholarships and improved salaries should be awarded. - Simply encouraging parents and community leaders to get involved in school management is not sufficient. To get involved effectively, parents require training, empowerment (authorization) and some control over financial resources to get engaged. - School nutrition programs are an important incentive for student attendance and retention at school as well as of nutrition for poor children. - Co-financed projects require careful project design and attention to the distribution of financing by components, sub-components and categories of investment. It is important that cofinanciers harmonize procurement procedures among them and with governments.
P035495 | SOCIAL PROTECTION | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1996 | 1999 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/573511474596238315/text/000020051-20140528123711.txt | http://documents.worldbank.org/curated/en/573511474596238315/pdf/000020051-20140528123711.pdf | An important lesson is that, during project preparation, the Bank should focus on institutional interrelationships in order to avoid potential overlaps in mandates and responsibilities.
P035544 | Solar Home Systems | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/329001475070259958/text/Indonesia-Solar-Home-Systems.txt | http://documents.worldbank.org/curated/en/329001475070259958/pdf/Indonesia-Solar-Home-Systems.pdf | (1) The competitiveness of SHS units may depend on the level of Government intervention in the rural energy market to promote access to some energy sources. In this case, nominal retail prices of SHS units rose by about 400% over about two years as a result of currency depreciation but continuing subsidies for kerosene and diesel softened their price hikes to only 12% and 58%, respectively. This significantly lowered the competitiveness of SHS.(2) To develop a new SHS market and encourage the participation of new dealers, significant upstream support for market development and business planning is needed, in part to reduce perceived commercial risks. This support must also be extended to participating financial organizations who also face high information and other market entry costs.(3) Market-based projects need to be flexible enough to allow for the adjustment of product lines and business models in response to changing market signals.
P035590 | ECONOMIC RECOVERY CR | Western and Central Africa | Mali | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1994 | 1995 | 2008 | PPAR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/445971468283183450/text/40070.txt | http://documents.worldbank.org/curated/en/445971468283183450/pdf/40070.pdf | 7. Lessons for the Future 7.1 The main lessons learned from t h s review are\. Country ownership matters very much. The components o fthe loans that were owned bythe country, such as the public resource management and some o f the structural adjustment components were generally successfully implemented. By contrast, the components for which country commitment was not as strong, such as civil service reform, gender development, and fundamental cotton sector reform; didnot fare very well. As a generalrule, it would be very useful for the Bank to listenbetter and to go to extra lengths to explain its positions, and to solicit views and seek genuine agreement with country authorities. This could improve country ownership of programs. According to keyofficials inMali, the Bankhas become a better listener duringthe last few years, and the Resident Mission has played an importantrole inthis regard. This i s a good development which shouldbe sustained andbuilt upon. It is importantto keep a good andsubstantive dialogue with the main development partners; again by listeningbetter to their view points, keepingthem better informedabout those o fthe Bank, and seeking to reach agreements when possible. Ths would increase the effectiveness o f the support being givento a country by development partners as a group as well as individually. As hashappened already with SAC N,itwouldbepreferable to keep the design o f adjustment operations simple and focused on a limitednumber o fkey policy areas, whose implementationcanberealistically expectedwithin the short disbursement period dictated by an adjustment operation. A well-designed monitoring and evaluation system (M&E) could further help facilitate implementationand avoid stalemate situations.
P035592 | ECONOMIC RECOVERY CR | Western and Central Africa | Senegal | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1994 | 1996 | 2000 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/397901511188972455/text/multi-page.txt | http://documents.worldbank.org/curated/en/397901511188972455/pdf/multi-page.pdf | 6. KEY LESSONS LEARNED\n6.1 Lessons from the ERC are\.\n* A single-tranche operation can be highly effective in improving the policy regime while\nholding down inflation after a large devaluation; and\n* Goals and targets beyond the first tranche conditions should be very limited in number\nand chosen with caution, especially in view of the difficulties of projecting the revenue\nsituation.0\n6.2 Lessons from the PSAC are\.\n* Bringing together the private business sector, labor and Government in commissions to\ndesign the different aspects of this many-sided project contributed greatly to the quality\nof the project and to the country's sense of ownership of the many measures taken. The\nWorld Bank provided discreet guidance favoring the needs of the private business\ncommunity.\n* The two tranche design, with most of the conditionality up front, was very effective. The\ninitial conditions were well chosen, and further effective results came from negotiations\nof second tranche conditions.\n* Shared objectives and views of the Government and the World Bank helped to make this\nproject (and the ERC) successful.\nAs suggested in the ICR, the so-called safety net funding of CFAF 15 billion could ideally have been\nbetter aimed at the poorest regions and classes, but the general effect was nonetheless healthy in helping to\nhold down inflation and ensure nation-wide supplies of rice, bread and medicines.
P035593 | ECONOMIC RECOVERY CR | Western and Central Africa | Burkina Faso | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1994 | 1995 | 2000 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/668541511187370299/text/multi-page.txt | http://documents.worldbank.org/curated/en/668541511187370299/pdf/multi-page.pdf | 7. LESSONS 7.1 Underestimated Constraints. Perhaps the most important lesson to be learnt from the Bank's experience with structural adjustment in Burkina is that, notwithstanding meticulous project design, ample technical assistance, and apparently firm government and public support, it can nonetheless remain a very slow and difficult process if the government's implementing capacity is weak, there is lingering political opposition to important elements of the program, and the Government does not fully subscribe to the program's underlying economic rationale. Where, as a result, implementation of important components is slow and difficult, the internal coherence of an adjustment program can easily be lost and the anticipated beneficial results seriously delayed. This courts the risk of adverse political reactions and government backsliding. 7.2 Need for More Realism and Longer-Term, Consistent Commitment. The Bank needs to be considerably more realistic, not only about the time required to implement the components of an adjustment program, but also about the time required for it to realize tangible results. It needs a clearer understanding at the outset of the institutional capacity, social and political constraints. Identification of these constraints should be an integral feature of project preparation. Bank experience with structural adjustment in many countries is that it typically requires as much as a decade or more to complete successfully. On the Bank side, this calls for staff continuity, persistence and the institutional retention of a great deal of detailed knowledge if the government involved is to be adequately supported. Frequent Bank reorganizations and staff rotations are highly disruptive. 7.3 Questionable Efficacy of Fast-Disbursing Loans. Fast-disbursing loans with early tranche release dates have shown themselves to be somewhat ill-suited to providing support for structural adjustment. Such a process requires long-term monitoring and supervision. The Bank should monitor closely the effectiveness of alternatives, such as floating tranche loans, or series of smaller loans addressing successive adjustment priorities in the context of an agreed long-term adjustment strategy. Other vehicles should be considered as the basis for rapidly disbursing loans intended to meet emergency country financing requirements. 7.4 Other Lessons. Burkina's experience again confirms that resort to internal wage and price compression as the means to redress external economic imbalance is typically incompatible with rapid economic recovery and can be very costly in economic and social terms. For the CFAF zone, a nominal depreciation was clearly needed. Public finance and other reforms in Burkina, as elsewhere, could have been carried out more rapidly and successfully if the nominal depreciation of the CFA franc that finally took place in January 1994 had been carried out much earlier. The inflexible link between the CFAF and the French franc/Euro needs to be reexamined in order to ascertain whether it is in the CFA zone's best interests. Finally, the Bank's experience in Burkina suggests that elaborate technical assistance programs with numerous components are difficult both to implement and to supervise. Smaller projects focused on the key priorities seem likely to be more successful.
P035595 | TRANSPORT SECTOR TA | Western and Central Africa | Gabon | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1995 | 2000 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/943631475099278873/text/000020051-20140529160537.txt | http://documents.worldbank.org/curated/en/943631475099278873/pdf/000020051-20140529160537.pdf | The ICR identifies the following lessons with broad applicability: It is more effective to develop overall sector strategies and investment plans by first carrying out a limited number of specialized and focused analyses of sub-sector issues. A participatory approach to prepare sector strategies requires much time and resources. Policy reform should be accompanied by investment packages to leverage Bank's assistance to effect policy reforms.
P035599 | TRNSPT SECTOR T. A. | Western and Central Africa | Cameroon | Blend |  | Infrastructure | Transport | IDA | IPF | 1995 | 1999 | 2000 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/320241474635963501/text/000020051-20140528125150.txt | http://documents.worldbank.org/curated/en/320241474635963501/pdf/000020051-20140528125150.pdf | The following lessons with broad applicability emerge from the project: The budgetary and social impact of privatization, including severance payments, should be addressed during project preparation.Involvement of senior management (from the Bank and the government) in the process of reform implementation is crucial.Continuity in Bank support strategy through successive projects is essential for supporting the different phases of reforms and for consolidating those achieved under the project.
P035601 | POPULATION & AIDS CONTROL | Western and Central Africa | Chad | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/421141474555167012/text/000020051-20140607152628.txt | http://documents.worldbank.org/curated/en/421141474555167012/pdf/000020051-20140607152628.pdf | The ICR lists several lessons, many of which are common to similar projects:Monitoring and evaluation arrangements need to be put in place early in the project and continually assessed by Bank and borrower.Achieving social change in a traditional society, particularly in matters related to sexuality and reproduction, is a long-term process, but a multi-faceted strategy incorporating IEC, social marketing, stakeholder workshops, and community-based activities may help increase awareness eventually contribute to behavior change.The extent of borrower commitment to policy goals (family planning or HIV/AIDS) need to be clearly assessed, and a strategy of policy dialogue, research, and stakeholder consultation put in place to help strengthen commitment. Appointing high-level political officials to chair multi-sectoral commissions (e.g., for population) does not guarantee political support, and may make it more difficult to implement activities.The first population project in this extremely poor, sparsely populated, post-war country with low health indicators and high fertility should have focused first on gaining acceptance of family planning to promote birth spacing and improved maternal and child health, rather than on promoting smaller families and slower population growth.
P035601 | POPULATION & AIDS CONTROL | Western and Central Africa | Chad | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2002 | 2005 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/544801468770125526/text/31746.txt | http://documents.worldbank.org/curated/en/544801468770125526/pdf/31746.pdf | 6. Findings andLessons 6.1 TheBank can be instrumental in stimulating government commitment with regard topopulation and HIV/AIDS throughpolicy dialogue, advocacy, technical support and lending, but such support is insufficient to consolidateand sustain that commitment. Throughpolicy dialogue andtechnical assistanceprovidedinthe context o f project preparation, the Bank supported the development and approvalby Government o f policy and strategic documents for addressing population issues and for fighting HIV/AIDS. Government's agreement to borrow for HIV/AIDS was inconsiderable part attributable to the Bank's persistence inhighlightingthe risks andconsequences o fnot addressing HIV/AIDS duringthe preparation o f the healthoperation in 1994. The Bank's persistence and candor helpedopen a national discussion on HIV/AIDS. 6.2 Otherfactors that are critical to raising and sustaining Government commitment are (i) the relevance of the objective, determined inpart by the availability of local evidenceand data; and (ii) the degreeof mobilization of civil society. The support o f HIVlAIDS research, data collection and analysis, studies andthe strengthening o f a sentinel surveillance system have providedconcrete, country-specific (and regionspecific) information to sensitize officials onthe progression o f the epidemic, and its socioeconomic consequences. Over and above these data, the fight against HIV/AIDS becamemore relevant (especially inthe south) as the epidemic progressed andmore people observed first-hand andwere affected bythe disease and its consequence^.^' The objectives o f the second medium-term plan(to prevent fwther infection, to care for those infectedandto mitigate the social and economic impact o f the disease), thus have immediate andgrowing relevance. As civil society mobilized itselfto undertake its own action, as new local associations o f vulnerable and affected groups were formed, and as public-private partnerships were formalized, civil society advocacy has raisedpressure for public sector engagement and accountability (associations o fPLWHA at the local level, andnationalNGOs o fwomen ministers andparliamentarians are two cases in point). 6.3 Datawas also generated on populationsize, growth and dynamics inChad and projections were available as early as 1994, assessingthe consequences o frapid population growth on the socio-economic development prospects o fthe country. While 67. Informantsat the local levelfrequently referredto the infectionor death of a family memberor close friend. there was general consensusinChad about the desirability o f implementingthe populationpolicy components aimed at improving the rights, opportunities, services and well-being of mothers and children, the notion o f limitingfamily size was met with some reticence. Highinfant andchild mortality andpoverty have propelledcouples to have more children for social security intheir old age and for supplemental householdincome andlabor. As opposed to HIV/AIDS, the relevance andimmediacyo fobjectives to reduce the rate o fpopulation growth were not nearly as apparent. Eventhe use o fmodern contraception for child spacing -which can lower child mortality and improvematernal andchildhealth-- has not beenfully embraced.As a consequence, civil society advocacy around the objective o fincreasing the modem contraception rate has not happened. 6.4 Successful achievementofpopulation and HIEAIDS objectivesrequires the conviction and commitment of public sector and nongovernmental leaders and decision-makers in all layers of Chadian administration and society. Thestimulation and nurturing of national commitmentrequires continuous and multiple efforts, given population mobility and turnover in leadershipandpublic sectorpositions. 6.5 Capacity building of public sector institutions will not be successful if efforts are not aligned with the official mandates of these institutions. The institutional framework for the fight against HIV/AIDS had already beenestablished at the project's outset. By government m6te6*the PNLS was giventhe responsibilityfor the coordination andmanagement o fHIV/AIDS/STD activities inthe country, including the provisiono f technical oversight and support to nationalpartnersintheir fight against HIV/AIDS/STDs, and for epidemiologicalsurveillance andother relevant data collection and analysis. However, becausethe PNLSineffect was so weak, andbecausethe other components o fthe institutional framework for HIVIAIDS were not considered to be sufficiently ftlll~tional,~~ the project was set up to give the PCTMoPC the defacto responsibility for inter-sectoral coordination. 6.6 Because PNLS's mandate was never changed, there was confksion and frustration about its role. Tracking and coordinationo ffinancial and technical assistanceto the fight against HIV/AIDS, as well as strategic programcoordination andoversight, have not been effectively carried out to date.70An institutionalaudit has recentlybeen carried out that has launched a reflection within Government andbetweenGovernment and its partners about a realignment o fresponsibilities inline with comparative advantages, on which basis adequate staffing and capacity buildingcan be envisioned. 68. Arr6te No. 5771MSPIDGl98of April 28, 1998, modifyingarr6te No. 59IMSPASISE/DG/PNLS/91of May 13, 1991, modifyingArrete No. 31IMSPISEIDG/O131DAFM/DIW88. 69. The NationalCommittee for the fight against HIVIAIDS,created in 1988 by governmentdecree No. 035lPWPSPl88of March 19, 1988, and the TechnicalCommissionfor the FightAgainst HIVIAIDS, created by governmentarrete No. 012lPMT195 of February 12, 1995. 70. As a consequence, this evaluationwas unableto provide an overviewof the nature,levelsand impacts of other partners'contributionsto HlVlAlDScontroleffortsduring the life of this project. 6.7 Bythe sametoken, aninstitutionalframework for the coordinationand implementation o fpopulationpolicy hadbeen established before the project, but an institutional assessmentwas not undertaken to inform the design o f the project's capacity buildingefforts. Effortsto amendthis framework duringimplementationwere unsuccessful. 6.8 The channeling of funds to inter-sectoral committeesresponsiblefor population and HIV/AIDS at the regional level stimulated decentralized, multi-sectoral action. However, the absenceof full-time staff at the regional level to undertakeHIV/AIDS program management and coordination has undermined the effectiveness and efficiency of regional level operations. 6.9 Financing and technical support alone will not optimize the individual and collectiveefforts of the various sectors. Theproject stimulated and supported the preparation andimplementationo fHIV/AIDSproposals from seven sector Ministries, andelicited Government Co-financingo f20 percent o fthe costs o fthese activities. The stimulus was the availability o f supplemental funds (both those providedby the project andthose providedthroughbudget supplements). A number o fministries didnot (fully) include intheir proposals key activities for which they have the comparative advantage. For example, the Ministry o fJustice supported targeted activities for prisoners, but has an important role to play indefining and defendinga legal framework for the fight against HIV/AIDS, includingthe protectionofrights ofpeople livingwith HIV/AIDS. Another example cited i s the potentialrole o fMinistryo f Social Affairs and Family to expand its role beyond the care o f orphans to encompass ways andmeans o freducing vulnerabilities. A definition o froles, comparative advantages and target groups might have elicited the most critical responsesfrom respective sector ministries for higher impact results, more fully responsive to national objectives. Currently there is little rigor inthe specification andmonitoringofaccountabilities for results. Forthe mostpart HIV/AIDS activities are designedand implementedbyHIV/AIDS focal persons or designated units, with little involvement o f the rest o fthe Ministry; andinter-sectoral coordinationhas not fully exploitedpotentialsynergies across sectoral responses. 6.10 Absence of a strategy on communicationsfor behavior change and the lack of clarity of roles and responsibilities across the multiple institutions that carry out IEC, have undermined the quality and effectiveness of public sector and nongovernmental action. Virtually all sector ministries andnon-publicpartners design their ownprevention messages and campaigns. There i s no one entity responsible for coordinationand oversight. Ministryo f Communicationhas a full-time personresponsible for HIV/ALDS activities (training o fjoumalists and radio andtelevisionmedia campaigns), the IEC unit within PNLShas developed some IECmaterial and carries out an ongoingHIV/AIDS campaign carried out by and for youth, but does not have the capacity for oversight and coordinationo f all communications efforts for prevention. Some sector ministries have an IEC unit. The Population IEC unit, responsible for coordinating and overseeing all population-related IEC has remarked that they have great difficulty inmobilizing various IEC experts from different ministries for discussion andcoordination because they are not sufficiently elevated inthe public sector hierarchy or have sufficient authority to oversee IEC activities inother ministries. The project missed an opportunity to clarify roles and responsibilities and strengthen coordinationcapacity inthis regard. 6.11 Even in the context of a multi-sectoral approach to the achievement of HIV/AIDS andpopulation objectives,the role of the health sector ispivotal. The health sector's ability to carry out its potential role effectively was undermined. First, its mandate is not fully or clearly defined inthe healthpolicy document, nor are accountabilities o frelevant departments and divisions o f MoPH specified; Second, the healthsector response i s limitedbyvery weak health sector capacpity Project support has made headway instrengthening epidemiologicalsurveillance, but this capacity must bemainstreamed into the MoH, beyondthe PNLS. However, the health sector i s very behindintakingon other core activities that are public goods. Technical experts interviewedhave estimated that the blood supply is still unsafe. Training, guidelines andprotocols andthe provisiono f drugs have started to buildcapacity o f health services to diagnose andtreat STIs and opportunistic infections, but the quality and coverage and reliability o f these services are lacking. Testing capacity i s far below what i s needed, especially now that the Government i s subsidizing ARVs, which will stimulate increased demand for tests. Preventiono f transmission within healthfacilities i s inadequate. Itwas mentionednumerous times duringfield visits and exchanges with actors at the national level that health sectorpersonnel are amongthe least mobilized o f all civil servants working on HIV/AIDS andthat more effort is neededto informand involve them inthe fight and to relieve them o f the fear and stigma with which they tend to be associated. 6.12 The absence of baseline datafor many of the key indicators and of a monitoring and evaluationplan has undermined opportunities to track theperformance and impact of nationalpopulation and HIUAIDS efforts and to refine approaches and increase effectiveness in light of experience. Informationon trends i s limitedthus far to HIV among pregnant women, which isnotparticularlyuseful for gaugingtrends innew infections. Some trends on knowledge, awareness andbehavior canbe derived from the DHS(1996/97),the UNICEFmultipleindicatorsurvey (2000) andthe2003 KAP, but questions andindicators vary across surveys makingthem non-comparable. Furthermore, data collection activities were not designed to measure many o fthe indicators identified at project appraisal. Informants have pointedout the absence o f denominators o fkey target groups such as number o f orphans, schools, etc. and ofcurrent coverage o fthese groups (numerators) that make it impossibleto set viable targets for coverage o f services. Implementationo fthe civil society projects has been evaluated and auditedby the Social Fund, butprogram effectiveness would benefit from results-focused evaluations. The hctional relationship between the M&Eunit o fPPLS andthe PNLS/MoH i s weak. 71. The 2000 health policy makes referenceto the PNLS as the responsibledepartmentfor HlVlAlDS activities, makingno referenceto any responsibilitiesof other departments.It also highlightsthe importance of multisectoralcollaborationwithout clearly distinguishingMoPH's role and comparativeadvantages. 72. Overallweaknesses in healthsystem capacity, include\. humanandfinancialresourcesconstraints,low service quality and utilization rates (seeAnnex D),sporadicavailabilityof drugs and supplies, and many competing priorities. 34 6.13 TheBank can be effective in influencing theBorrower to supportpublic goods and high-impact interventions. Withinthe overall context o fpopulationpolicy andthe second medium-termplanfor HIV/AIDS, the Bank supported the productiono fpublic goods, interms o f collection andmaintenance o fbasic epidemiological, behavioraland populationdata, that most likely would not have enjoyed such highpriority inthe absence o f Bank assistance. 6.14 The inclusiono f a well-designed component on social marketingo f condoms channeled resources to a potentiallyhigh-impact intervention. The social fund supplemented the borrower's implementationcapacity with that o f civil society and established partnerships with civil society and across development sectors. Within those partnerships the Bank encouraged the targetingo fhigh-risk groups, and (as experience was gained) the definitiono fmandates o fpublic and civil society actors inline with in line with their comparative advantages. The Bank's support o f intermediaryNGOs for capacity buildingo f local associations was also a good strategic choice. As ARVs became more affordable and Parliament passeda billto subsidize their costs, the Bank continuedstrong advocacy for maintaining a priority on prevention. The Bank was less successful inencouraging targeted behavior change interventions, as opposed to IEC. 6.15 The strategy o f intensive IEC inthe early years o f the project to inform civil society about the social fund, followed bythe recruitment o fintermediary NGOs to build capacity insubproject proposal writing and implementation andto stimulate the formation o f additional relevant local associations, provedto be very effective in gradually engaging civil society inpopulationand HIVlAIDS while providingthem with needed support and guidance. This experience also points to the need for improved coordination andmonitoringand evaluation o fNGOactivity. 6.16 Government financing o f NGOssupported not only a complement to publicsector activities, but also strengthenedadvocacy role o f civil society. The creation o f associations o fPLWHA andprostitutes give legitimacy to these groups and contribute for humanrightsandequity advocacy. The support of associations ofParliamentarians, highlevel civil servants, the business sector andretiredtechnicians has created an important force indemandingthe involvement and accountability o fpublic officials inaddressing HIV/AIDS. 6.17 A second Population andAIDSproject continuesBank support to Chad's population policy and HIV/AIDS strategicplan. Its development objective i s to contributeto the behavior change o f different populations inan effort to reduce the risks o fHlV infection, closely spacedbirths, andunwantedpregnancie~.'~ 73. Credit No. 3548 was approved on July 12,2001, and became effective on April 11,2002. 74. To this end it supports\. (i) scaling up multi-sectoraland decentralizedactivitiescarried out by publicand privatesector agenciesand civil society; (ii) targeted behaviorchange interventions;(iii) an increasein voluntarytesting and counseling\.(iv) reductionin vulnerabilityfactors through incomegeneration,women's education,and care of those infectedand affectedby the epidemic\.and (v) an increase in the availabilityof condomsand contraceptivesto enable adoption of healthy behaviors.Support is channeledthroughfour components\. (a) strengtheningof the capacitiesof the key ministries; (b) strengtheningof grants and micro- 6.18 Inaddition, the HealthSector Support Project75supports the strengthening o fbasic health services, includingreproductive health, and includes an HN/AIDS component to support epidemiological surveillance andhealthcare practices for limiting the risks o fHIV transmission (enhanced blood safety, improved STItreatment and control, andreduction o f risks o f clinical infection). 6.19 The Government is currently financing ARV treatment for about 80 AIDS patients and the Global Fundwill support expansion o f this program. Additional patients are accessing ARV through a Government subsidyprogram.76While HSSP does not finance the purchase o f ARV drugs, it haspositioneditselfto support needed strengthening o ftreatment and referral services. The second Population and AIDS Project i s financing a consultant to help MoPHdevelop a global care and treatment framework, a management system for ARVs, and a national reference guide. 6.20 Current Bank support to populationandHIV/AIDS remains strong andreflects manylessons learned duringthe implementationofthe first operation, corroborated by other relevant OED reports, 77notably\. (a) continuedemphasis on prevention; (b) the development o f a communications strategy for behavior change and definition o froles andresponsibilities for its coordination, management andimplementation; (c) continued efforts to address vulnerabilities, buildingon the experience and outcome o fmicrofinance for women and expanding to other vulnerable groups (such as prisoners); (d) review and revision o fthe institutionalframeworks for population andHN/AIDS for greater efficiency; (e) intensified support to MoPH capacity; and (f) improvementsto program monitoring and evaluation. 6.2 1 The importance o f sound andrigorousmonitoringandevaluationcannot be overemphasized. With the ongoing Bank support a project monitoring and evaluation planwas developed andagreedthat defines 24 indicators and specifies data collection methodologies and responsibilities. Impact indicators focus on behaviors, HN prevalence, and measures o f STDs among keypopulations. A second DHS i s planned, along with the first nationalHNsero-prevalence survey and a beneficiary assessment. A full-time M&Eexpert has been recruitedinto the %, However, there i s scope for intensifying efforts on a number o f fronts, notably\. establishment o fbaseline data for all program indicators; greater consistency inthe type and frequency o fdata collection to enable the tracking o f trends over time; and inclusion o fmeasures o f incidenceto track rates o fnew infections among the general populations and among high-risk groups. credits underthe social fund; (c) supportto the social marketingprogram; and (d) populationpolicy implementation. 75. Credit No. 3342 was approved on April 27,2000, and became effectiveon February28,2001. 76. The monthly costof ARV is 20,000 CFAfrancs, or about US$40 (price at which the Central Procurement Agency buys the drugs)\. underthe Government's ARV subsidy program,Parliamentvoted a budgetwhich finances 15,000 CFA francs of the monthly costsof ARV and the patientco-paysthe balanceof 5,000 CFA francs. 77. NongovernmentalOrganizationsinWorld Bank-SupportedProjects, 1999\.Social Funds\.Assessing Effectiveness,2002; and OED Reviewof Bank Lendingfor Linesof Credit, 2004.
P035603 | AGRIC SECTORAL ADJUS | Western and Central Africa | Cote d'Ivoire | IDA |  | Sustainable Development | Agriculture and Food | IDA | DPF | 1996 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/229141475070798421/text/Cote-d-Ivoire-Agricultural-Sector-Adjustment-Credit.txt | http://documents.worldbank.org/curated/en/229141475070798421/pdf/Cote-d-Ivoire-Agricultural-Sector-Adjustment-Credit.pdf | (1) A conducive macroeconomic environment is important for the success of sector policy reform projects. In this case, the devaluation of the CFA franc, and an ongoing macroeconomic policy that has maintained the competitiveness gains arising from the devaluation, was been a key ingredient in the success of the project, particularly in comparison with the previous Agricultural Sector Adjustment Loan.(2) It is important for the implementing agency -- in this case the Steering Committee -- to have sufficient responsibility and authority to manage policy reforms on a day-to-day basis, and to develop and maintain a consensus for the reforms among the key local stakeholders. However, the Committee should have made greater efforts to disseminate information about the reforms beyond the membership of the committee, since vested interests opposed to the reforms, both internal and external, delayed the reforms on a number of occasions.(3) Bank supervision from the field and staff continuity on both sides contributed positively to the relatively smooth implementation of the project.(4) Appropriate Bank flexibility during project supervision can help project success. In this case, the Bank demonstrated appropriate flexibility in agreeing to waivers for the release of both the second and third tranches, which paid off on both occasions. Timely Bank disbursements were crucial for meeting a tight debt repayment schedule and the government met the initial conditions not long after tranche release in both cases.(5) During the privatization process, both the Bank and the borrower need to do more and better analytic work to balance the state's fiscal interests against those of producers and consumers. In this case, the government appeared to be too favorable to the interests of the buyers of the privatized companies.
P035605 | SAC I | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1997 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/964851474566584022/text/000020051-20140528123323.txt | http://documents.worldbank.org/curated/en/964851474566584022/pdf/000020051-20140528123323.pdf | In order to guide implementation, an effective privatization program requires specific goals clearly outlining the anticipated status of individual enterprisesEarlier analytical work performed on the cotton sector would have benefited the proposed reform processThe design of the overall reform program, consisting of a series of single-tranche operations with disbursement against conditions met prior to effectiveness, was innovative and effectiveGovernment commitment was key to reform progressThe economic unit in charge of reform was located in the Presidency during implementation, which gave it the high visibility needed to effectuate reforms
P035608 | NE TRANSP. INFRA. REHAB | Western and Central Africa | Niger | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/131761475089168218/text/000020051-20140612103337.txt | http://documents.worldbank.org/curated/en/131761475089168218/pdf/000020051-20140612103337.pdf | When major exogenous events occur (such as a coup d'etat) it is often appropriate to review the implications for successful completion of the project.The project design should be in balance with the resources and capacity available to the Borrower.
P035615 | COMMUNITY NUTRITION I | Western and Central Africa | Senegal | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/567191474555140726/text/000020051-20140604052237.txt | http://documents.worldbank.org/curated/en/567191474555140726/pdf/000020051-20140604052237.pdf | The project confirms a number of long-standing lessons, including the importance of adequate project preparation, and the positive impact of community participation for the effectiveness and sustainability of local nutrition and water programs.Private entities and contracting arrangements can be an effective means to implement local poverty programs, but explicit coordination with line ministries should be established to ensure policy coherence and linkages among local programs. In particular, management of severely malnourished children requires coordination between communities and local health facilities, and readiness by facilities to take on these children.Despite the apparent success of the contracting approach, more information is needed on the relative cost effectiveness and sustainability of the contracting approach compared to alternatives (e.g., use of NGOs).The project provides both positive and cautionary lessons regarding monitoring and evaluation. An initial pilot was evaluated, and findings fed into developing the operations manual. AGETIP and nutrition committees regularly monitored data regarding clients served and success rates, taking corrective action when necessary. But despite significant M&E activities, they were insufficient to answer key questions regarding the relative impact and efficiency of alternative approaches. Key evaluative questions thus should be explicitly reflected in project design and M&E arrangements.
P035617 | Mali:GRASSROOTS HUN/POVT | Western and Central Africa | Mali | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/231431474569735248/text/000020051-20140612145154.txt | http://documents.worldbank.org/curated/en/231431474569735248/pdf/000020051-20140612145154.pdf | 1. Pilot projects need to include solid monitoring and evaluation including both quantitative and qualitative measurement if they are to effectively inform future operations.2. Project objectives and component design should be carefully thought through and clearly specified to prevent confusion during implementation.
P035617 | Mali:GRASSROOTS HUN/POVT | Western and Central Africa | Mali | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2004 | 2018 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/749441519826286063/text/123411-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/749441519826286063/pdf/123411-PPAR-PUBLIC.pdf | 6. Lessons 6.1 Projects that seek to improve living conditions need to define, benchmark, and measure a project's attributable contribution to changes in human welfare. Measuring access to assets is an insufficient metric. One tool that could be utilized by World Bank rural development projects is the Aga Khan Foundation's Quality of Life Assessment, which has been rolled out and used in their rural development programs. 6.2 Private productive investments should not be relied on to finance the operations and maintenance of core public services provided by World Bankâ€“financed projects whenever local revenue recovery is not feasible. The returns on investment for micro and small enterprise development are not likely to contribute to significant autonomy of public finance in rural areas in the short to medium term without major advances in productivity, market connectivity, and consumer demand. Project objectives should focus on the marginal but important household income and revenue benefits that can accrue, while acknowledging that financially sustainable public infrastructure requires a more conducive policy environment at higher levels (region and central government). 6.3 A pilot project should be designed to generate lessons\. its M&E System should therefore double as a learning lab to test and adapt interventions within the country and sector context. PAIB was a pilot project, but its M&E system was limited mainly to output indicators. There were no tests or efforts to adapt the project based on learning along the way, and no parallel or special studies conducted to learn why these innovations worked or didn't work, with the aim of scaling what worked in a second phase. 16 On the agenda since 1977, decentralization in Mali gained new momentum with democratization in the 1990s. Decentralization provided a platform for the new civilian regime to redefine the nature of the state after decades of military rule and dictatorship. Its purpose was also to bolster state legitimacy in the north after the Tuareg Rebellion of 1990. Building on traditions that go back to the Malian Empire, decentralization was framed as a political solution to the state's security and development challenges (Baudais 2006; Whitfield 2009). With a reported 170,000 beneficiaries in 185 villages, the average project village had a population of about 920. This village would be larger than average; most villages in Mali have between 150 and 600 residents. Visit http\.//www.akdn.org/news/akdn-quality-life-assessment-programme-brochure to download the Aga Khan Development Network's Quality of Life Assessment brochure. This differs from the number reported in the external assessment, which include an additional 39 latrines ADC that appear to have been built for the community agents that resided in villages in support of PAIB. Estimated at CFAF 37.5 million, U.S. dollars calculated using an exchange rate of $1 = CFAF 547. Distribution of costs was estimated at 2.5 percent for preparation (initial survey, participatory diagnosis, and feasibility study), 30.5 percent for 'soft' investment, that is, community mobilization, social organization, capacity building activities, and NGOs' honorariums, and 60 percent for the physical realization (World Bank 2004, 9).
P035620 | FINANCIAL INST. DEV. | Eastern and Southern Africa | Tanzania | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 1999 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/415321474398330846/text/000020051-20140528122003.txt | http://documents.worldbank.org/curated/en/415321474398330846/pdf/000020051-20140528122003.pdf | (i) Follow-on projects should draw on the lessons from past projects (ii) Achievement of critical objectives in institutional development projects can be helped if they reinforced by the SAC and the IMF program. (iii) Flexibility in resource allocation among project components in small projects can assist in the achievement of the critical objective but the hierarchy of objectives (from most critical to less critical) should be made clear in the staff appraisal report. (iv) The Bank should give due importance to public information campaigns to garner public support especially when the enterprises (banks and nonbanks) involved are well-known by the local population and there is distrust of foreign participation.
P035621 | Pilot Female Literacy Project | Western and Central Africa | Senegal | IDA |  | Human Development | Education | IDA | IPF | 1996 | 2003 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/840831475078546926/text/000020051-20140612135432.txt | http://documents.worldbank.org/curated/en/840831475078546926/pdf/000020051-20140612135432.pdf | Demand for adult literacy can be strong, particularly among women. Large scale programs for reaching illiterate populations can be successfully implemented in a relatively short period of time by using the outsourcing approach if the project is well designed and implementation arrangements are appropriately tightened. The involvement of local women ' s associations in project implementation is important for the success of the program as is the provision of adequate incentives to providers.- Evaluation procedures for adult literacy can be overly complex and may not be effective. Innovative means are needed to obtain estimates of attendance and achievement when large numbers of classes take place. Nevertheless, mechanisms to simulate and control unit costs, conduct cost-effectiveness analysis, and follow-up on progress of literacy programs based on an agreed set of indicators are key to sound monitoring.
P035623 | CAPACITY BUILDING | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2000 | 2001 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/667871475075209992/text/000020051-20140529203537.txt | http://documents.worldbank.org/curated/en/667871475075209992/pdf/000020051-20140529203537.pdf | It is better to improve domestic economic management capability early. This was delayed in Chad, and the expected surge of tax revenues from petroleum risks being misspent. External control of expenditures (to prevent misuse) undermines efforts to improve domestic economic management capability.
P035626 | PILOT COM. INFRA. UP | Western and Central Africa | Gabon | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/500511474657993228/text/000020051-20140613033853.txt | http://documents.worldbank.org/curated/en/500511474657993228/pdf/000020051-20140613033853.pdf | A LIL should be accompanied by intensive monitoring and evaluation to understand the effectiveness of the approach being tried. The performance indicators reported in the ICR are focused on the use of the methodology (such as number of micro-projects, number of neighborhood projects using TIPPEE), rather than its effectiveness in reducing poverty in the target communities. Effectiveness of the new methodology could have been assessed through tools such as beneficiary surveys, which would have greatly enhanced the learning from this project.It is critical that the actual results of a pilot project are known before a larger project, based on the pilot, is designed or implemented. The ICR reports that close to 95% of final project costs were focused on infrastructure works and many of the planned activities for M&E, such as a baseline survey, ex-post evaluation or even a technical audit, were not carried out due to lack of funds. Given that this project was conceptualized as a pilot using the LIL instrument, there should have been greater Bank management oversight to ensure that adequate M&E information was available to inform the design of the follow-on project. A proactive plan of action is necessary to disseminate the projectâ€™s innovations. The project was more focused on designing and testing a new methodology than on disseminating the innovations outside of the original participants. As its experience shows, preparation of manuals and procedures may not be sufficient to effectively disseminate the project's innovations or to generate sufficient interest among nonparticipating municipalities. A dissemination plan, including activities such as workshops and other events to promote interaction of participating and nonparticipating municipalities, may be useful in generating demand for innovations tested by such pilot projects.Pilot projects should be adaptable and flexible in implementation. Partway through the project, the approach was modified to combine components A and B, which were then implemented concurrently. This modification facilitated the learning-by-doing approach as the methodology developed under component A could be constantly revised on the basis of experience and tested in actual works implementation under component B.
P035628 | ENTERPRISE DEVELOPMENT | Eastern and Southern Africa | Zimbabwe | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2003 | 2003 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/519931474656110267/text/000020051-20140612064435.txt | http://documents.worldbank.org/curated/en/519931474656110267/pdf/000020051-20140612064435.pdf | In a country where political and economic governance has deteriorated to the point of distorting lending schemes in favor of privileged political party members, the Bank should discontinue operations which may become a vehicle for such activities.
P035630 | AGRICULTURAL SERVICES AND PRODUCER ORGANIZATIONS PROJECT | Western and Central Africa | Mali | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2002 | 2010 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/993001475088792094/text/000020051-20140624170053.txt | http://documents.worldbank.org/curated/en/993001475088792094/pdf/000020051-20140624170053.pdf | The ICR offers a number of lessons. Four of these are offered here with some adjustment.1. Multi-stakeholder financing mechanisms can be effective for the allocation of funds provided the activities are relevant and consistent with the needs of producers. However, there is a necessary learning phase and the process needs to be carefully monitored and supported by training for producer organizations.2. In supporting far-reaching institutional reforms of government departments, there is a need during project preparation to pay particular attention to the level of, and locus of, political commitment, and, during implementation, to pay particular attention to the sequencing of reforms and the associated operational arrangements.3. In projects supporting agricultural services there needs to be particular attention to financial and economic analysis capacity within research and extension organizations in order to help guide resources towards areas of the highest economic and social returns.4. The privatization of agricultural extension should be designed as a long-term process calling for supportive policies, analytical work, public funding, and capacity building. There is a need to enhance public sector capacity in extension planning, extension contract performance monitoring, and the development of standards for the training of extension staff.
P035634 | PRIV. SECTOR COMPETI | Eastern and Southern Africa | Uganda | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/349261475079716154/text/000020051-20140612090550.txt | http://documents.worldbank.org/curated/en/349261475079716154/pdf/000020051-20140612090550.pdf | 1. The Bank should assess project relevance in the context of its overall lending strategy for the country and country progress in macroeconomic, institutional and structural reforms. While every project can be designed to be relevant, the Bank should support only those activities or policies where it is likely to have the most impact. 2. Impact indicators reported in the ICR must be specific to the project. FDI flows reported in the ICR is not a good indicator for this project's success. 3. Project documentation should give the reader a good indication of how far along the project will take Uganda in improving the competitive environment for private sector development (for example, MOP Schedule B states that 300 firms receive services...over 150 investors in specific sector contacted. However, the proportion of investors, firms (large or small) being reached by this project is unclear). 4. The Bank should do upstream work to assess beneficiary interest and capacity in undertaking complex schemes, like the equity fund program in this project, before introducing them as project components.
P035637 | SL:ERRC | Western and Central Africa | Sierra Leone | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2000 | 2001 | 2002 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/355981474596133776/text/000020051-20140607140443.txt | http://documents.worldbank.org/curated/en/355981474596133776/pdf/000020051-20140607140443.pdf | Security conditions in a post-conflict situation are an unpredictable factor affecting program implementation. Flexibility in operation design and the transition to a medium term framework is required. Development objectives should be realistic in the short term and the Bank's program should explicitly recognize the need for pragmatism.An effective partnership with the IMF and other donors, including complementarity in aid programs and agreement on timing of donor inputs, assists in increasing program effectiveness. This collaboration needs to be closer than for "normal" aid programs.
P035637 | SL:ERRC | Western and Central Africa | Sierra Leone | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2000 | 2001 | 2010 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/445421468184767944/text/54899-PPAR-P035637-P074642-P078623-P083477-Box396251B-PUBLIC.txt | http://documents.worldbank.org/curated/en/445421468184767944/pdf/54899-PPAR-P035637-P074642-P078623-P083477-Box396251B-PUBLIC.pdf | Lessons 7.8 Overall, the ERR operations were effective in providing critical budget support to GOSL during the initial post-conflict years. The effectiveness was greater in directly supporting the demobilization effort under the DDR program, achieving the initial protective, social, and economic security advances, and in accomplishing process improvements, than in achieving better governance, improved allocation of budget resources and development results in the longer run. 7.9 The following main lessons for the design of future support programs in post-conflict situations are derived from the review\. 7.10 Early start of Bank interventions and informed risk taking can help consolidate the peace process\. The Bank team reacted promptly to the narrow window of opportunity created by the initial Lome peace accord (July 1999) and skillfully used stand-alone adjustment operations fitting them pragmatically with the slowly evolving country development and Bank assistance strategy. Despite obvious risks, an early effort to create a sensible interim assistance strategy and prepare a development policy operation was well justified. The first ERR provided critical budget support to restore basic state functions, initiate economic and social recovery. This clearly demonstrated the benefits of peace, curbed the impact of renewed hostilities (May 2000), and tilted the balance in favor of achieving a firm peace settlement (January 2001). 7.11 Delayed adoption of country strategy and programmatic budget support weakens ownership, creates funding uncertainty, and hampers capacity building\. Under the circumstances, more could have been done to secure an early adoption of a multi-year country strategy and programmatic budget support. In substance, the interim PRSP provided a sufficient basis for a country assistance strategy, while the IMF's 2001-2005 PRGF rendered a solid macroeconomic backing for a programmatic series of DPOs. Instead, formal criteria prevailed and the Bank postponed the adoption of the first post-conflict CAS and the programmatic DPOs till FY2006, almost six years after the Lome peace accord. This weakened ownership of the reforms, introduced additional uncertainty in the budget process and inadvertently destroyed the continuity of the decentralization and capacity building effort 7.12 To produce sustainable longer-term development results in a typical post-conflict situation, the Bank needs a stable strategy, much more careful project design, greater quality of prior actions and tranche release conditions derived from a detailed results chain and strongly related to expected outcomes. Although outputs achieved under the ERR series appear to be highly positively correlated to desired outcomes, the absence of fully defined developed result chains and well specified performance indicators makes it very difficult to assess the outcome of the Bank program on program objectives, particularly in achieving sustainable advances in improving decentralization, public governance and better management of public resources. 7.13 Stronger signaling of longer-term resource availability for budget support and capacity building substitutes for the lack of formal programmatic framework\. In situations where programmatic instruments were not possible due to funding or other constraints, Bank efforts to secure as much continuity as possible in the content and design of stand-alone operations were well justified. More could have been done if these efforts were supplemented with stronger signaling of potential longer-term resource availability for budget support and capacity building. 7.14 While project/program designs were kept simple and realistic, more could have been done to develop an appropriate results framework calibrated to post-conflict country circumstances. Additionally, more resources could have been allocated to adequately monitor the achievement of outcome indicators. Critical outcomes, especially in the area of better governance, could then be more fully owned by the Government (and other stakeholders) and implemented in time. This would also help achieve a better balance between government efforts aimed at satisfying conditionality and participating in other Bank supported activities, including sustained capacity building. 7.15 The Bank is (often) expected to assume a leading role in mobilizing and coordinating external donor assistance in post-conflict situations, and is not always adequately resourced to do this. In recognition of this, post-conflict Bank programs may benefit from senior management support that would enable country teams to more appropriately structure and adequately resource their efforts in mobilizing and coordinating donor assistance. Alternatively, other viable solutions would need to be found and endorsed by the Consultative Group meetings and other donor fora. 7.16 Discussions in Sierra Leone confirmed that the Bank's significant role in mobilizing donor support, administering a multi-donor trust fund, and in coordinating donor activities (see paragraph 3.5 on page 12) represented a heavy demand on limited operational budget. In the absence of adequate funding, this invariably diminishes resources available for other critical activities in the immediate post-conflict period, including the necessary ESW to gain improved knowledge of the economy, support for capacity building in the Government, and the establishment of an effective results monitoring system.
P035641 | PSREP (ESAC III) | Eastern and Southern Africa | Zambia | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2002 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/959961474946436840/text/000020051-20140602105345.txt | http://documents.worldbank.org/curated/en/959961474946436840/pdf/000020051-20140602105345.pdf | 1) The Bank must carefully assess the impact of adjustment lending and related technical assistance credits on sensitive privatization transactions, particularly in high-need balance of payments situations. Disbursement timing, conditionality and institutional or program funding should all send appropriate messages and create appropriate incentives for transparent and timely action on agreed privatization. In this case, IDA's earlier BOP support cushioned mining losses, but failed to provide added incentives (e.g. funding labor retrenchment) or results-oriented conditionality to conclude the privatization. Technical assistance funding for the negotiating team also lacked results-based financial incentives. 2) Sequencing of privatization can have a significant impact on economic recovery. Earlier tackling of large, important privatizations such as the mines would have led to faster economic recovery, in turn contributing to continued political will and public acceptance of reform.3) Weak conditionality limits the impact of adjustment lending. Adoption of action plans (e.g. PSRP) should be linked to monitorable indicators of implementation progress as a trigger for tranche release.4) Thorough analysis of the trade regime and effective protection (including an assessment of the regional trade environment) and of the business environment is necessary to design effective reforms for investment and export promotion.5) Macroeconomic adjustment operations should avoid overstating the impact of social expenditure protection, which is just one step--and often only a modestly effective one--toward improved delivery of social services.
P035641 | PSREP (ESAC III) | Eastern and Southern Africa | Zambia | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2004 | PPAR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/413971468781171324/text/27053.txt | http://documents.worldbank.org/curated/en/413971468781171324/pdf/27053.pdf | 4. Summary Findings andLessons 4.1 The summaryfindings and lessons draw primarilyfrom the performance assessments, but also benefitfrom the findings o f OED's 2002 Country Assistance Evaluation for Zambia. Issuestranscending the individual operations are raised, particularlyas regards the highand sustainedlevels o fBank adjustment lendingto Zambia. In this way, it i s anticipated that broad lessons for countries inAfrica engaged inlongtermreformprogramswill emerge. Issue 1\. When pressuresto maintaina Clientcurrenton the service of itsexternal debt havea major impacton lendingdecisions,it is incumbentuponManagementto discussthesepressures,andany impactthey hadon the timing, content, and size of a proposedoperation, with the Boardat the time of loanpresentation. 4.2 Findings. Judging from a successiono f CAS reports and adjustment lending appraisal documents, there i s ample evidence for the view that the volume and frequency o f IDA's adjustment lendingto Zambiawere influencedbythe desire to keep the Borrower current on its external debt service obligations. Indeed, IDA staffhave defended the frequency o f adjustment lendingby arguing that, hadZambia failed to meet its payment obligations, the economy would have been thrown into a tailspin. Reflecting thisbelief, the CASs of 1994,1997, and 1999providedfor a steadyrhythmo fadjustment operations, at the rate o f one per year. The lendingamounts associatedwith these operations exceededagreedIDA allotments by a wide margin.24Yet, never was the goal ofkeepingZambia current with its external debt obligations mentioned amongthe stated objectives o fthese operations. 24According to IDA financial riskassessment specialists, actual IDA lending commitments exceeded the agreed amounts for the FY98-00periodby +I36 percent for Zambia, whereas, inthe remainder o f the Africa Region, there was a shortfall o f 19percent. Agreed IDA lending targets are determined usinga standardized allocation formula based onpopulationand policy performance, adjusted for certain other factors agreed between the Region inquestion and the financial risk department. 4.3 The pressure for large and fiequent IDA credits undermined quality at entry. Pressures to disburse on a schedulecompatible with Zambia's debt service requirements ledto conditionality which relied onnumerous, but often superficial, tranche requirements. Supported reforms relied excessively on easy-to-implement stroke o fthe pen measures, whose ultimate impact was bluntedbythe lack ofwider support inside and outside the public sector for implementation and enforcement. The hghvolume o f IDA quick-disbursinglending also diminishedpressure on a reluctant Borrower to act more expeditiously on crucial, but politically-sensitive, reforms, such as privatizationo f the copper mines. Finally, quick-disbursing instruments were inappropriate vehicles, in manycases, for supporting longandcomplex reforms (e.g., public sector reform inthe PSREP operation andZCCMprivatizationsupportedbyERIP,ESAC11,andPSREP operations). 4.4 IDAwas slow to acknowledge the fact that Zambia's external debt burdenhad becomeunsustainable, and inneedo f substantial reduction rather thancontinued servicing, ifthe considerable investment needs o f the economy were to be adequately financed. Other advocacy groups anddonors were quicker ingivingvoice to this reality.25 4.5 Lesson. Pressuresto lendfor debt andbalance o fpayments reasons can easily leadto hastily-conceived, superficial conditionality which generatesfew long-term benefits. The drive to findnew sectors to lend oftenpiles on new conditionality, even though previously-supported reforms have not yet been consolidated. The HIPC initiative helps separate debt servicing considerations from support for structural reform, butonly partially so. For example, H P C debt reliefto Zambia, as presently configured, will not lower debt servicepayments significantly untilafter 2005. Hence, IDA will continue to face pressures to relyexcessively on quick-disbursing vehicles inZambia, such as programmatic lending, when such vehicles have repeatedly failed to achieve the desiredreformresults. Issue2\. Stroke ofthepen measuresare an unreliableindicator of Borrower commitmentto genuinereform 4.6 Findings. The Chiluba regimewon international praise for its initial roundo f reforms inthe early nineties. However, many o fthese reforms were what have been termed stroke o f the pen measures, meaningthey couldbe placedinto effect solely withthe consent of the ChiefExecutive. This includedmeasuresto liberalizeprice, interest rate, and exchangerate controls, which experience has shown were sustained. 4.7 Onthe other hand, with thebenefit o fhindsight, other stroke o fthe pen reforms . haveprovenless durable, possibly because they were adopted without having securedthe 25For example, OED's 1996 CountryAssistance Review (Report No. 15675, June 3, 1996)noted (para. 6.29, p. 107) that some inZambia still believe the debt service curtailment in1987-89 was the appropriate approach. They suggest that paying off arrears andcontinuing full debt servicing postponed investment in infrastructure and diverted management attention to debt service, both delaying recovery. The implied criticism is that the Bank has failed to deal realistically with Zambia's debt overhang, and has misplaced priorities-focusing onrestoring creditworthiness rather thanrecovery o f economic growth, and emphasizing servicing o fthe debt rather than debt forgiveness. 22 requisitesupport o fkey affected stakeholders. For example, there is the case o fZCCM privatization, wherein the initialbiddingprocess was subsequently annulled, leading to costly andprotracted rebidding. Another areawas reform o f the public sector. The PSREPwas initiallypremisedon securingreformofthe civil service, withthe agreement o fthe President andthe Ministero fFinance. However, afier serious oppositionsurfaced fromaffected civil service organizations, PSREPhadto berefocused, as bothIDAand the GRZ acknowledged that the required broad support for such reform didnot exist. IDA hasnow opted for amore gradual approach, extending adaptableprogramloans for public service reform over the anticipated space o f at least a decade. 4.8 Lesson. Stroke ofthe pen measures do not provide reliable guidance about the true extent o f commitment to structural reform. The small core ofreformers inthe Presidency and the Ministryo f Finance found their efforts quickly stymied, once the affected interest groups became aware o f what was beingplanned, and how it would affect their interests. Participatory approaches, including evidence o fpublic support fiom key interest groups, stand a better chance o f elicitingthe requisite support for core reforms, even ifthe process takes longer, and the reforms dilutedrelative to what would have been ideal. Issue 3\. Inconsistent macroeconomic performance severely constricts the benefits of reform intended to promote private sector-led growth. 4.9 Findings. The appraisal documents o f the EMP, ESAC11,andPSREPoperations underlinedthe importance o f continued satisfactory implementationo f an acceptable macroeconomic framework. Yet, the Borrower repeatedly faltered incomplying with this framework. 4.10 After loweringinflationfrom triple-digit levels in 1990to roughly 50percent in 1994, budgetarydiscipline lapsed, with the result that inflation duringthe remainder o f the decade floundered indouble digits, with severe consequences for private sector growth. Inparticular, private sector representatives cited chronic inflation andexchange rate instability, bothby-products o fthe Borrower's uncertainmacroeconomic management, as key constraints to investment. Inflation also thwarted the development o f a market for long-term credit, a key aim o fthe EMP-supportedbank reforms, which has posedanother bottleneck to private sector development, especially for the multitude o f small and medium enterprises. 4.11 Lesson. Steadyprogress toward consolidating macroeconomic stability is asine qua non for successfully achieving the sort o fprivatization andfinancial sector reforms supportedbythese operations, as well as for attaining the desired private sector response. Issue4\. Diversificationofproductionhasnot occurredat the pacethat would have beendesirable, inpartbecausethe reformssupporteddidnotincludemeasuresto addressother key non-priceconstraints,such as the poor conditionof Zambia's infrastructureand itsweak governance. 4.12 Findings. Although recognized as one key to sustainablegrowth, Zambia's manufacturing sector remains largely undiversifiedand dependentupon the copper miningsector. 4.13 Thereforms supportedby IDA adjustment lendinginthe 90s were necessary, but far from sufficient to produce atangible result. For example, reductions inimporttariffs stimulated only amodest export response, constrained by a varietyo f supplybottlenecks. One difficulty hasbeenthe limitedmanagement experience o fmost Zambiannon-mining companies. Other factors includedthe poor condition o fZambia's infrastructure, inefficiency inthe deliveryof most public sector services, over-regulation, andthe impact of HIV/AIDSon the supply andquality o fthe work force. 4.14 Lesson. A multivalent focus, addressing the full range o f constraints onprivate sector development, will beneeded, ifthe pace o f diversificationi s to be accelerated. This task is all the more urgent, now that the largestprivately-ownedminingcompany has decided to terminate its mininginterests inZambia.
P035643 | THIRD EDUCATION | Western and Central Africa | Gambia, The | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/449911474484644330/text/000020051-20140613090817.txt | http://documents.worldbank.org/curated/en/449911474484644330/pdf/000020051-20140613090817.pdf | Establishment of a government task team at the early preparation stage is important. In addition tobuilding ownership of the project, it allows the Bankâ€™s team to assess the implementation capacity of the borrower and provide technical assistance as needed. It also enables the Bank's team to provide support for project effectiveness and at the early stages of implementation.Private-public partnerships. Enrollment growth in secondary education can be accompanied by importantdevelopments in private sector participation and household cost sharing. For example, the private sector can get involved in the management of the school and government can provide subsidies to keep the units costs down. In terms of household cost sharing, students can contribute nominal registration fees and funds for textbook rental with waivers available for students from poor households.Girl's scholarships have important impacts on enrollment at the post-basic level. Scholarships for girls ensure that cost considerations do not keep them out of school and permits raising enrollment of girlssignificantlyEnsure sustainability of EMIS and create a data-driven culture, which is essential for policy making.It is essential to keep data up to date and staff trained in data collection and analysis to allow for reliablemonitoring and evaluation, achievement of triggers, and objectives. This may require different pay scales for staff who may have little problem finding better paying jobs in the private sector.Create incentives (financial and nonfinancial) that support a project and are performance-based. For example, in order to keep qualified teachers in the system, financial incentives, even small ones that do notsignificantly affect the budget, can make a difference. It is also important to provide capacity building opportunities to teams in order to prevent an entire system from collapsing when some individuals leave the system.Teacher training programs need to be given sustained attention. Rather than try to increase pre-serviceintake rapidly to fulfill teacher shortages in the system, serious attention needs to be given to the caliber of recruits and to revising the program in terms of content knowledge, pedagogic methodology, and teaching practice.Strong coordination is needed among donors to ensure consistency among the respective education projects in alignment with the priorities of governmentâ€™s national education policy. Despite much discussion at preparation, donor coordination often does not occur during implementation. Government ownership of the coordination, harmonization of procedures, and alignment of project objectives aresuggested means to enhance donor coordination. In addition, common indicators for measuring education quality should be used by all key donors and the government.
P035645 | SOCIAL FUND | Western and Central Africa | Benin | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/973501474586878531/text/000020051-20140612133337.txt | http://documents.worldbank.org/curated/en/973501474586878531/pdf/000020051-20140612133337.pdf | 1. A weak MIS can reduce the ability of project management to continually finetune project implementation. 2. Social intermediation between the poor and the existing formal financial system, and technical assistance to small-scale entrepreneurs and savings/credit groups can play an important role in income-generation. 3. In a project with community empowerment as an objective, the performance measurement system should be set-up to measure both quantitative and qualitative progress. 4. The Bank and other donors need to harmonize approaches at the community level to avoid confusion and maximize development effectiveness.
P035648 | 1ST DECEN.CITY MGMT. | Western and Central Africa | Benin | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2005 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/915991474492052836/text/000020051-20140613045309.txt | http://documents.worldbank.org/curated/en/915991474492052836/pdf/000020051-20140613045309.pdf | Capacity building should be integrated with project coordination. Having better access to resources, centrally placed project coordination can at the same time be an effective instrument of local capacity building.Even small organizations require well planned budgets and financial control systems. Project difficulties with maintenance came about mainly because small agencies, after delivering infrastructure, had not foreseen the current expenditure requirements needed to finance the future maintenance of them.Project implementation estimates should factor in the likelihood and pace of turnover of local staff that can introduce significant delays.Micro-projects for urban services can only be successfully implemented if there is strong community involvement and participation by the direct beneficiaries.
P035655 | Education & Training Support | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Human Development | Education | IBRD | IPF | 1998 | 2013 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/183801474660200603/text/000020051-20140626080107.txt | http://documents.worldbank.org/curated/en/183801474660200603/pdf/000020051-20140626080107.pdf | The ICR (p. 24-25) provides several lessons, which IEG has synthesized to the following:Approved projects should not be closed due to suspensions. The project played a key role in providing needed resources to the education sector each time the country emerged from civil unrest. Emergency projects are an option but take time to prepare, unlike this (existing) project where money was immediately available after each Bank re-engagement. This proved invaluable for getting teachers and children back in school quickly after each crisis and helping the country attain "quick wins" towards stabilization.Oversight bodies with the overall picture of system play an invaluable role in advising sub-sector ministries. The task force established under the project was responsible for helping prepare the 2011 Country Status Report, overall sector policy, ensuring coordination of donor activities, preparing the 2011 Global Partnership Education application, and advising all three education ministries. The task force remains the oversight body for the education sector, which has proven instrumental in setting out a policy framework for the sector and ensuring Government ownership.In post-conflict and fragile states, basing task team leaders (TTLs) in-country is essential for ensuring successful implementation of Bank-supported projects. In this case, the presence of the TTL in the country provided invaluable daily support and monitoring of project implementation. Experience with other Bank-supported projects in post-conflict countries has shown that having the TTL in-country is critical for ensuring timely project implementation.Having a Project Implementation Unit outside the government structure is helpful for project implementation in a post-conflict environment. The benefit of having the Implementing Bureau as a semi-autonomous unit outside the Ministry's structure was important for maintaining continuity and staffing that were committed to the project. The Bureau remained operational because key staff were not Ministry staff and therefore were not subject to political staffing changes. Limited project implementation was maintained, even during the 2004-2008 suspension. It was easy to augment the hiring of consultants to provide support. Therefore, in a post-conflict fragile state situation, consideration should be given to establishing a semi-autonomous Unit with the plan of integrating future Units into the organizational structure of the Ministry.
P035669 | SOCIAL FUND 2 | Eastern and Southern Africa | Madagascar | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2001 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/481431475073660500/text/000020051-20140529065143.txt | http://documents.worldbank.org/curated/en/481431475073660500/pdf/000020051-20140529065143.pdf | * Investments in community mobilization and outreach before, during, and after making resources available to communities are often essential to ensure that communities agree on and choose priority activities, feel a stake in and ownership towards them, and maintain them over time. These mobilization and outreach activities should be explicitly budgeted for. In many cases, FID lacked the resources to adequately address these issues since, inter alia, it was committed to keeping its operating expenses at 10 percent of total expenditure.* Ensuring the continuing operation of the investments financed by a social fund requires that there is coordination with sector ministries and strategies and that the creation of new facilities by the social fund is in line with the ministries' capacity and willingness to provide the necessary complement of inputs for running the facilities.* A technical focus in training programs for small and medium firms and contractors who execute physical works under a social fund project is appropriate although complementing it with sensitization in participatory and sociological techniques and approaches will also help to better address the community development goals of these projects. * The institutional location and organizational structure of the social fund agency including the composition of key decision-making bodies (e.g., Board, Executive Committee) needs careful design and checks and balances to prevent politicization while at the same time ensuring that the social fund agency enjoys adequate political support. * Microcredit/loan programs cannot operate outside a country's financial markets; they must be consistent with and linked to existing financial policies, markets, and institutions.* There can be trade-offs between speed and quality. FID disbursed much more rapidly than originally anticipated; the ICR hints that fast disbursements might likely have prevented the project from benefiting from "additional early (impact) studies" and have hindered adequate improvements in community mobilization (page 9).
P035672 | National Transport Program Support Project | Western and Central Africa | Chad | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2008 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/608651474488995853/text/000020051-20140620064440.txt | http://documents.worldbank.org/curated/en/608651474488995853/pdf/000020051-20140620064440.pdf | In countries with weak institutions and a high risk environment, project should have simple designs, and avoid components that spread across ministries or independent agencies.The introduction of performance-based maintenance contracts for unpaved roads proved successful and is being expanded widely across the Africa region. The experience could be improved by better studying the level of service that will be demanded from the contractor, by documenting lessons learned and by developing capacities of local small and medium enterprises to carry out this type of contract.An effective M&E requires not only the definition of a good set of performance indicators during project preparation, but that it be supported by a well articulated monitoring and evaluation framework. Continuous and close monitoring is essential to readily identify and address issues that surface during implementation.Institutional components require that initiatives be demand-driven and developed in a participatory manner. This would help limit the shortfalls observed on components that required changes in practices such as those on road safety and HIV/AIDS.
P035673 | COMMUNITY-BASED RURAL DEVELOPMENT PROJECT | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/719681474666238573/text/000020051-20140618194255.txt | http://documents.worldbank.org/curated/en/719681474666238573/pdf/000020051-20140618194255.pdf | Building on the ICR the following lessons are emphasized:Projects aimed at capacity enhancement and community participation should explicitly and systematically monitor and evaluate the extent to which these are achieved using both quantitative and qualitative measures and appropriate baselines. The execution of community based programs necessitates a good knowledge of local conditions and the adoption of simple management procedures. In addition flexibility in implementation procedures is essential without which it would not be possible to execute a large number of micro-projects in a short time period.Effective harmonization of donor activities is critical to maximize local development impact. Not only is strong government leadership key to achieving this goal but what is also needed is commitment among donors to harmonize their support around a national program.
P035688 | National Health Development Program | Western and Central Africa | Guinea-Bissau | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/136461474664603887/text/000020051-20140619074631.txt | http://documents.worldbank.org/curated/en/136461474664603887/pdf/000020051-20140619074631.pdf | When civil works are added to a project under a Supplemental Credit the recurrent costs implications have to be estimated in order to assess and plan for the future burden on the sector.The identification of risks without appropriate risk mitigation actions that are implementable and for which resources are provided does very little to improve project performance.
P035689 | Health Sector Investment Program | Western and Central Africa | Mauritania | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/356511474649925387/text/000020051-20140613063444.txt | http://documents.worldbank.org/curated/en/356511474649925387/pdf/000020051-20140613063444.pdf | A sector wide health operation in a low income country is a complex undertaking requiring the buy in of a wide range of stakeholders. Additional resources devoted upfront to reaching a concensus is a worthy investment. In Mauritania, PERs and other analytical work were essential in providing the evidence base and establishing the framework for the SWAP.The HIPC initiative made a strong contribution to the project outcomes, by placing health in the center of policy dialogue. This was the impetus which mobilized additional government funding (exceeding appraisal amounts) to the sector.Demand for health services often has to be generated, and can be achieved through health promotion and education activities, which are very cost effective. This will help increase utilization of services. Even though the outcomes of performance management interventions introduced by the project have not been fully realized, because they are well designed they are expected to enhance the professionalism and quality of health services.
P035691 | KE - NAIROBI MOMBASA ROAD | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 1996 | 2006 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/561691475073770575/text/000020051-20140613043028.txt | http://documents.worldbank.org/curated/en/561691475073770575/pdf/000020051-20140613043028.pdf | Stand-alone road investment projects should be developed within a framework for policy and institutional reform which has strong government support. Contracts for technical assistance and studies need to take into account implementation realities and the ability to effectively deliver a particular task. Where capacity is weak, the projects technical team should include financial management experts for proper accounting, reporting and payment processing to avoid delays.
P035693 | GEF- Efficient Industrial Boilers | East Asia and Pacific | China | IBRD |  | Infrastructure | Energy & Extractives | GEF | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/370361474486388316/text/000020051-20140613041915.txt | http://documents.worldbank.org/curated/en/370361474486388316/pdf/000020051-20140613041915.pdf | 1. Standard procurement processes may not be appropriate for non-standard items, for which the market in industrialized countries is disappearing.2. GEF support can make a critical difference for the introduction of energy-efficient technology, especially when it is sustained through all stages of the product introduction cycle - design, demonstration, manufacture and marketing.3. Consistent government support is also critical, especially during a period of rapid economic change, including privatization of manufacturing enterprises.
P035697 | MONGOLIA COAL PROJ. | East Asia and Pacific | Mongolia | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/344641474510954682/text/000020051-20140607153011.txt | http://documents.worldbank.org/curated/en/344641474510954682/pdf/000020051-20140607153011.pdf | The financial and productivity impacts of the performance of downstream user companies must be clearly factored into any comprehensive approach to rehabilitating the energy sector; and Undue attention to numerical targets may detract from attention to more strategic goals.
P035698 | Hunan Power Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/123591474590908071/text/000020051-20140615110049.txt | http://documents.worldbank.org/curated/en/123591474590908071/pdf/000020051-20140615110049.pdf | As the ICR points out, the main lessons are:Â· It would be useful to give more guidance on procurement in unusual cases, such as the bankruptcy of the winning bidder. This is especially so where the Borrower, like HEPC, has no previous experience of dealing with the Bank.Â· Much of the work intended for international consultants was in fact carried out successfully at a local level. The Bank should seek to avoid bias towards large international firms. Lists of firms providing advisory services should increasingly include practitioners (in this case, power companies) as well as management consultancies. In particular more consideration should be given to in-house engineering and supervision services rather than the use of consultants. Â· Bank guidelines and practice should be adjusted to ensure more realistic cost estimates (and hence lower financial charges for the Borrower) at the appraisal stage.Â· More care should be directed towards assessing training needs and the related budget for training expenses. In Hunan, these were constantly changing as sector reforms progressed. Moreover, training on institutional reform is useful only if the trainers are thoroughly familiar with the country, the sector and the institutions concerned.Â· The success of the resettlement reflects strong commitment at all levels of Government, flexibility in the light of changing circumstances, and soundly designed resettlement action plans.
P035707 | TN-Water Sector Investment | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/953121475099631571/text/000020051-20140619085406.txt | http://documents.worldbank.org/curated/en/953121475099631571/pdf/000020051-20140619085406.pdf | From the ICR:Well-defined development objectives and indicators are necessary to know clearly what the intended benefits are and whether they are being achieved. The outputs of this project are significant and exceed expectations. However, these investments did not generate intended benefits because the objectives and results indicators do not actually reflect the activities. And the project objectives were too imprecisely defined with limited linkages between components. This imprecision allowed those managing the project to focus on the component outputs rather than the overall strategic objective. (For IEG, this lesson highlights the importance of having a clear results chain in the project design).Proper estimation of economic returns of project investment, both at appraisal and completion, is necessary to assess the efficiency of project achievements. The economic analysis carried out at appraisal was imprecise (taking only certain activities into account) and as such did not form a good basis for evaluating the economic impact of the project. The absence of proper calculations at appraisal and low rate of returns at project closing did not result in any significant benefits from the project. Additionally from IEG:Partial involvement of state water agencies in O&M of irrigation schemes is instrumental when water users associations lack management and financial experience. The local water users associations in Tunisia are new and yet to gain financial and managerial autonomy. Despite the initial plans to transfer entire responsibility of irrigation schemes to WUAs, these young and inexperienced non-governmental institutions proved to be weak and not ready to manage the schemes. In this case, support of state water agencies to manage the schemes is necessary until the WUAs become self-sustaining.
P035717 | Rural Poverty Alleviation - Bahia | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/622041475070234239/text/000020051-20140604060204.txt | http://documents.worldbank.org/curated/en/622041475070234239/pdf/000020051-20140604060204.pdf | From the many listed in the ICR, the following stand out:(a) By assigning greater responsibility to local organizations and municipal goverments, community demand-driven projects can help build institutional capacity in poor rural areas;(b) Community-driven approaches can reduce bureaucracy and administrative obstacles and reinforce accountability for project performance by reducing the distance between decision-makers and beneficiaries.(c) Decentralization of the Bank supervision effort---in this case, directed from the Recife office---can greatly enhance implementation, by ensuring rapid response to problems, timely advice giving, and careful monitoring.(d) Screening of projects should be conducted by municipal councils (rather than sending proposals to be vetted by a technical agency in the state capital) because this helps to build local capacity, with benefits extending beyond the project (potentially citizens acquire more voice in municipal planning).(e) Productive subprojects should be subjected to rigorous selection, preparation, technical assistance and supervision criteria and linked to a graduation strategy which facilitates beneficiary communities access to formal credit.
P035722 | DO NATIONAL HWY. PROJ. | Latin America and Caribbean | Dominican Republic | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2004 | 2004 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/964081474513001270/text/000020051-20140612131252.txt | http://documents.worldbank.org/curated/en/964081474513001270/pdf/000020051-20140612131252.pdf | A passive approach to funding maintenance is less effective than a development of coherent framework/plan for maintenance financing.Adequate coordination among the institutions involved in project implementation is critical for successful project outcomes.Medium sized contractors are not interested in routine maintenance. Therefore, these types of contracts should be designed for small contractors with short lengths of the road network and contract period.
P035728 | Bahia Water Resources Management Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/296161475072054196/text/000020051-20140615105841.txt | http://documents.worldbank.org/curated/en/296161475072054196/pdf/000020051-20140615105841.pdf | Projects that aim to bring reforms in the water sector need to account for such arduous processes of consensus-building and recognize and build political support for reforms. In this case, reforms moved relatively well when there was political support at the highest level and suffered delays as political priorities shifted.Rather than spreading efforts too thinly, the focus upon a few selected river basins will more likely result in more readily observable impacts.Planning and site selection for dams should be based on multiple evaluation criteria. It should be responsive to the demands for diverse water uses so as to maximize benefits, while ensuring a benign environmental impact. Decentralizing water resource management activities to final users helps give them a stronger sense of the importance of water as a scarce resource. Environmental education for water users is an important instrument to achieve this.The role of the State should be restricted only to the provision of the basic infrastructure (the dams in this case), leaving to the private sector the responsibility for investing in the use of the water (such as for irrigation).Legalizing title to the land for those moved is essential for resettlement to be successful.The possibility of permanently preserving a reservoir perimeter, and protecting it from construction can meet with the support of users and landowners, especially if it can be used to generate employment, such as in leisure activities, for example.
P035730 | OECS: Telecommunication Reform | Latin America and Caribbean | OECS Countries |  |  | Infrastructure | Transport | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/926411474894729882/text/000020051-20140613053337.txt | http://documents.worldbank.org/curated/en/926411474894729882/pdf/000020051-20140613053337.pdf | Small nations can benefit from sharing the fixed costs of regulatory institutions.High level of country demand and political commitment enabled the project to deal with the complexities involved in a multi-country operation.Commitment on the part of governments and the willingness to cooperate on collective actions in a timely manner is especially crucial for regional projects.
P035733 | National Environmental Policy Reform Project | Latin America and Caribbean | Dominican Republic | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/433101475082397121/text/000020051-20140612065133.txt | http://documents.worldbank.org/curated/en/433101475082397121/pdf/000020051-20140612065133.pdf | Simplicity and flexibility in project design (e.g. clear and concise components, concrete objectives in line with institutional capacity, realistic timing in output delivery, etc.) are essential characteristics for loans with short implementation periods. Projects that build in a flexible approach (e.g., demand-driven capacity building activities) are better equipped to adapt to unforeseen shocks encountered during implementation, ensuring their completion.Adopting a participatory consultative process to develop project outputs and implement project activities enhances continuity and sustainability in project execution. Activities that fully involve local communities in decision-making, building ownership and trust from the proposal stage until the closure of the project tend to be more successful.
P035737 | GT RURAL & MAIN ROADS | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/503761474506151107/text/000020051-20140618084817.txt | http://documents.worldbank.org/curated/en/503761474506151107/pdf/000020051-20140618084817.pdf | 1. Projects in conflict-affected areas should have a flexible design and implementation plan. Social conflict and insurgency affects project design and implementation. The project team should have substantial leeway to redefine project components as long as the project objectives do not change. Institutional strengthening strategies in particular need to go beyond technical aspects and address the need to facilitate dialogue and build trust among actors involved.2. Rural roads projects need to be realistic in balancing expected poverty impacts and investment sustainability. Transport services are only one of many of social and economic elements in a poverty reduction strategy which requires the coordination and complementary interventions from the central government. A further challenge is that the poorest municipalities often lack the technical and financial resources to ensure sustainability. 3. Project sustainability is determined by beneficiariesâ€™ participation in project design and implementation, and financing of maintenance activities, which is the single most important challenge in the rural roads. Most rural roads projects benefit communities without all-year roads; they are normally also isolated from the mainstream. Early involvement of beneficiaries is essential to ensure that project design responds to the local needs. Adequate and sustainable resources are likely to consist of central government transfers, especially in the beginning, but prudent funding mechanisms also include local resources from road users. 4. Well-defined and monitorable indicators, preferably with baseline values, are important to ensure good monitoring of project execution, and accurate evaluation of outcomes achievement. A good M&E system is also useful for flagging potential issues so that these can be addressed. Beneficiary workshops and household surveys are powerful instruments to keep relevant agencies focused and induce improvements in policy and operational procedures. The results of surveys should inform the design of future operations.
P035740 | PE LIMA TRANSPORT PROJECT | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2004 | 2011 | 2013 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/627461475097737527/text/000020051-20140625185749.txt | http://documents.worldbank.org/curated/en/627461475097737527/pdf/000020051-20140625185749.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation of language:Â· Strengthen project implementation agencyâ€™s capacity for mainstreaming environmental and social management into urban transport project preparation and supervision. A dedicated full-time and well-equipped environmental and social management team should be set up in the project implementation agency to ensure due diligence in terms of: (i) quality assurance of EIA/EMP and social mitigation plans, (ii) supervision of the implementation of environmental and social management plans, (iii) sound legal analysis to establish the local environmental authority and find any legal vacuum in the local legislation, and (iv) timely and systematic reporting of main findings to agencyâ€™s senior management and the Bank team.Â· Focus on how to achieve the target ridership (and hence financial sustainability) prior to operation of the system or during the first year of operation. Experience shows that the passengers will not use the rapid transit system right away or during the first year of operation. Future rapid transit project design should consider allocating resources for a communication campaign on a modal shift as early as possible prior to operations, enforcement of rationalization of bus routes and implementation of bus scrapping, analysis of competition for feeder routes and taxis, careful analysis of service demand at bus stations to adequately design access to the BRT system, study of fare integration to attract more users, among others. Â· Consider at appraisal key elements that are likely to facilitate the successful implementation of complex BRT projects. These include basing cost estimates on thorough feasibility studies prepared before implementation, consideration of the costs of interference with utility networks, careful analysis of the procurement plan for civil works, analysis of models and contracts to be used for private sector participation, and strengthening of both Bank and Borrower teams in environmental and social safeguards management Â· Modal shift requires a complex cultural change and thus a long-term engagement. Successful bicycle-use promotion requires a long-term engagement, which cannot be ensured through a single financed project.
P035740 | PE LIMA TRANSPORT PROJECT | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2004 | 2011 | 2016 | PPAR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/551201468185372206/text/102352-PPAR-P035740-SecM2015-0359-OUO-9-Box394831B.txt | http://documents.worldbank.org/curated/en/551201468185372206/pdf/102352-PPAR-P035740-SecM2015-0359-OUO-9-Box394831B.pdf | 7. Lessons Â· Improving mobility and accessibility for the poor through Bus Rapid Transit systems requires integrating the main corridor effectively with feeder services and other public transport system that reach close to the traveler's origins and destinations. While the Metropolitano BRT was able to provide mobility to a significant number of poor residents, it is not likely to reach its potential for serving this population segment without extensive penetration of feeder routes with multiple modes, to their work, school, hospital and residential locations. Â· Realistic scenarios and sound risk allocation are crucial for public-private partnerships if high service standards are to be maintained and the use of the assets providing the service is to be maximized. In this project, the private bus operator concessions did not include a minimum revenue guarantee from the Metropolitan Municipality of Lima. The number of passengers was below the target at project completion even after five years of operation, and the situation was particularly serious in the initial operating stage. To close the gap between the planned and actual scenarios, analysis for competition with other transport modes, enforcement of a sound regulatory framework and communication to citizens needed to be strengthened. Â· Given the complex urban settings in which rapid urban transport systems are typically situated, it is important to inform and consult with all categories of project affected persons, to anticipate and take effective measures to prevent possible negative environmental and social impacts and related disputes. In this project, insufficient information was provided to residents of a locality that was eventually impacted by re-routing of traffic from the project, resulting in a complaint and an Inspection Panel investigation, which contributed to delays in project implementation. Â· A shift towards non-motorized transport can be expected to take a long time even with enabling and supporting factors and facilities in place. The experience with promoting bicycle usage in the LMR demonstrates the slow pace at which non-motorized transport is adopted. The bikeway infrastructure development and awareness raising campaigns could be necessary conditions, but they are not sufficient. In this case, this transformation was delayed further by insufficient attention to other supporting factors, such as safe parking space and raising drivers' awareness of the need to share the road with bicycles. More broadly, the prevailing cultural attitudes toward using bicycle should be taken into account.
P035741 | 2nd National Environmental Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/907371475099000722/text/000020051-20140617132226.txt | http://documents.worldbank.org/curated/en/907371475099000722/pdf/000020051-20140617132226.pdf | 1. The project reaffirmed the viability of a decentralized approach to environmental management. By transferring decisions and implementation down to the State level, the Federal Government was able to leverage policy and regulatory change at the State level; generate enthusiasm, energy and counterpart funding for state selected priorities; and build capacity for environmental management at the State level. The project demonstrated that there is a great deal more interest and capacity for environmental protection at the local level, especially when state-level entities are allowed to set their own priorities and develop their own way of approaching the problem. The project also demonstrated that states are quite willing to have their capacity and performance evaluated objectively, especially when the financial incentive to support state-defined subprojects is added. 2. Yet even in a nominally decentralized system, there may be some resistance by central government to allow decentralized decision making. Often this resistance comes indirectly in the form of fiscal controls. In Brazil, there were several occasions on which financial transfers could not be made to eligible states in a timely fashion because of alleged financial defaults in the statesâ€™ obligations to the Federal Government. While these controls are important from the perspective of fiscal discipline, they were sometimes counterproductive in terms of achieving voluntary compliance with national objectives in the environmental area. Often, the fiscal issue was outside the area of control of the State agency. 3. It is important to build an effective communications component into projects. The success of a project may often depend on its capacity to identify key stakeholders and to communicate with them effectively, inboth directions. 4. The lack of a comprehensive baseline to measure actual improvements in environmental quality through the implementation of subprojects at the state level inhibits project monitoring; without baseline data, there is no basis for comparing overall improvements in environmental quality at the end of a specificintervention..6. A flexible, demand driven, grant-retailing mechanism -- designed in this case to support State access to subproject investments for enhanced environmental management - should be closely monitored so that grant applications prioritize the most pressing environmental problems rather than select priorities that match well the expected size of the matching grant.
P035743 | Environmental Management and Cartography Project | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/922511475073722748/text/000020051-20140612153225.txt | http://documents.worldbank.org/curated/en/922511475073722748/pdf/000020051-20140612153225.pdf | 1. Future environmental institutions projects should be designed to mainstream the environment and diverse environmental management instruments across sectors and national/subnational levels (including the private sector), rather than to focus on consolidating a central environment ministry and command-and-control approaches. (On a positive note, environmental mainstreaming was integrated in more recent LAC projects, notably the Mexico-Environment SAL I.)2. In this type of project that seeks to reform and strengthen a country's environmental management capacity, the participation and ownership of the personnel and senior officials from involved Government agencies is critical, throughout the project cycle but particularly at the project conceptualization and preparation stages.
P035751 | Community Forestry II (PROCYMAF II) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2009 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/671951474592680591/text/000146597-20140619170633.txt | http://documents.worldbank.org/curated/en/671951474592680591/pdf/000146597-20140619170633.pdf | Appropriate indicators need to be devised to capture the consolidation of social capital--one of the key aspects of this project. The project used a number of credible proxy indicators: preparation of regulations; development of zoning and forest management plans; level of participation in assembly meetings; and number of inter-community seminars. The use that the community made of the roster of trained technical service providers and the frequency with which it was updated would be another measure. Projects of this nature can be effective ways of engaging indigenous communities in climate change mitigation. In Mexico, indigenous communities own around 65 percent of the country's forests making them vital interlocutors for the climate change debate. The participatory and community-driven approach to forestry development is potentially an effective vehicle for engaging indigenous groups in attempts to control emissions and reduce deforestation.Community Zoning Plans can help communities focus their development and conservation efforts while facilitating access to other donor and government programs. In this project, preparation of the Plans has helped communities secure financing from the Payment for Environmental Services Program and from NGOs. The appraisal and evaluation of community-driven development projects like this needs to take into account the economic viability of the forest management and income-diversification strategies that are promoted. The competitiveness of wood and forest products is an important consideration, as is the assessment of returns to forestry relative to other land uses. Attention needs to be given to the scope for promoting "green labeling": obtaining a price premium for timber and other forest products that have been certified as harvested in a sustainable manner.
P035751 | Community Forestry II (PROCYMAF II) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2009 | 2010 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/552121468056077220/text/554160PPAR0P001fficial0Use0Only1610.txt | http://documents.worldbank.org/curated/en/552121468056077220/pdf/554160PPAR0P001fficial0Use0Only1610.pdf | 8. Lessons 8.1 Improved stewardship of natural resources is probably the main contribution of community forestry in Mexico. Community forestry will not wipe out rural poverty in Mexico because the program is necessarily limited to communities with abundant forests and no land conflicts; and even in these communities incomes from forest activities will always make up only a small share of total incomes. Nor does it promise to reverse the declining supply and lack of competitiveness of timber in Mexico, because communities have been slow to affiliate horizontally and vertically, restricting the scope for reaping scale economies. Nevertheless, it is an important part of the broader effort to protect the natural resource base, because communities own over two-thirds of Mexico's forestland. By promoting zoning and forest management and conservation plans, the Procymaf projects provided a solid platform for the expansion of conservation and sustainable land management in a globally important ecosystem. The community zoning plans successfully sponsored by Procymaf offer a platform for developing synergies with the (well-funded, high-profile) schemes that are now paying for environmental services (carbon sequestration, groundwater recharge, soil erosion control). 8.2 There are no quick fmes f o r building community capacity and institutional arrangements to manage and conserve forests. Plugging technical and infrastructure gaps is easy compared to the work of building trust in communities who have been ill served by Mexican governments for decades. The hefty contribution made by Procymaf communities to training and investment initiatives, the broad-based participation in land zoning exercises and the significant survival rate of the forest enterprises established by Procymaf is the best evidence yet that the programs are building capacity and sustainable institutional arrangements. But there is still a long way to go in developing the business acumen that communities need to develop and exploit the niche markets for timber and non-timber goods and services. One way to reward community initiative in this respect would be to develop better schemes for certifying that timber is sustainably produced\. the lack of a price premium for certified timber in local and national markets limits the incentive for communities to harvest and process timber more sustainably. 8.3 It is important to embed support to individual communities within a broader framework that strengthens cooperation between communities and municipal and state governments and develops a network o professional expertise on forest-centered activities. f Although Procymaf has so far made little headway in promoting supply chain development centered on timber processing, from the beginning it emphasized the creation of regional fora which brought communities and state governments together to set priorities and discuss the allocation of investment resources. This framework helps to promote the development of the complementary infrastructure (roads, schools) that will help to make forest communities more viable. Equally important is the support that Procymaf has given to building up networks of accredited private sector professionals able to provide technical assistance to communities across the full spectrum of forest-centered activities (not confined to harvesting timber).
P035752 | Integrated Irrigation Modernization Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2004 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/176641474652798486/text/000020051-20140620083121.txt | http://documents.worldbank.org/curated/en/176641474652798486/pdf/000020051-20140620083121.pdf | Drawing from the ICR with some adaptation, the main lessons are:Modernization of irrigation infrastructure and on-farm technology improvements is a necessary but not sufficient condition to increase competitiveness in irrigated agriculture. Irrigation improvements need to be complemented with agricultural productivity enhancing activities and support to farmers and producers, particularly small ones, in the areas of organization, financial management, and commercialization. The complementary activities should also include technical assistance to farmers. In cases where a separate institution is responsible for implementation of complementary activities, as was the case with SAGARPA, the parameters of engagement and its commitment need to be established during project preparation.Careful design of the M mitigation measures need to be identifiedTo maximize project benefits for all groups, targeting mechanisms need to be put in place including eligibility criteria and special financing terms to small farmers and producers. Great care has to be taken at appraisal to ensure that the Bank's safeguard policies are not negated by ambivalence. In this case the Borrower was led to believe incorrectly that its own safeguard policies could substitute for the Bank's. To compound the problem the Bank did not adequately supervise safeguard compliance.
P035753 | NI HEALTH SECTOR II | Latin America and Caribbean | Nicaragua | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/907411474633636616/text/000020051-20140613063537.txt | http://documents.worldbank.org/curated/en/907411474633636616/pdf/000020051-20140613063537.pdf | Project interventions cannot be too scattered across a wide geographical area to have meaningful impact. In this case, project supported civil works and performance based management systems were concentrated in the same hospitals to optimize patient care. Testing alternative models of health care delivery can help identify the most innovative and cost effective approach. But if too many different approaches are being tested simultaneously, it can lead to scattered strategies, competing models, and increased supervision costs.Immediate goals of human resources development and financial management need to be linked to the higher project objectives of delivering quality health services in an equitable manner. Eg. excessive attention to cost-containment can undermine the project objectives of quality and equity.It is important to coordinate the different activities of project cofinanciers in the same sector to reduce duplication, enable greater synergy, and optimize results.
P035757 | POWER MAINTENANCE | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1995 | 1999 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/328801475075160203/text/000020051-20140529160407.txt | http://documents.worldbank.org/curated/en/328801475075160203/pdf/000020051-20140529160407.pdf | The lessons learned as a result of the disbursement and implementation delays are (i) to use less optimistic disbursement forecasts for projects with borrowers and implementing agencies that are new to the Bank; and (ii) to provide adequate hands-on training in procurement and disbursements (not just once, but as many times as necessary). Additionally, the Region noted that in the last year of the project, virtually all of the delays in the USAID grant implementation were due to the different computer systems used by the Bank's accounting and disbursement departments.In the face of unexpected and catastrophic accidents, as happened in May 1995 at the Gyumush Hydropower Plant, Bank flexibility in amending a project's legal agreements in a timely manner can significantly contribute to a project's satisfactory outcome, while allowing Bank funds to be redirected to meet the greatest needs.
P035759 | Public Finance Management Project | Europe and Central Asia | Turkiye | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/420681474896127360/text/000020051-20140612072552.txt | http://documents.worldbank.org/curated/en/420681474896127360/pdf/000020051-20140612072552.pdf | The overall design of this project was too ambitious. The larger components in this project, such as Customs Administration, public expenditure management, and tax administration, could each be a separate project. Maintaining commitment and implementation support across multiple agencies is difficult. The component which was most successful, Customs, had one primary responsible agency. Components should be designed so that limited counterparts are involved. Realistic assessments of commitment and implementation capacity during project preparation are critical.Projects with implementation issues should be downgraded to reflect those problems.
P035761 | Community Social Infrastructure Project | Europe and Central Asia | Russian Federation | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2004 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/433241474896007255/text/000020051-20140612104730.txt | http://documents.worldbank.org/curated/en/433241474896007255/pdf/000020051-20140612104730.pdf | Based on the ICR the key lessons are: (i) A multi sectoral project can be complex and challenging to implement. Designing of such projects requires a thorough assessment of the institutional capacity in the country. Where capacity is limited, there may be a strong advantage in limiting an investment that aims at infrastructure development and significant institutional change to just one sector. (ii) The demonstration effect of Bank projects on the government, particularly in terms of quality of construction and rehabilitation of infrastructure can be immense. The improved architecture, design and materials brought by the Bank project helped develop an understanding among local officials of the importance of quality and the linkage between quality, durability and consequent cost savings.(iii) The importance of making the design of regional projects consistent with the federal government reform agenda cannot be underestimated. In the current project, several critical institutional reforms could not take place as they were dependent upon changes in the Federal legislation and policies in health, education and water and sanitation sectors that did not take place.(iv) Instability of the project implementing and executing agencies can undermine project outcomes. In the current operation the federal implementing agency went through several reorganizations and the administration in the Novosibirsk oblast also changed twice.
P035762 | Financial Sector Adjustment Loan (FSAL) | Europe and Central Asia | Kazakhstan | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 1998 | 1999 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/731451474629538123/text/000020051-20140519073506.txt | http://documents.worldbank.org/curated/en/731451474629538123/pdf/000020051-20140519073506.pdf | The ICR suggests that some of the key elements of successful reform of the financial sector include: (1) denying insolvent enterprises access to banking system credit; (2) having government absorb the losses of non-performing loans it had directed banks to make, while giving the banks legal authority to work out the rest of their non-performing portfolio; (3) gradually easing entry of foreign banks over two to three years, while domestic banks are taking steps to become stronger and more competitive; (4) dividing banks into weaker and stronger groups, allowing stronger banks to engage in a wider variety of banking operations while they attain international banking standards, while restricting weaker bank's activities until they address their portfolio problems.
P035762 | Financial Sector Adjustment Loan (FSAL) | Europe and Central Asia | Kazakhstan | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 1998 | 2000 | PPAR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/928811511188993330/text/multi-page.txt | http://documents.worldbank.org/curated/en/928811511188993330/pdf/multi-page.pdf | LESSONs LEARNED 3.28 The project was successfully planned and implemented. It succeeded in transforming the financial sector which was dominated by the public sector banks to one in which the private sector banks played the predominant role. The project helped the adoption of prudent banking practices, which enabled some banks to gain international acceptance and recognition. The lessons pertain to the factors that were associated with the satisfactory performance on this project. 3.29 Political will to implement reforms is important for the success of reforms during transition as any weakening of the resolve to continue with the reforms will undermine the situation and prolong the hardships. The large scale closure of problem banks caused hardships in terms of staff layoffs and reduction in the services offered by the banks. The consistency of the political will proved crucial to the success of the program. 3.30 The autonomy, power, integrity and competence of the central bank to enforce discipline are key factors for any financial sector reforms. The central bank plays the most important role in setting standards, establishing procedures, undertaking monitoring of banks and taking action where necessary. These functions can most adequately be performed if the central bank has the independence, the integrity, the competence and the powers to undertake its job. 3.31 Separation of the non-performers (loans and banks) from the performers is useful. Kazakhstan segregated bad loans from good ones, bad banks from good ones, the more advanced from the less advanced. This helped the adoption of separate remedies for different categories of loans.
P035764 | Bridge Rehabilitation Project | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2004 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/838641474482140745/text/000020051-20140612104902.txt | http://documents.worldbank.org/curated/en/838641474482140745/pdf/000020051-20140612104902.pdf | For straightforward design and construction work (and in conditions of uncertainty), when implementing major construction programs, the use of demonstration sub-projects is recommended to speed-up later implementation; but, for more complex bridge projects it is important to obtain high quality designs before tendering for better cost effectiveness.Where the traditional way of designing and implementing projects is superceded by the introduction of Bank procedures, it is important to have special training initiatives to ensure ownership and understanding of the new technical methodology.
P035764 | Bridge Rehabilitation Project | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2004 | 2005 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/480181468107677565/text/324300rev.txt | http://documents.worldbank.org/curated/en/480181468107677565/pdf/324300rev.pdf | 5. Conclusionsand Lessons 5.1 The two projects reviewedhere were implemented during aperiodof significant political and economic instability andwere adversely affected by the financial crisis o f 1998-99, leadingto the cancellation o f various components ineach case. They both yielded positive benefits and, inthe case o f the Urban Transport Project, initiated a major process o f reform that i s still unfolding. The staff and officials associated with this project deserve credit for their ability to move the project forward so that the momentum o f reformwould be sustained well beyondthe end o f the loan. Some more specific lessons can also be drawn\. Formulationof DevelopmentObjectives, Inneitherthe urbantransport nor the bridge rehabilitation project were the objectives formally changed to meet the new situation after the financial crisis. Inthe former case the spare parts component had become redundant, six cities had dropped out and a major new trolleybus contract was canceled, while muchmore emphasis was placedon sector-wide reform. The latter case in tumplacedmore focus onthe Moscow component as opposedto the federalhegional component. Inboth projects the opportunityto modify the objectives was presentedwhen the restructuring proposals were sent for Board approval, and inboth cases this was not 15. See for example letter datedDecember2,2003 from Yu Roslyak, DeputyMayor, MoscowCity Government. followed-up. Ifthe projects been evaluated against the requirement(to be introducedin the 2006 financial year) to the effect that changes inobjectives must be formally approved at Board level, the rating for these projects would have beenless positive. 5.2 Need to budget sufficient Bank staff resources for projects with dispersed operations. Russia i s an enormous country and both projects had very widely-spread operations. The urbantransport project operated across 14 widely dispersed cities up to 1,500 miles apart, while the bridgeproject had operations scattered over an even wider geographic area. Modest budgetsprevented the task teams from supervisingthe project in situ. Thus the Bankwas forced to relyheavily on informationfrom the PIUS,which sometimes meant that inadequate attention was given to important local needs or concerns. The cities would have benefitedfrom more contact with Bank staff, while inthe bridge project the Bank reliedtoo much on the PIUand did not recognize from the outset that the regionalhighway authorities had some valid concerns that neededto be addressed. Future similar dispersedprojects inlarge countries needto givemore attention at project design stage to the adequacy o f supervisory budgets and practical guidance inhandling logistical management. 5.3 Covenant inconsistencies in the legal agreement. Cities inthe urban transport project were committed to undertake legal reforms which they didnot necessarily have the legal power carry out. Moreover, insome cases the conditionality of the covenants was either weak or open-ended. An example is\. Cities should take all the necessary measures to support the provision o f transport services byprivate individuals or companies.. .. The wording i s vague and cannot bemeasured. This condition i s also directly inconflict with the imperativeto increase cost recovery for public sector passenger transport companies. 5.4 Foreign exchange risk. With the onset o f the Russian financial crisis several cities inthe urbanproject andthe regionalandfederal components ofthebridge rehabilitation project hadto leave the project. The Bank's standard advice to client governments i s not to pass foreign exchange risk o f dollar-denominated loans to sub-national entities, whose revenue sources are limitedto domestic currency. This principle was compromisedin these projects on the insistence o f the RussianFederation Ministryo fFinance and ultimately ledto largecomponents o f bothprojects beingcanceled. 5.5 The primarylessons learned from these projects are that\. k Theformulation of realisticand measurableproject objectives is crucial and when there is a major restructuring of aproject, the task team should take the opportunity to review the original objectives in the light of the changed circumstances. k Banksupervision arrangements should be realistic and budgets should be higher whenprojects are decentralized or spread over a wide area involving more than one implementing authority. Project design should take this into account. k Covenantsshouldnot be imposed on authorities that do not have the legalpower to carry out the commitment. Weak or open-ended conditionality should be avoided and objectives should not be conflicting. P It is unwise to let local sub-national borrowers carryforeign exchange risk in unstable macroeconomic conditions, especially when their revenues are in local currency.
P035765 | HIGHWAY | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Transport | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/981151474637366304/text/000020051-20140602104645.txt | http://documents.worldbank.org/curated/en/981151474637366304/pdf/000020051-20140602104645.pdf | Overall road costs can be reduced by 50% or more compared to Soviet Period operations.Pooling equipment and renting it out to private contractors requires demand estimation. Selectivity in the types of equipment is necessary, if it is to be utilized at a level permitting commercial sustainability for the government-owned supplier.
P035768 | Social Investment Fund Project (SIF) | Europe and Central Asia | Armenia | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/133211474572843135/text/000020051-20140604052417.txt | http://documents.worldbank.org/curated/en/133211474572843135/pdf/000020051-20140604052417.pdf | In projects with multiple objectives, development impact can be enhanced through a focused approach, identifying the hierarchy of objectives and giving higher priority from the outset to key objectives.The time and skills needed to mobilize community participation tend to be underestimated, especially where existing community organization is weak, as it often is in the poorest communities. Communities that already have an active formal leadership and commitment to participation tend to benefit in terms of community development, while those that are passive tend to remain passive. Without a very strong focus in project design (including performance indicators) on capacity building and other requirements for sustainability, these aspects tend to be neglected in favor of physical implementation targets. Social fund projects should incorporate systematic ex-post reviews of samples of subprojects, to monitor effectiveness, efficiency, welfare impacts, and sustainability, as well as quality of works.Once a social fund agency has been established with a focus on technical engineering functions geared to rapid processing of infrastructure subprojects, it can be very difficult to shift its focus to less tangible outputs and longer term impacts.
P035770 | Pilot Reconstruction Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2006 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/441861475071563622/text/Azerbaijan-Pilot-Reconstruction-Project.txt | http://documents.worldbank.org/curated/en/441861475071563622/pdf/Azerbaijan-Pilot-Reconstruction-Project.pdf | As in the ICR:- emergency reconstruction operations should not be combined with broad sectoral policy reform efforts that require different kinds of interventions and institutional set-ups. -operations involving multiple donors must be carefully designed to allow for different agendas, financing arrangements, and funding timetables among donors. This is particularly important in emergency-type operations.
P035771 | FIRST CADASTRE | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/837031474574066953/text/000020051-20140618083805.txt | http://documents.worldbank.org/curated/en/837031474574066953/pdf/000020051-20140618083805.pdf | Based on the ICR the key lessons are: Cadastre projects need a long and sustained effort in preparation and implementation. There is also a need to give sufficient attention to financial sustainability on project closure. Modern technology is important but needs significant budgetary provision for maintenance.A unified cadastre system that is not tied to a sector ministry eases the necessary coordination process and avoids specialized interests or a focus on a particular sector at the expense of the other (eg.agriculture vs. urban properties). Building an adequate system of M&E (including baseline data collection) is not only essential to assess progress but also to make effective mid-course corrections during implementation as and when needed. M&E needs to be in place in advance of implementation and needs to include a focus on project outcomes and impacts.
P035775 | Transport Project | Europe and Central Asia | Estonia |  | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2006 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/188141474490479796/text/000020051-20140613071150.txt | http://documents.worldbank.org/curated/en/188141474490479796/pdf/000020051-20140613071150.pdf | The EU accession policy can play a catalytic role in accelerating institutional and policy reform in the region, especially through encouraging the attainment of road traffic safety and pavement upgrading standards.When loans are repaid at an earlier stage than anticipated it is important to ensure that appropriate provision has been made for ongoing routine expenditure, including maintenance.An internet forum can be an inexpensive and efficient way to exchange trade information and share specialist advice on transport and trade topics.
P035776 | Klaipeda Port Project | Europe and Central Asia | Lithuania |  | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2009 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/313861474648610171/text/000146597-20140619161448.txt | http://documents.worldbank.org/curated/en/313861474648610171/pdf/000146597-20140619161448.pdf | For projects involving building of containment facilities for dredged contaminants, the Bank needs to ensure that: (i) there is a comprehensive knowledge of a countryâ€™s laws and regulations vis a vis the Bankâ€™s own rules and guidelines. It can also include a binding agreement on the location of the facility prior to the Board approval or Effectiveness date; (ii) there is realistic time frame for effective consultation; and may precede by TA to tackle sensitive issues.
P035776 | Klaipeda Port Project | Europe and Central Asia | Lithuania |  | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2009 | 2010 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/293321468332358122/text/549020PPAR0P031IC0disclosed08131101.txt | http://documents.worldbank.org/curated/en/293321468332358122/pdf/549020PPAR0P031IC0disclosed08131101.pdf | 6. Conclusions and Lessons 6.1 Both ports have increased their competitiveness by combination o major f rehabilitationhpgrade o their marinefacilities with transformation, more radical than f foreseen in the Bank's forecasts, in the structure o their traffic. Klaipeda responded f effectively to unexpected loss of much of its transit trade by converting many of its facilities to better meet the needs of other traffics, national and transit, and has become mainly a national port. Szczecin-Swinoujscie was equally called upon to cope with significantly larger than expected reduction in its traditional (bulk) traffics, and it achieved a very rapid growth of new and more profitable container and ferry traffics despite links with its hinterland much weaker than in the case of Lithuania, due to their different histories in the last few decades. The new roles that the two ports carved out were fully consistent with both national and EU objectives, and indeed constituted important contributions to their countries? economic strategies. 6.2 The transformations described are major accomplishments of the new landlord port authorities which the two governments had created in the 1990s in accordance with their preferences for the ports sector. Both authorities successfully completed large-scale privatization programs, converting the subsidiaries that they inherited from previous integrated structures into independent, self-standing companies owned mostly by combinations of employees and investors. The port authorities have created a sound competitive environment for the operation of the companies and seen them respond increasingly well. 6.3 Taking advantage of the large improvements to the marine infrastructure brought about by the port authorities and the Maritime Office Szczecin, the private companies that were created in the ports, along with gradually increasing numbers coming to the port from outside, have been making rapidly growing investments in terminals and other service installations. At Klaipeda such investments already cumulate to some US$700 million equivalent; at Szczecin-Swinoujscie, very recent and current private investment on port lands already amounts to nearly US$lOO million equivalent. The investments made have often been important elements in attracting new traffics. Companies in Lithuania especially have had increasing experience of working in inter-modal groups, often involving also the national railways, to develop integrated packages combining infrastructure, equipment, operating practices, pricing and other aspects to win the business of major potential customers. 6.4 Besides improvements to navigational safety, the authorities responsiblefor port and water services have also strengthened environmental standards, particularly with regard to handling o ships? waste, and to minimizing oil spills, and their spread f when they do occur. In line with the emphases of EIAs developed in preparation of the World Bank loans, both ports have considerably strengthened the monitoring of their seabeds, of the extent of contamination in any area proposed for dredging, of the changes brought about by dredging, and of the effect of dredging operations on fish life and movements. Strict permitting arrangements have been sufficient to avoid attempts to dredge in seriously contaminated areas. But neither port has yet built facilities, such as were provided for in the World Bank loans, which would offer a long-term solution to the problem posed by contaminated sludge, and hence enable the ban on dredging in such areas to be temporarily lifted when and where highly necessary for instance in some ship repair facilities. Considerable progress has however been made on examination of alternative possible solutions, and it is pointing in both countries to use of chemical treatment capacity, as is now being built near Szczecin, for converting such sludge into material useable safely for road foundations and embankments. 6.5 The experience of these two projects suggests lessons that may be useful for the handling of other projects (not only ports) in four main areas. These are spelled out below. 0 Even in countries with comparatively high levels of education, technical assistance can be vital for efficient application of unfamiliar techniques or procedures. The Bank needs to make careful judgments on specific needs, defend those judgments strongly with higher-level country officials, and match concessions on any of them with appropriate compensatory actions to substitute for the assistance or reduce the need. 6.6 There is little doubt that the exceptionally smooth implementation of the Klaipeda project owed much to the very careful attention given by the Bank staff and government to preparatory studies, detailed engineering, selection of PIU staff, and related training. Grants in support of Klaipeda project preparation were mobilized from the Japanesefinanced PHRD fund and from the Netherlands. One minor element covered, for example, was assistance from three specialized trainers to help ensure adequate capacity for treatment of all the topics that would have to be handled by the PIU. In outlining its view of the overall experience of implementing the Klaipeda port project with the Bank, the Lithuanian Ministry of Transport and Communications gave special emphasis to the key role played by the PIU and the importance of the way it had been set up and trained. 6.7 There were, however, also occasions when Lithuania turned down the opportunity to receive Bank-financed technical assistance. In 2002, for instance, it convinced the Bank to drop provisions in the loan agreement regarding hiring of technical assistance on various management and financial subjects that the Bank's appraisal mission had considered important. The funds were diverted to civil works. But advice was still sought, though more from local sources. The port authority has itself commissioned studies2by national and international consultants on topics to which the Bank had drawn attention, including work that has contributed to current policy adjustments on land lease rates and incentives for landwarehouse redevelopment by lessees. 6.8 Poland has also adopted a selective approach to technical assistance. For instance, the SSSA accepted in 2006 the suggestion from the World Bank Warsaw Office to hire a Contract Engineer for the works at Grabowski Island (finally selecting a DanisWPolishjoint venture for the job), and it has stressed in this review the highly useful contribution made both directly for supervising execution of the contracts and indirectly for diversifying the experience of its own staff. On the other hand, the government did decide in 2000 to exclude from the proposed project and loan quite extensive technical assistance provisions that had been a reed between government representatives and the appraisal mission for the project! The only reference to technical assistance in the eventual loan agreement was for that on dredging management, which MOS was to hire for itself. Among studies produced (in Lithuanian language) are\. Lithuania Free Market Institute, 2005. Study of Port Management Policy\. Challenges, Ways, Decisions. Lithuania Free Market Institute, University of Klaipeda and Economic Consultation Research, 1995.Study of Klaipeda State Seaport's Economic and Social Impact for Klaipeda City and Region and the Lithuanian State. and Carl Bro and ERT group, 'I 2006. Study of Klaipeda Port Dues and Competitiveness On SSSA organizational matters, financial management, preparation of cost-based tariff, performance monitoring of port operators, and the process of divestiture of its remaining shares in the port operating companies, as noted inthe agreed Aide Memoire of the Appraisal Mission January 24 February 2,2000. S 6.9 The worries that therefore arise in retrospect are, first, that some of the weaknesses that manifested themselves in the execution of the Polish project arose specifically in areas that had been intended to be covered by the technical assistance and, second, that there is no evidence of other adjustments by the Bank (either within the loans or in its own support plans) to compensate for the absence of the technical assistance that its appraisal mission had considered essential. Indeed, some sections of the PAD retain
P035777 | Rural Land Titling & Cadastre Development Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2003 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/236291467986261763/text/ICRR14640-P035777-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/236291467986261763/pdf/ICRR14640-P035777-Box393183B-PUBLIC.pdf | The ICR lists the following lessons: Land administration interventions tend to be long and complex, involving a heavy investment in preparation; they tend to work best when there is a programmatic approach involving a series of investment projects, possibly with supporting policy-based operations. High level political support and direction is essential for any project that seeks to introduce fundamental reforms (such as land privatization), and from the start project teams need to realistically assess the political economy.When projects prove to be unworkable it is advisable to restructure as soon as possible. Expert consultants are often needed to advise on the procurement of the complex mapping and information technology typically applied to land administration; the Bank may not have the necessary skills in-house.
P035780 | Health Project | Europe and Central Asia | Lithuania |  | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/671181474577224463/text/000020051-20140618063249.txt | http://documents.worldbank.org/curated/en/671181474577224463/pdf/000020051-20140618063249.pdf | Continuity of relationships is important, particularly in an environment of low political commitment and institutional capacity. High rates of turnover of political and ministry leadership and personnel require greater efforts at consistency among Bank team personnel. Even in a relatively developed country, a variety of circumstances can complicate project design and implementation. Adequate attention must be paid to political risk and to the interests of a wide range of stakeholders. Too much complexity in project design reduces the chances of success unless these factors are carefully taken into account. A skilled and dedicated PCU can compensate for many other challenges and shortcomings in project design and implementation. Noting the existence of problems during implementation does not guarantee that those problems will be resolved. Both the Bank team and management, for example, commented during implementation on problems with the projectâ€™s structure and M&E arrangements, yet no one appears to have taken the responsibility to act on those observations.
P035781 | Rural Finance Project | Europe and Central Asia | Moldova | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/931491474635097375/text/000020051-20140607141149.txt | http://documents.worldbank.org/curated/en/931491474635097375/pdf/000020051-20140607141149.pdf | The project is a LIL and it is important that the lessons identifed by the ICR which are extremely relevant for the future sustainability of project activities are given serious attention in the design of the follow-on project. Five lessons from the ICR are repeated here. (i) Share Capital of RFC and SCA. For institutions like RFC and SCAs, establishing a sound capital base should be priority. Before expanding lending, capitalization of RFC and actions to mitigate the lending risks of RFC and the SCAs need to be taken; (ii) Donor Coordination. The abundance of donor funds, from a large number of different sources with different objectives, has undoubtedly led to higher operational costs and weaker budgeting and controls. To ensure sustainability and reduce reliance on donor funds, stronger coordination and cooperation between all participating agencies with clearly defined roles and responsibilities to prevent overlapping and duplication need to be assured; (iii) Introduction of Service Fees. While justifiable for the inception period, free training and free post-creation support services cannot be sustained indefinitely. After a certain period following establishment and licensing, SCAs should be required to pay an annual fee for the services of the SSB. In addition, continued technical assistance provided to SCAs should be fee-based. A portion of these fees payable to service providers could come from the lending margin of participating financial institutions, as was envisaged at appraisal of the project; (iv) Financing of RFC. When a subsidy provision is provided in the project for a financial intermediary, there should be a clear sunset clause with a specific financial target for the financial institution to adhere by and phase out the subsidy. Although intentions were good, the provision of an interest free subordinated loan to RFC lacked justification. This loan resulted in an implicit continuous subsidy to RFC, an undue advantage when competing with other financial institutions and unearned benefits to its shareholders. In the future, there may be sound reasons to provide additional subordinated loans to RFC to facilitate raising of funds on the market; however, such loans should be at customary lending terms in respect of repayment periods and interest. (v) Strengthening of the State Supervisory Body. Supervision and regulation of the State Supervisory Body of SCAs is critical for the sustainability of the SCA system. The ES adds the following lesson: The abundance of donor funds can also generate a sense of complacency and can weaken the will to become self sustainable quickly. Donors should be aware of this and should provide grant resources only when they are strictly required and not as a matter of routine.
P035783 | SIAULIAI ENVIRONMENT | Europe and Central Asia | Lithuania |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1996 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/247071474748719020/text/000020051-20140607141236.txt | http://documents.worldbank.org/curated/en/247071474748719020/pdf/000020051-20140607141236.pdf | Water demand estimates in a transition economy, is better based on "elasticity of demand", than on "affordability analysis". Given the uncertainties of water demand forecasts in transition economies, investments in water supply and treatment should be phased to avoid building significant overcapacity. Elimination of market distortions and price disequilibriums, can lead to higher than expected price increases in operations and maintenance"Twinning" is a low cost but effective method of teaching, training and networking to improve utility performance with mutual benefits to both parties.
P035783 | SIAULIAI ENVIRONMENT | Europe and Central Asia | Lithuania |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1996 | 2001 | 2003 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/813741468757014839/text/261130LT0PPAR.txt | http://documents.worldbank.org/curated/en/813741468757014839/pdf/261130LT0PPAR.pdf | Lessons 0 Participationinregional environmental forums can assist Bank efforts to synergize the policy agenda and external assistance. Regionally sponsored environmental initiatives in response to inter-govemmental action plans provide good opportunities for the Bank to 43. HELCOM. 2001. Baltic SeaEnvironment Proceedings Nos. 82A and 84; Baltic EnvironmentalForum2000.2nd Baltic State of the EnvironmentReport. 44. Lithuaniareceiveda Bank trust fund grantto address this issue, and more importantly,the optimizationo f management and ownership ofthe water companies. exercise its comparativeadvantage inleveraginginstitutionalreformthroughtargeted lending.When linkedwith grant funding from bilateraldevelopmentpartners it provides a powerful and influentiallobby for reform. 0 When extendingloans for water supply andwastewater treatment to new client countries or sectors, the Bank could usefullystart with minimalor emergencyinvestmentslinked to an institutionaldevelopmentpackagethat could be the start for a phasedinvestment program.The morerecently introducedAdaptable ProgramLoanwould havebeenan ideal initial lendinginstrumentinthis case as it would have allowedtime to develop refinedcriteria and argumentsto facilitate Governmentagreement to more appropriate infrastructure designs and investments. 0Inwater supplyprojectsa combinationofmastermetersandin-housemetersis more effective at enablingrevenue collectionthan in-housemetersalone
P035784 | Power Rehabilitation Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/358961474500949975/text/000020051-20140604043708.txt | http://documents.worldbank.org/curated/en/358961474500949975/pdf/000020051-20140604043708.pdf | Private strategic investors involved in recovery of the power sector must have sufficient clout to resist political power and vested interests, and derive their commercial interests from a sustained and efficient operation rather than short term political and "commercial" deals.In a complex political and institutional environment, government ownership of the project and enabling reform is critical for the success of the project.
P035786 | Lviv Water and Wastewater Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/157941474851811461/text/000020051-20140619080426.txt | http://documents.worldbank.org/curated/en/157941474851811461/pdf/000020051-20140619080426.pdf | 1. Strong resistance from the Borrower to hiring foreign firms for project management or otherwise can be a cause of significant delay in project implementation where it requires restructuring project design. Very high differences in remuneration between local staff (in this case, LVK staff) and foreign consultants can lead to tension or resentment, compromising the project outcomes. In the case of the Lviv Water And Wastewater Project, the removal of the requirement to hire a foreign utility operator to manage the project and replacement with advisory services from foreign consultants satisfied the Borrower and allowed the project to move forward. 2. Effective M&E systems should be designed for use by the Borrower and the implementing agency in tracking the outcome(s) of the project, not just for the purpose of Bank supervision. The Borrower itself needs to be sure of the value of M&E to help it manage a project, and not view it as merely a Bank requirement. This is especially so in cases, such as this project, where pre-existing data is lacking and/or of poor quality and tracking project outcomes is more challenging. 3. Under-qualified subcontractors can significantly delay project implementation. The Bank's standard bidding documents do not preclude pre-qualification, therefore an analysis of subcontractor qualifications is essential to avoiding this problem. In the case of this project, the necessary change in subcontractor contributed to a one year delay in implementation.
P035787 | Agroprocessing Development Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2000 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/242271474943066385/text/000020051-20140529210829.txt | http://documents.worldbank.org/curated/en/242271474943066385/pdf/000020051-20140529210829.pdf | (1) The World Bank should not provide lines of credit to be on-lent through state-owned banks. These are subject to too much political interference, and lack the same incentives as private banks to appraise and supervise loans adequately.(2) Institution-building, such as establishing a new project management unit (the TSU), is very difficult. Success depends on quality leadership, dedication of key staff, and building appropriate incentives within the organization to achieve its stated objectives.
P035802 | Municipal Development Project | Europe and Central Asia | Lithuania |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/994281474487009550/text/000020051-20140613084129.txt | http://documents.worldbank.org/curated/en/994281474487009550/pdf/000020051-20140613084129.pdf | The actual comparative advantage of the Bank in a competitive financial market environment should be assessed more objectively before making lending decisions.Institutional development and policy objectives must be supported by corresponding resources if their credibility is to be preserved.
P035805 | Municipal Development Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/763541474850216135/text/000020051-20140615100157.txt | http://documents.worldbank.org/curated/en/763541474850216135/pdf/000020051-20140615100157.pdf | Strong, sustained and pragmatic support by the government is necessary to bring reforms to the water sector. Through successful communication with water users, the government made it clear to them that it supported linking debt forgiveness with installing water meters, as well as cutting service and applying court proceedings in cases of non-payment of bills.Reducing unaccounted for water in a deteriorated network can be very difficult and only achievable over the long term. Increased water pressure, for instance, can lead to greater water losses. In the short term, if water supply is not constrained and before all the necessary network rehabilitation can be completed, the aim should be to achieve a 24 hour supply to all users thus increasing revenue. The long time is takes to recruit a private operator for a water project, either prior to project approval, or during implementation (as in this case), needs to be factored into project design.
P035806 | Agricultural Reform Support Project | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/322321474487029405/text/000020051-20140613090018.txt | http://documents.worldbank.org/curated/en/322321474487029405/pdf/000020051-20140613090018.pdf | The ICR has extracted a number of useful lessons from the experience with this project: It is crucial to have a careful and hard-nosed assessment of the health of potential PFIs, and to ensure rigorous monitoring of a credit-line program. The tender process should have included a more detailed prudential examination of the possible PFIs, given the poorly developed and rapidly changing state of the Armenian banking industry.It is essential for the government and contributing donors to agree upon overall strategy, target outcome, and coordinated approach to the reform of a national agricultural knowledge and information system. In the absence of this, the different actors tended to intervene on the basis of differing policy and strategic objectives, which caused confusion and a suboptimal use of scarce resources. The differences in institutional vision between the Armenian Agricultural Academy and its USDA technical assistance team on the one hand and the Ministry of Agriculture (MOA) on the other proved virtually insurmountable -- with the former envisaging a model patterned after the American Land Grant Universities and the latter a public-good service provider operating under the oversight of MOA. The project's research grant system should have been open to non-governmental institutions as well as to university and institute researchers. The latter focused mainly on technical issues which they considered important, to the relative neglect of economic and socio-economic issues facing small-scale farmers in an evolving market economy.It is unrealistic and premature to press ahead too quickly for user-financed extension services, in a setting where agriculture is predominantly a smallholder and subsistence activity, and where farmers are still learning how to be farmers and rural incomes are very low. The government should accept the responsibility, for the time being, of providing extension information and advice as a public good, even if it is contracted out to private providers.
P035806 | Agricultural Reform Support Project | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2005 | 2010 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/453991468005956033/text/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.txt | http://documents.worldbank.org/curated/en/453991468005956033/pdf/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.pdf | 6. Lessons (a) General Lessons 6.1 Given the large attitudinal shift involved in the agricultural transition, government officials and project staff needed substantial technical assistance and training before operations could be expected to succeed. Governments showed strong commitment to the preparation of the projects under review. Yet once the loans were approved, delays in declaring effectiveness were experienced for several of the loans, while during early implementation even staffs of the project units often did not fully understand how specific project activities linked to objectives. If this was true at the center, it was even truer in the localities where projects were implemented. Consultant services were not always used as effectively as they might have been (this was the case for credit operations in the Armenia ARSP and Georgia ADP). There was an attitudinal lag\. most government officials in the agricultural ministries still exhibited a command and control mentality with respect to agricultural development. 6.2 When the leadership of project implementation units was skilled and motivated and their staffs were well trained, project implementation generally proceeded smoothly once some experience with the Bank's procedures had been acquired. This was especially the case with project units for the Romania ASSP and Georgia ADP, whose performance improved rapidly once professionally adept managers were recruited to replace earlier political appointees. Similarly, the appointment of a technically trained person to manage a purely technical agency such as the Romania's ANCPI for the GCLR Project resulted in a rapid acceleration of project implementation. 6.3 In the complex and rapidly changing ECA environment, sound donor coordination was critical. The two Romania projects rebounded from a very poor start once the Bank and other members of the donor community began working together to help Romania meet the European Union accession requirements. Together they helped Romanians to take advantage of the grants-in-aid made available under the Community's special accession program for agriculture and rural development. 6.4 Where donor coordination was less sharp, progress was slow. Management of the land registration component of the Georgia ADP was, at times, complicated by conflicting donor expectations that proved hard to resolve. In Tajikistan, it took the Bank until 2003 to realize that if donors spoke with one voice to the government on land reform, it might create conditions more favorable for the farms that the project had restructured. (b) Lessons from the Sub-sectors Agricultural and agribusiness services 6.5 Farmers and rural business owners will respond enthusiastically to innovative technologies corresponding to their needs. Experience from the assessed projects showed that agricultural research and extension works best when it is consultative and demanddriven. In Romania, the competitive grant approach proved to be an excellent vehicle both for generating applied research findings and extending these to farmers. But, as Armenia showed, the competitive grant scheme can also lack the strategic focus needed to effect a comprehensive strengthening of agriculture research. To respond to farmers' needs, competitive research grants should be open to all applicants, including non-governmental organizations, universities, and government research institutes. For pure farm extension work, the financial sustainability of advisory services in a setting with many small, semisubsistence farmers can only be achieved if government acknowledges its responsibility to provide these citizens with appropriate and effective advice and information. This will probably entail some measure of subsidy given the low incomes of many of the clients; but that need not preclude use of private contractors to deliver the service. Land administration 6.6 The Bank's international experience with land policy issues has strengthened the design of projects in ECA; but there is no uniquely correct model for land administration or land reform and effectiveness depends on responsiveness to local conditions. Whether grounded in restitution (Romania), or in the granting of more or less equal allotments to agricultural workers and other rural residents (South Caucasus), or being limited to the transfer of usufruct rights only (Tajikistan), each program was designed to accommodate socio-political necessities in the aftermath of de-collectivization. In Tajikistan however the project design was overly ambitious and not tailored enough to the local circumstances. 6.7 It makes sense to adopt a unified approach to land administration. Cadastral and land recording/land registration services are both technology and information intensive. These two services need to be closely linked and preferably digitalized to increase efficiency and enhance access. The unified approach worked well in each of projects reviewed here that had a land administration component (Azerbaijan FPP and ADCP; Georgia ADP, and Tajikistan FPSP). Rural finance 6.8 With appropriate regulation, technical advice and staff training banks that lend to rural areas can operate sustainably. To realize the potential from scaling up commercial bank lending to rural areas, it is essential\. (a) to confirm that supervision and prudential regulation has been developed and can be effectively enforced; (b) to prequalify the banks deemed eligible to participate in tendering for loan proceeds, based on rigorous prudential examination; (c) to ensure rigorous monitoring of the credit program, with the assistance of international expertise if necessary; (d) to ensure that the terms, maturities and grace periods of loans are proportional to the expected returns and the estimated economic life of the investment; and (e) to allow intermediaries to administer credit reflows in accordance with their own terms and conditions. 6.9 The non-bank financial intermediaries have an important role to play in rural areas; but it is important to be realistic about their capabilities. There is a strong demand for locally-based credit facilities (such as credit unions) in rural villages, and for rural financial institutions that take credit. These institutions must be savings-driven and encouraged to diversify their loan portfolio rather than focus only on farm lending. Sustained, strong support in the form of training and supervision is required if they are to evolve into viable financial institutions. The volume of lending needs to keep step with the growth in management skills and savings mobilization among members (overly-rapid expansion in the Georgia ADP and ambitious targets in the Azerbaijan ADCP considerably stressed implementation of farmer credit programs in these two projects). In general, these projects have shown that small village-based credit cooperatives are not an appropriate mechanism for large-scale credit delivery.
P035807 | WELFARE REFORM | Europe and Central Asia | Latvia |  |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/735091474896862708/text/000020051-20140612134148.txt | http://documents.worldbank.org/curated/en/735091474896862708/pdf/000020051-20140612134148.pdf | Â· Adequate expertise and attention on the part of the Bank and the Borrower, to fully monitor IT components, are crucial if IT components are to be implemented successfully .Â· Public information campaigns can gain support for pension reform, especially at the beginning of the reform.Â· The implementation of modern management practices for social insurance operations can reduce costs and improve client satsifaction.Â· The pension reform process is improved by the implementation of actuarial models that allow officials to monitor current and future trends in revenues and expenditures.
P035810 | Consolidation Structural Adjustment Credit (CSAC) | Europe and Central Asia | Kyrgyz Republic | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2005 | 2006 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/866571474655992602/text/000020051-20140613053934.txt | http://documents.worldbank.org/curated/en/866571474655992602/pdf/000020051-20140613053934.pdf | The 2001 CAE on Kyrgyz Republic warned about overoptimism and the complex nature of the CSAC (see p.16, para.4.13). The failure of this operation underscores the need to better assess government's commitment to reform, to take into account country specific conditions, to choose the right instruments, and to keep the operation focused and simple.
P035811 | PSD 2 | Europe and Central Asia | Moldova | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/433421474566801475/text/000020051-20140613075048.txt | http://documents.worldbank.org/curated/en/433421474566801475/pdf/000020051-20140613075048.pdf | Management training programs and foreign internships can help firms in emerging market economies to increase their access to foreign markets, find more reliable suppliers, and forge joint venture partnerships.Management training programs should be tailored to the needs of participants. Managing directors are likely to find training of two to three months too long to be away from the enterprise, so it may be better to provide them with shorter courses on specific themes. In contrast, some line managers may be interested in much longer courses, especially in the application of new technologies.Internship programs designed to send managers from developing countries to host companies in developed market economies need to be based on a business-oriented rationale. Many host companies are unwilling to give the time needed to mentor a manager for two to three months without some business-oriented purpose, such as the prospect of a joint venture in a market that interests them.
P035813 | Agricultural Development & Credit Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/377351474563736437/text/000020051-20140615101503.txt | http://documents.worldbank.org/curated/en/377351474563736437/pdf/000020051-20140615101503.pdf | 1. Using a private third party as a cofinancer and thus a risk sharer as the manager of a credit program can have advantages, but there are also potential drawbacks. A private agency was selected through competitive bidding to coordinate the credit program. The arrangement included that the selected agency should put 20 percent of its own funds into cofinancing the credit program. The advantage was that the agency had an incentive to make careful decisions in approving credit applications and needed to monitor and provide technical assistance to borrowers. Repayment rates were 97 and 95 percent respectively for the Credit Unions and Borrowing Groups, and the average size of the loans was US$1000 for the CUs and US$370 for the BGs, indicating that farmers with low to modest incomes were also particpating. The disadvantages were/might have been that: (i) the agency, with its own finances at stake, might have an incentive to lend to larger farmers and enterprises (a risk which was not, in the event, apparent); (ii) risk of an overly top down and controlling approach by the agency as its own money is at stake (this occured at the start); (iii) risk of financial failure of the company and a hiatus in the credit program until another agency was appointed; (iv) delays in the procurement process before selection of an agency (occurred); and (v) the possibility in a high risk situation or country of getting no offers at all (nearly occurred and required tendering twice). Another risk was possible confusion, an implementation gap and credit defaults in the handover from the company to a government agency at the end of the project, though the ICR advises that this was not a major problem. Azerbaijan's experience would merit further review as an unusual case study in rural finance.(What is not clear in the ICR, and would have been a desirable discussion area, is why, after choosing the private cofinancer model for the first phase of the APL,, a decision was taken to hand over to a government agency for the second phase.)2. Overly complex projects may entail high Bank costs and risk lack of focus on individual components: The combined staff and ancillary costs of project preparation and supervision were US$1.6 million. The project was largely succesful in all three components, but not without high Bank costs. The ICR comments that there was a risk that individual components would not receive sufficient attention. Each of the three field components - land registration, rural advisory services and rural finance are distinctly different in staff staff skill needs, and are not infrequently treated as stand-alone projects. The option of splitting the project up into two or three projects, might have been considered in project design, although in the event, this project was finally successful. (The ICR mentions that Land registration will now be handled as a separate project).
P035813 | Agricultural Development & Credit Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2006 | 2009 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/453991468005956033/text/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.txt | http://documents.worldbank.org/curated/en/453991468005956033/pdf/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.pdf | 6. Lessons (a) General Lessons 6.1 Given the large attitudinal shift involved in the agricultural transition, government officials and project staff needed substantial technical assistance and training before operations could be expected to succeed. Governments showed strong commitment to the preparation of the projects under review. Yet once the loans were approved, delays in declaring effectiveness were experienced for several of the loans, while during early implementation even staffs of the project units often did not fully understand how specific project activities linked to objectives. If this was true at the center, it was even truer in the localities where projects were implemented. Consultant services were not always used as effectively as they might have been (this was the case for credit operations in the Armenia ARSP and Georgia ADP). There was an attitudinal lag\. most government officials in the agricultural ministries still exhibited a command and control mentality with respect to agricultural development. 6.2 When the leadership of project implementation units was skilled and motivated and their staffs were well trained, project implementation generally proceeded smoothly once some experience with the Bank's procedures had been acquired. This was especially the case with project units for the Romania ASSP and Georgia ADP, whose performance improved rapidly once professionally adept managers were recruited to replace earlier political appointees. Similarly, the appointment of a technically trained person to manage a purely technical agency such as the Romania's ANCPI for the GCLR Project resulted in a rapid acceleration of project implementation. 6.3 In the complex and rapidly changing ECA environment, sound donor coordination was critical. The two Romania projects rebounded from a very poor start once the Bank and other members of the donor community began working together to help Romania meet the European Union accession requirements. Together they helped Romanians to take advantage of the grants-in-aid made available under the Community's special accession program for agriculture and rural development. 6.4 Where donor coordination was less sharp, progress was slow. Management of the land registration component of the Georgia ADP was, at times, complicated by conflicting donor expectations that proved hard to resolve. In Tajikistan, it took the Bank until 2003 to realize that if donors spoke with one voice to the government on land reform, it might create conditions more favorable for the farms that the project had restructured. (b) Lessons from the Sub-sectors Agricultural and agribusiness services 6.5 Farmers and rural business owners will respond enthusiastically to innovative technologies corresponding to their needs. Experience from the assessed projects showed that agricultural research and extension works best when it is consultative and demanddriven. In Romania, the competitive grant approach proved to be an excellent vehicle both for generating applied research findings and extending these to farmers. But, as Armenia showed, the competitive grant scheme can also lack the strategic focus needed to effect a comprehensive strengthening of agriculture research. To respond to farmers' needs, competitive research grants should be open to all applicants, including non-governmental organizations, universities, and government research institutes. For pure farm extension work, the financial sustainability of advisory services in a setting with many small, semisubsistence farmers can only be achieved if government acknowledges its responsibility to provide these citizens with appropriate and effective advice and information. This will probably entail some measure of subsidy given the low incomes of many of the clients; but that need not preclude use of private contractors to deliver the service. Land administration 6.6 The Bank's international experience with land policy issues has strengthened the design of projects in ECA; but there is no uniquely correct model for land administration or land reform and effectiveness depends on responsiveness to local conditions. Whether grounded in restitution (Romania), or in the granting of more or less equal allotments to agricultural workers and other rural residents (South Caucasus), or being limited to the transfer of usufruct rights only (Tajikistan), each program was designed to accommodate socio-political necessities in the aftermath of de-collectivization. In Tajikistan however the project design was overly ambitious and not tailored enough to the local circumstances. 6.7 It makes sense to adopt a unified approach to land administration. Cadastral and land recording/land registration services are both technology and information intensive. These two services need to be closely linked and preferably digitalized to increase efficiency and enhance access. The unified approach worked well in each of projects reviewed here that had a land administration component (Azerbaijan FPP and ADCP; Georgia ADP, and Tajikistan FPSP). Rural finance 6.8 With appropriate regulation, technical advice and staff training banks that lend to rural areas can operate sustainably. To realize the potential from scaling up commercial bank lending to rural areas, it is essential\. (a) to confirm that supervision and prudential regulation has been developed and can be effectively enforced; (b) to prequalify the banks deemed eligible to participate in tendering for loan proceeds, based on rigorous prudential examination; (c) to ensure rigorous monitoring of the credit program, with the assistance of international expertise if necessary; (d) to ensure that the terms, maturities and grace periods of loans are proportional to the expected returns and the estimated economic life of the investment; and (e) to allow intermediaries to administer credit reflows in accordance with their own terms and conditions. 6.9 The non-bank financial intermediaries have an important role to play in rural areas; but it is important to be realistic about their capabilities. There is a strong demand for locally-based credit facilities (such as credit unions) in rural villages, and for rural financial institutions that take credit. These institutions must be savings-driven and encouraged to diversify their loan portfolio rather than focus only on farm lending. Sustained, strong support in the form of training and supervision is required if they are to evolve into viable financial institutions. The volume of lending needs to keep step with the growth in management skills and savings mobilization among members (overly-rapid expansion in the Georgia ADP and ambitious targets in the Azerbaijan ADCP considerably stressed implementation of farmer credit programs in these two projects). In general, these projects have shown that small village-based credit cooperatives are not an appropriate mechanism for large-scale credit delivery.
P035814 | Enterprise Development Adjustment Loan (EDAL) | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 2001 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/956411474562991083/text/000020051-20140529070909.txt | http://documents.worldbank.org/curated/en/956411474562991083/pdf/000020051-20140529070909.pdf | (i) It is important to build a consensus with all key players before moving ahead with major policy reform, as well as with complicated technical assistance. The government was not initially committed to the TA component, due to changes in personnel; a broader base of support would have reduced the influence of one individual. Parliament has put obstacles in the way of the mass privatization approved by the Cabinet. (ii) The results from policy reforms in transition economies are greatly enhanced by accompanying TA that trains key players in how to operate in the new environment. (iii) Questions about the quality of mass privatization in Ukraine and in other countries would argue in favor of carrying out research on this topic.
P035814 | Enterprise Development Adjustment Loan (EDAL) | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 2001 | 2001 | PPAR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/533691511189144974/text/multi-page.txt | http://documents.worldbank.org/curated/en/533691511189144974/pdf/multi-page.pdf | 6. Key Lessons Learned\n6.1 The first lesson, consistent with experience in other countries, is that combining\nstructural adjustment with a complex technical assistance component makes a project\ndifficult to manage. In this case, it has slowed the completion of EDAL I. The objectives\nof the TA component were sound\. to learn how to restructure and improve the\ncompetitiveness of firms swept up in the privatization process, and to test out methods of\nassisting them. The results and lessons are now emerging, and a majority are promising.\nBut the TA component might have been better designed as a separate project, financed\npartly by grants from other donors.\n\n\n11\n6.2 A second lesson is that early involvement of participants from a variety of\npolitical spheres-including the Parliament-might have improved the country level\nsupport for reform.\n6.3 Another lesson that emerges from this experience is that a large and ambitious\nproject can rally donors together to support it and coordinate their actions based on a\nsensible division of labor. In EDAL I and II, many policy reforms were required in\nsynchrony, with advice from many donors. Obtaining timely and intelligent TA in this\nmanner may prove difficult in future projects, but the Bank with its limited resources will\nhave to continue to rely on other donors. The largest of them have more staff in the\ncountry and some offer grant money and specialized expert services.\n6.4 A key lesson emerging from the TA component, which will be applied in the PSD\nproject, is the great value of training Ukrainians, both as consultants and within firms,\nwith each recipient of training in turn training others; this technique is establishing a\nnetwork of Ukrainians who can bridge the gap in understanding between Western\nconsultants and former Soviet managers. Other lessons include the feasibility of low-cost\nrestructuring of enterprises on a large scale with Ukrainians providing most of the\nconsulting advice under the supervision of outside consultants; the feasibility of turning\nsome bankrupt firms around through consultant assistance; the value of creating and/or\nstrengthening crucial professional associations; and the value of a battery of multimedia\ntraining courses, given by Ukrainians to large numbers of managers and high officials of\nprivatized enterprises, with Ukrainian firms serving as case studies.
P035821 | DISTRICT PRIMARY EDUCATION PROJECT II | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1996 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/799961474849212452/text/000020051-20140612095923.txt | http://documents.worldbank.org/curated/en/799961474849212452/pdf/000020051-20140612095923.pdf | This project made important contributions in showing:the power of strong government ownership of the various intervention strategies at all levels coupled with strong support from resident Bank professionals; the desirability of keeping the project design simple and focused: the core of this project -- district level changes in educational access and quality, measured by simple indicators -- made sense and allowed for focusing of efforts; the peripheral parts of the project (nonformal education for those too far from schools, mainstreaming the disabled, strengthening early childhood education programs, and distance education for inservice training) were barely reported on and may have been better treated in separate projects. the desirability of building local level institutions/channels to deliver services (block and cluster resource centers) supported professionally by existing entities at the district, state, and national levels;the positive impact of good analytical work during preparation coupled with the government's determination to foster change based on experience and field-based lessons;the contraversial nature of building international technical assistance into project loans in countries like India, which have a strong domestic skills base. In the end, the GOI decided to forego the use of DPEP international technical assistance. It would be useful to know why this decision was made and whether it had any impact on the quality of the Project and its implementation. If such technical assistance would have been useful but the decision was made because of its high expense relative to other inputs, there may be a strong case for finding ways of financing international TA outside of project loans.
P035823 | Protected Areas Management Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/253041474589748165/text/000020051-20140624160817.txt | http://documents.worldbank.org/curated/en/253041474589748165/pdf/000020051-20140624160817.pdf | The experience of this project suggests the following lessons:The time required for innovative and transformational projects should be properly reflected at the design stage. In this case, a five-year stand-alone project provided insufficient time to allow the social learning and institutional cultural changes to occur to cement the operation's conservation goals and their sustainability. The Borrower's comments in the ICR stated that: "The process of community organization for participatory natural resource management is highly sensitive, complex and lengthy" (pages 34 - 35). Sustained commitment at all levels of Government and among all stakeholders is needed to realize the full potential of initial gains made in terms of community involvement and the development of social capital. The need to ensure the realization of sustained PA management requires secure, long-term financial resources in order to be dependable and realistic. The establishment of an operational endowment fund should have been given a higher priority from the beginning of the project. This would have allowed time for the endowment fund to grow and thereby honor the promises made to local communities that, if they refrain from unsustainable, destructive activities (e.g., hunting and fuelwood collection) within PAs, they would receive other economic benefits in exchange.Adequate attention to M&E design and implementation is especially important for projects testing new methods or modalities that may serve as models for replication in other locations, such as this project did with its co-management approach to PA management. It is imperative to have a robust and sound basis for data analysis on measured outcomes and impacts in order to make a compelling case for (or against) using that innovative method elsewhere.
P035824 | Diversified Agricultural Support Project (DASP) | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/900201474512599251/text/000020051-20140612152541.txt | http://documents.worldbank.org/curated/en/900201474512599251/pdf/000020051-20140612152541.pdf | Use of an independent agency for monitoring and evaluation improves quality and timeliness of reporting, contributing significantly to user feedback and effective project monitoring and management.Good market linkages and private sector involvement are necessary if farm incomes are to be raised.Administrative and financial decentralization need to occur together to be effective.Early and adequate training in financial management for project staff and concerned staff of implementing agencies/departments, is essential in view of the time required to absorb and apply these skills.
P035825 | STATE HEALTH SYS II | South Asia | India | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/124411474596546628/text/000020051-20140612153010.txt | http://documents.worldbank.org/curated/en/124411474596546628/pdf/000020051-20140612153010.pdf | Appropriate selection of indicators to be monitored is critical for useful feedback during project implementation.Recognition of the role of the private sector/NGOs and their incorporation into work with the State Governments can make health care much more accessible.A framework supporting referral from primary health care to first level referral hospitals can significantly improve the allocation of health care resources.
P035827 | Women & Child Development | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/286331475092075471/text/India-Women-Child-Development-WCD.txt | http://documents.worldbank.org/curated/en/286331475092075471/pdf/000020051-20140615114717.pdf | The ICR draws the following general lessons:A. The Bank and the government should agree on the timing of government approval of a Bank-assisted project. The Bank should not go to the Board before the Cabinet approves the project proposal, so that the project can become effective soon after Board approval. B. Lessons learned from previous projects, both positive and negative, should be rigorously analyzed and applied to the subsequent project design, and a new initiative should be pilot tested on a small scale. The health and nutrition aspects of the ICDS program have not been adequately implemented under the current project due mainly to the one worker and one helper model of the AWC, although alternatives have been demonstrated in other projects. Also, this project, like ICDS I and II projects, suffered from serious problems with project funds release, procurement, and disbursement. GOI and the Bank should have anticipated such problems since this project was a third operation of the same nature and modality in the same WCD sub-sector but on a larger scale. C. The quality at entry of the project profoundly affected efficiency of project implementation. The inclusion of a nation-wide training component without proper appraisal and the lack of defined monitoring and evaluation indicators at negotiation delayed the start-up of the project and adversely affected the subsequent project implementation processes. Baseline data should be collected early so that it can serve as a basis for preparing and agreeing on Project Implementation Plans. E. In addition to input and process indicators, more output indicators (e.g. proportion of mothers who changed their child caring behaviors) should be used, so that the input and process indicators can be more persuasively linked to project outcome indicators. F. The weak financial management and disbursement documentation were important causes of project implementation delays. Some audit disallowances have still not been resolved. An in-depth review of the processes, streamlining them, and making arrangements for training of local staff in these aspects are essential before continuing with another Bank operation. G. A specific investment project is not an optimal tool for meeting the varied needs and capacities of different states in a large federated nation as India. Once the Government's project preparation and implementation capacity is increased and experience accumulated, a program loan approach would be preferred with different roles played by the central government, states, and the Bank.
P035828 | Conservation and Sustainable Use of Medicinal Plants Project | South Asia | Sri Lanka | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/688131474561888499/text/000020051-20140613044112.txt | http://documents.worldbank.org/curated/en/688131474561888499/pdf/000020051-20140613044112.pdf | It is important to build a broad national constituency for biodiversity conservation projects that cut across traditional ministerial boundaries before project approval. This becomes imperative when some elements - such as medicinal plants - may appear irrelevant to western-oriented health agencies.Do not substitute external expertise for deficient local capacity at the central and local levels. Paying inadequate attention to building and sustaining in-country capacity undermines project ownership and adversely affects outcomes.Monitoring and evaluation needs to be comprehensively tailored to all project objectives and components - a standardized approach may only yield only partial results.
P035914 | CYCLONE REHABILITATI | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1994 | 1998 | 1998 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/960341474895356060/text/000020051-20140516161127.txt | http://documents.worldbank.org/curated/en/960341474895356060/pdf/000020051-20140516161127.pdf | The main lessons are as follows: (i) successful implementation of emergency recovery projects hinges on the responsiveness of the project design to Government's expectations and population needs; (ii) sustainability of works in a country subject to frequent cyclone damage call for early agreements on arrangements to ensure future operation and maintenance of infrastructure work; (iii) up-front commitments to rapid procurement are key; and (iv) early agreements on the overall reconstruction strategy and plans for donor co-ordination are essential.
P035915 | Transport and Urban Infrastructure Project | Western and Central Africa | Guinea-Bissau | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/613841474664542666/text/000020051-20140602113314.txt | http://documents.worldbank.org/curated/en/613841474664542666/pdf/000020051-20140602113314.pdf | Projects that are re-started at the end of the war/conflict need to be re-appraised or restructured to respond to new circumstances and conditions. Firm commitment from all donors prior to signing or effectiveness is necessary for successful completion of the project.Bank supervision team needs to work closely with the project implementation agency to avoid procurement problems. Procurement irregularities can be eliminated if procurement audits are done after the first year of project implementation.
P035917 | Mulanje Mt. Biodiversity Conservation Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2008 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/764151474906585485/text/000020051-20140619112318.txt | http://documents.worldbank.org/curated/en/764151474906585485/pdf/000020051-20140619112318.pdf | Among the useful and more widely applicable lessons that can be drawn from this project are the following: 1. The institutional framework and supporting policies should be designed such that accountability is clear to all stakeholders and lies where there is both sufficient capacity and commitment. This project supported an NGO (MMCT) with the capacity to finance conservation of MMFR, but for which it was not accountable. Conversely, the Government's Forest Department was accountable for management and conservation of MMFR, but did not have the commitment and institutional capacity to carry out these functions. As a result. while MMCT was able to achieve some positive results, it was ultimately unable to effectively address the challenges faced by the Reserve during the project period. 2. Community involvement is as important as park management. Efforts to promote alternative livelihoods and more sustainable natural resource use by communities in protected area buffer zones may often be as important as improved park management per se for achieving local biodiversity conservation objectives. Early, intensive, and continuous engagement of local communities should be a core element of any future project carried out under similar circumstances. 3. Endowment Trust Funds need to be carefully sized and management agreements thoroughly vetted before project approval. ETTs can be a useful mechanism for establishing long-term financial streams and attracting other partners to support conservation objectives at particular localities of high global environmental significance. But their size and management need to be carefully established up-front, including adequate attention to potential down-side economic/financial risks, and closely monitored. Complementary sources of funding, including other donor assistance, may be needed over the short and medium terms until such Funds can achieve full self-sufficiency as sustainable stand-alone financing sources. 4. Country-based supervision has advantages for environmentally sensitive projects when local institutional capacity is weak. This is especially likely to be the case when new institutions and/or implementing agencies previously unfamiliar with Bank procedures are involved and/or when serious institutional conflicts that adversely affect implementation emerge as was the case with the present project. Supervision budgets also need to be sufficiently flexible to permit adaptive management on the Bank's part when required.
P035922 | ERC III | Eastern and Southern Africa | Mozambique | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1997 | 1999 | 2000 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/993331474596972987/text/000020051-20140526222358.txt | http://documents.worldbank.org/curated/en/993331474596972987/pdf/000020051-20140526222358.pdf | The Bank's experience with the TERC offers four lessons of broad applicability. First, the HIAL approach to simplifying and front-loading conditionalities prior to effectiveness does lock-in ownership and ensures flexibility. These approaches have already been applied to other HIAL countries in the AFR region. Second, a sequentially-designed program of assistance with serial operations allows the Bank and borrower to pursue a critical path of reform over long periods of time. Third, forging and sustaining a critical path will require institutional knowledge on the part of the Bank and borrower. This requires continuity of staffing in the Bank and counterpart agencies, as illustrated by the TERC. Finally, a high quality ESW (diagnostic) program helps identify points of entry (for microeconomic reforms) that could produce important gains in macroeconomic performance.
P035923 | ZA-GEF Cape Penninsula SIL (FY98) | Eastern and Southern Africa | South Africa | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/211221475079203395/text/000020051-20140614184917.txt | http://documents.worldbank.org/curated/en/211221475079203395/pdf/000020051-20140614184917.pdf | Principal lessons from the project were: The Cape region is world renowned for its biodiversity and there are a large number of local parties with strong interests in maintaining the biodiversity. Where a program is to operate in a region of this type it is important to (i) create stakeholder buy-in and commitment to implementation at the outset; (ii) use limited resources to catalyze projects and leverage other sources of funding; and (iii) where possible, align agencies and programs.
P035923 | ZA-GEF Cape Penninsula SIL (FY98) | Eastern and Southern Africa | South Africa | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2010 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/674831468115470197/text/527930PPAR0P10101Official0Use0Only1.txt | http://documents.worldbank.org/curated/en/674831468115470197/pdf/527930PPAR0P10101Official0Use0Only1.pdf | LESSONS 67. I n countries where the World Bank does not have an active lending program, it may consider the benefits o f implementinggrant financing from the Global Environment Facility, if available, in a manner that integrates global environmentaland poverty alleviation objectives. Landscape restoration activities, such as invasive alien clearing, offer opportunities for both conservation o f native flora and fauna and j o b creation and entrepreneurial skills development, if the project i s designed to target disadvantaged communities. If designed correctly, members o f communities trained to clear IAS in key biodiversity sites can also engage in annual maintenance, however recurrent funding is required and few countries apart from South Africa have yet to assign a high national priority to the activity. 68. Efforts to restore native flora and fauna should take into account both the level o f public awareness and competingpublic values concerning invasive alien species. Biodiversity values will need to be balanced against other public use values such as recreation, as in the case o f the decision to remove the pine trees from Table Mountain National Park. A decision to eradicate one alien species in favor o f another native one such was the case concerning the removal o f the Himalayan tahr in favor o f the Klipspringer should be vetted publicly and options other than eradication should clearly be considered. Public consultation and consensus building campaigns can help to determine the optimal level o f eradication o f local flora and fauna that will benefit the biodiversity agenda and secure community support for local conservation efforts. 69. Projects that finance research, whether basic o r applied, should include a mechanism to adapt research findings into ongoing implementationo f complementary project activities. A heavy investment was made in invasive alien species clearing and rehabilitation, both through a subcomponent o f this project and through several applied research grants funded by the Table Mountain Fund. This research was published and disseminated, but not systematically incorporated into the ongoing overall program. A mechanism was also needed to channel information arising from implementation to update the Table Mountain Fund's grant proposal processes t o align it with program needs i.e. so that the Fund could effectively serve as a think tank for on-the-ground project implementation. 70. Managing a small grant mechanism for biodiversity conservation requires an investment in project development to assure that the fund as a whole i s geared toward achieving its programmatic (and landscape) goals. Project development necessarily involves thinking about partnerships, often at the design stage, since the right combination o f actors will be needed to apply and adapt research beyond the small pilot applications supported by a fund such as the TMF. A range o f partners should be brought into the project development process, including local land use decision makers in the government and/or conservation agencies, community based organizations and NGOs that can provide follow-on resources, universities interested in furthering the research aim, donors, and the private sector. Since applied research will need to be adapted and scaled-up, getting buy-in from those key constituents that are charged with land-use decisions up-front can help t o prioritize grant approval processes and can contribute to enhanced sustainability o f the outcomes o f successful interventions.
P035991 | ERAC | Western and Central Africa | Togo | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1999 | 2000 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/924331474893601553/text/000020051-20140526205639.txt | http://documents.worldbank.org/curated/en/924331474893601553/pdf/000020051-20140526205639.pdf | This was the third successive adjustment operation for Togo to be rated unsatisfactory. The Bank should have had firm confirmation of broad ownership of the reform program before proceeding. A new government in itself is not adequate assurance that a reform program can be implemented. Simply disbursing funds in such cases is not ultimately helpful to the country. With a poor track record, ownership should be tested with a tightly focused program with floating tranches.
P035995 | JO-EXPORT DEVELOPMENT | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2000 | 2001 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/982831474571987549/text/000020051-20140529165741.txt | http://documents.worldbank.org/curated/en/982831474571987549/pdf/000020051-20140529165741.pdf | At the design stage, project stated objectives, components and performance indicators should be consistently linked. The principal objective of export development has no clear link to the use of the credit line in the absence of effective targeting of the sub-loans to the export sector.
P035996 | Education and Health Rehabilitation Project | Middle East and North Africa | West Bank and Gaza |  |  | Human Development | Education | SPF | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/711611474628336727/text/000020051-20140607143113.txt | http://documents.worldbank.org/curated/en/711611474628336727/pdf/000020051-20140607143113.pdf | Â· The key to a successful project in a post-conflict context, with newly formed and inexperienced government agencies is to establish a simple project with modest goals and spell out staffing requirements, responsibilities and implementation steps in considerable detail.Â· For technical assistance to be available when and as needed, agencies must be very clear about their needs and absorptive capacity. Also, the parameters for TA must be clearly spelled out, to avoid the creation of parallel management structures and to ensure that the beneficiary develops its own implementation capacity. Â· Integration of implementing units into ministries regular activities and continuity of staff are essential for sustaining capacities created by a project after the project has closed.
P035997 | JO-SECOND TOURISM DEV. | Middle East and North Africa | Jordan | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/944751474508743251/text/000020051-20140613084842.txt | http://documents.worldbank.org/curated/en/944751474508743251/pdf/000020051-20140613084842.pdf | The ICR highlights several lessons including:Take account of political reality. The complexity of the local political environment should be well understood at appraisal and adequate allowances should be made for its complexity in project design and during implementation.Make certain that all stakeholders subscribe to the reform agenda. The capacity of key participating agencies and their commitment to core project objectives - both prior to and during project implementation - should be accurately gauged. PRA and DOA seem to see their role mainly as custodial but were being asked under the project to undertake developmental, managerial and service delivery tasks - which they were and still are ill-equipped to perform. In addition, the professional incentives faced by the leadership of these organizations are also not always in line with protecting the park and its environs.Build consensus on action plans. A clear consensus should be established with the counterpart agency on the need for and relevance of strategic planning and programming and also to ensure that the agency has the will and capacity to undertake the task effectively.
P036004 | Montreal Protocol Reduction of the Consumption of Ozone-Depleting Substances Project | Latin America and Caribbean | Uruguay | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1995 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/980021474506813988/text/000020051-20140607170627.txt | http://documents.worldbank.org/curated/en/980021474506813988/pdf/000020051-20140607170627.pdf | In a small country like Uruguay, and with an umbrella program such as the GEF funded ozone activity, consideration might be given to reducing the number of individual agencies pursuing overlapping sub-programs.
P036007 | Environmental Management Project | Latin America and Caribbean | Trinidad and Tobago | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/979341474502296995/text/000020051-20140604045121.txt | http://documents.worldbank.org/curated/en/979341474502296995/pdf/000020051-20140604045121.pdf | The importance of credibility with the public. This leads to two main lessons: the need for regulatory agencies to demonstrate quickly their ability to enforce environmental laws that will address some of the expectations and engender public confidence; the value of strengthening the legal framework in advance, including bringing forward preparation of enabling legislation and related related requirements as an integral part of the preparation process.
P036007 | Environmental Management Project | Latin America and Caribbean | Trinidad and Tobago | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1995 | 2001 | 2003 | PPAR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/485311468777245838/text/multi0page.txt | http://documents.worldbank.org/curated/en/485311468777245838/pdf/multi0page.pdf | Lessons Learned 4.9 The project design was weak in having no environmental improvement goals, leaving the project with open-ended institutional objectives and insufficient purpose. Specific and monitorable development objectives are a strong incentive to effective project implementation. Also, generating support for environmental management would have been easier if the project had included specific environmental objectives that included tackling some of the acknowledged environmental issues. A commitment to at least starting on some critical environmental rehabilitation work, as a condition of Bank involvement, would have given the project some much-needed impetus and greater impact. 4.10 Justification for Bank involvement in the institutional groundwork of such a longterm process as environmental management should be built on a clear understanding between the parties and a commitment by the Bank as to continued assistance. The failure to follow-up with a related operation, for whatever reasons, has weakened the value and impact of 27. The Caroni River has long been a catalyst of environmental concem. In 1959 a commission of enquiry on pollution of the river, led by Justice Blagdon, recommended the establishment of an agency to manage environmental matters. 28. Competing priorities and concems are public safety and the crime rate, corruption, employment and social services, education and a series of close elections resulting in frequent govemment changes or, as most recently a tie and a constitutional impasse. The record of the heavily attended 1997 National Consultation on Sustainable Development listed the following priorities\. Human Development, Human Welfare, Planning and Resource Management, Governance, Pollution, and Management and Mitigation of Natural Hazards. But the first five issues listed provide another insight to the prominence of environmental concems in the conference proceedings\. Poverty and underemployment, Land use, Exploitation of wildlife, Health, and Waste Management. 29. As in many ICRs, significant points such as this one raised by borrower in their ICRs, or in comments on the Bank's ICR, are seldom explicitly addressed by the Bank's ICR. This failure to complete that loop reduces the value of the borrower's contribution and can give the impression that the borrower's views are not given full consideration in the ICR process. the Bank's role in the initial institution-building phase, which was only the starting point of a long process. 4.11 EMA should be located in a neutral part of the government structure, or even outside it, where there is no possibility of a real or perceived conflict of interest arising in its environmental activities. It should be more detached from the day-to-day political scene where its decisions can be based on technical and economic considerations without political factors intruding. Outlook 4.12 Much has been achieved in putting in place new organizations for environmental management (EMA, the Environmental Commission, the Green Fund, and the Special Environmental Police unit) and introducing some of the required institutional rules of the game for EM (the EM Act and some environmental laws), but there are substantial issues needing attention if the EM system is to be able to accelerale to full effectiveness. At the moment EM is coasting along at a comfortable pace, without noticeable impact on major environmental issues. Some knowledgeable environmentalists are skeptical whether the recent institutional efforts will actually yield significant environmental benefits. There is a general belief in such circles that there is less than fully earnest efforts being made in important areas of concern, and this impression needs to be corrected. A determined effort to act on correcting past environmental problems, as policy suggests is intended, is a high priority. The current environmental situation requires an extended period of vigorous activity by EMA and others to make up the backlog of concern on pollution and conservation issues before a steady state of environmental management to the benefit of all is achieved. It is to some extent too early to know whether political will, public support, and institutional resources are sufficient to make a real difference to Trinidad and Tobago's environmental status.
P036011 | KLAIPEDA GEOTHERMAL | Europe and Central Asia | Lithuania |  |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/387741474856815192/text/000020051-20140612071959.txt | http://documents.worldbank.org/curated/en/387741474856815192/pdf/000020051-20140612071959.pdf | The Bank and the Borrower should ensure extensive oversight over design and implementation to minimize technical problems, especially in pioneering and demonstration type of projects. Enforcing contractual arrangements is likely to be difficult when ownership of public utilties changes hands, and in the absence of laws that govern legal obligations between contracting parties, whether they are public or private entities.
P036013 | RAILWAY REHABILITATION | Europe and Central Asia | Romania | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2004 | 2004 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/127451474628378769/text/000020051-20140612131552.txt | http://documents.worldbank.org/curated/en/127451474628378769/pdf/000020051-20140612131552.pdf | In projects with significant institutional development or restructuring objectives, the supervision needs to be much broader than just the review of the progress of project components. Supervision missions need to become review and consultation meetings to guide the process towards the shared objectives between the client and the Bank. For effective implementation, the Bank sometimes needs to increase supervision intensity. The restructuring projects should not be spelled out in detail far in advance, but a carefully formulated mission statement and mandate is needed. If there are specific targets, they should be reviewed and revised from time to time.
P036013 | RAILWAY REHABILITATION | Europe and Central Asia | Romania | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2004 | 2006 | PPAR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/913231468332659846/text/326880rev.txt | http://documents.worldbank.org/curated/en/913231468332659846/pdf/326880rev.pdf | 5. Conclusions and Lessons StrongAdvisory Role of the Bank 5.1 The Bank's strong advisory support role duringthe implementationphase o f IRIS was key to the successful completion o fthis project component and should be replicated insimilar projectsinthe future. Thistimely andeffectiveinterventioncoupledto the Borrower's strong commitment ensured the project was a success. The close attention to facilitating the resolution ofmisunderstandings and givingexamples o f successful projects elsewhere also contributed substantially to the outcome. Increase Usage of IRIS 5.2 Although IRIS has been implemented, it is not yet fully used. To ensure that it reaches its full potential, additional training for middle andupper management staff o f Calatori andMarfawill be required. Impressingoperating companies' managers o fthe benefits o fmore fully usingthe system should ensure maximum use. The management training and development component o f the forthcoming Transport RestructuringProject will strengthen railwaymanagement training substantially. 5.3 Itis also necessaryto ensurethat informationalready available from IRIS is includedinconcise reports givento railway management. Highlightingrelevant data outputs inthis way and bringingthem to the attention o f the responsible staffon a timely basis will help ensure better use o fthe data system. Improve Traffic Costing Capability 5.4 The operating companies needto strengthen their traflc costing capability. This may take the form o f an interimcosting system prior to the full implementationo f IRIS andOracle that would have the capabilityto estimate costs ofoperating specific services on a route-specific basis. Re-evaluate the Method for Allocating Electric Power Costs 5.5 There i s still some element o f cross-subsidy between freight andpassenger service, particularly inthe areao f allocation o f electric power costs. This causes a distortioninthe market mechanism. A more appropriate distribution of eZectricpower costs is neededone which results inpayments equivalent to the activity levels o f each area o f service. PSOSubsidies to be Service-Specific 5.6 Public Service Organizationsubsidy payments made to CFR Calatori are based on estimated revenue shortfalls compared with costs to providepassenger services, with the constraint o f available funds from the Ministryo f Finance. While this i s consistent with the objectives o fthe project, the PPAR mission considers that infuture, the PSO subsidy should rather be adjusted to support speclfic services that the government considers socially necessary. A service-specific subsidy would ensure that government subsidy funds are supportingonly those services that require such support with the remainder o f services either commercially viable or abandoned. However, this can only be implementedwhen a traffic costingsystem is inplace to evaluate specific services and/or routes. 5.7 The following lessons may be drawn from the experience o f this project\. 0 Policy changes are more likelyto be implemented successfully when Bank support i s providedjust at the time when public entities have committed to the process of commercialization,and supportive sector-wide reforms are being put inplace; 0 Where railway companies are movingtoward commercial operation, their long-term financial healthneeds to be assuredby rationalizing subsidy support andintroducingan appropriate costing model; 0 A critical success factor ina complex task such as the installation o fan integrated management system i s that sufJicient technical supervision and support must be available to assist with resolvingproblems as they arise; 0 Maximizingthe benefits o f a complex informationsystem requires that middle and upper level management see and understand the benefts o f usingthe system. Extensivetraining is important; 0 Public Service Obligation Subsidy should be for specific services that the government considers socially necessary; such services shouldbe transparent, explicitly defined and fully compensated as part o f a Contract Plan. 10.For example, recent studies (Railway Modernization Project of Bucharest ConstantaLine; Management Assistance and Institutional Development Requirements, Interim Report #2; August 2004) have demonstratedthat, based on a proposed costing system format, intercity services probably meet their operating costs from revenues; and these services should be designated as commercial and should not be part of the subsidy. Other passenger services couldbe defined as social services and would be supported by the PSO subsidy payments.
P036015 | IMPR FIN REP & AUDIT | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/829951474908751828/text/000020051-20140613080710.txt | http://documents.worldbank.org/curated/en/829951474908751828/pdf/000020051-20140613080710.pdf | As noted in the ICR, more advance work must be done to assure the support of multiple stakeholders, especially when vested interests are threatened. In addition, policy changes that affect vested interests may need to be supported through the overall country dialogue as well as single projects. - Keep projects simple, particularly in countries with low institutional development capacity. - Be more realistic on implementation time, especially for institution building projects.
P036030 | BIODIVERSITY RESTORA | Eastern and Southern Africa | Mauritius | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1996 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/205371475088970819/text/000020051-20140612062315.txt | http://documents.worldbank.org/curated/en/205371475088970819/pdf/000020051-20140612062315.pdf | There is as much to learn from failure as from success, as illustrated from the experience at Round Island, where trial and error led to a fuller understanding of how the ecosystem of the island can be restored. Collaboration between an NGO and public entities benefits from being clearly spelled out, and is best organized through the use of a formal memorandum of understanding.
P036037 | 3A-GEF WIO Islnds Oil Spl Con SIL (FY99) | Other | Africa |  |  | Infrastructure | Energy & Extractives | GEF | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/646901475073748617/text/000020051-20140613031452.txt | http://documents.worldbank.org/curated/en/646901475073748617/pdf/000020051-20140613031452.pdf | 1. The ability of a regional body, the IOC, to coordinate project activities was a key factor in the relatively smooth implementation of a project spanning four countries at markedly different levels of development, as was the strong commitment of all four countries to the project objective.2. The use of earmarked taxes for operating and maintaining project facilities gives reasonable assurance of project sustainability, which is often a weak point for GEF projects.3. The project demonstrated that private sector support is desirable and possible for oil spill projects, though such support may have fallen short of appraisal expectations.
P036038 | Population and Family Planning Project | Eastern and Southern Africa | Malawi | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2004 | 2004 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/246541474577088008/text/000020051-20140612132714.txt | http://documents.worldbank.org/curated/en/246541474577088008/pdf/000020051-20140612132714.pdf | A mistake was made in not discussing sustainability of the CBD agents with the communities at the outset, generating expectations which could not be met. The response by the Ministry of Health was tailored to the situation (with the decision to train more of their own staff (the HSA), and to develop sustainable community programs to support the CBD Agents.) Where there is a large unmet need for family planning, there is no need to wait until the rest of the health system has been fixed. A functional referral chain is essential in the design of CBD programs. While the CBD increased the number of clients, long-term and permanent methods of contraception (i.e. Depo Provera) are still obtained in health facilities. Efficient back-up services are therefore vital for the provision of comprehensive reproductive health services.Effective community mobilization through IEC and support supervision, rather than financial incentives alone, is essential for a successful CBD program in reproductive health.Putting in place a strong monitoring and evaluation program, with prompt feedback at every level and incorporating the CBD Agents, enables quick identification of needed adjustments.
P036041 | FISCAL TECHNICAL ASSISTANCE PROJECT | East Asia and Pacific | China | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1995 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/143171474510725763/text/000020051-20140612070224.txt | http://documents.worldbank.org/curated/en/143171474510725763/pdf/000020051-20140612070224.pdf | In a TA project, if the Borrower's policy priorities change substantially, the Bank should formally restructure the project or consider cancellation
P036042 | BANKING SYSTEM MODERNIZATION | East Asia and Pacific | Viet Nam | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/921671474649664838/text/000020051-20140612135348.txt | http://documents.worldbank.org/curated/en/921671474649664838/pdf/000020051-20140612135348.pdf | While the Bank and the Borrower were fortunate to rescue the project with strong supervision, experience has shown that poor quality at entry can only rarely be turned around in this way.Before undertaking a technically and managerially complex project, the Bank needs to place a special emphasis on assuring that adequate institutional and procurement capacity is in place
P036047 | BALI URBAN INFRASTRUCTURE PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/526791474908990830/text/000020051-20140613063633.txt | http://documents.worldbank.org/curated/en/526791474908990830/pdf/000020051-20140613063633.pdf | Projects should have flexibility to adapt to changing environments, while staying focused. The East Asian financial crisis changed the conditions in the country dramatically between appraisal and implementation. Despite the difficult circumstances, the project has completed most of its activities satisfactorily and achieved most of its objectives, albeit with significant shortcomings. Several new sub-components were added to respond to the changed circumstances but these did not alter the original focus of the project. Land consolidation provides an effective option for obtaining land for infrastructure projects in complex or expensive areas, when the government is unable to provide cash compensation. However, this approach must be implemented in a fully participatory and transparent manner.
P036047 | BALI URBAN INFRASTRUCTURE PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2005 | 2006 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/794301468283544395/text/35624.txt | http://documents.worldbank.org/curated/en/794301468283544395/pdf/35624.pdf | 5. Lessons Learned Localgovernments in Indonesia should continue to build upon their demonstrated capacity to successfully implement improvements in infrastructure delivery, which has also been supportedby a long line of Bankprojects. However, local governments could be more responsivestill to urban development needs expressed through local communityparticipation. Communityparticipation inurban investment planningis often viewed only a formality and investments plans are often only an expression o f technical priorities which are identified by local officials themselves. Local governments needto engage more effectively incommunity consultation to ensure that urban investment plans also reflect expressed community priorities. A cross-sectoralframework such as Integrated UrbanInfrastructure , Development Program, can work wellfor local governmentsprovided the investment resources within it are sufficiently concentrated to adequately address needs in all included sectors. When resources are spread too thinly over a large area interms o fneed, itcanunderminethe expectedbenefits ofintegratedplanningresultinginincremental, rather than substantial, improvements inurban infrastructure. e All stakeholders, including local governments themselves,need to agree and understand clearly thepurpose behind local innovations-be it to increase efficiency, to increase client-responsiveness-rather than treat innovation as a benefitper se. Local governments inIndonesia are both interested and capable o f introducing innovative service delivery improvements, but while new approaches to municipal service delivery should be encouraged, new may not necessarily mean better. Local government should always articulate andmonitor the expected benefits from the innovation. As recognized inthe 2003 CAS, theBank has experienceand a rich knowledge basefrom many years of investing in local services through government (and more recently local government) drivenprojects. Ensuringthat local governments are always included as partners, with continuous emphasis upon improvingtheir performance, should be a mainstay o f all Bank assistanceto local service provision. Monitoring and Evaluation (M&E) systems need to be designedand implemented to track outcomes related toproject objectives, as well as the inputs and outputs of project activitiesthat will help achieve these outcomes.All three projects assessed inthis report focusedmainlyon successful implementationandinsufficientefforts were made to monitor the achievement of expectedbenefits -andpoor outcomes were not always identifiedintime. M&Ei s particularly important ingeographically spread-out projects and tracking meaningful indicators (which have a plausible link to project objectives and activities) can make up for the lack o f frequent supervision missions to participatingtowns.
P036048 | Coral Reef Rehabilitation and Management Project (COREMAP) | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2005 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/734281474649760209/text/000020051-20140613045551.txt | http://documents.worldbank.org/curated/en/734281474649760209/pdf/000020051-20140613045551.pdf | Conservation projects need to take a broad look at the various competing interests and incentive structures and develop a coherent approach. Specifically, establishment of community management should lead introduction of enforcement measures to ensure local ownership. Sufficient time must be allowed for community to internalize what is needed, and to reach agreement on and develop a common approach to reef and fisheries management.Allowing communities to determine program targets that are realistic is often more appropriate than setting artificial and monitorable targets that do not yield any meaningful benefits to the community.
P036048 | Coral Reef Rehabilitation and Management Project (COREMAP) | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2005 | 2004 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/998461468772759521/text/28325.txt | http://documents.worldbank.org/curated/en/998461468772759521/pdf/28325.pdf | LESSONS 59. Themain lessons that emerge from the experience of the project point to the need to proceed with caution with the expansion of the program in Phase I1in order to allow workable and sustainablearrangementsto be established for the implementation of the strategy, the integration of project activitieswith impact data gathering and monitoring, and the provisionof technical guidance for community-baseddecisionmaking. Importance ofAdaptability and Timefor Pilot Projects 60. As the pilot for a three-phase APL, the subjectproject was designedwith ample allowances for flexibilityand learning. Even so, the project required three extensions from its original completion date, and severalkey requirements for the success of COREMAP, such as the internal organization and implementation arrangementswithin DKP, the integration of project activities with data gathering and impactmonitoring, and theprovision of technical guidanceto local communities,remain incomplete and untested. In addition, the sustainabilityof the CBM-centeredstrategyhas not been demonstrated. Thispoints to the need for adaptabilityand cautionin regard to the expansion of the COREMAPprogram in Phase 11,until the viabilityof the approachhas been established. It also points to the advisabilityof extendingthe APL beyond the 15- year horizon envisaged at appraisal. Need to Integrate Project Activities with Impact Data Gatheringand Monitoring 61. A major flaw in project implementationwas the lack of coordinationbetween the CBM and MCS activitiesand the baseline surveysand monitoring provisionscarried out under a complementaryproject fundedby the ADB. Without close integrationbetween baseline surveys,sanctuarycreation, and surveillanceactivities,it will not be possibleto determinethe impact and validate the rationale for the COREMAPstrategy, even in the long term. This unsatisfactory stateof affairs appearsto be largelydue to the PMO's having been managed by a part-timedirectorfor the first three years of the project, and it being organizedalong thematic lines, with assistantdirectors and technicalteams responsiblefor MCS, CRTICs, CBM, and public communications for the entire COREMAPprogram, without geographicalresponsibilities.The ensuing lack of integrationcouldhave been avoidedwith the assignment ofmanagerswith geographical responsibilitiesand the dutyto ensurethat the different components are effectively integratedat all 10cations.'~ 19.Another approachwould be to have criticalparts of the programfundedby pooled funds, which would require close coordinationbetween donors. Need toAssign Full TimeStafffor Project Implementation 62. The PMO's extensivereliance on part-time staff significantlyreduced the ability of managers and staffto maintain controland direction over the technical aspects of the project, and encouraged a situationwhere most of the work was done by consultantsand contractorswith littleintegrationbetween consultantsand PMO technical staff. This contributedto significant delays in project implementation,inadequate integration between different project components and limited transfer of knowledge from consultants to national staff.Many of these problems couldhavebeen avoided with the appointment of full-time staff for the implementation of the project. Need to Provide Technical Guidance to Community-basedDecisions 63. While community empowermentwas a vital element of the COREMAP strategy, it can lead to poor decisions,as indicated by the findings about the qualityof biodiversity in one of the chosen sanctuaries,and investments in unviable electrificationschemes.The failureof the seaweed cultureprojects was particularly unfortunate, given LIPI's expertise in this area. This points to the need to ensurethat community-based decisionmaking processes be informed by sound technical guidanceto ensurethat mistakes are avoided. FUTURE DIRECTIONS 64. Based on the project's experience,it is possibleto identify additional directions that could enhance the benefits from the COREMAP strategy, and deserveto be considered for Phase I1and futureprojects. Potentialfor Local Fisheries Development 65. The commercial and artisanalfisheries in the project areas appearto be far from being fully and efficientlydeveloped, but the project has done little to examinehow the local communities could extract additional benefits from the fisheryresources around them. While the communities have been given full authorityover village grant and seed funds, their decisionsoften have not been informedby adequateexpertiseon technical and commercial aspects.In light of the ample fisheryresourcesin the project areas, the provision of additional expertise on technical and market issues to aid their sustainable developmentby the local communitieswould seemto be an area worth consideringto enhancethe localbenefits of the program. PotentialforRenewabJeEnergiesDeveJopment 66. Three of the five TakaBone Rate villages where CBM has been fully implemented chose to invest one of their three village grantsin a diesel-basedelectricity supplysystem.Whle this choice reflects village priorities, it was clear to the mission that the electrificationschemeshave not been designed to adequatetechnical standards,and are not being managed in a financially sustainableway.2oThe installations are precarious, unsafe, and certainto fail, and shouldnot have passed the technicalreview process of the NGOs and PMOS.In light of the limited capacity of the villagesto manage and maintain an electrificationscheme,it would appear that simpler, more decentralized approaches, includingsolarphotovoltaic home systems, should also be considered. Potentialfor GreaterEmpowerment of Participating Villages 67. Based on the experience of the project, there seem to be additional opportunities to pursue the COREMAPobjective empoweringthe coastal communities as owners and managers of local reef resources. Thepotentialto transfer fwtherproject responsibilities to the communitylevel, and the need to supplement the village entities' sourcesof revenue present two directionsthat deserveto be pursued. 68. While the project has already engineered a major transfer of budgetary, development, and enforcementresponsibilities from the nationalto the districtlevels,the financial management aspects remains centralized, with extensivedelaysbetween community-level decisions,district-levelreviews, and central-level approvals. Thiswas the most important sourceof complaintsnoted by the mission. The need to address this issue would seem to offerthe opportunityto transfer greater authorityand responsibility for project implementationto the villages. 69. The sustainabilityof village support for the CBM and MCS components of the strategywill require greater attention to enhancing the communities'sourcesof revenue. The development of a user charge system that would enable the villages to collect and retain license fees from fishingboats, divers and tour operatorswould seem to be appropriate.Somesuch user charges already exist,but they are far fromreflectingthe economicvalue of the resource, and the revenues are sentto the central government. 20. E.g., tariffs do not cover operatingcosts, andthere is no provision for equipmentmaintenance, repair andreplacement. 21.Some lessonsmay be learned fromthe experience with similar systemsin remote Pacificisland countries. See\. SoIarEnerrzv\. Lessons fromthe PacificIsland Experience,by A. Liebenthal, S. Mathur and H. Wade, World Bank TechnicalPaper 244 -Energy Series,Washmgton, 1994.
P036049 | ID-EARLY CHILD DEVELOPMENT | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/406481474633927270/text/000020051-20140618080335.txt | http://documents.worldbank.org/curated/en/406481474633927270/pdf/000020051-20140618080335.pdf | Recruitment of teachers within project communities positively affects sustainability of ECD programs (section 6 of the ICR). The local villages nominated their own qualified teacher candidates who were instrumental in convincing the communities to enroll their children in ECD programs. Before their employment, the programs were not popular. It seems that the implicit demand by these trained teachers to remain in employment (after their training) was an added motivation for them to sell the program to the community. Integration of education, nutrition and health, and parental education is more effectively achieved at the village/program level (than at the district, provincial, or national levels). The ICR reported that experience from the project showed that involving several government ministries in provision of services for young children was often challenging while involving ECD teachers, village health workers, and women volunteers was much easier, at the community level. A unified management approach is likely to lead to better results in implementation of ECD programs. The ICR reported that the project had challenges because it was managed by Directorate of Community Education (under Directorate General of Non Formal Education) to ensure its role of empowering communities while the line authority for Kindergarten and Primary Schools was under the Directorate General of Primary and Secondary Education.
P036052 | MN-UB SERV. IMPRMVT | East Asia and Pacific | Mongolia | IBRD |  | Sustainable Development | Water | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/959031474893260724/text/000020051-20140612141808.txt | http://documents.worldbank.org/curated/en/959031474893260724/pdf/000020051-20140612141808.pdf | Improving the quality, quantity and reliability of water supply for low-income population requires a well- established development policy at a higher level, which is supported by a well-trained and technically competent staff to articulate the policy goals and adequate data and information about operational management. Although institutional development of USAG was successful overall, a number of second generation issues remain. These include the development of policies for metering and house connections, an appropriate role for the private sector, and further improvements to maintenance, development and implementation of a communication strategy.The risk of financial sustainability implied by USAG, especially when such a company was planned to be converted into a self-financing commercially-oriented public utility, should be carefully taken into account during the appraisal process. A number of design issues came to light particularly as a result of the project in Mongolia. Chief among these was the extent of protection required against freezing. Another issue was the need to standardize designs of pumping stations, bath houses and water kiosks.
P036053 | Second Sulawesi Urban Development Project | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/912421474854373121/text/000020051-20140612132120.txt | http://documents.worldbank.org/curated/en/912421474854373121/pdf/000020051-20140612132120.pdf | The five most significant, according to OED:Borrower project management units (PMUs) should routinely carry out, with the assistance of consultants as needed, technical audits of completed subprojects to ensure that technical and costs specifications of completed works are fully met in every case.To help ensure M&E to overcome inherently weak sustainability of projects such as this in Indonesia, the Bank and government could consider greater involvement of civil society (including local NGOs). Civil society involvement can help bring greater pressure upon local government to provide adequate funding for the operation and maintenance of infrastructure services.The Bank should make greater efforts during supervision to ensure that management tools introduced through the project--such as POMMs for instance--are actually put into practice by local government stakeholders.Given the sensitivity of Bank supervision missions reporting concerns about possible corruption in mission aide memoires, standard procedures for staff to report their concerns to Bank management should be put in place. As part of its anti-corruption drive, Bank management should not hesitate to seek changes in the borrower personnel composition of tender committees when there are justifiable concerns about the probity of procurement processes.The Bank should be cautious about 'scaling up' a project by extending the original design's coverage to include many additional cities, when such extension is driven by lobbying by cities whose genuine commitment and implementation capacity are weak.
P036055 | SAL | Latin America and Caribbean | Ecuador | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1995 | 1998 | 1999 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/199541475327928693/text/000020051-20140519082216.txt | http://documents.worldbank.org/curated/en/199541475327928693/pdf/000020051-20140519082216.pdf | SALs are inappropriate instruments for the support of complex, long-term policy and institutional reforms.
P036056 | Judicial Reform Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 2006 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/429081474570715016/text/000020051-20140612090113.txt | http://documents.worldbank.org/curated/en/429081474570715016/pdf/000020051-20140612090113.pdf | 1. The participation of non-judicial, nongovernmental CSOs in project design, combined with exceptional openness of Ecuador's judiciary to dialogue with civil society, ensured that new areas were squarely placed on the Government's agenda for judicial reform. 2. By focussing on tangible, achievable goals for improving judicial process, support for deeper reforms can be mobilized within the judiciary and in civil society. 3. Engaging Ecuador's law schools in the judicial reform process proved a savvy recipe for encouraging judiciary acceptance of the need for change. 4. Infrastructure support and computerization alone cannot carry a judicial reform program.
P036060 | National Roads Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Transport | IDA | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/337651474898333709/text/000020051-20140612095340.txt | http://documents.worldbank.org/curated/en/337651474898333709/pdf/000020051-20140612095340.pdf | A strong Project Implementation Unit is essential for relatively complex infrastructure projects, when the local administration lacks experience and is affected by continuous change.Contractual arrangements may have to be strengthened when parallel financing is envisaged.When there are insufficient funds to complete the project as envisaged, serious consideration should be given to using some of the scarce funds to cover the institutional/capacity building tasks, possibly even at the expense of the least viable infrastructure element. The rationale for prioritizing some components ahead of others should be put forward.
P036060 | National Roads Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Transport | IDA | IPF | 1996 | 2003 | 2007 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/101991468209652046/text/39934.txt | http://documents.worldbank.org/curated/en/101991468209652046/pdf/39934.pdf | 5. Lessons 5.1 The following main lessons can be extracted from these interconnected projects, taking into account the very difficult circumstances under which they were implemented\. ROADS Inconditions where government capacity i s weak the establishment o f a separate project implementation unit for each operation may be necessary in the short term, but ways must also be sought to strengthen government capacity so that regular departments can take over PIU responsibilities in the medium term, after which PIUs can be wound up. Emergency credits can provide a quick response to a crisis situation, but should be kept as simple as possible if they are to be effective. Long term sustainability o f a road network depends o n a reliable funding stream. This can be achieved through either a road fund or by means o f a multi year expenditure framework. However, as exemplified in Albania, unless there i s government commitment to fund maintenance, current capital expenditures are likely to be seriously jeopardized in future years because o f asset deterioration. PORTS Organizational restructuring projects should not be planned in excessive detail up front, since it is very difficult to assess the degree o f government commitment to reform and the time it will take to put the legislative and regulatory framework in place. Effective supervision provides an opportunity to adapt the details as the project proceeds. In these cases a more programmatic approach with milestones may b e better suited, such as an adaptable program loan. The Port o f Durres project shows the dangers o f proceeding with civil works o n the basis o f poor cost estimates and preliminary design. Although speed is important inadequate designs can lead to time losses during implementation and any reallocation o f credit components, because o f higher than expected costs, can jeopardize project outcome. The key lesson for the Bank in responding to an emergency unexpectedly arising during implementation i s to ensure that all stakeholders are treated equally, and that a flexible attitude i s taken so that the credit can be amended in response to changing circumstances.
P036061 | Port Access & Management Project | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/287941474570797971/text/000020051-20140612104134.txt | http://documents.worldbank.org/curated/en/287941474570797971/pdf/000020051-20140612104134.pdf | In projects involving substantial institutional restructuring, efforts at appraisal to set up significant policy dialogue with the Borrower are likely to lead to highly positive outcomes.Requests to scale down technical assistance that is part of the initial project design should be considered very carefully before a decision is made.
P036062 | Ecodevelopment | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2004 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/418971474488900454/text/000020051-20140613044354.txt | http://documents.worldbank.org/curated/en/418971474488900454/pdf/000020051-20140613044354.pdf | Learning the features for scaling up: The primary learning for Government and the Bank stems from the practical experience gained under the project, resulting in a broad array of specific design and implementation lessons, further enriched by the different issues encountered between the seven parks. These form a valuable base for Government's scale-up intentions. The ICR includes a number of such lessons, but more can be anticipated. It would be useful for biodiversity practicioners, in India and elsewhere, if the project's design and implementation lessons, both positive and negative, could be further documented.The need for sustainability planning: In a community driven environmental management project, there is need to establish the features for participating communities to remain motivated and financially viable. Each PA prepared an action plan to this effect, and a number of communities also prepared plans, but this was not the general case.Community driven projects may need program-type support: New community organizations and government processes may need longer to fully mature and become sustainable than the period available in a conventional investment project. A program approach or use of follow-on projects may be better. (The Region is now preparing a follow-on project, but this is currently envisaged only for new PAs.)Project extensions should harmonize with time requirements for community investments: The two successive one year extensions for this project created uncertainty regarding funding beyond the first year. As a result, not all of the communities were able to participate, reducing ecological protection. For a community driven project, if an extension is justified, the extension period is best made as a one-time decision in line with the time required to complete ongoing community investments and/or to start and complete additional investments.
P036076 | SAL I | Middle East and North Africa | Algeria | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1996 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/976371475085937572/text/000020051-20140519081404.txt | http://documents.worldbank.org/curated/en/976371475085937572/pdf/000020051-20140519081404.pdf | The project confirms the validity of the Bank's "best practices." The proper sequencing, depth and speed of reform are critical in shortening the transition period, reversing expectations and bringing about sustained growth of income and output. Furthermore, while stabilization is necessary, broad structural reforms are also vital to sustain the short term improvements in macroeconomic performance.
P036087 | LB-POWER SECT. RESTRUCT | Middle East and North Africa | Lebanon | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2003 | 2003 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/200731474511072301/text/000020051-20140607163306.txt | http://documents.worldbank.org/curated/en/200731474511072301/pdf/000020051-20140607163306.pdf | The project confirmed lessons that have already been learned from experience in other client countries: -Hard political decisions, tariff increases and enabling legislation need to be implemented before the Bank commits substantial funds for infrastructure upgrading.Technology issues need to be reviewed and resolved before Board presentation.Sustained attention needs to be paid to resolving systemic institutional financial accounting problems when these problems impact the integrity of the financial auditing process.
P036089 | Health Sector Transition Project | Europe and Central Asia | North Macedonia | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1996 | 2002 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/805081474490598315/text/000020051-20140612073101.txt | http://documents.worldbank.org/curated/en/805081474490598315/pdf/000020051-20140612073101.pdf | A highly complex program of sector reform needs strong government ownership, coupled with the capacity to negotiate between the winners and losers. The fact that the Ministry of Health had a total staff of only 25, mostly with medical rather than managerial training, should have signalled the need for an especially strong Implementation Unit and tighter supervision efforts in the early stages.Insufficient attention was paid to the set-up, maintenance, and systematic use of a monitoring and evaluation framework, which could have helped to avoid some of the project weaknesses, especially cancellation of important sub-components.
P036405 | CN-Wanjiazhai Water | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2007 | 2009 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/967771474664040802/text/000020051-20140619073434.txt | http://documents.worldbank.org/curated/en/967771474664040802/pdf/000020051-20140619073434.pdf | â€¢ The project design should have considered how to achieve the project development objectives in the most effective way based on realistic water demand projection and should have given much greater priority to demand management and efficiency improvements among industrial water users rather than focusing primarily on large-scale engineering solutions.â€¢ Broadly defined project development objectives coupled with indicators with weak causal linkages not only impede supervision and impact evaluation, but they can result in wasted resources, both financial and temporal.â€¢ Projects that include infrastructure aspects as well as reform to institutions and financial policies can require increased attention to the institutional aspects, especially in the early stages, in order to ensure the two stay synchronized.
P036414 | GUANGXI URBAN ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/336971475094577479/text/000020051-20140619082115.txt | http://documents.worldbank.org/curated/en/336971475094577479/pdf/000020051-20140619082115.pdf | Improvements in collection and treatment of domestic wastewater alone are not sufficient to improve the water quality. Complementary industrial pollution reduction programs are necessary to improve the quality of water bodies like the Chaoyang Stream and the Yongjiang in Nanning, and the Lijiang and its tributaries in Guilin.While planning for water transmission for city uses through rural areas, it is worthwhile to consider the needs of local farmers and rural populations en route and to provide some benefits to them. This will avoid at least initial opposition from local farmers towards construction of water transmission lines going through rural areas.The introduction of new contracting methods, such as turnkey contracting, should be done only after model bidding documents are available, or after adjustments to standard documents have been thoroughly discussed and understood during project preparation. Worker contracts need to have provisions for price escalation, as absence of such provisions may compromise the quality of works should unit costs of key imports rise.Community participation in infrastructure planning, implementation and management is a viable even in rapidly growing cities as demonstrated by the small area improvement subcomponent.The approval of ICB equipment contracts took a long time in China thus causing implementation delays. This affects all World Bank-financed projects in China, and the Bank needs to improve this situation through policy dialogue with the central government.
P036417 | POVERTY ALLEVIATION FOR VULNERABLE GROUPS | East Asia and Pacific | Mongolia | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/351621474589463348/text/000020051-20140602112100.txt | http://documents.worldbank.org/curated/en/351621474589463348/pdf/000020051-20140602112100.pdf | The ICR identifies the following lessons of broad applicability:Successful implementation of a bottom-up, demand driven approach is facilitated by open public meetings at grassroots level.The establishment of a cross-sectoral implementing agency facilitates project implementation but creates conflicts and uncertainty. Since poverty reduction is an issue that transcends sectoral boundaries, the proper location for a poverty programme PMU is either under the Prime Minister or in a cross-sectoral ministry such as Finance, Planning or Local Government. A social sector ministry is a poor choice and can create conflict during implementation. The construction or rehabilitation of local infrastructure can have a quick and direct impact on income earning opportunities and standards of living. However, the temporary employment created by public works programmes is too short to have significant impact on livelihood's of the poor.Sustainable access to credit for the poor requires the creation of a rural finance system and training of beneficiaries in simple business management skills.
P036947 | CN-Sichuan Power Transmission Project | East Asia and Pacific | China | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1995 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/283821474563279322/text/000020051-20140612135043.txt | http://documents.worldbank.org/curated/en/283821474563279322/pdf/000020051-20140612135043.pdf | (1) During project supervision, the Bank should periodically review the key performance indicators of projects requiring substantive reforms and restructuring to determine if they remain valid or need fine-tuning. This is particularly important when the project experiences major external shocks such as a natural disaster or a regional financial crisis or a change in the provincial or regional administrative status that affects the development indicators.(2) Construction of high-voltage transmission networks in mountainous areas requires a careful evaluation of capacity and capabilities of local contractors as well as the interface of specifications with foreign suppliers. Failure to pay sufficient attention to such matters delays implementation and risks significant cost overruns.(3) In power transmission projects, the resettlement analysis needs to be closely aligned with facilities design and routing in order to minimize the social impact. Resettlement plans should be developed during appraisal, and they must include clearly stated details regarding compensation. .
P036947 | CN-Sichuan Power Transmission Project | East Asia and Pacific | China | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1995 | 2004 | 2005 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/874411468215967444/text/32664.txt | http://documents.worldbank.org/curated/en/874411468215967444/pdf/32664.pdf | Lessons Learned 140. The experience gained under the three projects reviewed inthis report, as well as from the pursuit ofconcurrent power sector reforms at the national level, offers the following lessons of general applicability\. 0 As amply illustrated inthe ICR for the Ertanhydroelectric project, good institutions for resettlement are kef. Chinahas three institutionalfeatures that facilitate successful resettlement and canbereplicated elsewhere\. (i) enlightened policies by central andprovincial governments that establish the principles and incentives for resettlement as a development opportunity; (ii) planningand execution based on sound guidelines, managedby dedicated local authorities and open to a fair andParticipatoryprocess; and (iii) o fpost-resettlement funding activities by a levy from project-generated income. Power shortages are a barrier to the pursuit ofmarketreforms aimed at increasing competition. This emerges clearly from the short-lived experience with competition for generation dispatch inboth Sichuan andZhejian provinces68. 0 Effective regulatory arrangements should be inplace at the same time (ifnot sooner) as power supply entities are unbundled,inorder to reduce abuses o f marketpower such as that which occurred inSichuan following the commissioning ofthe Ertanhydroelectric plant6'. 0 Indicativepower system planningat the national level is essential inorder to avoid boom-bust investment cycles such as the one currently buildingup inthe Chinese power sector. The absence o fnational-level oversight andplanning, combined with imperfections inthe flow o f informationto investors was well as to the authorities andinadequate controls on lending(due diligence) by the Chinese financial system, have contributed to over-investment ingeneration and under-investment intransmis~ion~~. 67. This lesson is reproduced verbatim from the ICR o f ErtanI1since it is bothclear and succinct. The Bank's E. Asia Regionproject staff commented that It is the interference o f government incase o f tight supply that createdthe problems not the market. Reformcouldbe implementedintight supply conditions and ifmarkets are well designed they will rationpower inthe most optimum way. 69The Bank's E. Asia Regionproject staff commented that The real lesson i s that it would be a long process to change from command-and-control type o f operation to market operation based on contracts and rules, and from old style government control to modem light-handed regulation. The reformprocess should be designedto recognize this. 70The Bank's E. Asia Region project staff commented that No doubt China needs better energy planning ingeneral andpower systemplanninginparticular. Butthis isnotthe root o fthe current over-investment. This seems to be more o f the issue o f state owned company governance (bank governance as well) rather thanthe issue of sector planning and regulation.
P036949 | CN-Nat Hwy3-Hubei | East Asia and Pacific | China | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/494201474501045379/text/000020051-20140613054925.txt | http://documents.worldbank.org/curated/en/494201474501045379/pdf/000020051-20140613054925.pdf | City development plans should be incorporated early in the project design of national and provincial transportation links.Clear commitment and strong client ownership are a prerequisite to include policy-related studies as part of a project.
P036950 | Third Basic Education | East Asia and Pacific | China | IBRD |  | Human Development | Education | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/859941474595401911/text/000020051-20140607154444.txt | http://documents.worldbank.org/curated/en/859941474595401911/pdf/000020051-20140607154444.pdf | In order to avoid over emphasis on inputs and physical targets, and neglect of outcomes during implementation, projects should include specific qualitative improvement objectives. Â·Direct assistance to poor students for school related expenses such as textbooks, and tuition fees is essential in order to retain these students, and promote learning;Â·Project design should not only include investments to enhance the capacity to produce statistical data, but also to promote their utilization. There is also need to address the factors which mitigate against their collection, analysis and utilization;Â·National expertsâ€™ panels have the potential to play an important advisory role both in the preparation and implementation of projects provided their expertise is related to the sector, and their input is clearly detailed; Â·In order to improve the quality of instruction, there is need to place greater emphasis on the quality of teacher training programs, and the mechanisms for transferring knowledge and skills to the classroom. During supervision, focus must be on the classroom practices, and instructional outcomes, and the factors which may prevent the application of acquired teaching skills.
P036950 | Third Basic Education | East Asia and Pacific | China | IBRD |  | Human Development | Education | IDA | IPF | 1996 | 2002 | 2002 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/264611511185211679/text/multi0page.txt | http://documents.worldbank.org/curated/en/264611511185211679/pdf/multi0page.pdf | 4. Lessons 4.1 The preceding review combined with key findings from the experience of the eight assessed projects offers two broad categories of lessons with implications for the Bank's future involvement in China\. enhancing the development impact of projects and strengthening the focus on poverty reduction. 4.2 Enhancing the development impact of projects. The experience of the assessed projects and the cross-sectoral review indicate that while Bank-supported projects in China may achieve their physical targets, the achievement of development outcomes can be mixed. Maximizing development impact requires more focus in Bank-supported projects on achieving development outcomes, especially on institutional issues. * Attention to institutional issues is essential for improving impact. These issues received less attention than warranted in the assessed education and agriculture development projects. In the agriculture projects, the physical targets were achieved while the major institutional issue of provincial capacity to manage water resources was not much improved. In the education sector project, perhaps because of political pressures and the need to ensure basic education for all, the emphasis was on increasing access while the quality of the education imparted received less attention. Intended outcomes and institutional issues need to be identified early and consensus reached with the borrower on how to resolve them. * Continued and deepening Bank engagement is needed to ensure robust benefits. In response to government demand in the education sector, the Bank has focused with each succeeding project on spreading the benefits of its investments in new provinces and counties rather than engaging in a deeper relationship in the same areas over longer periods of time. There are obvious trade-offs, but in order to maximize development impact, the Bank's future efforts in the social sectors could be informed by the need for sustained and far-reaching improvements in quality, and efficiency. 4.3 Strengthening the focus on poverty reduction. The Bank has been a valuable partner in helping the Chinese catch up with other countries through infrastructure development and the transfer of technology and knowledge about international procedures. It has also provided valuable support to significantly reduce poverty levels. However, tackling the remaining poverty remains a major concern. * Sharpening the focus on poverty reduction will require adjustments to targeting. Improving support for China's poverty reduction strategy rests not only on increasing attention to the nationally identified poor counties but also to improved targeting at the township level. On the borrower's side, there is need for greater government coordination of all Bank poverty-related efforts be it in the context of multi-sectoral poverty reduction projects or under sectoral projects (like the eight projects OED assessed). Strengthening such coordination would help to mainstream poverty reduction activities within sectoral operations. * Coordination ofsectoral efforts needs to be improved. In Henan and Hebei the Bank could have made more effort to coordinate and link the activities of the assessed projects to maximize the poverty impact. Coordination between different levels of government in China, across central bodies, and between various departments and agencies also is weak and needs improvement, but experience of the assessed projects shows that the Bank was unable to engage China on this issue. Poorer provinces have special needs that require particular attention. China's high level of decentralization has spurred the overall development process in the country. At the same time, it has created pressures against investment in sectors that do not yield quick financial returns but are crucial to reducing poverty. It has also put the poorer states in a position where they lack resources to deal adequately with poverty. Furthermore, since IDA resources are no longer available to China it has become difficult for the poorer provinces to borrow, especially for poverty alleviation efforts. China needs to consider a differentiated policy for giving special treatment to the poorer provinces. Government officials are keen on the Bank adjusting its lending terms and procedural requirements to make it easier for poor provinces to borrow for projects that can help the Bank and the country fulfill their poverty reduction objectives. Building on the recent agreement with DFID to provide grants for blending with IBRD loans, the Bank and China should continue to work together to ensure that lack of availability of IDA resources to China does not become a constraint on its ability to help the poorest provinces.
P036952 | CN-BASIC ED. IV | East Asia and Pacific | China | IBRD |  | Human Development | Education | IDA | IPF | 1997 | 2004 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/629281475097892374/text/000020051-20140612131728.txt | http://documents.worldbank.org/curated/en/629281475097892374/pdf/000020051-20140612131728.pdf | 1. Demand-side approaches (targeted subsidies) to increased basic education participation among the poor can be effective; they are particularly effective when local commitment to them is strong enough to generate funding from recurrent budgets or social contributions.2. In poverty reduction schemes which include basic education participation, it is good to rely on the local educational infrastructure for the planning and execution of the education part, given sector's professional resources and village level connections, but this does not mean that the sector should work in isolation. Connections to the other parts (sectors) in the scheme should be maintained and evaluated. 3. When programs of increasing access are planned and managed well, there need not be a trade off between access and quality. 4. A mix of solid policies, management capacity building, flexibility in using resources and political will can accelerate a country's attainment of universal primary and lower secondary education. 5. Ministries of Education having bold programs of educational attainment and quality improvement would do well to build in measures that would allow for impact assessment. This would entail either setting up a controlled experiment or a quasi-experimental design (in which project schools are compared to those of a control group).
P036953 | China Health Nine Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2008 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/934551474419648343/text/000146597-20140619154301.txt | http://documents.worldbank.org/curated/en/934551474419648343/pdf/000146597-20140619154301.pdf | Engagement on health system and policy issues is essential, particularly in a policy environment that is relatively immature and rapidly evolving. Support for training and specific interventions risks becoming stale and irrelevant if not accompanied by ongoing policy dialog. This project may have been more influential if it had concentrated more on system-level issues and less on direct technical assistance (as was the case with the blood safety subcomponent).Inconsistent supervision and slow implementation put a projectâ€™s relevance at risk. Lack of continuity of Bank task managers and limited presence in Beijing contributed to a failure to sustain relationships and trust with government counterparts and development partners and to reprioritize (or redesign) project activities as circumstances changed. Stability and visible presence of project management is essential.If an â€œinformation cultureâ€ does not exist when a project is launched, the Bank must make explicit efforts to build one. More attention in this project could have been focused on process evaluation and lesson learning during implementation.Medical Financial Assistance (MFA) programs for poor women and children could usefully be integrated into overall poverty reduction programs or into governmental medical assistance programs. The MFA program of this project achieved important social benefits by making primary MCH services available for poor pregnant women and children from poor families.
P036956 | ID-SAFE MOTHERHOOD | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/812971475077355299/text/000020051-20140613060809.txt | http://documents.worldbank.org/curated/en/812971475077355299/pdf/000020051-20140613060809.pdf | Decentralization can work, but requires(a) clear strategies and technical solutions in place; (b) well developed tools to aid district-level planning and a district-led planning process, and (c) integrated planning and funding mechanisms. Decentralization also helped with multi-sectoral coordination. However, it is important to ensure that districts, at least initially, have access to technical guidance and support.Institutional incentives are key: In the Indonesian context, long-term success of the integrated safe motherhood program will require a clear resolution of the issues of cooperation between the two responsible government agencies. Coordination meetings and workshops, even planning mechanisms may not be enough if stronger incentives forcoordination are not in place. The combination of demand and supply approaches can lead to positive outcomes. The projectâ€™s.emphasis on ensuring that both demand- and supply-side interventions were included helpedensure better outcomes.The role of medical providers other than doctors is constrained by the dominance of the medicalcommunity: More work is needed to persuade obstetrician-gynecologists to agree to the expanded role for midwives in managing emergency obstetrical services and to participate in other Safe Motherhood Program activities.
P036973 | Enterprise Housing Divestiture Project | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/755321474906070769/text/000020051-20140612152151.txt | http://documents.worldbank.org/curated/en/755321474906070769/pdf/000020051-20140612152151.pdf | Bank preparation work needs to incorporate the inputs of staff and consultants with expertise on the process in hand (i.e. enterprise housing divestiture) and the sectors and sector reform likely to be affected by any of the project components (i.e. housing, municipal development, and social safety nets). There always needs to be consistency between project objectives and project components in project design, with components posited as instruments to achieve the objectives.During project preparation, the Bank should ensure that project objectives enunciated by the legal agreements are identical in content and form to those of the project documents, especially the SAR.Project preparation should always benefit from the inputs of relevant ESW and related projects, and Bank management should ensure that preparation work be closely coordinated with closely related projects (the Russia Housing Project Ln3850, in this case).If a project aims to improve the performance of target beneficiaries (participating cities, in this case), project design needs to make explicit the performance indicators that will demonstrate how the results will be monitored and verified. Typically, they will include data for identical indicators in project and non-project cities, whose different values will attest to impact of the project.Sustaining good relations and ensuring effective communications between diverse project stakeholders should always be an implicit aim of the project experience (beyond explicit development objectives) in order for all parties to make the most of the learning experience afforded by the value added that the international collaboration over a project of this kind can bring.
P036973 | Enterprise Housing Divestiture Project | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2004 | 2006 | PPAR | >=100 million | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/396321468294975360/text/32689.txt | http://documents.worldbank.org/curated/en/396321468294975360/pdf/32689.pdf | LESSONS 5.5 The project experiences highlightthe following OED lessons\. Having demonstrated that housingmarkets can work inRussia, reformers need to move on quickly to find sustainable solutions for the poor, who have drawn no benefit from project results thus far. For more public land to become available for private urban development inRussia's cities, the concerns o f municipalities (reluctant to part with their source o f power and influence) andprivate developers (unsureo f security o ftenure and that infrastructure will beprovided) needto be addressed. To help improve city levelperformance (of any kind), project designshould incorporate performance-related criteria to determine the allocation o f resources across cities. When Borrowers find themselves indisagreement with project objectives, the Bank should help themrecognize the need to formally restructure or cancel an operation.
P036977 | Rural Water Supply & Sanitation Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/288981474652347207/text/000146597-20140619155113.txt | http://documents.worldbank.org/curated/en/288981474652347207/pdf/000146597-20140619155113.pdf | The "rules of the game" need to be fully and clearly explained to the participants in community-managed water projects. It took some time for people to understand that they were not paying for water but for the services to deliver clean and reliable water. Delays in explaining the rules may lead beneficiaries to think that water is free and make them more reluctant to start paying for it to be delivered.In-kind community contributions may have drawbacks. In most IDA countries in-kind contribution by beneficiaries is regarded as a good signal of community buy-in and ownership but in this project, reliance on in-kind contribution (mostly labor) caused implementation delays, conflict with contractors, and resulted in poor quality of construction.The viability of the supply chain for O&M needs to be appraised for community-managed infrastructure projects. In this project the CDWUUs had to rent equipment, which in many cases was unaffordable. A revolving fund could have enabled groups of closely located CDWUUs to buy equipment and repay the cost in installments. Alternatively, guarantees from local government could have facilitated access to credit.
P037005 | REGULATORY REF & CAP | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1995 | 1999 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/454491475088017446/text/000020051-20140526223029.txt | http://documents.worldbank.org/curated/en/454491475088017446/pdf/000020051-20140526223029.pdf | The development of a clear regulatory system and the dissemination of information to workers and investors on the advantages of the program were key to the successful divestiture of public enterprises that, in earlier periods, the Bolivian government had considered to be politically impossible to divest. Thus to gain acceptability for a capitalization/privatization program among the majority of a country's population, it is important to ensure transparency and a competitive regulatory framework. It is also important to diffuse potential political resistance to the program through a public information campaign that stresses the program's benefits.
P037006 | Water Sector Institutional Strengthening | Latin America and Caribbean | Trinidad and Tobago | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1995 | 1999 | 2000 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/299831474596294217/text/000020051-20140528124448.txt | http://documents.worldbank.org/curated/en/299831474596294217/pdf/000020051-20140528124448.pdf | The Bank should include legal and privatization specialists early in the process of privatization contract preparation to ensure the contract is clear and enforceable;When the main objectives of a project are institutional reform and policy implementation an adjustable program loan may be more effective for managing conditionalities;The Bankâ€™s procurement rules need to evolve to deal with successive privatization contracts (for instance determining the eligibility of the incumbent winner of an Interim Operational Agreement to bid on a subsequent Long Term Agreement);Financial audits should include monitoring of compliance with specific covenants;When projects are linked (in this case a Flood Control and Drainage Project was promised) this should be formalized to avoid misunderstanding;Water Resources Management and Water Supply Sector Reform should be more closely coordinated yet the sectoral specializations of most task teams has meant these are followed independently of each other, with limited interaction.
P037047 | RURAL RDS. REHAB & M | Latin America and Caribbean | Peru | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2001 | 2002 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/202091474665904086/text/000020051-20140602112835.txt | http://documents.worldbank.org/curated/en/202091474665904086/pdf/000020051-20140602112835.pdf | The ICR identified the following lessons: For effective poverty reduction, rural accessibility interventions must find a balance between poverty targeting and promotion of economic opportunities.Communities benefiting from sub-projects need to be effectively mobilized from project initiation through the project post-completion for successful implementation and sustainability of the project. Workshops during the selection and the design phases are important for creating project ownership and defining priorities. Post-completion workshops are a powerful way of changing communities attitudes towards maintenance which is necessary for the sustainability of the projects. The role of local and provincial authorities in supporting sub-projects also needs to be strengthened to ensure sustainability in particular project operation and maintenance resources.OED carried out the Project Performance Assessment simultaneously with the preparation of the ICR. It identified following valuable lessons:Transport projects need to be put into a broad socioeconomic context. View projects as an experiment and observing its results allows for social learning - and development.Structure participation as a progressive and continuous dialogue.Interactions with the borrower and beneficiaries should take place in terms that they understand and in a context they set.Acknowledge the complexity of the problem and keep the interpretation of objectives flexible.Focus more on analyzing problems, than on achieving results; explore failures and successes together with the borrower; and finally, learn to use emotional communication for facilitating change. This requires that project management show leadership and be a spokesman for the project, be capable for conducting sectoral and intersectoral negotiations, and establish good relations with the spokesmen for the stakeholders. Project management must also be backed up by an excellent project information and management system.
P037047 | RURAL RDS. REHAB & M | Latin America and Caribbean | Peru | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2001 | 2002 | PPAR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/503851511185884898/text/multi0page.txt | http://documents.worldbank.org/curated/en/503851511185884898/pdf/multi0page.pdf | 4. Conclusions and Lessons Learned 4.1 The Bank's preparation, implementation, and supervision of the project were, albeit indirectly, outcome-producing\. created strong local ownership, developed institutions, and achieved tangible and desirable results. There are several lessons in how that was done. Undoubtedly, the project concept and its implementation, developed together and owned by all, were key to the project's success. But why did the success happen or, in the words of the Learning ICR team leader, what causes change? The interpretations in the lessons that follow may be unconventional, but they are not made hastily nor are they without a solid empirical basis if the evidence is interpreted that way. Thus, although this assessment inspired the lessons, their 18. For example, Schein, E. (1990) Models of consultation\. What do organizations of the 1990s need? Consultation\. An International Journal, 9 (4), pp. 261-275; Talvitie, A (1998) Transport policy and the transport problem. The question offinding cure. Paper in the 4f' WCTR Conference, Antwerp, Belgium Willson, R. (2001) Assessing Communicative Rationality as a Transportation Planning Paradigm Transportation, 28 (1), pp. 1-31, and Talvitie's discussion of Willson's paper in the subsequent issue Transportation 28 (2); Ellerman, D. (2001) The Indirect Approach, World Bank; and references in these papers. roots are long and reach several assessments, observations, and literature on learning, teaching and development, and organizational change. The lessons are advanced as hypotheses to be tested and discarded or adopted as more evidence accumulates * View the project as an experiment and include society broadly in it. Transport projects nearly always need to be put into a broad socioeconomic context. The beneficiary workshops demonstrated beyond doubt that, for the beneficiaries, economic activities, markets, human resources, health, education, and technology are inter-related and could be addressed in a transport project. Many benefits were perceived after a project was completed (para 3.11). If such important results are ignored, the project's benefits are misunderstood and the learning effects overlooked. Viewing projects as experiments and observing its results allows for social learning-and development. Markets and services cannot develop without a good transport system, and training and technology are critical for meaningful improvements in the functioning of markets and social services. Beyond the immediate beneficiaries, civil society, especially universities and think tanks, also need to become involved to study and analyze all aspects of projects viewed as experiments. This multi-layered approach informs the public debate and increases the cohesion of the society. The project did this admirably, but more could be done. * Structure participation as progressive and continuous dialogue. Despite some acknowledged flaws in the project's dialogue-some people felt left out or at least not heard, and at least one mayor excluded women from the dialogue-participation in this project worked. Participation worked in this project because it was not a one-time effort but continuous dialogue from start to finish. An analogue clarifies this. Computerization that merely automated processes without adapting them is less likely to result in expected productivity improvements. Similarly, community participation is most likely to bring the expected productivity improvements if it is a continuous process. Community participation that is done only at the beginning of a project to define it but that leaves the project processes unchanged, vulgarizes the notion of participation. Progressive dialogue, as done in RRRMP, recognizes that participation is a learning process and a way to shape the product and the outcome. Continuous participation can also reduce transaction costs of participation for subsequent projects, because once all parties are on board, there is no need to start out all over again in organizing participation for entry. * Interactions with the borrower and beneficiaries should take place in terms that they understand and in a context they set' Although it is part of the Bank's ethos to display 19. The word 'experiment' should be understood in a complex scientific sense where the experimenters and observers (the lender and the borrower) are part of the experiment. The dimensions of the experiment's outcome are unknown, affected by the experimenters and observers themselves and who, furthermore, are part of the outcome. A peer reviewer elaborated on why a project should be seen as an experiment as follows\. the experimental nature of projects is that they can be both learning tools as well as pilots. By providing the opportunity to work, projects allow the client to 'learn-by-doing'. And once the learning happens, a certain human capital is accumulated to allow development to take place on a larger scale. In the transport sector, this would mean that the client uses projects to learn on how to organize the transport system and to use this experience to restructure the sector to make it responsive to the development needs of the country. Hirschman's concept of 'the centrality of side-effects' also supports the idea of projects as experiments. Hirschman (1967) Development projects observed. World Bank Vice-President Callisto Madavo (New York Times, May 12, 2001) called the recently approved oil-pipeline project in Chad an experiment in the sense recommended in this assessment. 20. Several times workshop participants told the PMU and Bank and IDB staff thank you for coming into our world. expertise and mastery and give advice, it is preferable not to do so. This project demonstrated a better way\. learn how the client (or the group) thinks and what motivates the client by asking questions (called contact functioning in the literature). New ideas, such as competition or the Bank's procurement procedures can be introduced indirectly, on the job (as was done in this project) and with questions at opportune moments. This can be difficult. In the early community participation events, attendees had difficulty thinking in terms of objectives, strategies, and outcomes. It is not known how much the introduction of foreign thinking affected the final product. This may seem a fine point, but it is important and must not be ignored. It would have been possible-but probably not as easy-to follow the contact function and the line of thinking of the participants. * Watch for the huge problem and allow a measure offlexibility in the objectives. In the workshops conducted for the Learning ICR, Peru was said not to have many problems, but rather a single huge problem that is cross-sectoral, interconnected, difficult to quantify, and about which perceptions change. A single project, such as the rural transport project, can be part of the solution to such a problem only if it allows for flexibility in its intermediate outcomes. But such a conception is somewhat at odds with the logical framework, which tends to reinforce particular intermediate outcomes as the only route to an expected result. Using participatory approaches, the core of the problem can be conceptualized and the project designed to begin scaling toward its solution. This was done in RRRMP. By using participation on a continuous basis to discuss problems and select investments, the project in effect brought cross-sectoral influences to bear on the outputs and outcomes. In RRRMP most objectives were quantifiable, but leeway was allowed in how to measure their achievement, although the connection between an objective and its monitorable indicators was not clear cut.22 * Continuous analysis and patient listening will more likely lead to success than will yoo mechanistic a focus on achieving results. An excessively narrow focus on achieving results diverts attention from the problems and prevents the achievement of the results. The key is to analyze the resistances and problems that stand in the way of making good decisions. This project provides many examples that demonstrate the validity of this lesson. For example, in the cofinancing discussions, the desired result of 35 percent share was not the central concern. The central concerns were analyses of what prevented the municipalities from assuming that responsibility, what where the (many) implications, and what had to happen for them to maintain the roads using competition as the mode of work.23 Project issues-such as the cofinancing issue-should be explored and analyzed 21. This does not mean that World Bank professionals should not be experts. They should be broadly competent experts and professionals. The issue raised here is how this expertise is used\. the technique of how to work with the client. 22. When the size of the project is known, it is often a straightforward task to calculate the jobs generated and the number of kilometers to be maintained or rehabilitated. Though important, these output indicators are less relevant to success that an indicator of outcome, such as reduced transport costs. However, the indicator used in this project, a 30 percent reduction in freight tariffs, was difficult to measure and was not achieved. Clearly, without engaging in further discussion, these-r the other-logframe objectives and indicators hardly had much impact on the project's implementation, they merely defined it; the logframe's most important use was as the organizing concept for tracking the implementation progress. 23. This last sentence introduces an important dimension to analysis\. it is a vehicle to introduce new ideas-such as competition and entry to market. It is also acknowledged in this context that it is difficult (for Bank management) to ignore results because it blurs accountability and because the Borrower may opt for actions leading to results that the Bank (management) has difficulty in accepting. Nonetheless, if after substantial, skillfully conducted discussions, the Borrower opts for actions that the Bank (management) does not agree with, the Bank can refuse cooperating in such project. However, it is worth minding that actions and results desired have cultural underpinnings and it may not be together in the participation meetings, and designs or approaches changed to meet the needs of the beneficiaries (as was done), alternatively, the beneficiaries may find it to be in their interest to change. If it is believed that a bad decision is being made, the best approach is to try to prevent it by postponing, acknowledging the validity of decisionmakers' or community's views on the matter, and engaging them to discuss and analyze the issues. Pushing for decisions and convincing the client are counterproductive in the long run. Decisions are made when they can be made, and the borrower should make them, freely, only when ready to do so. Again the referenced cofinancing meeting was an excellent example of not acting hastily or demanding decisions.' Explore with the stakeholders why something succeeded or failed to define benefits and costs. It is important that the Bank (staff) and the borrower attempt to say why something worked or failed (e.g., to achieve a time-bound objective). Successes and failures never have one cause. In this way all factors bearing on success or failure become known or at least suspect. Even successes may have a dark side. For example, the success of this project was widely recognized during the Learning ICR mission. Still, both direct beneficiaries and academic researchers raised the issue of aid dependency. Aid dependency was recognized as a serious problem that can prevent self-directed solutions. Although awareness does not prevent or cure aid dependency, acknowledging the validity of the issue is the first step to cure. Another issue that merits examination in the present project is the popularity of the non-motorized transport tracks. The tracks were associated with low impacts and perceived instability of income, yet they seemed hugely popular. Why? There must be perceived benefits. More broadly, exploring successes and failures together helps define all benefits and costs. As indicated (para. 3.11), the beneficiary workshops gave a much broader picture of project benefits than what is normally calculated in standard benefit-cost analyses. Change is caused by emotional communications, rarely by interpretations or facts. The final lesson returns to the question the team leader posed during the Learning ICR mission\. what causes change? This project, consciously or not, was guided from the beginning by the notion of two kinds of changes\. alloplastic change (the material, external world is changed, leading to changes in perceptions and choices) and autoplastic change (the non-material, inner world is changed, also leading to changes in perceptions and choices). This was implicit in the workshop discussions and explicitly acknowledged and discussed in the think tank meeting. There is knowledge of how to make alloplastic changes, but there is less knowledge about what motivates autoplastic changes that precede the former. The academic tradition believes that facts and intellectual education consistent with the Bank's values to pursue results with such single-mindedness that lead to cultural homogenization (even though some degree of cultural homogenization is inevitable). 24. This lesson is subtle in its workings. An example clarifies. Recently, a consultant working on ministry restructuring was at an impasse. The client wanted something that, we agreed, was not good governance. He asked me what constituted success in that project because he had a deadline. I told him that we had time and he should quit pushing the minister and his staff to agree with him and to decide. Instead of trying to convince, he should work to prevent the minister from making a bad decision, which he was about to do. He could do this by agreeing with the minister and his staff by telling them that there are many unresolved issues and the matter is not ready for decision. These should be explored and discussed more. About a month later the consultant called and told me that the minister is ready to make a good decision and now wants his help to get it thorough the parliament! A hypothesis is that my readiness to accept delay was the right kind of emotional communication that removed pressure from the consultant who was then able to work effectively and with less pressure on the minister and his staff. . Often the Bank works with results-oriented, time-bound action plans. This is counterproductive and rarely works. Even when the results are achieved they are normally short-lived or attended by undesirable side effects. cause changes in perceptions and behaviors. Recent research casts doubt on such belief and supports emotional education and emotional communication as the mechanism of change. The issue is how can emotional communications be developed and used scientifically and without coercion? Without reviewing the literature on the matter hereit does exist-it suffices to note that before emotional communications are possible the transport analyst needs to learn how the client thinks, what motivates him, and everything about the problems and issues; in short, continuous dialogue and the development of long-term relationships are prerequisites for emotional communication. The RRRMP project pursued an extensive participation program complemented with academic studies. This approach is appropriate and justifiable. That is a good beginning. More research is needed to understand better change processes and the attendant ethical issues. 4.2 The assessment concludes with three specific lessons\. * A PMU is more than the manager ofprocurement and the Special Account. The Bank requires financial management and procurement assessments and certification of the PMU competence in both. This project demonstrates amply that these attributes of the PMU, while desirable, fall far short of what is needed. The PMU director needs to be a spokesman for the project, an active negotiator for coordination of intersectoral interests, and above all, provide visible leadership and know the spokesmen of the project's beneficiaries and become known to the beneficiaries for his work. The PERT-PCR has assumed and developed into such a role. Part of the success of the project must surely be ascribed to the PERT-PCR leadership and to its excellent and personal relationships with the beneficiaries. * A good project monitoring system is necessary for its management. Any project needs a database and accurate records in the background to support management. The RRRMP had both comprehensive and specific objectives. The PMU project information and monitoring system supported and served both types of objectives. The Operational Manual defined uniform guidelines and procedures for the execution of the project. Without such a database and manual, it would have been impossible to hold the RRRMP together, which covered 12 provinces and hundreds of projects, employed numerous consultants and contractors, and arranged several coordination meetings with multiple groups of beneficiaries. Data collection for the database is also good way to learn and it informs the management team of its beneficiaries and tasks. * The unfinished decentralization agenda remains an important issue and should be pursued. Although the change from centralized to decentralized road management cannot be done top-down, it should be compatible with the administrative structure of the general-purpose government. Decentralizing a road administration also requires a process that is incremental and appropriate to a country's development stage to match both the perceived needs and the institutional capacity. It must be accompanied with stable and predictable financing and fair mechanisms for allocating the road budget between areas and road classes and road programs. The previous attempt at road sector decentralization in Peru failed because the transfer of road ownership was not accompanied with a budget and human resources or institutional capacity to manage the roads, only responsibility for road management was transferred. This equation does not hold true. 25. Of course people in advertising, the arts, religion, and politics have known this all along. Facts and data can also be emotional communications, especially after long (emotionally involved) study of a subject matter, which normally includes a personal relationship. 4.3 This project is consistent with an emerging paradigm for transport planning and (economic) development (Willson 2001). It recognizes the fluidity of values, the dependency between ends and means, and the centrality of putting experiences and perceptions into wordsparticipation-for demand-driven change. For the Bank to be effective its satff needs to be open to new ways of doing things, experiment, observe, and assist in change by being and using doctors, content experts, and process consultants (Schein 1990). This RRRMP project is novel and innovative. The lessons learned outlined how a new approach, a new model of working with the client for development, evolved during project. The essential features of the model were\. view the project as an experiment; engage in continuous dialogue with the borrower; interact with the borrower and beneficiaries in terms that they understand and in a context they set; watch for the huge problem and allow flexibility in the objectives; focus on analyzing problems, not achieving results; explore failures and successes together with the borrower; and finally, learn to use emotional communication for facilitating change. This is the idea side. On the practical side, the PMU must show leadership and be a spokesman for the project, be capable for conducting sectoral and intersectoral negotiations, and establish good relations with the spokesmen of the stakeholders. In the background, the PMU must have an excellent project information and management system to keep track of the project. And finally, the PMU must quietly look ahead and prepare to tackle the sector's priorities, the unfinished agenda. Final Word 4.4 The RRRMP is a path-breaking and innovative experiment with interesting and promising results. It should become an example and an experiment for institutional learning. It also is deserving of recognition. All the partners in the project share this recognition\. the Bank team and the IDB team who conceived and supervised the project together, the PMU and the country office who managed the project, and the beneficiaries who cooperated and owned the project. Much work remains. It would be desirable for the Bank to remain connected and continue working with the borrower and the beneficiaries because autoplastic changes require time. It is a reassuring signal that the government of Peru regards this project as important and, despite the present political turmoil, wants to go ahead with its successor project.
P037049 | AR PUB.INV.STRENGTHG | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1996 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/847911474487989351/text/000020051-20140618064220.txt | http://documents.worldbank.org/curated/en/847911474487989351/pdf/000020051-20140618064220.pdf | 1. Although in this specific case the project contributed to maintain the Bank/Borrower dialogue during a highly volatile political situation, there are cases when it might be appropriate to cancel a project when too many operational difficulties and/or too long delays arise. 2.M&E Indicators should be linked to the objectives and defined as allowing measuring progress in outcomes in qualitative and quantitative terms.
P037079 | PH - AGRARIAN REFORM COMM | East Asia and Pacific | Philippines | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/936831474657966554/text/000020051-20140612144346.txt | http://documents.worldbank.org/curated/en/936831474657966554/pdf/000020051-20140612144346.pdf | The eligibility criteria for communities to participate in a project of this nature can be designed to maximize the likelihood of long-term development impact, particularly by favoring local governments willing to assume responsibility for counterpart funding--although this circumscribes the pool of potential beneficiaries (the poorest may be left out) it helps to ensure sustainability; It is possible to simultaneously build up, in a complementary fashion, the capacity of community groups on the one hand, and local government on the other, thus avoiding the tendency of many community-driven development projects to sideline existing political institutions;Sustainability can be enhanced by using local inspectors to monitor subproject performance and by providing conditional local government grants that are converted into loans if the operation and maintenance of completed subprojects is not satisfactory;The transition to regular operations will be facilitated when, as in this case, project activities are coordinated by line agency staff in line with the government's regular program.
P037086 | Thailand Metropolitan Distribution Reinforcement | East Asia and Pacific | Thailand | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/606781474939638981/text/000020051-20140612102623.txt | http://documents.worldbank.org/curated/en/606781474939638981/pdf/000020051-20140612102623.pdf | Projects to restructure, corporatize and privatize a utility should incorporate the flexibility to respond to changes in Government policy.When economic and financial crisis strikes a country, utilities need to take timely and drastic measures to restructure their investment plans, exercise greater financial discipline and improve operational efficiency.Active support rather than reluctant acquiescence of utilities is necessary to push through a complex reform agenda.
P037088 | KH-SOCIAL FUND (Project closed) | East Asia and Pacific | Cambodia | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1995 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/651691474562529975/text/000020051-20140529203626.txt | http://documents.worldbank.org/curated/en/651691474562529975/pdf/000020051-20140529203626.pdf | (a) Sustained efforts through project identification and implementation are needed to ensure community driven demand for sub-projects.(b) The agency needed to strengthen its management and technical skills to adequately handle larger and more complex projects, as well as the smaller average project. More attention needed to be paid to the cost/ benefit analysis and poverty alleviation potential of more complex and costly ventures. (c) The development of systems to proactively deal with problems such as sub-project technical defects, design shortcomings, and delays in completion and handover is important. A system of site checks and close monitoring of the work of internal agency and external staff is critical.(d) Communities benefiting from sub-projects need to be effectively mobilized from project initiation through the project post-completion period to ensure sustainability.(e) The role of local and provincial authorities in supporting sub-projects also needs to be strengthened to ensure sustainability in particular project operation and maintenance resources. (f) A comprehensive system for monitoring project impact which would include rapid evaluation of completed projects, would provide important information to all participants in the sub-project evaluation and implementation process.(g) Better coordination with NGOs and beneficiary communities would also strengthen the impact of projects financed by the Social Fund.
P037095 | MALUKU REG. DEV | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/322201474649166656/text/000020051-20140604042245.txt | http://documents.worldbank.org/curated/en/322201474649166656/pdf/000020051-20140604042245.pdf | The PCN derives the following lessons: (i) Complex projects with geographically dispersed characteristics could be more successfully implemented at a more decentralized level; (ii) Coordination mechanisms should be priority aspects for regionally oriented development project designs; (iii) Project management and supervision decisions taken by the Bank and clients require corporate continuity and consistency in approach to assist project performance; (iv) Implementation readiness at all levels needs to be determined and strengthened before activities start; (v) Post-conflict reviews and/or assessments of needs and sector rehabilitation potential would provide longer-term planning benefit to the client and the Bank for loan projects closed because of civil unrest.
P037097 | ID-EAST JAVA & NTT JR. SECONDARY EDUC. | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2004 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/272091474649909980/text/000020051-20140613060723.txt | http://documents.worldbank.org/curated/en/272091474649909980/pdf/000020051-20140613060723.pdf | During times of financial crisis, or political change, flexible supervision allows the potential for rapid restructuring as the need arises so the project can be re-oriented toward changing needs.Decentralization proved to allow a more effective use of resources, and proceeded without too many problems once the institutional context was in place. However, within the framework of decentralization, central government has a role in targeting strategies to address the educational needs of the poorest communities if national goals for basic education are to be achieved.There are advantages in cost effectiveness and efficiency when several similar projects are funded concurrently, with similar PDOs and KPIs, and managed as a single program rather than as separate projects.The establishment of a strongly staffed, and well managed project implementation unit (PIU) can be a key contributing factor to successful implementation.The experience of the Scholarship Grants Program (SGP) provides lessons on using scholarships to respond to a crisis situation. During the financial crisis the dropout rate has been low in primary school and that the transition to junior secondary school is the most important attrition point in the system, particularly for the poor. This suggests that the program was most effective in its support of the critical transition from primary to junior secondary education. This finding would suggest that: (a) there can be some narrowly targeted scholarships for the poorest children at the primary level, but the bulk of the program should be more broadly focused on junior secondary school; and (c) the pool of candidates for grade 7 scholarships has to be taken from children who complete primary school not from those who are already enrolled in grade 7.
P037097 | ID-EAST JAVA & NTT JR. SECONDARY EDUC. | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1996 | 2004 | 2006 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/439611468039272095/text/36427.txt | http://documents.worldbank.org/curated/en/439611468039272095/pdf/36427.pdf | 5. Lessons 5.1 This assessment confirms a number of IEG lessons from the education sector\. It is possible to target successfullypoor areas for interventions aimed at increasingenrollments, even in times of financial crises. Scholarships administered to the poor and disbursed to them promptlymay be effective in sustainingenrollmentsand preventing dropout (para. 2.17, Annex C) Community involvementmay be cost-effective and reliable means to build and support schools, particularly when the population has basic education and poverty is not extreme. Nevertheless, school committeemembers may not be able or willing to keep school expenditureslow, maynot have much time to spend on school affairs, and may be unable to advise the principal effectively on educational matters (para.2.27) Decentralization pronlotes effectiveuse of resources. However, not all local authoritiesare equally competent or interestedin educatingthe poor. A central government may find it necessaryto meet the basic educationalneeds of the poorest communities directly if national goals for basic educationare to be achieved (para.2.26) International assessmentsmay provide critical feedback to governmentsinterested in increasingthe competitiveness of their human capital. They may alsoprovide means to help countriesimprovetheirperformance (paras. 2.23,4.3).
P037156 | IODINE DEFICIENCY DISORDERS CONTROL | East Asia and Pacific | China | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/544491474595105005/text/000020051-20140604042547.txt | http://documents.worldbank.org/curated/en/544491474595105005/pdf/000020051-20140604042547.pdf | The ICR includes a range of lessons for China and other countries addressing IDD. This project also was reviewed as part of an OED study of the Bank's experience in addressing IDD. Some major lessons include:Salt iodization is a highly cost-effective means to reduce iodine deficiency, but the approach and strategy for iodization must be aligned with the structure and incentives of the country's salt industry. China's IDD program was successful because it gave a central role to the salt industry, and aligned industry objectives with a social objective -- rather than working exclusively through the health sector. State control over the salt industry (through licensing, quotas and other regulations) facilitated implementation, however; different approaches may be necessary in countries with a large number informal salt producers and distributors, and/or with weaker regulatory capacity.Effective IDD campaigns should be based on a comprehensive approach, including analysis of national IDD status; awareness building among political leaders and stakeholders; market and social analysis of consumer preferences regarding iodized salt; development of a strategy identifying key interventions, responsibilities of implementing agencies and partners, and coordination mechanisms; and a program of technical assistance through local and international agencies. In China, sound scientific analysis of IDD greatly helped in generating high level and multisectoral support.Attention to developing appropriate monitoring indicators and enforcement mechanisms is also essential, as well as identifying the appropriate institutional "home" for these functions. Industry and MOH initially had different methods, standards, and definitions for reporting and monitoring iodine concetration in salt, which have since been resolved. The salt industry is now responsible for its own quality control, while the MOH monitors compliance, and tracks population trends in IDD. Although there was no formal project partnership with UNICEF, the Bank signed Memoranda of Understanding (MOUs) with UNICEF and three other UN agencies to clarify roles and responsibilities under the National IDD Elimination Program. This contributed to a high level of cooperation, which was sustained throughout the project.
P037294 | Third Road Rehabilitation & Maintenance | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 1999 | 2006 | 2006 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/767561474482492115/text/000020051-20140615095053.txt | http://documents.worldbank.org/curated/en/767561474482492115/pdf/000020051-20140615095053.pdf | Building capacity is only likely to lead to sustainable change if accompanied by parallel public administration reforms and if backed by real government commitment to reform.Institutional development needs to be properly monitored with measurable performance indicators related to outcomes and not just outputs.The independent "engineer" role of the lead consultants in respect of their obligations of quality and certification should be separated from that of the "employer" in accordance with international practice.
P037339 | Podhale Geothermal District Heating & Environment Project | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/990621474572145330/text/000020051-20140613075703.txt | http://documents.worldbank.org/curated/en/990621474572145330/pdf/000020051-20140613075703.pdf | It would be difficult to add much to the 27 project-specific lessons set out in Section 8 of the ICR. Some general principles of wider application might be:1. While geothermal heat projects may appear relatively straightforward, this may not be the case in practice. They need a robust business plan, an implementing agency with construction experience and financial know-how and sufficient working capital to provide a cushion against unforeseen events.2. While geothermal projects may be competitive with fossil fuels when global benefits are monetized, they will not be financially viable unless grants are provided (from GEF or elsewhere) to cover incremental global costs.3. Governments should not undercut their renewable energy policies with royalties and other taxes.
P037575 | MUNICIPAL SUPPORT | Western and Central Africa | Cote d'Ivoire | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2004 | 2005 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/413911474596621414/text/000020051-20140613040328.txt | http://documents.worldbank.org/curated/en/413911474596621414/pdf/000020051-20140613040328.pdf | The relationship between poverty alleviation and economic development on the one hand, and the promotion of employment, participation of the local private sector and decentralized delivery of services on the other, must be clearly transmitted to the authorities at the local level. The project could not solidly establish an institution which would promote these concepts within municipalities and the municipalities have not yet understood the necessity for establishing partnerships with the private sector or of developing an orientation towards essential urban services, which is compromising the sustainable use of the infrastructure.Participatory project management increases the likelihood of successful completion and durability of infrastructure investments. The sub-projects for priority urban works which applied these arrangements for beneficiary participation obtained the best results in terms of meeting deadlines, quality of works and use of investments. In contrast, the components which were administered and financially managed from the central level met with many problems and needed several extensions.Elected heads of local government can be a strong driving force to promote the decentralized provision of infrastructure services. In this project, mayors were an important driving force for decentralized service delivery when they realized that their constituents judged them by how well they succeeded in providing essential urban services.Effective technical supervision of infrastructure works carried out under subprojects is critical to ensure their quality and sustainable usage. Outputs were not adequately monitored in this project, mainly because the supervision consultants were inexperienced, and technical audits carried out at the end of the project revealed that a significant portion of works and equipment was of poor quality or not in use. Improving technical supervision, either through training and capacity building to create a pool of experienced consultants or regular technical audits during implementation, is critical to overcome this problem.Projects should be simple and focused, particularly when it is venturing into an area in which the borrower has limited experience. Local governments had limited experience with demand-driven delivery of infrastructure services and because the project had too many objectives, components and sub-components, the project implementation unit in particular was overwhelmed and could not provide sufficient assistance, monitoring and supervision to the municipal activities supported by the project.
P037580 | BJ-GEF Nat Parks Cnsv & Mgmt SIL (FY00) | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/841491475072089151/text/000020051-20140615111820.txt | http://documents.worldbank.org/curated/en/841491475072089151/pdf/000020051-20140615111820.pdf | Conservation trust funds should be considered against simpler means of securing recurrent cost financing and should not supplant the need for long term political commitment by governments for long term recurrent budget support for the management of protected areas, their surrounding areas and human needs. The benefits of establishing a conservation trust fund should be weighed against the complex financial and administrative arrangements required as well as the opportunity cost of tying up a substantial level of capital if only very small amounts of net income are expected to be generated. The design of Multi-donor environment programs should consider whether preparatory grants and technical assistance activities are needed to help strengthen the capacity of a national or local implementing agency to manage donor coordination and consultation during the envisioned project period. Even so, a common results framework and financing plan increases the manageability of the program for the country and increases accountability among donors for overall results.
P037581 | IVC:EXPORT PROMOTION AND | Western and Central Africa | Cote d'Ivoire | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1995 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/851911474849252372/text/000020051-20140612102231.txt | http://documents.worldbank.org/curated/en/851911474849252372/pdf/000020051-20140612102231.pdf | Pilot schemes are a good way to sensitize intended beneficiaries. The project was preceded by a successful pilot phase designed with participation from the intended beneficiaries -- the private agribusiness sector and small farmers.
P037582 | AG SEC MGT PROJECT | Eastern and Southern Africa | Uganda | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1996 | 2002 | 2005 | ICRR | Less than 10 million |  | Unsatisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/777881474652301565/text/000020051-20140612153649.txt | http://documents.worldbank.org/curated/en/777881474652301565/pdf/000020051-20140612153649.pdf | The ICN draws no lessons.
P037588 | IVC:AGRIC. SVCS. II | Western and Central Africa | Cote d'Ivoire | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1999 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/392541474657579307/text/000020051-20140612102317.txt | http://documents.worldbank.org/curated/en/392541474657579307/pdf/000020051-20140612102317.pdf | The ICR states a series of lessons learned, but these are generally more assertions than lessons, e.g. publicly financed/publicly managed agricultural services do not work Project experience does suggest one key lesson: Functional independence does insulate an organization from political paralysis and enable actions to be taken even under adverse economic and social conditions, even if operations have to be scaled back.
P037709 | HN/SOC INV FUND III | Latin America and Caribbean | Honduras | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2000 | 2001 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/440871474944022931/text/000020051-20140529071938.txt | http://documents.worldbank.org/curated/en/440871474944022931/pdf/000020051-20140529071938.pdf | 1. An organization that delivers physical infrastructure effectively cannot automatically be assumed to be equally effective at undertaking social assistance or services projects and dealing with issues of utilization, behavioral responses, and community participation. Special procedures and staffing will generally be necessary and will require adequate investments in technical assistance, training, and piloting.2. Adequate coordination among those responsible for the operation/staffing of the infrastructure built/rehabilitated by the social fund is crucial for the effective operation and sustainability of the infrastructure and requires a conscious and timely effort.3. A well-designed Management Information System including monitoring and evaluation is essential to assess social fund expenditures and impact and to be able to take follow-up action.4. Greater attention than in the past is needed to defining the intended development impact of social fund projects and to understanding the relationship between physical inputs (such as capital construction) and the other necessary inputs for getting the desired results (such as community involvement and revenue funding).
P037709 | HN/SOC INV FUND III | Latin America and Caribbean | Honduras | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2000 | 2006 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/397491468249687503/text/36592.txt | http://documents.worldbank.org/curated/en/397491468249687503/pdf/36592.pdf | 4. Lessons Three lessons are identified here. Lessonl\. While social funds are attractive for donors and can initially be successful in providing remote communities access to basic health and educational facilities, the experience o f the Honduras social fund shows that they are not a long-term sustainable solution for providing basic infrastructure. The maintenance issue, especially o f health and education facilities, goes beyond social funds and needs to be seriously addressed as a part o f the overall policy dialogue o f the Bank with the country. Social funds may contribute by training o f user committees, but that in itself can never be sufficient for securing maintenance. Lesson 2\. Because o f the apparent success in i t s core activity o f financing basic infrastructure projects, FHIS has been and continues to be attractive for donors for programs that do not belong to the core activity (example, the Basic Needs Program that involved funding for priority social programs in nutrition, childcare, training o f midwives, care for elderly and disabled, etc. and the Nuestras Rakes Program which involved social assistance for indigenous communities). However i t took much longer for the Basic Needs Program and the Nuestras Rakes Program t o achieve some efficacy. Currently FHIS has become a patchwork o f donor-financed programs. Donors should be cautious in channeling money to social funds for carrying out non-core activities. Lesson 3 \. FHIS had a positive institutional development impact in promoting decentralization by helping to strengthen local government capacities in project planning and implementation. However, once these capacities are strengthened, i t can be questioned whether donors should s t i l l fund small infrastructure projects through FHIS instead o f searching for more direct channels to finance local governments.
P037827 | NORTHERN HEALTH | South Asia | Pakistan | Blend |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/292841474906537358/text/000020051-20140602112318.txt | http://documents.worldbank.org/curated/en/292841474906537358/pdf/000020051-20140602112318.pdf | Substantive involvement of the Ministries of Finance and Planning during preparation may avoid subsequent funding shortfalls and contribute to sustainability. Projects that heavily involve NGOs in partnership with government can be successful, particularly if those NGOs have acknowledged competencies and are involved early in the design phase. Baseline performance indicators and interim benchmarks should be identified at appraisal and regularly tracked in supervision as well as used in final evaluation; these indicators should be for intermediate outcomes, rather than population-level impact. Gender priorities in health projects are important to articulate in project design, can be met in project implementation, and can result in increased MCH/FP service use.
P037828 | Parana Rural Poverty Alleviation & Natural Resources Management Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/263471474632462623/text/000020051-20140615114232.txt | http://documents.worldbank.org/curated/en/263471474632462623/pdf/000020051-20140615114232.pdf | The project illustrates a number of features that can be helpful when implementing community-based environmental management: Features found important for this project (by their presence or insufficient presence) were: (i) an enabling overall policy; (ii) clarity across all parties in operational modalities, a detailed operational manual and training being the usual needs; (iii) decentralized management under local governments; (iv)) some degree of financial contributions from the local governments; (v) substantial participation and buy-in from the community organizations, including significant contributions to investment (financial, labor, materials); (vi) substantial training across the board - for communities, local governments and involved agencies; (vii) timely review and provision of finances when sub-projects are ready; (viii) an MIS to keep track of project activities; (ix)) good coordination between involved implementing agencies; and, not least, an outcome focused MMonitoring and Evaluation Needs to Focus on Outcomes: Beyond a good Management Information System for monitoring physical progress, a project needs M&E to generate data on outcomes (i.e. in the case of this project, impacts on welfare and the environment)
P037834 | NORTHERN EDUCATION | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1998 | 2004 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/127771474563813813/text/000020051-20140612105039.txt | http://documents.worldbank.org/curated/en/127771474563813813/pdf/000020051-20140612105039.pdf | 1. A realistic assessment of implementation capacity, especially for project start-up, should be made to avoid delays in project implementation.2. Although the activities in NA and AJK had the same objectives, the activities themselves were different. The benefits of combining them in a single project are not evident. Project management may have benefitted from separate projects.3. It is advisable to have back up plans for co-financed activities essential to project design, lest the co-financier should not deliver.
P037835 | SOCIAL ACTION PRG II | South Asia | Pakistan | Blend |  | Human Development | Education | IDA | IPF | 1998 | 2002 | 2004 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/503021474496170707/text/000020051-20140612073332.txt | http://documents.worldbank.org/curated/en/503021474496170707/pdf/000020051-20140612073332.pdf | Based on the ICR, key lessons are: generating political commitment and ownership of a reform program requires consistent and continuing engagement with stakeholders in program preparation, design, and implementation. projects that aim to bring about significant institutional and governance reforms need to ensure changes in orientation and mindset, attitudes, work ethics, and even political culture if they are to have lasting impact. institutional reforms in specific sectors are difficult to implement without addressing issues of poor governance across the board.
P037857 | Health and Population Program Project | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/834851474484626004/text/000020051-20140613085624.txt | http://documents.worldbank.org/curated/en/834851474484626004/pdf/000020051-20140613085624.pdf | The first set of lessons relates to the use of the SWAp approach: (a) DP coordination is a difficult and time consuming task, requiring negotiating skills, leadership and presence in the field. A Code of Conduct with clear rules of engagement for coordination and management of the SWAp needs to be defined up-front, to ensure decisions are taken swiftly, that time is not consumed by numerous meetings to reach consensus, and tomaintain the focus of the program. Given the lack of experience with SWAps by both DPs and GoB, considerable time was spent on reaching agreements, as rules for engagement were not clear. (b) SWAps have to be carefully and diplomatically managed. Putting all â€œeggs in one basketâ€ means that the program can easily be derailed if both sides do not handle issues in a constructive manner.The experience of the project also holds lessons related to managing institutional development. In particular, not carrying out the necessary analyses of the political economy of reforms can lead to failure. Opposition needs to be identified, whether within the MOHFW, physicianâ€™s associations, other workerâ€™s associations, and users of the services themselves. Managing institutional change is a difficult process, and one that needs to take into account all stakeholders. Analyses should be made of what is at stake for everyone, and benefits for each need to be identified to bring them on board. They need to be consulted and convinced of the benefits of the process for them. Commitment to or at least understanding and agreement regarding the rationale for the institutional change sought could have been built among those most affected, and new elements could have been brought in as a result of negotiation with these stakeholders. Other lessons: (a) It is often assumed that the poor always opt for public services as they cannot afford private services. However, some are too poor even to consume government services as the costs are not always financial and when they are, they are not evident. As Service Delivery Surveys indicated, the very poor did not benefit from MOHFW services, as informal fees charged made it costly for them. (b) Participatory preparation, while enhancing ownership, can dilute the focus of a project design. A balance needs to be struck to ensure both goals are met. A review of the resulting proposal can be submitted to independent technical analysis for suggestions on how to improve the overall product without losing the key aspects of the design. (c) Project objectives need to be closely linked with program inputs and outputs, and the targets set need to be related to the capacity of the implementing entity. In this case, MOHFW services alone could not have improved maternal and child health. (d) An adequate risk management strategy is needed. Management of risks must be an essential part of the APRs and routine project supervision.
P037857 | Health and Population Program Project | South Asia | Bangladesh | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/784711468002177460/text/36564010BD.txt | http://documents.worldbank.org/curated/en/784711468002177460/pdf/36564010BD.pdf | 5. LESSONS LEARNED 5.1 Aid-financed health infrastructure can work in improving health outcomes.. . provided other conditions are inplace\. this PPARhas produced additional evidence in support o f the main argument o f IEG's impact evaluation that the creation o f an extensive health and family planningsystem inBangladesh, with considerable assistance from external finance, has made a demonstrable improvement to the healthoutcomes o f Bangladeshis. However, this success was achieved through the balanced growth o f infrastructure and appropriately trained staff, The experience o fthe community clinics shows that services will not be usedifthey lack resources or the skills o fthe staff are inadequate for what i s expected o f them. 5.2 Public andprivate provision are complementsnot substitutes\.The health demands o f Bangladeshis are met bybothpublic and private providers. These suppliers do not work inparallel, but Co-exist through various symbiotic relationships. 5.3 A SWAP takes time to implement and is an evolutionaryprocess. InBangladesh it can be said it took 20 years ofdonor coordinationto beginthe process o fimplementing a SWAP. It i s not feasible tojump from a project approach to fully-fledged SWAP overnight. Rather institutionsneedto evolve from one to the other, though a series o f interiminstitutionalarrangements.Thechanging way inwhich donor funds havebeen handled under FPHP, HPSP andHNPSP i s an example o f this. 5.4 Wide stakeholderparticipation inpreparation helps ownership but can weaken design.The broadparticipatoryprocessmade it difficult to prioritize, notably with respect to ESP. A compromise needbe sought betweenparticipation andtechnical guidance to working $goups inorder to maintain satisfactory quality at entry. 5.5 Think through the implications of the new system. The move to a SWAP implies a change inhow things are done for bothDPs and government inways which are often not well understood. It i s imperative to think through how systemswill actuallywork, andmake sure that all involvedunderstandthis. This process will necessarily take time. 5.6 Draw on the appropriate skills mix. Many aspects o fthe design and implementationof a SWAP do not fall withinthe competence o fhealth specialists. Thus, theneedfor appropriate expertise should berecognized anddrawn on. Bank staff should seek to draw on the Bank's experience with similar issues inother countries, making sure that local staff, DPs and government can all benefit from this experience. 5.7 Failure to assessfully thepolitical economy of reform and toprepare both a proactiveplanfor addressing/mitigatingrisks and a contingencyplan will considerably diminishprospectsfor successful reform. Ina politicked environment policy reversals are the norm not the exception. DPs should beprepared to adapt their approach\. maybe renaminginstitutions will suffice, but it may not be so. 5.8 Too much donorBank intervention can undermine government capacity and ownership of a SWAP approach. Preparation o fthe SWAP startedwith a highdegree o f local ownership. But the extensive role playedby donors inthe review process, and the importance o f the tasks which eventually fell to HPSO, but would have beenbetter carried out by government, reduced local ownership. 5.9 Be realistic in'tackling major reform objectives. HPSP combined the move to a SWAP withtwo major sets ofreforms\. unification and decentralisation, as well as the introduction o f a new tier o f service delivery at community level. This was rather a lot to hope to achieve ina single project. A more phased approachmay have yielded more lasting results ina less acrimonious manner.
P037960 | Treasury Modernization Project | Europe and Central Asia | Kazakhstan | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/326511474495976155/text/000020051-20140612073420.txt | http://documents.worldbank.org/curated/en/326511474495976155/pdf/000020051-20140612073420.pdf | (i)Better analysis of the political economy and institutional stake-holders might have mitigated the very slow start-up of the project. (ii) Close coordination from the design phase between the IMF and the Bank is important in achieving significant project impact. In this case, the IMF supported the design and implementation of the underlying legal framework and setting up of the Treasury as a separate organization under the MOF. (iii) Unwavering support from the MOF was critical in overcoming resistance from other powerful ministries who were reluctant to give up separate bank accounts.
P038021 | DPEP III (BIHAR and Jharkhand) | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/582041474946706017/text/India-District-Primary-Education-Project-DPEP-III-Bihar-and-Jharkhand.txt | http://documents.worldbank.org/curated/en/582041474946706017/pdf/000020051-20140617133401.pdf | 1. The DPEP model in India has the strength of focusing on both enrollment expansion and improved learning outcomes. The lesson from this project is that both can occur at the same time, even in some of the most difficult parts of the country. 2. Joint efforts and collaboration with many partners, including UN agencies like UNICEF (already deeply involved in basic education), NGOs, and women's organizations can greatly strengthen project effectiveness. 3. Project preparation for a comprehensive and complex intervention such as DPEP is challenging, especially in a state having relatively weak institutions and governance. In such an environment, it is especially important to undertake capacity assessments and to create robust strategies for addressing the multiple risks that can be anticipated. 4. Monitoring and evaluation design is important and flawed designs and systems can undermine a project's ability to reveal its strengths and accomplishments. For example, this project would have been much better served had it used gross or net enrollment rates to show improved access with breakdowns for all disadvantaged groups, including learning disabled and working children. 5. This and other DPEP projects have not yet dealt effectively with student retention (or dropout). Setting goals that are over-ambitious (like DPEP standard of pushing dropout to below 10 percent) is problematic, but it is no better to set goals which are too modest (like the current's goal which would still leave dropout above 50 percent). A reasonable level needs to be set, which is both practical and significant (pressing a state to reach universal primary completion in a reasonable time), and interventions developed which target areas where problems are especially acute, using strategies known to work.6. Household surveys conducted in the states are a promising means to demonstrate change in enrollments and dropout, avoiding the flaws in school system data bases. Used in a time series they can also help to sort out questions of attribution to particular interventions (like DPEP or SSA). It is important that these data be reconciled with the education data (EMIS) and that there be a differentiation between children who are dropouts and those who have never been to school. 7. There needs to be a clearer understanding of what contributes to the improvement of student learning outcomes. Many passages in the ICR seem to indicate that despite increased in-service teacher training under DPEP, most teachers have not abandoned their traditional approaches to instruction and rote learning. It is important to find out, therefore, what is the driving force in large increases in learning outcomes. It is also important to find out and deal with reasons for the almost negligible impact of the training on teacher performance. 8. Although the production of new, qualified teachers was not a goal of this project, the lack of a stream of new teachers became a significant constraint. The GOB and GOJ would be well advised to institutionalize systems for teacher production and deployment to remove teacher shortages as a constant deterrent to the reaching of EFA goals. 9. Supervision of projects with IDA funding needs to be expanded to cover financial management, since this is an area of vulnerability in many states, especially those with weak governance records. 10. With the maturation of the GOI's efforts to promote universal enrollment in quality primary education it is time for the government to create more impact-oriented program designs, providing managers with the data they need to be able to attribute change to specific project interventions and to determine where (among districts) strengths and weaknesses are evident (with a willingness to provide remediation where weaknesses are found). This would mean addressing the counterfactual in project designs and bringing India's strong analytical skills to bear on project efforts and impacts.
P038090 | Social Benefits Reform Administration Project | Europe and Central Asia | Slovak Republic |  | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2002 | 2008 | 2009 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/506751475084702902/text/000020051-20140619091438.txt | http://documents.worldbank.org/curated/en/506751475084702902/pdf/000020051-20140619091438.pdf | The following lessons presented in ICR are endorsed:Long preparation time combined with disagreements between the implementing agencies is an indication of potential problems during project implementation and calls for Quality-at-Entry check. Weak ownership is a key risk factor. Government and wider ownership should be assessed before designing a complex social reform project.Stalled projects due to lack Governmentâ€™s commitment are likely to fail. The Bank should seriously and promptly consider closing stalled project as an option. Bank TA for MIC is still a relevant and highly valued tool in the new EU countries provided TA is aligned with the countryâ€™s needs and delivered in a timely and appropriate manner. M&E indicators should be fully defined and agreed by the project teams ahead of implementation.
P038091 | Road Improvement & Traffic Safety Project | Europe and Central Asia | Turkiye | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/630161474512269794/text/000020051-20140612093432.txt | http://documents.worldbank.org/curated/en/630161474512269794/pdf/000020051-20140612093432.pdf | Where several organizations are involved in project conceptualization, it is sometimes advisable to adopt a "second best" solution if strong ownership is achieved through the compromise.It is difficult to resolve governance problems at project level and serious lack of trust issues should be escalated at an early stage if they are to be expected to lead to confrontation.
P038091 | Road Improvement & Traffic Safety Project | Europe and Central Asia | Turkiye | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2003 | 2005 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/557381468764972727/text/31520.txt | http://documents.worldbank.org/curated/en/557381468764972727/pdf/31520.pdf | 5. Conclusions and Lessons The Governance Issue 5.1 Achieving a satisfactory and genuine development partner relationship i s a major challenge, especially at the operational level. This i s the classic case where the implementing agency exhibitedrent-seekingbehavior and saw the Bank as a commercial rather than a development partner. Real change to address KGM's inefficiencies came about only after matters were brought to a head by a financial crisis, which helped focus the Treasury andPrime Ministryonthe eliminationofpoor practices that hadbecome accepted over the years. It illustrates that improvements ingovernance cannot always be achieved at project level and often requires a holistic approach. Today, the Bank gives greater prominence to poor governance issues andthese are increasinglybeingtackled through institutionalreformprojects that do not go forward unless backed by political will. The Request for a Loan Extension 5.2 Itwas a difficult decision to denythe loanextension and it is understandable that this call hadto bemade urgentlyduringa financial crisis. The decisionto reduce the size of the loan portfolio was jointly taken betweenthe Bank andthe Treasury and a clear message was also signaled that the problems and poor practices encountered at the operational level had to be eliminated. One could question whether the matter hadto be addressed insuch a radical way, since it created muchbitterness with KGMand its partners, but clearly a strong stance i s sometimes necessaryto bring about change and decisions o f this nature are always ajudgment call. The Traffic Safety Component 5.3 This component had some interestingfeatures. Iti s unusual for a road safety projectto have such a high level o fpolitical support and, even though the project was not completed as designed, it did achieve a great deal. The task team and the implementing agency showed great flexibility intailoring itto the NTSP andto ensuring there was strong local ownership. While the approach followed may not have been ideal intheory, the fact that aparticipatory opportunity existedfor all stakeholders to contribute ideas, more than compensated for this. It should also be mentionedthat KGMshowed strong leadership inensuringthat the diverse traffic safety team worked together successfully. The learningfrom this project could beuseful inother roadtraffic safety initiatives elsewhere and inparticular it is noted that very significant benefits can be derived from low-cost black spot improvements. 5.4 The following lessonsmay be drawn from the experience ofthis project\. P Improvements ingovernance can best be achievedwhenthere is a holistic program o f institutional reform mandated at the highest levels o f government, with interactive communication with operational staffto ensure that the changes take place inthe field as envisioned. Trafic safety projects can be particularly successful where there i s strong government commitment and support and where a participatory approach i s pursuedto ensurethe support of all the diverse stakeholders. The key to successi s to show what can be done and to have the right information, monitoring and evaluation systems inplace so that a nationalprogram can be rolled out and its success measured. The elimination of road accident black spots can be a highly cost effective way to reduce both the accident rate and the degree o f severity o f the accidents occurring.
P038092 | Social Reform Project | Europe and Central Asia | North Macedonia | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1995 | 2000 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/555901474748895218/text/000020051-20140528123109.txt | http://documents.worldbank.org/curated/en/555901474748895218/pdf/000020051-20140528123109.pdf | 1. Success of complex projects depends on Government commitment during appraisal and implementation, as well as the implementation performance of those directly involved in project implementation, in this case, the privatization agency where the PCU was established, the Employment Bureau and the Ministry of Labor and Social Protection. 2. The IBRD should emphasize the importance of public information campaigns with borrowers. These components in several countries are not achieving desired results, undermining support for the reform programs. 3. Gender aspects should explicitly enter the design of social reform projects and should be evaluated at project completion. The impact study for the labor redeployment fund (which includes gender analysis), integrated in the follow-up project will allow an assessment of the sustainability of project achievements. 4. Technical assistance works only when it is demand driven and should extend beyond the mere provision of equipment (as was the case in this project). 6. A general lesson emerging from TA that provides physical components is that the provision must take into account maintenance. The reforms appear likely to be sustained given the continued emphasis on labor restructuring, Government commitment and a follow-on project but equipment that the borrower cannot maintain can adversely affect sustainability. In Macedonia, implementation agencies that received computer equipment will have difficulty in maintaining and servicing the new systems because of a lack of financial resources. This problem is expected to be addressed in the next operation.
P038334 | RAJASTHAN POWER SECTOR RESTRUCTURING PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2006 | 2008 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/117391474850992418/text/000020051-20140617133030.txt | http://documents.worldbank.org/curated/en/117391474850992418/pdf/000020051-20140617133030.pdf | The main lessons are:1. The political viability of the reforms supported by the project should be established through extensive consultation with actual and potential political leaders. It is important to make sure of government commitment. A signed policy letter, while no guarantee, is nonetheless an important comfort for the Bank.2. Alternative approaches to achieving agreed policy goals should be carefully analyzed during preparation.3. In a large country like India, the country-wide context, including central government policy and recent developments in the power sectors of other States, should be examined and taken into account in project preparation.4. Project objectives should be determined realistically, in terms of what is likely to be achieved given the short life and limited leverage of a relatively small intervention.5. Risks to project outcome should be more carefully analyzed and taken into account. In particular, attention should be paid to climatic hazards and to subsidy regimes in other States and their likely impact on the political viability of proposed reforms.6. Broader policy issues, such as power subsidies for agriculture, should be addressed at the level of country policy dialogue since they will inevitably and significantly affect the outcome of projects such as this.7. Consumer subsidies should be clearly defined and transparent, adequately budgeted for, and provided by the government in a timely manner.8. Clear, user-friendly and quantitative M&E targets should be developed during project preparation and systematically used through project closure to measure the outcomes of the projectâ€™s goals. This is especially important when the objectives embrace an ambitious State-wide sector reform, as in this case.
P038334 | RAJASTHAN POWER SECTOR RESTRUCTURING PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2006 | 2010 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/346791468260122036/text/536210PPAR0P031IC0disclosed08121101.txt | http://documents.worldbank.org/curated/en/346791468260122036/pdf/536210PPAR0P031IC0disclosed08121101.pdf | 7. Lessons BOX 1 Selected Lessons from Power Sector Restructuring in Four Indian States Learning the Lessons Subsidized power supply to agriculture is a deeper public policy issue and not a from Similar Projects mere sectoral issue. The problem of subsidized power supply to agriculture and resistance to metering is embedded in distorted agricultural policies and political economy factors. Both the Bank and India have to recognize that sustainable 7.1 The RPSRP was not an improvement in power sector requires addressing this complex economic and political problem stemming from the agriculture sector. National consensus of the isolated exercise\. it was the political parties is necessary for a meaningful solution. While there is growing latest in a series of five Bank awareness and recognition of this issue, the progress is likely to remain modest in the next few years. (Andhra Pradesh ICR) projects supporting State level power sector restructuring (see Financial restructuring of the power utilities is akin to a bankruptcy proceeding where burden sharing by various stakeholders is required. The GOAP provided paragraph 2.4 above). The PAD substantial support for financial restructuring, but the support from financiers and (page 6) states that\. The project suppliers of power (central PSUs) was delayed. It was only recently in 2003 that the GO1 finalized a securitizationscheme to restructure the overdue liabilities of has been designed drawing from the state power companies to reinforce reforms. Until the full cost recovery the lessons learnt from through tariffs is achieved by the utilities, timely and full payment of subsidy support by the state government will be important to ensure adequate cash flow implementation of similar for the utilities to enable them to operate and maintain the power system. (Andhra programs in India (Orissa, Pradesh ICR). Haryana, Andhra Pradesh and The financial crisis of the power sector is so deep and the reforms initiated by Uttar Pradesh) and in other Haryana so comprehensive (and disruptive) that it would be difficult (if not impossible) to capture, over the initial two or three years of a reform program, and countries, adapted to local through standard financial covenants (profitability and financial performance of realities. This statement raises the utilities) any meaningful improvements. (Haryana ICR) an important issue concerning The scope and nature of reforms pursued under a loan should be consistent with the extent to which, or at least the lending instrument and firmly grounded in a realistic appreciation of the Bank's relative leverage in a given situation. This operation was an investment the speed with which, the Bank loan in which, by definition, disbursements were determined by contract does in fact learn from negative implementation and as such, ill-suited to serve as drivers of a contentious and challenging reform program. Reform expectations in this case were unrealistically experiences in other projects. high given the relatively short period of project implementation and even more so With regard to worldwide relative to the Bank's limited contribution to the utility's overall investment program. (Uttar Pradesh ICR) trends, a World Bank Board Discussion paper3' notes that\. Government should provide financial support for the subsidies made necessary by its policies. In particular, the subsidies of favored groups of consumers should be Following the post- 1997 sufficient to avoid creating pressures to increase cross-subsidies from other downturn in private investment, consumers (Box 14\. Lessons from Orissa from Besant-Jones op. cit., page 53). reforming countries have experienced particular difficulty in attracting and retaining private investors to their distribution businesses. Concerning the other four projects in India, the outcomes of three of them were rated as Unsatisfactory by their respective ICRs (table 1.1 of this report) mainly because of failure to carry out the necessary reforms needed to turn sector finances around and attract and retain private investors. 7.2 It could be argued that at the time of project preparation, in 1999 and 2000, the fill extent of the world wide aversion to private investment in power distribution in developing countries was not yet apparent. Moreover, none of the other four similar State power sector restructuring projects in India had yet closed. The latest information available to the RPSRP 30 Reforming Power Markets in Developing Countries\. What Have We Learned, by John E. Besant-Jones, Energy and Mining Sector Board Discussion Paper No. 19, September, 2006. The quotation is on page 48. appraisal team on the status of these projects was in the Supervision Reports which indicated, in all cases, a much more favorable situation than that which was later to prevail at closure31. 7.3 The same cannot be said regarding the knowledge available to the RPSRP's supervision team at the time of the MTR held in June, 2004. By then, international trends were clear, three of the four State restructuring projects had closed, and the other was to close within six months. Lessons fiom their implementation (Box 1) were available. From these lessons, and from experience to date with the RSPRP itself, it was clear that achievement of financial recovery was beyond the reach of the project and even highly unlikely to be achieved over a longer time period (say, by 2012). Indeed, with hindsight, it should not have been included as a PDO in the first place. In Rajasthan, as in the other four States, the preconditions were not present. These include (i) a nationwide resolution of the issue of power subsidies to the agricultural sector; (ii) a willingness by various stakeholders to share the financial burden; (iii) sufficient fiscal strength on the part of the State government to ensure full and timely payment of subsidies; (iv) recognition that financial recovery is a long term process; and (v) consistency between the reform goals and the Bank lending instrument supporting them. Opportunity could have been taken at the MTR to restructure the project and remove the objective. It is true that such a restructuring would have required Board approval, and this might have been difficult to obtain based on the experience of this project alone. Backed, however, with the lessons fiom the other four projects, a much stronger case could have been made. Lessons from the Design and Implementation of the RPSRP A thorough analysis should be made of the political economy of the reform program to be supported by the project, at both State and national levels. This should be done not only through extensive consultations at both a local and national level, but also through a realistic appraisal of national policies such as those determining power subsidies to agriculture which will impact on project outcomes. These should be addressed at the level of country policy dialogue. A careful assessment of international trends in power sector private investment in developing countries should also be part of the exercise. 31The latest Supervision Development Objective ratings available at the time of appraisal of the Rajasthan project and the ICR ratings at closure were as follows\. SpN ICR Orissa PSRP S U Haryana PSRP S U Andhra Pradesh PSRP S S Uttar Pradesh PSRP S U Risks to project outcome should be carefdly analyzed and taken into account. In particular, attention should be paid to climatic hazards and to subsidy regimes in other States and their likely impact on the political viability of proposed reforms. Covenanted objectives should reflect a more realistic judgment of the leverage accorded by investment projects on complex policy issues, and of factors outside the control of the project. In India, the recent appraisal of a new proposed operation in Haryana indicates that this lesson has been learned. More systematic monitoring of experience in other, similar projects (particularly in the same country) would have helped to avoid the repetition of over-ambitious design apparent in the five State power sector restructuring operations in India. Even though convincing evidence may not have been fully available at the preparation stage, the opportunity should have been taken during implementation to restructure and simplify the project when justified. Such monitoring would facilitate a clearer and more objective assessment of Development Objectives during supervision missions. It is noteworthy that in the case of all five State power sector restructuring projects in India, ISRs continued to rate DO progress as satisfactory when it must already have been obvious that certain objectives were highly unlikely to be attained. These satisfactory assessments were all that was available to the team preparing the Rajasthan project.
P038391 | EDUCATION REHABILITATION PROJECT | Europe and Central Asia | North Macedonia | IBRD |  | Human Development | Education | IDA | IPF | 1998 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/473031474907484177/text/000020051-20140604053912.txt | http://documents.worldbank.org/curated/en/473031474907484177/pdf/000020051-20140604053912.pdf | Heavy political control may negatively affect project implementation, particularly in cases where implementation capacity is limited. The Bank should insist on clear, performance-based hiring and firing criteria for project staff.- High-quality technical assistance that is focused on outcomes may create national technical expertise, particularly when counterpart staff are motivated, and when there are clear opportunities to apply the expertise. - Innovative components that require the development of new institutions (such as a teacher training resource center) may fail due to a lack of support from existing institutions. Rather than creating radical changes, capacity building for innovation might start within existing structures.
P038392 | Social Sectors Adjustment Loan | Europe and Central Asia | North Macedonia | IBRD |  | Human Development | Social Protection & Jobs | IDA | DPF | 1999 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/889881474505455895/text/000020051-20140529160920.txt | http://documents.worldbank.org/curated/en/889881474505455895/pdf/000020051-20140529160920.pdf | 1. Lifting labor mobility restrictions while simultaneously improving social assistance programs was important given an expected increase in layoffs with the planned closure of loss-making enterprises and the downsizing of public administration. 2. Parallel technical assistance and investment operations are important for the success of adjustment operations such as the SSAC.
P038393 | Structural Adjustment Loan & Credit (SAL/SAC) | Europe and Central Asia | North Macedonia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/697141474398427632/text/000020051-20140526224948.txt | http://documents.worldbank.org/curated/en/697141474398427632/pdf/000020051-20140526224948.pdf | In restructuring the agricultural sector, privatization--without fundamental changes in ownership/management, private business environment, and assistance to strengthen reforms including post-privatization enterprise support--may not fully achieve its expected benefits in terms of private sector growth and job creation.
P038395 | Water Utility Improvement Project | Europe and Central Asia | North Macedonia | IBRD |  | Sustainable Development | Water | IBRD | IPF | 2001 | 2003 | 2004 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/426211475070043606/text/000020051-20140612104455.txt | http://documents.worldbank.org/curated/en/426211475070043606/pdf/000020051-20140612104455.pdf | Projects should not be approved during periods of high political unrest just before general elections. It carries a high risk that the new government may not support the previous government's initiatives. Thus it is better to wait until after elections and embark on additional support-building for the concept, should that be necessary.A strategic communications strategy is essential to identify all stakeholders, to build and maintain support for politically sensitive projects.
P038399 | Irrigation Rehabilitation Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/376141474564497746/text/000020051-20140618080155.txt | http://documents.worldbank.org/curated/en/376141474564497746/pdf/000020051-20140618080155.pdf | 1. If a project's design is weak, major changes in design can pay off even when made late in project implementation. Major changes were made in the project's institutional arrangements during the last three years (and after the initial closing date) of project implementation: a new legal base for decentralized and participatory irrigation; liquidation of the Water Management Organizations (the originally intended main implementers of the project); and establishing new Water Economies, and Irrigation Water Communities. Resultantly, a failing project rapidly improved performance.2 Establishing an enabling legal base should be a a prior condition for a reform program. The 1998 Water Law established at the beginning of the project was inconsistent with the envisaged institutional reform program. This stalled institutional changes, also helping perpetuate the ineffective WMOs. It was not until 2004, less than 3 years before project closure, when new laws legitimized the new institutions and their respective roles. 3. When designing an institutional reform program, the political and economic motivations of involved institutions should be examined. The Water Management Organizations proved completely unsuitable to be Government's operational arm at field level. These inefficient government agencies had been allowed to function as unregulated monopolies, with high operating costs. Supporting farmer organizations was against their vested interests. Consequently, they were a disruptive rather than supportive influence. If an analysis of the political, social and financial motivations of the WMOs had been conducted during project preparation, alternative institutional arrangements could have been found.4. The productivity of irrigation investment can be further enhanced if the irrigation improvements are accompanied by improved agricultural extension. The project only focused on improving irrigation infrastructure and management. The ICR draws attention to other desirable improvements, including in agricultural advice, that could further boost the productivity of the irrigation investment.
P038404 | ODS Phaseout 2 Project under Montreal Protocol | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1996 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/447681474508409852/text/000020051-20140619080514.txt | http://documents.worldbank.org/curated/en/447681474508409852/pdf/000020051-20140619080514.pdf | IEG endorses the ICR's main lessons from the project:Continuity of Bank staff contributed to project success: From project approval in 1995 until completion in 2007, the World Bank Task Manager and the TTGV Project Manager remained the same. This resulted in substantial continuity of project knowledge, helped consensus building with the officials of pertinent government agencies, and an enhanced the ability to streamline project procedures.A nongovernmental organization can be effective in financial intermediation: TTGV possessed the technical and administrative knowledge to manage PODS-II effectively. The agencyâ€™s contacts with SMEs facilitated their promulgation of PODS requirements and identification of potential grant/loan applicants. Their experience in PODS-I was very helpful in understanding project requirements and facilitating contact with relevant GoT agencies.Building and maintaining inter-agency cooperation takes time and requires adequate resources: Although MoEF, MARA, and the Undersecretariat of Customs had collaborated during PODS-I, they required much time at the start of PODS-II to coordinate and reach a policy consensus with private businesses on the development of regulations and implementation of the National Ozone Plan. Through many interactions and meetings during PODS-II, their contacts improved greatly and became much more efficient.The private sector's timetables require faster actions compared to the long delays involved in donor project approval processes: The private participants viewed the timeframe for project approval as cumbersome. TTGV tried to speed up project review and approval both TTGV and the Bank. However, the process took many additional months when the funding applications were sent to the MP Executive Committee for approval as per MP procedures. Overall, the process required from 6 to 12 months, which was viewed as a very long delay especially by private applicants.
P038550 | Coal Sector Adjustment Loan | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1996 | 1998 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/366861474558223611/text/000020051-20140607155418.txt | http://documents.worldbank.org/curated/en/366861474558223611/pdf/000020051-20140607155418.pdf | Complex reform programs in difficult economic and political environment require time and flexibility;Government commitment and political will, and effective stakeholder participation are crucial in undertaking complex and politically contentious reform programs; and Field office staff can play an important role in ensuring the success of a major reform program through effective day-to-day management of operations.
P038550 | Coal Sector Adjustment Loan | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1996 | 1998 | 2003 | PPAR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/263461468781516840/text/260670RU0PPAR.txt | http://documents.worldbank.org/curated/en/263461468781516840/pdf/260670RU0PPAR.pdf | lessonsof generalapplicability in the caseof complex andpolitically contentiousreform programswith a high social impact\. l Governmentcommitment andpolitical will areindispensable. External financing in supportof coal restructuringin Russiaprovided apowerful incentive to staythe course,but the decisivefactor in securingsuccesswas the fundamental commitment of the Government. l Effective stakeholderparticipationcan greatlyenhancerobustnessof the achievementsandlessenthe implementationandinformation burdensof the Governmentandthe Bank. A particularstrengthof the designand implementationof both Coal SECALs wasthe constantattentionto and involvement of the variousrestructuringstakeholders,beginningwith the analytical sectorwork by the Bank andthe Government'ssectorpolicy statement in the yearsprecedingthe operations. l A strengthenedsafetynet helpsgreatlyin gaining acceptanceof enterprise closuresamongworkers andtheir communities, evenin difficult andpolarized situations. l Adequateattentionandfunding shouldbe devotedup front to the environmental aspectsof enterpriseclosures(especiallyin the caseof mines) to minimize the problem of largeresidualliabilities that may hold up the liquidation of enterprises that havealreadyceasedoperations. l Finally, implementation schedulesshouldbe realistic andflexible, while disbursementsshouldbe tailored to concreteprogressin agreedreforms. The Coal SECAL II wasunderimplementation for four yearsinsteadof the originally plannedtwo years,with most of theprogressrecordedin the lasttwo years. Moreover, the 1999restructuringof theloan's original floating tranchesinto smaller, more manageabletrancheswas instrumentalin facilitating implementation of the agreedrestructuringactions.
P038551 | Municipal Heating Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/453551475099660496/text/000020051-20140619103953.txt | http://documents.worldbank.org/curated/en/453551475099660496/pdf/000020051-20140619103953.pdf | Frequent changes in task team leaders (TTLs) should be avoided to the extent possible. If inevitable, mechanisms such as ensuring some overlap between TTLs, or other key staff or consultants should be put in place to ensure continuity in approaches to implementation and supervision of the project.The success of regional development programs is particularly dependent on strong local leadership, timely availability of counterpart funding, and local implementation capacity.Sub-loan arrangements can work better if the final beneficiary â€“ in this case the district heating company â€“ is given a say in financial decision-making by being included as a signatory to the agreement between the MOF and intermediary institutions â€“ in this case, Rosstroi, the Oblast Administration and the City Administration.The Results Framework and the accompanying performance indicators should be finalized ahead of project implementation. Otherwise, their role in decision-making and resource allocation will be limited.
P038569 | Social Sector Adjustment Credit (SOSAC) | Europe and Central Asia | Kyrgyz Republic | IDA |  | Human Development | Social Protection & Jobs | IDA | DPF | 1999 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/479191474555999551/text/000020051-20140529161835.txt | http://documents.worldbank.org/curated/en/479191474555999551/pdf/000020051-20140529161835.pdf | Particularly for social adjustment programs, it is advisable to put in place systems that monitor the impact on poverty and gender issues. It appears that the removal of labor market support programs, and measures to increase efficiency of pension reform programs may have come at the cost of increased poverty. It may be necessary to put in safety net programs that address potential adverse social outcomes.
P038570 | TZ-River Basin Management & Small Holder Irrigation Improvements | Eastern and Southern Africa | Tanzania | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/591351474486346187/text/000020051-20140613034031.txt | http://documents.worldbank.org/curated/en/591351474486346187/pdf/000020051-20140613034031.pdf | Addressing cross-sectoral water allocation issues through a river basin framework involving participation of all stakeholders enables trade-offs to be investigated and provides a uniform basis for determining appropriate water user fees.A comprehensive approach to improving agricultural productivity that includes water management and infrastructure improvements is better than dealing with water issues separately.A comprehensive approach to river basin management must be sensitive and incorporate significant local differences in water use practices and demand, local customs and preferences.
P038571 | Medical Equipment Project | Europe and Central Asia | Russian Federation | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/849781474648763849/text/000020051-20140607174508.txt | http://documents.worldbank.org/curated/en/849781474648763849/pdf/000020051-20140607174508.pdf | (1) Initial health sector projects should be kept simple. (2) If such projects largely involve purchase of hardware, they still must give adequate attention to software components such as training and other capacity-building, and policy work. (3) Predominantly infrastructure projects with health objectives still must identify and use appropriate health output and outcome indicators (in addition to hardware process and outcome indicators). (4) Restricting equipment provision to primary and secondary facilities, particularly if provision is based on decentralized decision-making, is a good idea in itself, and may create a dynamic toward restructuring and reform in a formerly highly-centralized health system. In such cases, provision of technical assistance to guide individual institutions in their investment decisions can be useful. (5) It is important to balance the interests of local industry with those of the beneficiaries, and doing so does not necessarily jeopardize either quality or competitiveness. (6) International Competitive Bidding and Consolidated Procurement can result in significant savings. (7) Work on policy reform requires proper institutional arrangements from the beginning; staffing a unit that is working on aspects of reform solely with consultants may diminish use of the work and sustainability of the unit.
P038572 | Tax Administration Project | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/964921475100342246/text/000020051-20140602111218.txt | http://documents.worldbank.org/curated/en/964921475100342246/pdf/000020051-20140602111218.pdf | Projects should be based on clear indications of government ownership. TA projects such as this should not be allowed to proceed unless they receive firm indications of government support. Incentives for successful support need to be structured into projects. TA projects such as this need a careful balance of procurement of goods, organizational development, staff development, and strategic planning for successful implementation.
P038572 | Tax Administration Project | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1995 | 2001 | 2003 | PPAR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/685011468757814711/text/multi0page.txt | http://documents.worldbank.org/curated/en/685011468757814711/pdf/multi0page.pdf | 69. Conclusions and lessons are\. Ownership can be built from the bottom up. It can be engendered by demonstrating change from the bottom up, using regional pilots and judicious sponsorship from the top. Large-scale top-down institutional reforms may not be an option from the outset, particularly for large countries with diverse regions, when headquarters are distant from client services and local problems, and when there are strong vested interests in the status quo and fear of change. The project suffered neglect at the Headquarter of the Ministry soon after approval, but the pilot regions maintained ownership and commitment and demonstrated improvements at the front line. Ironically, a weak central. project management unit at the start may have allowed the regions to develop their own solutions without undue interference. The regions were at the frontiers, faced with excessive workload and unsatisfied customers, thus perhaps more prepared for change. Then, a reform-minded leadership did help turn around the project on measures that were necessary to come from the center. But as the pilots are now expected to be scaled up, it will become more important to broaden such ownership beyond the new regions to be covered, to include both headquarters and the general public. The project also demonstrated that blueprint conditionality and the financing of a large volume of TA and studies cannot substitute for ownership. Russia must be seen to drive the change. Local change agents should be exposed to outside perspectives and alternative models. Piloting change and engendering local ownership through training, experience demonstration, study tours and support to champions are essential. Piloting is judicious when there is a need for integrating comprehensive and complementary reforms on a scale where complexity and risks are manageable and early results are necessary. In this case, it was critical to carry out several complementary reforns that cover functional reorganization, process changes, mission-oriented training, and substantial computerization. C arrying out these complementary activities is necessary to realize the benefits from investments in computerization. But doing so on a large scale from the start would have involved unmanageable complexity and risks, and this could have ended with a major failure. Piloting presents a dilemma since it still requires the commitment of stakeholders at all levels, even while keeping project scope End implementation focused on the pilot area or constituency. Hlowever, piloting could be an effective instrument if it is designed for learning from the start, that is, to test explicit hypotheses and strategies and to identify risks and tradeoffs. Scaling up remains a challenge, but now a road map has been established, skills built, mindset changed, and hopefully, the core project management systems sufficiently developed. * Pacing change and maintaining flexibility are critical to major organizational change. A pilot implies a lack of a blueprint, of consensus on mreans, and of certainty about the feasibility and pace of change. Therefore it would misleading to prematurely judge early performance or to consider the deviations that are likely to arise from learning and adaptation as failures. In this case, the project was about to be cancelled in midcourse. Bank staff continuity, flexibility, persistence, pro-activeness, and their partnership with reform-minded local counterparts were critical to adapt and reshape the project. Critical to such flexibility is the availability of adequate resources for supervision and knowledge transfer. The pilot was prepared in record time in response to an urgent need, so risk taking was inevitable. It also set ambitious targets, in line with client aspirations. But time to develop software, build management systems and change organizational behavior is often underestimated. The project has stretched client capacity. But Bank and client staff persisted with the project, with the objectives rather than a blueprint, and TAMPI ultimately exceeded Bank expectations. An important byproduct of this flexible yet persistent approach is that the client organization learned how to learn and now accepts change as a continuous process. Strategic management, including sequencing of hardware and software and organizational change are important in introducing comprehensive organizational development and large-scale computerization. It takes strategy, time and sequencing to develop new management systems and practices. But to the extent project progress is measured by disbursements, the all too common bias to proceed with hardware ahead of less costly and more difficult investments in intangibles will continue. Expertise in organizational change, management systems, and human resource development will be even more essential to the scaled up program. These managerial capabilities must be embedded within the Ministry, not just the PIU. The Ministry is cognizant of this lesson and for the second project it created a Modernization Department, well staffed and technically capable. This modernization department will carry out modernization of all regions, not only the ones under the project, thus ensuring that the government would realize the benefits on a larger scale than the Bank's financed program. * Bank procurement procedures should be adapted to deal with the relatively unpredictable but critical process of customized software development. Tax systems often require more customized and complex software than other government applications. Customization also entails more concerted efforts to ensure system sustainability and IT staff support. In this case, the Bank did not adequately evaluate the technical soundness of the prototype that was developed with IMF/EU, despite the criticality of this application software. As a result of delays in such software development, the hardware was procured earlier, and had to be upgraded to match the new demands. Thus the pilot indicates the need for better protocols to further adapt and deploy the tax software in the follow up program. Moreover, Bank procurement procedures prevented the Bank from financing software development because it was carried out by a specialized company that serves the Ministry--not an unusual practice that enable governments to recruit and retain highly specialized skills and adapt such capabilities to government's special business requirements. Under Bank rules, such companies are also barred from competing with private companies if and when the government opts for outsourcing such services through competitive bidding. Also, because of the confidential nature of the software algorithms, Russia could not accept open bidding for the software development effort. The Bank's team could not reconcile Russia's concerns (and the criticality of software development to project success) with the Bank's procurement requirements, which proved to be rigid. It is therefore recommended that the Bank reviews its software Lu procurement procedures to meet both the objectives of efficiency and responsiveness to clients' concern with confidentiality and emerging specialized expertise. * Social marketing and image building are important activities to facilitate change in client behavior and to scale up institutional reform efforts. Political will and public support must be nurtured. This is critical to overcoming the massive bureaucratic resistance to change as similar modernization is extended to other regions rather rapidly and as the support systems at headquarters will have to change accordingly. During implementation, the Ministry grew increasingly convinced that taxpayer education and mass communication are good investments, and essential to enhance compliance and institute self-reporting by taxpayers. Such activities will need to be further developed, scaled up and sustained under TAMP II. Similarly, the Bank and the Ministry need devote more attention to publicize the success of the pilot, and the lessons learned. Attention to external relations is particularly critical in Russia to improve the Bank's image and to encourage further modernization of public sector institutions under the eRussia program. * E-government programs should build on local experience with pilot computerization and organizational change, and on and the technical platforms and standards already established. The experience of TAMPI indicates that line management ownership at the ministerial and local levels is critical to government-wide modernization. It also point to the competencies, technical and managerial, that will be critical to implementing eRussia, a high priority national program to use information and communication technologies to improve governance, modernize public services and enhance the competitiveness of the whole economy. To realize the benefits of computerization, substantial efforts are needed to change mindsets and ways of doing business. Exposures to homegrown success and international best practice are needed. It would be costly for each ministry to reinvent this experience. The project also points to opportunities to adopt common standards and databases, and to build a common communication infrastructure across ministries. In doing so, lead roles and responsibilities for key ministries will need to be defined. Since modernization of many strategic systems will be necessary (and given the current low levels of computerization in Russia), and these systems and platforms cut across ministries, it is the right time for the Bank and government to worry about these issues. For example, a unified national registration (or personal identification) system needs to be adopted by all ministries and levels of governments. The MinTax has successfully developed such a system, so it should not be re-invented by other ministries. Even more important, a unified system would enable all ministries to share data, and would help further cross-checking of all types of information for consistency, reliability, transparency, and anti-corruption.
P038573 | SPAL | Europe and Central Asia | Russian Federation | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1997 | 2001 | 2002 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/316021475092291732/text/000020051-20140602113224.txt | http://documents.worldbank.org/curated/en/316021475092291732/pdf/000020051-20140602113224.pdf | 1. While the Bank should be guided by the IMF's assessment of a country's macroeconomic framework, it needs to rely on and be accountable for its own assessment. The failure of the Borrower to implement the SPAL's conditionality regarding payment of minimum pensions relates to the failure of both the Borrower and the Bank to appreciate weaknesses in the macroeconomic framework. 2. While a broadly based project such as the SPAL may increase the visibility of sector reforms, there is an important trade-off to be considered between this visibility and achieving specific goals of a project. 3. A strong outreach program, in support of Government, is important in promoting wide ranging reforms.
P038573 | SPAL | Europe and Central Asia | Russian Federation | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1997 | 2001 | 2003 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/744581511185199145/text/multi0page.txt | http://documents.worldbank.org/curated/en/744581511185199145/pdf/multi0page.pdf | 7. Lessons 7.1 A major lesson to be learned from these two projects is the need to have reasonable expectations about the pace at which a democratic society can reform its social protection institutions and to tailor Bank assistance strategy accordingly. Conditions attached to adjustment loans appear to be an effective way to encourage action in an area where a reasonable consensus already exists about the need for and general direction of change. The experience with the SPAL suggests that they are unlikely to be effective where no such consensus yet exists. This implies that the Bank should restrict itself to providing analytical and advisory services and a small technical assistance loan until such time as a reasonable consensus has finally emerged around a reform that the Bank is willing to support. At that point, larger loan assistance to help cover any transition or institutional investment costs is appropriate. Whether budget support linked to policy conditions is also appropriate in that situation depends on the Government's commitment to the overall macroeconomic and structural reform program. 7.2 A second lesson is the need to reconsider carefully the wisdom of proceeding with a loan when the Borrower wants to drop elements that are important to achieving the longer-term reform agenda. Arguably, the Bank could have refused to finance the computerization of the local social protection offices in the absence of progress toward a pension reform plan that covered both the policy aspects of the reform and the institutional aspects of the reform. While such a stand might have diminished the quality of service supplied by the local pension offices for at least a year or two, it might also have forced the dialogue about pension reform to have started some three years prior to the initiation of the SPAL project. It might also have forced the Government to decide earlier on a pension administration strategy, saving it from the wasted effort of enhancing the collections and financial management of the pension fund in the late 1990s only to transfer the functions to the Ministry of Taxation in 2001.
P038641 | PRE-EXPORT GUAR. FAC | Europe and Central Asia | Moldova | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1995 | 2004 | 1999 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/156941475089202295/text/000020051-20140519080753.txt | http://documents.worldbank.org/curated/en/156941475089202295/pdf/000020051-20140519080753.pdf | The project illustrates two basic lessons. First, projects should assess systematically the demand for a new financial instrument among its potential clients. This assessment should also be done early and it should consider alternative pricing scenarios. Second, the project shows the importance of government's ownership. Only a government committed to not interfere with the market can credibly support an agency that sells insurance against government interference in private business.
P038661 | FIN/PRIV.SCTR.CAPACI | Western and Central Africa | Mauritania | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1995 | 2000 | 2001 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/791831474850686226/text/000020051-20140529162828.txt | http://documents.worldbank.org/curated/en/791831474850686226/pdf/000020051-20140529162828.pdf | The legal reform process takes a great deal of time and effort; a consensus-building process including the stakeholders had to be carried out before the laws could be finalized, adopted and effectively implemented.
P038661 | FIN/PRIV.SCTR.CAPACI | Western and Central Africa | Mauritania | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1995 | 2000 | 2005 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/145691468774842122/text/Mauritania-Private-Sector-Development-Private-Sector-Development-and-Capacity-Building-Public-Resource-Management-and-Fiscal-Reform-Support-Credits.txt | http://documents.worldbank.org/curated/en/145691468774842122/pdf/Mauritania-Private-Sector-Development-Private-Sector-Development-and-Capacity-Building-Public-Resource-Management-and-Fiscal-Reform-Support-Credits.pdf | Lessons 5.7 The following are lessons o f general application. 0 In programs or projects with a heavy agenda o f legal and regulatory reforms, the conditionality should extend to the issuance of application decrees, and not only to the revision o f laws. Also, the texts should be well adapted to local conditions, short, simple and clear. In those programs or projects, the Legal Department should be involved early on in preparation and design. e Floating tranches are useful when the time required to complete a task or adopt a measure i s uncertain or dependent on the Legislative. 0 One-tranche operations based solely on actions taken prior to appraisal do not allow monitoring o f implementation. e Tax and trade reforms can be effectively implemented if they are based on sound analytical work and careful preparation. In Mauritania's case, these reforms were based on two high quality studies and, during preparation, their impact on reducing revenues was taken into consideration. However, the analytical work should have taken the local traditions more into account. In this connection, i t i s worth noting that the downgrading o f many performance indicators in the present PPAR, compared to the evaluation summaries prepared by OED, i s largely due to the fact that the latter were solely based on the ICRs, which, in this case, clearly failed to reflect the reality on the ground. 27
P038674 | LB-NATIONAL ROADS | Middle East and North Africa | Lebanon | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2005 | 2005 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/765491474899267735/text/000020051-20140613044207.txt | http://documents.worldbank.org/curated/en/765491474899267735/pdf/000020051-20140613044207.pdf | Operations developed in post-conflict situations should be open to corrections amid emerging realities on the ground. Such projects should be reassessed and adjusted at their mid-terms to reconfirm the validity of objectives and components.Bank funding for ambitious and far-reaching reforms is most effective when undertaken to support and deepen reforms that are Government-initiated (commitment is secured), and responsibility for implementing stated reforms is at the highest ministerial level (ownership is established). Diagnostic mechanisms and tools to strengthen a road administrationâ€™s capacity to evaluate road programs should be developed in the early stages of project implementation for their potential demonstration effect.
P038687 | LB - VOCATIONAL & TECH.ED | Middle East and North Africa | Lebanon | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/880741474851588493/text/000020051-20140612143318.txt | http://documents.worldbank.org/curated/en/880741474851588493/pdf/000020051-20140612143318.pdf | Publicly funded vocational education continues to play an important role in human resource training options. However, its policy and implementation are often complex and require considerable expertise and commitment. Unless there is suitable expertise and institutional capacity in government agencies, VTE projects have limited outcomes.- VTE investments may be used best if in part they are dedicated to developing effective partnerships with the private sector. Without a commitment from the private-sector and supportive network for institutions and graduates VTE projects may not be implemented successfully.- In post-conflict countries where institutions have a dire lack of material and human resource repairs, attempts to fix them through the lens of a single project are risky. Interventions might best be focused on prioritized strategic gaps in the system and making long-term, and progressive changes.- Peer review comments during project preparation provide a valuable safeguard with respect to quality at entry. Taking them substantively into account when designing a project may improve development effectiveness.
P038695 | DZ-MASCARA EMERG.RECONS | Middle East and North Africa | Algeria | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1995 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/169701474493455327/text/000020051-20140529080154.txt | http://documents.worldbank.org/curated/en/169701474493455327/pdf/000020051-20140529080154.pdf | OED has long suggested that emergency projects (ERLs) should allow for a longer implementation period than three years so that vulnerability reducing activities and improved disaster management practices can take hold. In this case, in spite of appraisal expectation for a three-year implementation, the project took 46 months to completion.It is essential to obtain an independent and technically credible assessment of the extent of the damages and an estimate of the reconstruction costs involved.Mutual assistance and self-help among people affected by any major catastrophe is normal. It should be anticipated, and it should be enhanced by activities within the project specifically designed to increase social resilience.Expensive temporary shelter should not be financed under Bank projects unless weather conditions are life-threatening. People are able to provide themselves with adequate temporary shelter using materials from damaged buildings, and families that did not lose their dwellings take friends and relatives in. The Bank should require that the PIU director and his staff be thoroughly familiar with its procurement and disbursement procedures before project launching and following changes in the project management. Given the evolving needs of disaster victims, there is a need for highly flexible disbursement procedures following an emergency, without sacrificing proper diligence and control. Given that since appraisal, the country has experienced political turmoil and terrorism, making it unsafe to travel, the use of project management software would have helped the PIU to prepare its periodic reports on time and provided officials with a detailed account of the project status at any point in time. As it happened, this information was incomplete, and mostly out-of-date.If, for any security reason, supervision teams cannot make site visits for a certain period of time, the Bank should consider suspending disbursements, if there is a doubt that disbursements are not properly made or that project implementation is not progressing as expected. Provision for proper maintenance of assets financed by the project should be a concern of the PIU long before the completion of each component.
P038698 | ST. LUCIA BASIC EDUCATION REFORM PROJECT | Latin America and Caribbean | St. Lucia | Blend |  | Human Development | Education | IBRD | IPF | 1995 | 2001 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/439581475098778280/text/000020051-20140602104338.txt | http://documents.worldbank.org/curated/en/439581475098778280/pdf/000020051-20140602104338.pdf | Projects expecting to make extensive organizational changes should include a communication and change management strategy so that all stakeholders are fully aware of objectives and implications.- Implementation and disbursement projections ought to take an agency's implementation capacity in consideration. Often they are too optimistic, and outcomes turn out to be disappointing.- Monitoring and impact indicators must be clearly articulated prior to implementation and given emphasis throughout implementation.- Persons who are expected to implement a project should participate in the analysis of issues and project design. They should also be informed of details through project launch workshops.
P038700 | JM- STUDENT LOAN | Latin America and Caribbean | Jamaica | IBRD |  | Human Development | Education | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/133941474575924199/text/000020051-20140607171958.txt | http://documents.worldbank.org/curated/en/133941474575924199/pdf/000020051-20140607171958.pdf | 1. In designing student loan schemes, consider past performance including arrears, and incentives for all key participants -- especially realistic market-based incentives for financial institutions, and student loan repayments that are realistic and linked to employment/unemployment rather than fixed amounts; involve them throughout.2. Good communications strategy can make cost recovery in tertiary education and reallocation of education sector budgets among subsectors acceptable.3. Bank should not change task team leader multiple times during the project cycle (here, three times during preparation).4. Bank needs to be involved in policy dialogue on national and sector context and outcomes (here, changes in composition of tertiary student body by consumption quintile), not just in individual project. This project won a battle, but the war for equitable access to tertiary education was lost. 5. Bank and borrower should focus supervision and reviews sharply on achievement of development objectives.
P038820 | HYDROPOWER REHAB & SYST CNTRL | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1995 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/756361474572990132/text/000020051-20140607172256.txt | http://documents.worldbank.org/curated/en/756361474572990132/pdf/000020051-20140607172256.pdf | (1) A donorsâ€™ working group can be a valuable instrument to assist the Government in project implementation by exploiting the comparative advantages of the donors. In this project the Bankâ€™s experience in power sector rehabilitation was successfully complemented with Canadaâ€™s support with technical assistance in project management, Norwayâ€™s support in water reservoir management, and Switzerlandâ€™s supply and installation of switchgear equipment.(2) Since financial discipline is a key factor in power sector reforms, the pressure on the Government generated by the project can be boosted by including specific financial targets in Bankâ€™s Program Adjustment Lending and IMFâ€™s Extended Fund Facility Program operations in the country. In this project, the inclusion of specific targets for cash collections in those lending operations helped the power sector to reach their highest level of cash collection ever.
P038882 | BR RECIFE M.TSP | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1995 | 2004 | 2005 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/470921474508830297/text/000020051-20140613031634.txt | http://documents.worldbank.org/curated/en/470921474508830297/pdf/000020051-20140613031634.pdf | Decentralization of an urban rail system from Federal to State or lower level of government can be an extremely lengthy, complicated and highly politicized process. For the process to be completed within the lifetime of the project, decentralization should be a condition of effectiveness for a rehabilitation and modernization loan, with the respective rights and obligation of the transferring and receiving parties laid out in a binding way in advance.Effective measures need to be undertaken to prevent additional resettlements that may occur once the project becomes known. Also, it is critical to follow-up on families that accepted cash contributions (during the resettlement process) to determine whether they were able to restore their previous income level and quality of life. The time indicated by contractors for train rehabilitation is generally optimistic and should be carefully evaluated since long delays can have devastating and sometimes irreversible impacts on demand diversion to other modes.The scheduling of civil works for construction of stations need to be carefully evaluated. One way to do is to bid the stations in a progressive way in order to make operation on a partial network possible.
P038882 | BR RECIFE M.TSP | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1995 | 2004 | 2006 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/774341468020698401/text/365890for-Phyllis.txt | http://documents.worldbank.org/curated/en/774341468020698401/pdf/365890for-Phyllis.pdf | 8. Lessons Learned The followingare the main lessons that the Bank has learned from its involvement in the Recife and the Belo Horizontemetropolitan transport projects\. 9 It is essentialto createan enablingenvironmentforthe financialsustainabilityofurban transport operations;one that achieves a balance between being market-oriented but, at the same time, takes into account the urban environment and affordabilityissues. It is also important to define a fare policy that squarelyfaces the issues of cost recovery including, transparent passenger subsidiesfor the poor and fundingmechanisms to cover operating deficits. 9 Thedecentralizationofurbanrail systemsfromthe federaltothe stateor alowerlevelof government is desirable because it brings the operator closer to the users, thus allowing for the serviceto be more responsiveto user needs and wishes. Decentralization is also likelyto facilitateintegrationwith other transport modes since there will be fewer levels of government that have to be in agreement with tariff and subsidypolicies. 9 Conflictsamonggovernmentinstitutions,politicalparties, aswell asworker andprivate sector lobbies can be a major source of disruption in the executionof largeurban transport projects. The Bank shouldbe prepared to assist in the mobilization of negotiating skills for conflictresol~~tionshould they be needed. 9 Thetimeittakesto rehabilitaterolling stockshouldnotbe underestimated. Bothprojects show that the private firms responsible for deliveryof the rehabilitated trains have experienced serioustechnical, administrative and financial problems that had to be resolved.
P038883 | ENT.EXPORT DV. | Latin America and Caribbean | Argentina | IBRD |  | Other | Trade & Competitiveness | IBRD | IPF | 1996 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/431901474493226209/text/000020051-20140529073107.txt | http://documents.worldbank.org/curated/en/431901474493226209/pdf/000020051-20140529073107.pdf | The primary lesson of general applicability is that the management of a publicly financed program by a private entity will only work smoothly if the contract between the Government and the entity is clear and simple. This is true also with regard to the use of a performance-linked incentive scheme in a management contract: it should be clear and concise with realistic targets, so as to avoid excessive emphasis on quantity over quality.
P038884 | Rural Poverty Alleviation - Ceara | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/341611474590874774/text/000020051-20140604060335.txt | http://documents.worldbank.org/curated/en/341611474590874774/pdf/000020051-20140604060335.pdf | From the many listed in the ICR, the following stand out:(a) By assigning greater responsibility to local organizations and municipal goverments, community demand-driven projects can help build institutional capacity in poor rural areas;(b) Community-driven approaches can reduce bureaucracy and administrative obstacles and reinforce accountability for project performance by reducing the distance between decision-makers and beneficiaries.(c) Decentralization of the Bank supervision effort---in this case, directed from the Recife office---can greatly enhance implementation, by ensuring rapid response to problems, timely advice giving, and careful monitoring.(d) Screening of projects should be conducted by municipal councils (rather than sending proposals to be vetted by a technical agency in the state capital) because this helps to build local capacity, with benefits extending beyond the project (potentially citizens acquire more voice in municipal planning).(e) Productive subprojects should be subjected to rigorous selection, preparation, technical assistance and supervision criteria and linked to a graduation strategy which facilitates beneficiary communities access to formal credit.(f) The community-based approach to land reform piloted in Ceara has proven to be more cost effective than previous land reform strategies, lending itself to scaling up and possible replication in other countries.
P038885 | Rural Poverty Alleviation - Sergipe | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1995 | 2001 | 2002 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/559321474592407362/text/000020051-20140604060248.txt | http://documents.worldbank.org/curated/en/559321474592407362/pdf/000020051-20140604060248.pdf | From the many listed in the ICR, the following stand out:(a) By assigning greater responsibility to local organizations and municipal goverments, community demand-driven projects can help build institutional capacity in poor rural areas;(b) Community-driven approaches can reduce bureaucracy and administrative obstacles and reinforce accountability for project performance by reducing the distance between decision-makers and beneficiaries.(c) Decentralization of the Bank supervision effort---in this case, directed from the Recife office---can greatly enhance implementation, by ensuring rapid response to problems, timely advice giving, and careful monitoring.(d) Screening of projects should be conducted by municipal councils (rather than sending proposals to be vetted by a technical agency in the state capital) because this helps to build local capacity, with benefits extending beyond the project (potentially citizens acquire more voice in municipal planning).(e) Productive subprojects should be subjected to rigorous selection, preparation, technical assistance and supervision criteria and linked to a graduation strategy which facilitates beneficiary communities access to formal credit.
P038895 | Federal Water Resources Management Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/628781475071917065/text/Brazil-Federal-Water-Resources-Management-Project.txt | http://documents.worldbank.org/curated/en/628781475071917065/pdf/Brazil-Federal-Water-Resources-Management-Project.pdf | The following lessons are summarized for the five lessons presented in the ICR:Reform of water resources management is institutionally difficult and time is required to agree a consensus on new directions and policies and implement them. This is doubly difficult in a Federal system of government. In that sense water resources management reform projects do not fit well within the normal Bank's 5-7 year project cycle. Since this project was designed, APLs have been introduced and they may be more appropriate for a evolving reform agenda.An intersectoral approach to water issues is key to the achievement of results that go beyond the WRM agenda.The diversity of Brazilâ€™s physical characteristics, socioeconomic realities and institutional structures imposes challenges related to the management and use of water. Renewing its water policies and strengthening investment capacity is essential to ensure that the water sector can make important contributions to the reduction of poverty and inequality, the protection of the environment and the sustainable growth of the economy.
P038896 | Rural Poverty Alleviation - Rio Grande do Norte | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/320851475072683283/text/000020051-20140612064518.txt | http://documents.worldbank.org/curated/en/320851475072683283/pdf/000020051-20140612064518.pdf | Poor rural communities working through beneficiary associations are able to set priorities, and execute, operate and maintain investment projects using funds directly transferred to the association bank account.Project-supported municipal councils can play a role outside the project, improving links between beneficiaries and local governments and providing information about alternative sources of grant and credit financing. Productive sub-projects need to be rigorously selected and prepared, with attempts made early on to encourage financial self-sufficiency, or access to credit; each subproject should receive a single (start-up) grant---no more. Quality supervision, involving closeness to the client and fast-response trouble shooting, is vital for smooth project implementation.
P038916 | NI/FISE II | Latin America and Caribbean | Nicaragua | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 1998 | 1999 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/664791474589692439/text/000020051-20140521032602.txt | http://documents.worldbank.org/curated/en/664791474589692439/pdf/000020051-20140521032602.pdf | 1. The conditions for sustainable service delivery need to be built upfront into project design.2. Social Funds with service delivery and capacity building goals are supervision-intensive and require inputs from sectoral experts with the relevant skills-mix and technical competencies.3. Clearly-specified and objective criteria as well as explicit mechanisms for resource allocation/project selection are critical and their application should be closely and regularly monitored.4. While experienced senior management is key to project success, the need for competent intermediate-level staff should not be overlooked.5. The likely demand for private contractors and materials in the project area should be estimated upfront, and contingency plans made if this is likely to outstrip supply.
P038932 | GENERTN RCOVRY&IMPRV | Latin America and Caribbean | Jamaica | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 1998 | 1999 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/169011474563799842/text/000020051-20140519084146.txt | http://documents.worldbank.org/curated/en/169011474563799842/pdf/000020051-20140519084146.pdf | One important lesson emerges from this project. It is not advisable to mix objectives aimed at fixing a physical emergency with objectives pursuing hard policy and institutional objectives because the implementation of the latter will necessarily lag the implementation of the physical objectives. The pressure to resolve the physical emergency makes the Borrower implement the physical components of the project at a much faster pace than the execution of the studies that normally precede the design of policy and institutional development changes. Once the physical emergency is resolved the Borrower tends to be lax in initiating hard reforms derived from on-going studies-in this case electricity tariff reform.
P038947 | BR- SC. & TECH 3 | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/773311474512076140/text/000020051-20140613044026.txt | http://documents.worldbank.org/curated/en/773311474512076140/pdf/000020051-20140613044026.pdf | Public-private technology partnerships that foster the effective interaction of companies and academia, can be a highly effective mechanism for benefitting markets. - The science and technology projects most likely to transfer technology successfully are those with a high level of private sector involvement and funding.- Competitive funding in science and technology fosters commitment and a high quality of output.
P038978 | MA-PSD III-VOC TRG. | Middle East and North Africa | Morocco | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/491751474556516195/text/000020051-20140612072217.txt | http://documents.worldbank.org/curated/en/491751474556516195/pdf/000020051-20140612072217.pdf | Participation of a broad range of parties (government, labor, business) was key to project successThe Bank should have been more pro-active in implementation of the impact study
P038988 | Heilongjiang Agricultural Development | East Asia and Pacific | China | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/138021474653024521/text/000020051-20140613033039.txt | http://documents.worldbank.org/curated/en/138021474653024521/pdf/000020051-20140613033039.pdf | (1) It is important to have flexibility in the implementation of an agricultural development project of this nature in order to adjust quickly to changing market opportunities and central government policies which affect the sector.(2) The timely and adequate provision of counterpart funds is important. Counterpart funds for private investments (as opposed to public goods) should be self-mobilized. More active involvement of local financial institutions during project design might have mitigated this problem.(3) Improved technology plays a key role in projects of this nature. Financing for research and development should be accessible on a competitive basis rather than allocated to a single institution.(4) Voluntary farmers' associations have begun to play a key role in agricultural development in China. It would be good to enhance their role with additional investments in leadership and management training.
P039002 | Istria Water Supply & Sewerage Project | Europe and Central Asia | Croatia | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1989 | 2000 | 2002 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/518911474484996647/text/000020051-20140602112014.txt | http://documents.worldbank.org/curated/en/518911474484996647/pdf/000020051-20140602112014.pdf | (1) Turnkey contracts are complicated to design and supervise. In this case, the contract went seriously wrong;(2) Demand projections and project design always need to incorporate flexibility, and particularly for transition economies; and(3) For the Bank to be able to influence the implementation of a given component, it should finance a share of costs, sufficient to provide leverage. In this case, the Bank financed nil of the sewerage and treatment works, yet these had been included in the project.
P039002 | Istria Water Supply & Sewerage Project | Europe and Central Asia | Croatia | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1989 | 2000 | 2004 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/479841468770636358/text/27494.txt | http://documents.worldbank.org/curated/en/479841468770636358/pdf/27494.pdf | LESSONS 39. Following are some key lessons from the project's experience\. During implementation, it is important to maintain the balance between the construction of infrastructure and institutional strengthening according to the priorities established in the project design. Projects with major physical investments tend to become focused on these investment components, favoring them in project supervision as well. In this project, the entities responsible for institutional aspects and operational improvements were less closely supervised by the Bank than the Project Implementation Unit and, thus, the components under their purview received less attention during project supervision. Responsibilities for implementation should be assigned in a manner that ensuresthat the requisite balance is maintained (see paras. 13-l 7). l In extraordinary circumstances such asfollowing a major interruption in implementation, substantial revisions or adjustments to the project components may be needed. This project provides a good example of how new demand projections and corresponding changesin project design can be called for under drastically changing conditions. If such circumstances arise, a careful review and appropriate revisions should be carried out. In this case, it should have taken place around 1995 (after the war) when the project was re-launched for final implementation (seeparas. 17 and 29). The implementation plan for reducing unaccounted water, including detailed annual targets, needs to be specified in the project preparation documents. These are difficult issues and achieving concrete results often requires more time than is available within a normal project cycle. Had this plan been designed better with detailed annual targets, its implementation and supervision would have been less disrupted by the difficult wartime circumstances. Therefore, design of activities, and particularly the implementation priorities, have to be defined with extra care (see paras. 25-26).
P039003 | Istria & Slovene Coast Water Supply & Sewerage Project | Europe and Central Asia | Slovenia |  |  | Sustainable Development | Water | OTHER | IPF | 1989 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/917581474508676751/text/000020051-20140522105714.txt | http://documents.worldbank.org/curated/en/917581474508676751/pdf/000020051-20140522105714.pdf | First, demand forecasting needs to be conservative in the face of major macro-economic and structural reforms that can often reduce industrial and commercial demand for water. Under the original project design demand was probably over-estimated. Second, successful programs to reduce unaccounted-for-water require strong Borrower commitment and a well-designed and strongly supported action program. The Borrower's success in reducing unaccounted-for-water is exemplary. Third, where the Bank chooses to include financial covenants it should pay sufficient attention to ensure effective financial supervision.
P039015 | MZ-Natl Water 1 (FY98) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/620261474490313344/text/000020051-20140615095640.txt | http://documents.worldbank.org/curated/en/620261474490313344/pdf/000020051-20140615095640.pdf | 1. Divest all non-essential features from a complex project: For a complex project in particular, the design should support the core thrust(s) of the project, and not add any components, sub-components or activities that are not central to achieving the objectives. This was a highly complex project involving major institution building and innovation in three demanding areas: water resources management, rural water supply and sanitation, and privatization of urban water supply. The project contained a number of sub-elements under various components, usually for infrastructure, which were not needed. (Recognizing this, the Bank team and Government took several such sub-elements out of the project during implementation.)2. Successfully piloting a new approach, even on a small scale, can have major impact: The Rural Water Supply and Sanitation component constructed only 130 point source and 3 piped scheme water supply facilities to pilot a demand-driven approach which was entirely new to Mozambique. The Government and a number of development agencies were sceptical initially, but became strong supporters as they witnessed success. The new approach is now fully espoused by the Government and has attracted large donor support for a major scale-up - US$35 million from various donor agencies and a commitment of US$100 million from the African Development Bank. Designing and supervising the pilot required substantial Bank staff expertise and time, but the pay-off has been large.3. Mozambique's largely successful project experience in: (i) developing capacity for planning and monitoring water resources management for international rivers; (ii) privatizing urban water supply, and (iii) introducing a demand-driven rural water supply program, could be of interest to other countries, especially in Africa.
P039016 | FISC SUST.CR. I | Eastern and Southern Africa | Zambia | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2000 | 2002 | 2003 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/322521474652986590/text/000020051-20140607172849.txt | http://documents.worldbank.org/curated/en/322521474652986590/pdf/000020051-20140607172849.pdf | Before undertaking major reforms, consensus should be achieved between cognizant ministriesA public information program is a key element supporting a reform agendaThe amount of time allocated for important reforms was insufficient, and it would have been helpful to have a more systematic plan laying out each step of the reform process, and the linkages between actions, along with the estimated time required
P039019 | First National Roads Improvement Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2007 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/525961474505134168/text/000020051-20140619084037.txt | http://documents.worldbank.org/curated/en/525961474505134168/pdf/000020051-20140619084037.pdf | Where major institutional development is attempted and involves significant changes in work processes and financial arrangements, both government commitment and substantial political support should be reasonably confirmed before project effectiveness.New technical and business processes should be tailored to the existing capacity, and should be introduced in stages and in parallel with corresponding changes in the existing institutional framework and processes to be sustainable. In this project new computerized systems covering various aspects of road sector management proved to be overwhelming for the existing organization. Where there is a likelihood of collusion and corrupt practices in procurement, the supervision process should place high priority on tracking such issues, and respond promptly and appropriately.
P039021 | VN-Rural Transport | East Asia and Pacific | Viet Nam | IBRD |  | Infrastructure | Transport | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/540771474485958290/text/000020051-20140607160538.txt | http://documents.worldbank.org/curated/en/540771474485958290/pdf/000020051-20140607160538.pdf | Upfront efforts should be directed at building ownership of design standards by government and beneficiaries. In this Project, commitment to the spot improvement technique was weak, and the borrower preferred a higher standard that was subsequently implemented inadequately and at higher cost.The lack of systematic traffic data collection inhibits identification and prioritization of necessary interventions on roads and hampers the ability to readily monitor the impact of projects. The result may be road expenditures that are not cost-effective.
P039021 | VN-Rural Transport | East Asia and Pacific | Viet Nam | IBRD |  | Infrastructure | Transport | IDA | IPF | 1997 | 2002 | 2004 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/643701468780567480/text/28168.txt | http://documents.worldbank.org/curated/en/643701468780567480/pdf/28168.pdf | 5.6 The primary lessons learnt from these projects are\. 0 Where significant involuntary resettlement i s anticipated a special effort i s requiredat the outset to ensure that careful monitoring and excellent communication concerning Bank policies and safeguards takes place with all parties at all levels at an early stage inthe process. This i s especially true for a new Borrower likely to beunfamiliar with such details; 0 Where economies are inrapid transition or recovering from extreme situations such as, for example, conflict or natural disaster, projects preferably should be designedto accommodate expected future capacityneeds andnot simply to restore collapsed infrastructure; 0 When framing institutional and capacitybuildingobjectives, the challenge is to ensure they are achievable, that the Borrower has full ownership o fthem and they are given sufficient priority early inimplementation; and Road standards needto be adapted to meet local conditions and a flexible approach usedintheir adoption to take into account local circumstances, but, without compromising the basic principles o fbest international practice, especially for low volume roads indeveloping countries.
P039022 | LGU URBAN WATER & SANITATION | East Asia and Pacific | Philippines | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/225791474851714707/text/000020051-20140612143748.txt | http://documents.worldbank.org/curated/en/225791474851714707/pdf/000020051-20140612143748.pdf | Involvement of private sector in water sector requires improvements in the overall regulatory environment and should be accompanied by adequate legal and administrative arrangements for conflict resolution. Also, for countries embarking on decentralized service delivery, a consistent national policy on local government financing with regard to grant/subsidies is needed.
P039029 | JM- SOC. INVEST. FUND | Latin America and Caribbean | Jamaica | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2002 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/403091474491535836/text/000020051-20140607145406.txt | http://documents.worldbank.org/curated/en/403091474491535836/pdf/000020051-20140607145406.pdf | Creating a social fund for short-run purposes can be useful for dealing with emergencies, for devoping new approaches, etc. However, uncertainties about a fund's longevity or future may cause undesirable ambiguities about responsibilities for activities initiated, potentially leading to a significant loss of benefits.
P039082 | TOLL ROAD CONCESSION | Latin America and Caribbean | Colombia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2001 | 2003 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/444651474909135631/text/000020051-20140604054216.txt | http://documents.worldbank.org/curated/en/444651474909135631/pdf/000020051-20140604054216.pdf | Bidding processes should be designed to discourage the success of "overly" aggressive bids that contribute to added financial and technical risks on the concessionaire. In this project, the requirement that the concession contract be awarded to the bid that represented the least expected cost to the government proved to be shortsighted. The successful bidder proposed a government capital contribution that was USD$83 million less than the immediate competitor and was the only bidder not to request any instruments offered by Government and the Bank to mitigate financial risk. The government should have been able to consider such facts in its award decision.Regulatory capacity should be sufficiently established before the bidding process begins for a concession. In this project, the establishment of a regulatory commission with responsibility for road concessions was decreed only after the project had begun, and it was not operational by the close of the Bank loan.
P039084 | HEALTH SERVICES MODERNIZATION PROJECT (MODERSA) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/461621474905826667/text/000020051-20140618082032.txt | http://documents.worldbank.org/curated/en/461621474905826667/pdf/000020051-20140618082032.pdf | Good and timely supervision can help to define the changes needed for a project with unsatisfactory implementation.Projects should be more consistent in setting indicators and a results chain.Projects must be more realistic in assessing the institutional capacity and the political support for the implementation of the project.For countries with difficult contexts and weak institutions, the project content should be less complex.It is not feasible to reform the health sector under the leadership of a PCU without strong influence within the MOH and without leverage on other relevant agencies at the national and local levels.
P039086 | Urban Property Rights Project | Latin America and Caribbean | Peru | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/914891475090780021/text/000020051-20140613034736.txt | http://documents.worldbank.org/curated/en/914891475090780021/pdf/000020051-20140613034736.pdf | A comprehensive approach to property rights should be consistent with modern markets and organizations. It should address the causes of informal property through modern practices that promote the long-term development of a real estate market based upon secure and transferable rights. The long-term sustainability and legitimacy of property rights must be addressed at the outset and assured through participation, effective legal measures, information dissemination, conflict resolution mechanisms and effective collaboration at central and local levels.Recognition of property rights is just one step in a long process of improving the living conditions of those receiving titles.Given the political sensitivity of property rights high level consensus and commitment to reforms is crucial. Without it, progress can falter, as it did under this project prior to 2000.
P039154 | EMERG. RECOVERY CRED | Eastern and Southern Africa | Rwanda | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1995 | 1998 | 1999 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/133921474576988995/text/000020051-20140519082259.txt | http://documents.worldbank.org/curated/en/133921474576988995/pdf/000020051-20140519082259.pdf | Design of emergency operations should be kept simple. It is necessary to be flexible and sensitive in dealing with assistance in post-conflict situations. And attention to national capacity building, and presence on the ground are important in emergency operations.
P039161 | Railway Modernization & Restructuring Project | Europe and Central Asia | Croatia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/462411475079165059/text/000020051-20140613084038.txt | http://documents.worldbank.org/curated/en/462411475079165059/pdf/000020051-20140613084038.pdf | 1. The Bank should lend for railway restructuring only when government support for such reform is adequate and defective past policies are to be replaced by more appropriate policies. PAL programs are likely to be effective in this regard.2. Consensus with labor unions helps in the retrenchment process. Dialogue at an early stage is necessary and the labor unions should experience genuine participation.3. The requirement to sign PSCs should precede efforts to discontinue services, and the public needs to be prepared gradually for any curtailment of services.4. The (incumbent) railway management cannot be expected to drive the restructuring process without government leadership.5. When high government officials are members of the Supervisory Board this will seriously diminish the capacity of the Ministries to provide effective oversight to railway reform.
P039166 | Danube Delta Biodiversity GEF Project | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1995 | 1999 | 2000 | ICRR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/851731474419958867/text/000020051-20140528131202.txt | http://documents.worldbank.org/curated/en/851731474419958867/pdf/000020051-20140528131202.pdf | Particularly in societies where public participation has been minimal, and where the collaboration of local users is important for successful management of an ecosystem, well-planned public education and awareness programs are needed early in the project to get the public involved in a meaningful way.
P039166 | Danube Delta Biodiversity GEF Project | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1995 | 1999 | 2005 | PPAR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/868281468316451928/text/326830rev.txt | http://documents.worldbank.org/curated/en/868281468316451928/pdf/326830rev.pdf | 4. Findings and Lessons The objective ofthe project to establish a viable biosphere reserve was substantially established but with some shortcomings, the main one being very modest progress on developing stakeholder participationinthe management of the reserve authority. The organizational setup ofthe Reserve Authority inwhich the Academy of Sciences managesthe reserve and scientific research is not working well as it creates a number o f conflicts o f interest between the scientific agenda andmanagement needs. A better model may be to set up a separate reserve management authority that deals with administration, public relations, territorial access, and regulation andthis could be staffed and managed by the Ministryof the Environment that has the greater public interest as one o f its responsibilities. The Academy o f Sciences could then establish a biosphere reserve scientific institute to deal with the scientific aspects o f research and conservation. Such a model has beensuccessfully adopted inRomania. More attention to involvement o f local stakeholders inthe management o f the reserve mighthave reduced the perceptions that the reserve staffis a fairly elitist group who are not concerned with the local economic interests. Because this was not done, the MOT found local communities willing to support their proposal to cut the reserve intwo because it potentially better served the locals' economic interest. The prosecutions brought against the reserve authority were basedon allegations brought by local citizens that the Reserve Authority was misappropriating revenues generated by activities inthe Biosphere Reserve. These allegations are strongly denied by the reserve staff who allege political intimidation, and the matter i s still subjudice. Participationo f stakeholders inproject designand implementation was a newpractice in the early 1990s when thisproject was beingdesigned and it took several years to understand what works best. Comprehensive evaluationo fparticipatory experience only started to emerge in 1997 following a number of studies by the Bank, GEF and OED's thematic study Participation Process Review (2001.)25 More recently, UNDP/GEFproduced guidelines to improve the design 25. The World Bank. 1997.A Review of Participationinthe World Bank's GEF Portfolio. Environmental Department Dissemination Notes. No.52. March 1997. The World Bank.2002. Biological Resource Management -IntegratingBiodiversity Concerns inRural Development Projects and Programs. Robin Grimble and Martyn Laidlaw. Environment Department Papers. Paper No. 85. January 2002. The World Bank. 2004. Participatory Conservation for Protected Areas An Annotated Bibliography of Selected Sources (1996-2001). Nancy Diamond, ElisabethNkrumah andAlan Isaac. Environment Department Papers. Paper No. 95. January 2004. of small business development strategies inbiodiversityprojects, recognizingthat sustaining benefitstreams for local stakeholders is a key development challenge.26Many oftheir findings resonate with the lessons derivedfrom this evaluation. These are to build participation as soon as possible and recognize that significant project resources may neededfor local capacity building; use neutralparties to engenderparticipation; seek ways to increase income potential from ecosystems targeted for conservation; provide alternatives to biodiversity-damagingactivities; and generate sufficient income at the boundary o f protected areas to reduce encroachment. The Bustroy Canal, which splits the strict reserve area into two, raises two questions. First,how big should a protectedareabeto remainviable for biodiversity conservation? Second, what should be the scope of an EIA o f infrastructure development affectingprotected areas? More researchmay be neededto correctly size the Danube delta biodiversity conservation area inUkraine the strictly protected area at almost 15,000 ha forms about a third of the biodiversity conservation reserve. Conversely, inthe almost identical landscape inthe Romanianportion o f the delta, their 15 strictly protected areas intotal cover less than ten percent o f the total reserve area, rangingfrom 50 hato 21,410 ha.27It i s unclear how far the size o fthese various areas meets the criteria for well-designed conservation landscapes.Are there with representative systems o f conservation areas o f sufficient size, condition and connectivity to maintain eventhe most sensitive species and ecological process?28Part of the MOT'Sargument infavor ofthe Canal isthat the Romaniadeltareserve is bisectedbythe SulimaCanal with few illeffectsandthattheirapparentlyviablestrictlyreservedsubareasareonaveragesmallerand widely dispersed. Thus a first step inmaking a decision about the environmental impacts o f the Canal on biodiversity would be to identify the critical delta ecosystems that needprotection and directing scientific research to scale the area o f contiguous habitat neededto maintainthem. A whole series ofregional development issues may also affect the firture viability o fthe Danube Biosphere Reserve. Many ofthe objections to the canal proposal are based on lack o f dueprocess andthe very narrow scope ofthe environmentalimpact assessmentthat only looked at the local economy rather than looking at a more regional level that is necessaryto fully understand the dynamics of the Black Sea-Danubenavigational system. The Future-Shouldthe BankGet Involved? The Bustroy controversy raises four issues that are germane to the Bank's missionin Ukraine\. 0 The Canal has potentially adverse effects on the sustainability of a completed GEF/Bank investment. 0 Itis important that Ukraine abides bythe internationalagreements andconventions it has signed. 26. UNDP/GEF. 2003. Local Business for Biodiversity Conservation. Andrew Bovanick and Ajay Gupta (Authors). August 2003. 27. Strictly protected area Nos. 8 (ArinigulErenciuc) and 10 (Sacalin-Zatoane). 28. Olsen, DavidM.,E.Dinnerestein, G.V.N. Powell and E.D.Wickramanayake. 2002. Conservation Biology for the Biodiversity Crises. Conservation Biology Editorial. Vol. 16, No. 1, pages 1-3, February 2002. Fighting corruption, ensuringgood governance andpromoting the rule o f law are key to the sustainability ofthe Bank's investments. Important investmentdecisions should be made only after sound economic, environmental, and social appraisal to ensure the best use o f resources and stakeholder buy-in.Failingto ensurethat Ukraine applies the higheststandardsto investment decisions affecting a GEF/Bank financed project would sendthe wrong signal to government. WHAT VALUEWOULDTHEBANKADD? The Bustroy Canal is a reactionto inadequate economic development inthe Pridunajskogo regiono f southwest Ukraine, motivatedby frustrationthat Romania i s getting the lion's share of the Danubenavigationand transit benefits, a sense that Ukraine must secure its frontier against the incursion o f the expandedEU, and anger at havingto pay an estimated US$l milliodyear intransit fees to Romania. Inreality, however, the Bustroy Canal may become irrelevant as the Black Sea-Danube regional navigationsystem continues to evolve. The Bank i s uniquelyplaced to bringcross-sectoral perspective to the table and anintegrated approach to a transboundary problem. WHATSHOULD BECONSIDERED? Putthe BustroyCanalincontext.The real issue is not environmental but one o f regional economic development andtrade. Navigation i sjust a meansto achieving these broader objectives and the investmentdecision should be based on the benefits and costs o f navigation, taking environmental aspectsinto account. The demand for localnavigationvia the Danube river inthe Ukraine, Moldova, andnortheastern Romanianeedsto becarefully appraised. The MOT is arguingthat towns along the Ukrainianpart ofthe Danube(Izmail andReni) are ineconomic decline because o f silting o f the Ochakivsky Rukuv waterway and the Porva Canal, and the highcost ofusingthe Selima Canal inRomaniato reachthese towns. Inpractice, it couldbethat navigationhas declined becauseo f falling production inthe region. It is, o f course, possible that production will increase inthe future, but this needs to be assessed based on likely regional development scenarios. Fewforeign ships use the Ukrainianaccessto the Danube because transaction costs are highandthere i s little economic activity. Even so, MOTC believes the Bustroy Canal is neededbecause (according to them) Danube transportation tonnage will increase 300 percent by 2015, attracting foreign ships to Ukrainiannavigationfrom the Romanian Danubetransport system. The BustroyCanalis unlikelyto be competitivefor regionalcargoes. The Black SeaDanube navigationsystemwill be upgraded inthe mediumterm andthis will make the Danube Deltaportionredundant except for local shipping. The Danube flows easterly along the southern border o f Romaniaand at Cernovoda inRomania, 65 kilometers from the Black Sea, it turns north to flow another 300 kilometers before discharging through the DanubeDelta. The Constanta Canal, 7 to 8.5 meters deep and capable o f taking 5.5-meter draft ships, connects Cernovoda via a single set of lock gates to Constanta, Romania's biggestport inthe western Black Sea. Thus the Constanta Canal saves 300 kilometers o f slow river navigation and avoids time-consuming Ukrainiancustoms and immigration checkpoints. There are discussion in Romania about upgradingthe Constanta Canal by improving the lock and increasing the draft would enable it to cater for all potential users of the canal except those wanting to dock in Ukraine andMoldova. Determinethe true costs of the canalproposaland realisticalternatives. Current cost estimates for the Bustroy Canal are confinedto engineeringthe canal and do not include operation andmaintenance or other costs (e.g., environmental). Giventhat some cargoes will needto betransferred from deeper-draft ships, a transfer port facility plus support infrastructure would also be needed andthis would probably be located inthe reserve area. Thus the cost base needs comprehensive appraisal. Determiningthe likely environmental impacts (andbenefits) will require transboundary analysis notjust of the impacts on the biosphere reserves, but on the regionas a whole. This would include modeling the effect of deepening the Bustroy channel on theregional flow patterns andwater quality inthe Danubedistributaries. Changed flow regimes would also affect the delta and near-shore sedimentation patterns andmay affect navigation in Romania. Changed water quality could affect seasonal fish-spawning patterns, fish stocks, aquatic flora, andbirdmigration andbreedingpatterns. LESSONS Experience with this project confirms a number o f OED lessons\. 0 Biodiversity conservation cannot be carried out inisolation. Ithas to be integrated within the economic interests o f local andregional communities. Resentmenti s created when financing o f nature conservation appears to have preference over unmet local needs, be it delivery ofbasic services or employment. Failureto integrate local interestsinthe conservation and management strategy o f a biosphere reserve can endanger its longerterm sustainability. 0 Conservation areas will be sustainable only ifthere i s good management and sufficient funding to maintain it, Thus it i s incumbent upon GEF project designersto facilitate establishment o f sound management and governance arrangements that include local stakeholders andpromote income-generating activities that will provide sustainable income for management. 0 Biodiversity conservation may require trade-offs, particularly on the size of the restricted area inwhich all economic and humanactivities are banned. Too large an area creates very highoverheads on policing andregulation andpossibly strong local oppositionthat may undermine longer-term sustainability. The size o fthe area depends onthe conservation objectives. Thus there should be sufficient funding and time to facilitate agreement on the species and/or landscapethat are the targets o f conservation, and for research to determine requiredminimumviable habitats/landscapes andtheir connectivity to larger-scale ecosystems. 0 When establishing biodiversity reserves it i s important to promote networking of the reserve staff with the national and internationalNGOs and promote recognitionby internationalconventions. By doing so, a supportive network can be created that can quickly mobilized to support the objectives o f conservation management should these be threatened by political, financial, or disaster-related events.
P039171 | Yemen - Seeds and Agricultural Services | Middle East and North Africa | Yemen, Republic of | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/683871474594556400/text/000020051-20140613035636.txt | http://documents.worldbank.org/curated/en/683871474594556400/pdf/000020051-20140613035636.pdf | The Bank should explain to the Borrower at the outset the relevance and significance of its procurement and disbursement procedures in order to avoid implementation delays.
P039196 | BR RGS ST.REF | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 1999 | 2000 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/380201475085283079/text/000020051-20140522104645.txt | http://documents.worldbank.org/curated/en/380201475085283079/pdf/000020051-20140522104645.pdf | The Bank can and should work with sub-national governments to address relevant issues. However, while sub-national governments are key elements within the framework of a country's overall reform program, they can only do so much in the absence of a consistent national system of incentives and an adequate framework at the federal level. Operations should focus on a few, significant reforms that are hard to reverse (such as privatization in this case). Reform loans should support the state's own reform program. Despite the irreversibility of privatization reforms, the project raises the question of whether greater consensus can be achieved with respect to these reforms. The Bank should focus on those sub-national governments that are most willing and able to implement major reform programs, which will offset in part the risk of reforms being stalled.
P039196 | BR RGS ST.REF | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 1999 | 2003 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/630131468743965662/text/25971.txt | http://documents.worldbank.org/curated/en/630131468743965662/pdf/25971.pdf | 5. Lessons Learned 5.1 The lessons learned are not particularly new, especially for those deriving from the technical assistance andcredit line loans. Indeed, they have beenreiterated inmany OED reports and PPARs. Major lessons o f general applicability from the five loans assessed include\. 0 Technical assistance which lacks a clear blueprint i s hardto manage, and provides too manytemptations to apply unallocated funds to low-priority activities. 0 Macroeconomic instability and the absence o f market-determined interest rates greatly increase the risk o f failure for financial sector loans, confirming the findings o f the Levy Report. 0 Credit lines (financial intermediary loans) are unlikely to be appropriate instruments for supporting financial sector reform. 0 Fullandcomplete accounting for project expenditures is a core Bankresponsibility. 0 Lending to sub-national governments can be a powerhl instrument for advancing specific country strategies. 0 Continuity o f Bank interventions across state administrations promotes lasting institutional change inBrazilian state governments. Sub-national programmatic loans may prove to be better instruments thantime-bound SRLs. A prime example is the regulatory agencies, which have sufferedbecause, once the SRLs closed, the Bank effectively abandoned the agencies while they were still intheir infancy. 0 A functioning regulatory agency with an establishedregulatory environment isvital to optimal privatization o fpublic services. 0 The benefits o f dialogue during loanpreparation and supervision can outweigh the importance o f the funding, when complex issues o fprivatization and regulation are being addressed. Officials inall three SRL states cited the Bank's informal technical assistance as the most important benefit they derived from these loans. 0 The SRLs were cumbersome instrumentsbecause o f their investment loan characteristics. Sub-national adjustment loans (SNALs) should be a major improvement, allowing the Bank and Borrower to focus on what is important -policy reforms -rather than the minutiae o f disbursement andprocurement.
P039197 | BR RJ ST.PRIV. | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 1999 | 2001 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/194031474665313629/text/000020051-20140529065832.txt | http://documents.worldbank.org/curated/en/194031474665313629/pdf/000020051-20140529065832.pdf | The ICR distills important lessons from this experience. These include (a) Splitting of the state bank into "good" and "bad" banks leaves the state a large fiscal, legal and administrative burden after privatization; (b) Independence of state regulatory agencies may be safeguarded through state constitution or the federal regulatory powers; and (c) Legal conflicts of competence must be resolved before including any public agency in a concession program.
P039197 | BR RJ ST.PRIV. | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 1999 | 2003 | PPAR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/630131468743965662/text/25971.txt | http://documents.worldbank.org/curated/en/630131468743965662/pdf/25971.pdf | 5. Lessons Learned 5.1 The lessons learned are not particularly new, especially for those deriving from the technical assistance andcredit line loans. Indeed, they have beenreiterated inmany OED reports and PPARs. Major lessons o f general applicability from the five loans assessed include\. 0 Technical assistance which lacks a clear blueprint i s hardto manage, and provides too manytemptations to apply unallocated funds to low-priority activities. 0 Macroeconomic instability and the absence o f market-determined interest rates greatly increase the risk o f failure for financial sector loans, confirming the findings o f the Levy Report. 0 Credit lines (financial intermediary loans) are unlikely to be appropriate instruments for supporting financial sector reform. 0 Fullandcomplete accounting for project expenditures is a core Bankresponsibility. 0 Lending to sub-national governments can be a powerhl instrument for advancing specific country strategies. 0 Continuity o f Bank interventions across state administrations promotes lasting institutional change inBrazilian state governments. Sub-national programmatic loans may prove to be better instruments thantime-bound SRLs. A prime example is the regulatory agencies, which have sufferedbecause, once the SRLs closed, the Bank effectively abandoned the agencies while they were still intheir infancy. 0 A functioning regulatory agency with an establishedregulatory environment isvital to optimal privatization o fpublic services. 0 The benefits o f dialogue during loanpreparation and supervision can outweigh the importance o f the funding, when complex issues o fprivatization and regulation are being addressed. Officials inall three SRL states cited the Bank's informal technical assistance as the most important benefit they derived from these loans. 0 The SRLs were cumbersome instrumentsbecause o f their investment loan characteristics. Sub-national adjustment loans (SNALs) should be a major improvement, allowing the Bank and Borrower to focus on what is important -policy reforms -rather than the minutiae o f disbursement andprocurement.
P039199 | Low Income Sanitation Technical Assistace Project - Prosanear - TAL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/726441474632325255/text/000020051-20140619075118.txt | http://documents.worldbank.org/curated/en/726441474632325255/pdf/000020051-20140619075118.pdf | 1. Projects must accurately assess and respond to the relationships between national and local governments in a decentralized system during the development and program design phases. In PROSANEAR-TAL, decentralized decision-making and procurement processes could have been more accurately written into the overall project design, thus either eliminating or anticipating implementation delays. Accurately characterizing the relationships between national and local governments in a decentralized system, determining the degree of financial and political autonomy, and responding to these conditions during program development and appraisal will allow implementation to flow more smoothly through the life of the project. 2. Decentralization does not leave all municipalities equally able to implement projects. A decentralized institutional structure means that program implementation must be flexible enough to respond to the needs of individual municipalities, whether they need minimal technical assistance or full-scale project management partnerships. In the case of PROSANEAR-TAL, this may have included the development of a streamlined procurement process meant to suit multiple municipalities with similar needs.3. The project results framework should establish causal links between project development objectives and on-the-ground interventions and impacts. A TA project is very good at building capacity and offering technical guidance at the government level, but this activity is one level removed from on-the-ground infrastructure provision. In both program design and program evaluation, it is important to explicitly recognize the difference between actual project objectives and their intended effects. In PROSANEAR-TAL, a clearer link needed to be built between the stated project objectives and their anticipated impacts on the urban poor, so that those assumptions can be monitored throughout the program and evaluated at program close.
P039200 | ENERGY EFFICIENCY (ELETROBRAS) | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2008 | ICRR | Less than 10 million |  | Unsatisfactory | Unsatisfactory | Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/256521474595645168/text/000020051-20140618053853.txt | http://documents.worldbank.org/curated/en/256521474595645168/pdf/000020051-20140618053853.pdf | The main lessons which may be drawn from this operation are:1. The macroeconomic climate is of great importance for the success of any operation involving on-lending to third parties. This is the first of the conclusions drawn in a 2006 IEG study: â€œWorld Bank Lending for Lines of Credit: An EIG Evaluation.â€ This is particularly the case in a country such as Brazil, with a history of high inflation and macroeconomic instability. Even though inflation was declining at the time the project was prepared, the weakness of the currency and persisting high real interest rates were testimony to the prevailing lack of confidence in the durability of a stable climate. It is especially unfortunate that this dimension received such inadequate attention during project preparation.2. The regulatory framework and the incentive system should be analyzed carefully to determine whether they provide a sufficient counterbalance to contrary forces. In this case, there was a significant disincentive for power utilities to invest in energy efficiency demand side measures which would tend to depress their revenues. The regulatory framework in place at the time of project approval was insufficient to counter this. The benefits of the accompanying GEF project, including increasing consumer awareness of energy efficiency, were not yet apparent.3. Project supervision should be both candid and pro-active. Most supervision missions not only failed to find solutions to the problems facing the project, but persisted for most of the time in rating it as â€œSatisfactoryâ€ in the virtual absence of disbursements for four years. The framework of prevailing Bank staff incentives which led to this situation might merit further inquiry.4. Care should be taken in the choice of implementing agency, and the effects of changing national and sector policies on the agency should be rigorously analyzed. The project was prepared at a time of great flux and change in Brazilâ€™s power sector. It could have been foreseen that these changes would undermine the previously monolithic position of ELECTROBRAS. The company was subject to reorganization, downsizing and management changes that undermined its commitment to the project, as well as its ability to manage it effectively.
P039203 | UY FOREST PROD.TSP | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/383731474513255985/text/000020051-20140617140847.txt | http://documents.worldbank.org/curated/en/383731474513255985/pdf/000020051-20140617140847.pdf | The ICR draws the following lessons:Railway reform requires strong government support and a decisive actions.The design of institutional arrangements and forms of private participation should be customized to the country's needs.A multimodal/logistics project should have broad outcome indicators that measure the global output, and not just modal output for M&E.
P039250 | Roads 2 Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/976901474506684015/text/000020051-20140617140555.txt | http://documents.worldbank.org/curated/en/976901474506684015/pdf/000020051-20140617140555.pdf | The ICR suggested a number of lessons, of which the following appear to be of general interest:The Bank needs to ensure that any agreed cofinancing is delivered in a timely manner as if the sub-components which are dependent on cofinancing do not materialize the project cannot fully meet its development objective.The merit of using the remaining unallocated loan/credit amount for additional works need to be carefully assessed taking into account time implications for concluding further construction.To avoid large cost overruns, sufficiently detailed engineering designs should be used. In Romania, the designs were substantially less detailed than those normally used in Western European countries.
P039250 | Roads 2 Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2006 | 2009 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/761071468295230171/text/474140PPAR0P03101Official0Use0Only1.txt | http://documents.worldbank.org/curated/en/761071468295230171/pdf/474140PPAR0P03101Official0Use0Only1.pdf | 6. Lessons 6.1 This project coincidedwith Romania's move towards amarketeconomy. The continued support for the modernizationo fthe country's road system was important and necessary, butthe most interestingaspects ofthe project concernedthe ambitious attempts to make improvements relatedto transport andhealththat would helpRomania conform with EUnorms. Although there was an unexpected setback inhding arrangements, the project was able to accomplish muchwith the resourcesat its disposal. The project also provides a good example o fongoing partnershipandcooperation betweeninternational funders. There is, however, a danger that ifthe GOR lacks resolve inits future support for roadsafety, itwill fall shortofits aspirations.Themainlessonsto betaken from this PPARare\. That a holistic approachto road safety is necessaryinvolvingthe three Ed' engineering, enforcement andeducationto bringdownthe national accidentrate. Inthe RomaniaRoadsTwo Project this approachhashadsome success, but itwas found that a good coordinatingbody is essentialto bringtogether departmentsand entities unusedto working together, while continued political commitment is important to sustainthe initiative once this processhasbegun. InRomania a renewed, action-oriented emphasisis neededto ensure that the positive progress achievedto date is continued. Theroad improvement programwas effective, but the Romanianexperience highlights the importance of forecasting traffic as accurately as possible, of ensuringthere is a clear planto fundroadmaintenanceactivities, andof ensuring that there i s an appropriateprotocol inplace for the relocation o futilities. In the RomaniaRoadsTwo project specific arrangementscould havebeen madeto protect small works contractorsfacing avery steep rise ininflationary costs. Although aprice escalationclause is not usually included insuchcontracts it couldbe arguedthatforce majeure circumstancesapplied inthis particular case. Complex road safetyprograms canbenefit greatly from continuous and coordinatedpartnershipsbetweeninternational organizations over an extended timeperiod. The RomaniaRoadsTwo project exemplifies the mannerinwhich the partnerswere able to provide additional support at short notice when one of the componentshad a fundingshortfall.
P039251 | Private Sector Institution Building Loan (PIBL) | Europe and Central Asia | Romania | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/668601474907985633/text/000020051-20140613055943.txt | http://documents.worldbank.org/curated/en/668601474907985633/pdf/000020051-20140613055943.pdf | Twinning a genuine policy reform loan with a technical assistance loan, when expertise for reform implementation is clearly needed, helps ensure successful outcomes.
P039264 | Community Development Fund | Eastern and Southern Africa | Eritrea | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/803661474511949216/text/000020051-20140607142610.txt | http://documents.worldbank.org/curated/en/803661474511949216/pdf/000020051-20140607142610.pdf | Four lessons from the ICR aimed at improving future ECDF operations are: Depending on existing decision-making structures, explicit measures may be needed to support the processes of community mobilization and participation through information dissemination and knowledge-sharing, or more structured training in specific activities and functions. Physical output targets can get emphasized over longer term and less visible objectives of institutional development and sustainability unless clear mechanisms and incentives are in place. Maximizing development impact requires a focus on more complete investments and on ensuring that the necessary complementary inputs including software are in place. Ensuring sustainable service flows over the operational life of the investment requires that: (i) capacity building measures are well-articulated and defined collaboratively at the outset, pro-active implementation is undertaken, and there is systematic follow-up on results; and (ii) institutional, financial, and technical mechanisms for operations and maintenance are in place at all relevant levels.
P039264 | Community Development Fund | Eastern and Southern Africa | Eritrea | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2002 | 2002 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/817351511185054682/text/multi0page.txt | http://documents.worldbank.org/curated/en/817351511185054682/pdf/multi0page.pdf | 3. Lessons 3.1 The project provided many lessons that are outlined in the ICR. Several of these reflect discussions during the parallel AFR-OED mission, including the important role of ECDF in Eritrea's post-conflict situation. The focus here is on four of those lessons that are especially relevant for achieving lasting qualitative improvements in the population's living standards. 3.2 Lesson 1\. Building on existing institutional structures is good practice, and allowing existing\. village councils and regional administrations to elicit and screen community demand offers many advantages. However, depending on the nature of existing structures, they may need to be supported by explicit measures to ensure their effective, inclusive, and participatory functioning, for example, through information dissemination and knowledge-sharing, or more structured training in specific activities and functions. 3.3 ECDF uses existing village, sub-regional, and regional institutions to achieve community participation, with its own community mobilization and outreach being more limited. While ECDF has made some efforts to support and enhance the operation of these structures, a concerted and systematic effort at community mobilization and participation was absent. The project lacked a coherent operational strategy for ensuring inclusive decision-making. The Mid-Term Review for the pilot project had noted that the various structures of participation mandated by the government, in particular the various subcommittees at the village level (e.g., for agriculture, education, health, and social affairs), were overly limited in their functions and operational capacity, often simply relaying information to the local administration. The paper Future Directions of ECDF (Eritrea Community Development Fund, Future Directions of ECDF, ECOSOC, WOLDTAM, GECON Consultancy Services, Asmara, Eritrea, March 2000) hereinafter called Future Directions of ECDF paper, also noted that much remained to be done with regard to promoting active participation of communities and more support from stakeholders. Furthermore, an ethnographic study for Eritrea noted that an integral part of the new development strategies in Eritrea is to sustain and enhance national sentiments created during the liberation war by disentangling the closely knit rural communities, dismantling their corporate character, and linking the individual citizen directly to the state apparatus in order to foster an all-embracing notion of national identity.' Under the circumstances, this assessment observes that pressures on ECDF against using the community as 3. Mai Weini\. A Highland Village in Eritrea, Kjetil Tronvoll, The Red Sea Press, Inc., 1998. the unit of decision-making are likely to have been significant with obvious implications for the seriousness and depth of community participation. 3.4 Lesson 2\. Physical output targets may get emphasized over longer-term, less visible objectives like institutional development and sustainability unless clear mechanisms and incentives are in place. The trade-offs need to be confronted in the project design stage and the hierarchy of objectives needs to be defined and established up front. Insofar as sustainability and institutional development impact are important objectives of the project, explicit measures are needed to compensate for the natural bias toward maximizing immediately visible and more easily measurable results. Performance indicators are a useful tool to signal the outcomes valued by the project. 3.5 ECDF's capacity building component received low priority throughout the project's life. The Capacity Building Officer was recruited late in the project, left soon after, and the position has been vacant since. Effective implementation of this component could have had an important institutional development impact at various levels. It would also have helped to define institutional relationships and establish linkages between the ECDF's organizational structures and those of the government, both at the central and local level. 3.6 Lesson 3\. Maximizing development impact requires that the necessary complementary inputs, including software, be in place. Unless holistic investments are provided development impact is likely to be compromised. For example, health clinics without safe water supply or water investments without sanitation cannot be expected to maximize health benefits. This calls for better design and implementation and may necessitate coordination between different service delivery agents. Similar observations have been made in other OED assessments (e.g., Brazil Low Income Areas PPAR, and Abidjan Environmental Protection PPAR). 3.7 The need for holistic investments in ECDF has been noted in a number of sectors. With respect to health facilities, the Future Directions of ECDF paper noted the importance of ensuring complementary investments such as the provision of water facilities, electricity, sanitation, and waste disposal infrastructure. The Beneficiary Assessment also found that health centers lacked their own water source or pipe-connected water system. With respect to water supply subprojects, these have lacked proper drainage facilities or sanitation components or have provided water without cattle troughs, reducing the health benefits from water provision. With respect to schools, the Beneficiary Assessment found that some schools lack water and latrine facilities and the absence of fences is also common. The existence of facilities lacking critical complementary inputs was reiterated at the stakeholder workshop and observed during field visits conducted for this assessment. 3.8 Lesson 4\. Ensuring sustainable service flows over the operational life ofthe investment requires that (i) capacity building measures are well-articulated and defined collaboratively at the outset, proactive implementation is undertaken, and there is systematic follow-up on results; and (ii) institutional, financial, and technical mechanisms for operations and maintenance are in place at all relevant levels. Sustainability of investments should not be thought of at the end of the project, but rather as the justification of the project up front. Training and the establishment of sustainability mechanisms should be pursued early and vigorously during the execution of the project. In addition, continued engagement with the community in the post-completion phase of the project in order to provide technical assistance and training as operations and maintenance issues arise and close monitoring and follow-up on recurrent costs can also enhance sustainability. 3.9 In the absence of adequate sustainability arrangements to ensure that communities and other responsible entities had the ability to undertake the necessary maintenance activities, the continued flow of benefits from ECDF investments cannot be taken for granted. The Beneficiary Assessment noted for the health sector, the transfer of responsibility from ECDF to the commuffity or the regional adffin istratidn is too loose to isute its -gustainability. Most of the health stations and centers are already showing wear and tear. Consequently, the local administrations have already been overwhelmed by maintenance costs. The ministry of Health is already showing some uneasiness about the maintenance costs. The education sector seemed to perform better on ensuring sustainability. Water supply and sanitation investments faced several sustainability issues that ECDF is addressing, some using innovative measures.
P039281 | Ghazi Barotha Hydropower Project | South Asia | Pakistan | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/301871474908207957/text/000020051-20140612142113.txt | http://documents.worldbank.org/curated/en/301871474908207957/pdf/000020051-20140612142113.pdf | (1) Deciding to finance a project by assuming funding sources subject to great political and social influences should be carefully analyzed or better avoided at the time of project appraisal. In this project, WAPDAâ€™s counterpart funds estimated at appraisal (US$1,000 million) depended largely on improving the finances of WAPDA through tariff increases and corporatization, two subjects highly susceptible to social and political influences. Because these two assumptions did not fully materialize due to Government intervention, WAPDA was able to contribute only about US$690 million as counterpart funds.(2) To avoid conflicts of interest, it does not seem to be a good practice to involve, in new projects, the persons affected in the valuation of land and other assets or charged with retrofiting a past legacy issue. In this case, the valuation of land carried out during project implementation with participation of persons affected led to significant higher valuation than the appraisal estimate by a factor greater than three. This created delays in project implementation and a legal investigation of the way the land was valuated. Moreover, the retrofitting of pending compensations for persons affected by the Tarbela Dam did not work. (In response, the region pointed out that the positive contribution of participatory and consultative approaches for valuing land, income, or other asset losses has been acknowledged in many reviews, e.g., the QAG review of this Project (July 1998), the World Commission on Dams report (November 2000), etc. Similarly, a study by the US GAO (in 1998) observed that the consultative process adopted in GBHP was one of its strengths.)(3) The potential social impacts of a hydropower development can be reduced by a rigorous evaluation of alternatives, public consultation and awareness building. In the GBHP, the layout of the water channel and location of the barrage and power house avoided consciously existing villages and settlements, even at somewhat higher cost. This reduced the scale of resettlement and relocation without unduly affecting the economic and financial viability of the GBHP.
P039291 | Urban Environmental Management Project | Latin America and Caribbean | Colombia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/538631474665646610/text/000020051-20140612082244.txt | http://documents.worldbank.org/curated/en/538631474665646610/pdf/000020051-20140612082244.pdf | The financial risk implied by varied interpretations of the legal framework -- especially when such a framework is new -- should be taken into account during the appraisal process.Projects should build in a mechanism for inter-institutional coordination when coordination will be critical to the implementation process, and a periodic redefinition of roles and competencies in light of implementation experience should be undertaken when relevant problems occur. TA projects would be more effective if they include investment components in the project's later years to help generate greater political support; andTo make full use of the knowledge generated from a TA project, an adequate documentation center and related dissemination is important in order to create an institutional memory.
P039292 | SOCIAL INVESTMENT FUND | Latin America and Caribbean | Belize | Blend |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/409451474509371839/text/000020051-20140612083301.txt | http://documents.worldbank.org/curated/en/409451474509371839/pdf/000020051-20140612083301.pdf | Based on the ICR, key lessons include: Poverty targeting needs special attention in a demand-driven approach which, as in Belize, tends to favor communities better able to prepare viable subproject proposals who typically are the less poor. The trade-off between operational speed and intensive community participation is a real one and should be explicitly acknowledged and addressed, and reflected in performance indicators. It is difficult to transform a SIF from an engineering outfit to a community development organization. In Belize, a successful transformation would have required a culture change within the SIF and was not easy. The appropriate role and focus of the social fund agency should be anticipated to the extent possible from the outset and SIF staffing and institutional arrangements should reflect that. Inter-agency cooperation needs considerable and explicit attention and cannot be taken for granted. There must be appropriate incentives for cooperation on both sides.
P039312 | SECOND EAST JAVA URBAN DEVELOPMENT PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/856481475073193416/text/Indonesia-Second-East-Java-Urban-Development-Project.txt | http://documents.worldbank.org/curated/en/856481475073193416/pdf/000020051-20140607161357.pdf | The ICR highlights important lessons from this experience:Central government's subsidiary loan agreements with local governments need to be simpler, yet more rigorous in encouraging local governments to be more open to borrowing for financing urban investments.Central government and provincial governments need to define more stringent mechanisms to ensure that audit findings and recommendations are followed up and that project loan covenants are adhered to.There is a need for central government and the Bank to identify better solutions for sanitation, in view of the shortcomings of the approach adopted by this project.
P039312 | SECOND EAST JAVA URBAN DEVELOPMENT PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 2002 | 2006 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/794301468283544395/text/35624.txt | http://documents.worldbank.org/curated/en/794301468283544395/pdf/35624.pdf | 5. Lessons Learned Localgovernments in Indonesia should continue to build upon their demonstrated capacity to successfully implement improvements in infrastructure delivery, which has also been supportedby a long line of Bankprojects. However, local governments could be more responsivestill to urban development needs expressed through local communityparticipation. Communityparticipation inurban investment planningis often viewed only a formality and investments plans are often only an expression o f technical priorities which are identified by local officials themselves. Local governments needto engage more effectively incommunity consultation to ensure that urban investment plans also reflect expressed community priorities. A cross-sectoralframework such as Integrated UrbanInfrastructure , Development Program, can work wellfor local governmentsprovided the investment resources within it are sufficiently concentrated to adequately address needs in all included sectors. When resources are spread too thinly over a large area interms o fneed, itcanunderminethe expectedbenefits ofintegratedplanningresultinginincremental, rather than substantial, improvements inurban infrastructure. e All stakeholders, including local governments themselves,need to agree and understand clearly thepurpose behind local innovations-be it to increase efficiency, to increase client-responsiveness-rather than treat innovation as a benefitper se. Local governments inIndonesia are both interested and capable o f introducing innovative service delivery improvements, but while new approaches to municipal service delivery should be encouraged, new may not necessarily mean better. Local government should always articulate andmonitor the expected benefits from the innovation. As recognized inthe 2003 CAS, theBank has experienceand a rich knowledge basefrom many years of investing in local services through government (and more recently local government) drivenprojects. Ensuringthat local governments are always included as partners, with continuous emphasis upon improvingtheir performance, should be a mainstay o f all Bank assistanceto local service provision. Monitoring and Evaluation (M&E) systems need to be designedand implemented to track outcomes related toproject objectives, as well as the inputs and outputs of project activitiesthat will help achieve these outcomes.All three projects assessed inthis report focusedmainlyon successful implementationandinsufficientefforts were made to monitor the achievement of expectedbenefits -andpoor outcomes were not always identifiedintime. M&Ei s particularly important ingeographically spread-out projects and tracking meaningful indicators (which have a plausible link to project objectives and activities) can make up for the lack o f frequent supervision missions to participatingtowns.
P039376 | BULGARIA OZONE DEPLETING SUBSTANCES PHASEOUT PROJECT | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1996 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/905981474630159526/text/000020051-20140529155921.txt | http://documents.worldbank.org/curated/en/905981474630159526/pdf/000020051-20140529155921.pdf | To ensure the grant funds were allocated to companies with good prospects for survival and growth, the Bank and the Government agreed to temporarily suspend project implementation in enterprises undergoing privatization. Although this led to delays, the outcome was positive since all the participating enterprises are fully functional today. This points to the wisdom of being aware of risks in the course of project implementation and taking necessary measures to mitigate them.
P039437 | Poverty Reduction and Local Rural Development (PROLOCAL) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2002 | 2008 | 2009 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/281101474576734424/text/000020051-20140618194038.txt | http://documents.worldbank.org/curated/en/281101474576734424/pdf/000020051-20140618194038.pdf | Building on the useful lessons in the ICR three are emphasized: Projects aimed at capacity enhancement and community participation should explicitly and systematically monitor and evaluate the extent to which these are achieved using both quantitative and qualitative measures and appropriate baselines. The building of adequate community participation requires time, resources and explicit attention to incentives for the stakeholders. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured. While CDD projects because they support scattered sub-projects can be non-threatening for local and regional elite, they also have limited capacity to influence structural constraints that could limit the impact of the projects. Issues like unequal land distribution, quasi monopolis over water and markets in the targeted micro-regions constrained the achievements of the PROLOCAL project.
P039449 | HIGHER EDUC | Europe and Central Asia | Hungary |  |  | Human Development | Education | IBRD | IPF | 1998 | 2005 | 2003 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/438711474420468791/text/000020051-20140604054529.txt | http://documents.worldbank.org/curated/en/438711474420468791/pdf/000020051-20140604054529.pdf | Policy reforms are more likely to succeed if consultations are held with multiple stakeholders, including the opposition. It may also be useful to include political experts on preparation teams to provide guidance on minimizing the risk of policy reversal and to advise on how best to appeal to the interests of stakeholders and political actors who may potentially oppose reforms.-When a project expects to significantly change behaviors and rules of the administration, institutional experts should be included on preparation teams to advise on strategies and priorities for doing so. -For complex project designs, one must think through clearly priorities and the sequencing of actions and build in implementation flexibility. Some project components may advance quickly, and others may lag.-When planning large scale civil works in a country where the Bank lacks much experience, it is useful to engage local experts to lay out all the steps, estimate the time involved with each, and advise on how to optimize implementation time.-Having Bank procurement expertise in a regional Bank office facilitates project procurement but by no means guarantees success.
P039450 | Health Project | Europe and Central Asia | Croatia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1995 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/385271475099291306/text/000020051-20140529154754.txt | http://documents.worldbank.org/curated/en/385271475099291306/pdf/000020051-20140529154754.pdf | Borrower commitment to a projectâ€™s strategy, goals, and implementation is critical to successful project performance.Indicators of project performance, in terms of both outputs and health outcomes, need to be regularly collected and used for project management as well as final evaluation.Baseline studies need to be done prior to health promotion interventions in order to assess subsequent changes in health behaviors. Such studies need to have high priority at project startup if preventive health strategies and goals are an important component of a project. The provision of equipment and training alone is insufficient to shift health system emphasis to primary care in the absence of effecting other changes within the health system (e.g., salaries of various levels of health care providers).
P039455 | WTRSHED & ENVIRON MT | Latin America and Caribbean | St. Lucia | Blend |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 1998 | 1999 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/864821474570263217/text/000020051-20140519080617.txt | http://documents.worldbank.org/curated/en/864821474570263217/pdf/000020051-20140519080617.pdf | (i) The acceptance by the Bank of flexible procurement procedures, within the Guidelines, is of critical importance to ensuring efficient operation of project which respond to emergency situations;(ii) The infusion of local knowledge from national staff can be important in the design of emergency operations;(iii) The active participation of affected communities is important in achieving effective and sustainable management of watershed areas and ensuring government accountability.
P039455 | WTRSHED & ENVIRON MT | Latin America and Caribbean | St. Lucia | Blend |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 1998 | 2006 | PPAR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/225621468302682830/text/326771rev0pdf.txt | http://documents.worldbank.org/curated/en/225621468302682830/pdf/326771rev0pdf.pdf | Lessons TheBank needs to be more involved in the immediatepost-emergemy period, and it needs to be able to quicklyfund activities that do not require detailed preparation, but it needs to take the necessary time toprepare infrastructure rehabilitation components that require careful attention to design. Ifthe Bank i s eventually going to be involved inreconstruction, it needs to sit down at the table withthe early responders. The Bankshould bepresent inthe immediate aftermath o f a natural disaster when decisions are made which influence future reconstructionactivities. Bank staffwith disaster knowledge needto advise governments on reconstruction andmitigation, and other players needto have an understandingofwhat the Bank will ultimately do. Since SIDS tend not to have large reserves available for disaster reconstruction, small-scale but nearly instant fundingis crucial inthe immediate aftermath of a disaster. The experience of these two projects illustrates the perils o finadequate attention to design, including taking into account the motivation and perceptions o fkey stakeholders. P In theabsence of borrowerstaff experiencedin Bankprocurementpractices, early training and support needs to beprovided, especially under the timepressures that are normalfor emergency operations.DuringWEMP it took a long time for the involved govemment staffto learnBank procedures. Inthe context o f SIDS, it i s important to take into account the capabilities o f the country. A small country with limitedhumanresourcesneeds assistanceifit is to produce the same amount o fdocumentation as a large country. Targeted procurement support needs to be tailored to the capacity o f individual SIDS. P Wheninterveningin thenatural behavior of a river, it shouldbe realizedthat thereis a danger of triggering unexpected and negative effects. For this reason it i s sometime preferable to keep land adjoiningrivers free o f construction and to allow the river to have some freedom o fmovement. I n order to work out a feasible action plan for watershed and environmental management it is imperative to identcjj the main constraints hampering sound management. In St. Lucia constraints have included turf issues between relevant public institutions, the movement o f farming to the hillsides, the nature o f local crops, and local perceptions o fhazards (causes andremedies). P With adequatepreparation, infrastructure can be rebuilt in three years, but creating viable institutions at the national, district, and community level takes much longer. Grappling with well entrenched environmental bad practice i s even more challenging and time-consuming.
P039584 | AR B.A.URB.TSP | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/225311474627361584/text/000020051-20140625192723.txt | http://documents.worldbank.org/curated/en/225311474627361584/pdf/000020051-20140625192723.pdf | The ICR has identified a number of lessons and the most important ones are listed below with some adaption of language:Â· Consolidation of transport reforms cannot be sustained without building capacity for future generations of transport leaders. Where there is limited availability of skills that could conceptualize urban mobility in a comprehensive manner, the Bank could help address this challenge effectively under its projects.Â· Public consultations can have a significant impact on project design and community ownership. Projects can benefit from consultations carried out continuously throughout project implementation. Participatory process need not only take place at appraisal or at the onset of a project. Â· Institutional integration agendas are difficult, political and time-consuming. Metropolitan Transport Agencies are highly political and it remains a challenge to support such ambitious institutional agendas within the constraints of the Bankâ€™s instruments for investment loans. Even though at appraisal the political environment might seem beneficial for institutional change, the project design should conservatively assess the risk of drastic political changes.Â· Client- focused application of the Bankâ€™s procurement policy can add a lot of value. Focusing Bank's Procurement Guidelines to the actual needs and circumstances of the client and adapting them pragmatically to the situation on the ground can allow the Bank to engage and contribute to broader reform agendas.
P039584 | AR B.A.URB.TSP | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2011 | 2017 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/318981493400281122/text/113664-PPAR-P039584-PUBLIC.txt | http://documents.worldbank.org/curated/en/318981493400281122/pdf/113664-PPAR-P039584-PUBLIC.pdf | Lessons 7.1 Private sector participation cannot achieve efficiency gains if incentives are misaligned. After the economic crisis in 2001 in Argentina, both partiesâ€”the government and the private firmâ€”faltered on their obligations under the concession contract, which became a management contract. The concessionaire received compensation for the costs incurred but it lacked incentives for cost control and efficiency in urban rail operations. In addition, low fares maintained through government subsidies subsequently contributed to a growing fiscal deficit, while underinvestment in the system continued. This example demonstrates how a public-private partnership scheme can underperform if sector reforms and the right price signals are not in place. 7.2 The creation of new institutions brings long-term gains and benefits when voluntary association and political will are present, as international experience also shows. In Argentina, the decision to form an entity for metropolitan transport coordination in Buenos Aires was first made in 1991. It took more than 20 years for it to be established in 2014, and 2 additional years to become operational. A currently functioning Metropolitan Transport Agency was largely due to an unprecedented level of political alignment facilitated by the new administration that came to power in December 2015. Previously, the national government and the city administration were held by different political parties; this was partly a barrier for cooperation and policy coordination at the metropolitan level of Buenos Aires. The current political situation offers an opportunity to act on measures that could ensure sustainability. Overall, institutionalization of a new entity should not be an objective but rather a means to achieve the aspired development results. Political commitment and consensus bring progress and functionality to institutions. 7.3 Potential fiduciary problems are difficult to detect, which emphasizes the critical importance of training project staff. The presence of red flags related to potential fraudulent practices in procurement and project implementation does not imply corrupt activities. Likewise, the absence of warnings or red flags does not guarantee the absence of fraud. In Argentina, allegations of irregularities in World Bankâ€“financed contracts appeared in the local media, prompting investigation and forensic auditing. Misprocurement was subsequently declared on several contracts almost two years after the project closing date. The World Bank project staff was cleared of any wrongdoing. Along with training staff to diagnose and enhance detection of risks to integrity, it is essential to help project teams with information about how to address such risks, including how to interact with the various forms of media to manage the risk of potential reputational damage to the World Bank.
P039643 | ID-STD/AIDS | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2000 | 2001 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/776871475090653045/text/000020051-20140529074909.txt | http://documents.worldbank.org/curated/en/776871475090653045/pdf/000020051-20140529074909.pdf | All projects--and certainly pilot projects potentially destined for national replication -â€” need agreed-upon baseline data against which to measure the results and efficacy of project interventions.NGO involvement in STD/HI V/AIDS activities is a critical part of a comprehensive national AIDS Prevention Program. Thus government procedural impediments to NGO involvement must be addressed at the appraisal stage, and removed, if possible, before project approval.Optimal consideration of PMU structure, composition, capabilities, and responsibilities must be given continuing Bank attention. Experience in Indonesia suggests that PMUs should focus on project administration, while responsibility for policy and technical issues should rest with line departments. The PMU needs to exercise leadership and facilitate communication to peripheral levels without becoming a bottleneck or a source of conflict and/or technical miscommunication.
P039643 | ID-STD/AIDS | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2000 | 2005 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/372521468048914553/text/32572.txt | http://documents.worldbank.org/curated/en/372521468048914553/pdf/32572.pdf | 6. Lessons 6.1 There are risks of amplifiing HIVIAIDS messages in theface of the inherent uncertainty in a nascent epidemic. Political commitment was too closely tied to the expectation that HN/AIDS would imminently explode under CSW-driven transmission, inthe absence ofearly action. As theProjectentered into execution, MOHstaffcould see that the alarming scenarios that established a rationale for emergency intervention were not being realized, underminingpolitical commitment for the Project. The attention ofpolicymakers inevitably turned to other subjects inthe wake o f the financial crisis. Yet, there were still good grounds, inthe experience ofother countries, for the GO1to devote attentionandpolicy energyto HW. 6.2 A strategicfocus on HRG andpublic goods is not enough to ensure results in a nascent epidemic. Investmentsininstitutional development andmobilization o fpolitical support amongrelevant decision-makers andimplementers are even more important. Close supervisiono f interventions for HRGi s critical to ensure that the focus is not lost inimplementation. Thepressuresto broadenservices beyondHRGwere evident in Indonesia and the focus on HRGwas diluted inimplementation. Investments ina lowlevel epidemic that call for reachingout to dis-empowered andmarginalizedpopulations, such as commercial sex workers and IDU,need to include continuing activities to nurture andexpand political support. 6.3 More donorfunds may be available than can be absorbed in direct HIV'AIDS services in a nascent epidemic. Discussions with donors inIndonesiasuggest that this was the case with NGOs. Policy development and institutionalpreparedness may initiallybe more important thanwidespread service delivery 6.4 Closenessof the task manager to day-to-day Project activities does not necessarily strengthen supervision. In the HSPMP it appeared to make the conduct o f regular supervisionmissions seem unimportant. It is notjust proximity to the client that i s important, but the right kind o fproximity. 6.5 It is unrealisticin threeyears to expect to build capacity, institutions, and political commitment among the many stakeholders inside and outside governmentfor controversial activities in highly contested areas like CSW and IDU. I h e HSPMP S A R appropriatelyforesaw the Project as the first phase o fa long-term engagement, but the GO1andthe Bank expected to accomplishtoo muchinthe limitedperiod o f a three-year operation. 6.6 TheIndonesiaHSPMP experience underscores the country specijkity of decisions on institutional roles and responsibilities and the needfor analysis of institutional options. InIndonesia, the Bank staff chose to focus their work on strengthening HIVlAIDS institutions inthe health sector by creation o f an MOHProgram Management Unit, rather than a more simple Project ImplementationUnit. Given the growing importanceo f sexually transmitted diseases (STDs) inthe country andtheir importance as a vehicle for addressing HIV issues, the choice o f focus on the MOHwas appropriate. The National AIDS Commission was too weak, institutionally and politically, to be leadinterlocutor. However, the institutional arrangements withinthe MOHpromotedbythe project didnot anticipate the duplicationofroles andconflicts among units within the MOH, due inlarge part to weak institutional analysis at the time o fproject design.
P039644 | ID-W. JAVA BASIC EDUCATION | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/628181474574914723/text/000020051-20140613060938.txt | http://documents.worldbank.org/curated/en/628181474574914723/pdf/000020051-20140613060938.pdf | 1. During times of financial crisis, or political change, projectsdesign should allow for flexibility, and the potential for rapid restructuring as the need arises.2. School mapping can be useful to education agencies at all levels. For instance, school mapping may be used to provide a better understanding of: (a) inequities in resource allocations between geographical areas; (b) physical limitations to school access (i.e. lack of roads, infrastructure, services); (c) imbalances in district or provincial education officer assignments for school oversight; (d) preferred locations for new school establishment, based on needs; and (e) preferred locations for school expansion to meet increasing enrollment demand.3. The use of contract teachers has proven to be a viable management option to address issues of temporary teacher shortage and the need to introduce increased flexibility into the civil service.
P039749 | HEALTH SECTOR REFORM | Middle East and North Africa | Jordan | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/996011474593398697/text/000020051-20140613063719.txt | http://documents.worldbank.org/curated/en/996011474593398697/pdf/000020051-20140613063719.pdf | An institutional capacity assessment would have identified key constraints in coordinating the three public sector providers and thus mitigating measures could have been included in the project design. In particular, the challenge of coordinating the financial management systems and establishing consistent accounting practices was not adequately addressed and thus the project activities geared towards the financial sustainability objective were not implemented. Closer attention should have been paid to implementing this quality-at-entry assessment recommendation.
P039754 | Second Technical Assistance Project for the Public and Private Provision of Infrastructure | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1995 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/746481474666307954/text/000020051-20140607160916.txt | http://documents.worldbank.org/curated/en/746481474666307954/pdf/000020051-20140607160916.pdf | Many of the problems of private investment in infrastructure during the financial crisis were the result of debt and equity in foreign currency. These projects will continue to be vulnerable to external shocks until domestic financial markets are more fully developed.The policy framework for PPI should be part of an overall infrastructure framework, so that public and private infrastructure development do not compete with each other.Demonstration projects are essential: it is only when faced with real situations arising in pilot projects that practical difficulties are brought to the attention of policymakers.Changing the mindset of government officials who are accustomed to public provision of infrastructure services, to support private sector participation, is a long process. It is further complicated when the public sector is undergoing a process of decentralization.
P039787 | Biodiversity Conservation Project (GEF) | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2008 | 2009 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/325431474632397583/text/000020051-20140619103103.txt | http://documents.worldbank.org/curated/en/325431474632397583/pdf/000020051-20140619103103.pdf | Recognizing that "development is not a linear process and processes need to be sufficiently flexible to adapt to changes on the ground," the ICR highlights several well-known generic lessons for biodiversity conservation projects, specifically: (1) the creation of a protected area is a complex process that involves diverse actors and requires substantial coordination; (2) monitoring and evaluation of biodiversity should be carried out at ecosystem levels; and, (3) local participation in the management of protected areas is a key tool for enhancing conservation. In addition, the project experience reveals the importance of simple and straightforward project design, based in part on previous Bank sector work, as well as the advantages of "hybrid" approaches to the expansion and consolidation of national protected areas systems through parallel and associated IBRD and GEF operations. This approach helps increase the leverage of each project in relation to the other and to strengthen the same borrower institutions, in this case the APN. It also affords economies of scale in Bank assistance to the client during project preparation and implementation/supervision.
P039787 | Biodiversity Conservation Project (GEF) | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2008 | 2011 | PPAR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/148491468207856941/text/609470PPAR0P040e0only0900BOX361497B.txt | http://documents.worldbank.org/curated/en/148491468207856941/pdf/609470PPAR0P040e0only0900BOX361497B.pdf | 6. Lessons Learned 6.1 There were four lessons learned from these two projects involving the adoption of technological advances to monitor rapidly changing environmental conditions, the blending of financial instruments to cross-subsidize different project objectives, the risks and uncertainties of experimenting with innovative land-use practices, and the importance of having well-defined and focused objectives. 6.2 The Bank should encourage natural resource project managers to take advantage of rapidly changing advances in biodiversity conservation methods and tools to complement traditional on-the-ground monitoring of indicator species surveys. These include satellite imagery and aerial photographs of habitat vegetation cover, or real-time remote monitoring devices and camera traps when conservation of specific species is the objective. The ABC Project took an approach to biodiversity monitoring that focused on surveys of key indicator species in each of the five parks established by the project. This approach turned out to be more problematic than anticipated, generating information of poor quality and reliability. Taking advantage of recent technological advances and falling costs of these new tools might result in technically complementary and cost-effective ways to assess key habitat and species. The costs involved in monitoring changing conditions over time will depend on the project objective, but whatever approach is taken should aim to provide information that is relevant for decision-making. 6.3 Satellite imagery complemented by aerial photography and light detection and ranging (LiDAR) technologies or pre-positioned camera traps are becoming increasingly prevalent and affordable for landscape conservation planning and management. In rapidly changing environments where a new dirt road or airstrip can open up access to illegal activities in large, remote natural areas with little government presence, the Bank should provide more support to project managers to work with implementing agencies and other partners to take advantage of these new technologies to obtain more accurate and real-time monitoring data. Over the past 20 years, a number of second-tier institutions such as NGOs and universities have developed very sophisticated conservation management approaches, tools, and technologies to locate and quantify species diversity and measure effective habitat management. For instance, the World Bank and WWF have developed a Monitoring Effectiveness Tracking Tool that allows project participants and managers to quickly and accurately assess the quality of perceived interventions among project beneficiaries and other stakeholders. This tool is now commonly used by GEF financed projects as a simple and cost-effective means to gauge the degree of effective management across a range of issues in protected areas. 6.4 Blending different lending instruments, such as IBRD loans with GEF grants, to achieve different forestry or natural resource management objectives can be an effective way to engage clients in addressing the full range of sector challenges they face. For example, the decision to use an IBRD loan to help Argentina increase park system revenues under the NFPA Project while preserving ecoregions of global significance under the ABC Project justified the use of a GEF grant. It was unlikely that the government would have agreed to pay the start-up costs of these new parks without GEF support given their low tourism potential. In terms of financing projects with both global and national benefits, blended packages of financial support can create the right combination of incentives needed to engage clients in a full discussion of their national forest objectives for both productive and conservation purposes. 6.5 When experimenting with new techniques or approaches to land-use practices or natural resource management, it is best to approach experimental interventions in a measured way assuming that unexpected difficulties, costs, and delays will inevitably arise. The NFPA Project conducted applied research projects on compatible land-use practices in productive landscapes while the ABC Project introduced alternative, less destructive productive activities in park buffer zones. Both took more time and effort to accomplish than expected, and results were mixed. This should be expected given the uncertainty and risk perceived by those considering adopting innovative approaches. Changing practices is not a linear or smooth process, and it requires addressing all of the incentives and concerns of the intended end-users. 6.6 For example, the Applied Research and Studies program under the NFPA Project was designed to generate a number of case studies demonstrating the costs and benefits of mixed cattle-ranching and agro-forestry practices that are more compatible with maintaining the environmental services associated with native forests in collaboration with local land-owners. Identifying capable local NGOs, universities, and government agencies to collaborate with the project in carrying out these demonstration pilots proved to be more difficult and time-consuming than expected. Secondly, land-owners were riskadverse and not as willing to experiment with novel approaches to land-use management as expected without project funding to reduce their financial risk. The results from the demonstration sites were mixed and have not been replicated on a large scale for a number of reasons. One of the reasons for the lack of replication among other landowners was that the analysis conducted at the demonstration sites focused mostly on the environmental costs and benefits of the alternatives, but did not focus enough on the economic and social aspects (that is, the costs, benefits, and risks) to the land-owners of changing commonly used practices. It is critical to take this into account when promoting novel approaches or methods that bear directly on peoplesâ€Ÿ livelihoods. 6.7 A similar experience was encountered with the sub-projects to promote sustainable productive activities in buffer zones around the new parks established by the ABC Project. These sub-projects experienced many delays and setbacks, and did not uniformly achieve the lasting changes that were sought. Some of the productive activities that were introduced to local families by project facilitators were successful and sustained; many others were not. This should be expected since experimentation involves failing some of the time. Because results are difficult to predict upfront, achieving quantified targets can be problematic. These risks should be carefully assessed and mitigated in project design and appraisal. 6.8 The more focused an objective or target audience is defined, the more likely it is to be achieved. For example, one objective of the NFPA Project was to increase the environmentally sustainable level of tourism in four selected national parks. Increasing tourist visits and the revenues generated by them in those four parks was achieved by improving the capacity of APN to manage and protect those parks, and by enhancing the experiences of visitorsâ€Ÿ by improving infrastructure and concession services in the parks. Related to this lesson was the observation that more tangible and measurable activities, such as mortar and bricks types of infrastructure interventions, were more often achieved than were the softer institutional-strengthening or behaviorchanging activities in both projects. It is harder to change organizational cultures or individualsâ€Ÿ behaviors than it is to get them to change specific analytic techniques or to modernize facilities and equipment. The more an intervention can focus on a specific client or place, the more likely it is to be successful. For instance, it was found that the management plans developed for the five individual parks under the ABC Project were better utilized in setting up the management of those parks than the system-wide strategic plan to modernize APN by creating a Vision for a Reformed APN under the NFPA Project.
P039826 | ECO RECOVERY PROGRAM | East Asia and Pacific | Papua New Guinea | Blend |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1996 | 1997 | 2000 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/688401511188665205/text/multi-page.txt | http://documents.worldbank.org/curated/en/688401511188665205/pdf/multi-page.pdf | 00. Lessons from the Bank's past experience with adjustment lending in PNG applicable to this proposed operation include\. * Broad ownership of the reform agenda should be ensured. During the 1990s, several incoming governments avowed commitment to reforms and made the right initial moves, but eventually failed to sustain these efforts. Reform commitments tended to be made by a narrow circle of public sector officials and lacked broad-based support. Moreover, even among these officials, there appears to have been only limited appreciation of the purpose of reforms. Ownership of the reform agenda is essential to ensure sustained implementation during both hard and good times. * Adjustment lending to PNG should be undertaken only in the context of progress in addressing a broad front of sociopolitical constraints. Stimulating the desired supply response is likely to require parallel efforts aimed at improving governance, civil service reform, improving law and order, political reform, land reform, and consensus-building at the village/clan level. Future adjustment lending should be part of a much wider reform effort that begins to redress these issues. * Future adjustment programs should aim to achieve gradual, consistent implementation of reforms over an extended period. In retrospect, an overly ambitious and fast-paced reform agenda in the past generated opposition that helped inhibit substantial progress from taking place. A key concern for the private sector, moreover, is policy movement in a consistent direction, rather than rapid achievements that are then reversed. * Close collaboration with other development partners should be ensured so that the Bank can focus on longer-term structural reform. Both Bank-funded operations in the 1990s were implemented during periods of macroeconomic crisis and as a consequence focused on shortterm stabilization issues. Future adjustment lending should be done within a comprehensive development framework with other partners to ensure that Bank operations can focus on longer-term obstacles to changes in the production structure. * The government should be assisted in developing a public awareness campaign to broadbase the consensus for reforms. The Bank should encourage the GOPNG take the lead in developing a public awareness campaign, encompassing village-level groups, political leaders, the civil service, religious leaders, the press, the private sector, and NGOs in order to broaden understanding of the costs and benefits of structural adjustment and build public support. * A focus on improving incentives in the civil service is necessary to expand access to key public services. The elusive supply response is unlikely to be realized in the absence of expanded access to infrastructure in rural areas. A critical obstacle to expanding infrastructure access in the past has been poor performance among key public agencies, including the Department of Works. These public agencies need restructuring and incentives to improve the delivery of services. * The Bank should maintain a close relationship with the GOPNG and civil society and develop full awareness of the social, political, and cultural implications of adjustment operations. An appropriately staffed field office in PNG, which has been absent in the past, is likely to enhance this end.
P039838 | CN ODS IV PHASE OUT PRJ | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1998 | 2013 | 2015 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/838141474941458222/text/000012394-20150309074955.txt | http://documents.worldbank.org/curated/en/838141474941458222/pdf/000012394-20150309074955.pdf | The following lessons were selected, condensed and edited from the Lessons Learned section of the ICR (pp.23-24). 1. ODS production issues should be tackled in a more upstream manner within the context of ODS phaseoutstrategies. Experience gained in particular through the ODS IV Project's CFC production phase-outeffort compelled not only the Government, with the Bank's support, but also the MLF ExCom to invest inan upstream effort to curb HCFC production early on in the accelerated phase-out timeline in order tobalance global efforts to phase-out HCFC consumption with elimination of production capacity.2. Addressing the phase-out of ODS at the sector level is a more rational and cost-effective manner bywhich to curb large, non-uniform and dispersed consumption and production of ODS. The use of a three-pronged phase-out approach that supports policy development, technical assistance activities and thefinancing of ODS phase-out on at enterprise level based on annual sector reduction targets addresses thekey aspects of sustainable management of complex sectoral or national initiatives. 3. Performance-based programming, where funds are released annually based on pre-determined phase-outschedules, targets, and specific performance indicators having been met, provides an excellent implementation structure with which to motivate and incentivize stakeholders to find the most cost-effective ways to convert to non-ODS technologies or to phase-out ODS production. Housed within a consolidated sectoral or national framework, such programming lends itself to effective planning and can be very effective in generating higher-level, sustainable results.4. Investment in the development of a comprehensive MIS, complemented by verification of both financial records (conducted by the national audit body) and technical results by World Bank experts, were key to gauging the accuracy of results generated. The MIS tool allowed FECO to establish a tool with which to accurately report national, aggregate data, as required under Article 7 of the Protocol, as well as at the sector-specific data.Based on these lessons learned, Chinese ODS phase-out activities further require: (a) sound sector phase-out strategies as a pre-condition for a national program, (b) flexibility in project design, and (c) provision of training to national implementing agencies and implementing consulting firms.
P039856 | SAC II | Western and Central Africa | Cameroon | Blend |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1996 | 1999 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/356381474484436558/text/000020051-20140604050310.txt | http://documents.worldbank.org/curated/en/356381474484436558/pdf/000020051-20140604050310.pdf | A bold approach was successful in helping a country overcome very serious problems and a legacy of inadequate performance. SAC II was a high-risk, high-reward operation that achieved most of its goals. The project was the centerpiece of the 1996 CAS, which recommended a large IDA allocation to be disbursed against actual implementation of critical reforms designed to address deep-seated problems. Bank restructuring under SAC II was successful because it: (1) was conducted within a stable macroeconomic environment; (2) included strengthening of the regulatory and supervisory regimes; (3) involved a complete financial and operational restructuring of the firms; (4) marked the withdrawal of the state from ownership of financial institutions.
P039876 | BIODIVERSITY RESOURCE DEVELOPMENT (GEF) | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/966161474663558867/text/000020051-20140615105000.txt | http://documents.worldbank.org/curated/en/966161474663558867/pdf/000020051-20140615105000.pdf | 1. Training and employing local experts in taxonomy (parataxonomists) to collect, sort, preserve and analyze ecological specimens prudently builds on local communities' unique knowledge, increases local awareness about the value of biodiversity from a revenue and non-revenue generating perspective, increases local incomes (of farmers, teachers, students etc), imbues globally transferable scientific skills, and can relieve some pressure on the environment by offering alternative livelihoods to select groups (like cattle farmers in Costa Rica, for example). The training methods developed through this aspect of the program can be transferred to countries within and outside of the region, 2. The willingness of national governments to sustain the production and delivery of goods and services of global environmental value after incremental financing for these goods ends often affects the sustainability of stand-alone global environmental investments. Strengthening national or sub-national institutions, like INBio, already engaged inproviding information on conservation and potential values of biodiversity increases the likelihood that global benefits will be sustained. INBio, conceived as a private, nonprofit, public interest association, is also well positioned as a source of information not only for government entities such as SINAC (Costa Rica's Protected Areas System), but also educational and private entities. Further proof of INBio's commitment to sustain the global environmental knowledge produced by this project lies in its willingness to lead mentoring programs with Argentina, Nicaragua and Peru. 3. Discoveries such as a new species of fungus that can fight pathogens in the vanilla plant potentially have global application for World Bank client countries like Madagascar. Other ongoing research, for example, into vector control for dengue fever have widespread application potential for the Bank's client countries in sub-Saharan Africa. The Bank should strive to disseminate project research and findings outside of MesoAmerica. 4.Investing in the type of state-of-the-art bar coding technology and associated training adopted by INBio for rapid specimen scanning and data retrieval can potentially lower the marginal costs of biodiversity inventory processing, however INBio's capacity is more advanced than any other similar institution in the developing world - making the replicability of this investment in other Bank projects unlikely in the near term.
P039882 | Benin - Private Sector Project | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/892011474563606419/text/000020051-20140619084544.txt | http://documents.worldbank.org/curated/en/892011474563606419/pdf/000020051-20140619084544.pdf | In countries with weak capacity, projects should avoid including many components and multiple implementing agencies. Moreover, the Bank should provide sufficient support during implementation as building institutional capacity is laborious and time-consuming. The monitoring and evaluation system should be appropriate for the situation. This project's results reinforce the lesson that consistent political commitment is vital for success.
P039892 | TRANSPORT | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Transport | IDA | IPF | 1996 | 1999 | 2000 | ICRR | >=10 million & <25 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/878951474898822797/text/000020051-20140526210150.txt | http://documents.worldbank.org/curated/en/878951474898822797/pdf/000020051-20140526210150.pdf | There is one broad lesson: Coordination among agencies implementing IDA projects would result in increased efficiency and benefit everyone. Other lessons are specific to the situation in Georgia.
P039914 | DEBT REDUCTION | East Asia and Pacific | Viet Nam | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1998 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/631121474501914851/text/000020051-20140522102510.txt | http://documents.worldbank.org/curated/en/631121474501914851/pdf/000020051-20140522102510.pdf | Consideration should be given to complementing DDSR-type operations with measures to ensure implementation of continuing reforms key to facilitating access to international capital markets.If bolstering government debt management and monitoring capability is critical to the GVN reintegrating into the international economy--as ICR states--serious consideration should be given to complementing DDSR-type operations with adequate TA, not only to achieve initial debt purchase, but to broaden development of relevant institutions.
P039929 | Social Investment Fund Project (SIF) | Europe and Central Asia | Georgia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 1998 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/739741474851845733/text/000020051-20140619083131.txt | http://documents.worldbank.org/curated/en/739741474851845733/pdf/000020051-20140619083131.pdf | The ICR contains the following lessons:The sustainability of social investment fund sub-projects depends on the continuing support of communities, which tends to diminish after sub-project completion as collective enthusiasm falls off. The sustainability of infrastructure investments also depends on the degree to which local utilities assume the responsibility for operation and maintenance.The choice of the scope and size of micro-projects needs to balance technical aspects (e.g., the need to replace whole sections of buildings) with projected use -- particularly in communities with outmigration and declining fertility.The share of counterpart funds expected from communities needs to be carefully chosen, taking into account the particular circumstances of the country and the ability to pay on the part of poor communities.
P039935 | ILFS-Private Infrastructure Finance | South Asia | India | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/458101474650725305/text/000020051-20140607145741.txt | http://documents.worldbank.org/curated/en/458101474650725305/pdf/000020051-20140607145741.pdf | The most important lesson is that (i) in untested areas and in weak institutional environments, the Bank should only offer TA and small pilot investment projects to foster institutional development. If policy changes are called for, an adjustment operation may be considered. A (large) credit line is not the appropriate instrument to deal with either poor policies or institutions. Another lesson is that (ii) once a loan is approved, the Bank should try to make the best of it for either commercial or development purposes rather than contributing to its non-utilization five years later. Other lessons well elaborated in the ICR are that: (iii) while public-private partnerships in infrastructure are possible even in non-enabling environments, enhancement of capacity and actions in improving the enabling environment in the public sector ought to be emphasized from the start; (iv) country-, state-, and project-specific frameworks for private sector participation are often more important bottlenecks than the lack of appropriate financing; (v) the Bank should leave to IFC, which is comparatively better suited for this kind of operations, the financing and capacity building of private sector entities.
P039983 | PY 4th RURAL WATER SUPPLY & SANITATION | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/463231475081806757/text/000020051-20140618084734.txt | http://documents.worldbank.org/curated/en/463231475081806757/pdf/000020051-20140618084734.pdf | 1. The use of output-based subsidies makes it easier to provide subsidies targeted to the poor. The payment of a direct subsidy to the private constructor-operator is a good incentive for the local private sector to participate in the rural water sub-sector. 2. Participation of local communities contributes to the success of private sector financing of rural water supply projects. This makes the process more transparent and facilitates relations between the private sector and users. 3. Government/community collaboration is an effective mechanism for providing water supply services to the rural population. A collaborative approach allows both groups to utilize their strengths, thus producing outputs of higher quality that the ones each would achieve working alone.4. Pilot projects offer a practical approach to institutional and organizational change in the sector, as they provide opportunities for learning-by-doing on a small scale. The severity of the consequences of failure is reduced.5. Increasing per-capita costs can result from provision of services to smaller and more distant and dispersed communities. This is due to insufficient economies of scale and the application of the same technology and design criteria to all projects. Exploration of possibilities to increase the cost-effectiveness of the systems should be emphasized in future projects.6. Substantial up-front work to determine community demand for a given service should be carried out in order to avoid ineffective and inefficient interventions. The use of a supply-driven approach for the provision of sewerage services in this project failed to undertake this important step and faced high fiscal costs, inefficient sector investments, poor service coverage, and poor targeting of subsidies.7. Budgetary constraints for day-to-day activities severely hamper the effectiveness of a public sector organization in important areas like social promotion, technical assistance to communities, and follow-up on projects. 8. Building on the successes of previously implemented projects can improve the likelihood that a project will produce successful results as well.9. Contracting out for community promotion services may not produce satisfactory results. The reasons for this include lack of coordination between firms carrying out promotion and construction, for example; or, in the case of one firm carrying out both activities, promotion may be deemed a lower priority.10. Close supervision and dialogue combined with flexible project design allowing incremental changes can improve component outputs.11. Failure to confront implementation issues early on can result in significant delays. It may prevent management from taking action to help resolve project issues.12. Isolated communities require at least as much attention as communities that are easier to reach. Promoters assigned to them need to be instructed to spend the same amount of time interfacing with the community organization as they do with those easier to access.
P039983 | PY 4th RURAL WATER SUPPLY & SANITATION | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2007 | 2012 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/230771468026978574/text/635780PPAR0P0300803101100BOX361536B.txt | http://documents.worldbank.org/curated/en/230771468026978574/pdf/635780PPAR0P0300803101100BOX361536B.pdf | 5. Lessons Sector reform and the related shift in institutional culture require political support and time 5.1 It is important to identify the potential risks up front, and carry out proper stakeholder analysis and to make a realistic projection of the time it takes to change the roles of the Government agencies and to devolve the WSS investment and O&M responsibilities to the local government or the community level. 5.2 Both Ecuador and Paraguay experienced delays in project effectiveness and implementation due to political instability and social unrest. They also faced difficulties in reforming the public sector agencies to be credible partners in facilitating the investments in the RWSS sector. 5.3 In the case of Paraguay the central agency, SENASA had already been in operation for 25 years at the time of project approval since its establishment in 1972. Prior to RWSS IV, the Bank had supported SENASA through three previous projects where practical rules for organizing and building the capacities of the WBAs to operate and maintain their RWSS systems were tested and mainstreamed. While the three preceding projects together created more than 400 WBAs providing services to more than 400,000 beneficiaries, even with this track record and three and a half years of project extension, RWSS IV struggled to reach its target number of beneficiaries, primarily due to political instability. RWSS IV was successful in enabling SENASA to fully transform its role from being an implementer to becoming a promoter of RWSS investments through contracting out its core implementation and technical assistance functions to the private sector, non-governmental organizations, and association of WBAs. Thirty years of continuous Bank support for phased reforms may be a factor in explaining these good results in Paraguay. 5.4 In contrast, Ecuador attempted to achieve the difficult reform objective of shifting investment responsibility from the central government level to the municipal government level during the five-year first phase of the APL. The reforms in Ecuador were particularly difficult because the institutional culture of the Ecuadorian Institute of Sanitary Works or Instituto Ecuatoriano de Obras Sanitarias in Spanish , a central government agency that controlled the water sector for almost 30 years, was still dominant at the time of the project, although IEOSâ€Ÿ responsibilities had been transferred to the Ministry of Urban Development and Housing (Ministerio de Desarrollo Urbano y Vivienda, MIDUVI)/ Subsecretariat of Environmental Sanitation (Sub-secretaria de Saneamiento Ambiental, SSA). The new organization under MIDUVI/SSA was established only eight years before the project was approved, and the WBA model under the jurisdiction of municipal governments was introduced by PRAGUAS for the first time, during the first phase of its APL. While Paraguay created 48 WBAs in its first project implemented during 1978-83, and only achieved the creation of 594 WBAs in its fourth project, Ecuador aimed to establish 588 WBAs already in its first phase at the same time as building the capacity of the municipalities to implement the investments. Formalization of consistent policies is critical for reform 5.5 The comparison of the WSS sectorâ€Ÿs institutional framework in Ecuador and Paraguay reveals the importance of formalizing sector policies through legal decrees and formal approvals by the Congress to ensure that the financial and investment policies are enforced. While they may not be sufficient, formalization of the policies and sector institutional responsibilities seem to be necessary for the implementation of reforms especially as the countries face political changes. 5.6 In Paraguay, rules for engaging various stakeholders were embedded in laws and decrees. This facilitated the implementation of coherent and consistent financial and investment policies across the sector regardless of who is funding the investments. In Ecuador, on the other hand, the main elements of the institutional and financial policies were not formalized prior to project initiation. Instead, arrangements were agreed on an investment by investment basis. While PRAGUAS would require community contribution to investment financing, other projects led by the government may provide new rural WSS systems for free. Lack of formal sector policies has caused the ad hoc approaches to community participation in WSS investments and undermined the importance of community ownership through beneficiary contributions. This has hampered the sustainability of WSS sector investments in Ecuador. WBA models show good financial sustainability 5.7 While the physical sustainability does not only depend on the level of O&M cost recovery as there are other influencing factors such as the capacity and incentives of the service providers to carry out proper maintenance, long-term financial sustainability depends on whether the institutional arrangements for implementing cost recovery policies are sound and responsive to local conditions. This assessment of the two RWSS projects have enabled a comparison of; (i) independent regulation; (ii) regulation by contract, and (iii) social accountability as the means of enforcing the cost recovery policies in rural areas and small towns. Â· Independent Regulation\. In the case of Paraguay, there is a Regulator whose mandate is to ensure that tariffs are set according to the cost recovery rules and in accordance with the affordability to the consumers. While there is a remaining challenge for ERSSAN to regulate the increasing number of WBAs, results so far show that the tariff revenues cover the O&M costs and often even part of the capital costs in Paraguay. Â· Regulation by contract\. In the case of Ecuadorâ€Ÿs municipal company models, in which the private sector operators (PSOs) are paid for their services out of tariff revenues cost recovery is self-enforced provided tariffs are set according to the cost recovery rules. This is because the contractual obligations with the PSOs include clauses related to tariff adjustments to compensate for cost increases. Â· Social accountability\. In the rural areas where WBAs are accountable to their communities, they wonâ€Ÿt be able to operate and maintain their water supply schemes if they do not collect sufficient tariff revenues. Without other sources of funds to pay for operations and maintenance, the service would deteriorate. Knowing that cost recovery can help avoid service interruption, local rural communities in both countries seem to be disposed toward paying the necessary tariffs. 5.8 In contrast to the above three regulation models, the small towns of Ecuador have a municipal regulatory arrangement. Water utilities in these small towns are experiencing difficulties achieving their cost recovery as the tariffs are typically set below the O&M costs. The municipalitiesâ€Ÿ Boards of Directors include local politicians who see water supply as a public service that ought to be free. They believe that general municipal revenues will be used to cover any deficits resulting from low tariff revenues. As a result, the conventional WBA models in both countries and the PSO models in Paraguay show stronger financial sustainability compared to the municipal models implemented in Ecuador where tariffs are approve by municipal authorities. Sanitation requires more attention 5.9 Both projects included components to increase coverage of improved sanitation, but the real outcomes achieved through the project activities have been generally poor or difficult to assess due to lack of available data on outcomes. In the case of Ecuador, 14,000 people had received sanitation facilities only (mostly flush toilets, hand washer sink and shower facilities), and 129,000 people had received both water connections and sanitation facilities under PRAGUAS, but no evidence of the usage of these facilities or the outcomes in the form of health or environmental impacts were available. In the case of Paraguay, only three out of the planned ten sewerage system pilots were constructed under RWSS IV because there was lack of demand from the beneficiaries who already have other means of sanitation, and lack of experience in promoting and financing sewerage projects in the country. 5.10 Because of the environmental and health externalities of the current low levels of sanitation coverage in both countries, it is important for the Government and the Bank teams to pay more attention to and effectively track the progress in the sanitation sub-sector both during project preparation and implementation. Post construction technical support and capacity building enhance the sustainability of community participatory water supply services 5.11 The importance of demand-responsive, community participatory approach has been identified to ensure successful implementation of the water supply and sanitation investments in rural areas and small towns. For the water systems to be sustainable, there also needs to be an institutionalized arrangement for technical assistance and post-construction support for continuous capacity building of WBAs. In the case of Paraguay, initially SENASA and later the Association of WBAs have provided such support in the form of training and seminars. As a result, even if there are no subsidies allocated for the purpose of O&M, most of the rural WSS systems managed by the WBAs in Paraguay are reported to be functioning three years after completion. In contrast, the indigenous communities systems in Paraguay and WBAs in Ecuador that do not have such institutionalized systems for support, are experiencing sustainability issues as the systems built cannot be easily repaired or replaced by the WBAs and the communities by themselves.
P039994 | Programmatic Financial Sector Adjustment Loan I | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2005 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/426091474851099897/text/000020051-20140618062331.txt | http://documents.worldbank.org/curated/en/426091474851099897/pdf/000020051-20140618062331.pdf | Design of projects particularly those supporting major structural and legal changes should strike a balance between what is needed to be done and what can be delivered given the capacity of the country. In assessing capacity and in addition to institutional capacity, the country's political economy should be given more weight.For operations requiring major new legislation and where political support is weak, it would be advisable to design and launch the operation after the required legislation has been approved. Financial sector reform programs aimed at reducing systemic vulnerability need to be inclusive of all important sectors. In this case, lack of fuller attention to the cooperative sector resulted in enhanced vulnerability of the financial sector to possible shocks. When designing reform programs, the downstream implications of reform should be recognized and an appropriate strategy should be developed to deal with them. In this case, given the track record of banks and finance companies in Paraguay, it should have been recognized that new prudential norms would have major implications in terms of the quality of portfolio, provisioning requirements and capital adequacy ratios, and most likely, there would be resistance from banks and finance companies. A well-conceived strategy to handle such an eventuality could have ensured a smoother implementation of the new prudential norms.
P040019 | Public Capacity Building Project | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2003 | 2004 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/451191474482788300/text/000020051-20140612083656.txt | http://documents.worldbank.org/curated/en/451191474482788300/pdf/000020051-20140612083656.pdf | In countries with a recent democratization process and little experience in adjustment, a strong and frank dialogue should concentrate on building a consensus on reorganizing/streamlining deficient key institutions prior to strengthening them by training, TA and equipment; this is especially the case for central ministries.Politically sensitive reforms should not be part of a project unless there is a full commitment by the Government and all stakeholders.
P040019 | Public Capacity Building Project | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2003 | 2006 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/556251468299697257/text/362870MG.txt | http://documents.worldbank.org/curated/en/556251468299697257/pdf/362870MG.pdf | 7. Lessons 7.1 The following lessons emerge from the assessment. 0 The recordo ffragile political stability inMadagascarpleads for designing policy development operations ina flexible mannerbasedeither on amenu-based approach to tranche release, or preferably, or on a programmatic series o f one-tranche operations withprior actions. 0 GivenMadagascar's relatively low absorptive capacity, TA operations for supporting reforms should be well focused andhave limitedobjectives initially aimed at implementationbottlenecks. 0 New institutions inMadagascar need continued assistancefrom the donor community. Establishingnew institutions does not ensure their effective operations. Continued support i s required, for example, to strengthenthe different regulatory authorities created inthe public service sectors and competition ingeneral, as well as the business fi-amework. Similarly, continuedassistancei s needed to strengthen the judiciary, which i s a long term undertaking. 0 Consideration should be given to revive the Private Sector Support Fund, which provedsuccessful, or to set up a similar schemeto promotePSD. 0 The tax effort inMadagascar i s particularly low. Muchgreater attention than in the past should be givenby the authorities andbythe Bankto revenue mobilization andreallocationo fpublic resources for povertyreduction, without which recent improvements insocial indicatorswill not be sustained.
P040028 | RAILWAYS RESTRUCTURG | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/193611474566280313/text/000020051-20140612065433.txt | http://documents.worldbank.org/curated/en/193611474566280313/pdf/000020051-20140612065433.pdf | (i) It is important to establish a regulatory framework prior to the initiation of the privatization program so that clear rules are established for efficient and equitable operation by the private sector, the regulatory agency and the government.(ii) There is a need for public-private partnership especially in corridors where investment needs are beyond the financial capacity of the concessionaires. (iii) To minimize social cost of staff retrenchment, there should be a clear focus on the training and outplacement assistance of the ex-employees and the training courses should be delivered in a timely manner.
P040033 | MG STATE PRIV. | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2000 | 2000 | ICRR | Less than 10 million | [5 empty] | http://documents.worldbank.org/curated/en/602071474503393283/text/000020051-20140526231315.txt | http://documents.worldbank.org/curated/en/602071474503393283/pdf/000020051-20140526231315.pdf | Never lend to an agent to carry out reforms that the agent does not want to do
P040061 | ID - BENGKULU REGIONAL DEVELOPMENT | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/448311474650263354/text/000020051-20140615104829.txt | http://documents.worldbank.org/curated/en/448311474650263354/pdf/000020051-20140615104829.pdf | 1. Community managed revolving funds can be effective vehicles for alleviating poverty and increasing rural productivity and growth. Each village's revolving fund provided access by individual families to microfinance and the means to purchase agricultural inputs or investments. Village management allowed for flexibility in how the fund was utilized, and peer pressure encouraged generally good loan recoveries. Family incomes increased and the proportion of poor families decreased significantly. 2. Major change in design and implementation modalities, if corrective of critical design flaws, can help turn a weak project into a successful performer. The Bank team and the Government learned quickly from the project's first several years and the problems with the initial project design. The project was reformulated - in effect to become a new project - and became successful. 3. A strategy should be devised for a community managed program to enable, subsequent to project closure, continued technical support to the community organizations, especially the ones formed in the last years of the project. This was only considered towards the end of the project, which was risky given the need for continuation of some degree of technical support to the communities. It is likely that not all projects would find solutions with such last-minute attempts to provide for support after the project period. (Encouragingly, the province and district governments now appear on the way to finding solutions; they have budgeted some funds themselves, and FAO may provide funding for technical assistance.)
P040085 | Participatory Rural Investment Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/133181475068569984/text/000020051-20140617133830.txt | http://documents.worldbank.org/curated/en/133181475068569984/pdf/000020051-20140617133830.pdf | The project illustrates several familiar findings from projects implemented by multiple local governments and communities: that demand driven, participatory and community managed approaches can be successful relative to top-down planning and implementation; that training and capacity building for local governments and communities is a major need (in this project, one-third of project costs), and that a systematic M&E system measuring outcomes as well as inputs is needed. Specifically, the project experience yields two major lessons: 1. A strong financial management system, including internal and external fiduciary oversight, is a particularly critical need for a decentralized community development program: Such a system was not developed during project preparation, and the initial implementing agency had a poor fiduciary management record. Inadequate financial management and controls provided a fertile medium for fiduciary irregularities until financial management was revamped. Development at the outset of a strong financial management and oversight system should be a central part of project preparation. 2. An operation and maintenance strategy, with accompanying detailed implementation features, needs to be a formal part of a local government and community implemented investment program: There were no formal arrangements for O&M by municipalities of larger infrastructure such as roads. The ICR comments on the need for a special account for O&M in municipal budgets. Additionally, a specific O&M plan for each municipality would have been helpful. At the level of communities, preparing a simple O&M plan with expected activities, costs and revenue sources included, should be part of sub-project preparation and be openly discussed and agreed to by the community.
P040086 | Indigenous and Afro-Ecuadorian Peoples Development Project | Latin America and Caribbean | Ecuador | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2003 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/542771474595593116/text/000020051-20140607174553.txt | http://documents.worldbank.org/curated/en/542771474595593116/pdf/000020051-20140607174553.pdf | A project design that emphasizes decentralized implementation is crucial for successfully dealing with ethnic and cultural diversity of beneficiaries. In such instances, design cannot rely on "one size fits all" methodologies, but procedures should be tailored to different cultures, types of organizations, and settings. An ethnic vision of development, that builds on the positive qualities of indigenous cultures (including a sense of ethnic identity) to mobilize labor and capital, can be an effective vehicle for promoting local employment and growth. Participation and social capital do not guarantee the absence of discrimination; for example, when administering scholarship programs, care must be taken to design checks and balances in the selection process to reduce favoritism and co-opting by elites; also, the social mechanisms of reciprocity do not extend easily into the management of enterprises.
P040102 | REGULATORY REFORM TECHNICAL ASSISTANCE PROJECT | Latin America and Caribbean | Colombia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2005 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/441471474565944334/text/000020051-20140613043713.txt | http://documents.worldbank.org/curated/en/441471474565944334/pdf/000020051-20140613043713.pdf | Â· Dissemination of best practice can be criticalâ€”Through seminars and workshops, executing agencies played a key role disseminating best practices and other experiences in promoting and regulating private participation. As a result, there is widespread knowledge among key participants (e.g., central government, sector agencies, municipal agencies, investment banking and engineering design firms) of the key aspects and pitfalls of the private participation process.Â· Agency participation in technical discussions can be highly beneficialâ€”A technical committee was established for each study performed under the project through which the beneficiary agency and the Government monitored the progress of consultants developing the studies and discussing key policy issues. The ongoing interaction with these committees was extremely valuable for the beneficiary agencies.Â· A sound strategy to manage contingent liabilities can be key to stimulating private participationâ€”The project supported development of a methodology to quantify and confront contingent liabilities. This established risk mitigating measures in advance and significantly improved Government capacity to manage private participation.
P040106 | Ecuador International Trade and Integration Project | Latin America and Caribbean | Ecuador | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/954471474562326208/text/000020051-20140612095247.txt | http://documents.worldbank.org/curated/en/954471474562326208/pdf/000020051-20140612095247.pdf | A participatory approach can be very beneficial--The project design benefitted from substantial participation by private sector stakeholders of varying sizes and from various regions.Changes in the legislative and regulatory framework for international trade are necessary but not sufficient--While legislative and regulatory progress under the project was helpful, without further investment in institutional strengthening and enforcement of regulations, the resultant benefits have been relatively limited.Use of indicators of development impact can be extremely useful--The PAD provided sound monitoring indicators by which to measure project development impact, including the use of a control group of firms that did not benefit from the project. Had these indicators been utilized, the Bank's understanding of the value of the various parts of the project, and their effect on the country's economy, would have been enhanced.
P040107 | Judicial Reform Project | Latin America and Caribbean | Peru | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2002 | 2001 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/751051474905590690/text/000020051-20140529071122.txt | http://documents.worldbank.org/curated/en/751051474905590690/pdf/000020051-20140529071122.pdf | In countries, where there has been 'no strong tradition of independent judiciary' and where a reform project would per force be implemented in a 'potentially unstable' environment,' project scope and objectives must be kept modest and realistic.The project also took a cookie-cutter approach (thrusting solutions that have worked in different socioeconomic, political, and cultural contexts), without meaningful consultation with all affected. Country ownership in general, therefore, seems to have been low, and the stakeholder analysis and participatory processes were inadequate.
P040108 | Postal Services Reform Project | Latin America and Caribbean | Trinidad and Tobago | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/545951475094436376/text/000020051-20140618055023.txt | http://documents.worldbank.org/curated/en/545951475094436376/pdf/000020051-20140618055023.pdf | Under certain postal reform programs, corporatization with increased autonomy while maintaining government ownership is an option worth considering in lieu of full privatization, although the latter could well be achieved if the former is successful. Postal reform and transformation is a long-term process of which regulatory and supervisory capacity, market-based service standards, and broad-based commitment from stakeholders are key and pre-eminent requirements.
P040109 | CO PUBLIC FINANC. MANAGEMENT PROJECT II | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2001 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/666741475071132888/text/000020051-20140624165401.txt | http://documents.worldbank.org/curated/en/666741475071132888/pdf/000020051-20140624165401.pdf | IEG concurs with the lessons drawn in the ICR, but would extend a bit the discussion of the lessons learned from the delay in the completion of SIIF II. The ICR concludes from the experience (Section 6) "....there was a lack of consultation with final users in the design/programming of SIIF II with negative consequences." This lack of coordination and consultation undoubtedly played a role. It is possible, however, that the Bank - which did not address the issue of technical risks at appraisal of the original project and may not have done so adequately at restructuring when it was decided to develop and implement SIIF II (please see Section 8 of this review on the cutting edge nature of the planned SIIF II) - while admirably addressing institutional issues that have undermined technology-focused operations in the past, may have paid too little attention to technical system issues. The ICR also notes with regard to difficulties associated with the SIIF II. "The new web-based SIIF II was not successively launched as hoped for in January 2009 due largely to the complexity of SIIF II (with 14 macro-processes which will cover 166 entities with about 5000 users of which 2000 could be expected to be on line simultaneously), limited communications between end users and the programming team during development, and a lack of periodic feedback and testing of the new system whose programming had been outsourced to a privatefirm." (ICR, Section 2.2). The ICR well states the lessons with regard to communication, but the SIIF II experience reminds us that purely technical difficulties can also undermine projects based on development and implementation of information systems, and these risks and challenges merit equal consideration in project design.
P040110 | FINANCIAL DECENTRALIZATION & ACCOUNTABILITY PROJECT | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1998 | 2003 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/109281474505982390/text/000020051-20140612145028.txt | http://documents.worldbank.org/curated/en/109281474505982390/pdf/000020051-20140612145028.pdf | 1. By themselves, changes in computer systems do not bring institutional change in public administration. For the institutional change to happen, IDA needs to design projects with institutional development support and policy changes and have indicators of institutional change that permit identify the deficiencies in design and to monitor the project and evaluate results.2. Once more, the delays in the project show that timely identification of problems during preparation can prevent delays in implementation and increase the benefits of the project. Therefore, IDA should devote more resources to identify and prepare a project properly rather than to re-designing it once this has been declared effective.
P040115 | RAILWAYS REHAB | Western and Central Africa | Cote d'Ivoire | IDA |  | Infrastructure | Transport | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/933591474486512319/text/000020051-20140607142736.txt | http://documents.worldbank.org/curated/en/933591474486512319/pdf/000020051-20140607142736.pdf | Two of the lessons mentioned in the ICR are of significant, broad interest in the context of privatization:The problems between SIPF and SITARAIL suggests that creation of a landlord company with a role in financial intermediation, procurement and monitoring of the concession agreement, may not be an efficient arrangement, both in terms of cost to the government and operations by the concessionaire. A timely government contribution (donor-funded or otherwise) to finance large and costly infrastructure is essential to support the launching of a concession such as for railway services, which are essential for the economy, but are capital intensive and not highly profitable.
P040115 | RAILWAYS REHAB | Western and Central Africa | Cote d'Ivoire | IDA |  | Infrastructure | Transport | IDA | IPF | 1996 | 2001 | 2003 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/682021468770637285/text/multi0page.txt | http://documents.worldbank.org/curated/en/682021468770637285/pdf/multi0page.pdf | 7. Lessons 7.1 Design of Railway Concessions. The SITARAIL concession had two interrelated aspects that generated significant transaction costs for the operator without providing any significant benefit for the govemment as conceding power\. (i) the creation of an asset landlord company and (ii) the design of the concession as an affermage(leasing) rather than outright sale of equipment. While govemments may want to retain ownership of strategic assets, which could include the railways' infrastructure, retaining ownership of equipment in a 15-year concession (now extended to 30 years), makes no sense since by the end of the concession practically all the equipment will be obsolete. 7.2 Public and Private Benefits of Performance Monitoring. Under the project, a well-designed system of performance reporting, with detailed monthly reports, was established. Such reports allow government officials and financiers to follow the performance of the concessioned operation. The operator has found that such reporting is useful for the management of the company, and has retained the same format and frequency of performance monitoring report after closure of the project. 7.3 Managing the Redundancy Process. The SITARAIL concession offers an excellent lesson about the way labor redundancy can be addressed to mitigate the negative effects. Termination grants (supported by cofinanciers), early retirement, outsourcing works to individuals made redundant, and close and open communications between management and the labor union were key ingredients to successfully tackling this delicate issue. 7.4 Renegotiation of Concessions. In line with what is becoming the norm in infrastructure concessions, the SITARAIL concession was renegotiated. Renegotiations are a way to avoid putting the concession out again for bid at the end of the original concession term. Yet, renegotiations undermine transparency in competitive bidding. As a minimum, renegotiations should be deferred as much as possible. SITARAIL's renegotiations happened about seven years after the initial award of the concessions. This is better than most infrastructure concessions. Renegotiations may be required when conditions (for example, relevant legislation) change and substantively alter the framework of the concession. Concession agreements should define the conditions under which renegotiations are to take place. Experience shows concessionaires sometimes submit too good a bid for the government, in 9 Bank mission back-to-office report, May I1, 1995. the expectation that the terms of the concession will soon be renegotiated. Yet, bids are busmiess decisions that involve risk analysis and risk taking. Post-bid negotiations are exhaustive (nine months for the SITARAIL concession), and are the right place for the parties to ensure that the proposed concession framework is tenable, and to establish the basis and trigger for eventual renegotiations. Unforeseen events such as armed conflict should be covered underforce majeure clauses. 7.5 Role of the Bank in Railway Concessions. The fact that only two bids were received, only one of which was valid, points to the difficulties in finding private investors interested in operating railways in Sub-Saharan Afnca. In this situation, the Bank appears to have a significant role to play by contnbuting as a financier, with its knowledge of world-wide experience with railway concessions, and as an honest broker in the design and operations of railway concessions. The Bank's role appears to be especially important in regions, like Sub-Saharan Africa, where attracting pnvate investors to the infrastructure sectors is especially difficult. 7.6 Suspensions of loan disbursements andprivatized operations. The Bank suspended for a time disbursements in all its operations in Cote d'Ivoire. The privatized company was not reimbursed for investments made during that period because the project closed before the suspension was lifted. This situation affected the finances of the private operator, although the target of the suspension should have been solely the borrower. The Bank should try to find ways to prevent the measures it may take based on country conditions from harming private operators engaged under a Banlcsupported operation.
P040123 | DDSR | Latin America and Caribbean | Peru | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1997 | 1997 | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/969001474512365639/text/000020051-20140519065449.txt | http://documents.worldbank.org/curated/en/969001474512365639/pdf/000020051-20140519065449.pdf | DDSR operations can provide valuable assistance in reducing future debt obligations, but the quality of the country's reform program and the government's commitment to sustained implementation are critical.
P040125 | PE-FONCODES II | Latin America and Caribbean | Peru | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2000 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/404941474577355775/text/000020051-20140602102554.txt | http://documents.worldbank.org/curated/en/404941474577355775/pdf/000020051-20140602102554.pdf | (a) The experience of this project has shown that demand-driven social investment funds can achieve their objective effectively. However, weaker communities may need promotional help in preparing project proposals.(b) Delegation of decision-making activities to regional offices is key to making project processing more efficient.(c) Further improvements are needed to ensure sustainability, especially more training in operations and maintenance, inclusion of local governments (for the maintenance of larger projects, and provision of funds) and assessments of the capacity of the community to pay fees.
P040139 | INVESTMENT RECOVERY | Europe and Central Asia | Croatia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2003 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/471151474571784194/text/000020051-20140612064651.txt | http://documents.worldbank.org/curated/en/471151474571784194/pdf/000020051-20140612064651.pdf | 1. Care should be taken during project implementation to follow through on performance indicators identified in the PAD. In the absence this aspect of supervision, a project's capacity to guide meaningful follow-up is substantially compromised. 2. Line of Credit projects should be used sparingly, in line with the Levy Report recommendations, restricted to situations where value added can be clearly demonstrated. They should be kept as simple as possible and disbursement mechanisms should be carefully and fully discussed with the clients, in order to avoid problems noted by some of the PCBs in this project. 3. Making clients fully responsible for implementing their institutional development reforms may provide for better commitment to following through on these.
P040142 | CAPITAL MARKET DEV. | Europe and Central Asia | Croatia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 1999 | 2000 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/121171475088060114/text/000020051-20140526230443.txt | http://documents.worldbank.org/curated/en/121171475088060114/pdf/000020051-20140526230443.pdf | Transformation of a planned-econmy to a market-based economy is a slow process that requires the enhancement of the legal and institutional environment, particularly the existence of an efficient financial sector and a sound judicial system. Laws that regulate financial/economic activities must be enforced to create an environment conducive to financial institutions development.
P040142 | CAPITAL MARKET DEV. | Europe and Central Asia | Croatia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 1999 | 2005 | PPAR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/977801468770733906/text/28600.txt | http://documents.worldbank.org/curated/en/977801468770733906/pdf/28600.pdf | 3. SummaryFindingsandLessons e Easeo f entry andexit, hardbudgetaryconstraints, andchecks andbalancesto ensurecorporateaccountability arenecessarycomplementsof successful privatization. e Prolongedrehabilitationprocedureswhich leaveexistingbankmanagementin control cansignificantly increasethe final cost o fbank bailouts. e The experiencewiththe EFSALsuggests that, althoughadditional delays maybe incurred andcosts increased, onbalancelong-run developmentbenefits are likely to be enhancedbycancelingprojects withmajor design flaws andaddressingthe reformneedswith a superior instrument. e Development of domestic capital markets makes little sense, untilfimdamental problems ofprivatization andrestructuringhavebeenresolved. e Lack of sound, transparent, andpredictablejudicial enforcement is amajor impedimentto privatization andthe launchofcapitalmarkets. e Mass voucherprivatization seldomworks, ifchecks andbalanceson corporate governanceare not inplace andfunctioning properly.
P040150 | BZ ROADS AND MUNICIPAL DRAINAGE PROJECT | Latin America and Caribbean | Belize | Blend | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2006 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/586961474908908469/text/000020051-20140615094707.txt | http://documents.worldbank.org/curated/en/586961474908908469/pdf/000020051-20140615094707.pdf | Projects in hurricane risk areas should take into account safety features to cope with severe storms at the design stage. Road infrastructure projects such as the one in this project that speed up the potential egress of people from an area in an emergency should be included in the updating of hurricane preparedness plans as soon as possible.Project design could have been improved by reformulating the existing objective for institutional reform to be more specific and establishing target dates for follow-up actions.Implementation experience suggests that small local private firms could have been given a larger percentage of consultancy and contracting assignments than were provided in the procurement plan.The Bank needs to take heed of the experience of the local implementing agency in respect of the speed with which contracts can be executed, unless it has good reason to take a contrary view.
P040150 | BZ ROADS AND MUNICIPAL DRAINAGE PROJECT | Latin America and Caribbean | Belize | Blend | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2006 | 2008 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/131991468207581083/text/442490PPAR0P041x327410B01PUBLIC1pdf.txt | http://documents.worldbank.org/curated/en/131991468207581083/pdf/442490PPAR0P041x327410B01PUBLIC1pdf.pdf | 4. Looking Forward and Lessons 69, The project clearly demonstratesthat municipal drainage cannot bedesignedand implementedinavacuum. Physically, drainage has to beplannedon a watershedbasis taking into account the expectedchangesto that watershed inthe future. Inmunicipal areas this requires that careful attention be given to urbanplanning and development and the changes inthe landuse. Factorsthat change the watershedhydrologic characteristics suchas increasedimpermeable area, causeways, embankments andchanges oflandlevel haveto betaken into account. Thus drainage designis an integral part ofthe threedimensionalurbanplanning process. 70. The designof sustainable drainagerequiresthat there bestrong coordination of the various aspects o furbanand service provision planning andthat one agency hasthe final say on design. The project also clearly demonstratedthat the provision o fpublic goods (such as drainage) isjeopardized by faulty eminent domain institutions. It also clearly demonstratedthat apoor regulatory environment may allow private action by individuals to damage public sector infrastructure. The piecemeal approach o fthe project to municipal drainage also overlooked the fact that implementation o f drainage should start from the lowest elevation and spreadupwards from there. As designed, some o f the drainage infrastructure served to accelerateupstreamrunoffinto lower-lying areas that had inadequate drainage, thus augmenting or shifting the location of flooding rather than minimizing it. 71, Good municipal management inBelize is hinderedby lack o f local autonomy, an inadequate tax base andplanningdecisions made independently andremotely inthe capital. There are significant untapped local resources that could greatly increase revenues, which, ifused wisely, could build local capacity to better manage municipal areas. A first step would be to update the property tax inventory usingobjective and standard criteria andkeepingthese up-to-date. Additional revenue would be collected if good governance was enhanced. Strengthened municipal magistrates courts would aid pursuit o fthe large proportionof people who avoid paying property taxes. This requires action from the center. Increasedrevenues could be sufficient to relieve central agencies of the burdeno fthe physical maintenance of the municipal infrastructure. While this will clearly provide an opportunity to contract specialist maintenance to the private sector, considerable care has to be taken that the contracting arrangements are fair and transparent, containperformance andexit clauses and are free from political interference. These measures, ifimplemented, would broadly accord with the new government's policy to devolve more authority to local government. Facilitating such an effort would fit well withthe Bank's comparative advantage and global experience. The proposal for the institutional reform of the MoWT i s still valid -it only requires political will to implement it.Again, the Bankhad a considerable comparative advantage inthis area should it wish to become re-engaged. 72. Experience withthis project confims five IEGlessons\. 0 Inadequate attentionto local institutions and their governance arrangements may jeopardize achievement o f urbandevelopment objectives. While it i s temptingto think ofinfrastructure projects asbeingfocusedonengineering, thereality inBelize is that little o f the infrastructure will be able to h c t i o n because sound institutions and good governance are weak or absent. 0 Technical Assistance inthe form of strategies andplans for infrastructure investment may be ineffectual inthe absence o f a defined medium-term fiscal framework within which to situate them, and government ownership. As this framework was missing in Belize the technical assistance was effectively wasted. 0 Simple engineering solutions can deliver substantial development impacts even when there are adverse institutional andpolitical circumstances. Inthis project the Burrell Boom Bridge greatly enhancedthe capacity o f Belize's road infrastructure, particularly for disaster management following hurricanes. 0 Drainage androads are component parts o f town planningand cannot be planned independentlyor randomly. Although strong and well-coordinated planning institutions are pre-requisites for planning infrastructure investment for urban areas these were not available inBelize. o Drainage systems cannot be designedpiecemeal. They have to bedesignedwithinthe context o f a watershed, taking into account the future plans for that watershed in terms of landuse, and be structured insuch a way that they incrementally improve the drainage. The lack o f comprehensive planning andpoor sequencing o f municipal drainage works inBelize demonstrated that an ad hoc approach will not work.
P040174 | VE CARACAS SLUM UPGRADE | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/496451474632190378/text/000020051-20140617140215.txt | http://documents.worldbank.org/curated/en/496451474632190378/pdf/000020051-20140617140215.pdf | Strong community participation is essential to the success of urban upgrading operations, but it does require intensive management by executing agencies, and there are some areas in which it may be less effective, notably in operations and maintenance of urban infrastructure.Through leading mobilization and community education activities, women can serve as catalytic agents in community infrastructure projects.Patience and flexibility in dealing with the client during periods of severe political and institutional instability can help create opportunities for success even in unexpectedly volatile conditions.Irrespective of the fiscal and political constraints they face, municipalities should always be active stakeholders in urban development and projects in this area should always try to work with them particularly through the provision of technical assistance to them. With a well designed M&E system in hand, it is crucial to actually implement and use it. Simply recognizing a need for baseline data is not enough by itself, for instance. The data has to be collected too.
P040177 | Financial Sector Technical Assistance Credit | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2003 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/117901475115811609/text/000180307-20141203053635.txt | http://documents.worldbank.org/curated/en/117901475115811609/pdf/000180307-20141203053635.pdf | The ICR drew reasonable lessons for designing technical assistance projects in the financial sector. It highlighted the needs for an in-depth assessment of existing business processes and technologies, simplified and carefully sequenced implementation arrangements, as well as ensuring adequate qualifications of management and staff of the project coordination unit. The Borrower, however, has noted that there are limits to simplification. Some reforms require complex inter-agency coordination and cannot be done piecemeal. An additional lesson that might be drawn is that collaboration with key stakeholders needs to start early in the project cycle, including the consultation and design stage, to make sure that the issues are understood, the outcomes are valued and the solutions are known.
P040179 | PA HEALTH PILOT | Latin America and Caribbean | Panama | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/939181474908054730/text/000020051-20140613061845.txt | http://documents.worldbank.org/curated/en/939181474908054730/pdf/000020051-20140613061845.pdf | The importance of M&E should be stressed in both design and implementation. The lack of proper M&E of SMHR means that it is very difficult to draw any lessons from its experience, not to make a case for the reforms carried out on a pilot basis in that region.Pinning reforms down in legislation helps preserve them in the fact of opposition. The new legislation which under-pinned key reforms on which the project was built helped ensure changes took place in the face of opposition. Without these changes prior to effectiveness it is far more likely that the project would have stalled. Performance management can enhance effectiveness and efficiency. The change in incentives in HISMA appear to have brought about improvements in a range of indicators. (Weaker incentives in the SMHR reforms may explain the differential in performance, but this cannot be known).Persistence can be required for a learning experience to take place. The first months and even years of project implementation were not easy at all for all those involved with this project. The Bank could have opted to cancel the loan. Rather, it insisted in helping to make it feasible. Today, this question can be asked: what would have happened in absence of this Project? Most probably, Panamaâ€™s health sector would have continued its inertia, with limited learning experiences to feed a needed reform process. Thanks to the persistence from all those involved, today the scenery is quite different, as the countryâ€™s health sector has valuable experiences and instruments with which to face its future.Ensure buy in from all major institutional stakeholders. Attempts to get MOH and CSS to cooperate failed as MOH was assigned a lead role with inadequate efforts to get CSS into the project.Frequent changes in personnel in both Bank and borrower undermine institutional development.
P040185 | SHANDONG ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/880501474637221792/text/000020051-20140615110223.txt | http://documents.worldbank.org/curated/en/880501474637221792/pdf/000020051-20140615110223.pdf | 1. China's rapid progress in the last decade in recognizing the size and health impact of its many environmental problems and in acting vigorously to address them, provides a useful model for other rapidly developing economies.2. As a result of a firm approach by the Bank, involuntary resettlement issues in this case were handled in full compliance with Bank policies.3. Setting up new institutions, such as utility companies, and bringing them to full self-sufficiency typically takes longer than a single project.4. The Borrower reports that the project experience was valuable in accessing international experience in project management and institutional development.
P040195 | Quality of Undergraduate Education | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/982831474561928006/text/000020051-20140613041134.txt | http://documents.worldbank.org/curated/en/982831474561928006/pdf/000020051-20140613041134.pdf | Resource allocation through competitive grant applications is effective in distributing funds equitably and through transparent criteria. This mechanism can increase accountability in the use of public funds as well as provide flexibility to the government to adjust priorities as needed. To protect the institutions that serve poorer or more remote areas, a â€œbottom-upâ€ planning approach with the direct involvement of end users might improve the effectiveness of the award mechanisms.- It is possible to continue to carry out projects effectively within a tight fiscal environment if efforts are made to plan effectively, seek low prices, and involve beneficiaries directly in implementation.
P040196 | Sumatra Basic Education Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/595971474629938756/text/000020051-20140617130847.txt | http://documents.worldbank.org/curated/en/595971474629938756/pdf/000020051-20140617130847.pdf | Large-scale decentralization should proceed cautiously. Incentives should be carefully thought through, decided upon, resourced and made consistently available, before community participation and the establishment of decentralized education programs begin. Otherwise, staff, management, and planning mechanisms may not be ready to accommodate the decentralization needs.- Communities in many countries are able to assume some responsibility and to construct and equip schools through the help of block grants. However, training and follow-up are needed for this level of involvement to occur.- It is possible to mitigate the effects of an economic crisis through targeted interventions at vulnerable students attending critical stages of their education.
P040197 | NI FISE III | Latin America and Caribbean | Nicaragua | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2005 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/305341474569250574/text/000020051-20140612134454.txt | http://documents.worldbank.org/curated/en/305341474569250574/pdf/000020051-20140612134454.pdf | 1. The creation of a Preventive Maintenance Fund may only transfer the sustainability problem elsewhere rather than solve it--the sources of financing for such a fund need careful attention.2. Allocating resources in strict adherence to a pre-agreed Poverty Map can help to ward-off political pressures and promote transparency. However, an accurate Poverty Map is critical.3. Projects aimed at capacity enhancement and community participation should explicitly and systematically monitor and evaluate the extent to which these are achieved using both quantitative and qualitative measures.
P040198 | GT FIS II | Latin America and Caribbean | Guatemala | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/741101475101097038/text/000020051-20140612140714.txt | http://documents.worldbank.org/curated/en/741101475101097038/pdf/000020051-20140612140714.pdf | Drawing on lessons identified in the ICR: Subproject Sustainability. Initiatives to enhance subproject sustainability must be adequately funded in proportion to the amount for subprojects and fully incorporated into the subproject cycle. Subprojects should routinely include an operations and maintenance plan for each subproject with an assessment of the operating costs and agreement among all parties on how those costs will be covered and/or shared by communities, municipalities, and/or line ministries. Training for communities in operations andmaintenance must be an integral part of all subprojects.Integration of Community Training. A strategy to integrate community participation and training into the existing operational structure of a bureaucracy should be carefully planned and phased, with a significant investment in building ownership of the concept and implementation capacity among the organizationâ€™s staff members. The community training activities themselves should have adequate funding to provide training in routine issues as well as new empowerment and community organization issues. Social funds can help encourage community participation by developing community participation procedures for all phases of the subproject cycle. These procedures should also include mechanisms to involve the local municipal and regional authorities.Subproject Monitoring and Completion. Once subprojects become "problem" subprojects and are unfinished for some reason, it becomes even more difficult to actually complete them due to expired guarantees, old material, disenchanted community laborers, and/or high administrative costs for the contractor. Emphasis should be placed on consistent supervision and monitoring of the execution of the works in order to avoid a persistent problem, which is then much more difficult to address.Electoral Distortion/Close Attention to Supervision. It is very difficult for social funds to avoid the influence of politics, particularly at the time of an election. As in this case, the use of transparent targeting criteria for subproject resource allocation is the only way a social fund can withstand the political pressures to lend to particular municipalities and communities. Social funds also run the risk of starting hundreds of subprojects during an election year to show results in communities, but then due to lack of supervision, these subprojects become "problem" subprojects and ultimately have high administrative and transaction costs for the institution..
P040199 | MX Basic Educ Dev APL I | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/234201474575737560/text/000020051-20140607155038.txt | http://documents.worldbank.org/curated/en/234201474575737560/pdf/000020051-20140607155038.pdf | The APLâ€™s flexibility in allowing for the incorporation of lessons learnt in subsequent phases of the program is an ideal instrument for providing assistance to education sector programs that require long term investment. - Provision of resources at the state and regional level fosters innovation in meeting local needs, such as for compensatory programs. National programs can then be informed to address identified needs.- The educational needs of street children, although urgent and acute, still require careful analysis, identification of appropriate agencies and development of a system to implement the proposed interventions to address the range of needs.- Innovations such as schemes involving inter-state competition must take into account political issues, strive to ensure that regulations are not unduly complex, and the human resources to provide technical assistance, assess proposal are readily available.-Publicizing and disseminating project objectives and activities at the state and local levels serve to strengthen ownership and improve the implementation process.
P040409 | Emergency Oil Spill Recovery & Mitigation Project | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1995 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/898791474487376506/text/000020051-20140607172213.txt | http://documents.worldbank.org/curated/en/898791474487376506/pdf/000020051-20140607172213.pdf | If it is ncecessary to work with an implementing agency that is a prospective candidate for restructuring or change in ownership, it may be necessary to consider in advance, the legal documentation needed to maintain continuity in the implementing agency's obligations; Emergency projects should, to the extent feasible, provide for dealing with the historical context of the problem, that goes beyond the urgent action for mitigating immediate major impacts. In this project, the focus was primarily on mitigating the immediate negative impacts of the recent oil spill, but no provision was made for the accumulated effects of a long history of previous oil spills, leaving the local communities with a residue of grievances.In consulting affected stakeholders on social mitigation projects, care should be taken not to increase expectations beyond the realistic physical and financial scope of the project.
P040462 | ESSENTIAL SOCIAL SER | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1995 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/871671474420404940/text/000020051-20140521041857.txt | http://documents.worldbank.org/curated/en/871671474420404940/pdf/000020051-20140521041857.pdf | The key lesson from this project is that the operational elements of a project including procurement and disbursement modalities are just as important as its conceptual design. Unless operational details are worked out upfront, substantial delays can occur in implementing the project and reduce project impact especially under emergency situations in which time is of the essence.
P040497 | FINAN. SEC RESTRUCTU | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1995 | 1997 | 1999 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/554021474555079670/text/000020051-20140519082000.txt | http://documents.worldbank.org/curated/en/554021474555079670/pdf/000020051-20140519082000.pdf | Emergency or relief programs are not good vehicles for pursuing institutional or legislative reforms. This is especially true when, as in this case, the Banks financial contribution is a relatively small part of a large package. Unless there is a single reform package on which all partners have agreed, concerns of major partners will dominate. The pressure for disbursement in emergency situations also weakens the Bank's leverage in enforcing policy conditions. The nine-month period foreseen between effectiveness and disbursement of the final tranche was not a reasonable time span for accomplishment of the project's reform agenda. Country counterparts also tend to pay more attention to short term concerns (in this case keeping the banking system from collapsing).
P040503 | GAZA INDUSTRIAL EST. | Middle East and North Africa | West Bank and Gaza |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/948661475070378915/text/000020051-20140613084216.txt | http://documents.worldbank.org/curated/en/948661475070378915/pdf/000020051-20140613084216.pdf | The following lessons highlighted in the ICR are particularly relevant:When designing development objectives for projects in conflict situations, it is advisable to put more emphasis on institutional aspects than on economic outcomes. In countries of limited capacity, it might be more effective for project implementation to set up a semi-independent regulatory authority, instead of a fully independent one. This way the authority could have the ability and the high-level support needed to develop as planned. The experience with PIEFZA illustrates this point.
P040505 | GZ-WATER & SAN. SERVICES/GAZA | Middle East and North Africa | West Bank and Gaza |  |  | Sustainable Development | Water | SPF | IPF | 1997 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/786311475089038135/text/000020051-20140612082942.txt | http://documents.worldbank.org/curated/en/786311475089038135/pdf/000020051-20140612082942.pdf | Operator contracts for public utilities should give the contractor sufficient responsibility and authority to implement investments and manage operations efficiently, with built-in performance targets and incentives and periodic independent audit to confirm performance and monitor fiduciary aspects.
P040506 | GZ-ELEC.SEC.INV.& MGMT | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Energy & Extractives | SPF | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/421201475068651521/text/000020051-20140618062934.txt | http://documents.worldbank.org/curated/en/421201475068651521/pdf/000020051-20140618062934.pdf | 1. The project reinforces previous experiences regarding the importance of maintaining flexibility in project implementation when working in conflict areas, including the possbility of maintaining the momentum on components which may be relatively unaffected by such events (e.g. training, implementation of IT systems, preparation of legal and regulatory documents) 2. The impact of political factors on the conversion of a state-owned enterprise into a corporate company should not be underestimated. This is particularly true when the revenues of an enterprise have previously formed part of the general revenues of the government. In addition to losing day-to-day management control of the corporate company, the government may lose a significant part of its revenue base.
P040513 | Second Henan Provincial Highway Project | East Asia and Pacific | China | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1996 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/834471475073876146/text/000020051-20140613051857.txt | http://documents.worldbank.org/curated/en/834471475073876146/pdf/000020051-20140613051857.pdf | Well designed covenants on road maintenance can be an effective device to engage the Borrower and maintain a dialogue on the road maintenance issue. Highway maintenance was considered an important sector issue but no specific component was included in the project. Instead a covenant in the Project Agreement called for Annual Highway Maintenance Reports to be submitted to the Bank for joint reviews. This proved to be quite effective and the need to modernize the maintenance systems and tools in the province became apparent. This was addressed under the follow-on project.For institutional strengthening activities to be effective, key ingredients for project's experience appear to be: support from central and provincial level; firm grounding in sectoral strategy; proper and timely selection of local/foreign consultants; and recognizing that process of change takes time and devising short-term and long-term action plans.
P040521 | SECOND VILLAGE INFRASTRUCTURE PROJECT | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2010 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/947921474630173454/text/000020051-20140529162615.txt | http://documents.worldbank.org/curated/en/947921474630173454/pdf/000020051-20140529162615.pdf | The key lessons from this project are:Beneficiaries will take advantage of the opportunities offered by programs if: (a) the programs are advertised and communities are well informed about their eligibility, and (b) they are involved in program design.For programs covering a large proportion of villages and not just poor villages, self-targeting instead of village targeting is preferable as self targeting will benefit the poorer segments within villages.
P040521 | SECOND VILLAGE INFRASTRUCTURE PROJECT | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1997 | 2010 | 2006 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/236891468042265551/text/35585.txt | http://documents.worldbank.org/curated/en/236891468042265551/pdf/35585.pdf | lessonsfor thewide expansionof theapproachthatfollowed.Both projects largelybypassed the district level.With respectto thebroaderpovertyreductionaim,field visits andaproject impactstudysuggestwidebeneficiarysatisfactionwith theinvestments.Howeverthereare concernsaboutmaintenancewhich applyto bothVIP2 andKDP(para2.3below).In addition, (but alesserreasonfor not goingto aHighly Satisfactoryrating)giventhepovertyreduction intentof theproject,theinclusionof anumberof lesspoorvillages,partly for political reasons,undercutthepovertyfocus.Thatsaid,in villageswheretheproj.ectintervened attendanceof thepooratmeetingsappearsto havebeenat leastadequate,but thequalityof inputEromthepoorremainsunclear.However,it would beunreasonableto expectveryrapid . gainsin thevoiceof thepoorgiventhelong-entrenchedsocialenvironment. 22 Theoutcomeof KDP isratedModerately Satisfactorybasedontheassessmentof relevance,efficacy,andefficiencydiscussedbelow.As with VIP2,KDP strengthenedvillage andkecamatangovernments,thoughweaknessesremainin achievingtheaccountability elementof theobjectiveassignificantleakageof resourcesandcorruptionoccurreddespite thecreativeanti-corruptionmeasuresput in placeto preventthem.Whiletheproject objectivesdidnot explicitlyclaimto strengthenthedistrict government,supportfor decentralizationwasimplicit in theproject.TheKDP economicloanscomponent(23percent of total costs)is generallyacknowledgedto havenotbeensuccessfulandit exhibitedmarginal efficiencyasacreditoperationbecauseof weakrepayment.Thisisthedeterminingelementin thejustification for goingto onlyModeratelySatisfactory,nearlyaquarterof theproject fundingresultedin unsatisfactoryperformance.4However,aconcernaboutmaintenanceasan elementin assessingoutcomenotedin thefollowingparagraphalsoappliesto KDP. Further, owingto thesocialpatternsin communities,in bothprojects,despitegoodmeeting attendance,progresstowardgenuine,high-qualityparticipationin decisionmakingbythe poorermembersof thecommunityandwomenwasprobablymodest. 4. IEG rates a project as moderately satisfactory when it is expected to achieve most of its relevant obj ectives but with significant shortcomings as in the case of the economic loan component. 23. Giventheobjectiveof establishingacommunityparticipationprocess,concernsabout communitymaintenancecapacity,andthereforesustainability,areseenasintegralin assessing outcome,in bothprojects.It seemsclearfrom missionobservationthatvillagesdonot have the'capacityto maintaintheescalatingvolumeof infrastructurethattheyareexpectedto maintainevenif, for aperiod,theycanmaintainsomeof it. Thereremain,therefore,questions aboutwheresuchprogramsareheadedin theabsenceof greatercommunityrevenuecapacity, especiallyin poorercommunitiesandwhereasphaltroadshaveincreased,andwhether constructionof furtherinfrastructureis reallyasoundstrategygiventhispersistent maintenanceissue.Thetechnical/economic/socialdilemmaisthat, in theveryhighrainfall of muchof Indonesia,dirt roadsdonot lastwell, asphaltplacedontop of low costdirt*roadsnot designedto takeasphaltlastonly somewhatbetter,andgoodasphaltlastswell givengood drainagebut is generallyoutof reachof mostcommunitiesfor maintenance.Thesolutionof rebuildingroadsthroughoutsidesupport(donoror government)everytenyearsmaystill give an'acceptableERRbut isnot anefficient developmentstrategyandin theendis likely to underminecommunityparticipation.Notethattheissueis not onesimplyrelatedto VIP or KDP-fundedinfrastructureandthequalityof maintenanceof thosequitemodestsizedpieces, theissueisrelatedto all villageinfrastructureandtheplaceof VIP andKDP within that infrastructurechallenge? RELEVANCE 24 Relevanceof bothprojectswassubstantial,butwith somequalification.Theobjectives wererelevantto boththeBankandcountrystrategyatthetimeandremainedsothroughoutthe 199?98economiccrisis.KDP wasparticularlyrelevantgivenitstimingin relationto the economiccrisisandtheconcernwith respectto increasedcorruption.6 s 25 Thisassessmentdidnothavethecapacityto pursueseveralrelevancequestionsrelated to thetwo projects.First,extendingvillage,infrastructurethroughnewinvestmentsmayhave beenlessrelevantfor meetingpovertyobjectivesthanenhancingmaintenanceof existing 5\. A KDP project document noted in 2004 that all the consulting teams were in agreement that the most pressing post-construction issue that needed to be addressed comprehensively by l!%P management was maintenance. In many villages hard won benefits were in real danger of eroding to pre-project conditions, especially for roads. The report also found that very little serious thought had been given to the high repair costs that arise periodically as natural wear-and-tear begins to take its toll. Costs of repairs for roads and water systems were significantly underestimated. For the villages analyzed, it was clear that the O&M burden, especially for roads, was too great for the majority of villages to shoulder. 6. Corruption has a long history in Indonesia. It has plagued governments since early independence (which was declared in 1945 and internationally recognized in 1949), although it arguably reached the greatest heights-in terms of sheer scale, sophistication, and damage-when the new Order began in 1966. In the period of parliamentary liberal democracy (1950-59) and during the Sukamo-dominated Guided Democracy (1959.65), corruption and abuse of power had already commonly taken the form of alliances among political patrons and business clients who were regularly given special privileges in the shape of licenses and other nontransparent business opportunities. This was to be apattern replicated during the New Order. The big difference was that the economic cake was to grow so much larger-as was scale of the resources that could be misappropriated. V.Bhargava and E Bolongaita 2004. Challenging Corruption in Asia The World Bank. infrastructure,at leastin somevillages.7Second,giventhepovertyreductionintentof the projects,theinclusionof anumberof lesspoorvillages,partly for politicalreasons,undercut thepovertyfocus.Thepovertyselectionprofile wouldhavebeendifferenthadvillagesbeen strictly povertyrankednationally.*Third,theIndonesiangovernmentinstitutedamajor decentralizationprogramin 1999.'It isnot clearhow KDP, in bypassingthedistrict level, conformedwith thatprogram.It is alsonotclearhow far thebypassingof government institutionsandthecreationofparallel institutionsto overseetheimplementationof theKDP programaffectedtheoveralldecentralizationprogram.loTheseissuesarewider thanthe experienceof theseindividualprojects,however,andshouldbeexploredfurther.Fourth, agriculturaltechnologyremainsweak,especiallyoutsidetheareasof moreintensive cultivationandhigherrainfall,andseemsto beunder-investedin nationally.Thisraisesthe questionof whetheranequivalent(or greater)investmentin agriculturalresearchand extensionmighthaveequaledor exceededthepovertyreductionimpactof theseprojects. Supportfor agriculturaltechnologyhasgenerallyshownveryhigheconomicreturnsand satisfactorypovertyimpacts,andthereforemighthavebeenacompetitivealternative.The _ missiondid nothavetheresourcesto pursuethisquestionfar enoughin relationto therecent supportfor research(AgriculturalResearchProject'2with total costsof*@2million at completion)andthefurtherassistanceproposed. EFFICACY 26 Efficacy-the extentto whichtheprojectobjectiveswereachievedtakinginto account theirrelativeimportance-is ratedsubstantialfor VIP2 butmodestfor KDP, although baselineindicatorswerelimited. . 7. It could be argued that some of the investment was, in fact, delayed maintenance. 8. The mission visited. several VIP2 and KDP project villages in West Java where the majority of households appeared quite well off relative to those seen, for example, in Kalimantan. 9. Decentralization Law 22 that assigns all government expenditure to the districts (kabupaten) except for fmance, foreign affairs, defense, religion and state administration was passed on May 7, 1999 and Law 25 that provides the details of fiscal decentralization was passed on May 19, 1999. 10. KDP provided for funds to flow directly from a central project account to ajoint village account at a local sub-district bank, processed by the branch office ofthe national Treasury. At no stage do funds pass through a government ministry.. .. ... ...It runs counter to a Bank-wide trend during the 1990's to move away from heavy reliance on project implementation units by putting government in the driver's seat, strengthening government institutions, and insisting that projects and programs be implemented by government agencies. In fact, ,the KDP National Management Consultants office in Jakarta is in reality a PIU, or at best an inhouse NGO. It also runs counter to some decentralization initiatives that originate with federal government offices, and subsequently cascade down through development plans prepared at various levels. Judith Edstrom Indonesia '8sKecamatan Development Project Is It Replicable? Social Development Papers, Paper No. 39, The World Bank, March 2002. 11. Agricultural technology has been neglected both nationally and by donors in recent years and, globally, IEG has concluded that this decline has gone beyond what would be justified by the falling percentage of agriculture in GDP. 27. Theobjectivesagainstwhich VIP2 isratedarethosein thetext of theappraisal.Based onmonitoringandevaluationdata,theobjectiveof building small infrastructure was achievedat alevelof morethandoubletheoriginaltargetwith alittle overaone-year extension.VIP2built infrastructurein 7,044villagesagainsttheplanof 2,600atalocal currencyvalueof nearlythreetimestheplan.HoweverasindicatedearlierunderOutcome, thereareconcernsaboutthecapacityof communitiesto maintaintheinfrastructure. Decentralization atthedistrict levelwasnot reallyhelpedmuchbyVIP2,but,theproject madesignificantprogresswith theobjectiveof decentralizationandcommunityparticipation at kecamatan andvillagelevels,thelowerlayersin thedecentralizationhierarchy.12 Communityparticipationwascertainlyincreasedasis evidentin mostvillagesfrom village meetingrecords.With respectto theobjectiveof reducingpoverty, it is difficult to measure andattributein aggregatesignificantchangesin broaderruralpovertyindicatorsto modest lengthsof villageroadsorbridges,oftenrelevantonlyto oneparticularhamlet.However,the economicanalysisfor VIP2,thesubsequenteconomicanalysisfor KDP for similar infrastructure,andindividualstructuresassessedby missionfield visits,partly through discussionof landvalues,implyhighfinancialandeconomicbenefitsto thosebeneficiaries within theserviceareaof theinfrastructurebuilt by theproject.Themissionobservedthat while communityparticipationhadbeenclearlyenhancedat thecommunitylevel,some uncertaintiesremainedabouttheextentto whichthepoorestandwomenhadtakentheir voice qualitativelybeyondmerelyattendanceatmeetingsandparticipationin labor.13The achievementvariedbyprovince. 28 Theobjectivesusedto evaluateKDP weretakenfrom theLogicalFramework(see para.-1.4).With respectto thefirst of thoseobjectives,KDP doesappearto havestrengthened kecamatan andvillagecommunitiesby supportingthemin themanagementof increasedfunds andgivingthemfull responsibilityfor fundsmanagementandimplementation,including substantialfacilitationsupportandtraining.With respectto thekecamatanlevel,whiledifficult to measure,thedecisionmakingneededto allocatethecompetingprojectresourcesandthe facilitationandtrainingprovidedappearto haveimprovedskillsatthatlevel.Capacityfor book keepingandcommunityfacilitationhasalsobeenenhancedatthekecamatanlevelthrough trainingandpractice,althoughsustainabilityisquestionable.A numberof outputandoutcome changeshaveoccurred,including\.theactivitiesof community-operatedvillageimplementation teams(observedbyjournalistsandreportedinmonitoring),increasingcommunitydemandson government(reportedin studies),-increasedopennessof biddingprocess&atvillagelevel(arule thatwasimposedandfollowed-as reportedinmeetingsminutes),greaterinformation(still 12. .However, in VIP2 the project manager was located at district level and some technical skills were located at that level. 13. In weighting the importance of targeting the poor, M. Ravallion and S. Chen, TVhat Can New Survey Data Tell Us about Recent Changes in Distribution and Poverty? World Bank, 1997, is a relevant study. It uses Indonesia data and finds that even at apoverty line of 20 percent of the population, nearly halfthe population are vulnerable to poverty given the evidence on income variability. Households in Indonesia have about an even chance of facing a poverty episode once in three years. The authors point out that the poor at any given time are only a fraction of those who must worry about, and struggle to avoid, falling into poverty. This would suggest, for Indonesia, that the extent to which poverty targeting is critical to project poverty performance should not be under-estimated. evidentoncommunitynoticeboards),increasedreportingof andactiononcorruption(as reportedin astudyof corruptionandbymonitoringreports),greaterattendanceatmeetings,and increasednumbersof proposalsfromwomen(anoutsideinterventionthatbecamearequirement underKDP). However,considerableevidencefrom Bankinternalfilesandfrom theliterature showsthatleakageof resourcesandcorruptionremainsignificantproblemsin KDP. Thisraises concernsabouthowmuchkecumatunandvillagegovernmentswereactuallyableto become accountable. 29 With respectto creatingeconomicopportunityatthevillagelevel,therearethree findings.First,theimpactof smallinfrastructureonincome,oftenrelevantmainlyto one hamlet,is difficult to measureandattribute,butthegenerallyhighsubprojecteconomicrates of returnin theeconomicanalysiscasestudies(andin morerecentanalysisundertakensince theIEG mission),supportedby missionfield questioningof individualsaboutlandvaluesand missioncalculationsonsite,suggestthateconomicopportunitywasenhancedsignificantlyin thebeneficiaryhamlets.Second,theinfrastructurewascreatedwith very labor-intensive methodsproviding25million workdaysfor.about2.8million peopleatatime of economic crisis.Third, asubstantialnumberof productiveinvestmentswith incomeearningcapacity werebuilt, including5,200irrigationsystems,400marketstructures,and260village electrificationactivities.Fourth,women'slaborwasreleasedthrough2,800cleanwaterunits. Theactualnumberof subprojectswasmorethantwice thenumberplannedat appraisaldueto lowerunit costs,additionalfundingdueto devaluationandthe supplementalcredit,and additionalsupportfrom government.l4Fifih, creditmustbegivenin weighingthescaleof thesebenefitsfor the factthatKDP (buildingontheearlierVIP experience)providedthe knowledgebasefor anumberof whathavebeentermedKDP copy-catprojectsbyboththe governmentandotherdonors.However,aswith VIP2,theseinfrastructureachievementsmust betemperedwith theconcernsaboutcommunitycapacityto maintainitstotal stockof infrastructure.Sincemuchof theinfrastructureis still relativelynewthefull burdenof thisis still ahead. 2.10 With respectto thequestionof whetherthepoorestkecamatanwerereached,thedata for selectedkeiamatanandvillagessuggeststhattherewassomebendingof theselection rulesfor politicalreasons.If anationalrankingregardlessof provincehadbeenused,selection wouldhavebeendifferentlydistributedin provincesandislands. 2.11 In particular,asignificantweaknesswasthat in theloanscomponent,which wasabout 23percentof totalprojectcosts,eficiencywasmodestdueto variablebut oftenweak repayments.Thiscomponentis discussedin moredetailbelow(para.2.16). 14. The Region in its comments notes that the physic&l achievements under the KDP project need to be seen in the context of the prevailing country environment\. a collapsing portfolio, currency crisis and civil war in nearly a third of the participating provinces. VIP2 Infrastructure Achievements in Detail 2.12 Theoriginalprojectobjectivesremained,but thenumberof villages.assistedincreased from theoriginaltargetof 2,600to 7,044.An extendedprogramwasaddedfor JavaandBali covering2,596villages.No initial sub-projectinvestmenttargetsweremadenorwere projectionsattempted;projectdocumentsarguedthatthiswasimpossiblegiventhevillagers' freedomto choose.Villagesbuilt atotal of 15,069kilometersof roads,42.5kilometersof bridges,4.9kilometersof piers,8,722communalwatersupplyunits,4,877sanitationunits, 140irrigationsystems,58markets,and84othertypesof infrastructure.All infrastructurewas of.modestdesigncomplexityto keepcostsdown.In fmancialyear1998/99,dueto the economiccrisis,thegovernmentinitiatedamorewidespreadworksprogramwith its own funds(PDM-DKI). Dueto implementationdifficultiesin Sumatra-thisislandwasleft out of thethird programyearandput in with anOECFprogram,which alsobecameaform of VIP as it shiftedresponsibilityfor managingcontractsfrom theagenciesto thevillages..Thisis one exampleof thedemonstrationimpactof VIP. More recently,theKecamatanDevelopment Projectcoveredsomesubdistrictson Sumatra.. 2.13 Whiletherewerenotargets,atotalofjustunder2millionpersonsworkedontheVIP2 projectfor approximately50million person-daysof work, anaverageof about25daysper personemployed.Approximately40percentof thefundingwentdirectlyto villages,with another40percentfor materialssuchasstone,whichalsorequiredlocallabor,and20percent for imported materialssuchascementandtransport.Annualincomefromtheprojectper workeremployedwasapproximately$25.Thiscompareswith typicalannualincomesperpoor personof $150to $200peryear.Approximately'15percentof thevillagepopulationsworked directlyontheproject\.58percentweremen,15percentwomen,and30percentyouths. 2.14 Nearly6millionpersonsappearto havebenefited,representingabout50percentof the populationof thebeneficiaryvillages.TheVIP2ImpactStudynotedin para2.1covered233 villagesby 1997/98,butthemethodologyfor benefitestimationwasquitesubjectiveasbenefits wereestimatedqualitativelybybeneficiariesasgood, fair, or poor, andcommunity estimatesof financialbenefitsfi-omsubprojectswerewithin ranges(e.g.,Rp 0to Rp 10million; Rp 10millionto Rp 25million, etc.)andit isnotclearhowthesewereestimated.Nonquantifiedbenefitsreportedby villagesincludedeasiervisitsto healthcenters,additionalvillage business,changesin croppingpatterns,improvedsecurity,andeasiertravelto school.Basedon theseestimates,some40percentof villageswereestimatedto haveachievedbenefitsequalto or _ abovecostswithin asingleyear.Otherstookalittle longerto breakeven.A post-construction . reviewstudyin 2000assessedthestandardsof maintenanceandratesof infrastructure deteriorationandconcludedthatby thefinalyearof theproject,about7percentof roadsand bridgesbuilt in Javaweredeficientin qualitydueto lackof maintenanceandabout12percent weredeficientin Sumatra,wheretheprojecthadnotperformedwell for qualityeveninitially. KDP Infrastructure Achievements in Detail 2.15 With respectto theobjectiveof supportingcommunitiesto buildinfrastructure throughlabor-intensivemethods,thetargetswerenot definedbytypeof infrastructuresince choicewasopen.However,thenumberof subprojectagreementswasplannedat 6,000and actualachievementwith thesupportof thesupplementarycreditof $48.2million was 15,000. By projectclosing95percentof theworkshadbeencompleted(comparedto aprojectionof 80percent).Theamountof localfundsdisbursedwasaboutfour timestheprojection alongsidean80percentdevaluationof therupiahandthesupplementarycredit.With respect to quantities,19,000kilometersof roadwerebuilt or upgraded,and3,500bridges,2,800 water supplyunits,5,200irrigationsystems,1,300sanitationunits,and400marketswere built. Thereisno doubtfrom field discussionthatlabor-intensivemethodswereused,albeit probablyatsomecostto qualityandsustainability,particularlyfor roadsbuilt onsoilswhere compactionisimportant.Thepurposeof thelabor-intensivemethodswaspartly to provide incomesupportto thepoorercommunitymembersduringtheextremeeconomicdeclinegiven thatamainobjectivewaseconomicopportunity.Whilethiswasachieved,it wasnot clearto themissionthat theintendedself-targetingworkedeffectively.It wasanticipatedthatwages wouldbesufficientlylow thatonlythepoorestwouldbeinterested;however,owingpartlyto theeconomiccrisis,interestin this work waswidespread,at leastin Java,andin mostcases supplyanddemandhadto bebalancedby someform of rationing,suchassharingout labor betweenhouseholdapplicants.Nevertheless,thisunderscorestheimportanceof incomeasa crisismitigationmeasure. Efficacy of the EconomicLoans(Micro-Credit) Component 2.16 As reportedin theICR, thiscomponentin KDP wasunsatisfactory.Theeconomic loansormicro-creditelementof this componentwasbarelytouchedonin themaintext of the appraisal.It isnot mentionedin thecomponenttableanddiscussionof therepaymentissueis hiddenin the CostBenefitAnalysisAnnex.It is doubtfulwhetheranExecutiveDirector's office would havenoticedthattherewasacreditcomponent.Ashasbeenpointedoutby IEG before,thestructureof appraisaldocuments,whichasksonly for asummarytableof componentsandcostsin themaintext, encouragesinadequatedescriptionof project components.In this appraisal,theheadingin themaintext tableKecamatanDevelopment Grantsis actuallymisleadingsinceaportionwasto beloans.l5Repaymentrateswereabout 20percentin areasthatweremoreremote,poorer,andhadnohistoryof creditbutrangedup to 90percentin areasthat,werelesspoor andhadexperiencewith credit.Thejoint and severalliability for repaymentwithin groupsoftendidnotwork becausetherewasno expectationof continuity,no institutionallinks,andsomeof thegroupswerehastily assembled.Therefore,whenonepersonin thegroupdefaulted,insteadof grouppressureto repay,oftenotherssimplydecidedthat therewasnoreasontheyshouldrepayeither.While individualrecordswerekeptatvillagelevelandgrouprecordskeptat theFinancial ManagementUnit atthekecamatanlevel,theassessmentmissionfoundthat,oncetheproject closed,collectionefforts for thiscomponentwerenot stronglypursued.In onecase,theloan 15. The Region in its comments disputes this fading but on further review IEG fmds the comment still valid. Reference to the PAD shows that under the Project Description Summary the only reference to credit is within a parenthesis which sayswith respect to self-targeting (e.g. wages at local rural minimum . ... and repayment of credits . ..) In the section on Project Alternatives it is not mentioned. In the section on Risk it is only mentioned once in the context, again, of self-selection. Nowhere in the document is there any substantive discussion of the issues, risks and experiences of managing credit. recordswerenot evenpassedonto newstaff. TheImpactStudy16foundthatonly7percentof loanswentto thepooranda similarpercentageto women.However,onesourcesuggeststhat, while womenmaynot havebeenthenominalborrowers,in practicetheir enterprises(e.g., livestock)wereoftentheobjectof theloan.Onereasonfor thelow participationbythepoor, apartfrom their ownperceivedrisksof indebtedness,wasthatmanyless-poorborrowersdid notwish to begroupedwith poorborrowerswho theydidnot know andwhomightbea repaymentrisk.17 Efficacy of Community Processes 2.17 It is difficult to isolatethe changesthathavebeenbroughtaboutin community processesby thetwo projectsunderreviewfrom thosethathavecomeaboutbecauseof the seriesof KDP andotherCDD interventionsin thecountry.'*However,both projects appear to havecontributedto enhancedcommunitydecisi.on-makingprocesses,but dueto traditional dominationby theelite,previoustop-downdevelopmentpractices,andwidespread corruption,muchremainsto bedoneto reachfully equitableparticipation.As notedby EG's recentevaluationof community-basedand-drivenapproaches,Bankstaff increasinglyare awareof theneedfor long-termsupportto buildcommunitycapacity.lgIn thiscontext,the criteriaunderKDP 3for selectingthosecommunitiesthathavereceivedsupportunderKDP 1 and2 is sensibleandwill likely contributesignificantlyto communitycapacityenhancement. Theevidencefor theenhancedprocessescomesfrom anumberof studiesandthemonitoring andfrom anecdotalreporting,andamix of inputandoutput/outcomeevidence.It includes\. l Increasingnumbersof recordedincidentsof spontaneouscommunitydemandsonthe administrationfor performanceandactiononcorruption,someof thisreportedby journalists.Thisincludesthereportingof about1,400casesof financialabuse,most in casesthatit is generallyagreedwouldneverhavebeenreportedin thepast. l Theuniversalcommunitypracticeof requiringthatsupplierspresenttheirquotations to thevillageatpublicmeetings. 0. Thegreaterinformationthroughprojectsignboards,accessbybeneficiariesto village projectrecdrds,andopenaccountabilityreportingmeetings. 16. Kecamatan Development Project Impact Study, 2001. The Demographic Institute, University of Indonesia. 17.The Region does not dispute the rating of this component but asks what would have been the alternative. IEG suggests that the alternative would have been simply shifting the funds into more grants and leaving income to arise from the infrastructure alone or just leaving out that component. The global experience is virtually unanimous on the efficiency and equity problems of pushing credit outside an effective institution in this way and some of that experience has come from countries where part of the justification at the time was some form of urgent need. . 18. The quality of the capacity building effort undertaken in year 1 and 2 for KDP is also a concern since the project was scaled rapidly. Year 1 covered 3,000 villages rather than the 1,250 anticipated at appraisal and year 2 rose to more than 12,000 villages rather than the 3,000-4,000 included in the original timetable. 19. The Effectiveness of World Bank Support for Community-Based and -Driven Development\. An OED Evaluation, 2005. l AttendanceatKDPmeetingsoftenreachedin therangeof 50to 100whenpast meetingsweresaidtohaveincludedonlyahandfulof theelite. l Evidencefrom theseverallocallevelinstitutionstudiesjointly supportedbythe WorldBankandBappenasthatfoundthatoldelitewerebeingreplacedin many villagesbymoreprogressiveindividuals.Thiswasassociatedwith thebroader decentralizationreforms. 0 Theincreasingnumberof women'sproposalsactuallyfunded. l Reportsthatwomen'sincreasedrolein KDP decisionshasspilledoverinto other communityactivities. l Theemergenceof participatorymonitoringbycomntunityteamsandevenvillager auditsin othervillages. 0 Improvedbookkeeping,management,andmonitoringcapacitiesthroughtraining. l Communitiesaccessingpilotprogramsin two provincesfor legalaidservices. l Increasednumbersof meetingsunderKDP recordedathamletlevelwheremuchof thesocialcohesionreallylies,asopposedto atvillagelevel(Box 1). Box 1. Village Community Structure and Functioning To understandthe challengeof enhancingparticipation of the poor in Indonesiait is important to understandsomethingof the community stru&ure,which is complicatedandvariesby area.The role of the Village Head is unclearon many facetsof responsibility.The main community social cohesiveness actually lies below the village level, at the hamlet level. The electedVillage Head is a government servant (screenedby the district government)and largely seen to be so by the community. His accountabilityfor public resourcesis similar to that of highergovernmentlevels,thoughhis (rarelyher) responsibilities are not always clear. The Village Head,while elected,has almost absolutepower at village level, but is subordinateto higher-level officials. Becoming a Village Head costs at least entertainmentmoney, if not a more direct buying of votes.Leadersat hamlet level areseenasmore relevantby their community. Thereareothervillage officersaswell (elected,but from amongcandidates chosenby the Village Head).A LembagaMusyawarahDesa, a committeecomposedpartly of village officers, channel community opinions to the Village Head and review proposals.Another committee, the LembagaKetahananMasyarakatDesa, provides a forum for discussionof developmentpriorities. (Thesearrangementsare changingwith new legislation.)Even Village Heads, who are ex-officio chairmenof the bodies,often find it difficult to distinguishthe roles of thesetwo bodies. There are also traditional leaders,often hereditary. Often, the hamlet headsare traditional leaders but they still have to be approvedby the District Head. There is also village religious leadership,sometimespowerful. Hamlets haveconsiderablede facto autonomyandmay only consult the Village Head when they really needto look outsidehamlet issuesor needresourcesthey cannot raise. SomeVillage Headsarenow openingtheir financial managementto community scrutiny,partly due to VIPKDP rules on disclosureandpublic notices.Under KDP, consultationsby facilitators on proposalswere held at both hamlet andvillage level, usually in the presenceof heads.Under KDP, although in theory an openprocess,in practice Village Headsand facilitators still had considerable influence over which proposalswere put forward to competewith the other proposalsat the intervillage kecamatanmeeting. 2.18 \. In VIP2, dueto thetypeof questionsin thesurvey,theImpactStudyoffersno quantitativeevidenceof communityprocesschangesattributableto theproject.However, missiondiscussionsin thefield andsignedlistsof attendeesandminutesof meetings confirmedthatprocesseshavehadsignificantparticipation,thoughstill somewhatlimited for womenandthepoorerhouseholds.Indeed,oneconcernistheamountof timethatthese processesdemandof beneficiarieswho atthetime of participationhaveno guaranteeof havingtheir investmentchoiceselected. 2.19 In KDP theImpactStudyattemptedto assesschangesin communityprocessesand householdwelfae. Thestudyfoundsurveyresponsesweregenerallypositiveandthatthe relativedifferencesbetweenKDP andnon-KDPprojectswerealsopositive,althoughmodest. Table1summarizessomekeyfindings,buttheseneedto beinterpretedwith cautionsincethe studymethodologywasproblematic.2oFirst,thebaselineandfinal surveywereonlyoneyear apart,givinglittle chanceto discernattributablechanges,particularlyin arapidlyevolving economiccrisisoverlaidondrought.Second,thesurveysattemptedto comptieISDPwith non- 20 .The Region in its comments alsodraws attention to the deficiencies in thb impact study. KDPprojects(innon-KDPareas),,butthereislittle evidenceof whatthesenonXDP projects were,in particular,whethertheywereotherdonorprogramsor governmentprogramsfollowing asimilarapproach(whichmanybythendid),orwhethertheyweretotallydifferenttypesof programs.SomemayevenhavebeenVIP2.In somecasestheywereprivatesectorprograms. ThesecontrolswereselectedbynonKDP communityleadersasbeingthebestprojectsin their.communityfor povertyimpact,makingthecomparatorunrepresentativeandsettingahigh barfor performance.Third,andperhapsmostimportant,with arandomsamplingof households acrossthewholevillage,manyhouseholdsinterviewedwerenot livingin hamletscloseto the particularinfrastructurein questionandthereforehadlittle interestin orknowledgeaboutit and little reasonto havebeeninvolvedin decisionmaking.21 Table 1. Selected KDP Impact Study Findings ... .... . . ____ ._ .__ Question KDP NonKDP % households who know of project 79 68 % households actively involved 45 42 % households involved in planning 13* 7 % households involved in execution
P040528 | Western Java Environmental Management Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2010 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/141161475112213619/text/000020051-20140618075502.txt | http://documents.worldbank.org/curated/en/141161475112213619/pdf/000020051-20140618075502.pdf | Some lessons from this project experience identified in the ICR, include:APL design features, such as provision over a relatively longer period and in-built triggers to assess progress before moving to the next phase, are particularly suited for projects supporting changes in attitudes as well as political processes. The APL allows the flexibility to design each phase in line with the progress made during previous phases. However, great care should be taken when identifying trigger conditions to ensure that they can be realistically achieved within the target period set.The typical TA design (â€œhigh intensity â€“ short durationâ€) may be suitable for the preparation of technical studies, but may be less effective in providing advice and inputs into ongoing and often complex political processes where a contrary â€œlow intensity â€“ long durationâ€ model is likely to be more effective.Projects involving a large number of implementing agencies, should be avoided. WJEMP was implemented through sixteen implementing agencies, each one with a different capacity to effect complex changes in their organizational, legal and political processes needed. Not surprisingly, the results achieved were mixed and some key, but very complex, activities, such as the establishment of regional waste management corporations, progressed only slowly. The project design in this case required the input of several different agencies for progress to be made. The ICR itself does not identify any lessons that specifically derive from this GEF project component. IEG's however, include:While the subsidy approach may provide short term benefits, such as meeting output targets, design elements - such as phasing out or picking winners - need to be built in to the approach to ensure that it leads to the establishment of a sustainable industry.M&E systems need to cover both outputs and outcomes. Focusing on one element, such as an output target, will not provide good M&E data nor indicate when design changes for project steering are needed.
P040544 | Farm Privatization Project | Europe and Central Asia | Azerbaijan | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/333531474482357757/text/000020051-20140612143012.txt | http://documents.worldbank.org/curated/en/333531474482357757/pdf/000020051-20140612143012.pdf | (1) That the process of privatizing the former state and collective farms is perceived to be fair and equitable by the participants is a key to its acceptance and success, as measured both by the speed at which the program was rolled out and by the impacts in terms of improved agricultural productivity and the changing agricultural production mix.(2) For agricultural credit programs to be successful, it is important to address the risks and constraints that are perceived by farmers and that affect their demand for credit.(3) NGOs do not automatically bring a grass-roots perspective to their work. In this case, the performance of the NGO in implementing the community development component was more like that of a for-profit consulting firm.
P040544 | Farm Privatization Project | Europe and Central Asia | Azerbaijan | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2004 | 2009 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/453991468005956033/text/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.txt | http://documents.worldbank.org/curated/en/453991468005956033/pdf/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.pdf | 6. Lessons (a) General Lessons 6.1 Given the large attitudinal shift involved in the agricultural transition, government officials and project staff needed substantial technical assistance and training before operations could be expected to succeed. Governments showed strong commitment to the preparation of the projects under review. Yet once the loans were approved, delays in declaring effectiveness were experienced for several of the loans, while during early implementation even staffs of the project units often did not fully understand how specific project activities linked to objectives. If this was true at the center, it was even truer in the localities where projects were implemented. Consultant services were not always used as effectively as they might have been (this was the case for credit operations in the Armenia ARSP and Georgia ADP). There was an attitudinal lag\. most government officials in the agricultural ministries still exhibited a command and control mentality with respect to agricultural development. 6.2 When the leadership of project implementation units was skilled and motivated and their staffs were well trained, project implementation generally proceeded smoothly once some experience with the Bank's procedures had been acquired. This was especially the case with project units for the Romania ASSP and Georgia ADP, whose performance improved rapidly once professionally adept managers were recruited to replace earlier political appointees. Similarly, the appointment of a technically trained person to manage a purely technical agency such as the Romania's ANCPI for the GCLR Project resulted in a rapid acceleration of project implementation. 6.3 In the complex and rapidly changing ECA environment, sound donor coordination was critical. The two Romania projects rebounded from a very poor start once the Bank and other members of the donor community began working together to help Romania meet the European Union accession requirements. Together they helped Romanians to take advantage of the grants-in-aid made available under the Community's special accession program for agriculture and rural development. 6.4 Where donor coordination was less sharp, progress was slow. Management of the land registration component of the Georgia ADP was, at times, complicated by conflicting donor expectations that proved hard to resolve. In Tajikistan, it took the Bank until 2003 to realize that if donors spoke with one voice to the government on land reform, it might create conditions more favorable for the farms that the project had restructured. (b) Lessons from the Sub-sectors Agricultural and agribusiness services 6.5 Farmers and rural business owners will respond enthusiastically to innovative technologies corresponding to their needs. Experience from the assessed projects showed that agricultural research and extension works best when it is consultative and demanddriven. In Romania, the competitive grant approach proved to be an excellent vehicle both for generating applied research findings and extending these to farmers. But, as Armenia showed, the competitive grant scheme can also lack the strategic focus needed to effect a comprehensive strengthening of agriculture research. To respond to farmers' needs, competitive research grants should be open to all applicants, including non-governmental organizations, universities, and government research institutes. For pure farm extension work, the financial sustainability of advisory services in a setting with many small, semisubsistence farmers can only be achieved if government acknowledges its responsibility to provide these citizens with appropriate and effective advice and information. This will probably entail some measure of subsidy given the low incomes of many of the clients; but that need not preclude use of private contractors to deliver the service. Land administration 6.6 The Bank's international experience with land policy issues has strengthened the design of projects in ECA; but there is no uniquely correct model for land administration or land reform and effectiveness depends on responsiveness to local conditions. Whether grounded in restitution (Romania), or in the granting of more or less equal allotments to agricultural workers and other rural residents (South Caucasus), or being limited to the transfer of usufruct rights only (Tajikistan), each program was designed to accommodate socio-political necessities in the aftermath of de-collectivization. In Tajikistan however the project design was overly ambitious and not tailored enough to the local circumstances. 6.7 It makes sense to adopt a unified approach to land administration. Cadastral and land recording/land registration services are both technology and information intensive. These two services need to be closely linked and preferably digitalized to increase efficiency and enhance access. The unified approach worked well in each of projects reviewed here that had a land administration component (Azerbaijan FPP and ADCP; Georgia ADP, and Tajikistan FPSP). Rural finance 6.8 With appropriate regulation, technical advice and staff training banks that lend to rural areas can operate sustainably. To realize the potential from scaling up commercial bank lending to rural areas, it is essential\. (a) to confirm that supervision and prudential regulation has been developed and can be effectively enforced; (b) to prequalify the banks deemed eligible to participate in tendering for loan proceeds, based on rigorous prudential examination; (c) to ensure rigorous monitoring of the credit program, with the assistance of international expertise if necessary; (d) to ensure that the terms, maturities and grace periods of loans are proportional to the expected returns and the estimated economic life of the investment; and (e) to allow intermediaries to administer credit reflows in accordance with their own terms and conditions. 6.9 The non-bank financial intermediaries have an important role to play in rural areas; but it is important to be realistic about their capabilities. There is a strong demand for locally-based credit facilities (such as credit unions) in rural villages, and for rural financial institutions that take credit. These institutions must be savings-driven and encouraged to diversify their loan portfolio rather than focus only on farm lending. Sustained, strong support in the form of training and supervision is required if they are to evolve into viable financial institutions. The volume of lending needs to keep step with the growth in management skills and savings mobilization among members (overly-rapid expansion in the Georgia ADP and ambitious targets in the Azerbaijan ADCP considerably stressed implementation of farmer credit programs in these two projects). In general, these projects have shown that small village-based credit cooperatives are not an appropriate mechanism for large-scale credit delivery.
P040551 | Nutrit. Child Dev. | Eastern and Southern Africa | Uganda | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2007 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/732071475097046707/text/000020051-20140615104232.txt | http://documents.worldbank.org/curated/en/732071475097046707/pdf/000020051-20140615104232.pdf | More suitable indicators should have been used to measure improvement in cognitive skills, given that the project period was too short to allow the 0-3 year old cohort to demonstrate improved school readiness.The effectiveness of training of community child workers can be reduced to the extent that the trainees are illiterate. Their sustained participation depends on providing continued material incentives.Significant changes were made to the project design very late in the process - expanding district coverage and allocating significant funds to a new project component to conduct a household survey - without an immediate project restructuring or expansion of financing. This hampered the implementing agenciesâ€™ ability to fully carry out activities.It is possible for lower-performing projects to demonstrate important, innovative activities and intermediate impacts, when timely and well designed monitoring and evaluation is implemented.
P040553 | Municipal Solid Waste Management Project | Europe and Central Asia | Latvia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/372851475073389992/text/000020051-20140613063806.txt | http://documents.worldbank.org/curated/en/372851475073389992/pdf/000020051-20140613063806.pdf | 1. Disposal of municipal solid waste is as much a social problem as it is technical (cf. Lebanon). This was only partly recognized during preparation and appraisal of this project, though the social problems which did arise were effectively dealt with by project management and the Bank.2. Because of the problem of social acceptability, projects to demonstrate modern disposal methods and standards are vitally important. The success of the present project in smoothing the way for another project in Latvia is noted in the ICR.3. The project's technical design was commendably straightforward but allowed it to demonstrate that recycling of leachate, to prevent ground and surface water contamination, is feasible and that collection of methane for electricity production is both a cost-effective means of reducing greenhouse gas emissions and a profitable source of revenue for the landfill enterprise.
P040555 | Health Sector Development Project | Europe and Central Asia | Georgia | IBRD | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2003 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/393211474574279571/text/000020051-20140625234602.txt | http://documents.worldbank.org/curated/en/393211474574279571/pdf/000020051-20140625234602.pdf | Lessons drawn from the ICR, with adaptation by IEG:The proper project management arrangements can enable a project to sustain operations in the midst of a politically unstable environment. In the case of this project, the project management unit, which had been established as an independent entity within the Ministry of Labor, Health and Social Affairs, had clearly defined project management functions and continuity of experienced staff; therefore, it was able to continue implementation despite frequent changes in government leadership and sector reform priorities.In an environment of ongoing (and rapidly shifting) reforms, restructuring the project can be an avenue to sustain engagement in the sector; however, this needs to be balanced against the time and resources expended in restructuring.
P040556 | Roads Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/803721474908921745/text/000020051-20140615101030.txt | http://documents.worldbank.org/curated/en/803721474908921745/pdf/000020051-20140615101030.pdf | Mainstreaming of institutional principles such as efficiency and accountability can prove to be a difficult task in a sector already showing signs of â€œreform fatigueâ€ and the effects of a hurried dismantling of existing structures without sound provisions for their replacement. A longer time-frame may help to develop local ownership.Where feasible and considered desirable from experience, legal covenants should incorporate some flexibility into the institutional means used to achieve a given objective. If for some reason the original scheme cannot be employed, it will at least permit other options to be explored without the time-consuming process of revisiting the covenants;Monitoring indicators should properly balance both the quantitative and qualitative aspects of outcomes/outputs. The support of stakeholders concerned with both aspects should be sought, to ensure appropriate design and implementation of the indicators; andIncreased Bank TA in the form of sector work and advice should be considered if a policy and sector experience vacuum is produced by a political and administrative transition.
P040556 | Roads Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2008 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/772921468246593461/text/429040PPAR0P1070130Box327369B01public1.txt | http://documents.worldbank.org/curated/en/772921468246593461/pdf/429040PPAR0P1070130Box327369B01public1.pdf | 5. Lessons Learned from the Projects 5.1 Particular attention should be paid during preparation to the degree of commitment by government to implement reforms discussed. Stated commitments should be backed up with Letters of Intent; 5.2 During supervision the Bank should be perceptive to reasons for tardiness in the implementation of reform components of the project, so that intervention can be made earlier if need be, and at an appropriate level; 5.3 Institutional reform needs to be backed up by a professionally designed training program in which the participants can understand the strategic direction of the overall reform process, and their role within it; 5.4 Learning and Innovation Projects such as the Transport Ministry Restructuring Project should be designed to achieve a higher level of monitoring and evaluation for learning purposes than that expected of other projects, with key performance indicators and measurable outcomes to support future adjustments in direction .
P040557 | GH -ERSO II | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2003 | 2004 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/743621474491027777/text/000020051-20140612093832.txt | http://documents.worldbank.org/curated/en/743621474491027777/pdf/000020051-20140612093832.pdf | 1. The ICR cites lack of capacity in the Ministry of Finance as a reason why this project failed. Yet, the Bank had worked closely with the Ministry of Finance in previous adjustment operations, leading one to suspect that the Bank's eagerness to provide financing as a response to a quickly evolving government financial crisis was the important factor, overriding concerns about capacity. The lesson is that even in times of stress, as Ghana faced with the terms of trade decline in 1999 and 2000, capacity constraints need to be addressed. 2. Failure to raise petroleum prices as needed generated a large deficit which was partly financed by the GCB, thereby undermining efforts to privatize GCB as previously interested international banks lost interest with the deterioration in GCB's balance sheet. The best way to address this would have been to make pricing reforms a condition of credit negotiations. The lesson is that key reforms should be implemented up front and not left to implementation during adjustment operations.
P040558 | Energy 2 Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2004 | 2012 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/169221475077187904/text/000020051-20140625232652.txt | http://documents.worldbank.org/curated/en/169221475077187904/pdf/000020051-20140625232652.pdf | The following lessons are summarized from the ICR:The difficulty of introducing modern SCADA/Telecommunications systems should not be underestimated with respect to complexity and time required for implementation. Adequate time needs to be allowed for development of technical specifications. A utility unfamiliar with this advanced technology should therefore have an in-house independent engineering consultant actively engaged in all aspects of project design and implementation. PPFs can be effective instruments for undertaking pilot investments, and can assist in the early creation of a Project Implementation agency (PIU). The use of the PPF in the Ungheni pilot project provided both an early demonstration of the results/impact of heating/energy efficiency improvements and a test of the proposed solution to connect residential buildings, provided that the residents are willing to pay for the heat. It also introduced an element of competition for participating municipalities and thereby triggered higher commitment to successfully complete the sub-projects and ensure sustainability.Project Design: If the institutional framework to ensure the viability of heating investments in the household sector is weak due to ambiguous and often contradictory legal basis of home owner associations, it is better to focus on public buildings where the social benefits accrue to all. Importance of selection criteria. Up front statement of clear and transparent selection criteria for choice of investment locations can considerably reduces potential political pressures and influence both during the selection of project beneficiaries, as well as during the implementation of investments. Including policy reforms in the project, accompanied by priority investments, was instrumental in leveraging additional domestic and donors financing. The reform actions combined with the demonstration effect of priority investments played a catalytic role in attracting additional resources, which, in turn, contributed to achievement of improved outcomes and enhanced sustainability.
P040560 | Financial Sector Structural Adjustment Loan | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2001 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/664431475094904592/text/000020051-20140607165433.txt | http://documents.worldbank.org/curated/en/664431475094904592/pdf/000020051-20140607165433.pdf | 1 Loans based on sound sector work are more likely to succeed even in a difficult economic and political environment.2. The shared view within the government is needed for reforms to succeed.
P040564 | COAL SECAL | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1997 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Highly Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/902841474496522438/text/000020051-20140602114003.txt | http://documents.worldbank.org/curated/en/902841474496522438/pdf/000020051-20140602114003.pdf | Closure of uneconomic mines was identified to be the single most important action that was fully under the control of the implementing agency and had the most positive impact on the operating mines.The key action needed now is to improve the closure procedure and apply lessons learned from the SECAL to the next round of mine closures.
P040564 | COAL SECAL | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1997 | 2001 | 2002 | PPAR | >=100 million | Satisfactory | Highly Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/463731468781194246/text/multi0page.txt | http://documents.worldbank.org/curated/en/463731468781194246/pdf/multi0page.pdf | 5. Lessons and Recommendations 5.1 In addition to the recommendations on specific issues presented in the textt the project provides some broad lessons that are applicable across the Bank's lending program, and also several recommendations related to future Bank support for Ukraine's coal sector restructuring. 17. There was a dramatic economy-wide increase in cash payments in 2000. In the coal sector they are believed to have reached over 85 percent. However, many mines still find it necessary to use barter arrangements to finance their capital expenditure programs. 5.2 Quick disbursing SECALs are inappropriate vehicles for supporting sector restructuring programs. Sector restructuring is a long, complicated process, particuiarly in a transitional economy where strong economic forces are aligned against it. 5.3 SECALs in support of mine closures should be designed with a several small, flexible tranches, rather than a small number of large tranches. Each tranche should include a limited set of conditions, and should provide financial support for the implementation of a government decision to close some predefined, limited number of mines (possibly 5 to 10). 5.4 The financial and economic performance of pilot project activities needs to be carefully monitored. The activities initiated by a pilot proiect need to be monitored from the start in order to be able to inform decisions on the design and implementation of the remaining phases of the programStakeholder sirveys c-an play an essential rmle in this prncess. Recommendatnnrs for future aora Ir IonAing-;r e in Ulc TrJrna onal eorfAr __ flrss_sasa o ss *wn _..nnr nan1-e *-- v--. .. _ _..un.. _waLnnnln s 5.5 ~ ~ ~ ~ ~ ~ ~ ~ ~ ~~~~~~~~1-, Pr3.sdge ospo o!scoletu.uig st aez.ear focus o poverty reduction objectives. To achieve this goal, the Bank needs to structure its lending to the scLtoI 1in a way tiiat it piuviue nIIIULr suppUo Lor tIhe sciUll safety net expendiLULUS adU less support for physical mine closure activities. The most important areas of support are the payment or social liabilities to redundant miners and the rehabilitation of social infrastructure (particularly housing, heating, water, and electricity) that is to be transferred from the defunct mining company to the local administrations. This social infrastructure plays a central role in the well-being ot the affected population. Communities cannot survive Ukraine's extreme winters without these essential services. This shift in focus would take the Bank out of the mine closure business, and put it back into the social mitigation and poverty alleviation business, its primary area of concern. 5.6 The Bank needs to make greater efforts improve the efficiency of mine closure activities. More attention is needed to the provision of technical assistance with the design of efficient individual mine closure programs that take into account sDecific local conditions and include timetables for their implementation. 5.7 The Bank has no blueprint for increasing private sector job creation in a shrinking economy. The Bank should, therefore, consider working more closely with other bilateral and multilateral agencies IY that are providing seed money for establishing local cooperat_-e -anote e-hl ns;ttos esiotttosr.ypoeobegd U5I'.a ~A& ~ .RZRp J5aAU JUL. IIll.LILULtVII3 xiiiay pJluyv E) D%, r,00U intermediaries to finance new small-scale enterprises.
P040566 | Rural Water Supply and Sanitation | Middle East and North Africa | Morocco | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/366991474570669865/text/000020051-20140612070435.txt | http://documents.worldbank.org/curated/en/366991474570669865/pdf/000020051-20140612070435.pdf | Projects cofinanced and even parallel financed by multiple donors require exceptional donor coordination during appraisal to ensure that the various players will be on the same schedule. Of course, coordination efforts are required throughout implementation to ensure a successful outcome for the project and that all communities are treated in a similar manner. Beneficiary participation in O have adequate participation by women, well trained in both social mobilization, O and provided with sufficient means to operate (vehicle, per diem etc.). Different water supply technologies and management models need to be considered according to local conditions. The approach successfully adopted under the project â€“ based on a local source of groundwater and a simple RWS system serving and managed by a WUA â€“ is reaching its limits. This model is appropriate for small communities, with an easily accessible water resource, and where social cohesion is strong. Where easily accessible groundwater is scarce, more complex RWS systems and multi-village management models will need to be considered. The Bank needs to move beyond the first step of mandatory representation of women (i.e. in the SMT and WUA) and include more systematic gender awareness and womenâ€™s leadership training programs to raise the voices of women.
P040578 | Eastern Indonesia Region Transport Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2010 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/588781474666120456/text/000020051-20140617131235.txt | http://documents.worldbank.org/curated/en/588781474666120456/pdf/000020051-20140617131235.pdf | Lessons from ICR: Projects involving multiple implementing agencies need to clearly define the agencies responsibilities and should include explicit implementing arrangements.Government commitment to reforms is critical for carrying out institutional reforms. Commitment at all levels - from Government ministries to the implementing ministry is necessary.Bank staff need to be closely involved in providing advice and engaging with governments in studies of an institutional nature.Empowering independent supervision consultants is necessary if they are to carry out their responsibilities for supervision of the technical aspect of works. In case of this project independent supervision consultants were to "assist" the provincial staff in supervising the works and were not assigned responsibility as the Engineer in the contract due to the Ministries requirements. This did not work well and was not cost effective.Following lessons are taken from the Borrower ICR:To ensure that the Standard Operating Procedures for environmental actions are followed, the contract should include specific penalties if the parties breach the contract.Decentralization of the Project Management Report (PMR) should have included on-job training in provinces, not just classroom training in Jakarta. In order for technical audit to be effective and independent, they should not be linked with payments for work done.
P040599 | Second Tianjin Urban Development and Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2012 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/738611474483109052/text/000020051-20140625235410.txt | http://documents.worldbank.org/curated/en/738611474483109052/pdf/000020051-20140625235410.pdf | The ICR reported two broad lessons: 1) Innovation should be encouraged, but a balance of innovation and risk should also be considered when preparing projects. This project involved many innovative activities and technologies, which should be encouraged and valued, but which inevitably involve uncertainties and risks that challenge their implementation. Under this specific project, some innovative activities were implemented as planned such as Dagu Canal rehabilitation, but at higher cost, both financially and timely. Some activities were dropped. 2) Projects should select the right instrument depending on the project composition and substance. This project was complex with various activities and technology uncertainties. In hindsight, an APL would have been a more suitable instrument than SIL.
P040599 | Second Tianjin Urban Development and Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2012 | 2014 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/136611468023049623/text/886070PPAR0P04010Box385279B00OUO090.txt | http://documents.worldbank.org/curated/en/136611468023049623/pdf/886070PPAR0P04010Box385279B00OUO090.pdf | 4. Lessons â€¢ Great care is needed in project preparation and appraisal to ensure that all proposed interventions are feasible. In the case of the Tianjin-II project, some originally designed components and activities, such as the Dagunanlu interchanges and the water reuse activities, were cancelled or modified because the feasibility studies showed that these activities were not feasible. The changes led to project restructuring and implementation delays. The Bank projects should have more thorough and solid project appraisal including the detailed feasibility studies. â€¢ A well-phrased and clearly defined project development objective statement and a comprehensive M&E framework is a key step towards a results-focused Bank operation. Both the Tianjin-II and Chongqing small cities project face similar challenges of PDOs that are not clearly defined and non-comprehensive M&E framework, making it difficult to monitor and assess the project implementation progress towards achieving the development objectives. IEG's interaction with task team leaders across the Bank suggests that phrasing an accurate and relevant PDO appears to be a common challenge; more support to the project teams is needed in this area. â€¢ By continuing to tailor its services and instruments to the more localized needs and capacity of the Borrower, the Bank can maintain the effectiveness of its support. The interaction with local officers in Tianjin and Chongqing suggested that there is still strong demand for the Bank's support in urban development in China. However, in more developed urban areas like Tianjin, demand is mainly for the Bank's innovation and knowledge rather than the Bank's financing. For less developed urban areas like the secondary cities in Chongqing, the Bank's financing and project management experiences with special attention to environment and vulnerable groups are very much appreciated. â€¢ While the Bank's engagement has supported the development in China, its prolonged internal decision-making processes may decrease its competitiveness in helping address fast-paced changes. In the case of Tianjin-II, the project implementation often could not keep up with local development, resulting in the cancelation of project activities. Such an experience is quite common across the Bank's projects in China. Inefficiency on the Bank side is often cited by the borrower and the Bank's TTLs as the main reason. The Chinese borrower suggested that the Bank could become more efficient though simplifying the procedures and granting TTLs more authority so that the TTLs could make more timely decisions to accelerate project implementation.
P040610 | Rajasthan Water Sector Restructuring Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2013 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/266381474633262873/text/000020051-20140626121305.txt | http://documents.worldbank.org/curated/en/266381474633262873/pdf/000020051-20140626121305.pdf | Among the most important lessons from this project, none of which, however, are new, are: 1. Managing complexity in complex sectors. A project designed to address complex institutional and policy reform issues in politically sensitive sectors, such as those involving water resource management and use, is unlikely to achieve its objectives in 5 to 6 years, and more time and one or more closing date extensions, or alternatively more than a single operation (perhaps in the form of an APL) is likely required. Thus, it is important to differentiate the implementation requirements of longer-term policy and institutional capacity building goals from short-term physical infrastructure development ones. This is particularly important in low-income states such as Rajasthan, where there may also be significant institutional capacity constraints. 2. User fees for water are not easily reformed. Again, this is a politically sensitive matter, and simply mandating that fees be increased does not guarantee that this will happen in practice. Furthermore, simply establishing increased fees does not necessarily result in increased revenues if incentives to pay and adequate enforcement mechanisms are not in place. 3. Developing well-functioning Water User Associations (WUAs) is a long-term process. It is, thus, important that the pertinent government agencies have adequate programs to provide technical support, training and capacity building. A key corollary is the need to invest appropriately in the capacity of these institutions to provide such services in a sustainable way. This also suggests the preferability of a multi-project approach rather than attempting to achieve such time-consuming objectives in a single operation.
P040612 | Basic and Primary Education Project II | South Asia | Nepal | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2005 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/336171475090821482/text/000020051-20140613043116.txt | http://documents.worldbank.org/curated/en/336171475090821482/pdf/000020051-20140613043116.pdf | Bringing good primary education to out of school youth in remote locations or minority groups, having disabilities, or bound by tradition (girls, low castes) require special strategies and innovations, including alternative or non-formal education programs. These were highlighted in Project appraisal documents, but appeared to be marginalized during Project implementation. The Project shows the need to take a holistic view of the teaching learning process compared to a view which merely focuses on meeting subcomponent targets (as occurred in the Project). With a holistic view, focused on the classroom, a Project will put into place the critical mass of interrelated inputs needed to improve student performance, i.e., adequate physical space, books and materials, teacher attendance, time on task, teacher training, and management support. Educational planners and managers need to ensure sufficient financial support for non-salary recurrent costs (e.g., learning materials and building maintenance). This was lacking under BPEP2, limiting the impact of some quality enhancement measures such as teacher support at resource centers and better use of teaching aids.Teacher training needs to have a practical, hands-on orientation. That provided during BPEP2 was considered to be too abstract; on-site training is always more effective, allowing teachers to learn about and practice new techniques in their own classroom environment (a feature of the new IDA-funded Community School Support Project in Nepal). It was important to have the Government driving the project and to have donor agencies working together under the Government's agenda and leadership. In BPEP2 this helped to reduce tension, competition and duplication among donors and to decrease their putting their own "stamps" on projects. It is not enough simply to set up data collection systems if the data generated are of poor quality. Quality assurance must be built into the systems so that an accurate picture of performance can be formed and decision making, at all levels, can be better informed.
P040612 | Basic and Primary Education Project II | South Asia | Nepal | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2005 | 2009 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/101991468059704807/text/491210PPAR0P111C0disclosed071241091.txt | http://documents.worldbank.org/curated/en/101991468059704807/pdf/491210PPAR0P111C0disclosed071241091.pdf | 5. Lessons 5.1 This assessment provides a number o f lessons for the education sector\. Government commitment and donor financing can be effective in increasing access for the poor and disadvantaged children in low-income countries. Decentralization o f management to district levels may help attain this goal if budgetary outlays are also decentralized (para.3.7). To improve learning outcomes, however, attention must be given to instructional aids and the learning conditions o f classrooms (paras. 3.12- 3.18). Scholarships targeting the very poor or disadvantaged may not always be distributed as expected, particularly when criteria are unclear and decisions are l e f t up to local school authorities (para.3.24). Small scholarship amounts may also have limited practical value. More research i s needed to understandthe value o f small scholarships as an incentive for the very poor. Collection o f reliable data i s crucial to donor and government activities. However, local-level inaccuracies and incentives to over-report enrollments may result in significant statistical distortions. Triangulation o f data from other sources may be needed to arrive at estimates that approximate true values (para. 4.6).
P040613 | Nepal Health Sector Program Project | South Asia | Nepal | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2005 | 2011 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/859501475109979287/text/000020051-20140624195843.txt | http://documents.worldbank.org/curated/en/859501475109979287/pdf/000020051-20140624195843.pdf | The ICR provides several useful lessons, as follows:Ambitious expectations for policy and institutional reforms in uncertain political and security environments need to be realistic; in this case, the original ambitions for decentralized management of the health sector were not realistic given political and social turbulence at the local level in Nepal.Projects, and by implication, sector reform programs with a focus on improving access for the poor and underserved must anticipate the need for disaggregated data to enable specific tracking of progress. Basic routine administrative reporting systems are not likely to be adequate for this task, suggesting that arrangements for mainstreaming survey or other mechanisms to enable local level measurement should be considered as an element of sector reform.Improving access to essential health care requires comprehensive and consistent work to address systemic constraints. These include overall sector finance, more robust human resource management systems and strengthening underlying procurement, logistics and distribution systems. The EHSP implemented through NHSP did not adequately address malnutrition. Nepal had one of the highest rates of stunting among children under five at the time of project appraisal, but the issue was not effectively addressed in defining development objectives for the NHSP and the project.The placement of the TTL in the field for sector wide operations can facilitate project implementation by facilitating collaboration and coordination with government as well as EDPs.Improving key elements of sectoral governance, including procurement and financial management, requires a continuous long term approach, likely better integrated with review and advice on broader budget management and execution issues. The introducing of the Governance and Accountability Action Plan as part of the additional financing was helpful in recognizing links between sectoral specific problems and the need to strengthen country systems.
P040631 | ZM-Econ Mgmt & Growth Credit (FY05) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2005 | 2006 | 2007 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/261921474506561966/text/000020051-20140617130709.txt | http://documents.worldbank.org/curated/en/261921474506561966/pdf/000020051-20140617130709.pdf | In policy-based lending, the Bank needs to focus to a greater extent on the consistency of project conditions with the objectives being addressed.The lending instrument needs to be consistent with the objectives being sought, which was not the case for the EMGC
P040642 | ZM-ERIPTA (FY96) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/757771475071635433/text/000020051-20140615100611.txt | http://documents.worldbank.org/curated/en/757771475071635433/pdf/000020051-20140615100611.pdf | The privatization of utilities is very complex, and should generally be considered separately from privatization of other enterprises. Provision should be made for development of adequate regulatory capacity.Lack of transparency can seriously erode public support for privatization.In a project supporting privatization, greater account needs to be taken of the Political Economy of Reform.
P040649 | COMMUNITY REINTEGRATION & REHABILITATION | Western and Central Africa | Sierra Leone | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2004 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/718851474896465404/text/000020051-20140612102101.txt | http://documents.worldbank.org/curated/en/718851474896465404/pdf/000020051-20140612102101.pdf | The project provides many lessons. The most important are:Reintegration (DDR) and rehabilitation (RRR) activities should be implemented separately but in parallel. These functions require different structures from a service delivery perspective because reintegration of ex-combatants requires a tightly controlled top-down, targeted approach whereas reconstruction, resettlement and rehabilitation requires a bottom-up approach focused on empowering communities. While it is important to strive for maximum community participation in reconstruction of communities destroyed by conflict, it is equally important to be realistic about the extent of participation feasible during early post-conflict conditions when many community residents are moving back from IDP camps.Independent and professionally managed financial management and procuring units can increase the effectiveness of post-conflict investments particularly by increasing donor confidence to invest in and help improve administration of the project.When using NGOs as implementing partners, it is important to conduct a capacity assessment of the sector and plan up-front capacity building during the project design phase.Under post-conflict conditions where information/data area scarce, a simple logframe - focusing on a few key indicators, supported by base-line studies - should be used to monitor project progress.
P040650 | Education Sector Expenditure Program | Western and Central Africa | Mali | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/225951474633289453/text/000020051-20140618064309.txt | http://documents.worldbank.org/curated/en/225951474633289453/pdf/000020051-20140618064309.pdf | National programs instituted to improve both access and quality need to assess quality not only in terms of inputs (books, buildings) and processes (improved teaching), but also in terms of learning outcomes. Before such programs are launched the capacity for such assessment needs to be either identified or included as a capacity building priority. Fluent reading skills in early grades is a key to desired levels of educational achievement in all subjects and is an appropriate educational goal in development projects. Systems and the capacity for measuring such outcomes need to be assured prior to launching interventions in this area. They should not be seen as a substitute for routine student learning assessments. Reforms in funding policies, management structure (decentralization), curricular design, and the delivery of inputs and services (e.g., textbooks), all are essential to the improvement of educational access and quality, but unless they impact service on the ground at the school and classroom level, they will not have their intended affects. M&E systems need to be able to provide feedback on school level outcomes and intermediate outcomes. Countries like Mali, in which few children speak the metropolitan language, often find it difficult to implement established policies of using national language of instruction, even when national and regional research findings and pilot programs show great advantages to children in doing so. Strong political and continued R&D results are needed to bring such programs to fruition. Under some circumstances government support for community schools (e.g., paying the salaries of locally hired of teachers and providing textbooks and learning materials) can be a cost-effective way of expanding access to basic education. Major government programs to expand education access and quality need to be planned within the context of overall sector improvement, recognizing important cross-and intra-sectoral synergies. Projects and programs growing out of such plans, however, need to focus on a limited number of reforms and innovations (those minimally required for success), in order to avoid system overload. Temporal sequencing of reforms and innovations is a way to eventually cover a comprehensive list. Coordinated development agency support for well planned government programs can reduce transactional costs and conflicting agendas and add stature to a reform agenda. The full potential of such cooperation will only be realized when agencies harmonize their reporting and procurement procedures. Note: This is an important phase of a crucial educational reform series, the project has already been observed in the field by IEG as part of the Mali case study in its Primary Education Evaluation.
P040652 | Health Sector Development Program | Western and Central Africa | Mali | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/197561474940186315/text/000020051-20140618053641.txt | http://documents.worldbank.org/curated/en/197561474940186315/pdf/000020051-20140618053641.pdf | The establishment of overly ambitious objectives and targets is likely to undermine a program's prospects for success. In the case of this program, while end-of-program data on many indicators revealed positive trends, they fell short of targets and objectives, which caused program outcome to be deemed less than satisfactory.Whatever the financial instrument, there is no substitute for conducting the analytical work essential for avoiding major design flaws. In this case, the lack of in-depth analytical work might explain why the PDOs and many intermediate objectives were not discussed realistically. There is an inherent tendency to over-promise on sector management results as well as health outcomes and impact. Though often agreed on in haste, the modalities for entering into and transitioning from project to program arrangements are complex and require careful study. Arrangements must take into account all potential implementing structures and all sources of financing. The use of increased amounts of untargeted funding on current needs may have the consequence that any abrupt cessation of funding is keenly felt by the implementing units as well as by the Ministry and its partners.A failure to reach agreement on the determinants of health status during project preparation will result in the use of funds for activities that are easier to implement rather than those which are most strategically important.
P040653 | Rural Community Development Project | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/419721475112742944/text/000020051-20150113011516.txt | http://documents.worldbank.org/curated/en/419721475112742944/pdf/000020051-20150113011516.pdf | Among the key lessons that can be derived from this project are the following: 1. Community-driven Development (CDD) approaches may be particularly effective when crisis situations occur. In the present case, the civil conflict in the northern part of the country in 2012 revealed that, while central institutions may be weakened, a CDD approach can facilitate the reconciliation process between communities affected by the conflict. 2. Capacity building at all levels is essential for community empowerment. This includes pertinent central and local government (i.e., communal) institutions, local public and private sector service providers, and the affected rural communities themselves. According to the ICR (para. 117, pg. 27) more specifically, "providing training through local expertise (civil society organizations) has...enabled capacity building to reach the micro level (villages) throughout the country and this was critical for communities to develop socio-economic and productive investments." 3. There is a need to ensure that all project stakeholders are fully in line with project arrangements. This lesson is derived from the initial procurement, financial management and implementation problems experienced with the community infrastructure component, which the ICR (para. 115, pg. 27) concludes appeared to be the result of the fact that "implementation arrangements were insufficiently prepared."
P040653 | Rural Community Development Project | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2014 | 2018 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/375171507898648434/text/120119-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/375171507898648434/pdf/120119-PPAR-PUBLIC.pdf | 6. Lessons 6.1 Investment in rural service delivery requires an informed analysis and consideration of human geography, including the factors that influence population movement and household investment decisions. In Mali, an increasing percentage of the rural population is living outside of formally recognized administrative areasâ€”in hamlets as opposed to villages. In the PACR project, the use of existing administrative systems, budgeting, and planning tools was insufficient to address the needs of those living in informal settlements, or hamlets. Neglecting these human geography dimensions can reinforce income inequality and exacerbate societal tensions. Gender is also a key factor; women migrants who reside in hamlets are the most disadvantaged, in terms of access to the productive factors. 6.2 Rural productive investments made through CDD projects should build on established skills sets and tested economic relationships. They should avoid promoting excessively risky behavior by offering options to expand ongoing, profitable activities, linked to agriculture. Support for transformation or commercialization activities should be underpinned by market and value chain analysis that is povertyand gender-sensitive. In Mali, in the PACR project, the most successful productive investments are associated with established productive groups who were enabled to deliberately and thoughtfully choose their investment based on their established skill sets and their own knowledge of local market. 6.3 Projects can be used to demonstrate the benefits of citizen engagement, but mechanisms to promote sustained engagement must extend beyond project boundaries. Projects can lay the groundwork for more inclusive local development planning by demonstrating the benefits of participation to local policy makers. These efforts can lower perceived risks about participation if local government is engaged. But for a project to have sustained participation effects, attention must be paid toâ€“and indicators need to measureâ€“the influence of the participatory mechanisms on local planning processes in the absence of the project, including the expectations raised and how demand manifests itself in the local systems the project has sought to influence.
P040659 | Community-based Poverty Reduction Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/233711474570152063/text/000020051-20140615100937.txt | http://documents.worldbank.org/curated/en/233711474570152063/pdf/000020051-20140615100937.pdf | ICR suggests a number of important lessons: Given the short time and limited resources allocated to LILs, such projects should not be complicated in design and implementation. The project had three different components dealing with three different sectors and three government institutions. This slowed down the project's start-up creating delays and increasing costs, thus hindering the success of the project. Bank staff need to be more engaged in the preparation of LILs in order to explain the learning and innovation nature of this lending instrument, especially if the project in preparation is the first LIL in the country. The project proved that when this is not done properly, the risk of delay increases (in this case, there was misunderstanding by some members of the Parliament about the nature of LILs).In project of this nature it is crucial to have a well structured M&E with quantifiable poverty-related indicators, in order to back up and use the lessons learnt.
P040685 | INFRA. PRIVATZTN TA | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 1999 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/846081474659853507/text/000020051-20140529070739.txt | http://documents.worldbank.org/curated/en/846081474659853507/pdf/000020051-20140529070739.pdf | (i) It is important to determine precisely, by sector, the political commitment to privatization during project preparation. (ii) Because of the importance of the regulatory framework to the functioning of newly privatized institutions, it is important to focus on the regulatory framework before privatization. (iii) One of the Bank's key contributions can be in the intellectual area of providing international expertise in techniques for privatization; the quality of Bank staff and consultants is critical.
P040685 | INFRA. PRIVATZTN TA | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 1999 | 2003 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/462181468774652050/text/262020ME0PPAR.txt | http://documents.worldbank.org/curated/en/462181468774652050/pdf/262020ME0PPAR.pdf | Lessons Transport Air Quality 90, An externalpanel o freputable, international experts to provide advice andreview duringimplementationis especiallyuseful for projects addressing new areas, where several sectoral agencies and levels o f governments needto be coordinated, andwhere external experts can provide credible andunbiased recommendations on sensitive matters. 91. Muchprogress can be achieved inreducing the impact of road transport on air quality through a combination ofpublic andprivate sector measures, startingwith an adequate systemo f incentives put inplace by federal and state governments. Highway Rehabilitation 92. Decentralization in the management of the highway network, while generally advisable especially inlarge countries, i s bound to fail ifrequisite conditions are not obtained. Critical among these are ensuring that local governments receive adequate finding corresponding to their new responsibilities for highway maintenance, andthat they have the required expertise to manage the roadnetwork. 93. Allocation of highway maintenancefunds optimizes outcome (measured as condition o fthe network) when finding i s used for routine andperiodic maintenancein preference over rehabilitation. However, this approach i s only valid for a few years, and unless finding levels are increased to allow rehabilitation works to proceed, the condition o fthe roadnetwork i s likely to worsen. Infrastructure Privatization 94. Infrastructure privatization, to gainpublic acceptance, requires as necessary (but not always sufficient) conditions, a transparent privatization process, compliance with commitments byprivate operators, and government provision o f social protection to users o fnon-commercial services and to staff made redundant 95. Establishing a regulatovyframework for the infrastructure sectordenterprises to beprivatized should be considered early on inthe design o fthe privatizationprocess, together with an assessment o f the capacity o f existing agencies with regulatory functions, incase fiscal and administrative constraints make it politically impossible to create new regulatory bodies.
P040712 | Water Management Improvement Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/656071498229189567/text/ICRR-Disclosable-P040712-06-23-2017-1498229172820.txt | http://documents.worldbank.org/curated/en/656071498229189567/pdf/ICRR-Disclosable-P040712-06-23-2017-1498229172820.pdf | The ICR presented 9 lessons learned namely three under each of three headings (General, Project Design and ProjectImplementation). Most lessons listed were focused on this project and were not generally applicable. However, the most significantlesson which had general applicability was as follows: Complex institutional core reforms, ifincorporated in a Projects design, are better implemented in a focused and phased manner. Unconnected to reformactivities and multiple actors engaged in implementation typically overwhelm responsible agencies and beneficiaries, and distractthem from achieving the core reforms. A phased approach ensures stronger commitment and sustainability of core reforms.
P040713 | Silk Development Pilot Project | South Asia | Bangladesh | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/654611475083648196/text/000020051-20140612100745.txt | http://documents.worldbank.org/curated/en/654611475083648196/pdf/000020051-20140612100745.pdf | Pilot projects, if well designed and supervised, can be very successful in demonstrating new technologies and in supporting politically sensitive institutional reforms;Because they involve less money than standard investment projects, pilots are less a hostage to the Bank's typical emphasis on rates of disbursement; and Pilots offer both a safe space for experimentation and the freedom to fail, these being essential for innovation;Not-for-profit foundations can effectively accommodate the interests of a number of stakeholders; but it may be difficult to secure autonomy for foundations initially suppported with government funds and it may also be hard to attract capable managers from the private sector.
P040713 | Silk Development Pilot Project | South Asia | Bangladesh | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2003 | 2007 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/208921468205174549/text/36295010BD.txt | http://documents.worldbank.org/curated/en/208921468205174549/pdf/36295010BD.pdf | 6. Lessons and Considerations for Future Development 82. Four specificlessonsregardingthe pro-poor growth challenge, and a final lesson related to the Bank's strategyfor Bangladesh's rural sectorhave emergedfiom this review. The first four lessons are closelyinterlinked, and, together, provide two important observations. First, the projects illustratepracticalways to emphasizegrowth and social equityat the sametime, and even demonstratinghow improving equity can also improve productivity. Second,actions across the four areas canbe mutually reinforcing.Pro-poor and gender-inclusiveagriculturalgrowth canbe further stimulatedwhen more than one action area is tackled simultaneously. (1) Dedicated focus on enhancingproductivity pays off. Breakthroughsinproductivity canbe triggeredby making a quantum improvementin productivity a major goal and specifically addressing this in the project's design. Without designingthe project with this in mind, productivitybreakthroughs may not occur. 83. The SDPP and the HORTEXcomponent of the ASIRP placed their major focus on stepped up productivity, and achievedthe breakthroughsthey aimed for. The FRMF did not emphasizeproductivity enhancement, aid no major gains in the productivity of the forestry sectoroccurred. 84. The achievementsreflected the emphasisthat each project placed onproductivity. The very essence of SDPPwas to bring about a quantum leap in the silk sector's productivity to enableBangladeshto be more competitivein relation to the internationalmarket. Nearly all of the SDPP7smonitorable indicatorsmeasuredproductivity.Likewise, the major objective of the horticulturalexport component of ASIRP was to help Bangladeshiexporters to break through the barriers to entryinto the much higher-value international market, compared to the lower-value (and lower-productivity)of the domesticmarket. The FRMP was more in the mold of traditionalBank projects. Its design and impactwas on increasing the number of hectares ~mdercultivated forests, coastalprotection, environmental management and iiistitutionalimprovement. It also had a smallresearch component, as often found ill a Bank rural project. While the FRMP successfullyachievedits objectives, a major jump in productivitywas not its centralpurpose and was not achieved.33 85. The SDPP and HORTEX achieved their breakthroughsthrough a combinationof institutional as well as technologicalinnovations.The enhancement of silk sector productivitywas primarilythrough introducingtechnical improvements, but drivingthis was the new Silk Foundationand the NGO sector. The export breakthroughfor horticultural products involved substantialnew technologiesfor Bangladesh in growing, grading, packaging and transportingof produce,but it was pioneered and then catalyzedthrough an institution, HORTEX, designed and dedicated exclusivelyfor this purpose. - - 33. The reference to improve theproductivity in FRMP's developmentobjectivesreferredto the expansionof forestplantations, not to an improvementinproductivity per hectafe. 86. The SDPP and HORTEX successesmight, however, be exceptionsto the more typical situationfound in Bangladesh's agriculturalsector,where technical knowledge to enhanceproductivitymay be limited. The IEG mission was informed that research was a smallpart of government's expenditure in agriculture-only about 0.2percent of agricultural GDP.34A revolution in agriculturalproductivityis likelyto need a much strongertechnical base than Bangladesh's relatively small researchprogram can currently provide.35 (2) Sociallyinclusiverural developmentneed not constrain rapid agricultural growth. Project design featuresthat target benefits for the poor and women may even enhance agriculturalgrowth. 87. Over 80 percent of the SDPPparticipantswere poor women, and they showed greater interest and care in rearing andreeling-hence in adoptingsericulture and achieving higherproductivity-than wealthierhouseholds. Poor women were the primary target of the SDPP's NGO extensionservices.Under the FRMP's communityforestryprogram, higher productivity,sustainabilityand social inclusionwere found to be mutually complementaryto each other. Tree survivaland groundcover significantlyincreased and yields will likelybe higher, andpoor families and women were the primarybeneficiaries. The key factorleading to increased productivity and sustainabilitywas the switchto communitymanagement by the sociallydisadvantaged, who took greatercare of the plantations than governmentor villagers with higher incomes.. (3) Government-civil societypartnerships can enable large gains in development capacity, both for social inclusion andfor agricultural growth. 88. Bangladeshis known for particularly large inefficienciesin the public sector, and in governance generally.By contrast,the country is rich in its non-government sector, particularlyin its NGOs. Two of the projects reviewed, the SDPP and the ASIRP, indicate that partnerships between government and civil society canbe a major source of increased vitality and productivityin Bangladesh's rural sector. 89. Promotionof the silk sectoris based on a partnershipbetween the Silk Foundation (technical,promotionaland seed production) and the NGO sector, which does most of the extensionand field support,as well as seedproduction. The commercialprivate sectoris fast developing as an additional actor in reeling,weaving, and garment manufacture. The Silk Foundation's technical skillsare conlplementedby the NGO sector's far wider reach and greatercapacityto provide extensionservicesskilled in socialoutreach.Under the horticulturalexport component of ASIRP, horticultural exports were promoted through partner activitiesbetweenHORTEX and the private sector.36Under the DAE component of ASIRP, the partnershipsbetween DAE and NGOs at the upazila level became the centerpiece of the agriculturalextensionprogram. DAE emphasizedto the IEG mission that this 34. Source\.WB ReportNo. 34543-BD; Bangladesh\.Revitalizingthe Agricultural TechnologySystem, November 30,2005. 35 Globalevidence has indicatedthatreturns to research are higher than for any other investmentin agriculture. 36. The partnership for the first exportwas with an NGO. Sincethen, the commercialprivate sectorhas become the dominantsource of horticultural exports. approach could greatlyincrease the effectivenessof agriculturalextension-the DAE providing its technical skills, but others, especiallythe NGO sector, being better in field outreach. 90. By contrast, the FRMP projectwas implemented mostly by the Forestry Department,indicatingthat governmentimplemeiitationwithout partners can alsobe success~l,at least for forestry.However, the pilot activitiesin communityforestry all involve the FD working with small NGOs, the formermainly in technical areas and the latter in local-level social support.The initial experiencewith the FD-NGO partnerships appears promising. 37 (4) To enhancebenefiltsfor women andthe poor, project formulation needs the systematicintegrationof measuresto achieve this. Measures to achieve such social objectivesneed to be organicallyintegratedin the project\. i.e., specificallyfeaturedin the project's design, costing, institutional arrangements, staffing,management processes, the logical framework and monitoring. 91. All threeprojects took somepositive stepsto target women and the poor. These actions, which are typical of other Bank projects, arenoted immediatelybelow, but they were more in the nature of add-ons to project implementationrather than being systematically integratedinto the projects. A more systematicapproach could likely have achieved more. 92. With its labor-intensiveand cottage-based activities,the silk sector is pre-eminent in includingwomen and the poor. Silkrearing and reelingprovide regular income and can be donepart time and on marginal f m s or by the landless. The IEG mission also observed a high proportion of women employed in weaving and garmentmanufacture.Additionally, the NGO extension activities in the SDPPwere specificallytargeted to women and the poor. Based on mission discussions in the field, perhaps over 95percent of beneficiaries were poor, of which over 85percent were women. 93. Concerningthe ASIRP, DAE said that extensionworkers were asked to target women and poor liouseholds.The mission was also told that in choosing communitiesfor sub-project grants, the local (upazila) committeesfavored communitieswith a high proportion of women and the poor, but there is no datarelative to this. Assuming that the sub-projectsdid have some successin socialinclusion, this would have been importantin counteringthe natural societal tendency for minority groupsto be left behind. It is possible that the gender and poverty impact of the ASIRP would have been quitemodest without the project's efforts, sincethe mission visits found the usual tendency for men and wealthier individualsto have the primary influenceon village-level decisionmaking. 94. The FRMPprovided the most striking example of gender and poverty alleviation outcomesinfluencedby project actions. In the mission's visits to several communitymanaged plantations,the great majority of the beneficiarieswere women and the poor. As with the other two projects, the primary reason was that selectionof participants by the Forestry Departmentand local committees strongly emphasized gender and poverty criteria. 37. There is also positive global evidence where forestrydepartmentshave worked withNGOs.; for instance, in India and Nepal. This was appropriatesinceinternational experienceindicatesthat forestry development can have negative social impactsunless there are specificmeasures for social inclusion. The development of government-managedplantations commensuratelyreduces the number of hectares under traditional forests.Even when degraded, such lands provide for traditional forest-based activitiesimportant for the livelihoodsof women and the 95. However, none of the projects employed a systematicapproachto social inclusion, which would likelyhave enhanced gender and poverty alleviationoutcomes. The IEG mission noticed the followinggaps. First, the capacityto plan, implement and monitor the projects' gender and poverty aspectswas limited in both the government and Bank task teams. Themission did not encounterany social specialistsin the project agencies, and data in the ICRs indicatethat the Bank team for the FRMP onlyinvolved a social specialistin project preparation,and for the ASIRP, onlyin supervision.Second,none of the projects had a gender andpoverty alleviationplan, which should also have been integrated into the project's detailed design. Third, therewere no monitorableindicators on poverty and gender impactsin the log fiames, and project data on outcomes was limited. Hence the key features for systematicallyenhancingbenefits forwomen and alleviatingpoverty were largely absent.39 (5) The Bank's rural project portfolio in Bangladesh would merit scaling-up, prioritizing, a longer-termprogram approach, and a better strategicframework. 96. The Bank's lendingto Bangladesh's rural sectorhas declined significantly over the last 5-10 years. (See the completelistingof Bank projects to Bangladeshin Annex C.) Out of 25 ongoingprojects in the Bangladeshportfolio as of February2006, only oneproject is rural (2006 CAS, Annex B8). And only onerural project was approved during the last five years FYOl to FY0540-compared to 23 approvedprojects in the overallBangladesh lending program. None of the three projects reviewed in this PPAR had follow-onprojects. 97. This situationcontrasts sharplywith the messages expressedin Bank and Governmentpolicy documents. The government's 2005 PRSP sees agriculture as the key driver of pro-poor growth. The Bank has also emphasizedthe importanceof the rural sector and highlighted this in each of the last three CASs (1998,2001 and 2006). The 1998CAS comments that faster agriculturalgrowth and rural development are critical in a country where more than 90 percent of the poor live in rural areas. It also commentsthat several 38. Socialrisks alsoneed to be tackled in project.designand implementation. In missiondiscussionswith forestrycommunity groups,a vulnerabilityof the extremepoor to pressuresby locally influentialpersons (to sell forestrights at well below market value for instance) appearedto be a risk. Adaptationsto reduce this risk might be considered,such as strengtheningcommunity-levelinstitutions and making individualdecisions subjectto reviewby the whole community. 39. In this situation,even understanding the social impact of project activitiesis difficult, and making adjustments duringproject implementation has littlebasis on whlch to plan. In the appraisalreports and some government documents, there was also a tendencyto highlightthe expectedgender andpoverty alleviation impacts in the main text, but with limited further reference and implementationdetails in the annexes. 40. This was the Microfinanceproject (approved in FYO1)which is partly rural. Two otherprojects with impact on the rural sector in the FYOl to FY05 period were the Rural Electricity-Renewable Energy Development Project (FY02) and the Rural TransportImprovementProject (FY03). strategicprioritiesprovide the framework for our assistance, of which agriculturewas one. Sincethree of these priorities were macro or cross-cutting(macroeconomic management, private sectordevelopment, and public sectormanagement), agriculturewas one of onlytwo sectors, along with human development,that were singled out. The 2001 CAS considered rural development as one of three priorities for pro-poor growth. Whilethe 2006 CAS is less explicit in highlightingrural development,the first of the CAS's two pillars (improving the investment climate) includes agriculture-along with infrastructure,water resourcesmanagement and informationand communicationstechnology-in its listingof four sectors critical to pro-poor growth. Yet the priorityplaced on agriculture in these policy statementsdoes not appear to have been translated into the lendingprogram. This situationappears likelyto continue, sincethe 2006 CAS has only one rural development project -the proposed National Agricultural TechnologyProject -amongthe 24 projects listed in the proposed lendingprogram for 2006 to 2009 (2006 CAS, Annex B3). It should, however be noted that there are severalpast and proposed projects that supportrural developnlentmore broadly.41Whilethese projectshave potentially significantimpacts on the rural sector,none of theseprojects directlytackles the rural sector's need for a major shift in agriculturalproductivityand pro-poor growth. For this, additional direct engagement in agriculture,water and forestryis needed. 98. The IEG mission frequentlyheard the view that rural sectorlendingis more difficult and its resultsmore disappointingthan in other sectors. The threeprojects reviewed in this PPAR do not support this view. All three projectswere worthwhile, with outcomes at least moderately satisfactory. TheFRMP achieved all its physical objectives,helped improve institutional capacity, developed environmental management plans for Bangladesh's nature reserves,helped develop coastalmangrovesto improveprotection against storm surgesand started successfi~lpiloting of community-based forestry. The SDPP significantlyraised productivity in the silk sector, which had a positive impact on gender inclusion and poverty alleviation.The ASIRP pioneered and catalyzed a breakthroughin horticultural exports, and the agriculturalextensionpart of the project may alsohave had a significant impact. With sensibledesignsthat play to Bangladesh's strengths(such as the NGO sector),with the introductionof technological and institutionalinnovationsas needed, and with strong implementationsupport, ruralprojects in Bangladesh can succeed 99. In fact, the averageperformanceof the three PPAR projects is not substantially different from the aggregate situationacrossthe Bank's entireBangladesh portfolio. Excludingthe PPAR projects, nine of the 17projects completed between the beginningof 2000 and end of February 2006 had a satisfactoryoutcome, six were moderately satisfactory, onemoderatelyunsatisfactory, and one unsatisfactory. 100. The Bank should not downplay the importanceof relevance. If development of the rural sector is a strategicpriority, it does not make senseto neglect it. The question of why support for rural development has declined, is appropriateto pose across the board; not only 41. TheRural Departmentofthe Bank's SouthAsia Regionhas commentedonanearlier draftof the PPAR that it also envisages other operationsinrural livelihoods, water managenlent,fisheriesand landmanagement. The Rural Departmenthas also madereferenceto otherproposedor ongoingprojects supportingrural development suchas rural electrification,rural finance,andlocal governance. to the Bank, but also to other development agenciesand to the government.42It is better for the Bank to support a highlyrelevant development thrust, eachproject having a moderately successfL1o~~tcome,than to support areas of less relevancebecause these are easier.Not supportingrural development in Bangladesh is walking away from one of the country's highest priorities. 101. Bank lendingto the rural sectorhas also sufferedfrom a lack of continuityin recent years. Thiswas not so in the past. Both the FRMP and the ASIRP followed previous projects in their respective sectors,the Bank having supported two projects in forestryand three projects in agriculturalresearch and extensionprior to the FRMP and ASIRP. The ASIRP followedon almost immediatelyfrom the Agricultural Support ServicesProject, which had startedpioneering the new extensionapproaches and had provided initial supportto HORTEX.None of the threeprojects reviewed in this PPAR had follow-onBank support, even though two projects in particular-SDPP and ASIRP-supportedprograms which required a longertime period to become hlly established. 102. The lack of continuityin lendinghas been compoundedby uliduly shortproject durations\.The ASIRP had only a 3%year implementationperiod, and the SDPP 5%years, which included the establishmentof a new agency, the SF, to implementthe project. The 9% years implementationperiod for FRMP was more realistic and about right for the large program that the FRMP supported (thoughthis unusually long implementationperiod could have been broken down into two shorter projects). Thismore realistic time fiamehas probably contributed to the higher outcome and sustainabilityratings for the FRMP relative to the other two projects. 103. The IEG missionnoted the particular vulnerability of the ASIRP's agricultural extension component. In field discussions,it was encouraging to find, four years afterproject closure, enthusiasm still present amongDAE staff for the new extension approachintroduced under the ASIRP. However, as one district officer expressed it, we stillhave the partnerships,but, sincethere is no money, nothing for the partners to do. The ASIRP began a new extensionprogram, followingthe initial stepsthat were taken in the later years of the ASSP, but, inevitably, the program was far from fully establishedwhen the 3%year project ended. StoppingBank lendingat that stagewas unfortunate, since a strongresearch aid extensionprogram is a paramount need for acceleratedagriculturalgrowth in Bangladesh. The FRMP, SDPP and HORTEX programs, although lessurgently in need of continued nurturing,would also have benefited from continuedtechnical and financialsupport. 104. The sparse rural sectorwork in the last decademay have contributed to the Bank's limited attentionto Bangladesh's rural sector.The situationis better now; papers on the rural non-farm sectorand on agriculturaltechnology were issuedrespectively in 2004 and 2005, water management has alsobeen reviewed, and there arethree ongoing studies-on agribusiness, rural finance, and a public sector expenditurereview. Work on an agricultural masterplan has also been done, in partnership with the Government. However, this impressivearray of activityappearsto be pieces of a pie rather than a comprehensiverural 42. ResidentBank stafftoldthe IEG missionthat they hadobserveda decline inrural lendingby most of the donorcommunity.And the Governmentdoes not always apply sufficient funds to the areas it has prioritized;for instance, the muchreduced funding of the agriculturalextensionprogramafterASIRP closed. strategy.What still appears missing is a thorough sector analysiswith sufficient depth and breadth to prepare an overallrural sector strategy. This could also be used to engage the Government and the donor community in a strategic and broad-ranging dialogue on sector policy and lending.
P040716 | Highway Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/480781475070685242/text/000020051-20140620070235.txt | http://documents.worldbank.org/curated/en/480781475070685242/pdf/000020051-20140620070235.pdf | There should be greater focus on capacity building for planning and programming in the road sector. The design and implementation of projects in the road sector should give equal or more weight to the issues of improving the effectiveness of the governmentâ€™s investment program than to the issue of quantity of expenditures. There appears to be a marked emphasis during project implementation on funding issues, disbursement rates and contract execution of the civil works under the project as reflected in supervision reports and letters to the Borrower. A strategic methodology is necessary to tackle the different problems retarding a shift towards modern road management. Problems with institutional capacity require a long-term program of staffing, training and career development with clearly stated short, medium and long-term targets. The subject of the cultural and generational gaps affecting the pace of reform requires an integral partnership of the public and private sectors and academia. Future road engineers and practitioners should be exposed to new ideas, develop problem-solving capacity and decision making abilities. The Bank should promote best practices in these types of partnerships and should consider incorporating the support for these activities in future operations.Flexibility in project implementation may provide unforeseen provide benefits. The decision to include the construction of the Tovuz by-pass involved greater risk in terms of the complexity of the civil works financed under the project. The result was not only a substantial improvement to the countryÂ´s road network but also to the legal and regulatory framework of land acquisition.
P040721 | Agriculture Support Services Project (ASSP) | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 1998 | 2008 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/744791474630552213/text/000020051-20140619104933.txt | http://documents.worldbank.org/curated/en/744791474630552213/pdf/000020051-20140619104933.pdf | Building on the useful lessons in the ICR four are emphasized:Projects aimed at policy and institutional reforms across multiple sectors or subsectors require coordination between multiple stakeholders and careful handling of the political process.Project design should accommodate the clientâ€™s implementation capacity and include an appropriate M&E system with a defined methodology to measure progress and impact and capture the full benefit of the projectâ€™s experience.A multi-component project covering an entire sector of the economy can be an effective tool to address issues across a range of related subsectors and thereby generate important synergies. It also provides more flexibility than a more narrowly focused project to respond more quickly and readily to unforeseen new needs and requirements, by allowing resource reallocations, shortening decision-making processes and facilitating inter-agency coordination and collaboration.Effective donor cooperation at the country and project levels significantly improves the prospects for achieving development objectives by generating positive synergies, minimizing duplication and overlap, avoiding conflicting and/or confusing advice, and facilitating mutual support across projects.]
P040721 | Agriculture Support Services Project (ASSP) | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 1998 | 2008 | 2011 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/927871468263984612/text/609460PPAR0P040e0only0900BOX361497B.txt | http://documents.worldbank.org/curated/en/927871468263984612/pdf/609460PPAR0P040e0only0900BOX361497B.pdf | 10. Lessons 10.1. The main lessons from this review are\. 1. Broad-spectrum change in a complex sector where there is limited experience can be made effective through a learning-oriented and continuously adaptive program approach aimed at establishing a platform for future development. ASSPâ€Ÿs fundamental achievement was that it explored and created a starting set of technical modalities, experience, institutions and legislation for the future development of Kyrgyzâ€Ÿs agricultural support services (para. 6.9). 2. While financial independence for providers of agricultural services is generally desirable, self-financing options need to take account of the public goods nature of some services, the special needs of poorer rural communities, and the rate at which communities and entrepreneurs can adapt to a pay-for-service environment. The ASSP/AISP programâ€Ÿs drive to achieve financially independent agricultural extension services could apply a sharper differentiation between charged (private goods) services and services for which charging would be impractical or socially costly (for instance, extension to poor and isolated communities), and for charged services, the time frame to achieve self-sufficiency should be adaptive as experience is gained and farmers and service providers respond to the changing financing environment (paras. 9.1 to 9.6). 44. As found in a World Bank survey of four ECA countries\. Legislation and procedures that appear gender neutral because they do not make a distinction between the rights of men and women may, nevertheless, affect men and women in very different ways, given how traditional gender relationships and stereotypes affect access to information, resources and power. Dudwick, N., Fock, K and Sedik.D, 2007. Land Reform and Farm Restructuring in Transition Countries. The Experience of Bulgaria, Moldova, Azerbaijan, and Kazakhstan. (World Bank, 2007). 3. Inclusion of women and poorer families in rural development can be particularly effective if based on proactive investigation of the needs of vulnerable groups, practical social and economic measures to respond to these needs, and monitoring and adapting these measures during implementation. ASSPâ€Ÿs proactive approach found ways to enhance participation of vulnerable groups across all components (paras. 9.7 to 9.10). 4. A strong M&E system is particularly important for projects that pioneer new approaches, and may need adjustment as implementation progresses. Monitorable indicators to measure achievements against the project objectives, and M&E arrangements, need to be detailed prior to project commencement including processes that enable learning from evaluation results. Had a responsive M&E system been in place for ASSP, decisions could have been more sharply focused on what activities needed adjustment and what interventions yielded strong results (paras. 2.7, 2.8 and 6.5).
P040739 | Planning for Adaptation to Global Climate Change Project (GEF) | Latin America and Caribbean | Caribbean |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1997 | 2003 | 2003 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/370731474636069373/text/000020051-20140607164759.txt | http://documents.worldbank.org/curated/en/370731474636069373/pdf/000020051-20140607164759.pdf | 1. For small developing countries, with scarce human resources and weak adaptive capacity, most effective use can be made of resources by adopting a regional approach (where possible) to meeting their obligations under multilateral environmental agreements. 2. The use of SDR denominated GEF grants introduces a currency risk that needs to be taken into account by building contingency funds in the financing plan. 3. There is a danger that the efforts promoted by GEF and the UNFCCC at large in the area of climate change may be seen by some as an opportunity to capture financial resources instead of the mechanism by which adaptation needs are understood, formulated, internalized and acted upon. 4. Political buy-in is a major implementation and sustainability issue in adaptation to climate change and can be enhanced through a highly visible regional coordination institution, multi-stakeholder committee, public awareness campaigns and involvement of a variety of relevant national ministries. 5. Data networks need strong support at the national level to perform at the level that is expected.
P040795 | Railway Restructuring (PKP) Project | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/434371474487541246/text/000020051-20140615102051.txt | http://documents.worldbank.org/curated/en/434371474487541246/pdf/000020051-20140615102051.pdf | Projects involving a major restructuring/privatization efforts, a protracted period of project preparation is worthwhile to build political will for a difficult social change. Consensus with labor unions helps in the retrenchment process and dialogue at an early stage with key stakeholders is necessary for smooth implementation of the retrenchment process. Social monitoring i.e. the monitoring of the employees post-layoff is important to evaluate the labor redundancy activities and an explicit performance indicator should be included.
P040808 | Native Forests & Protected Areas Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1997 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/953361474586243101/text/000020051-20140618090418.txt | http://documents.worldbank.org/curated/en/953361474586243101/pdf/000020051-20140618090418.pdf | Flexibility on the part of both the Bank and the borrower, while keeping their focus on overall objectives, can pay off in the face of difficult country circumstances such as fiscal crises or institutional changes. Investing time and resources in developing a sound technical, social and legal knowledge base can help underpin a sound sectoral legislative and regulatory framework. Applied research projects that are attempted on a large scale in different regions and levels should take into account local capacity to ensure acceptable quality, and if necessary should be supplemented by outside expertise.
P040808 | Native Forests & Protected Areas Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1997 | 2007 | 2011 | PPAR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/148491468207856941/text/609470PPAR0P040e0only0900BOX361497B.txt | http://documents.worldbank.org/curated/en/148491468207856941/pdf/609470PPAR0P040e0only0900BOX361497B.pdf | 6. Lessons Learned 6.1 There were four lessons learned from these two projects involving the adoption of technological advances to monitor rapidly changing environmental conditions, the blending of financial instruments to cross-subsidize different project objectives, the risks and uncertainties of experimenting with innovative land-use practices, and the importance of having well-defined and focused objectives. 6.2 The Bank should encourage natural resource project managers to take advantage of rapidly changing advances in biodiversity conservation methods and tools to complement traditional on-the-ground monitoring of indicator species surveys. These include satellite imagery and aerial photographs of habitat vegetation cover, or real-time remote monitoring devices and camera traps when conservation of specific species is the objective. The ABC Project took an approach to biodiversity monitoring that focused on surveys of key indicator species in each of the five parks established by the project. This approach turned out to be more problematic than anticipated, generating information of poor quality and reliability. Taking advantage of recent technological advances and falling costs of these new tools might result in technically complementary and cost-effective ways to assess key habitat and species. The costs involved in monitoring changing conditions over time will depend on the project objective, but whatever approach is taken should aim to provide information that is relevant for decision-making. 6.3 Satellite imagery complemented by aerial photography and light detection and ranging (LiDAR) technologies or pre-positioned camera traps are becoming increasingly prevalent and affordable for landscape conservation planning and management. In rapidly changing environments where a new dirt road or airstrip can open up access to illegal activities in large, remote natural areas with little government presence, the Bank should provide more support to project managers to work with implementing agencies and other partners to take advantage of these new technologies to obtain more accurate and real-time monitoring data. Over the past 20 years, a number of second-tier institutions such as NGOs and universities have developed very sophisticated conservation management approaches, tools, and technologies to locate and quantify species diversity and measure effective habitat management. For instance, the World Bank and WWF have developed a Monitoring Effectiveness Tracking Tool that allows project participants and managers to quickly and accurately assess the quality of perceived interventions among project beneficiaries and other stakeholders. This tool is now commonly used by GEF financed projects as a simple and cost-effective means to gauge the degree of effective management across a range of issues in protected areas. 6.4 Blending different lending instruments, such as IBRD loans with GEF grants, to achieve different forestry or natural resource management objectives can be an effective way to engage clients in addressing the full range of sector challenges they face. For example, the decision to use an IBRD loan to help Argentina increase park system revenues under the NFPA Project while preserving ecoregions of global significance under the ABC Project justified the use of a GEF grant. It was unlikely that the government would have agreed to pay the start-up costs of these new parks without GEF support given their low tourism potential. In terms of financing projects with both global and national benefits, blended packages of financial support can create the right combination of incentives needed to engage clients in a full discussion of their national forest objectives for both productive and conservation purposes. 6.5 When experimenting with new techniques or approaches to land-use practices or natural resource management, it is best to approach experimental interventions in a measured way assuming that unexpected difficulties, costs, and delays will inevitably arise. The NFPA Project conducted applied research projects on compatible land-use practices in productive landscapes while the ABC Project introduced alternative, less destructive productive activities in park buffer zones. Both took more time and effort to accomplish than expected, and results were mixed. This should be expected given the uncertainty and risk perceived by those considering adopting innovative approaches. Changing practices is not a linear or smooth process, and it requires addressing all of the incentives and concerns of the intended end-users. 6.6 For example, the Applied Research and Studies program under the NFPA Project was designed to generate a number of case studies demonstrating the costs and benefits of mixed cattle-ranching and agro-forestry practices that are more compatible with maintaining the environmental services associated with native forests in collaboration with local land-owners. Identifying capable local NGOs, universities, and government agencies to collaborate with the project in carrying out these demonstration pilots proved to be more difficult and time-consuming than expected. Secondly, land-owners were riskadverse and not as willing to experiment with novel approaches to land-use management as expected without project funding to reduce their financial risk. The results from the demonstration sites were mixed and have not been replicated on a large scale for a number of reasons. One of the reasons for the lack of replication among other landowners was that the analysis conducted at the demonstration sites focused mostly on the environmental costs and benefits of the alternatives, but did not focus enough on the economic and social aspects (that is, the costs, benefits, and risks) to the land-owners of changing commonly used practices. It is critical to take this into account when promoting novel approaches or methods that bear directly on peoplesâ€Ÿ livelihoods. 6.7 A similar experience was encountered with the sub-projects to promote sustainable productive activities in buffer zones around the new parks established by the ABC Project. These sub-projects experienced many delays and setbacks, and did not uniformly achieve the lasting changes that were sought. Some of the productive activities that were introduced to local families by project facilitators were successful and sustained; many others were not. This should be expected since experimentation involves failing some of the time. Because results are difficult to predict upfront, achieving quantified targets can be problematic. These risks should be carefully assessed and mitigated in project design and appraisal. 6.8 The more focused an objective or target audience is defined, the more likely it is to be achieved. For example, one objective of the NFPA Project was to increase the environmentally sustainable level of tourism in four selected national parks. Increasing tourist visits and the revenues generated by them in those four parks was achieved by improving the capacity of APN to manage and protect those parks, and by enhancing the experiences of visitorsâ€Ÿ by improving infrastructure and concession services in the parks. Related to this lesson was the observation that more tangible and measurable activities, such as mortar and bricks types of infrastructure interventions, were more often achieved than were the softer institutional-strengthening or behaviorchanging activities in both projects. It is harder to change organizational cultures or individualsâ€Ÿ behaviors than it is to get them to change specific analytic techniques or to modernize facilities and equipment. The more an intervention can focus on a specific client or place, the more likely it is to be successful. For instance, it was found that the management plans developed for the five individual parks under the ABC Project were better utilized in setting up the management of those parks than the system-wide strategic plan to modernize APN by creating a Vision for a Reformed APN under the NFPA Project.
P040818 | DURRES PORT | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Transport | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Highly Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/546741475074948951/text/000020051-20140613063850.txt | http://documents.worldbank.org/curated/en/546741475074948951/pdf/000020051-20140613063850.pdf | Organizational restructuring projects should not be planned in detail far in advance. During project preparation, what is important is to assess the Government commitment to the reforms and agree on the basic principles of such reforms. Supervision provides an opportunity for more detailed work on the project's policy and institutional components. Also, supervision missions need to assist in continually building support for the necessary reforms at the Government level. The Bank should ensure that sound feasibility studies have been undertaken with solid cost estimates for the financing of important civil works. In cases where the Bank is funding multiple projects in the same jurisdiction, the Bank needs to establish an internal coordinating committee to avoid conflict. In the case of the Port of Durres, the Bank had funded two projects under different Ministries. In one case, an agreement was reached between the Ministry of Transport and the Agricultural Ministry to tear down structures built under this project.
P040818 | DURRES PORT | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Transport | IDA | IPF | 1998 | 2005 | 2007 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Highly Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/857311468767440222/text/31626.txt | http://documents.worldbank.org/curated/en/857311468767440222/pdf/31626.pdf | 5. Outlook and Lessons 44. The assessed projects were prepared and implemented during a time o f major political and economic changes in Albania. The projects successfully addressed urgent rehabilitation needs to ensure the continuity o f the vital water supply and sewerage services with the main focus on the rehabilitation o f the existing facilities. Performance was less successful on institutional issues although this improved under the Urgent Rehabilitation project. Generally, institutional objectives were too optimistic compared with a realistic timeframe to build a constituency and accomplish fundamental reforms. 45. A comprehensive approach to provision of water supplies i s required to address competition for scarce water resources. Thus, sustainability o f Durres water supply depends very not only on rehabilitating water infrastructure within the urban areas but also on addressing and regulating the water supply needs of adjacent rural areas. l4 46. Since the Durres project, however, the government's water sector reform has gathered momentum and i s developing along the principles outlined in the Policy Letter o f 2000. Specifically, government agreed to strengthen i t s stewardship and management o f water resources and water quality through appropriate laws and regulation, and devolve investment and decision-making on water and wastewater services to local governments. Government also agreed that water and wastewater utilities should become corporatized and autonomous entities operating o n a commercial basis, and that water and wastewater tariffs should be allow to increase to cover all operating costs. T o facilitate commercialization, private sector participation would be allowed, initially on management or lease contracts. 14. The Mayor o f Durres notes (Annex C)\. Durres water supply system i s composed by a main transmission o f 45km long up to the distribution reservoir. There are connected around 40 villages along this main transmission. These villages do not have correct distribution networks, which make difficult the improvement o f the water management in these areas. Representing only 40% o f the population served, the rural area i s consuming (and misusing) 60% o f the water. I t remains available for Durres city a quantity o f the water corresponding to 70lldaylcapita. 47. The Council o f Ministers formally adopted a National Water Supply and Sanitation Strategy and a Rural Water and Sanitation Strategy in 2003 that translates the Policy Letter into Albanian legislation. Within the context o f the N W S S S , govemment has defined an action plan to improve the performance o f water utilities. The general Directorate o f Water Supply and Sewerage will no longer have a service delivery function and instead focus on monitoring sector performance, defining capital and management needs and improving public service sector performance. Under the L a w on Organization and Function o f Local Government, ownership o f water supply and sewerage infrastructure i s transferred to local governments and with i t the powers to set tariffs and manage utilities. A Water Utility Regulatory Commission has been set up to license water supply utilities and provide a methodology for transparent setting o f tariffs. 48. New water tariff proposals were cleared by the Municipal Councils for Fier and Lezha in mid-2004 and submitted to the Water Regulatory Entity for final approval. In Dunes and Saranda the issue o f tariff increases has become politicized, as has the independence o f the utilities from municipal interference. An ongoing public awareness program may help to mitigate some o f these problems which are well-known problems in the transition to private and commercial management. 49. This project performance assessment supports three lessons for broader application\. Lesson 1. I t is important to exercise flexibility when a project faces implementation problems in a seriously difJicult situation. Under these two projects, the Bank was flexible enough to terminate the first project and quickly move on to the next step, an interim operation to ensure the continuation o f urgently needed rehabilitation o f existing service facilities. With this arrangement, the Bank bought more time to prepare a firmer base for fundamental sector reforms. At the same time, this move made i t possible to cope with even more urgent issues arising from the crisis caused by the influx o f refugees from Kosovo. Lesson 2. Sequencing o f demanding reform activities and major rehabilitation efforts, as well as the timeframe for their implementation, need to be adequately analyzed to take full account ofpractical priorities and the available implementation capacity. Too many demanding activities at one time may heavily over-tax the implementation capacity o f utilities moving out o f the public sector a thorough evaluation o f local capacity i s essential. The Bank also needs to take the time to ensure a full understanding o f the impact o f reforms and the real political commitment among stakeholders to accomplish them. In the evaluated projects, the need for institutional reform only became clear to many stakeholders when investment in infrastructure improvement alone failed to significantly improve service delivery and operational indicators. Thus the ongoing Municipal Water and Wastewater Project, Credit 37300 approved in March 2003, has been able to give a much greater prominence to capacity building and institutional reform. Lesson 3. Establishment o f a benchmarking system as early as possible in the sector support cycle is important for facilitating appropriate monitoring of progress and evaluation of impact of activities. The Urgent Rehabilitation project initiated the benchmarking o f sector activities and it was not a moment too early. Reliable data on sector and project performance i s enabling, for the first time, comparison and analysis o f factors affecting utility performance. More comprehensive operational data will facilitate the introduction and scaling up o f PSP in more utilities in Albania.
P040824 | SV COMPETITIVENESS ENHA | Latin America and Caribbean | El Salvador | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/942411474659387353/text/000020051-20140613033214.txt | http://documents.worldbank.org/curated/en/942411474659387353/pdf/000020051-20140613033214.pdf | In the area of competitiveness, the most important change may be in the mentality of firms -- with respect to exports, quality and productivity, and innovation.Institutional change takes time, and projects that have substantial institutional objectives may benefit from longer timeframes and greater flexibility.Building consensus -- both between the public sector and the private sector, and within the public sector, among different government agencies -- is critical to the success of this type of project.
P040826 | PROV.BANK PRIV. | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1995 | 1997 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/822211474944726622/text/000020051-20140526224305.txt | http://documents.worldbank.org/curated/en/822211474944726622/pdf/000020051-20140526224305.pdf | In a bank privatization project, use of a Privatization Trust Fund, which extends loans to provinces to purchase less attractive assets of privatizing banks, can greatly facilitate progress.In privatizing banks that are of lower quality, in order to create an entity attractive to buyers, it is necessary to apply significant resources to "buy out" or otherwise dispose of poor quality assets.In bank privatization, residual asset recovery can be a major problem; the most promising approach is to begin as early as possible to inventory assets and evaluate their quality, and involve the private sector to the greatest feasible extent.
P040830 | Technical Assistance Project in Support of Enterprise and Financial Sector Reform | Europe and Central Asia | Croatia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2000 | 2001 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/980501474510841502/text/000020051-20140529073605.txt | http://documents.worldbank.org/curated/en/980501474510841502/pdf/000020051-20140529073605.pdf | Timely provision of analytic and consulting advice can substantially help with enterprise restructuring and reformFlexibility in project design was exceedingly important in achieving a positive outcomeProject management arrangements were innovative in that they gave several implementing agencies responsibility for executing their own components. This avoided bottlenecks and overload of the principal PIU.
P040830 | Technical Assistance Project in Support of Enterprise and Financial Sector Reform | Europe and Central Asia | Croatia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2000 | 2005 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977801468770733906/text/28600.txt | http://documents.worldbank.org/curated/en/977801468770733906/pdf/28600.pdf | 3. SummaryFindingsandLessons e Easeo f entry andexit, hardbudgetaryconstraints, andchecks andbalancesto ensurecorporateaccountability arenecessarycomplementsof successful privatization. e Prolongedrehabilitationprocedureswhich leaveexistingbankmanagementin control cansignificantly increasethe final cost o fbank bailouts. e The experiencewiththe EFSALsuggests that, althoughadditional delays maybe incurred andcosts increased, onbalancelong-run developmentbenefits are likely to be enhancedbycancelingprojects withmajor design flaws andaddressingthe reformneedswith a superior instrument. e Development of domestic capital markets makes little sense, untilfimdamental problems ofprivatization andrestructuringhavebeenresolved. e Lack of sound, transparent, andpredictablejudicial enforcement is amajor impedimentto privatization andthe launchofcapitalmarkets. e Mass voucherprivatization seldomworks, ifchecks andbalanceson corporate governanceare not inplace andfunctioning properly.
P040858 | EG - SOHAG Rural Development | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/767281475085089856/text/000020051-20140619110617.txt | http://documents.worldbank.org/curated/en/767281475085089856/pdf/000020051-20140619110617.pdf | There should be one agency in charge of implementation in order to keep lines of responsibility clear and to facilitate coordination of components.The establishment of appropriate M&E targets enables the project team to highlight problems and recommend timely actions to improve performance. The success of a decentralization program depends to a large extent on the commitment of the central government to allocate funds to the local governments (in the case of this project, Governorate of Sohag).
P040904 | BANK REFORM | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1996 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/546241474659281197/text/000020051-20140526224356.txt | http://documents.worldbank.org/curated/en/546241474659281197/pdf/000020051-20140526224356.pdf | In a bank privatization project, a strong selection bias may occur whereby banks that perform poorly may be more likely to seek Fund support.In a banking sector consolidation project, if a goal is to utilize stronger banks as acquirers, it might be more effective to have flexible criteria so that stronger banks can obtain better terms in obtaining funding.
P040907 | Energy Sector Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2001 | 2014 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/813571468188665447/text/ICRR14796-P040907-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/813571468188665447/pdf/ICRR14796-P040907-Box393228B-PUBLIC.pdf | Realistic capacity assessment is crucial during Project preparation at all levels of implementation ranging from government agencies through implementing agencies to the grassroots levels. In this Project, the insufficient capacity assessment across the board substantially contributed to the lengthy Project implementation (e.g., overly complex contracts were applied that exceeded contract management capability; implementation capacity of aimags were systematically overrated and the availability of counterpart funding was not properly verified upfront). Early discussions between the government agencies and the Bank are essential in defining the responsible framework and approval authorities. Some tentativeness in this respect contributed to misunderstandings between the parties and implementation delays in this project Technical Assistance targeting sector reforms should be carefully selected and sequenced reflecting the (i) countryâ€™s initial standing along the evolutionary continuum of reform measures; and (ii) governmentâ€™s political readiness to carry out sensitive sector reforms. This Project, especially with respect to tariff reforms, failed to fully factor in both constraints under the TA component.
P040909 | H. INSURANCE REFORM | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | DPF | 1996 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/292771474666422896/text/000020051-20140526220607.txt | http://documents.worldbank.org/curated/en/292771474666422896/pdf/000020051-20140526220607.pdf | The project provides a number of important lessons both for health insurance reform in middle income countries, and health adjustment lending:In designing adjustment loans, the focus should be on negotiating conditions based on desired outcomes of reform rather than specific restructuring measures, in order to allow flexibility in planning and implementation. It is clear that in major social sector reforms, conditions cannot simply be imposed by the Bank.Thorough analytic work prior to project preparation was essential to establish clear and achievable program goals, The parallel technical assistance loan played a critical role in helping the Obras to restructure in response to the reforms;Monitoring and impact evaluation are critical to assess whether the objectives were being achieved, and to make appropriate adjustments if necessary -- the project appropriately emphasized developing local capacity in data collection;Major reforms must be built on broad- multi-agency support, not just narrow sectoral backing, require high level political support to ensure implementation and avoid political backsliding;In any complex reform, the "law of unintended consequences" inevitably applies, requiring flexible responses by the Bank and borrower, as well as willingness to engage in appropriate follow on activities; The Bank and government appropriately recognized that the reforms would be a long-term and politically contentious process, and deliberately chose to focus on a few key initial steps, while keeping in mind the long-term reform vision.
P040960 | Ozone Depleting Substances (ODS) Phaseout Project | Europe and Central Asia | Slovenia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1996 | 1998 | 1999 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/563571474490507347/text/000020051-20140521033645.txt | http://documents.worldbank.org/curated/en/563571474490507347/pdf/000020051-20140521033645.pdf | As pointed out by the Borrower, regional workshops on ODS phaseout sponsored by project made a significant contribution to its success. The exchange of experiences and lessons learned with other countries (e.g., Czech Republic, Hungary) with policy issues and incentives were helpful for addressing problems that emerged, and contributed to the design of the 3-R scheme that is being implemented.
P040975 | Land Development Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/327711474634726692/text/000020051-20140613053847.txt | http://documents.worldbank.org/curated/en/327711474634726692/pdf/000020051-20140613053847.pdf | The project experience revealed the limits of the community-based approach to broader urban development and management issues. To scale up a project's institutional development impact, local government capacity building needs consolidating while efforts continue to enhance community participation. Municipalities often need technical assistance on all fronts of municipal operations such as resource management, infrastructure planning and operation, social service delivery and urban management, community-based infrastructure development to broader municipal operations. Community participation should not be taken as a pretext for ignoring municipal capacity building. The two processes need to go hand-in-hand.Urban infrastructure investment plans need to consider primary as well as secondary networks in order to effectively address deficiencies. Improving primary networks requires the coordinated effort of central government and donors, as well as municipalities. With some cities tripling their population in less than ten years, there are urgent needs for massive investments in solid waste and sewerage to prevent irreversible environmental damage.Special attention should be given to integrating youth group and social infrastructure--such as, schools, kindergarten, parks and community centers--in municipal investments, to ensure the full participation of young people and women in the project benefits.Urban land tenure regularization and titling remains a major issue beyond the jurisdiction of municipalities alone. Residents value secure titles very highly. For effective development assistance in these areas, separate projects specifically focused upon these issues might be necessary. In order not to lose the skills and experience accumulated by project management, it is important to incorporate the staff of the project coordination unit into the responsible ministry.
P040981 | Second Subic Bay Freeport Project | East Asia and Pacific | Philippines | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/432451474851439480/text/000020051-20140612130752.txt | http://documents.worldbank.org/curated/en/432451474851439480/pdf/000020051-20140612130752.pdf | When a project experiences a crisis in leadership or problems related to political issues, the Bank should critically re-assess the situation and call for either a time bound action plan or a definite deadline for suspension or cancellation of the project.Future projects for freeports and economic zones should give the highest priority to institutional strengthening and capacity building, since these are the critical success factors.In any major project it is important to ensure that a full-time competent and experienced project manager is in place before work commences.
P040985 | Poverty Alleviation Microfinance | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/240761475085055518/text/000020051-20140602110822.txt | http://documents.worldbank.org/curated/en/240761475085055518/pdf/000020051-20140602110822.pdf | Participatory approach to project preparation benefits the design of the overall project.Strong institutional development efforts for involved partner organizations can contribute to overall success of microfinance programs.Ability of the apex NGO (PKSF in this case) to maintain strong ownership and keep itself outside political influences helps to earn a good reputation and the respect of stakeholders.
P040990 | CV-Energy & Water SIL (FY99) | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 1999 | 2009 | 2010 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/405271475087131108/text/000146597-20140619170914.txt | http://documents.worldbank.org/curated/en/405271475087131108/pdf/000146597-20140619170914.pdf | Laxity of supervision on the scale shown in this project, although fortunately very rare, calls for a strong and determined management response, The ICR reports that management "suggested" remedies such as including the country economist in supervision missions and a quality assessment of supervision, but that these were not taken up. When faced with such a situation, decisive corrective action by sector, country and (if necessary) Regional management is called for. Given the complexities and risks involved in utility privatization, full consideration should be given to other means of achieving reform goals.Experience has shown that it is critically important to have the appropriate legal and regulatory framework in place before attempting to privatize utilities. Many ingredients for successful utility regulation are sector specific. Strong and sustained input from sector specialists is necessary to support the reform process and to build capacity. The time required for establishing an effective regulatory framework is normally long, especially when starting from scratch.Privatizing a combined water and power utility is especially complex and to be avoided, whenever possible, by splitting the entity before attempting privatization.Even where there is excellent potential for wind-generated power and other renewable energy sources, as in Cape Verde, this cannot be successfully developed in the absence of an appropriate policy and regulatory framework. Inter alia, attention needs to be paid to demand-side issues such as affordability and incentives to undertake the necessary investments in RES systems.Utility reform needs to combine a robust and realistic tariff adjustment mechanism with affordability for poorer consumers.
P041150 | Ghana:VILLAGE INFRASTRUCTURE | Western and Central Africa | Ghana | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/838981474495944131/text/000020051-20140613035340.txt | http://documents.worldbank.org/curated/en/838981474495944131/pdf/000020051-20140613035340.pdf | M&E indicators should be realistic and appropriate. In designing an M&E framework for a community demand driven project, setting performance indicators based on achieving certain types of micro-projects (such as number of bore-holes constructed) may not be appropriate. Such an approach risks distorting the demand-driven principle of the project, resulting in micro-projects which may not reflect community priorities. Community infrastructure projects should be accompanied by capacity building and training for beneficiaries, to ensure optimal use of the infrastructure provided. In particular, beneficiaries may need to be trained on how to carry out maintenance, which would contribute to the sustainable use of the infrastructure. Capacity building and training components should be accompanied by space and opportunity to utilize the knowledge and skills. Training programs provided through the project are estimated to have reached close to 13,000 communities, but the extremely large reach of this component was not matched by the project's other components which provided the space to use these skills. Often, capacity is better created through a learning-by-doing approach than by training programs alone.
P041150 | Ghana:VILLAGE INFRASTRUCTURE | Western and Central Africa | Ghana | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2004 | 2007 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/695021468030674414/text/36597.txt | http://documents.worldbank.org/curated/en/695021468030674414/pdf/36597.pdf | Lessons for the Future 94. All o fthe principal lessonsfrom this performance assessmentrelate directly or indirectly to Ghana's decentralization program; from the apex organizations and local governments to the local communities. While all three projects are inthe water sector, the lessons are inmost cases not only relevantto water. They provide lessons for other sectors providing local public services inGhana, and for decentralization programs inother countries as well. 95. All three projects werepath-makers. Underthe UESP a start was madetowards decentralization inthe urbanenvironmental sanitation sector. The CWSP-2 andthe VIP took . decentralization further, succeeding intransferring implementationto the DAs, and then to rural communities. The CWSP-2 andthe VIP decentralized well before nearly all other sectors inthe country. The CWSP-2, the VIP and, to a lesser extent, the UESPhave shown that decentralization can be successful. Initselfthis i s important as reassuranceto individuals andinstitutionsthat are skeptical ofdecentralization. These projects provide a rich experience as concerns their specific implementationmodalities, mostly inbest practice, but also with lessons stemming from mistakes or problems encountered. 96. The lessonsfall under three broad areas. First, from the projects' experiences there are a set of lessonsrelatingto what is needed inthe institutionaland policy environment. Second, all o f the projects found that major capacitybuildingwas needed. Third, sustainabilitywas amajor issue, andneededto be addressedas a priority. Table 5 summarizes the points Co~ered.~' 1. ANENABLING INSTITUTIONALAND POLICY ENVIRONMENT 0 Long-termcommitment\.Decentralizationis a long-termprocess, andneeds consistent and sustained support inorder to succeed. This has beenthe case inGhana. The Government's interest indecentralization started to develop inthe early 199Os, well before the three projects commenced. The Bank has consistently supportedthe 49. It shouldbe emphasizedhere that the points beloware the practicallessons directlyderived fromthe three projects reviewed. While the lessons are wide-ranging, they are not intendedto providecomprehensive coverageofall issuesrelatedto decentralizationand communitydrivendevelopment. decentralization agenda, starting inthe mid-199Os,and the 2004 CAS emphasizes continued support. A demand-drivenapproachincludingbeneficiarycontributions\.The CWSP-2 and the VIP were implementedthrough a demand-driven approach requiringDAs and the communities to select themselves as project participants. Inparticular, they requiredanup-front financial contribution from the DA and community. The project experience has found this to be important\. for DAs to demonstrate their commitment; for creating community ownership o fthe facilities; andto helpreduce the cycle o f dependency (expecting everything fiee) which hastendedto prevail inGhana's rural societies. 0 Agreed institutionalroles\. These needto be clear andagreed. The VIP involveda numberofdifferent ministriesandagencies. Their roles and specific responsibilities were clearly defined. This was thenformally agreed inMemorandums of UnderstandingbetweenRICUandeach agency. The projects also established the responsibilities o f the PU, CWSA or RICU relative to those o fthe MASor DAs.For thetwo ruralprojects (the CWSP-2 andthe VIP), clear rolesbetweenthe DAsandthe communities also hadto be defined andwidely understood. 0 Clear andwidely distributedrules of the game\. Understandingwhat to do and how to do it is key many new actors are involved andthey needto operate effectively. The Pxoject Operation Manuals (POMs) for boththe VIP andthe CWSP- 2 were clear, detailed, anddistributed to all staffand agencies with implementation roles. Hence, there was sound guidance and minimalambiguity at all levels. The CWSP-2 went further. After the POM (primarily for CWSA staff), there was thena D O M(District Operation Manual) for the DAs, andthena C O M (Community OperationManual). Thus, the DAs and Communities had focused material specifically needed for them. 0 Harmonizedimplementationmodalities\.The borehole programs underthe CWSP- 2 andthe VIP commenced a harmonizationprocess, bothamong donors andamong differentgovernment departments. The progress made, while only partial, hasbegun to exempli@ the advantages o fharmonized implementation. Previously, eachdonor tended to have its own implementationmodalities, andprojects even overlapped geographically. This confusedthe DAs and communities. Progressively, donors and government have been convergingtowards a single implementation model; for instance, for boreholes, essentially the CWSA model. This inturnwill facilitate further harmonizationto programapproaches, withcombined and simplified donor assistance. 0 Minimalpoliticalinterference\. Caseswhere localpolitical interests have influenced borehole committee membership have beenreported, which would not necessarily enhancethe committees' social cohesion and capacity. Processesto minimize local politicalinfluences would be desirable. 2. A MAJOR DRIVETOBUILDIMPLEMENTATIONCAPACITY 0 Software, and software first\. Capacity buildingshould be emphasized as muchas or more than infrastructure, and most capacity buildingshould be done up-front. The CWSP-2 andthe VIP emphasizedsohare (training, extension, technical assistance) for capacity building.Further, for every DA and every community, the capacity buildingwas done before the infrastructure. For communities, completionofthe requiredtraining andformation oftheir committees were mandatory before any construction. These two projects, andthe UESP, providedsubstantial training for the DAsor MASandfor the communities inthe case o f the rural projects. 0 Massive training\. Trainingwas massive. For the two CDD projects, training covered all actors\. communities, DAs, andprivate mechanics and suppliers o f spare parts. The UESPhadintensivetraining for the MAS'Waste Management Departments.The scale ofthe training considerednecessaryfor the CDD projects bears emphasizing for other decentralizationprojects. The CWSP-2 trained over 3800 communities, groups or individuals. The VIP, covering all o f Ghana's districts andrequiringa greater rangeo f skillneeds, hadsome 5800suchtrainings. 0 Strong central coordination\. Strong central coordination and guidance is necessary. Thevery natureofdecentralization meansthat manyinstitutions haveto quickly master their new responsibilities. Eachproject hada strong coordination unit\.the PUfor the UESP, RTCU for the VIP and CWSA for the CWSP-2. Eachmanaged to provide the MASor DAswiththe necessarysignificant training andtechnical assistance. 0 M&Eto facilitate programadaptation\. Capacity to assessandprovidefeedbackto managementonproject impacts is needed. M&E for all three programs was not sufficiently developed duringproject implementation to inform management onproject impacts andissues. Thus, had CWSA's M&Ebeenstrong, issues such as the needor otherwise for follow-on supportto communities would be clearly known, whereas, even now, this remains a question. Underthe UESP, the PUandmunicipal WMDs, could have hadmonitoringsystems providingregular reports onthe state o f maintenance and funds. This mighthave helpedbetterdecision makingbythe municipalities regardingboththe allocation o f funds andthe needfor increased municipal revenues. 0 Development of private sector service providers\. The CWSP inparticular included trainingofinterestedindividuals to beprivate mechanics, andfacilitated the development of a network of shopkeepersto stock andsell spare parts for boreholes. Over 650 private individuals or entities were trained. These included\. drillers, contractors, consultants, mechanicsandother privateparties where capacity enhancementwas neededto foster the development o fa private sector support network. 0 Includinghygiene education\. The CWSP-2 (inparticular) andthe UESP included education inhygiene practices. For the CWSP-2 ,this was a fully integratedpart o fthe trainingofthe WATSANs. A healthspecialist was included ineachDWST's extension team (the other two were anengineeranda CDD specialist). Significant improvements incommunityhealthwerereportedbyseveralWATSANs visited. Hygieneeducation initiativesby an urbanschool were considered important. Hygiene education and extension i s anatural concomitant inwater supply and sanitation programs. The costs of includinghygieneeducation are usually modest relative to thebenefits. 3. MAKING SUSTAINABILITY A CENTRAL FOCUS 0 Prioritizingrevenuesfor O&M financing\. For the urbanwater and sanitation sector O&M fundingneedsto be atop priority. The UESPwas well designedand implemented from anengineering perspective, butthe primary issue for the U W S S sector-inadequaterevenues andfinancial allocations for O&M, and, consequently, inadequate O&M -was not tackled. Itwould havebeenbetter to have placed as much, or even more, attention to the fundinglO8zh.lissue as to the physicalworks. Creatingself-sustaining support services\. This i s importantto ultimate success. The CWSPmodelisparticularlyinteresting. Three needswere identifiedto provide longterm support to borehole communitiesunder a demand-driven approach\. (i) availability o fspareparts, (ii)availability o fprivate mechanics, and (iii) availability o ftechnical assistanceon a demand basis. The CWSP-2's promotiono ftheprivate sector rather thangovernment asthe long-termproviderto communities ofspareparts and mechanics, is more likelyto be sustained over time than services reliant on government. Follow-on training for localgovernments\. Giventhe chronic Ghanaianproblemo f turn-over of govemment staff, the follow-on project to the VIP and CWSP-2-the CBRDP will needto provide refresher trainingfor the DAs as well as training for the CBRDP's specific implementationneeds, The sameneedispresent for the UESP, thoughthe follow-on UESP-2maybe able to providethe necessarytrainingfor the W M D S . 0 A possibleneed for follow-on training for communities\. Neitherthe CWSP-2nor theVIP, northe designofthe commencingfollow-on project, CBRDP; included continuedtechnical support (extension visits, refresher training) to the community organizations. At thisjuncture, it is not clear whether the communities' social cohesion andfinancial strengthsare decliningor remainingstrong. Morefieldassessmentsare neededto assess on-the-ground realities andwhat may or may not beneededto address the situationthat is found. Table 5. Some Key Features for SuccessfulDecentralization An Enabling Institutional and Policy Environment\. Long-term commitmentto decentralizeddevelopment A demand driven approach including beneficiary contributions Agreed institutionalroles Clear and widely distributedrules of the game Harmonized implementationmodalities Minimal political interference A Major Drive to BuildImplementation Capacity\. Software, and softwarefirst Massive training Strong centralcoordination M&Eto facilitate programadaptation Enabling developmentof private sector service providers Includinghygieneeducation(forWSS projects) Making Sustainability a Central Focus\. Prioritizingrevenuesfor O&Mfinancing Creatingself-sustainingsupportservices Follow-ontrainingfor localgovernments A possibleneedfor follow-on training for communities
P041199 | RY SOCIAL FUND DEVPT | Middle East and North Africa | Yemen, Republic of | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/371601474896315186/text/000020051-20140612093746.txt | http://documents.worldbank.org/curated/en/371601474896315186/pdf/000020051-20140612093746.pdf | Based on the ICR, key lessons include:Building adequate cooperation between government agencies needs considerable attention and cannot be taken for granted. There is need to give particular attention to the incentives for cooperation on both sides. Development of an efficient monitoring and evaluation system is crucial in such an operation. This is so not only for assessing outcomes and impacts but for making efficient mid-course corrections, as and when required. The building of adequate community participation requires time, resources and explicit attention to incentives for the stakeholders--factors that need to be explicitly recognized and built into a project. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured. In projects with a clear poverty alleviation objective, performance indicators should also be framed in terms of poverty alleviation. This should be backed up in design by a monitoring and evaluation system capable of measuring poverty impact. In projects where it is difficult to calculate a rate of return ex-ante, at least such a calculation should be attempted ex-post to get an accurate assessment of efficiency.
P041261 | SAC | Europe and Central Asia | Azerbaijan | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2001 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/119711474503243070/text/000020051-20140529204851.txt | http://documents.worldbank.org/curated/en/119711474503243070/pdf/000020051-20140529204851.pdf | The broad lesson is that satisfying the agreed tranche release conditions does not ensure that the objectives are met. The ICR notes that the sustainability of the reform may be fragile and the Government ownership of the objectives were weak.
P041264 | INTEGRATED WATERSHED DEVELOPMENT PROJECT | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2006 | 2006 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/495321475077001532/text/000020051-20140614183827.txt | http://documents.worldbank.org/curated/en/495321475077001532/pdf/000020051-20140614183827.pdf | The ICR has extracted a number of relevant lessons from the experience with this project.(1) Involving local communities in the planning and implementation of natural resource management interventions improves outcomes by enhancing ownership, by accessing exclusive local knowledge and information, and by better integrating the conservation goals with local livelihood concerns.(2) That having been said, mobilizing local communities and building their capacity in support of conservation and development objectives takes time. But such efforts are as critical as external finance in achieving project objectives and work powerfully when matured.(3) Since many conservation measures in watershed projects typically benefit landowners, it is also important to have pro-poor interventions targeting the weaker and marginal segments of the community in order to increase their stake in the project as well.(4) For projects with a demand-driven planning and implementation modality and with multiple -- conservation and productivity -- objectives, it is essential to have a well planned and executed monitoring and evaluation framework with relevant output and outcome indicators, especially to help assess the trade-offs involved in large allocational changes across project components and to help project staff and the beneficiaries make more informed choices consistent with both conservation and development.
P041264 | INTEGRATED WATERSHED DEVELOPMENT PROJECT | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2006 | 2011 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/776591468043460343/text/610650PPAR0Box00210201100INDIA0PPAR.txt | http://documents.worldbank.org/curated/en/776591468043460343/pdf/610650PPAR0Box00210201100INDIA0PPAR.pdf | 1. Findings and Lessons Watersheds and Forestsâ€”A Unified Perspective 1.1 This report assesses a mix of Bank-supported activities intended to further watershed development and improve forest management. A handy portmanteau definition of watershed development is as follows\. â€•A watershed may be defined as a geographic area that drains to a common point. Integrated watershed development is generally understood as an approach that combines soil and water conservation with social and institutional development, in addition to pursuing a broad range of activities that meet the felt needs of communities across many sectors, such as rural access, water supply, and income-generating activities.â€–1 To clarify, the watershed projects examined here are typical of the period in which they were developed, emphasizing agricultural and community-driven development rather than water management. With respect to forests, the Andhra Pradesh project that is assessed in this report involved an approach (â€•community forest managementâ€–) that represented the evolution of an earlier model (â€•joint forest managementâ€–) that was conservation rather than exploitation-centered\. both â€•communityâ€– and â€•jointâ€– models were based on a partnership between communities and state government forest departments, the purpose of which was to regenerate degraded forestland formally assigned to the forest department but, to varying degrees, claimed and exploited by the communities living on the forest fringe. 1.2 Assessing watershed development and forest interventions side-by-side is no idle juxtaposition. Obviously, all forests fall within watersheds so there is some merit to having a natural resources management strategy that includes both. The need for an integrated approach to forests and watersheds was one of the recommendations of IEG's 2000 study of Bank support to forestry in India.2 In the past this has been problematic because governments in the individual states of India have assigned watershed development and forestry to separate departments with separate programs that are not closely coordinated. The Forest Departments in the various states have legal claim to large tractsâ€”averaging one-quarter of the territory nationwide. If Forest Departments do not cooperate with the agencies leading watershed development initiatives the comprehensive (â€•ridge to valleyâ€–) approach that is now the prevailing paradigm for watershed development will be compromised and the scope for better husbandry of natural resources will be restricted. 1.3 With the push to decentralize, the logic of integration has become more compelling\. the various levels of local government (the Panchayati Raj Institutions) now have considerable resources owing to transfers they receive from the central government (the â€•centrally sponsored schemesâ€–â€”most importantly the National Rural Employment Guarantee Scheme that has operated since 2006).3 Throughout India local governments and village-level beneficiary organizations engage in participatory planning exercises that 1 World Bank 2005\.1. 2 IEG 2000b\. 54. 3 Government of India 2008. 2 embrace both forests and watersheds and have to decide what share of resources to give to these interventions relative to other initiatives. 1.4 In designing watershed and forest interventions there is a common theme. Both types of project are beset by problems of property rightsâ€”rights that have been incompletely specified or questionably assigned or are simply missing. Managing watersheds, and in particular the forests and commons that are an integral part of them, is complicated by the contested usufruct of the various forms of â€•non-private landâ€– (where the rights of village communities are poorly defined), the over extension of the state's forest domain (where the legitimacy of the rights assigned may be questioned) and the poverty of landless peoples and nomads (for whom property rights are largely absent). The success of many watershed development and forest management projects has been qualified by the failure by the Government of India to settle these unresolved issues of property rights. Summing up, decentralized institution building and the resolution of property rights conflictsâ€”these are the unifying themes that will be examined in this assessment of Bank support to watershed and forest interventions over the past decade or so. 1.5 Closely related to the theme of property rights is the concept of externalities. â€•An externality exists whenever one individual's actions affect the well-being of another individualâ€”whether for the better or for the worseâ€”in ways that need not be paid for according to the existing definition of property rights in the society.â€–4 In economics, an externality (or transaction spillover) is a cost or benefit, not transmitted through prices, incurred by a party who did not agree to the action causing the cost or benefit. A benefit in this case is called a positive externality or external benefit, while a cost is called a negative externality or external cost. In the case of watersheds, for example, one group of people may cut trees on the upper slopes leading to soil erosion and the silting up of reservoirs on the lower slopes that are used by the community at large or owned by private farmers (a negative externality); alternatively, steps taken to protect forests on the upper slopes will help to reduce siltation generating a positive externality from the viewpoint of users of reservoirs on the lower slopes. 1.6 Other externalities are generated by forest management. For example, measures taken to strengthen the protection of state-controlled forest land may lead to a rise in the number of wild animals living in the reserve forest; these animals may damage crops on land operated by farmers on the forest fringe (â€•rogue elephantsâ€– are a significant negative externality from the standpoint of villagers in India). One way to contain negative externalities is to develop mechanisms that oblige the generators of the damage to shoulder the cost that they are causing society at large (an approach referred to as â€•internalizing the externalityâ€–). If property rights are clarified (for example, if communities are given legal rights to forestland) the scope for generating externalities and for internalizing them may increase. But if property rights remain fuzzy it will be impossible to fully internalize externalities, even if communities are paid for the environmental services they provide.5 At the same time, population pressure on land is 4 â€•A Glossary of Political Economy Termsâ€– website. 5 See footnote 30 below on challenges facing a Payment for Environmental Services scheme in the Himalayas. 3 such that enforcing rights to land and ensuring adequate stewardship of natural resources will remain a challenge however much the tenure regime is clarified. 1.7 This report assesses two watershed development projects and one forestry project. The objectives of the watershed development projects in the Shivalik Hills and in Karnataka were similar\. both sought to improve the productive potential of selected watersheds and to build the institutions needed for improved management of the natural resource base, including community organizations. The objective of the Andhra Pradesh Community Forestry Management Project was to reduce rural poverty through improved forest management with community participation. This report also evaluates two sector analytic studies, one devoted to examining how to improve management of watershed externalities and the other addressing ways to improve the livelihoods of forestdependent communities. The objective of the externalities study was to understand the nature of externalities generated within watersheds and the ways in which these have been internalized in good practice' management. The forest study sought to analyze ways in which community-based forest management could be strengthened to improve livelihoods and reduce poverty. Figure 1\. Indiaâ€”Number of Bank Activities Approved Per Five-Year Period 6 5 4 3 2 Forestry Watershed development 1 0 Source\. Annex B. â€•Activitiesâ€– refers to sector work as well as projects 4 Changing Levels of Bank Support for Watersheds and Forests 1.8 In India, the World Bank has supported 11 watershed development projects since FY1981 for a total commitment of US$808 million. Eighteen forest projects have been supported since FY1976, totaling US$941 million in commitments. All the projects are listed in Annex B, together with an indication of which projects were subject to fieldbased assessment by IEG. 1.9 There were two booms in support to forestry, each associated with a particular Indian policy initiative\. â€•social forestryâ€– in FY1979-FY1985 and â€•joint forest managementâ€– in FY1992-FY2003 (Figure 1). Before FY2002 disbursements for forestry projects exceeded those for watershed development projects; after that date the position was reversed (Figure 2). With respect to Bank administrative spendingâ€”which includes the cost of analytic (â€•sectorâ€–) work as well as project preparation and supervisionâ€”the cross-over point occurred somewhat laterâ€”around FY2006 (Figure 3). The watershed development portfolio continues to flourish with projects active in Uttarakhand and Himachal Pradesh and a new Karnataka project (a follow up to the operation assessed in this report) will be approved in FY2012. In contrast, the Bank's only involvement in forestry today is limited to a joint forest management subcomponent (a commitment of US$3.1 million) of the Assam Agricultural Competitiveness Project. Figure 2\. Indiaâ€”IBRD/IDA Project Disbursements, FY1995-FY2010 70.0 60.0 50.0 US$ millions 40.0 30.0 Watershed Foresty 20.0 10.0 0.0 FY95 FY96 FY97 FY98 FY99 FY00 FY01 FY02 FY03 FY04 FY05 FY06 FY07 FY08 FY09 FY10 Source\. Business Warehouse 5 Figure 3\. Indiaâ€”IBRD/IDA Administrative Spending 900 800 US$ thousands 700 600 500 400 Forestry 300 Watershed 200 100 0 Source\. Business Warehouse. Note\. Administrative spending refers to staff costs and other expenses incurred by the Bank in a broad spectrum of activities, ranging from analytic and advisory activities (including â€•sector workâ€–) to project preparation and supervision. 1.10 The Bank's approach to watershed development and forests in India has evolved over the past two decades or so. Both types of intervention have progressively given more weight to participatory processes and building community organizations, in line with the broader Bank-wide trend in support of community-driven development and decentralization. In India, moves by the national government to bolster local governments (the Panchayati Raj Institutions), underpinned by substantial fiscal transfers, have been echoed in the design of Bank projectsâ€”although to this day opinions differ within the Bank about whether the priority should be to support the strengthening of local government institutions through community capacity building or to support producer groups through promoting market linkages (promoting â€•value chainsâ€–). In the case of watershed development, the approach has become more labor-intensive (less use of heavy machinery and less focus on large earthworks, with greater use of vegetative barriers to soil erosion such as vetiver grass), more comprehensive (addressing the whole watershed rather only part of it), and the attempt has been made to make watershed user groups integral parts of local government rather than separate entities. In the case of forests, the approach shifted from afforestation of land outside the domain of state-level Forest Departments (the â€•social forestryâ€– of the 1980s) toward regeneration of degraded areas within the land claimed by the Forest Departments (the joint forest managementâ€– of the 1990s, so called because it involved a partnership between the Forest Departments and communities on the forest fringe). The Andhra Pradesh project examined in this report was a more evolved variant (and the last in the Bank-supported series), intended to give more weight to boosting the forest-derived incomes of the communities and reducing poverty. 1.11 The work on forests has proved to be more contentious than the work on watersheds, and it is this which explains the mid-2000s switch in Bank priorities. Under 6 joint forest management, communities receive a share of the income from forest regeneration in exchange for helping to implement tighter controls over the use of forestlandâ€”limitations on the collection of timber and other forest products and restrictions on grazing. Forest rights activists6 and certain skeptics within the Bank argued that forest departments were not seriously committed to handing over rights and responsibilities to forest communities, pointing out that the benefits extended to these communities through JFM were rather paltry; and that the interest of the poorâ€” particularly tribal peoplesâ€”were being harmed by JFM. The swelling opposition (internal as well as external) and the perceived risk to the Bank's reputation, explain why the Bank scaled back its support for forest interventions in the 2000s. But, to some extent, there was a rearguard action. Both the forest sector work and the Andhra Pradesh forestry project examined in this report explored ways to make JFM serve forest-dependent communities better, considering how it might be reconciled with the Bank's commitment to poverty reduction. 1.12 The report is organized as follows. The remainder of this chapter outlines the issues addressed by watershed development and forest projects in India and synthesizes the findings and lessons from the five activities that are the subject of the assessment, emphasizing cross-cutting themes. Each of the chapters 2 to 6 is devoted to one of the assessed activities. Annex A contains background information on project costs, dates and staffing. Annex B lists all the Bank-supported watershed and forest projects approved for India between FY1996 and FY2012 and provides a time-line of key events occurring during the period that the five assessed activities were implemented. Annex C explains the criteria used for this pilot evaluation of Bank analytic sector work. Annex D contains detailed responses, specific to the two assessed reports, to a checklist of questions keyed to the evaluation criteria outlined in Annex C. Annex E lists the name and the affiliation of all the persons interviewed for this assessment. Annex F contains the comments that the Borrower made on this report. References are located at the tail end of the report. Watershed Development OVERVIEW 1.13 Watershed development rests on the premise that the scope for further expansion of the irrigated area (a driver of the Green Revolution) is limited and the challenge is to promote agriculture in rainfed areas by harvesting water.7 Around the turn of the millennium, almost two-thirds (89 million ha) of India's cultivable area of 142 million hectares, was unirrigated, producing 45 percent of the nation's foodgrains.8 One of the ways that the Bank addressed the challenge of boosting agriculture in the drylands was to promote watershed development\. as this report will show, watershed development was dryland agricultural development by another name; the sustainable management of water was very much a secondary objective. 6 Sarin 2003, 2009; Sarin and Springate-Bajinski 2010. 7 World Bank 2010b\.5, 2009c; Government of India 2008. 8 Sharma 2005\. 69. 7 1.14 Current Bank strategy distinguishes â€•two basic approaches to watershed management. In the first, management interventions address very specific objectives and indicators related to water resources and hydrologic outcomes, whereas in the second, the principal focus is on wider goals and objectives, such as improved management of land or other natural resources, poverty alleviation or rural development. Unless land and water interactions and upstream-downstream impacts are critical issues, the mainstreamed approach usually makes sense, because it achieves natural resource goals and rural poverty objectives.â€–9 The two watershed projects evaluated in this report conform to the second approach. This was confirmed by a recent Bank survey of Indian watershed projects, which concluded that â€•the objectives of watershed development' relate to broader goals of sustainable land and natural resources management, poverty alleviation, and rural development. They contain no specific objectives related to water resources and/or the hydrologic interactions of land, land use and vegetation.â€–10 A 2008 review of the watershed management portfolio observed that\. â€•The interactions of watershed management with the water cycle are important. However, the projects reviewed focused more on land management than on the water cycle. Hydrology and water management were neglected until recently, so that water outcomes were largely unknownâ€”and may even have been negative in some cases. Newer projects, such as the Karnataka Project in India or the Turkey Anatolia Project, have begun tackling this challenge. In addition, scientific findings and recommendations exploring the role of some watershed management measures in improving the hydrological cycle have been little applied.â€–11 1.15 Watershed development encompasses a suite of techniques or â€•treatmentsâ€– (Table 1). Watershed projects aim to capture water during rainy periods for subsequent use in dry periods. This involves conserving soil moisture to support crop growth, capturing surface runoff water in small ponds or tanks, and encouraging water infiltration to recharge aquifers. In hilly areas the main project activity is the construction of water harvesting structures (for example, small dams) in the drainage lines of upper catchments to capture runoff water. To be sustainable, water harvesting requires the protection of the upper reaches of watersheds against erosion that would reduce water storage capacity in the lower reaches. In principle, this approach allows productivity and conservation objectives to be pursued simultaneously. 9 World Bank 2009c. (One of the authors of this Policy Note was task team leader of the Karnataka Watershed Development Project that is assessed in this report.) 10 Smyle and Lobo 2010\. 58. 11 Darghouth, Ward, Gambarelli, Styger and Roux 2008\. xvii.
P041267 | RY-TRANSPORT REHABILITATION | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Transport | IDA | IPF | 1996 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/447311474595562448/text/000020051-20140607170333.txt | http://documents.worldbank.org/curated/en/447311474595562448/pdf/000020051-20140607170333.pdf | The ICR identifies the following lessons of broad applicability:Procurement problems were a principal reason for long implementation delays. Short training courses were proven inadequate, and the need for stronger remedies, such as a full-time procurement specialist, amply justified. The Bank needs to identify performance indicators which track efficiency and effectiveness, not just the quantity of output. Conflicts among agencies or changes in leadership may lead to weak commitment to institutional and policy reforms. For successful implementation of institutional and policy reforms, the Bank must undertake more thorough institutional analysis at an early stage of project identification and preparationFuture phases of the investment program should be made contingent on up-front measures to launch sector reforms.
P041267 | RY-TRANSPORT REHABILITATION | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Transport | IDA | IPF | 1996 | 2002 | 2005 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/242361468764124440/text/303960RY.txt | http://documents.worldbank.org/curated/en/242361468764124440/pdf/303960RY.pdf | 7.5 The primary lessons learned from these projects are\. That in a post conflict, country unification situation such as Yemen's, to avoid fruitless expenditure and wasted resources, additional r i s k analysis i s appropriate to ensure that the Government i sfully committed to the reforms proposed and the timetable for the reform agenda. Project objectives should be framed realistically, taking into account the borrower's ability to achieve stakeholder support for proposed changes. Genuine community ownership and participation can enhance the likelihood o f project success as evidenced by Yemen's Public Works program. These Yemeni projects show that inter-ministerial, agency and stakeholder coordination are crucial to project sustainability and that the Bank could be more proactive in helping to improve the general level o f coordination.
P041268 | CN-Nat Hwy4/Hubei-Hunan | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/540411475084560506/text/000020051-20140618055630.txt | http://documents.worldbank.org/curated/en/540411475084560506/pdf/000020051-20140618055630.pdf | 1. The project experience shows that it is better to have two separate projects rather than a single two-province project, from both a preparation/supervision point of view and in terms of implementation. During implementation, each province was focused on their own activities and there were few interactions or exchanges of knowledge and experience between the two provinces.2. Studies carried out by provincial agencies, but requiring the participation and involvement of central government agencies (which are not part of the project), are difficult to implement.3. Procurement awards to the lowest bidder can create problems, in spite of the prequalification process. It can lead to problems during execution, with the contractor being unable to perform as per the contract. Prices may be set unrealistically low. The procurement process as it stands appears to make it difficult to address this.
P041280 | PUBLIC ENTERPRISE RESTRUCTURING AND PRIVATIZATION SUPPORT PROJECT | Western and Central Africa | Togo | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2002 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/324791475088982731/text/000020051-20140612065042.txt | http://documents.worldbank.org/curated/en/324791475088982731/pdf/000020051-20140612065042.pdf | In countries with uncertain economic performance and fragile institutions, extra caution at preparation/appraisal should guide the complexity and scope of operations, whether investment or adjustment, even if it means for the Bank to expend more resources over a longer period of time to achieve the end result. In those cases, a series of limited successes is better than attempting to attain all the desirable goals at once, with all the attendant risks. This is particularly the case when the appraisal team is faced with impending elections with uncertainty as to the results.
P041302 | EC.REC.CR.(ERC) | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1998 | 1999 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/103651474586429532/text/000020051-20140519081448.txt | http://documents.worldbank.org/curated/en/103651474586429532/pdf/000020051-20140519081448.pdf | The credit demonstrates the value of designing a program consistent with the Government's commitment and institutional capacity and then following it up quickly with the next phase to sustain the momentum of reform. Furthermore, in countries with weak institutional capacity, complementary technical assistance not only facilitates coordination across various Ministries, but can also sustain the reform momentum.
P041303 | EMERG. DROUGHT RECOV | Middle East and North Africa | Morocco | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1996 | 1998 | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/297131475092904084/text/000020051-20140521031822.txt | http://documents.worldbank.org/curated/en/297131475092904084/pdf/000020051-20140521031822.pdf | There are instructive lessons (set out at length in the ICR) about the prerequisites for fast implementation of an emergency project: these include using an expert panel and off-the-shelf design for engineering components. Speedy action by government---removal of taxes on feed imports and advance of funds for building water points---was also a critical ingredient of project success.
P041396 | INTEGRATED SOLAR COMBINED CYCLE POWER PROJECT | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2007 | 2013 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/829071474907754285/text/000180307-20141202110459.txt | http://documents.worldbank.org/curated/en/829071474907754285/pdf/000180307-20141202110459.pdf | The following useful lessons can be derived from the project's implementation experience (as adapted from the ICR):The use of integrated solar combined cycle (ISCC) technology can be a stepping stone for scaling-up concentrated solar power (CSP). The integrated design allowed ONEE to take a measured risk and test the feasibility of introducing solar power in its generation system without hampering its objective of ensuring reliable electricity supply. The fossil fuel supply, however, needs to be guaranteed.The choice of wet or dry cooling technology should to be fully evaluated. ONEE required bidders to submit separate proposals for both wet cooling technology and dry cooling, with associated required levels of water consumption. This approach allowed ONEE to take an informed decision, which yielded the best technical solution at a lower cost. Bid the ISCC project with a single contract. Bidding the project with a turnkey contract for the construction, operation and maintenance of the plant enhances the prospects for achieving its smooth operation. An operations and maintenance agreement for five years is preferable to the standard contract of two years. as the longer contract significantly reduces project risks . This procurement arrangement lowered ONEEâ€™s operational risks by transferring these risks to the contractor and has assured the plantâ€™s satisfactory performance to date. The turnkey Engineering, Procurement and Construction (EPC) consortium should include the suppliers of the key ISCC plant components. This could reduce possible delays. At Ain Beni Mathar, the supplier of the steam turbine was not a member of the turnkey consortium contract for the design, construction, operation and maintenance of the plant. The inclusion of the steam turbine supplier in the consortium could probably have reduced unnecessary delays during construction because of the risk-sharing EPC arrangement.Independent power producers (IPP) are unlikely to be interested in projects that lack a firm Power Purchase Agreements unless they have a fully operational, large scale market for electricity, with many independent producers and consumers. Initial IPP tenders in 2002 for this project failed primarily because it was considered too risky by potential bidders for a project in Morocco, where there were very few potential buyers of electricity.
P041410 | Pumping Stations Rehabilitation III | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1999 | 2008 | 2008 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/218021474563549263/text/000020051-20140618194211.txt | http://documents.worldbank.org/curated/en/218021474563549263/pdf/000020051-20140618194211.pdf | In follow-on projects institutional reform should be given priority if this was evident from the previous project. Not to do so poses a high risk for project efficiency and substantial risks to development effectiveness. When sound MIS arrangements are essential to sector operational efficiency they should be given high visibility at appraisal and in project conditionality agreements.
P041442 | Municipal Water & Wastewater Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2010 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/576831474660076192/text/000020051-20140624160637.txt | http://documents.worldbank.org/curated/en/576831474660076192/pdf/000020051-20140624160637.pdf | The ICR provides a number of useful lessons, the most import of which are summarized as follows:Preparatory work for Management Contracts should involve thorough assessment of the political economy of the sector to gauge the level of commitment of key stakeholders and participating utilities. The commitment of utilities could have been better assessed during preparation, for instance by requiring them to meet higher pre-project hurdles to demonstrate local ownership of the project. In addition risks associated with staffing reductions need thorough appraisal especially where project outcomes are partly dependent on such reductions. Staff should be recognized as key stakeholders and their concerns considered in the social analysis. The Bank needs to give adequate attention to strengthening support for contract management during implementation and not just for procurement of contracts. Much effort was put in preparation and procurement of the Management Contract to ensure that the Borrower got value for money. Less effort seems to have been put on contract management during implementation to address arising problems in order to be able to deliver the desired results.Ensure the sector's governance framework supports Performance-based Management Contracts. The sectorâ€™s governance framework should support key elements of the concept such as full delegation to the private operator of decision-making responsibilities concerning management of utility operations. Adequate attention must be paid during design of Management Contracts to ensure that they are fully aligned to the existing legal and regulatory framework to avoid any issues that could potentially undermine the effectiveness of the Contract.Technical reviewers for Performance-based Management Contracts should be appointed prior to commencement of the Contracts. This will allow their involvement in collection of the baseline data on sector performance and input on reporting requirements in order to improve the M&E function for the MC. In this case, the Technical Reviewers only came on board several months after the Management Contract commenced and took issue with the reporting arrangements and some of the baseline indicators.Performance indicators should be designed to capture all critical elements of service performance more effectively in order to encourage Operators to focus on improving services in all key areas. Unaccounted-for water was not a performance indicator in this Management Contract.
P041528 | SN-Long Term Water Sec SIL (FY01) | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2009 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/553171474483871204/text/000020051-20140620074549.txt | http://documents.worldbank.org/curated/en/553171474483871204/pdf/000020051-20140620074549.pdf | This project generated some broadly applicable lessons:The long-term commitment of IDA in Senegal was a major factor of success. It meant that the Bank was able to: (i) play a catalytic role in leveraging investment funding from other donors; (ii) smooth friction and bring a cooperative spirit; and (iii) provide continuous support to the full execution of contractual and regulatory obligations.Determining willingness to pay for peri-urban sanitation is vital for success. The peri-urban sanitation component faced serious start-up problems due to the fact that the householdsâ€™ contribution (50 percent of the cost of the facilities) was perceived as too high and that the large-scale NGOs involved in outreach activities were not able to communicate and work efficiently with beneficiaries. Modifications were rapidly brought to (i) decrease the contribution to 25 percent; and (ii) shift outreach responsibilities to community-based organizations, which were closer to households. The pace of execution was then multiplied by a factor of ten.
P041528 | SN-Long Term Water Sec SIL (FY01) | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2009 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/532141468294656002/text/9419150PPAR0P00ater0project000final.txt | http://documents.worldbank.org/curated/en/532141468294656002/pdf/9419150PPAR0P00ater0project000final.pdf | Lessons Learned 3.45 Premature cessation of donor engagement could lead to a loss in momentum for major sector reform. The Government of Senegal had high ownership of the adopted a strategy (1995 and 2005) in the water and sanitation sector but this has recently waned. Through sustained commitment of IDA, the Bank was able to (i) play a catalytic role in leveraging investment funding from other donors; (ii) smooth friction and bring a cooperative spirit; and (iii) provide continuous support to the full execution of contractual and regulatory obligations. However, the IEG mission found that the Bank and the donor community have recently shifted their focus away from the relatively well performing urban water and sanitation, to rural water and sanitation sector. As a result, the Government slowed down on its reform agenda, as evidenced by the absence of an updated water sector policy and non-compliance of the lease contract with the private operator, potentially losing the momentum generated to sustain earlier reforms. 3.46 Benefits of water investments may not be realized without adequate attention to sanitation. Recognizing the existence of a comprehensive and integrated approach to sanitation, evidenced by Senegal's urban sanitation strategy which was based on the diversification of technologies, the assessment found that more resources and more attention were devoted to water production and distribution at the expense of the sanitation sub-sector in Senegal. This finding is reflected in the mismatch between the sanitation infrastructure and the country's needs, and the lack of solutions to set up sustainable approaches to manage public and semi-public sewerage networks and wastewater treatment plants. According to the interviews carried out during the IEG mission, the supply of increased urban water facilitated by the Bank's project had led to major pressure on the existing sewerage infrastructure. As the imbalance between the water and sanitation investments and reforms persists, sanitation conditions may worsen, leading to unhealthy conditions and increasing risks of water-borne diseases to the population that benefitted from water services. 3.47 Raising tariffs only for one customer group may not be effective for ensuring long term sustainability. Since 2006, the water tariff for the private consumers had been frozen by the Government in contradiction to the lease agreement prescribing annual water price adjustments in line with the inflation.16 In contrast, while the tariffs increased for the public sector entities, the exploding bills were only partially paid by the government and, as a result, arrears often accumulated and as a consequence, there were limited resources available to fund the sector's major financial needs. In the absence of steady tariff increases, the sector risks a declining quality of the infrastructure and services. 3.48 Determining the right threshold of the beneficiary contribution is vital for the successful delivery of peri-urban sanitation services. The peri-urban sanitation component faced serious start-up problems because the required household contribution was perceived to be too high, and the large-scale NGOs involved in outreach activities were not able to communicate and work efficiently with the beneficiaries. Modification of beneficiary contribution from 50 to 25 percent of the facility cost, and shifting of outreach responsibilities to community-based organizations, increased beneficiary participation in the on-site and the semi-collective sanitation program. 3.49 Complex management and institutional arrangements lead to implementation delays. The procedures for Global Partnership for Output-Based Aid were complex and implementation arrangements were cumbersome. Obstacles to rapid project implementation were not promptly identified and removed during trust fund negotiation and processing. The payment schedules mandated by the GPOBA approach were overly complex, and the Project Team took a long time to get used to the 16. The mission was informed that the Government finally decided to increase the tariffs in September 2014. Trust Fund procedures, leading to delays in launching and implementing the project, causing delays in proper establishment of sustainability enhancing measures. The lesson from this experience is the importance of identifying the institutional issues early and simplifying the management and implementation arrangements to avoid delays in project implementation. It is also important to weight the transaction costs associated with the funding size of GPOBA, and the institutional viability of such approach compared to a larger, project scale initiative that is more integrated with the government program.
P041548 | Privatization & Reg CB TA | Western and Central Africa | Gabon | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2004 | 2006 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/759971474420238974/text/000020051-20140613061430.txt | http://documents.worldbank.org/curated/en/759971474420238974/pdf/000020051-20140613061430.pdf | Building effective regulation capacity is a longer term endeavor. Under this project, the Government has made a good start in regulating the water and power sectors by contract and in setting up regulatory agencies in telecommunications and postal services. The ultimate objective was to make all these regulatory arrangements converge, in the medium-term, into an independent, fully operational, multi-sectoral regulatory agency. The progress made to date needs to be sustained and put in line with international best practices.Bank supervision effort should be consistent throughout the project life. To ensure continued dialogue and avoid delays in project implementation, the Bank should have increased the number of supervision missions and strengthen presence for continued follow up on mission conclusions. Cofinancing is a risk factor requiring mitigation throughout project implementation. Even if a cofinancier is identified during project preparation, the Bank team should attempt to define realistic objectives taking into account the potential impacts of the Bank loan. In this case, the suspension of the African Development Bank loan affected negatively the implementation of the project.
P041553 | PE/TA | Western and Central Africa | Cameroon | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/556361475070247727/text/000020051-20140604045943.txt | http://documents.worldbank.org/curated/en/556361475070247727/pdf/000020051-20140604045943.pdf | Even though the privatization program was proceeding well, greater emphasis should have been placed on making progress in the public awareness campaign, to explain and build greater momentum for this difficult political-economic undertakingBefore starting efforts such as the judicial reform or private sector development components, Bank staff need to determine that there is sufficient government commitment (which was not the case in this project)
P041566 | Social Development Fund Project | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/919091475084493017/text/000020051-20140617134750.txt | http://documents.worldbank.org/curated/en/919091475084493017/pdf/000020051-20140617134750.pdf | The ICR has a useful discussion of lessons -- see ICR page 25-26. This ICR Review emphasizes an important ICR lesson that institutional issues need to be dealt with early on and explicitly. There are dangers to pitting local governments versus country-based approaches against each other -- a blended approach that is inclusive of both and that taps their respective comparative advantage is the most appropriate approach.
P041567 | Endemic Disease Control Project | Western and Central Africa | Senegal | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/449861474596601282/text/000020051-20140613033628.txt | http://documents.worldbank.org/curated/en/449861474596601282/pdf/000020051-20140613033628.pdf | Late, retrospective collection of performance and impact data shortchanges the opportunity to focus the project teams throughout the life of the project on the final outcomes and to adapt project implementation to problems identified in a timely manner.Strong technical preparation of a health project is not sufficient to achieve results. Adequate attention must also be paid to the coherence and integration of such an effort with the broader environment, as well as to ensuring adequate ownership and capacity to implement.Strong ownership of health projects by the regions and the districts requires effective decentralization of responsibility for management of activities and of financial resources.IDA support of simultaneous projects in the same sector will not be efficient in the absence of strong coordination and complementarity both in terms of the projects' objectives and in terms of the Bank's and Government's teams involved in design and implementation. Consensus and clarity in the institutional set-up of projects are essential to success.
P041568 | Population & Reproductive Health | Western and Central Africa | Guinea | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/665471474628876815/text/000020051-20140612142417.txt | http://documents.worldbank.org/curated/en/665471474628876815/pdf/000020051-20140612142417.pdf | In using an APL as a lending instrument, financing should be adequate to complete all activities planned in each phase, and a commitment to sustain support for the full APL cycle should be fulfilled unless the trigger conditions are not met.The administration of the NGO Fund was assisted by having an intersectoral committee which reviewed NGO project proposals, and the availability of institutional development grants for NGOs that had successfully submitted two or more proposals helped to strengthen a number of local NGOs.To discourage FGM, an integrated approach of policy changes, engaging religious and opinion leaders, media campaigns, and local NGO activities can be effective in reinforcing attitude change.
P041642 | PRODUCTIVE PARTNERSHIPS SUPPORT PROJECT | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2002 | 2009 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/201371474549989739/text/000146597-20140619153143.txt | http://documents.worldbank.org/curated/en/201371474549989739/pdf/000146597-20140619153143.pdf | Among the many lessons identified in the ICR, the following stand out:sub-projects;A competitive technical selection and approval process based on publicized criteria and strict adherence to the "rules of the game" are crucial for promoting grant-financed sub-projects;Productive partnerships of the sort promoted under this project are most likely to succeed when they are linked to well-established (crop-specific) Producer Associations--and the respective value chains;For partnerships to work there needs to be a significant investment in training and the transfer of business skills;Sound feasibility studies provide vital background for decisions about which sub-project proposals to finance;Decentralized management units are critical for developing and supervising partnerships and facilitating linkage to the private sector; and If the set-up grants for productive partnerships are repaid into a revolving fund managed by producer organizations, commercial banks will have stronger evidence of credit worthiness and are more likely to lend to the producers involved.
P041642 | PRODUCTIVE PARTNERSHIPS SUPPORT PROJECT | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2002 | 2009 | 2016 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/405511468178459319/text/99886-PPAR-P041642-SecM2015-0323-Box393245B-OUO-9.txt | http://documents.worldbank.org/curated/en/405511468178459319/pdf/99886-PPAR-P041642-SecM2015-0323-Box393245B-OUO-9.pdf | 7. Lessons 7.1 There are four main lessons from the project that were derived from this project performance assessment\. 7.2 In Productive Partnership Projects, sufficient attention needs to be paid to the needs of both farmers and buyers. In the case of the first phase of the Colombia Productive Partnership project, more attention was paid to the productive capacity of the smallholders than to the commercial entities, the latter requiring greater awareness about the new opportunities for engagement created by the project. 7.3 Revolving credit mechanisms in rural areas should be designed in line with the capacity of the user. In the first phase Colombia Productive Partnership project, revolving funds were an effective tool for mature producer organizations for accessing essential financing. Established relationships and trust within existing organizations led to the effective use of these funds. Less mature partnerships however were unable to effectively utilize these fund mechanisms. Given the very limited repayment rates of immature partner organizations, a grant scheme would have been a more relevant tool, as the project's design had originally proposed. 7.4 Producer Alliances require a differentiation in design that takes into account trust, relationships, and maturity to determine the level of value added that a productive partnership project is likely to generate. Coffee producers, for example, already had mature linkages through the Federation of Coffee Producers, while some other alliances had access to Government financing. In these cases the value added by the project may have been minimal, and the funds may have been put to better use in less mature producer organizations. Likewise, the project could have been grounded in a better understanding of the effects that conflict has on trust when forming alliances in conflicted affected areas. 7.5 Productive partnership projects are more likely to succeed when they are part of an integrated rural development approach. Such an approach would include attention to binding constraints in the rural space that limit the income earning potential of the farmer alliances. In Colombia, theses constraints included poor rural infrastructure (storage roads and power) and weak extension services. These constraints were particularly felt by productive partnerships engaged in the production of perishable items, where the lack of cold storage and the high costs of transport limited their income earning opportunities.
P041680 | SV SECONDARY EDUCATION | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/824471474663815583/text/000020051-20140615102831.txt | http://documents.worldbank.org/curated/en/824471474663815583/pdf/000020051-20140615102831.pdf | Transferring responsibilities to schools may foster ownership, efficiency in resource allocation, and transparency. However, there are tradeoffs to be considered in decentralization. Central control is necessary to ensure policy consistency, equity across the sector, and quality control. Decentralization to the school level must be accompanied by adequate resource transfers, appropriate training of stakeholders, continuous support to them, and supervision to ensure compliance.- Education reforms should be based on long-term goals but have flexible implementation strategies so that different administrations can embrace them as their own. - The involvement of non-governmental organizations, agencies, and private institutions in the implementation of education services can generate efficiencies for the sector, as well as bringing external expertise in searching for alternatives to address sector issues.
P041723 | National Rural Infrastructure Project | Western and Central Africa | Mali | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/608461475098198981/text/000020051-20140619084221.txt | http://documents.worldbank.org/curated/en/608461475098198981/pdf/000020051-20140619084221.pdf | Significant lessons from the project including those mentioned in the ICR:Participatory projects covering several sectors are better managed through a multi-sector coordinating mechanism. Otherwise synergy among the project components may be hard to maintain and cross-cutting activities may receive less attention.When starting from a low institutional base, effective implementation of reforms required a realistic timeline to build capacity, consensus, and government commitment, and needs continuous policy dialogue.Systems for Monitoring & Evaluation should be functional early during project implementation. This is particularly important in a project that involves several activities occurring simultaneously in multiple sectors.
P041741 | BANKING & ENT-BESAC | East Asia and Pacific | Mongolia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1997 | 1999 | 2000 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/168821474899335460/text/000020051-20140526222003.txt | http://documents.worldbank.org/curated/en/168821474899335460/pdf/000020051-20140526222003.pdf | A project with a broad reform agenda needs to have a length of much more than a year, and should probably have more than one tranche--with associated conditionalityProject objectives should give priority to implementation and enforcement of a new law, not just its passage
P041741 | BANKING & ENT-BESAC | East Asia and Pacific | Mongolia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1997 | 1999 | 2002 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/158311511185850609/text/multi0page.txt | http://documents.worldbank.org/curated/en/158311511185850609/pdf/multi0page.pdf | 5. Lessons * Parallel efforts were required to support private sector development. The Bank's emergency loans helped maintain short-term stability but had limited impact on the longer-term goal of establishing a market-economy. Unlike in other transition countries, the Bank did not have significant parallel interventions aimed at private sector development and the impact of propping up select public services and industries on the rest of the economy was overestimated as a range of other factors impeded a strong supply response. * Emergency-type operations should include a mechanism for mid-stream review. Emergency response operations should retain a good degree of flexibility, including a mechanism for a midstream review in order to ensure that changing circumstances on the ground have not eroded the relevance of the response. * Effective donor coordination requires full agreement on the strategic approach to a sector. In the interests of promoting donor coordination, the Bank supported other donors' lead in banking reform without fully reaching agreement on design and implementation strategies. This contributed to an unsatisfactory program design and less than effective supervision. In retrospect, differing approaches should have been addressed and fully resolved prior to the commitment of large amounts of financing. * A comprehensive sector review must precede significant financial assistance in a complex reform area. As designed, BESAC was inadequate in terms of the strength and duration of the actions specified to meet the magnitude of the sector's problems. Preparation of a comprehensive sector review (which was done several years after the design of BESAC) prior to financing reforms would have enhanced the relevance of the program and its likelihood of success. * Effective institution-building efforts should go beyond creation of new agencies and regulations. Bank support helped establish new agencies and design and pass new regulations. However, weaknesses are apparent in both the effectiveness of the new agencies and in the implementation of the new regulatory framework. For effective institution-building, equal attention must be paid to strengthening institutions rather than just their creation, and implementation of new laws rather than just their passage.
P041790 | Atlantic Biological Corridor (GEF) | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1997 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/661391475114343532/text/000020051-20140615095007.txt | http://documents.worldbank.org/curated/en/661391475114343532/pdf/000020051-20140615095007.pdf | 1. Decentralization, participation, communication and capacity building are typical core needs in a biodiversity program: Under the project, decentralization of management to local governments and communities promoted ownership and actions where the actions needed to be made. Maximizing participation, leadership and implementation by local stakeholders capitalized on their local knowledge, interest and human resources. The program also involved the participation of a diverse resource structure (government, universities, NGOs, private sector) to provide technical support and guidance. Communication was a major thrust of the project and helped create public awareness of the need for conserving the nation's natural resources. Major training and capacity building was also provided. As a new program, all stakeholders needed to acquire the understanding and skills to implement their roles.2. Establishing a biodiversity conservation program generally requires a long-term program approach. The significant institutional achievements of the project have made a start towards fully establishing and achieving a biodiversity conservation program. The forthcoming Nicaragua/Honduras Corazon Transboundary Biosphere Reserve Project will support the substantial further activities required to develop and consolidate the ABC biodiversity program. Some degree of further support even beyond the successor project's closure may also be needed. However, the project's appraisal report and ICR do not explicitly discuss such a long-term and continuous approach. It would have been better, and considerably less risky, if a long-term approach, and the resources to do this, had been planned and assured from the start.
P041807 | PUBLIC SECTOR LEGISLATIVE AND ADMINISTRATIVE MODERNIZATION PROJECT (FORMER PUB SEC MOD & DECEN) | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2006 | 2004 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/644221475089148418/text/000020051-20140612104410.txt | http://documents.worldbank.org/curated/en/644221475089148418/pdf/000020051-20140612104410.pdf | In highly politically volatile countries, the Bank should reassess government ownership each time there is a change in Government or of key ministers.In this case, the Bank was much too slow, both during preparation/appraisal and implementation, to react to the shifting political situation in the country. Although it showed flexibility in trying to accommodate the request for restructuring, once the latter proved to be excessively prolonged, the Bank should have closed the discussions and cancelled the Loan. The rationale for maintaining the dialogue on the basis of country relations may have been self-defeating, in that the interests of neither the country nor the Bank were served, as noted by QAG.
P041820 | CONTRACTUAL SAVINGS | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1997 | 1998 | 1998 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/788911474596689888/text/000020051-20140519063553.txt | http://documents.worldbank.org/curated/en/788911474596689888/pdf/000020051-20140519063553.pdf | Bank loan demonstrated how politically sensitive reform can be supported, by making sure there was agreement on a reform agenda, mounting a highly competent technical team, ensuring that key measures were taken before loan approval (thus de-emphasizing "conditionality,:) and taking a "low profile".
P041820 | CONTRACTUAL SAVINGS | Latin America and Caribbean | Mexico | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1997 | 1998 | 2001 | PPAR | >=100 million | Highly Satisfactory | Highly Satisfactory |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/597561511189121582/text/multi-page.txt | http://documents.worldbank.org/curated/en/597561511189121582/pdf/multi-page.pdf | 10. Findings and Lessons 10.1 The main finding is that, with respect to all but a few (important) elements, the Mexican pension reform program has been successful and should consequently be given high marks. However, among those few problematic elements have been the failure to achieve certain critical objectives (i.e., lack of progress in fundamental INFONAVIT reforms and inability to loosen restric Lions on SIEFORE investments) which can endanger the whole reform process. Other shortcomings, especially in the inability to expand coverage significantly and to implement some of the important complementary reforms elsewhere in the financial sector, continue to impede realization of many of the benefits of pension reform. 10.2 One lesson of this experience is that single tranche operations can be more effective, efficient, and realistic instruments for providing timely balance of payments support than multi-tranche operations. A series of single tranche operations allows the reform process to proceed at the pace determined by the client country, rather than by the tight time-frame required for multi-tranche adjustment loans. 10.3 The newness and far-reaching complexity of pension reform made it particularly attractive to use a series of single tranche operations for technical reasons\. as pension reform unfolded, important details of certain technical issues that were not originally obvious became clearer over time. The need under CSDP-II for fine-tuning the regulatory infrastructure and for paying more attention to certain complementary developments in the financial sector (e.g., improved provision of annuities and insurance services, development of new financial instruments, expanded infrastructure such as rating agencies and custodial services, etc.) are clear examples of this. However, single tranche operations can also increase the temptation to postpone essential reforms that face political barriers from the first operation to later ones. At the time CSDP-I was undertaken, it was possible to overcome seemingly major political obstacles and initiate the pension reform process in Mexico with a considerable degree of success. By the time of CSDP-II, with the worst of the financial crisis past, the momentum to overcome such political obstacles may have been lost. Nevertheless, on balance, the advantages of single tranche operations outweigh their disadvantages. 10.4 The other lesson on pension reform is its far-reaching complexity and the need for major complementary financial sector reforms in order for the benefits of pension reform to achieve their full potential. As emphasized above, great progress has been made in the Mexican case in the design and implementation of the regulatory regime and in providing crucial infrastructure that allows pension contributions to flow quickly and accurately to the proper individual account and for this information to be immediately available to the regulatory body, CONSAR. As witnessed by the earlier Mexican experience with pension reform under SAR92, failure to provide this seemingly mundane infrastructure can undermine the entire activity and cause on-going problems that can take years to resolve. 10.5 With respect to complementary reforms in the financial sector, the Mexican experience suggests four lessons\. (1) pension reform benefits will be incomplete unless individuals in the pension system have access to attractive complementary annuity and insurance products; (2) the array of instruments available to pension fund managers must be expanded to include those that are long term, but have reasonable liquidity and risk profiles, something not quick and easy to achieve when there was no market for such instruments before pension reform; 16 It is also important to note that, at the same time the pension reform process was able to move ahead, the operation to resolve the banking crisis met with great difficulties. Thus, even with a multi-tranche operation, the political obstacles to pension reform might not have been overcome. (3) the array of risk and return options available to individuals will not be on the efficient frontier unless the regulatory regime focuses on portfolio risk rather than on the risks of individual securities; and (4) pension reform benefits will be greatly reduced if the government directs the investment of pension funds to specific institutions or sectors (e.g., INFONAVIT) and/or prohibits investments that are essential for constructing portfolios with optimal risk-return profiles (e.g., prohibition of investments in foreign securities). 10.6 Two final lessons come out of the Mexican experience that may also be generalizable to pension reform elsewhere\. (1) An important objective of pension reform is to expand coverage, particularly to government workers and workers in the informal sector. It may be more difficult to incorporate government workers later in the process as their benefits may need to be adjusted downward or those of private sector workers upwards to reach equality at a later date (with major fiscal costs that are more difficult to deal with when they come as later surprises). In addition, concerted efforts would be required to bring informal sector workers into a pension system, by both the government in carrying out a public awareness campaign of the long-term benefits of pensions, and by private pension providers to actively seek out these workers as clients. (2) Mexico and many other developing and transitional countries are subject to substantial country risk premiums. This results in high real interest rates which mean that domestic debt instruments offer more attractive returns than foreign ones. At the same time, many grade A borrowers have access to funds in foreign financial markets on attractive terms, and thus are unlikely to issue higher real interest rate instruments in domestic markets. This makes reforms to reduce country risk very important for pension reform. Otherwise, pension fund investment managers are likel y, regardless of the regulatory regime, to see government debt instruments as the only logical choice, so that they fail to gain much portfolio management experience. Under such circumstances, moreover, pension reform becomes a more roundabout, and likely expensive, way of financing the government's debt.
P041887 | MUNICIPAL SERVICES | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1999 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/214411474492395468/text/000020051-20140625235953.txt | http://documents.worldbank.org/curated/en/214411474492395468/pdf/000020051-20140625235953.pdf | The following are distilled by IEG from the Bank and Borrower ICRs:The project demonstrated that a municipal development fund, BMDF, could be established and become operational in a large low-income country, with rapid, large scale urban growth. The BMDF applied a simple model designed to respond directly to municipal demands for financing. However, even a simple model requires the highest technical standards for its own work as well high quality technical assistance to help its municipal clients prepare priority projects for BMDF financing.To be successful a municipal development fund must enjoy the full support of and close coordination with higher-tier authorities that oversee and work with it. This project showed that closer coordination between BMDF and LGED could have made BMDF operations more agile and readily accessible to municipalities. LGED/MSU was an effective vehicle for this in Bangladesh.Adequate technical support at the outset needs to be built into projects working with a large number of municipalities. In the view of the Borrower, this project's 12 municipal engineers for 141 sub-projects in 65 municipalities over a 15 month period were insufficient. Designing sub-projects proved particularly challenging because municipalities lacked engineers.
P041890 | CN-Liaoning Urban Transport | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/796941474664659567/text/000020051-20140615105756.txt | http://documents.worldbank.org/curated/en/796941474664659567/pdf/000020051-20140615105756.pdf | Introducing too many components and greater complexity into projects should be avoided, especially where supportive institutional capacity and culture is lacking, and is unlikely to evolve to required levels during project implementation.Urban transport development on various fronts cannot move forward in a coherent way in the absence of an overall urban transport strategy, that takes a balanced view of improving physical assets, and developing appropriate institutions and processes.Sensitization of key decision-makers is crucial for successful implementation of urban transport innovations, even if broad support exists amongst the rank and file and the public at large.Foreign consultants should be employed if the necessary skills are not available locally, or when there is a strong possibility of adding value to the project.The tendency for road construction and improvement to predominantly serve the needs of motorized traffic should be tempered so that the requirements of public transport systems, bicycles, and pedestrians are better served.Knowledge transfer and institutional development can be long processes, and a project should provide for sufficient time for them to accepted and implemented.
P041894 | ID-SUMATRA SECONDARY EDUCATION | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1997 | 2004 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/359451474577013151/text/000020051-20140613060636.txt | http://documents.worldbank.org/curated/en/359451474577013151/pdf/000020051-20140613060636.pdf | During times of financial crisis, or political change, flexible supervision allows the potential for rapid restructuring as the need arises so the project can be re-oriented toward changing needs.Decentralization proved to allow a more effective use of resources, and proceeded without too many problems once the institutional context was in place. However, within the framework of decentralization, central government has a role in targeting strategies to address the educational needs of the poorest communities if national goals for basic education are to be achieved.There are advantages in cost effectiveness and efficiency when several similar projects are funded concurrently, with similar PDOs and KPIs, and managed as a single program rather than as separate projects.The establishment of a strongly staffed, and well managed project implementation unit (PIU) can be a key contributing factor to successful implementation.The experience of the Scholarship Grants Program (SGP) provides lessons on using scholarships to respond to a crisis situation. During the financial crisis the dropout rate has been low in primary school and that the transition to junior secondary school is the most important attrition point in the system, particularly for the poor. This suggests that the program was most effective in its support of the critical transition from primary to junior secondary education. This finding would suggest that: (a) there can be some narrowly targeted scholarships for the poorest children at the primary level, but the bulk of the program should be more broadly focused on junior secondary school; and (c) the pool of candidates for grade 7 scholarships has to be taken from children who complete primary school not from those who are already enrolled in grade 7.
P041894 | ID-SUMATRA SECONDARY EDUCATION | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Education | IBRD | IPF | 1997 | 2004 | 2006 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/439611468039272095/text/36427.txt | http://documents.worldbank.org/curated/en/439611468039272095/pdf/36427.pdf | 5. Lessons 5.1 This assessment confirms a number of IEG lessons from the education sector\. It is possible to target successfullypoor areas for interventions aimed at increasingenrollments, even in times of financial crises. Scholarships administered to the poor and disbursed to them promptlymay be effective in sustainingenrollmentsand preventing dropout (para. 2.17, Annex C) Community involvementmay be cost-effective and reliable means to build and support schools, particularly when the population has basic education and poverty is not extreme. Nevertheless, school committeemembers may not be able or willing to keep school expenditureslow, maynot have much time to spend on school affairs, and may be unable to advise the principal effectively on educational matters (para.2.27) Decentralization pronlotes effectiveuse of resources. However, not all local authoritiesare equally competent or interestedin educatingthe poor. A central government may find it necessaryto meet the basic educationalneeds of the poorest communities directly if national goals for basic educationare to be achieved (para.2.26) International assessmentsmay provide critical feedback to governmentsinterested in increasingthe competitiveness of their human capital. They may alsoprovide means to help countriesimprovetheirperformance (paras. 2.23,4.3).
P041895 | ID-SULAWESI BASIC EDUC. | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/643631474637284173/text/000020051-20140617130931.txt | http://documents.worldbank.org/curated/en/643631474637284173/pdf/000020051-20140617130931.pdf | Large-scale decentralization should proceed cautiously. Incentives should be carefully thought through, decided upon, resourced and made consistently available, before community participation and the establishment of decentralized education programs begin. Otherwise, staff, management, and planning mechanisms may not be ready to accommodate the decentralization needs.- Communities in many countries are able to assume some responsibility and to construct and equip schools through the help of block grants. However, training and follow-up are needed for this level of involvement to occur.- It is possible to mitigate the effects of an economic crisis through targeted interventions at vulnerable students attending critical stages of their education.
P041896 | ID-HR CAPACITY BUILDING | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2001 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/876041474592350552/text/000020051-20140604052936.txt | http://documents.worldbank.org/curated/en/876041474592350552/pdf/000020051-20140604052936.pdf | The project illustrates several long-standing OED lessons, including the importance of thorough project design; adapting project complexity to borrower capacity and commitment; maintaining proactive supervision and avoiding excessive staff turnover; and putting in place adequate arrangements for monitoring and evaluation. Other lessons include:Technical assistance/capacity building projects must be based on a thorough diagnosis of capacity constraints; take time to develop consensus with clients regarding needs and priorities; and put in place implementation arrangement prior to effectiveness.When seeking to strengthen strategic planning capacity, project design and supervision must strike a balance between production of outputs (e.g., studies and strategies); the expected technical quality of those outputs; and capacity building objectives. An excessive output orientation can undermine capacity building objectives.The project also illustrates the challenges and tensions that can emerge following the decision to close a problem project.
P041971 | HT TAP II | Latin America and Caribbean | Haiti | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/440461474503110925/text/000020051-20140529075346.txt | http://documents.worldbank.org/curated/en/440461474503110925/pdf/000020051-20140529075346.pdf | The Bank cannot implement projects in a situation of political fragmentation, corruption, and lack of ownership of proposed reforms from both the government and civil society. Along with other donors, the Bank should first work to strengthen the country's governing system, including a dialogue with civil society; without improvements in these areas, no project can be implemented satisfactorily.
P041994 | UY-Second Basic Education Quality Improvement Project | Latin America and Caribbean | Uruguay | IBRD |  | Human Development | Education | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/853311474906053706/text/000020051-20140612152108.txt | http://documents.worldbank.org/curated/en/853311474906053706/pdf/000020051-20140612152108.pdf | #NAME?
P041994 | UY-Second Basic Education Quality Improvement Project | Latin America and Caribbean | Uruguay | IBRD |  | Human Development | Education | IBRD | IPF | 1999 | 2004 | 2006 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/708581468309325444/text/35012.txt | http://documents.worldbank.org/curated/en/708581468309325444/pdf/35012.pdf | 7. Lessons This assessment confirms a number o fIEGlessons from the education sector\. 0 Preschool attendanceoffers significant academic benefits to low-income students in terms o freduced grade repetitionas well as long-term academic achievement (para. 4.4) 0 A longer school day may offer important academic and socialbenefits to disadvantaged students, including improved test scores. To maximizeperformance inhighergrades, however, studentsinlower gradesmightspendpartofthe extra time practicingthebasic skills that serve asprerequisites for further learning(paras. 3.10,4.13, and 6.5). 0 Quality o f education depends on a strong and functional supervisory chain. If government policies and learning activities are to be carried out effectively at the school level, teachers mustbe supervisedclosely by knowledgeable and interested staff. Although supervision i s often costly interms o f salaries and vehicle support, it i s a prerequisite for improvedlearningoutcomes (paras. 3.8 and 5.10). 0 Project efficiencymaybe enhanced through instructionalmethods that enable most o fthe students to achieve educational objectives within the prescribed instructional time. Efficientinstructionmaybemore important for disadvantaged children, who receive less home support andwho often have higher dropout and grade repetition rates. Further research and experimentation would help determine which instructional activities are more cost-effective inthe Uruguayancontext (paras. 5.3 and 5.9). 0 Vocational-technical education project appraisals may overestimate the number o f likely graduates and not adequately take into account dropout rates or changing demand for training. Appraisals o f future projects should take into account country experience on dropout rates as well as demand changes duringtimes o f economic hardship (paras. 2.2-2.4,2.6).
P042014 | Karst Ecosystem Conservation GEF Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2008 | 2009 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/968681474489717916/text/000020051-20140619081538.txt | http://documents.worldbank.org/curated/en/968681474489717916/pdf/000020051-20140619081538.pdf | Among the main lessons that can be drawn and/or confirmed from this project, as highlighted in the ICR, are: (1) Thorough project preparation leads to a well-tailored design; (2) Government and park staff ownership and continuity are critical to project success; (3) A local PIU, decentralized management of the small grants program, and strong support of local governments were essential for its success; and (4) Benefits to protected areas from sustainable rural development can be optimized when designed in concert with park management plans. To these lessons, this review adds: (5) The project's straightforward and relatively simple design -- one national component and one local component, each with several clearly defined and manageable subcomponents -- and appropriate institutional arrangements also greatly facilitated its smooth implementation and ability to achieve its intended results; (6) Careful monitoring and evaluation, including of project outcomes, are essential to adaptive management, lesson learning, and replicability -- as demonstrated in this operation especially with respect to the small grants component -- and should be continued, if possible, after the project itself has concluded in order to help identify and assess its medium and longer-term impacts; and, (7) Decentralization and continuity of Bank project staff, together with a sustained productive working relationship with those responsible for project preparation and implementation on the borrower's side, can also make an important contribution to project success.
P042039 | MZ-Railway & Port Restr (FY00) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/194431475070762471/text/000020051-20140620080711.txt | http://documents.worldbank.org/curated/en/194431475070762471/pdf/000020051-20140620080711.pdf | Outcome indicators should be fully reflective of the expected achievement of the project development objectives. These indicators should be backed by an appropriate framework to facilitate improved monitoring by the implementing authorities, unambiguous evaluation of performance at every stage, and identification of timely corrective actions. Staff rationalization is complex and difficult: successful implementation requires not only a good severance package, counseling services and job training but also a provision for follow up services. Guidance to staff should be continued for a number of years and future progress monitored closely. Railway concessioning and revitalization is complex and time-consuming: it requires a balanced risk sharing structure, a good understanding of the local business environment and of the entire logistics chain, a good marketing strategy and a realistic timeline. Economic and financial analysis should be repeated when project is substantially delayed, prior to the actual investment decision.
P042039 | MZ-Railway & Port Restr (FY00) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2009 | 2012 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/501421468058728106/text/698130PPAR0P000C0disclosed070160120.txt | http://documents.worldbank.org/curated/en/501421468058728106/pdf/698130PPAR0P000C0disclosed070160120.pdf | 4. Conclusions and Lessons 4.1 Lack of close coordination of working on different transport modes impedes greater synergies and a more strategic and holistic approach to transport sector policy and institutional and regulatory frameworks. The two reviewed operations were individually prepared and implemented. Hence, the opportunity was lost to look at the strategy of the entire sector and advise the government on inter-connectivity issues and trade-offs, as well as on ways to improve the sector's funding and spending efficiency. It is also an example where incentives of the various institutions within the WBG and the various donors need to be carefully aligned. While the Borrower needs to take the lead in ensuring a holistic approach to sector policy, this does not exempt the various development partners from their responsibility to bring about a comprehensive view of the sector into the discussions. 4.2 Improved infrastructure does not necessarily ensure efficient trade and logistic networks along infrastructure corridors or across the country. The aspect of regional trade and transport facilitation and logistics comes strongly into play in the case of Mozambique. The areas around Beira, Zambezi Valley, Nacala, and Limpopoâ€”all covered by the railroad corridorsâ€”see their economic potential powered by complementariness with the economies of landlocked neighbors (Zimbabwe, Zambia, and Malawi) whose closest and natural ports are Beira, Maputo, and to a lesser extent Nacala. The central and south railway lines depart from the Beira and Maputo ports, respectively, and connect with a network of primary and secondary roads that extend to Malawi, 41 Zimbabwe, and South Africa (AICD, 2011).While the Railways and Ports Restructuring Project had improved international traffic as an overarching project development objective, the projects had no direct support for transport facilitation and logistic aspects on the transport corridors they were investing on. Besides limited support provided to some standalone specific trade and logistics initiatives, there was little consideration for the importance of linking the transport infrastructure being supported with the need to develop efficient trade and logistic networks along the corridor and across the country. 4.3 Restructuring into leaner organizations is worth attempting in its own right. Successful restructuring requires planning for redundancy payments, pension liabilities and re integration costs of the labor force into the job market. While it is widely accepted that privatization of transport services generally delivers more sustainable results and the enabling environment is well understood, more often than not, the restructuring of parastatals is all that projects are able to achieve and transport services remain in the hands of the state. Even without concessions, lean restructured entities are better placed to run the infrastructure assets in a more commercial way. Supporting governments through these changes and maintaining a neutral partnership is paramount if any progress is to be achieved at all. Despite deciding against privatization efforts, the government and the Bank successfully formed a working partnership to implement CFM's restructuring and achieving solid results in this respect. 4.4 Including extraneous components that are peripheral to achieving the project's objectives result in a project that is too ambitious and complex for the institutional capability of the borrower. This is particularly so due to limited resources and a small window of opportunity to support a specific sector in a given country, especially those benefiting from IDA resources. The Railways and Ports project could have benefitted from a simpler set of components more aligned with the key development objective of the project. In contrast, the roads project included a flexible project design that relies on phased investment plans and annual project reviews that ensured acceptable outputs even under a One of the most promising emerging rail corridors is that running from Moatize to Nacala via Malawi (the north system) which along with Nacala port forms part of a concession. Currently the railway part of the corridor is not complete. There are 200 km of rail missing just outside the Malawi border. As one of the main economic drivers for the development of the Moatizeâ€“Nacala railway is the potential for coal export from the Tete area, and the port of Beira is insufficient to manage the 20â€“25 million tons of coal that can be produced, this necessitates the completion and upgrading of this railway to connect to the other natural exit port at Nacala. As the railway must pass through Malawi, this creates the challenge of defining and relying on regional agreements and building regional infrastructure in coordination with Malawi (AICD, 2011) weak institutional environment and in a post-conflict situation where reconstruction needs were great. 4.5 Given the increasing role of the private sector in many aspects of transport and transport services, there is a growing overlap in activities across the World Bank Group, mounting duplication of skills and escalating inefficiencies; failure to tap into the right expertise of other parts of the World Bank Group results in unnecessary delays, fatigue of all the parties involved, and often failure of private sector initiatives. Project concepts and project documentation fail to show whether other parts of the Bank Group have been consulted, and to give reasons as to why private sector activities are not being undertaken by other parts of the group where the expertise resides and which are best placed to make the initiatives succeed. Selecting the right partner in a concession or in any public-private partnership can determine the success or failure of any initiative. Greater progress, with less fatigue, would probably have been made in finding appropriate partners had the Bank tapped into the right expertise of other parts of the World Bank Group in structuring PPP transactions, discuss the merits and pitfalls of other approaches selecting long-term partners such as multidimensional auctions or beauty contests which may have been more in line with the government's strategy at the time, and ensure that concession contracts specified desired performance outputs rather than inputs. 4.6 The danger to railway concessions of intermodal competition with road transport for freight, and the difficulty for concessionaires to finance substantial investment in track and rolling stock can contribute to the failure of the concessions. There have been important failures in railway concession in the region, most of which have been documented along with evidence on performance (AICD 2009). The experience with intermodal competition between road transport and the Mozambique railway concessions provides further lessons for other railway concessions in Africa. 4.7 Simply involving private concessionaires doesn't ensure sustainability of railway infrastructure. In the absence of a regulatory framework for railways in Mozambique, private concessionaires neglected maintenance and allowed the railway beds to deteriorate to a point that government had to step in with additional costly rehabilitation investments before they could be re-bid.
P042042 | Lake Ohrid Conservation GEF Project (Albania/FYR Macedonia) | Europe and Central Asia | Western Balkans |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/123991475077404818/text/000020051-20140613063938.txt | http://documents.worldbank.org/curated/en/123991475077404818/pdf/000020051-20140613063938.pdf | There is a need to integrate M an initial extension of 18 months and two six month extensions. The short durations of the last two extensions created uncertainty and made planning more difficult. A single, one year extension would have been better.
P042109 | Second Beijing Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2000 | 2011 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/245801474633104267/text/000020051-20140625070851.txt | http://documents.worldbank.org/curated/en/245801474633104267/pdf/000020051-20140625070851.pdf | The following lessons were selected from the "Lessons Learned" section of the ICR (pp.20-21) and condensed and edited.1 .Wastewater Sector Institutional Reform. Sustainable wastewater service provision requires a combination of (i) politically feasible tariffs; (ii) ensuring service provision at low cost; (iii) municipal government assumption of responsibility for servicing debt; and (iv) provision of timely cash transfers to meet shortfalls, especially in relation to new investments.2. Water Re-use. Adequate water re-use in water scarce areas (at least 50%) requires addressing the following: (i) adequate quality and reliability of re-claimed water; (ii) market-related pricing of reclaimed water; and (iii) analysis of the costs and benefits of using water supplied through the system vs. reclaimed water.3. Participation of International Experts and Sharing of Knowledge. The utilization of international expertise is important for the effective adoption of a new technology, such as natural gas boiler technology transfer and heating conservation. 4. Intervention in Commercial Operations. In areas involving significant commercial operations (such as boiler conversions), newly established municipal entities with no commercial expertise are not likely to succeed. It might be more effective in such circumstances for a relevant government entity to partner with a commercial company. Alternatively, conversion to the new technology might be left to market forces with some incentives provided to end-users.
P042236 | POWER DEVELOPMENT | East Asia and Pacific | Viet Nam | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1996 | 2000 | 2001 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/789051474512456813/text/000020051-20140529155003.txt | http://documents.worldbank.org/curated/en/789051474512456813/pdf/000020051-20140529155003.pdf | Careful coordination between the Bank, IFC and the Borrower is necessary when preparing fast track projects involving the private sector and IFC financing. The processing of this project was particularly strenuous largely due to IFCâ€™s view that the Project be redesigned to create a separate entity to own and operate Phu My that would include IFCâ€™s participation in the capital structure at the outset. The issue was resolved with the Government deciding that it was not prepared to risk possible delays with the IFC's proposal and that it was not ready to establish a separate entity with a majority private ownership. However, the Government agreed to have Phu My 2-2 constructed under a BOT approach, the condition laid down by IDA to ensure private sector participation. In transitioning political systems, the Bank and the Borrower should have a realistic view of the risks associated with protracted government approval processes.
P042237 | Provincial Infrastructure Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Infrastructure | Transport | IDA | IPF | 1999 | 2007 | 2009 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/152441475068833817/text/000020051-20140619083502.txt | http://documents.worldbank.org/curated/en/152441475068833817/pdf/000020051-20140619083502.pdf | Key lessons from the ICR included:Project funding for components designed to meet the project objectives (including poverty reduction) should be allocated among local provinces according to performance-based criteria.Especially when local capacity for project preparation is weak, the design of key components should be well advanced prior to project start-up if not appraisal.Consideration has to be given early--within the same project, or a follow-on operation--to solutions to the increased production of waste water that inevitably follows the expansion of water production and distribution. In addition to providing road (or any other) infrastructure, there have to be appropriate measures to prevent its use by vehicles whose weight exceeds the design limit of the pavement.IEG adds:In designing road infrastructure, it is important to take into account the likely demand. This would include projected volumes of traffic and vehicle types. If the latter will include heavy trucks and buses, then the standards of the design should be able to meet that demand.Especially in remote areas of countries that have had no experience of working with the Bank, a thorough appraisal of the local institutional capacity should be part of project preparation, leading to proposals within the project itself to remedy shortcomings. Inadequate financial management and weak local planning are key shortcomings that need to be addressed.
P042237 | Provincial Infrastructure Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Infrastructure | Transport | IDA | IPF | 1999 | 2007 | 2011 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/807411468266673467/text/620730PPAR0P070e0only0900BOX361491B.txt | http://documents.worldbank.org/curated/en/807411468266673467/pdf/620730PPAR0P070e0only0900BOX361491B.pdf | 6. Lessons 6.1 Within a broader national and international context of buoyant economic growth, new and upgraded infrastructure can help integrate poorer remote areas of a country and contribute to reduce their poverty. This project's improved road infrastructure gave the beneficiary provinces better access, allowing them to keep pace with South-East Asia's rapid economic growth, contributing poverty reduction. 6.2 Infrastructure that foments economic growth can also trigger unexpected demands for the infrastructure itself. This requires continuous monitoring to identify problems and inform appropriate responses. In the case of this project, the success of economic integration means that the roads are carrying much heavier trucks than they were designed for. More intense maintenance, strengthening the pavement or restricting vehicle weights are among possible responses. The chosen response has to be within local financial and management capacity constraints. 6.3 On-the-job training prepares local officials and professional cadres to carry on the work of development assistance after a project has closed. It could be eligible for project funding. Formal training programs and courses have roles to play, too, but project design and implementation should ensure that the learning from them is relevant to achieving an operation's intended outcomes.
P042263 | TELECOM REG & PUBL.. | South Asia | Sri Lanka | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/535911474589866614/text/000020051-20140602112231.txt | http://documents.worldbank.org/curated/en/535911474589866614/pdf/000020051-20140602112231.pdf | (1) To be effective, regulatory authorities need complete institutional autonomy and adequate powers, backed by appropriate legislation. This will foster greater private sector confidence and willingness to invest.(2) A transaction oriented approach that focuses on maximizing privatization proceeds can be at the expense of long term goals of the development of a fully competitive market. Greater consideration needs to be paid to the trade-offs between these approaches.(3) Reforms should give appropriate focus to rural access by stipulating roll out obligations and service targets in operating licenses.(4) Delays in complex procurement activities could have been mitigated by the early implementation of a training program on procurement and bidding procedures.
P042266 | Teacher Education and Teacher Deployment | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 1996 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/154141475084380201/text/000020051-20140615102218.txt | http://documents.worldbank.org/curated/en/154141475084380201/pdf/000020051-20140615102218.pdf | Excessive teacher deployments and the provision of higher education through teacher training institutions may constitute political benefits for strained countries in civil conflict. Clear government commitment is needed to rationalize a sector that offers many jobs to people, particularly in rural areas. -Successful project implementation depends on adequate and trained staff in financial management and procurement are in place prior to commencing implementation.-To ensure successful implementation of policy reforms which depend upon completion of prior inputs, broad stakeholder consultations and sufficient time are needed; without substantial agreement, reforms may flounder in a weak political environment.-Before a functioning strategic entity is dismantled, a replacement institutional structure should be established to ensure continuity of sector or project policy, planning, coordination and implementation.
P042268 | TH-Distr. Autom & Relia | East Asia and Pacific | Thailand | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/475411474508929408/text/000020051-20140613064023.txt | http://documents.worldbank.org/curated/en/475411474508929408/pdf/000020051-20140613064023.pdf | In promoting complex power sector reform agendas, the Bankâ€™s optimal role is that of an advisor and facilitator, which requires a keen understanding of the local political economy. In this project, the Thai push for full liberalization yielded only small efficiency gains (because the utilities were already efficient, and there were too many entrenched bureaucracies and special interest groups) and did not address the more critical issue of the fiscal and financial performance of the Thai electricity supply industry.For the Bank to play an effective advisory role, knowledge of the incentives of different players is required, in order to determine the most pragmatic route to improved sector efficiency as well as the most realistic timing and sequencing of reform steps, as governments and circumstances change. In the event of a crisis (which this project encountered), this knowledge would enable the Bank and the borrower to keep the reform goals and processes durable, minimize being driven by disparate pressures, while at the same time respond to the crisis by restructuring investment plans, exercising great financial discipline, and intensifying efforts to improve operational efficiency to cut costs.The Bank needs to focus on countries that have already embarked on the path of power sector reforms, and where utilities already actively support the reform agenda. For this purpose, the Bank needs to put greater emphasis on developing staff skills in understanding the local political economy and acquiring knowledge of the incentives of different key players.
P042287 | ECAL I | Middle East and North Africa | Tunisia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1997 | 1998 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/434961474588211484/text/000020051-20140521042026.txt | http://documents.worldbank.org/curated/en/434961474588211484/pdf/000020051-20140521042026.pdf | More highly-focused adjustment lending--complemented by TA, ESW, and public education--is required to make significant progress in privatization, and in the shipping and telecomms sectors.
P042287 | ECAL I | Middle East and North Africa | Tunisia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1997 | 1998 | 2005 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/231191468760755829/text/31017.txt | http://documents.worldbank.org/curated/en/231191468760755829/pdf/31017.pdf | Lessons Learned 4.6 The main lesson are\. e Tunisia's successful economic performance hasbeendue to three attributes\. ownership andbroadpolitical consensus, awell-developed humanresource . base, and a stable macroeconomic environment. e Experience inprivatization andthe financial sector shows the need for the Bankandthe development partnersto staythe course andshow flexibility intheir support, providedthere is evidenceofgenuine andsustainedreform efforts. For example, by acceptingpartialreforms insome areas, and l2 The prior authorizations of investment are numerous and ihbit startups. Inefficient operations and the lack of competition and the dockers' monopoly are amongst the issues cited inthe Bank's 2000 Private Sector Assessment Update. Since then, under E C A L 111, 60 percent o f all prior authorization for start-ups were removed. Customs documentation has been simplifiedbut the ports still constitute a major bottleneck, leading to hghcosts and delays. Goods untilrecently spent up to 18 days instorage inport because traders usedit as a substitute for inland storage. Recent reforms are reportedto have greatly reduced clearance times for goods to 4 days. buildingonpartial successesto deepenthem insubsequent operations, the support fkom the Bank andother partners was ultimately effective. Patience, perseverance and flexibility paidoff. a An important lessonfor other small emerging countries seekingto laythe foundations for sustainable growth andpoverty reduction i s the success o f Tunisia increating a competitive economy by the coordinated use o fmacro andstructuralpolicies andreforms.
P042299 | CN-Tec Coop Credit IV | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 1999 | 2010 | 2011 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/176271475081918839/text/000020051-20140624162854.txt | http://documents.worldbank.org/curated/en/176271475081918839/pdf/000020051-20140624162854.pdf | Strong government support, reasonable sub-project design, and steady project management team are key factors for the success of the project (Borrower's ICR)A results framework that clearly identifies the desired outcomes is important in a demand-driven project. To be fully effective, however, sub-project proposals should explicitly link the sub-project objectives and associated monitoring indicators with the overall desired outcomes.
P042305 | PRIMARY EDUCATION PROJECT | Eastern and Southern Africa | Malawi | IDA |  | Human Development | Education | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/154401474554982670/text/000020051-20140602113752.txt | http://documents.worldbank.org/curated/en/154401474554982670/pdf/000020051-20140602113752.pdf | On a project with the primary objective of education quality improvement, more attention should have been given to high-impact inputs like teacher training and the provision and effective use of instructional materials, rather than to classroom construction.Project implementation arrangements need to be premised less on Bank policies and dispositions, and more on unique country realities. For instance "Substantial roles allocated to communities and NGOs despite their evident capacity limitations seem to have been more guided by the Bank's emphasis on working with communities and civil society than on Malawi realities." The role of the PIUs was "de-emphasized" despite the clear capacity limitations and lack of capacity development plans for regular Ministry structures.
P042399 | Power System Improvement Project | Europe and Central Asia | North Macedonia | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/121051474573295588/text/000020051-20140613084706.txt | http://documents.worldbank.org/curated/en/121051474573295588/pdf/000020051-20140613084706.pdf | A carefully-staffed and well-functioning Project Implementation Unit (PIU) is very important to project success. In order to do so, PIU members should be released from any other obligations at the company, so they can concentrate on the project tasks.Splitting a whole project into several smaller subprojects based on the nature of the components and consequently hiring different contractors for each of the subprojects can reduce project costs. However, in order for the benefits to be materialized, a competent and diligent PIU is essential. In the case of Macedonia power system improvement project, the project was divided into five packages and was awarded to different contractors for each package. By splitting project into several packages each contractor faced substantially less risks and therefore reduced the total project costs. However, this placed considerably more responsibilities on the PIU and required the PIU to closely monitor more than 20 contracts. A capable and trustworthy PIU is the precondition to the success of such an approach.
P042400 | Financial & Enterprise Sector Adjustment Loan 2 (FESAL 2) | Europe and Central Asia | North Macedonia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2001 | 2004 | 2005 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/428431474657953082/text/000020051-20140612142928.txt | http://documents.worldbank.org/curated/en/428431474657953082/pdf/000020051-20140612142928.pdf | 1. Projects design and quality at entry are substantially enhanced by drawing lessons from the shortcomings of past projects. This project benefitted by developing specific measurable triggers for tranche release, and focussing clearly on priority issues, based on the lessons and shortcomings of previous Bank-supported enterprise and financial sector reforms in Macedonia. 2. Coordinated donor support can be very useful in providing technical assistance. 3. Social mitigation (in this case supplied through a separate Bank operation) can play a crucial role in developing ownership and broad support for adjustment operations.
P042414 | MA-COOR/MON SOCIAL PRO | Middle East and North Africa | Morocco | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/681151474482251666/text/000020051-20140612133742.txt | http://documents.worldbank.org/curated/en/681151474482251666/pdf/000020051-20140612133742.pdf | Use of labor-intensive methods to create rural infrastructure has dual benefits of creating infrastructure and transferring income to poor rural families which provide a possible alternative to the current fashion for community-driven approaches.Arrangements for sustainability need to be clearly understood and agree prior to investments taking place; this project did not create such understandings with consequent adverse consequences, specifically irregular maintenance of roads.A multi-sectoral approach can work, and need not imply a single multi-sectoral project. By splitting a larger project into three separate parts, this project side-stepped the coordination problems that frequently beset multi-sectoral interventions.The Bank and borrower should assess the social and political implications of proposed legal covenants before agreeing to them: the legal covenant required that EOO be reoriented from urban areas to support the rural poor, but EOO is part of the country's safety net scheme in urban areas and attempts to reduce it proved political sensitive.
P042415 | SPI - HEALTH | Middle East and North Africa | Morocco | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/314221475101110869/text/000020051-20140612141503.txt | http://documents.worldbank.org/curated/en/314221475101110869/pdf/000020051-20140612141503.pdf | Physical access to facilities does not automatically translate into utilization.Manpower rationalization, deployment, and training is at least as important as the construction and equipping of the facilities to achieve the project objectives.The difficulty of implementing coordinated projects can readily be underestimated.Clearly identified baseline data, with subsequent follow up, is crucial for assessing the project needs and effectiveness.
P042442 | Sierra Natural Resources Management & Poverty Alleviation Project | Latin America and Caribbean | Peru | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/797391474503959346/text/000020051-20140612153350.txt | http://documents.worldbank.org/curated/en/797391474503959346/pdf/000020051-20140612153350.pdf | Poor farmers will successfully adopt tried and tested technical packages.Unlike technical packages, participatory planing and micro-catchment management strategies cannot be "pulled off the shelf" and require substantial time and commitment to bring to fruition. In projects of this nature it is important to get the balance right between investments in works and investments in institutional development. Community procurement arrangements have the potential to empower beneficiaries but will not prosper if the Bank is inconsistent and tends to fall back on more standardized, centralized approaches.
P042516 | PUBLIC ENTERPRISE/PR | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2004 | 2006 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/345141474908007529/text/000020051-20140613055233.txt | http://documents.worldbank.org/curated/en/345141474908007529/pdf/000020051-20140613055233.pdf | An ambitious privatization program should be well sequenced within a long time-frame, taking into account many factors necessary for its achievement (e.g., consistent government commitment across time, political realities of the country, labor/redundancies issues, and a conducive business climate).
P042540 | ID-IODINE DEF. CONTROL | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/258761474586924551/text/000020051-20140612142030.txt | http://documents.worldbank.org/curated/en/258761474586924551/pdf/000020051-20140612142030.pdf | The project design (M&E system) which provided for good data collection, analysis and use, enhanced project management and effective health policy making.Central block grants to local (district level) proposals against set criteria, proved to be a very successful decentralization mechanism, building both institutional capacity in local government and their commitment to sustaining project initiated activities after project completion.Social enforcement activities involving women's groups and NGOs are good options in the absence of an effective legal environment. This is particularly true if their activities and findings are disseminated through advocacy workshops with government officials and parlimentarians.
P042565 | Rural Poverty Alleviation - Paraiba | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/853491475094345463/text/000020051-20140617140502.txt | http://documents.worldbank.org/curated/en/853491475094345463/pdf/000020051-20140617140502.pdf | Based on the ICR, the key lessons are:Community-driven approaches can reduce bureaucratic and administrative obstacles by reducing the distance between decision-makers and beneficiaries. However not all the challenges in implementing such approaches can be visualized upfront. Hence the importance of an efficient monitoring and evaluation system to report on both quantitative and qualitative goals is essential. Electricity and water supply investments can have an immediate impact on quality of life. Political, bureaucratic and financial impediments to implementation require astute supervision with clear objectives.Loan size should be calibrated to Borrower fiscal capacity.
P042566 | Rural Poverty Alleviation - Pernambuco | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/200211474555226810/text/000020051-20140607162727.txt | http://documents.worldbank.org/curated/en/200211474555226810/pdf/000020051-20140607162727.pdf | The main lesson refers to the successful use of the R-NRDP new model for rural poverty alleviation. Following piloting in the 1990s and drawing from some well tested principles (Rochdale, Community Development, Comilla, Daudzai and AKF programs) the project demonstrated again that such an approach enables poor people with a little guidance and seed resources to improve their communities by selecting and implementing small-scale investments. The value was proven of decentralization, social organization and social capital formation, community participation with TA where necessary, demand-driven investment choice, institutional transparency, poverty targeting, M&E/MIS to evaluate and adjust on the go, and eventually community graduation to self-sufficient development. The missing link of the absent final impact evaluation is a further lesson of the importance of such documentation in completing the record and substatiating that the overall objective was achieved.
P042568 | Coastal Wetlands Protection and Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/462061474853729922/text/000020051-20140619082346.txt | http://documents.worldbank.org/curated/en/462061474853729922/pdf/000020051-20140619082346.pdf | 1. The use of Community Boards in supervision and monitoring of project investments at the commune level can enhance transparency and accountability.2. Making special efforts to ensure that land titles and land rights include the names of husband and wife, can prevent injustice and abuse and give husbands and wives equal say over the use of the land and the decision on whether and how it should be used for collateral. 3. The establishment of contractual arrangements with small farmers to promote environmental restoration and related supervision and maintenance can work very well and is a model worthy of wide replication.
P042568 | Coastal Wetlands Protection and Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2008 | 2009 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/188211468130815035/text/487560PPAR0MUL1C0disclosed071231091.txt | http://documents.worldbank.org/curated/en/188211468130815035/pdf/487560PPAR0MUL1C0disclosed071231091.pdf | LESSONS 8.26 The projects' experience suggest the following lessons\. The achievementsof Bank-financed waterprojects in many subsectors are often constrainedby environmentalproblems thatpre-dateproject appraisal. InVietnam it is increasingly likely that projects that build water infrastructure will be called on to perform environmental restoration as well as their core activities, ifthey are to have sustainable outcomes. The four projects studied share certain characteristics. First and foremost i s the nature o f their relationship to the environment. Whereas traditionally Bankwater sector projectshadeither aninstitutional or infrastructurefocus or both, it is becoming nearly impossible to avoid addressing environmental restoration and environmentally related landuse questions inmany areas o f the country. InVietnam . (which i s not uniqueinthis respect) Bank-financed projects inmany sectors are increasingly constrained by environmentalproblems that pre-date project appraisal. Inthe 37 Vietnam's Infrastructure Challenge\. Water Supply andSanitation Strategy, Staykovaand Kingdom, The World Bank,2006. four evaluated projects it was assumed that investmentsininfrastructure would overcome what were inessence environmental problems. The project experience o fthe IRP, WSP, Inland Waterways, and CWP projects showsjust how difficult it has become, even in widely different subsectors focusing on highly divergent activities, to achieve anything lasting without addressing the problems that have beencausedby an extended period o f environmental neglect. Environmental restoration is challenging because thepeople causing theproblem have to becomepart of the solution. Ifall the mangroves have been destroyed it i s never enoughjust to plant new ones\. reforestationand forest protection have to address the underlyingsocial causes of encroachment andprovide alternative sources o f income if they hope to stop environmentally negative actions that produce income for the malefactors. Conversely, addressing livelihood problems can have positive environmental impacts . Waiting to confront major issues on which the Bank and borrower disagree until after loan approval can lead to major delays, enormous costs, andforegone opportunities. While there were other factors contributingto the early-stage delays identified inthis report, resolving policy differences between Bank and Borrower before Board approval i s perhaps the easiest to correct. A common problem, associated with the design ofthe four water-related projects evaluated inthis report, i s that important aspects o f each project were not ready to implement after the loan was approved. Highlevel engagement i s needed to find a way to move project preparation further along and speed up implementation. When the economic incentivesshift, thepriorities of water serviceproviders willfollow with negative effects on the environment. As users become accustomed to not paying fees, service providers become accustomed to not thinking about them as clients. Although the country was moving towards integrating user charges and fees to support institutional and service sustainability, the recent suspension o f most user charges for the use o f irrigation water and river transport, as well as the freezing o f urban water tariffs are quite an about-face. Subsidized water for urban users further strains existingsupply andtreatment problems, and the removal o f incentives to conserve water use inirrigated areas has several pernicious results including higher levels o f agricultural chemicals that make their way to the rivers, which are tapped for drinkingwater, and so on. Water resources are dijjicult to manage efficiently and effectively when there is no mechanismfor involved agencies to communicate, much less coordinate. The four projects point to a number o f challenges which Vietnam needs to overcome to progress towards integrated water resources management. First, that key players have a longway to go before they integrate. Agencies that should be talking to each other and planning ways to maximize synergies are not yet at that point. Second, there i s still greater emphasis and attention givento end o f pipe solutions that increase the available supply thanto managing the watershed inways that will make the delivery ofwater services easier inthe next year and during those that follow. Water utilities are more concerned with gettingpollutants out ofthe water they deliver than they are about stopping polluters. And around the major cities new factories open at an alarming rate. Third, the abolition of economic incentives to conserve and make services economically sustainable (use charges and tariffs in line with costs) poses risks for water quality and river health going forward, and increases the likelihood that conflicts over access to water between various user groups will increase; and this ina hture where climate variation looks likely to reduce supply.
P042573 | Central Asia Biodiversity GEF Project | Europe and Central Asia | Central Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1999 | 2006 | 2008 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/595411474850856203/text/000020051-20140617133643.txt | http://documents.worldbank.org/curated/en/595411474850856203/pdf/000020051-20140617133643.pdf | As concluded by IEG's Review of Regional Programs, regional programs often reflect an appropriate rationale for adopting a multicountry approach, such as an ecosystem wide approach to conservation of a hotspot, yet as in this case of the Central Asia Biodiversity project, they are often weakly linked to the country's development objectives, at least as articulated in the Bank's country assistance strategy. A Regional Program, as concluded by IEG's Review of Regional Programs, is more effective when there is a clear delineation and coordination of the roles of national and regional institutions. In the case of the Central Asia Biodiversity project, implementation arrangements were split between regional strategic coordination and national level implementation. The National and Transboundary Steering Committees provided the strategic guidance and coordination, while the national PIUs implemented national activities at national level.The success of regional activities planned through a regional project often depends on the adequate contribution of the national structures. In this case, frequent delay of one of the sides delayed execution of all activities. To avoid such problems it is necessary to strengthen the role of a regional supervisory body, such as the Transboundary Steering Committee.Regional projects are usually challenging in terms of overall management to sustain ownership and commitment from the individual countries. This requires more time to achieve a consensus when this is essential, as in the case of the tripartite agreement to establish the Transboundary Biosphere. Even with the necessary coordinating mechanisms in place, projects should be realistic about the efforts required to harmonize legislation across countries with disparate land ownership and resource rights regimes.
P042622 | Capital Market Development Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2011 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/648481475071528007/text/000020051-20140624203415.txt | http://documents.worldbank.org/curated/en/648481475071528007/pdf/000020051-20140624203415.pdf | When addressing a complex development issue, it will likely be more efficient to design a series of smaller projects rather than a large project which may be subject to changing priorities and government policies over time. Especially for Middle Income Countries, the Bank needs to be flexible in project design. For example, fast track but modest sized TA projects could facilitate more effective and efficient interventions than larger projects for which changes in environment are more difficult to forecast. Strong macro-economic analysis should be an important input in the design of any financial sector operation, since financial sector development is so closely linked to macro developments. A sequence of smaller, well-targeted projects might have allowed the Bank to better adapt to changing client needs over time.
P042720 | St. Petersburg Center City Rehabilitation Project | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/956211474588414974/text/000020051-20140607170029.txt | http://documents.worldbank.org/curated/en/956211474588414974/pdf/000020051-20140607170029.pdf | This project demonstrates the crucial importance of aligning the project design with the set objectives. This lesson is clearly discussed in the ICR and, together with the lessons on the contracting of TA activities and the initial assessment of the reform climate, it covers the most significant findings of this ICR. One might add another lesson on the need to obtain a firm commitment for reforms prior to project approval, a fact that was obviously overlooked in this case.
P042722 | Highway Rehabilitation & Maintenance 2 Project | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2005 | 2001 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/714871474573961717/text/000020051-20140529155441.txt | http://documents.worldbank.org/curated/en/714871474573961717/pdf/000020051-20140529155441.pdf | The key lessons that emerge from this project are:The Bank faces considerable difficulties in operating in countries with uncertain and fast-changing environment as in the case of Russia. When project approval occurs shortly after a major economic crisis, the feasibility of additional borrowing by Regions under the proposed project needs to be carefully reassessed.It is important for the Bank to be rigorous about its audit and accounting requirements.
P042793 | Structural Adjustment Credit (SAC) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1998 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/314911474650114057/text/000020051-20140522105506.txt | http://documents.worldbank.org/curated/en/314911474650114057/pdf/000020051-20140522105506.pdf | Continuity of the core country team, and continuing involvement of sector specialists in general discussion, can be appropriate to promote broad-ranging and effective support for adjustment. Core country teams give added leverage in gaining support for needed reforms. Considerations of financing gaps should not lead to tranche releases if there are substantial shortfalls in policy implementation and lack of government commitment to continuing reform. Intensive supervision is essential with new clients implementing complex reforms.
P042793 | Structural Adjustment Credit (SAC) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1996 | 1998 | 2003 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/945021511185175484/text/multi0page.txt | http://documents.worldbank.org/curated/en/945021511185175484/pdf/multi0page.pdf | 8. Key Lessons Learned\n8.1 When adjustment projects are synergistic with sectoral investment projects,\neffectiveness can be enhanced\. During the course of the 3 SAC projects, investment projects\nlinked to the adjustment program were undertaken in the education, irrigation, and power\nsectors, and considerable synergy with the adjustment credits was achieved. The financial\ninducement of the SACs provided an incentive for the Ministry of Finance to become an\nadvocate for sectoral reforms, and cooperation between ministries was enhanced. However, the\nEnterprise Development Project was not designed as complementary to the SACs, and thus did\nnot achieve synergy.\n8.2 For an adjustment program focused on private sector-led growth, key constraints\nto private sector development must be confronted\. While considerable emphasis was placed\non privatization and financial sector development, insufficient weight was accorded to critical\ncomplimentary aspects of private sector development, including\. a business environment\nconducive to private enterprise and the entry of new firms; effective enterprise restructuring and\ngovernance; building adequate government capacity to support a market economy; and effective\nprocedures for bankruptcy and liquidation.\n8.3 As a reform program advances, progress may become more difficult\. First\ngeneration reforms, such as trade and price liberalization and the promotion of open markets,\ndid not for the most part pose a major challenge to vested interests. However, further progress\ninvolved fundamental changes in political, judicial, and social institutions, and in many cases\nchallenged powerful interests. Bank staff found that overcoming these important opposing\nconstituencies was much more difficult than earlier reforms, and more difficult than they\nexpected.\n8.4 It is unrealistic to assume that if the fundamentals are in place, an automatic\nsupply response will take place\. A key assumption of the Bank\'s reform program was that, if\nthe fundamentals (i.e., first generation reforms) were in place, a supply response (i.e., broad-\nbased growth stimulated by the private sector) would be forthcoming. The Bank vastly\noverestimated the ability of Armenian workers, entrepreneurs, and institutions to overcome the\nlegacy of decades of Communism and the power of indigenous vested interests. Also\nunderestimated was the cost of the breakup of the Soviet Union to Armenia\'s productive assets.\n8.5 Legal reform should take adequate account of enforcement capacity\. Important\nprogress was achieved by the passage of new legislation, and an impressive framework was put\ninto place. However, the adjustment program placed insufficient emphasis on strengthening the\njudiciary and the actual role the legal system could play in furthering an improved business\nclimate.\n8.6 Continuity and dedication of the country team are key to program effectiveness\.\nDuring the six years covered by this PPAR, there was substantial continuity of the task team\.\ntwo Country Directors, three country economists, no more than two TMs for any of the\nadjustment operations. In addition, project supervision and coordination of the country team\n\n\n31\nwith sectoral specialists was very successful. This contributed significantly to Bank\neffectiveness.\n8.7 Turnover among policy officials hindered reform progress\. During the six years\ncovered by this PPAR, there were seven Prime Ministers and four Ministers of Finance. There\nwas also substantial turnover among other officials concerned with implementing the reform\nprogram. For an official contemplating a brief tenure, it is more difficult to appreciate the\nbenefits of reform, and so this turnover made reform progress considerably more difficult.\n\n\n\n33\nREFERENCES\nEBRD, Transition Report 2000.\nFIAS, Armenia\. Administrative Barriers to Investment, May 2000.\nIMF, Armenia Financial System Stability Assessment, March 2001.\nIMF, Recent Economic Developments and Selected Issues, December 2000.\nIMF, Recent Economic Developments and Selected Issues, May 2001.\nNorwegian Refugee Council, www.idpproject.org.\nOxford Analytica, Armenia Financial Sector, July 24, 2000.\nRamachandran, S. Evaluating Adjustment Lending\. Some Suggestions, Informal Paper, August 2001\nUSAID, Investigation of Factors Inhibiting FDI in Armenia, August 1999.\nWorld Bank, Between State and Market\. Mass Privatization in Transition Economies, September 1997\nWorld Bank, Seize the State, Seize the Day\. State Capture, Corruption, and Influence in Transition;\nAnticorruption in Transition, a Contribution to the Policy Debate, (2000).\nWorld Bank, Armenia\. Restructuring to Sustain Universal General Education, Technical Note, 2001.\nWorld Bank, ECSPE, Armenia/Georgia Country Unit, Growth Challenges and Government Policies,\n2001.\nWorld Bank, Armenia/Georgia Country Unit, Public Administration in Transition, September 1996.\nWorld Bank, Armenia/Georgia Country Unit, Public Expenditures in Armenia, November 1997.\nWorld Bank, Armenia/Georgia Country Unit, Armenia CAS, 2001.\nWorld Bank, ECA, Transition After a Decade, November 2000.\nWorld Bank and IMF (European II Department), Poverty Reduction, Growth, and Debt\nSustainability in Low-Income CIS Countries, February, 2002.\nWorld Bank, ECSPF, Armenia Targeted Financial Sector Review, June 2000.\nWorld Bank, LEGEC, Analysis of Public Awareness on Judicial Reforms, December, 1999- January\n2000.\nWorld Bank, OED, IDA Review of Private Sector Development, March 2001.
P042882 | RENW. ENER SMAL PW P | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2002 | 2005 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/349081474503181352/text/000020051-20140612153820.txt | http://documents.worldbank.org/curated/en/349081474503181352/pdf/000020051-20140612153820.pdf | A satisfactory business environment is necessary for success in a market development project.
P042927 | Mekong Transport and Flood Protection Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2011 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/596081475083590154/text/000020051-20140625074411.txt | http://documents.worldbank.org/curated/en/596081475083590154/pdf/000020051-20140625074411.pdf | The following three lessons selected from the ICR are deemed the most significant:Where a road construction industry is dominated by state-owned enterprises, a strategic approach, agreed between the Bank and the Government, is necessary to establish a competitive and efficient market.Better management of capital resources can improve implementation efficiency and reduce delays. A more accurate estimation and subsequent timely availability of counterpart funds, particularly for land acquisition and resettlement, would help keep projects within their expected delivery schedule.The definition of the project development objectives should reflect all project components. In this case, it largely excluded the goals pursued under institutional strengthening. As a result, there were no objectives-level performance indicators targeting technical assistance based activities, such as Ministry of Transport management strengthening or the need for official adoption of updated road and bridge standards.
P042940 | DZ-LOW INCOME HOUSING | Middle East and North Africa | Algeria | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/536891475096985564/text/000020051-20140612103852.txt | http://documents.worldbank.org/curated/en/536891475096985564/pdf/000020051-20140612103852.pdf | (i) It is important to understand the degree of a Borrower's political commitment to a project and how economic and political changes might affect that commitment.(ii) A flexible project design would be useful to facilitate adjustments in the project if policy changes. In designing a project with a phase approach, a well-defined monitoring and evaluation mechanism would be important so that the Bank and the Borrower can monitor performance and make necessary changes.(iii) Up-front commitments from beneficiaries are needed. Once the sub-projects are in place, operators face various resistance from the beneficiaries to pay. Alternative scenarios such as use of resident savings as an incentive and screening device to which subsidies could be attached could have been considered.(iv) Having institutional arrangements for the provision of land tenure is critical for successful housing outcomes.
P042940 | DZ-LOW INCOME HOUSING | Middle East and North Africa | Algeria | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2003 | 2006 | PPAR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/713801468052844398/text/554270PPAR0Box1ficial0Use0Only01061.txt | http://documents.worldbank.org/curated/en/713801468052844398/pdf/554270PPAR0Box1ficial0Use0Only01061.pdf | 4. Conclusions and Lessons 4.1 Both Algeria and Morocco are committed to housing sector reforms, although each country finds itself at a different stage of reform; Algeria seeding it and Morocco sustaining it. The 2003-2008 period under review was a good time for housing sector reform. Economic growth of both countries was buoyant. Reform was needed because of the inadequacies of the existing housing stocks, particularly overcrowded dwellings and poorly constructed units especially in the bidonvilles. Good quality formal houses are in short supply, making them very expensive and inaccessible to the poor especially. Key reform themes that arise from this context include housing finance, slum upgrading and institutional consolidation. All three of the Bank-supported operations addressed one or more of these themes. Thus the Algeria Mortgage TA Project planted some seeds of housing finance reform by helping the banks manage mortgage lending and bringing greater confidence to property titles and their registration. But these were not enough for the mortgage market to function well and at scale as intended, simply because supply-side constraints meant that there were few houses to finance. The connection of Morocco's Housing DPL and the Slum Upgrading PSIA to GOM's Villes sans Bidonvilles Program was a sure way of harnessing these operations to ongoing housing sector reform in the country. It was a two-way interaction with reasonably good results. The operations supporting the reforms underway, and the reforms themselves, particularly the large scale VSB and Al Ornrane consolidation, conferred an importance upon the operations that they otherwise would not have enjoyed in the country. 4.2 Bank support came in the form of three different instruments, a SIL, a DPL and a PSIA. Although the performance across them varied, a variance that had more to do with the housing sector reform context in which they were implemented than the type of instrument used. The experience of these operations demonstrates that reform can be supported by many different types of instruments. The chances of success will depend more upon the local commitment to reform and the diagnosis of it, than the choice of instrument itself. 4.3 The PPAR draws key lessons from the performance of these operations around the three key issues highlighted in the main text of this report, as well as others deriving from the broader assessment of performance summarized in the Annexes. As the operational experience in Algeria and Morocco were so different, the lessons are grouped separately for each country. ALGERIA o Seeding housing reform by focusing upon a selected bottlenecks-such as in bank processing of mortgage loans and in the registration of property titles---cannot guarantee that the reform will take root. Even if they constitute necessary conditions for reform, they must be calibrated with other actions-to ease the supply of new housing, for example-to achieve the well-functioning markets promised by the housing sector reform. o When sector reform is embryonic, support at the early stages needs to concentrate on the most basic and urgent changes and improvements. In the case of the Algeria, this means focusing first upon strengthening the primary mortgage market. This has to be well established before reform can move on to consider more sophisticated instruments of housing finance, such as mortgage insurance and securitization. The latter did not take root in the Algerian case. o Housing sector reforms need to be calibrated and synchronized in order to succeed. In Algeria, improving the origination and processing of mortgage loans went ahead even though demand for such loans was weak. In such cases, reform measures might need to be scaled back or delayed. o The success (or failure) of housing sector reform requires readily available data and information to demonstrate the results of reported changes and to measure the baselines prior to these changes. The lending and other operations that support the reform can themselves support and include actions to encourage greater dissemination of data and information upon their sector. MOROCCO o Policies and programs aimed at achieving cities without slums need to treat slums as a dynamic feature of urban development. Without appropriate urban planning and land use controls, the formation of new slums can overwhelm the achievements of upgrading and redeveloping existing ones. o For housing reform to be sustained, it is important to modernize and consolidate the institutional framework for taking the reform forward through a powerful and financially sound agency such as A Z Omrane that enjoys hi1 government support. o A sector policy loan can perform well and help achieve reforms if it has realistic objectives that focus upon pursuing a few well-chosen prior actions and triggers, as was the case of the Morocco Housing DPL. o Sector reform is more likely to succeed if harnessed to a flagship program that is well understood by all stakeholders and beneficiaries, such as the VSB Program in Morocco.
P043101 | RY-FINANCIAL SECTOR ADJ. CREDIT | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1998 | 2000 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/913061474577310615/text/000020051-20140602104907.txt | http://documents.worldbank.org/curated/en/913061474577310615/pdf/000020051-20140602104907.pdf | (i) Several second tranche conditions were restricted to "preparing and adopting action plans" . In retrospect, such conditions should have been included as effectiveness conditions, with full implementation of the actions plans as conditions for final tranche release. (ii) The project would have benefited from collaboration with other donors during preparation to arrange grant technical assistance funding.
P043102 | SOCIAL FUND II | Middle East and North Africa | Egypt, Arab Republic of | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1996 | 2001 | 2002 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/474001474895659439/text/000020051-20140604061211.txt | http://documents.worldbank.org/curated/en/474001474895659439/pdf/000020051-20140604061211.pdf | 1. Project objectives should be defined in terms of the intended development impacts, the project should be designed implemented to reflect these, and project outcomes should be regularly monitored to ensure optimal results. 2. In order to ensure sustainability of benefits, operations & maintenance arrangements must be carefully planned early on and should not be automatically assumed.
P043109 | PUBLIC WORKS PROJECT | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1996 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/930031475068930419/text/000020051-20140529161522.txt | http://documents.worldbank.org/curated/en/930031475068930419/pdf/000020051-20140529161522.pdf | From the Bank ICR:Adoption of an appropriate project design supported by good implementation arrangements can deliver substantial benefits. This would include detailed, adequate and up-front arrangements to handle human relations (especially coordination procedures between government agencies and ministries), as well as employing competent project staff and providing the right salary and incentives.Requiring measurable local stakeholder participation helps to target results and ensure sustainability, but it also requires appropriate skills and effort;It is not necessary to create a bureaucracy to deliver substantial development benefits on a large number of sites;Good and transparent business procedures lower costs and build up institutional capacity and development. This would include the recognition that small contracts require their own set of simple and straight forward procedures and documents.From the Borrower ICR:Long term sustainability can be achieved if community involvement in operations and maintenance occurs in all sub-projects irrespective of their source of funding.Non-institutional (informal sector) contractors can perform satisfactorily and abide by procedures given the right framework for enforcement.From OED:For sustainable results, project management need to ensure that, where the future operations of a sub-project depends upon government financial and technical support, such support is confirmed with high level authorities prior to the start of implementation.Sub-project selection driven by community demand may have to be constrained. In this case, the community wanted many more education sub-projects than the PMU allowed, and community demand for sanitation sub-projects was very weak, despite the environmental objectives of the project.
P043124 | Health Project | Eastern and Southern Africa | Eritrea | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/339661474566323030/text/000020051-20140613064107.txt | http://documents.worldbank.org/curated/en/339661474566323030/pdf/000020051-20140613064107.pdf | Avoid ambitious development objectives and inappropriate key performance indicators, especially in post-conflict and ongoing border dispute situations. Be realistic and modest with what one project can achieve.Follow the principle of the Bank's Log-Framework (or Result Framework) in project design and M&E. Avoid using higher level objectives (such as mortality reduction) as project development objectives.Project design should be built on solid economic and sector work (ESW). This project suffered from a lack of analytical work in the country. Looking back, some health sector analyses, particularly on the status of the country's primary and secondary health care, would have helped the project preparation significantly and would have improved quality at entry.
P043124 | Health Project | Eastern and Southern Africa | Eritrea | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2009 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/501291468027274736/text/485690PPAR0p101C0disclosed071141091.txt | http://documents.worldbank.org/curated/en/501291468027274736/pdf/485690PPAR0p101C0disclosed071141091.pdf | Lessons 4.2 Inpost-conflictsettings engagement is a means to an end, and needsto be accompaniedby a sustainedpolicydialogueto ensure that developmentgains are realized inthe mediumterm. The experience of Eritrea confirms one o fthe lessons from IEG's 2006 evaluation, Engagingwith Fragile States.98Inthe late 1990s the Bank's dialogue with Eritrea's health was highly contentious, but despite the initial technical disagreements the Bank engaged the sector. While the HealthProject was not fully successful, itis unlikely that the development gains inthe decade that followed under the HAMSeTprojects would have been realized inthe absence o f the early engagement inthe sector. The content o f the sectoral dialogue that followed the initial engagement was able to steer the sector from the post-conflict reconstruction mode'' to a development mode.'' The reorientation o f the sectoral priorities was only possible with sustained and sometimes challenging dialogue underpinnedby analytical work. 4.3 Inthe area of HIV/AIDS a demand-drivenmodelof community sub-projectsis moreappropriatefor service deliveryinterventionsthat are responsiveto localcommunity needs (such as home-basedcare, support to orphansandvulnerablechildren)than for preventiveinterventionstargetingstigmatizedriskgroups or stigmatizedbehavior. The community component was based on a demand-driven model that i s implemented inmany AIDS projects. Inthe HAMSeT Control Project the community component financed a combination o f HIV/AIDSprevention, care andsupport activities. The project experience demonstrated that community demand (on which the demand-driven approach i s based) i s sub-optimal as a basis for allocation for programs aimed at stigmatized risk groups or behavior. 4.4 Community activitiesthat are strategicallyplannedand coordinatedwith the local healthauthoritiescan providean importantcomplementto healthfacility-baseddisease controlefforts. Community outreach and community-basedactivities proved to be key elements o f the highly successful malaria control efforts. Malaria agents (specialized community health workers) were trained by the malaria control program and served as health educators, assisted with bed-netdistribution, bed-net re-impregnation, liaison with community leaders and coordinating o f community source reduction efforts. Inaddition, they provided a link between communities and the health systems, referring complicated cases to health facilities and 98. IndependentEvaluationGroup, 2006. participating incase reporting for M&E. Incontrast, some o f the deficiencies o f the tuberculosis control efforts can be linkedto the limitedcommunity involvement. The NTCP was based on a health facility-centered model o f disease control and strongly relied on passive case detectionfor tuberculosis control. There was only limitedoutreach to communities causing case detectionto be one o fthe weakest aspects o f the NTCP. It is a missed opportunity that there has not been greater learning and sharingo f practices across these two disease control programs. 4.5 Disease control projects can be complementary to-and need not u n d e r m i n e cross-cutting health system functions. Inthe HAMSeT Control Project various cross-cutting functions and systems were strengthened (e.g., healthpromotion, disease surveillance, laboratory service, drug distribution) because the sector's leadership sought to achieve programmatic efficiencies across individual disease control programs instead o f duplicating these systems for each disease control program. This experience i s particularly important giventhe debates inthe international health community about the negative impacts o f disease-specific projects on health systems. 4.6 Multi-sector projects, such as A I D S projects, achieve better results if the sectors involved are strategically chosen according to their comparative advantage in disease prevention and control. The HAMSeT Control Project prioritized the participation o f sectors based on the comparative advantage o f each sector inHAMSeT disease control, allowing the country's disease control efforts to balance comprehensiveness with selectivity inorder to achieve maximal disease impact. Value-added 4.7 The most important areas o fvalue-added o fthe Bank can be dividedinto the following areas\. a) Scale. Against the counterfactual o f no Bank support, all officials felt that the interventions under the HealthProject as well as under the HAMSeT Control Project would have been implemented but at a smaller scale and with fewer resources. b) Community-based approach. A key contribution o fthe Bank was stressingthe importance o f community action to complement the increase inservice delivery offered by the MOH. According to interviewees, without the Bankthe M O Hwould have focused mainly on the supply-side (i.e., service delivery), but not on the demand-side (raising community awareness or generating demand for services). An important caveat is that community involvement has to be strategically plannedand coordinated with the local disease health authorities inorder to complement health facility-based disease control efforts. c) Bank involvement brings credibility and international approval. The Bank was, and continues to be, a respected partner. Both projects were o f a large scale and relatively complex. Particularly with the first project the government needed the Bank's support and impliedapproval because o f the weight it carries interms o f getting support and approval o f the rest o f the multilateral and bilateral donors. Imulementation support andtechnical advice. The achievements under the two projects strongly benefitedfrom the Bank's technical advice and implementation support. These were particularly important inan isolated country such as Eritrea. While not uncritical o f the Bank,various M O H staff as well as donor partners acknowledgedthe Bank's support inthese two areas. This value addedwas particularly noticeablewith the initiationo fthe GFATM activities-which occur largely inthe absence o f the implementation support and technical advice. Readiness to accept GFATM assistance. The foundation laid by the HAMSeT Control Project and its successor was a key contributor to the country's ability to qualify for and successfully utilize the Global Fundresources. This i s not a trivial achievement giventhe country's isolation and dire economic situation. The Bank's value-added has evolved over time. Inthe 1990sthe Bankwas primarily viewed as a source o f financing for infrastructure improvements. This evolved over time, as discussed earlier, to a partnershipthat spans hardware and software interventions. A trusted relationship has evolved over time that has formed the basis o f a strong sectoral dialogue, although this does not imply that the M O H or the GOE agrees with all the Bank's policy recommendations. With the increase inGlobal Fundfunding, the importance o f the Bank's financing for disease control has reduced, and the Bank i s increasingly focusing on under-funded priority areas such as human resource strengtheningand reproductive health. RemainingChallenges 4.9 The Eritreanhealthsector has experienced significant changes since independence, startingwith reconstructiono fdevastated healthfacilities, expansion of disease control efforts focusing especially on the HAMSeTdiseases, and now a strong focus on reproductive health and humanresources. There are several challenges remaining, andtwo are highlightedhere. 4.10 Improving sectoral efficiency. Hospitals account for half o fthe MOH's total expenditure yet hospitals operate at very low levels o f efficiency, evidenced by the low bed occupancy rates.99 The challenging economic environment will continue to place pressure on the MOH's resources, and heightenthe need to ensure optimal returns to existing health expenditure, especially hospital spending. A candid assessment i s needed by the M O H to explore ways to improve the efficiency o f hospital service delivery-for example, through outsourcing o f excess hospital capacity inurban centers where appropriate, reduction o f untapped capital investments through selling o f new and unusedhospital equipment especially inthe new hospitals, management training for hospital superintendants, and establishing hospital performancetargets and monitoring hospital management performance. 4.11 Getting the most out of disease-specific development assistance.The HAMSeT experience has demonstrated that disease-specific resources can contribute to improving various systems inthe sector (for example, disease surveillance, laboratory services, and drug 99. In2005 hospitalsaccountedfor 47 percent o f MOH expenditure(2005 World Bank 2008b). The median bed occupancy rate for the country was 42 percentbasedon 2006 HMIS data (MOH 2007a). distribution) without losingthe focus and outcome orientation of diseasecontrol programs. The availability of large amounts of development assistancethrough the Global Fundprovides another opportunity to improve health outcomes among the poor while strengthening the systems necessary for the sustainability of the diseasecontrol efforts. Indoing so the Eritreanhealth sector will move beyond the vertical versus horizontal debates, and give practical meaningto the call for synergy betweendisease control and systems strengtheninginthe Bank's new 2007 HNP Strategy.
P043163 | FEDERAL ROADS MODZTN | Latin America and Caribbean | Mexico | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 1999 | 2001 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/492241474564447936/text/000020051-20140529155357.txt | http://documents.worldbank.org/curated/en/492241474564447936/pdf/000020051-20140529155357.pdf | The key lesson that emerges relates to the need to carefully assess the borrower's ownership of the project's objectives, including improvement of resettlement practices in the course of preparation and appraisal. Without strong ownership, the project is likely to be less resilient to unforeseen risks, as illustrated by the experience of this project.
P043178 | Irrigation & Drainage 2 Project | Europe and Central Asia | Albania | IBRD |  | Sustainable Development | Water | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/454801475075539626/text/000020051-20140613082001.txt | http://documents.worldbank.org/curated/en/454801475075539626/pdf/000020051-20140613082001.pdf | Participation of farmers in the operation and maintenance of irrigation systems allied with measures to ensure the up-front co-financing of rehabilitation and improved governance yields high returns.Ensure balanced attention to institutional support and capacity-building. While bypassing ineffective ministries and line agencies through establishments of independent PMUs may facilitate efficient project implementation, it must be recognized that they do have an important coordinating, policy, regulatory and monitoring functions that also needs to be strengthened.
P043195 | Rijeka Gateway Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2004 | 2013 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/788041474895166761/text/000020051-20140626105943.txt | http://documents.worldbank.org/curated/en/788041474895166761/pdf/000020051-20140626105943.pdf | Project complexity, especially requiring inter-agency cooperation, increases implementation risk, This multi facetted project, not only involved large civil works in difficult terrain for the roads and the port, but also the encouragement of private sector participation, a staff redundancy program and the resolution of institutional issues at the interface between the port and the city. The urban component could easily have been dropped without materially compromising the project development objectives and the road component (dealing with different implementing agencies) could, if necessary, have been a separate project to simplify coordination.The results framework should link the project actions with outputs and the achievement of objectives. In this context the framework should be relatively uncomplicated and data collection should be within the implementing agencies' capacity's to collect and manage the data. This also means that the time frame to deliver on the targets set should be realistic. If during implementation, it becomes clear that the framework needs revision this should be done formally as soon as possible.The implementation of project activities that depend on legislative changes increases project risk. Legislative hurdles are sometimes beyond the control of the implementing agencies and a specific investment loan may not be the best financial instrument to make progress in such an environment.Institutional reform requires commitment from the Government and built-in incentives in the project design, since it is natural for an enterprise to resist relinquishing its business through privatization. Although it had a Project Policy Letter and the agreed upon targets, the Bank had limited leverage in moving privatization along. In retrospect, better sequencing of activities with conditions on or incentives for privatization progress might have prompted faster and deeper institutional reform. (From the Borrower ICR). A realistic assessment of the future needs, priorities and capacities is essential in making future commitments. Any potential risks should be identified in project preparation stage and dealt with proactively.
P043231 | Institution Building Technical Assistance | Europe and Central Asia | Tajikistan | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/557591474508958891/text/000020051-20140602111045.txt | http://documents.worldbank.org/curated/en/557591474508958891/pdf/000020051-20140602111045.pdf | With adequate Borrower commitment, a TA loan can be an effective way for the Bank to lay the foundation for and facilitate reformA TA loan is generally more effective if it is closely tied to an adjustment operation
P043254 | Health Reform Support Project (HRSP) | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2002 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/879631475071317358/text/000020051-20140624192104.txt | http://documents.worldbank.org/curated/en/879631475071317358/pdf/000020051-20140624192104.pdf | Focusing on vertical health programs (i.e malaria, immunization) was more appropriate for a country with low capacity, rather than focusing on an integrated approach at the local level.Strong and committed leadership at the highest levels of Ministries is essential for ensuring implementation, particularly in countries where the public sector operates under many constraints such as weak capacity.A detailed M&E plan should be developed at the beginning of the project to ensure that M&E is implemented and utilized. This would likely include surveys/studies to evaluate outcomes and the resources to implement them.Utilizing the PMU of another project that has a proven track record can be an effective way to ensure that the "bricks and mortar" elements of a project are moving forward as needed at the start of the project.The use of a rapid results approach can be very useful to motivate staff and ensure momentum, as it emphasizes clear and realistic targets, assignment of responsibility and provision of support.
P043255 | RY Basic Education Expansion Project | Middle East and North Africa | Yemen, Republic of | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/599131474575567884/text/000020051-20140618083634.txt | http://documents.worldbank.org/curated/en/599131474575567884/pdf/000020051-20140618083634.pdf | In countries or areas where implementation capacity is limited, a single development objective and a simple project design can achieve substantial changes in development trends. Under such circumstances, it may be wise to limit the projectâ€™s scope to a small number of provinces.-Community involvement in the definition of educational needs is important in ensuring the enrollment of poor students. However, clear research evidence is needed to understand better how (or if) parental involvement improves learning outcomes.- Decentralization of task managers to country offices facilitates rapid response to project-related problems as well coordination with donors.
P043310 | COAL ENV & SOCIAL MITIGATION | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1996 | 2002 | 2005 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/186901475100880755/text/000020051-20140612134237.txt | http://documents.worldbank.org/curated/en/186901475100880755/pdf/000020051-20140612134237.pdf | Several important lessons are identified by the ICR. Five are repeated here for their broad applicability:Banks leverage over implementing agencies to take action to change policies or comply with Bank's safeguard policies is substantially reduced if environmental and social safeguard issues are separated from the main investment loan. Safeguard policy frameworks agreed with the borrower needs to be specific and detailed on the obligations of the Borrower regarding assistance and entitlements. Determination of Borrower obligations must not be left to decisions during project implementation. Community development activities such as the IPDPs need to incorporate a clear time-bound exit strategy for external support, to enable an assessment of the performance of organizational arrangements to promote sustainability at a stage, which still leaves time during the project period for follow-up actions where problems exist.Mitigation activities that are implemented to establish compliance with national laws, and which are monitored by state agencies (such as those relating to environmental mitigation) have a higher likelihood of success than mitigation activities that are not subject to similar compliance requirements. The Bank should be actively involved in improving the policy framework in key borrower countries.Resettlement Policy Framework at project design and should include as many options for income restoration as are feasible in a given context.
P043311 | Nepal Power Development Project | South Asia | Nepal | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2003 | 2014 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/454881535088120308/text/Nepal-NP-POWER-DEVELOPMENT-PROJECT.txt | http://documents.worldbank.org/curated/en/454881535088120308/pdf/Nepal-NP-POWER-DEVELOPMENT-PROJECT.pdf | The ICR draws the following three main lessons from implementing this project, with some modification oflanguage:(1) At appraisal, it is necessary to have an analysis of political economy considerations,particularly before investingin a country during an insurgency period.The lack of apolitical riskassessment identifying the key issuesin the case of this project constrained implementation and taking correctiveactions.(2) Adequate preparation forsafeguards (e.g., forthe detailed routesurvey, availabilityof land, and permission for forest clearances),isespeciallyrequired in countries wherethe implementing agencies have less experience in project preparation. For instance, in this project the Environmental andSocial Impact Assessment prepared for the Khimti-Dhalkebar had weak analysis, which contributed to the social conflicts thatsurfaced during implementation.(3) The project design needs to be realistic, particularly incountries with weak implementation capacity. This project with three implementing agencies wasambitious in terms ofaddressing complex and multiple issues faced by Nepals power sector, which included everything from hydro and dieselgeneration, to transmission and distribution, andoff-grid and rural electrification. This necessitatedthescaling-backof project activities duringthe first restructuring.
P043338 | GZ-HOUSING FINANCE | Middle East and North Africa | West Bank and Gaza |  |  | Infrastructure | Urban, Resilience and Land | SPF | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/463451474492449588/text/000020051-20140613075313.txt | http://documents.worldbank.org/curated/en/463451474492449588/pdf/000020051-20140613075313.pdf | 1. Improving access to mortgage financing should be done only once the most important bulding blocks for a housing finance system are in place. 2. A stable political and economic environment are important pre-conditions for a Line of Credit to efficiently develop long-term financial instruments.3. Adequate performance indicators should be used to monitor outcome.
P043339 | GZ-MUNICIPAL DEVELOPMENT | Middle East and North Africa | West Bank and Gaza |  |  | Infrastructure | Urban, Resilience and Land | SPF | IPF | 1996 | 2003 | 2004 | ICRR | >=25 million & <50 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/415301475092957370/text/000020051-20140612101806.txt | http://documents.worldbank.org/curated/en/415301475092957370/pdf/000020051-20140612101806.pdf | Even with the full delivery of the physical outputs of urban infrastructure, actual services and any net benefit flows from them can disappear altogether if war and insecurity prevents the intended beneficiaries using them on the scale for which they were designed.With force majeure, such as the September 2000 intifada, that points to the difficulty of achieving the original project objectives, those objectives should be revised as soon as possible and in an explicit manner so that all parties are fully cognizant and supportive of a new direction that project has to take.There may be a point in project implementation--say when more than 80% of funds have been disbursed--when cancellation of remaining funding and an early closure of the project is a preferred option to costly restructuring and revision of objectives near completion that will have little effect upon outcomes so late in the day. (in this case restructuring occurred when 94% of all funds had already been disbursed).In very difficult conditions--such as the intifada and Israeli response--local government and its agencies are able to demonstrate considerable initiative and resilience, although focus upon day-to-day survival may displace attention from long-term development efforts. Effective lateral support between and coordination among supervision missions of different Bank projects can enable the Bank to respond more effectively to demands by the client, that are evolving and volatile in such difficult conditions as West Bank/Gaza.
P043367 | RY-TAIZ WATER SUPPLY PILOT | Middle East and North Africa | Yemen, Republic of | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/553011475077798699/text/000020051-20140607163224.txt | http://documents.worldbank.org/curated/en/553011475077798699/pdf/000020051-20140607163224.pdf | Several important lessons are identified: It is important to formally revise project development objectives to reflect new circumstances. Piloting new approaches with emergency measures is likely to lead to problems. There is a need for up-front social/institutional analysis that: (a) identifies water rights both formal and informal; (b) identifies other users and their rights and relation to the water rights holders; (c) analyses the existing organizational and institutional structure; (d) conducts a â€œsociopoliticalâ€ assessment of the dynamic and the scope for change; and (e) allows adequate time for the water rights and transformation to be facilitated.It is important to build local support for the project from the beginning and to regularly update community leaders and beneficiaries of project performance.
P043367 | RY-TAIZ WATER SUPPLY PILOT | Middle East and North Africa | Yemen, Republic of | IDA |  | Sustainable Development | Water | IDA | IPF | 1997 | 2002 | 2006 | PPAR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/734051468164976302/text/35004.txt | http://documents.worldbank.org/curated/en/734051468164976302/pdf/35004.pdf | 5. Lessons 66. Sana'a WSSP's success inhelpingto pioneer the establishment o f water sector corporations and to improve corporate management was an important contributioninthe urbanwater sector. However, the main lessons from assessingthe three projects relate to water resources management. The issues underlying the four lessons below have substantially contributed to the lacuna regarding groundwater management, and to the lack o f attention to other related institutional and policy needs. They may also have relevance to other countries with similar gaps. The lessons relate to\. a lack of prioritization, a lack of sector work, a lack of cross-sectoral coordination, and a lack of forward planning\. Lesson1\. Identifyingandtacklingthe dominant issue(s)is keyto a program's relevanceandoutcome 67. There is needto identify andprioritize the issue or issues that really matter\. in Yemen's case, the groundwater depletionissue. It took the Bank nearly 20 years and 20 projects to start to tackle groundwater depletion. Hadgroundwater depletion been prioritized earlier, Yemenwould be inmuchbetter positionthan it i s today. Tackling groundwater depletionhasbecome increasinglydifficult over time\. the technical problems are greater with deeper water tables; the number o f agriculturaltube-wells has mushroomed, the habits andperceived acquired rightso f farmers havebecome entrenched; and urbandemand has expanded rapidly. Mitigatingthe problem would not have been easy even20 years ago, but the complexities and costs o fmitigationtoday are likely to be vastly greater. For both the Bank and Government, a clear andurgent need i s to integrate groundwater resourcesmanagement into project design inall water sectors, whether they beprojects for rural, urban, power, industry or other sectors. Lesson2. A comprehensivestrategy is essential 68. A strategic analysis andprogram approachwas largelyabsent inYemen's water sector for the first 25 years o fthe Bank's involvement. The largelynon-responsive succession o fprojects was the result. Ifa comprehensive strategy hadbeendeveloped earlier, the groundwater issue would likely have receivedattention earlier. The corporate management agenda, only effectivelyintroducedunder the Sana'a WSSP, might also have beenpromoted inearlier projects. The Bank's water programinother aspectsmight also have beenmore relevant\. ininstitutionalchange, pricingpolicy, legislation, regulation and other water related aspects o fYemen's economy and socio-political structure. Lesson3\. Multi-sectoralapproachesandbetter coordinationare needed 69. Inthe caseofYementhiswas largelyabsent. A great improvementwas made in 2003 when a Ministryo f Water and Environment was created andmost water agencies were transferred to be under this ministry. However, irrigation, the largest user o fwater, remains under the Ministry o fAgriculture and Irrigation. Inthe Bank, rural and urban water are typically indifferent departments. Such arrangements can bemanageable if good inter-linkages exist, but this was not the case inYemen. Irrigationhas tended to be seen by agricultural agencies as an input to farming, without broader perspective o fthe needs o f other sectors, while urbanwater agencies have tendedto treat water as a resource to be exploited, with little consideration o f sustainability. Such dichotomies are still ongoing. Sana'a water corporation focuses on water abstraction without consideration for management o f the water resources, while the Sana'a BasinWater Management Projecttries to find ways to conserve and replenishwater. 10.Just as multi-sector approaches needto be appliedto water management, water also enters into similar multi-dimensional needs for other issues. For instance, the cultivation and consumption o f Qat is now a large part o f agricultural area and is significantly usedby adults, especially men. Amongst poorer households Qat can consume a large part o f family income, limitingother expenditures such as on food, clothing and schooling. Qat, with consumption typically starting inthe early afternoon, has also been cited as contributing to lower working hours. Resolving such issues would likely involve multi-sector actions Lesson 4\. Rural-urban water markets needto be developed 70. Expandingurban demand will increasingly needrural-urbantransfer o fwater through an equitable mechanism. Formalwater markets have not yet beendeveloped in Yemen. One adaptation from the usual modelmaybeto use andhelpexpandthe already thriving informal water markets o fprivate truckers (such vendors provide 60 percent o f Sana'a's water). Key adjustment needs would include establishing water rights and a regulatory systemto limit water abstraction to sustainable yield, perhaps largely self-monitored andregulatedbyrural communities. Looking ahead, piloting of practical options should beginnow. 6. TheWay Forward 71. While it has taken an extraordinarylengtho ftime for the Bank andYemen to beginreorientingapproachesto better tackle the strategic needs o fYemen's water sector, a major move forward has occurred over the last several years. Early elements o f change are found inthe three projects themselves\. LWCP pilotingrural groundwater conservation, Sana'a WSSP beginningmore fundamental institutionalreforms inthe urban sector, and Taiz WSPP providing a first and learningexperience inattempting compensation for rural-urbanwater transfer. InFY98, the first significant Bank report on Yemen's water sector was produced; entitled Towards a Water Strategy. The major changes, however, have been since 2000. 72. Bank and Government strategy work significantly expanded after 2000, in particular over the last two years, andresulted insector strategy papers issued in2005 by both Government and the Bank. These are the first comprehensive strategies produced for Yemen's water sector, and they broadlyharmonizeindiscussion o f issues and strategy. The new strategy i s beginningto be mirroredinthe new projects. The two most recent water sector projects\. the Sana'a BasinWater Management Project (FY03) and the Groundwater and Soil Conservation Project (FY04) are both focused on the water resources management agenda. The UrbanWater Supply and Sanitation APL (FY03) i s promoting the urbancorporate reform agenda, and ifcoupled with a greater WRM focus, can make a major difference inthe urbansector. The Rural Water Supply and Sanitation Project (FY02) promotes water conservation as well as ruralwater services. Another positiveinitiative i s that a cross-sectoral water team hasbeen establishedbetweenthe rural and urbanunits o f the MENA region. including insocial outreach, education, regulation, prices and incentives, agriculture, irrigation and other interventions. 11. Typically, such formal water markets would bebased onestablishing win-win situations for both rural and urbancommunities (i.e. prices for farmers greater than the value o f water for its highest irrigation usage, and prices for urbanconsumers lower than the water utility's prices). Such markets would need other accompanying features such as regulation o f water extraction and quality, features to protect social welfare, and, probably, community self monitoring and management. Development experience indicates that water markets need careful, practical and highlyparticipatorypreparation, specifically designed to the particular needs and culture o f the country and locality concerned. 73. The new directions are increasinglyencompassing the first three major lessons\. (i) keyissue-groundwaterdepletion hasbeenputatthecenterofactivity; (ii) the the programnow has an articulated strategy; and, (iii) a more multi-sectoral approach i s emerging, thoughthis isnot yet strongly evidentinaction. The performance o fthe new generation o fprojects has yet to be demonstrated. As they are innovative, they are also risky(several ofthese projects are currentlyhavingstart-up problems Butintheir conceptual directions, they are muchmore relevant than the supply side and infrastructure dominatedprojects o fthe past. 74. A core need, however, will beto implementthe new strategy. Beyondindividual projects, broad and often difficult sector changes will be needed; likely inpolicies, legislation, regulation, pricing, institutions and other measures. Carrying out the strategy i s now the challenge. 75. The Way Forward is the cover title for Government's new strategy paper, NWSSIP, andmay be an apt expression for the new approach that both the Bank and Government have articulated. The current strategic framework and the new generation projects are promising. Taken together, and, if implemented, the new approach offers a muchmore positiveprognosis for the way forward\. the management into the future o f Yemen's water resources. 12. Severalofthese projects currently have problematicimplementationperformance While possiblyto be expectedat the beginning ofprojects forging new directions, these implementationdifficulties will needto beresolvedfor the projectsto usefullypilot the innovationsbeingpromoted.
P043412 | Morocco Basic Education Reform Support Program | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2005 | 2009 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/937831474652717066/text/000020051-20140620080315.txt | http://documents.worldbank.org/curated/en/937831474652717066/pdf/000020051-20140620080315.pdf | From the ICR (with some modification of the ICR wording):The roles and responsibilities of all parties in a SWAp, particularly concerning the use of country safeguards fiduciary policies and procedures need to be clearly specified during preparation to avoid confusion and misinterpretation both by the Bank and the Borrower teams.The effective implementation of some reforms requires time, especially in the human development sectors. It is therefore important to take into account the time required to build the capacity of executing agencies when preparing the reform implementation plan. IEG would add:Increasing access to quality education by underserved communities needs to go beyond provision of standard school infrastructure. For example, in this project, the provision of transport and boarding facilities to these groups of children was vital. Project objectives need to be matched by relevant output and outcome indicators for effective monitoring and evaluation. For example, in this project, improvements in education quality could not be fully evaluated due to lack of adequate evidence on appropriate learning outcome indicators
P043418 | AR Aids and Sexually Transmitted Diseases Control Project | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/645271474563501100/text/000020051-20140612140804.txt | http://documents.worldbank.org/curated/en/645271474563501100/pdf/000020051-20140612140804.pdf | Ensuring ownership and commitment by decentralized agencies and local governments-- those responsible ultimately for implementing policy and project activities--is essential for achieving objectives.Institutional development can be successful when it takes into account the local political and institutional realities. LUSIDA launched a separate HIV/AIDS prevention program independent of the Ministry of Health's AIDS treatment and care activities, strengthened the prevention activities and commitment to them by various stakeholders, then integrated the two branches in the final years. Had this integration been attempted from the start, prevention activities would have had a lower profile.The involvement of NGOs and CSOs in implementing prevention programs can create political pressure on a reluctant government for a prevention debate in the country.The presence and perseverence of the Bank can lend legitimacy to controversial efforts to involve marginalized, high-risk groups in prevention programs.
P043420 | BR WATER S.MOD.2 | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2009 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/797631475085138464/text/000146597-20140619154700.txt | http://documents.worldbank.org/curated/en/797631475085138464/pdf/000146597-20140619154700.pdf | Do not adopt inflexible views on the means to achieve development objectives as this undermines Borrower ownership and may derail the project. The case for private sector participation (PSP) as the solution to inefficient operation and management of the WSS sector needed more nuanced and persuasive advocacy at the outset, with greater willingness to consider pluralistic approaches. Currently PSP is widely considered by sector practitioners and most Bank clients as one of a range of options for improved service delivery and performance.Technical Assistance Projects can actively contribute to sector reform. They can do this in two ways: first, by generating solid analytical materials, such as studies and information systems, on which to base decision-making; and second, by promoting national debate on key issues and helping to resolve differences.Systemic institutional reform of the WSS sector requires considerable time, engagement with stakeholders, and patience. Management and financing of water and wastewater services is generally controversial once efficiency considerations influence ownership and management of utilities, particularly in countries with a proactive and well-educated civil society concerned with equity and social safety nets. Several years are needed for results to be evaluated, for findings to be disseminated, and for building consensus on options and preferred alternatives.
P043421 | BR RJ M.TRANSIT PRJ. | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/855461474852694288/text/000020051-20140620080032.txt | http://documents.worldbank.org/curated/en/855461474852694288/pdf/000020051-20140620080032.pdf | When complex institutional changes are attempted, the commitment of all important entities and overall political feasibility should be judged objectively. Shortcomings in these factors in the current project limited progress in respect of institutional changes that cut across different levels of government and modes of transport, despite a greatly extended time-frame.Demand projection models should be based on realistic assumptions, especially where such projections are crucial for the overall outcomes of a project. In this project, demand for ridership on CENTRAL/FLUMITRENS was greatly overestimated, and resulted in much lower benefits than anticipated.Realistic levels of counterpart funding should be proposed for projects. For the larger portion of this project, acute shortage of counterpart funds affected the procurement of new rolling stock, thus delaying higher capacity utilization and benefits.
P043434 | PRE-EXP GUAR FAC | Europe and Central Asia | Ukraine | IBRD |  | Other | Other | IBRD | IPF | 1997 |  | 2001 | ICRR |  |  |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/877201475091547788/text/Ukraine-Pre-Export-Guarantee-Facility.txt | http://documents.worldbank.org/curated/en/877201475091547788/pdf/000020051-20140529160320.pdf | The main lesson is that the Bank should better understand at the project preparation phase the political complexity and the decision making processes in the country that would affect the project approval and implementation. In situations of conflict between executive and legislative branches, the Bank should brief parlamentarians directly to ensure proper understanding of the coverage and operational mechanism of the project and to assess ownership beyond government ministries. When an operation such as the PGF is an integral part of the sector assistance strategy, consideration should be given to possible cross-conditionality among operations in the sector (e.g. making parlamentiary approval of the PGF a condition of the Ag SECAL in the case of Ukraine).
P043444 | Municipal Environmental Infrastructure Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1998 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/474691474563563194/text/000020051-20140619091346.txt | http://documents.worldbank.org/curated/en/474691474563563194/pdf/000020051-20140619091346.pdf | When land needs to be acquired for proposed infrastructure, issues of environmental impact, land registry, public acceptance and local zoning should be acknowledged, planned for and resolved well before scheduled construction. In cases where there are many levels and agencies involved in implementation -- national agencies and banks, regional public utilities and local municipalities --having just one project implementing agency to coordinate the operation can be more effective at fulfilling project goals.Existing capacity, appropriate institutions and applicable standards should be carefully assessed during preparation of a monitoring and indicator plan, and the results of this assessment should figure among the baseline measures at the start up of an operation. Borrower ownership and commitment to improvements is crucial to improving financial and operational performance. The Bank needs to keep in mind, during supervision, what the borrower believes is relevant and realistic. In this case the Borrower did not feel there was a need for cost recovery or for controlling unaccounted-for water.
P043446 | Public Finance Management Project | Europe and Central Asia | Hungary |  |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/825771474636021285/text/000020051-20140607173148.txt | http://documents.worldbank.org/curated/en/825771474636021285/pdf/000020051-20140607173148.pdf | 1. Public Finance Management projects are most useful where there is a strong commitment to improved fiscal management. In this case, public opinion favored prudent fiscal management (as noted in the ICR) and the government was committed to this improvement. Hungary's accession negotiations to the EU also played an important role in this regard. 2. Technical assistance projects seem to turn into black boxes or slush funds more frequently than investment projects. It is therefore particularly important to clearly define a TA project's objectives, components, and implementation modalities. 3. Qualified staff, and staff continuity, are important for project formulation and implementation.
P043447 | PRIV SECT DEVT | Europe and Central Asia | North Macedonia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1996 | 2000 | 2001 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/435691474565635952/text/000020051-20140529164830.txt | http://documents.worldbank.org/curated/en/435691474565635952/pdf/000020051-20140529164830.pdf | (1) As the ICR notes, lending through intermediaries should go side-by-side with intense technical assistance, as it is difficult to introduce major policy changes and build ownership without a substantial component of technical assistance. The Bank was prepared to offer technical assistance as a component of this project, but in the event this was provided by other donors. This TA was not effective and poorly coordinated. A more satisfactory performance by the Borrower would have resulted in better utilization of technical assistance. (2) An independent implementation unit can devote more appropriate levels of resources, including manpower, to the project. The formulation used in this project, where the implementation unit comprised part-time allocations of staff, was not satisfactory. This was another aspect of unsatisfactory borrower performance.
P043700 | TN-TRANSPORT SECTOR INVESTMENT PROJECT | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/756421475110831660/text/000020051-20140615103218.txt | http://documents.worldbank.org/curated/en/756421475110831660/pdf/000020051-20140615103218.pdf | An Adaptable Program Loan may be a superior option compared to adjustment lending, where complex sector reform needs dedicated resources and time to be implemented and stabilized.Too many time-bound covenants may become counter-productive, since they risk becoming too demanding for the borrower, and difficult for the Bank to monitor and follow up.The expected pace of reforms and related risks should be carefully assessed in terms of past experience in the given context.A strong business base for services and market trends is important in reaching financial sustainability objectives for revenue generating entities.Achieving privatization objectives depends upon the convergence of a supportive environment and strong and continuing Government commitment.In the course of staff reduction, unconditional volunteering may deplete the most skilled resources. Instead, setting criteria for the eligibility to redundancy package should be considered.
P043724 | DZ-RURAL EMPLOYMENT | Middle East and North Africa | Algeria | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/645991474594936194/text/000020051-20140613083413.txt | http://documents.worldbank.org/curated/en/645991474594936194/pdf/000020051-20140613083413.pdf | The ICR has extracted a number of useful lessons from the experience with this project.It is possible to address urgent issues of rural unemployment in conflict-affected and otherwise unstable political situations and, at the same time, create economic assets with long-term benefits that contribute to sustainable livelihoods. The erosion control and agricultural development activities were labor-intensive activities that generated both employment in the present and productive investments for the future.It is important to involve local communities throughout planning and implementation of project activities in order to ensure their willing and effective collaboration with governmental organizations and private agencies. Project staff need to be trained to work with them and to understand what makes them willing participants. Simple, easy-to-manage investments are typically preferred by beneficiary communities and also have a better chance of being sustainable beyond the life of the project. It is possible to effectively outsource M&E activities, in this case to a national consulting firm, as long as these remains closely connected to project management and as long as the data generated by the M&E system are constantly and readily available to decision makers. This is a particularly important lesson for projects in conflict-affected areas, or where the implementing agency is too weak. The firm satisfactorily complemented the work of Bank supervision missions whose movements were restricted by the security situation -- a model endorsed by QAG for other conflict-affected situations.
P043725 | MA-RAILWAY RESTR & PRIV | Middle East and North Africa | Morocco | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/660221474575965562/text/000020051-20140613051809.txt | http://documents.worldbank.org/curated/en/660221474575965562/pdf/000020051-20140613051809.pdf | Strong government commitment and political will are crucial for accomplishing major reform affecting many stakeholders, such as commercialization and corporatization of parastatals;A holistic approach to parastatal reform, which adequately judges and accounts for institutional capacity, market-oriented pricing of services, and provision for fair compensation to labor can greatly improve the chances of success; andEven a relatively small WB portion of overall project cost can result in a disporportionately large contribution to project outcomes, when targeted towards crucial institutional components.
P043728 | ENV CAPACITY BLDG TA | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/234791474659410008/text/000020051-20140613035904.txt | http://documents.worldbank.org/curated/en/234791474659410008/pdf/000020051-20140613035904.pdf | 1. Projects prepared and appraised in haste to meet Bank-imposed constraints, such as the availability of IDA funds at the end of the fiscal year, have a tendency to come undone.2. Careful consideration of project alternatives at the outset may well pay dividends in smoother implementation and greater Borrower commitment. In this case, the alternatives could have included: a smaller first TA operation; piggybacking TA on a series of investment projects; or, now, an APL. 3. Restructuring a project following an MTR should be more than an exercise in finding ways to use the money on activities somewhat related to the original project which fit the Borrower's current interests but should be carried out with the same rigor as an appraisal, with careful attention to objectives, priorities, alternatives, performance indicators, and evaluation systems. When changes are significant, they should be recorded through a formal amendment to the legal documents, with notification to the Board.
P043728 | ENV CAPACITY BLDG TA | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2004 | 2008 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/392901468269405416/text/442500PPAR0P041sclosed0July02902008.txt | http://documents.worldbank.org/curated/en/392901468269405416/pdf/442500PPAR0P041sclosed0July02902008.pdf | 8. Lessons Learned 72. Strengtheningmanagementcapacity does not necessarily or automaticallylead to improvementsin environmentalquality.Improving managementcapacityfocused on a well-defined and socially demanded set of environmentalgoals wouldprobably yield better results. While it is sometimes assumed that enhanced environmental management capacity will naturally lead to better environmental quality, this hypothesis has never been adequately tested and is not necessarily the case. But this was still the prevailing, if implicit, assumption when the EMCB Project was designed. Bank experience over the past two decades has shown, however, that projects for environmental management are more effective ifthey are linkedto a specific program o f action which may consist o f regulatory reform, strengthened enforcement, and the use o f new instruments to influence private decision making. 73. Environmental monitoring is a necessary but not sufficient conditionfor improvingenvironmentalquality. Monitoringprograms should be designed around the demandfor data by decision makers rather than thesimple demandfor data. Monitoring alone will not yield improvements inenvironmental quality unless it i s designed to fit into decision systems inwhich information i s accessible, reliable, understandable, andused to support actions to improve environmental quality. Monitoring systems, thus, should be conceived in a broader context to enhance the likelihood that the data generated will be used by decision makers and the public in general to take action.26Inaddition, more information does not always produce better decisions, which arise when decision makers are motivatedto achieve a goal such as to reduce exposure by the public to hazardous chemicals. Often, moreover, databaseshave been designed and compiled but are not maintained. Preparation o f databases, atlases, and action plans, thus, can be a futile exercise, inshort, unless they are not closely linked to concrete actions to improve environmental quality and geared to the actual decisions that must be taken.28An adequate environmental monitoring system will provide timely information ina form that decision makers can understand and use to improve their decisions. 74. To enhancethe effectiveness of projects like EMCB, apriority-settingprocess which involves variousstakeholdersshouldprecedeproject design and appraisal. The project could have benefited from a prior exercise instrategic environmental analysis, focusing on policies andprograms in specific sectors and/or regions. The principal lesson inthis regardis that such projects require formulation ofclear priorities and commitment to achieve these objectives. This analysis should be carried out ina political-economic framework. Commitment i s measured invarious ways, but certain tests can be applied to assure that there will be commitment to actually solving environmental problems. Some o f the relevant questions are indicated below. While not all o f these indicators may be positive, at least some o f them must be presentinorder for environmental problems to be effectively addressed and solved. Does the general public, as well as environmental specialists, recognize the existence and magnitude o f specific environmental problems? Who loses and who gains inthe current distribution o f pollution and degradation? Is there political support for solving environmentalproblems? Do political leaders recognize the importance o fthe issue? Which stakeholders might oppose the proposed policies? Which stakeholders can be counted on for support o f new policies? 26. Decision makers may include officials seekingto allocate scarce resources amongobjectives or investors seekingto minimizethe regulatory burdenon their activities. The public at large may also be consideredto be decisionmakers concernedwith places to live or for recreationwhere the air and water are healthful and secure. Ifdecision makers find data useful, they will often be willing to pay for it. Maintenanceofupdateddatabases is often contingent on willingness to pay by the users 27. There is an unspokenpremiseinthe allocation ofresourcesto construct databases, such as GIS systems, that information will be usedto take better decisions. It follows that greater quantities of information or information of greater precision compiled into a database is ipso facto desirable. However, this premiseneedsto be consideredinlight of actualdecision-makingprocesses. Insome cases, decision makers refer to information but use it selectively or not at all. Inothers, decisionmakers would like to have better information, but only ifit is available in a format and at a scale that they can utilize. Time-series data are essential for environmental monitoring because, without it, environmental conditions cannot be linked to specific events such as increase in industrial output or the implementation of an enforcement campaign 28. Inthe Maldives, for example, decisions are currently being taken on the use of islandsfor tourism, as residential islandsor safe islands, as industrial islands, and even as landfill islands. To date, such decisionshave beentaken with regardto many factors, not including the fragility or vulnerability ofthe habitatto the proposeduse. 0 Are decisionmakers open to new ways o f dealing with environmental problems, such as pollution taxes, tradable permits or other instruments? 0 Can resolving environmental problems be linked to improvements inquality o f life for a segment o f the population (e.g. reduction o f disease)? 0 Are financial resources available to manage the problems that exist? 0 Are environmentalists inand outside government willing to prioritize, such as attackingthe more serious problems first? 0 Are the indirect measures for environmental management such as improved monitoring or adoption of new standards, developed ina context inwhich information i s likely to lead to environmental management policies or decisions? 75. Associated lessons are that a sharper focus on environmentalresultsand a betterex ante analysisof the politicaleconomy of environmentalregulationcould havemadethis a moresuccessfulprojectwith moresustainableoutcomes.Finally, the project also clearly demonstrates the risks ofdesigninganoperationaroundthe interests o f individual institutional champions, as occurred both at the central Ministryo f Environment and Forests and inthe Gujarat Ecology Commission, because, once those champions leave, the impetus may soon be lost. A strong focus on specific desiredenvironmental outcomes and basingproject design on a broader up-front stakeholder consultation process would helpto insulate it from the kinds o f abrupt changes and insufficient follow-through that characterized implementation o f the EMCB operation and could also contribute to more effective enforcement o f and compliance with environmentallaws and regulations.
P043736 | CI-PSD TA (FY98) | Western and Central Africa | Cote d'Ivoire | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/318121474571641992/text/000020051-20140613054758.txt | http://documents.worldbank.org/curated/en/318121474571641992/pdf/000020051-20140613054758.pdf | 1. Realism. The Bank should move more assertively to cancel a project when a major change in the political environment indicates that little would be achieved by extending closing dates. The deteriorating environment was clear already in 2001, and rather than attempting to restructure the project, a candid assessment of the probability of success should have been made and actions formed around that. 2. Poor project design and poor implementation contributed as much to an unsuccessful outcome in this project as the political developments. The key project targets were over-ambitious, even in a normal situation, and the project risk was under-estimated. In high risk projects, it is important to subject mission back-to-office reports (and the accompanying aide-memoires) to outside reviews as and when they are written, with a representative drawn from a Bank-wide department, to complement the Region's review. For example, at the sector level, a clear lesson here is the difficulty of continuing to mount a private sector operation in what turned out to be a non-conducive production/trade environment. 3. The ICR argues that support to enterprises might be more effective if provided to clusters of firms, but this would require clear arrangements of ownership and responsibilities.
P043868 | Natural Resources Management & Rural Poverty Alleviation - Rio Grande do Sul | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/335281474637189364/text/000020051-20140615103627.txt | http://documents.worldbank.org/curated/en/335281474637189364/pdf/000020051-20140615103627.pdf | The project experience provides or confirms the following implementation lessons:1. Community based natural resources management can be more effective when combined integrally with income generating activities and investment in small-scale social infrastructure. The project concept was to integrate NRM with income generation activities and small village infrastructure, though at the beginning of the project they were treated as separate and not necessarily complimentary project components. The NRM and income generation and social infrastructure components were then combined, and the task team has advised that this had better effect in providing incentives and mobilizing community interest and achievement. The ICR sees full integration of NRM with income generation and village infrastructure as important for successful resource management.2. Communities need individualized attention tailored to their specific needs. The implementation modalities that are appropriate may be quite different between, for instance, poorer or indigenous communities and wealthier communities. In early project implementation it was found that a uniform process for engaging communities and providing technical assistance was not appropriate. Indigenous, agrarian reform, isolated communities, poor and wealthier communities and those near urban areas, required different approaches. There needed to be variation in the selection process, the degree of community contributions, the type of income generating schemes and social infrastructure most suitable, the time and nature of technical assistance to help the communities, and other implementation processes. The Operational Manual was adjusted to provide for such different needs. This kind of adaptation may be a need for other community driven development projects where the social structures of communities have substantial differences. 3. Decentralized and community driven development needs a clear, detailed and periodically updated Operational Manual. The project involved numerous civil society and government partners, and thousands of community organizations, and clarity and guidance on what to do was critical. The task team and government placed considerable attention to development of the operational manual, and revised it as needed. Lesson 2 provides one example of adaptation.The project's OM is now being used in other NRM projects in Brazil. 4. Contracting out M&E can be effective in quality and relevance, but continuity between contracts is needed. M&E was contracted out to partner institutions. The quality of surveys and data produced was good while such consultancies were ongoing. However, the contract for environmental monitoring only commenced in 2001, allowing only three years for M&E of the project, instead of eight as originally planned. Further, the contract ceased at the end of 2004, a far from ideal situation for a continuous development program.
P043869 | Santa Catarina Natural Resources Management and Rural Poverty Reduction Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2002 | 2010 | 2011 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/898691474634924596/text/000020051-20140620083442.txt | http://documents.worldbank.org/curated/en/898691474634924596/pdf/000020051-20140620083442.pdf | The project's implementation experience points to the following lessons (the first three are adapted from the lessons presented in the ICR, and IEG has added the fourth):1- The quality of extension services is critical for micro-catchment based projects. The approach requires a strong field presence and implementing agencies at all levels need access to quality technicians. It is important to establish a clear professional criteria for selecting technicians up-front.2- Complex and innovative projects of broad scope may require longer time frames to allow adequate time for organization, training and institutional strengthening during the first half of implementation, without shortening the implementation time for more difficult activities that can only be carried out once a sufficient level of training and organizational capacity is reached. A follow on operation may also be required to consolidate and deepen initial gains.3- Clear and objective targeting parameters and a strong institutional commitment to their compliance are essential to ensure that a project's poverty focus is realized. Participatory targeting mechanisms, combined with a conscious efforts on the part of both implementing agencies and the Bank to ensure that priority populations are included in all activities, and close oversight of applicants qualifications for participation throughout implementation are important. 4- Micro-catchment projects that include a poverty focus must be realistic about the expected beneficiary contribution. In this case financing of technical assistance activities was originally planned on a declining scale but due to the low base that many participants were starting from 100% grant support was maintained throughout the life of the project.
P043871 | Rural Poverty Alleviation - Piaui | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/348751474496606332/text/000020051-20140607162645.txt | http://documents.worldbank.org/curated/en/348751474496606332/pdf/000020051-20140607162645.pdf | The most important lesson refers to the good results achieved by application of the new R-NRDP model. Despite some shortcomings the basic strategy has proved highly successful. A combination of benevolent authorities and enthusiastic beneficiaries (piloted under R-NRDP in the mid-1990s) showed that a project strategy drawing from some well tested principles (Rochdale, Community Development, Comilla, Daudzai and the AKF projects) enables poor people with a little guidance and seed resources to improve their communities. The value was proven of decentralization, social organization and social capital formation, community participation (with TA where necessary), institutional transparency, demand-driven subprojects, poverty targeting by location, M&E/MIS to evaluate and adjust on the go, and eventually community graduation to self-sufficient development.
P043873 | Agricultural Technology Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1997 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/498521474555683450/text/000020051-20140615112211.txt | http://documents.worldbank.org/curated/en/498521474555683450/pdf/000020051-20140615112211.pdf | The ICR offers a number of useful lessons, although some stated lessons in the ICR are formulated more as comments than generic lessons. The most important lessons, adapted with modification from the ICR, are the following:1. Competitive research grants are an essential element in achieving research system efficacy and efficiency and, provided the right social and environmental parameters are set for grant approval, enable a research focus on the needs of society and the environment.2. Simple and straightforward institutional arrangements with appropriate, largely external, membership in key committees can give confidence in R&D investments and effective social focus of research investment.3. Project designers of agricultural research projects need to be realistic about the timeframe. Bidding, approval, contracting, research project set-up and implementation are all very time consuming and are phased and dependent. Better techniques of forecasting the steps (perhaps computerized project management flow charts?) would enable greater realism. While individual research program delays may be quite unpredictable, delays in whole research projects are more predictable drawing from past Bank experience.4. Systematic, collaborative oversight is important in programs with significant R&D resources and large numbers of subprojects.
P043873 | Agricultural Technology Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1997 | 2006 | 2009 | PPAR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/277821468057286448/text/491490PPAR0p061fficial0Use0Only1pdf.txt | http://documents.worldbank.org/curated/en/277821468057286448/pdf/491490PPAR0p061fficial0Use0Only1pdf.pdf | 6. Conclusions and Lessons 6.1 An importantfinding o this four-project assessment is the lack o hard f f evidence about the results o competitivefund investments in research and extension. f In each o f these countries, agricultural productivity has risen since the mid 1990s, with growth increasingly based on intensification rather than area expansion. Potentially, the assessed projects contributed to this expansion. But, with the exception o f Peru, there i s no robust survey evidence linking productivity and income changes to the project interventions. Even in the case o f Peru there are doubts about which o f the steps in the results chain were most critical for achieving the increase in farm incomes. For example, extension services potentially have a role to play in the technology transfer chain but it i s unclear just how a critical a role. In each o f these four countries extension has withered on the vine; but from the evidence generated by these projects it i s impossible to conclude if this attrition i s truly significant-or whether, for example, tighter linkage o f farmers to producer associations i s an effective substitute. 6.2 With respect to the viability o f the competitive fund model, more study i s needed to compare the efficiency o f the model with the alternative-a single (public) supplier with fiinds directly assigned by government. There is a perception-stronger in Brazil and Colombia than in Peru and Nicaragua-that the competitive process has been managed in a way that i s both fair and transparent and has tended to raise the quality o f the research proposals that are approved for funding. But there i s no indication o f how costs per unit o f technology adopted vary between the competitive and the direct assignment approach. 6.3 Thefourprojects included in this assessment, and thefollow-on projects that have succeeded them, have generated substantial learning, both by the Bank and by the countries concerned. InNicaragua, there i s now greater realism about what can be achieved in a context o f weak institutions and high donor dependence. In Peru, the importance o f integrating the competitive fund approach with the broader public sector apparatus o f research and extension has been acknowledged; and the government's commitment to maintainingthe regional network o f INCAGRO bodes well for increased decentralization. In Colombia, the progress under the follow-on project in linking subprojects to commodity chains and increasing engagement with producer associations i s resulting ina more strategic allocation o f competitive fund resources that will help to enhance the country's agricultural competitiveness under the terms o f the new free trade agreement with the USA. In Brazil, the returns to increasing EMBRAPA'S connectedness with diverse research institutions, both within the country and beyond, have become f i l l y apparent. 6.4 The findings from this assessment suggest lessons o f broad relevance that are likely to apply beyond the four countries studied. A principal lesson concerns the importance o strengthening the capacity o research organizations, not just financing f f research. Competitive funds can be an important vehicle for research financing and have a strategic role to play in piloting new ways o f working, or focusing research on new topics; but they are most likely to make a sound and lasting contribution when they complement a relatively strong public-sector framework for research (in this respect, prospects were brighter to begin with in Brazil and Colombia than they were in Nicaragua and Peru). Public funding i s essential for agricultural innovation systems and private funding complements rather than substitutes for higher levels o f public funding 6.5 Second, to be able to compete, research institutions must have a minimum budget and a critical mass o staff-all f institutions need a portion o the budget that is f f f corefunded to cover costs o maintenance and upgrading o physical and human resource infrastructure. Competitive grants usually only fund operating costs; and the subprojects they finance have only 2-3 years' duration.' The sustainability o f the public sector research apparatus in general and the competitive funding model in particular depends on a continuing commitment o f government funds. The new model is unlikely to flourish in a climate o f fiscal austerity because there i s only limited scope for private funds to substitute for public money. 6.6 Third, the competitive fund model i s more likely to strengthenthe strongest agencies providing research and extension services than it is to reduce the disparities between the strong and the weak. Thus, in Brazil, the model strengthenedan agency that was pre-eminentto begin with. At the other extreme, in Nicaragua, the model was underfundedfrom the outset, i t s transformative capacity was limited by the weakness o f all the actors in the competitive arena, and the government provided little support to it. The principle o f competition between alternative service providers breaks down where the range o f providers i s limited (a problem at the municipal level and for small countries) and many o f the potential providers lack the skills needed to prepare viable sub-project proposals. 6.7 Fourth, the competitive model has not itselfled to a large growth in the role o f f the private GforprofiQ sector as a provider o agricultural research and extension; but it has contributed to the broaderprocess o private sector development. Compared to high- f income countries, in Brazil, Colombia, Nicaragua and Peru, commercial f i r m s have played a smaller role as providers relative to public and private nonprofit agencies. To the extent that commercial f i r m s have played a role, they have largely done so outside the framework o f competitive grant schemes; this i s the case, for example, for the partnership between EMBRAPA and the private multinational Monsanto for producing herbicide-tolerant soybeans2O n the other hand, under the competitive schemes, through the medium o f subproject Co-payments, producers have provided private funds as a complement to public sector grants; they have received training in the preparation o f business plans; and they have become more market-oriented owing to partnerships with producer associations that have been facilitated by competitive funding agreements. In this sense, the competitive fund model has contributed to the broader goal o f private sector development without entailing a major role for commercial f i r m s as service providers.
P043874 | BR- DISEASE SURVEILLANCE - VIGISUS | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/393831475100541053/text/000020051-20140612154027.txt | http://documents.worldbank.org/curated/en/393831475100541053/pdf/000020051-20140612154027.pdf | Choice of Loan Instrument. The choice of loan instrument (APL) allowed flexibility for a long-term institutional development project in the context of an evolving decentralization process, and increases the likelihood of a successful and sustainable outcome.Financing Mechanisms in a Decentralized Context. Health sector projects in the context of decentralization require a better integration of Bank financing mechanisms with country financing mechanisms. The use of contracts and subprojects governed by Bank rules required formalities that were slow and cumbersome and introduced an entirely different set of rules for decentralized entities. More agile funding streams, coherent with country mechanisms, are required.Financing Mechanisms for Public Sector Strengthening. Public health surveillance is a public good and an element of the MoH's stewardship function, squarely in the government's domaine. When investing in public health surveillance (or other public health functions), it is important to ensure that there is adequate flexibility in the legal agreement to permit subsidies to a variety of public institutions, as well as to factor in government mechanisms for funding such institutions.Efforts to extend health services to marginalized populations. In remote areas these need to be accompanied by ways and means of ensuring the long-term availability of qualified professionals to deliver these services.
P043881 | Irrigation Rehabilitation & Reform Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2004 | 2012 | 2014 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/332921474483212535/text/000180307-20141201083956.txt | http://documents.worldbank.org/curated/en/332921474483212535/pdf/000180307-20141201083956.pdf | The ICR extracted many lessons. They can be summarized as:Where difficult reforms and entrenched interests are involved, the Bank should require more concrete evidence of commitment to the projectâ€™s objectives before approval The absence of implementation readiness aggravated an already ambitious and difficult project.Weak M&E contributed to many implementation problems problem, The economic analysis of projects under preparation should be used as an iterative planning and design tool, rather than as a simple requisite to justify pre-defined investmentsWhere insufficient commitment is evident, the Bank should be ready to walk away from the project.When subsidies on water tariffs are phased out in irrigation systems the viability of agricultural production depends on adjustments in cropping patterns and improved technology which is not likely to happen without strong technical support through extension and improved marketing efficiency.Irrigation development projects require good managers and sound institutional arrangements with good multi-disciplinary teams including social and agronomic expertise to succeed. A lesson that could have been added for this project is the importance of a soundly designed and executed M&E system providing timely information and analysis of the project's progress and achievements. The absence of a sound M&E system was a major drawback during project implementation.
P043882 | AGRICULTURAL SUPPORT SERVICES PROJECT | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/672991474573756440/text/000020051-20140615104149.txt | http://documents.worldbank.org/curated/en/672991474573756440/pdf/000020051-20140615104149.pdf | 1. A Competitive Grants Scheme (CGS) for agricultural extension, associated with technical assistance and applied research, can significantly improve agricultural technology and productivity. Competitive grant schemes for applied research are commonplace in Bank rural projects, but CGS as the primary vehicle for extension services is less common. The ASSP reinforces experience emerging from other projects introducing CGS for extension that impact can be considerable with suitable design and implementation. ASSP only used the CGS and mass media programs, and did not use a classic network of agricultural extension providers. The CGS went almost entirely to supporting either dissemination proposals (74 percent of the grants) or to combined dissemination and applied research (25 percent). The project's largely successful experience suggests that, among the various innovations in agricultural extension that Bank projects are pioneering, a CGS approach may be one of those that are particularly promising. Under ASSP, impact on productivity appears to have been good, and costs will have been lower than most traditional extension approaches. In the case of the ASSP, the following features appear to have been helpful: (i) the training of potential grant recipients in how to formulate grant proposals; (ii) using a two-stage bidding process - a brief concept note to quickly screen out weak candidates followed by a more detailed proposal; (iii) basing a CGS on a clear Operational Manual available to all interested parties; (iv) establishing a good MIS/M (v) training the team that will evaluate grant proposals; (vi) assessing and making allowance for in institutional design, the size of the staff complement that will be needed over time to evaluate and monitor the competitive grants; (vii) up-front training of grant recipients in procurement and financial management, and (viii) the requirement that the proposing entities put some of their own funds into the proposed subprojects, thus demonstrating seriousness.2. Mass-media processes for awareness and technical assistance to induce technology change can have rapid positive impact on agricultural productivity. Romanian farmers, hitherto bereft of access to technical advice, were particularly receptive to mass-media (radio, technical pamphlets) advice. A project final assessment workshop assessed that radio broadcasts had been an effective tool to pass on specific technical messages to farmers. Essential to success was that the technical quality of the messages was good, and that adoption of the technology would have significant positive impact on farm productivity. The perceived worth of the radio programs is partly illustrated by the continuation of the program, without project funding, by a number of counties.3. Fostering Public-Private Sector Partnerships can substantially enhance the capacity and impact of government extension and research services . The project experience contributes to the findings in a number of Bank projects concerning the value of government - civil society partnerships (with the private sector, academia, NGOs) in extending the impact of extension and research services. The ASSP involved over 220 such civil society partnerships, often with more than one partner involved.
P043882 | AGRICULTURAL SUPPORT SERVICES PROJECT | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2000 | 2006 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/453991468005956033/text/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.txt | http://documents.worldbank.org/curated/en/453991468005956033/pdf/Europe-and-Central-Asia-Agricultural-Reform-Support-and-Agricultural-Development-Projects.pdf | 6. Lessons (a) General Lessons 6.1 Given the large attitudinal shift involved in the agricultural transition, government officials and project staff needed substantial technical assistance and training before operations could be expected to succeed. Governments showed strong commitment to the preparation of the projects under review. Yet once the loans were approved, delays in declaring effectiveness were experienced for several of the loans, while during early implementation even staffs of the project units often did not fully understand how specific project activities linked to objectives. If this was true at the center, it was even truer in the localities where projects were implemented. Consultant services were not always used as effectively as they might have been (this was the case for credit operations in the Armenia ARSP and Georgia ADP). There was an attitudinal lag\. most government officials in the agricultural ministries still exhibited a command and control mentality with respect to agricultural development. 6.2 When the leadership of project implementation units was skilled and motivated and their staffs were well trained, project implementation generally proceeded smoothly once some experience with the Bank's procedures had been acquired. This was especially the case with project units for the Romania ASSP and Georgia ADP, whose performance improved rapidly once professionally adept managers were recruited to replace earlier political appointees. Similarly, the appointment of a technically trained person to manage a purely technical agency such as the Romania's ANCPI for the GCLR Project resulted in a rapid acceleration of project implementation. 6.3 In the complex and rapidly changing ECA environment, sound donor coordination was critical. The two Romania projects rebounded from a very poor start once the Bank and other members of the donor community began working together to help Romania meet the European Union accession requirements. Together they helped Romanians to take advantage of the grants-in-aid made available under the Community's special accession program for agriculture and rural development. 6.4 Where donor coordination was less sharp, progress was slow. Management of the land registration component of the Georgia ADP was, at times, complicated by conflicting donor expectations that proved hard to resolve. In Tajikistan, it took the Bank until 2003 to realize that if donors spoke with one voice to the government on land reform, it might create conditions more favorable for the farms that the project had restructured. (b) Lessons from the Sub-sectors Agricultural and agribusiness services 6.5 Farmers and rural business owners will respond enthusiastically to innovative technologies corresponding to their needs. Experience from the assessed projects showed that agricultural research and extension works best when it is consultative and demanddriven. In Romania, the competitive grant approach proved to be an excellent vehicle both for generating applied research findings and extending these to farmers. But, as Armenia showed, the competitive grant scheme can also lack the strategic focus needed to effect a comprehensive strengthening of agriculture research. To respond to farmers' needs, competitive research grants should be open to all applicants, including non-governmental organizations, universities, and government research institutes. For pure farm extension work, the financial sustainability of advisory services in a setting with many small, semisubsistence farmers can only be achieved if government acknowledges its responsibility to provide these citizens with appropriate and effective advice and information. This will probably entail some measure of subsidy given the low incomes of many of the clients; but that need not preclude use of private contractors to deliver the service. Land administration 6.6 The Bank's international experience with land policy issues has strengthened the design of projects in ECA; but there is no uniquely correct model for land administration or land reform and effectiveness depends on responsiveness to local conditions. Whether grounded in restitution (Romania), or in the granting of more or less equal allotments to agricultural workers and other rural residents (South Caucasus), or being limited to the transfer of usufruct rights only (Tajikistan), each program was designed to accommodate socio-political necessities in the aftermath of de-collectivization. In Tajikistan however the project design was overly ambitious and not tailored enough to the local circumstances. 6.7 It makes sense to adopt a unified approach to land administration. Cadastral and land recording/land registration services are both technology and information intensive. These two services need to be closely linked and preferably digitalized to increase efficiency and enhance access. The unified approach worked well in each of projects reviewed here that had a land administration component (Azerbaijan FPP and ADCP; Georgia ADP, and Tajikistan FPSP). Rural finance 6.8 With appropriate regulation, technical advice and staff training banks that lend to rural areas can operate sustainably. To realize the potential from scaling up commercial bank lending to rural areas, it is essential\. (a) to confirm that supervision and prudential regulation has been developed and can be effectively enforced; (b) to prequalify the banks deemed eligible to participate in tendering for loan proceeds, based on rigorous prudential examination; (c) to ensure rigorous monitoring of the credit program, with the assistance of international expertise if necessary; (d) to ensure that the terms, maturities and grace periods of loans are proportional to the expected returns and the estimated economic life of the investment; and (e) to allow intermediaries to administer credit reflows in accordance with their own terms and conditions. 6.9 The non-bank financial intermediaries have an important role to play in rural areas; but it is important to be realistic about their capabilities. There is a strong demand for locally-based credit facilities (such as credit unions) in rural villages, and for rural financial institutions that take credit. These institutions must be savings-driven and encouraged to diversify their loan portfolio rather than focus only on farm lending. Sustained, strong support in the form of training and supervision is required if they are to evolve into viable financial institutions. The volume of lending needs to keep step with the growth in management skills and savings mobilization among members (overly-rapid expansion in the Georgia ADP and ambitious targets in the Azerbaijan ADCP considerably stressed implementation of farmer credit programs in these two projects). In general, these projects have shown that small village-based credit cooperatives are not an appropriate mechanism for large-scale credit delivery.
P043923 | GD- BASIC EDUCATION REF | Latin America and Caribbean | Grenada | Blend |  | Human Development | Education | IBRD | IPF | 1996 | 2002 | 2003 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/725711475072295117/text/000020051-20140607145658.txt | http://documents.worldbank.org/curated/en/725711475072295117/pdf/000020051-20140607145658.pdf | Provision of teacher training is not sufficient to guarantee changes in behavior; hands-on work in the classroom is necessary.-Project design should reflect capacity of the implementation agency. Inexperienced project management units ought not be implementing heavily "front loaded" projects since there is need to factor in a period for assimilating Bankâ€™s procedures.- Project costs should be based as far as possible on actual designs in order to reduce cost over runs.
P043933 | SICHUAN URBAN ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/664631474487950940/text/000020051-20140618084055.txt | http://documents.worldbank.org/curated/en/664631474487950940/pdf/000020051-20140618084055.pdf | In addition to lessons indicated in the ICR (and not repeated here): (i) project development objectives should be formulaed to make it very clear what the project is actually designed to accomplish and to provide a more realistic picture of what is achievable; (ii) projects such as this one that seek in part to protect "public health, especially of lower income groups" by reducing water pollution should include adequate monitoring and evaluation mechanisms to determine the extent to which they actually generate the desired public health benefits for low income groups and this should also be reflected in both the ex-ante and ex-post economic analysis; and (iii) greater attention should be given during preparation, implementation, and ex-post reporting to project evironmental and social aspects and results, including those associated with application of Bank safeguard policies.
P044033 | TRANSISTION ASST CDT | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1997 | 1997 | 2005 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/793831468740693918/text/31343.txt | http://documents.worldbank.org/curated/en/793831468740693918/pdf/31343.pdf | 5. Lessons When original design intentions for a quick-disbursing operationhave to be drastically reduced inscope, inthe face of practical and political difficulties, then this should give riseto areassessmentofthe whole operation, inparticular the credit amount, to ensure that there remains a relationship betweenthat amount andthepolicy adjustments being supported. 0 Providing general budget support into a situation where there i s virtually no auditing of, or accountability for, government expenditures i s unwise, inthe absenceo f a watertight, monitorableagreement with the borrower on the use o f those funds. Insofar as current IDApolicy i s not to concern itselfwith the use o f h d s inaquick-disbursing operation, then either that policyhasto change or IDA has to forego the provision o fbudget support insuch circumstances. Providingbudget support, inthe face o fmajor tax evasion and excessive government expenditures, can bepotentially counter-productive, inthe absence o f an agreed and concerted direct attack on those elements. Otherwise the presence o fbudget support reducesthe naturalpressure on governments to take urgent and meaningful action. Inasituationwherethereisnotclearborrowercommitmenttoacourseofaction, or there i s a history o fback-tracking or non-implementationo f laws and regulations, the mere passageo f legislationor promulgationo fregulations is not usually a good basis for tranche release conditionality. There also needs to be a periodo f implementationor, better, release conditionalitybasedon actual results achieved. Onany issue, includingmacro-economic andtax-related issues, IDA should maintain an independent position. Ifthere i s disagreement between IDA andthe InternationalMonetary Fund(&IF), IDA support shouldbe basedon its own assessment. 0 Inahighlychargedpoliticalatmosphere,progresscanbeachievedbybringing conflicting parties together for technical discussions, with IDA staff or TA consultants present. To be successful, however, it requires the involvement o f particularly empathetic staff, the careful choice andbriefingofTA consultants, andintensive supervision-all ofwhich happened under the two PFSAC operations andSOSAC. Inthese respects, these three operations represent good practice. When a long and complicated agenda o freforms i s needed and where future detailed actions can only be properly prescribedafter further discussions and developments on the ground, careful sequencing o f operations is required. This was done for PFSACandPFSAC2,to be followed bythe proposed Economic Management SAC; and for SOSAC,to be followed by the proposed SOSAC2. Such careful sequencing is another example o f goodpractice. By contrast, there was no immediate follow-up to TAC,compounding its poor design as a onetranche operation.
P044056 | Structural Adjustment Loan (SAL) | Europe and Central Asia | Lithuania |  |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/860391474501184558/text/000020051-20140526211419.txt | http://documents.worldbank.org/curated/en/860391474501184558/pdf/000020051-20140526211419.pdf | Participatory approaches to build support for reforms pay off. The participatory approach taken by the project team included having the SAL team brief multi-party committees through this period of parliamentary elections. Effective donor coordination, including (or especially) concerning technical assistance, is critical to project success.
P044110 | COAL PILOT | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/775631474946554939/text/000020051-20140602113920.txt | http://documents.worldbank.org/curated/en/775631474946554939/pdf/000020051-20140602113920.pdf | Flexibility and adaptability as demonstrated under the CPP should be maintained for future mine closure operations.Piloting that encounters difficulties can lead to successful new products - the Bank, in close cooperation with DOA and MOF, helped establish a Municipal Credit Line for noncommercial projects with eligibility based on having accepted social assets. This was successfully implemented under the Coal SECAL. MOR issued the credits and DOA guaranteed them.Agencies for mine closures should be closely tailored to circumstances - normally physical closure and social mitigation would be vested in separate agencies. In this case the MOF and MCI functions were combined in UDKR which greatly contributed to smooth implementation.Mine closure projects should concentrate on the essentials - acceptable statutory social benefits and first phase environmental mitigation limited to reduction of risks to safety and health.
P044110 | COAL PILOT | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2001 | 2002 | PPAR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/463731468781194246/text/multi0page.txt | http://documents.worldbank.org/curated/en/463731468781194246/pdf/multi0page.pdf | 5. Lessons and Recommendations 5.1 In addition to the recommendations on specific issues presented in the textt the project provides some broad lessons that are applicable across the Bank's lending program, and also several recommendations related to future Bank support for Ukraine's coal sector restructuring. 17. There was a dramatic economy-wide increase in cash payments in 2000. In the coal sector they are believed to have reached over 85 percent. However, many mines still find it necessary to use barter arrangements to finance their capital expenditure programs. 5.2 Quick disbursing SECALs are inappropriate vehicles for supporting sector restructuring programs. Sector restructuring is a long, complicated process, particuiarly in a transitional economy where strong economic forces are aligned against it. 5.3 SECALs in support of mine closures should be designed with a several small, flexible tranches, rather than a small number of large tranches. Each tranche should include a limited set of conditions, and should provide financial support for the implementation of a government decision to close some predefined, limited number of mines (possibly 5 to 10). 5.4 The financial and economic performance of pilot project activities needs to be carefully monitored. The activities initiated by a pilot proiect need to be monitored from the start in order to be able to inform decisions on the design and implementation of the remaining phases of the programStakeholder sirveys c-an play an essential rmle in this prncess. Recommendatnnrs for future aora Ir IonAing-;r e in Ulc TrJrna onal eorfAr __ flrss_sasa o ss *wn _..nnr nan1-e *-- v--. .. _ _..un.. _waLnnnln s 5.5 ~ ~ ~ ~ ~ ~ ~ ~ ~ ~~~~~~~~1-, Pr3.sdge ospo o!scoletu.uig st aez.ear focus o poverty reduction objectives. To achieve this goal, the Bank needs to structure its lending to the scLtoI 1in a way tiiat it piuviue nIIIULr suppUo Lor tIhe sciUll safety net expendiLULUS adU less support for physical mine closure activities. The most important areas of support are the payment or social liabilities to redundant miners and the rehabilitation of social infrastructure (particularly housing, heating, water, and electricity) that is to be transferred from the defunct mining company to the local administrations. This social infrastructure plays a central role in the well-being ot the affected population. Communities cannot survive Ukraine's extreme winters without these essential services. This shift in focus would take the Bank out of the mine closure business, and put it back into the social mitigation and poverty alleviation business, its primary area of concern. 5.6 The Bank needs to make greater efforts improve the efficiency of mine closure activities. More attention is needed to the provision of technical assistance with the design of efficient individual mine closure programs that take into account sDecific local conditions and include timetables for their implementation. 5.7 The Bank has no blueprint for increasing private sector job creation in a shrinking economy. The Bank should, therefore, consider working more closely with other bilateral and multilateral agencies IY that are providing seed money for establishing local cooperat_-e -anote e-hl ns;ttos esiotttosr.ypoeobegd U5I'.a ~A& ~ .RZRp J5aAU JUL. IIll.LILULtVII3 xiiiay pJluyv E) D%, r,00U intermediaries to finance new small-scale enterprises.
P044123 | Strucutral Adjustment Loan (SAL) | Europe and Central Asia | Latvia |  |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2000 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/472891474573235997/text/000020051-20140522102427.txt | http://documents.worldbank.org/curated/en/472891474573235997/pdf/000020051-20140522102427.pdf | A broad-based agenda is appropriate if Government is sufficiently motivated. The participatory approach followed in Latvia, with the inter-governmental committee formed as part of the SAL process, greatly facilitates progress, even through a change in government. Strong leadership from key civil servants plays a key role in SAL implementation.
P044139 | ERDL II | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 1999 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/373591474632073273/text/000020051-20140519065106.txt | http://documents.worldbank.org/curated/en/373591474632073273/pdf/000020051-20140519065106.pdf | The lessons the ICR indicates were learned from this project - the importance of "ownership" and the value of building on past success - are generic/. However, this project also demonstrates the potential usefulness of supporting adjustment with a series of one-tranche adjustment operations with actions taken before board presentations, provided the operations are built around a comprehensive, well thought through reform agenda.
P044139 | ERDL II | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2001 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/366891511185568183/text/multi0page.txt | http://documents.worldbank.org/curated/en/366891511185568183/pdf/multi0page.pdf | 5. Lessons The main lessons from ESAL and ERDL 1-111 are\. * Changes in the incentive regime are necessary but not sufficient conditions for efficient and rapid economic growth. Linking rapid growth to these policy changes in a short Country Assistance Strategy period gives rise to expectations that may not be fulfilled. As a consequence, policy makers in borrower countries, and the policy reforms themselves, become politically vulnerable. That vulnerability could result in the government being voted out of office at the next elections. * Sequencing reforms to emphasize sectors with growth potential, such as exports, at the beginning would bolster belief in the benefits of the incentive changes and soften the blow of job loss when uncompetitive sectors begin to decline. It would also bolster private sector confidence and encourage investments that are internationally competitive. * A resident mission and timely and substantial technical assistance are crucial for the successful implementation of complex reforms involving several government agencies, new institutions and laws. The subsidiary lessons from ESAL and ERDL I-III are\. * Government ownership of reforms and political consensus for some sensitive reforms such as privatization are crucial for project success. It is advisable to assist in developing political consensus rather than pushing for early implementation. * In complex and wide-ranging policy programs that require substantial legal and institutional change, confining conditionality to core activities would increase the prospects for successful implementation. * Institutional change, especially when full consensus has not been reached, tends to take a long time, usually longer than expected by Bank staff. These delays should be factored into project design. * Series of single tranche operations that are disbursed after agreed reforms are implemented offer flexibility for reform programs with uncertain time lines.
P044140 | CO CARTAGENA WTR SUPPLY & SEWERAGE ENV. | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2009 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/357521475076346419/text/000020051-20140624161330.txt | http://documents.worldbank.org/curated/en/357521475076346419/pdf/000020051-20140624161330.pdf | 1. Long term bank involvement in the water sector can nurture institutional reforms: The Bank's continued support of ACUACAR was instrumental to consolidating the sector reforms initiated in Cartagena under a previous Bank operation, and to establishing the needed credibility of the mixed enterprise model. ACUACARâ€™s positive experience has served as a model for the transformation of the water sector at a national level. 2. Large wastewater projects should not underestimate the risk of delays from social, environmental and political factors and set realistic project durations. Even through the project was well-prepared technically, implementation took over a decade due to complications in obtaining the environmental license, local opposition to the outfall solution, and the Inspection Panel case (as well as procurement delays). The average life of Category A WSS project in the LAC region is estimated at 8.4 years, and this project was appraised to take 5.5 years. 3. Social assessment and consultation are key to successful infrastructure projects near areas with large populations. A comprehensive communication strategy would have created a better understanding of the project and dissipated erroneous information. Complex projects should include stakeholder and political analysis during project preparation to help identify project champions and those in opposition, understand personal interests, and anticipate probable reactions. Promised activities that benefit the affected population should be conducted at an early stage during project implementation.4. Private sector participation in the water sector can be pro-poor. Not only the affluent sections of the city but also the poor neighborhoods are receiving good service. The resources for expanding coverage in poor areas were generated mainly from efficiency improvements and subsidies, with only minor increases in tariffs. 5. For large complex wastewater projects it is important to make the necessary up-front investments in planning and design and to include a panel of experts. The careful attention to technical considerations during project preparations with in-depth engineering studies and technical consultations with experts was instrumental in successfully working through the environmental licensing and inspection panel processes.
P044140 | CO CARTAGENA WTR SUPPLY & SEWERAGE ENV. | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2009 | 2017 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/861101484347779976/text/111404-PPAR-P082973-P044140-P065937-PUBLIC.txt | http://documents.worldbank.org/curated/en/861101484347779976/pdf/111404-PPAR-P082973-P044140-P065937-PUBLIC.pdf | 5. Lessons 5.1 The key lessons derived, based on the findings of this PPAR, are the following\. â€¢ Consolidation of smaller WSS operations servicing poorer neighborhoods can foster economies of scale and cross-subsidization in achieving financial sustainability at the aggregate level. The success stories of smaller operators relate to private sector operators in large urban areas extending their services to nearby small towns. In the case of the WSRAP, what worked was done through consolidation of smaller operations. The Triple A began operating in neighboring municipalities that were considered poor. To make service provision profitable, Triple A designed and proposed a regional tariff methodology aimed at cross-subsidizing service costs between municipalities served by the same provider. â€¢ Small municipalities with limited service coverage require large capital investments. Because of their lack of financial autonomy, government subsidies would be required until full cost recovery is achieved. In the case of large operators such as Cartagena, all costs were to be paid by users. Small operators normally receive a government contribution to cover investment costs (the user charges that they collect cover administration and maintenance costs). The contractual arrangements required private operators to invest in the supply systems to a limited extent, but the major investments had to be financed through capital subsidies from the government. In practice, because the investment needs of the small and medium-size operators were not adequately assessed, the capital investment received was insufficient, and in many cases it had to be renegotiated with the government. â€¢ It is crucial to phase and/or sequence project activities to ensure achievement of the objectives of utility operators. The WSRAP and WSSSP were simultaneously trying to build the capacity of operators with no operational capacity to immediately implement an expansion of WSS services and improve service quality. This can work in cases such as Cartagena, where the operator of the project, ACUACAR, was already experienced and ready to undertake activities to improve access and quality of services. Because it takes time to build capacities, one approach might be to move more slowly, emphasizing capacity strengthening first, and then to focus on implementation. Another approach could be to ensure the selection of an operator that has adequate experience and management capacity. â€¢ Management capacity of the utility can be strengthened by contracting a competent operator. Selection of operators for the water utility companies in WSRAP was based mainly on opting for the lowest cost for the government. However, the quality of the operator was an important omission in the bidding requirements. This led to a focus on the short-run financial benefit for the government rather than on selecting an operator with a minimum of experience and the quality capacities needed to run the water utilities. â€¢ A carefully designed M&E system and comprehensive planning is essential for success. The Cartagena Project included relevant and systematic design and implementation of M&E throughout the project period, while the WSRAP and WSSSP suffered from a relatively weak M&E framework and poor M&E implementation. In the case of the WSSSP, the demand-driven selection process resulted in a piecemeal operation, with subprojects financing components or parts of an overall system. A carefully designed M&E system with specified required indicators for the different types of interventions would have been essential to enable adequate monitoring of the project outcomes. For small-scale, demand-driven projects, substantial capacity building in addition to careful M&E design is critical for success.
P044147 | Second Structural Adjustment Loan | Europe and Central Asia | Moldova | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1998 | 2001 | 2001 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/453241474944054373/text/000020051-20140529074520.txt | http://documents.worldbank.org/curated/en/453241474944054373/pdf/000020051-20140529074520.pdf | The reform agenda was too ambitious for the time allocatedMoldova has been slow to privatize large segments of its industry, placing a heavy burden on the budget and the rest of the economy. Reform progress overall will be slow unless these large loss-makers are privatized
P044174 | DJ-TECH.ASSIST (PATARE) | Middle East and North Africa | Djibouti | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/990931475110292975/text/000020051-20140612143236.txt | http://documents.worldbank.org/curated/en/990931475110292975/pdf/000020051-20140612143236.pdf | 1. Technical assistance of this sort without a clearly outlined structural adjustment program and strong government ownership provides little support for development. Without such TA being integrated into an ongoing program, there is little focus nor demand for outputs. 2. TA in countries with low institutional capacity should be well focussed and modest in objective, or used to prepare pilot projects which can be replicated as and when firmer government ownership emerges and as capacity is enhanced over time. 3. The Bank needs to be prepared to invest heavily in supporting TA in countries with low capacity. 4. Mid-Term reviews are essential for poorly performing projects. There was no mid-term review for this project.
P044175 | Biodiversity & Natural Resource Management GEF Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/321741475096568572/text/000020051-20140619111159.txt | http://documents.worldbank.org/curated/en/321741475096568572/pdf/000020051-20140619111159.pdf | 1. Project design, objectives, and indicators need to be realistic, especially when the project aims to introduce new management practices requiring considerable change in legal frameworks and institutional behavior. To this can be added the need for the Bank to adequately understand the legal, institutional, and political context in which its proposed projects will be implemented. 2. Changes in Protected Area management require a substantial time frame and buy-in from a broad set of stakeholders, ranging from local project staff and communities to senior central government decision makers. This project provided support for a specified time and set of activities through a number of pilot projects. The project's long-term success and sustainability, however, will depend on how well these changed practices are adopted beyond the Project Management Team and pilot sites and are internalized and institutionalized within ministry practice. 3. While conservation targets and management objectives and priorities are generally determined on the basis of biological parameters (e.g., changes in species diversity and endemism), implementing successful PA planning and management depends largely on social and economic factors. The Small Grants Program, targeted outreach activities, a national conference on biodiversity and PA management, and other forms of collaboration with NGOs at both the national and pilot project levels helped to strengthen partnerships between government and civil society and further the conservation agenda. This may prove to be one of the most significant long-term outcomes of the project. Similar activities should be considered in other operations having similar objectives. 4. Many of the issues which threaten biodiversity at the project sites and elsewhere in Turkey are related to sectoral priorities and programs (e.g., water management) are beyond the influence of the particular general directorate or Ministry responsible for GEF project implementation. In this regard, the Bank could play a stronger role by better integrating its GEF-supported biodiversity conservation priorities into its larger multi-sectoral portfolio and government dialogue. This is especially important for small projects such as this one which may have comparatively little visibility either in the Bank's country portfolio or in that of the responsible government Ministry. 5. This project experience illustrates the potentially critical significance of a timely Mid-term Review together with highly committed project staff on both the Bank and Borrower's side. However, it also demonstrates the importance of a supportive institutional environment and strong country ownership of project objectives.
P044176 | Biodiversity Conservation Management Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1999 | 2007 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/462301474628670377/text/000020051-20140615105043.txt | http://documents.worldbank.org/curated/en/462301474628670377/pdf/000020051-20140615105043.pdf | World Bank projects geared towards biodiversity conservation in EU Accession countries can benefit from establishing partnerships, such as in this case, with the Danish and Dutch governments, in order to complement activities being implemented under Natura 2000. Since some EU accession countries, like Romania, have developed cost estimates for the implementation of Natura 2000, World Bank projects, including WB implemented GEF projects, can help to build country capacity to meet accession requirements related to EU's overarching Habitats Directive. Although small grants programs designed to support eco-friendly revenue-generating activities are correctly focused towards developing alternative livelihood approaches in fragile park areas, the scope and scale of such a program should be considered against the livelihood needs of the populations surrounding and inside parks. Livelihood needs traditionally fulfilled through timber harvesting, grazing, and mineral harvesting are hard pressed to be surplaced by small eco-tourism opportunities. Payments for environmental service schemes aimed particularly in this case at the private landowner could be considered alongside the development of other sustainable livelihood approaches.
P044200 | BUREAU OF ECON POL | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/872091474566822180/text/000020051-20140613075138.txt | http://documents.worldbank.org/curated/en/872091474566822180/pdf/000020051-20140613075138.pdf | 1. Formulating an independent think tank which is, however, closely linked to government demands for policy analysis can be an effective way to generate policy options and improve economic management. However, such think tanks should be based on a robust financing structure which would allow for changes in procurement and other government policies, if they are to be able to operate for a reasonable length of time. 2. Decentralizing project management to the field is an effective way to promote effective project formulation and supervision.
P044202 | Pilot Poverty Alleviation Project | Europe and Central Asia | Tajikistan | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/150961474510970850/text/000020051-20140607153730.txt | http://documents.worldbank.org/curated/en/150961474510970850/pdf/000020051-20140607153730.pdf | PPAP confirmed that lessons learned in other countries were applicable in a Tajik context. Many communities, even if poor and disadvantaged, were able and willing to play a major role in the identification, preparation, execution and sustainability of micro-projects, and were also willing to contribute to costs through donated labor. Even in remote regions an acceptable quality of work was produced by the small private contracting industry that emerged in response to competitive bidding procedures.High-level and sustained borrower commitment and clarity about the roles and responsibilities of the SIF executive, its Board, the Government and IDA, are needed to overcome serious management implementation problems.Service improvements with sector ministries must be coordinated to ensure the rationalization and utilization of resources.Staff training is important at every level, and in particular it is necessary to invest in project implementation capacity by financing the training of staff in World Bank procedures.
P044213 | FIN MKTS ASSISTANCE | Eastern and Southern Africa | Uganda | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/941861474512505399/text/000020051-20140613042930.txt | http://documents.worldbank.org/curated/en/941861474512505399/pdf/000020051-20140613042930.pdf | The ICR draws the lesson that a small loan cannot induce a major change opposed by "vested interests"; but the more appropriate lesson is that the Bank should heed country developments. The Bank greatly underestimated public skepticism of privatization's merits, especially on the heels of an earlier costly failure. The approach embodied in the project (relying on regulation to correct major problems in a state owned entity) was also inappropriate.
P044305 | TD-TD/CM Pipeline (FY00) | Western and Central Africa | Chad | IDA |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/973641474664832686/text/000020051-20140617134051.txt | http://documents.worldbank.org/curated/en/973641474664832686/pdf/000020051-20140617134051.pdf | Regional energy projects (REPs) are a special breed of regional interventions above all because they may be designed to be little more than big infrastructure projects. Their risks may be high but manageable since rather typical of big infrastructure projects. So are most lessons. The following three emphasize differences with national projects. 1. Much more than national projects, REPs can be politically controversial , and they better have obvious and immediate benefits which is often less the case for improving networks and market organization, than for increasing production .2. Much more than for national projects, complexity is around the corner so REPs should not involve more countries and reforms than needed to optimize the reward-to-risk ratio, i.e., tap a resource and/or economies of scale before those of competition.3. In REPs, governments provide each other some kind of checks and balances and international standards are often followed as common grounds acceptable to all . Thus more than national projects, REPs include features that add robustness and efficiency:Clear and equitable agreements on costs and benefits sharing that tend to really "stick". Project management and operation that are ring-fenced against political interference and very capable, possibly by entrusting it to global energy investors i.e the Consortium of oil majors for the CCPDP.Supervision processes that inspire trust and respect by diverse stakeholders and can work with them all in an agile way i.e. minimizing â€œsilo effectsâ€.The CCPDP's recourse to external independent bodies is a good example.
P044305 | TD-TD/CM Pipeline (FY00) | Western and Central Africa | Chad | IDA |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2010 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/565481468224677215/text/503150PPAR0P05101Official0use0only1.txt | http://documents.worldbank.org/curated/en/565481468224677215/pdf/503150PPAR0P05101Official0use0only1.pdf | 4. Lessons and Future Implications 4.1 The well-known lesson that government ownership and commitment are the major influence o n the effectiveness of projects and programs i s underlined by the experience o f the Chad-Cameroon program. Other lessons learned from the program are identified belowmany o f them also well known but brought in sharp relief by this experience. Because the findings and conclusions are discussed in the earlier sections, the lessons and implications are listed below with a minimum o f elaboration. (Project-specific lessons are included in the corresponding annex.) RELEVANCE, R I S K S , AND TIMING 4.2 International experience has shown that adequate expenditure management mechanisms should be in place, and tested, before a large revenue increase i s likely to accrue. In this case, the time available for capacity-building after Board approval and before the flow o f o i l revenue was much shorter than expected and the revenue much larger-adding to the difficulty o f building capacity contemporaneously with program implementation. A secondary lesson is therefore to build expenditure management capacity as robust as necessary to fit a high scenario o f revenue increase. (The capacity created will be useful to the country even if the high scenario does not materialize.) 4.3 Setting up institutional enclaves and special mechanisms to protect resources and accomplish quick results can damage local capacity in the long term. Such enclaves are generally not successful beyond the short term and, even when successful in the short term, they tend to undermine the already weak local systems and thus long-term development. In this case, although the rationale for the establishment o f the revenue escrow account and the earmarking arrangements was strong in the specific country context in 2000, when tested by reality these mechanisms failed to achieve their objectives and meanwhile stood in the way o f sustainable improvements in fiscal and expenditure management capacity. 4.4 While protecting inputs must remain a paramount consideration, development objectives should be formulated in terms o f outcomes (ifpossible), meaningful outputs, or concrete process improvements-rather than in terms o f inputs-and performance indicators should be limited to thefew key indicators that are critical to achieving the PDOs and are monitorable. Even when the immediate aim o f the project i s to increase resource availability, reduce the cost o f input acquisition, or channel resources toward priority uses, a failure to define clearly the expected results in terms o f key outputs, outcomes, or major process improvements risks distorting the actual design o f the project away from those results. In this case, defining the main project objective for Chad in terms o f budgeted expenditure to be achieved diverted attention away from the efficiency o f expenditure and budget execution. And to l i s t dozens o f key performance indicators o f diverse importance and questionable monitorability makes monitoring impossible. AND DESIGN APPROACH 4.5 If the WBG decides to risk involvement in ambiguous and fluid situations, it pays not to do so in overly detailed and rigid ways. Utmost clarity is needed o n the objectives, principles, and parameters, but the design and implementation modalities should be as fluid as the situation itself, rather than rely on binary choices and numerical rules. This approach, however, may in practice foster a propensity to make successive small compromises, cumulating in the risk that continued Bank engagement may result in acquiescence to inefficient use o f resources. Thus, in addition to clarity o f purpose, an adaptable engagement grounded on flexible but robust dialogue requires a strong fabric o f reciprocal trust between staff and management and continuity o f both. 4.6 Revenue transparency i s necessary-specially for revenues from extractive industries-but i s not sufficient. Transparency on the expenditure side i s critical as well. In this case, setting as the main target a global minimum percentage spending on several sectors implied that the global target could be met even if the intersectoral allocation o f the resources was very different from what had been agreed, and without regard to the efficiency o f their use. 4.7 Project design must be based on recognition o f institutional and administrative capacity. I t i s important in countries with weak capacity to focus on addressing the basic problems rather than attempting to introduce sophisticated practices. In this case, paradoxically, major components o f the program in effect assumed the prior existence o f the very capacity they aimed to build. 4.8 An innovative design, even if it proves unsuccessful, may contain novel elements worthy o f consideration and possible replication. In this case, there are three such elements\. The formation o f the Collige de ContrGle was an excellent and exciting idea, even if it did not enjoy the necessary government support-and such joint publidprivate/ NGO entities have the potential to foster expenditure efficiency as well as social accountability in countries with a government reasonably interested in a prodevelopment, pro-poor expenditure policy. The Provisional Committee to allocate the 5 percent o f the direct o i l revenue to the oil-producing region can be an illustration for similar arrangements in other countries with valuable mineral resources, despite flaws in i t s operation in this case. Finally, the cover and voice given to local NGOs through the dialogue on the preparation o f the program and during i t s implementation should be a regular feature o f all such WBG interventions. WBG PERFORMANCE 4.9 Although in complex and high-profile cases strategic guidance and major decisions must come from the top leadership o f the WBG, it i s not clear in this case that the top-down direct intervention by the Bank President's Office in 2006 was helpful to formulate a new agreement with a better chance o f enforcement. 4.10 In large, complex WBG projects with multiple stakeholders, good WB-IFC cooperation i s important to improve the chances for positive results. In this case there was good WB-IFC cooperation on the main pipeline project, but it also extended to Advisory Services operations. In late-2004, when the IDA-funded capacity-building projects were found to be progressing slower than expected, IFC was able to provide new funding for sustaining the capacity-building initiatives. 4.1 1 IFC's Advisory Services have a signijkantpotential role to help the local private sector. They can enable local companies to participate in the economic activity created by the project; help the sponsors-typically large multinational corporations-meet national content 47 requirements; and promote local economic development. In this case, the Enterprise Center-the focal point o f IFC's Chad SME program-became the cornerstone o f Exxon's procurement platform that was the sole source for all o f i t s purchases in Chad, starting in 2005. 4.12 Whether the World Bank or the I F C i s involved, the concern with development effectiveness goes beyond the gates o f individual projects-however well they may be technically done-to the results o f the overall program. There i s no contradiction between viewing favorably the technical and financial success o f the pipeline project even though the weight o f other unfavorable outcomes leads to a negative conclusion o n the development outcome o f the program o f which it was a component, as in this evaluation. However, the evaluation illustrates the basic point that a part o f a program, however well carried out, cannot be separated from the overall program and the broader setting within which its impact i s being assessed\. a project or a subproject cannot be ring-fenced in the assessment. 4.13 Continuity is critical to manage a project that i s central to a program, and a minimum o f in-house technical competence is necessary to supervise consultants. In this case, the revenue management project had six task team leaders in its seven years, and the Chad capacity-building project relied almost entirely on consultants for the first years, without any in-house expertise in the technical dimensions o f o i l exploration and production. 4.14 Good communications and transparency are particularly important in the context o f a difficult decision. Senior management would want to appropriately consider the views o f key operational managers and staff and ensure the fullest possible measure o f advance consultation with key development partners. IMPLICATIONS FOR THE FUTURE MAJOR 4.15 With substantial o i l revenue expected to continue for many years, it i s s t i l l possible for Chad to escape the resource curse. The difficulties are known. Institutional and organizational capacity remain weak. Macroeconomic sustainability i s injeopardy. Fiduciary risk i s likely to increase in the short t e r m with the unexpected fall in o i l price and revenue in 2009 and 2010-producing pressures to preserve security and regime maintenance expenditures, and hence a downward pressure on pro-development, pro-poor expenditure. Budgeting systems and skills remain quite insufficient for efficient resource allocation, and motivation and integrity have been weakened by the lack o f consequences for the spreading non-compliance with fundamental rules. However, there are scenarios under which a good development outcome in the long run is s t i l l conceivable. The Bank could cooperate with the IMF in monitoring overall fiscal and expenditure outcomes and make a useful contribution by providing good and flexible advice in public sector management-focused o n the basics, recognizing capacity realities, and supported by assertive cooperation o f certain major bilateral partners. But the most important factor would be a new and genuine determination by Chad's government to use the o i l resources for development and poverty reduction, and do so responsively and efficiently. 4.16 The Chad-Cameroon o i l development and pipeline construction program exemplifies the inherent tension between the limits o f the WBG as an international organization and i t s mandate to foster development and poverty reduction. The WBG went very far in 1999 toward the development side, by setting up complicated and prescriptive arrangements to maximize the probability that the Chad government would use the o i l revenue windfall mainly for development and poverty reduction. For various reasons, the revenue windfall turned out to be used in large part for military expenditure and other regime maintenance and for wasteful construction. The governance climate in Chad did not improve-rather the reverse. 4.17 However, it should not be concluded from this experience that the WBG should not intervene in supporting extractive industries because doing so carries reputational risks and success i s unlikely. Indeed, despite the disappointing overall outcomes o n the development and governance side, WBG involvement contributed to a notable increase in expenditures in social sectors and environmental and social protection within the confines o f the project better than they would have been otherwise. The analysis o f this report suggests that realistic and constructive WBG involvement in extractive industries could rest o n combining an insistence on high standards o f environmental and social protection with flexible conditionality o n the composition o f all expenditure and its efficiency-complemented by assistance to strengthen a unified budget system, ensure transparency in both revenue and expenditure, and build capacity in accountability institutions. T o be effective, WBG involvement must be buttressed by an agreement with all other major donors that violation o f the environmental and social standards or backsliding o n fiscal transparency or accountability would trigger consequences for the overall f l o w o f aid t o the government concerned.
P044324 | ENTERPRISE DEVELPMNT | Eastern and Southern Africa | Zambia | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 2003 | 2004 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/439611474857084854/text/000020051-20140612101931.txt | http://documents.worldbank.org/curated/en/439611474857084854/pdf/000020051-20140612101931.pdf | The success of MGS depends on solid ESW and market investigation prior to appraisal and on continuous advice during supervision. In addition, MGS must be accompanied by well planned M&E mechanisms.The success of lines of credit depends largely on solid ESW and a thorough analysis of the conditions prevailing in the private sector.
P044325 | SUPREME COURT MODERNIZATION | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2001 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/589371474908514795/text/000020051-20140607163815.txt | http://documents.worldbank.org/curated/en/589371474908514795/pdf/000020051-20140607163815.pdf | 1. Involving an "NGO unit" in a project to assist with implementation can help build bridges with skeptical civil society groups and help develop solutions to difficult problems. 2. Substantial and widespread improvement of judicial systems seems to benefit from collaboration of diverse stakeholders and a variety of concerned groups. Improved equipment alone is not enough. 3. Improving the integrity and competence of a Supreme Court can have wide-ranging benefits for the whole judicial system. 4 Transparency and participation, as promoted by this project, play crucial roles in establishing credible and effective judicial systems. 5. Defining realistic objectives, and, in the context of a LIL, flexibility in adapting objectives in the light of new information, play an important role in creating successful projects.
P044343 | Biodiversity in Priority Areas Project (GEF) | Latin America and Caribbean | Honduras | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/397111475070500157/text/000020051-20140613090149.txt | http://documents.worldbank.org/curated/en/397111475070500157/pdf/000020051-20140613090149.pdf | Coordinate conservation activities with land management projects. GEF operations demonstrate increased effectiveness when they are tightly coordinated with implementation mechanisms established by and for the underlying investment (Bank or other IA). The ICR reveals that PROBAP enjoyed a more productive period (1998-2001)when PAAR was engaged with policy dialogue with GOH and PROBAP was hence able to deal with the "practical issues of biodiversity conservation and NRM in the field (ICR. p. 15)." The involvement of local communities in the planning and implementation of sustainable resource management and biodiversity protection is important for the development of strategic protected area management plans in accordance with local needs, however NGO capacity/authority to implement these plans is lacking. Management plans will also require long term attention to ensuring full participation for adaptive management, evaluation, and updating. While partnership with NGOs and grassroots organizations is fundamental, a well structured and adequately supported national public institution is necessary to support civil society reform for more effective policy and regulations related to protected areas [fund], land rights of indigenous peoples located in protected areas. Projects that are co-managed require an articulation of clear written responsibilities in the project assessment document to ensure clear reporting, accounting and oversight.
P044383 | URBAN TRANSPORT REFORM AND CAPACITY BUILDING TECHNICAL ASSISTANCE PROJECT | Western and Central Africa | Senegal | IDA |  | Infrastructure | Transport | IDA | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/800191474420488414/text/000020051-20140604055048.txt | http://documents.worldbank.org/curated/en/800191474420488414/pdf/000020051-20140604055048.pdf | Public transport reform entails continued political support and participation from major stakeholders.Successful private sector participation in public transport reform requires economic tariffs and an effective regulatory framework. Mini-bus competition is beneficial in keeping the tariffs low. However, inappropriate regulatory framework can cause safety problems and over supply of services.It is important to provide timely investment to the sector while improving the institutional framework.
P044387 | Structural Adjustment Technical Assistance Credit (SATAC) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2000 | 2000 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/108941474484538821/text/000020051-20140522105031.txt | http://documents.worldbank.org/curated/en/108941474484538821/pdf/000020051-20140522105031.pdf | (a) Tight timetables can help focus counterparts on priority actions, but they also increase the likelihood of project extensions as occurred in this case, which can reduce Bank credibility. (b) Extra care needs to be taken to ensure that procurement rules are followed. The breech of regulations was especially unfortunate (see point (a) under significant shortcomings) in this case as its repercussions slowed down a range of activities.
P044387 | Structural Adjustment Technical Assistance Credit (SATAC) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 2000 | 2003 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/945021511185175484/text/multi0page.txt | http://documents.worldbank.org/curated/en/945021511185175484/pdf/multi0page.pdf | 8. Key Lessons Learned\n8.1 When adjustment projects are synergistic with sectoral investment projects,\neffectiveness can be enhanced\. During the course of the 3 SAC projects, investment projects\nlinked to the adjustment program were undertaken in the education, irrigation, and power\nsectors, and considerable synergy with the adjustment credits was achieved. The financial\ninducement of the SACs provided an incentive for the Ministry of Finance to become an\nadvocate for sectoral reforms, and cooperation between ministries was enhanced. However, the\nEnterprise Development Project was not designed as complementary to the SACs, and thus did\nnot achieve synergy.\n8.2 For an adjustment program focused on private sector-led growth, key constraints\nto private sector development must be confronted\. While considerable emphasis was placed\non privatization and financial sector development, insufficient weight was accorded to critical\ncomplimentary aspects of private sector development, including\. a business environment\nconducive to private enterprise and the entry of new firms; effective enterprise restructuring and\ngovernance; building adequate government capacity to support a market economy; and effective\nprocedures for bankruptcy and liquidation.\n8.3 As a reform program advances, progress may become more difficult\. First\ngeneration reforms, such as trade and price liberalization and the promotion of open markets,\ndid not for the most part pose a major challenge to vested interests. However, further progress\ninvolved fundamental changes in political, judicial, and social institutions, and in many cases\nchallenged powerful interests. Bank staff found that overcoming these important opposing\nconstituencies was much more difficult than earlier reforms, and more difficult than they\nexpected.\n8.4 It is unrealistic to assume that if the fundamentals are in place, an automatic\nsupply response will take place\. A key assumption of the Bank\'s reform program was that, if\nthe fundamentals (i.e., first generation reforms) were in place, a supply response (i.e., broad-\nbased growth stimulated by the private sector) would be forthcoming. The Bank vastly\noverestimated the ability of Armenian workers, entrepreneurs, and institutions to overcome the\nlegacy of decades of Communism and the power of indigenous vested interests. Also\nunderestimated was the cost of the breakup of the Soviet Union to Armenia\'s productive assets.\n8.5 Legal reform should take adequate account of enforcement capacity\. Important\nprogress was achieved by the passage of new legislation, and an impressive framework was put\ninto place. However, the adjustment program placed insufficient emphasis on strengthening the\njudiciary and the actual role the legal system could play in furthering an improved business\nclimate.\n8.6 Continuity and dedication of the country team are key to program effectiveness\.\nDuring the six years covered by this PPAR, there was substantial continuity of the task team\.\ntwo Country Directors, three country economists, no more than two TMs for any of the\nadjustment operations. In addition, project supervision and coordination of the country team\n\n\n31\nwith sectoral specialists was very successful. This contributed significantly to Bank\neffectiveness.\n8.7 Turnover among policy officials hindered reform progress\. During the six years\ncovered by this PPAR, there were seven Prime Ministers and four Ministers of Finance. There\nwas also substantial turnover among other officials concerned with implementing the reform\nprogram. For an official contemplating a brief tenure, it is more difficult to appreciate the\nbenefits of reform, and so this turnover made reform progress considerably more difficult.\n\n\n\n33\nREFERENCES\nEBRD, Transition Report 2000.\nFIAS, Armenia\. Administrative Barriers to Investment, May 2000.\nIMF, Armenia Financial System Stability Assessment, March 2001.\nIMF, Recent Economic Developments and Selected Issues, December 2000.\nIMF, Recent Economic Developments and Selected Issues, May 2001.\nNorwegian Refugee Council, www.idpproject.org.\nOxford Analytica, Armenia Financial Sector, July 24, 2000.\nRamachandran, S. Evaluating Adjustment Lending\. Some Suggestions, Informal Paper, August 2001\nUSAID, Investigation of Factors Inhibiting FDI in Armenia, August 1999.\nWorld Bank, Between State and Market\. Mass Privatization in Transition Economies, September 1997\nWorld Bank, Seize the State, Seize the Day\. State Capture, Corruption, and Influence in Transition;\nAnticorruption in Transition, a Contribution to the Policy Debate, (2000).\nWorld Bank, Armenia\. Restructuring to Sustain Universal General Education, Technical Note, 2001.\nWorld Bank, ECSPE, Armenia/Georgia Country Unit, Growth Challenges and Government Policies,\n2001.\nWorld Bank, Armenia/Georgia Country Unit, Public Administration in Transition, September 1996.\nWorld Bank, Armenia/Georgia Country Unit, Public Expenditures in Armenia, November 1997.\nWorld Bank, Armenia/Georgia Country Unit, Armenia CAS, 2001.\nWorld Bank, ECA, Transition After a Decade, November 2000.\nWorld Bank and IMF (European II Department), Poverty Reduction, Growth, and Debt\nSustainability in Low-Income CIS Countries, February, 2002.\nWorld Bank, ECSPF, Armenia Targeted Financial Sector Review, June 2000.\nWorld Bank, LEGEC, Analysis of Public Awareness on Judicial Reforms, December, 1999- January\n2000.\nWorld Bank, OED, IDA Review of Private Sector Development, March 2001.
P044388 | SATAC | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 1999 | 1999 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/352581475070328643/text/000020051-20140522102258.txt | http://documents.worldbank.org/curated/en/352581475070328643/pdf/000020051-20140522102258.pdf | Three lessons emerge from the SATAC. First, follow-up TA projects should draw from the lessons and priorities that emerge from past efforts, particularly in countries that are new to IDA/Bank lending. Second, persistence in priority areas can pay off, although this should go hand in hand with greater selectivity in determining which cases deserve patience. Third, dissemination of information and discussion of issues related to reforms are key knowledge activities that are often underestimated (particularly with regards to their impact on sustainability).
P044388 | SATAC | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1996 | 1999 | 2004 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/746081468751804137/text/26439.txt | http://documents.worldbank.org/curated/en/746081468751804137/pdf/26439.pdf | 8. Lessons Learned 8.1 Georgia's weak governance severely limitsthe country's ability to create conditions conducive to economic development and the effective use of development assistance-The problems that limit growth inGeorgia transcend economic policy. The political and geographic fragmentation o f the country poses severe challenges to the executive. The inability o f the executive to overcome obstacles posed by the parliament and regional officials, establish a minimumlevel o f the rule o f law, and overcome a pervasive culture o f corruption severely limits the country's ability to establish sustained, broad-based growth with significant job creation. 8.2 For a country such as Georgia, which experienced economic collapse, it is incumbent that the Bank give high priority to prompt measures that can directly mitigate conditions for the poorest. 53This section is based on interviews with energy sector firms, govemment officials, and Bank staff. 8.3 Turnover on the country team limited program effectiveness-From 1994to 1998,there was one Country Economist for Georgia. Officials interviewed cited the benefits that they believe this continuitybrought. However, since 1998, there have been3 Country Economists, and an interval o f around6 months duringwhich the position was unfilled. While there werejust two Country Directors duringthe periodcoveredby this PPAR, and good continuity on the rest o fthe Country Team, the tumover diminished the continuity o f the program, andprobablyconstrained the ESW that was performed. 8.4 A more robust and timely ESW programwould have been beneficial to the design o f the reformprogram-The Country's first poverty studywas completed in 1999; the design o f the reform program would have benefited from earlier work inthis area. A study o fthe sources o fgrowth might also have beenbeneficialbyidentifyingsectors from which growth might be expected to flow, and then considering means by which to facilitate such growth. A Public Expenditure Review-a veryuseful analytical tool for a country with Georgia's perennially weak fiscal situation-was completed in 1996, and then not again until 2002. Fiduciary reports (CFAAs and CPARs) were completed infrequently. The rapid tumover inCountry Economists was probably part o fthe reason for the weak ESW. 8.5 Turnover among policy officials hinderedreform progress-During the seven years coveredby this PPAR, there were seven Prime Ministers and four Ministers of Finance. There was also substantial tumover among other officials concerned with implementingthe reform program. For an official contemplating a brieftenure, it i s more difficult to appreciate the benefits o f reform, and so this tumover made reform progress considerably more difficult.
P044389 | EMG RECOVERY | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 1996 | 1998 | 2000 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/468441474589669381/text/000020051-20140522111346.txt | http://documents.worldbank.org/curated/en/468441474589669381/pdf/000020051-20140522111346.pdf | Four lessons from the ERP are worth noting for other reconstruction operations. First, in emergency operations, intensive efforts at aid coordination are absolutely crucial if development finance is to be disbursed rapidly and effectively. When it is involved early in peace negotiations (as it was in Dayton), the Bank is better positioned to exercise leadership in this regard. Second, when knowledge of the environment is limited (as it often it in post-conflict settings), projects should be designed with enough flexibility to be adapted to the changing needs of the client. Third, an early focus on social sectors is critical to focus attention on restoring social and human capital in war-torn areas. Finally, implementing agencies in post-conflict situations should be managed by a credible, highly professional authority and backstopped by a strong RM.
P044389 | EMG RECOVERY | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 1996 | 1998 | 2004 | PPAR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/520611468768015596/text/28288.txt | http://documents.worldbank.org/curated/en/520611468768015596/pdf/28288.pdf | Lessons * Even in very complex post-conflict situations, traditional Bank assistance in rehabilitating infrastructure and restarting business credit can yield very worthwhile results for the recovery of the war-affected borrower. l The Bank should avoid involvement in activities beyond its core competence. Inexperience and lack of familiarity with landmine clearance, for example are ingredients for failure. l Designs of projects that rely on PIUS for implementation can make for speedy disbursements, but should always include exit strategies to help governments move toward normal operations.
P044390 | EMG TRANSPT RECONST | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Transport | SPF | IPF | 1996 | 1999 | 2000 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/840361474503368867/text/000020051-20140526225642.txt | http://documents.worldbank.org/curated/en/840361474503368867/pdf/000020051-20140526225642.pdf | The lessons of this project cannot be fully evaluated yet. An audit is recommended. Tentatively, the results to date support the following four lessons:(i) Decentralized project management works well; that is, when there are many financiers it is often best to allow each financier to follow its own rules and synchronize the project management by creating a structure for information exchange.(ii) Use local knowledge effectively by involving and engaging the local administrative, informal organizations and local private industries in all aspects of the project and its implementation.(iii) Start institutional development 'organically' [that is don't rush it] as part of the project design and implementation process and use the private sector whenever possible.(iv) Keep the project compatible with the local implementation capacity.
P044391 | EMG GAS REHAB | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2000 | 2000 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/946841474512698143/text/000020051-20140526231959.txt | http://documents.worldbank.org/curated/en/946841474512698143/pdf/000020051-20140526231959.pdf | The financial and institutional objectives under emergency projects demand adequate attention to ensure the objectives are achieved. This requires the involvement of Government in identifying how it can best help achieve these objectives and provide its support for the overall financial and institutional development of the implementing agency.When preparing Emergency Recovery Loans (ERL) , the project's scope should be limited to restoring assets and production levels in the disrupted country. According to OP 8.50, "ERL's do not attempt to address long-term economic, sectoral, or institutional problems, and do not include conditionality linked to macro-economic policies." As the experience with this project illustrates, the physical objectives were achieved, but sectoral issues related to gas pricing reforms and the long-term institutional weaknesses of Sarajevogas could not be addressed adequately in the project's two-year implementation time frame.
P044392 | EMG DIST HEAT REHAB | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | SPF | IPF | 1996 | 1999 | 2000 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/132371475097862661/text/000020051-20140526232512.txt | http://documents.worldbank.org/curated/en/132371475097862661/pdf/000020051-20140526232512.pdf | (a) emergency operations require flexibility in project design, intensive Bank supervision (ideally partially field-based), and strong internal coordination within the Bank (particularly on disbursement matters)(b) when an emergency operation requires that a project goes ahead without a firm financing plan, procurement packaging should insure that Bank-financed components will not be affected by delays in cofinancing.(c) a strong project implementation unit (PIU) within the beneficiary is required for emergency projects(d) PSAs are cumbersome to administer and alternative advance mechanisms (e.g. extended PPFs) may be more appropriate
P044393 | Emergency Landmine Clearance Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Transport | IDA | IPF | 1997 | 1999 | 2000 | ICRR | Less than 10 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/887191474574702622/text/000020051-20140526205531.txt | http://documents.worldbank.org/curated/en/887191474574702622/pdf/000020051-20140526205531.pdf | The ICR contains well thought out lessons. The following deserve special mention:i) In the immediate post-conflict period, it is crucial to focus on information collection and dissemination - for designing programs of action, defining priorities, and deciding on commercial versus non-commercial methods of deminingii) Commercial approach to demining has proven to be much more effective than any other method, at least for priority areas where the importance of demining is greatestiii) The Bank's comparative advantage in stand-alone demining projects is in building institutions, in helping develop sustainable and commercially based demining activities and in the application of sound project management principles.The Borrower noted that a higher level of implementation performance could have been achieved if procurement had been streamlined including simplified bidding documentation and Bank review process. This observation is of generic value to all emergency projects.
P044393 | Emergency Landmine Clearance Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Transport | IDA | IPF | 1997 | 1999 | 2004 | PPAR | Less than 10 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/520611468768015596/text/28288.txt | http://documents.worldbank.org/curated/en/520611468768015596/pdf/28288.pdf | Lessons * Even in very complex post-conflict situations, traditional Bank assistance in rehabilitating infrastructure and restarting business credit can yield very worthwhile results for the recovery of the war-affected borrower. l The Bank should avoid involvement in activities beyond its core competence. Inexperience and lack of familiarity with landmine clearance, for example are ingredients for failure. l Designs of projects that rely on PIUS for implementation can make for speedy disbursements, but should always include exit strategies to help governments move toward normal operations.
P044394 | EMG FARM RECONSTR | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Sustainable Development | Agriculture and Food | SPF | IPF | 1996 | 1998 | 1999 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/222021474849767018/text/000020051-20140519064419.txt | http://documents.worldbank.org/curated/en/222021474849767018/pdf/000020051-20140519064419.pdf | (i) Emergency reconstruction projects should be simple so that implementation can be rapid.(ii) Those who do not qualify for agricultural production assistance should be given alternative assistance, rather than create failing agricultural units.(iii) Even in emergency situations, beneficiaries should participate in specification of goods and services to be procured.(iv) Cost recovery is feasible and desirable even in emergency projects, but financial institutions handling credit should participate more fully in design.(v) Delegation of project supervision to a Bank team located in a field office is highly desirable for effective and efficient implementation.
P044395 | EMG ELEC POWER REC | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 1999 | 2000 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/229691475097816788/text/000020051-20140526224043.txt | http://documents.worldbank.org/curated/en/229691475097816788/pdf/000020051-20140526224043.pdf | It is advisable to avoid the use of a Project Start-Up Advance (PSA) to procure goods and services before Board Approval because the handling transfers and adjustments of funds between projects (in this case the District Heating, Gas and Power Projects) create difficulties when disbursements are to be made. It would be better to consider the use of an enlarged Project Preparation Facility (PPF) for such purposes.
P044395 | EMG ELEC POWER REC | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 1999 | 2004 | PPAR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/102001468740692990/text/264720BA0PPAR.txt | http://documents.worldbank.org/curated/en/102001468740692990/pdf/264720BA0PPAR.pdf | 5. Findings and Lessons 5.1 The following findings emerge from the performance assessmentof these two projects\. l When electricity supply cannot be organized in a manner that is technically and economically optimal there are high costs to a country in terms of lost efficiency and economies of scale. l In the face of political obstacles, it may be slightly easier in electricity than in other sectorsto bring about greater trade across frontiers becauseelectricity is not a highly visible commodity and the presenceof power lines is no indicator of whether power is flowing or in which direction. However, BiH is probably unique in electricity being used to spearheadinternal political unification and nation building. The jury is still out on whether this tactic can succeed. l The Bank can deliver successful emergency reconstruction projects on a fast track basis, despite internal constraints that work against rapidity. 40. The Region pointed out that . .significant funds are required for the social costs and for the concurrent investments for the mines. The Bank is under tremendous pressure to be selective as the availability of IDA funds shrank from US$lOO million/year under IDA12 to US$30 &yr under IDA14. 41. The OED mission was not able to ascertain the views of the government of the Republika Srpska on this issue. l The Bank's current guidelines for emergency recovery projects do not explicitly indicate whether it is acceptable to not apply the Bank's usual environmental safeguardsto such projects for reasonsof urgency and speedof processing. 5.2 The experience offers two lessons of note\. l Power sector restructuring in a heavily coal-based power system cannot be delinked from reform of the coal industry becauseof the predominance of coal in the cost of producing electricity from it. Reforms in both sectors should be addressedin parallel, or preferably coal sector reforms should precede electricity, but not lag behind; l EPBiH's experience with tariff increases and improved revenue collection in the immediate aftermath of the peace accord, shows that consumers arewilling to contribute to the cost of the rapid restoration of electricity supply.
P044424 | WAR VICTIMS | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1996 | 2000 | 2001 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/697711474560520196/text/000020051-20140529070650.txt | http://documents.worldbank.org/curated/en/697711474560520196/pdf/000020051-20140529070650.pdf | The ICR highlights the following three lessons:Sufficient staff must be deployed for implementation (procurement, disbursement and supervision tasks and--even in a difficult post-conflict situation--for monitoring and evaluation (inc. a patient and service tracking system).Strengthening procurement capacity in the immediate post conflict situation--where a borrower typically has insufficient skills in this area--is essential to overcome delays in implementation.It is necessary to match post-conflict objectives to long-term objectives. This project took the opportunity of the post-conflict situation to meet immediate needs and to introduce a new model of care that, while now widely accepted as standard in OECD and some developing countries, was a radical shift for Bosnia and Herzegovina. The introduction of this new paradigm may not have been possible in Bosnia and Herzegovina under any other circumstances.Two more lessons derive from the experience:Even in a disruptive post-conflict situation of physical and institutional devastation, project design should incorporate explicit performance targets and arrangements to monitor and evaluate their achievement. These need be only a few and simple, but which directly relate project outputs to the intended development outcomes. A sophisticated multi-variate monitoring system is not necessary to effectively track outcomes that reveal the efficacy and efficiency of project performance.Some proportion of Bank project preparation and supervision effort should be focused upon securing the ownership of co-financing donors and keeping them on board.
P044444 | Electricity Market Development Project | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2000 | 2001 | ICRR | >=50 million & <100 million | Highly Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/455761474586469629/text/000020051-20140529154533.txt | http://documents.worldbank.org/curated/en/455761474586469629/pdf/000020051-20140529154533.pdf | In a country where the economy is basically barter-based and the Government condones the culture of non-payment, the introduction of an advanced model of a competitive power market is bound to fail.The Bank should not finance the purchase of fuel as a way to create working capital of a power utility, unless there exists a genuine force majeure transient circumstance. Working capital should be financed through short-term borrowing, suppliersâ€™ advances and equity.Peer reviewersâ€™ opinions should be given more weight in the project approval process, specially when they are critical of an operation. In this case, peers expressed reservations about the project, particularly about generation companies borrowing long-term to finance fuel, the role of the regulator when the power enterprise are in the public sector, and the insufficient emphasis on privatization
P044445 | PROV.PENSION1 | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1997 | 1998 | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/581891474590828509/text/000020051-20140521035324.txt | http://documents.worldbank.org/curated/en/581891474590828509/pdf/000020051-20140521035324.pdf | For a sophisticated Borrower, providing analytical tools--so they can perform their own analyses--can be an effective way to help achieve "buy-in." Consistency of objectives and coordination between Bank operations help assure successful outcomes. The loan was designed to complement extensive technical work (at the provincial level) which had been performed in previous Bank operations.Strong link between the project and important GOA goals helps assure ownership. The GOA had established as high-priority goals the strengthening of its national pension system, and the reduction of its financial vulnerability produced by unsustainable fiscal deficits in the provincial public sector. Projects must design incentives around the needs of subnational borrowers to successfully complete projects. This project utilized fiscal savings, reduced administrative burden, and the removal of pressures to expand benefits as incentives to stimulate the cooperation of provincial authorities. The stakeholders were heavily involved and all parties acted in a coordinated manner.
P044447 | PROVINCIAL REFORM ADJUSTMENT LOAN - CATAMARCA | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2001 | 2006 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/443961475099052734/text/000146597-20140617162600.txt | http://documents.worldbank.org/curated/en/443961475099052734/pdf/000146597-20140617162600.pdf | The likelihood of success of sub-national adjustment lending is conditioned by several strategic contextual factors and a number of operation-specific design factors. Important contextual factors are: (a) an adequately supportive macroeconomic environment and policy framework, (b) an adequately supportive sectorial policy environment at the national level, (c) a consistent, well-defined framework of intergovernmental finances; (d) a partner government with a good reform track record operating within an adequately supportive political environment.The likelihood of success of sub-national adjustment lending is also conditioned by a number of operation design factors: (a) a reform agenda that is well-defined and ready for or, better, already in implementation; (b) focused on results, as distinguished from intermediate steps; (c) well-defined monitoring indicators, including baselines and targets, at appraisal to guide implementation.
P044447 | PROVINCIAL REFORM ADJUSTMENT LOAN - CATAMARCA | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2001 | 2006 | 2009 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/323551468220163744/text/489850PPAR0Arg1IC0Disclosed07121091.txt | http://documents.worldbank.org/curated/en/323551468220163744/pdf/489850PPAR0Arg1IC0Disclosed07121091.pdf | 6. Conclusion and Lessons 6.1 This chapter discusses two issues that cut across iLLe operations\. first, the question o f whether, as a result o f the crisis, the design and restructuring o f the PRL-I11 operations supported weaker reforms that would have been supported otherwise, and the lessons that can be extracted from their implementation. Did the crisis prompt resource transfers against weaker reforms than would have been supported otherwise? 6.2 This question can be posed in the two steps o f the PRL-I11 operations in which the reforms that the loans supported were defined\. during their design and during their restructuring. Regarding the design o f the loans, this PPAR answers the question by analyzing the history o f the P R L operations in Argentina, including the way they fitted within the country assistance strategy, their objectives and the thoroughness o f their design. To answer the second aspect o f the question, the report examines the process o f loan redesign from 2002 to 2003, and the consistency between the reforms supported by the redesigned loans and their original objectives. THEDESIGN OF THE OPERATIONS 6.3 I t i s clear that the PRL-I11 loans were part o f the efforts that the Bank, along with the rest o f the international financial community, was making in 1999-200 1 t o help Argentina stem the incoming crisis. It i s also clear that the two objectives o f the operations-to improve the provincial governments' ability to deliver social services while improving their fiscal situation--coincided exactly with the policies that the government was pursuing regarding the provinces in its attempts to stave o f f the crisis. Further, the design o f the operations as fast-disbursing ones facilitated the rapid transfer o f resources under critical circumstances-in fact they were disbursed very close t o the collapse o f the currency board. All these facts seem to lend credence to the idea that the loans were just part o f the ultimately failed efforts to avert the collapse o f the currency board. 6.4 Yet, the PRL-I11operations were not improvised vehicles hastily designed t o help in an urgent macroeconomic stabilization effort. O n the contrary, their objectives had been part o f the strategies o f the government and the Bank throughout the 1980s and the 1990s. They were reasonable operations with worthy objectives that proved very important for the long-term stability o f the country. Moreover, the outcomes o f the operations, which was at least Moderately Satisfactory in the three PRL-I11 (as rated by the I C R and t h i s report), belie the idea that the structural reforms dimension o f the operations was neglected. Finally, the fact that the first disbursements o f t w o o f the three PRL-I11 operations were delayed for almost one year until the provincial governments complied with the loan conditionalities indicates that the Bank was giving first priority to meeting the objectives o f the structural reforms rather than to transferring the resources urgently. Still, even though the operations were reasonable and well designed, disbursing so close to the collapse o f the currency board could be judged negatively. However, the Bank could not legally stop disbursements if the borrower had complied with all the established conditions for disbursement-which was the case o f the PRL-111. 6.5 Thus, to the question o f whether the PRL-I11 operations were just excuses to transfer resources to Argentina during the 2001 crisis, this report answers no. They were bona fide structural reform operations and they were designed as such. RESTRUCTURINGS THELOAN 6.6 Regarding the quality o f the conditionality o f the conditionality that replaced the original one as a result o f the 2003 restructuring, the experience in the PRL-I11operations was mixed. In some instances substantive actions that should have been taken by the government were replaced with the completion o f studies. This happened in all three PRL-I11 loans. Yet, in the most important instances restructuring adapted the actions needed to attain the loans objectives to the new circumstances prevailing after the crisis. This was the case, for example, o f the modification o f the privatization conditions in the three PRL-I11operations. Certainly, the measures that became the restructured conditions (mostly mimicking administrative measures that private operators would have undertaken) were second best actions; the fact, however, was that the first best conditions were unattainable. Even more substantially, in Catamarca the condition regarding the provincial bank was changed from privatization to liquidation, a politically difficult condition that the province implemented. 6.7 Thus, while there were some cases o f watering down o f conditions, with respect to the most important objectives the restructuring represented an adjustment t o a change in circumstances. Lessons (1) I t is possible to attain satisfactory results in provincial structural adjustment reform and operations even in extremely difficult conditions. 6.8 The first lesson answers the basic question posed to t h i s PPAR. The three PRLI11 operations evaluated in this report were carried out under extremely difficult macroeconomic conditions; still, they had outcomes that were at least Moderately Satisfactory; risks to development outcomes that were uniformly Moderate and Bank and borrower performances that were either Moderately Satisfactory or Satisfactory. In fact, the only unsatisfactory operation-the San Juan loan-was implemented under favorable macroeconomic conditions. This shows that the macroeconomic condition o f the country was not the crucial factor determining the success o f the operations. 6.9 This lesson contradicts one drawn by the I C R o f the Santa Fe PRL, which states the following\. Provincial policy development operations such as Santa Fe's P R L are only appropriate under stable macroeconomic conditions. While this type o f operation requires an overall satisfactory macroeconomic policy framework, such framework is the responsibility o f the national government and beyond the sphere o f action o f provincial authorities. As illustrated by the experience o f Argentina's last series o f PRLs, including that o f Santa Fe, failings or uncertainties at the macroeconomic level can override substantial achievements at the provincial level, leading to loan cancellation. 6.10 Reading this lesson in isolation would give the impression that the Santa Fe operation had been rated Unsatisfactory by the ICR. Yet, the I C R rated the outcome o f the Santa Fe operation Moderately Satisfactory, clearly contradicting the idea that these operations cannot produce satisfactory outcomes in difficult circumstances. Moreover, the same I C R further contradicts such idea in yet another lesson, with the following words\. The Bank's continuous engagement during critical periods can help sustain ongoing reforms and protect previous achievements. The experience o f Santa Fe's PRL, indicates it was beneficial to have an operation in place providing a clear roadmap for enhancing service delivery in key social sectors during times o f economic, political and institutional chaos. The substantial financial resources attached to the PRL became even more attractive in face o f the overall lack o f liquidity in the country in 2001-2002, providing the province additional incentives t o sustain the ongoing reforms in the short and medium term. The experience o f Santa Fe's P R L also shows that sector reforms are possible even when the overriding priority i s fiscal adjustment; however, sector budgets need to be protected, in particular to ensure that cost savings from efficiency gains can be reinvested into the sector. 6.1 1 In the opinion o f this PPAR, this lesson, which clearly supports the idea that provincial reform loans can be satisfactory even in very difficult conditions, can be applied to all the reviewed PRL-I11 operations. O f course, it would be better t o have stable economic conditions for any Bank operation; yet, even if a country i s in situations as unstable as that o f Argentina in 2001-2002, operations aimed at supporting important objectives in terms o f fiscal stability and the delivery o f social services can be extremely useful if properly designed and owned by the borrowers. 6.12 Moreover, structural adjustment operations may be highly desirable in cases o f macroeconomic instability if-as was the case with the PRL-I11loans-they were aimed at resolving macroeconomic imbalances and improving the delivery o f social services, both o f which tend t o deteriorate in unstable macroeconomic situations. (2) The sub-national approach may be optimal to deal with the improvement and protection of social services in times of crisis in cases where such services are decentralized to the provinces. 6.13 Prior to the P E S , the volume o f resources available for social services, mostly based o n transfers from the federal government, had been highly unreliable because social expenditures were frequently adjusted to accommodate fiscal needs at the federal level. Furthermore, the volume and quality o f the services afforded by these resources were diminished by substantial inefficiencies at the provincial level. By helping Argentina to institutionalize the transfers under a predictable system as well as by helping the provinces to increase the efficiency o f their social services delivery, the PRL-I11 operations effectively protected such delivery much beyond what could have been attained with operations at the national level. (3) Good economic and sector work and close relationship between the supervision teams, the country office, and the borrower are key factors contributing to the success of operations. 6.14 The fact that PRL-I11 was able to produce three loans that were rated at least Moderately Satisfactory in the midst o f a catastrophic environment i s largely attributable to the long and conscientious preparation o f the PRL series, which in turn was based o n solid economic and sector work as well as in the experiences with the previous PRL operations in Argentina. 6.15 The results were also favorably influenced by the quality o f the Bank supervision. Development policy operations pose a challenge in terms o f supervision even under normal circumstances. This challenge was much greater in the case o f the PRLs given the extraordinary economic and political circumstances o f the 2001-2002 crises. The supervision teams forged close relationships with the provincial authorities, and helped in designing solutions for implementation problems, as well as provided efficient coordination with different networks in the Bank. Through their continuous contact, these teams and the country office helped to maintain the commitment o f the provincial governments to the reforms as well as to find solutions to problems encountered during the implementation o f the loans. Also, in most cases, the Bank adjusted the conditions regarding some reforms that became unfeasible as a result o f the macroeconomic crisis .in fully satisfactory ways or in acceptable second best ways. (4) Large numbers o f conditions render the supervision and evaluation o f operations difficult, particularly if the conditions are not prioritized. 6.16 The reviewed operations had 272 conditions before the 2003 restructuring. Just the three PRL-I11operations had 256. Certainly, some o f these conditions were crucial strategically while others were just preconditions to attain the crucial ones, or less important complements to them. Nonetheless, the large number o f non-prioritized conditions creates severe problems in the implementation o f the loans, in their supervision, in the authorization o f disbursements, and in evaluation. In fact, the evaluation o f some o f the operations could be significantly different if priorities had been established at the time o f appraisal. 6.17 For example, this PPAR rated the outcome o f the Catamarca PRL Moderately Satisfactory (and not Satisfactory or Highly Satisfactory) because it failed in some educational reforms. T h i s rating may underestimate the performance o f Catamarca, which, for example, was able to liquidate the provincial bank when it failed to privatize it. This was a feat that the more developed Cordoba could not or was not willing to do. The Catamarca government also concessionedthe water company, while neither Cordoba nor Santa Fe was able to fmd a comparable solution when they also failed to privatize their energy companies. Inthe absence o f prioritization o f the loan components in the PRLs, it is impossible to compare these achievements with the creation o f a system to track cost recovery in hospitals, or the creation o f new criteria for the licensing o f physicians. (5) The idea that provinces should increase their tax collections as a presumptive objective should be subject to scrutiny, as that objective needs to be balanced with other objectives such as the efficiency of taxation and the need to improve the business environment, depending on the situation. 6.18 The PRLs assumed that increasing the share o f own-resources in total provincial revenues was a desirable objective. This, however, i s not necessarily always the case. There are two instances in which reducing the share o f local taxes could be optimal. The first one i s when national taxes are more economically efficient (they cause lesser distortions) or cheaper t o collect than provincial ones at the margin. In this case, the optimal taxation policy would be to raise all taxes nationally and then allocate them to the provinces. This principle was applied in Cordoba and Santa Feywhere the governments reduced their respective tax revenues by eliminating distorting taxes. The second i s when the reduction o f taxes reduces the cost o f doing business, such as in the case o f Cordoba. In this instance, although the eliminated taxes were efficient, their elimination was optimal because the private sector could allocate the liberated resources better than the government. In sum, increasing the share o f local taxation could be optimal or not, depending o n the circumstances. B o t h Cordoba and Santa Fe were correct in eliminating distorting taxes, meeting one o f the conditions o f the loan, even if they then failed to comply with the objective o f increasing their own tax collections-particularly because after that they attained fiscal surpluses. (6) Political feasibility of reforms must be a factor in the evaluation of new operations 6.19 The contrast between the generally satisfactory outcome o f the PRL-I11loans in the midst o f a serious macroeconomic crisis and the highly unsatisfactory one o f the San Juan PRL-I1 loan within normal macro circumstances illustrates the limits that politics may set for the effectiveness o f Bank operations. The factor that led to the highly unsatisfactory outcome o f the San Juan operation was the government's inability to overcome the political resistance against a measure that would have been extremely controversial almost anywhere\. reducing the salaries o f the teachers. This resistance provoked widespread fiscal and political failure. The PRL-I11operations, which focused on less politically controversial objectives, were more successful overall. The unsatisfactory educational outcome o f the PRL-I11 Catamarca operation was also related to the political obstacles found in that area. This experience suggests that political economy considerations should be taken into account in the design o f loans. O f course, assessing the political feasibility o f reforms is more o f an art than a science. Yet, there are some cases, as it in San Juan, in which reforms are clearly too risky because they include measures that could be perceived as too radical or illegitimate by significant portions ofthe population.' ' It should be noted that the reduction in salaries was not part o f the conditionality o f the San Juan loan. The provincial government reduced those salaries in 1995, two years before the approval o f the loan, as part o f i t s own program o f reforms. The reduction, however, caused a backlash that eventually destroyed the reforms program that the loan supported. (7) The benefits of Bank operations can be substantially enhanced through a flexible approach to reforms 6.20 The provincial governments and the Bank took a flexible approach to the operations that greatly enhanced their ability to help Argentina t o meet their original objectives while accommodating the economic crisis. While, as acknowledged in the previous section, some o f the restructured conditions o f the PRL-I11operations watered down the initial objectives o f the loans, most o f them did meet those objectives, or some second best, through other means when the original ones became unfeasible. Moreover, the Bank showed additional flexibility by accommodating different adjustments in different provinces. In this way, for example, when privatization o f the provincial bank became impossible, Catamarca liquidated it while Cordoba opted for hiring professional bankers while instructing them to mimic private administrative rules in managing it. Catamarca concessioned its water company while Santa F e and Cordoba rationalized the management o f their electricity companies. W h i l e the outcomes o f the restructured measures tend to fall short o f the original objectives, they represent substantial improvements relative to the original conditions.
P044449 | RURAL WOMEN'S DEVELOPMENT | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/319551474482452936/text/000020051-20140615094153.txt | http://documents.worldbank.org/curated/en/319551474482452936/pdf/000020051-20140615094153.pdf | Based on the ICR several key lessons are identified. (i) In a multi-state project, clearly defined functions and responsibilities of the Center and the individual states are necessary for successful implementation. (ii)A robust monitoring and evaluation system that provides critical information on the process and outputs and outcomes is essential to ensure not only that the project is on track but also to assess how far the various components contribute to achievement of project objectives.(iii) Mapping and assessing the expertise and capacities of partner organizations for implementing/supporting different project objectives is critical.(iv) The project experience points to the need to tie women's training to market demand to ensure sustainability. This means not simply assessing market demand but also assessing demand at a price and estimating whether the to-be-trained women can deliver adequately at that price.
P044457 | EMG TRANS/MINE CLR | Europe and Central Asia | Croatia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/781581474553490822/text/000020051-20140607152544.txt | http://documents.worldbank.org/curated/en/781581474553490822/pdf/000020051-20140607152544.pdf | Favorable conditions such as sustained funding, timely payments, well-drafted and enforceable contracts, adequate regulatory capacity, and private sector access to debt financing may promote a rapid increase in the number of private sector contractors, as well as promote development of their quality and performance. In addition to promoting economic activity and job creation, governments may achieve substantial savings in costs, through efficiency gains as well as avoiding expenditures on equipment that the private sector may be able to finance on its own. In this Project, the mine clearing component serves an example of the speed with which private contractors may develop, once favorable conditions have been established.Discrete, though related, components result in different implementation speeds, and this needs to be coordinated both at the design stage and during implementation. Whereas transport components dealt with established institutions, landmine clearing was new, and institutions had to be developed, priorities defined and procedures established. As a result, there were significantly different implementation speeds.
P044457 | EMG TRANS/MINE CLR | Europe and Central Asia | Croatia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2002 | 2004 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/497791468770732994/text/28381.txt | http://documents.worldbank.org/curated/en/497791468770732994/pdf/28381.pdf | 6. Lessons 6.1 The following lessons emerge from the two projects\. P Highway 'sector' projects needto take a comprehensiveview o fthe sector, andinclude appropriate, sector-wide performance indicators. One key indicator i s the overall condition o f the roadnetwork, since it is useful tojudge the level ofresoiirces allocated for highway maintenance, the efficiency o f roadmaintenance planning and operations, and the impact o f road sector expenditures on the operating costs o f road vehicles. Barring exceptional circumstances, overall roadnetwork condition should be expected to improve duringproject implementation. Such sector projects should take the necessary actions to ensure that the responsiblehighway agency has inplace an adequate system to monitor road network condition. Separation o f agencies and funding sources for the maintenance and improvement o fthe national road network and for the construction o fmodem motorways, as Croatia didin 2001,can be an effective way to ensure a stable level o f funding for roadmaintenance. To ensure that resources are well utilized, especially for the modernization o f the road system, there should be stringent rules for the allocation o f the funds, including conduct of outsourced feasibility studies and transparent competitive procurement. Finance.Foreigninvestorsare likely to be moreconcemedbythe fiscal policiesrather than by a fast-developingtransport system. 21. The Status of Projectstable, dividedintogoods andworks sub-tables,providedfor each contractfinanced underthe project, contract number, description, methodof procurement, signingdate, quantity (in square meters), contract value (inDEM), disbursedfromWorldBank, from government funds, undisbursedbalance, and area actuallycleared. Bank-financed projects byrequiringcompetitive procurement andexemplifying its advantages can leadto the establishment o f competitive procurement throughout a whole industry andto the development of qualified domestic contractors, as it happened with the demining industry inCroatia. The need to improve transparency of its public procurement process is an important issue inCroatia's publicpolicy, inview ofcasesof non-competitiveprocurementinthe motonvay program and ofcomplaints byunsuccessful bidders for demining contracts, both inthe emergency transport project under review and the earlier Emergency Reconstruction project.22 22. The PPAR of the Emergency Reconstructionproject noted that complaints had been duly investigated and that they reflected fractious competition rather than corrupt practices.
P044458 | WATER, SAN & URG WORKS | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Sustainable Development | Water | SPF | IPF | 1996 | 1999 | 2001 | ICRR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/551911474657979921/text/000020051-20140529072726.txt | http://documents.worldbank.org/curated/en/551911474657979921/pdf/000020051-20140529072726.pdf | (1) Emergency projects necessarily focus on meeting urgent needs but should also be designed to gradually meet objectives that are relevant for the long-term sustainability of sector operations;(2) The multiplicity of donors and their differing financing terms can create tensions between municipalities that receive widely differing financing terms for similar investments. The necessary harmonization of financing terms could be helped by creating a central financing facility that would finance all emergency works under the same terms, and through which all external aid would flow; and(3) Implementation should utilize locally available expertise to a maximum,. and (more expensive) expatriate technical staff should be limited to areas where they clearly add value.
P044458 | WATER, SAN & URG WORKS | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Sustainable Development | Water | SPF | IPF | 1996 | 1999 | 2004 | PPAR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/112871468743656172/text/274920BA.txt | http://documents.worldbank.org/curated/en/112871468743656172/pdf/274920BA.pdf | Lessons 30. Two main lessons emerge from this project experience. 0 In an emergency reconstruction program, it is essential to have a workable coordination system in place to avoid duplication of effort and inconsistent applications of policy that lead to different treatment regimes. The objectives of this project were not attained at the planned level, as most funding aid-agencies opted to work on their own (instead of contributing to the agreed upon SRP). The use of differing sets of policy and procedures caused confusion during project implementation, and unplanned overlaps in donor activities led to a reduction in the overall program scope. In the end, lack of coordination weakened sector reform activities, and prevented the phased implementation of the rest of the SRP operations within the anticipated timeframe (seeparas. 13 and 15). 0 The rapid post-emergency appraisal of operations sometimes requires flexibility, but it is still necessary that key components be fully defined within the project implementation period. In this case, institutional strengthening should have included well-specified and realistic activities that would have assisted sector agencies to improve operational efficiency in incremental steps. In the midst of hectic repair and rehabilitation efforts, institutional development measures such as reducing unaccounted water, improving efficiency and skills of staff and improving collection of bills, received lower priority. A stepwise package of the most urgent measures should have been defined in the project documents to ensure that the various entities could take needed first steps to return to normal operations after the crisis (seeparas. 17, 19-- 21, and 26).
P044459 | EMG HOUSING REPAIR | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 1998 | 1999 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/879281475098822787/text/000020051-20140519081103.txt | http://documents.worldbank.org/curated/en/879281475098822787/pdf/000020051-20140519081103.pdf | (a) Emergency projects should be of low complexity, (b) the policy content of emergency projects should be in harmony with the post-war social context and with other donors activities in the country, (c) emergency projects should be of modular nature, allowing for continuous adjustment of project size and scope, (d) continuous technical assistance should be built into emergency projects, and (e) delegation of project supervision to Bank staff located in a field office is essential to ensure timely client service.
P044485 | CN-Shanghai Waigaoqiao | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/418271474420856228/text/000020051-20140618055239.txt | http://documents.worldbank.org/curated/en/418271474420856228/pdf/000020051-20140618055239.pdf | The main lessons which may be drawn from this successful operation are:1. Experience during implementation confirms that of other recently completed power sector projects in China â€“ construction management was successfully performed by the implementing agencies. There is really no need, in China (or perhaps in other countries where implementing agencies have staff of a high technical competence), for the relatively heavy provisions for engineering and construction management TA which have been included in most projects. The use of external support on a selective, as-needed basis, determined in consultation with the implementing agency, is to be preferred to the use of international consultants for the entire task. 2. The project demonstrates the success of piloting new processes and new approaches â€“ in this case, for example, the Bubble Concept for more cost-effective emissions reduction, and the innovative approach to accessing international finance. However, possible extension to other countries should depend upon the presence â€“ as in China â€“ of highly competent implementing agencies and strong, demonstrated governmental commitment to sector reform.3. Procurement based on separate packaging of goods can lead to lower bid prices through greater competition. However, such packaging is demanding for the implementing agencies which must deploy considerable skill and time in resolving inevitable conflicts and interface problems. There is a trade-off between potential price advantages and the risks arising from the use of the packaging approach.4. As with many other successful power projects in China and elsewhere, this operation demonstrates the importance of a strong Bank project preparation and supervision team, drawing on all the necessary range of skills. Continuity of personnel is of great importance. The practice of using the same team to supervise multiple projects in the same country is not only cost-effective, but benefits from inter-project synergies.
P044521 | EMG DEMOB & REINTEG | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2000 | 2000 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/383851474493210956/text/000020051-20140528125401.txt | http://documents.worldbank.org/curated/en/383851474493210956/pdf/000020051-20140528125401.pdf | In uncertain circumstances such as obtained in BiH after the war, projects need to be kept simple, formulated in a modular fashion to allow adjustments to availability of donor financing (rather than hold up progress on a critical element while awaiting decisions from donors). In these circumstances, it is also important to provide well-seasoned management assistance with substantial experience.
P044521 | EMG DEMOB & REINTEG | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2000 | 2004 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/520611468768015596/text/28288.txt | http://documents.worldbank.org/curated/en/520611468768015596/pdf/28288.pdf | Lessons * Even in very complex post-conflict situations, traditional Bank assistance in rehabilitating infrastructure and restarting business credit can yield very worthwhile results for the recovery of the war-affected borrower. l The Bank should avoid involvement in activities beyond its core competence. Inexperience and lack of familiarity with landmine clearance, for example are ingredients for failure. l Designs of projects that rely on PIUS for implementation can make for speedy disbursements, but should always include exit strategies to help governments move toward normal operations.
P044522 | Essential Hospital Services Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1997 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/832371475079027119/text/000020051-20140607165858.txt | http://documents.worldbank.org/curated/en/832371475079027119/pdf/000020051-20140607165858.pdf | 1. Projects can be mounted under extremely difficult political (post-civil war) circumstances, if the project is kept relatively simple. 2. It is important to ensure a skills component in health projects meant to restore and improve clinical services.
P044523 | BASIC HEALTH | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/274901475100567729/text/000020051-20140613030030.txt | http://documents.worldbank.org/curated/en/274901475100567729/pdf/000020051-20140613030030.pdf | Intense supervision of high quality can have a significant impact on the effectiveness of project implementation, especially with new borrowers. Structural changes to a system need buy-in at every level. Pilot projects must be designed with a view to scaling up from the outset.
P044524 | EMG ED REC | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Education | IDA | IPF | 1996 | 1999 | 1999 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/787141474850395106/text/000020051-20140521034210.txt | http://documents.worldbank.org/curated/en/787141474850395106/pdf/000020051-20140521034210.pdf | Emergency projects should be of low complexity, using a simple design as well as simplified procurement procedures, as long as there is sufficient local Bank-staff presence and/or international technical assistance to support the project implementation unit in the effective utilization of these simplified procedures.Emergency projects should be designed in a modular nature, allowing for flexibility in re-allocating resources during implementation as the emergency situation evolves.
P044531 | MEXICO: KNOWLEDGE AND INNOVATION | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/402821474567127103/text/000020051-20140615103850.txt | http://documents.worldbank.org/curated/en/402821474567127103/pdf/000020051-20140615103850.pdf | 1)To be effective, public programs that support technology development in the private sector need adequate gestation time and marketing to stimulate demand from the private sector. In countries where the private sector lacks appreciation of and experience in technological research and development issues, and lacks confidence in public sector programs, stimulation of demand can be a particularly long process. 2) The importance of well designed dissemination activities that actually reach its targeted beneficiaries cannot be underestimated. In this project, because dissemination was considered secondary and not pursued actively, adequate links with and demand from the private sector could not be generated, and compromized the potential impact of an important component. 3)To foster successful organizational change, project design needs to carefully assess the organizational culture of the institution to be reformed, and manage effectively the process of restructuring. Effective communications and engagement with staff are necessary to break down resistance from internal stakeholders. 4) Developing human resources and research capacity is a long term endeavor that requires concerted public efforts. Under this project, the Science and Technology Council successfully collaborated with line ministries and state / provincial governments to pool together a funding source to fund scholarships and research grants. 5) Project design needs to define clear performance indicators which are closely connected to project objectives and interventions. Further, performance indicators of policy interventions in the area of innovation are often hard to identify because a long lag time is required before results and positive spillovers can be fully observed.
P044584 | Djibouti Social Development and Public Works Project | Middle East and North Africa | Djibouti | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2008 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/145601474566967276/text/000020051-20140619062259.txt | http://documents.worldbank.org/curated/en/145601474566967276/pdf/000020051-20140619062259.pdf | The ICR identifies a number of useful lessons, particularly for post-conflict situations, including:there is a need to prepare projects with realistic targets and timetables, with associated risks flagged up front. Implementation in clear phases would facilitate results at a reasonable pace while consolidating support for the project. project preparation should be thorough but envisage a flexible project design to adapt to the development pace of the country, and in this case the evolution of the executing agency.Close support and intense supervision is required for projects in countries with low implementation capacity to ensure that problems are identified early on and that solutions are put in place and followed up.
P044585 | Djibouti School Access and Improvement Program | Middle East and North Africa | Djibouti | IDA |  | Human Development | Education | IDA | IPF | 2001 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/145471474627477789/text/000020051-20140613083641.txt | http://documents.worldbank.org/curated/en/145471474627477789/pdf/000020051-20140613083641.pdf | Basing the project on a government reform program, which was itself the outcome of a wide consultation process, helped ensure a success in implementation of the reforms.Substantial programs of school building can help increase enrolments, and do so without quality suffering.The ability of the Bank to finance recurrent costs under the new Bank policy on expenditure eligibility (approved for Djibouti in May 2005) provided the flexibility needed for program implementation when government was unable to provide its counterpart financing.The governmentâ€™s reform program contains long-term objectives which cannot be met in a single loan. The APL has thus far proven a good instrument for such circumstances, in which the Bank can make a long term commitment whilst retaining flexibility in program design.Good M&E design is not sufficient to ensure good M&E. Bank supervision needs to pay attention to this issue to ensure that data are being collected as planned.
P044597 | Brazilian Biodiversity Fund - FUNBIO (GEF) | Latin America and Caribbean | Brazil | IBRD |  | Sustainable Development | Agriculture and Food | GEF | IPF | 1996 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/720351475090714936/text/000020051-20140612153605.txt | http://documents.worldbank.org/curated/en/720351475090714936/pdf/000020051-20140612153605.pdf | A lesson identified in GEF's global portfolio of trust funds was that trust funds can promote decreases in government funding of protected areas by substituting trust fund financing for regular appropriations. This was not found to be the case in the FUNBIO project, which focused its investments on conservation projects outside the realm of traditional government responsibilities. The GEF trust fund evaluation also recommended that GEF support should be structured to provide incentives to encourage raising additional capital and developing innovative capitalization approaches.The project experience indicates the importance of facilitating biodiversity conservation activities by communities or groups of people who have a vital interest in conservation, either because their livelihoods depend directly on biological resources, or because their quality of life depends significantly on use and existence values of biodiversity.Biodiversity conservation projects need to develop a clear definition of goals and targets and indicators to measure outcomes.
P044601 | Second Rural Roads Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/628651475873181609/text/000020051-20140618052802.txt | http://documents.worldbank.org/curated/en/628651475873181609/pdf/000020051-20140618052802.pdf | Impact evaluations can be time-consuming and expensive, but can potentially put a project design and evaluation on a firm footing, by providing baseline and performance data.Simple improvements like NMT tracks can represent a major improvement for most rural communities and be sufficient to relieve bottlenecks to some income-generating activities. On the other hand, rural roads improvements alone may generally not be sufficient to alleviate poverty but may need to be combined with other types of interventions e.g wider rural infrastructure or broader development initiatives to enhance their impact.Womenâ€™s involvement in road project design and maintenance activities of rural roads can promote social outcomes that are commonly ignored by traditional road upgrading systems.Diverse staff in a roads agency â€“- economists and social scientists in addition to engineers -- strengthens institutional culture that goes beyond roads and draws attention to wider linkages to the economy.Strong coordination between financing partners can bring added value to project design and supervision and promote learning, besides making procurement and other procedures more efficient.
P044613 | ET- Road Sector Development Phase 2 | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2003 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/924421475076391816/text/000020051-20140624165227.txt | http://documents.worldbank.org/curated/en/924421475076391816/pdf/000020051-20140624165227.pdf | Training and capacity building need to be undertaken at both sectoral and national levels to be effective. Inability to retain key staff must be tackled in the context of separating ERA staff from Government remuneration structures if progress is to be made..Where there is an urban interface with rural road projects typical complexities such as integrating design standards, access, and financial responsibilities need to be resolved at national level but in coordination with all stakeholders.Road asset management requires needs-based maintenance programming. Especially when a road network is being improved and expanded, road maintenance needs to be fully incorporated into the maintenance planning cycle to enable good long-term strategic allocations of resources to preserve the assets.
P044614 | SCHOOLS REHABILITATION | Europe and Central Asia | Romania | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory |  |  | Satisfactory | Modest | http://documents.worldbank.org/curated/en/702501474503163740/text/000020051-20140612151512.txt | http://documents.worldbank.org/curated/en/702501474503163740/pdf/000020051-20140612151512.pdf | Stand-alone educational infrastructure projects make sense in countries that have a large number of buildings in condition of disrepair.- Differences in procurement methods used by donors and governments often create confusion and delays. Differences are compounded when multiple donors participate in a project, each expecting use of their own criteria. Procurement harmonization must be dealt with early on in project design.
P044614 | SCHOOLS REHABILITATION | Europe and Central Asia | Romania | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2004 | 2008 | PPAR | >=50 million & <100 million | Satisfactory |  |  | Satisfactory | Modest | http://documents.worldbank.org/curated/en/798211468092642406/text/418070PPAR0P0446140Box334049B01PUBLIC1.txt | http://documents.worldbank.org/curated/en/798211468092642406/pdf/418070PPAR0P0446140Box334049B01PUBLIC1.pdf | LESSONS 5.4 This assessmentprovides anumber of lessonsfor the education sector\. 0 Educationalinfrastructure i s an appropriate project objective when it i s coupled with a lendingprogram that i s focused on quality issues. Large stand-alone 18 Cronin 2007. http\.llwww.ipsnews.netinews.asp?idnews=38420 l 9CEB roughly estimatedstaff cost involved inthe project is as follows\. 72 staff* 400Euros average salary (charged) per month 12months(per year) 6 years (1998 -2003) = 2,073,600 Euros. * * operations focused on rehabilitating or constructing educational facilities may have a development effectiveness ifthe operations are strongly linked to a country's education quality improvement policy anddevelopment agenda (para 1.7 ); 0 Whenprojects involve large amounts of civilworks, it may be efficient to separatethe educational and the construction roles. A specialized entity with a mandate limitedto construction may carry out this role more efficiently than an agency that also has responsibilities for quality, policy and capacity building issues. Conversely, an implementing agency o f an education project without an infrastructure component would be able to focus its efforts and resources effectively on complex education content and quality intervention(para 2.3); Maintenance and the associated long-term expenditures are an important aspect to consider ineducational infrastructure. Contractor quality must be carefully monitoredto ensure that works are built to last and do not require extensive repairs soon. Warranty periods shouldbe carefully assessed(para. 3.7 ); and Many middle-income countries findthe Bank's advice and technical assistance highlyvaluable. The ability o fBank staffto help government counterparts to implementcomplex projects is an advantage over commercialbanks andother organizations. This is one reason for involving competent technical specialists as task managers or membersofproject teams (para. 4.7). To reduce the numbero f small schools it may be possible to transport students to larger schools intown. However, this policy would create tradeoffs interms of expenditures and environmental effects. These couldbe assessed infuture projects (para. 3.12).
P044651 | ER ROAD SECTOR ENGINEERING PROJECT | Eastern and Southern Africa | Eritrea | IDA |  | Infrastructure | Transport | IDA | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/350571474634259087/text/000020051-20140607170758.txt | http://documents.worldbank.org/curated/en/350571474634259087/pdf/000020051-20140607170758.pdf | The ICR identifies the following lessons of broad applicability:Policy reforms and capacity building interventions should be accompanied by investment operations to ensure continued leverage in long-term application of the reform agenda. Bank staff during supervision must be flexible enough to consider alternative options for achieving project objectives.International procurement should be limited to specific tasks/goods for which local capacity is not available. Project experience shows that procurement of proprietary spare parts and new management systems from domestic providers was more effective than what was obtained through the international market.The borrower identified the following important lesson - for countries with critical shortage of professional staff, Bank involvement in overseeing the hiring consultants and reviewing and commenting on consultants reports (e.g. feasibility studies, detailed design studies, etc.) in a timely manner is essential to avoid implementation delays.
P044674 | Emergency Reconstruction | Eastern and Southern Africa | Eritrea | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2001 | 2005 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/867761474631800094/text/000020051-20140615110946.txt | http://documents.worldbank.org/curated/en/867761474631800094/pdf/000020051-20140615110946.pdf | The ICR offers some useful lessons of wider applicability which this review endorses:Advance preparation. Because the PMU had done a thorough investigation soon after the cessation of war to determine critical bridge locations and some road improvement needs prior to Bank mission arrival, rapid identification of road sections for restoration of access to economic and social services was possible.Donor coordination. Multi-donor operations are complex to manage. It is important that responsibilities for donor coordination are well-established early in the program; that different emergency procurement and disbursement procedures are well harmonized; and that flexibility in these procedures is introduced, since in an emergency situation speed of implementation is as critical as accountability. An agreement to follow harmonized procedures (those presented through the manual of procurement procedures managed by the PMU) facilitated smooth donor coordination. Joint participation at appraisal was effective in getting early funding commitments.Cash assistance. Displaced families require some support as an incentive for returning to their villages. The primary need identified by resettling families is food security. While the goal is for communities to attain food security through agricultural production, it is crucial that returning families have access to adequate cash or food support as they await the harvest of their first crop.M&E. Emphasis needs to be given to ensuring the establishment of an effective participatory M&E system from project appraisal, including adequate beneficiary assessment and feedback. Monitoring and evaluation should be accompanied by an Economic Sector Work (ESW) program that includes household and community studies that address human and social capital issues as well as income generation needs and constraints.Balance between large and small. Smaller and more focused projects that involve fewer implementing agencies improve the management's chance of success with regard to implementation. At the same time, those projects should be sure to cover all inputs. For example, financing of crop production inputs need to be provided as a package. When only some inputs, such as seeds or fertilizers are provided, the benefit to beneficiaries (and satisfaction) is minimal or nonexistent.Flexibility. Emergency operations should be flexible and open to mid-course corrections responding to realities on the ground.
P044679 | Second Economic and Financial Management Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/168631475097674847/text/000020051-20140618055925.txt | http://documents.worldbank.org/curated/en/168631475097674847/pdf/000020051-20140618055925.pdf | IEG agrees with the four lessons outlined in the ICR. In addition, IEG notes that timely implementation of a mid-term review is likely to help salvage a seemingly poorly prepared project (or its components) from unsatisfactory performance. The changes suggested by the mid-term review with respect to the IFMS and the proposal for supplementary credit and extension of credit closure helped turn the project around.
P044695 | National Agricultural Advisory Services Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2001 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/254221474565856474/text/000020051-20140624162215.txt | http://documents.worldbank.org/curated/en/254221474565856474/pdf/000020051-20140624162215.pdf | The ICR provided five lessons, three were specific to the project and the following two general lessons are emphasized: In pluralistic technology systems, attention to the supply of services is as important as assurance of mechanisms to support demand and accountability. Significant investment is needed to train, certify, and monitor providers of services. The elements of a technology system both nationally and regionally, particularly educational institutions and research organizations, should be explicitly engaged for this purpose.Advisory services appear to have had a greater impact than subsidized provision of inputs under the program. The NAADS experience suggests that focusing on provision of advice and technology demonstrations achieved the most impressive gains. The returns when inputs became relatively more important in the program appear to be more mixed. However, according to the ICR such finding is provisional and warrants further investigation especially that the widespread distribution of subsidized fertilizer is viewed by many African governments as necessary for achieving rapid gains in productivity and incomes.
P044711 | MR-Iirrigated Agr Integr Dev APL (FY00) | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/542061475114310588/text/000020051-20140613090647.txt | http://documents.worldbank.org/curated/en/542061475114310588/pdf/000020051-20140613090647.pdf | Agricultural diversification in Mauritania is a viable growth and employment strategy and should be strongly promoted. Care should also be taken to ensure that the smaller farmers and women's groups equally benefit from such initiatives.An efficient M&E system should be designed early at project start and should be easily accessible and user friendly, to provide timely and reliable data for implementing agencies and project management. This is especially important when there are multiple implementing agencies across different sectors.Cooperative farmers are the ones most interested and in need of participating in irrigation schemes. Thus more attention should be paid to providing incentives such as access to credit, transparent subsidies and cofinancing, and the registration of their lands.
P044728 | Ozone Depleting Substances Phase-Out GEF Project | Europe and Central Asia | Ukraine | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/833691474633680322/text/000020051-20140613064157.txt | http://documents.worldbank.org/curated/en/833691474633680322/pdf/000020051-20140613064157.pdf | 1. Project implementation units (PIUs) need to be given executive powers sufficient to minimize implementation constraints. A PIU approach for project management was chosen, and the PIU was placed within the Ozone office of the responsible ministry. The PIU was, thus, within the organic structure of the implementing ministry for Ukraine's ODS program. This was sensible for a PIU approach, and is likely to better enable maintaining technical and administrative capacity for continuing the program after project closure. However, the ozone office and PIU were at a low level within the ministry. The ICR comments that this reduced the PIU's capacity to make decisions, to enforce standards and to get clearance for procurement and disbursement decisons. A higher level of executive authority would have been better. 2. Over-reliance on grant funding may reduce the commitment and sustainability of government and involved agencies: The project virtually fully funded government activities and a large part of the funding for the implementing enterprises. For government, the ICR comments that there is no indication that government financing of the PIU budget will continue. For the participating enterprises, the most successful at implementing their sub-projects were those that contributed significant and timely counterpart funds. Those enterprises that relied more on government funding, and which were late in providing their funds, performed weakly. Project start-up could have been conditional on a minimum first financial allocation by government. A condition for enterprise participation might also have been up-front funding.3. Project implementation periods need to be realistic: The original project closure date was only 2 1/2 years after Board approval. In the event, after extensions accumulating to 4 years, project implementation was 6 1/2 years. In part, the chosen short duration period was to achieve reduction of ODS at a pace to remain in line with the Montreal ODS protocol. However, duration objectives that are clearly not possible might have been better explained up-front to the global ODS program.
P044729 | Ozone-Depleting Substances Phase-Out GEF Project | Europe and Central Asia | Belarus | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/900511475100120882/text/000020051-20140602112447.txt | http://documents.worldbank.org/curated/en/900511475100120882/pdf/000020051-20140602112447.pdf | The ICR lists many lessons. Among them:1. A good monitoring system and continuous dialogue can help ensure that the financial viability of enterprises is maintained.2. Combining investments in phase-out with legislative controls to discourage the use of ODS was effective.3. The clear, detailed procurement plan of this project worked better than less clear or more flexible plans in other projects in the country.4. Information transfer between Belarus and the Ukraine and Russia projects and Central European projects helped build a more cohesive regional program.5. Training resident mission staff and having them spend time with the headquarters project team helped build long-term capacity in the resident mission and assisted in supervision.
P044748 | Social Infrastructure Retrofitting Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2011 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/982361474503920261/text/000020051-20140624212253.txt | http://documents.worldbank.org/curated/en/982361474503920261/pdf/000020051-20140624212253.pdf | The following key lessons that can be learned from the project's preparation and implementation are taken from the ICR with adaptation:When initiating or resuming lending to client countries where there has been no prior Bank lending or where operations have been suspended temporarily, it is important to focus on the sector(s) for which the Government has consistently shown adequate commitment, and select high priority projects with large and visible economic and social benefits, especially if the macroeconomic and institutional environment continues to be uncertain.Baseline data at entry and end-of-project outcome indicators need to be quantified prior to implementation in order to ensure that project performance is measurable during supervision and attributable to the project at completion.To facilitate least-cost procurement in cases where contracts may be too small and too geographically dispersed to attract international bidders, the procurement approach needs to include: (i) the provision of workshops and information to local bidders; (ii) revision of the conditions and terms of the bidding documents to elicit a sufficient number of bids; and (iii) meeting(s) between the Bank team, the PMU, and potential local bidders to inform them about the Bankâ€™s procurement procedures and determine the reasons for their lack of interest or failure to bid.To avoid costly change orders and contract amendments during implementation, it is important to ensure the accuracy of basic data for technical specifications, by following these steps: (i) require the beneficiary institution to sign off on the data; (ii) have the design and supervision consultant and the project implementing agency visit the sites before finalization of the technical specifications to verify the basic data; and (iii) request the contractors to visit the sites before the start of works.To minimize investment and operation and maintenance costs, if is important to review and revise the design practices in the country with a view to reducing the capacity requirements and the potential over-sizing of boiler specifications.
P044789 | Private Sector Infrastructure Development | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2007 | 2008 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/502551474664773923/text/000146597-20140618141842.txt | http://documents.worldbank.org/curated/en/502551474664773923/pdf/000146597-20140618141842.pdf | PSIDPPrior to encouraging private infrastructure development, starting from a low base, a coherent enabling policy and regulatory environment needs to be in place.In creating new institutions, due consideration must be given to the interplay with the political economy of old institutional arrangements and incentive structures.Government commitment at the highest level is essential to ensure the transparent conduct of policy and implementation of transactions for private participation in infrastructure development.PFRAPEmergency recovery operations should take into consideration local implementation capacity and the fact that such capacity might be hindered in the aftermath of a disaster.In a situation that is prone to periodic natural disasters, a long-term approach should be taken such as creating a dedicated disaster management fund with a clear mandate, processes (including procurement), staff resources, and appropriate institutional linkages for coordination.While there may be a need to simplify and speed up procedures during an emergency response, basic procurement procedures and transparency should be maintained.
P044796 | Structural Adjustment Credit 2 (SAC 2) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2000 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/618091474943243128/text/000020051-20140522105548.txt | http://documents.worldbank.org/curated/en/618091474943243128/pdf/000020051-20140522105548.pdf | (1) Continuity of SAC teams (both government and Bank) is highly advantageous. (2) Supervision teams comprised of the core country team ensure that SAC supported policies will be directed toward the top sectoral priorities. (3) The pressure to fill financing gaps can affect policy considerations for tranche release, and the result can be weak compliance with the reform program if tranche release is premature, thereby raising questions about sustainability.
P044796 | Structural Adjustment Credit 2 (SAC 2) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2003 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/945021511185175484/text/multi0page.txt | http://documents.worldbank.org/curated/en/945021511185175484/pdf/multi0page.pdf | 8. Key Lessons Learned\n8.1 When adjustment projects are synergistic with sectoral investment projects,\neffectiveness can be enhanced\. During the course of the 3 SAC projects, investment projects\nlinked to the adjustment program were undertaken in the education, irrigation, and power\nsectors, and considerable synergy with the adjustment credits was achieved. The financial\ninducement of the SACs provided an incentive for the Ministry of Finance to become an\nadvocate for sectoral reforms, and cooperation between ministries was enhanced. However, the\nEnterprise Development Project was not designed as complementary to the SACs, and thus did\nnot achieve synergy.\n8.2 For an adjustment program focused on private sector-led growth, key constraints\nto private sector development must be confronted\. While considerable emphasis was placed\non privatization and financial sector development, insufficient weight was accorded to critical\ncomplimentary aspects of private sector development, including\. a business environment\nconducive to private enterprise and the entry of new firms; effective enterprise restructuring and\ngovernance; building adequate government capacity to support a market economy; and effective\nprocedures for bankruptcy and liquidation.\n8.3 As a reform program advances, progress may become more difficult\. First\ngeneration reforms, such as trade and price liberalization and the promotion of open markets,\ndid not for the most part pose a major challenge to vested interests. However, further progress\ninvolved fundamental changes in political, judicial, and social institutions, and in many cases\nchallenged powerful interests. Bank staff found that overcoming these important opposing\nconstituencies was much more difficult than earlier reforms, and more difficult than they\nexpected.\n8.4 It is unrealistic to assume that if the fundamentals are in place, an automatic\nsupply response will take place\. A key assumption of the Bank\'s reform program was that, if\nthe fundamentals (i.e., first generation reforms) were in place, a supply response (i.e., broad-\nbased growth stimulated by the private sector) would be forthcoming. The Bank vastly\noverestimated the ability of Armenian workers, entrepreneurs, and institutions to overcome the\nlegacy of decades of Communism and the power of indigenous vested interests. Also\nunderestimated was the cost of the breakup of the Soviet Union to Armenia\'s productive assets.\n8.5 Legal reform should take adequate account of enforcement capacity\. Important\nprogress was achieved by the passage of new legislation, and an impressive framework was put\ninto place. However, the adjustment program placed insufficient emphasis on strengthening the\njudiciary and the actual role the legal system could play in furthering an improved business\nclimate.\n8.6 Continuity and dedication of the country team are key to program effectiveness\.\nDuring the six years covered by this PPAR, there was substantial continuity of the task team\.\ntwo Country Directors, three country economists, no more than two TMs for any of the\nadjustment operations. In addition, project supervision and coordination of the country team\n\n\n31\nwith sectoral specialists was very successful. This contributed significantly to Bank\neffectiveness.\n8.7 Turnover among policy officials hindered reform progress\. During the six years\ncovered by this PPAR, there were seven Prime Ministers and four Ministers of Finance. There\nwas also substantial turnover among other officials concerned with implementing the reform\nprogram. For an official contemplating a brief tenure, it is more difficult to appreciate the\nbenefits of reform, and so this turnover made reform progress considerably more difficult.\n\n\n\n33\nREFERENCES\nEBRD, Transition Report 2000.\nFIAS, Armenia\. Administrative Barriers to Investment, May 2000.\nIMF, Armenia Financial System Stability Assessment, March 2001.\nIMF, Recent Economic Developments and Selected Issues, December 2000.\nIMF, Recent Economic Developments and Selected Issues, May 2001.\nNorwegian Refugee Council, www.idpproject.org.\nOxford Analytica, Armenia Financial Sector, July 24, 2000.\nRamachandran, S. Evaluating Adjustment Lending\. Some Suggestions, Informal Paper, August 2001\nUSAID, Investigation of Factors Inhibiting FDI in Armenia, August 1999.\nWorld Bank, Between State and Market\. Mass Privatization in Transition Economies, September 1997\nWorld Bank, Seize the State, Seize the Day\. State Capture, Corruption, and Influence in Transition;\nAnticorruption in Transition, a Contribution to the Policy Debate, (2000).\nWorld Bank, Armenia\. Restructuring to Sustain Universal General Education, Technical Note, 2001.\nWorld Bank, ECSPE, Armenia/Georgia Country Unit, Growth Challenges and Government Policies,\n2001.\nWorld Bank, Armenia/Georgia Country Unit, Public Administration in Transition, September 1996.\nWorld Bank, Armenia/Georgia Country Unit, Public Expenditures in Armenia, November 1997.\nWorld Bank, Armenia/Georgia Country Unit, Armenia CAS, 2001.\nWorld Bank, ECA, Transition After a Decade, November 2000.\nWorld Bank and IMF (European II Department), Poverty Reduction, Growth, and Debt\nSustainability in Low-Income CIS Countries, February, 2002.\nWorld Bank, ECSPF, Armenia Targeted Financial Sector Review, June 2000.\nWorld Bank, LEGEC, Analysis of Public Awareness on Judicial Reforms, December, 1999- January\n2000.\nWorld Bank, OED, IDA Review of Private Sector Development, March 2001.
P044797 | SAC 2 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2000 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/348321475085264639/text/000020051-20140522103444.txt | http://documents.worldbank.org/curated/en/348321475085264639/pdf/000020051-20140522103444.pdf | It is important to have a high-level champion to see implementation through.
P044797 | SAC 2 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2004 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/746081468751804137/text/26439.txt | http://documents.worldbank.org/curated/en/746081468751804137/pdf/26439.pdf | 8. Lessons Learned 8.1 Georgia's weak governance severely limitsthe country's ability to create conditions conducive to economic development and the effective use of development assistance-The problems that limit growth inGeorgia transcend economic policy. The political and geographic fragmentation o f the country poses severe challenges to the executive. The inability o f the executive to overcome obstacles posed by the parliament and regional officials, establish a minimumlevel o f the rule o f law, and overcome a pervasive culture o f corruption severely limits the country's ability to establish sustained, broad-based growth with significant job creation. 8.2 For a country such as Georgia, which experienced economic collapse, it is incumbent that the Bank give high priority to prompt measures that can directly mitigate conditions for the poorest. 53This section is based on interviews with energy sector firms, govemment officials, and Bank staff. 8.3 Turnover on the country team limited program effectiveness-From 1994to 1998,there was one Country Economist for Georgia. Officials interviewed cited the benefits that they believe this continuitybrought. However, since 1998, there have been3 Country Economists, and an interval o f around6 months duringwhich the position was unfilled. While there werejust two Country Directors duringthe periodcoveredby this PPAR, and good continuity on the rest o fthe Country Team, the tumover diminished the continuity o f the program, andprobablyconstrained the ESW that was performed. 8.4 A more robust and timely ESW programwould have been beneficial to the design o f the reformprogram-The Country's first poverty studywas completed in 1999; the design o f the reform program would have benefited from earlier work inthis area. A study o fthe sources o fgrowth might also have beenbeneficialbyidentifyingsectors from which growth might be expected to flow, and then considering means by which to facilitate such growth. A Public Expenditure Review-a veryuseful analytical tool for a country with Georgia's perennially weak fiscal situation-was completed in 1996, and then not again until 2002. Fiduciary reports (CFAAs and CPARs) were completed infrequently. The rapid tumover inCountry Economists was probably part o fthe reason for the weak ESW. 8.5 Turnover among policy officials hinderedreform progress-During the seven years coveredby this PPAR, there were seven Prime Ministers and four Ministers of Finance. There was also substantial tumover among other officials concerned with implementingthe reform program. For an official contemplating a brieftenure, it i s more difficult to appreciate the benefits o f reform, and so this tumover made reform progress considerably more difficult.
P044800 | Forests Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2003 | 2009 | 2010 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/644181475093461065/text/000146597-20140619160027.txt | http://documents.worldbank.org/curated/en/644181475093461065/pdf/000146597-20140619160027.pdf | The ICR offers two main lessons that this ICR Review partly concurs with but are presented here with amended language.1. Projects having a period of significant policy change thrust upon them should be budgeted for enhanced supervision to support project design adjustment or reassessment of relevance. This may need to include outside experts as was done in this case. 2. Strong central government leadership offers opportunity for reform but to be sustained this also requires strong political buy in at all levels down to community level and this must be fostered at an early stage of project design.
P044803 | PRIMARY EDUCATION FOR DISADVANTAGED CHILDREN PROJECT | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2003 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/990261475076439509/text/000020051-20140625055832.txt | http://documents.worldbank.org/curated/en/990261475076439509/pdf/000020051-20140625055832.pdf | ICR Review lesson: The M accurate baseline data; consistent definitions of terms from the start to the end of the project; and M&E design consistent with the capacity of the Borrower.ICR lesson: The FSQL was an effective tool in providing a "ladder" to national, higher, standards by setting realistic and attainable targets for schools serving disadvantaged populations.
P044804 | Rural Development Project | Europe and Central Asia | Latvia |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/679521474652889931/text/000020051-20140607161610.txt | http://documents.worldbank.org/curated/en/679521474652889931/pdf/000020051-20140607161610.pdf | (a) Although a truism, the value of property ownership (hence land titling especially) and a transparent property market to facilitate small-scale collaterized lending was well demonstrated; and (b) Rural financial operations can be jump-started with subsidies to attract both borrowers and banks to participate, but this may risk undermining and constraining the growth of sustainable commercial lending in the longer term.
P044804 | Rural Development Project | Europe and Central Asia | Latvia |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2002 | 2005 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/853391468772477445/text/29516.txt | http://documents.worldbank.org/curated/en/853391468772477445/pdf/29516.pdf | 7. Lessons 7.1 Experience with these two projects confirms a number o f OED lessons\. (1) Thesuccess of a line of creditproject is dependentnot only upon its design but also on the institutional environment and human resource capacity of the country. Credit markets are intertemporal markets and therefore institutionally intensive. They require well-defined property rights, enforceable rules (such as foreclosure rules), and adequate humanresource capacity to function well. A government must allow these institutional rules to operate unhindered for a credit market to operate inan efficient manner and for borrowers to understand that the loans must be repaid. The design o f line o f credit projects needs to take into account the institutional environment and the humanresource capacity that exists ineach country, and where these are not adequate, to invest resources intheir improvement. (2) It is important topay close attention to the incentivestructuresthat are built into financial instruments like lines of credit, since these can represent the major difference between success andfailure. Boththe ADP andRDP took great care inbuildingthe appropriate incentive structures into the sub-loans. Careful and thoughtful program design minimizedmoral hazard problems andresulted invery highrates o f repayment. The special credit line only paid a subsidy to borrowers (small-scale rural entrepreneurs) once the loanwas fully repaid. This high-powered incentive had the desired effect on the behavior o f the borrowers. (3) When a government creates a newfinancial instrument such aspublicly provided credit to enhance the efficient functioning ofprivate markets, it is important to have an exit strategy to move this instrument to theprivatesector. Inthe case o f Latvia, the government createdthe publicly owned Agricultural Finance Corporation under the ADP and mergedthis with the publicly owned Mortgage and Land Bank under the RDP. While privatizing the MLB was an objective o f the RDP, this did not occur inpart because there was not a detailed plan for doing so. The government decided not to privatize the MLB because the MLBwas performingwell under its current ownership structure, because the government hadhigher priorities, and because the government might want to use the MLBto subsidize credit inother credit markets (such as housing) inthe future.
P044809 | Legal and Judicial Reforms Project | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/503091474506252543/text/000020051-20140618082728.txt | http://documents.worldbank.org/curated/en/503091474506252543/pdf/000020051-20140618082728.pdf | Legal and judicial reform is a lengthy process and it is important to ensure that Bank support is nestled in the client's long-term reform strategy. The project must have clearly defined, specific, modest and achievable objectives along with monitorable indicators, linked to the client's long term goals.Legal and judicial reform is highly complex and has significant country-specific attributes. It is important for Bank Management to consult experienced practitioners, familiar with country systems and processes, in designing and supporting the implementation of such legal and judicial operations.
P044810 | Legal and Judicial Capacity Building Project | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2001 | 2009 | 2011 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/386941475081893970/text/000020051-20140624155840.txt | http://documents.worldbank.org/curated/en/386941475081893970/pdf/000020051-20140624155840.pdf | 1. Relevance of judicial independence. The Executive played, and still plays, a key role in running the judiciary. Judicial reform needs to be guided by an independent judiciary, extending to budget, staffing, and establishing the modalities of operations. While the project focussed on business practices and access, it was not possible to improve these while the Executive played such a strong role in running the Judiciary. 2. Functional Institutional arrangements. Minimal local capacity is needed to implement the project. The Supreme Court was to have played the key role in managing and supervising consultants from IRIS who in turn were to have been key to project implementation. When the Bank realized that the Supreme Court did not have this capacity, it quickly provided funds for Reform Advisory Consultants (RAC) consultants to manage the IRIS contract, but when relations between RAC and IRIS deteriorated, the government played only a minor role in trying to reach a solution, with much time lost. 3. Monitoring and Evaluation. Even a well-devised system of performance indicators loses its value if it is not an ongoing operational tool into which is fed timely updates and from which are drawn lessons for mid-course corrections. 4. Restructuring -- When it became clear at the Mid-Term Review that the project would not achieve its objectives, the project should have been restructured.
P044811 | Financial Institutions Development | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/676781474591848167/text/000020051-20140615114407.txt | http://documents.worldbank.org/curated/en/676781474591848167/pdf/000020051-20140615114407.pdf | A training needs assessment during project design or early in implementation permits efficient structuring of training events and better coordination among participating government agencies.For projects with innovative components, understanding of and buy-in to the project can be improved through clear outreach programs prepared and budgeted for during project design.The success rate of reform measures to be taken during project implementation can be enhanced by a careful assessment of their champions and opponents. Complex and innovative projects need to be carefully phased, ensuring government commitment before moving to the next phase.The liability assumed by government authorities for projects under their supervision needs to be reasonable, balancing fiduciary duty with the flexibility needed to take business risks in good faith.
P044824 | Social Fund Project | Eastern and Southern Africa | Comoros | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/932431474505824991/text/000020051-20140613031208.txt | http://documents.worldbank.org/curated/en/932431474505824991/pdf/000020051-20140613031208.pdf | This review draws two lessons, also drawn by the ICR.Implementation of micro-credit activities should be kept separate from community infrastructure or service/capacity building subprojects. Successful management of micro-credit schemes requires specific skills, special implementation, and governance arrangements. These are distinct from those needed in a social fund aiming at rehabilitating or constructing small local infrastructure and providing community services.Staying engaged is important in post conflict situations. The Bank did not totally withdraw even when operations were suspended. The Bank engaged in a continuous dialogue with the authorities and with FADC in particular. This allowed the Bank to restart project operations swiftly after the suspension.
P044829 | Transport Project | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Transport | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/704641475085764453/text/000020051-20140613064250.txt | http://documents.worldbank.org/curated/en/704641475085764453/pdf/000020051-20140613064250.pdf | Political commitment and ownership are essential for the successful implementation of a sector reform program and especially one involving privatization. This is particularly true when applying private sector management in countries in which the private sector did not formerly exist. The Bank in these cases should carefully assess the conviction of the government to implement such a new paradigm and its willingness to assume the sometimes heavy political cost that this implies.To improve sector planning, the Bank should not only involve sector authorities but also relevant stakeholders outside the sector including civil society and the Ministry of Finance and/or Planning.
P044830 | Oil Institution Building TA Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/164551474649208569/text/000020051-20140604043623.txt | http://documents.worldbank.org/curated/en/164551474649208569/pdf/000020051-20140604043623.pdf | The project reinforces the following elements as crucial to a succesful operation: (i) minimal changes in the composition of the Bank's task team; (ii) continuous and effective support from management, especially in a situation fraught with political sensitivities; (iii) intensive supervision supplemented by regular communication; and (iv) fostering a high level of coordination and trust between the Bank team and the counterpart in the borrowing country.
P044832 | KIEV DISTRICT HEAT | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/402501474508315152/text/000020051-20140619062120.txt | http://documents.worldbank.org/curated/en/402501474508315152/pdf/000020051-20140619062120.pdf | 1. There were two main, and closely interlinked, reasons why this project failed to meet its development objectives â€“ lack of counterpart funding and serious underestimation of installation costs. Additional financing for the latter could not be considered because of the Borrowerâ€™s inability to guarantee its share. The first lesson, therefore, is the importance of ensuring upfront that appropriate mechanisms are in place to ensure the financial viability of the implementing agency. If tariffs are not adjusted for political reasons, it is insufficient to rely on compensation from the municipal government. 2. An independent regulatory agency should be established to determine the appropriate level of tariffs. This should not be left to a political body such as the municipality.3. Care should be taken during preparation to estimate carefully and accurately installation costs for equipment such as boilers and pipes. This is all the more important if such costs are expected to be the Borrowerâ€™s responsibility. 4. Sufficient account should be taken of the implementing agencyâ€™s lack of experience in dealing with international lenders like the Bank and with managing projects of this size. A phased approach consisting of a series of smaller, simpler operations should be considered.
P044840 | SOCIAL INVESTMENT FUND | Europe and Central Asia | Moldova | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/746761475073362085/text/000020051-20140613051343.txt | http://documents.worldbank.org/curated/en/746761475073362085/pdf/000020051-20140613051343.pdf | Special attention and creative methodologies are needed to effectively monitor progress on non-physical objectives such as empowering rural communities. If targeting the poor is an objective, special measures will be needed to ensure that the poor are actually reached -- broadly targeting communities may miss the poor.
P044851 | Export Development Project | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/136021474512950639/text/000020051-20140613040752.txt | http://documents.worldbank.org/curated/en/136021474512950639/pdf/000020051-20140613040752.pdf | (1) A turnaround in banking management was possible without outsourcing or privatization. (2) A key question is whether the benefit of strengthening a state-owned bank, with its commercial advantages, outweighs the cost of lessening banking competition. (3) Another question is whether the capacity building provided by this project for the EXIM bank is sufficient to overcome the risk of banking abuses (insider lending, directed loans, etc.) posed by weak corporate governance.
P044852 | Enterprise Incubator LIL | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2007 | 2008 | ICRR | Less than 10 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/353201475099499480/text/000020051-20140618061711.txt | http://documents.worldbank.org/curated/en/353201475099499480/pdf/000020051-20140618061711.pdf | The main lessons largely derived from the ICR are:A LIL is probably not the best instrument for launching enterprise incubators since there has already been considerable global experience with them.In defining a monitoring framework it is important to clarify the hierarchy and interrelationships of the final outcome indicators, and intermediate indicators. There should also be a clear link between the monitoring indicators and the learning hypothesis to be tested and not just the general overall objectives.Where an incubator project includes a building to be purchased or rented, there must be a clear arrangement in place to ensure this will be available in a timely manner.
P044876 | Female Secondary School Assistance Project-II | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2002 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/624431475098238090/text/000020051-20140619105339.txt | http://documents.worldbank.org/curated/en/624431475098238090/pdf/000020051-20140619105339.pdf | The lessons in the ICR were used to inform the follow-on project (in fact, lessons in the ICR and exactly the same as those in the PAD of the follow-on project). The lessons below complements some of the lessons in the ICR:The project confirmed a lesson from the experience with conditional cash transfers, namely that while demand-side initiatives may stimulate enrollment, the development impact depends on the quality of the education being supplied.On the demand-side complementary efforts are needed to facilitate uptake among the poor such as awareness raising and community mobilization efforts to inform poor households of the existence of incentive programs, the eligibility criteria and practical advice on how to enroll.Without information on the incidence of stipends access among the poor cannot be assessed, and the impact of outreach activities cannot be fully evaluated.
P044912 | URBAN LAND MGMT | Western and Central Africa | Cote d'Ivoire | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2002 | 2002 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/206521474596814614/text/000020051-20140604055509.txt | http://documents.worldbank.org/curated/en/206521474596814614/pdf/000020051-20140604055509.pdf | The Bank needs to ensure that there is full government commitment on land management reform at both the policy and line management levels. A step-by-step approach beginning with basic building blocks is better than proceeding with a broad based agenda. A simple program focusing on key policy and institutional improvements is more effective than a complex project which tries to do a little of everything.When new agencies are being established, more supervision missions are necessary in the beginning stages.The design of projects should carefully consider the institutional capacity that exists and build on that first, before attempting complicated land management reforms.
P044942 | Pilot Water Supply Project | Europe and Central Asia | Uzbekistan | Blend |  | Sustainable Development | Water | IBRD | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million |  | Unsatisfactory |  |  |  | http://documents.worldbank.org/curated/en/378211474555127594/text/000020051-20140604052015.txt | http://documents.worldbank.org/curated/en/378211474555127594/pdf/000020051-20140604052015.pdf | The PCN suggests that a Project Preparation Facility or other instrument with lower transaction costs for the Bank, would have been equally effective in facilitating the preparation of the full scale project.
P044973 | LA-SOUTHERN PROVINCE RE | East Asia and Pacific | Lao People's Democratic Republic | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/499781474574883294/text/000020051-20140613053246.txt | http://documents.worldbank.org/curated/en/499781474574883294/pdf/000020051-20140613053246.pdf | The OED review considers the following as important lessons:Lower-income households are unable to benefit as much from grid and off-grid rural electrification as better-off families do. As the results of the socio-economic survey conducted for this project show, while electricity use can significantly reduce the monthly energy expense of low- (and other) income households, the poor make little use of electrification because of a lack of disposable income. This may be the case even where costly, participatory approaches are adopted for off-grid electrification. Electrification may therefore contribute to increasing the gap between the wealthy and the poor. While covenants may be seen as essential for a project, particularly where risks regarding borrower performance exist, there is the possibility that they may not serve during implementation as effective tools in getting the borrower to carry out the necessary steps. Quality risk assessment during project design is therefore critical, and based on it the required actions to minimize the risks and ensure that all the necessary conditions for project success exist should be taken during appraisal.Where resettlement is involved, the Bank must ensure that all implementing parties, particularly those at lower levels of government which may be directly responsible for implementing Resettlement Action Plans, are knowledgeable on the RAP and its requirements, and agree to comply with them.
P044973 | LA-SOUTHERN PROVINCE RE | East Asia and Pacific | Lao People's Democratic Republic | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2005 | 2008 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/984111468047362876/text/424130PPAR0P0449730Box327369B01public1.txt | http://documents.worldbank.org/curated/en/984111468047362876/pdf/424130PPAR0P0449730Box327369B01public1.pdf | Lessons learned 5.8 Consumers are willing to pay tariffs at cost recovery levels. The willingness to pay analysis shows that consumers are willing to pay for electricity at levels exceeding supply costs. Lao PDR has been able to implement sizeable tariff increases in a short space of time with no adverse social impact or notable demand reductions (indeed it can be argued that any reduction in usage by already connected customers helps extend supply to new locations). Tariffs have already reached historical highs, and will reach full cost recovery for short run marginal cost (O&M) plus a return on capital by 2011 ï¿½ the WTP calculations show that these levels will be acceptable to consumers. 5.9 But poorer households remain unconnected. Even after the grid has been in a village for more than 10 years some 20 percent of households remain unconnected. Smart connection subsidies for late connectors would help achieve government's 90 percent coverage target. 5.10 Explicit attention needs to be paid to technical efficiency. Technical problems of system losses and outages reduce financial performance and undermine project benefits. Explicit components are needed to tackle these issues. 5.11 Off-grid components promote social equity in electrification coverage... but are not necessarily the most cost effective strategy. The off-grid component has helped reach remote communities which would not otherwise have got electricity for a decade or more. However, the rate of return to these investments is lower than that to grid extension, or of subsidizing connections for late connectors, and it not proven that the beneficiaries from off-grid programs are poorer than those benefiting from grid extension. 5.12 In countries where the private sector is relatively undeveloped substantial support may be required to provide off-grid services in poor areas. At the same time subsidies should not crowd out purely commercial actors. A sensible balance would direct project supported companies to the more remote areas unlikely to be attractive to purely commercial firms, but the subsidy scheme needs to ensure that such activities are sufficiently attractive.
P044974 | SAC III | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2000 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/205191474493198249/text/000020051-20140528123153.txt | http://documents.worldbank.org/curated/en/205191474493198249/pdf/000020051-20140528123153.pdf | In order to guide implementation, an effective privatization program requires specific goals clearly outlining the anticipated status of individual enterprisesThe design of the overall reform program, consisting of a series of single-tranche operations with disbursement against conditions met prior to effectiveness, was innovative and effectiveGovernment commitment was key to reform progressThe economic unit in charge of reform was located in the Presidency during implementation, which gave it the high visibility needed to effectuate reforms
P044975 | SAC II | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1997 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/847091475088109483/text/000020051-20140528123452.txt | http://documents.worldbank.org/curated/en/847091475088109483/pdf/000020051-20140528123452.pdf | In order to guide implementation, an effective privatization program requires specific goals clearly outlining the anticipated status of individual enterprisesThe design of the overall reform program, consisting of a series of single-tranche operations with disbursement against conditions met prior to effectiveness, was innovative and effectiveGovernment commitment was key to reform progressThe economic unit in charge of reform was located in the Presidency during implementation, which gave it the high visibility needed to effectuate reforms
P045029 | PILOT RDC | Eastern and Southern Africa | Zimbabwe | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2000 | 2001 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/702451474506085406/text/000020051-20140529161350.txt | http://documents.worldbank.org/curated/en/702451474506085406/pdf/000020051-20140529161350.pdf | Lessons noted by OED include:Even well-designed projects can flounder in the face of macro-economic crisis, civil disturbance and a breakdown of governance.The demand by local government for loans through lines of credit will be undermined if these governments have access to grant funding.Local development project design should ensure that institutional support interventions for local government go hand-in-hand with physical investments in infrastructure.Project cofinancing should be combined with an active partnership among cofinancers lest a project loses its unity becoming dismembered into unrelated parts.However difficult the circumstances on the ground, it is important for project evaluation to focus upon concrete evidence--recognizing candidly when data are not available--of delivery of project outputs and their links to the achievement of a project's intended development outcome. From the ICR, key lessons include:In the short run, local governments in some areas are willing and able to respond positively to performance incentives despite little accountability.State lands in potential growth poles of Zimbabwe are a major underutilized local resource.
P045029 | PILOT RDC | Eastern and Southern Africa | Zimbabwe | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2000 | 2002 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/491871468762378038/text/multi0page.txt | http://documents.worldbank.org/curated/en/491871468762378038/pdf/multi0page.pdf | LESSONS 5.4 A one-size-fits-all approach to urban project design should give way to a design firmly anchored to the particular conditions of a borrower's cities and urban development. In Zimbabwe, these included an unusually high level of urban services, strong city management and segregated spatial structure and housing market. Zimbabwe's cities need less help in overcoming deficits than those of other developing countries do, according to the Bank's standard urban prescription. In Zimbabwe, there is a need to address the spatial distortions of segregation the cities inherited. Support for housing finance in Zimbabwe could also have paid more attention to the historic and financial constraints that prevented building societies lending to the poor. 5.5 Project objective statements should clearly signal intended development results. These can guide implementing agencies-the RDCs in Zimbabwe, for instance-in their choice of relevant investments, as well as indicate the process improvements-such as better accounting-they are expected to make. Without a clear focus on their roles in rural development, some inexperienced RDCs made investments that did not provide essential services for their communities. One way of providing the necessary guidance is for a project to provide a menu of eligible options, from which implementing agencies can choose.
P045030 | FRDP II | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2000 | 2001 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/126261474558181447/text/000020051-20140529162232.txt | http://documents.worldbank.org/curated/en/126261474558181447/pdf/000020051-20140529162232.pdf | (i) Fiscal restructuring and civil service reform must begin with a fundamental reconsideration of the role of the government undertaken at the political level; (ii) the reform agenda under FRDP I and II has been too broad and the scope and sequencing of reforms should be reconsidered; ; (iii) protecting pro-poor fiscal outlays may prevent further deterioration of services, but cannot address deep-seated problems of equity, efficiency, and quality of services; (iv) the Bank must closely assess whether its budgetary support that helps deter short-term crises also does not help postpone critical longer-reforms that underpin the short-term crises.
P045030 | FRDP II | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2000 | 2007 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/406021468271544252/text/37810.txt | http://documents.worldbank.org/curated/en/406021468271544252/pdf/37810.pdf | Lessons Incentives within the Bank can motivate unwise lending\. The desire to transfer resources and establishHIPC eligibility were important motivations to the initiationof FRDP III.Despite the poor macroeconomic climate andlack o f reformprogress under the previous credits, FRDP111was enlarged by US$20million (over the originally-conceived amount) andhastily structuredas a one-tranche loanmainly to facilitate establishment o fHIPC eligibility. Further, theoperationwas over-dimensioned for the scope ofitspolicypackage. 0 The region's macroeconomic assessments need to have greater realism and consistency\. The analyses o f the macroeconomic environment inthe FRDP 11 andIIIproject documents are unbalanced andlack realism andconsistency. The existence of a Fundprogram should not be a suficient conditionfor the Bank to initiate adjustment lending. Policy-based lending inan unstable macroeconomic environment is unwise\. The Malawian experience ofturbulent macroeconomic performance fiom 1994to 1998, with on-again, off-again Fundprograms shouldhave alerted the Bank that M e r adjustment lending after FRDPI\.(1) was not warranted; and (2) was unlikely to have a significant impact due to the negative effect ofmacroeconomic turbulence on the efficacy of structuralreform. Inpromoting reform, the Bank needsto take account of the incentives that a program creates\. MTEF, IFMIS,andcivil service reformwere unsuccessful in largemeasure because GOMofficials-at all levels-did not perceive that it was intheir interest to implement these reforms. While anofficialbudgetwas prepared, itwas routinely circumvented andexceededbypolitical intervention. Tenyears o feffort on MTEFandUS$2.3 milliono fexpenditure on IFMIS have produced virtually no results. 0 The Bank should structure lending to Malawiwith more earmarked, targeted aid, and tighter fiduciary controls\. To assure that funds are used in the manner intended, budgetary support should be subject to tighter fiduciary controls. Also, greater use shouldbe made o f earmarked assistance, including that which is delivered directly fiom suppliers to users, such as the successful CIDA textbook program (box 4.2).
P045031 | Community Action Project | Eastern and Southern Africa | Zimbabwe | Blend |  | Human Development | Social Protection & Jobs | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/524371474569400887/text/000020051-20140612141859.txt | http://documents.worldbank.org/curated/en/524371474569400887/pdf/000020051-20140612141859.pdf | Three lessons:(i) The building of adequate community participation requires time, resources and explicit attention to incentives for the stakeholders. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured. (ii) In a project with community empowerment as an objective, the performance measurement system should be set-up to measure both quantitative and qualitative progress. (iii) The project experience illustrates the need for clearer guidelines to operational staff as to when they should draft and process an ICR as opposed to a Project Completion Note (PCN). In the case of a project that gets cancelled after a brief implementation period OP 13.55 only notes that "An ICR is not prepared for a loan that fails to become effective or is cancelled before significant implementation." It is not clear what exactly constitutes 'significant' implementation.
P045049 | ANDHRA PRADESH DISTRICT POVERTY INITIATIVES PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/718581474892669029/text/000020051-20140618080245.txt | http://documents.worldbank.org/curated/en/718581474892669029/pdf/000020051-20140618080245.pdf | The ICR lists a large number of lessons. The following selection focuses on those of general importance and which seem well-supported by the evidence: It is not realistic to expect a poverty reduction project such as APDPIP to achieve its objectives within a five year time frame. Such projects should rather be implemented over a long-term horizon, say 10-15 years, so that the government can adopt a programmatic approach towards planning such programs.Autonomous institutions need appropriate institutional arrangements, quite different from a normal PIU. Such institutions may need to deal with new types of products, such as insurance and marketing, and need the flexibility to recruit from the open market.Follow-on projects should wait until the preceding project is well under implementation. It would have been better that the follow-up APRPRP was launched at least a year later so that, by that time DPIP could have been more well entrenched and well established without any distractions, and the problems associated with a program expanding too rapidly could have been avoided.Capacity building should be given very high priority. Implementation of sub projects should start only after sufficient capacity building is achieved. Any attempt to fast track without proper foundation can result in manipulation and diluting project objectives.Scaling up can not happen through external teams. These projects need to invest in community to community mechanisms of scaling up and mobilization.Mechanisms for transparency and disclosure, community monitoring and social audit ensure effective and efficient use of project funds and have important spill-over effects. For example, these elements induce communities to amplify their voice in making public expenditure work for them by participating in local government processes. Social Audit, with a transparency of process and participatory process, is a very effective tool for ensuring fiduciary safeguard.There are limits to social mobilization in reaching certain groups: The project has mobilized a large proportion of POP and Poor households into the SHG fold. However, certain households (migrants, seasonal migrants, households with aged persons and the destitute) could not be mobilized into the SHGs. There are inherent limitations to social mobilization. A separate strategy would be required to address households and individuals who cannot be mobilized into the SHGs.Common interest groups are less likely to survive in the absence of SHGs. In the absence of micro-finance activities, there was no cementing factor in the CIGs that could ensure their sustainability. Closely knit and functionally effective SHGs are a prerequisite for fund management, asset promotion, retention and its productive use.Institution of appropriate book-keeping arrangements are an essential prerequisite for successful financial management. Providing hand holding support to the book-keepers, periodic auditing of accounts, institution of suitable audit arrangements of the project are an integral part of transparent and accountable financial management for sustainability of the CBOs.CBOs provide a lower risk credit market for banks:The project experience reveals that the CBOs provide an elastic and risk free credit market for the banks. The very high SHG loan recovery ratio (95%) in the project districts is a testimony to the good repayment behavior of the SHGs.
P045049 | ANDHRA PRADESH DISTRICT POVERTY INITIATIVES PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2007 | 2015 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/107971468033309842/text/952740PPAR0P04020Box385455B00OUO090.txt | http://documents.worldbank.org/curated/en/107971468033309842/pdf/952740PPAR0P04020Box385455B00OUO090.pdf | 4. Lessons There are four main lessons from the two projects\. 15 As an example of what is available, some Districts, using the SERP data system and data of their own, offer summarized District Data-at-a-Glance information sheets on the internet giving a wide selection of data including\. overall district statistics, poverty distribution, SHG statistics including savings and corpus, training, mandal performance data, audit coverage, human resources, bank linkages component achievements, action and investment plans, people trained, the CIF funding use, achievements of the various programs, marketing activities, food security, land purchase, Community Managed Sustainable Agriculture achievements, Poorest of Poor strategy, employment achievements including job training and placement, education achievement including pass results, disabled component achievements including certification, pensions, and revolving funds, health and nutrition activities including the health risk fund, kitchen gardens, sanitary achievements, weaning foods, community pharmacy, early education fund use, social security pensions achievements by caste, widows pension and death claims data, dairy program achievements, and grain bank achievements. 16It found\. better value for money from community implemented works compared to contractors; a better sense of ownership leading to enhanced sustainability; despite being strong on need identification they scored poorly on search for bidders and tendering; and, the need to ensure in the design inclusive participation. Â· Support for the establishment of women's self-help groups with linkages to bank finance and within a supportive policy and institutional environment can lead to enhanced confidence and capacity of women both collectively and individually. The evidence from Andhra Pradesh suggests that collective empowerment can support greater accountability for service delivery that, in turn, can positively affect the livelihoods of the poor. Â· In the early phases of rural development projects that support large-scale community group formation as a means to leverage more equitable service delivery, including finance, there is a need to think long-term about the transition strategy for the chosen implementing agency. In the case of Andhra Pradesh, the implementing agency support became an essential pillar of the built system, undertaking roles and responsibilities for service delivery that overlapped with the line ministries. Without an effective transition strategy that integrates the philosophy, training and acquired skills into the broader administration, there is a risk that gains made under the project will be lost and efforts to reach the poorest of the poor may not be sustained. Â· Reaching the poorest of the poor can prove difficult through group formation owing to rigid rules of attendance, set savings contributions, joint liability, and other group non-negotiables. Going forward, the strategy may need to be altered towards household or individual support, or differentiated models that consider the needs of the poorest of the poor, prior to group formation. This multi-stage approach is bound to incur additional costs. This implies trade-offs between depth and coverage and between short-term and longterm impact that should be accommodated in project design. Â· The pursuit of a single group model, such as women's self-help groups, to the exclusion of other approaches, limits the ability to learn from the user â€“ about what works and why in different contexts and to test alternatives in parallel rather than in sequence. Greater experimentation during the first phase, when the project was rolled out in the first six districts, could have laid the ground for more creative destruction, adaptation, and learning prior to scaling.
P045050 | RAJASTHAN DISTRICT PRIMARY EDUCATION PROJECT | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/651251475094732168/text/000020051-20140615110652.txt | http://documents.worldbank.org/curated/en/651251475094732168/pdf/000020051-20140615110652.pdf | 1. There is a need for a reliable monitoring and evaluation system to assess project impact. A monitoring evaluation system that is functional from the beginning of a project is critical for understanding the impact of various interventions, identifying problems and bottlenecks, and for taking corrective actions. 2. Implementation and supervision performance are greatly impacted by adequate numbers of key staff members and their stability. During a period of rapid expansion in the state, the number of school supervisors did not expand and staff turn over (especially at the state level) was extremely high, effecting continuity of leadership and quality control. 3. Teacher availability and productivity are key ingredients for achieving overall program outcomes. Teacher policies need to include incentives for placement and retention of teachers in difficult areas and improved teacher attendance (on which the current project was strangely silent). There needs to be a more careful examination of the policy implications and incentives from a teacher management system having both civil service appointments and the hiring of contract teachers. 4. Greater accountability in service delivery across institutional levels will be important for accelerating the pace towards better educational outcomes. Educational managers at all levels, in state offices to the school, need to be made accountable for outcomes (e.g., improved student learning outcomes and better management performance); this will require more results-oriented evaluation and oversight by supervisors and civil society (more engaged and active community education committees and NGOs). 5. Effective implementation of decentralization plans (down to the community level) requires careful assessment of the motivations of key stakeholders and realistic timelines for capacity and consensus building. This often takes more time than expected. 6. The growth of low-cost private primary education, a new phenomenon in Rajasthan (and throughout India), requires more attention and careful evaluation, since it is unclear how equitable and effective such schools are. Also, it is necessary that the EMIS be modified to include the growing private schools enrollments. 7. Project supervision by the World Bank should be regularized and harmonized with that undertaken by the government as done effectively in DPEP1, but Bank task team leaders also need the freedom to undertake supervision activities on an ad hoc basis and in response to emerging problems. 8. It is important for projects like DPEP1 to draw expertise and creativity from the existing pool of experts and resource persons, but it is also energizing for projects to take advantage of fresh insights and new thinking provided by a limited number of non-insiders.
P045051 | Second National HIV/AIDS Control Project | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/373471474487049735/text/000020051-20140615113759.txt | http://documents.worldbank.org/curated/en/373471474487049735/pdf/000020051-20140615113759.pdf | NGOs have a critical role to play in mapping high-risk behavior and delivering services to the most marginalized groups. However, limited NGO capacity and difficulties in contracting procedures remain major constraints to expanding service coverage of high-risk groups, and the efficacy of NGO-delivered interventions has not been evaluated.National HIV/AIDS programs tend to under-spend on interventions for high-risk groups and over-spend on interventions for the broader population, even in countries like India where high-risk groups are the main drivers of the epidemic. Only two-thirds of planned spending on targeted interventions was disbursed, compared to nearly double the amount planned for prevention in the general population.The use of inappropriate indicators, sporadic monitoring, and the lack of periodic evaluation of individual components severely limits the scope for improving program effectiveness. The project failed to monitor trends in risk behavior among the groups targeted by the project, or to evaluate the efficacy of key program components.Autonomous SACS have functioned more efficiently than previous institutions linked to the state Ministries of Health, but continued high turnover of directors and staff vacancies, including NGO coordinators reduce their effectiveness.Financial issues, such as budget allocations and disbursements, should be clarified with relevant government planning agencies so as to mitigate financial flow problems and avoid disbursement delays.
P045052 | ROAD MAINTENANCE AND DEVELOPMENT | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/101201474575531750/text/000020051-20140618085116.txt | http://documents.worldbank.org/curated/en/101201474575531750/pdf/000020051-20140618085116.pdf | 1. Projects in conlict-affected areas should have a flexible design and implementation plan. Social conflict and insurgency affects project planning and implementation. The project team should have substantial leeway without undue process burden to redefine project components as long as the project objectives do not change. In this project the components were changed, but for overall benefit the change could have taken place earlier.2. Local consultants and contractors are more effective than foreign entities in conflict areas. Projects in conflict areas could be implemented with local consultants and contractors, who can negotiate with the conflicting parties to implement projects with their safeguards.3. Dissemination and application of project experience is best carried out by staff who have hands-on experience with all IFI funded projects. The project experience supports integrated project management, not a separate PIU. 4. Financial incentives improve compliance with safeguards. Contractors can be reluctant to follow EMP (environment management plan) if there is no financial incentive to do so. EMP - related items should be put in the bill of quantities and unit rates to motivate contractors to comply with (environmental) safeguards.
P045053 | RURAL INFRASTRUCTURE PROJECT | South Asia | Nepal | IDA |  | Infrastructure | Transport | IDA | IPF | 1999 | 2004 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/675011474493007866/text/000020051-20140612103244.txt | http://documents.worldbank.org/curated/en/675011474493007866/pdf/000020051-20140612103244.pdf | Building on the ICR, the main lessons are: (i) Not all the challenges in implementing a project that has significant community participation can be visualized upfront. Hence the importance of an efficient monitoring and evaluation system to report on progress and make mid course corrections if required. (ii) In the difficult hill terrain of Nepal, rural roads offer critical access and travel time saving benefits to isolated rural communities. Adequate weight needs to be given to these factors in the economic analysis of these operations. (iii) Though community-based organizations provide a viable option for carrying out small scale civil works, adequate technical assistance and clear policy guidelines are required to ensure quality outcomes. (iv) The small size of sub-projects and high costs of environmental assessments is no justification for not doing due diligence on environmental issues.
P045073 | BAKU-CEYHAN OIL EXPORT PIPELINE TECHNICAL ASSISTANCE | Europe and Central Asia | Turkiye | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 1999 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/736651474907418206/text/000020051-20140529164535.txt | http://documents.worldbank.org/curated/en/736651474907418206/pdf/000020051-20140529164535.pdf | This project highlights the potential benefits from relatively small TA loans. In this particular case, the feasibility study is for a pipeline that would carry oil from the landlocked countries of Azerbaijan, Kazakhstan and Turkmenistan to the Turkish port of Ceyhan, thus improving these countries' ability to export their crude to international markets. Therefore, the potential benefits from this small initial study could be far-reaching and cross-national.
P045091 | Human Resources Development Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2000 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/405351474555809801/text/000020051-20140624164036.txt | http://documents.worldbank.org/curated/en/405351474555809801/pdf/000020051-20140624164036.pdf | There is generally a strong need for infrastructure and human capacity investment in a post-war environment. In such cases, project designs should prioritize and focus on fewer activities. This may also require a need to revisit Bank procurement rules to ensure speedy procurement (e.g. rules for tendering of international construction firms to build schools if there are only few private firms available locally).Project design should be kept flexible if a country is preparing for decentralization that affects sector management. This is particularly important if the project is implemented in collaboration with local governments who might be affected through the decentralization process.Projects that include sub-components managed by communities (e.g. community based school rehabilitation) should include activities to train community members in financial and project management.Extending a rather complex project to 8.5 years will create some "loss in momentum" among all partners, and may affect the quality of implementation. In such cases, it may be better to conduct a first order restructuring, with substantial streamlining of project design to facilitate implementation.
P045134 | FORESTRY PROJECT | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/627141474573156314/text/000020051-20140612092500.txt | http://documents.worldbank.org/curated/en/627141474573156314/pdf/000020051-20140612092500.pdf | The ICR notes three broad lessons: (a) In a divided country an emphasis on technical investments can achieve quick results on the ground and help build broader-based trust and collaboration between stakeholders; (b) projects seeking to achieve institutional reform benefit from a mixture of credit and grant funding; and (c) support for a participatory approach to institutional reform is more likely to be successful than a purely technical approach. In addition the outcome of the project suggests that a strong M & E system is critical for monitoring and controlling environmental impacts.
P045174 | Education Development Project | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2000 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/751241474488536185/text/000020051-20140624163025.txt | http://documents.worldbank.org/curated/en/751241474488536185/pdf/000020051-20140624163025.pdf | Sufficient institutional capacity is a prerequisite for embarking on a major reform initiative.In addition to technical input, a political consensus-building process is critical to support a significant reform agenda.In a post-conflict setting, targeted reforms should be implemented on a step-by-step basis while building capacity for more sector-wide reforms.
P045175 | HEALTH SECTOR REFORM | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/462301474506488434/text/000020051-20140620083216.txt | http://documents.worldbank.org/curated/en/462301474506488434/pdf/000020051-20140620083216.pdf | Health financing/insurance reform requires a clear and effective legislative and regulatory framework, as well as collaboration and shared leadership between the Ministry of Health and the insurance entity.Intersectoral integration is necessary to provide essential health services to the poor, with collaboration between ministries of social services, health, and finance, as well as relevant non-governmental organizations.Political economy analysis to identify potential support and resistance to reform is critical; information and outreach to all stakeholders and the public to explain reforms and their potential benefits should be an integral part of the reform process.The presence of local champions, leading a committed local reform team with requisite technical capacity, is essential for success.
P045182 | Rural Water Supply and Sanitation Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/809051474664994635/text/000020051-20140619082944.txt | http://documents.worldbank.org/curated/en/809051474664994635/pdf/000020051-20140619082944.pdf | (1) Public-private sector partnership (PPP) has a strong potential for the delivery and development of improved water services. Community-based management seems more appropriate for point sources (springs or hand pumps) than for piped systems. The Rwandese experience showed that (i) Water users' associations offer limited accountability, (ii) maintenance and cost recovery is quite challenging, and (iii) local private operators can be found anywhere. In situations where the operating conditions and actual demand are uncertain, it is not advisable to try to impose the use of standard contracts. The Rwandese districts decided instead to design themselves very simple contracts for candidates offering a minimum of qualifications, which resulted in quite satisfactory arrangements.(2) Self-standing rural water supply and sanitation (RWSS) projects can also aim at facilitating harmonization and preparing to scale up and to shift to a sector-wide approach and budget support by (i) providing a complete set of tested guidelines and procedures for preparing and implementing investments and for managing and delivering services; and (ii) enabling sector staff, rather than consultants, to elaborate objectives and policy matrix actions. As it was the case in Rwanda, only a strong sectoral leadership at the ministerial level can create incentives for staff and donors to internalize the change in approach and to ensure harmonization.(3) Despite some resistance by users to the principle of paying for water, experience shows that without user fees the delivery of quality water services on a sustainable basis is extremely difficult. Through establishing special arrangements for the poorest users and the design of systems based on user's ability to pay can make such schemes more acceptable to the population. For example, at the Mid-term review it was found that over 50% of the water users' associations were no longer operational due in part to users' low willingness to pay. In order to tackle the problem, community contribution rules were revised to emphasize in-kind and labor contributions. In addition, to alleviate the financial burden for the poorest part of the rural population, the districts keep a list of vulnerable households (widows, poor single-parent households), who get free access to water points.
P045188 | GH-GEF Forest Biodiversity SIL (FY98) | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2007 | 2009 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/215541475098124219/text/000020051-20140618193955.txt | http://documents.worldbank.org/curated/en/215541475098124219/pdf/000020051-20140618193955.pdf | Borrower ownership is key to achieving project objectives. It is essential to gauge support at higher levels of government than the concerned environmental agencies. Care has to be taken that international environmental pressure, vested interests and the understandable enthusiasm of the Bankâ€™s own appraisal process does not lead to financing of worthy causes that governments are unwilling to support. Sound environment policy and management require inclusion of all stakeholders and incentives to keep them engaged. Care has to be taken that individuals and community stakeholders are empowered in the decision-making process, particularly over allocation of rights to utilize natural resources. Insecure property rights allied with centralized, top-down award of concessions to commercial timber operations and capture of economic rents creates conflict and promotes non-sustainable natural resource utilization that adversely affects biodiversity.Renewable natural resources and biodiversity management are different sides of the same coin and should not be considered in isolation. Insufficient attention to addressing the causes of rural poverty drives people to live off the environmental commons where short-term survival interests typically outweigh consideration of longer-term stability. Baseline data are particularly important for biodiversity conservation to demonstrate project impact. M&E to ensure this happens should be established during appraisal. This will require up-front funding commitment and a clear allocation of the responsibility to a line agency.Designers of GEF projects that are subcomponents of larger Bank projects should ensure that inadequate project documentation, phasing and cross-support expected from the Bank do not pose high risks. In this project a 6 year GEF project was attached to a 2 year first phase of an APL and the GEF project was given very cursory treatment - a proper PAD was not prepared for it and, in effect, it became a component that received insufficient attention. When the APL was cancelled after the first phase the GEF component was left an orphan with fairly minimal supervision.
P045251 | QUICK START GAS TURB | Europe and Central Asia | Hungary |  |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 1999 | 2000 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/412531474553754032/text/000020051-20140528115703.txt | http://documents.worldbank.org/curated/en/412531474553754032/pdf/000020051-20140528115703.pdf | Completing procurement prior to project effectiveness can accelerate loan disbursement and shorten significantly the project implementation period.
P045264 | Smallholder Cattle Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/429311474487187150/text/000020051-20140615102610.txt | http://documents.worldbank.org/curated/en/429311474487187150/pdf/000020051-20140615102610.pdf | The ICR offers three useful lessons, which are presented here with some modification:1. To be competitive with the increasing range of loan alternatives and in rapidly changing economies, IBRD lending procedures need to function faster. This can enhance operational efficiency and avoid projects being overtaken by rapidly changing country developments. 2. Flexibility of both lending procurement procedures and investment production models is particularly important in a rapidly developing rural economy where expanding commercial operations demand nimble adaptation to shifting market conditions and where there is a need to respond quickly to any revealed weaknesses or gaps in project design and to respond to shifts in commodity demand.3. Rural projects calling for integration of production and marketing benefit from strong coordination between public and private sector agencies and farmer associations. In this case Project Management Offices at local level played a key coordinating role.
P045303 | Pilot Water Supply Project | Europe and Central Asia | Kazakhstan | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/296761474503601331/text/000020051-20140607161440.txt | http://documents.worldbank.org/curated/en/296761474503601331/pdf/000020051-20140607161440.pdf | Due to limited sector knowledge and data availability, the feasibility studies for the pilot may be inadequate. The feasibility study for the full scale project in Kazakhstan brought out many issues with respect to economic feasibility of the Atyrau Water Supply and the state of the Syr Darya River, that had significant implications to project design. Therefore, the investments designed under the pilot may have limited impact on the targeted population.Implementation of investments under the pilot, without sufficient consideration of financial issues such as cost recovery, and associated institutional issues, can affect the sustainability of the investments. Although the project objectives included gaining experience on cost recovery aspects, the delays in initiation of the full scale project mean that the financial situation for the water utilities continues to be very difficult.
P045310 | EMG PUB WORKS & EMPL | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2000 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/521951474750357017/text/000020051-20140529073021.txt | http://documents.worldbank.org/curated/en/521951474750357017/pdf/000020051-20140529073021.pdf | (1) Issues of employment creation are not necessarily clear-cut. At an early stage in the project, direct employment through the subprojects was viewed as a priority. During implementation as municipal priorities manifested themselves more clearly, the emphasis shifted to getting municipal infrastructure in order as a necessary precondition to promote business and improve the longer term prospects for employment. (2) Financing of large slices of municipal budgets as in this public works project should be considered where possible within the broader framework of municipal budgets. This would enhance sustainability, as in allowing a more careful evaluation of maintenance capacity. However, in a post-conflict situation such as this, proceeding before such information is available may be warranted. (3) Involvement of local communities in decision-making and other parts of the project cycle is important so as to ensure greater responsiveness to citizen needs, greater transparency, and accountability and representation of all, regardless of ethnicity.
P045311 | Local Initiatives Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2000 | 2001 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/683901475075173226/text/000020051-20140529161611.txt | http://documents.worldbank.org/curated/en/683901475075173226/pdf/000020051-20140529161611.pdf | Targeting the microfinance sector with a modest amount of well-directed financing and working with select NGOs can have a strong impact on economic activity. It is important to focus on institutional development in order to sustain the benefits on microfinance operations.
P045311 | Local Initiatives Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1997 | 2000 | 2004 | PPAR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/520611468768015596/text/28288.txt | http://documents.worldbank.org/curated/en/520611468768015596/pdf/28288.pdf | Lessons * Even in very complex post-conflict situations, traditional Bank assistance in rehabilitating infrastructure and restarting business credit can yield very worthwhile results for the recovery of the war-affected borrower. l The Bank should avoid involvement in activities beyond its core competence. Inexperience and lack of familiarity with landmine clearance, for example are ingredients for failure. l Designs of projects that rely on PIUS for implementation can make for speedy disbursements, but should always include exit strategies to help governments move toward normal operations.
P045312 | Health Recovery Project | Europe and Central Asia | Albania | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/805851474501138246/text/000020051-20140613064343.txt | http://documents.worldbank.org/curated/en/805851474501138246/pdf/000020051-20140613064343.pdf | In projects where substantial sectoral restructuring and reforms are intended, but which also include large infrastructure investments, specific disbursement conditions linking progress on reforms with infrastructure development could be included in the credit / loan agreement. Monitoring and evaluation indicators should include key benchmark points, especially where activities require substantial implementation time. The time schedules for lengthy implementation activities should allow for each step of the process, and also reflect the experience and expertise of the implementation agency.Multiple changes in IDA task management and in MOH leadership do not lead to good project outcomes
P045313 | Education Reconstruction 2 Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Education | IDA | IPF | 1998 | 2000 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/584961474556013888/text/000020051-20140529164150.txt | http://documents.worldbank.org/curated/en/584961474556013888/pdf/000020051-20140529164150.pdf | Rapid reconstruction provides immediate access to schools but has medium-term costs in terms of delayed policy and institutional reform. While reconstruction must proceed, key policy issues must also be addressed.- Better communication and coordination are essential among donors and different levels of government in difficult post-conflict situations.- The need to provide education and communicate on important issues may help promote reconciliation among populations in conflict, but the payoff may come after several years.
P045337 | ID-KECAMATAN DEV FUND | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/520631475082567361/text/000020051-20140612085809.txt | http://documents.worldbank.org/curated/en/520631475082567361/pdf/000020051-20140612085809.pdf | Several important lessons are identified by the ICR. Five are repeated here for their broad applicability:Capacity building requires training that is addressed through a sustained strategy for developing capacities continuously and transferring skills gradually over a period of time, rather than one-time generic training workshops.Community participation can be substantially improved through better facilitation, communications and outreach. The Bank needs to substantially improve the poverty targeting mechanism for allocating funds at the village level.Women's representation at meetings does not necessarily translate into women's empowerment or investments that benefit them. The Bank needs to move beyond the first step of mandatory representation and include more systematic gender awareness and womenâ€™s leadership training programs to raise the voices of women.Independent civil society groups including NGOs and media can provide quality monitoring.
P045337 | ID-KECAMATAN DEV FUND | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2003 | 2006 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/236891468042265551/text/35585.txt | http://documents.worldbank.org/curated/en/236891468042265551/pdf/35585.pdf | lessonsfor thewide expansionof theapproachthatfollowed.Both projects largelybypassed the district level.With respectto thebroaderpovertyreductionaim,field visits andaproject impactstudysuggestwidebeneficiarysatisfactionwith theinvestments.Howeverthereare concernsaboutmaintenancewhich applyto bothVIP2 andKDP(para2.3below).In addition, (but alesserreasonfor not goingto aHighly Satisfactoryrating)giventhepovertyreduction intentof theproject,theinclusionof anumberof lesspoorvillages,partly for political reasons,undercutthepovertyfocus.Thatsaid,in villageswheretheproj.ectintervened attendanceof thepooratmeetingsappearsto havebeenat leastadequate,but thequalityof inputEromthepoorremainsunclear.However,it would beunreasonableto expectveryrapid . gainsin thevoiceof thepoorgiventhelong-entrenchedsocialenvironment. 22 Theoutcomeof KDP isratedModerately Satisfactorybasedontheassessmentof relevance,efficacy,andefficiencydiscussedbelow.As with VIP2,KDP strengthenedvillage andkecamatangovernments,thoughweaknessesremainin achievingtheaccountability elementof theobjectiveassignificantleakageof resourcesandcorruptionoccurreddespite thecreativeanti-corruptionmeasuresput in placeto preventthem.Whiletheproject objectivesdidnot explicitlyclaimto strengthenthedistrict government,supportfor decentralizationwasimplicit in theproject.TheKDP economicloanscomponent(23percent of total costs)is generallyacknowledgedto havenotbeensuccessfulandit exhibitedmarginal efficiencyasacreditoperationbecauseof weakrepayment.Thisisthedeterminingelementin thejustification for goingto onlyModeratelySatisfactory,nearlyaquarterof theproject fundingresultedin unsatisfactoryperformance.4However,aconcernaboutmaintenanceasan elementin assessingoutcomenotedin thefollowingparagraphalsoappliesto KDP. Further, owingto thesocialpatternsin communities,in bothprojects,despitegoodmeeting attendance,progresstowardgenuine,high-qualityparticipationin decisionmakingbythe poorermembersof thecommunityandwomenwasprobablymodest. 4. IEG rates a project as moderately satisfactory when it is expected to achieve most of its relevant obj ectives but with significant shortcomings as in the case of the economic loan component. 23. Giventheobjectiveof establishingacommunityparticipationprocess,concernsabout communitymaintenancecapacity,andthereforesustainability,areseenasintegralin assessing outcome,in bothprojects.It seemsclearfrom missionobservationthatvillagesdonot have the'capacityto maintaintheescalatingvolumeof infrastructurethattheyareexpectedto maintainevenif, for aperiod,theycanmaintainsomeof it. Thereremain,therefore,questions aboutwheresuchprogramsareheadedin theabsenceof greatercommunityrevenuecapacity, especiallyin poorercommunitiesandwhereasphaltroadshaveincreased,andwhether constructionof furtherinfrastructureis reallyasoundstrategygiventhispersistent maintenanceissue.Thetechnical/economic/socialdilemmaisthat, in theveryhighrainfall of muchof Indonesia,dirt roadsdonot lastwell, asphaltplacedontop of low costdirt*roadsnot designedto takeasphaltlastonly somewhatbetter,andgoodasphaltlastswell givengood drainagebut is generallyoutof reachof mostcommunitiesfor maintenance.Thesolutionof rebuildingroadsthroughoutsidesupport(donoror government)everytenyearsmaystill give an'acceptableERRbut isnot anefficient developmentstrategyandin theendis likely to underminecommunityparticipation.Notethattheissueis not onesimplyrelatedto VIP or KDP-fundedinfrastructureandthequalityof maintenanceof thosequitemodestsizedpieces, theissueisrelatedto all villageinfrastructureandtheplaceof VIP andKDP within that infrastructurechallenge? RELEVANCE 24 Relevanceof bothprojectswassubstantial,butwith somequalification.Theobjectives wererelevantto boththeBankandcountrystrategyatthetimeandremainedsothroughoutthe 199?98economiccrisis.KDP wasparticularlyrelevantgivenitstimingin relationto the economiccrisisandtheconcernwith respectto increasedcorruption.6 s 25 Thisassessmentdidnothavethecapacityto pursueseveralrelevancequestionsrelated to thetwo projects.First,extendingvillage,infrastructurethroughnewinvestmentsmayhave beenlessrelevantfor meetingpovertyobjectivesthanenhancingmaintenanceof existing 5\. A KDP project document noted in 2004 that all the consulting teams were in agreement that the most pressing post-construction issue that needed to be addressed comprehensively by l!%P management was maintenance. In many villages hard won benefits were in real danger of eroding to pre-project conditions, especially for roads. The report also found that very little serious thought had been given to the high repair costs that arise periodically as natural wear-and-tear begins to take its toll. Costs of repairs for roads and water systems were significantly underestimated. For the villages analyzed, it was clear that the O&M burden, especially for roads, was too great for the majority of villages to shoulder. 6. Corruption has a long history in Indonesia. It has plagued governments since early independence (which was declared in 1945 and internationally recognized in 1949), although it arguably reached the greatest heights-in terms of sheer scale, sophistication, and damage-when the new Order began in 1966. In the period of parliamentary liberal democracy (1950-59) and during the Sukamo-dominated Guided Democracy (1959.65), corruption and abuse of power had already commonly taken the form of alliances among political patrons and business clients who were regularly given special privileges in the shape of licenses and other nontransparent business opportunities. This was to be apattern replicated during the New Order. The big difference was that the economic cake was to grow so much larger-as was scale of the resources that could be misappropriated. V.Bhargava and E Bolongaita 2004. Challenging Corruption in Asia The World Bank. infrastructure,at leastin somevillages.7Second,giventhepovertyreductionintentof the projects,theinclusionof anumberof lesspoorvillages,partly for politicalreasons,undercut thepovertyfocus.Thepovertyselectionprofile wouldhavebeendifferenthadvillagesbeen strictly povertyrankednationally.*Third,theIndonesiangovernmentinstitutedamajor decentralizationprogramin 1999.'It isnot clearhow KDP, in bypassingthedistrict level, conformedwith thatprogram.It is alsonotclearhow far thebypassingof government institutionsandthecreationofparallel institutionsto overseetheimplementationof theKDP programaffectedtheoveralldecentralizationprogram.loTheseissuesarewider thanthe experienceof theseindividualprojects,however,andshouldbeexploredfurther.Fourth, agriculturaltechnologyremainsweak,especiallyoutsidetheareasof moreintensive cultivationandhigherrainfall,andseemsto beunder-investedin nationally.Thisraisesthe questionof whetheranequivalent(or greater)investmentin agriculturalresearchand extensionmighthaveequaledor exceededthepovertyreductionimpactof theseprojects. Supportfor agriculturaltechnologyhasgenerallyshownveryhigheconomicreturnsand satisfactorypovertyimpacts,andthereforemighthavebeenacompetitivealternative.The _ missiondid nothavetheresourcesto pursuethisquestionfar enoughin relationto therecent supportfor research(AgriculturalResearchProject'2with total costsof*@2million at completion)andthefurtherassistanceproposed. EFFICACY 26 Efficacy-the extentto whichtheprojectobjectiveswereachievedtakinginto account theirrelativeimportance-is ratedsubstantialfor VIP2 butmodestfor KDP, although baselineindicatorswerelimited. . 7. It could be argued that some of the investment was, in fact, delayed maintenance. 8. The mission visited. several VIP2 and KDP project villages in West Java where the majority of households appeared quite well off relative to those seen, for example, in Kalimantan. 9. Decentralization Law 22 that assigns all government expenditure to the districts (kabupaten) except for fmance, foreign affairs, defense, religion and state administration was passed on May 7, 1999 and Law 25 that provides the details of fiscal decentralization was passed on May 19, 1999. 10. KDP provided for funds to flow directly from a central project account to ajoint village account at a local sub-district bank, processed by the branch office ofthe national Treasury. At no stage do funds pass through a government ministry.. .. ... ...It runs counter to a Bank-wide trend during the 1990's to move away from heavy reliance on project implementation units by putting government in the driver's seat, strengthening government institutions, and insisting that projects and programs be implemented by government agencies. In fact, ,the KDP National Management Consultants office in Jakarta is in reality a PIU, or at best an inhouse NGO. It also runs counter to some decentralization initiatives that originate with federal government offices, and subsequently cascade down through development plans prepared at various levels. Judith Edstrom Indonesia '8sKecamatan Development Project Is It Replicable? Social Development Papers, Paper No. 39, The World Bank, March 2002. 11. Agricultural technology has been neglected both nationally and by donors in recent years and, globally, IEG has concluded that this decline has gone beyond what would be justified by the falling percentage of agriculture in GDP. 27. Theobjectivesagainstwhich VIP2 isratedarethosein thetext of theappraisal.Based onmonitoringandevaluationdata,theobjectiveof building small infrastructure was achievedat alevelof morethandoubletheoriginaltargetwith alittle overaone-year extension.VIP2built infrastructurein 7,044villagesagainsttheplanof 2,600atalocal currencyvalueof nearlythreetimestheplan.HoweverasindicatedearlierunderOutcome, thereareconcernsaboutthecapacityof communitiesto maintaintheinfrastructure. Decentralization atthedistrict levelwasnot reallyhelpedmuchbyVIP2,but,theproject madesignificantprogresswith theobjectiveof decentralizationandcommunityparticipation at kecamatan andvillagelevels,thelowerlayersin thedecentralizationhierarchy.12 Communityparticipationwascertainlyincreasedasis evidentin mostvillagesfrom village meetingrecords.With respectto theobjectiveof reducingpoverty, it is difficult to measure andattributein aggregatesignificantchangesin broaderruralpovertyindicatorsto modest lengthsof villageroadsorbridges,oftenrelevantonlyto oneparticularhamlet.However,the economicanalysisfor VIP2,thesubsequenteconomicanalysisfor KDP for similar infrastructure,andindividualstructuresassessedby missionfield visits,partly through discussionof landvalues,implyhighfinancialandeconomicbenefitsto thosebeneficiaries within theserviceareaof theinfrastructurebuilt by theproject.Themissionobservedthat while communityparticipationhadbeenclearlyenhancedat thecommunitylevel,some uncertaintiesremainedabouttheextentto whichthepoorestandwomenhadtakentheir voice qualitativelybeyondmerelyattendanceatmeetingsandparticipationin labor.13The achievementvariedbyprovince. 28 Theobjectivesusedto evaluateKDP weretakenfrom theLogicalFramework(see para.-1.4).With respectto thefirst of thoseobjectives,KDP doesappearto havestrengthened kecamatan andvillagecommunitiesby supportingthemin themanagementof increasedfunds andgivingthemfull responsibilityfor fundsmanagementandimplementation,including substantialfacilitationsupportandtraining.With respectto thekecamatanlevel,whiledifficult to measure,thedecisionmakingneededto allocatethecompetingprojectresourcesandthe facilitationandtrainingprovidedappearto haveimprovedskillsatthatlevel.Capacityfor book keepingandcommunityfacilitationhasalsobeenenhancedatthekecamatanlevelthrough trainingandpractice,althoughsustainabilityisquestionable.A numberof outputandoutcome changeshaveoccurred,including\.theactivitiesof community-operatedvillageimplementation teams(observedbyjournalistsandreportedinmonitoring),increasingcommunitydemandson government(reportedin studies),-increasedopennessof biddingprocess&atvillagelevel(arule thatwasimposedandfollowed-as reportedinmeetingsminutes),greaterinformation(still 12. .However, in VIP2 the project manager was located at district level and some technical skills were located at that level. 13. In weighting the importance of targeting the poor, M. Ravallion and S. Chen, TVhat Can New Survey Data Tell Us about Recent Changes in Distribution and Poverty? World Bank, 1997, is a relevant study. It uses Indonesia data and finds that even at apoverty line of 20 percent of the population, nearly halfthe population are vulnerable to poverty given the evidence on income variability. Households in Indonesia have about an even chance of facing a poverty episode once in three years. The authors point out that the poor at any given time are only a fraction of those who must worry about, and struggle to avoid, falling into poverty. This would suggest, for Indonesia, that the extent to which poverty targeting is critical to project poverty performance should not be under-estimated. evidentoncommunitynoticeboards),increasedreportingof andactiononcorruption(as reportedin astudyof corruptionandbymonitoringreports),greaterattendanceatmeetings,and increasednumbersof proposalsfromwomen(anoutsideinterventionthatbecamearequirement underKDP). However,considerableevidencefrom Bankinternalfilesandfrom theliterature showsthatleakageof resourcesandcorruptionremainsignificantproblemsin KDP. Thisraises concernsabouthowmuchkecumatunandvillagegovernmentswereactuallyableto become accountable. 29 With respectto creatingeconomicopportunityatthevillagelevel,therearethree findings.First,theimpactof smallinfrastructureonincome,oftenrelevantmainlyto one hamlet,is difficult to measureandattribute,butthegenerallyhighsubprojecteconomicrates of returnin theeconomicanalysiscasestudies(andin morerecentanalysisundertakensince theIEG mission),supportedby missionfield questioningof individualsaboutlandvaluesand missioncalculationsonsite,suggestthateconomicopportunitywasenhancedsignificantlyin thebeneficiaryhamlets.Second,theinfrastructurewascreatedwith very labor-intensive methodsproviding25million workdaysfor.about2.8million peopleatatime of economic crisis.Third, asubstantialnumberof productiveinvestmentswith incomeearningcapacity werebuilt, including5,200irrigationsystems,400marketstructures,and260village electrificationactivities.Fourth,women'slaborwasreleasedthrough2,800cleanwaterunits. Theactualnumberof subprojectswasmorethantwice thenumberplannedat appraisaldueto lowerunit costs,additionalfundingdueto devaluationandthe supplementalcredit,and additionalsupportfrom government.l4Fifih, creditmustbegivenin weighingthescaleof thesebenefitsfor the factthatKDP (buildingontheearlierVIP experience)providedthe knowledgebasefor anumberof whathavebeentermedKDP copy-catprojectsbyboththe governmentandotherdonors.However,aswith VIP2,theseinfrastructureachievementsmust betemperedwith theconcernsaboutcommunitycapacityto maintainitstotal stockof infrastructure.Sincemuchof theinfrastructureis still relativelynewthefull burdenof thisis still ahead. 2.10 With respectto thequestionof whetherthepoorestkecamatanwerereached,thedata for selectedkeiamatanandvillagessuggeststhattherewassomebendingof theselection rulesfor politicalreasons.If anationalrankingregardlessof provincehadbeenused,selection wouldhavebeendifferentlydistributedin provincesandislands. 2.11 In particular,asignificantweaknesswasthat in theloanscomponent,which wasabout 23percentof totalprojectcosts,eficiencywasmodestdueto variablebut oftenweak repayments.Thiscomponentis discussedin moredetailbelow(para.2.16). 14. The Region in its comments notes that the physic&l achievements under the KDP project need to be seen in the context of the prevailing country environment\. a collapsing portfolio, currency crisis and civil war in nearly a third of the participating provinces. VIP2 Infrastructure Achievements in Detail 2.12 Theoriginalprojectobjectivesremained,but thenumberof villages.assistedincreased from theoriginaltargetof 2,600to 7,044.An extendedprogramwasaddedfor JavaandBali covering2,596villages.No initial sub-projectinvestmenttargetsweremadenorwere projectionsattempted;projectdocumentsarguedthatthiswasimpossiblegiventhevillagers' freedomto choose.Villagesbuilt atotal of 15,069kilometersof roads,42.5kilometersof bridges,4.9kilometersof piers,8,722communalwatersupplyunits,4,877sanitationunits, 140irrigationsystems,58markets,and84othertypesof infrastructure.All infrastructurewas of.modestdesigncomplexityto keepcostsdown.In fmancialyear1998/99,dueto the economiccrisis,thegovernmentinitiatedamorewidespreadworksprogramwith its own funds(PDM-DKI). Dueto implementationdifficultiesin Sumatra-thisislandwasleft out of thethird programyearandput in with anOECFprogram,which alsobecameaform of VIP as it shiftedresponsibilityfor managingcontractsfrom theagenciesto thevillages..Thisis one exampleof thedemonstrationimpactof VIP. More recently,theKecamatanDevelopment Projectcoveredsomesubdistrictson Sumatra.. 2.13 Whiletherewerenotargets,atotalofjustunder2millionpersonsworkedontheVIP2 projectfor approximately50million person-daysof work, anaverageof about25daysper personemployed.Approximately40percentof thefundingwentdirectlyto villages,with another40percentfor materialssuchasstone,whichalsorequiredlocallabor,and20percent for imported materialssuchascementandtransport.Annualincomefromtheprojectper workeremployedwasapproximately$25.Thiscompareswith typicalannualincomesperpoor personof $150to $200peryear.Approximately'15percentof thevillagepopulationsworked directlyontheproject\.58percentweremen,15percentwomen,and30percentyouths. 2.14 Nearly6millionpersonsappearto havebenefited,representingabout50percentof the populationof thebeneficiaryvillages.TheVIP2ImpactStudynotedin para2.1covered233 villagesby 1997/98,butthemethodologyfor benefitestimationwasquitesubjectiveasbenefits wereestimatedqualitativelybybeneficiariesasgood, fair, or poor, andcommunity estimatesof financialbenefitsfi-omsubprojectswerewithin ranges(e.g.,Rp 0to Rp 10million; Rp 10millionto Rp 25million, etc.)andit isnotclearhowthesewereestimated.Nonquantifiedbenefitsreportedby villagesincludedeasiervisitsto healthcenters,additionalvillage business,changesin croppingpatterns,improvedsecurity,andeasiertravelto school.Basedon theseestimates,some40percentof villageswereestimatedto haveachievedbenefitsequalto or _ abovecostswithin asingleyear.Otherstookalittle longerto breakeven.A post-construction . reviewstudyin 2000assessedthestandardsof maintenanceandratesof infrastructure deteriorationandconcludedthatby thefinalyearof theproject,about7percentof roadsand bridgesbuilt in Javaweredeficientin qualitydueto lackof maintenanceandabout12percent weredeficientin Sumatra,wheretheprojecthadnotperformedwell for qualityeveninitially. KDP Infrastructure Achievements in Detail 2.15 With respectto theobjectiveof supportingcommunitiesto buildinfrastructure throughlabor-intensivemethods,thetargetswerenot definedbytypeof infrastructuresince choicewasopen.However,thenumberof subprojectagreementswasplannedat 6,000and actualachievementwith thesupportof thesupplementarycreditof $48.2million was 15,000. By projectclosing95percentof theworkshadbeencompleted(comparedto aprojectionof 80percent).Theamountof localfundsdisbursedwasaboutfour timestheprojection alongsidean80percentdevaluationof therupiahandthesupplementarycredit.With respect to quantities,19,000kilometersof roadwerebuilt or upgraded,and3,500bridges,2,800 water supplyunits,5,200irrigationsystems,1,300sanitationunits,and400marketswere built. Thereisno doubtfrom field discussionthatlabor-intensivemethodswereused,albeit probablyatsomecostto qualityandsustainability,particularlyfor roadsbuilt onsoilswhere compactionisimportant.Thepurposeof thelabor-intensivemethodswaspartly to provide incomesupportto thepoorercommunitymembersduringtheextremeeconomicdeclinegiven thatamainobjectivewaseconomicopportunity.Whilethiswasachieved,it wasnot clearto themissionthat theintendedself-targetingworkedeffectively.It wasanticipatedthatwages wouldbesufficientlylow thatonlythepoorestwouldbeinterested;however,owingpartlyto theeconomiccrisis,interestin this work waswidespread,at leastin Java,andin mostcases supplyanddemandhadto bebalancedby someform of rationing,suchassharingout labor betweenhouseholdapplicants.Nevertheless,thisunderscorestheimportanceof incomeasa crisismitigationmeasure. Efficacy of the EconomicLoans(Micro-Credit) Component 2.16 As reportedin theICR, thiscomponentin KDP wasunsatisfactory.Theeconomic loansormicro-creditelementof this componentwasbarelytouchedonin themaintext of the appraisal.It isnot mentionedin thecomponenttableanddiscussionof therepaymentissueis hiddenin the CostBenefitAnalysisAnnex.It is doubtfulwhetheranExecutiveDirector's office would havenoticedthattherewasacreditcomponent.Ashasbeenpointedoutby IEG before,thestructureof appraisaldocuments,whichasksonly for asummarytableof componentsandcostsin themaintext, encouragesinadequatedescriptionof project components.In this appraisal,theheadingin themaintext tableKecamatanDevelopment Grantsis actuallymisleadingsinceaportionwasto beloans.l5Repaymentrateswereabout 20percentin areasthatweremoreremote,poorer,andhadnohistoryof creditbutrangedup to 90percentin areasthat,werelesspoor andhadexperiencewith credit.Thejoint and severalliability for repaymentwithin groupsoftendidnotwork becausetherewasno expectationof continuity,no institutionallinks,andsomeof thegroupswerehastily assembled.Therefore,whenonepersonin thegroupdefaulted,insteadof grouppressureto repay,oftenotherssimplydecidedthat therewasnoreasontheyshouldrepayeither.While individualrecordswerekeptatvillagelevelandgrouprecordskeptat theFinancial ManagementUnit atthekecamatanlevel,theassessmentmissionfoundthat,oncetheproject closed,collectionefforts for thiscomponentwerenot stronglypursued.In onecase,theloan 15. The Region in its comments disputes this fading but on further review IEG fmds the comment still valid. Reference to the PAD shows that under the Project Description Summary the only reference to credit is within a parenthesis which sayswith respect to self-targeting (e.g. wages at local rural minimum . ... and repayment of credits . ..) In the section on Project Alternatives it is not mentioned. In the section on Risk it is only mentioned once in the context, again, of self-selection. Nowhere in the document is there any substantive discussion of the issues, risks and experiences of managing credit. recordswerenot evenpassedonto newstaff. TheImpactStudy16foundthatonly7percentof loanswentto thepooranda similarpercentageto women.However,onesourcesuggeststhat, while womenmaynot havebeenthenominalborrowers,in practicetheir enterprises(e.g., livestock)wereoftentheobjectof theloan.Onereasonfor thelow participationbythepoor, apartfrom their ownperceivedrisksof indebtedness,wasthatmanyless-poorborrowersdid notwish to begroupedwith poorborrowerswho theydidnot know andwhomightbea repaymentrisk.17 Efficacy of Community Processes 2.17 It is difficult to isolatethe changesthathavebeenbroughtaboutin community processesby thetwo projectsunderreviewfrom thosethathavecomeaboutbecauseof the seriesof KDP andotherCDD interventionsin thecountry.'*However,both projects appear to havecontributedto enhancedcommunitydecisi.on-makingprocesses,but dueto traditional dominationby theelite,previoustop-downdevelopmentpractices,andwidespread corruption,muchremainsto bedoneto reachfully equitableparticipation.As notedby EG's recentevaluationof community-basedand-drivenapproaches,Bankstaff increasinglyare awareof theneedfor long-termsupportto buildcommunitycapacity.lgIn thiscontext,the criteriaunderKDP 3for selectingthosecommunitiesthathavereceivedsupportunderKDP 1 and2 is sensibleandwill likely contributesignificantlyto communitycapacityenhancement. Theevidencefor theenhancedprocessescomesfrom anumberof studiesandthemonitoring andfrom anecdotalreporting,andamix of inputandoutput/outcomeevidence.It includes\. l Increasingnumbersof recordedincidentsof spontaneouscommunitydemandsonthe administrationfor performanceandactiononcorruption,someof thisreportedby journalists.Thisincludesthereportingof about1,400casesof financialabuse,most in casesthatit is generallyagreedwouldneverhavebeenreportedin thepast. l Theuniversalcommunitypracticeof requiringthatsupplierspresenttheirquotations to thevillageatpublicmeetings. 0. Thegreaterinformationthroughprojectsignboards,accessbybeneficiariesto village projectrecdrds,andopenaccountabilityreportingmeetings. 16. Kecamatan Development Project Impact Study, 2001. The Demographic Institute, University of Indonesia. 17.The Region does not dispute the rating of this component but asks what would have been the alternative. IEG suggests that the alternative would have been simply shifting the funds into more grants and leaving income to arise from the infrastructure alone or just leaving out that component. The global experience is virtually unanimous on the efficiency and equity problems of pushing credit outside an effective institution in this way and some of that experience has come from countries where part of the justification at the time was some form of urgent need. . 18. The quality of the capacity building effort undertaken in year 1 and 2 for KDP is also a concern since the project was scaled rapidly. Year 1 covered 3,000 villages rather than the 1,250 anticipated at appraisal and year 2 rose to more than 12,000 villages rather than the 3,000-4,000 included in the original timetable. 19. The Effectiveness of World Bank Support for Community-Based and -Driven Development\. An OED Evaluation, 2005. l AttendanceatKDPmeetingsoftenreachedin therangeof 50to 100whenpast meetingsweresaidtohaveincludedonlyahandfulof theelite. l Evidencefrom theseverallocallevelinstitutionstudiesjointly supportedbythe WorldBankandBappenasthatfoundthatoldelitewerebeingreplacedin many villagesbymoreprogressiveindividuals.Thiswasassociatedwith thebroader decentralizationreforms. 0 Theincreasingnumberof women'sproposalsactuallyfunded. l Reportsthatwomen'sincreasedrolein KDP decisionshasspilledoverinto other communityactivities. l Theemergenceof participatorymonitoringbycomntunityteamsandevenvillager auditsin othervillages. 0 Improvedbookkeeping,management,andmonitoringcapacitiesthroughtraining. l Communitiesaccessingpilotprogramsin two provincesfor legalaidservices. l Increasednumbersof meetingsunderKDP recordedathamletlevelwheremuchof thesocialcohesionreallylies,asopposedto atvillagelevel(Box 1). Box 1. Village Community Structure and Functioning To understandthe challengeof enhancingparticipation of the poor in Indonesiait is important to understandsomethingof the community stru&ure,which is complicatedandvariesby area.The role of the Village Head is unclearon many facetsof responsibility.The main community social cohesiveness actually lies below the village level, at the hamlet level. The electedVillage Head is a government servant (screenedby the district government)and largely seen to be so by the community. His accountabilityfor public resourcesis similar to that of highergovernmentlevels,thoughhis (rarelyher) responsibilities are not always clear. The Village Head,while elected,has almost absolutepower at village level, but is subordinateto higher-level officials. Becoming a Village Head costs at least entertainmentmoney, if not a more direct buying of votes.Leadersat hamlet level areseenasmore relevantby their community. Thereareothervillage officersaswell (elected,but from amongcandidates chosenby the Village Head).A LembagaMusyawarahDesa, a committeecomposedpartly of village officers, channel community opinions to the Village Head and review proposals.Another committee, the LembagaKetahananMasyarakatDesa, provides a forum for discussionof developmentpriorities. (Thesearrangementsare changingwith new legislation.)Even Village Heads, who are ex-officio chairmenof the bodies,often find it difficult to distinguishthe roles of thesetwo bodies. There are also traditional leaders,often hereditary. Often, the hamlet headsare traditional leaders but they still have to be approvedby the District Head. There is also village religious leadership,sometimespowerful. Hamlets haveconsiderablede facto autonomyandmay only consult the Village Head when they really needto look outsidehamlet issuesor needresourcesthey cannot raise. SomeVillage Headsarenow openingtheir financial managementto community scrutiny,partly due to VIPKDP rules on disclosureandpublic notices.Under KDP, consultationsby facilitators on proposalswere held at both hamlet andvillage level, usually in the presenceof heads.Under KDP, although in theory an openprocess,in practice Village Headsand facilitators still had considerable influence over which proposalswere put forward to competewith the other proposalsat the intervillage kecamatanmeeting. 2.18 \. In VIP2, dueto thetypeof questionsin thesurvey,theImpactStudyoffersno quantitativeevidenceof communityprocesschangesattributableto theproject.However, missiondiscussionsin thefield andsignedlistsof attendeesandminutesof meetings confirmedthatprocesseshavehadsignificantparticipation,thoughstill somewhatlimited for womenandthepoorerhouseholds.Indeed,oneconcernistheamountof timethatthese processesdemandof beneficiarieswho atthetime of participationhaveno guaranteeof havingtheir investmentchoiceselected. 2.19 In KDP theImpactStudyattemptedto assesschangesin communityprocessesand householdwelfae. Thestudyfoundsurveyresponsesweregenerallypositiveandthatthe relativedifferencesbetweenKDP andnon-KDPprojectswerealsopositive,althoughmodest. Table1summarizessomekeyfindings,buttheseneedto beinterpretedwith cautionsincethe studymethodologywasproblematic.2oFirst,thebaselineandfinal surveywereonlyoneyear apart,givinglittle chanceto discernattributablechanges,particularlyin arapidlyevolving economiccrisisoverlaidondrought.Second,thesurveysattemptedto comptieISDPwith non- 20 .The Region in its comments alsodraws attention to the deficiencies in thb impact study. KDPprojects(innon-KDPareas),,butthereislittle evidenceof whatthesenonXDP projects were,in particular,whethertheywereotherdonorprogramsor governmentprogramsfollowing asimilarapproach(whichmanybythendid),orwhethertheyweretotallydifferenttypesof programs.SomemayevenhavebeenVIP2.In somecasestheywereprivatesectorprograms. ThesecontrolswereselectedbynonKDP communityleadersasbeingthebestprojectsin their.communityfor povertyimpact,makingthecomparatorunrepresentativeandsettingahigh barfor performance.Third,andperhapsmostimportant,with arandomsamplingof households acrossthewholevillage,manyhouseholdsinterviewedwerenot livingin hamletscloseto the particularinfrastructurein questionandthereforehadlittle interestin orknowledgeaboutit and little reasonto havebeeninvolvedin decisionmaking.21 Table 1. Selected KDP Impact Study Findings ... .... . . ____ ._ .__ Question KDP NonKDP % households who know of project 79 68 % households actively involved 45 42 % households involved in planning 13* 7 % households involved in execution
P045348 | National Agricultural Extension and Research Program Support Project | Western and Central Africa | Cameroon | Blend |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/235021475088654263/text/000020051-20140613035143.txt | http://documents.worldbank.org/curated/en/235021475088654263/pdf/000020051-20140613035143.pdf | Provision of grant-funding for productive equipment and infrastructure can fruitfully be combined with attempts to strengthen farmer organizations and boost incomes: in this case, the infrastructure provided helped to increase farmer solidarity while enabling them to increase farm output and revenues.It is both fiscally prudent and developmentally effective to move from a mass saturation (T in the long run, demonstration effects may encourage persons outside these groups to adopt new technologies. If the private sector and NGOs are to deliver extension services effectively there often needs to be some previous initiative to strengthen their financial and managerial capacities.
P045483 | Electric Power Reconstruction 2 Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/711151474650758725/text/000020051-20140607151818.txt | http://documents.worldbank.org/curated/en/711151474650758725/pdf/000020051-20140607151818.pdf | Coordination of project implementation should be centralized in one Project Coordinating Unit or Center when several entities of other regions of the country are in charge of the execution of project components. The location of the Project Coordinating Unit or Center should be made in accordance with the prevailing laws of the country. In the BiH project, the creation of a Joint Power Coordination Center (ZEKC) was a key action to resolve coordination problems and technical decisions among the three power companies implementing project components in different regions. This is particularly important when the project is financed by a large number of donors.
P045483 | Electric Power Reconstruction 2 Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2002 | 2004 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/102001468740692990/text/264720BA0PPAR.txt | http://documents.worldbank.org/curated/en/102001468740692990/pdf/264720BA0PPAR.pdf | 5. Findings and Lessons 5.1 The following findings emerge from the performance assessmentof these two projects\. l When electricity supply cannot be organized in a manner that is technically and economically optimal there are high costs to a country in terms of lost efficiency and economies of scale. l In the face of political obstacles, it may be slightly easier in electricity than in other sectorsto bring about greater trade across frontiers becauseelectricity is not a highly visible commodity and the presenceof power lines is no indicator of whether power is flowing or in which direction. However, BiH is probably unique in electricity being used to spearheadinternal political unification and nation building. The jury is still out on whether this tactic can succeed. l The Bank can deliver successful emergency reconstruction projects on a fast track basis, despite internal constraints that work against rapidity. 40. The Region pointed out that . .significant funds are required for the social costs and for the concurrent investments for the mines. The Bank is under tremendous pressure to be selective as the availability of IDA funds shrank from US$lOO million/year under IDA12 to US$30 &yr under IDA14. 41. The OED mission was not able to ascertain the views of the government of the Republika Srpska on this issue. l The Bank's current guidelines for emergency recovery projects do not explicitly indicate whether it is acceptable to not apply the Bank's usual environmental safeguardsto such projects for reasonsof urgency and speedof processing. 5.2 The experience offers two lessons of note\. l Power sector restructuring in a heavily coal-based power system cannot be delinked from reform of the coal industry becauseof the predominance of coal in the cost of producing electricity from it. Reforms in both sectors should be addressedin parallel, or preferably coal sector reforms should precede electricity, but not lag behind; l EPBiH's experience with tariff increases and improved revenue collection in the immediate aftermath of the peace accord, shows that consumers arewilling to contribute to the cost of the rapid restoration of electricity supply.
P045484 | Emergency Transport Reconstruction 2 Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Transport | IDA | IPF | 1998 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/766251474850800777/text/000020051-20140529210916.txt | http://documents.worldbank.org/curated/en/766251474850800777/pdf/000020051-20140529210916.pdf | The Bank has a comparative advantage in rebuilding the basic infrastructure of economies recovering from post-conflict situation.Project implementation in post-conflict situation should be managed by a special, highly professional unit like the "Project Implementation Directorate" as in Bosnia. This can be integrated into more established administrative system overtime.Emergency projects necessarily focus initially on restoring physical infrastructure. They should nevertheless be designed to promote economic recovery and gradually meet the long term institutional needs of the sector for the sustainability of sector operations.In emergency reconstruction projects as in all operations financed by the Bank, project design should incorporate explicit performance targets and arrangements to monitor and evaluate project achievement. Performance targets are important for tracking the project outcome.
P045499 | The Second National Drainage Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/799541468024592966/text/ICRR-Disclosable-P045499-06-10-2016-1465563498839.txt | http://documents.worldbank.org/curated/en/799541468024592966/pdf/ICRR-Disclosable-P045499-06-10-2016-1465563498839.pdf | The ICR containsfourteen lessons. The following threelessons are emphasized from the ICR with some adaptation oflanguage: The achievement of an objective that spans across the mandate of different agenciesrequiresa clear mechanism to coordinate activities and streamline operations among these agencies to ensure successful achievement ofoutcomes. The project experience showed thattackling environmental issues provedto be beyond the mandate ofthe implementing agency and more coordination with other institutions was required. Project design should berealistic and appropriate to the institutional capacity of the client, taking into consideration the qualifications and skills ofthe staff. The projects experience showed that the implementing agency proved to be less efficient inenvironmental and socioeconomic issues since most of the staff had an engineering background. Therefore, operations that requireexpertise outside the capacity of the implementing agency should have responsibilities well-defined; and risks and mitigationmeasures clearly identified. ME design should include key performance indicators that reflect capacitybuilding and institutional support especially when they arereflected in the objectives.The inclusion ofrelevant key performance indicators is essential to capture the impact of the the project; and the presence of these indicatorsmight be a factor that causes the implementing agency to give the deserved attention tothe associated activities evenif they are financed through parallel financing.
P045546 | Public Finance Structural Adjustment Credit (PFSAC) | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1998 | 1999 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/507391474596348334/text/000020051-20140529072420.txt | http://documents.worldbank.org/curated/en/507391474596348334/pdf/000020051-20140529072420.pdf | A participatory approach is invaluable, especially in post-conflict situations. Working groups and other detailed work programs can play an important role in bridging previously large differences. Well-targeted and well managed TA plays a key role in achieving such objectives. Intensive supervision and monitoring are essential - these projects are not cheap, but have a very high payoff.
P045546 | Public Finance Structural Adjustment Credit (PFSAC) | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1998 | 1999 | 2005 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/793831468740693918/text/31343.txt | http://documents.worldbank.org/curated/en/793831468740693918/pdf/31343.pdf | 5. Lessons When original design intentions for a quick-disbursing operationhave to be drastically reduced inscope, inthe face of practical and political difficulties, then this should give riseto areassessmentofthe whole operation, inparticular the credit amount, to ensure that there remains a relationship betweenthat amount andthepolicy adjustments being supported. 0 Providing general budget support into a situation where there i s virtually no auditing of, or accountability for, government expenditures i s unwise, inthe absenceo f a watertight, monitorableagreement with the borrower on the use o f those funds. Insofar as current IDApolicy i s not to concern itselfwith the use o f h d s inaquick-disbursing operation, then either that policyhasto change or IDA has to forego the provision o fbudget support insuch circumstances. Providingbudget support, inthe face o fmajor tax evasion and excessive government expenditures, can bepotentially counter-productive, inthe absence o f an agreed and concerted direct attack on those elements. Otherwise the presence o fbudget support reducesthe naturalpressure on governments to take urgent and meaningful action. Inasituationwherethereisnotclearborrowercommitmenttoacourseofaction, or there i s a history o fback-tracking or non-implementationo f laws and regulations, the mere passageo f legislationor promulgationo fregulations is not usually a good basis for tranche release conditionality. There also needs to be a periodo f implementationor, better, release conditionalitybasedon actual results achieved. Onany issue, includingmacro-economic andtax-related issues, IDA should maintain an independent position. Ifthere i s disagreement between IDA andthe InternationalMonetary Fund(&IF), IDA support shouldbe basedon its own assessment. 0 Inahighlychargedpoliticalatmosphere,progresscanbeachievedbybringing conflicting parties together for technical discussions, with IDA staff or TA consultants present. To be successful, however, it requires the involvement o f particularly empathetic staff, the careful choice andbriefingofTA consultants, andintensive supervision-all ofwhich happened under the two PFSAC operations andSOSAC. Inthese respects, these three operations represent good practice. When a long and complicated agenda o freforms i s needed and where future detailed actions can only be properly prescribedafter further discussions and developments on the ground, careful sequencing o f operations is required. This was done for PFSACandPFSAC2,to be followed bythe proposed Economic Management SAC; and for SOSAC,to be followed by the proposed SOSAC2. Such careful sequencing is another example o f goodpractice. By contrast, there was no immediate follow-up to TAC,compounding its poor design as a onetranche operation.
P045572 | CZECH REPUBLIC - Kyjov Waste Heat Utilization Project | Europe and Central Asia | Czechia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1999 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/376461474650583335/text/000020051-20140604054132.txt | http://documents.worldbank.org/curated/en/376461474650583335/pdf/000020051-20140604054132.pdf | (1) Future heat loads need to be carefully assessed for CHP plants so that, for maximum efficiency, the electric generation capacity of CHP is only as large as the available heat load allows. Moreover, a sufficiently high heat load is needed for the cogeneration of electricity at a CHP plant to be competitive with other sources of electricity.(2) While stakeholders with diverging objectives can come together in joint ownership and risk-taking on an attractive project, the ensuing compromises on prices in contractual arrangements can lead to its undoing, particularly in a dynamic energy market being restructured. A rigorous assessment of likely future changes in the structure of the energy sector and energy prices must be undertaken at project design to better understand the risks that these changes might pose to the project.(3) Early testing of waste heat boilers should be undertaken as soon as possible to detect any technical problems arising from industrial processes. In this case, delays in the start-up of the waste heat boilers occurred as technical problems were encountered from the intake of huge amounts of particulate matter from the glass production furnaces into the boilers.
P045576 | GZ-EMERGENCY REHAB. II | Middle East and North Africa | West Bank and Gaza |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 1996 | 1999 | 2000 | ICRR |  | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/615321474897907038/text/000020051-20140526230223.txt | http://documents.worldbank.org/curated/en/615321474897907038/pdf/000020051-20140526230223.pdf | There are two broad lessons. First, emergency assistance projects require good judgments and flexibility of response to quickly changing circumstances, including cases where prior information proves flawed or simply does not exist. This means that project staff, in the Bank and on the ground, must be able to monitor the projects in order to learn quickly to modify behavior appropriately. Second, good dialogue with the borrower, its organizations, and, especially, with the direct beneficiaries throughout the project, makes crucial contributions to project success.
P045588 | PUB. FIN. MGMT. TAP | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1997 | 2004 | 2005 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/519111474586863455/text/000020051-20140612134750.txt | http://documents.worldbank.org/curated/en/519111474586863455/pdf/000020051-20140612134750.pdf | 1. As noted in the ICR, the project confirms the need of sufficient attention to institutional issues at the initial stages of project design, noting that the project lacked a clear vision, and lacked adequate attention and agreement from the start of the project as to how technical support arrangements were to be organized and their migration through implementation of ongoing maintenance was going to be achieved. 2. Project design needs to take adequate account of implementation capacity and borrower ownership. A simpler project focussing on core reforms fully endorsed by the government would have been more appropriate in this case.
P045600 | States' Road Infrastructure Development Technical Assistance Project | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/673861474652237633/text/000020051-20140607152249.txt | http://documents.worldbank.org/curated/en/673861474652237633/pdf/000020051-20140607152249.pdf | Technical assistance is most effective in supporting policy and institutional reforms when these reforms are linked to future investment support. The Bank's transport network does not have a sufficiently good, objectively verifiable and practical set of performance indicators for institutional reform. More resources could be devoted to the development of such indicators to better measure the impact of projects or their components designed to address institutional constraints.The Bank needs to seek ways of reducing the time frame of project preparation without compromising quality and preparedness at Board approval. Different lending instruments for infrastructure investment such as an Adaptable Program Loan may be an option.
P045600 | States' Road Infrastructure Development Technical Assistance Project | South Asia | India | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1997 | 2002 | 2007 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/455641468035340540/text/38108010REPLACEMENT.txt | http://documents.worldbank.org/curated/en/455641468035340540/pdf/38108010REPLACEMENT.pdf | 5. Lessons Learned 5.1 The following lessons may be derived from this project\. The risks of multi-state projects shouldbecarefilly assessedduring preparation, especially due to the greater complexity o f supervisionrequired. The commitment ofthe central government implementingagency andthe possibility for the Bankto supervise the project from the country office are two keyways to minimize such risks. Systematic exchanges o f information duringimplementationamongthe participating states shouldbepart o fthe projects' design. Entry conditions requiringcommitment to reforms are usefulwhen such commitments are formalized vis-&vis o fboth the central government andthe Bank;the states aremore likely to agree to such commitments iftheyperceive arealistic expectation o f receivingfbnding from follow-on projects. Resettlement and rehabilitation policies are an issue which can cause conflict especially instateswhich are confrontedwith Bankregulations for the first time.A more intense Bank effort is advocatedto discuss the rationaleof such regulations with local officials at the outset andto the extent possible, endeavor to adapt the application o f such regulations to local conditions where possible.
P045622 | COAL IAP | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1996 | 2004 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/668211474561799572/text/000020051-20140607152334.txt | http://documents.worldbank.org/curated/en/668211474561799572/pdf/000020051-20140607152334.pdf | Complex reform programs in difficult economic and political environment require time and flexibility;Government commitment and political will, and effective stakeholder participation are crucial in undertaking complex and politically contentious reform programs; and Field office staff can play an important role in ensuring the success of a major reform program through effective day-to-day management of operations.
P045628 | Transmission, Distribution and Disaster | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2007 | 2008 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/417221475079845119/text/000020051-20140618090150.txt | http://documents.worldbank.org/curated/en/417221475079845119/pdf/000020051-20140618090150.pdf | The ICR offers lessons from project design and implementation.The lesson from project design is:"Smarter" tariff covenants should focus on inducing actions to achieve good performance, including cost-cutting, and open a range of options for both the Bank and the Borrower, instead of relying on heavy sanctions. While trariffs should be set at proper levels, the approach of scheduling progressive increases to reach an agreed tariff level does not appear to have been successful. Issues can arise that level and timing may have been set incorrectly and country/sector circumstances may have changed, making the original agreements difficult to implement. In lieu of tariff covenants, the Bank and the Borrower could focus instead on financial performance, which could offer a range of options including to cut costs. Agreement on a tariff methodology which could minimize or remove the political dimension to tariff setting, which would serve as the basis for regulators to agree on tariffs. The financial performance targets would still be covenanted, but they should not be formulated as 'all or nothing' actions for which suspension is the only outcome for non-compliance. More nuanced covenants, for example, by applying interest rate or grace period penalties for the time that the covenant is breached, may be more effective at sustaining the dialogue while providing a clear incentive for action.The ICR's lessons from implementation are:Project preparation needs to provide better cost estimates and demand forecasts. The cost estimates used at appraisal were evidently flawed, and, notwithstanding the price decreases resulting from the East Asian financial crisis, could have been developed using more up to date information and a more realistic basis. Demand forecasts, which affect the sizing of equipment (and thus the cost estimates) are risky in a system that is growing as rapidly as in Vietnam.Delays in taking action had high costs and should be minimized or avoided. Early and decisive action to deal with slow project implementation and costs savings is essential. Failing to do so sends mixed signals to the Borrower (and to some extent within the Bank itself) and threatens the project's value. No one benefits from putting off action, however hard the choices may be. Pilots can be useful low-risk market tests. A positive lesson is the way in which the piloting of DSM was used to assess interest and capacity. This enabled it to be scaled up to a standalone project later, thus reducing risks while learning important lessons about how best to design the project. Several other aspects of the dialogue have also been developed into subcomponents in other projects, and this technique appears to work well in Vietnam.
P045628 | Transmission, Distribution and Disaster | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2007 | 2014 | PPAR | >=100 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/217991468329657329/text/885430PPAR0P040C0disclosed060240140.txt | http://documents.worldbank.org/curated/en/217991468329657329/pdf/885430PPAR0P040C0disclosed060240140.pdf | 5. Lessons In supporting the sector to move towards long-term financial viability and fiscal sustainability, the Bank should lay primary emphasis on broader institutional and policy measures for cost recovery. In contrast, specific target-oriented and timebound measures in the form of tariff or financial performance covenants carry excessive political implementation risks and are prone to noncompliance by the Borrower. Despite a number of financial performance measures that were included in their design, the three Bank operations were not effective in helping improve Vietnam's power sector finances, let alone place the sector on the road to sustained financial recovery. Considering this experience, the Bank should have pushed for a more systemic solution to the sector's long-simmering financial crisis through the introduction of a sound tariff methodology to ensure sustainable cost recovery and the power sector's future operational/financial sustainability, while making the sector more attractive to much-needed external private finance. A national push for universal electricity access provision will primarily depend upon the pursuit of a least cost path for grid expansion backed by appropriate sector policies, complemented by off-grid electricity in the interim or for the longterm as needed. In Vietnam, as the electricity grid expanded faster than expected, the decreasing necessity and relevance of off-grid electrification was not adequately foreseen, resulting in some off-grid facilities falling into disuse or neglect. This experience points to the need for planning ahead, and making technical provision for integrating off-grid and mini-grid facilities with the grid when it arrives, so that the expected benefits are realized from the investments. Rapid growth in electrification can be accompanied by sub-optimal use of electricity especially in a situation of relatively low or subsidized tariffs. This calls for early and serious policy attention to improving Energy Efficiency and implementation of dedicated Energy Efficiency operations on a sizable scale. The evidence shows that the Bank's program has essentially provided a supply-side support program for Vietnam's power sector, largely following demand, as the GOV has done, with less attention to demand side management. The marginal Bank-supported Energy Efficiency efforts (typically a small demand side management-style component under various power sector operations) has not been effective in to making a material difference to the Energy Efficiency landscape, let alone nationwide scale-up. The Transmission Distribution sector â€“ continues to play catch-up with increasing demand which needs to be moderated through appropriate measures including tariffs that better reflect cost-recovery levels. The extremely large reservoir of untapped Energy Efficiency opportunities calls for the creation of a solid framework for energy-saving efforts, including sizable programmatic support for Energy Efficiency, extending well beyond the piecemeal approach applied to date. The Bank should work to develop an understanding with client countries over the role of key institutions before embarking on full-fledged support for them. Otherwise, weak understanding might result in less than desirable institutional performance and sub-optimal use of technical assistance resources. In Vietnam, the Bank should have pushed for agreement on a more autonomous professional regulatory agency, before committing to a large amount of capacity building support to ERAV. In the absence of serious support from the Government in this respect, ERAV's regulatory role has weakened somewhat over the years, and some of its resources have been diverted to non-regulatory type activities (e.g., administration of the competitive generation market) instead of focusing on core regulatory activities such as tariff methodology and quality-of-service regulation, monitoring and enforcement. While ERAV's overall technical competency may have improved over the years with sustained support from the Bank, the outcomes from its efforts are weak â€“ sector finances continue to deteriorate, and the quality and reliability of electricity service for consumers has seen a downward trend in recent years. In a rapidly evolving sector environment, a de facto flexible approach should be adopted to adjust to changing priorities as well as new institutional and on-theground developments. Even if the changing situation could not be foreseen at the project design stage, such an approach would enable more smooth and successful implementation of the project. This aspect is illustrated in all three projects and particularly in the SEIER project where both the Bank and Borrower responded to changed circumstances through project restructuring to allow flexibility for investing in subprojects that took on greater priority. The project M&E framework should focus on identifying the direct causal links between project interventions and outcomes to the maximum extent possible. This is particularly important, albeit challenging, in large and rapidly evolving sector context in which Bank-supported interventions only partially influence but do not determine overall outcomes. In addition to being unnecessarily complicated with too many performance indicators, several key outcome indicators related to improved T&D reliability and efficiency were defined at the national system level, which made an accurate outcome assessment for the T&D component largely impossible or tentative at best under the TDDR and SEIER projects. While they are usually more challenging to design, in similar situations project-level indicators or appropriate proxies should be used for the relevant project areas. The community's involvement in the design, construction and operation of new rural electricity supply networks, and cost-sharing can lead to successful implementation and a sense of ownership. Ensuring local participation in all aspects of the project helped mobilize and maintain local support and commitment to rural electrification, while ensuring a rapid pace of the process, creating employment, building local capacity and thereby laying the foundation for the sustainable management and operation of the networks. Significant cost sharing by local governments and the communities was an important element of the Vietnamese financing model for rural electrification. Mobilization of local funds was essential to close the funding gap. This requires appropriate mechanisms and enabling institutional and legal frameworks, not only at national, but also at local levels.
P045629 | URBAN WATER SUPPLY PROJECT | East Asia and Pacific | Cambodia | IDA |  | Sustainable Development | Water | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/974671474946168964/text/000020051-20140613042652.txt | http://documents.worldbank.org/curated/en/974671474946168964/pdf/000020051-20140613042652.pdf | 1. When it is already clear at preparation that participating entities will not be given autonomy by the government, for the Bank to repeatedly request that they be given autonomy may not change things much. Exploring more realistic avenues, such as simple management contracts, may solve important aspects of the problem.2. Delays in project implementation can be reduced if, before start-up, key personnel can be provided assistance and training in Bank policies and procedures.3. Twinning arrangements must take place as much as possible in parallel with project preparation and be based on TORs prepared by the Bank.4. Critical ingredients for success as revealed by this project's experience include: seminars that raise awareness of best practices; continuity in the Bank team; a well-thought out TA strategy developed with borrower consultation; borrower ownership; and strategic Bank support (whether in the form of conditionality, covenants or advice) to overcome bureaucratic apathy and help local staff to resist political influence.
P045631 | Financial Sector Technical Assistance (TA) Project | Europe and Central Asia | Kyrgyz Republic | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1996 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/672791475084183398/text/000020051-20140607161913.txt | http://documents.worldbank.org/curated/en/672791475084183398/pdf/000020051-20140607161913.pdf | In an environment in which grant funding is abundantly available, a Borrower may be disinclined to borrow for TA or consultant servicesFor a Borrower with highly constrained budgetary resources, a TA project should make provision for subsequent O&M costs for IT upgradesA thorough assessment of PIU capacity to manage a complex procurement program should be conducted, and capacity strengthened during preparation if necessary, so that program implementation can begin soon after effectiveness.
P045644 | Post Conflict Social Reconstruction Project | Eastern and Southern Africa | Angola | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/129771474509142597/text/000020051-20140612070650.txt | http://documents.worldbank.org/curated/en/129771474509142597/pdf/000020051-20140612070650.pdf | Resettlement is a gradual process. The project experience shows that initially male members would commute back and forth between their areas of origin and areas of dislocation. Once the basis of families â€œlivelihoodâ€ is established, the entire family would move. The primary need identified by resettling families is food security. While the goal is for communities to attain food security through community-based agricultural production, it is crucial that returning families have access to adequate food rations as they await the harvest of their first crop. Emphasis needs to be placed on the special needs of the very large number of female-headed households and orphaned children.Close coordination is required with other externally supported initiatives and line ministries to improve access to health, education and other basic services. The roles and responsibilities of NGOs, communities and local governments need to be clearly defined and fostered through meaningful capacity building, close collaboration among actors, and mentoring. Careful screening of NGOs is crucial to ensure cost effective project implementation. It may be more effective to contract the services of several NGOs in their particular areas of specialization, rather than choosing a single NGO per municipality. In addition, up-front training is required to ensure that implementing NGOs have a clear understanding of financial management and reporting requirements to ensure timely disbursement.
P045676 | Jordan - ERDL III | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2000 | 2002 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/282021474491101306/text/000020051-20140602111305.txt | http://documents.worldbank.org/curated/en/282021474491101306/pdf/000020051-20140602111305.pdf | Changes in the incentive regime are a necessary, but not a sufficient condition for efficient and rapid economic growth. Linking rapid growth to these policy changes in a short CAS period gave rise to expectations that could not be fulfilled. An analysis of sources of potential growth for Jordan and advice on how to develop these prospects might have permitted reforms to be sequenced to emphasize sectors with growth potential. This would have bolstered belief in the benefits of the incentive changes, and softened the blow of job losses when uncompetitive sectors declined.
P045676 | Jordan - ERDL III | Middle East and North Africa | Jordan | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2000 | 2001 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/366891511185568183/text/multi0page.txt | http://documents.worldbank.org/curated/en/366891511185568183/pdf/multi0page.pdf | 5. Lessons The main lessons from ESAL and ERDL 1-111 are\. * Changes in the incentive regime are necessary but not sufficient conditions for efficient and rapid economic growth. Linking rapid growth to these policy changes in a short Country Assistance Strategy period gives rise to expectations that may not be fulfilled. As a consequence, policy makers in borrower countries, and the policy reforms themselves, become politically vulnerable. That vulnerability could result in the government being voted out of office at the next elections. * Sequencing reforms to emphasize sectors with growth potential, such as exports, at the beginning would bolster belief in the benefits of the incentive changes and soften the blow of job loss when uncompetitive sectors begin to decline. It would also bolster private sector confidence and encourage investments that are internationally competitive. * A resident mission and timely and substantial technical assistance are crucial for the successful implementation of complex reforms involving several government agencies, new institutions and laws. The subsidiary lessons from ESAL and ERDL I-III are\. * Government ownership of reforms and political consensus for some sensitive reforms such as privatization are crucial for project success. It is advisable to assist in developing political consensus rather than pushing for early implementation. * In complex and wide-ranging policy programs that require substantial legal and institutional change, confining conditionality to core activities would increase the prospects for successful implementation. * Institutional change, especially when full consensus has not been reached, tends to take a long time, usually longer than expected by Bank staff. These delays should be factored into project design. * Series of single tranche operations that are disbursed after agreed reforms are implemented offer flexibility for reform programs with uncertain time lines.
P045687 | AR-Health Insurance TA | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1996 | 2001 | 2003 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/719571475073179365/text/000020051-20140607160749.txt | http://documents.worldbank.org/curated/en/719571475073179365/pdf/000020051-20140607160749.pdf | Policy and regulatory reforms, even when successfully adopted (such as competition between insurance Funds) may not lead to the expected outcomes. Similarly the technical content of planned reforms may be significantly altered by lobbying from various interest groups, effectively undermining their intended objectives. As with the Provincial Health Sector Reform Project to which this one was linked, there was misjudgment of political commitment, and efforts to build stakeholder support were insufficient.
P045788 | CN-Tri-Provincial Hwy | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/673351474564561355/text/000020051-20140618085747.txt | http://documents.worldbank.org/curated/en/673351474564561355/pdf/000020051-20140618085747.pdf | 1. The Bank can manage projects that cover areas (provinces) with different levels of socioeconomic development and professional capacity. The key is to have good performance indicators, focus on the objectives, and be responsive to the clients' needs and levels of competence.2. Success in infrastructure projects is strongly dependent on client motivation. In the Tri-provincial Highway project the clients, the provincial communications departments, were highly motivated to succeed. They learned from mistakes, adjusted to changes--for example resulting from weather-related setbacks--and implemented the (planned) project on time.3. Successful projects, like the China Tri-provincial Highway project, are an experiential learning opportunity. The increased economic activity, whether resulting from this or other projects in affected areas, the reductions in accidents, the competence to deal with large projects and related environment and resettlement issues, gave an incentive and confidence for the participating provinces. They have embarked on their own initiative on new road construction and rehabilitation works for all road classes. The socioeconomic benefits and reductions in poverty from them are likely to be substantial.
P045788 | CN-Tri-Provincial Hwy | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2007 | 2009 | PPAR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/661891468262751670/text/489660PPAR0P041C0Disclosed071171091.txt | http://documents.worldbank.org/curated/en/661891468262751670/pdf/489660PPAR0P041C0Disclosed071171091.pdf | 7. Conclusion and Lessons 7.1 The Bank's lending to China's highway sector continues to deliver some important benefits. The value of the Bank support lies less, however, in the actual loans (which are a tiny percentage of the country's total transport investments), but more in the form of less quantifiable benefits such as the best practice application of safeguard policies and the development of road management methodology through studies, advice and training. In the projects reviewed in this PPAR the inclusion of the rural road components also over time may help to unlock the potentially substantial benefits that can come from improving rural access by contributing to the debate about how jurisdictional and funding issues can be overcome. According to several officials interviewed by the IEG mission, the Bank has had a very useful and even transformational effect on motivating local transport sector professionals to think out of the box. From this overview come four lessons\. It is important to ensure during project preparation that the mandate of the implementing entity is consistent with the scope of the project. The implementation of the two highway projects in China proved unexpectedly challenging because the implementing entity had no jurisdiction over the rural roads and the traffic safety components. A middle income country can still benefit substantially from the Bank's technical assistance and expertise. The provincial officials involved in these major highway projects learnt quickly from the experiences from the training programs, study tours and advice from Bank staff. In respect of safeguards policies there was ample evidence of a movement from a compliant paradigm to one in which society was better off because of the intervention. Technical expertise was also passed on in respect of inter alia road maintenance by contract, expressway management, and good practice in road safety. Some adjustments in the scheduling of safeguards procedures could be considered. The completion of the full Resettlement Action Plan before the preliminary engineering highway design was completed wasted scarce resources as it had to be re-done because the road alignments changed significantly. Since the gap between safeguard policies in the Bank and China on highway projects is now quite small, good supervision is the key to ensuring that the policies are followed. In China, at least in the provinces where the projects were assessed, performance-based project lending has sufficed in respect of safeguards, but the application of the country systems with periodic supervision by the Bank could be contemplated.
P045820 | Emergency Industrial Restart Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 2004 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/870951474897951474/text/000020051-20140613050613.txt | http://documents.worldbank.org/curated/en/870951474897951474/pdf/000020051-20140613050613.pdf | 1. There needs to be clear demand-based assessments done before launching a credit insurance operation. In the context of support for an emergency operation under OP/BP 8.50, this project was an appropriate response. However, the short timetable in which to prepare the emergency operation did not fit well with the time needed to undertake broad demand-based assessments. 2. The ICR concludes that the IGA should have been given the authority to insure commercial risk, besides the non-commercial risk that it was insuring. OED concurs with this view.
P045864 | 4M-MEKONG WATER UTILIZ. | East Asia and Pacific | Viet Nam, Cambodia, Laos CMU |  |  | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2000 | 2008 | 2013 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/641311474492235787/text/000146597-20140619165326.txt | http://documents.worldbank.org/curated/en/641311474492235787/pdf/000146597-20140619165326.pdf | Consensus building through dual/parallel track approaches to forge agreements on various technical matters is critical for transboundary organizations. In the case of the MRC, the four countries differ in terms of geographical location (upstream/downstream) as well as the level of the development; therefore, the demand for the water resources development differs between them. The formal negotiation pursued by the project often encountered difficulties as the member countries did not always understand each other's positions. This process might have been improved had the project included informal meetings with additional stakeholders to establish a deeper understanding of the different needs of each country and promote consensus. Only after this should formal meetings have taken place. In an international river organization, the quality the staff in member countries is crucial factor to ensure ownership and sustainability and technical outputs need to be met with adequate human resources. Technical assistance alone cannot attain improved water utilization and better environmental management. The project was successful in producing important outputs for the functioning of the MRC and success of a water resources management plan. It did not, however, include a dedicated plan to increase the capacity of human resources within the MRC countries to better facilitate communication and coordination between the line ministries in each member country and the MRC.A better communication strategy to the stakeholder regarding the application of the hydrological models and water utilization procedures is important to solidifying outcomes. The progress and final outcome of the water utilization procedures should have been disclosed and disseminated not only to the line ministries, but also to the riparian communities and local governments which were directly affected by the procedures. Action at the community level (i.e. investment and capacity building) is also critical to effectively coordinate water resource utilization and prevent or mitigate conflicts among stakeholders.
P045864 | 4M-MEKONG WATER UTILIZ. | East Asia and Pacific | Viet Nam, Cambodia, Laos CMU |  |  | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2000 | 2008 | 2012 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/124231468051012766/text/703320PPAR0P040Official0Use0Only090.txt | http://documents.worldbank.org/curated/en/124231468051012766/pdf/703320PPAR0P040Official0Use0Only090.pdf | 8. Lessons Â· The development of a Decision Support Framework to assist Mekong countries make more informed decisions about water resource management has demonstrated the opportunities and limits of bringing scientific and technical innovation to bear in an environment fraught with political economy constraints. The premise that water resource management decisions could be based on scientifically determined acceptable levels of water flow and quality and that subsequent modeling could be used to evaluate Basin proposals in line with a minimum set of flow and quality criteria proved to be too constraining. Rather, the models have been used to determine the winners and losers of proposed basin development and subsequent negotiations have focused on individual, rather than collective interests. Â· Human Resource development at the national level is critical for the effective implementation of international and regional water resource agreements. Participating nations require strong water expertise. Donor programs that seek to support effective implementation of water resource agreements at the international and regional level should consider how to support skills enhancement and training of water engineers, hydrological experts, water resource planners, and social and environmental specialists correspondingly at the national level.
P045910 | HEBEI URBAN ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/482411474502964293/text/000020051-20140619105517.txt | http://documents.worldbank.org/curated/en/482411474502964293/pdf/000020051-20140619105517.pdf | High caliber management capacity in central project management offices can help ensure that policy changes are executed.Knowledge sharing can be successful and an important product of the project when it has strong central government backing.Solid technical inputs, particularly in engineering, are essential for a project like this to succeed.Analysis of water pollutants should be based upon the sampled collection of empirical data. Theoretical parameters, as used commonly by design institutes in China, do not provide the correct inputs for the analysis that is needed.Financial covenants regarding the performance of project implementation agencies should be realistic and only cover those aspects of financial performance that are relevant to the project outcomes.
P045915 | Urumqi Urban Transport Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/342041474851794771/text/000020051-20140619082532.txt | http://documents.worldbank.org/curated/en/342041474851794771/pdf/000020051-20140619082532.pdf | 1. There is a need to develop performance indicators for urban transport and can be measured regularly. There appears to be a disconnect between the Bankâ€™s requirements for measurement of outcomes, and the clientâ€™s interest in outputs and the capacity to measure both. Task teams would benefit from constructive guidance and development of a relevant and straightforward set of indicators that are parsimonious, comprehensive and measurable regularly (by the borrower). Indicators should also be robust to exogenous factors to ensure that they meaningfully reflect the outcomes and outputs of the project.2. Project components and schedule must be cognizant of a â€œlearning curveâ€ in development and structure institutional capacity development accordingly. For a first-time borrower, like Urumqi, the Bankâ€™s fiduciary and safeguard requirements can be a challenging prospect. Urban transport projects are usually complex, with features prominent on government's agenda, and with multiple components that are implemented sequentially. The challenge is to design projects that do not overwhelm, but complement the borrowerâ€™s gradually improving implementation capacity. One approach, whenever possible, is to integrate the development of corridors with road, public transport, environmental management, safety and traffic management investments starting with the simpler subcomponents. There needs to be recognition that institutional competence evolves and that physical and institutional components may progress at different rates.
P045937 | Atlantic Mesoamerican Biological Corridor Project (GEF) | Latin America and Caribbean | Panama | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/296661474586814265/text/000020051-20140613085713.txt | http://documents.worldbank.org/curated/en/296661474586814265/pdf/000020051-20140613085713.pdf | Integration of indigenous people in the design and implementation of project activities can have an appreciable impact on project success. Given that indigenous peoples generally occupy some of the best lands for biodiversity conservation, it is critical to ensure their full participation in determining how biodiversity is best conserved.A common weakness of projects providing small grants for productive investments is the lack of attention to marketing issues as part of subproject design, and of technical assistance to beneficiaries to address these challenges during implementation. Many organizations benefiting from subprojects in this project were ill-equipped to face these challenges.In GEF projects with a community driven development subprojects component, the potential and actual contribution of these subprojects to the conservation of biodiversity of global importance needs to be better analyzed ex-ante and measured ex-post. Furthermore, the targeting of certain types of subprojects to locations where they could make the best contribution, needs to be considered.
P045940 | Social Protection Support Project | Europe and Central Asia | Ukraine | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 2000 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/890961475099968036/text/000020051-20140529163223.txt | http://documents.worldbank.org/curated/en/890961475099968036/pdf/000020051-20140529163223.pdf | (a) This is a project in which the Bank appears to have fruitfully built upon the relationship which a bilateral donor had already established with the line ministry and designed a project which required a great deal of specialized technical assistance which the bilateral donor continued to provide. It is a model worth emulating where feasible.(b) Broad policy goals should not be included as objectives in the project monitoring indicators because there is a very low probability that they will be achieved and the Bank has almost no means of exerting pressure on a government to achieve the objective.(c) While the project had a relatively short implementation period, it would have been useful to carry out the impact evaluation at an earlier period and perhaps at two different times during project implementation.
P046006 | CONTRACT. SAVINGS II | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 1999 | 2000 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/202761474903604938/text/000020051-20140526232555.txt | http://documents.worldbank.org/curated/en/202761474903604938/pdf/000020051-20140526232555.pdf | 1. Single tranche operations are useful tools, and reduce risks of delays; they also can be better tailored to suit the pace of reform that works for the client.2. Pension reform is complex and highly technical; each phase of the reform process highlights new constraints that may not be apparent at the outset.3. Reform of a highly politicized institution requires more than technical solutions or even government commitment. INFONAVIT is important to a number of politically important interest groups. Thus, in spite of strong government commitment to reform INFONAVIT political interests prevented effective reform. 4. As noted in the ICR, both strong government commitment and continuity of a strong Bank staff team helped ensure the success of the reforms.
P046006 | CONTRACT. SAVINGS II | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 1999 | 2001 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/597561511189121582/text/multi-page.txt | http://documents.worldbank.org/curated/en/597561511189121582/pdf/multi-page.pdf | 10. Findings and Lessons 10.1 The main finding is that, with respect to all but a few (important) elements, the Mexican pension reform program has been successful and should consequently be given high marks. However, among those few problematic elements have been the failure to achieve certain critical objectives (i.e., lack of progress in fundamental INFONAVIT reforms and inability to loosen restric Lions on SIEFORE investments) which can endanger the whole reform process. Other shortcomings, especially in the inability to expand coverage significantly and to implement some of the important complementary reforms elsewhere in the financial sector, continue to impede realization of many of the benefits of pension reform. 10.2 One lesson of this experience is that single tranche operations can be more effective, efficient, and realistic instruments for providing timely balance of payments support than multi-tranche operations. A series of single tranche operations allows the reform process to proceed at the pace determined by the client country, rather than by the tight time-frame required for multi-tranche adjustment loans. 10.3 The newness and far-reaching complexity of pension reform made it particularly attractive to use a series of single tranche operations for technical reasons\. as pension reform unfolded, important details of certain technical issues that were not originally obvious became clearer over time. The need under CSDP-II for fine-tuning the regulatory infrastructure and for paying more attention to certain complementary developments in the financial sector (e.g., improved provision of annuities and insurance services, development of new financial instruments, expanded infrastructure such as rating agencies and custodial services, etc.) are clear examples of this. However, single tranche operations can also increase the temptation to postpone essential reforms that face political barriers from the first operation to later ones. At the time CSDP-I was undertaken, it was possible to overcome seemingly major political obstacles and initiate the pension reform process in Mexico with a considerable degree of success. By the time of CSDP-II, with the worst of the financial crisis past, the momentum to overcome such political obstacles may have been lost. Nevertheless, on balance, the advantages of single tranche operations outweigh their disadvantages. 10.4 The other lesson on pension reform is its far-reaching complexity and the need for major complementary financial sector reforms in order for the benefits of pension reform to achieve their full potential. As emphasized above, great progress has been made in the Mexican case in the design and implementation of the regulatory regime and in providing crucial infrastructure that allows pension contributions to flow quickly and accurately to the proper individual account and for this information to be immediately available to the regulatory body, CONSAR. As witnessed by the earlier Mexican experience with pension reform under SAR92, failure to provide this seemingly mundane infrastructure can undermine the entire activity and cause on-going problems that can take years to resolve. 10.5 With respect to complementary reforms in the financial sector, the Mexican experience suggests four lessons\. (1) pension reform benefits will be incomplete unless individuals in the pension system have access to attractive complementary annuity and insurance products; (2) the array of instruments available to pension fund managers must be expanded to include those that are long term, but have reasonable liquidity and risk profiles, something not quick and easy to achieve when there was no market for such instruments before pension reform; 16 It is also important to note that, at the same time the pension reform process was able to move ahead, the operation to resolve the banking crisis met with great difficulties. Thus, even with a multi-tranche operation, the political obstacles to pension reform might not have been overcome. (3) the array of risk and return options available to individuals will not be on the efficient frontier unless the regulatory regime focuses on portfolio risk rather than on the risks of individual securities; and (4) pension reform benefits will be greatly reduced if the government directs the investment of pension funds to specific institutions or sectors (e.g., INFONAVIT) and/or prohibits investments that are essential for constructing portfolios with optimal risk-return profiles (e.g., prohibition of investments in foreign securities). 10.6 Two final lessons come out of the Mexican experience that may also be generalizable to pension reform elsewhere\. (1) An important objective of pension reform is to expand coverage, particularly to government workers and workers in the informal sector. It may be more difficult to incorporate government workers later in the process as their benefits may need to be adjusted downward or those of private sector workers upwards to reach equality at a later date (with major fiscal costs that are more difficult to deal with when they come as later surprises). In addition, concerted efforts would be required to bring informal sector workers into a pension system, by both the government in carrying out a public awareness campaign of the long-term benefits of pensions, and by private pension providers to actively seek out these workers as clients. (2) Mexico and many other developing and transitional countries are subject to substantial country risk premiums. This results in high real interest rates which mean that domestic debt instruments offer more attractive returns than foreign ones. At the same time, many grade A borrowers have access to funds in foreign financial markets on attractive terms, and thus are unlikely to issue higher real interest rate instruments in domestic markets. This makes reforms to reduce country risk very important for pension reform. Otherwise, pension fund investment managers are likel y, regardless of the regulatory regime, to see government debt instruments as the only logical choice, so that they fail to gain much portfolio management experience. Under such circumstances, moreover, pension reform becomes a more roundabout, and likely expensive, way of financing the government's debt.
P046031 | MAGDALENA MEDIO REGIONAL DEVELOPMENT PROJECT | Latin America and Caribbean | Colombia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/631391474571725428/text/000020051-20140604043405.txt | http://documents.worldbank.org/curated/en/631391474571725428/pdf/000020051-20140604043405.pdf | 1. Community based participatory approach works well even in a conflict-prone area when the change agent (the Consortium) is trusted by all sides.2. Individual and community participation in decision making requires a well specified mechanism (here, the nucleus of the citizens' network).3. Any model specifically tailored to local circumstances cannot be copied or "scaled up" easily. Consequently, M&E must be built in carefully each time.4. Despite M&E, external evaluation is useful because it provides a structured way to re-assess developments and lessons.
P046042 | Irrigation Rehabilitation Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 1998 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/817621475099014613/text/000020051-20140617132637.txt | http://documents.worldbank.org/curated/en/817621475099014613/pdf/000020051-20140617132637.pdf | 1. Rehabilitation of irrigation networks and dams needs to be planned and implemented within a whole systems water management approach based on hydrological units. The project was considered a high priority, needing rapid rehabilitation of works across as many schemes as possible. Inadequate time to do a hydrologically based detailed plan for each scheme on a whole-system basis, sometimes resulted in piecemeal rehabilitation, with lower impact than would have been the case had an integrated water management approach been taken.2. Mechanisms and buy-in for adequate funding of maintenance need to be built into an irrigation rehabilitation project. The reason for the IRP was to rehabilitate irrigation schemes and dams that had deteriorated as a result of past inadequate funds for maintenance. At least an overall maintenance plan could have been prepared by the government, and specific plans prepared for each scheme, formally agreed to by users as part of the preparation work for each scheme.3. A simplified project objective need not be at the expense of dealing with broader issues in a sector-wide perspective. The project was deliberately narrowly focused to deal with an assessed urgent need. The ICR comments that - through several studies, interaction with government during IRP supervision, and preparation/implementation of other water sector projects (the On-farm Irrigation Project and the Water Management Improvement Project) - a broader policy dialogue and action program was nevertheless enabled.
P046043 | Rural Enterprise Support Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2002 | 2008 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/704701474491949362/text/000146597-20140619151812.txt | http://documents.worldbank.org/curated/en/704701474491949362/pdf/000146597-20140619151812.pdf | The ICR notes: Project components that are intended to facilitate access to credit should provide customers with a broad menu of investment categories and financial products. This will broaden the range of customers and encourage portfolio diversification, helping rural clients manage risks more efficiently and enter into new profitable activities.The rehabilitation and operation of irrigation and drainage schemes should be adequately funded (to ensure that the works have a long life) and the priorities for rehabilitation, sequencing of the work and contracting arrangements should involve close consultation with Water User Associations. The designers of projects need to be realistic about the ability and the willingness of farmers to pay for advisory services; and, where appropriate, they should make the case that there is a public good argument for government to fund these services through annual budget allocations.
P046044 | Real Estate Registration Pilot Project | Europe and Central Asia | Kazakhstan | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/569641474906520107/text/000020051-20140602111656.txt | http://documents.worldbank.org/curated/en/569641474906520107/pdf/000020051-20140602111656.pdf | The decision to operate the new registration system on a fee for service basis confirmed experience in other countries, increasing sustainability and lessening dependence on the national budget. CRS experience contrasts with the SLC, whose survival now requires either amalgamation with the CRS or increased budget allocation and/or a new donor funded project. Development of equipment, training and systems, developed for SLC under the project, is hampered by lack of funds.Government support, which was initially strong, slipped during the latter part of the project, confirming that "high-level" support and long-term commitment is critical to project success" (MOR, page4.)The difficulty in CIS countries of establishing a system due to "institutional conflicts amongst the agencies involved" was confirmed in Khazakhstan.
P046045 | Syr Darya Control & Northern Aral Sea Phase I Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2013 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/484771475100762057/text/000020051-20140625055217.txt | http://documents.worldbank.org/curated/en/484771475100762057/pdf/000020051-20140625055217.pdf | This IEG review highlights 3 important lessons (different from those outlined in the ICR):1. The pursuit of components where governments have expressed an unwillingness to use loan funds is unlikely to end in a successful implementation of such activities. It is better to secure grant funds up front before the inclusion of such components. 2. The failure to implement monitoring and evaluation makes it difficult to correctly attribute outcomes. This becomes more important where investments for a large program (such as the ASBP) are phased, and the design of succeeding phases needs to be guided by the implementation performance of the earlier phases. 3. Projects need to build the anticipated impacts of local standards and practices on contracting, contract management, and other requirements, into the design and implementation phasing when they are not consistent with international practices. The provision of consultants alone is unlikely to fully address these issues.
P046046 | Legaql Reform Project | Europe and Central Asia | Kazakhstan | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2004 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/270151474573003828/text/000020051-20140607174259.txt | http://documents.worldbank.org/curated/en/270151474573003828/pdf/000020051-20140607174259.pdf | 1. The reform of legal and judicial institutions takes time, often requiring a social and political consensus that must be nurtured and developed incrementally with advice, technical assistance, educational efforts, consensus building which are all slow in pace, and do not involve large-scale resource transfers. The Bank has to find instruments that will allow for this. 2. Legal and judicial reforms should be based on an agreed overall governance/institutional reform strategy, which shows how the range of public sector institutions fit together, helps separate important problems and their causes from secondary ones, and shows the areas in which the Bank has a clear comparative advantage. This can guide the selection of activities which are worth the effort. 3. The evaluation of results should be based on realistic expectations given the complex, long-term nature of reforms and the fact that Bank operates on the margins of the client countryâ€™s own efforts at legal and judicial reform.
P046047 | Structural Adjustment Credit 2 (SAC 2) | Europe and Central Asia | Tajikistan | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/301041474594612279/text/000020051-20140613040238.txt | http://documents.worldbank.org/curated/en/301041474594612279/pdf/000020051-20140613040238.pdf | The credit would have had a greater chance of success if it had concentrated on fewer areas but with more focus on producing actual results.
P046051 | Higher Education Reform | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/360771474587038377/text/000020051-20140615095137.txt | http://documents.worldbank.org/curated/en/360771474587038377/pdf/000020051-20140615095137.pdf | Effective coordination, staff training, and integration of technical assistance and management activities are necessary to carry out complex projects with multiple partners implementing large-scale reforms.-Although poorer educational institutions may benefit from partnerships with others that are better off, they must be given some control of funds for their own use rather than depend on the priorities of the better-off institutions for project implementation.
P046052 | Ceara Water Pilot Project | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/522411474656135978/text/000020051-20140612070133.txt | http://documents.worldbank.org/curated/en/522411474656135978/pdf/000020051-20140612070133.pdf | Thorough evaluation of lessons learned for projects augmented by detailed study of the issues raised by integrated water resources management of a region significantly lowers the risk for subsequent investment projects. This is particularly true given the complexity of water resources management in the water short NE region of Brazil containing several river basins and states and the sometimes conflicting demands of several water-using sectors.Inclusion of all stakeholders requires systematic planning and establishment of a permanent core group to facilitate their involvement in project design and implementation.Analysis of options for financing operation and maintenance of multiple sector water supply facilities shows potential areas of conflict and highlights institutional development needs at local, state and national level.
P046052 | Ceara Water Pilot Project | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2002 | 2006 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/671521468016803730/text/36591.txt | http://documents.worldbank.org/curated/en/671521468016803730/pdf/36591.pdf | LESSONS 0 Especially in poor, drought-stricken regions like C e N water resource infi-astructure investments need to be sensitive to demand in order to be efficient in boosting development. 'T h i s rating results from shortcomingin achieving P R O W ' Sobjective of increased efficiency o f water use in C e d . . ' In the opinion of the Borrower (Annex C), the rating should be ( I l l y ) satisfactory, citing IEG's conclusion (para. 3.1) that PROURB was successfully implemented. IEG wishes to clarify that outcome ratings are determined by the results of the project in achieving its intended objectives, not by how well it was implemented. ERRS provide useful measures o f efficiency and indicators o f demand when using actual cost and benefit data that are calibrated with the real constraints o f the local economy and the capacities o f local agencies. Bank assistance can help nurture a culture o f self-evaluation by borrowers and implementing agencies, and stimulate them to continuously monitor results. Project upgrading o f low income urban areas can bring significant improvements to the living conditions o f the poor even in remote cities o f the interior.
P046061 | Moscow Urban Transport Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/690431474632709508/text/000020051-20140620072632.txt | http://documents.worldbank.org/curated/en/690431474632709508/pdf/000020051-20140620072632.pdf | Choice of internal or external PIU: Whether the PIU should be setup as separate unit, to maximize implementation efficiency, or within partner institutions, to contribute to institution building requires a very careful consideration i.e. weighting in as explicit a manner as possible the pros and cons of either approach.Source of Qualified Staff for New Institutions: In building institutional capacity of a newly created institution, the source of qualified staff need to be seriously considered. This would require broadening the scope of preparation to include national universities and technical colleges, possibly resulting in project-funded support for an expansion of the relevant course programs, within the same or under a separate project.Communication and Decision-making during the INT Investigation: According to the ICR, there are no clear guidelines for the staff on communication with the Borrower, and on how disbursements should be treated during INT investigations. This should be clarified.
P046112 | Pasto Education Project | Latin America and Caribbean | Colombia | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/611641475098005408/text/000020051-20140612140211.txt | http://documents.worldbank.org/curated/en/611641475098005408/pdf/000020051-20140612140211.pdf | It is possible for well-organized and motivated municipalities to implement World Bank projects on their own with little support from a central government. To succeed, implementation might take into consideration the implications of the decentralization model for the various national and local actors, including the respective spheres of authority and responsibility. - Participation of local stakeholders, including communities and universities, remains a key to the success of regionalized projects. Stakeholder participation may protect the project from political and economic instabilities and reduce opposition from specific groups. - It is important to have a well-designed and fully operational monitoring and evaluation system in place at the early stages of the project cycle. Locally conducted impact evaluation studies have the additional benefit of ownership that may facilitate decisionmaking on the basis of feedback from the study.
P046448 | ENT RES SERVS | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2003 | 1999 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/435921475076652465/text/000020051-20140522080550.txt | http://documents.worldbank.org/curated/en/435921475076652465/pdf/000020051-20140522080550.pdf | Market demand for TA lending operations in countries in transition may be low, and the Bank should carefully investigate this before proceeding with lending operations in this field. Among the lessons from the pilot projects are: (1) in difficult economic conditions such as existed in Russia in 1998/99, commercial banks are unwilling to bear risks associated with engaging consulting services for enterprise restructuring unless the banks have an equity position in the enterprise and the size of the loan is sufficient to minimize the administrative burden assumed by the bank in evaluating proposals for guarantees, and (2) enterprises need to be coached (given examples, etc.) on the benefits of hiring consultants to formulate restructuring plans.
P046496 | SOC PROT IMPL | Europe and Central Asia | Russian Federation | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/338961474854456806/text/000020051-20140612133837.txt | http://documents.worldbank.org/curated/en/338961474854456806/pdf/000020051-20140612133837.pdf | 1. This was an extremely complex project which made supervision difficult. The Bank should be wary of projects where detailed technical assistance programs are spread out over so many sectors, resulting in hundreds of contracts to be supervised. 2. If the Bank uses a PIU for project implementation, it needs to ensure that its staff is of high quality (PIU management had to be changed in mid-stream) and that it does not act as a barrier between staff and government ministries.
P046497 | Health Reform Implementation Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2003 | 2009 | 2011 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/338491475087214225/text/000020051-20140620074636.txt | http://documents.worldbank.org/curated/en/338491475087214225/pdf/000020051-20140620074636.pdf | Data and evidence are crucial for building and sustaining political support for reform. In this case, the demonstrated successes from the two project regions have led to adoption by other regions of the tools developed under the project.Health sector reform requires holistic and well-sequenced approaches. In this case, an important lesson was learned from previous experience in Russia: increased capacity and stewardship in the federal MOH, as well as strengthening of the primary care network, are necessary preconditions to hospital rationalization.Effective champions are key to navigation of the complex political and institutional waters of the reform process. In this case, officials at the highest levels of the federal MOH, as well as the governors of Voronezh and Chuvashia, were instrumental in ensuring sustained political support for the reform process.The Bankâ€™s leverage comes not just from lending operations, but also from policy development and the development and dissemination of analytical work.
P046499 | Health Restructuring Project | Europe and Central Asia | Kazakhstan | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977281474595533316/text/000020051-20140607164113.txt | http://documents.worldbank.org/curated/en/977281474595533316/pdf/000020051-20140607164113.pdf | This project confirms a number of lessons from other projects, most notably that high government ownership is critical to project success. Conversely, its absence almost guarantees failure and should be a red flag about a potential projectâ€™s moving forward. An indicator of such lack of ownership and commitment is the (almost absolute) refusal to accept outside technical assistance, as was the case in this project. Additional lessons are that given the inherently political and far-ranging nature of health reform, technical and political aspects must be dealt with in concert, pro-actively, and continuously. Implementing and donor partners are important co-factors in project success and should be involved in all stages of the project. With new Borrowers (especially), intensive â€œeducationâ€ with respect to Bank procedures, as well as optimal structuring and use of the PCU, can greatly facilitate timely, transparent and effective implementation.
P046563 | TARIM BASIN II PROJECT | East Asia and Pacific | China | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/777621475073422566/text/000020051-20140613064434.txt | http://documents.worldbank.org/curated/en/777621475073422566/pdf/000020051-20140613064434.pdf | In most respects the project is a best practice example of irrigation sector reform in a developing country. As there are, to date, few such successes, the project could be useful as a demonstration for other Bank countries. Lessons include: Strong government commitment was essential: The project would not have been successful without strong political support, which enabled the project's changes. Highly competent government staff, and full attention to providing the needed project support, such as counterpart funds, were also instrumental. A strong coordinating agency was important to success: The multi-sectoral approach of the project and the basin defined project area crossed technical, administrative and political boundaries. The project implementation agency was highly competent and had sufficient political weight to achieve the combined and synchronized efforts required from the different entities.Establishing water rights created further incentives for change: Linked with improved water monitoring, water rights encouraged water savings, conjunctive use of surface and groundwater, water quality improvements and and investment in drainage. Volumetric water tariffs significantly enhanced water savings: After introduction of volumetric water charges, farmer water use fell by 17% and crop production increased by 18%. Due to lower water use by farmers, farmer's overall water bills were lower, even after an increase in the water tariff. Investment early in data and modelling had significant advantages: A modern and effective data collection system and computer models are fundamental for informed, knowledge based decisions. A combined "bottom-up" and "top-down" approach to sector reform proved a key necessary feature: Working simultaneously on establishing the basin apex institution and the grass-roots farmer organizations was important in demonstrating and implementing the reform process.Broad based stake-holder "ownership" was key: Basin management arrangements should be based on consultation and representation of all stakeholder groups. Consultations when developing basin plans improved quality and consensus: During preparation of the basin plan, a consultation process involving communities helped overall acceptance of water allocation decisions.
P046563 | TARIM BASIN II PROJECT | East Asia and Pacific | China | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1998 | 2005 | 2008 | PPAR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/812911468218977436/text/41122.txt | http://documents.worldbank.org/curated/en/812911468218977436/pdf/41122.pdf | CONCLUSIONS AND LESSONS 3.42 Duringthe Xiaolangdi andTarimBasinProjectsthe Bankwas able to work with national-level organizations o f water policy issues giventhe cross-cutting nature o fthese enterprises. For the first and only time the Bank was inthe privilegedposition o f assisting MWR with the integrated planning ofthe Yellow RiverandTarimRiverBasins. This was importantbecausethe incremental impact o fthe projects the Bank supported on water resourcesmanagement could be modeledat the river basin scale andfully integrated with China's large portfolio o fpotentialprojects. Inboth cases, this approach indicatedthat the Bankassistedprojects were better than project alternatives that were thus rejected. And in both cases the Bank-assisted projects put a large emphasis on saving water ina river basin context. 3.43 Reviewingthe post-1990 portfolio o fagriculturalwater projects supported bythe BankinNorthandWest Chinathere hasbeena clear trendfrom buildingnewirrigation that increasesbasin-wide water demand, to projects that seek to improve water use efficiency and conservation efforts. However, there have beensome strategic mistakes that should have beenavoided -the Guanghong IrrigationProject approved in 1999 effectively doubled water use for irrigation inthe mid-reaches o fthe Yellow River near Xian. At the same time the downstream Water Conservation Project approved in2001 was extremely effective inreducing overall water consumption and i s a prime example o fwhat the Bank should support. There are three lessons\. The Bankneedsto elevateitsengagement in China's water resources policy discussions above the provinciallevelto emphasizethe perverseincentivesthat are created by extensive agricultural water subsidies. Subsidiesfor irrigation and landmanagementjeopardize water conservation effort, longer term sustainability o f irrigation and landreclamationprojects and water availability for towns, cities, industryand environmental management. Despite more than two decades o fBank partnership and several state-of-the art projects piloting new approachesthese tendto be enclave projects. While Chinese senior planners and politicians at the center acknowledge that pricing should play a role inensuring more efficient and rational allocation anduse o f water this i s still as at an early stage o f applicationand far from politically acceptable inthe provinces. Without such a change inthe near future water shortages and environmental consequences o fresource mismanagement will continue to grow to crisis proportions; 0Monitoring and Evaluation requires capacity building and reorientation to measureoutcomes and impacts.There is little virtue inimplementing development models for reclaiming degraded lands or for river basin management if impacts on welfare, incomes andthe economy cannot be accurately measured. While this is less o f a problem for physical achievements it is a major problem for measurement o f socio-economic outcomes and impacts. Muchmore attention has to be givento understandingthe appropriate counterfactual and ensuringunbiased sampling. There i s also an issue around selection o fthe most effective M&Emodel considering the outcomes expected and the cost o f the projects. Appropriate training to redressthe problems found inM&Ei s clearly indicated. Inaddition, more attention should be givento fully utilizing existing Chinese resources. The Ministry o f Finance has indicatedthat it has a national network o f monitoring that include socio-economic indicators and that consideration should be givento working with themto triangulate evaluative findings; and 0 Muchgreater care is required in dealingwith issues of attribution when estimatingex-post economic rates of return. Specifically this means clearer definition o fthe project counterfactual and a systematic accounting o fthe effects o f exogenous actors and investmenton project impact. Without such attention to these exogenous factors there i s a danger that estimated ERRSgive a false impression o f project impacts. This, inturn, may leadto incorrect lessons on development effectiveness and the efficacy o fpolicy, institutionaland engineeringmeasures utilized to achieve development objectives.
P046564 | Gansu and Inner Mongolia Poverty Reduction Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2006 | 2008 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/199451474659966183/text/000020051-20140618062809.txt | http://documents.worldbank.org/curated/en/199451474659966183/pdf/000020051-20140618062809.pdf | Counterpart funding needs to be arranged and firmly secured prior to project start-up in order to avoid delays in project implementation, where possible, by integrating project activities with the borrower's own programs. An appropriate level of flexibility should be built into projects with agricultural activities, particularly in areas prone to natural disasters and market uncertainties.Provision of regular credit to farmers may be more efficient than providing directed credit through Bank loans, in situations where production patterns need to respond quickly to market signals.Loans for the ultimate beneficiaries should be preferably channeled by the Bank through financial intermediaries rather than on-lending through local financial bureaus. The latter arrangement has suffered from a lack of expertise for appraising sub-projects, produced low repayments rates, and has also been a disincentive for development of new financial intermediaries.
P046648 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Senegal | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/225931474664245755/text/000020051-20140613041827.txt | http://documents.worldbank.org/curated/en/225931474664245755/pdf/000020051-20140613041827.pdf | Detailed designs should be completed prior to launching the bidding process. This would avoid the contractor having to produce detailed designs during contract execution, with subsequent uncontrolled and uncontrollable cost overruns.To avoid project delays, procurement bidding documents should be completed and distributed before negotiations. This is particularly important when there are likely to be different contractors for different segments of the project, all of which need to be coordinated.With may co-lenders, rules related to procurement and payments processing should be fully coordinated before project implementation to avoid delaying project execution. An environmental impact mitigation program, including especially a resettlement program for expropriated populations, should be in place and the appropriate institutions actively engaged in implementing it before the project is made effective.
P046648 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Senegal | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2007 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/942181468051004677/text/38134.txt | http://documents.worldbank.org/curated/en/942181468051004677/pdf/38134.pdf | 27. Lessons. At the project level, the experience of implementing RHDP yields the following lessons (lessons at the regional level are discussed later in the report)\. At the design and preparation stage, good technical preparation is essential if delays and cost increases are to be avoided. For the RHDP, the lack of detailed design studies for the power plant, the transmission lines, and the dispatching center led to numerous delays and successive cost increases. Procurement activities related to the key components should be as advanced as feasible prior to negotiations, in order to allow sufficient time for project management to take any necessary corrective measures and avoid delays. Harmonization of donor procedures, particularly on procurement, should be established prior to implementation. Financing and disbursement procures should also be harmonized to achieve better coordination among Co-lenders in the processing of payments. Mitigation of environmental impacts should be appropriately covenanted in the legal documents, and time-bound with provisions for remedial actions by IDA.. In the case RHDP, the long delay in signing the Water Charter and implementing the Manantali Reservoir Management Program posed serious risks in terms of escalating the negative environmental impacts of the Manantali dam, undermining the resettlement of expropriated populations, and delaying their compensation.
P046650 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/770641474482023853/text/000020051-20140613041604.txt | http://documents.worldbank.org/curated/en/770641474482023853/pdf/000020051-20140613041604.pdf | Detailed designs should be completed prior to launching the bidding process. This would avoid the contractor having to produce detailed designs during contract execution, with subsequent uncontrolled and uncontrollable cost overruns.To avoid project delays, procurement bidding documents should be completed and distributed before negotiations. This is particularly important when there are likely to be different contractors for different segments of the project, all of which need to be coordinated.With may co-lenders, rules related to procurement and payments processing should be fully coordinated before project implementation to avoid delaying project execution. An environmental impact mitigation program, including especially a resettlement program for expropriated populations, should be in place and the appropriate institutions actively engaged in implementing it before the project is made effective.
P046650 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2003 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/942181468051004677/text/38134.txt | http://documents.worldbank.org/curated/en/942181468051004677/pdf/38134.pdf | 27. Lessons. At the project level, the experience of implementing RHDP yields the following lessons (lessons at the regional level are discussed later in the report)\. At the design and preparation stage, good technical preparation is essential if delays and cost increases are to be avoided. For the RHDP, the lack of detailed design studies for the power plant, the transmission lines, and the dispatching center led to numerous delays and successive cost increases. Procurement activities related to the key components should be as advanced as feasible prior to negotiations, in order to allow sufficient time for project management to take any necessary corrective measures and avoid delays. Harmonization of donor procedures, particularly on procurement, should be established prior to implementation. Financing and disbursement procures should also be harmonized to achieve better coordination among Co-lenders in the processing of payments. Mitigation of environmental impacts should be appropriately covenanted in the legal documents, and time-bound with provisions for remedial actions by IDA.. In the case RHDP, the long delay in signing the Water Charter and implementing the Manantali Reservoir Management Program posed serious risks in terms of escalating the negative environmental impacts of the Manantali dam, undermining the resettlement of expropriated populations, and delaying their compensation.
P046651 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Mali | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2004 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/841781474561872654/text/000020051-20140613041652.txt | http://documents.worldbank.org/curated/en/841781474561872654/pdf/000020051-20140613041652.pdf | Detailed designs should be completed prior to launching the bidding process. This would avoid the contractor having to produce detailed designs during contract execution, with subsequent uncontrolled and uncontrollable cost overruns.To avoid project delays, procurement bidding documents should be completed and distributed before negotiations. This is particularly important when there are likely to be different contractors for different segments of the project, all of which need to be coordinated.With may co-lenders, rules related to procurement and payments processing should be fully coordinated before project implementation to avoid delaying project execution. An environmental impact mitigation program, including especially a resettlement program for expropriated populations, should be in place and the appropriate institutions actively engaged in implementing it before the project is made effective.
P046651 | REGIONAL HYDROPOWER DEVELOPMENT PROJECT | Western and Central Africa | Mali | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1997 | 2004 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/942181468051004677/text/38134.txt | http://documents.worldbank.org/curated/en/942181468051004677/pdf/38134.pdf | 27. Lessons. At the project level, the experience of implementing RHDP yields the following lessons (lessons at the regional level are discussed later in the report)\. At the design and preparation stage, good technical preparation is essential if delays and cost increases are to be avoided. For the RHDP, the lack of detailed design studies for the power plant, the transmission lines, and the dispatching center led to numerous delays and successive cost increases. Procurement activities related to the key components should be as advanced as feasible prior to negotiations, in order to allow sufficient time for project management to take any necessary corrective measures and avoid delays. Harmonization of donor procedures, particularly on procurement, should be established prior to implementation. Financing and disbursement procures should also be harmonized to achieve better coordination among Co-lenders in the processing of payments. Mitigation of environmental impacts should be appropriately covenanted in the legal documents, and time-bound with provisions for remedial actions by IDA.. In the case RHDP, the long delay in signing the Water Charter and implementing the Manantali Reservoir Management Program posed serious risks in terms of escalating the negative environmental impacts of the Manantali dam, undermining the resettlement of expropriated populations, and delaying their compensation.
P046768 | SN SUST.PART.ENGY.MGMT. | Western and Central Africa | Senegal | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2005 | 2006 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/440021474486991148/text/000020051-20140613053056.txt | http://documents.worldbank.org/curated/en/440021474486991148/pdf/000020051-20140613053056.pdf | The establishment of environmentally and socially sustainable NR supply systems can best be achieved through the introduction of community-based NR management schemes. Because governments lack the resources and the private sector the incentive to manage forests and other natural resources, these systems constitute the least cost option and offer the highest success opportunities for this kind of intervention, while generating significant rural development impacts. Supporting diverse NR-based income-generating activities in communities to complement the economic benefits of woodfuel management supply may be necessary to ensure that these communities maintain their incentive to manage forests sustainably and to make a significant impact on community incomes.For community-based woodfuel management systems to succeed in environmental conservation and community development, it is necessary for managed production to occur throughout the country. The continued existence of unmanaged production and unregulated producers have the potential to ultimately undercut the sustainable systems. A "minimum policy and regulatory platformâ€ is required to underpin a well functioning sustainable woodfuel supply system, consisting of (i) clear and legally enforceable forest resource and land tenure rights and responsibilities that give communities the incentive to sustainable manage the resource base; (ii) a fair and transparent decentralized fiscal and taxation system to adequately fund the oversight and supervision functions of the respective local levels of government; (iii) a clear and fair pricing system; and (iv) guaranteed and open access of woodfuel producers to consumer markets.
P046821 | AR PENSION TA | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/196031474553540389/text/000020051-20140613090455.txt | http://documents.worldbank.org/curated/en/196031474553540389/pdf/000020051-20140613090455.pdf | 1. Care should be taken in diagnosing corruption and in designing anti-corruption strategies which do not compromise other project objectives. In this case, the ICR notes that a full-fledged anti-corruption campaign was implemented, but may not have been fully warranted. More careful sampling of files before implementation might have enabled a fine-tuning of the anti-corruption campaign. In the event, the full-fledged campaign draw a great deal of attention and distracted those involved from other ongoing work which detracted from implementation of some project components. 2. The likely tenure of champions needs to be carefully assessed, as their departure seriously interrupts implementation. 3. Encouraging bottom-up participation in reform efforts can yield important gains. In this case, staff from field service units developed the automatic system for computation and adjustment of retirement benefits.
P046829 | CN-Renewable Energy Development | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1999 | 2008 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/650511474648556250/text/000146597-20140619154348.txt | http://documents.worldbank.org/curated/en/650511474648556250/pdf/000146597-20140619154348.pdf | The lessons emerging from this review are as follows:For interventions in rural PV markets, it is important to conduct a rigorous and extensive market study early in the preparation stage to provide information on market characteristics and barriers and to lay a solid foundation for effective project design. Linking subsidies to quality improvements has proven effective in situations where consumer perception of and feedback on quality was limited. A technology-neutral and bottom-up approach that avoids prescribing designs and sizes can be critical in unleashing the creativity of business in developing products that meet local needs. Clear policies regarding feed-in tariffs are critical preconditions for private sector-led renewable energy development.A market-based approach to PV dissemination requires a consistent and well-coordinated approach by all PV project supporters. Market-based approaches risk limited uptake if they compete with heavily subsidized approaches.
P046829 | CN-Renewable Energy Development | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1999 | 2008 | 2010 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/495181468279844359/text/548320PPAR01PUBLIC0Disc0July081.txt | http://documents.worldbank.org/curated/en/495181468279844359/pdf/548320PPAR01PUBLIC0Disc0July081.pdf | 11. Lessons and Outlook 11.1 Although the growth of the EMC business has been impressive, the scale of the industry remains small compared to the needs and potential of energy conservation in China. In 2007, the China EMC-deployed energy efficiency investment amounted to US$889 million, whereas the projected energy efficiency investment in China could reach as high as US$l 1 billion per year according to EMCA estimates. By comparison, although the energy intensity of the United States is smaller than that of China,14the annual investment of the US Energy Service Companies market is approximately $2.5 billion (NAESC 2007). 11.2 The IEG mission identified two major market and institutional barriers that constrained a wider-scale implementation of the EMC business\. Limited financing constitutes a major constraint to more aggressive and sustained growth of EPC business. There are various reasons for the shortfall in financing. Lack of experience in dealing with investors on the part of EMCs is one 14. According to the US Energy Information Administration, China's energy intensity is about 13,780 Btu per US.dollars in 2006, compared to 8,840 in the United States. reason, but more issues seem to be related to the general impediments for smalland medium-size enterprises to access finance in China. Most of the Chinese EMCs are small start-ups, with registered capital ranging between US$35,000 and $600,000. Because of the EMCs' small size, Chinese domestic banks have generally been unwilling to lend. This phenomenon, although common to all smalland medium-size enterprises in China, has especially restricted the EMCs' potential growth. This is because executing EMC business usually requires a substantial working capital to support the up-front tax obligation, project financing, and project construction and commissioning before finally generating revenues through client payments. The follow-up phase I1 project has created a guarantee fund for EMCs, aiming to engage the Chinese financing community as the key financier for EMCs. The IFC CHUEE Program provided bank guarantees to energy efficiency loans, as well as technical assistance to stimulate energy efficiency lending in China. However, the IEG mission discovered that financing difficulty still remains as the biggest obstacle. The IEG evaluation on the CHUEE program (IEG, 2010) also recognizes that one of the main challenges that smaller companies continue to face is access to finance for energy efficiency investments. Lack of contract enforceability remains a fundamental challenge to EPC market development. In a business environment where trust and long-term relationship are more emphasized than the enforceability of the contact, EMCs usually incur huge administrative costs to secure creditworthy customers. The high risk of counterpart breach of contract, both in terms of collection of repayment and verification of energy savings, increases the investment hurdle rate. Anecdotal evidence suggests that companies are far more cautious about the counterpart risk that is inherent in performance contracting and willing to forgo business opportunities if the perceived contractual risks are too high. In fact, the IEG mission discovered that both Beijing and Shandong EMCs have turned away from the original full-service sharedsavings model in order to minimize client credit risk. The Beijing EMC now focuses on developing outsourcing of energy system management EPC, whereas the Shangdong EMC was reorganized into a financial leasing company. 11.3 To address the challenges for the future development of the EPC business in China, the PPAR identified several strategies for all parties involved. Future Outlook STRATEGIES BORROWER 11.4 To meet the large market potential for energy efficiency in China, it is important for the EMC industry and the government to work collaboratively to remove several market and policy barriers. The EMCs need to enhance technical skills to provide more comprehensive service packages and to secure project financing. The government must establish financial and contract enforcement policies to address financing and client creditworthiness issues.l5 BANKSTRATEGIES 11.5 The Bank has been persistent in promoting the EPC mechanism in China, including provisions for only supporting EPC-type subprojects. Although such a narrow focus has been paramount for the success of the project, the choice of business models would be best determined by market conditions, by financing practices and systems, and by the institutional environment. To meet the ends of improving energy efficiency investment, a variety of approaches could tried, such as direct energy efficiency lending to small-and-medium-size enterprises, energy utility demand-side management, technical assistance to domestic banks, and so on. It is commendable that the follow-up Bank projects, such as China Energy Efficiency Financing, are moving in this direction. EMC INDUSTRY STRATEGIES 11.6 New Sectors and Product Lines. The EPC market is dominated by industrial customers and focused quite narrowly on energy saving concepts. The industrial sector represents 97 percent of the total investment for Shandong EMC and 82.5 percent for the Liaoning EMC. The Beijing EMC is an exception, for which the building sector constitutes 75 percent of investment. At the industry level, 63.1 percent of the EMC revenues in 2008 were attributable to the industrial sector market segment, and 33.4 percent and 3.5 percent were attributable to building and transportation sectors, respectively. Although industry is the largest energy consumer in China, other sectors, especially heating and cooling in the housin sector, have enormous potential for energy savings (McKinsey Global Institute 2008).' The EMCs may wish to consider identifying a broader range of energy efficiency investments across the sectors to capture the rich energy-saving opportunities in the economy. 11.7 Single versus Bundled Projects. The EMCs usually focus on certain product lines instead of conducting comprehensive energy audits to identify all the feasible improvements that will save energy at the facility. As a result, the scope of energy savings was narrower. The literature suggests that bundledcomprehensive projects that optimize energy through a series of improvements tend to achieve an overall greater gain in dollar and /or energy 15. In its effort to spur the development of the local EMC industry, the Shanghai municipal government has taken some cutting-edge initiatives. .An interministerial committee, Shanghai EMC Director Committee, chaired by the vice mayor, was established. The committee sponsors a third-party evaluation on both the technical risk and the creditworthiness of the client for each EPC project. The municipalor district-level government also works directly with guarantee agencies and local banks to ensure viable financing to EPC projects (conversation with Shanghai Economic and Trade Commission, Shanghai Energy Conservation Supervision Center, the EMC Committee of Shanghai Energy Conservation Association and the office of Shanghai EMC Supervision Committee, April 22,2009). 16. Heating and cooling of commercial and residential buildings constitutes 20 percent of the total energy consumption. According to Chou Baoxing, Vice Minister of Construction, using highly efficient energy technology to transform existing buildings may save about RMB 600 billion (US$SO.tibillion) each year. savings. (DOE 2005). Of the 357 PMO documented projects, only 3 are this kind. Furthermore, large enterprises usually prefer a systematic approach to maintain the reliability of manufacturing process rather than changing one production process based on one single technology. l 7 The single-project approach risks losing an important segment of the clients. Lessons 1 1.8 The main lessons emerging from this assessment are as follows\. 0 EPCs require quick implementation and closure, so it is important for the Bank's procurement procedures to be flexible to provide the quick response necessary to get the private sector involved in the EMC business. 0 For an energy efficiency project to succeed, it is important to engage government officials across ministries in practical and operationally focused dialogues to address specific implementation challenges, such as regulatory instruments, financial incentives, and provision of information. 0 Although EPCs are meant to be a market solution for energy efficiency, in a transitional economy like China, strong government support is crucial for the market to deliver successful results. In the case of the Energy Conservation Project, the Government's policies, regulations and instructions on reducing energy intensity had been important drivers of the expansion of the EMC business. 0 Strong country ownership requires adapting the project to the country-specific context. Bank-generated ideas work best when they are appropriately adapted to country circumstances. In the case of the Energy Conservation Project, the Government had adjusted tax treatment and legal interpretation of EMCs, thereby creating an enabling environment for the dissemination of the EPC concept in China. 17. Conversation with Shanghai Economic and Trade Commission, Shanghai Energy Conservation Supervision Center, the EMC Committee of Shanghai Energy Conservation Association and the office of Shanghai EMC Supervision Committee. April 22,2009.
P046832 | TN-MUNICIPAL DEV. II | Middle East and North Africa | Tunisia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1997 | 2003 | 2004 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/671381474857045408/text/000020051-20140612101051.txt | http://documents.worldbank.org/curated/en/671381474857045408/pdf/000020051-20140612101051.pdf | Sector reform projects have to incorporate and use a well-designed monitoring and evaluation system to assess outcomes and ensure that the project is on track during implementation.Focusing only upon municipal 'organizational' efficiency (improving and rationalizing internal procedures) will have a limited impact upon sector reform. 'Institutional' efficiency of the sector (through better incentives and regulatory environments) needs to be tackled too.A participatory approach to development at the municipal level, in devolving responsibilities away from standardized and familiar national programs, is constrained by municipal decision-making and programming capacities, that are limited in the Tunisian context.
P046836 | UG: Lake Victoria Env. Proj. (IDA) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/220261474506640020/text/000020051-20140615104531.txt | http://documents.worldbank.org/curated/en/220261474506640020/pdf/000020051-20140615104531.pdf | 1-Regional dimensions of national projects are vulnerable to failure if one of the partners do not deliver on agreed joint plans. Safeguards to mitigate such risks should be built into the design of regional programs.2-Scientific research must be targeted, provide usable information for management decisions and bewidely accessible.3-The Basin perspective is critical to address the key environmental issues of large systems such as Lake Victoria. 4-Regional projects necessitate greater emphasis on clarity of project objectives, monitorableframeworks, at multiple levels, and adequate mechanisms for governance.5-Capacity building has to address both current and projected needs of regional cooperation.6-Implementation in the medium to longer term can be undertaken through strengthening national agencies and governmental structures.7-Environmental benefits must be strongly linked to improved livelihoods for local people andcommunities.
P046837 | TZ-Lake Victoria Environment (IDA) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/487251474631782807/text/000020051-20140615104404.txt | http://documents.worldbank.org/curated/en/487251474631782807/pdf/000020051-20140615104404.pdf | 1-Regional dimensions of national projects are vulnerable to failure if one of the partners do not deliver on agreed joint plans. Safeguards to mitigate such risks should be built into the design of regional programs.2-Scientific research must be targeted, provide usable information for management decisions and bewidely accessible.3-The Basin perspective is critical to address the key environmental issues of large systems such as Lake Victoria. 4-Regional projects necessitate greater emphasis on clarity of project objectives, monitorableframeworks, at multiple levels, and adequate mechanisms for governance.5-Capacity building has to address both current and projected needs of regional cooperation.6-Implementation in the medium to longer term can be undertaken through strengthening national agencies and governmental structures.7-Environmental benefits must be strongly linked to improved livelihoods for local people andcommunities.
P046838 | KE: Lake Victoria Env. Proj. (IDA) | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1997 | 2006 | 2007 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/470601474849380088/text/000020051-20140615105541.txt | http://documents.worldbank.org/curated/en/470601474849380088/pdf/000020051-20140615105541.pdf | 1-Regional dimensions of national projects are vulnerable to failure if one of the partners do not deliver on agreed joint plans. Safeguards to mitigate such risks should be built into the design of regional programs.2-Scientific research must be targeted, provide usable information for management decisions and bewidely accessible.3-The Basin perspective is critical to address the key environmental issues of large systems such as Lake Victoria. 4-Regional projects necessitate greater emphasis on clarity of project objectives, monitorableframeworks, at multiple levels, and adequate mechanisms for governance.5-Capacity building has to address both current and projected needs of regional cooperation.6-Implementation in the medium to longer term can be undertaken through strengthening national agencies and governmental structures.7-Environmental benefits must be strongly linked to improved livelihoods for local people andcommunities.
P046952 | Forestry Development In Poor Areas | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/756241474577628510/text/000020051-20140615105711.txt | http://documents.worldbank.org/curated/en/756241474577628510/pdf/000020051-20140615105711.pdf | The ICR and the borrower report offers four main generic lessons which are given here with some adaptation:1. A strong research-extension-training linkage is essential to transfer new production and management technologies to poor farmer communities. The available in-country skills, often scattered and uncoordinated, need to be harnessed through an institution and linked to potential beneficiaries, as was achieved in this case through a highly qualified senior consultancy group. 2. Superior planting material and management of that material through the transfer of skills is a key to high productivity and thus efficiency.3. In pursuing broad environmental land management objectives and participatory approaches, the short time horizon of poor rural households, and their need for immediate income, should be understood and accomodated in the form of quick return non-timber forest products or fast growing species and products (e.g. poles), and complementary crop or livestock enterprises. Credit can be problematic with longer-term timber enterprises in the absence of such shorter-term revenue sources.4. Small enterprise development and lending in rural areas calls for careful analysis of proposals by qualified staff, well-trained in small enterprise investment, who can realistically project and assess the market demand and the commercial viability.
P046952 | Forestry Development In Poor Areas | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2012 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/103301468242639821/text/678820PPAR0P100C0disclosed070160120.txt | http://documents.worldbank.org/curated/en/103301468242639821/pdf/678820PPAR0P100C0disclosed070160120.pdf | 5. Lessons 5.1 This assessment of forest projects and AAA has highlighted the steps the Bank has taken to move beyond its (highly successful) engagement with plantation development in China. Renegotiating its support for forest interventions involves supporting new activities, and finding new interlocutors. The Bank has been more successful in the first of these switches than it has in the second. As the FY2010 Shandong Ecological Afforestation Project and the FY2010 Integrated Forestry Development Project have shown, the Bank is now seeking to involve local forest authorities, village leaders and farmers in the design of forest management plans that would ultimately take the place of the logging quota system, which lacks transparency and is unevenly enforced. This is the latest phase in the evolution of a more participatory approach to forestry that dates back to the FY98 Forestry Development in Poor Areas, assessed in this report. In addition, recent analytic work builds on the 2010 Forest AAA that was evaluated here. The FY2012 North East State Forest Reform Study aims to develop a roadmap for the State Forestry Administration, to support policy and institutional reforms in the management of state-owned forests in Northeast China, with a view to enhancing management efficiency, economic viability resource sustainability, and local livelihoods. Progress in the dialogue on policy reform will depend in no small measure on the Bank's ability to engage with new government agencies in China\. the State Forestry Administration's Project Management Center has proved to be a highly effective partner for plantation establishmentâ€”with a first-rate performance record, probably unparalleled in the worldâ€”but if the Bank is to broaden its engagement on forest interventions it needs to develop a dialogue with other interlocutors in addition to PMC. Since the sector work evaluated in this report was completed there is some evidence that the Bank's forestry team in China has diversified the scope of its engagement\. although continuing to work with the Project Management Center (specifically, on plantation establishment), the Bank is working with other departments in the State Forestry Administration and directly with provincial governments. 5.2 Based on the assessment of the projects and AAA in this report, IEG draws three lessons. 5.3 Even if poverty reduction is not an objective of the project, there is a sound case for monitoring and evaluation to measure project-driven changes in the incomes of beneficiaries because these are likely to influence the incentives for beneficiaries to consolidate project achievements. The Forestry Development in Poor Areas Project made provision for three household surveysâ€”baseline, midterm and final. These surveys were included in order to assess attainment of the outcome target of increasing incomes by 60 percent; and, more broadly, because poverty reduction was an explicit objective of the project. The Sustainable Forestry Development Project did not include poverty reduction or income enhancement in its objectives, and made no provision for household surveys. There was close monitoring of plantation establishment and, given the tight quality controls, there was good reason to infer that the incomes generated from this component would be substantial, creating an incentive for farmers to pursue the recommended tending and harvesting guidelines in order to maximize returns. However, unlike in the earlier project, there is no indication whether poorer households invested in plantations. More importantly, in the case of the protected area and natural forest management components, it was less certain that incentives were sufficient for communities to commit to conservation and sustainable forest management. These components included modest efforts to improve livelihoods and to boost incomes but in the absence of evidence from household surveys it is impossible to know whether the impact was big enough to generate the incentive needed to consolidate project gains in natural resource management. Given the steep rise in wages in China, labor devoted to (poorly remunerated) conservation activities carries a high opportunity cost, making it all the more important that projects have the monitoring and evaluation apparatus needed to measure livelihood changes and assess the level of incentives. 5.4 Until recently, the scope for the Bank to broaden its operational engagement with forest issues in China was limited by governments' insistence that, where IBRD funds are on-lent, producers and local governments must repay them with interest; central and provincial governments now recognize the public good nature of forests and are more willing to assume direct responsibility for repaying Bank loans that provide forest environmental services. Making loan recipients responsible for repayment 53 rewards solid performance but is hard to justify where there is no revenue stream to amortize debt obligationsâ€”that is, where loans are used to finance delivery of public goods. The â€•responsibility systemâ€– lends itself to the financing of commercial wood plantations but is harder to apply to conservation-oriented forestry and environmental protection. The experience from the projects assessed here shows that poorer counties and poorer farmers have difficulties meeting loan repayment obligations, partly because the government's enforcement of the logging ban and protection of natural forest and nature reserves reduces their sources of income. Excluding the poor from IBRD-funded projects is not desirable. Neither is it realistic to expect that grants will fully substitute for IBRD loans. (The Sustainable Forestry Development Project pushed in this direction, seeking to graft on a European Union grant to a World Bank project, with unsatisfactory consequences.) Had central and provincial governments not been willing to assume a larger share of the responsibility for paying back loans, it would have been difficult for agencies like the Bank to move away from financing commercial plantations. In recent years, government policy has evolved to emphasize the contribution of forest environmental services to China's development. The central government, and some provincial governments, are now willing to use Bank loans to support the provision of forest public goods through direct government budget expendituresâ€”rather than solely for on-lending to planting entities for forestry production activities. This trend is evident in the Bank-supported Shandong Afforestation Project and the proposed Hunan Forest Restoration and Development Project. 5.5 Parallel-financing by another donor is difficult to supervise if it is applied to a single component of a Bank-supported project, and may be best dealt with as a separate operation. The Bank used its convening power to elicit grant funds from the European Union for the natural forest management component of the Sustainable Forestry Development Project. This was a valid attempt to diversify the range of Bank engagement toward public good forestry, which the Chinese government was unwilling to finance on IBRD terms. The component was parallel-financed, not Co-financed, meaning that the European Union was in charge of supervising the component. At appraisal, the Bank stated that the two partners would cooperate closely, participating in each other's supervision missions. In practice, this failed to happen. Cooperation was limited, in part, because the Bank-supervised components were implemented by PMC while the EU component was implemented by a separate department of the State Forestry Administration. Moreover, the practice of the Chinese government has been to deal with each donor separately with no encouragement to collaboration between them. The poor performance of the consultant team fielded by the EU slowed down implementation of the component and, incidentally, delayed the closing of the overall project and pulled down the outcome rating. The potential for shared learning between the Bank and the EU was not realized.
P047039 | GT JUDICIAL REFORM | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/613181474486660181/text/000020051-20140619062351.txt | http://documents.worldbank.org/curated/en/613181474486660181/pdf/000020051-20140619062351.pdf | A results framework needs to be carefully formulated at project appraisal, and realistic and measurable indicators need to be included all within an analytical framework which explains the linkages between the outputs, outcomes, and final impact. It is very important for Bank management to then ensure that the task team focuses on ensuring that systems are in place for monitoring the indicators and assessing both development outcome and implementation progress.It is inadequate to only recognize political economy issues; it is equally important that such risks influence the formulation of more realistic project objectives and that indicators are included that can signal whether the risks are materializing.
P047057 | Rehabilitation Project | Europe and Central Asia | Bulgaria | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2000 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/258921474898842156/text/000020051-20140526210722.txt | http://documents.worldbank.org/curated/en/258921474898842156/pdf/000020051-20140526210722.pdf | Governments need to be fully committed to reforms of this magnitude. In this case, the government fell short in implementation, lost credibility, and thereby exacerbated existing problems. The Bank needs to take a very hard look at ownership and commitment to reform before proceeding with operations of this sort.
P047065 | MICROENTERPRISE | Middle East and North Africa | West Bank and Gaza |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 1997 | 2003 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/621901474856638120/text/000020051-20140612062801.txt | http://documents.worldbank.org/curated/en/621901474856638120/pdf/000020051-20140612062801.pdf | microenterprise lending schemes, when well designed, well supported, and well operated, can have a positive demonstration effect on the industry;- the same applies for job creation;- the financing plan, including for the provision of TA, must be agreed at time of negotiations;- a domestic M&E system must be designed jointly by the borrower and the Bank at time of project preparation.
P047067 | GZ: PALESTINIAN NGO PROJ | Middle East and North Africa | West Bank and Gaza |  |  | Human Development | Social Protection & Jobs | SPF | IPF | 1998 | 2004 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/161221474549714632/text/000020051-20140612085938.txt | http://documents.worldbank.org/curated/en/161221474549714632/pdf/000020051-20140612085938.pdf | In a sub-grant type operations, to ensure efficient implementation, all procedural aspects of the project should be fully elaborated by the time of appraisal.
P047110 | GZ-COMMUNITY DEVELOPMENT | Middle East and North Africa | West Bank and Gaza |  |  | Human Development | Social Protection & Jobs | SPF | IPF | 1997 | 2000 | 2001 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/884241474563010525/text/000020051-20140529072248.txt | http://documents.worldbank.org/curated/en/884241474563010525/pdf/000020051-20140529072248.pdf | For this type of project: 1. The importance of having competent overall project management to guide sub-project selection, oversee implementation and supervision of construction, monitor the multiplicity of activities, and follow up on maintenance issues and beneficiary assessments after the construction phase.2. The importance of coordinating selection and implementation of the sub-projects with governmental line ministries, to ensure that the infrastructure (health clinics, schools) are properly staffed and supplied with necessary inputs.3. Key to ensuring that the sub-projects are priorities for a good portion of the community is to incorporate widespread community participation in the decision-making process, reasonably significant financial contribution by the community in the construction phase, and community awareness of and commitment to operating and maintaining the infrastructure.4. Beneficiary assessments can be an important part of feedback for monitoring progress on selection, implementation, and follow up maintenance issues of sub-projects.
P047111 | LEGAL DEVELOPMENT | Middle East and North Africa | West Bank and Gaza |  |  | Equitable Growth, Finance and Institutions | Governance | SPF | IPF | 1997 | 2004 | 2005 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/224001475078534012/text/000020051-20140612145933.txt | http://documents.worldbank.org/curated/en/224001475078534012/pdf/000020051-20140612145933.pdf | As noted in the ICR:- Judicial reforms should probably not be a first priority in areas that are in-conflict, when other priorities would take precedence.- Judicial reform should be set in the larger context of agreeing on the appropriate framework and roles for the legislative, executive, and judiciary branches of government (this project failed to do this and it resulted in lack of agreement on basic reforms supported under the project);- Judicial reform needs commitment and participation of a range of stakeholders (executive branch including ministry of justice and prosecutors, judicial branch of government, business community -- if it commercial laws involved), who should be actively involved from the earliest phase of project preparation onward. - the importance of close supervision for TA operations cannot be underestimated
P047250 | KM-Infrast, Water & Env Prj (FY01) | Eastern and Southern Africa | Comoros | IDA |  | Infrastructure | Transport | IDA | IPF | 2001 | 2004 | 2004 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/443771475083362354/text/000020051-20140612093250.txt | http://documents.worldbank.org/curated/en/443771475083362354/pdf/000020051-20140612093250.pdf | In a situation of absence of functioning government and mutual distrust of the political leaders, it appears judicious to focus development assistance on communities and civil society.
P047309 | BR ENERGY EFFICIENCY (GEF) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | Modest | http://documents.worldbank.org/curated/en/284491474903683567/text/000020051-20140617132551.txt | http://documents.worldbank.org/curated/en/284491474903683567/pdf/000020051-20140617132551.pdf | (1) Electricity utilities will not have an automatic incentive to invest in EE measures because this will lower their sales and revenues. Consumers do have an incentive to improve EE, but often lack sufficient information on specific cost-effective measures and the means to finance investments. For these reasons, standards and labeling programs (like the one supported by this project) can be very important for improving EE by setting minimum efficiency standards for energy-consuming equipment.(2) The key project indicators should be flexible and be adapted during implementation as conditions change and the project develops, particularly if the project is restructured at some point in time. In this project, some of the indicators designed at the project concept stage became irrelevant later and the target values became unrealistic because they were set for the entire EE program while the project only embraced Phase I of the program. (3) Although energy crises are not a desirable event, they provide an opportunity for making consumers aware of the importance of making efforts to save energy and money, particularly in electricity consumption. The rationing program that was put in place in Brazil in 2002 to deal with severe cuts in electricity supply was effective in reducing consumption. Although this resulted in large financial losses to the distribution utilities it also gave them an incentive to take measures to reduce their operation costs. (4) To develop an EE industry -- including true ESCOs that enter into shared-savings or performance contracts and provide financing for EE investments -- takes time and require an appropriate regulatory and financial environment. When ESCOs are small and undercapitalized companies, as is the case in Brazil, they will not be able to finance EE investments on their own and usually cannot obtain sufficient credit from commercial banks. Unfortunately, the ESCO financial facility envisioned by the original project design was deleted from the restructured project because conditions in Brazil were not favorable to assist in the development of ESCOs.
P047319 | Quality Education for All Program | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/390781474595087157/text/000020051-20140615103401.txt | http://documents.worldbank.org/curated/en/390781474595087157/pdf/000020051-20140615103401.pdf | 1. SWAPs can be effective instruments under certain circumstances, but, as this Project shows, their effectiveness can be compromised if: The government is not able to control funding flows among sub-sectors (in this case undiminished flows of university scholarships reducing funding available for primary school quality improvement and for the expansion of lower secondary education);There is no mechanism for pooling development agency funding (such that delays in funding from one agency can slow down the entire project); Agencies are not able to reach agreements on standards (such as the unit costs of buildings). 2. Similarly, use of the Adaptable Program Loan (ALP) can be an effective way to support a long-term reform effort, allowing new and innovative programs to be field tested and evaluated before being brought to scale, but this approach requires that the government has the capacity and commitment to operate in an experimental mode (testing options, evaluating them, and making evidence based judgments as to whether innovations are ready for scaling up). 3. Institution development includes the development of planning and financial management mechanisms and staff development, but it also requires elaboration and enactment of clear rules of that game as to what agency has authority for what and how different parts and levels of the government should interact. 4. Improved learning outcomes in basic skills like reading can be put into project designs, but are often difficult to implement, given management's temptations to realign projects towards quantitative goals such as expanded access. Governments need to resist the temptation to expand access to higher levels of education if quality of education is still poor at lower levels: it makes no sense to pass greater proportions of students to lower secondary education if primary school graduates have not yet acquired basic skills such as reading fluency. 5. Monitoring and evaluation can be delegated by the government to external research centers, but at some point an in-house capacity is needed for agencies to be able to make well grounded decisions. 6. Good management information systems are a first step in determining whether teachers are serving where they are supposed to, but unless there is strong political will the inefficiencies identified by such systems will not be overcome. 7. A true commitment to effective learning outcomes assessment and evidence of movement in that direction should be a prerequisite for Bank support to any project having quality improvement goals.
P047345 | Huai River Pollution Control Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2008 | 2010 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/289991474483253152/text/000020051-20140619111022.txt | http://documents.worldbank.org/curated/en/289991474483253152/pdf/000020051-20140619111022.pdf | Water pollution reduction project should be based on integrated river basin plans. This not only ensures that the most strategic pollution hot-spots are tackled first but it also leverages institutional attention and target-setting to higher levels of government and oversight.Lowest-cost procurement of civil works does not always lead to selection of the best contractors. Many of the lower cost contractors do not have sufficient experience to price-in project risks and hiring them may result in significant delays when unforeseen problems occur. This suggests that the post-qualification process and other criteria (as described in the Bank's Procurement Guidelines para 2.49-2.58) may require greater application in China.
P047438 | Structural Adjustment Credit (SAC) | Europe and Central Asia | Tajikistan | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2002 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/107901474665427786/text/000020051-20140602110957.txt | http://documents.worldbank.org/curated/en/107901474665427786/pdf/000020051-20140602110957.pdf | A program of rapid privatization paid off; privatization was achieved while reform sentiment was strong, and before the quality of enterprise assets could deteriorateFinancial sector reforms were greatly helped by the presence of strong "champions" in the NBT
P047582 | MA-CONTRACTUAL SAVINGS | Middle East and North Africa | Morocco | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 1999 | 2000 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/816611474656082962/text/000020051-20140528124535.txt | http://documents.worldbank.org/curated/en/816611474656082962/pdf/000020051-20140528124535.pdf | There is a strong contrast between the generally good implementation of the short term reforms, prior to tranche release, and the uneven implementation of the medium term reforms subsequent to tranche release. Perhaps there should have been a better matching of the time frame of the instrument and its objectives. For example, floating tranches might have been used to better match financial support with policy implementation. Alternatively, a stronger assessment of ownership of the reforms, including popular support which would endure possible changes in government, could have resulted in a better formulation of the project's policy agenda. These considerations are even more important with changes in government as with this project.
P047683 | MN-BANK,ENT,LEG,TA(BELT | East Asia and Pacific | Mongolia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 2001 | 2002 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/231281474651255949/text/000020051-20140607150845.txt | http://documents.worldbank.org/curated/en/231281474651255949/pdf/000020051-20140607150845.pdf | TA projects should be carefully designed with respect to sectoral needs (taking into account activities of other donors, work to be undertaken later, etc.)"Pilot" projects should have an explicit mechanism by which experience and lessons can be promulgated to a wider audienceWith an inexperienced borrower, the Bank needs to assure that sufficient expertise exists in areas such as procurement and project financial management
P047690 | Agricultural Research and Extension Project | Latin America and Caribbean | Peru | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/739811474490149953/text/000020051-20140613083022.txt | http://documents.worldbank.org/curated/en/739811474490149953/pdf/000020051-20140613083022.pdf | (1) The principal lesson generated by this project was that adequate provision needs to be made to ensure that the project implementing unit, or some other body, is adequately staffed in order to liaise with and assist other partners, when a program involving support for sub-projects proposed and implemented by others is to be established. This may require provision for TA to provide this support, particularly when the operation is intended to be operated on a decentralized basis, so that regional offices are required, and when it is intended to work, at least in part, with disadvantaged groups (e.g. ethnic minorities and/or the poor). In both cases partners are likely to be much less familiar with procedures and requirements involved in government run programs.(2) Competitive grants can make a significant contribution to strengthening the national capacity to do research by drawing out latent capacity beyond the formal agricultural research system as well as leveraging resources that might otherwise not be available for agricultural research.(3) The present practice of requiring what is effectively a whole new appraisal for second and subsequent stages of an APL can impose a considerable load on the central staff of the ongoing project.
P047690 | Agricultural Research and Extension Project | Latin America and Caribbean | Peru | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 2000 | 2005 | 2009 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/277821468057286448/text/491490PPAR0p061fficial0Use0Only1pdf.txt | http://documents.worldbank.org/curated/en/277821468057286448/pdf/491490PPAR0p061fficial0Use0Only1pdf.pdf | 6. Conclusions and Lessons 6.1 An importantfinding o this four-project assessment is the lack o hard f f evidence about the results o competitivefund investments in research and extension. f In each o f these countries, agricultural productivity has risen since the mid 1990s, with growth increasingly based on intensification rather than area expansion. Potentially, the assessed projects contributed to this expansion. But, with the exception o f Peru, there i s no robust survey evidence linking productivity and income changes to the project interventions. Even in the case o f Peru there are doubts about which o f the steps in the results chain were most critical for achieving the increase in farm incomes. For example, extension services potentially have a role to play in the technology transfer chain but it i s unclear just how a critical a role. In each o f these four countries extension has withered on the vine; but from the evidence generated by these projects it i s impossible to conclude if this attrition i s truly significant-or whether, for example, tighter linkage o f farmers to producer associations i s an effective substitute. 6.2 With respect to the viability o f the competitive fund model, more study i s needed to compare the efficiency o f the model with the alternative-a single (public) supplier with fiinds directly assigned by government. There is a perception-stronger in Brazil and Colombia than in Peru and Nicaragua-that the competitive process has been managed in a way that i s both fair and transparent and has tended to raise the quality o f the research proposals that are approved for funding. But there i s no indication o f how costs per unit o f technology adopted vary between the competitive and the direct assignment approach. 6.3 Thefourprojects included in this assessment, and thefollow-on projects that have succeeded them, have generated substantial learning, both by the Bank and by the countries concerned. InNicaragua, there i s now greater realism about what can be achieved in a context o f weak institutions and high donor dependence. In Peru, the importance o f integrating the competitive fund approach with the broader public sector apparatus o f research and extension has been acknowledged; and the government's commitment to maintainingthe regional network o f INCAGRO bodes well for increased decentralization. In Colombia, the progress under the follow-on project in linking subprojects to commodity chains and increasing engagement with producer associations i s resulting ina more strategic allocation o f competitive fund resources that will help to enhance the country's agricultural competitiveness under the terms o f the new free trade agreement with the USA. In Brazil, the returns to increasing EMBRAPA'S connectedness with diverse research institutions, both within the country and beyond, have become f i l l y apparent. 6.4 The findings from this assessment suggest lessons o f broad relevance that are likely to apply beyond the four countries studied. A principal lesson concerns the importance o strengthening the capacity o research organizations, not just financing f f research. Competitive funds can be an important vehicle for research financing and have a strategic role to play in piloting new ways o f working, or focusing research on new topics; but they are most likely to make a sound and lasting contribution when they complement a relatively strong public-sector framework for research (in this respect, prospects were brighter to begin with in Brazil and Colombia than they were in Nicaragua and Peru). Public funding i s essential for agricultural innovation systems and private funding complements rather than substitutes for higher levels o f public funding 6.5 Second, to be able to compete, research institutions must have a minimum budget and a critical mass o staff-all f institutions need a portion o the budget that is f f f corefunded to cover costs o maintenance and upgrading o physical and human resource infrastructure. Competitive grants usually only fund operating costs; and the subprojects they finance have only 2-3 years' duration.' The sustainability o f the public sector research apparatus in general and the competitive funding model in particular depends on a continuing commitment o f government funds. The new model is unlikely to flourish in a climate o f fiscal austerity because there i s only limited scope for private funds to substitute for public money. 6.6 Third, the competitive fund model i s more likely to strengthenthe strongest agencies providing research and extension services than it is to reduce the disparities between the strong and the weak. Thus, in Brazil, the model strengthenedan agency that was pre-eminentto begin with. At the other extreme, in Nicaragua, the model was underfundedfrom the outset, i t s transformative capacity was limited by the weakness o f all the actors in the competitive arena, and the government provided little support to it. The principle o f competition between alternative service providers breaks down where the range o f providers i s limited (a problem at the municipal level and for small countries) and many o f the potential providers lack the skills needed to prepare viable sub-project proposals. 6.7 Fourth, the competitive model has not itselfled to a large growth in the role o f f the private GforprofiQ sector as a provider o agricultural research and extension; but it has contributed to the broaderprocess o private sector development. Compared to high- f income countries, in Brazil, Colombia, Nicaragua and Peru, commercial f i r m s have played a smaller role as providers relative to public and private nonprofit agencies. To the extent that commercial f i r m s have played a role, they have largely done so outside the framework o f competitive grant schemes; this i s the case, for example, for the partnership between EMBRAPA and the private multinational Monsanto for producing herbicide-tolerant soybeans2O n the other hand, under the competitive schemes, through the medium o f subproject Co-payments, producers have provided private funds as a complement to public sector grants; they have received training in the preparation o f business plans; and they have become more market-oriented owing to partnerships with producer associations that have been facilitated by competitive funding agreements. In this sense, the competitive fund model has contributed to the broader goal o f private sector development without entailing a major role for commercial f i r m s as service providers.
P047761 | TZ-Tax Administration (FY99) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/998961475099878294/text/000020051-20140618063755.txt | http://documents.worldbank.org/curated/en/998961475099878294/pdf/000020051-20140618063755.pdf | Piecemeal efforts at tax reform are inadequate. In preparing this project, the Bank should have first assisted the Government in preparing a comprehensive strategy for tax reform that would have covered local government levels also. Such a strategy will also provide a framework where donors can support the Government in a comprehensive and effective manner.
P047762 | Rural Water Supply and Sanitation Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2008 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/323591475098211861/text/000020051-20140619105740.txt | http://documents.worldbank.org/curated/en/323591475098211861/pdf/000020051-20140619105740.pdf | Demand-responsive projects require considerable attention during appraisal to beneficiaries and their institutions. This is to ensure that they are able to exercise their governance, organizational, management and financial responsibilities. Where there are shortfalls in capacity remedies should be addressed in project design. It is essential to allow sufficient time for capacity-building.Multiple service providers for design and technical implementation of RWSS projects may create coordination problems. It is better to have a single intermediary institution between government and communities that has responsibility for coordinating design and implementation. IEG notes in their assessment of the Nepal RWSS project that NGOs performed this role very satisfactorily (Report 44368 of 06/23/2008).
P048026 | AGRI RES & EXTENSION | South Asia | Nepal | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1998 | 2003 | 2003 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/960861475092443903/text/000020051-20140612063816.txt | http://documents.worldbank.org/curated/en/960861475092443903/pdf/000020051-20140612063816.pdf | The main ICR lessons, which are sound, include:Major institutional reform and adoption of new management systems requires long-term support and is only possible with broad commitment from the borrower.Project preparation should include a thorough institutional and organizational analysis of project agencies to achieve commitment and effective project implementation arrangements.The need for a Project Coordination Unit should be carefully assessed and justified. (In this case, as in many cases, this arrangement impacted negatively on institutional sustainability).Both technical assistance and training need to be planned for and mplemented very early if they are to positively impact on the project. This ES adds a further lesson, that when projects are significantly changed, whether formally or informally restructured, the objectives and the supporting intermediate milestones should be very carefully revisited. OED sees many cases where results-based performance suffers because objectives are left alone but design is signifcantly adjusted.
P048202 | PETROLEUM SECTOR MANAGEMENT CAPACITY BUILDING PROJECT | Western and Central Africa | Chad | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/698701474486611459/text/000020051-20140618062636.txt | http://documents.worldbank.org/curated/en/698701474486611459/pdf/000020051-20140618062636.pdf | 1. Effective implementation of capacity building projects requires solid commitment from the Borrower at a high level, and must take place in the context of clear policy objectives with the political commitment to reach them.2. Human, financial and institutional constraints must be carefully assessed. Only on the basis of such an assessment can realistic expectations be built as to what can be achieved through this type of project.3. There must be an early and strong emphasis on building capacity. Training should be the core of such exercises. 4. Temptations to cover too many sectors and too many activities should be avoided. Inclusion of, for example, infrastructure building components are likely to prove a serious distraction for both financial and human resources. 5. There should be the maximum clarity as to what types of capacity need to be created and which personnel are to be targeted. Moreover, capacity building should be properly sequenced. 6. An adequately equipped team and continuity of team leadership are essential for smooth implementation7. In nearly all cases, but especially in extractive industries, an appropriate legal, institutional and regulatory framework should be in place before production starts. This would facilitate the building of capacity.8. Capacity building should focus on existing, permanent national institutions rather than relying on temporary entities which have political or operational authority, and are thus unable to mainstream reforms.
P048202 | PETROLEUM SECTOR MANAGEMENT CAPACITY BUILDING PROJECT | Western and Central Africa | Chad | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2000 | 2007 | 2010 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/565481468224677215/text/503150PPAR0P05101Official0use0only1.txt | http://documents.worldbank.org/curated/en/565481468224677215/pdf/503150PPAR0P05101Official0use0only1.pdf | 4. Lessons and Future Implications 4.1 The well-known lesson that government ownership and commitment are the major influence o n the effectiveness of projects and programs i s underlined by the experience o f the Chad-Cameroon program. Other lessons learned from the program are identified belowmany o f them also well known but brought in sharp relief by this experience. Because the findings and conclusions are discussed in the earlier sections, the lessons and implications are listed below with a minimum o f elaboration. (Project-specific lessons are included in the corresponding annex.) RELEVANCE, R I S K S , AND TIMING 4.2 International experience has shown that adequate expenditure management mechanisms should be in place, and tested, before a large revenue increase i s likely to accrue. In this case, the time available for capacity-building after Board approval and before the flow o f o i l revenue was much shorter than expected and the revenue much larger-adding to the difficulty o f building capacity contemporaneously with program implementation. A secondary lesson is therefore to build expenditure management capacity as robust as necessary to fit a high scenario o f revenue increase. (The capacity created will be useful to the country even if the high scenario does not materialize.) 4.3 Setting up institutional enclaves and special mechanisms to protect resources and accomplish quick results can damage local capacity in the long term. Such enclaves are generally not successful beyond the short term and, even when successful in the short term, they tend to undermine the already weak local systems and thus long-term development. In this case, although the rationale for the establishment o f the revenue escrow account and the earmarking arrangements was strong in the specific country context in 2000, when tested by reality these mechanisms failed to achieve their objectives and meanwhile stood in the way o f sustainable improvements in fiscal and expenditure management capacity. 4.4 While protecting inputs must remain a paramount consideration, development objectives should be formulated in terms o f outcomes (ifpossible), meaningful outputs, or concrete process improvements-rather than in terms o f inputs-and performance indicators should be limited to thefew key indicators that are critical to achieving the PDOs and are monitorable. Even when the immediate aim o f the project i s to increase resource availability, reduce the cost o f input acquisition, or channel resources toward priority uses, a failure to define clearly the expected results in terms o f key outputs, outcomes, or major process improvements risks distorting the actual design o f the project away from those results. In this case, defining the main project objective for Chad in terms o f budgeted expenditure to be achieved diverted attention away from the efficiency o f expenditure and budget execution. And to l i s t dozens o f key performance indicators o f diverse importance and questionable monitorability makes monitoring impossible. AND DESIGN APPROACH 4.5 If the WBG decides to risk involvement in ambiguous and fluid situations, it pays not to do so in overly detailed and rigid ways. Utmost clarity is needed o n the objectives, principles, and parameters, but the design and implementation modalities should be as fluid as the situation itself, rather than rely on binary choices and numerical rules. This approach, however, may in practice foster a propensity to make successive small compromises, cumulating in the risk that continued Bank engagement may result in acquiescence to inefficient use o f resources. Thus, in addition to clarity o f purpose, an adaptable engagement grounded on flexible but robust dialogue requires a strong fabric o f reciprocal trust between staff and management and continuity o f both. 4.6 Revenue transparency i s necessary-specially for revenues from extractive industries-but i s not sufficient. Transparency on the expenditure side i s critical as well. In this case, setting as the main target a global minimum percentage spending on several sectors implied that the global target could be met even if the intersectoral allocation o f the resources was very different from what had been agreed, and without regard to the efficiency o f their use. 4.7 Project design must be based on recognition o f institutional and administrative capacity. I t i s important in countries with weak capacity to focus on addressing the basic problems rather than attempting to introduce sophisticated practices. In this case, paradoxically, major components o f the program in effect assumed the prior existence o f the very capacity they aimed to build. 4.8 An innovative design, even if it proves unsuccessful, may contain novel elements worthy o f consideration and possible replication. In this case, there are three such elements\. The formation o f the Collige de ContrGle was an excellent and exciting idea, even if it did not enjoy the necessary government support-and such joint publidprivate/ NGO entities have the potential to foster expenditure efficiency as well as social accountability in countries with a government reasonably interested in a prodevelopment, pro-poor expenditure policy. The Provisional Committee to allocate the 5 percent o f the direct o i l revenue to the oil-producing region can be an illustration for similar arrangements in other countries with valuable mineral resources, despite flaws in i t s operation in this case. Finally, the cover and voice given to local NGOs through the dialogue on the preparation o f the program and during i t s implementation should be a regular feature o f all such WBG interventions. WBG PERFORMANCE 4.9 Although in complex and high-profile cases strategic guidance and major decisions must come from the top leadership o f the WBG, it i s not clear in this case that the top-down direct intervention by the Bank President's Office in 2006 was helpful to formulate a new agreement with a better chance o f enforcement. 4.10 In large, complex WBG projects with multiple stakeholders, good WB-IFC cooperation i s important to improve the chances for positive results. In this case there was good WB-IFC cooperation on the main pipeline project, but it also extended to Advisory Services operations. In late-2004, when the IDA-funded capacity-building projects were found to be progressing slower than expected, IFC was able to provide new funding for sustaining the capacity-building initiatives. 4.1 1 IFC's Advisory Services have a signijkantpotential role to help the local private sector. They can enable local companies to participate in the economic activity created by the project; help the sponsors-typically large multinational corporations-meet national content 47 requirements; and promote local economic development. In this case, the Enterprise Center-the focal point o f IFC's Chad SME program-became the cornerstone o f Exxon's procurement platform that was the sole source for all o f i t s purchases in Chad, starting in 2005. 4.12 Whether the World Bank or the I F C i s involved, the concern with development effectiveness goes beyond the gates o f individual projects-however well they may be technically done-to the results o f the overall program. There i s no contradiction between viewing favorably the technical and financial success o f the pipeline project even though the weight o f other unfavorable outcomes leads to a negative conclusion o n the development outcome o f the program o f which it was a component, as in this evaluation. However, the evaluation illustrates the basic point that a part o f a program, however well carried out, cannot be separated from the overall program and the broader setting within which its impact i s being assessed\. a project or a subproject cannot be ring-fenced in the assessment. 4.13 Continuity is critical to manage a project that i s central to a program, and a minimum o f in-house technical competence is necessary to supervise consultants. In this case, the revenue management project had six task team leaders in its seven years, and the Chad capacity-building project relied almost entirely on consultants for the first years, without any in-house expertise in the technical dimensions o f o i l exploration and production. 4.14 Good communications and transparency are particularly important in the context o f a difficult decision. Senior management would want to appropriately consider the views o f key operational managers and staff and ensure the fullest possible measure o f advance consultation with key development partners. IMPLICATIONS FOR THE FUTURE MAJOR 4.15 With substantial o i l revenue expected to continue for many years, it i s s t i l l possible for Chad to escape the resource curse. The difficulties are known. Institutional and organizational capacity remain weak. Macroeconomic sustainability i s injeopardy. Fiduciary risk i s likely to increase in the short t e r m with the unexpected fall in o i l price and revenue in 2009 and 2010-producing pressures to preserve security and regime maintenance expenditures, and hence a downward pressure on pro-development, pro-poor expenditure. Budgeting systems and skills remain quite insufficient for efficient resource allocation, and motivation and integrity have been weakened by the lack o f consequences for the spreading non-compliance with fundamental rules. However, there are scenarios under which a good development outcome in the long run is s t i l l conceivable. The Bank could cooperate with the IMF in monitoring overall fiscal and expenditure outcomes and make a useful contribution by providing good and flexible advice in public sector management-focused o n the basics, recognizing capacity realities, and supported by assertive cooperation o f certain major bilateral partners. But the most important factor would be a new and genuine determination by Chad's government to use the o i l resources for development and poverty reduction, and do so responsively and efficiently. 4.16 The Chad-Cameroon o i l development and pipeline construction program exemplifies the inherent tension between the limits o f the WBG as an international organization and i t s mandate to foster development and poverty reduction. The WBG went very far in 1999 toward the development side, by setting up complicated and prescriptive arrangements to maximize the probability that the Chad government would use the o i l revenue windfall mainly for development and poverty reduction. For various reasons, the revenue windfall turned out to be used in large part for military expenditure and other regime maintenance and for wasteful construction. The governance climate in Chad did not improve-rather the reverse. 4.17 However, it should not be concluded from this experience that the WBG should not intervene in supporting extractive industries because doing so carries reputational risks and success i s unlikely. Indeed, despite the disappointing overall outcomes o n the development and governance side, WBG involvement contributed to a notable increase in expenditures in social sectors and environmental and social protection within the confines o f the project better than they would have been otherwise. The analysis o f this report suggests that realistic and constructive WBG involvement in extractive industries could rest o n combining an insistence on high standards o f environmental and social protection with flexible conditionality o n the composition o f all expenditure and its efficiency-complemented by assistance to strengthen a unified budget system, ensure transparency in both revenue and expenditure, and build capacity in accountability institutions. T o be effective, WBG involvement must be buttressed by an agreement with all other major donors that violation o f the environmental and social standards or backsliding o n fiscal transparency or accountability would trigger consequences for the overall f l o w o f aid t o the government concerned.
P048204 | Cameroon Petroleum Environment Capacity Enhancement (CAPECE) | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2000 | 2008 | 2010 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/603901474508379969/text/000020051-20140619084405.txt | http://documents.worldbank.org/curated/en/603901474508379969/pdf/000020051-20140619084405.pdf | Significant lessons from the project, including those mentioned in the ICR, are as follows:(a) Setting PDOs: When seeking to improve capacity from a low base, expectations from a project should be realistic and may prove to be counter-productive if they are too ambitious in their scope. In the case of this project, the focus should have been kept on the immediate needs relating to the Chad-Cameroon Pipeline rather than seeking to improve the larger environmental and social monitoring capacity of the country.(b) Packaging of TA components: A technical assistance project with a relatively small outlay should avoid the temptation of packing in too many interventions at multiple levels, which can result in a disproportionate amount of attention and energy being expended on procurement and logistics. In this project the large number of sub-components became all the more difficult to handle due to lack of familiarity and experience with Bank procedures. (c) Leveraging Investments: Capacity-building operations can work in a complementary manner with investment projects. While capacity-building projects are necessary to strengthen the overall policy and institutional framework, investment projects that are associated with them could transform these policies into actions on the ground while providing hands-on experience to the concerned institutions and staff.
P048204 | Cameroon Petroleum Environment Capacity Enhancement (CAPECE) | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2000 | 2008 | 2010 | PPAR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/565481468224677215/text/503150PPAR0P05101Official0use0only1.txt | http://documents.worldbank.org/curated/en/565481468224677215/pdf/503150PPAR0P05101Official0use0only1.pdf | 4. Lessons and Future Implications 4.1 The well-known lesson that government ownership and commitment are the major influence o n the effectiveness of projects and programs i s underlined by the experience o f the Chad-Cameroon program. Other lessons learned from the program are identified belowmany o f them also well known but brought in sharp relief by this experience. Because the findings and conclusions are discussed in the earlier sections, the lessons and implications are listed below with a minimum o f elaboration. (Project-specific lessons are included in the corresponding annex.) RELEVANCE, R I S K S , AND TIMING 4.2 International experience has shown that adequate expenditure management mechanisms should be in place, and tested, before a large revenue increase i s likely to accrue. In this case, the time available for capacity-building after Board approval and before the flow o f o i l revenue was much shorter than expected and the revenue much larger-adding to the difficulty o f building capacity contemporaneously with program implementation. A secondary lesson is therefore to build expenditure management capacity as robust as necessary to fit a high scenario o f revenue increase. (The capacity created will be useful to the country even if the high scenario does not materialize.) 4.3 Setting up institutional enclaves and special mechanisms to protect resources and accomplish quick results can damage local capacity in the long term. Such enclaves are generally not successful beyond the short term and, even when successful in the short term, they tend to undermine the already weak local systems and thus long-term development. In this case, although the rationale for the establishment o f the revenue escrow account and the earmarking arrangements was strong in the specific country context in 2000, when tested by reality these mechanisms failed to achieve their objectives and meanwhile stood in the way o f sustainable improvements in fiscal and expenditure management capacity. 4.4 While protecting inputs must remain a paramount consideration, development objectives should be formulated in terms o f outcomes (ifpossible), meaningful outputs, or concrete process improvements-rather than in terms o f inputs-and performance indicators should be limited to thefew key indicators that are critical to achieving the PDOs and are monitorable. Even when the immediate aim o f the project i s to increase resource availability, reduce the cost o f input acquisition, or channel resources toward priority uses, a failure to define clearly the expected results in terms o f key outputs, outcomes, or major process improvements risks distorting the actual design o f the project away from those results. In this case, defining the main project objective for Chad in terms o f budgeted expenditure to be achieved diverted attention away from the efficiency o f expenditure and budget execution. And to l i s t dozens o f key performance indicators o f diverse importance and questionable monitorability makes monitoring impossible. AND DESIGN APPROACH 4.5 If the WBG decides to risk involvement in ambiguous and fluid situations, it pays not to do so in overly detailed and rigid ways. Utmost clarity is needed o n the objectives, principles, and parameters, but the design and implementation modalities should be as fluid as the situation itself, rather than rely on binary choices and numerical rules. This approach, however, may in practice foster a propensity to make successive small compromises, cumulating in the risk that continued Bank engagement may result in acquiescence to inefficient use o f resources. Thus, in addition to clarity o f purpose, an adaptable engagement grounded on flexible but robust dialogue requires a strong fabric o f reciprocal trust between staff and management and continuity o f both. 4.6 Revenue transparency i s necessary-specially for revenues from extractive industries-but i s not sufficient. Transparency on the expenditure side i s critical as well. In this case, setting as the main target a global minimum percentage spending on several sectors implied that the global target could be met even if the intersectoral allocation o f the resources was very different from what had been agreed, and without regard to the efficiency o f their use. 4.7 Project design must be based on recognition o f institutional and administrative capacity. I t i s important in countries with weak capacity to focus on addressing the basic problems rather than attempting to introduce sophisticated practices. In this case, paradoxically, major components o f the program in effect assumed the prior existence o f the very capacity they aimed to build. 4.8 An innovative design, even if it proves unsuccessful, may contain novel elements worthy o f consideration and possible replication. In this case, there are three such elements\. The formation o f the Collige de ContrGle was an excellent and exciting idea, even if it did not enjoy the necessary government support-and such joint publidprivate/ NGO entities have the potential to foster expenditure efficiency as well as social accountability in countries with a government reasonably interested in a prodevelopment, pro-poor expenditure policy. The Provisional Committee to allocate the 5 percent o f the direct o i l revenue to the oil-producing region can be an illustration for similar arrangements in other countries with valuable mineral resources, despite flaws in i t s operation in this case. Finally, the cover and voice given to local NGOs through the dialogue on the preparation o f the program and during i t s implementation should be a regular feature o f all such WBG interventions. WBG PERFORMANCE 4.9 Although in complex and high-profile cases strategic guidance and major decisions must come from the top leadership o f the WBG, it i s not clear in this case that the top-down direct intervention by the Bank President's Office in 2006 was helpful to formulate a new agreement with a better chance o f enforcement. 4.10 In large, complex WBG projects with multiple stakeholders, good WB-IFC cooperation i s important to improve the chances for positive results. In this case there was good WB-IFC cooperation on the main pipeline project, but it also extended to Advisory Services operations. In late-2004, when the IDA-funded capacity-building projects were found to be progressing slower than expected, IFC was able to provide new funding for sustaining the capacity-building initiatives. 4.1 1 IFC's Advisory Services have a signijkantpotential role to help the local private sector. They can enable local companies to participate in the economic activity created by the project; help the sponsors-typically large multinational corporations-meet national content 47 requirements; and promote local economic development. In this case, the Enterprise Center-the focal point o f IFC's Chad SME program-became the cornerstone o f Exxon's procurement platform that was the sole source for all o f i t s purchases in Chad, starting in 2005. 4.12 Whether the World Bank or the I F C i s involved, the concern with development effectiveness goes beyond the gates o f individual projects-however well they may be technically done-to the results o f the overall program. There i s no contradiction between viewing favorably the technical and financial success o f the pipeline project even though the weight o f other unfavorable outcomes leads to a negative conclusion o n the development outcome o f the program o f which it was a component, as in this evaluation. However, the evaluation illustrates the basic point that a part o f a program, however well carried out, cannot be separated from the overall program and the broader setting within which its impact i s being assessed\. a project or a subproject cannot be ring-fenced in the assessment. 4.13 Continuity is critical to manage a project that i s central to a program, and a minimum o f in-house technical competence is necessary to supervise consultants. In this case, the revenue management project had six task team leaders in its seven years, and the Chad capacity-building project relied almost entirely on consultants for the first years, without any in-house expertise in the technical dimensions o f o i l exploration and production. 4.14 Good communications and transparency are particularly important in the context o f a difficult decision. Senior management would want to appropriately consider the views o f key operational managers and staff and ensure the fullest possible measure o f advance consultation with key development partners. IMPLICATIONS FOR THE FUTURE MAJOR 4.15 With substantial o i l revenue expected to continue for many years, it i s s t i l l possible for Chad to escape the resource curse. The difficulties are known. Institutional and organizational capacity remain weak. Macroeconomic sustainability i s injeopardy. Fiduciary risk i s likely to increase in the short t e r m with the unexpected fall in o i l price and revenue in 2009 and 2010-producing pressures to preserve security and regime maintenance expenditures, and hence a downward pressure on pro-development, pro-poor expenditure. Budgeting systems and skills remain quite insufficient for efficient resource allocation, and motivation and integrity have been weakened by the lack o f consequences for the spreading non-compliance with fundamental rules. However, there are scenarios under which a good development outcome in the long run is s t i l l conceivable. The Bank could cooperate with the IMF in monitoring overall fiscal and expenditure outcomes and make a useful contribution by providing good and flexible advice in public sector management-focused o n the basics, recognizing capacity realities, and supported by assertive cooperation o f certain major bilateral partners. But the most important factor would be a new and genuine determination by Chad's government to use the o i l resources for development and poverty reduction, and do so responsively and efficiently. 4.16 The Chad-Cameroon o i l development and pipeline construction program exemplifies the inherent tension between the limits o f the WBG as an international organization and i t s mandate to foster development and poverty reduction. The WBG went very far in 1999 toward the development side, by setting up complicated and prescriptive arrangements to maximize the probability that the Chad government would use the o i l revenue windfall mainly for development and poverty reduction. For various reasons, the revenue windfall turned out to be used in large part for military expenditure and other regime maintenance and for wasteful construction. The governance climate in Chad did not improve-rather the reverse. 4.17 However, it should not be concluded from this experience that the WBG should not intervene in supporting extractive industries because doing so carries reputational risks and success i s unlikely. Indeed, despite the disappointing overall outcomes o n the development and governance side, WBG involvement contributed to a notable increase in expenditures in social sectors and environmental and social protection within the confines o f the project better than they would have been otherwise. The analysis o f this report suggests that realistic and constructive WBG involvement in extractive industries could rest o n combining an insistence on high standards o f environmental and social protection with flexible conditionality o n the composition o f all expenditure and its efficiency-complemented by assistance to strengthen a unified budget system, ensure transparency in both revenue and expenditure, and build capacity in accountability institutions. T o be effective, WBG involvement must be buttressed by an agreement with all other major donors that violation o f the environmental and social standards or backsliding o n fiscal transparency or accountability would trigger consequences for the overall f l o w o f aid t o the government concerned.
P048314 | Morocco Protected Areas Management Project | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2008 | 2009 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/136831474635643883/text/000020051-20140619105107.txt | http://documents.worldbank.org/curated/en/136831474635643883/pdf/000020051-20140619105107.pdf | The ICR highlights several relevant lessons: 1. the critical importance of formulating early on a fully functional financial system to ensure the efficient flow of funds for implementation of project activities; 2. the necessity to formulate a realistic project design grounded in practical and achievable activities with solid and measurable outputs; and 3. decentralized, multipurpose projects require close, constant, and efficient supervision, so that adequate staffing and budgets must be allocated to achieve this level of oversight and support. To this can be added, the importance of: (1) maintaining continuity of task team leaders to the extent possible, especially when borrower institutions are themselves in considerable flux; and (2) proactive management oversight and support to the task team for projects facing significant implementation problems for the very beginning.
P048315 | Protected Areas Management Project | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/459641474551762475/text/000020051-20140620065444.txt | http://documents.worldbank.org/curated/en/459641474551762475/pdf/000020051-20140620065444.pdf | The experience of this project highlights a number of useful generic lessons with respect to biodiversity conservation and effective project implementation more generally. The most important of these are the following: 1. Coupling park management with community development, including income generating/alternative livelihood activities, and awareness raising programs can be instrumental in generating local support for Protected Areas and biodiversity conservation. 2. Expectations about what can be achieved in the first phase of a participatory natural resource management project should be carefully managed. This includes informing communities of budget constraints when elaborating Community Development Plans (CDPs) to avoid long wish lists and encourage prioritization. 3. Readiness for implementation is key to effective project start-up. Participatory planning should start during the preparation stage, project institutional arrangements and monitoring and evaluation mechanisms should be established, and required procurement procedures should be advanced as much as possible.
P048357 | CENTRAL BANK TECHNICAL ASSISTANCE LOAN I | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/278931474513061367/text/000020051-20140612150146.txt | http://documents.worldbank.org/curated/en/278931474513061367/pdf/000020051-20140612150146.pdf | 1. Effective partnering may give the beneficiary (here the central bank) much latitude over the project. While this flexibility allowed details to be decided as the project unfolded, it entailed delays when the central bank's priorities were not clear (three central bank Presidents over the project's life).2. Defining departments and persons in the central bank responsible for various components helped the project weather changes (although not without delays).
P048389 | EMERG.REINT&RECOV CR | Eastern and Southern Africa | Rwanda | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1997 | 1999 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/456871474508633814/text/000020051-20140522101011.txt | http://documents.worldbank.org/curated/en/456871474508633814/pdf/000020051-20140522101011.pdf | First, emergency quick-disbursing operations should dispense with links to imports and follow the simplified procedures for adjustment operations. Second, when an emergency operation is founded on a reform program, the operation should track the progress of the program to promote the transition from an emergency outlook to a focus on sustainable development. Third, staff of implementing agencies would benefit from early training in disbursement and procurement procedures.
P048461 | ENTER & BANKING PRIV | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1999 | 2002 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/259021474512175099/text/000020051-20140612063732.txt | http://documents.worldbank.org/curated/en/259021474512175099/pdf/000020051-20140612063732.pdf | In spite of a difficult post-conflict situation, if there is commitment to reform at the highest level, even a complex adjustment operation may be quite successful.In complex bank or enterprise privatization cases, it pays to resort to specialized outside expertise early on in the process.
P048462 | Reconstruction Assistance to Republika Srpska Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/203311474396712797/text/000020051-20140604044047.txt | http://documents.worldbank.org/curated/en/203311474396712797/pdf/000020051-20140604044047.pdf | Initial assistance to war-affected farmers should not be on a strictly commercial basis, since market conditions and production support may not exist in a post-conflict situation. The poorest among them cannot be expected to contribute to full cost recovery.Despite their political sensitivity, project attention should focus more upon occupancy and tenure issues in the housing sector in a post-conflict situation.Institutional capacity can be strengthened through on-the-job training of local counterparts in the management and implementation of a project. Important assistance--especially concerning procurement matters--can be best provided through specialists based in Bank Resident Missions.Management of broad-based procurement though ICB and LCB can be too time-consuming in an emergency situation.
P048462 | Reconstruction Assistance to Republika Srpska Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2001 | 2004 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/520611468768015596/text/28288.txt | http://documents.worldbank.org/curated/en/520611468768015596/pdf/28288.pdf | Lessons * Even in very complex post-conflict situations, traditional Bank assistance in rehabilitating infrastructure and restarting business credit can yield very worthwhile results for the recovery of the war-affected borrower. l The Bank should avoid involvement in activities beyond its core competence. Inexperience and lack of familiarity with landmine clearance, for example are ingredients for failure. l Designs of projects that rely on PIUS for implementation can make for speedy disbursements, but should always include exit strategies to help governments move toward normal operations.
P048505 | Agricultural Productivity Improvement Project | Latin America and Caribbean | Mexico | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2003 | 2005 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/946411475078559464/text/000020051-20140612142500.txt | http://documents.worldbank.org/curated/en/946411475078559464/pdf/000020051-20140612142500.pdf | In countries like Mexico where Bank funds tend to be "non-additional" more than usual attention must be paid at the design phase to creating incentives for the line agencies to participate and to working out (before loan aproval) the details of a system for monitoring and evaluating project results. Projects that are assigned to the Bank's program of targeted interventions need to contain within their design the necessary mechanism to ensure that funds are indeed properly targeted.
P048505 | Agricultural Productivity Improvement Project | Latin America and Caribbean | Mexico | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2003 | 2006 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/565941468122353723/text/327321rev0pdf.txt | http://documents.worldbank.org/curated/en/565941468122353723/pdf/327321rev0pdf.pdf | 5. Findings and Lessons 5.1 Agricultural productivity growth has lagged in Mexico compared to other countries in comparable circumstances. Since 1980 cereal yields have risen by one-third in Mexico; in Brazil they doubled. In Mexico, agricultural value added per worker increased by 22 percent over the past two decades; in Brazil it rose by 139percent. 5.2 The three projects assessed here need to be viewed in the light of Mexico's weak agricultural productivity growth. The three projects could not by themselves have overcome this weakness; but they did not go as far as they could to improve productivity. 5.3 The design of the two irrigation projects assessed here was consistent with a push for higher productivity; but the expected results have not yet been delivered. The shortfall has little to do with the performance of the implementing agency (Comision Nacional del Agua), and is primarily a reflection of weaknesses in the incentive environment and the absence of institutions needed to generate and disseminate improved farm technologies. The Alianza program is explicitly intended to boost productivity but has not targeted its resources at farmers (generally smaller, poorer producers) who have the biggest potential for technical upgrade; a substantial share of the programs resources finance the replacement of existing technology rather than achieving upgrade to a higher technical plane. The Bank-supported input to Alianza (the ALCAMPO project) did not have the leverage needed to address this design weakness. 5.4 In addition to this general finding, this assessment makes the following specific observations\. Investments in irrigation in Mexico continue to depend substantially on public sector support and there is no indication of fiscal savings following the peak period of District hand over (see paragraph 3.39 above). Although there was an immediate improvement following transfer, the quality of irrigation services has not continued to improve since then (paragraph 3.44). User associations have taken only limited steps toward financial self-sufficiency (paragraph 3.25). Producers in the Districts have not substantially diversified into higher-margin crops (paragraph 3.29). Weak control over the rate at which water is extracted from dams and aquifers, and the non-measurement of water use is the biggest problem facing Districts and Units (paragraphs 3.41, 3.45). The absence of an integrated planning framework for Districts and Units makes it harder to address the growing problem of water scarcity (paragraph 3.14). The absence of adequate technical support to farmers is a continuing problemone that ALCAMPO did not adequately address (paragraph 4.10). 5.5 This assessment confirms the following OED lessons of broader relevance\. Projects need to dovetail with programs; but well-designedprojects can rarely turn around a poorly-designedprogram. This is a particularly important lesson for the Bank's work in Mexico where leverage is limited. Mexico has ample access to alternative sources of funding, private as well as public. In line with the Bank's poverty reduction mandate, its resources should be tightly targeted, rather than added to programs where there is a high potential for subsidies to be captured by better-off groups. The Bank's leverage may be substantially diluted when project fundsflow into a multi-state program in which state governments have considerable influence over the use to which resources areput. The number of interlocutors is so large that it may make it difficult for the Bank to influence the overall direction-of project as much as program. For example, it is often difficult to secure support of state governments for a monitoring and evaluation framework, particularly one that is of uniform design applying the same approach in all states. Also, ALCAMPO demonstrates how difficult it can be to persuade state governments to follow Bank procedures for procurement andjustification of expenses. Pvograms as large as Alianzn are candidatesfor formal impact evaluation. The main limitation of the FAOISAGARPA evaluation of Alianza is the absence of a control group of non-beneficiaries, a striking oversight given the level of funding committed. The evaluation should have sampled those who did not apply to the program; and those who applied but were rejected. (It is not clear that a list of the rejected is maintained.) Without this control it is impossible to assess claims about the program's leverage\. much of the investment (and the income growth attributed to it) might have occurred without a subsidy. Subsidies may have leaked to better-off groups who don't need them.
P048521 | JO-AMMAN WATER & SANITATION | Middle East and North Africa | Jordan | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/871021475094521356/text/000020051-20140618063429.txt | http://documents.worldbank.org/curated/en/871021475094521356/pdf/000020051-20140618063429.pdf | â€¢ Allowing the prospective bidders to bid on the percentage of the incentive fee was suboptimal and created more risks to the bidders. When given the opportunity to indicate the amount of fixed management fee and the amount of performance-based compensation (a percentage of the incremental improvement of the cash flow of the operation) the structure of the bids demonstrated that bidders were risk-averse and preferred to rely on the fixed fee. â€¢ Management attention should not be taxed by an over-diffusion of targets. Performance targets should be limited to those most tied to the problems at hand. The Operator should be given more leeway to propose innovative ways to manage and operate the system instead of focusing their energy on monitoring a large number of performance indicators.â€¢ Significant institutional improvements take considerable time to stick. When the private operator is entering a relatively weak environment, the duration of the MC should be six years and upwards since this is the minimum time to achieve significant improvements in such a weak environment.
P048522 | EMERGENCY FLOOD REHABILITATION PROJECT | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2002 | 2002 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/950351474635110282/text/000020051-20140607150119.txt | http://documents.worldbank.org/curated/en/950351474635110282/pdf/000020051-20140607150119.pdf | 1. Emergency projects, in particular, require strong political commitment and high-level oversight and coordination. 2. Selectivity is important in emergency projects, and although directing support to affected areas is necessary, community receptivity is also important for rapid implementation and sustainability.
P048588 | Local Government Finance & Development Project (LOGOFIND) | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/755151474648986974/text/000146597-20140619165109.txt | http://documents.worldbank.org/curated/en/755151474648986974/pdf/000146597-20140619165109.pdf | From the ICR: An Adaptable Policy Loan (APL) would be a more appropriate instrument [than a Specific Investment Loan (SIL)] to support a reform process aimed at improving the provision of subnational finance. Project design and desired outcomes should be kept realistic and achievable in an environment where institutional capacity is established to be wanting.Funding support to LGUs should be viewed comprehensively and in an overall context of broader fiscal transfer policies.LGU investment decisions are highly sensitive to the availability of "soft" loans and grants, as alternative sources of funding.IEG would add:A project whose implementation is stalled and is evidently failing to meet its objectives should be formally restructured. Such restructuring could reset objectives and performance indicators seeking the formal concurrence of the Board with the new direction proposed.When the failure to meet performance targets becomes evident during implementation, an evaluation should include a thorough assessment of why the original targets are not being met. Downgrading the targets to be achieved requires a strong case to be made as part of a process of restructuring. Retrofitting targets to suit the likely level of achievement should not be an immediate reaction.
P048606 | IND.COMPET&JOB CREAT | Eastern and Southern Africa | South Africa | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/824381475111499743/text/000020051-20140613064523.txt | http://documents.worldbank.org/curated/en/824381475111499743/pdf/000020051-20140613064523.pdf | Interventions to develop markets for business development services require an initial market assessment to determine the constraints to the demand for and/or supply of services. Similarly, efforts to develop vertical and horizontal linkages among firms require a good understanding of interfirm relationships and the incentives to collaborate.Especially in a new client relationship, it is useful to take stock of Government and Bank procedures and practices in order to anticipate and prevent delays in project implementation.Clear performance targets should be established during project design, and periodic measurement and feedback to agencies and contractors should be done during implementation.Projects or components that target specific disadvantaged groups need to maintain focus on that goal.
P048651 | HN Fourth Social Investment Fund | Latin America and Caribbean | Honduras | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2004 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/649121474570782449/text/000020051-20140612094047.txt | http://documents.worldbank.org/curated/en/649121474570782449/pdf/000020051-20140612094047.pdf | Based on the ICR, three key lessons are: When the mission of a Bank project is altered by events beyond Borrower and Bank control, it is essential that both parties be realistic about what can no longer be achieved. Recognition of the new reality and the resultant restructuring need to happen quickly to prevent resources from being used for purposes that are no longer viable.Social Investment Funds have the potential to play an important role in emergency situations, however, what happens in the immediate post-disaster period has an impact on the reconstruction process that follows, and often influences the long-term development of the country. The appropriateness of the social fund to address the emergency situation should be assessed in the light of alternatives available. Major disaster events provide no holiday from the exigencies of good practice. The experience of earlier FHIS projects was that, even without a disaster, more attention to the social aspects of sustainability was necessary. Reducing long-term vulnerability to disaster (as called for in OP8.50) requires high standards of construction and adequate attention to maintenance. Equally important, significant attention needs to be given to the social structure upon which the continued use of the project-built infrastructure will depend. Attention to these sustainability issues should never be left entirely to a follow-on.
P048651 | HN Fourth Social Investment Fund | Latin America and Caribbean | Honduras | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2006 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/397491468249687503/text/36592.txt | http://documents.worldbank.org/curated/en/397491468249687503/pdf/36592.pdf | 4. Lessons Three lessons are identified here. Lessonl\. While social funds are attractive for donors and can initially be successful in providing remote communities access to basic health and educational facilities, the experience o f the Honduras social fund shows that they are not a long-term sustainable solution for providing basic infrastructure. The maintenance issue, especially o f health and education facilities, goes beyond social funds and needs to be seriously addressed as a part o f the overall policy dialogue o f the Bank with the country. Social funds may contribute by training o f user committees, but that in itself can never be sufficient for securing maintenance. Lesson 2\. Because o f the apparent success in i t s core activity o f financing basic infrastructure projects, FHIS has been and continues to be attractive for donors for programs that do not belong to the core activity (example, the Basic Needs Program that involved funding for priority social programs in nutrition, childcare, training o f midwives, care for elderly and disabled, etc. and the Nuestras Rakes Program which involved social assistance for indigenous communities). However i t took much longer for the Basic Needs Program and the Nuestras Rakes Program t o achieve some efficacy. Currently FHIS has become a patchwork o f donor-financed programs. Donors should be cautious in channeling money to social funds for carrying out non-core activities. Lesson 3 \. FHIS had a positive institutional development impact in promoting decentralization by helping to strengthen local government capacities in project planning and implementation. However, once these capacities are strengthened, i t can be questioned whether donors should s t i l l fund small infrastructure projects through FHIS instead o f searching for more direct channels to finance local governments.
P048652 | UNIVERSALIZATION OF BASIC EDUCATION PROJECT | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/140661474659579278/text/000146597-20140619160917.txt | http://documents.worldbank.org/curated/en/140661474659579278/pdf/000146597-20140619160917.pdf | The ICR offers 13 lessons on project design and implementation that this ICR review concurs with. The following two are highlighted (with a slight adjustment from the ICR wording).Pilot experiences provide lessons that facilitate project implementation. In addition to lessons obtained from previously implemented projects, pilot experiences helped the PRONADE activities to move quickly, achieving the targets earlier than planned.In multiethnic and multicultural countries, education is not only a technical-pedagogical matter, but also a sociological issue that plays a key role on how to move forward. The conventional wisdom from pedagogical literature is that teaching and learning in a native language is critical to successful learning achievements in the first years of education. However, parents in Guatemalan indigenous communities requested that their children be taught in Spanish, since it was perceived as the way to overcome exclusion.
P048654 | GT TAX ADMIN. TAL | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/511981474493124129/text/000020051-20140618082217.txt | http://documents.worldbank.org/curated/en/511981474493124129/pdf/000020051-20140618082217.pdf | The ICR contains several lessons, but two stand out. First, in the area of tax reform, it is important for the Bank to persevere even in very difficult times, because tax reform issues are not only technical and institutional in nature, but primarily political. Second, in inherently controversial reform initiatives, such as tax reforms, communication campaigns are invaluable.
P048657 | Integrated Financial Management II | Latin America and Caribbean | Guatemala | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2003 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/971521474898065567/text/000020051-20140612070949.txt | http://documents.worldbank.org/curated/en/971521474898065567/pdf/000020051-20140612070949.pdf | 1. Project success hinges on Government commitment. A number of political decisions needed to be made expeditiously for this project to succeed, and this was only possible with a strong government commitment to the objectives of the project. Conversely, in the few areas where government commitment was lacking, such as restructuring the CGC, implementation was delayed, although it was ultimately successful. 2. Solutions which require development of new technical and computer programs should be avoided. Widely-available, off-the-shelf components facilitate implementation.
P048697 | MG-Urban Infrastructure Project | Eastern and Southern Africa | Madagascar | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/325381475075566846/text/000020051-20140613084527.txt | http://documents.worldbank.org/curated/en/325381475075566846/pdf/000020051-20140613084527.pdf | The level of municipal contributions needs to be set after an evaluation of their capacity to mobilize funds is completed.A labor-intensive approach is not always compatible with community preferences and infrastructure needs. Employment creation can be achieved through investment in local economic development.Improving infrastructure requires a long-term commitment. Involving municipalities, extending the project to more cities, and shifting the focus from subprojects to Priority Investment Programs of Municipalities (PIPMs) generated interest from local officials to intensify investments in their cities. To confront issues of economic development and revenue enhancement, better asset management and a more aggressive capacity building agenda is necessary.Improving infrastructure requires a concomitant effort to enhance municipal finances because maintaining infrastructure requires ongoing capacity and the money to purchase supplies, repair equipment, etc..
P048715 | ID: Information Infrastructure Development Project | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/424711474631004068/text/000020051-20140613032043.txt | http://documents.worldbank.org/curated/en/424711474631004068/pdf/000020051-20140613032043.pdf | Especially for a cross-sectoral project such as this, the design should carefully avoid involving too many agencies and government ministries and the complexities of implementation that their large numbers invoke.Alternative options of investment in the proposed IT improvements should be considered more aggressively up-front, in order to delimit project interventions to areas where commercial interests are presently not forthcoming.More efforts have to be made to provide IT services throughout the country in order to provide a greater stimulus to national development (not just Jakarta's, as often happened under this project).The convergence of IT services and markets necessitates more high calibre public sector institutions to skilfully and efficiently regulate this process. For successful M&E of this kind of project, with a clear focus upon assessment the achievement of development objectives, it is important to establish clearly understood and agreed baselines and sets of performance indicators.
P048756 | Private Participation in Infrastructure Technical Assistance | Latin America and Caribbean | Guatemala | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2004 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/499741475110038144/text/000020051-20140612072042.txt | http://documents.worldbank.org/curated/en/499741475110038144/pdf/000020051-20140612072042.pdf | 1. As the processes and stages of infrastructure reform frequently differ from sector to sector, PPI project designs should not be overly complex and should only concentrate on a few sectors at similar stages of reform. 2. The Bank should only support PPI where there is clear government commitment and ownership of reforms, as seen by actual steps made towards restructuring prior to Bank involvement. It is important to recognise in this regard that government commitment to reform in some infrastructure sectors may not necessarily signify similar commitments to reform in other sectors.
P048790 | Azov Black Sea Corridor Biodiversity Conservation GEF Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2007 | 2007 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/947121474487583687/text/000020051-20140615104911.txt | http://documents.worldbank.org/curated/en/947121474487583687/pdf/000020051-20140615104911.pdf | Thoroughly appraise intuitional capacity in former NSU states and provide support to build local capability. Particular problems that need attention are poor cross-sectoral coordination and lack of intersectoral management skills, and non-familiarity with free-market procurement and commercial financial management.GEF projects have to cognizant of and sensitive to the macro-political environment. This is not only a matter of awareness but also of timing. When there are pressing national political and economic management problems it is unlikely that biodiversity issues will receive much attention and grant recipient ownership my be very low.
P048791 | Protected Areas Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/517461474907622578/text/000146597-20140619165722.txt | http://documents.worldbank.org/curated/en/517461474907622578/pdf/000146597-20140619165722.pdf | The most important lessons (the first two of which are drawn largely from the ICR), are: 1. Government commitment and institutional capacity to mainstream biodiversity conservation in production landscapes should be carefully evaluated and the associated risks to, and institutional requirements for, achievement of this objective realistically assessed during project preparation and appraisal. 2. The extent to which traditional local land use patterns, such as sheep grazing, may be affected within new or existing Protected Areas and, thus, de facto, trigger the Bank's resettlement policy, should be carefully assessed up-front rather than after project implementation has already begun. 3 High quality technical assistance from peer organizations, such at the US National Park Service in the present case, can provide significant benefits in terms of helping to strengthen national capacity in Protected Area planning and management. 4. Appropriately designed and managed small grant programs can be an effective way of increasing local community awareness of the importance of, and involvement in, environmentally-friendly activities associated with Protected Areas, such as ecotourism, thus giving local populations a greater stake in biodiversity conservation.
P048795 | Baltic Sea Regional GEF Project - Phase I | Europe and Central Asia | Europe and Central Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2003 | 2007 | 2008 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/708611474940209646/text/000020051-20140618193909.txt | http://documents.worldbank.org/curated/en/708611474940209646/pdf/000020051-20140618193909.pdf | Among the various important lessons drawn in the ICR, one that especially merits highlighting is that "strong central coordination is necessary to ensure delivery of results in regional projects." A second one, which is also of generic importance, is that "the implications of political-economic changes must be assessed even for environmental projects." If anything this lesson might have been stated more strongly with an alternative ending: "especially for regional environmental projects" because environmental measures are often politically sensitive in any country and this even more likely to be the case when several neighboring countries are involved. A third lesson of more general relevance is that "limited GEF resources can still have a major impact if the policy environment is conducive and participants are committed" and, it could be added, the requisite technical and other capacity is sufficiently in place. Actual experience under this regional initiative, finally, also reinforces the importance of the three lessons highlighted in the ICR as having been incorporated into project design as "critical measures for success": (i) sustained political and public commitment to the long-term objectives of the program; (ii) a shared vision provided through a commonly prepared strategic action program; and (iii) a broad-based partnership to support implementation of the agreed actions.
P048825 | TN-Cultural Heritage | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2012 | 2014 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/127231474628308658/text/000020051-20140625224052.txt | http://documents.worldbank.org/curated/en/127231474628308658/pdf/000020051-20140625224052.pdf | The first two of the following lessons are drawn by IEG and the third is taken from the ICR:Once it becomes clear that a project's objectives and design no longer coincide with the strategy or priorities of the Borrower, the sooner the operation is restructured, the better: In this case, this was not done.A robust M&E framework requires up-front agreement with the implementing agencies concerning the importance and reliability of data and its collection: In this case, because the attention of the Project Implementation Unit was mainly directed towards construction activities, and because indicators on institutional reform, market development and stakeholder involvement in the sustainable cultural heritage development, were inadequate, monitoring of progress towards attaining the projectâ€™s development activities was weak. Risk evaluation on the ownership of, and commitment to, major sector reform plays a core role in setting appropriate and feasible project objectives and scope. The risk of weak coordination of implementing agencies was well analyzed during preparation, and the Steering Committee proposed to mitigate it. However, after the government policy changed, it became clear that not all the relevant stakeholders shared the same vision of sector reform.
P048851 | Commodities Market Development Project | Europe and Central Asia | Turkiye | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/916911474482867834/text/000020051-20140612093156.txt | http://documents.worldbank.org/curated/en/916911474482867834/pdf/000020051-20140612093156.pdf | (i) Expectations of the time needed to implement projects supported by Learning and Innovation Loans need to be flexible: precisely because the approach is innovative and not all obstacles can be foreseen. (ii) The development of draft legislation and the establishment of the project implementing unit should be conditions for loan effectiveness.(iii) Where major policy change is starting to occur, a small investment project can have substantial leverage and spillover effects.
P048852 | National Transmission Grid Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2008 | 2009 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/946671474632343265/text/000020051-20140619075550.txt | http://documents.worldbank.org/curated/en/946671474632343265/pdf/000020051-20140619075550.pdf | Based on the experience with this project, analytical reports from the Bankâ€™s energy practice, and IEGâ€™s evaluation study on â€œPrivate Sector Development in the Electric Power Sectorâ€, the crucial ingredients for successfully implementing difficult reforms in the electricity sectors of client countries would include the following:the Governmentâ€™s commitment--through tariff reform as one of the best ways to demonstrate concrete action--and its taking the driver's seat. (In this particular project, Turkey's prospect of EU accession was also a key driver of reform.)a clear roadmap for reform, often involving a long timeframe of 10 to 15 yearsthe consistent support of strong local champions buoyed by the Bankâ€™s persistence in pursuing sector policy dialoguethe Bankâ€™s foresight and agility to provide policy advice just at the right time to address issues of highest relevance in the reform sequencethe Bankâ€™s willingness to support high risk-high reward operations within a long-term lending program that allows crucial reform milestones to be carried out through successive lending vehiclesthe initial stages of reform already taking place when the Bank steps up its involvementThis ICR Review also endorses the lessons cited in the ICR regarding the resource intensity of reform-focused lending operations, particularly in terms of necessary TA and supervision; and the specific recommendation regarding the need to give more autonomy to TEIAS.
P048869 | BR SALVADOR URBAN TRANS | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1999 | 2008 | 2009 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/358221474906562296/text/000020051-20140619110250.txt | http://documents.worldbank.org/curated/en/358221474906562296/pdf/000020051-20140619110250.pdf | The ICR has identified a number of lessons and the more important are listed below:In planning large urban transport (metro rail) projects, the project design should allow for the possibility of splitting the lines into sections. This is critical if the project has to survive through difficult times such as an economic crisis leading to large devaluations and a lack of counterpart funds. The decentralization of urban service provision can improve service delivery as it puts more pressure on the locally appointed management to show results and be transparent and accountable. The Bank should continue to support decentralization efforts in urban transport service provision although it must be careful regarding operating subsidies that are required to take into account the buying power of the users who may have a very low-income. In decentralization, the role of the federal agency does not disappear but instead changes from service provider to that of: (i) setting standards of service, (ii) providing oversight and technical support to the sub-national levels that now provide the service, and (iii) allocating Federal funds among the sub-national governments. Therefore, future projects that support decentralization efforts should also include answers to the question of what happens to the Federal agency as the decentralization process advances. The experience with the Tribunal Federal de Contas (TCU) in this project and other Latin American countries suggests that the Bank could undertake research to illustrate Comptrollerâ€™s Offices best practice and share this among the agencies in the Latin America Region. It could also invite TCU representatives to courses on Bank procurement guidelines and to discuss advanced procurement methods, such as turnkey bidding processes. This training can be very important because in this project the TCU argued that it needed to know all the unit prices for the bids for the turnkey contract (the concessionaire did not disclose the unit price).
P048870 | BR MT STATE PRIV. | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/432921474665817181/text/000020051-20140607145031.txt | http://documents.worldbank.org/curated/en/432921474665817181/pdf/000020051-20140607145031.pdf | Conditions regarding liquidation/closures (often used inter-changeably) should be formulated more precisely. Closure means that all agencies and offices are closed, operations have stopped and most employees have been dismissed. Liquidation is a long process with steps not always under the control of the liquidator. Conditionality should refer either to the start of liquidation (decreeing liquidation and liquidator in office) or to completion of liquidation (extinction).Regulatory agencies are best established as early as possible to allow it to build-up capacity before the privatizations start.In a Federative Republic it is advisable and essential that key features of regulatory agencies be established in Federal laws in order to avoid easy changes to regulatory bodies created by State laws.The Bank should provide more specific guidelines on how to carry out the economic cost-benefit analysis of severance payments and on how to evaluate the restructuring of benefits.
P048870 | BR MT STATE PRIV. | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2002 | 2003 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/630131468743965662/text/25971.txt | http://documents.worldbank.org/curated/en/630131468743965662/pdf/25971.pdf | 5. Lessons Learned 5.1 The lessons learned are not particularly new, especially for those deriving from the technical assistance andcredit line loans. Indeed, they have beenreiterated inmany OED reports and PPARs. Major lessons o f general applicability from the five loans assessed include\. 0 Technical assistance which lacks a clear blueprint i s hardto manage, and provides too manytemptations to apply unallocated funds to low-priority activities. 0 Macroeconomic instability and the absence o f market-determined interest rates greatly increase the risk o f failure for financial sector loans, confirming the findings o f the Levy Report. 0 Credit lines (financial intermediary loans) are unlikely to be appropriate instruments for supporting financial sector reform. 0 Fullandcomplete accounting for project expenditures is a core Bankresponsibility. 0 Lending to sub-national governments can be a powerhl instrument for advancing specific country strategies. 0 Continuity o f Bank interventions across state administrations promotes lasting institutional change inBrazilian state governments. Sub-national programmatic loans may prove to be better instruments thantime-bound SRLs. A prime example is the regulatory agencies, which have sufferedbecause, once the SRLs closed, the Bank effectively abandoned the agencies while they were still intheir infancy. 0 A functioning regulatory agency with an establishedregulatory environment isvital to optimal privatization o fpublic services. 0 The benefits o f dialogue during loanpreparation and supervision can outweigh the importance o f the funding, when complex issues o fprivatization and regulation are being addressed. Officials inall three SRL states cited the Bank's informal technical assistance as the most important benefit they derived from these loans. 0 The SRLs were cumbersome instrumentsbecause o f their investment loan characteristics. Sub-national adjustment loans (SNALs) should be a major improvement, allowing the Bank and Borrower to focus on what is important -policy reforms -rather than the minutiae o f disbursement andprocurement.
P048983 | Reconstruction Project for Eastern Slavonia, Baranja and Western Srijem | Europe and Central Asia | Croatia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/544001475092531872/text/000020051-20140613071106.txt | http://documents.worldbank.org/curated/en/544001475092531872/pdf/000020051-20140613071106.pdf | Linking direct infrastructure investments to their possible consequences on the environment has important demonstrative and positive effects to build beneficiary and government ownership.Including land mine clearing activities within a larger civil work contract for building or repairing infrastructure or facilities increases efficiency by giving high priority to land mine clearance that is relevant to the work..The Bank should promote flexibility as an incentive to efficient Project management. The quality of procurement and the knowledge of Bank procedures by experienced teams contribute to increase competition and efficient financial management, eventually, translating into the generation of savings.
P049012 | Coastal Contamination Prevention & Marine Management Project (GEF) | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2008 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/927011474851972718/text/000020051-20140619105248.txt | http://documents.worldbank.org/curated/en/927011474851972718/pdf/000020051-20140619105248.pdf | Public-private partnerships can add unexpected value and benefits to projects, and should be systematically sought out, analyzed, and taken full advantage of during project preparation, design, and implementation. Involvement by local NGOs, universities, and research institutions in the matching funds grant program was one of the most successful elements of the project, reflected by the important contributions they made to the projectâ€™s eventual outcomes. Thus, the lesson learned here is the importance of considering and then attempting to align project activities with those of local civil society groups so as to leverage project resources and expand the project's ultimate impact/outcomes. Knowledge generation is a necessary, but insufficient without a means to leverage it to build public and political support to drive policy initiatives and reform. It does not appear that the borrower was fully committed to the PDO/GEO of this GEF project, as evidenced by the lack of and high turn-over of project staff in SAyDS, and then by the lack of funding to continue staffing to fully realize the development objectives of the project. Thus, building local knowledge and information-sharing networks is not enough in itself, nor an end in itself, but rather a means to a greater end when it is put to use. It is important to define realistic and measurable parameters of expected results or benefits to be achieved as a result of project interventions. In this project there was considerable confusion around the two PDOs and the three means selected to achieve them in the ICR. This created a ripple effect throughout the ICR in terms of failing to distinguish between outputs and outcomes or results. The almost total lack of targets for objectives and the dates by when they would be achieved (e.g., X % reduction in pollution loadings by year Y) made it very difficult to determine how to assign weights to the relative importance of various outputs' contributions toward achieving project objectives or desired outcomes. For example, how much reduction in marine pollution was expected to be achieved from ship-based sources relative to land-based sources, or what would be define as a â€œsuccessâ€ in terms of strengthening management capacity for biodiversity protection?
P049051 | BEPEKA AUDIT MODERNIZATION PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1997 | 2005 | 2006 | ICRR | >=10 million & <25 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/370711474629424325/text/000020051-20140613051154.txt | http://documents.worldbank.org/curated/en/370711474629424325/pdf/000020051-20140613051154.pdf | 1. Use of PIUs -- is it needed? The ICR says: "despite weaknesses and shortcomings, persistent and close attention of BPK enabled the project to get strong internal support at top management levels. As a result, BPK was able to innovate and strengthen the quality of its audits." The design involved the setting up of a project implementation unit (PIU) within BPK. However, the nature of a project to improve government audits in the public sector could possibly have had a stronger outcome, if BPK would have worked directly with the audit departments of the main line implementing agencies, without creating a PIU. By having a PIU, it may have undercut the extent of institutional support from across the range of line agencies. The alternative approach of not having a PIU would have been more in line with various OED findings on capacity-building and with Bank Operations Policy on strengthening country systems. 2. Lack of foreign dependence. BPK managed to operate its IT infrastructure and network on its own, with limited support from a local consultant as needed. The initial design from foreign consultants was substantially modified to fit the Indonesian context. This is a good case of transfer of skills and technology and lack of dependence on foreign technical input.3. How much training and where? The ICR points to the over-emphasis on foreign masterâ€™s degrees, which caused some attrition of trained staff, when they inevitably sought new jobs on their return. Nevertheless, the specialized training that BPK staff received helped to improve the quality of the audit function.
P049166 | EG East Delta Ag. Serv. | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/658701475088765148/text/000020051-20140624162805.txt | http://documents.worldbank.org/curated/en/658701475088765148/pdf/000020051-20140624162805.pdf | As noted by the ICR, this project offers a rich array of lessons. These are summarized here with some adaptation.1. A project preparation team should identify and verify for itself key outcome-determining factors, such as, in this case, irrigation and drainage operation requirements.2. A project preparation team should fully understand the lending policies of a participating bank to ensure consistency with the project objectives and design, particularly with respect to collateral requirements and interest rates.3. It is possible for restructuring to provide corrective measures to compensate for weak project design provided this is tackled early and decisively and has full borrower support.4. Project design teams should be particularly aware of the potential for coordination problems when there are many institutions involved in a project. In such cases, high quality management and clear lines of authority and areas of responsibility are particularly important. A strong PMU can substantially compensate for the coordination problems of multiple institutions.5. In large irrigation and drainage infrastructure projects aimed at attracting people to newly reclaimed land, social and community service components are particularly important to provide an attractive package of services to complement the infrastructure.
P049172 | Education Improvement Project | Europe and Central Asia | Latvia |  |  | Human Development | Education | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/887001474748758558/text/000020051-20140613043213.txt | http://documents.worldbank.org/curated/en/887001474748758558/pdf/000020051-20140613043213.pdf | It is possible to make old buildings more energy efficient and to increase the density of student population. Appropriate remodeling can be cost-effective, particularly in areas of low temperatures and strained environmental resources.- It is possible to increase the institutional competency of public agencies through intensive training, a clear communication strategy, and provision of high-level technical assistance.- Piloting activities are essential for the introduction of major instructional reforms. They give teachers the tools to communicate with students and colleagues and facilitate feedback regarding the process.
P049174 | Treasury Systems Project | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/699271474653084145/text/000020051-20140613051951.txt | http://documents.worldbank.org/curated/en/699271474653084145/pdf/000020051-20140613051951.pdf | Design of information systems such as the Treasury Data System should be based on functional rather than technical factors.Strong local capacity was important to project success. Both in the functional and technical areas, knowledge of local constraints was key to the design of an effective system.Close Bank/Fund collaboration was instrumental in project achievement.Strong Government support was critical to project success. As noted above, active support from a number of agencies was key to ratification of the project by Parliament.
P049200 | Social Development Fund (SDF) (APL #1) | Europe and Central Asia | Romania | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/557231474628364986/text/000020051-20140607151654.txt | http://documents.worldbank.org/curated/en/557231474628364986/pdf/000020051-20140607151654.pdf | The best facilitators and promoters are people from graduating villages.Decentralization measures are needed to shorten the period between sub-project submission and grants approval. Information, education and communications activities, directed at both beneficiaries and LAs, enhance effectiveness of the RSDF procedures and raise awareness and public support for partnership building, participatory approaches and community development.Beneficiaries can take responsibility for implementation, including contracting and procurement, provided sufficiently close monitoring and support is provided by SDF supervisors .
P049203 | SAL | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2002 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/262171474573874000/text/000020051-20140602103311.txt | http://documents.worldbank.org/curated/en/262171474573874000/pdf/000020051-20140602103311.pdf | (a) Ownership is essential for the success of an adjustment program; thus, the end vision must be clear, mutually agreed, and broadly owned at the outset, in a programmatic fashion. (b) Separate sectoral operations, back-loaded disbursements, and floating tranches should be used to assure a tighter linkage between increases in the country's debt to IBRD and the implementation of irreversible reform measures in a highly volatile political environment and varying degrees of commitment and capacity across sectors.
P049203 | SAL | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2003 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/625211468304275740/text/multi0page.txt | http://documents.worldbank.org/curated/en/625211468304275740/pdf/multi0page.pdf | 6. Lessons 6.1 The Bank's experience with the two RLs confirms a number of lessons that have been learned in other emergency support operations\. Assure flexibility in the use of rehabilitation loans and avoid pre-identification of specific imports. For operations designed to address key social needs and/or production bottlenecks, projects require a maximum degree of funding flexibility. Earmarking portions of rehabilitation loans complicates implementation and in some cases can delay disbursements beyond a time when they are urgently needed. * Ensure adequate supervision coefficients. For rehabilitation loans and emergency import projects, standard supervision coefficients may not be appropriate. This is especially for so for new borrowers unfamiliar with Bank procedures. * Sound macroeconomic management is a pre-requisite for the positive responses expected to flow from structural reform, under all policy-based type of lending. 6.2 The lessons from the Bank's experience with SAL I and SAL I1, although not fully recognized in the ICR, have been subsequently incorporated in SAL III\. * Broad country ownership is crucial. TIhus, it is important for the Bank to pay close attention to the political and institutional aspects of reforms and consult with all relevant units of government and civil society, so as to improve the relevance and design of its activities and avoid operations where commitment is weak. * In the face of a poor track record and narrow country ownership of reform, a large adjustment lending program, especially one with front-loaded disbursements, risks delaying rather than accelerating reform.22 * In the face of a poor track record and a new consensus on a reform program, adjustment lending should be available only after the government has publicly adopted the necessary reforms or has begun implementing them, as was the case for the Coal SECALs. Separate sectoral operations, back-loaded disbursements, and floating tranches should be used to assure a tighter linkage between increases in the country's debt to IBRD and the implementation of irreversible reform measures. Disbursements should be backloaded and carefully modulated on the basis of solid progress in implementation, including enforcement of laws and regulations.23 * There needs to be strong strategic coordination and integration of actors, instruments, and interventions supporting common objectives in programs 22 ECA management is skeptical that advice alone, however useful, could have carried much weight in Russia. 23 The Coal SECALs and SAL III, especially after their restructuring in 1999, were good examples of such an approach. The ECA Region's management, however, in their cormments to a previous ICR review by OED of SALs I and II and again to the Russia CAE, have questioned whether adjustment loans should only be offered after adoption of reforms. In their view, in cases where the Bank is called upon to provide adjustment lending to help resolve a rapidly unfolding crisis, for example, it is unrealistic to think that such support should only be provided when there is strong prior political ownership and consensus about the reform path. Moreover, there is often a lag in the take-up of new policies, as in Russia prior to the year 2000. supported by the Bank as well as by Russia's other development partners. For the most part, the TA provided to the Russian authorities under SALs I and II worked well in the design of specific measures and in their implementation. But in some areas, the integration between TA and on-the-ground implementation of policy measures was insufficient, such as in the financial sector. 6.3 Common to all four operations as well as the rest of the Bank's assistance in Russia are other important lessons\. * The Bank should pay attention to the quality of public institutions and governance. While considerable Bank support has been provided for institutional development since the inception of the Bank's program of assistance to Russia, the problem of governance was not frontally addressed. It is clearly a serious impediment to development-the absence of rule of law, for example, has been one of the most serious deterrents to foreign direct investment and a major factor behind capital flight. The issue has been complicated by the weak tradition of property rights, exacerbated in the communist period, where control rather ownership has long been the basis for the beneficial use. It has also been complicated by the major distortions in Russia's post-communist economy, which have created all kinds of perceived inequities, and by the use of wild accusations of corruption as a standard part of the political battle. In terms of ensuring that the funds it lends are safeguarded, the Bank should address the important challenge of improving the overall quality of expenditure controls and accountability in Russia's budgetary system. * Keep windows of opportunity in perspective. One of the clearest lessons from all the Bank assistance in Russia is the under-estimation of the complexity of the task of structural reformn. Deep-rooted political, social, and individual behavioral changes are necessary before the transformation will be complete. This will take time-perhaps another generation. In this context, the focus must be maintained on structuring operations that bring about and support the implementation of mediumand long-term structural change, not quick fixes. This is another argument for TA and multiple-tranche operations, in support of well-articulated medium and long-term reform roadmaps.
P049265 | RECIFE URBAN UPGRADING PROJECT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2011 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/818841474483039453/text/000020051-20140625231228.txt | http://documents.worldbank.org/curated/en/818841474483039453/pdf/000020051-20140625231228.pdf | 1. Defining project sub-areas for project improvement based on technical aspects, rather than political or administrative boundaries, can improve project performance, by increasing legitimacy, decreasing political interference, and facilitating an integrated public infrastructure improvement approach. (IEG, adding to ICR). In this project, the improvements were based on "sanitation collection units" (UEs).2. A resettlement plan should be based on objective criteria of need and eligibility, grounded in data collected in a census, usually carried out early in project implementation, if not prior to appraisal. Even if a resettlement plan calls for the implementation to be carried out in stages, the eligibility criteria must be clearly planned and communicated to the Government and the affected population at the outset. The Bankâ€™s Resettlement Policy (OP/BP 4.12) recommends setting a cutoff date at the same time that the census is completed. After this date, no entitlements should be offered to people who settle in the area or make improvements to their homes or businesses. Making these conditions clear would take political pressure off the Government to provide entitlement to new squatters. (IEG, restating lesson in ICR)3. Planning of Urban Upgrading projects should incorporate a review of the urban zoning regulations, and processes to consult existing and potential residents, to ensure alignment of the regulations with the aspirations of the residents, and the economic development opportunities. (IEG, broadening ICR author's lesson). In this project, the Borrower decided to build single family dwellings and town houses, to preserve the traditional way of living of poor families, while upgrading infrastructure; it neglected to consider the need for formal business spaces. As a result, many new residents expanded their homes to accommodate informal businesses, such as bars, hair dressing and convenience stores, which did not fully satisfy their needs, or the preferences of other residents for mixed development.4. When assigning implementation responsibility for complex investment programs to inexperienced sub-national agencies, project-specific institutional capacity assessments should be carried out, to determine if components for technical assistance need to go beyond the conventional WB project management processes, to include technical support , including those related to safeguard compliance. (IEG)5. Preparation for complex urban upgrading projects incorporating resettlement should include review of land use and land titling laws, and plans should be made to regularize tenure of all residents, not just those benefitting from the project, so as to avoid inequities, (IEG)
P049267 | UY TRANSPORT II | Latin America and Caribbean | Uruguay | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2004 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/594271474490235279/text/000020051-20140612132300.txt | http://documents.worldbank.org/curated/en/594271474490235279/pdf/000020051-20140612132300.pdf | Several important lessons are identified by the ICR. Three are repeated here for their broad applicability:The strict policy of prioritizing maintenance in times of budgetary crisis can stall road deterioration to a limited extent. However, after a point in time there is a need for a reasonable amount of more costly periodic maintenance and rehabilitation investments, otherwise the road assets value will inevitably decrease.The CREMA-type performance-based contractual arrangements are powerful instruments to carry out road maintenance and rehabilitation in an efficient and effective way even in a situation of budgetary pressure. The decline in road sector funding and uncertainties regarding future funding adversely impacts implementation of institutional initiatives that are piloted under the Bank funded project. For example, MTOP could not further expand the micro-enterprise program with former DNV staff and the performance agreements between DNV and some of its maintenance Districts, or launch new CREMA contracts, for all of which there was strong interest among potential participants but unclear ability to meet their funding requirements on a timely basis.
P049268 | AR-SOCIAL PROTECTION 2 | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1997 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/502271474852104268/text/000020051-20140528123407.txt | http://documents.worldbank.org/curated/en/502271474852104268/pdf/000020051-20140528123407.pdf | 1. In a public works program meant to alleviate poverty, close monitoring is needed during project execution to ensure that targeting is working. 2. Effective monitoring and supervision of subprojects including periodic on-site visits, is essential to ensure high quality of works.
P049269 | AR-Social Protec.3 | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/315741474898112651/text/000020051-20140612073820.txt | http://documents.worldbank.org/curated/en/315741474898112651/pdf/000020051-20140612073820.pdf | Based on the ICR, a number of lessons are highlighted below: The cost effectiveness of safety net programs like TRABAJAR depends in large part on the value of the assets created through the subprojects. Effective subproject evaluation, monitoring and supervision are critical to ensuring that the subprojects produce benefits for poor communities that go beyond temporary income transfers to unemployed members. To ensure proper targeting of the poor, close monitoring is necessary during project execution. Project management can bemuch strengthened if resources are allocated (at appraisal) to carry out rigorous, high-quality evaluations during project execution and the results are used to inform decision-making.Self-targeted public works programs can successfully reach the poor, provided the wage rate is set no higher than the ruling market wage for unskilled labor.
P049290 | Nam Theun 2 Social and Environment Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2005 | 2018 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/771561570478690919/text/Lao-Peoples-Democratic-Republic-LA-Nam-Theun-Social-Environment.txt | http://documents.worldbank.org/curated/en/771561570478690919/pdf/Lao-Peoples-Democratic-Republic-LA-Nam-Theun-Social-Environment.pdf | 1) While a comprehensive approach to hydropower development that was applied to NT2 is consistent with prevailinggood practice, it may have also led to some targets that extend beyond the capacity of the project (implementing agencies) todeliver. Although the entire NT2 effort may be considered ambitious given the circumstances, establishing a new agencysuch as the WMPA and entrusting it to develop the capacity to carry out a mandate of no further degradation of habitats orin declines of threatened species may have been unrealistic. This is especially the case since illegal logging and poachingin the area pre-dated the WMPA, and eliminating these activities altogether may have been beyond the existing capacity of the newlyestablished agency.2) The NT2 appears to have spillover effects that have contributed totransformational impacts in policies that may have paved the way for future hydropower investments in Laos Given the scaleand complexity of NT2 and its first-of-its-kind nature in the country, the project provided a premise to impact the overall policyand institutional frameworks for sustainable hydropower development in Laos. The PPP and ES frameworks in particular appear tobe formalized and mainstreamed (although the design was thought by some to be gold-plated and not conducive toreplication), and being applied in many hydropower projects that have been developed in Laos sinceNT2.3) The World Bank (and other IFIs) commitment at the early stage of a PPP program appeared to haveprovided the necessary confidence to the private sector, especially when attempting to undertake large-scale financing in a lowcapacity country. While the total IFI guarantees were modest in scale, it was a requirement for the internationaldollar financiers for extending loans to NTPC. The involvement of the IFIs through the guarantees seems to have provided theinitial confidence to extend financing with the assurance that the GoL will honor its obligations under the project. The GoLhonoring its obligations to date under NT2 may have contributed to investor confidence where such backstops were not as critical todeveloping subsequent hydropower IPPs.4) The long 12-year World Bank implementation periodprovided sufficient time to oversee the progress with key outcomes and adapt as necessary to improve performance. Whilesuch an extended implementation period is not common for World Bank projects, NT2 had the benefits of a longer-than-typicalimplementation period that was resourced by a charge to NTPC once the project was approved (i.e. after financialclosure). This partially enabled the oversight and validation of the power plant operation and export potential (ability to absorbelectricity in Thailand) since the project closing date was sevenyears past commissioning. In addition, it provided adequateoversight during the implementation of the ES plan, which required several adjustments to deliver the final results. While thelength of implementation for NT2 may be exceptional, other infrastructure projects with long gestation periods maybenefit from a longer period pf World Banks implementation support.5) Identifying a qualifieddeveloper and vesting GoL interests in the hydropower operation appear to have provided a smooth pathway to constructing thehydropower project in a timely and cost-effective manner. The selection of a well-qualified developer as the primaryequity holder in the NTPC consortium appears to have played a major role in the efficient construction and operation of the dam andpower facilities with very modest cost and time overruns. Additionally, the GoL, committing through its equity in NTPC (throughLHSE) and the guarantees backstopped by the IFIs also provided incentive for it to honor its obligation in terms of policy andregulatory aspects.6) Extended project preparation contributed to the initially quick start and efficientimplementation of the project. While the NT2 underwent a preparation period of unusual length of about a decade, thesignificant work carried out in this effort led to numerous benefits. By World Bank Board approval, many necessary policies wereissued and institutions established. The extended analysis and appraisal enabled informed risk taking such as the future offtakecapacity of electricity exported to Thailand, a decision that has subsequently been validated. The project design and feasibilitywork were also fully completed by project approval with the selected developer ready to proceed with financial closure andimplementation. As a result, the project was made effective less than two weeks following Board approval, and a large and complexhydropower facility was constructed within budget with only minor delays.
P049296 | ECONOMIC MANAGEMENT TECHNICAL ASSISTANCE | Latin America and Caribbean | Nicaragua | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/367001475077269950/text/000020051-20140613045639.txt | http://documents.worldbank.org/curated/en/367001475077269950/pdf/000020051-20140613045639.pdf | Strong political commitment was key to the achievement of substantially increased capacity in economic and financial management.Dealing with a politically sensitive issue such as Civil Service Reform, the Bank needs to take time to make a thorough assessment of the political ground that needs to be covered in order to achieve reform.
P049301 | A.P. EMERG. CYCLONE | South Asia | India | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1997 | 2004 | 2004 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/592561474939508823/text/000020051-20140612103148.txt | http://documents.worldbank.org/curated/en/592561474939508823/pdf/000020051-20140612103148.pdf | 1) Combining long-term disaster mitigation activities into a three-year emergency reconstruction project proved to be unrealistic. As a result, some of the disaster mitigation activities were not completed within the expected time frame. Long-term disaster mitigation requires a longer period of time, extensive capacity building and, most importantly, strong ownership on the Borrower's part for successful mainstreaming into state-wide developmental efforts.2)?Greater involvement of local Bank staff towards the end of the project produced more continuous, hands-on supervision, as well as more timely follow-up in resolving project implementation issues.
P049385 | AP Econ Restructuring | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/936211474504603943/text/000020051-20140617140657.txt | http://documents.worldbank.org/curated/en/936211474504603943/pdf/000020051-20140617140657.pdf | The ICR contains a number of useful lessons beyond the usual lessons on the importance of ownership including particularly (with some selection and adaptation):1. Synergistic opportunities in multi-sector projects must be identified at the design stage and pursued in implementation. An over-arching strategy and over-arching set of development objectives at the outset is important for achieving this.2. Early funding and initiation of baseline surveys, with at least the M&E design and any contracts for the baseline ready for approval ahead of project effectiveness, would help to ensure actionable and timely M&E findings.3. Great care is needed in the choice of indicators that they not only reflect the intent of the project but are also measurable and, to the extent possible, test attribution.4. The ICR contains also some other useful sector lessons worth referring to.
P049386 | GT RECONSTRUCTION & LOCAL DEV. | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/530601474420739904/text/000020051-20140617134919.txt | http://documents.worldbank.org/curated/en/530601474420739904/pdf/000020051-20140617134919.pdf | Design projects and institutional arrangements to ensure commitment and ownership at the Government level. The experience of this project illustrates the lack of commitment and ownership at the Government level. Special attention to Government priorities and needs, and adaptability to a changing economic context must be considered at the preparation stage to avoid delays at project implementation.Use a monitoring and evaluation (M&E) system to follow key outcome indicators. The project did not develop an appropriate M&E system to effectively assess outputs, outcomes and impacts. As a result, PCU staff was unable to monitor progress towards fulfillment of development objectives. Specific measurable indicators and targets are essential factors to incorporate into project design.Prepare upfront an Operations Manual incorporating key project design features prior to loan effectiveness.Incorporate a participatory approach throughout implementation to foster ownership and sustainability. This project lacked training activities, especilly with respect to operation and maintenance. In order to avoid this, permanent training activities and communication strategies must be put into practice to assure the sustainability of subprojects.Creating a PCU in parallel to a line agency can hamper implementation rather than support it. Countries' and the Bank's priorities are increasingly focused on strengthening institutional structures to carry out operations and improve sustainability to address specific needs. In this particular project, a separate PCU created a parallel structure at the regional level, which left little capacity to improve the Government's institutional and administrative organization. Establishing a PCU with a mandate to implement the project in San Marcos, where FONAPAZ also had a field office, resulted in poor coordination, lack of ownership by FONAPAZ, and inefficiency.
P049395 | ENERGY ACCESS PROJECT | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2003 | 2013 | 2016 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/499931468185393338/text/ICRR14821-P049395-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/499931468185393338/pdf/ICRR14821-P049395-Box394823B-PUBLIC.pdf | The ICR presents seven lessons; the three most important are summarized below:Multi-sector energy project without a strong, centralized cross-sector institutional focus can result in a loss of commitment and underachievement of objectives. EAP was committed to simultaneously expand access to modern energy and increase the availability of biomass energy but it appears that the appraisal team misread the ownership of the biomass component by the Ministry of Agriculture and Rural Development. If project scope and design are not tailored to the institutional capacity of the implementing agencies, there is a substantial risk of delays and limited achievement of project objectives. the was extremely ambitious in design, scope, institutional framework, objectives and time framework for project completion. There were three major investment components, each implemented by a different ministry or implementing agency, as well as an institutional and capacity building component. With hindsight, in a country with weak institutional capacity, there probably should have been three separate projects, one for each major investment component: rehabilitation of the distribution system, expansion of electricity access, and improved biomass management. Detailed coordination of rehabilitation work for urban power distribution systems with city planning authorities is essential. The master plan for urban development in the city reportedly changed frequently during project implementation, often without warning, causing delays in the rehabilitation work. Similarly, lack of prioritizing and sequencing of investments caused a shortage of building materials, higher prices and implementation delays.IEG adds one further lesson:Ensure that supervision missions have enough staff , skills and time to adequately examine project implementation and report realistically on findings. In this project, supervision was very thin mainly because the majority of missions had to cope with a sector-wide brief or up to 6 projects. As a consequence, most attention was given to solving implementation bottlenecks of the most visible and problematic projects, and routine, systematic and thorough fieldwork seems to have suffered as a result.
P049436 | CHONGQING URBAN ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2009 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/242551474594071083/text/000020051-20140624160951.txt | http://documents.worldbank.org/curated/en/242551474594071083/pdf/000020051-20140624160951.pdf | In formulating project objectives, project designers have to consider the baseline upon which improvements can be made, to establish targets for achieving the intended outcome, and select performance indicators to measure progress toward that achievement. Thus, in aiming to supply adequate safe water for a growing population and economy, this project should have made the counterfactual and baselines of unsafe water explicit, as well as setting targets, whose achievement could be measured by indicators of water quality in the supply.Where professional standards in component design and construction supervision by local design institutes and consultants may be uneven, as the ICR reports they were in the case of this project, it is important that project preparation verify that local mechanisms for redress exist in cases of professional negligence.The Bank's traditional wastewater utility model designed for where a utility itself directly controls the financing of its own service provision (and can therefore be held responsible for meeting project financial covenants), cannot apply to a situation where a single municipal holding company exercises these responsibilities on behalf of the utility, as in the case of this project.Bank and Borrower need to deploy more resources for project preparation and implementation in smaller and more remote cities that have less experience of project design and of working with the Bank.
P049448 | BANKING SECTOR REF | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1998 | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/893741474590928140/text/000020051-20140521034703.txt | http://documents.worldbank.org/curated/en/893741474590928140/pdf/000020051-20140521034703.pdf | The ES agrees with the ICR that full government ownership is critical to success, that dealing with the underlying governance and corruption issues is a bold and necessary approach to addressing the root causes of problems in the financial sector, and that sequencing reforms is important.
P049477 | KERALA FORESTRY | South Asia | India | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/839501474486897818/text/000020051-20140612134320.txt | http://documents.worldbank.org/curated/en/839501474486897818/pdf/000020051-20140612134320.pdf | The ICR notes a number, the most generally relevant of which are: Community participation, if established on a sustainable basis with adequate and equitably distributed benefits, has proved to be a highly effective and efficient means of ensuring protection of natural forests from fire and biotic influences, and managing fragile ecosystems. Site specific, bottom-up planning provides not only a more realistic approach to forest and plantation management, but engenders a greater sense of involvement and responsibility amongst divisional and field staff. Early and transparent agreement on policy reforms and immediate emphasis on agreed institutional strengthening are key to underpinning successful project implementation and sustainability.
P049502 | Enterprise Development Adjustment Loan 2 (EDAL 2) | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2000 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/594541474486291321/text/000020051-20140528115754.txt | http://documents.worldbank.org/curated/en/594541474486291321/pdf/000020051-20140528115754.pdf | When a government is committed at high levels, despite divisions within itself, to a well designed reform program, and has strong, well coordinated support from the donor community, it can move forward quickly to implement the program. However, it would have been useful to involve participants from a greater variety of political spheres to encourage greater cooperation between the Government and Parliament.
P049502 | Enterprise Development Adjustment Loan 2 (EDAL 2) | Europe and Central Asia | Ukraine | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2000 | 2001 | PPAR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/533691511189144974/text/multi-page.txt | http://documents.worldbank.org/curated/en/533691511189144974/pdf/multi-page.pdf | 6. Key Lessons Learned\n6.1 The first lesson, consistent with experience in other countries, is that combining\nstructural adjustment with a complex technical assistance component makes a project\ndifficult to manage. In this case, it has slowed the completion of EDAL I. The objectives\nof the TA component were sound\. to learn how to restructure and improve the\ncompetitiveness of firms swept up in the privatization process, and to test out methods of\nassisting them. The results and lessons are now emerging, and a majority are promising.\nBut the TA component might have been better designed as a separate project, financed\npartly by grants from other donors.\n\n\n11\n6.2 A second lesson is that early involvement of participants from a variety of\npolitical spheres-including the Parliament-might have improved the country level\nsupport for reform.\n6.3 Another lesson that emerges from this experience is that a large and ambitious\nproject can rally donors together to support it and coordinate their actions based on a\nsensible division of labor. In EDAL I and II, many policy reforms were required in\nsynchrony, with advice from many donors. Obtaining timely and intelligent TA in this\nmanner may prove difficult in future projects, but the Bank with its limited resources will\nhave to continue to rely on other donors. The largest of them have more staff in the\ncountry and some offer grant money and specialized expert services.\n6.4 A key lesson emerging from the TA component, which will be applied in the PSD\nproject, is the great value of training Ukrainians, both as consultants and within firms,\nwith each recipient of training in turn training others; this technique is establishing a\nnetwork of Ukrainians who can bridge the gap in understanding between Western\nconsultants and former Soviet managers. Other lessons include the feasibility of low-cost\nrestructuring of enterprises on a large scale with Ukrainians providing most of the\nconsulting advice under the supervision of outside consultants; the feasibility of turning\nsome bankrupt firms around through consultant assistance; the value of creating and/or\nstrengthening crucial professional associations; and the value of a battery of multimedia\ntraining courses, given by Ukrainians to large numbers of managers and high officials of\nprivatized enterprises, with Ukrainian firms serving as case studies.
P049531 | Financial Enterprise Structural Adjustment Loan (FESAL) | Europe and Central Asia | Bulgaria | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1998 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/390511474492122761/text/000020051-20140526211235.txt | http://documents.worldbank.org/curated/en/390511474492122761/pdf/000020051-20140526211235.pdf | Coordination among the IFIs is essential to support reforms of the kind pursued in the EFSAL, and this is a case where the division of labor between the IMF and the Bank appears to be satisfactory. Continuity of task management has a high payoff in efficiency and effectiveness.
P049537 | AP POWER APL I | South Asia | India | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1999 | 2004 | 2004 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/549711474939378035/text/000020051-20140612103610.txt | http://documents.worldbank.org/curated/en/549711474939378035/pdf/000020051-20140612103610.pdf | The expectations of the pace at which the reforms can be implemented and the outcomes realized should be realistic. Given the socio political constraints, the pace of reforms will be determined by the willingness and capacity of the governments to address key reforms issues. Expectations of financial turnaround and phasing out subsidies to create space for social sectors investments need to be moderated. This would require substantial financial support to the utilities during the transition period to meet the cost of reforms.Subsidized power supply to agriculture is a deeper public policy issue and not a mere sector issue. Reduction/elimination of subsidies to agriculture is a complex economic and political problem the solution of which involves a cascade effect on the whole economy of the country by increasing the cost of agricultural products, and a change in the attitude of farmers towards electricity metering. Tariff reforms and cost recovery improvement are essential for the financial turnaround of the power sector. Tariff subsidy to consumers must be explicitly defined and transparently delivered without compromising the utilityâ€™s finances. The subsidy should be adequately budgeted by the government and provided in a timely manner. Unless the distribution business becomes viable and the commercial risk of power supply to agriculture is minimized the successfully privatization of the DISCOMs would be difficult.A strong Regulatory Commission with autonomy in funding and managing of its budget, staffing and functioning can play a significant role in promoting reforms. Critical aspects of the reform are improvement of sector oversight, facilitation of access of public to information, and promotion of efficiency and better customer services by enforcing technical norms and performance standards.Upfront integration of the social and environmental safeguards results in smooth implementation of power system schemes as well as easy implementation of these safeguards.
P049539 | ID-PROVINCIAL HEALTH II | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2001 | 2010 | 2009 | ICRR | >=50 million & <100 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/823251474508356206/text/000020051-20140619082256.txt | http://documents.worldbank.org/curated/en/823251474508356206/pdf/000020051-20140619082256.pdf | Provision of Bank funding for decentralized activities entails considerable risk to project success in a situation where lower level entities (districts) do not have clear indication of what specific functions they are authorized to carry out, particularly if these functions are not set forth in legislation.Decentralization will be difficult to implement if authority is decentralized without provision of specific standards for implementing these authorities. One of the major frustration of provinces and districts was being given authority in the laws for undertaking general functions that could be used to foster reforms, but then not having the ability to set standards for ensuring that these functions could be properly performed.Where localities have weak capacity to implement decentralized responsibilities, the provision of extensive technical guidance and advice is critical. Provincial and district actors involved in project implementation supported project objectives for health reform but reported that neither the central ministry nor the Bank supplied enough specific operational guidance (e.g., how to increase public accountability). Bank support was appreciated, but not as extensive or frequent as needed.In situations of great institutional change and turbulence, reform oriented projects should prioritize and sequence the implementation of reforms. Attempting to implement too wide a scope of reforms all at once places a large burden on implementers operating in situations of great uncertainty.
P049539 | ID-PROVINCIAL HEALTH II | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2001 | 2010 | 2014 | PPAR | >=50 million & <100 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/840601468336698944/text/778780PPAR0P04000Box379866B00OUO090.txt | http://documents.worldbank.org/curated/en/840601468336698944/pdf/778780PPAR0P04000Box379866B00OUO090.pdf | 5. Lessons 5.1 Policy reform in a volatile environment. When undertaking extensive policy reforms in a rapidly changing political and institutional environment, challenges and risks posed by traditional ways of doing business are likely to be formidable; and even thorough analytical work and sound technical designs may not be enough to achieve good results. The three projects are cases in point. They were all based on strong analytical work and best practice. Still, the results were unsatisfactory. This may well reflect that insufficient attention was being paid to the political economy environment. In Indonesia, reluctance to introduce accompanying regulations to new laws was an indicator that new institutional arrangements had yet to mature; and that government was not yet ready to firm up its options for defining new responsibilities. Such risks need to be recognized and planned for. 5.2 Monitoring and evaluation. The Bank can support high-risk/high potential projects, but a prerequisite must be that strong M&E in place; and that it incorporates appropriate technical as well as political economy indicators; includes a schedule for rigorous assessment of progress and results; and allows lessons to be drawn for subsequent projects. 5.3 Goals and project organization need to be well understood and supported by the client for effective M&E and learning. Successful introduction of new institutions requires that clients in this case MOH and sub-national governments understand the changes that are being sought, believe they are feasible, support them, and are ready to pursue them. This requires collaborative project development and continuous awareness-building of the project among participants to ensure that the client is able to understand what is going on, support it, and ultimately own it. The importance of this is highlighted by discussions with representative clients during project completion workshops and during interviews for this PPAR. There was uncertainty about project goals and institutions at all three levels of government. An insufficiently elaborated results framework and related monitoring and evaluation arrangements underscored the vagueness of the activities 5.4 An objective assessment of the client's technical capabilities to take on new roles is a prerequisite for success. The design and timing of inputs the roadmap for implementation must be calibrated to client absorptive capacity, especially where there may be multiple clients of varying levels of maturity. In this case, capacity was strong in some localities, but limitations in others made project targets much less feasible. Design needs to be calibrated to the environment, and this may require adjustments to design, capacity building, and resource planning. 5.5 Conventional government processes that enter into project design have to be functioning well, geared to facilitating implementation, and amenable to adjustment if necessary, especially when the emphasis is on piloting new methods. This is particularly important when complex new approaches are being tested. The experience under these three projects provides an illustration. Slow budget processes caused major delays in the districtlevel planning and implementation process, disturbing the learning experience. Fiduciary controls proved inadequate, delaying purchasing processes, and in one instant causing cancellation of resources for one project (PHP2). 5.6 Sequencing of projects. All three projects were piloting new complex reforms in an unsettled environment. All three were closely sequenced, offering limited opportunity for transmitting learning from one project to another. Projects introducing new institutions must be seen as opportunities for learning and improving, and sequencing should have that in mind. 5.7 Additional lessons more specific to these decentralization projects may be drawn from the summary of two learning workshops provided in Attachment 1. The workshops were conducted at the province level in East and West Kalimantan and one at the central level, and may serve as a basis for drawing broader lessons in designing projects.
P049543 | UG-Road Sec & Inst Supt (FY98) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 1998 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/276441475094632140/text/000020051-20140619083643.txt | http://documents.worldbank.org/curated/en/276441475094632140/pdf/000020051-20140619083643.pdf | In undertaking major institutional reforms that introduce new work content and processes, it is essential to take into account the existing level of capacity and to adequately account for it through additional training or technical assistance through qualified and experienced consultants.The time that may elapse in arriving at political and intra-governmental consensus should be carefully evaluated in light of similar experiences. This should be factored into time estimates for a project so that unrealistic expectations are not set up.When inordinate delays are experienced in achieving an overarching and key objective, the Bank should give serious consideration to restructuring a project. Interim arrangements should be designed so as not to create disincentives for moving towards full-fledged institutional arrangements . In this project, the creation of RAFU in some respects reduced the sense of urgency for moving towards UNRA as a full-fledged road agency.
P049543 | UG-Road Sec & Inst Supt (FY98) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 1998 | 2008 | 2011 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/822071468311443100/text/624330PPAR0P040e0only0900BOX361497B.txt | http://documents.worldbank.org/curated/en/822071468311443100/pdf/624330PPAR0P040e0only0900BOX361497B.pdf | 4.8 The following main lessons are drawn from this PPAR\. Ã˜ The Road Agency model has provided sufficient institutional capacity in low income countries such as Tanzania and Uganda to improve the delivery of new main roads and their maintenance. Supporting Road Funds can further enhance road sub-sector reform provided they are properly designed and adequately resourced. Working together, these institutions can substantially improve the performance of road management and coverage of maintenance needs from a dedicated fund. Ã˜ During road reform initiatives, the Borrowerâ€Ÿs absorptive capacity, the degree of opposition to change and the time it takes to prepare and adopt new legislation, have often been miscalculated by the Bank and other development partners. The Bank thus needs to ensure appropriate training and skills deployment to i) assess and address the Borrowerâ€Ÿs institutional and absorptive capacity limitations; ii) gauge the degree of resistance to change and make a plan to deal with it, and iii) realistically estimate the time it takes to prepare, adopt and apply new legislation. Ã˜ An annual assessment of the condition and traffic usage of the roads in the network enables the decision makers and the public to understand the implications of greater or lesser funding. The development partners can also ascertain the extent to which the assets created using their finance are being preserved. Ã˜ When two modes such as road and rail are competing for freight traffic in the same corridor an improvement or deterioration in the one mode will affect the traffic using the other. This has implications for transport policy and strategy and should also be built into the risk analysis before an investment is made. 23 24 Ã˜ Rehabilitating and reforming rail systems is a demanding and complex undertaking that normally requires dedicated staff and expertise. This should be accomplished through an exclusive and separate operation, and not tacked on to an existing road project. In the case of competing transport modes, key decisions need to be made about infrastructure provision. If the railways are to be shut down, the roads must be built with stronger pavements. If the railways are to continue functioning, then serious investment is necessary, and the willingness to bear some of the cost by mining companies and other major users and stakeholders assumes importance. The balance between road and rail can be altered by regulation, but before taking such action a thorough cost benefit analysis is needed. Ã˜ Public private partnerships will only be successful if there are real opportunities for gain by both parties, as was the case in the port of Dar es Salaam. If, as in the railway case, the track is old, the equipment worn out, and the market forecasts uncertain, top quality investors will not be interested unless there is a subsidy from Government. Ã˜ Contingency plans are necessary when concessions are considered to determine the strategy that should be followed in the event of delay or lack of interest. It is in such a hiatus that institutional capacity can become weakened and maintenance neglected. nnex A\. Evaluation of Tanzania Second Integrated Roads Project (Credit 2598-TA)
P049545 | PROVINCIAL HEALTH I | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/355901474628581200/text/000020051-20140619081146.txt | http://documents.worldbank.org/curated/en/355901474628581200/pdf/000020051-20140619081146.pdf | Inequalities across regions are likely to persist or be exacerbated under decentralization projects if special interventions are not included to address such inequalities. Yogyakarta had the advantages of being a well-resourced province with substantial capacity and access to one of the country's preeminent universities (Gadjah Mada University), with which it enjoyed a long history of collaboration. Lampung, on the other hand, was under-resourced, had weaker capacity and much less access to good technical expertise. Special support to Lampung to compensate for these disadvantages may have mitigated inequities in outcome.The ability and willingness of central MoH to amend its structure and functions in support of decentralization should not be assumed. MoH's weak commitment to the project and its failure to change its mind-set, scale back on its implementation activities and assume new leadership roles emerged as major obstacles to effective decentralization of the health system. Future projects need to address or adapt to the weak leadership from the central level.Decentralization support, which fails to assess the political economy of such reform and which is not grounded in institutional/organizational theory, is less likely to be successful.Because health sector decentralization is dependent on policies beyond the health sector, projects supporting such objectives should be vigilant in adjusting targets and indicators as new policy is promulgated.
P049545 | PROVINCIAL HEALTH I | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2008 | 2014 | PPAR | >=25 million & <50 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/840601468336698944/text/778780PPAR0P04000Box379866B00OUO090.txt | http://documents.worldbank.org/curated/en/840601468336698944/pdf/778780PPAR0P04000Box379866B00OUO090.pdf | 5. Lessons 5.1 Policy reform in a volatile environment. When undertaking extensive policy reforms in a rapidly changing political and institutional environment, challenges and risks posed by traditional ways of doing business are likely to be formidable; and even thorough analytical work and sound technical designs may not be enough to achieve good results. The three projects are cases in point. They were all based on strong analytical work and best practice. Still, the results were unsatisfactory. This may well reflect that insufficient attention was being paid to the political economy environment. In Indonesia, reluctance to introduce accompanying regulations to new laws was an indicator that new institutional arrangements had yet to mature; and that government was not yet ready to firm up its options for defining new responsibilities. Such risks need to be recognized and planned for. 5.2 Monitoring and evaluation. The Bank can support high-risk/high potential projects, but a prerequisite must be that strong M&E in place; and that it incorporates appropriate technical as well as political economy indicators; includes a schedule for rigorous assessment of progress and results; and allows lessons to be drawn for subsequent projects. 5.3 Goals and project organization need to be well understood and supported by the client for effective M&E and learning. Successful introduction of new institutions requires that clients in this case MOH and sub-national governments understand the changes that are being sought, believe they are feasible, support them, and are ready to pursue them. This requires collaborative project development and continuous awareness-building of the project among participants to ensure that the client is able to understand what is going on, support it, and ultimately own it. The importance of this is highlighted by discussions with representative clients during project completion workshops and during interviews for this PPAR. There was uncertainty about project goals and institutions at all three levels of government. An insufficiently elaborated results framework and related monitoring and evaluation arrangements underscored the vagueness of the activities 5.4 An objective assessment of the client's technical capabilities to take on new roles is a prerequisite for success. The design and timing of inputs the roadmap for implementation must be calibrated to client absorptive capacity, especially where there may be multiple clients of varying levels of maturity. In this case, capacity was strong in some localities, but limitations in others made project targets much less feasible. Design needs to be calibrated to the environment, and this may require adjustments to design, capacity building, and resource planning. 5.5 Conventional government processes that enter into project design have to be functioning well, geared to facilitating implementation, and amenable to adjustment if necessary, especially when the emphasis is on piloting new methods. This is particularly important when complex new approaches are being tested. The experience under these three projects provides an illustration. Slow budget processes caused major delays in the districtlevel planning and implementation process, disturbing the learning experience. Fiduciary controls proved inadequate, delaying purchasing processes, and in one instant causing cancellation of resources for one project (PHP2). 5.6 Sequencing of projects. All three projects were piloting new complex reforms in an unsettled environment. All three were closely sequenced, offering limited opportunity for transmitting learning from one project to another. Projects introducing new institutions must be seen as opportunities for learning and improving, and sequencing should have that in mind. 5.7 Additional lessons more specific to these decentralization projects may be drawn from the summary of two learning workshops provided in Attachment 1. The workshops were conducted at the province level in East and West Kalimantan and one at the central level, and may serve as a basis for drawing broader lessons in designing projects.
P049581 | COMMUNITY INFRA.DEV. | Middle East and North Africa | Jordan | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/915761474653123861/text/000020051-20140613031954.txt | http://documents.worldbank.org/curated/en/915761474653123861/pdf/000020051-20140613031954.pdf | When estimating a realistic implementation period, it is important to observe experiences in similar projects of this nature, especially those in the same country.Selecting clear performance indicators for both outputs and outcomes from the onset of the project would have helped to monitor the targeting of activities and re-focus them when circumstances required.Transparent and reliable procurement and payments processes create goodwill, build trust and increase competition; eventually cost savings result from this approach.
P049582 | Tashkent Solid Waste Management Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/730041475094318087/text/000020051-20140617135706.txt | http://documents.worldbank.org/curated/en/730041475094318087/pdf/000020051-20140617135706.pdf | 1. Social Assessments, when operationally targeted and used systematically, can be a useful tool for management and investment decisions in urban services projects: The project was unusual for an urban infrastructure project in that the Bank used systematic and operationally targeted Social Assessments to track consumer views of the project and their ideas for improvement, adjustment, and future investment. The project had major Social Assessments at project preparation, mid-term-review and completion - and a number of targeted Social Assessments on specific areas linked to project management decisions. Examples of Social Assessment usage are: (i) during project preparation, survey findings on the relative importance to consumers of service quality and tariff levels were used to convince the municipality to raise tariffs; (ii) more consumer friendly waste collection points were designed reflecting strong community preferences; and (iii) the locations of waste transfer points were changed. The Social Assessments also tracked consumer satisfaction with the SWM service, providing feedback for making adjustments in service management. Overall, the project's experience with Social Assessments indicates good potential for usage elsewhere. Amongst the improvements that could be made as experience is gained is that, to encourage "ownership", the Borrower rather than, as in this case, the Bank, should be the manager and financer of the Social Assessments. 2. Cofinancer and Bank conditionalities need to be reviewed and harmonized during project preparation: EBRD's highly unrealistic disbursement conditions (section 2d) delayed the project's EBRD financed components by nearly 2 years, and partly delayed the Bank financed components. The project delays could have been avoided if EBRD conditionalities and processes had been reviewed as part of project appraisal and negotiations.3. Embedding international consultants in a project's management unit can be effective if combined with hands-on training for expeditious hand-over to local management: The international consultants were initially full time, working as part of the Project Implementation Unit team, and providing both management assistance and intensive training. By the 3rd year of the project, local staff had capacity to take over management, and the international consultants withdrew to become visiting advisors.
P049582 | Tashkent Solid Waste Management Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2006 | 2008 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/430041468131973481/text/441110PPAR00P01sclosed0July02902008.txt | http://documents.worldbank.org/curated/en/430041468131973481/pdf/441110PPAR00P01sclosed0July02902008.pdf | 8. Findings andLessons 8.1 Parallel funded operations inwhich all donors do not share akey objective (privatization inthis case) should generally be avoided andpreference given to a single donor approach. Ifoperations with divergent aims cannot be avoided, thenthe project design should ensure each donor has control over the components that are instrumental to the achievement of its own particular objectives. 8.2 Carehl assessments o fusers' willingness and ability to pay, borrower agencies' institutionaland financial performance, the financial impact o f a project uponusers and providers should always bepart o fthe appraisal o fprojects that incur significant operating costs over the mediumto longterm. Inthe case o fthe Tashkent SWMproject, only the first, willingness-to-pay, aspect was adequately covered. 8.3 Cost recovery andproject financial performance should bemonitoredthoroughly duringsupervision. The WB should bringproblems-such as financial shortfalls-that imperilproject achievementsimmediatelyto the attention of aborrower, continually offeringhighquality hands-on technical advice on solutions as needed.Ifcurrent revenues are insufficient andrepeatedrequests for strengtheningthem ignored, thenthe WB should seek remedies underthe legalagreements suchas suspensionof disbursementsand/or cancellation of aproject.
P049587 | Aquatic Biodiversity Conservation | South Asia | Bangladesh | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2005 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/836121475084505983/text/000020051-20140617142800.txt | http://documents.worldbank.org/curated/en/836121475084505983/pdf/000020051-20140617142800.pdf | 1. The effectiveness of an applied research program can be substantially enhanced if structurally linked with training, piloting and targeted mainstreaming: The ABCP could be viewed as primarily a research project. However, Mainstreaming research findings into practical conservation of the fisheries sector was ABCP's focus. In fact, the research program is not even mentioned in the project's Development Objective. Instead, the DO places emphasis on fisheries sector ecological management. Similarly, 3 of the project's 5 monitorable indicators target the preparation and commenced implementation of action plans for sector management rather than studies. Also, the project components included substantial piloting and training, contributing further to the project's practical focus. As a result of the project's strong orientation towards practical application of research, ABCP, while it had some shortfalls, made a significant contribution to sector policy, strategy and conservation actions. 2. Where critically important actions are required as precursors to proceeding with other project activities, these actions are best done during project preparation: This all too familiar lesson is illustrated particularly clearly by the project. It took 2 years before the contract for the studies was signed. This meant that the ABCP effectively lost 2 years. The FFP's implementation was also held up as it partly depended on the ABCP findings.3. Political support is particularly important for an environmental management program: While some of the ABCP activities were win-win both environmentally and in terms of enhanced stakeholder incomes, a number of actions related more to externalities and the longer term, or to community collaboration without immediate benefits for an individual stakeholder. There were also a number of policy and strategy documents to be approved which potentially could have been held up by vested interests. The Government strongly owned the project and wanted to push through with a fisheries sector action plan integrating environmental management. Implementation was much easier in this environment. Without the political commitment, achievement would have been seriously compromised.4. A pilot project provides a good opportunity to develop a broader M&E program. The project missed a ready opportunity to develop a comprehensive M&E system for aquatic environmental management. Individual studies provided some material for monitoring, but not an overall M&E system. Preparing an overall M&E system could have been one of the project's "studies".
P049599 | Second Social Action Fund (MASAF II) | Eastern and Southern Africa | Malawi | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/678711474851458642/text/000020051-20140612132617.txt | http://documents.worldbank.org/curated/en/678711474851458642/pdf/000020051-20140612132617.pdf | Multiple donor approaches can create confusion at community level. There is a need for harmonization of parallel funding mechanism and harmonization of planning and implementation structures vis-Ã -vis structures of MASAF.Strong MIS and M&E systems that include outcome monitoring can better guide project decision-making and management. The extent and nature of community participation and the extent to which the voice of the poor is heard need careful monitoring.
P049616 | Land Administration Project | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/466481474574049686/text/000020051-20140618081504.txt | http://documents.worldbank.org/curated/en/466481474574049686/pdf/000020051-20140618081504.pdf | Building on the ICR three lessons are emphasized:The project experience, which is consistent with global experience, shows that land administration reform can be expected to take decades. Hence the importance of a longer-term realistic framework to guide strategic and project design in important policy areas including, for example, broader issues of communal and traditional land rights.The project experience demonstrates that strong political support at the highest level of government is critical not only to undertaking of meaningful legal and institutional reform on land issues but also to the implementation process that follows the passing of laws. Building an adequate system of M&E (including baseline data collection) is not only essential to assess progress but also to make effective mid-course corrections during implementation as and when needed. M&E needs to be in place in advance of implementation and needs to include a focus on project impacts.
P049616 | Land Administration Project | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2007 | 2010 | PPAR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/546451468040131560/text/553410PPAR0P001e0note030project0IDs.txt | http://documents.worldbank.org/curated/en/546451468040131560/pdf/553410PPAR0P001e0note030project0IDs.pdf | 7. Lessons 7.1 Assumptions about the boost to tenure security that will result from land administration initiatives (and corollary assumptions about improved access to credit and reduced conjlict) should be carefully examined and tested with empirical evidence. The assessed projects make assertions about enhanced tenure security, increased credit access and reduced conflict over land rights but provided no evidence to back these claims up. There is a literature outside the Bank challenging these assumptions and the Bank has only recently begun to take this into account. There are a number of ways to measure tenure security and the progress toward increasing it (see paragraph 2.6 above); and these measures need to be taken into account in project design and monitored during implementation. Summing up, security of land tenure is not automatically boosted by land administration initiatives; good land administration is a necessary (but not sufficient) step toward secure land tenure. 7.2 Integrating the databases of cadastre and registry is important to facilitate land use planning and tax assessments; but this integration can be attained by providing separate cadastre and registry agencies with a common technical platform-it does not presuppose creation of a single cadastre/registry agency (which may not be politically feasible). EI Salvador-with its single agency-has made more progress toward technical integration than Guatemala with its separate agencies. A unified agency is preferred, if it can be politically established. If a unified agency is not politically feasible, effective arrangements for data integration must be introduced, otherwise the unsatisfactory experience of Guatemala will be repeated in other places. There are steps that can be taken during project design and implementation to make it more likely that integration will be effective (see paragraph 3.3 above). 7.3 Land administration initiatives need to be prioritized by geographic area; other development programs may be more appropriate for remote rural areas. Regularization may be more urgent, more feasible and more sustainable in urban areas and in fertile rural areas with dynamic land markets. Urban regularization could usefully be accompanied by complementary efforts to improve municipal services, municipal financing and slum upgrading. In rural areas, there is more of a need to adopt an integrated approach to land in private property, protected areas and indigenous communities (the last two typically having been orphaned in land administration projects). While a majority of the poor often live in rural areas it does not follow that land administration efforts should give special attention to rural areas; there may be more effective ways to reduce rural poverty. 7.4 The problems associated with Guatemala's attempt at market-assisted land reform need to be avoided in subsequent projects; there is much scope for learning from previous design flaws and factors tending to undermine government support-the relevance of land reform should not be lightly dismissed. The justification for the drop off in the government and the Bank's support for land reform in Guatemala and EI Salvador merits closer examination. lEG concurs with the findings of a recent Bank policy note\. Considering the pervasive and pernicious inequality of land distribution in Central America and the fact that these inequalities were a major factor that led to civil unrest and civil wars, it is sobering to note that World Bank land projects in Central America have ended up focused on land administration ... with a secondary and discontinued effort at piloting market-based land purchase programs.51 In 7.5 During the design and preparation of land administration and land redistribution projects mechanisms need to be developedfor ensuring that the poor will have access to the land administration process and to opportunities for obtaining land; and the. effectiveness o/these mechanisms needs to be continuously monitored. The three projects assessed here each listed poverty reduction as one of their objectives and yet there was little follow up to ensure that the poor were well served. In the case of land administration, systematic adjudication in principle covers poor and non-poor alike. But coverage of the poor should not be taken for granted; and once systematic adjudication is complete there is a need for special measures to encourage poorer groups to register subsequent changes in landholding. With respect to land reform, the eligibility criteria for participation in redistributive schemes should give weight to the needs of the poor with a vocation for farming and application of those criteria should be based on a systematic survey of the socioeconomic profile of the candidates. Also, for land policy initiatives to make a big impact on rural poverty complementary measures are called to boost agricultural productivity. 7.6 The net gains from land administration and land reform initiatives should not be regarded as self-evident; much more attention must be given to measuring the impact of these initiatives and this means that when projects are prepared-rather than laterprovision must be made for conducting baseline and follow-up surveys with appropriate control groups. None of the three projects assessed here made adequate provision for impact evaluation. This shortcoming is not limited to land policy projects; but because these projects are politically so problematic the analytical foundation on which they are based probably needs to be more carefully designed and carried out than is the case for many other types of projects.
P049618 | Nairobi Water and Sewerage Institutional Restructuring Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2004 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/704071475114804559/text/000020051-20140619091106.txt | http://documents.worldbank.org/curated/en/704071475114804559/pdf/000020051-20140619091106.pdf | Choosing implementing agencies that already have some capacity can increase the likelihood of success. The project focused its support on one Water Service Board (AWSB) and one Water Service Provider (NWSC) only. By doing so the project avoided overstretching financial resources as well as implementation capacity on the Borrowerâ€™s and the Bankâ€™s side.The project should be part of the overall strategy the Government has for the sector. The design was to directly support the implementation of the already existing strategy the Government had for the sector. This strategy was outlined in the GoKâ€™s PRSP document (the ERSWEC) and the Water Act (2002). The main project activities were spearheading and complementing other Government activities for sector reform.Ring fencing the main agencies in charge of service delivery and provide them with operational autonomy and accountability is critical for success. Both entities in charge for water supply which were supported by this project were autonomous entities. AWSB was created by MOWI based on the Water Act (2002) which provides for its autonomy and legal authority for water supply and sanitation services. NWSC (which was founded by CCN) is an autonomous, commercially run company founded in accordance with the Companies Act, with its own chairperson and a majority of Board members from outside CCN.Exclusive focus on institutional objectives without an investment component can limit achievements in more technical areas. While the assumption that institutional change alone, without major investments, can bringsignificant level of service improvement, was proven in some instances e.g., in increasing financial sustainability of operations and increasing provision of water to Nairobians, in others it was overoptimistic, e.g., the indicator of UfW should have taken into consideration that institutional reform alone can reduce administrative losses, but normally has only limited impact on technical losses.
P049621 | Bukhara & Samarkand Water Supply Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2002 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/708041475089370750/text/000020051-20140624193912.txt | http://documents.worldbank.org/curated/en/708041475089370750/pdf/000020051-20140624193912.pdf | The ICR findings underline the importance of having as much of the project as possible finalized before implementation.More needs to happen up-front. The activities of international consultants must be fully understood and agreed with the government and utilities in advance, and their selection and contracting should be done as early as possible. This is particularly important when introducing private sector participation in formerly socialist systems.Central and local government officials, and water utility staff should be fully involved in diagnosis, prognosis, project design and implementation. All agencies in charge of providing counterpart financing should understand the expected disbursement profile so that adequate planning can be made in advance. M&E plans and collection of baseline data should be in place for projects by time of appraisal, and that monitoring should be simple and adapted to client capacity.
P049621 | Bukhara & Samarkand Water Supply Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2002 | 2010 | 2015 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/222081468189534492/text/97564-PPAR-P009121-P049621SecM2015-0239-IDA-SecM2015-0153-Box391506B-OUO-9.txt | http://documents.worldbank.org/curated/en/222081468189534492/pdf/97564-PPAR-P009121-P049621SecM2015-0239-IDA-SecM2015-0153-Box391506B-OUO-9.pdf | 4. Lessons Learned 4.1 The key lessons derived, based on the findings of this PPAR, are the following\. Â· When designing infrastructure and service provision projects within the context of a regional environmental crisis it is essential to minimize objectives and keep them focused on interventions the borrower will support. In this case, driven by the Aral Sea crisis, the Water Supply, Sanitation and Health Project overly emphasized the need to mitigate a range of ill-defined public health problems when even provision of basic services like potable water supply was in jeopardy. Â· Adoption of community driven development models in a country where the culture of community self-help lacks prominence may require additional capacity-building efforts. In the case of Uzbekistan, the well-established community-driven model for implementing the sanitation, health, and hygiene components, based on the experience in Nepal, India, and Peru experienced difficulties. This was due to the insufficient attention paid to building the capacity in the local institutions responsible for project implementation, especially since the community centric culture did not exist in the country. The project however benefited from an extensive series of six social assessments, as these assessments clearly demonstrated that consulting communities in the design of pilot projects put pressure on authorities to give greater attention to the scale and cost of projects. Â· The practicality and realism of bringing about institutional strengthening of a developing country's main utilities through a performance-based management contract needs very careful appraisal. The Bank needs to adopt a flexible approach that can strengthen operating performance of the utility's business in key areas without imposing unacceptable foreign management. In the case of the Bukhara and Samarkand, the foreign Operator (with hindsight) did have a very positive impact on modernizing and providing a commercial orientation to the utilities. However, socio-political factors ignored at appraisal, and exacerbated by the imposed Court judgment beyond the control of the implementing agencies, clouded judgment during implementation and at closing about the effectiveness of this arrangement. This is because the private sector model antagonized the implementing agencies and had left a lingering resentment on the value-added by the private sector. This is particularly egregious given that the municipalityappointed utility staff, following capacity-building through the operator, has subsequently demonstrated their ability to manage the utilities effectively and sustainably. Â· Introduction of private sector or NGO participation in a new socio-political environment requires continuity of specialist Bank supervision and the right mix of skills. In the case of both projects the annual turnover of task team leaders led to a lack of proactivity on critical institutional issues that exacerbated delays and hindered the Bank's effectiveness and efficiency. Â· Proper tariff setting and demand management efforts are critical factors that lead to expansion in customer base and increased revenues for the utilities. In the case of Water Supply, Sanitation, and Health project, greater attention was paid to securing financial viability under the new decentralized arrangements. Activities included periodic water tariff increases proposed by the regional government for central government approval, and simplification of tariff structure. The project was also successful in demand management through physical actions to reduce water losses, creating and updating a water user database, metering, and financial incentives to conserve water. Once staff was trained, equipment procured and public awareness was raised, the demand management program was mainstreamed in all three utilities. As a result, the customer base was expanded and revenues were increased, leading to improvements in financial viability of the utilities. Â· Financial autonomy is important for long-term sustainability of water utilities. The Buhkara and Samarkand Water Supply Project managed to increase water metering significantly through various measures, leading to enhanced collection of revenues. However, due to lack of financial autonomy, the utility is experiencing difficulty collecting the arrears from government institutions. This is likely to adversely affect the utilities' commercial performance if the government does not address the utilities' autonomy issue soon.
P049665 | CN-Anning Valley Agric. Development | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/310771475084603160/text/000020051-20140618062459.txt | http://documents.worldbank.org/curated/en/310771475084603160/pdf/000020051-20140618062459.pdf | 1. Project design should distinguish between activities best suited for a "prescriptive" program and those where "framework" support would be better: The project primarily followed a prescriptive model, defining targets ex-ante. This was suitable for the water infrastructure main works, but the other project components were to support private sector activities, whether at individual farm level or commercial. For such components, the ICR comments that a demand-responsive framework approach - whereby the project sets eligibility criteria for individuals or groups to self-select themselves into a program - might have been better, particularly as all components had to be flexible and responsive to local market conditions 2. Integrating agricultural development with river basin management provides complementary development synergies: The project was one of the early prototypes for China of a rural development model (pioneering Government's Integrated River Valley Development Plan) combining agricultural development (most of the project's activities) with irrigation development and water resources management. This combined approach proved effective. 3. Monitoring Indicators and M&E need to be aligned to a project's development objectives, in particular the Outcomes of the objectives: Key Performance Indicators were primarily output indicators. The Outcome of the development objectives has had, in part, to be conjectured from this data. If the core features in the DOs - productivity, value added, poverty alleviation - had been the center of project monitoring and management decision making, the sharpened focus might have generated yet further initiatives towards the project objectives.
P049690 | PUB.EXP.MNG.ADJ.CRD- ICR | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1998 | 1999 | 2000 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/431921474398486543/text/000020051-20140526230708.txt | http://documents.worldbank.org/curated/en/431921474398486543/pdf/000020051-20140526230708.pdf | (i) Fast-disbursing adjustment lending is not a suitable instrument for influencing long-term changes in budgetary behavior. (ii) Capacity-building efforts must intensify at the start of structural reform operations to have reasonable chance of success, particularly in low-income borrowers.
P049690 | PUB.EXP.MNG.ADJ.CRD- ICR | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1998 | 1999 | 2004 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/729991468751529556/text/27166.txt | http://documents.worldbank.org/curated/en/729991468751529556/pdf/27166.pdf | 7. Key Lessons Learned\n7.1 Undertake a Solid Economic and Sector Work Program. A well-conceived\nand carefully executedprogram of economic work is essential to underpin policy lending\noperations. During the period under review the only economic report issued was the 1990\nCEM. Both the financial sector and the public expenditure reviews remained in draft\nstage and are not generally accessible.\n\n7.2 Focus Policy Reform on a Few Key Areas with Monitorable Performance\nIndicators. While numerous aspects of economic management need improvement,\ncapacity limitations require a focus on the most important areas where there is\ndemonstrated commitment from the authorities and a capacity to deliver. Rather than\nciting assertions of good intentions, tranche release conditions should focus on actual\nperformance outcomes, as assessed by readily available, time-bound, monitorable, and\nobjectively verifiable performance indicators.\n\n7.3 In the Presence of Persistent Fiscal Deficits, Address both Fiscal Revenue\nMobilization as well as Expenditure Procedure Issues.\n\n7.4 Underpin Civil Service Reform Efforts with Upstream Work. It would have been\nuseful to have had the civil service reforms underpinned by analytical work and a clearer\nagreement with and commitment from the highest level of the government on the goals,\nand the likely outcomes of civil service reform.\n\n7.5 Reserve Single Tranche Credits Onlyfor Governments with an Established Track\nRecord of Good Policy Reform Performance. Given the experience with one-tranche\noperations, the region should carefully assess how a series of one-tranche PRSCs can be\nstructured to ensure that key objectives are achieved and to manage the risk, given the\nexisting governance situation in Guinea.\n\n7.6 Ensure Proper Identification o f Resource Gap. Resource gaps can be exaggerated\nto get the attention of external donors and to serve to mobilize additional external\nresources. IDA should carefully ascertain that the resource gaps are based on a realistic\nassessment of ownership and effective implementation capacity.\n\n7.7 Ensure Continuity of IDA Stafl Management should plan for and manage rotation\nand turnover in a manner which is not disruptive to IDA\'s operations and client relations.\n\n7.8 Forewarn of Unsustainable IDA Risk Exposure. In the period encompassed by\nthis Review, IDA substantially increased its portfolio exposure in Guinea, shifting from\nbeing one of the smaller external creditors to the principal official external creditor. The\nconsequence was a major increase in IDA\'s risk exposure, a phenomenon which was not\nadequately assessed and communicated to IDA Management and the Board in a timely\nmanner. Despite its rising exposure as an official external creditor, IDA did not give\nsufficient consideration to the likely sustainable external debt burden for the country. It\nalso did not discuss the implications of sending to the Board relatively large lending\noperations that were increasing the debt burden. IDA did not identify or formulate the\n\x0c 27\n\ntrigger for an exit or the orderly reduction in its risk exposure. This culminated in the\ncountry requiring access to HIPC debt relief. Procedures for orderly reduction of IDA\nrisk exposure deserve more carehl attention. An adequate assessment of\ncreditworthiness of the country in the face of a rising and likely unsustainable debt\nburden could have provided the analytical underpinning for properly providing loan loss\nreserves for IDA'Sexpanding Guinean portfolio.
P049691 | URBAN INFRASTRUCTURE REHABILITATION PROJECT | Western and Central Africa | Niger | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1997 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/871411474849186364/text/000020051-20140612092926.txt | http://documents.worldbank.org/curated/en/871411474849186364/pdf/000020051-20140612092926.pdf | In Africa, delegating contract management to the private sector in can be an effective strategy for municipalities to execute infrastructure programs. Adequate training for consultants and SMEs is needed to ensure a satisfactory quality for the works ordered by the municipalities. The development of partnerships between the Government, municipalities, NIGETIP and local training institutions is needed to ensure sustainability of the transfer of know-how.
P049700 | Irrigated Agriculture Intensification II Project | East Asia and Pacific | China | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/998481475070514092/text/000020051-20140613083816.txt | http://documents.worldbank.org/curated/en/998481475070514092/pdf/000020051-20140613083816.pdf | Two features, also experienced in some other Bank projects, were confirmed as enablers of success:1. Combined agriculture-irrigation approaches pay off: While some degree of agricultural activities or an agriculture component is a common feature in irrigation projects, the agriculture part is often seen as an "add-on" to what is still considered an irrigation project. This project placed as much attention on agricultural innovation and improvement as it did on rehabilitation of the irrigation networks. The combination of agricultural and irrigation improvements provided good incremental production and value added. Farm incomes increased by between 40 to 65 percent and higher in two provinces.2. Involvement and active participation of the existing local government institutional structure was a large contributor to project success: The project's institutional framework was mostly integrated into the existing government structure. At all levels - central, provincial and local governments - there was firm commitment, leadership and participation. The ICR sees this as "one of the most positive factors in project success." Institutional roles were clear, thoroughly communicated and supported by training.
P049702 | SKILLS DEVELOPMENT PROJECT | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2004 | 2010 | 2011 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/642681475101278404/text/000020051-20140624192616.txt | http://documents.worldbank.org/curated/en/642681475101278404/pdf/000020051-20140624192616.pdf | 1) Engaging the private sector may greatly improve governmentâ€™s transparency, effectiveness and efficiency on fiduciary issues. In this project, hiring a private firm to build fiduciary capacity in the PIU "on-the-job" built capacity that was very much needed.2) The team took a wise and realistic approach given the small IBRD amount and kept project objectives modest instead of aiming to deliver broader labor market objectives. Although an ultimate objective of any skills development project is to increase firm's competitiveness and labor productivity in an economy, the duration of Bank projects is generally too short to have an impact on these longer-term dimensions.3) When there is severe training market failure and market information asymmetry, task teams should adequately plan for the time and institutional capacity required to develop the funding mechanism, identify communication channels, build a roster of qualified technical assistance, and develop a database for qualified training providers (especially in cases where a certification and accreditation system is lacking). Technical capacity should be established to identify and outreach to businesses, training providers, and training intermediaries. Such technical capacity would also help maintain the sustainability of various interventions.
P049706 | JO: ODS PHASEOUT II | Middle East and North Africa | Jordan | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1997 | 2013 | 2015 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201591474941611102/text/000012394-20150303135023.txt | http://documents.worldbank.org/curated/en/201591474941611102/pdf/000012394-20150303135023.pdf | A number of lessons are presented in the ICR and the four most relevant are:The â€œumbrellaâ€ grant agreement instrument was very advantageous to implementing a phased-in program with changing activities and targeted chemical substances over a long period of time (17 years) due to its flexibility and longevity. This funding instrument allowed the â€œrolling inâ€ of new substances to come under the projectâ€™s purview over time without having to change either the structure (components) or the PDO of the project. This avoided many of the high transaction costs and uncertainties associated with â€œone-on, one-offâ€ projects, and also allowed the project to have enough staying power to indicate its long-term commitment as a partner with Jordan helping it to meet this challenge and its obligations under the by the Montreal Protocol Convention.Active national involvement at the related international forums can be important in building national capacity for ODS elimination. These international exchanges provided critical exposure to global objectives setting as well as variances in project implementation from one country to another.Clear objectives and a comprehensive results framework provide the directions and road map for successful implementation. The ultimate success of this project was due in large part to taking on an important development challenge with a clearly articulated objective and well-defined structures and intermediate milestones to measure progress toward achieving that objective. Since there was no production of CFCs in Jordan, the project did not have to work with CFC manufacturers, but it did work to simultaneously on building government's capacity for regulation to reduce and then eliminate the importation of CFCs as well as change the incentives/sanctions in favor of non-ODS substitutes among the user community.A fuller alignment between Montreal Protocol guidelines and Bank environmental safeguards guidelines should be considered, as some differences still appear to exist between the two. In this project financing to reduce the use of CFCs was insufficiently complemented with adequate financing for long-term CFC disposal.IEG adds an additional lesson:Ensure that global programs have an institutional home in Bank operations. An unfortunate consequence of the unique characteristics of Montreal Protocol operations that were directed primarily by the MLF (instead of the Bank as executing agency) was that it left the project without a clear institutional â€˜homeâ€™ for much of its implementation. As a result, it was given limited Bank management priority, especially by the responsible sector unit, which led to delays in taking needed follow-up actions.
P049708 | Palestinian Expatriate Professional Project | Middle East and North Africa | West Bank and Gaza |  |  | Equitable Growth, Finance and Institutions | Governance | SPF | IPF | 1997 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/414411475085751081/text/000020051-20140613061204.txt | http://documents.worldbank.org/curated/en/414411475085751081/pdf/000020051-20140613061204.pdf | Projects in a â€˜development in conflictâ€™ or politically dynamic context have different start-up considerations to â€˜normalâ€™ projects. Project design should incorporate sufficient adaptability to accommodate changing political and contextual realities. Such projects should also incorporate a strong monitoring system to adapt to changing circumstances. The lack of clarity over development indicators contributed to later problems. The success of some PEPP recruitments reinforces the need for a results-based management system which not only measures inputs but also the quality of the outputs.Human resource projects in which senior staff are â€˜parachuted inâ€™ are both institutionally sensitive and complex to implement. They require a minimum of client ownership evidenced in, and backed by, organizational structures, goals and terms of reference in place to receive the recruits. Attracting and integrating managerial recruits into existing or embryonic institutions is sensitive, especially where such staff are seen as receiving preferential treatment, and requires careful preparation, clear terms of reference and close monitoring. Expatriate recruitment projects would also be more effective as part of a broader capacity building strategy based on institutional assessments of need. High risk projects should build in a risk mitigation strategy. Even if it was justifiable for PEPP to proceed with an ambitious plan for a high number of senior managers in such a high risk venture, measures to mitigate such risks or even a cut-off target for non-continuation, should have been specified.Operating policies and procedures should be tested during the pilot phase and then reviewed in light of the lessons learnt.
P049716 | GN-Srvc Delivery CB APL (FY00) | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/855131474664382306/text/000020051-20140613081317.txt | http://documents.worldbank.org/curated/en/855131474664382306/pdf/000020051-20140613081317.pdf | Bank management should be alert to fiduciary weaknesses as well as shortcomings in project design and implementation as soon as they are manifested. If the situation cannot be improved, then project closure must be considered as a viable option.In a project involving deconcentration and devolution, the Bank team should have a strong understanding of the political economy of reform, and anticipate the opposition in order to inform project planning.During CBSDP, the team preparing and negotiating the project became its contracted managers. This is a clear conflict of interest and should be avoided.
P049718 | Farm Privatization Support Project | Europe and Central Asia | Tajikistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/728691474509920112/text/000020051-20140615111249.txt | http://documents.worldbank.org/curated/en/728691474509920112/pdf/000020051-20140615111249.pdf | 1. Use of project management units can be an appropriate implementation structure for piloting a program where existing government capacity is weak. The project was implemented through a central Project Management Unit and regional Project Implementation Units. Given the disarray and weak capacity of the government agencies, and the initial scepticism to privatization of government staff (still firmly wedded to the state and collective farming institutional structures), use of a PMU and PIUs was the best solution to implement the pilot program. (As the program is scaled up, it would be appropriate to hand over, progressively if needed, to the government agencies.) 2. A strongly reformist government can enable successful implementation of major policy changes in a difficult environment. Changing from a state system culture to the promotion of market based private sector farming required a major shift in thinking for government staff, and breaking entrenched vested interests. It was only through the frequent and continued interventions of the government, broadbased across a network of senior officials, that the reform process was implemented. The other factors supporting reform were the consistent guidance of the Bank, including use of study tours of successful privatization programs; and, the demonstration value in the later years of the project from Tajikistan's own pilot program as it started to show positive results. 3. Succesful transformation of an entrenched culture and institutional approach is likely to require a program approach providing long-term support. The project is being succeeded by the LRCSP and similar support from other donors. Such continuity, through a succession of projects or other lending processes enabling the same long-term support to the program, will likely be necessary for the ultimate success of the scale-up to a national program.
P049718 | Farm Privatization Support Project | Europe and Central Asia | Tajikistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2006 | 2008 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/469051468173952244/text/443590PPAR0P041sclosed0July02902008.txt | http://documents.worldbank.org/curated/en/469051468173952244/pdf/443590PPAR0P041sclosed0July02902008.pdf | 6. Lessons from the FPSP Theproject experience suggests the following lessons\. Land tenure security andfarmers 'freedom to make their own management decisions are vitalfor successful farm privatization. Inthe case o f Tajikistan, strong support from the highest levels o f government was not enoughto restructure and privatize state andcollective farms throughout the country. In cotton-growing areas, local governments were more interested inprofitingfrom cottonproduction than sharing benefits with newly independent farmers. International experience may enrichproject design, but only when local conditions arefully taken into account. Inthe case o f Tajikistan, project design was overly ambitious andnot tailored enough to the local circumstances, including five years o f civil war and the functioning presence o f aspects o f a command economy. While the Bank's worldwide sectoral experience i s an asset, transferring a model which was successful inone country to another country can becounterproductiveifproject design does not sufficiently take local conditions into account. Care must be taken to identi!all thefactors constraining the achievement of project objectives, and then something needs to be done about each of them. While some o f the barriers to farm restructuring (such as improving access to water and credit), were dealt with at appraisal, the lack o f farm machinery was not recognizedas inissue, even though it was a highpriority for farmers. Donor coordination can assist with thepropagation of major reforms. In Tajikistan, it took the Bank until2003 to realize that ifdonors would speak with one voice to the government on landreform, it might create conditions more favorable for the project-restructured farms. Establishing WUAs along irrigation channels creates an incentive to tackle problems. InTajikistan, W A Swere set up according to political divisions like counties, but this ledto users havingno shared interest inimproving the system beingmanaged. Haduser associations beenset upbyirrigation channels there would have been a strong incentive to improve their hnctioning by addressing maintenance preventively. The experience with water measurement devices shows that installingphysical devices is not enough. The installation o fmeters needs to be accompanied by a public awareness campaign ifchanges inthe rules o f the game are going to leadto water conservation andother changes inpractice.
P049719 | Land & Real Estate Registration Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2009 | 2010 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/215201474486829813/text/000146597-20140619163317.txt | http://documents.worldbank.org/curated/en/215201474486829813/pdf/000146597-20140619163317.pdf | (i) The LRERPâ€™s success can be attributed in part to several good-practice design features: (a) use of a single agency combining all land administration activities; (b) establishing this institution and supporting legislation before project commencement; (c) prioritizing, with a major training program, the development of a cadre of professional staff; and (d) introducing complex activities such as digitization in phases corresponding with evolving management and technical capacity.(ii) Continuous monitoring of service indicators and flexibility to adjust registration procedures as experience is gained can significantly enhance service efficiency. (iii) With efficient operations and institutional arrangements, a land administration service can be financially autonomous. (The registration offices are state enterprises, which can earn, retain and spend revenues independent of government, and high operational efficiency has reduced costs.)(iv) The social aspects of land administration projects need to be considered at the design stage and built into project design. Social impacts need to be monitored, with flexibility to adapt the project in response to implementation experience.
P049719 | Land & Real Estate Registration Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2009 | 2010 | PPAR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/303271468263988147/text/553820PPAR0p041IC0disclosed08131101.txt | http://documents.worldbank.org/curated/en/303271468263988147/pdf/553820PPAR0p041IC0disclosed08131101.pdf | 4. Lessons 4.1 The experience of the Kyrgyz Republic Land and Real Estate Registration Project yields the following main lessons\. ï¿½ A single implementation agency for land administration has operational advantages over a dual or multi-agency approach. As the sole agency responsible for land administration, it was easier for Gosregister to coordinate cadastral and registration activities, to reduce bottlenecks, and to improve efficiency (paras. 3.6, 3.21 and 3.43). ï¿½ The project's success can be attributed in part to several design factors (a) the implementing agency and supporting legislation were established before project implementation; (b) the project prioritized development of a trained cadre of professional staff; and (c) large-scale or complex activities were introduced in phases. Gosregister could commence operations immediately. Major training built staff proficiency in all key skills. The network of registration offices and the digitization and information technology systems were developed progressively in line with evolving management and technical capacity (para. 3.6). ï¿½ Continuous monitoring of service indicators and flexibility to adjust procedures as experience is gained can significantly enhance service efficiency. Gosregister progressed from modest operational efficiency (about 22 days to register a transaction and involving 7 procedures) to one that most countries would wish to emulate (5 days for registering a transaction (of which Gosregister time is 3 days) and involving only 3 procedures). The difference was because of ongoing monitoring against service standards, and examination of procedures for cutting out if not needed (paras. 3.15 to 3.18). ï¿½ With efficient operations and institutional arrangements, a land administration service can be financially autonomous. Experience from other countries is that achieving financial independence is often difficult, and in some cases the point is made that self-sufficiency cannot be expected for services with a public goods element. Yet, subsequent to the initial investments, Gosregister has most of its LROs financially independent (paras 3.20 and 3.22 and Box 2) despite the relatively low fees it charges to clients (Tables 5 and 6). Factors behind Gosregister's relative success are\. (i) the enabling legislative and institutional arrangements (LROs, as state enterprises, can earn, retain and spend revenues independent of government); (ii) the single agency system (LROs and Gosregister cover both cadastre and registration) which streamlines operations and means that each office can cross-subsidize, as needed, cadastre from registration revenues; and, (iv) close monitoring by Gosregister, through a good management information system of the operational efficiency of each LRO. (paras 3.13 to 3.15) ï¿½ The social aspects of land administration projects need to be considered at the design stage and built into project design. Social impacts need to be monitored, with flexibility to adapt the project in response to M&E findings. Gosregister's good operational monitoring was not matched by monitoring and special studies on the social side. For issues such as the impact of cadastre and registration on the poor, women, less-educated and other potentially vulnerable groups, there is little knowledge of the land administration program's effect and how the welfare of these groups might be protected or improved (paras. 3.22 to 3.27 and 3.31 to 3.35).
P049721 | Agricultural Competitiveness Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2005 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/381331474487771730/text/000020051-20140626075152.txt | http://documents.worldbank.org/curated/en/381331474487771730/pdf/000020051-20140626075152.pdf | This Review finds the following lessons suggested by the experience of this project:1. Having a realistic development objective is key for project success. All elements of project evaluation are linked to the objectives- whether they are relevant, whether they are achieved and whether they are achieved efficiently. When a project has a very broad objective that is beyond the reasonable purview of the project, causal chain between inputs, outputs and outcomes/impacts are lost and achieving the objectives fully becomes very difficult.2. Setting up and implementing a proper M&E system to measure the achievement of project is another key element for success. The M&E system should include all the related, measurable key outcome and intermediate indicators to adequately monitor and measure achievement of the objectives. The institutional arrangements as well as data collection/implementation methods and analysis should be clearly defined. 3. World Bank teams as well as the Government should be proactive and nimble in resolving project bottlenecks. When problems such as unrealistic objectives, inefficient M&E system, or poorly disbursing components become evident, Bank teams together with the Implementing Agency/Government should try to restructure/redesign the Project as early as possible to address the apparent issues. In particular, where possible governmentâ€™s unduly bureaucratic procedures should be changed or adjusted for more efficient implementation.
P049723 | On-Farm Irrigation Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/515271475095109293/text/000020051-20140619103556.txt | http://documents.worldbank.org/curated/en/515271475095109293/pdf/000020051-20140619103556.pdf | The ICR offers the basis for the following lessons. These were selectively adapted from the ICR and made more generic.1. Support Units for Water User's Associations are very important in the development of mechanisms for decision-making to establish legally empowered institutions. Sequencing of the support is important.2. Water User's Associations need to be strengthened and consolidated before they have to start managing and maintaining rehabilitated structures.3. Irrigation command areas need to be treated as single units to ensure effective layout and design of regulatory structures.4. To take full advantage of rehabilitated structures farmers need support in water management, agriculture, and marketing. 5. It may be too ambitious to make yield gains the primary indicator of first phase outcome.
P049724 | Agribusiness & Marketing Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2005 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/768501475098597629/text/000020051-20140626120206.txt | http://documents.worldbank.org/curated/en/768501475098597629/pdf/000020051-20140626120206.pdf | Among the lessons in the ICR, two in particular merit highlighting: 1. Picking the winners allowed the project to achieve its full potential in terms of the achieved results.. (para. 99, pg. 35) More specifically, the lesson affirms that "a rigorous process of early selection (including whether management of the company is fully committed, whether the decision making process is streamlined, and whether the company is able to secure a loan or other funding, if needed) allowed the project to pick future winners for participation in the technical assistance packages." 2. The individual design of each [Technical Assistance] service package, according to the needs of the client, was crucial for the good results of the project.. (para. 100, pg. 36) Detailed action plans, designed by consultants, were also part of these packages, which covered a combination of financial management, technical and marketing services.
P049735 | PRIVATIZATION SUPPORT PROJECT | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2004 | 2004 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/741681474632948185/text/000020051-20140612091329.txt | http://documents.worldbank.org/curated/en/741681474632948185/pdf/000020051-20140612091329.pdf | In dealing with a politically sensitive subject such as privatization, during project preparation the Bank should cast as wide a net as possible in consultation with stakeholders.
P049735 | PRIVATIZATION SUPPORT PROJECT | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2004 | 2005 | PPAR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/242361468764124440/text/303960RY.txt | http://documents.worldbank.org/curated/en/242361468764124440/pdf/303960RY.pdf | 7.5 The primary lessons learned from these projects are\. That in a post conflict, country unification situation such as Yemen's, to avoid fruitless expenditure and wasted resources, additional r i s k analysis i s appropriate to ensure that the Government i sfully committed to the reforms proposed and the timetable for the reform agenda. Project objectives should be framed realistically, taking into account the borrower's ability to achieve stakeholder support for proposed changes. Genuine community ownership and participation can enhance the likelihood o f project success as evidenced by Yemen's Public Works program. These Yemeni projects show that inter-ministerial, agency and stakeholder coordination are crucial to project sustainability and that the Bank could be more proactive in helping to improve the general level o f coordination.
P049770 | Second Renewable Energy | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/603301474549951294/text/000020051-20140619091525.txt | http://documents.worldbank.org/curated/en/603301474549951294/pdf/000020051-20140619091525.pdf | The ICR suggests a number of lessons, of which those of broader applicability are presented below:A predictable policy and regulatory environment is a critical precondition for private sector led RE development, including predictable feed-in tariffs and policy decision making.Economic Valuation of Renewable Energy vis-Ã -vis Conventional Energy can provide significant policy and regulatory insights. In addition to direct power benefits such valuation should take into account other benefits such as local and global environmental benefits, improvements in energy security and fuel risk mitigation.SHP sub-projects can be extremely vulnerable to unforeseen variations in hydrology, especially in the first few years of commissioning. Adequate risk coverage/insurance products could be built in the business model to mitigate such risks for both the developers and lenders.Financial Intermediation projects which fund energy efficiency should allow for development of different business models to account for shifting market conditions. In India, end-user implemented approaches have been more successful when compared to ESCO and DSM type projects.Unlike larger firms with access to technical and financial resources, smaller energy efficiency projects in SMEs face several additional market constraints and barriers and may be best reached through decentralized means such as working through local financial institutions.
P049789 | MN-PRIV.SEC. DEVT CR | East Asia and Pacific | Mongolia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2005 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/689981475088700771/text/000020051-20140613043801.txt | http://documents.worldbank.org/curated/en/689981475088700771/pdf/000020051-20140613043801.pdf | Adoption of advanced banking techniques (making term loans and complying with modern disclosure and regulation) seems possible, even with a short period of exposure to commercial banking and limited institutional development at the outset.
P049790 | Export Diversification | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2004 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/612331474589969810/text/000020051-20140613050657.txt | http://documents.worldbank.org/curated/en/612331474589969810/pdf/000020051-20140613050657.pdf | (1) Bank assistance provided through matching grants often entails a high cost of administration and related advisory services. This appears to be true across regions, including for example Africa and South Asia.(2) While the specialized project coordination unit (the PCU in this case) greatly facilitated implementation, the ICR nonetheless concluded that it would have been better to set up (or rely on) a regular organ of the public service, such as a policy unit in the Ministry of Commerce. Such an institutionalized unit in the public service would have carried on the work after project completion and thus enhanced sustainability.
P049791 | Poverty Alleviation Fund | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/533121474504127759/text/000020051-20140613052919.txt | http://documents.worldbank.org/curated/en/533121474504127759/pdf/000020051-20140613052919.pdf | Projects that combine microcredit schemes with financing of small-scale infrastructure and training can successfully alleviate poverty. Building the capacity of partner organizations responsible for on-lending requires a broad range of measures, including strategic reviews, recurrent analysis of weaknesses and threats, mandatory submission of business plans, targeted training, and systematic monitoring.In projects of this nature it is vital to ensure that apex organizations are free from political pressures (e.g. to lend to the powerful) and that board members are not themselves eligible to receive loans from the project fund.Key operational decisions can be delegated to local managers provided that there is a clearly-written and well-explained operational manual and procedures for ensuring transparency.
P049838 | Privatization & Priv Sec Dev | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2010 | 2011 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/719921474854843680/text/000020051-20140624170501.txt | http://documents.worldbank.org/curated/en/719921474854843680/pdf/000020051-20140624170501.pdf | This Review agrees with the important lessons that are provided in the ICR. These focus on the need for: realism in setting performance targets, specificity in project design, systematic and candid reporting, the intensity of implementation support, timely project restructuring, sustained borrower commitment, and due diligence in privatization processes.
P049874 | Enterprise Dev (FY00) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/291561474563425023/text/000020051-20140617131809.txt | http://documents.worldbank.org/curated/en/291561474563425023/pdf/000020051-20140617131809.pdf | 1. The individual components of a private sector development project need to be clearly focused and should be linked with each other to create synergies and increase impact. 2. Monitoring and evaluation systems need to be developed and implemented to assure quality control and impact.3. With now 3 failed Lines of Credits in Mozambique, the Bank should abstain from this instrument until the main causes for poor intermediation are addressed. Instead of dragging on with promoting a Line of Credit, it might be better to cancel the component and focus the limited implementation capacity on the remaining components.
P049874 | Enterprise Dev (FY00) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2006 | 2014 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/474941468057552133/text/855960PPAR0P04080Box382166B00OUO090.txt | http://documents.worldbank.org/curated/en/474941468057552133/pdf/855960PPAR0P04080Box382166B00OUO090.pdf | 7. Lessons The assessment draws four lessons\. 7.1 In post conflict countries with weak institutions and capacity constraints, achieving major economic reforms requires continuous effort and liaison with many ministries and agencies, over a substantial period of time. Rather than a single project with multiple components, a programmatic approach could also have provided opportunities to learn from each phase as inputs to designing the next. The value of a phased approach was demonstrated by the follow on private sector development project, which incorporated lessons from the present project. This is another reason why multi-donor multi-year operations, with significant policy and institutional development content, have a very important role to play, and could be complementary to stand-alone operations. 7.2 Matching grant programs can potentially be an effective way of providing incentives to firms. To be successful such programs have to be well managed. Outsourcing to a wellestablished and well run institution with the right expertise helps. A successful matching grant program for business services requires a combination of international expertise, local knowledge, autonomy in administration, and adaptability to respond to market demand. Project's outsourcing of the management of the matching-grant to a firm with solid expertise in the field contributed to its relative success. 7.3 Too much dispersion in capacity building components could limit deeper institutional reforms. The main lesson from the Institutional Capacity Building component is that it is important to avoid focusing simultaneously on too many issues at the same timeâ€“ in this case promoting investment, developing an industrial zone, building ministerial capacity, supporting private sector institutions, and improving the business environment. The impact would have been deeper if institutional reforms had been addressed in separate projects. 7.4 Credit line operations that are designed solely to increase the supply of funds do not increase sustainable access to finance if other institutional, legal and regulatory constraints to financial sector development are not addressed. Lines of Credit require careful preparation, including assessments of\. (i) overall demand; (ii) factors that dampen demand (such as high interest rates); and on the supply side (iii) factors that may limit commercial banks' appetite to lend to small and medium enterprises, even if they have the resources (e.g. limited information on borrowers' creditworthiness legal, regulatory environment, and firmlevel constraints).
P049878 | MZ-EMPSO | Eastern and Southern Africa | Mozambique | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2003 | 2005 | 2005 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/742291474488937745/text/000020051-20140613035953.txt | http://documents.worldbank.org/curated/en/742291474488937745/pdf/000020051-20140613035953.pdf | When a project seeks to produce desired outcomes through changes in legislation, regulations, and processes, the project must also have well-defined, and achievable, results indicators for its ultimate objectives to be achieved.
P049892 | Pension & Social Assistance Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2004 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/946871475082291340/text/000020051-20140625072209.txt | http://documents.worldbank.org/curated/en/946871475082291340/pdf/000020051-20140625072209.pdf | The following are the most important lessons from the preparation and implementation experience of this project. The first is drawn by IEG. The others are taken from the ICR with some adaptation:Installation of MIS and similar new technology needs to be accompanied by a thorough training program in its use for the staff of the entities concerned. In this case, the emphasis placed on such training from project preparation onwards, and the inculcation of a training culture in the implementing agencies, paid significant dividends.Stakeholder acceptance of reform and system improvements, even when they result in enhanced client services and are accompanied by higher benefits, should not be taken for granted. This project included a systematic public awareness campaign. Despite this consistent effort, surveys conducted towards the close of the project indicated a need for a continuation and deepening of the campaign.Reforms in the social assistance sector require a long term engagement. In this case, IDA has succeeded in building a position of trust as a strong partner who is there for the long haul. This project was preceded by intense policy dialogue and social assistance sector interventions in other operations, including Development Policy Credits. It is followed by another ongoing project to sustain and expand the reforms.Improving governance and accountability are central elements to a successful reform of social protection programs. In this case, both the social insurance and social assistance systems prior to the project were characterized by lack of transparency in eligibility criteria and opportunities for corruption. The client surveys indicate that, while much has been done, building public trust is still an ongoing task.
P049894 | Primary Health Care Project | Europe and Central Asia | Tajikistan | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/889671474504253877/text/000020051-20140613075003.txt | http://documents.worldbank.org/curated/en/889671474504253877/pdf/000020051-20140613075003.pdf | Appropriate choice of lending instruments - had the project been viewed as a Learning and Innovation Loan (LIL), the Bank and the government may have been more conditioned to allocating priority and resources to the "learning by doing" approach and the evaluation exercise, which were key requirements in a pilot project.In attempting complex institutional reforms in fragile LICUS countries like Tajikistan, such as the introduction of a new health financing model (which is challenging in any country), the project design should carefully take into account the country's budget systems, administrative cultures and social expectations which are often firmly entrenched in the status quo.Nothing should be taken for granted when collaborating with other development partners. To avoid the misunderstandings that led to the omission of the impact evaluation activity in the project, it is necessary to clearly and explicitly document agreements, specifying terms and conditions, of the collaboration.
P049895 | MX HIGHER ED. FINANCING | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1998 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/254011474628468569/text/000020051-20140618062022.txt | http://documents.worldbank.org/curated/en/254011474628468569/pdf/000020051-20140618062022.pdf | Drawn partly from the ICR, the following are the most important lessons:It is important that all key performance indicators be tracked by a project, especially those related to main project outcomes. When the project fails to track certain indicators, an ICR should acknowledge this, find reasons for it, and attempt to find proxies for the unused indicators. If during the course of project implementation, managers find that certain indicators are unreasonable or unusable, the option of restructuring the project (and revising indicators) is a possibility. This would be preferable to leaving the indicators unaddressed;Well documented and carefully evaluated vanguard projects such as this one can provide useful information to an entire region on how to solve certain problems, contributing to a national and international knowledge bank. This contribution could have been even richer if the comparative insights (between the two innovative systems) had been sharper and more explicit; For a student loan system for higher education to be successful it is necessary that there be risk and cost sharing with the participating universities. For example, when universities share in the risk of loan default by borrowers, they will work to find ways to mitigate this problem;Some sustained period of public investment in student loans may be required in order to keep a student loan system running and to reach sustainability. Mexico is no different from other countries in this respect, even high income countries such as New Zealand and the United States. Such support is more feasible in countries (or states, e.g., Sonora) which are requiring a reasonable level of cost-recovery in higher education;A public-private partnership in student lending is desirable but difficult when financial risks are uncertain, uncertainly arising from the long period of time that it takes for the repayment of student loans (10 to 15 years). This calls for negotiated agreements between public and private entities with a long-term focus on the common interest in a large scale student loan system; Although providing low-cost student loans is a higher education policy instrument, it is also a financial instrument for which experience and know-how from the banking industry is crucial. The use of such expertise in the SOFES system is one explanation for its extraordinary management effectiveness;For success in implementing student loan systems, attention to collection cannot be overestimated. The project provided several examples of effective approaches to this and arrived at some suggestions to be tried out in the future; and Borrowing for higher education is not strongly embedded in cultures where an entitlement to low-cost, state subsidized higher education is assumed. Also, students and their families need to overcome a fear that borrowing for higher education will lead to early bankruptcy. It will take explicit efforts over a long period of time to help change such cultural norms.
P049924 | Rural and Small Towns Water Supply and Sanitation Project (PRAGUAS) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/361911474420758358/text/000020051-20140617143248.txt | http://documents.worldbank.org/curated/en/361911474420758358/pdf/000020051-20140617143248.pdf | The project has served as an important learning experience for demand-driven development of the rural water supply and sanitation sector. PRAGUAS' approach contains many of the features typically included in Bank rural water supply and sanitation projects in recent years. Hence, understanding what worked and did not work is of general interest and is the key lesson from the project experience. Its main features are: Communities and local governments are willing to pay a significant upfront contribution to investment if they are involved in the investment decision and are confident that the service will be effective. Under PRAGUAS (and contradicting initial fears that counterpart requirements were too large) municipalities and communities respectively contributed 20 and 30 percent of investment costs.Such financial and in-kind cost-sharing enhances ownership of the assets, which is anticipated to lead to better subsequent O&M.A demand-driven rural water supply and sanitation project requires time and significant resources for building community consensus and capacity. The strong orientation of PRAGUAS to "software" aspects was an important base for success. It also turned out that the time required for this had been considerably underestimated.Pre-qualification criteria pre-selects more motivated municipalities, and improves readiness for implementation. For PRAGUAS, these included the need for established financial and technical teams and a WSS Plan at municipality level, and, for both communities and the municipality, decisions on tariffs that would cover O&M costs, and the up-front investment contributions referred to above. Performance-based incentives can be helpful in stimulating reforms at local government levels. The government introduced a performance-based formula for providing general financial assistance to municipalities (beyond the specific financing for PRAGUAS infrastructure).Municipal water agencies need financial as well as technical capability. There had been more training in technical areas under PRAGUAS, and business capacity was weak.Reform may be needed of the policy, legal and institutional base. PRAGUAS worked on all of these aspacts to create a better platform for the demand-driven approach.There can be substantial gains from the integration of hygiene education with a water and sanitation program. The ICR strongly favors including Hygiene in community training, based on observed health benefits. A standardized Operational Manual should be disseminated widely so that all stakeholders understand procedures, roles and requirements.Water quality may need special emphasis. The PRAGUAS experience was that municipalities gave insufficient attention to water quality, and that communities had insufficient knowledge of the impacts of contaminated water, methods for reducing contamination and disinfection devices. Decentralized outsourcing of design and community organization services may be facilitated through large firms operating as intermediaries. An emphasis under the project was to employ local small firms or NGOs for providing technical assistance to communities, especially in community organization where local understanding is important. However, direct contracting required numerous contracts, and supervision of the quality of work was difficult. Hiring larger firms, who would themselves be responsible for sub-contracting and supervising the small firms and NGOs proved the most effective approach, with better quality works and faster implementation. A learning oriented, adaptive approach during project implementation is particularly suitable for a demand-driven rural water supply and sanitation program, especially at the beginning of a program where experience is limited.
P049924 | Rural and Small Towns Water Supply and Sanitation Project (PRAGUAS) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2007 | 2011 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/892581468286274197/text/629070PPAR0P040c070101100BOX361502B.txt | http://documents.worldbank.org/curated/en/892581468286274197/pdf/629070PPAR0P040c070101100BOX361502B.pdf | 5. Lessons Sector reform and the related shift in institutional culture require political support and time 5.1 It is important to identify the potential risks up front, and carry out proper stakeholder analysis and to make a realistic projection of the time it takes to change the roles of the Government agencies and to devolve the WSS investment and O&M responsibilities to the local government or the community level. 5.2 Both Ecuador and Paraguay experienced delays in project effectiveness and implementation due to political instability and social unrest. They also faced difficulties in reforming the public sector agencies to be credible partners in facilitating the investments in the RWSS sector. 5.3 In the case of Paraguay the central agency, SENASA had already been in operation for 25 years at the time of project approval since its establishment in 1972. Prior to RWSS IV, the Bank had supported SENASA through three previous projects where practical rules for organizing and building the capacities of the WBAs to operate and maintain their RWSS systems were tested and mainstreamed. While the three preceding projects together created more than 400 WBAs providing services to more than 400,000 beneficiaries, even with this track record and three and a half years of project extension, RWSS IV struggled to reach its target number of beneficiaries, primarily due to political instability. RWSS IV was successful in enabling SENASA to fully transform its role from being an implementer to becoming a promoter of RWSS investments through contracting out its core implementation and technical assistance functions to the private sector, non-governmental organizations, and association of WBAs. Thirty years of continuous Bank support for phased reforms may be a factor in explaining these good results in Paraguay. 5.4 In contrast, Ecuador attempted to achieve the difficult reform objective of shifting investment responsibility from the central government level to the municipal government level during the five-year first phase of the APL. The reforms in Ecuador were particularly difficult because the institutional culture of the Ecuadorian Institute of Sanitary Works or Instituto Ecuatoriano de Obras Sanitarias in Spanish , a central government agency that controlled the water sector for almost 30 years, was still dominant at the time of the project, although IEOSâ€Ÿ responsibilities had been transferred to the Ministry of Urban Development and Housing (Ministerio de Desarrollo Urbano y Vivienda, MIDUVI)/ Subsecretariat of Environmental Sanitation (Sub-secretaria de Saneamiento Ambiental, SSA). The new organization under MIDUVI/SSA was established only eight years before the project was approved, and the WBA model under the jurisdiction of municipal governments was introduced by PRAGUAS for the first time, during the first phase of its APL. While Paraguay created 48 WBAs in its first project implemented during 1978-83, and only achieved the creation of 594 WBAs in its fourth project, Ecuador aimed to establish 588 WBAs already in its first phase at the same time as building the capacity of the municipalities to implement the investments. Formalization of consistent policies is critical for reform 5.5 The comparison of the WSS sectorâ€Ÿs institutional framework in Ecuador and Paraguay reveals the importance of formalizing sector policies through legal decrees and formal approvals by the Congress to ensure that the financial and investment policies are enforced. While they may not be sufficient, formalization of the policies and sector institutional responsibilities seem to be necessary for the implementation of reforms especially as the countries face political changes. 5.6 In Paraguay, rules for engaging various stakeholders were embedded in laws and decrees. This facilitated the implementation of coherent and consistent financial and investment policies across the sector regardless of who is funding the investments. In Ecuador, on the other hand, the main elements of the institutional and financial policies were not formalized prior to project initiation. Instead, arrangements were agreed on an investment by investment basis. While PRAGUAS would require community contribution to investment financing, other projects led by the government may provide new rural WSS systems for free. Lack of formal sector policies has caused the ad hoc approaches to community participation in WSS investments and undermined the importance of community ownership through beneficiary contributions. This has hampered the sustainability of WSS sector investments in Ecuador. WBA models show good financial sustainability 5.7 While the physical sustainability does not only depend on the level of O&M cost recovery as there are other influencing factors such as the capacity and incentives of the service providers to carry out proper maintenance, long-term financial sustainability depends on whether the institutional arrangements for implementing cost recovery policies are sound and responsive to local conditions. This assessment of the two RWSS projects have enabled a comparison of; (i) independent regulation; (ii) regulation by contract, and (iii) social accountability as the means of enforcing the cost recovery policies in rural areas and small towns. Â· Independent Regulation\. In the case of Paraguay, there is a Regulator whose mandate is to ensure that tariffs are set according to the cost recovery rules and in accordance with the affordability to the consumers. While there is a remaining challenge for ERSSAN to regulate the increasing number of WBAs, results so far show that the tariff revenues cover the O&M costs and often even part of the capital costs in Paraguay. Â· Regulation by contract\. In the case of Ecuadorâ€Ÿs municipal company models, in which the private sector operators (PSOs) are paid for their services out of tariff revenues cost recovery is self-enforced provided tariffs are set according to the cost recovery rules. This is because the contractual obligations with the PSOs include clauses related to tariff adjustments to compensate for cost increases. Â· Social accountability\. In the rural areas where WBAs are accountable to their communities, they wonâ€Ÿt be able to operate and maintain their water supply schemes if they do not collect sufficient tariff revenues. Without other sources of funds to pay for operations and maintenance, the service would deteriorate. Knowing that cost recovery can help avoid service interruption, local rural communities in both countries seem to be disposed toward paying the necessary tariffs. 5.8 In contrast to the above three regulation models, the small towns of Ecuador have a municipal regulatory arrangement. Water utilities in these small towns are experiencing difficulties achieving their cost recovery as the tariffs are typically set below the O&M costs. The municipalitiesâ€Ÿ Boards of Directors include local politicians who see water supply as a public service that ought to be free. They believe that general municipal revenues will be used to cover any deficits resulting from low tariff revenues. As a result, the conventional WBA models in both countries and the PSO models in Paraguay show stronger financial sustainability compared to the municipal models implemented in Ecuador where tariffs are approve by municipal authorities. Sanitation requires more attention 5.9 Both projects included components to increase coverage of improved sanitation, but the real outcomes achieved through the project activities have been generally poor or difficult to assess due to lack of available data on outcomes. In the case of Ecuador, 14,000 people had received sanitation facilities only (mostly flush toilets, hand washer sink and shower facilities), and 129,000 people had received both water connections and sanitation facilities under PRAGUAS, but no evidence of the usage of these facilities or the outcomes in the form of health or environmental impacts were available. In the case of Paraguay, only three out of the planned ten sewerage system pilots were constructed under RWSS IV because there was lack of demand from the beneficiaries who already have other means of sanitation, and lack of experience in promoting and financing sewerage projects in the country. 5.10 Because of the environmental and health externalities of the current low levels of sanitation coverage in both countries, it is important for the Government and the Bank teams to pay more attention to and effectively track the progress in the sanitation sub-sector both during project preparation and implementation. Post construction technical support and capacity building enhance the sustainability of community participatory water supply services 5.11 The importance of demand-responsive, community participatory approach has been identified to ensure successful implementation of the water supply and sanitation investments in rural areas and small towns. For the water systems to be sustainable, there also needs to be an institutionalized arrangement for technical assistance and post-construction support for continuous capacity building of WBAs. In the case of Paraguay, initially SENASA and later the Association of WBAs have provided such support in the form of training and seminars. As a result, even if there are no subsidies allocated for the purpose of O&M, most of the rural WSS systems managed by the WBAs in Paraguay are reported to be functioning three years after completion. In contrast, the indigenous communities systems in Paraguay and WBAs in Ecuador that do not have such institutionalized systems for support, are experiencing sustainability issues as the systems built cannot be easily repaired or replaced by the WBAs and the communities by themselves.
P050036 | Anhui Provincial Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1999 | 2006 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/883451474650239790/text/000020051-20140615093940.txt | http://documents.worldbank.org/curated/en/883451474650239790/pdf/000020051-20140615093940.pdf | 1. A better understanding of the country's decision-making procedures concerning procurement especially will enable the project team to assess the risks better. In this project a major delay occurred in the procurement of the E&M works, which the Borrower finally asked the Bank to cancel and completed the E&M works at its own expense 10 months after opening of the expressway itself.2. Concurrent investments in "high-class" roads, such as the HAE, and in "lower-class" roads, such as the provincial roads in the HMP, helps achieve a broader mix of benefits and a better promotion of road sector programs. This lesson is not peculiar only to China. There are several countries that favor "high-class" roads over "lower-class" roads, probably because of their importance to long distance traffic, (political) visibility, and, in some cases, difficulty to lend local governments that maybe the owners of "lower-class" roads. By experience, the documentation of high ERRs from rehabilitation and maintenance, as in the present project, while important, does not seem sufficient to gain support for lower class roads. Apparently, the APCD professionals became convinced of the value of investments in lower class roads by positive experience. The ICR indicates that the reasons were alleviation of congestion and arresting road deterioration on the lower class roads, and tolls on the high class roads. This would imply that road and traffic information is of great value in designing projects.3. Overcoming barriers to intergovernmental cooperation, mandatory in traffic safety projects/components, yields large benefits. This lesson was clearly demonstrated by the success of the small traffic safety component, which required cooperation of the Traffic Police with APCD and support from the higher levels of Provincial Government, and reduced the crash rates by half on the target road and led to a larger component in the follow-on project. Also this lessons is not peculiar to China although intergovernmental barriers in China can be high.
P050046 | Education for All Project | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2002 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/565171467986263255/text/ICRR14707-P050046-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/565171467986263255/pdf/ICRR14707-P050046-Box393183B-PUBLIC.pdf | Lessons drawn from the ICR (page 34-35), adapted by IEG:Evaluative activities, including student assessments and pilot test assessments, have less impact when they are not strategically used to inform policy making and project implementation support. In the case of this project, some of these activities were conducted, but there was no systematic plan established at the outset to use the findings to inform decision-making.During periods of intense political transitions and crisis, maintaining a minimal level of communication with the government can facilitate swift re-engagement following the crisis and bring important dividends. In the case of this project, the Bank team demonstrated a high level of commitment to supporting the education sector by maintaining interactions with the government and key stakeholders even during the period of official disengagement.Lessons drawn by IEG:In a fragile environment, simplifying the project design and ensuring project readiness are critical factors for satisfactory quality at entry. In the case of this project, the multiple decentralized agencies and institutions involved made for an overly complex project, and the lack of prepared documents (i.e. operations manual) at project launch contributed to a slow start.Project restructuring would need to be undertaken as soon as it is feasible to improve likelihood of success. In the case of this project, much needed restructuring(s) did not take place until late into project implementation. Although the project performed on a more satisfactory level in the latter part of the project period, the majority of Credit/Grant had already disbursed and therefore the outcome rating remained in the unsatisfactory range.
P050140 | Health Financing & Primary Health Care Development Project | Europe and Central Asia | Armenia | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/470941474569264694/text/000020051-20140612140945.txt | http://documents.worldbank.org/curated/en/470941474569264694/pdf/000020051-20140612140945.pdf | A flexible approach by both government and the Bank can greatly enhance project effectiveness during implementation: adjustments were made to accommodate findings from analytical work and additional funding in ways that were very responsive to local needs.Project demonstrated that design weaknesses can be effectively addressed during implementation by using other Bank instruments. However, this requires proactive supervision and continuous engagement in policy issues by the project team.Introduction of provider contracting and changes in provider payment mechanisms need to be supported by substantial efforts to increase information flow, provider accountability, quality assurance, and appropriate service delivery reforms to achieve the expected results.
P050272 | Ethiopia - Private Sector Development Capacity Building Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Other | Trade & Competitiveness | IDA | IPF | 2005 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/113271475112441030/text/000180307-20150113074029.txt | http://documents.worldbank.org/curated/en/113271475112441030/pdf/000180307-20150113074029.pdf | IEG supports the thrust of the â€œlessons learnedâ€ section in the ICR, which includes both findings and lessons. Private sector development operations are most effective when inclusive of key stakeholders from both public and private sectors. Contingency plans can help to address known externalities such as elections, while being flexible enough to respond to new and unexpected policy priorities. A multifaceted approach can be effective in promoting export competitiveness including, inter alia, consideration of a competitive foreign exchange rate.
P050294 | LKD FRDP III | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2002 | 2003 | ICRR | >=50 million & <100 million | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/151041474585720318/text/000020051-20140612071603.txt | http://documents.worldbank.org/curated/en/151041474585720318/pdf/000020051-20140612071603.pdf | Credit amounts should be commensurate with the extent of the reforms undertaken, or the Bank risks losing credibility with the BorrowerIn a situation where Government commitment is uncertain and reform momentum has slowed, in the absence of a detailed, time-bound multi-year framework, a multi-tranche operation is preferable to assure that reforms are properly implemented
P050294 | LKD FRDP III | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2002 | 2007 | PPAR | >=50 million & <100 million | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/406021468271544252/text/37810.txt | http://documents.worldbank.org/curated/en/406021468271544252/pdf/37810.pdf | Lessons Incentives within the Bank can motivate unwise lending\. The desire to transfer resources and establishHIPC eligibility were important motivations to the initiationof FRDP III.Despite the poor macroeconomic climate andlack o f reformprogress under the previous credits, FRDP111was enlarged by US$20million (over the originally-conceived amount) andhastily structuredas a one-tranche loanmainly to facilitate establishment o fHIPC eligibility. Further, theoperationwas over-dimensioned for the scope ofitspolicypackage. 0 The region's macroeconomic assessments need to have greater realism and consistency\. The analyses o f the macroeconomic environment inthe FRDP 11 andIIIproject documents are unbalanced andlack realism andconsistency. The existence of a Fundprogram should not be a suficient conditionfor the Bank to initiate adjustment lending. Policy-based lending inan unstable macroeconomic environment is unwise\. The Malawian experience ofturbulent macroeconomic performance fiom 1994to 1998, with on-again, off-again Fundprograms shouldhave alerted the Bank that M e r adjustment lending after FRDPI\.(1) was not warranted; and (2) was unlikely to have a significant impact due to the negative effect ofmacroeconomic turbulence on the efficacy of structuralreform. Inpromoting reform, the Bank needsto take account of the incentives that a program creates\. MTEF, IFMIS,andcivil service reformwere unsuccessful in largemeasure because GOMofficials-at all levels-did not perceive that it was intheir interest to implement these reforms. While anofficialbudgetwas prepared, itwas routinely circumvented andexceededbypolitical intervention. Tenyears o feffort on MTEFandUS$2.3 milliono fexpenditure on IFMIS have produced virtually no results. 0 The Bank should structure lending to Malawiwith more earmarked, targeted aid, and tighter fiduciary controls\. To assure that funds are used in the manner intended, budgetary support should be subject to tighter fiduciary controls. Also, greater use shouldbe made o f earmarked assistance, including that which is delivered directly fiom suppliers to users, such as the successful CIDA textbook program (box 4.2).
P050342 | Women Development Initiatives | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2006 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/320931474944798646/text/000146597-20140617162407.txt | http://documents.worldbank.org/curated/en/320931474944798646/pdf/000146597-20140617162407.pdf | Among others, the ICR draws these lessons for Women in Development initiatives:Projects supporting group-based businesses have to ensure (i) group coordination; (ii) a sense of commitment to and ownershp of the group business; (iii) flexibility to diversify operations; and (iv) adequate funding based on business type and group size.Effective project implementation necessitates linkages with both public and private sector services because of the limited scope of services and technical skills that can be provided by local implementing bodies and/or other government agencies.It is possible to empower poor, illiterate women socially and economically through small-scale and group-based micro-business initiatives. Individually-operated and hybrid group modalities appear to be more profitable than group initiatives.A nation-wide pilot is not desirable from both financial and administrative perspectives, as it requires a complex and costly institutional set-up.
P050354 | Human Resource Development Project | Eastern and Southern Africa | Eritrea | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1998 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/287201474563064215/text/000020051-20140612142709.txt | http://documents.worldbank.org/curated/en/287201474563064215/pdf/000020051-20140612142709.pdf | Strong measures must be taken to ensure that students supported for overseas training do return to fulfill their intended role in government service.In planning training, the prior academic credentials of beneficiaries need to be adequately assessed, and programs tailored to respond to their needs.Rapid action to alleviate the impact on an affected population was effective through restructuring of the portfolio under UN auspices.Taking a flexible approach to recruitment of qualified deportees at local salaries enabled the number of expatriate experts to be significantly increased.
P050383 | Food Security Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2010 | 2014 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/191781475111631182/text/000020051-20140625071638.txt | http://documents.worldbank.org/curated/en/191781475111631182/pdf/000020051-20140625071638.pdf | The ICR reports the following lessons:Small loans for very poor households can lead to modestly positive impacts related to assets, incomes and resilience to shocks, but are insufficient in themselves to catalyze a transformation of household livelihoods. For better outcomes, the project needed to be paired with complementary and supplementary parts of the National Food Security Program. The project also showed that while providing small loans to very poor food insecure households is important, its impact is amplified if followed-up by repeater loans and technical assistance allowing a differentiated approach to the development of livelihoods.Targeting the poor and vulnerable groups can be done effectively in a highly decentralized setting if appropriate safeguards and monitoring are established. The project showed that if communities are appropriately mobilized to confirm the status of households, this can be achieved, still there is the risk of elite capture by those with positions of influence, which require appropriate safeguards and consistent monitoring.Training of local authorities on participatory approaches and putting in place systems that enable communities to influence decisions on the management of revolving funds is critical in ensuring proper operation of such funds.The project showed that when there is active engagement by communities both in the selection of borrowers and in determining appropriate action against potential defaulters, repayment is relatively high. Effective and sustainable management of financial services requires that they be provided through financial institutions. Project implementation showed that while community grants can be handled by local administrative bodies, the effectiveness of such institutions tends to be limited to oversight of its management and in facilitating community engagement. Administration of funds, is best managed by financial institutions. Funds flow arrangements in such a highly decentralized implementation systems, including the level of advances, need to be designed realistically so that implementation is not constrained by lack of funds. The related capacity for financial management reporting must be assessed objectively, and appropriate technical support put in place to ensure the possibility of timely funds replenishment while also ensuring adequate management of fiduciary risks.Well functioning M&E system is important to measure impacts as well as redirect project interventions. Collec tion of baseline data and appropriate arrangements for quantitative impact evaluation are important not only to measure program benefits but to identify ways to improve impact.Transitioning at scale from food insecurity will require a broad-based approach beyond specific food security focused interventions. While revolving fund type programs have demonstrated benefits, more comprehensive assistance is needed for the poor households along multiple paths. Furthermore, long-term food security cannot be achieved through exclusive attention to the vulnerable, particularly in low potential areas. Rather, complementary efforts are also needed to diversify livelihood and employment opportunities, in both rural and urban areas, as well as to enhance agricultural growth, in both low potential and high potential areas, and thereby reduce food prices.IEG also finds that:The scope of project activities should match project objectives. In this case the project development objective under the original project was too ambitious and beyond the scope of project activities. Project restructuring is an important opportunity to address project bottlenecks and resolve issues such as ambitious and broad objectives and unrealistic and hard to measure indicators. The project restructuring tried to address these issues but the revised indicators were inadequate. The food security is a long term objective. The insignificant results for this project show that building livelihoods and improving asset structure is a longer term goal that requires continuous reinvestment by households, with adequate capacity building mechanisms for revolving funds.
P050400 | ZM-PSCAP (FY00) | Eastern and Southern Africa | Zambia | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/320741474850119347/text/000020051-20140613090409.txt | http://documents.worldbank.org/curated/en/320741474850119347/pdf/000020051-20140613090409.pdf | 1. The Mid-term review was a lost opportunity The MTR should have made a harder assessment of progress, problems, capacity and willingness to implement the original project design. It did not take into account changes in government policy, and priorities, so that the relevance of continuing with the original design could be assessed. Ultimately, Phase 2 and Phase 3 of the APL were dropped and reforms were pursued through two SWAPs. No information is presented on how those SWAPs are faring. 2. Avoid disconnects between various project ratings through greater realism The PSRs and ISRs were not sufficiently candid.They maintained satisfactory ratings throughout and did not give an accurate picture of the mixed progress. Actual disbursements lagged estimated figures by 50 percent for much of the project period, hence the team had an incentive to maintain satisfactory ratings in order to keep up the disbursements. The problem goes back to the original three-year time frame versus the five years it actually took -- just for Phase 1. 3. Correct use of instruments is important. Data is not available on the performance of the two SWAps as Bank disbursement to them has not commenced and they were only approved by the Board on January 5, 2006. However the harmonized approach with other donors made possible under a SWAp has clear benefits in ensuring that agreed reforms get implemented. 4. Broader partner involvement The PAD mentioned that DFID, Irish AID and UNDP would be involved in the program. Ultimately it was only DFID. DFID commented that certain payrolls continue to be excluded from PMEC (uniformed defense payrolls, some parts of Office of the President among others), but it agrees with the ICR finding that implementation of PMEC was a significant achievement.
P050418 | TN-ASIL 2 | Middle East and North Africa | Tunisia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/370281474496151167/text/000020051-20140612082620.txt | http://documents.worldbank.org/curated/en/370281474496151167/pdf/000020051-20140612082620.pdf | Planning of investment in irrigation expansion should take careful note of alternative employment opportunities and incentives for farmer participation if costly over-investment is to be avoided;Objectives statements in appraisal documents should contain specific targets so that expected outcomes are clear, quantitative, time-bound and monitorable; andProject documents should be carefully reviewed to avoid inconsistencies, especially between legal agreements and intentions expressed in PADs.
P050429 | 3rd Ozone Depleting Substances Phase-out (Montreal Protocol) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1998 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/156831474420717710/text/000020051-20140617132323.txt | http://documents.worldbank.org/curated/en/156831474420717710/pdf/000020051-20140617132323.pdf | The main lessons are:1. The umbrella approach adopted in the subprojects is appropriate since it achieves economies of scale and accelerates the pace of conversion in a given sector.2. The phase-out achievements in individual sub-projects must be underpinned by an appropriate regulatory framework prohibiting consumption of ODS in the relevant sectors. This was accomplished in Mexicoâ€™s case.3. The experience of the chillers sub-project indicates the feasibility of a revolving fund that is sustainable over time and that can help to speed the replacement of ODS-consuming equipment. 4. Funding approvals for new equipment and processes under the MP should not be solely on the basis of cost, but should also be based on technology. In the mobile air conditioning sector some equipment is performing less than fully effectively because decision were based exclusively on least cost. 5. The indicative ceiling approach to MP grants is appropriate since it enables a flexible response to changing circumstances.6. Close supervision and oversight by the relevant government agency are critically important since relatively small problems can delay implementation for months.7. Documentation and reporting requirements for the MPMF are extremely rigorous and time consuming. As the Government points out in its comments, it would be beneficial to consider easing some of these requirements especially in the case of small and medium-sized beneficiary enterprises.
P050432 | Social Protection Adjustment Project | Europe and Central Asia | Romania | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1997 | 1998 | 1999 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/307511474576967481/text/000020051-20140519080704.txt | http://documents.worldbank.org/curated/en/307511474576967481/pdf/000020051-20140519080704.pdf | A single tranche release operations requires greater care in assessing borrower's commitment to reform.
P050432 | Social Protection Adjustment Project | Europe and Central Asia | Romania | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1997 | 1998 | 2001 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/128031511185515529/text/multi0page.txt | http://documents.worldbank.org/curated/en/128031511185515529/pdf/multi0page.pdf | 5. Lessons 5.1 The context is important for drawing lessons from FESAL and SPAL. Senior Bank management took the risk of providing strong support for the new government that came to power after the elections in late 1996. In their estimate, the government was serious about reform, as evidenced by some quick policy changes. Bank management was optimistic that the pace of reform would accelerate substantially. The revised FESAL and SPAL were an important part of the Bank's support for the reform process. When the original FESAL was designed, Bank management required a comprehensive loan covering the gamut of enterprise and financial sector issues. The revised FESAL extended and deepened an already complex loan, anticipating a quicker reform pace. SPAL was designed and appraised very rapidly to provide a temporary safety net for the poor because accelerated reforms were expected to exacerbate poverty. Evidently, Bank management misjudged the government's political commitment for reform and its ability to implement complex conditionality. While the analysis of Romania's situation and direction of reforms was generally appreciated, many commentators believed that the projects neither addressed well the complexity of the reforms nor their implementation. In short, Bank staff did not understand well the political economy of the reform process in Romania. 5.2 More specific lessons emerge from the flawed design of the projects (especially FESAL)\. * The design of the SPAL was weighted excessively toward short-term palliatives rather than structural improvements in the safety net. * Both loans included too many areas of reform and conditions. FESAL started with 27 conditions for the disbursement of four tranches and added 41 conditions after revision. Although SPAL was a simpler, one-tranche operation, it had 23 conditions for disbursement and 18 follow-up measures after disbursement. While maintaining reform linkages is important, adjustment operations should focus on reform segments with a maximum of two tranches disbursed over about one year. Reform linkages can be maintained by careful sequencing or processing several loans simultaneously. The number of conditions should be limited. A few meaningful outcome targets are preferred by borrowers because they retain the discretion over specific measures to achieve those targets. FESAL's follow-up operation, the Private Sector Adjustment Loan, was processed at about the same time as the ICR for FESAL. The ICR identified this lesson, but it was disregarded, as PSAL specified 45 conditions for disbursement. Apparently, implementation is proceeding successfully, partly because the conditionality is similar to FESAL's and less demanding. It conforms better with Romania's political commitment and implementation ability. * Many FESAL and SPAL conditions were linked to processes, such as design and implementation of plans and report preparation, or to outcomes that are difficult to measure, such as achieving substantial progress in reform. As a result, monitoring performance became difficult and time consuming. Disbursement conditions should be limited, with easily verifiable outcomes. Unfortunately, PSAL also contains numerous process-oriented conditions and outcomes that are difficult to measure. * Government ownership, delivery capacity and control over program implementation were inadequate for FESAL, especially for the revised program of 1997. It was negotiated with an outgoing government, and quickly collapsed in the subsequent pressures of a national election. Responsibility for program design and implementation was diffused over many agencies. The new and inexperienced government had little understanding of the scope of its commitment or the capacity needed to deliver the reforms. Bank staff were too involved in preparation, making the project too directive, resulting in an over ambitious program requiring micromanagement by a large complement of Bank staff and consultants during implementation. Government ownership and participation were greater for SPAL, and existing programs and structures were used. Several SPAL follow-up actions were delayed, however, partly because the political aspects of implementation were not fully considered. Assurance of government commitment and its ability to follow through on loan conditions is especially important for a one-tranche operation because the Bank loses leverage after disbursement. Working with a high-level counterpart group for project design and implementation is essential for adjustment operations. Ensuring that the program has stakeholder support and the government has capacity to implement it is also crucial. SPAL's success so far is also attributed to a Project Implementation Unit, backed by a senior government minister, that tracks implementation in several ministries. * Reform programs requiring legal changes must carefully assess the legislative, legal and judicial system's ability to facilitate program implementation. Where impediments exist, the process and system should be strengthened through a separate project. * Privatization targets should focus on the percentage of state-owned assets actually transferred to private ownership and control.
P050438 | UG-PRSC 1 (FY01) | Eastern and Southern Africa | Uganda | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2001 | 2002 | 2006 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/590211475074899411/text/000020051-20140613045124.txt | http://documents.worldbank.org/curated/en/590211475074899411/pdf/000020051-20140613045124.pdf | Lessons: (i) Implementation of a series of PRSCs requires flexibility in defining benchmarks, since progress in different areas is interrelated, and unrealistic goals in one area may affect progress in others. (ii) Expected outcomes should be stated in concrete and measurable terms. (iii) Progress in anti-corruption requires more than a few benchmarks in the PRSC.
P050438 | UG-PRSC 1 (FY01) | Eastern and Southern Africa | Uganda | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2001 | 2002 | 2009 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/332711468175737633/text/489420PPAR01mu101Official0Use0Only1.txt | http://documents.worldbank.org/curated/en/332711468175737633/pdf/489420PPAR01mu101Official0Use0Only1.pdf | 6. Findings and Lessons What worked well 6.1 The PRSCs constitutedan effective mechanismto transfer resources to Government and to support its budget. There is less clarity, though, as to whether the PRSCs constituted an effective tool to produce development results. Ifthe PRSCs become a defacto instrument to transfer resources only, the process accompanying its preparationand the associated conditions may not bejustified. IfBank assistance aims at supportingthe budget and producing development results, ,it is pertinentto ask ifmaking the support conditional on prior achievements o f specified outcomes (e.g., growth, fiscal deficit) might not be more effective thanthe approach used for the PRSCs under review. 6.2 Efficacy indevelopment results varied by area o f support. Substantial results were achieved ineducation, health, and water and sanitation, where coverage expanded and the quality o f service improved. Specifically, literacy rates inurbanand rural areas rose; child and infant mortality fell but maternal mortality remained unchanged; water and sanitation services expanded their coverage, but more so inurbanareas, where 13 percent o fthe people lives. 6.3 PRSCs reduce the constraint to the Government's budget, giving the Government more flexibility to allocate resources to sectors and activities. The support helped ensure a given level o f support for the budget for education. Inpart as a result o f the support, public expenditure ineducation reached about four percent of GDP. What did not work 6.4 Budget support i s unlikely to have improved the achievement o f development outcomes envisaged for the economy. The large inflow o f external funds created absorption problems, which resultedinan overvalued exchange rate, higher interest rates, and higher unit labor costs inthe non-traded goods sector. The traded goods sector, agriculture inparticular, was disadvantaged and its potential to grow hampered. Moreover, there was little improvement in local revenue collection, probably dampening the efforts to improve governance and efficiency inpublic expenditure, since anincrease inthe taxpayer's base increases the constituency for more accountability andbetter governance. 6.5 More could have been done on improving efficiency inthe use o f public resources, improving service delivery, andpromoting rural development. It i s unlikely that the efficiency o f public expenditures improved overall given the trends in Government employment andthe allocation o f expenditure. Government employment, after declining from 320,000 to 160,000 between 1990 and 1997, increased to about 220,000 by 2003 inthe absence o f a functional review. Public domestic expenditure expanded from 14.9 percent o f GDP in2000/01 to 17.6 percent o f GDP in2003/04, and the expansion o f Government investment, 0.2 percent o f GDP, was not commensurate with the foreign assistance receivedduringthe period. Actual expenditures by sectors came close to matching the allocations for PRSC1-3 but differed from the allocations, sometimes by substantial margins, for PRSC4. Also, expenditures indefense andpublic administration exceeded their budget allocations, while expenditures inhealth, agriculture, roads, and social services fell below their budgetallocations. 6.6 Regarding public service delivery, there i s little evidence to suggest that service delivery improved inareas o f public administration other than health, education, and water and sanitation inurbanareas. Regarding rural development, the PRSCs had few interventions inagriculture, and the interventions could not alter rural welfare directly duringthe period they were active. Farmers' income declined and rural welfare deteriorated duringthe period\. the proportion o f rural people under the poverty line increased from 39 percent in 1999/2000 to 49 percent in2002/03. The PRSCs might have affected agriculture indirectly, andnegatively, because the assistance financed a larger level o f expenditure that tended to reduces the price o ftraded goods (agriculture among them) relative to non-traded. Finally, it is unlikely that the PRSCs improved governance andsecurity since neither corruption, nor the quality ofbureaucracy, nor law and order improved duringthe period under review. 6.7 The policy matrices o fthe PRSCs tended to be too large and ambitious inscope. Their large size made it difficultto separate what the Bank could support with success from what it could not. Because such separation was not carried out, the Bank's program suffered from the ambiguities.A concise policy matrix compels to make evidentthe connection (or lack thereof) between actions and results, and imposes discipline in thinkingabout development outcomes andthe specific actions that could generate them. 6.8 With their ambitious objectives andcoverage, the PRSCs strained the Government's capacity. Carrying out the program unveiled the limitedcapacity o f its organizations to deliver results. The Ministry o f Finance, Planning and Economic Development could not force the program on the agencies executing it and ensure their ownership o f it. Shifting program coordination to the Office o fthe Prime Minister improved the preparation and execution o f PRSC4, and increased the interaction between different Government ministries and their involvement inreform. Thus, the selection o f an apex agency with the proper authority is a necessary aspect for preparing and implementingPRSCs. Ratings 6.9 The review concludes that the PRSCs had substantial relevance and modest efficacy. The credits and grants sought to solve important problems, makingthe relevance o f their objectives substantial. The design fell short o f what the programs intended to achieve\. the logical chain between actions and results was not specified and several o f the actions selected for support could not leadto the objectives sought. The relevance o f design was modest. This review rates overall relevance as substantial for all PRSCs but PRSC3 whose relevance was modest because o f its weak design. Overall efficacy was modest, except for PRSC4 which was negligible, because the expected outcomes did not materialize even though most prior-actions and triggers were met. As a result, the review rates the outcome for PRSC1-2 moderately satisfactory and the outcome for PRSC3-4 as moderately unsatisfactory. Table 9. Efficacy and Outcome Rating for PRSCI, PRSCP, PRSC3 and PRSC4 Operation Relevance Efficacy Outcome PRSCl Substantial Modest ModeratelySatisfactory PRSC2 Substantial Modest ModeratelySatisfactory PRSCB Modest Modest ModeratelyUnsatisfactory PRSC4 Substantial Negligible ModeratelyUnsatisfactory Lessons and Recommendations 6.10 The PRSCswere effective inprovidingtimely andpredictable resources for the Government budget but less so inproducing development results. To produce development results, the Bank needs to pay attention to the design o f the credit, the quality o f prior actions, and their relation to the expected outcomes. 6.11 PRSCs are unlikely to be as effective as investment and sector operations for solving specific sector issues. The PRSCstended to cover macroeconomic and sector issues ina broad manner, making it difficult to cultivate ownership inthe agencies responsible for implementing the program. The assistance i s more likely to succeed when the Bank targets specific problems andworks their solution with the agencies in charge o f executing the program. 6.12 A programof budgetsupport tends to create a higher permanent level o f Government expenditurethat may not be sustainable inthe medium-term. Predictable budgetsupport may create inflexibilities inexpenditure, forcing donors to continue their support beyond what was needed or desirable. Uganda exemplifies this situation as the PRSC series grew over time.
P050439 | Privatization & Utility Sector Reform | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2001 | 2014 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/402351474628008029/text/000146597-20140617163007.txt | http://documents.worldbank.org/curated/en/402351474628008029/pdf/000146597-20140617163007.pdf | In addition to the lessons learned outlined in the ICR, the following could be considered:For projects that have lost critical start-up time, it would be useful to accelerate a mid-term review to allow sufficient time for retrofitting of implementation schedules and to guide decisions on requests for extension. This will help avoid a situation in which a number of outstanding activities at project closure would be required to be completed with unidentified funding sources.Policy reversal and interference are highly likely in reforms characterized by political sensitivity. In such cases, it may be useful to (i) seek stakeholder consensus through participatory means; (ii) clearly define an adequate legal environment through appropriate legislation and enforcement; and (iii) deal with difficult issues transparently and up-front.
P050440 | Uganda Public Service Performance Enhancement Program (UPS-PEP) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/123851467986333185/text/ICRR14756-P050440-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/123851467986333185/pdf/ICRR14756-P050440-Box393191B-PUBLIC.pdf | The ICR identifies valuable lessons, including the following:Ensuring political and technical support is critical throughout the entire project cycle. In this project, effectiveness was delayed by 18 months awaiting approval by the parliament. Even though the Bank identified the risk of potential lack of commitment and support by top leadership during project appraisal and developed an information, education, and communication strategy to provide information to lawmakers and the public, the strategy was not fully implemented. This might have led to lack of information and awareness about reforms and therefore insufficient political support.Clear and simple implementation arrangements are important, especially when technical capacity in the implementing agency is weak. Even though the weak capacity of the Ministry of Public Service was identified as a potential risk during project preparation, the project was ambitious in terms of scope and included several complex components. Also, the Results Framework was too extensive and involved the tracking of a large number of difficult-to-measure indicators. This led to many implementation challenges and had a negative impact on the achievement of the projectâ€™s objectives.
P050441 | RURAL& MICRO FIN SVC | Eastern and Southern Africa | Tanzania | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/297771474575986431/text/000020051-20140613064624.txt | http://documents.worldbank.org/curated/en/297771474575986431/pdf/000020051-20140613064624.pdf | Policy reforms can best benefit industry participants if there has been close collaboration with stakeholders during the project preparation stage.The sustainability of project benefits is made more likely when project implementation is mainstreamed into the normal operations of the implementing agency.Project implementation can be delayed if World Bank/IDA procurement procedures are not aligned with national procurement systems.A LIL may not be an appropriate instrument to support policy reforms that require consensus-building and a long time to implement.
P050474 | Education Reform Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/761161474563534688/text/000020051-20140618060258.txt | http://documents.worldbank.org/curated/en/761161474563534688/pdf/000020051-20140618060258.pdf | Education systems can be transformed if a critical mass of complementary reforms is put into place simultaneously. Such reforms become mutually reinforcing and create the essential conditions for system transformation. Focusing on one or two reforms at a time will generally not have the same impact;In countries where professional capacity is widespread it is advisable to outsource many specialized functions such as organizing conferences, conducting training and capacity building, preparing training materials, and undertaking impact assessments. Outsourcing of such tasks to the right service providers can build additional experience and capacity in them and unburden often overloaded project implementation units;Programs which are rich in innovation and reform accompanied by research and evaluation results should strive to capture these through publication programs. Far too many programs fail to contribute to progress in the sector (and improvements in other locations) because their experiences have not been documented or are inaccessible to outside parties; andIt is important that realistic monitoring and evaluation indicators be chosen and appropriate baseline data be collected prior to project implementation. When in the course of implementation it is determined that indicators chosen are not realistic or appropriate, the project can be restructured to add or revise indicators.
P050483 | RY CHILD DEVELOPMENT | Middle East and North Africa | Yemen, Republic of | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/366861474555643687/text/000020051-20140615104316.txt | http://documents.worldbank.org/curated/en/366861474555643687/pdf/000020051-20140615104316.pdf | Where institutional capacity is limited, project design and implementation arrangements should be kept simple. The project proved to be difficult to implement because the complex design included several sectors, the project was implemented through several GOY ministries and agencies, it relied on decentralized implementation, and it engaged local communities in planning and implementation. A multi-sector area-based program requires a functional decentralized policy framework and a supportive management/administrative structure, neither of which was present in Yemen. Adequate attention should be given to areas of comparative advantage among partners. UNICEF brought to the table its technical capacity and knowledge of childhood issues, and their track record of working in the country. The Bank tended to defer to UNICEF, which focused disproportionately on the education sector, instead of better utilizing its own expertise in areas like health and water.An adequate monitoring and evaluation system should be in place at the very earliest stages of project implementation for assessment of project progress and maintaining focus on development objectives; informing annual planning; and maintaining a credible supervision process. Innovative programs need to be assessed and institutionalized before scaling up. A more rigorous assessment and institutionalization of the innovative ABP would have provided a sounder basis for scaling up the program in the form of the CDP. It had been piloted in a few districts in Yemen, but it was still in the early stages and not yet able to provide appropriate lessons needed to expand the scope and magnitude of the CDP. Candor and realism in project ratings are imperative to a project's success. Throughout project implementation, the project was rated satisfactory and considered to be on track to achieve the project's development objective. Had the project team been more candid in its assessments and reporting, adjustments to the implementation arrangements and overall scope could have positively impacted project progress.
P050484 | Secondary Education Enhancement Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 1999 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/209591474663190902/text/000020051-20140626111743.txt | http://documents.worldbank.org/curated/en/209591474663190902/pdf/000020051-20140626111743.pdf | IEG has synthesized the lessons presented in the ICR (pp. 35-37) to the following:Proper design and evaluation, as well as realistic objectives, are required. Given that this was the first Bank project in secondary education in Egypt, the goals and objectives needed to be modest, not attempting to address all issues. In this project, there was insufficient attention to analyses to develop the justification for the school conversion component, which led to design weaknesses. Preparation neglected baseline data collection, which was compounded by the lack of M&E expertise and inadequate attention to evaluation during implementation.
P050486 | COAL SECAL 2 | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1998 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/652321475097281730/text/000020051-20140607152419.txt | http://documents.worldbank.org/curated/en/652321475097281730/pdf/000020051-20140607152419.pdf | Complex reform programs in difficult economic and political environment require time and flexibility;Government commitment and political will, and effective stakeholder participation are crucial in undertaking complex and politically contentious reform programs; and Field office staff can play an important role in ensuring the success of a major reform program through effective day-to-day management of operations.
P050486 | COAL SECAL 2 | Europe and Central Asia | Russian Federation | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1998 | 2002 | 2003 | PPAR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/263461468781516840/text/260670RU0PPAR.txt | http://documents.worldbank.org/curated/en/263461468781516840/pdf/260670RU0PPAR.pdf | lessonsof generalapplicability in the caseof complex andpolitically contentiousreform programswith a high social impact\. l Governmentcommitment andpolitical will areindispensable. External financing in supportof coal restructuringin Russiaprovided apowerful incentive to staythe course,but the decisivefactor in securingsuccesswas the fundamental commitment of the Government. l Effective stakeholderparticipationcan greatlyenhancerobustnessof the achievementsandlessenthe implementationandinformation burdensof the Governmentandthe Bank. A particularstrengthof the designand implementationof both Coal SECALs wasthe constantattentionto and involvement of the variousrestructuringstakeholders,beginningwith the analytical sectorwork by the Bank andthe Government'ssectorpolicy statement in the yearsprecedingthe operations. l A strengthenedsafetynet helpsgreatlyin gaining acceptanceof enterprise closuresamongworkers andtheir communities, evenin difficult andpolarized situations. l Adequateattentionandfunding shouldbe devotedup front to the environmental aspectsof enterpriseclosures(especiallyin the caseof mines) to minimize the problem of largeresidualliabilities that may hold up the liquidation of enterprises that havealreadyceasedoperations. l Finally, implementation schedulesshouldbe realistic andflexible, while disbursementsshouldbe tailored to concreteprogressin agreedreforms. The Coal SECAL II wasunderimplementation for four yearsinsteadof the originally plannedtwo years,with most of theprogressrecordedin the lasttwo years. Moreover, the 1999restructuringof theloan's original floating tranchesinto smaller, more manageabletrancheswas instrumentalin facilitating implementation of the agreedrestructuringactions.
P050487 | Development of State Statistical System Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/379191475097180091/text/000020051-20140618085610.txt | http://documents.worldbank.org/curated/en/379191475097180091/pdf/000020051-20140618085610.pdf | ICR lists seven valuable lessons learned in the STASYS project which are fully applicable to all complex, IT intensive multi-agency projects, and beyond. Lessons range from multi-agency coordination problem to accommodating non-technical considerations, providing legal basis and external agency as the PIU. We would like to emphasize the importance of realistic project preparation and implementation with special attention given to adequate time allowances for unforeseeable delays and project risks which turned out to be a major stumbling block in ratification and project implementation. We would add an additional lesson learned from this project -- the value of continuously engaging the borrower in an evolving and expanding project design leading to enhanced ownership and greater leveraging of Bank lending resources for development results.
P050489 | Fiscal Federalism & Regional Fiscal Reform Project | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2002 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/892541474944941917/text/000020051-20140614184130.txt | http://documents.worldbank.org/curated/en/892541474944941917/pdf/000020051-20140614184130.pdf | 1. A competitive model for selecting participants in a reform program can be effective. This presented incentives for promoting reform among potential candidates, and then rewarding the successful candidates. At the same time, those not selected for an early round had a chance for selection in a later round, thereby keeping incentives alive. It is essential that such a competition be very transparent and according to well established rules, as was true in this case, where no complaints were received from those units not selected for participation. 2. Technical assistance is important for successful preparation and implementation of reforms, and needs to be properly phased in advance to ensure that reforms are ready for implementation. 3. Subnational fiscal reforms can be an important area for the Bank to support with policy based lending.
P050491 | Structural Adjustment Loan 2 | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1998 | 1999 | 2002 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/566021474905667812/text/000020051-20140602103354.txt | http://documents.worldbank.org/curated/en/566021474905667812/pdf/000020051-20140602103354.pdf | (a) Ownership is essential for the success of an adjustment program; thus, the end vision must be clear, mutually agreed, and broadly owned at the outset, in a programmatic fashion. (b) Separate sectoral operations, back-loaded disbursements, and floating tranches should be used to assure a tighter linkage between increases in the country's debt to IBRD and the implementation of irreversible reform measures in a highly volatile political environment and varying degrees of commitment and capacity across sectors.
P050491 | Structural Adjustment Loan 2 | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1998 | 1999 | 2003 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/625211468304275740/text/multi0page.txt | http://documents.worldbank.org/curated/en/625211468304275740/pdf/multi0page.pdf | 6. Lessons 6.1 The Bank's experience with the two RLs confirms a number of lessons that have been learned in other emergency support operations\. Assure flexibility in the use of rehabilitation loans and avoid pre-identification of specific imports. For operations designed to address key social needs and/or production bottlenecks, projects require a maximum degree of funding flexibility. Earmarking portions of rehabilitation loans complicates implementation and in some cases can delay disbursements beyond a time when they are urgently needed. * Ensure adequate supervision coefficients. For rehabilitation loans and emergency import projects, standard supervision coefficients may not be appropriate. This is especially for so for new borrowers unfamiliar with Bank procedures. * Sound macroeconomic management is a pre-requisite for the positive responses expected to flow from structural reform, under all policy-based type of lending. 6.2 The lessons from the Bank's experience with SAL I and SAL I1, although not fully recognized in the ICR, have been subsequently incorporated in SAL III\. * Broad country ownership is crucial. TIhus, it is important for the Bank to pay close attention to the political and institutional aspects of reforms and consult with all relevant units of government and civil society, so as to improve the relevance and design of its activities and avoid operations where commitment is weak. * In the face of a poor track record and narrow country ownership of reform, a large adjustment lending program, especially one with front-loaded disbursements, risks delaying rather than accelerating reform.22 * In the face of a poor track record and a new consensus on a reform program, adjustment lending should be available only after the government has publicly adopted the necessary reforms or has begun implementing them, as was the case for the Coal SECALs. Separate sectoral operations, back-loaded disbursements, and floating tranches should be used to assure a tighter linkage between increases in the country's debt to IBRD and the implementation of irreversible reform measures. Disbursements should be backloaded and carefully modulated on the basis of solid progress in implementation, including enforcement of laws and regulations.23 * There needs to be strong strategic coordination and integration of actors, instruments, and interventions supporting common objectives in programs 22 ECA management is skeptical that advice alone, however useful, could have carried much weight in Russia. 23 The Coal SECALs and SAL III, especially after their restructuring in 1999, were good examples of such an approach. The ECA Region's management, however, in their cormments to a previous ICR review by OED of SALs I and II and again to the Russia CAE, have questioned whether adjustment loans should only be offered after adoption of reforms. In their view, in cases where the Bank is called upon to provide adjustment lending to help resolve a rapidly unfolding crisis, for example, it is unrealistic to think that such support should only be provided when there is strong prior political ownership and consensus about the reform path. Moreover, there is often a lag in the take-up of new policies, as in Russia prior to the year 2000. supported by the Bank as well as by Russia's other development partners. For the most part, the TA provided to the Russian authorities under SALs I and II worked well in the design of specific measures and in their implementation. But in some areas, the integration between TA and on-the-ground implementation of policy measures was insufficient, such as in the financial sector. 6.3 Common to all four operations as well as the rest of the Bank's assistance in Russia are other important lessons\. * The Bank should pay attention to the quality of public institutions and governance. While considerable Bank support has been provided for institutional development since the inception of the Bank's program of assistance to Russia, the problem of governance was not frontally addressed. It is clearly a serious impediment to development-the absence of rule of law, for example, has been one of the most serious deterrents to foreign direct investment and a major factor behind capital flight. The issue has been complicated by the weak tradition of property rights, exacerbated in the communist period, where control rather ownership has long been the basis for the beneficial use. It has also been complicated by the major distortions in Russia's post-communist economy, which have created all kinds of perceived inequities, and by the use of wild accusations of corruption as a standard part of the political battle. In terms of ensuring that the funds it lends are safeguarded, the Bank should address the important challenge of improving the overall quality of expenditure controls and accountability in Russia's budgetary system. * Keep windows of opportunity in perspective. One of the clearest lessons from all the Bank assistance in Russia is the under-estimation of the complexity of the task of structural reformn. Deep-rooted political, social, and individual behavioral changes are necessary before the transformation will be complete. This will take time-perhaps another generation. In this context, the focus must be maintained on structuring operations that bring about and support the implementation of mediumand long-term structural change, not quick fixes. This is another argument for TA and multiple-tranche operations, in support of well-articulated medium and long-term reform roadmaps.
P050495 | VE- CARACAS METROPOLITAN HEALTH | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/399101474629376797/text/000020051-20140618081813.txt | http://documents.worldbank.org/curated/en/399101474629376797/pdf/000020051-20140618081813.pdf | An adequate political climate is crucial for project success, especially when the project involves the action and interaction of many actors and is implemented in the context of a newly adopted decentralization policy;For a project designed in support of a decentralized approach, a project management function that is too centralized is likely to be inefficient and to undermine the underlying principles of decentralization that the project is trying to apply; andInformation systems and data on government programs constitute a public good. The creation of systems and data which overlap with those already created and the failure to share these across public agencies will undermine a nationâ€™s ability to consolidate targets, goals and objectives and to track and improve the effectiveness of various interventions aimed at common objectives.
P050508 | Urban Transport Project | Europe and Central Asia | Uzbekistan | Blend | FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/679881474493514881/text/000020051-20140615112939.txt | http://documents.worldbank.org/curated/en/679881474493514881/pdf/000020051-20140615112939.pdf | For projects embarking on a challenging institutional transformation, getting the institutional framework right before the project starts can significantly reduce implementation risks. Monitoring and Evaluation (M&E) systems need to be carefully designed to ensure that monitoring efforts produce data that are useful in assessing project outcomes and impacts. In addition to quantitative outcome indicators, projects should also include qualitative monitoring. Also, projects should provide sufficient resources to carry out M&E. In case of projects with large contracts with new borrowers, it is important to agree during negotiations on the main procurements documents that would be required, so that procurement can start immediately after effectiveness and without delays.
P050529 | LB - Cultural Heritage and Urban Dev. | Middle East and North Africa | Lebanon | IBRD | FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/409191511361584388/text/ICRR-Disclosable-P050529-11-22-2017-1511361567204.txt | http://documents.worldbank.org/curated/en/409191511361584388/pdf/ICRR-Disclosable-P050529-11-22-2017-1511361567204.pdf | One particularly important lesson wasselected fromthe ICR, with some adaptation of thelanguage: In cultural heritage projects, there is an opportunity to contribute to socialcohesionthrough leveraging culturalheritage as a cornerstone of identity. Under this project, theimpactassessment showed that young people not only benefitted from employment opportunities butalso showed pride intheir cultural heritage and identity.IEG-identified anadditionallesson: Risks in cultural heritage projects areexacerbated by uncertainties ofchance discoveries on archeological sites. Under this project, delays associated with an unusually highnumber of chance discoveriesand uncertainties associated with rehabilitation works wereamplified withthetesting restrictions imposed on historical buildings and structures.
P050529 | LB - Cultural Heritage and Urban Dev. | Middle East and North Africa | Lebanon | IBRD | FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2017 | 2020 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/513381569466908292/text/Lebanon-Cultural-Heritage-and-Urban-Development-Project.txt | http://documents.worldbank.org/curated/en/513381569466908292/pdf/Lebanon-Cultural-Heritage-and-Urban-Development-Project.pdf | 4. Lessons 4.1 Assigning economic values of cultural heritage requires consideration of both its use and nonuse values. This principle has been well recognized by the World Bank's analytical work on the subject, including in the Economics of Uniqueness (Licciardi and Amirtahmasebi 2012). Whereas use values can be estimated by calculating entry prices to tourist sites or tourist spending, nonuse values require the calculation of public good benefits. These benefits include symbolic, spiritual, historic, scientific, and social values that vary among users and nonusers of the heritage. Some heritage sites may have cultural value but no economic value. The reverse is true for other sites. Therefore, the valuation of heritage requires a way of calculating the benefits and costs of tangible and intangible benefits, especially in the context of a World Bank loan. 4.2 Urban rehabilitation projects designed to expand public space require ex ante and intermittent analysis of the risks associated with local economic displacement caused by restricted access and the changing preferences of upgraded space. CHUD added a significant amount of pedestrian space by removing parking and narrowing roads. Although the quality of life in the city centers improved for many residents, cafes and restaurants displaced traditional shops in some upgraded areas. The need to accurately estimate the aggregate economic and social gains of urban rehabilitation activitiesâ€”including by understanding and mitigating the effects of economic displacementâ€”is both a social standard and a core tenant of good project design. 4.3 Infrastructure-led urban rehabilitation of economically dense and culturally sensitive urban cores requires complementary investments in soft skills to ensure effective two-way communication about project aspirations and to adapt to citizen concerns. CHUD had a technically sound urban planning focus, with interventions planned to reduce the effects of congestion and pollution on the heritage it was designed to protect. But in the more complex citiesâ€”especially those with weak enforcement capacityâ€”the integrity of urban reforms was undermined by the challenges associated with building consensus among citizens with disparate interests. Since then, the World Bank has engaged in building this type of capacityâ€”for example, in the participatory design of urban rehabilitation through mechanisms such as charrettes, which are creative, intense working sessions using public workshops and open houses (common in architectural design processes). 4.4 All cultural heritage and sustainable tourism investments must be designed to respect residents' needs and aspirations and to protect communities' residential right from unintended consequences. The CHUD experience reveals that residential upgrading requires a robust participatory design and implementation process to understand and honor residents' aspirations. It also requires close supervision to ensure that equipment and materials are of the highest quality and that contractors behave with integrity.
P050530 | RY-SANA'A EMERGENCY POWER | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/855211474492610545/text/000020051-20140613081638.txt | http://documents.worldbank.org/curated/en/855211474492610545/pdf/000020051-20140613081638.pdf | (1) The Bank should avoid the use of complex, innovative models to solve institutional problems in small countries with little potential for attracting foreign investments, particularly when the country has limited capacity to design, negotiate and supervise complex contractual arrangements with potential private investors. The saga of the failed O&M contract for DDP illustrates this. (2) Given the close relationship between gas and power, the Bank could have done a better job in advising and assisting GOY in expediting gas development for power independently of LNG export schemes in which the GOY was primarily interested. The delays of almost a decade in developing Yemen's gas fields amounts to very high macroeconomic losses for the country. (3) Capacity-building programs and reduction of energy losses should always be included in the Bankâ€™s power projects that seek to improve the performance of power utilities. They are often slow to yield results but they are recognized as a good practice for institutional strengthening when the objective is to achieve better electric utility performance.
P050540 | CRITICAL IMP REHAB | Europe and Central Asia | Bulgaria | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1997 | 1998 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/703731474849285824/text/000020051-20140526210804.txt | http://documents.worldbank.org/curated/en/703731474849285824/pdf/000020051-20140526210804.pdf | One-tranche quick disbursing operations are appropriate where: (i) an agreed multi-year program is in place to be supported by a series of lending operations; and (ii) there is uncertainty in the environment and weak institutions which require recalibration of program design and implementation details.
P050544 | LB - First Municipal Infrastructure Project | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/322691474652391110/text/000146597-20140619161220.txt | http://documents.worldbank.org/curated/en/322691474652391110/pdf/000146597-20140619161220.pdf | Among those reported by the Bank and Borrower ICRs, IEG highlights the following:In countries where short-term political interests are in play at the national level, a project team can adopt a decentralized mechanism of implementation that can shield municipalities from higher level political interference. The project lacked clearly defined monitoring indicators. For M&E to succeed it should focus upon achieving results, particularly for the poor and should be unduly burdensome for the municipalities to manage. Strong M&E can also help reduce the expense of cost-benefit analysis by providing the data needed to carry out economic analyses. Given the complexity of and resistance to cost recovery, it would be prudent for project designs to include realistic (i.e. modest) cost recovery systems. This particular project had no cost recovery mechanisms built into its design, in part because it would not be effective to expect large scale impacts from small-scale municipal investments.In countries like the Lebanon, where finance for municipal infrastructure is limited, a sustainable municipal development fund (MDF) type of intermediary can play an important financing role, as well as increasing municipal capacity to identify and implement local investments. There is a clear need for implementing agencies working with many municipalities to develop and maintain a central database to allow them to track the physical conditions of municipal infrastructure, particularly to learn where problems arise and to know where actions to fix them is needed.The experience of this project shows that central authorities should encourage and help municipalities prepare and implement Municipal Master Plans to help municipal authorities map out their responses to where and when urban services and infrastructure need to be improved.
P050567 | KUREIMAT SOLAR THERMAL HYBRID PROJECT | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2008 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/318111474750597540/text/000020051-20140625192044.txt | http://documents.worldbank.org/curated/en/318111474750597540/pdf/000020051-20140625192044.pdf | The ICR provides the following two significant lessons which are adapted slightly below: Projects that seek to demonstrate a new approach and technology (CSP in this case) can be highly effective when used as tools for â€œvisual learningâ€. The Kureimat Project has made significant impact as one of the first CSP projects in the region and contributed to learning and greater awareness for CSP technology within Egypt, in the region and globally. The procurement and implementation strategy for a project should be aligned with the capacity of the implementation agency. Early planning for this project envisioned a single Engineer, Procure, Construct (EPC) contract for the solar and power plant implementation. However, this was split into two different contracts due to separate sources of funding with their own procurement requirements. The project experience suggests that the split contract approach has hindered rather than helped the implementation process in both the construction and O&M phases. An approach involving a single EPC contractor with responsibility for operations and maintenance would have been a better model in this context.
P050576 | CO- YOUTH DEVELOPMENT | Latin America and Caribbean | Colombia | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/160401474490738497/text/000020051-20140612101008.txt | http://documents.worldbank.org/curated/en/160401474490738497/pdf/000020051-20140612101008.pdf | The ICR draws several lessons which this review supports. Some of the ICR lessons are listed below:1. While LILs are designed to be exploratory instruments, objectives must be precise in order to obtain interpretable results.2. A Strong monitoring system and rigorous evaluation are indispensable to derive useful lessons for future interventions.3. Participatory approaches to design and implementation of programs are feasible but need to be carefully directed and focused on clear objectives, stating the role of participation upfront.4. Youth enter programs with different vulnerabilities, a factor which affects the extent to which they can benefit from a less individualized approach.5. Schools are ideal vehicles to deliver youth services and promote youth activities involving students and out-of-school youth.6. Interventions addressing youth employment have to involve employers directly.7. It is important not only to give youth a voice in service design, but to give them public recognition.8. Project implementation is aided by continuity in Bank and client project staff.
P050578 | Rural Education Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/573911474635339864/text/000020051-20140618055107.txt | http://documents.worldbank.org/curated/en/573911474635339864/pdf/000020051-20140618055107.pdf | Working to provide â€œaccess to qualityâ€ education is an effective way to keep expansion and quality improvement in balance. Innovative pedagogical models which are demonstrated -- and recognized by parents and the community -- to have positive effects on student learning can help to increase demand for and better participation rates in basic education. Broad political support and participation/ownership at all government levels are important factors in assuring continuity of implementation even when governments change during the course of a project. It also helps for project objectives and design features to be well aligned with broad social policy goals. Where pedagogic renewal is being undertaken under conditions of management decentralization, it makes sense for the central government to exercise supply functions (standard setting, knowledge management â€“ testing and disseminating information about innovative models, quality control and teacher preparation) and localities determine their own mixes of innovations through bottom-up, demand driven approaches. Public-private partnerships (like the tripartite alliances in PER I) can be effective in creating community consensus in support of innovation and in generating new resources. Bringing innovative programs to scale is crucial if a change program is to have anticipated social impact, but it is important that scaling up be done over a reasonable time period to assure readiness and sustainability.
P050589 | Transport Sector Project | Europe and Central Asia | North Macedonia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/852281474420147984/text/000020051-20140613050201.txt | http://documents.worldbank.org/curated/en/852281474420147984/pdf/000020051-20140613050201.pdf | Before recommending a ready-made technical solution, ensure that it takes into account the specific features of the problem, and the client's institutional readiness to adopt new methods and processes.
P050595 | Land Administration Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2010 | 2012 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/644731474483695659/text/000020051-20140624201348.txt | http://documents.worldbank.org/curated/en/644731474483695659/pdf/000020051-20140624201348.pdf | The following lessons are inspired by the discussion in the ICR: Land administration projects work best when they facilitate the implementation of laws that are already on the statute books; given the time needed to secure the passage of legislation, project implementation is likely to be severely delayed if the necessary laws are not in place when the loan is made effective. Projects will not succeed in regularizing indigenous land rights unless they are preceded by broad consultation and consensus building; even after such consultation, consensus tends to be fragile given the diversity of the claims at stake. Where separate cadastre and registry institutions have existed for many years there will be powerful vested interests opposed to any attempt to shift to a single-agency model (partly because the registry is a major source of rent); even the more limited objective of developing a common technological platform between registry and cadastre (the approach pursued by this project) is likely to be difficult because of the institutional rivalry that has grown up.
P050601 | Social Fund II Project | East Asia and Pacific | Cambodia | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2005 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/637341474594874415/text/000020051-20140613082623.txt | http://documents.worldbank.org/curated/en/637341474594874415/pdf/000020051-20140613082623.pdf | The ICR has extracted a number of relevant lessons from the experience with this project.Monitor outcomes and evaluate impact to assess development effectiveness. To assess development effectiveness input and output indicators (amount disbursed, sub-projects completed) should be supplemented by outcome and impact (sustainability, benefits) indicators. For projects benefiting a large proportion of the population, use of household surveys to monitor impact (for example capacity enhancement) should also be explored. Find mechanisms to ensure appropriate targeting. Projects aimed at supporting poor communities and specific beneficiary groups should have a coherent targeting mechanism in place. In addition, indicators that measure whether project benefits are reaching the target groups should be developed and monitored to facilitate adjustments during implementation.Tackle transparency issues systematically especially for an effective procurement process. Well-defined procedures, adequate training, rigorous internal monitoring, regular independent external evaluations, and appropriate and enforceable penalties and a commitment to invoke them is required as well as continuity of Bank staff, frequent site visits, and through country knowledge. Communicate through regular and consistent dialogue with all stakeholders to achieve sustained impact. For example, SFKC could have a substantial institutional impact on the capacity of government agencies had it communicated and collaborated more extensively with them through dialogue, data sharing, technical assistance and training sessions. Plan for hand-over or exit strategy to ensure lasting institutional development impact. For all Social Funds and especially for this one where the implementing agency enjoys a high degree of autonomy, it is important to include mechanisms to ensure that the valuable processes, skills, and systems which are developed can be adopted by and/or passed on to national and local institutions.
P050608 | PA PUBLIC POLICY REFORM | Latin America and Caribbean | Panama | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/373821475088120686/text/000020051-20140528125614.txt | http://documents.worldbank.org/curated/en/373821475088120686/pdf/000020051-20140528125614.pdf | The objectives of this project were modestly chosen but achieved with a fairly high degree of success. As stated in the ICR, "Borrower ownership and selectivity in conditionality were key to the operation's success." Nevertheless, election year pressures were responsible for some shortfalls in achieving fiscal targets. These adverse impacts might have been mitigated by a public awareness campaign, which should generally be considered as an essential part of an operation such as this.
P050612 | SV EDUCATION REFORM | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/624151474549891497/text/000020051-20140617134401.txt | http://documents.worldbank.org/curated/en/624151474549891497/pdf/000020051-20140617134401.pdf | Community-management of schools is an important tool of expanding coverage and improving the quality of education where this is possible. The decentralization of school management may bring, among other impacts, an efficient use of funds and fosters innovation at the school level. - It is important to seek partnerships in order to implement policies and strategies. Different actors, such as universities, foundations, and unions contribute to strengthen participation, create solid national consensus around changes in education, and consolidate reforms.- Expansion of access in remote areas and efficiency improvements are often more difficult to achieve than expected. Targets for improved efficiency should be more conservative when the coverage goals are ambitious.
P050613 | NI SECOND BASIC EDUCATION PROJECT | Latin America and Caribbean | Nicaragua | IDA |  | Human Development | Education | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/117881475111541036/text/000020051-20140613075442.txt | http://documents.worldbank.org/curated/en/117881475111541036/pdf/000020051-20140613075442.pdf | Scholarships targeted to the underprivileged help to keep students in school. Interventions focused on the demand for education can be successful in reaching the students who are the hardest to reach.-Wider dissemination of information about the activities being implemented by a ministry can help win participation from key stakeholders and increase the impact of project actions. Involving the community in education decisions and infrastructure activities may pay off in cost-effectiveness of construction and maintenance.-Choosing adequate indicators can support assessing progress towards achievement of outcomes. Outcome indicators should best be defined from the beginning of project in order to assess achievement of development objectives along the way.- Investments on teacher training are most effective when based on clear strategies on how to improve teacher effectiveness through this vehicle. Training on the content necessary to teach students (e.g. 5th grade math) is often very much needed but neglected.
P050615 | PUB.SECTOR MNGT.PROG | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/639731475077528766/text/000020051-20140612134705.txt | http://documents.worldbank.org/curated/en/639731475077528766/pdf/000020051-20140612134705.pdf | 1. Broad ownership of reform is necessary before embarking on projects to support wide-ranging reforms. In the absence of such support, pilot projects are better suited to testing new approaches. 2. The implementing and coordinating agency needs to have authority commensurate with its task. In this case, the implementing agency faced opposition from agencies of substantial power which were to be reformed through the project.
P050616 | Second Community Water and Sanitation | Western and Central Africa | Ghana | IDA |  | Sustainable Development | Water | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/530391475077925747/text/000020051-20140613052747.txt | http://documents.worldbank.org/curated/en/530391475077925747/pdf/000020051-20140613052747.pdf | Capacity building for implementation at local level for operation and maintenance is critical for the success of decentralized implementation.Clear and enforceable "rules of game" should be developed for decentralized implementation of the project.The flow of funds from center to local level should be efficient. It is important to strengthen the financial management systems and oversight mechanisms necessary to ensure quick turnaround of funds by the Districts.Private sector capacity to respond to increased demand is crucial. Private sector support initiatives should be tailored to develop capacity of Small and Medium Enterprises (SMEs) in the water sector to respond adequately to business opportunities emanating from local demand and could be supported by projects or be part of the overall government capacity building programsFor effective promotion of sanitation, the Bank should aim at providing cheaper latrines (using for example local materials) and design sanitation interventions with an emphasis on sustained community-level marketing.
P050616 | Second Community Water and Sanitation | Western and Central Africa | Ghana | IDA |  | Sustainable Development | Water | IDA | IPF | 2000 | 2005 | 2007 | PPAR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/695021468030674414/text/36597.txt | http://documents.worldbank.org/curated/en/695021468030674414/pdf/36597.pdf | Lessons for the Future 94. All o fthe principal lessonsfrom this performance assessmentrelate directly or indirectly to Ghana's decentralization program; from the apex organizations and local governments to the local communities. While all three projects are inthe water sector, the lessons are inmost cases not only relevantto water. They provide lessons for other sectors providing local public services inGhana, and for decentralization programs inother countries as well. 95. All three projects werepath-makers. Underthe UESP a start was madetowards decentralization inthe urbanenvironmental sanitation sector. The CWSP-2 andthe VIP took . decentralization further, succeeding intransferring implementationto the DAs, and then to rural communities. The CWSP-2 andthe VIP decentralized well before nearly all other sectors inthe country. The CWSP-2, the VIP and, to a lesser extent, the UESPhave shown that decentralization can be successful. Initselfthis i s important as reassuranceto individuals andinstitutionsthat are skeptical ofdecentralization. These projects provide a rich experience as concerns their specific implementationmodalities, mostly inbest practice, but also with lessons stemming from mistakes or problems encountered. 96. The lessonsfall under three broad areas. First, from the projects' experiences there are a set of lessonsrelatingto what is needed inthe institutionaland policy environment. Second, all o f the projects found that major capacitybuildingwas needed. Third, sustainabilitywas amajor issue, andneededto be addressedas a priority. Table 5 summarizes the points Co~ered.~' 1. ANENABLING INSTITUTIONALAND POLICY ENVIRONMENT 0 Long-termcommitment\.Decentralizationis a long-termprocess, andneeds consistent and sustained support inorder to succeed. This has beenthe case inGhana. The Government's interest indecentralization started to develop inthe early 199Os, well before the three projects commenced. The Bank has consistently supportedthe 49. It shouldbe emphasizedhere that the points beloware the practicallessons directlyderived fromthe three projects reviewed. While the lessons are wide-ranging, they are not intendedto providecomprehensive coverageofall issuesrelatedto decentralizationand communitydrivendevelopment. decentralization agenda, starting inthe mid-199Os,and the 2004 CAS emphasizes continued support. A demand-drivenapproachincludingbeneficiarycontributions\.The CWSP-2 and the VIP were implementedthrough a demand-driven approach requiringDAs and the communities to select themselves as project participants. Inparticular, they requiredanup-front financial contribution from the DA and community. The project experience has found this to be important\. for DAs to demonstrate their commitment; for creating community ownership o fthe facilities; andto helpreduce the cycle o f dependency (expecting everything fiee) which hastendedto prevail inGhana's rural societies. 0 Agreed institutionalroles\. These needto be clear andagreed. The VIP involveda numberofdifferent ministriesandagencies. Their roles and specific responsibilities were clearly defined. This was thenformally agreed inMemorandums of UnderstandingbetweenRICUandeach agency. The projects also established the responsibilities o f the PU, CWSA or RICU relative to those o fthe MASor DAs.For thetwo ruralprojects (the CWSP-2 andthe VIP), clear rolesbetweenthe DAsandthe communities also hadto be defined andwidely understood. 0 Clear andwidely distributedrules of the game\. Understandingwhat to do and how to do it is key many new actors are involved andthey needto operate effectively. The Pxoject Operation Manuals (POMs) for boththe VIP andthe CWSP- 2 were clear, detailed, anddistributed to all staffand agencies with implementation roles. Hence, there was sound guidance and minimalambiguity at all levels. The CWSP-2 went further. After the POM (primarily for CWSA staff), there was thena D O M(District Operation Manual) for the DAs, andthena C O M (Community OperationManual). Thus, the DAs and Communities had focused material specifically needed for them. 0 Harmonizedimplementationmodalities\.The borehole programs underthe CWSP- 2 andthe VIP commenced a harmonizationprocess, bothamong donors andamong differentgovernment departments. The progress made, while only partial, hasbegun to exempli@ the advantages o fharmonized implementation. Previously, eachdonor tended to have its own implementationmodalities, andprojects even overlapped geographically. This confusedthe DAs and communities. Progressively, donors and government have been convergingtowards a single implementation model; for instance, for boreholes, essentially the CWSA model. This inturnwill facilitate further harmonizationto programapproaches, withcombined and simplified donor assistance. 0 Minimalpoliticalinterference\. Caseswhere localpolitical interests have influenced borehole committee membership have beenreported, which would not necessarily enhancethe committees' social cohesion and capacity. Processesto minimize local politicalinfluences would be desirable. 2. A MAJOR DRIVETOBUILDIMPLEMENTATIONCAPACITY 0 Software, and software first\. Capacity buildingshould be emphasized as muchas or more than infrastructure, and most capacity buildingshould be done up-front. The CWSP-2 andthe VIP emphasizedsohare (training, extension, technical assistance) for capacity building.Further, for every DA and every community, the capacity buildingwas done before the infrastructure. For communities, completionofthe requiredtraining andformation oftheir committees were mandatory before any construction. These two projects, andthe UESP, providedsubstantial training for the DAsor MASandfor the communities inthe case o f the rural projects. 0 Massive training\. Trainingwas massive. For the two CDD projects, training covered all actors\. communities, DAs, andprivate mechanics and suppliers o f spare parts. The UESPhadintensivetraining for the MAS'Waste Management Departments.The scale ofthe training considerednecessaryfor the CDD projects bears emphasizing for other decentralizationprojects. The CWSP-2 trained over 3800 communities, groups or individuals. The VIP, covering all o f Ghana's districts andrequiringa greater rangeo f skillneeds, hadsome 5800suchtrainings. 0 Strong central coordination\. Strong central coordination and guidance is necessary. Thevery natureofdecentralization meansthat manyinstitutions haveto quickly master their new responsibilities. Eachproject hada strong coordination unit\.the PUfor the UESP, RTCU for the VIP and CWSA for the CWSP-2. Eachmanaged to provide the MASor DAswiththe necessarysignificant training andtechnical assistance. 0 M&Eto facilitate programadaptation\. Capacity to assessandprovidefeedbackto managementonproject impacts is needed. M&E for all three programs was not sufficiently developed duringproject implementation to inform management onproject impacts andissues. Thus, had CWSA's M&Ebeenstrong, issues such as the needor otherwise for follow-on supportto communities would be clearly known, whereas, even now, this remains a question. Underthe UESP, the PUandmunicipal WMDs, could have hadmonitoringsystems providingregular reports onthe state o f maintenance and funds. This mighthave helpedbetterdecision makingbythe municipalities regardingboththe allocation o f funds andthe needfor increased municipal revenues. 0 Development of private sector service providers\. The CWSP inparticular included trainingofinterestedindividuals to beprivate mechanics, andfacilitated the development of a network of shopkeepersto stock andsell spare parts for boreholes. Over 650 private individuals or entities were trained. These included\. drillers, contractors, consultants, mechanicsandother privateparties where capacity enhancementwas neededto foster the development o fa private sector support network. 0 Includinghygiene education\. The CWSP-2 (inparticular) andthe UESP included education inhygiene practices. For the CWSP-2 ,this was a fully integratedpart o fthe trainingofthe WATSANs. A healthspecialist was included ineachDWST's extension team (the other two were anengineeranda CDD specialist). Significant improvements incommunityhealthwerereportedbyseveralWATSANs visited. Hygieneeducation initiativesby an urbanschool were considered important. Hygiene education and extension i s anatural concomitant inwater supply and sanitation programs. The costs of includinghygieneeducation are usually modest relative to thebenefits. 3. MAKING SUSTAINABILITY A CENTRAL FOCUS 0 Prioritizingrevenuesfor O&M financing\. For the urbanwater and sanitation sector O&M fundingneedsto be atop priority. The UESPwas well designedand implemented from anengineering perspective, butthe primary issue for the U W S S sector-inadequaterevenues andfinancial allocations for O&M, and, consequently, inadequate O&M -was not tackled. Itwould havebeenbetter to have placed as much, or even more, attention to the fundinglO8zh.lissue as to the physicalworks. Creatingself-sustaining support services\. This i s importantto ultimate success. The CWSPmodelisparticularlyinteresting. Three needswere identifiedto provide longterm support to borehole communitiesunder a demand-driven approach\. (i) availability o fspareparts, (ii)availability o fprivate mechanics, and (iii) availability o ftechnical assistanceon a demand basis. The CWSP-2's promotiono ftheprivate sector rather thangovernment asthe long-termproviderto communities ofspareparts and mechanics, is more likelyto be sustained over time than services reliant on government. Follow-on training for localgovernments\. Giventhe chronic Ghanaianproblemo f turn-over of govemment staff, the follow-on project to the VIP and CWSP-2-the CBRDP will needto provide refresher trainingfor the DAs as well as training for the CBRDP's specific implementationneeds, The sameneedispresent for the UESP, thoughthe follow-on UESP-2maybe able to providethe necessarytrainingfor the W M D S . 0 A possibleneed for follow-on training for communities\. Neitherthe CWSP-2nor theVIP, northe designofthe commencingfollow-on project, CBRDP; included continuedtechnical support (extension visits, refresher training) to the community organizations. At thisjuncture, it is not clear whether the communities' social cohesion andfinancial strengthsare decliningor remainingstrong. Morefieldassessmentsare neededto assess on-the-ground realities andwhat may or may not beneededto address the situationthat is found. Table 5. Some Key Features for SuccessfulDecentralization An Enabling Institutional and Policy Environment\. Long-term commitmentto decentralizeddevelopment A demand driven approach including beneficiary contributions Agreed institutionalroles Clear and widely distributedrules of the game Harmonized implementationmodalities Minimal political interference A Major Drive to BuildImplementation Capacity\. Software, and softwarefirst Massive training Strong centralcoordination M&Eto facilitate programadaptation Enabling developmentof private sector service providers Includinghygieneeducation(forWSS projects) Making Sustainability a Central Focus\. Prioritizingrevenuesfor O&Mfinancing Creatingself-sustainingsupportservices Follow-ontrainingfor localgovernments A possibleneedfor follow-on training for communities
P050619 | ERSO III | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2002 | 2003 | 2004 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/896511474896283842/text/000020051-20140612090507.txt | http://documents.worldbank.org/curated/en/896511474896283842/pdf/000020051-20140612090507.pdf | 1. Development of ownership may take some time after a new government comes to office, especially if capacity constraints limit the new government's ability to buy into a solid reform program. The long list of unmet objectives in the Letter of Development Policy suggest that whatever ownership which did exist did not transfer very well into implementation. Adjustment operations of this sort need to be carefully formulated to ensure a higher degree of ownership. The Bank will need to take a supportive capacity-enhancing role, but should be prepared to accept less robust programs (and adjust its support appropriately) while support for reforms develops. 2. Technical assistance should be seriously considered to assist in development and implementation of reforms. At the same time, care should be taken to ensure that this technical assistance supports capacity-building, rather than supplants it.
P050620 | Education Sector Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2004 | 2012 | 2013 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/962421474577560316/text/000020051-20140625192227.txt | http://documents.worldbank.org/curated/en/962421474577560316/pdf/000020051-20140625192227.pdf | The following lessons are derived from the ICR (pp. 23-25):A project's results framework should be explicitly linked to project objectives and interventions. The original framework for this project lacked a logical link between project activities, outcomes, and measures, and so it hampered the ability to measure progress.Pilot programs must establish sound monitoring and evaluation systems to measure impact, identify problems and take corrective measures. The lack of an appropriate monitoring system limited this project's ability to regularly assess programs and outcomes. At the end of the project, an evaluation was conducted and so the lateness of this information prevented it from being used and disseminated.A demand-driven competitive funding mechanism is an effective instrument for allocating public funding aimed at fostering innovation, relevance and quality in tertiary education as long as the selection criteria are clear, transparent, and well publicized. The funding mechanism for this project was linked to strategic priorities defined by beneficiary institutions and benefited from successful implementation. The efficient and timely implementation of project activities is contingent upon building and sustaining project implementation capacity. Ongoing capacity building is needed, which was not the case in this project. The sporadic training coupled with staff turnover at the district level did not build capacity, which resulted in delaying project implementation.
P050623 | GH-Road Sec Dev Project (FY02) | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2002 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/332071474853989996/text/000020051-20140619104040.txt | http://documents.worldbank.org/curated/en/332071474853989996/pdf/000020051-20140619104040.pdf | In supporting institutional development, a long term engagement by the Bank is important along with a well coordinated joint donor program.Maintenance of the existing assets needs to be given a priority over the expansion of road networks. Countries need to devise method/criteria for planning/ prioritization of expenditures to best manage the tension between the immediacy of the political agenda (i.e expansion of the network) versus the longer term maintenance of the network.A detailed monitoring and evaluation system is critical for effective supervision and to adapt the project to address specific needs during implementation.Supervision and monitoring of works especially for rural roads that are small in dollar terms but spread over large areas proves difficult. Output and Performance Based Road Contracts can be used. A first time preparation and implementation of safeguards requires extensive training and close supervision.
P050624 | URBAN 5 | Western and Central Africa | Ghana | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/609611475088667657/text/000020051-20140613041332.txt | http://documents.worldbank.org/curated/en/609611475088667657/pdf/000020051-20140613041332.pdf | The Bank should establish a comprehensive sectoral program before it agrees to support a long-term APL. This will give clearer signals to the borrower as well as other partners and would ensure that the Bank does not raise expectations of funding which does not later materialize if the APL is cancelled part way. In this instance, the Bank decided to discontinue the next two phases of the APL just three months before project closing. This decision affected the momentum created within the DAs and may have caused planning and credibility problems for the government and implementing agencies. Linking investment funds to performance incentives through â€œlearning-by-doingâ€ approaches improves local government capacity. This approach strengthens the effectiveness of training programs delivered as it links theory with practice and provides space to use the tools learnt.To improve the delivery of infrastructure projects, the procurement process should start with pre-qualification of contractors. Sub-projects, which are chosen with the participation of the affected population, should be prioritized by the DAs in Medium Term development plans, which will provide continuity of planning and implementation by reducing the risk of agreed plans being questioned or changed by successor governments.
P050637 | TN URBAN DEV II | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/593891475077293089/text/000020051-20140613052128.txt | http://documents.worldbank.org/curated/en/593891475077293089/pdf/000020051-20140613052128.pdf | Projects supporting decentralization should assess the risk of fluctuating State commitment to reforms as well as identify mitigating measures, at preparation. Decentralization is a process prone to reversals and decelerations but the project did not recognize at appraisal the substantial risk that the State may not sustain the reform process. In fact, the Tamil Nadu Urban Local Bodies Bill was never implemented and ULBs remain highly dependent on the support of the Government for important decisions. While municipal finances may improve with the introduction of partial private sector ownership, this approach has a number of limitations. The creation of TNUDF substantially improved operational efficiency. However, the environment and conditions faced by TNUDFâ€™s clients â€“ the ULBs â€“ did not change and TNUDF is still highly dependent on the decisions of Government to do business. However, many problems were resolved because the TNUDF maintained a good working relationship with the Government, which supported the objectives of the TNUDF.Projects focusing on the supply side of services, such as provision of urban infrastructure, should still monitor the projectâ€™s impact on the target population. While the sub-loans component was efficiently managed, in the absence of monitoring data it is difficult to assess the usefulness of this approach for poverty reduction in urban areas.
P050637 | TN URBAN DEV II | South Asia | India | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2008 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/123341468260075752/text/39929.txt | http://documents.worldbank.org/curated/en/123341468260075752/pdf/39929.pdf | 5. Lessons The TNUDF model i s a viable and effective model for financing urban infrastructure investments, capable o f being replicated elsewhere in India. But as the model will have limited success in the absence o f ULB capacity, i t should be replicated w i t h the design features which were most successful in improving ULB capacity, namely the grant fund for project preparation, and encouraging the development o f close working relations between ULBs and Fund, especially as a source o f easily accessible technical expertise. Priority infrastructural needs o f the urban poor are often not the same as that o f the urban population as a whole. The financial intermediary approach will have limited success in addressing the basic infrastructure needs o f the poor unless the there i s a delinking between subproject financing method and the expected (monetary) returns. The experience o f these two projects shows that there are strengths and weaknesses in both the financial intermediary approach and the direct provision o f infrastructure approach. W h i l e the first i s clearly more efficient, the second i s often better able to meet the needs o f the poor. Efforts should be made to find the right balance o f these two approaches, o n the one hand by targeting grant funding mainly to meet the needs o f the poor and other market failure situations, and o n the other by encouraging financial discipline and a debt culture among ULBs. Cost recovery o f infrastructure investments from the poor should be w e l l thought out and implemented in a transparent manner. Attempting to recover the full cost o f infrastructure investments from the poor and strictly enforcing such cost recovery can have unintended negative impacts such as increasing their vulnerability to exploitation and abuse, for example by moneylenders. When such cost recovery mechanisms are implemented their design should include a dispute resolution mechanism that the poor can access. The Bank i s able to have a less costly but s t i l l relevant role in financing small city infrastructure needs when it i s able to hand over subproject supervision to an intermediary such as the TNUDF.,In such instances the Bank's role i s redefined as a provider o f policy advice through intellectual support and technical knowledge, a role which it performed w e l l in TNUDP-11. Projects need to develop meaningful M&E frameworks at design, which focus on the development impact, and with a definite baseline and targets to measure performance as well guide project implementation.
P050638 | Second Uttar Pradesh Basic Education Project | South Asia | India | IBRD |  | Human Development | Education | IDA | IPF | 1998 | 2001 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/976841474946495895/text/India-Second-Uttar-Pradesh-Basic-Education-Project.txt | http://documents.worldbank.org/curated/en/976841474946495895/pdf/India-Second-Uttar-Pradesh-Basic-Education-Project.pdf | Borrower ownership of a project is critical to successful implementation, particularly in cases of innovative and difficult projects. Continuity of competent staff is critical to the quality of implementation. - Educational research and monitoring helps schools improve, and projects should finance such activities at the level of local academic institutions. - The startup of complex investments takes time, and as much planning as possible should be done before funds start flowing. Often, projects are finished by the time quality-related inputs start becoming more visible in schools.
P050646 | UP Sodic Lands II | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/137231474503509007/text/000020051-20140619062210.txt | http://documents.worldbank.org/curated/en/137231474503509007/pdf/000020051-20140619062210.pdf | Drawing on the ICRR the following lessons emerge: Projects scaled-up from pilots that explore development options and modalities and identify winning combinations tend to be successful provided all the lessons, positive and negative, are learned. However, as with the pilot, the appraisal team needs to bear in mind institutional and physical constraints and mitigate them. Involving project beneficiaries in project design at the field level builds local ownership and encourages development of local capacity to manage and maintain project assets after completion. Independent M&E, provided it is timely, greatly assists project managers to keep on track on achieving development objectives. However, because the independent M&E substitutes for the government's own efforts, consideration has to be given to ensure that there is sufficient government/agency capacity to maintain the M&E system after project closure.
P050647 | Uttar Pradesh Water Sector Restructuring Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2002 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/726751475110454368/text/000020051-20140625191656.txt | http://documents.worldbank.org/curated/en/726751475110454368/pdf/000020051-20140625191656.pdf | The following lessons are taken from the ICR with some adaptation:Strong Water User Associations (WUAs) can help to ensure sustainability of irrigation rehabilitation, provided they are strengthened and consulted at the outset. It is important to include water users in the design and implementation of irrigation system rehabilitation, to strengthen ownership and impart management skills and conflict resolution. This begins with eliciting their input at the design stage, which will decrease the risk that illegal cuts will be made after the designs are implemented, compromising the ability of the system to deliver the proper allocation of water to all the outlets. This experience should also increase the likelihood that Associations will be effective in assuming responsibility for Operations and Maintenance (O&M). Success would normally require a substantial long-term effort, beyond limited training. Provision needs to be made for continued strengthening of Association members and especially of newly elected officers.Institutional effectiveness requires consistent leadership at the chairman or director level. Frequent changes of senior management and key staff can hinder efficient implementation. The more consistency that can be achieved at leadership level, the better performance the project will likely achieve. But the costs and benefits of creating an independent or quasi-independent project implementation unit need to be carefully weighed.A benefit or impact evaluation needs to be well-designed in advance and adequately resourced. The intensive phase of evaluation of project benefits for the implementation completion report will need to be carried out during the last year of the project and should ensure that a suitable â€œwithout projectâ€ area is included in the survey to act as a control. However, the design of such an evaluation should be part of project preparation and a baseline survey should be undertaken before implementation in order to permit a "before-after" comparison of benefits.
P050649 | Tamil Nadu Road Sector Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2003 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/902221475073100464/text/000020051-20140625231909.txt | http://documents.worldbank.org/curated/en/902221475073100464/pdf/000020051-20140625231909.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation:Â· Adequate attention needs to be paid to enhancing the leadership and empowerment of dedicated implementation units at multiple levels. The units that are put together just for the sake of a project tend to lack full empowerment and leadership from within and often rely on the strength of individuals assigned to lead them. Â· In a project with a strong institutional development agenda, the teams may consider more outcome-based targets and indicators to measure achievements and impacts. Such targets, ideally, should relate not only to mere completion of all sub-components but also to the actual improvements achieved in project implementation and other operational efficiencies (e.g., reduction in time and cost overruns; reduction in per km costs of construction and maintenance).Â· Land acquisition through private negotiations, coupled with innovative approaches to valuation, offers significant promise to expedite land acquisition in a timely and amicable manner. The benefits of private negotiations that factored in current realities with regard to the land value include a higher compensation to the landowners, a simplified and faster payment of compensation for the land acquired, elimination of court reference cases thus avoiding litigations and additional costs to the government, and saving considerable time through reduction in land acquisition process. Â· Early planning, integrating with contracts, right sequencing, and inclusive approach are essential for addressing environmental and social safeguards in a proper and satisfactory way. The implementation of environmental measures during the construction stage is more effective if they are integrated as part of the construction contracts, with provisions for related bills of quantities and incidental items as well as penalties to address non- compliance. Also, an inclusive approach in consultation with local communities could help harness opportunities to create valuable community assets and generate positive response and good will.
P050651 | India: Maharash Health System | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/962791474492835792/text/000020051-20140615100752.txt | http://documents.worldbank.org/curated/en/962791474492835792/pdf/000020051-20140615100752.pdf | User fees contribute vital resources towards non-salary recurrent costs that can make a substantial difference to the quality of care at hospitals. Hospitals need to be given clear guidelines on who is exempt from such charges, and the purposes for which such funds can be used.Rationalizing service delivery through uniformity in the size and service mix at each type of hospital is possible and contributes to better management of the health system. For example, training programs can then be standardized, QA programs can be established, and a uniform reporting system can be put in place â€“ all measures that would increase the clinical effectiveness of the hospital. Establishing a strong monitoring mechanism is critical for good management. The system needs to be simple and user friendly, focusing on a few meaningful indicators. Ensuring that baseline data are made available prior to Project Effectiveness and following up systematically on the agreed indicators will provide a basis for measuring results and help in learning lessons. Also a feedback mechanism is necessary whereby all functionaries get regular comparative evaluations of their performance.Phasing in of civil works needs to be built into project design, and delays in implementing any phase should be dealt with decisively through cancellation of works. If not, the construction program drags on and the hospitals are barely commissioned at project closing. Thus many of the hospitals have to forego the opportunity of benefiting from software inputs and quality improvement measures. As a result, predicted project outcomes are not fully realized.
P050653 | IN Second Karnataka Rural Water Supply and Sanitation Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/471991468001178011/text/ICRR14709-P050653-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/471991468001178011/pdf/ICRR14709-P050653-Box393183B-PUBLIC.pdf | The ICR records a number of lessons. Following are two ICR lessons, with some adaptations: Decentralization. Strong institutions and political will are the building blocks for decentralized service delivery. The success of such an approach also requires significant dialogue between the Bank and the national stakeholders before project effectiveness, coupled with adequate time and flexibility built into the design of the planned intervention.Ensuring sustainability. A Sustainability Framework developed in close collaboration with the stakeholders involving the communities backed up by legislative support, is necessary to ensure consistent and uniform implementation of interventions, particularly related to water supply schemes.
P050655 | India: Rajasthan Health Systems Development Project | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2004 | 2012 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/509561475097763098/text/000020051-20140625185355.txt | http://documents.worldbank.org/curated/en/509561475097763098/pdf/000020051-20140625185355.pdf | Lessons from the ICR:The long-term payoffs of integration and harmonization with government programs need to be balanced with the short-term needs of project implementation. In the case of this project, careful integration with the government's newly introduced health programs helped to promote complementarities and sustainability; however, it reduced the PMU's singular focus on Bank project implementation.Capacity of procurement staff needs to be rigorously assessed. In the case of this project, the extensive preparation of procurement documents prior to effectiveness was not effective in preventing major procurement delays, given the existing capacity levels.Lessons drawn by IEG:The monitoring and evaluation framework needs to be robust (i.e. realistic and measurable) in order to be useful. In the case of this project, the M&E outputs were of limited usefulness to the implementing agencies and led to data quality issues for the purposes of evaluating the project's impact. In particular, indicators were inadequate for capturing intended outcomes among the targeted populations.
P050657 | Uttar Pradesh Health Systems Development Project | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2009 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/332981474852087394/text/000146597-20140619165553.txt | http://documents.worldbank.org/curated/en/332981474852087394/pdf/000146597-20140619165553.pdf | The ICR identifies 16 lessons on project design and implementation as well as on future operations that this ICR review concurs with. The following two are highlighted (with some adjustment from the ICR wording).Project designs need to identify and include measurable health status indicators in addition to intermediate outcome indicators.Developing systems that provide quality care to the poorest is a time-consuming process. It involves investment in strategic planning, human resources, and partnerships with all available stakeholders in the health sector.
P050658 | Third Technician Education Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2007 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/479391474586226844/text/000020051-20140618085428.txt | http://documents.worldbank.org/curated/en/479391474586226844/pdf/000020051-20140618085428.pdf | Technical education programs of high quality and relevance increase demand and promote efficiency. The problems often seen with demand for technical education may be overcome with new curricula and enhancements that increase the likelihood that students will learn the essential skills needed for their work.The perception of low prestige of technical education can be overcome with improved quality and relevance in instructional programs that increases the employability of graduates.
P050658 | Third Technician Education Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2007 | 2012 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/921301468269378610/text/660560PPAR0P070C0disclosed010250120.txt | http://documents.worldbank.org/curated/en/921301468269378610/pdf/660560PPAR0P070C0disclosed010250120.pdf | 4. Themes and Lessons 4.1 The two Projects, with their overarching objective of building the technical manpower of project states (and UT) in India, share a number of similarities in their components. These include improved quality and labor-market relevance of education, costrecovery mechanisms, and decentralized decision-making. At the same time, they operated within different contexts and focused on different parts of the technical education spectrum, with Technician Education III focusing on vocational education, TEQIP I on engineering education. Lessons of Experience 4.2 Both Projects were ambitious, focusing on key challenges in tertiary education, and operating under considerable constraints. Together, the two offer important insights into addressing the challenges of providing high-quality technical/vocational education.. The quality of education and labor market relevance\. Courses need to be aligned with economic needs, as well as students' employment aspirations 4.3 The two Projects focused on improving the quality of education primarily by initiating programs of study that were better aligned with the market and economy; providing superior equipment and trained teachers. These inputs were expected to translate into improved employability of graduates (and higher quality of technical/vocational work in the economy). 4.4 Overall, TEQIP I performed better in terms of the employment record of its graduates. It had two natural advantages over Technician Education III in this regard\. (1) on average, TEQIP I students had higher prior test scores in public examinations than Technician Education III students; and (2) TEQIP I institutes were typically located in areas with multiple sources of employment, both in the informal sector and the formal sector. This allowed their placement offices to be more effective. 4.5 From a project perspective, PPAR data suggest that TEQIP I performed better than Technician Education III in its student employment record because the programs of study were better aligned with students' employment aspirations. It supported programs that were geared towards formal sector employment, and students who were interested in formal sector employment. The match increased the likelihood of students seeking long-term employment in the area in which they are trained versus going in for more education or employment in a sector unrelated to their training. 4.6 Courses and students' long-term employment aspirations were not as well matched in Technician Education III. In the Project's institutes, a number of the new programs were in areas in the informal sector, such as garment technology and food processing, while the employer of choice was the government (formal sector). In order to counter the attraction of government jobs, the project needed to do more than merely provide technical skills to students in new programs. It needed to train students in skills that would make participation in the informal sector profitable and sustainable. In this sense, Technician Education III did not adequately understand or address the needs and constraints of the local economy and the local labor market in Project regions. The skills many of the new programs helped develop in students ended up being stand alone. The data in Tables 11 and 12 combined with PPAR interviews suggest most students using the diploma either as steppingstones to a degreegranting institution or as an eligibility mechanism for taking the public services commission exam of their respective state (the path to a government officer's job). 4.7 The importance of aligning courses with economic needs, as well as students' employment aspirations is crucial. This is, however, not an easy task. The difficulty in matching courses in vocational education with students' long-term aspirations is magnified when such courses are introduced into a system with a well-defined mainstream, and a clear ranking of status between the mainstream and the periphery. Further, although most people interviewed were supportive of education that built real world problem-solving skills in students, many questioned the merit of focusing too narrowly on labor market relevant education and whether such education should emphasize specific skills or general skills. Faculty and administrators worried that investing too heavily in building specific skills, in the face of uncertainty on the durability of the skills, would create problems for both institutions and students. From the institution's point of view, a labor market relevant course of study requires investing in specific equipment and teacher training, both of which take time and money. In terms of student concerns, vocational programs are unlikely to attract the best students, and are more likely to have students from lower social economic backgrounds than regular tertiary institutes. From this perspective, they are more vulnerable should their skill set become obsolete. 4.8 The structure of institute-industry collaboration envisioned under both projects to enhance the labor market relevance of education also provides important insights. This structure was better defined for TEQIP I institutes, where industry representation in the Board of Governors ensured a minimal amount of industry involvement in matters such as curriculum revisions, which require Board approval. In Technician Education III, the structure was relatively loose, with industry involvement occurring on the initiative of individual institutes. All the same, both Projects implicitly assumed that for education to be labor-market relevant, curriculum design/redesign needed white-collar industry involvement. This automatically put institutes in regions without industry at a disadvantage. Instead of emphasizing only industry collaboration, if the projects had also focused on improving students' problem-solving skills by encouraging them to get their hands dirty,ï¿½? the choices available for such education would open up. For instance, every habitation, no matter how rural, has some form of micro-enterprise in its vicinity, whether a small general store or a bicycle repair shop. These micro-enterprises can provide lessons in a number of fields ranging from accounting to mechanical engineering. Accreditation processes are difficult in remote regions, and are vulnerable to manipulation 4.9 Both projects encouraged the accreditation of programs within supported institutions as one way of ensuring basic quality standards had been met. In the tertiary education system in India, accreditation can be undertaken by two government entities\. All India Council of Technical Education's National Board of Accreditation and the University Grants Commission's National Assessment and Accreditation Council. The National Board of Accreditation was set up specifically to set standards in the technical education sector, while National Assessment and Accreditation Council covers all types of educational institutions. The two forms of accreditation rely upon government-appointed experts to visit institutions. 4.10 Both Projects expected â€”TEQIP I more than Technician Education III â€” that project institutions would be accredited (by the National Board of Accreditation). When carried out as expected, the National Board of Accreditation's certification is comprehensive and rigorous. However, in reality there are two problems that limit the soundness of certification. First, while it is easy to arrange for experts to visit institutes that are well or centrally located, there are logistic difficulties in getting experts to go to faraway places, where travel time could exceed a few days. As a result, evaluations and accreditations get delayed in such places, or conducted by people without relevant expertise. Second, there is potential for manipulation of the accreditation process, thereby devaluing its credibility as an instrument for accountability. 4.11 PPAR interviews highlighted the importance of a credible rating agency, potentially one operating outside the government. For instance, Crisil India, a Standard Poor's company with an established reputation for providing unbiased credit ratings of companies in India, has recently started rating MBA institutes in India to ensure these institutes meet the needs of the market. Leveraging alumni connections is an important mechanism for raising funds. Cost recovery through increased faculty consultancies risks devaluing teaching and fundamental research. 4.12 There were two main mechanisms for cost recovery employed by the Projects\. student fees and consultancy services offered by faculty. As discussed in Chapter 1, student tuition fees are highly regulated in both public and private institutes, making excessive reliance on such fees inadvisable. In both projects, internal revenue generation was undertaken through consultancy services offered by faculty. In interviews, faculty mentioned feeling incentivized to undertake such consultancy services, emphasizing how it helped build/enhance their professional credibility. Since they were required to pay only 30 percent of their consultancy income to the institute, such work provided financial incentives as well. 4.13 While encouraging faculty to undertake consultancy services to generate revenue is important, both from the perspective of enhancing their professional standing and providing financial incentives, there are at least two trade-offs with such work. This suggests the need for caution and balance in promoting internal revenue generation among faculty. First is the tradeoff between consultancy/research work and teaching. Relentless pursuit of industryrelevant consultancies means less time to prepare for lectures, potentially reducing the effectiveness of teaching and investments made in the training of teachers. One way in which institutes reported keeping faculty on track with their teaching responsibilities was through regular feedback from students and other faculty members. College of Engineering, Pune, for instance, collects feedback regularly from students on faculty, and conducts spot visits to various classes to ensure student learning does not suffer. Where faculty have not been performing well, they are mentored and provided feedback. Second is the tradeoff between industry-related practical research and fundamental research, which has limited immediate applicability. While TEQIP I institutes are not yet at the stage where such tradeoffs are apparent, it is important to invest in mechanisms to ensure the balance between practical research and fundamental research is maintained. 4.14 Alumni donations can provide an important source of funding. Technician Education III institutes do not appear to have benefited from alumni involvement in the way in which many TEQIP I institutes have. TEQIP I institutes such as University Institute of Chemical Technology and College of Enginnering, Pune provide examples of how alumni relations have been cultivated over decades, as a result of which both institutes benefit from donations received from alumni, consultancy and research work, and teaching inputs. For instance, College of Enginnering, Pune's Bhau Innovation Lab has been funded by alumni. University Institute of Chemical Technology has a number of named professorships, again funded by alumni. An additional advantage of alumni involvement is that it keeps processes within institutes in check, since alumni are more likely to monitor the effective use of their funds than the government may be able to. Autonomy is important, but institutes must be ready for it in terms of accountability and initiative 4.15 Technician Education III and TEQIP I emphasized institutional autonomy as a precondition for reforms, which would allow education decision-making to be decentralized to the institution level and reducing bureaucratic interference and delays. Both projects provide examples of institutes which received full autonomy, and benefitted in multiple ways. The benefits include programs in cutting-edge fields, improved employment of students, and improved research and better internal revenue generation. Autonomy, for instance, put institutes such as University Institute of Chemical Technology, Mumbai and Ambedkar Polytechnic, Port Blair on the path to self-sustained excellence. Autonomy allowed Ambedkar Polytechnic to adopt effective management principles. The Principal of the polytechnic was also made the Director of Technical Education, and reported directly to the Chief Secretary of the UT. Consolidating the office of the Principal and the Director in one person eliminated an intermediate layer of bureaucracy, thereby facilitating the ability of the polytechnic to undertake high-quality programs and cutting-edge research work without worrying about bureaucratic interference or delays. 4.16 Block grants â€” the core element behind TEQIP I's financial autonomy reforms â€” were adopted in the manner envisaged in the PAD in only one state, Haryana. In other states, they were adopted only partially. TEQIP I's experience highlights the challenges associated with states granting institutions autonomy. First is the political economy constraint discussed in Chapter 1, which potentially reduces the incentive of officials at the state level to grant autonomy. At the same time, the thrust on autonomy, specifically academic and financial autonomy, may have been premature, since many project institutions did not have proper oversight or accountability mechanisms. Equally important, a large number of institutions were not equipped to make effective use of autonomy, in terms of confidence, responsibility, and initiative. This questions the merit of expanding TEQIP I to nearly twice the number of states and institutes. Focusing on fewer institutions â€” those truly worthy of autonomy â€” may have allowed the Project to realize its reform goals more effectively. Systemic reform in Indian technical education should include private institutes 4.17 Private institutes enroll approximately 85 percent of all students studying engineering in India. Technician Education III and TEQIP I were open to private sector participation, but TEQIP I had a vision for including private providers. This was motivated precisely by the fact that much of the growth in engineering education has come from the private sector. Further, most of the quality concerns in engineering education in India emanate from the private sector. Nevertheless, TEQIP I's vision was not supported adequately by the Government of India. As a result, it failed to translate into a systematic plan for the improvement of private engineering colleges and institutes. As argued in Chapter 3, TEQIP I's design was biased in favor of state or centrally-funded institutes and against private sector participation. Private sector institutions were provided loans at the same rate at which states received the loan from the center. However, the fee structure of private institutes is highly regulated by the respective state, which means they cannot recover their costs solely through fees. This leaves research and consultancy services provided by faculty as the primary (flexible) source of income. This would have been alright if private engineering colleges in India had a history of research, but they do not, putting them at a disadvantage relative to government institutions in getting contracts for consultancies. While TEQIP I could have addressed this by helping private institutes build a strong research agenda, the terms of the loan reduced the likelihood of private institutes making long-term shifts in their research culture versus undertaking short-term assignments to repay the loan. Networking of institutes is likely to be effective only when institutes recognize mutual gains 4.18 Technician Education III and TEQIP I were both mindful of the gains from sharing intellectual resources and equipment, but TEQIP I had an elaborate and formal structure for the networking of institutions. Some institutions were designated as Lead institutions based upon their initial proposals, and the remaining as Network institutions. Lead institutions would assist in the development of network institutions through seminars, joint publication and training sessions. In this way, the investments made in and by Lead institutions would have positive externalities on Network institutions. 4.19 There were, however, specific aspects of the networking model that limited its effectiveness. First, designating some institutions as Lead and others as Network, instead of all as Network, created a hierarchy that was not attractive to many Network institutions (the majority of institutions) or conducive to partnership. PPAR interviews revealed that many Network institutions, with good reason, believed they had sufficient expertise to offer, but Lead institutions preferred to provide rather than receive any expertise. This defeated the spirit of networking, which is a reciprocal activity, and is likely to be successful only when mutual gains are recognized. One way of addressing this could be to have a revolvingï¿½? Lead-Network system where each institute gets a chance to be the Lead, and the performance of the entire cluster of institutions is jointly evaluated. Institutions with stronger institutional development proposals could be Leads in the first few years, and be evaluated or provided incentives for their ability to mentor weaker institutes to become Leads. This would require that all institutes be equally free to make changes in curriculum or teaching methods, and that institutions not be constrained in the choice of their partners. Follow-on Projects 4.20 Bank support in technical/engineering education in India continues through TEQIP II, which was prepared to carry forward the reforms initiated under TEQIP I (Table 26). TEQIP II seeks to strengthen selected institutions to produce more employable and higher quality engineers and prepare more post-graduate students to reduce faculty shortage. The Bank is not currently supporting diploma-level technical/vocational education in India, but is supporting certificate-level vocational training through the India Vocational Training Improvement Project.37 This project works with the Ministry of Labor (and not the Ministry of Human Resources Development as with Technician Education III). It seeks to improve the employment outcomes of graduates from the vocational training system by making the design and demand of training more demand responsive. The Vocational Training Improvement Project is being supported through IDA for USD 280 million. Table 26. The Two Operations and Subsequent Bank Support Approval Closing Project Name Subsequent Bank Research/Operation Date Date TEQIP I 11/14/2002 03/31/2009 TEQIP II (IDA\. $300 million) Technician None (Technician Education III was the final 09/07/2000 06/30/2007 Education III project in series) Source\. PAD 4.21 TEQIP II has attempted to address the problem TEQIP I faced with states implementing autonomy incompletely, by monitoring and enforcing a timely implementation of each state's commitment to policy reforms. It has also increased the participation of private engineering institutes, doubling it to 40 institutes. Further, the nature of financial support has been modified from a loan scheme to a grant scheme. TEQIP II is currently rolling out training sessions for Members of institutional Governing bodies to strengthen the accountability mechanisms. The Government of India has also increased the capacity of NPIU both in terms of staffing and in terms of training, and increased the range of NPIU's decision-making powers. Additionally, TEQIP II has improved its M&E system by designing a centralized online system of data management. At present, the Bank and the Government of India are in dialogue for TEQIP III, which includes discussion on ways to strengthen the quality of private institutes.
P050660 | Rural Environment Protection Project | Europe and Central Asia | Poland | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/219781474594474523/text/000020051-20140612153518.txt | http://documents.worldbank.org/curated/en/219781474594474523/pdf/000020051-20140612153518.pdf | For project implementation, a sustainable agency preferably outside the Ministryâ€™s administrative constraints should be considered. During negotiations, there needs to be a detailed discussion on the form of the implementing agency for a given project. For e.g. the Project implementation Unit (PIU) can provide a team of technical consultants rather than the politically involved Ministry employees. Privately managed advisory firms are more effective than state ones. Similarly, the experience of Local Implementation Team (LIT) showed that team members independent of central institutions such as a Ministry perform their job better because they are not weighted by the administrative constraints of their home institutions. Convincing farmers about the necessity of certain technological solutions is possible through displaying a demonstration farm on the local scale. The farmer has to see that improvements are possible in his area, not in some unfamiliar places abroad from where the technological solutions are being imported. Development of a project specific Management Information System (MIS) requires allocation of significant resources upfront. In the future, if possible, the system should be based on the simple existing systems that can be expanded overtime.
P050667 | Uttar Pradesh Third District Primary Education Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/790451474660103031/text/000020051-20140615114452.txt | http://documents.worldbank.org/curated/en/790451474660103031/pdf/000020051-20140615114452.pdf | 1. With strong government commitment (both political and financial) it is possible to create universal primary education programs that cover both improvements in access and learning outcomes; with effective implementation (as in UPDPEPIII both can move in a positive direction. 2. Continuity of project staff, especially at the state, district, sub-district, and school levels is important for the process of implementation and change to proceed smoothly. 3. Good preparation work, including the use of baseline learning data and social assessment surveys, can yield important contextualized information that can help in the customization of the intervention package (e.g., specification of intermediate outcomes). However, to be useful such features need to be tracked during the life of the project and responded to if they reveal weaknesses. 4. Setting good performance indicators is important but these need to be accompanied by accurate baseline values and realistic targets in order show whether or not progress was satisfactory. 5. For projects that aspire to improve equity (such as UPDPEPIII and its concern for improved primary school access and learning outcomes among the disadvantaged), outcome indicators must be broken down by social group, so that equity improvement can be tracked. 6. With the maturation of the GOI's efforts to promote universal enrollment in quality primary education it is time for the government to create more impact-oriented program designs, providing managers with the data they need to be able to attribute change to specific project interventions and to determine where (among districts) strengths and weaknesses are evident (with a willingness to provide remediation where weaknesses are found). This would mean addressing the counterfactual in project designs and bringing India's strong analytical skills to bear on project efforts and results. 7. The decision to support third party evaluation efforts with respect to risky and potentially controversial policy positions in the project was a reasonable one (reflected in project covenants), but the learning from such studies needs to be made available and passed on to the designers of follow-up projects.
P050668 | Mumbai Urban Transport Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/953301474493485269/text/000020051-20140625073602.txt | http://documents.worldbank.org/curated/en/953301474493485269/pdf/000020051-20140625073602.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation of language:Â· Poor inter-agency coordination can become a serious obstacle to the implementation of key activities of a project. Design should minimize the number of agencies involved in implementation in order to minimize delays resulting from weak cooperation and ineffective inter-agency coordination. The implementing agencies should have clear roles and responsibilities, and the coordinating agency should have sufficient authority to fulfill its role.Â·Â· The project design should adequately focus on capacity building of the client, in particular in new areas. Through active involvement, the Bank should gradually help develop capacity of the client to address difficult and sensitive issues through a sustainable and consultative approach. In particular, on issues related to resettlement, environmental management, and financial sustainability.Â·Â· Mechanisms for strengthening transparency, accountability, and good governance should be planned upstream and integrated in the project design in order to enhance implementation quality and outcomes. These measures, including third party monitoring and dispute resolution, should be incorporated as a part of a Governance and Accountability Plan In this project, such mechanisms were of critical importance in the ultimate success of the resettlement and rehabilitation activities.
P050668 | Mumbai Urban Transport Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2011 | 2016 | PPAR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/153071469129513999/text/106391-PPAR-P050668-Box396277B-OUO-9-india-0716.txt | http://documents.worldbank.org/curated/en/153071469129513999/pdf/106391-PPAR-P050668-Box396277B-OUO-9-india-0716.pdf | 6. Lessons 6.1 Several lessons can be drawn from the evaluation; some are adapted from the ICR and others from the final progress report in respect of the implementation of the Management Action Plan. The lesson on project objectives is based on IEG observations. 6.2 Project development objectives should be specific and measurable. The overall development objective in this project was too generalized and the results had to be based on sub-objectives, which were effectively proxies for the overall objective. This detracted from clarity on what the project was seeking to achieve and how well the project goals were met. 6.3 Large-scale resettlement is a complex operation that needs considerable planning, adequate provision of time, good negotiation skills, and strong capacity to implement successfully. At the time of appraisal, the scale of the Mumbai Urban Transport Project was unprecedented in an urban context in India. Not all groups being displaced were alike and initially there were insufficient opportunities for grievances to be heard empathetically. Poor inter-agency coordination and too many implementing agencies can also become a serious obstacle to the implementation of the key activities of such a project. 6.4 A lack of adequate synchronization of resettlement activities with civil works can cause significant time and cost overruns. This project demonstrates that civil works began prematurely before all the resettlement issues were resolved, especially those businesses and households affected by road links. This led to dissatisfied project affected groups appealing to the Inspection Panel for assistance and this delayed project progress significantly. Prior to the commencement of civil works, substantial land acquisition and resettlement should always be completed. 6.5 Transition from an administrative compensation approach to a win-win negotiated approach can resolve seemingly intractable problems with projectaffected groups. There is a need to understand the nature of peoples' grievances in a transparent way. In this project the state government went beyond normal procedures and was flexible in negotiating the resolution of some extremely contentious resettlement issues. 6.6 Introducing entitlements and market-based solutions was a major contributor to resettlement success. Provision of free, alternative housing with title has had an empowering effect on the project-affected households, which have acquired new social status and gained wider access to employment in the formal sector. The market solution of offering transfer of development rights as a tradable benefit in lieu of land compensation proved to be an attractive form of compensation to the legal owners for allowing resettlement on part of their land.
P050671 | NP: Telecommunications Sector Reform Project | South Asia | Nepal | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2002 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/911641474897888822/text/000020051-20140620082329.txt | http://documents.worldbank.org/curated/en/911641474897888822/pdf/000020051-20140620082329.pdf | IEG concurs with the lessons presented in the ICR. Projects can be successfully implemented when there is a strong stakeholder commitment to reform, and when there is strong political and administrative commitment to monitor progress and make flexible changes as required.Clear leadership, willingness to implement reforms at a senior level, and a broad consensus on priorities facilitate project implementation.The Bank could improve risk mitigation by adopting a more rigorous and methodical approach for projects that operate in challenging political contexts.Project activities identified as having â€œsignificantâ€ risks could also have multiple mitigation options. The private sector can play a major role in the telecommunications sector; even in challenging political and security environments.Even in geographically challenging countries like Nepal, a competitive market environment promotes enhanced service coverage, quality and leads to competitive tariffs and services for consumers.
P050706 | RY-CIVIL SERVICE MODERN | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2010 | 2011 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/572461474851362426/text/000020051-20140624194952.txt | http://documents.worldbank.org/curated/en/572461474851362426/pdf/000020051-20140624194952.pdf | 1. Civil service reform projects need to be highly focussed and in line with the country's administrative capacity and its social and political context. Such projects need to be focussed on responding to country demand for reform, and in the absence of such demand, ESW and other work should focus on showing way reform is needed, along with appropriate outreach campaigns.2. In addressing the problems of a bloated civil service, due attention must be paid to credible alternatives, including social safety nets, creation of productive jobs, or social transfers. 3. A candid and detailed risk analysis should underpin projects, especially difficult projects such as civil service reform projects4. Frequent rotation of TTLs is costly and should be avoided.
P050713 | AR MODEL COURT DEV. | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/867151474750690667/text/000020051-20140615102528.txt | http://documents.worldbank.org/curated/en/867151474750690667/pdf/000020051-20140615102528.pdf | Project readiness (in terms of clarity and soundness of institutional arrangements for implementation) is key, even when the project is a LIL and although the more so when the intervention is testing out activities with far reaching changes..For a legal and judicial reform intervention to be effective, wide ownership among a range of governmental and nongovernmental stakeholders is necessary. Such ownership should be built up before project effectiveness, and continued throughout project implementation.The LIL could have tested and tried the institutionalization of a few monitoring indicators that would have monitored outcomes systematically.
P050714 | Secondary Education 3 | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/253111474556453591/text/000020051-20140612063648.txt | http://documents.worldbank.org/curated/en/253111474556453591/pdf/000020051-20140612063648.pdf | An incremental approach to the implementation of curricula, and a thorough diagnosis of individual school issues may create an environment more likely to result in greater effectiveness rather than abrupt changes.It is important to do appropriate targeting to reach the population at risk. Projects aimed at improving equity are likely to be more effective when repetition rates, attrition, learning achievement, family and school location, are given adequate attention during design and implementation.School-based diagnosis involving stakeholders serves to empower stakeholders, increase ownership, promote improved school-community linkages, and ensures the relevance of interventions.
P050714 | Secondary Education 3 | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2003 | 2007 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/263681468205792884/text/38467.txt | http://documents.worldbank.org/curated/en/263681468205792884/pdf/38467.pdf | 5. Lessons 5.1 This assessment provides a number o f lessons for the education sector\. Argentina may benefit fkom interventions to maximize student engagement in learning activities and thus increase systemic efficiency and learning outcomes. Policies could include offering textbooks to students and rationalizing teaching hours in schools. Teacher guides to facilitate teachers' work may ensure that basic curricula are covered without stifling the creativity that educators in the country cherish (paras 4.3-4.8). 46. World Bank 2006. 47. In TIMSS video studies, class sessions have been videotaped and procedures coded for activities used teach math and science concepts. In the US. that scored low, students were more often taught definitions, practiced routine procedures, and learned specific rules rather than the underlying rationale. In the higher-scoring Japanese schools, students learned the principles that would enable them to solve complex problems, and they often connected abstract math topics to historical discoveries and real-world use. Problems solved in class were linked, creating a coherent knowledge structure. Teachers also asked students to memorize rules that they immediately put into practice. Deductive reasoning (math proofs) were used in 53 percent of Japanese classes and not at all in the US. classes. The study may also demonstrate the effect of distractions and noise level on consolidation; Japanese classes were never interrupted, while 31 percent o f U.S. classes were interrupted for extraneous reasons. Seatwork in both countries accounted for about 40 percent of class time; but in the low-scoring US., seatwork consisted o f 96 percent practice, 3.5 percent application, and 0.7 percent inventive thinking, whereas in Japan seatwork time consisted of 41 percent practice, 15 percent application, and 44 percent thinking (Sigler and Hiebert 1999, p. 71). 0 Reading skill influences achievement in secondary education, and l o w reading s k i l l s m a y account for students' failure in schools. Unless students get considerable practice in reading during primary school, they remain slow readers and may be unable to interpret complex text or get through the substantial amounts normally expected in secondary school (para. 4.10). Monitoring indicators to track progress towards the attainment o f longer term objectives such as improved learning outcomes must be included in the project design; otherwise it m a y be impossible t o evaluate whether changes are attributable to project interventions or the lack incentives t o focus on learning outcomes (para. 3.7). 0 Decentralization o f school management to provinces and municipalities i s not a panacea. Unless managers are strong and can effectively supervise and control quality, the poor may receive limited service due to ineffective oversight (para. 4.3).
P050716 | UY Non Communicable Diseases Prevention Project | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Highly Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/976101483050107141/text/ICRR-Disclosable-P050716-12-29-2016-1483050089945.txt | http://documents.worldbank.org/curated/en/976101483050107141/pdf/ICRR-Disclosable-P050716-12-29-2016-1483050089945.pdf | Lessons drawn from the ICR, adapted by IEG: Successful project monitoring requires aresults framework tobeclear and concise, with a manageable number of key relevant, well-defined and measurable indicators. In the case ofthis project, the results framework had some shortcomings including inaccurate baseline data, and inadequate definitions or captureof intended outcomes, which led to significant revisions more than halfway through the project period. Government budgetprocesses and decisions,external to the project arrangements, can have negative impact if not properly taken intoaccount. In the case of this project, the five-year budget cycle caused great difficulty in ensuring timely and formal budgetallocations to the project, which led to significant implementation shortcomings.
P050716 | UY Non Communicable Diseases Prevention Project | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2016 | 2019 | PPAR | >=10 million & <25 million | Highly Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/482781547487996593/text/131480-PPAR-P050716-PUBLIC.txt | http://documents.worldbank.org/curated/en/482781547487996593/pdf/131480-PPAR-P050716-PUBLIC.pdf | 7. Lessons 7.1 Preventing NCDs and promoting health requires a multidimensional approach that goes beyond strengthening the role of MSP and the provision of health services. Although this understanding was embedded in the project appraisal document, it was not fully articulated in project objectives or design. The project focused on secondary prevention under the control of MSP, paying limited attention to behavior change activities beyond that of providers. Strategies to influence behavior change of the population toward NCD risk factors were implemented at school and community levels, but their emphasis and scale were limited, and continuity and sustainability relied mostly on individuals or municipality interest. Better strategic use of other actors' roles and capacities on NCD prevention could have improved the focus, efficacy, and efficiency of the resources devoted to this area. The extent to which MSP can effectively work with and influence other ministries and key civil society actors should not be taken for granted but rather should be an explicit goal of these types of projects. Moreover, attention to promoting behavior change of the population should be as important as investments in equipment, technology, and incentives for health providers. 7.2 Projects implemented during important reform processes have to take into consideration the timing of the reform and adjust project expectations and ambitionsaccordingly. The project introduced incentives in providers' payments in three departments to motivate greater focus on NCD prevention and promotion of healthy activities. However, before the project was able to show results, these incentives were scaled up to all 19 departments with the reform. As project scale increased, expectations of results within the lifetime of the project became unrealistic\. providers were not used to reporting on performance; providers' structures, population served, and incentives to comply with performance measures differed; defining performance indicators for NCD management proved difficult; there was no information system in place and limited capacity to support effective reporting; and MSP did not have the capacity to monitor provider's compliance. Despite these factors the World Bank did not reassess feasibility, nor did it adjust project expectations accordingly. 7.3 Projects with a strong focus on capacity building need to be more realistic about what can be achieved within the project lifetime. Project design underestimated the time and resources needed to equip, motivate, and train providers at the primary care level on the importance of preventing NCDs, and to then define, measure, and monitor providers' performance (and the learning process involved in continuously redefining and adjusting those measures). Much of the institutional capacity, technology, and equipment funded by the project were not fully operational until later during implementation, which limited their use for NCD management at the provider level. 7.4 Innovative projects such as the PPENT should devote more attention to capture learning from implementation. The project included in its original design an impact evaluation of the pilot but did not include provisions to capture or systematize the learning from an innovative and appealing implementation model that relied extensively on the existing structure and staff of MSP. All stakeholders contacted by IEG confirmed the significant institutional strengthening and capacity building that ASSE and MSP received and the learning-by-doing that the project facilitated. This is especially evident in sustained changes implemented in management tools, evidencebased decision making, and information systems. However, this learning was not well captured by the World Bank, missing an important opportunity to share this experience in other contexts.
P050717 | CONTRACTUAL SAVINGS | Latin America and Caribbean | Uruguay | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 1998 | 1999 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/882161474420425501/text/000020051-20140521031117.txt | http://documents.worldbank.org/curated/en/882161474420425501/pdf/000020051-20140521031117.pdf | The lessons to be drawn from this operation are well articulated in the ICR: the value of the Bank's strong technical capacity, the need to take into account the political sensitivity of social security reform, and the importance of choosing an appropriate strategy and lending instrument, in this case a compromise, medium term reform strategy, with critical actions supported by a single tranche operation.
P050719 | Kyrgyz Urban Transport Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/809161474502444571/text/000020051-20140615103801.txt | http://documents.worldbank.org/curated/en/809161474502444571/pdf/000020051-20140615103801.pdf | It is important to be flexible and to be prepared to adapt project designs in response to changing circumstances, even when the need for such adjustments are only identified at a late stage.In a situation where local consultants and contractors are inexperienced, a balance needs to be established between using international and local expertise to ensure no costly implementation mistakes are incurred, but at the same time allowing local professionals to learn through experience.Assessing a proposed privatization of public sector assets needs to take into account the anticipated cash flow of funds for local contractors as well as contractor capability to handle the volume of work expected.In circumstances where the extent of funds for future maintenance may be uncertain, it could be cost effective to design thick pavement overlays to lessen deterioration of the pavement condition over time.
P050731 | GN-Microfinance LIL (FY98) | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2001 | 2005 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/157711474569555664/text/000020051-20140612150235.txt | http://documents.worldbank.org/curated/en/157711474569555664/pdf/000020051-20140612150235.pdf | 1. When planning support to weak and/or bankrupt institutions, key institutional analyses should be conducted before the project is finalized. 2. Firm, preferably formal, commitment from cofinanciers for key project components should be ensured prior to finalizing the project. 3. A LIL was an inappropriate instrument to address the extensive problems facing the bankrupt institutions or sector-wide issues in micro-finance. 4. As a learning device, the LIL should have focused more narrowly on the whether the MFI-building approach was effective or not and confined its scope to the relatively better-performing MFIs.
P050732 | GN-Village Community Support Program - Phase 1 (APL) - IDA Credit | Western and Central Africa | Guinea | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2008 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/798191474481462696/text/000020051-20140619103008.txt | http://documents.worldbank.org/curated/en/798191474481462696/pdf/000020051-20140619103008.pdf | The lessons from phase 1 are candidly and analytically assessed by the PAD for APL2. They are reproduced here in summary form: 'The structural transformations envisaged under the Government's decentralization reform program will require significant changes in the power balance between political and bureaucratic structures. ''A major challenge to the success of decentralization is harmonizing seemingly opposing approaches to local governance.''In order for decentralization reform to be sustainable, a transformation at local level needs to happen, particularly as relates to taxation and tax collection.''Supply of basic service infrastructure does not necessarily increase utilization of services.''Extra-budgetary procedures for investment funds undermine sustainable structures.'
P050738 | Land Titling and Related Services | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2007 | 2007 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/996161474635250504/text/000020051-20140617135844.txt | http://documents.worldbank.org/curated/en/996161474635250504/pdf/000020051-20140617135844.pdf | The key lessons from the ICR are:If there are serious issues precluding movement to a full land titling and registration project, a LIL can not get around the lack of Government ownership.It is important to provide full coverage of land parcels in a given territorial area where systematic titling is being carried out, including those with uncertain land rights. Strengthening the adjudication process to work out land right disputes is particularly important.Regular and reliable feedback from intended beneficiaries and other stakeholders should be ensured to verify that objectives are in fact being achieved.Titling exercises need a substantial program of prior national consultation. This can help to draw out the opposition and better understand the protagonists. Political mapping can also help.
P050740 | Sri Lanka: Health Sector Development | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2004 | 2011 | 2012 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/471461474570538754/text/000020051-20140624214655.txt | http://documents.worldbank.org/curated/en/471461474570538754/pdf/000020051-20140624214655.pdf | The following lessons are drawn from the ICR:Decentralized health services work best when roles and responsibilities are clear, the central level fulfills its stewardship functions, and the decentralized levels are provided with adequate resources. The programs with well established structures and positions at provincial and district levels, such as MCH, registered better performance compared with centrally managed ones, without similar structures.As discussed in the ICR (page 17), while reallocation of project funds to non-project-related activities is justified in emergency contexts, there should be a clear idea of how the reallocations will affect planned project activities and how the shortfalls will be addressed.M&E activities among multiple implementing units should be well coordinated to ensure optimal use of M&E data.
P050741 | Improving Relevance and Quality of Undergraduate Education | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2003 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/713101474630824288/text/000020051-20140624192339.txt | http://documents.worldbank.org/curated/en/713101474630824288/pdf/000020051-20140624192339.pdf | The ICR draws the following lessons:M&E in project design should have sufficient details on performance indicators (i.e. input, output and outcome indicators) relating to various components and sub-components at multiple time points (ICR, p. 18).Competitive funding for tertiary education institutes should pay attention to the following aspects (ICR, p 18):All faculties do not have the same level of implementation capacity. Hence, a tier-system and/or specific windows are often necessary when designing a scheme such as QEF. Initial and ongoing training (i.e. proposal writing and procurement procedures) for staff are critical for the success of competitive funds. The amount of a grant absorbable by study programs or departments and the time frame of implementation must be carefully thought through. Proper incentives (monetary and non-monetary) for the academic staff in charge of implementing the activities play an important role.Procurement can become a hindrance if not properly managed. Performance Indicators must be selected carefully, their number should be kept at a reasonable level, and the targets should be realistic.On quality assurance, transparency of the external assessment process is vital to build up the confidence in, and acceptance of, the external quality assessment, especially during the introductory phase. During the process of building quality assurance culture, university authorities should make every effort to induce the desire for quality as a main principle in every operation in their institutions to create a quality culture (ICR, p 18).It is essential to rally the university community and the general public at large around policy reforms in higher education by using robust public awareness campaigns publicizing the impact of investments in quality enhancement activities, and improved student learning outcomes (ICR, p 19). Additionally, IEG found that the absence of a comparison group, tracked at multiple time points over the project cycle, made it difficult to understand the extent to which project activities had influenced project objectives.
P050741 | Improving Relevance and Quality of Undergraduate Education | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2003 | 2010 | 2013 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/710341468101991374/text/718930PPAR0P050Official0Use0Only090.txt | http://documents.worldbank.org/curated/en/710341468101991374/pdf/718930PPAR0P050Official0Use0Only090.pdf | 4. Lessons 4.1 Since beginning the collaboration in the education sector with the various agencies of the Government, the Bank and the Government have achieved a holistic understanding of the problems of the school system, skill training and development, and the needs of higher education and the economy and the labor market. Given this holistic understanding, the two projects under review might have made more explicit links to take advantage of synergies such as aligning the curriculum changes to develop critical thinking. 4.2 Based upon the experience of the Undergraduate Education project, a few priority lessons can be drawn. Â· M&E activities for objectives related to economic and labor market relevance need to be carefully planned for early in the project cycle. The key performance indicators needed more careful definition in relation to the objective (for example, employability) and specification of methods for obtaining and analyzing the related data (for example, tracer studies, comparison groups, on-going or special household or establishment survey programs). Â· In designing higher education sector reform programs, it is helpful to be selective and pick the top priority, feasible, issues first, avoiding trying to do too much in one project. In Sri Lanka, the selection of quality and relevance, and the related systemic capacity building, were the entry points into a reform program that all stake holders could agree upon. This provided the initial momentum to get program of sector reform started, with the realization that it would take more than one project cycle. Â· Institutional and competitive grants provide a good incentive to overcome, for the most part, the accumulated inertia of past academic bureaucracy, at least in new programs. The use of institutional and competitive grants provided a good incentive as opposed to trying to create changes by administrative or legislative decree. In addition, it was recognized that there was a demonstration effect in which other academic programs improved, even if they did not directly receive a grant. This adds to the lessons about the effectiveness of competitive grants found in the IEG review of higher education lending during the 1990s. Â· In a reform where there is some initial resistance, it is important to have the support of a few respected champions within the sector. In Sri Lankan higher education, the quality assurance process succeeded in the end, after some initial suspicion and misunderstanding on the part of some professors, due to the effective leadership of a few energetic and respected professors. 4.3 The Education Sector Development Project also presents some useful lessons. Â· A sector-wide approach can increase ownership of sector goals and the work program by working through the country budgetary system and implementation arrangements. In the case of Sri Lanka, both provincial and national level officials became more involved in sector planning, programming and resource allocation as well as review and M&E of sector performance. Â· The SWAp can serve as an important catalyst to leverage both the financial and technical support provided by the Bank and other donors. In Sri Lanka, where this was the first SWAp, the Bank's sector-wide support initiated a broader and more regular policy-level dialogue with the Government and leveraged Bank influence on sector resource allocation beyond the resources it directly provided. Â· Learning assessments are critical to know whether the increased resources and inputs to improve education quality translate into improved learning outcomes. The National Assessment of Learning was very important in terms of measuring learning outcomes for reading and mathematics, as a result of the increased resources and inputs to improve quality measured by the M&E system. Â· Decentralization and school-based management has the potential to improve education processes and outcomes. In the situation of devolution to the provinces in Sri Lanka, the school-based management program enhanced ownership of the project objectives. The capacity building and support activities of the project were also major reasons for successful implementation. 4.4 Lessons from both projects have been incorporated into follow-on projects. The new higher education project, â€•Higher Education for the Twenty-First Centuryâ€– (2010), continues and builds upon using grants as a performance incentive mechanism. Grants will also be expanded to post-graduate level research and innovation to make better connections to the private economy. The quality assurance and accreditation activities are being extended to cover private as well as public universities. The new project â€•Transforming School Educationâ€– continues and updates the broad policy framework of the Education Sector Development Framework Program. The M&E system is now robust enough that this project is using the Results Based Method of Disbursement, the first time this is being done in Sri Lanka. Thus, some of the successes of these two completed projects provided the foundation for more ambitious operations.
P050745 | Arsenic Mitigation Water Supply | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2006 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/811291475099066717/text/000020051-20140618053118.txt | http://documents.worldbank.org/curated/en/811291475099066717/pdf/000020051-20140618053118.pdf | 1. Arsenic mitigation needs mainstreaming within the water supply and water resources management sector as a whole: The project's virtually exclusive focus on arsenic mitigation was at the expense of Bangladesh's broader water resources management needs. Addressing arsenic mitigation within an overall water management plan and strategy would reduce the possibility of conflicting investments, and might also enable increased mitigation impact through mutually complementary actions. 2. Safe water needs consideration of all major sources of risk to health - including bacteriological as well as other (arsenic) contamination: Bacteriologically unsafe water is estimated to cause the death of 110,000 children annually in Bangladesh. This is substantially more than the estimated annual 30,000 arsenicosis cases and 6,500 arsenic induced deaths from cancers. The project could have had greater impact if both hygiene practices and arsenic contamination had been dealt with together. Awareness building and extension in hygiene practices would have only slightly increased the costs of the project's awareness campaigns and community training, but incremental benefits would have been large. 3. Without a continued public awareness and education program, reversion to unsafe water consumption practices is a major risk: The unseen nature of arsenic pollution, and its impacts only in the long term, reduce the profile of arsenic contamination. A continuous public awareness program is likely to be needed if arsenic-safe water consumption practices are not to be progressively abandoned over time. 4. Bangladesh's experience using a decentralized, community based approach to arsenic mitigation is a promising model for consideration elsewhere: Bangladesh gave up a governmental, supply-driven approach to water supply and, for the arsenic mitigation program, embraced a new approach, with, as main features - decentralized management, involvement of local governments, transparency, community management, demand-driven investment decisions, and community contributions to investment costs. The new model was largely successful, and thus offers one arsenic mitigation model for potential consideration by other countries. 5. Inclusion of women and the poor in water investment and management wont necessarily happen automatically - specific project features are likely to be necessary: The project experience was that wealthier families influenced the location of wells to be nearer their residences (in part, because they contributed more to the investment than poorer families). Women are overwhelmingly the main fetchers and users of water, yet the ICR reports that they had limited voice in investment decisions. Adjustments could be considered in the mechanisms for making decisions, and of village institutions, so that women and poorer families necessarily play a larger role.
P050751 | National Nutrition Project | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2007 | 2007 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/947421474627992293/text/000020051-20140617135339.txt | http://documents.worldbank.org/curated/en/947421474627992293/pdf/000020051-20140617135339.pdf | Drawing on the ICR the following lessons can be identified:Government approvals: Projects should address possible contentious issues early on in project preparation by working closely with government. Keeping key political and bureaucratic stakeholders in the loop is essential so that when the time comes they will provide crucial support. Key government approvals must be obtained before project negotiations and Bank board approval. Assess available capacity when scaling-up a successful project. The process of scaling up should be undertaken with care. An essential prerequisite is to have a robust evaluation of the pilot, so that lessons learned can be incorporated into the new project. Political and bureaucratic commitment and institutional arrangements for effective scaling up should be carefully assessed and adjusted for. New elements should be added with caution, keeping in mind the capacity of the implementing agency. An assessment of the management capacity and available institutional arrangements should be undertaken early on and adequate investments should be planned in strengthening these constraints. .Maintain continuity of staff, with appropriate skills, including ensuring continuity from one project to another. Frequent changes of leadership and turnover of staff both within the Bank and the borrower, and among the implementing agencies are detrimental to implementation. Continuity of activities and ideas is essential to build upon previous initiatives and work according to an agreed upon strategy. New officers take time to familiarize themselves with their staff and project activities. This can be minimized by a strong technical cadre within a PMU that can advise the Project Director and keep the project on track.Keep flexibility in project design to be able to adjust project components based on emerging evidence from operations research. To give one example of the need for this flexibility in project design, there are a number of reasons why the supplementary feeding program under NNP (and BINP earlier) may not have fully contributed to the goals of improved growth among children, weight gain in pregnant women or birth weight of infants. It is important to re-visit the design of this component, keeping in mind the costs and human resource implications of the program. Invest in operations research and M (ii) program theory, and whether or not the inputs provided under the project are able to produce the desired outputs and outcomes, and how they could be re-designed to be more effective; and (iii) use of monitoring and evaluation findings to guide program and policy decision-making.
P050752 | Post-Literacy and Continuing Education for Human Development Project | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/278511475068942257/text/000020051-20140619090619.txt | http://documents.worldbank.org/curated/en/278511475068942257/pdf/000020051-20140619090619.pdf | The main lessons identified in the ICR and endorsed here are: Government agencies seldom have the organizational capacity or institutional arrangements for the contracting of large number of small NGOs and for the management and oversight of these contracts. A more effective and efficient approach is to contract larger, reputable NGOs to sub-contract with smaller NGOs while ensuring that the appropriate reporting mechanisms are in place for oversight of the large NGOs by the government agency.In order for study tours to yield their full benefit, several minimum requirements have to be met: study tour objectives should be clearly articulated and these should be reflected in the choice of participants and the study tour activities; participants should be required to produce a post-tour report and conduct seminars to share what was learned with nonparticipating staff.
P050761 | BR-Housing Sector TAL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/698691474899642135/text/000020051-20140624213809.txt | http://documents.worldbank.org/curated/en/698691474899642135/pdf/000020051-20140624213809.pdf | Establishing the relevance of an operation to the Borrower's priorities is of primary importance. In this project, the low relevance to the Borrower's priorities resulted in scaling down the project down drastically and major restructuring. A sector investment loan (SIL) may not be an appropriate instrument (compared to, say, non-lending technical assistance) when the primary project objectives relate to policy dialogue and sector reform. This is because the relatively higher process and supervision requirements of a SIL may distract from the main objectives at hand. Even in middle-income countries (MICs) with fairly advanced institutions, capacity for procurement and other process requirements in the implementing agency should not be taken for granted, and arrangements must be made to improve capacity where required. In this project, the lack of familiarity of the implementing agency with the Bank's procurement processes was a major reason for nearly three years of stagnation in project implementation, especially since the project design did not provide for sufficient mitigating measures.An under-performing project should be restructured sooner rather than later. In this case, the supervision process gave inadequate signals for more than two years on the lack of progress in implementation. Had the project been restructured earlier - and an action plan to speed up implementation put in place - the cancellation of a large portion of the loan might have been avoided or at least reduced to some extent.
P050762 | BR-Fundescola I | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/676441474502527754/text/000020051-20140604060018.txt | http://documents.worldbank.org/curated/en/676441474502527754/pdf/000020051-20140604060018.pdf | Microplanning, i.e. detailed planning focused on small areas that have distinct problems may be more successful in improving quality of education than wider and more diffused targeting of poor schools.- When working with state and municipal governments, extra care must be made to recognize early on and incorporate in the design the decisionmaking capacity and efficacy of grassroots organizations, such as parents' associations. - Empowering schools through direct interventions that are designed to generate greater school commitment to the project's development objectives may motivate and train school staff and parents, who might otherwise remain inactive.
P050762 | BR-Fundescola I | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Education | IBRD | IPF | 1998 | 2001 | 2002 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/551411468743667208/text/multi0page.txt | http://documents.worldbank.org/curated/en/551411468743667208/pdf/multi0page.pdf | Lessons 4.15 Experience with the projects confirms a number of OED lessons from education projects\. * Attention to state, municipal, or even school management is necessary but is not sufficient for improving classroom instruction effectiveness and efficiency. Attention must also be paid to how the precious classroom time is used. * States and municipalities that are better off are more likely to take advantage of Bankfinanced resources. The challenge is to encourage the poorer ones to benefit as well. * Political stability, stable project teams, and policies to help the poor receive quality education contribute a great deal to project success. * Decentralizing school management to the municipal level is not a panacea. Autonomy permits the poorest or least knowledgeable municipalities to fall behind, without much possibility for helping their residents. * In addition to achievement tests, classroom observations may be used as predictors of achievement. Unless there is after-hours coaching, children's knowledge is likely to reflect information processing in classrooms. Classroom observations can potentially provide feedback and promote improvements sooner than achievement tests, which must first be developed, administered, and analyzed. * Students' health needs and problems must be addressed to optimize cognitive development and classroom learning. However, agency coordination problems may make this task difficult, and means must be sought early on to eliminate obstacles. * Research financed by projects must be disseminated and put to action. Findings must be communicated clearly and succinctly, through means that are likely to change behaviors and attitudes. It may be cost-effective to spend money for translation (where needed) and develop a follow-up action plan. * The theories and hypotheses that Bank staff develop about improving educational outcomes should be validated and examined in light of pertinent research before being integrated into project designs. * The Bank should acquire more expertise with respect to improving basic skills, particularly in operations that target the poorest children.
P050763 | Second School Improvement Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/205001475098441475/text/000020051-20140615112849.txt | http://documents.worldbank.org/curated/en/205001475098441475/pdf/000020051-20140615112849.pdf | Long-term Bank support for well-defined national education programs may result in improving schooling outcomes. However, a clear line of reasoning and research evidence are necessary to link project inputs to expected learning outcomes. - It is important to document the effects of innovative interventions before pilots are applied on a large scale. However, appropriate monitoring and evaluation designs are needed to document long-term and large-scale changes.
P050772 | Land-Based Poverty Alleviation Project I | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/887821475093548573/text/000020051-20140620064357.txt | http://documents.worldbank.org/curated/en/887821475093548573/pdf/000020051-20140620064357.pdf | The ICR lists 15 lessons, some of which are conclusions rather than lessons. The principal lessons of general interest are: The community-based approach to land reform, relying on negotiated land sales and community implementation of investment sub-projects, can be an agile and effective mechanism to redistribute land to poor rural families. Even with a simple, beneficiary-driven model, the political and operational aspects of land reform introduce significant risks that potentially can delay or derail the process. Monitoring arrangements and performance under a Federally-financed project implemented at the State and local levels requires close supervision to ensure that key data are collected, stored and transmitted regularly to the center for aggregation, and that they are closely linked with the analyses to be undertaken. Working with small, poor communities in remote rural regions entails a series of constraints which may merit greater flexibility and creativity in the approach taken to applying Bank standards.
P050776 | Northeast Microfinance Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/593481474944609409/text/000020051-20140618081116.txt | http://documents.worldbank.org/curated/en/593481474944609409/pdf/000020051-20140618081116.pdf | A well prepared project (founded on a pilot, strong management commitment, substantial technical support, demanding monitoring and evaluation) can succeed in difficult circumstances (introducing a new commercial service to an area, being housed in a government owned institution, operating within distorted economic policies). Despite this success, it may be too early to recommend replication elsewhere. A thorough evaluation after CrediAmigo operates without Bank supervision, as well as the expected impact evaluation, would provide better guidance.
P050776 | Northeast Microfinance Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2007 | 2014 | PPAR | >=25 million & <50 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/413371468049875444/text/868030PPAR0P050C0disclosed040180140.txt | http://documents.worldbank.org/curated/en/413371468049875444/pdf/868030PPAR0P050C0disclosed040180140.pdf | 7. Lessons 7.1 A number of lessons can be drawn from the early pilot of CrediAmigo and the project's implementation that are useful for other microfinance institutions, the Bank, and other donors for the design of microfinance operations. The lessons can be considered under two rubrics\. those applicable to any project and those applicable specifically to microfinance. Lessons Applicable to All Projects 7.2 Flexibility in supervision to adapt to changing scenarios is essential for success, both when the changes are marginal and when they are fundamental to the point of rendering the attainment of the operation objectives impossible. In the former case, flexibility must be manifest in the willingness to sacrifice details for the sake of achieving the ultimate objectives of the operation. In the latter case, this requires courageous decisions from the project team, to the point of significantly restructuring the operation, should it be necessary to remain true to original objectives. 7.3 The Bank can help in building lasting reforms by limiting the scope of the projects to what can be accomplished within a certain political and economic environment, even if not fully market-oriented. Nevertheless it must be cognizant of the fact that the environment is fragile and may depart further from market based principles. 7.4 Donors such as the Bank can add value by setting benchmarks consistent with international best practice and putting the client institution in contact with top practitioners in each field. Lessons Applicable to Microfinance Projects 7.5 In principle, a viable and broadly independent microfinance institution can be set up within an existing public sector bank and there may be benefits to doing so. However, this leaves it open to influence by the prevailing political climate. In an environment where public sector financial intermediation, or some segments of it, may be subsidized by the state, it may be difficult to isolate the 'independent' microfinance program. Even if ring fenced today, unless spun off, the micro-finance institution remains vulnerable to future recapture by the parent institution. Tensions about the extent to which public or private sector principles apply persist. 7.6 There can be tensions between the achievement of expanded microfinance outreach and the achievement of financial sustainability. It may be tempting in some political environments to expand outreach at the expense of sustainability. The Bank's decision to remain engaged was anchored on real successes achieved in terms of outreach, which illustrates dilemmas about outreach versus sustainability. Yet expansion of outreach to a desired clientele is not necessarily an indicator of sustainability. 7.7 Transparency can be a powerful aid to sustainability. Subsidies can be explicitly taken into account through a Subsidy Dependence Index provided it is well defined. However, it is difficult to incorporate the measure of subsidies in funding. 7.8 While institutional aspects are crucial for the delivery of financial services to microenterprises, national economic policies are equally crucial. The operations of well managed institutions can reflect financial unsustainability from the point of view of the economy as a whole if the enabling environment reflects distortions in financial markets
P050780 | Pension Reform Adjustment Loan (PRAL) | Europe and Central Asia | Kazakhstan | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 2001 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/922411474939815180/text/000020051-20140607163101.txt | http://documents.worldbank.org/curated/en/922411474939815180/pdf/000020051-20140607163101.pdf | 1. Project conditionality should focus on outcomes. PRAL conditionality focussed on a large number of studies and plans, but a few monitorable indicators of outcomes would have been more useful. 2. Monitorable indicators should be incorporated in project design, especially for complex adjustment operations such as pension reform.
P050875 | Rural Poverty Reduction Project -Ceara | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/147091475093891183/text/000020051-20140620074317.txt | http://documents.worldbank.org/curated/en/147091475093891183/pdf/000020051-20140620074317.pdf | Drawing from the lessons in the ICR, with some adaptation, the main lessons are: 1. Targeting of benefits to the poorest requires an operational strategy to reach them through mobilization and organization which enables them from the outset to access the project on a more equal footing. Systematic consultation and information dissemination should be initiated before project effectiveness.2. Programs to foster successful integration of marginalized communities requires an aggressive, multi-pronged approach and are manpower intensive. Concentrated efforts to maximize the benefits of integration call for pro-activity in establishing a diverse network of partnerships, anchored within a consistent, pro-poor sector strategy which maintains focus on the ultimate beneficiaries.3. Preparation and analysis of small scale productive activities with groups with limited commercial experience need high quality inputs to ensure that plans are viable and appropriate technical skills are available. Training and technical assistance for productive sub-projects are crucial inputs. 4. Follow-up monitoring of small-scale investments is feasible. The project developed an innovative system for follow-up monitoring of project investments through the imaginative use of modern technology, such as GPS data bases, as noted in Section 10.
P050880 | Rural Poverty Reduction Project - Pernambuco | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2010 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/741961474907885497/text/000020051-20140624184824.txt | http://documents.worldbank.org/curated/en/741961474907885497/pdf/000020051-20140624184824.pdf | Lessons suggested by the ICR include the following: Community-driven development (CDD) can promote social capital formation if subprojects are rigorously and transparently selected and adequate training is given: "Tangible benefits from subproject investments strengthen collective capacity, generate a sense of citizenship, and raise the bar for local government accountability" (p. 28);Delegating responsibility for routine supervision to project monitoring unit regional offices (of which there were 8 in this project) helps increase project visibility at the local level, making the project more accountable to beneficiary families; andProductive subprojects are more likely to succeed if they are supported by business plans, allow for training and assess potential demand for the product. They are more likely to be sustainable if provision is made for linkage to banks.IEG adds:A complete assessment of the efficiency of CDD projects involves reviewing the evidence for cost-effectiveness, showing how this varies between subproject categories, and the extent of variation between the average for the project and the average obtained under other public programs. Intermediate outcomes, such as social capital, need to be properly quantified with well-designed indicators, baselines and targets.
P050881 | Rural Poverty Reduction Project - Piaui | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2010 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/825301474630748182/text/000020051-20140624184907.txt | http://documents.worldbank.org/curated/en/825301474630748182/pdf/000020051-20140624184907.pdf | Lessons suggested by the ICR include the following: Subproject preparation may be hampered by the lack of good-quality technical assistance services in rural areas, irrespective of whether or not part of the subproject budget is earmarked for funding technical assistance; Local capacity building is more likely to be sustainable if projects provide for continuous training of the people in participating agencies; andPlanning exercises will be more rigorous and transparent if participating institutions, like Municipal Councils, are given annual indicative budgets, within which trade-offs must be made.IEG adds:A complete assessment of the efficiency of CDD projects involves reviewing the evidence for cost-effectiveness, showing how this varies between subproject categories, and the extent of variation between the average for the project and the average obtained under other public programs (the ICR, pp. 33-34, provides relevant data); Intermediate outcomes, such as social capital, need to be properly quantified with well-designed indicators, baselines, and targets.
P050886 | Pilot Private Irrigation Development Project | Western and Central Africa | Burkina Faso | IDA |  | Sustainable Development | Water | IDA | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/242821474484558520/text/000020051-20140613080441.txt | http://documents.worldbank.org/curated/en/242821474484558520/pdf/000020051-20140613080441.pdf | Do not split responsibility for implementation of activities to achieve an objective. This may provide grounds for miscommunication among concerned organizations, severely hinder implementation and cause delays.
P050891 | ELEC SECTR REF | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1997 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/294001474634452419/text/000020051-20140618060442.txt | http://documents.worldbank.org/curated/en/294001474634452419/pdf/000020051-20140618060442.pdf | 1. The timing of a TA project and the reform program it is meant to support must be carefully synchronized. It is of little value breaking preparation time records for an operation which doesnâ€™t disburse for another four years. This is not only imprudent but also costly for the Borrower, who must pay commitment fees and interest.2. Linked to this, is the need for a careful assessment of the strength and sustainability of political support for the program and the degree of national ownership of the TA project and its design.3. By 1997, the year of the projectâ€™s preparation, enough experience had been garnered with TA projects, especially large ones supporting policy reform, to justify the utmost care and attention being paid to implementation arrangements. 4. Large and complex TA projects, with multiple implementing agencies, are especially vulnerable to implementation difficulties.5. Continuity of staff, especially team leaders on both Bank and implementing agency sides, is essential for smooth implementation.
P050892 | Emergency Pilot Credit for Republika Srpska | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2000 | 2002 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/114391475094709098/text/000020051-20140604045857.txt | http://documents.worldbank.org/curated/en/114391475094709098/pdf/000020051-20140604045857.pdf | 1. This project had several features which worked well and are a good basis for other projects: (a) Even in emergency situations, it is important for credit-line operations to allow banks to take credit risks, rather than have the banks act as an implementing agency, (b) Institutional autonomy is important for Project Coordination Units. 2. One aspect of the project which could have worked better was the technical assistance for enterprise support. This support might have been made even more relevant than it was if it had been institutionalized and delivered with some cost-recovery features to promote incentives to make the material as relevant as possible for entrepreneurs.
P050910 | Municipal Development & Decentralization Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/867671475082421425/text/000020051-20140612072825.txt | http://documents.worldbank.org/curated/en/867671475082421425/pdf/000020051-20140612072825.pdf | Rushing project preparation may leave many details to be worked out later with resulting higher costs and delays for implementation. The lack of a full policy dialogue during preparation can undermine institutional development achievements.Political commitment to reform should be cautiously assessed. Policy statements and declarations of intent should be interpreted with care, especially in a context populated by a wide variety of actors with diverging interests.Undue reliance upon local agencies with weak capacities can compromise project performance. External assistance to support them is appropriate in such circumstances.
P050910 | Municipal Development & Decentralization Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2003 | 2008 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/685481468274208735/text/443100PPAR0P071closed0July029020080.txt | http://documents.worldbank.org/curated/en/685481468274208735/pdf/443100PPAR0P071closed0July029020080.pdf | 8. Findings andLessons 8.1 Inproviding assistancefor the reformofany sector-municipal inthis caseBank and Borrower need also to help ensure that information systems are adequate for implementing the reforms and for monitoring progress. Inthe case o f these three projects, information on municipal finances and on the economic performance o f sub-project investments was sparse. Georgia's situation inthis regard could be improved by the greater use o fmunicipal experiences o fother countries. 8.2 Political volatility provides unusual challenges and opportunities for Bank supervision. It calls for more thorough documentationthan normal, detailing all actions agreed betweenBank and Borrower. It also requires greater oversight of project financial management. Inthe case o f Georgia, it didprovide opportunities for the Bank to act as valued and stable interlocutor intimes o f change. 8.3 Major political and economic transition, while offering opportunities for reform, may slow downprogress with municipal reform inparticular, as national governments work to establish the effectiveness o f their central control. 8.4 When municipal management i s very weak overall, it makes senseto work first with stronger andcreditworthy municipalities that are most likely to succeed. InGeorgia, the national government could recognize and foster these municipalities as models o f good practice and sources for inspiration andtechnical assistance for others to learn from. 8.5 Time gained through speedy project preparationcan be lost ifimplementationhas to be extended inorder to resolve matters overlookedby the hasty start-up. Speedy preparationitselfmay also be o f little benefit when the Bank is involved for the long haul, as it has been inGeorgia, where project achievements havebeenmade steadily but slowly.
P050911 | Integrated Coastal Management Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1999 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/647341474943353352/text/000020051-20140618082903.txt | http://documents.worldbank.org/curated/en/647341474943353352/pdf/000020051-20140618082903.pdf | This ICR contains an interesting set of lessons, several of which, being of broader applicability, should be highlighted): (i) managing project implementation in a politically dynamic country should imply regular scanning of political trends and flexibility in adjusting to changing times; (ii) success of a project under any line agency would depend on its ownership by a focal point in a politically strong branch of government; and (iii) management of protected area projects needs strong presence both centrally and locally. In addition, based on the observations in the ICR in relation to Bank performance, another important generic lesson would appear to be: in situations of considerable political, institutional, and/or policy changes at the national level that have an adverse impact on project performance, more proactive attention on the part of Bank management may be required.
P050938 | Capacity Building for Decentralized Service Delivery | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2003 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/348051474649026766/text/000146597-20140619170240.txt | http://documents.worldbank.org/curated/en/348051474649026766/pdf/000146597-20140619170240.pdf | IEG concurs with the lessons stated in the ICR, and adds the following:Where projects do not include an appropriate results framework for monitoring and evaluation, it is critical that this be developed during implementation.In demand based activities, the nature and number of sub-projects need to be monitored and a clear assessment of how these sub-projects contributed to the final outcomes needs to be documented.
P050945 | Education Quality Improvement Program (EQIP) | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2000 | 2007 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/514981474635264428/text/000020051-20140617140129.txt | http://documents.worldbank.org/curated/en/514981474635264428/pdf/000020051-20140617140129.pdf | The Bank and governments should pay attention to the staging of phases of an APL. While the APL instrument provided flexibility to the Government to make mid-course changes in the program, the overlap between EQIP 1 and EQIP 2 resulted in some implementation difficulties. Stakeholders in Bank projects should be included not only in developing underlying strategy but in the actual design of the project itself. The Government and Bank should be sure that any stakeholder that will be involved in implementing the project should be aware of and accept their roles and responsibilities and has the capacity to carry them out. This includes Government agencies (such as the Tender Board, which held up implementation because it did not accept the procurement guidelines for the project); communities (which were unprepared to create and implement school charters); and groups (such as teachers, who are responsible for utilizing their training to improve their teaching practices.)Design of monitoring and evaluation should focus on demonstrating project outcome rather than implementation. The project appears to have been quite successful, but the data are inadequate to conclude that the project development objectives were fully met.
P050956 | ECO. REFORMS SUPPORT | Western and Central Africa | Cabo Verde | Blend |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 2000 | 2001 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977221474650916979/text/000020051-20140529071554.txt | http://documents.worldbank.org/curated/en/977221474650916979/pdf/000020051-20140529071554.pdf | The concept of a Trust Fund which can back domestic debt with foreign exchange and utilize foreign earnings to service domestic debt payments is valid and could be useful in other contextsThe proceeds of privatization cannot be closely coordinated with the envisioned budgetary or Trust Fund impact, because of differing procedures and imperatives
P051026 | Structural Adjustment Technical Assistance Credit 2 (SATAC 2) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/839771475092370056/text/000020051-20140612083214.txt | http://documents.worldbank.org/curated/en/839771475092370056/pdf/000020051-20140612083214.pdf | Stronger Government leadership of the aid coordination process would enhance efficiency and assure that donor assistance is fully consistent with PRSP goals.TA provided under SATAC 2 was key to reform progress. The project supported work under 4 adjustment operations and was important across a number of sectors.A TA project can catalyze significant resources. SATAC 2 stimulated, or at least facilitated, expenditures by other donors in numerous areas, most notably regarding the census.
P051034 | Structural Assistance Technical Assistance Credit 2 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1998 | 2000 | 2001 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/813411475090677988/text/000020051-20140529072559.txt | http://documents.worldbank.org/curated/en/813411475090677988/pdf/000020051-20140529072559.pdf | A Technical Assistance project should include indicators designed to reflect a future level of performance.
P051034 | Structural Assistance Technical Assistance Credit 2 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1998 | 2000 | 2004 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/746081468751804137/text/26439.txt | http://documents.worldbank.org/curated/en/746081468751804137/pdf/26439.pdf | 8. Lessons Learned 8.1 Georgia's weak governance severely limitsthe country's ability to create conditions conducive to economic development and the effective use of development assistance-The problems that limit growth inGeorgia transcend economic policy. The political and geographic fragmentation o f the country poses severe challenges to the executive. The inability o f the executive to overcome obstacles posed by the parliament and regional officials, establish a minimumlevel o f the rule o f law, and overcome a pervasive culture o f corruption severely limits the country's ability to establish sustained, broad-based growth with significant job creation. 8.2 For a country such as Georgia, which experienced economic collapse, it is incumbent that the Bank give high priority to prompt measures that can directly mitigate conditions for the poorest. 53This section is based on interviews with energy sector firms, govemment officials, and Bank staff. 8.3 Turnover on the country team limited program effectiveness-From 1994to 1998,there was one Country Economist for Georgia. Officials interviewed cited the benefits that they believe this continuitybrought. However, since 1998, there have been3 Country Economists, and an interval o f around6 months duringwhich the position was unfilled. While there werejust two Country Directors duringthe periodcoveredby this PPAR, and good continuity on the rest o fthe Country Team, the tumover diminished the continuity o f the program, andprobablyconstrained the ESW that was performed. 8.4 A more robust and timely ESW programwould have been beneficial to the design o f the reformprogram-The Country's first poverty studywas completed in 1999; the design o f the reform program would have benefited from earlier work inthis area. A study o fthe sources o fgrowth might also have beenbeneficialbyidentifyingsectors from which growth might be expected to flow, and then considering means by which to facilitate such growth. A Public Expenditure Review-a veryuseful analytical tool for a country with Georgia's perennially weak fiscal situation-was completed in 1996, and then not again until 2002. Fiduciary reports (CFAAs and CPARs) were completed infrequently. The rapid tumover inCountry Economists was probably part o fthe reason for the weak ESW. 8.5 Turnover among policy officials hinderedreform progress-During the seven years coveredby this PPAR, there were seven Prime Ministers and four Ministers of Finance. There was also substantial tumover among other officials concerned with implementingthe reform program. For an official contemplating a brieftenure, it i s more difficult to appreciate the benefits o f reform, and so this tumover made reform progress considerably more difficult.
P051059 | Petroleum Development and Pipeline Project | Western and Central Africa | Cameroon | Blend |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2010 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/565481468224677215/text/503150PPAR0P05101Official0use0only1.txt | http://documents.worldbank.org/curated/en/565481468224677215/pdf/503150PPAR0P05101Official0use0only1.pdf | 4. Lessons and Future Implications 4.1 The well-known lesson that government ownership and commitment are the major influence o n the effectiveness of projects and programs i s underlined by the experience o f the Chad-Cameroon program. Other lessons learned from the program are identified belowmany o f them also well known but brought in sharp relief by this experience. Because the findings and conclusions are discussed in the earlier sections, the lessons and implications are listed below with a minimum o f elaboration. (Project-specific lessons are included in the corresponding annex.) RELEVANCE, R I S K S , AND TIMING 4.2 International experience has shown that adequate expenditure management mechanisms should be in place, and tested, before a large revenue increase i s likely to accrue. In this case, the time available for capacity-building after Board approval and before the flow o f o i l revenue was much shorter than expected and the revenue much larger-adding to the difficulty o f building capacity contemporaneously with program implementation. A secondary lesson is therefore to build expenditure management capacity as robust as necessary to fit a high scenario o f revenue increase. (The capacity created will be useful to the country even if the high scenario does not materialize.) 4.3 Setting up institutional enclaves and special mechanisms to protect resources and accomplish quick results can damage local capacity in the long term. Such enclaves are generally not successful beyond the short term and, even when successful in the short term, they tend to undermine the already weak local systems and thus long-term development. In this case, although the rationale for the establishment o f the revenue escrow account and the earmarking arrangements was strong in the specific country context in 2000, when tested by reality these mechanisms failed to achieve their objectives and meanwhile stood in the way o f sustainable improvements in fiscal and expenditure management capacity. 4.4 While protecting inputs must remain a paramount consideration, development objectives should be formulated in terms o f outcomes (ifpossible), meaningful outputs, or concrete process improvements-rather than in terms o f inputs-and performance indicators should be limited to thefew key indicators that are critical to achieving the PDOs and are monitorable. Even when the immediate aim o f the project i s to increase resource availability, reduce the cost o f input acquisition, or channel resources toward priority uses, a failure to define clearly the expected results in terms o f key outputs, outcomes, or major process improvements risks distorting the actual design o f the project away from those results. In this case, defining the main project objective for Chad in terms o f budgeted expenditure to be achieved diverted attention away from the efficiency o f expenditure and budget execution. And to l i s t dozens o f key performance indicators o f diverse importance and questionable monitorability makes monitoring impossible. AND DESIGN APPROACH 4.5 If the WBG decides to risk involvement in ambiguous and fluid situations, it pays not to do so in overly detailed and rigid ways. Utmost clarity is needed o n the objectives, principles, and parameters, but the design and implementation modalities should be as fluid as the situation itself, rather than rely on binary choices and numerical rules. This approach, however, may in practice foster a propensity to make successive small compromises, cumulating in the risk that continued Bank engagement may result in acquiescence to inefficient use o f resources. Thus, in addition to clarity o f purpose, an adaptable engagement grounded on flexible but robust dialogue requires a strong fabric o f reciprocal trust between staff and management and continuity o f both. 4.6 Revenue transparency i s necessary-specially for revenues from extractive industries-but i s not sufficient. Transparency on the expenditure side i s critical as well. In this case, setting as the main target a global minimum percentage spending on several sectors implied that the global target could be met even if the intersectoral allocation o f the resources was very different from what had been agreed, and without regard to the efficiency o f their use. 4.7 Project design must be based on recognition o f institutional and administrative capacity. I t i s important in countries with weak capacity to focus on addressing the basic problems rather than attempting to introduce sophisticated practices. In this case, paradoxically, major components o f the program in effect assumed the prior existence o f the very capacity they aimed to build. 4.8 An innovative design, even if it proves unsuccessful, may contain novel elements worthy o f consideration and possible replication. In this case, there are three such elements\. The formation o f the Collige de ContrGle was an excellent and exciting idea, even if it did not enjoy the necessary government support-and such joint publidprivate/ NGO entities have the potential to foster expenditure efficiency as well as social accountability in countries with a government reasonably interested in a prodevelopment, pro-poor expenditure policy. The Provisional Committee to allocate the 5 percent o f the direct o i l revenue to the oil-producing region can be an illustration for similar arrangements in other countries with valuable mineral resources, despite flaws in i t s operation in this case. Finally, the cover and voice given to local NGOs through the dialogue on the preparation o f the program and during i t s implementation should be a regular feature o f all such WBG interventions. WBG PERFORMANCE 4.9 Although in complex and high-profile cases strategic guidance and major decisions must come from the top leadership o f the WBG, it i s not clear in this case that the top-down direct intervention by the Bank President's Office in 2006 was helpful to formulate a new agreement with a better chance o f enforcement. 4.10 In large, complex WBG projects with multiple stakeholders, good WB-IFC cooperation i s important to improve the chances for positive results. In this case there was good WB-IFC cooperation on the main pipeline project, but it also extended to Advisory Services operations. In late-2004, when the IDA-funded capacity-building projects were found to be progressing slower than expected, IFC was able to provide new funding for sustaining the capacity-building initiatives. 4.1 1 IFC's Advisory Services have a signijkantpotential role to help the local private sector. They can enable local companies to participate in the economic activity created by the project; help the sponsors-typically large multinational corporations-meet national content 47 requirements; and promote local economic development. In this case, the Enterprise Center-the focal point o f IFC's Chad SME program-became the cornerstone o f Exxon's procurement platform that was the sole source for all o f i t s purchases in Chad, starting in 2005. 4.12 Whether the World Bank or the I F C i s involved, the concern with development effectiveness goes beyond the gates o f individual projects-however well they may be technically done-to the results o f the overall program. There i s no contradiction between viewing favorably the technical and financial success o f the pipeline project even though the weight o f other unfavorable outcomes leads to a negative conclusion o n the development outcome o f the program o f which it was a component, as in this evaluation. However, the evaluation illustrates the basic point that a part o f a program, however well carried out, cannot be separated from the overall program and the broader setting within which its impact i s being assessed\. a project or a subproject cannot be ring-fenced in the assessment. 4.13 Continuity is critical to manage a project that i s central to a program, and a minimum o f in-house technical competence is necessary to supervise consultants. In this case, the revenue management project had six task team leaders in its seven years, and the Chad capacity-building project relied almost entirely on consultants for the first years, without any in-house expertise in the technical dimensions o f o i l exploration and production. 4.14 Good communications and transparency are particularly important in the context o f a difficult decision. Senior management would want to appropriately consider the views o f key operational managers and staff and ensure the fullest possible measure o f advance consultation with key development partners. IMPLICATIONS FOR THE FUTURE MAJOR 4.15 With substantial o i l revenue expected to continue for many years, it i s s t i l l possible for Chad to escape the resource curse. The difficulties are known. Institutional and organizational capacity remain weak. Macroeconomic sustainability i s injeopardy. Fiduciary risk i s likely to increase in the short t e r m with the unexpected fall in o i l price and revenue in 2009 and 2010-producing pressures to preserve security and regime maintenance expenditures, and hence a downward pressure on pro-development, pro-poor expenditure. Budgeting systems and skills remain quite insufficient for efficient resource allocation, and motivation and integrity have been weakened by the lack o f consequences for the spreading non-compliance with fundamental rules. However, there are scenarios under which a good development outcome in the long run is s t i l l conceivable. The Bank could cooperate with the IMF in monitoring overall fiscal and expenditure outcomes and make a useful contribution by providing good and flexible advice in public sector management-focused o n the basics, recognizing capacity realities, and supported by assertive cooperation o f certain major bilateral partners. But the most important factor would be a new and genuine determination by Chad's government to use the o i l resources for development and poverty reduction, and do so responsively and efficiently. 4.16 The Chad-Cameroon o i l development and pipeline construction program exemplifies the inherent tension between the limits o f the WBG as an international organization and i t s mandate to foster development and poverty reduction. The WBG went very far in 1999 toward the development side, by setting up complicated and prescriptive arrangements to maximize the probability that the Chad government would use the o i l revenue windfall mainly for development and poverty reduction. For various reasons, the revenue windfall turned out to be used in large part for military expenditure and other regime maintenance and for wasteful construction. The governance climate in Chad did not improve-rather the reverse. 4.17 However, it should not be concluded from this experience that the WBG should not intervene in supporting extractive industries because doing so carries reputational risks and success i s unlikely. Indeed, despite the disappointing overall outcomes o n the development and governance side, WBG involvement contributed to a notable increase in expenditures in social sectors and environmental and social protection within the confines o f the project better than they would have been otherwise. The analysis o f this report suggests that realistic and constructive WBG involvement in extractive industries could rest o n combining an insistence on high standards o f environmental and social protection with flexible conditionality o n the composition o f all expenditure and its efficiency-complemented by assistance to strengthen a unified budget system, ensure transparency in both revenue and expenditure, and build capacity in accountability institutions. T o be effective, WBG involvement must be buttressed by an agreement with all other major donors that violation o f the environmental and social standards or backsliding o n fiscal transparency or accountability would trigger consequences for the overall f l o w o f aid t o the government concerned.
P051124 | PA UTILITIES RESTRUC TA | Latin America and Caribbean | Panama | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/243291474895590477/text/000020051-20140612152622.txt | http://documents.worldbank.org/curated/en/243291474895590477/pdf/000020051-20140612152622.pdf | Because many people consider water to be a basic right there is often resistance to privatization and the introduction of market-oriented reforms. In such circumstances much greater attention needs to be paid to the social and political acceptability of such measures and a program to build support (backed by the government) becomes a prerequisite.More emphasis needs to be placed on the rationale for the autonomy of regulatory bodies, charged with establishing privatized entities, to minimize direct government intervention.In telecommunications a competitive environment is often enhanced by favorable technological conditions and where monopoly rights assigned through concessions are for relatively short periods. In the energy sector the absence of pure energy traders can be a major shortcoming because small customers generally lack the expertise to negotiate directly with the power generators. The Bank could therefore pay more attention in the design of future utility restructuring technical assistance projects to increasing the potential benefits of greater competition.
P051151 | Social Protection Adjustment Loan | Europe and Central Asia | Bulgaria | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1999 | 2000 | 2002 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/431511474484416100/text/000020051-20140604045642.txt | http://documents.worldbank.org/curated/en/431511474484416100/pdf/000020051-20140604045642.pdf | First, the SPAL agenda was ambitious but was largely fulfilled because (a) Government's demonstrated commitment; (b) The Ministry of Labor and Social Protection was progressive; (c) Civil society was involved in pension reform. The Ministry of Labor and Social Protection worked with a "Working Group for Pension Reform" supported by USAID and included participation comprising academia, business, and experts. As a result pension legislation was passed by the Parliament in record time. Second, the Social Insurance Administration Project (SIAP) that preceded the SPAL was critical in building capacity for pension reform undertaken in the SPAL. An IDF grant was not as successful an instrument to build capacity for social assistance reform. Third, the focus in the SPAL was on appropriate legislation to underpin social protection reforms which was an essential first step but close monitoring of implementation is desirable, particularly in the context of EU Accession and the SPAL should be followed up with instruments that would allow regular monitoring. Fourth, analytical work on poverty should be sequenced so as to inform a social protection loan. In Bulgaria's case, the poverty assessment was somewhat ambivalent in its conclusions on the practical scope for improved targeting, pointing to the need for further analysis.
P051171 | Structural Adjustment Credit 3 (SAC 3) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/364221474595305276/text/000020051-20140604053149.txt | http://documents.worldbank.org/curated/en/364221474595305276/pdf/000020051-20140604053149.pdf | 1. Adjustment programs must address the many interrelated constraints to private sector development including an environment conducive to private enterprise and the entry of new firms. 2. Capacity must be built in the government to support a market economy. 3. Continuity and dedication of task managers can contribute to effective relations with the Government and receptiveness to Bank advice. In this operation. the same task manager and country director continued from appraisal in 1998 to closing in 2001 and the Government response to the operation as documented in the ICR has been positive.
P051171 | Structural Adjustment Credit 3 (SAC 3) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2001 | 2003 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/945021511185175484/text/multi0page.txt | http://documents.worldbank.org/curated/en/945021511185175484/pdf/multi0page.pdf | 8. Key Lessons Learned\n8.1 When adjustment projects are synergistic with sectoral investment projects,\neffectiveness can be enhanced\. During the course of the 3 SAC projects, investment projects\nlinked to the adjustment program were undertaken in the education, irrigation, and power\nsectors, and considerable synergy with the adjustment credits was achieved. The financial\ninducement of the SACs provided an incentive for the Ministry of Finance to become an\nadvocate for sectoral reforms, and cooperation between ministries was enhanced. However, the\nEnterprise Development Project was not designed as complementary to the SACs, and thus did\nnot achieve synergy.\n8.2 For an adjustment program focused on private sector-led growth, key constraints\nto private sector development must be confronted\. While considerable emphasis was placed\non privatization and financial sector development, insufficient weight was accorded to critical\ncomplimentary aspects of private sector development, including\. a business environment\nconducive to private enterprise and the entry of new firms; effective enterprise restructuring and\ngovernance; building adequate government capacity to support a market economy; and effective\nprocedures for bankruptcy and liquidation.\n8.3 As a reform program advances, progress may become more difficult\. First\ngeneration reforms, such as trade and price liberalization and the promotion of open markets,\ndid not for the most part pose a major challenge to vested interests. However, further progress\ninvolved fundamental changes in political, judicial, and social institutions, and in many cases\nchallenged powerful interests. Bank staff found that overcoming these important opposing\nconstituencies was much more difficult than earlier reforms, and more difficult than they\nexpected.\n8.4 It is unrealistic to assume that if the fundamentals are in place, an automatic\nsupply response will take place\. A key assumption of the Bank\'s reform program was that, if\nthe fundamentals (i.e., first generation reforms) were in place, a supply response (i.e., broad-\nbased growth stimulated by the private sector) would be forthcoming. The Bank vastly\noverestimated the ability of Armenian workers, entrepreneurs, and institutions to overcome the\nlegacy of decades of Communism and the power of indigenous vested interests. Also\nunderestimated was the cost of the breakup of the Soviet Union to Armenia\'s productive assets.\n8.5 Legal reform should take adequate account of enforcement capacity\. Important\nprogress was achieved by the passage of new legislation, and an impressive framework was put\ninto place. However, the adjustment program placed insufficient emphasis on strengthening the\njudiciary and the actual role the legal system could play in furthering an improved business\nclimate.\n8.6 Continuity and dedication of the country team are key to program effectiveness\.\nDuring the six years covered by this PPAR, there was substantial continuity of the task team\.\ntwo Country Directors, three country economists, no more than two TMs for any of the\nadjustment operations. In addition, project supervision and coordination of the country team\n\n\n31\nwith sectoral specialists was very successful. This contributed significantly to Bank\neffectiveness.\n8.7 Turnover among policy officials hindered reform progress\. During the six years\ncovered by this PPAR, there were seven Prime Ministers and four Ministers of Finance. There\nwas also substantial turnover among other officials concerned with implementing the reform\nprogram. For an official contemplating a brief tenure, it is more difficult to appreciate the\nbenefits of reform, and so this turnover made reform progress considerably more difficult.\n\n\n\n33\nREFERENCES\nEBRD, Transition Report 2000.\nFIAS, Armenia\. Administrative Barriers to Investment, May 2000.\nIMF, Armenia Financial System Stability Assessment, March 2001.\nIMF, Recent Economic Developments and Selected Issues, December 2000.\nIMF, Recent Economic Developments and Selected Issues, May 2001.\nNorwegian Refugee Council, www.idpproject.org.\nOxford Analytica, Armenia Financial Sector, July 24, 2000.\nRamachandran, S. Evaluating Adjustment Lending\. Some Suggestions, Informal Paper, August 2001\nUSAID, Investigation of Factors Inhibiting FDI in Armenia, August 1999.\nWorld Bank, Between State and Market\. Mass Privatization in Transition Economies, September 1997\nWorld Bank, Seize the State, Seize the Day\. State Capture, Corruption, and Influence in Transition;\nAnticorruption in Transition, a Contribution to the Policy Debate, (2000).\nWorld Bank, Armenia\. Restructuring to Sustain Universal General Education, Technical Note, 2001.\nWorld Bank, ECSPE, Armenia/Georgia Country Unit, Growth Challenges and Government Policies,\n2001.\nWorld Bank, Armenia/Georgia Country Unit, Public Administration in Transition, September 1996.\nWorld Bank, Armenia/Georgia Country Unit, Public Expenditures in Armenia, November 1997.\nWorld Bank, Armenia/Georgia Country Unit, Armenia CAS, 2001.\nWorld Bank, ECA, Transition After a Decade, November 2000.\nWorld Bank and IMF (European II Department), Poverty Reduction, Growth, and Debt\nSustainability in Low-Income CIS Countries, February, 2002.\nWorld Bank, ECSPF, Armenia Targeted Financial Sector Review, June 2000.\nWorld Bank, LEGEC, Analysis of Public Awareness on Judicial Reforms, December, 1999- January\n2000.\nWorld Bank, OED, IDA Review of Private Sector Development, March 2001.
P051173 | Social Protection Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/778291475079806021/text/000020051-20140618081243.txt | http://documents.worldbank.org/curated/en/778291475079806021/pdf/000020051-20140618081243.pdf | 1. The implementation process will not proceed smoothly without the continuous commitment of both the Government and the implementing agencies throughout the life of the project. 2. Project performance benchmarks can be successfully used as leverage to foster counterpart commitment. For example, in 2004 the project become at risk to fail due to the Government's sudden reversal of pension policy. However, the Bank team was able to regain the Government's commitment to the reforms by placing certain actions and project performance benchmarks as conditionalities for the continuation of Bank support.3. The absence of a strong M&E framework with measurable indicators will hamper supervision of the project the because the link between outputs to outcomes cannot be established. 4. To ensure long-term sustainability of the social protection system the project design should address the problems of tax revenue system/policy framework in conjunction with building the capacity of the implementing agencies.
P051174 | Health Investment Fund Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/404591474489643941/text/000146597-20140617164715.txt | http://documents.worldbank.org/curated/en/404591474489643941/pdf/000146597-20140617164715.pdf | Tension can emerge between the goals of health care restructuring with an emphasis on the provision of primary care, on the one hand, and the emergence of a national health insurance scheme with a guaranteed package of basic benefits, on the other. As patients come to expect free health care under the latter, it is important to make sure that: (i) there is ample capacity developed in the PHC system to accommodate this demand; and (ii) there are financial and other incentives in place to support the development of the primary care sector. In the Moldovan case, physicians have sometimes been subject to demands for free care in an environment where they used to receive out-of-pocket payments for services, without systemically compensating them with higher salaries or other incentives.Because of the many stakeholders whose core interests can be threatened by restructuring, a clear and high-visibility communication and information dissemination strategy is essential for success.Creating an entity outside the MOH can facilitate the launching of reforms. The MOH can contain too many players with a vested interest in old strategies, procedures, and habits; a new vehicle is often a prerequisite for reform.The training, practice and financing of family doctors as part of a health reform program, is a lengthy process requiring sustained attention following initial design and implementation.
P051272 | NE-Priv Reg Reform (FY99) | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/761921475084575859/text/000020051-20140618060621.txt | http://documents.worldbank.org/curated/en/761921475084575859/pdf/000020051-20140618060621.pdf | The ICR has several good lessons, but one stands out. Privatization objectives and timetables should be realistic, taking into account a number of factors such as political ownership, country economic situation, market conditions and public opinion support.
P051273 | Health System Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/630581474850232592/text/000020051-20140615103308.txt | http://documents.worldbank.org/curated/en/630581474850232592/pdf/000020051-20140615103308.pdf | Pilot projects are inherently politically challenging, with commitment to them difficult to sustain. Pilots are also problematic in a complex sector like health, where the interrelated nature of all elements of the system makes it difficult to isolate a single unit for experimentation with reform.International technical assistance is often politically sensitive, and therefore its value must be demonstrated to high-level policy makers early and often. All TA is not of equal value, and careful consideration must be given to the appropriateness and longevity of impact of each activity.Components with clearly defined and compartmentalizable activities, as well as easily identifiable end-goals, are most likely to achieve universally-agreed-upon success. In this project, for example, it was very easy to identify when the pharmaceutical waste had been eliminated and under what conditions. By contrast, the development and implementation of systemic reforms is by nature an ongoing process with no â€œfinish line.â€Systemic changes, in particular for provider payment schemes, are the most difficult part of any health system reform, due to their complexity, the likelihood of unintended consequences, and political and bureaucratic resistance from existing institutional structures. For this reason, significant preparatory work is essential, including detailed planning and analysis as well as inclusion of the broadest possible array of stakeholders (including potential opponents who need to be co-opted).
P051306 | Peace and Development Project (1st Phase APL) | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2015 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/583121468186252058/text/ICRR14625-P051306-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/583121468186252058/pdf/ICRR14625-P051306-Box393183B-PUBLIC.pdf | The ICR presents the lessons learned comprehensively. Of those lessons, this review would highlight in particular:a)The benefits of having a learning approach to lending. This project benefited immensely from the Learning and Innovation Loans that tested and evaluated the approach to working with communities.b)The flexibility of a community driven approach in building assets in conflict areas. c)The need to address the challenges of working with other levels of government in decentralized projects.d) The utility of having a soundly designed and implemented impact evaluation of the efficacy of the project.
P051306 | Peace and Development Project (1st Phase APL) | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2015 | 2018 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/875351533645481102/text/127212-PPAR-P051306-P166612.txt | http://documents.worldbank.org/curated/en/875351533645481102/pdf/127212-PPAR-P051306-P166612.pdf | 7. Lessons â€¢ Identifying and supporting activities that create lasting shared interest among community members is a critical building block for generating a community response to conflict. In terms of project design, this finding calls for CDD projects that include an open menu of subprojects to be supported, and reliance on extensive consultations with beneficiaries to help identify those subprojects that glue communities together. â€¢ Having separate but similar activities for IDPs and host communities is not advisable in a CDD project since such separation deters social cohesion via competition for resources. Findings from the mid-term review carried out in May 2007 revealed that the original design of having similar but separate components for IDPs and host communities was generating tensions and animosity between them. In response to this problem, the World Bank team restructured the project by merging the component supporting host communities (component A) and the component supporting IDPs (component B) into one single component at the additional financing stage. â€¢ The support of a respected and neutral third party organization can be key for the successful implementation of a CDD project in a conflict-affected area. When the project was approved, the intensity of the conflict was high and, thus, the presence of government and project workers on the ground would have been risky since they were perceived as a party in the conflict. In the case of the PDP, partner organizations played a critical role since they brought deep contextual knowledge of social and conflict dynamics and the legitimacy and impartiality needed for maneuvering amidst armed groups. â€¢ Projects that seek to deter displacement may not necessarily reduce exposure to conflict since displacement can sometimes be the only option for citizens whose lives or livelihoods are severely threatened. Woven throughout the PDP theory of change is the assumption that increased social cohesion paired with socioeconomic stabilization can play a role in deterring displacement leading to a reduced risk of exposure to conflict. However, the connection between deterred displacement and reduced risk of exposure to conflict is not straightforward. â€¢ Socioeconomic stabilization and a strengthened social fabric can deter preventive displacement, but both are insufficient to deter reactive displacement which is driven by direct threats. IEG fieldwork and interviews with program staff confirm that the project could not deter displacement driven by direct threats (reactive displacement). However, the fieldwork indicates that the project played a role in deterring preventive displacement, which is driven by loss of livelihoods, the collapse of institutions and basic services, and the breakdown in social ties. Altogether, these latter factors trigger displacement at lower levels of personal risk (preventive displacement). â€¢ Projects with participatory approaches implemented in conflict-affected situations that elevate the role of community members can put them in harm's way and, for this reason, must include protocols to mitigate the risk of leaders suffering victimization acts. IEG did not find evidence of beneficiaries suffering victimization acts that can be directly attributed to project participation. However, fieldwork evidence indicates that project participation can raise the visibility of community members, and thus, make them more likely to suffer victimizations acts. Moreover, evaluation findings indicate that participation can also lower risk perceptions by beneficiaries. The IEG mission could not find evidence of standardized procedures for dealing with this potential risk.
P051309 | Community Works Project | Europe and Central Asia | Albania | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2003 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/364431475094944326/text/000020051-20140607173832.txt | http://documents.worldbank.org/curated/en/364431475094944326/pdf/000020051-20140607173832.pdf | The following lessons learned are applicable to future community works programs in Albania: -A new and higher set of financial limits on sub-projects is needed to overcome the limitations imposed by the present ones. These limits can reduce benefit-cost ratios and prevent sub-project optimization. For instance the cost of a main water-supply pipe may be under the limit but distribution pipes would put it over. The coordinated co-funding of larger projects between all donors and government is another possible solution.Development coordination becomes increasingly important as a country moves from emergency to development. For instance conflicting procurement procedures cause confusion and a large number of donor-specific audits represents repetitive effort that may be highly disruptive of regular operations. ADF should concentrate on infrastructure projects where it has a comparative advantage, and its primary role should be an executing agency at the service of the communal and municipal authorities. ADF's board needs more representation from communes, municipalities and the 12 Qarks to counter national political pressures, broaden accountability and prevent corruptions as well as allay suspicion of corrupt practices.
P051310 | Microcredit Project | Europe and Central Asia | Albania | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/558861474590777001/text/000020051-20140613084345.txt | http://documents.worldbank.org/curated/en/558861474590777001/pdf/000020051-20140613084345.pdf | The ICR review concurs with the lessons stated in the ICR itself. Two are highlighted here:1. Adequate financing needs to be secured up-front, particularly if the financing is needed to reach a critical mass for self-sufficiency.2. Building sustainable micro-finance institutions takes a longer time, even if preceded by earlier support for lending activities through a funding mechanism. While the later can facilitate initial outreach, the institutional and regulatory framework still needs to be developed and implemented, and different products introduced. The Bank should consider, as it has done in other cases (i.e. Madagascar), to continue providing strategic and technical support for the healthy growth of the created structures, until they are fully financially independent and have expanded their products and outreach further.
P051357 | SN ENERGY SEC. ADJ. | Western and Central Africa | Senegal | IDA |  | Infrastructure | Energy & Extractives | IDA | DPF | 1998 | 2002 | 2004 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/680311475072468129/text/000020051-20140612085309.txt | http://documents.worldbank.org/curated/en/680311475072468129/pdf/000020051-20140612085309.pdf | Three important lessons can be highlighted from the unsatisfactory outcome of this adjustment lending operation: (i) If during project supervision there is a change of government soon before or after privatization of a public enterprise, Bank staff and management should carry out an extra effort to ensure political ownership of the privatization by the new government. However, success is not always guaranteed: the effort was done in this case but it did not bear fruit.(ii) The Bank should acknowledge the high risks associated with disbursing adjustment money based on bringing a public enterprise "to point of sale" and consequently design further safeguards in case the privatization does not materialize in a sustainable manner. In this operation the Bank was left in the position to disburse in spite of having serious concerns about achieving the program objectives. In the end, the privatization did not occur.(iii) Bank management should balance better the incentives and resources allocated to project preparation/appraisal and project supervision. There is a tendency to put more incentives into project preparation/appraisal than in supervision, a situation that may have affected the supervision of this lending operation.
P051370 | Health 2 Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2005 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/354971474750612064/text/000020051-20140625195943.txt | http://documents.worldbank.org/curated/en/354971474750612064/pdf/000020051-20140625195943.pdf | The ICR identifies several lessons from the project (page 25). IEG observes two additional lessons from the preparation and implementation experience of the project: Partnership can come in many forms and have a strong impact on achieving a project's objectives. As shown in the discussion on efficiency (section 5), the World Bank worked closely with the Asian Development Bank, allowing each agency to specialize in certain areas to support the government's health program. Although this was not formally a joint project, this cooperation had many of the same characteristics as a joint projects and gave each partners many of the same advantages. At the same time, partnership carries risk. At the same time, as discussed in the ICR, informal partnerships have risks. One of the assumptions during project preparation was the availability of USAID-financed technical assistance. This support was cancelled after a dispute between the government and USAID.
P051372 | Health Sector Reform 2 Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2001 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/911981474898748115/text/000020051-20140617132944.txt | http://documents.worldbank.org/curated/en/911981474898748115/pdf/000020051-20140617132944.pdf | Effective and consistent M&E, where analytic results can be generated and disseminated rapidly and efficiently, are essential for building support for project activities in a politically contentious environment. Positive data and analysis on intermediate project outcomes can generate political support for further project activities.Reform of health care systems is inherently complex, and its impacts reverberate across sectors. In particular, budget and finance institutions must be convinced that the health sector should retain savings accrued through structural realignment.Successful institutional development is required for effective health sector reform in a transition country. In order for effective health finance mechanisms to take hold, health ministries must relinquish their payer/provider functions and instead become stewards and policy makers.
P051372 | Health Sector Reform 2 Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2001 | 2006 | 2008 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/494371468278087995/text/445130PPAR0P051sclosed0July02902008.txt | http://documents.worldbank.org/curated/en/494371468278087995/pdf/445130PPAR0P051sclosed0July02902008.pdf | 4. LESSONS FROM HEALTHSECTOR REFORM PROJECTSIAND I1 4.1 The political economy of health sector reform inevitably creates bothwinners and losers. Early and comprehensiveanticipation of stakeholder interests, institutional analysis to facilitate understandingof those interests, and the generationof a coherent plan to build support for reform and to persuade and/or Co-opt potentialopponents is essential. Eventhe most informed risk assessment and management, however, may not always guarantee success; heavily entrenched interests (inthis case, those defendingthe existing structure oftertiary facilities inBishkekand Osh) may prove extremelydifficult to overcome (Paragraphs 2.14-2.1 5, 3.24-3.29, 3.38). 4.2 The Bank should not, however,underestimatethe potential leveragewielded by its financingand expertise. The opposition to rationalization o fhealth facilities, for example, was fierce everywhere, butthe failure inBishkekand Osh should not overshadow the Bank's success inthe rest o fthe Kyrgyz Republic outside those two cities. The Bank's contributions interms o freform sequencing, technical inputs, and political positioning were instrumentalineffecting meaningful hospital rationalization across the country. On other issue areas as well, at several key points duringHealthI and 11,Bank interventions -rangingfrom the firm but positive persuasion o fthe President by a Country Manager with considerable expertise inthe health sector, to the threatened stick o f suspendeddisbursements and withdrawn IMF support -broke political logjams and movedthe reform process forward. Onthe other hand, the Bank mustexercisejudgment indecidingwhento insist on implementation ofthe initially agreed-upon reformprogram, andwhen instead to be more flexible and accommodating o fthe political environment. Explicit and early political risk analysis is essential to the effective development o fthis goodjudgment (Paragraphs 2.49, 3.29,3.30,3.88). 4.3 One effective mechanism for countering political resistance to reform i s strong and consistent M&E,where analytic results can b e generated and disseminated rapidly and effectively, buildingsupport for project activities in a politically contentious environment. Positive data and analysis on intermediate project outcomes can generate broad support for further project activities. Inthis case, the IssykKulregionhasbecome arecognized demonstration site whose successeshave prompted other regions to accelerate their participation inthe reforms (Paragraphs 2.23, 3.100). 4.4 Another important tool for overcoming political resistance to reform i s the cultivation and even creation of civil society organizations that give health professionals and users o fthe health care system a voice inthe decisionprocess and a clear sense o f affiliation and identity. Inother words, supportingpotential winners, and creating pathways to transform losers into winners, can be as important as overcoming or sidestepping recalcitrant losers. The creation inthe Kyrgyz case o fthe Family Group Practice Association andrelated organizations demonstrates the potential long-term impact o f institutional development investments that may at first seem unsustainable or risky (Paragraphs 2.14,2.27). 4.5 The complexity of health care systems dictates that reforms b e carefully sequenced. Inthis case, capacity buildinginthe primary care sector through the family medicine and other primary care reforms was a precondition for hospital rationalization; revenue gains from financing and service delivery reforms made possible the later benefits package and Co-payment schemes; and the changes inrevenue collection and pooling were necessary prerequisites to the introduction o f new purchasingarrangements (Paragraphs 2.7,2.12,2.25, 3.55). 4.6 Tradeoffs between efficiency, equity/access, and quality of care will not be addressed in the absence of explicit and consistent attention to the balance between them and interventions to correct imbalances. Gains inefficiency do not automatically translate into improvements inequity; infact, the opposite may be true if there is not sufficient tracking and analysis o f inequities. The clear emphasis inHealth I and I1was on achievements inefficiency; although there were equity andaccess objectives inboth projects, and some evidence to indicate that progress was made inthis area, the bulk o fthe project's major activities and indicators focused on efficiency-related goals. Itmay be argued, however, that this point illustrates the earlier lesson on sequencing\. given limitedpublic financing for health care, enhanced efficiency may be seen as an essential prerequisite for meaningfulefforts toward (and adequate resources for) increased equity and access (Paragraphs 2.34,2.39). 4.7 Targeted interventions to improve clinical quality can demonstrably impact health outcomes. Inthe Kyrgyz case, the Bank's efforts to improve the quality and use o f clinical practice guidelinesfor highblood pressure have measurably reduced the incidence o f heart disease (Paragraph 3.69). While the direct impact o f immunization or nutrition interventions, which impact health risks more immediately, may be more easily measured, it i s reasonable and shouldbe expected that health systems interventionscan similarly affect health outcomes. 4.8 The presence of a clear sector strategy, authored andwholly owned by the MOH,can play a key role inachieving donor harmonization. Inthe Kyrgyzcase, the MOH's role as a leader and coordinator o f donor activity, inpartnership withthe Bank, has been central. Longevity and consistency o f donor support, along with clear division of labor among donors, i s also essential inanenvironment where donor presence i s strong. Itpreventsneedless duplication o f activity, assigns donors to activities best suited to their comparative advantages, and ensuresthat there is appropriate donor activity across all issue areas (Paragraphs 2.5,2.43,2.47,2.51, 3.5-3.6,3.20, 3.76). 4.9 Improved efficiency may result in the reallocation of public funds to other sectors, reducing the incentives for continued reform. Inthe Kyrgyz case, duringthe second project the government responded to the efficiency gains inthe health sector ina classic Soviet manner\. if input requirements decline, thenpublic funds should decline. This stealing of conserved resources from the health sector diminishedenthusiasm for the reforms andreduced the incentive to persist and deepen downsizing efforts. The input-based budgetingprocess punished the health sector for rightsizing health infrastructure and personnel. The introduction o f formal Co-payments had a similar crowd-out effect on public spending. It is therefore necessaryto negotiate proactively with ministries of finance and legislatures on the disposition of proceeds from efficiency gains (Paragraphs 3.31,3.87). The Bankdoes not always speak with one voice inthis area. Some Bank constituencies continue to pushfor reforms like increased budgetary flexibility for hospitals (including residual claimant status for small extrabudgetary income from user fees), while others stress the importance of strict input controls and of reflecting all revenue sources inthe treasury system. It is therefore importantto sustain dialogue onthis issue withinthe Bankitself. 4.10 Some elements of health sector reform can have spillover effects, leading to improvements in governance and accountability practices in other sectors. For example, modernizationinthe way that drugs are procuredhas benefits for all public procurement. Donors agree that success inthis area has met or surpassedthe expectations of all involved; health reforms have begunto improve the overall governance o fthe country, and the education sector and chamber o f accounts have begun (albeit ina preliminarymanner)to discuss transitioning to the use of internationallyaccepted procedures for procurement, financial management, and audit. 4.11 A variety of lessons from the experience o fHealthIand 11, andthe implementationo fthe Manas Iprogram, were explicitly applied to the development o f follow-on activities\. the Manas Taalimihealth reform program, and the sector-wide approach through which Manas Taalimi is being implemented (box 4.1). These include the needto synchronize the financing base and budget formulation and execution systems with healthreforms, so that healthproviders can retain and allocate funds saved through rationalization o fhealth infrastructureand healthbudgetscan be formed according to output-based formulas; a focus on governance, acknowledging the institutionaltransformationo fthe M O Hby investing heavily instewardship functions such as M&Eand stressing transparency and accountability inthe health sector; a commitment to deepen the rightsizing ofthe health sector and completing the process o f structural reform inBishkek and Osh cities, where the process remains incomplete; and stress on donor coordination, acknowledging that the highly successful informal collaboration supporting Manas Ishould be sustained through an explicit, Governmentdirected Programo f Work and through periodic, formal, structured meetings for sector monitoring anddonor coordination. The attentionto transparency is particularly important giventhe acknowledged extent o f corruption inthe public sector; the follow-on activities put special emphasis on disclosure and transparency and on strengthened complaint handingmechanisms coupled with specific remedial measures. Box 4.1\. Manas Taalimi Health ReformProgram The Manas Taalimi Health Reform Program was developed in2005 by the MOH as a successor to the Manas strategy. It i s an extension o fthe health goals embedded inthe 2002 National Poverty Reduction Strategy and Comprehensive Development Framework. The objective o f the Manas Taalimi program is, broadly, to improve health status through the creation o f an effective, comprehensive, and integrated delivery system o f individual and public health services, and through increased responsibility o f every citizen, family, society, and public administration bodies for the health o f each person and for society as a whole. It explicitly aims to institutionalize the reforms initiated under Manas Iand to strengthen the parts o fthe health care system that were relatively less emphasized under the earlier strategyeaInparticular, it seeks to strengthen the targeting o fresources and interventions at groups with worse health outcomes, including MDG outcomes; implement structural improvements inthe public health and health promotion systems; enhance capacity inthe MOHand other relevant institutions inpolicy formulation, priority setting, policy-based budget planning, and monitoring and evaluation; and strengthen quality o f care with a focus on priority health problems including maternal and child health, cardiovascular disease, respiratory illnesses, HIV/AIDS, and TB. Manas Taalimi was developed and refined inan open and transparent manner through extensive stakeholder consultation, including town hall meetings throughout the country, consultations with senior government officials, and numerous formal and informal consultations with health sector donors although it shouldbe stressed that the core strategy and ProgramofWork were developedby the Government through a genuinely indigenous process. The Government gave extended leave to fifteen key health specialists from the MOH, MOF, MHIF, SES, and other institutions to work on the strategy, providing reentry guarantees to their original posts once the strategy was finished. The preparation o f Manas Taalimi thus overcame any accumulatednegative experience and mistrust, evolving not only a consensus-based technical process, but also a process inwhich the players knew and understood one another's personalities, institutional constraints, and motivations. a. The name Manas Taalimi is significant\. Manas i s the Kyrgyz national hero, and it was considered desirable to keep that name for the sake o f continuity with the prior health reform program. Taalimi is an ancient Kyrgyz word signifyinga vast sense o f heritage and legacy. The name Manas Taalimi therefore stresses the extent to which this reform program i s explicitly based on the lessons learned from Manas I.
P051386 | SZOPAD SOCIAL FUND | East Asia and Pacific | Philippines | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/546241474898210697/text/000020051-20140612084544.txt | http://documents.worldbank.org/curated/en/546241474898210697/pdf/000020051-20140612084544.pdf | A social fund is an effective instrument for providing immediate basic infrastructure and short-term employment opportunities in post conflict situations. Community level capacity building interventions and organizational development and strengthening during the early stage of subproject implementation are critical for subsequaent O&M.It is important to have a clear beneficiary targeting mechanism, procedures for procurement, financial management and disbursement for efficient resource utilization.
P051418 | Health Sector Management Project | Europe and Central Asia | Slovenia |  |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/358261474491930278/text/000020051-20140613041029.txt | http://documents.worldbank.org/curated/en/358261474491930278/pdf/000020051-20140613041029.pdf | When there is likely to be resistance to project supported reforms, project design should provide for consulting the views of difficult stakeholders and marketing the reforms to them. In the case of this project, consultation with IPH and HIIS at the outset, would have lessened their resistance. When the project management and support team is from the key counterpart agency (in this case MOH), it allows for complete synergy between the work of the MOH and the project. Project funds were used effectively and project initiated reforms have greater likelihood of sustainability as they are endorsed in MOH policy documents and legal frameworks.In the absence of a supportive legal framework, the implementation of an integrated information system is difficult when certain stakeholders perceive information as a source of power and control. Upfront, project design should devote adequate resources to understanding the legal, institutional and political constraints to implementing such a system.
P051553 | THREE CITIES SANITATION PROJECT | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2008 | 2010 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/324241474492176816/text/000146597-20140619161633.txt | http://documents.worldbank.org/curated/en/324241474492176816/pdf/000146597-20140619161633.pdf | Care should be taken to ensure that PDOs are appropriate and practical, measurable and attributable to the project, and are the same in the PAD as in the DCA. If, after some project implementation, it is clear that they are not, the steps to formally revise them should be taken.When trying to achieve cost recovery the following should be seriously considered: the slow pace of related legal changes, the willingness of local agencies, and risks of a slowdown in the economy. Future projects should consider working with the Government to include house connections as part of the civil works. Slow uptake of house connections by households in the project areas reduced the efficacy of the sewerage system installed under this project. Projects working at a sub-national level need to address the issue of protracted delays in the approval of contracts, compensation and site clearances. Approval authority should devolve to the local governments.There is a need to ensure some design capacity in construction management (CM) teams. The frequent need for design changes in the field due to unforeseen circumstances requires some capacity in the CM teams to propose design changes so that they do not have to resort to engineering consultants. The valuable lessons on building the capability and services of sanitation and drainage companies should be captured in a systematic manner to guide future projects.
P051553 | THREE CITIES SANITATION PROJECT | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2008 | 2012 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/443761468320111731/text/682260PPAR0P050ite0Cover0Box369247B.txt | http://documents.worldbank.org/curated/en/443761468320111731/pdf/682260PPAR0P050ite0Cover0Box369247B.pdf | Lessons of the Investment Project â€¢ While good project design makes the links between project interventions and outcomes explicit through a results-chain, the rationale for attribution should have a sound theoretical foundation and appropriate performance indicators should be identified. Urban infrastructure investments in sanitation and drainage such as this project's can produce outputs that contribute to generalized project objectives such as reduced environmental pollution and flooding, but the links can be complex and difficult to monitor. Achievements can only be accurately measured when baselines are clear and data is current on all relevant performance indicators. â€¢ The project showed that urban households were satisfied with the septic tanks provided, regarding them as adequate final solutions to their sanitation needs, making connections to local sewer networks appear unnecessary to these households. As Vietnam continues to urbanize rapidly, sector specialists will need to monitor how well the household septic tank solution continues to perform with increasing urban densities. At the same time, the specialists would need to identify the incentives that households might need to eventually move to systemic solutions for urban sanitation. â€¢ In low-lying coastal and riverine cities vulnerable to floods, natural disasters and environmental pollution, as are most of Vietnam's, investment and O&M of urban infrastructure can be very expensive. Financing must be assured, usually government funding for investment and cost recovery from users for part of O&M.
P051564 | SOUTHERN AREA WATER AND SANITATION IMPROVEMENT PROJECT | Middle East and North Africa | West Bank and Gaza |  | FCS | Sustainable Development | Water | SPF | IPF | 1999 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/462931475094757817/text/000020051-20140615111950.txt | http://documents.worldbank.org/curated/en/462931475094757817/pdf/000020051-20140615111950.pdf | If project components are substantially changed to the extent that they undercut achievement of project objectives then formal restructuring of the project should be undertaken. Failure to do in a situation of force majeur is unrealistic. It provides a high risk that project outcome will be rated unsatisfactory even when project achievements may be outstanding given the changed operating and political environment. Successful contracts for utility management by independent operators require political stability and good governance. Where there is a risk that neither condition will last alternative approaches at institutional upgrading and reform that are more robust in a risky environment should be considered.Incentive payments to independent operators and local technical staff need to be very carefully constructed and in full consultation with local stakeholders. Failure to do so may create moral hazards and perverse incentives. In this particular project, the operator focused primarily on bonus-related activities and neglected organizational restructuring, training, and emergency planning. And for individual local staff bonus payment came to be seen as an entitlement that did not need to be justified by superior performance.
P051602 | Private Industry Recovery Project | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2003 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/303011475100518020/text/000020051-20140612151858.txt | http://documents.worldbank.org/curated/en/303011475100518020/pdf/000020051-20140612151858.pdf | Commitment to macroeconomic stability and structural reform can help reduce political risks and, as a result, the demand for political risk guarantees, making it unnecessary to maintain organizations set up especially to insure those risks.
P051609 | SN-Priv Inv Promotion SIL (FY03) | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2003 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/668201474944545643/text/000020051-20140625231409.txt | http://documents.worldbank.org/curated/en/668201474944545643/pdf/000020051-20140625231409.pdf | The following lessons are taken from the ICR with some adaptation:Consensus with the stakeholders on the content of project activities is critical to ensure ownership and successful implementation of the project(refer to 3rd bullet in section 8 (a)).Project supervision requires close oversight and active decision-making from the management in light of early warning signals i.e., the task team and management should be more proactive by restructuring the project at an early stage in order to maximize its impact (refer to 3rd bullet in section 8 (b)).Capacity of the implementing agencies should be thoroughly assessed prior to project approval or effectiveness (refer to bullet points 1 to 4 in section 9 (b)).Adequate M&E framework and impact evaluation mechanisms should be institutionalized at project inception (refer to sections 10 (a) and (b)).Steering committee composition should be balanced and inclusive, and benefit from high level representatives able to influence and/or accelerate decision-making (refer to bullet 4 in section 9 (b)).
P051610 | Senegal:AG.EXPORT PROMOTION | Western and Central Africa | Senegal | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/801311474512036652/text/000020051-20140613032824.txt | http://documents.worldbank.org/curated/en/801311474512036652/pdf/000020051-20140613032824.pdf | Technical assistance with hands-on experience of the relevant international markets, is an effective means of providing the demonstration efforts necessary to develop viable systems for activities such as the export of high-value, perishable crops. Working with the different parties involved to resolve issues, especially when the parties have different views on something that they all desire, in this case basic infrastructure, is likely to be most effective in moving towards an operational situation that is stronger overall with greater buy-in by all parties, than if a solution had been dictated from above. The standard four-five year credit implementation period is often too short to build sustainable institutional capacity. But it may be better to have the potential for a follow-on operation so that the first operation can be kept short to provide some pressure to complete activities.
P051693 | AR P.RFM(SALTA) | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/581831474629565024/text/000020051-20140529074604.txt | http://documents.worldbank.org/curated/en/581831474629565024/pdf/000020051-20140529074604.pdf | Quick-disbursing loans can serve as an important inducement for reluctant governments to introduce fundamental reforms.
P051694 | P.RFM(S.JUAN) | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2002 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/125871474484352500/text/000020051-20140604050034.txt | http://documents.worldbank.org/curated/en/125871474484352500/pdf/000020051-20140604050034.pdf | (1) Reforms of social sector expenditure need to be supported by a broad outreach program if they are to gain popular acceptance. One step in this direction would be to formulate a national reform program within which state initiatives can be implemented. (2) Sequencing is important. There may be more scope to achieve successful and sustainable social sector reforms if they are pursued after fiscal reforms have been achieved. (3) Loan disbursements should at least roughly be in step with the pace of reforms they are supporting. In this case, projected loan disbursement of 12 months was much too short of the 3-4 year reform program it was supporting. (3) Loans to support such reforms should be fully informed by social and institutional assessments and impact analysis.
P051694 | P.RFM(S.JUAN) | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2009 | PPAR | >=25 million & <50 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/323551468220163744/text/489850PPAR0Arg1IC0Disclosed07121091.txt | http://documents.worldbank.org/curated/en/323551468220163744/pdf/489850PPAR0Arg1IC0Disclosed07121091.pdf | 6. Conclusion and Lessons 6.1 This chapter discusses two issues that cut across iLLe operations\. first, the question o f whether, as a result o f the crisis, the design and restructuring o f the PRL-I11 operations supported weaker reforms that would have been supported otherwise, and the lessons that can be extracted from their implementation. Did the crisis prompt resource transfers against weaker reforms than would have been supported otherwise? 6.2 This question can be posed in the two steps o f the PRL-I11 operations in which the reforms that the loans supported were defined\. during their design and during their restructuring. Regarding the design o f the loans, this PPAR answers the question by analyzing the history o f the P R L operations in Argentina, including the way they fitted within the country assistance strategy, their objectives and the thoroughness o f their design. To answer the second aspect o f the question, the report examines the process o f loan redesign from 2002 to 2003, and the consistency between the reforms supported by the redesigned loans and their original objectives. THEDESIGN OF THE OPERATIONS 6.3 I t i s clear that the PRL-I11 loans were part o f the efforts that the Bank, along with the rest o f the international financial community, was making in 1999-200 1 t o help Argentina stem the incoming crisis. It i s also clear that the two objectives o f the operations-to improve the provincial governments' ability to deliver social services while improving their fiscal situation--coincided exactly with the policies that the government was pursuing regarding the provinces in its attempts to stave o f f the crisis. Further, the design o f the operations as fast-disbursing ones facilitated the rapid transfer o f resources under critical circumstances-in fact they were disbursed very close t o the collapse o f the currency board. All these facts seem to lend credence to the idea that the loans were just part o f the ultimately failed efforts to avert the collapse o f the currency board. 6.4 Yet, the PRL-I11operations were not improvised vehicles hastily designed t o help in an urgent macroeconomic stabilization effort. O n the contrary, their objectives had been part o f the strategies o f the government and the Bank throughout the 1980s and the 1990s. They were reasonable operations with worthy objectives that proved very important for the long-term stability o f the country. Moreover, the outcomes o f the operations, which was at least Moderately Satisfactory in the three PRL-I11 (as rated by the I C R and t h i s report), belie the idea that the structural reforms dimension o f the operations was neglected. Finally, the fact that the first disbursements o f t w o o f the three PRL-I11 operations were delayed for almost one year until the provincial governments complied with the loan conditionalities indicates that the Bank was giving first priority to meeting the objectives o f the structural reforms rather than to transferring the resources urgently. Still, even though the operations were reasonable and well designed, disbursing so close to the collapse o f the currency board could be judged negatively. However, the Bank could not legally stop disbursements if the borrower had complied with all the established conditions for disbursement-which was the case o f the PRL-111. 6.5 Thus, to the question o f whether the PRL-I11 operations were just excuses to transfer resources to Argentina during the 2001 crisis, this report answers no. They were bona fide structural reform operations and they were designed as such. RESTRUCTURINGS THELOAN 6.6 Regarding the quality o f the conditionality o f the conditionality that replaced the original one as a result o f the 2003 restructuring, the experience in the PRL-I11operations was mixed. In some instances substantive actions that should have been taken by the government were replaced with the completion o f studies. This happened in all three PRL-I11 loans. Yet, in the most important instances restructuring adapted the actions needed to attain the loans objectives to the new circumstances prevailing after the crisis. This was the case, for example, o f the modification o f the privatization conditions in the three PRL-I11operations. Certainly, the measures that became the restructured conditions (mostly mimicking administrative measures that private operators would have undertaken) were second best actions; the fact, however, was that the first best conditions were unattainable. Even more substantially, in Catamarca the condition regarding the provincial bank was changed from privatization to liquidation, a politically difficult condition that the province implemented. 6.7 Thus, while there were some cases o f watering down o f conditions, with respect to the most important objectives the restructuring represented an adjustment t o a change in circumstances. Lessons (1) I t is possible to attain satisfactory results in provincial structural adjustment reform and operations even in extremely difficult conditions. 6.8 The first lesson answers the basic question posed to t h i s PPAR. The three PRLI11 operations evaluated in this report were carried out under extremely difficult macroeconomic conditions; still, they had outcomes that were at least Moderately Satisfactory; risks to development outcomes that were uniformly Moderate and Bank and borrower performances that were either Moderately Satisfactory or Satisfactory. In fact, the only unsatisfactory operation-the San Juan loan-was implemented under favorable macroeconomic conditions. This shows that the macroeconomic condition o f the country was not the crucial factor determining the success o f the operations. 6.9 This lesson contradicts one drawn by the I C R o f the Santa Fe PRL, which states the following\. Provincial policy development operations such as Santa Fe's P R L are only appropriate under stable macroeconomic conditions. While this type o f operation requires an overall satisfactory macroeconomic policy framework, such framework is the responsibility o f the national government and beyond the sphere o f action o f provincial authorities. As illustrated by the experience o f Argentina's last series o f PRLs, including that o f Santa Fe, failings or uncertainties at the macroeconomic level can override substantial achievements at the provincial level, leading to loan cancellation. 6.10 Reading this lesson in isolation would give the impression that the Santa Fe operation had been rated Unsatisfactory by the ICR. Yet, the I C R rated the outcome o f the Santa Fe operation Moderately Satisfactory, clearly contradicting the idea that these operations cannot produce satisfactory outcomes in difficult circumstances. Moreover, the same I C R further contradicts such idea in yet another lesson, with the following words\. The Bank's continuous engagement during critical periods can help sustain ongoing reforms and protect previous achievements. The experience o f Santa Fe's PRL, indicates it was beneficial to have an operation in place providing a clear roadmap for enhancing service delivery in key social sectors during times o f economic, political and institutional chaos. The substantial financial resources attached to the PRL became even more attractive in face o f the overall lack o f liquidity in the country in 2001-2002, providing the province additional incentives t o sustain the ongoing reforms in the short and medium term. The experience o f Santa Fe's P R L also shows that sector reforms are possible even when the overriding priority i s fiscal adjustment; however, sector budgets need to be protected, in particular to ensure that cost savings from efficiency gains can be reinvested into the sector. 6.1 1 In the opinion o f this PPAR, this lesson, which clearly supports the idea that provincial reform loans can be satisfactory even in very difficult conditions, can be applied to all the reviewed PRL-I11 operations. O f course, it would be better t o have stable economic conditions for any Bank operation; yet, even if a country i s in situations as unstable as that o f Argentina in 2001-2002, operations aimed at supporting important objectives in terms o f fiscal stability and the delivery o f social services can be extremely useful if properly designed and owned by the borrowers. 6.12 Moreover, structural adjustment operations may be highly desirable in cases o f macroeconomic instability if-as was the case with the PRL-I11loans-they were aimed at resolving macroeconomic imbalances and improving the delivery o f social services, both o f which tend t o deteriorate in unstable macroeconomic situations. (2) The sub-national approach may be optimal to deal with the improvement and protection of social services in times of crisis in cases where such services are decentralized to the provinces. 6.13 Prior to the P E S , the volume o f resources available for social services, mostly based o n transfers from the federal government, had been highly unreliable because social expenditures were frequently adjusted to accommodate fiscal needs at the federal level. Furthermore, the volume and quality o f the services afforded by these resources were diminished by substantial inefficiencies at the provincial level. By helping Argentina to institutionalize the transfers under a predictable system as well as by helping the provinces to increase the efficiency o f their social services delivery, the PRL-I11 operations effectively protected such delivery much beyond what could have been attained with operations at the national level. (3) Good economic and sector work and close relationship between the supervision teams, the country office, and the borrower are key factors contributing to the success of operations. 6.14 The fact that PRL-I11 was able to produce three loans that were rated at least Moderately Satisfactory in the midst o f a catastrophic environment i s largely attributable to the long and conscientious preparation o f the PRL series, which in turn was based o n solid economic and sector work as well as in the experiences with the previous PRL operations in Argentina. 6.15 The results were also favorably influenced by the quality o f the Bank supervision. Development policy operations pose a challenge in terms o f supervision even under normal circumstances. This challenge was much greater in the case o f the PRLs given the extraordinary economic and political circumstances o f the 2001-2002 crises. The supervision teams forged close relationships with the provincial authorities, and helped in designing solutions for implementation problems, as well as provided efficient coordination with different networks in the Bank. Through their continuous contact, these teams and the country office helped to maintain the commitment o f the provincial governments to the reforms as well as to find solutions to problems encountered during the implementation o f the loans. Also, in most cases, the Bank adjusted the conditions regarding some reforms that became unfeasible as a result o f the macroeconomic crisis .in fully satisfactory ways or in acceptable second best ways. (4) Large numbers o f conditions render the supervision and evaluation o f operations difficult, particularly if the conditions are not prioritized. 6.16 The reviewed operations had 272 conditions before the 2003 restructuring. Just the three PRL-I11operations had 256. Certainly, some o f these conditions were crucial strategically while others were just preconditions to attain the crucial ones, or less important complements to them. Nonetheless, the large number o f non-prioritized conditions creates severe problems in the implementation o f the loans, in their supervision, in the authorization o f disbursements, and in evaluation. In fact, the evaluation o f some o f the operations could be significantly different if priorities had been established at the time o f appraisal. 6.17 For example, this PPAR rated the outcome o f the Catamarca PRL Moderately Satisfactory (and not Satisfactory or Highly Satisfactory) because it failed in some educational reforms. T h i s rating may underestimate the performance o f Catamarca, which, for example, was able to liquidate the provincial bank when it failed to privatize it. This was a feat that the more developed Cordoba could not or was not willing to do. The Catamarca government also concessionedthe water company, while neither Cordoba nor Santa Fe was able to fmd a comparable solution when they also failed to privatize their energy companies. Inthe absence o f prioritization o f the loan components in the PRLs, it is impossible to compare these achievements with the creation o f a system to track cost recovery in hospitals, or the creation o f new criteria for the licensing o f physicians. (5) The idea that provinces should increase their tax collections as a presumptive objective should be subject to scrutiny, as that objective needs to be balanced with other objectives such as the efficiency of taxation and the need to improve the business environment, depending on the situation. 6.18 The PRLs assumed that increasing the share o f own-resources in total provincial revenues was a desirable objective. This, however, i s not necessarily always the case. There are two instances in which reducing the share o f local taxes could be optimal. The first one i s when national taxes are more economically efficient (they cause lesser distortions) or cheaper t o collect than provincial ones at the margin. In this case, the optimal taxation policy would be to raise all taxes nationally and then allocate them to the provinces. This principle was applied in Cordoba and Santa Feywhere the governments reduced their respective tax revenues by eliminating distorting taxes. The second i s when the reduction o f taxes reduces the cost o f doing business, such as in the case o f Cordoba. In this instance, although the eliminated taxes were efficient, their elimination was optimal because the private sector could allocate the liberated resources better than the government. In sum, increasing the share o f local taxation could be optimal or not, depending o n the circumstances. B o t h Cordoba and Santa Fe were correct in eliminating distorting taxes, meeting one o f the conditions o f the loan, even if they then failed to comply with the objective o f increasing their own tax collections-particularly because after that they attained fiscal surpluses. (6) Political feasibility of reforms must be a factor in the evaluation of new operations 6.19 The contrast between the generally satisfactory outcome o f the PRL-I11loans in the midst o f a serious macroeconomic crisis and the highly unsatisfactory one o f the San Juan PRL-I1 loan within normal macro circumstances illustrates the limits that politics may set for the effectiveness o f Bank operations. The factor that led to the highly unsatisfactory outcome o f the San Juan operation was the government's inability to overcome the political resistance against a measure that would have been extremely controversial almost anywhere\. reducing the salaries o f the teachers. This resistance provoked widespread fiscal and political failure. The PRL-I11operations, which focused on less politically controversial objectives, were more successful overall. The unsatisfactory educational outcome o f the PRL-I11 Catamarca operation was also related to the political obstacles found in that area. This experience suggests that political economy considerations should be taken into account in the design o f loans. O f course, assessing the political feasibility o f reforms is more o f an art than a science. Yet, there are some cases, as it in San Juan, in which reforms are clearly too risky because they include measures that could be perceived as too radical or illegitimate by significant portions ofthe population.' ' It should be noted that the reduction in salaries was not part o f the conditionality o f the San Juan loan. The provincial government reduced those salaries in 1995, two years before the approval o f the loan, as part o f i t s own program o f reforms. The reduction, however, caused a backlash that eventually destroyed the reforms program that the loan supported. (7) The benefits of Bank operations can be substantially enhanced through a flexible approach to reforms 6.20 The provincial governments and the Bank took a flexible approach to the operations that greatly enhanced their ability to help Argentina t o meet their original objectives while accommodating the economic crisis. While, as acknowledged in the previous section, some o f the restructured conditions o f the PRL-I11operations watered down the initial objectives o f the loans, most o f them did meet those objectives, or some second best, through other means when the original ones became unfeasible. Moreover, the Bank showed additional flexibility by accommodating different adjustments in different provinces. In this way, for example, when privatization o f the provincial bank became impossible, Catamarca liquidated it while Cordoba opted for hiring professional bankers while instructing them to mimic private administrative rules in managing it. Catamarca concessioned its water company while Santa F e and Cordoba rationalized the management o f their electricity companies. W h i l e the outcomes o f the restructured measures tend to fall short o f the original objectives, they represent substantial improvements relative to the original conditions.
P051695 | P.RFM(R.NEGRO) | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1998 | 2000 | 2002 | ICRR | >=50 million & <100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/292601474555061719/text/000020051-20140604050358.txt | http://documents.worldbank.org/curated/en/292601474555061719/pdf/000020051-20140604050358.pdf | 1. Provincial governments may need to rely on a national framework for reform, and, in this case, governors needed to be seen to be carrying out fiscal reforms within a clear national program for reform. Public support for reforms at the provincial level can be undermined if it is thought that the national government might reverse some progress made at the provincial level. In the case of Rio Negro, the population thought that the national government might loosen the fiscal constraints faced by the province, thereby undercutting popular support for fiscal reforms. 2. Lending vehicles need to be synchronized carefully with the reforms they are supported. The disbursement profile of this project was too short to support the wide-ranging reforms it sought to support. 3. The formulation of effective reforms at the provincial level needs to be informed by Institutional and Social Assessments. 4. Clear output indicators as contained in this project documentation (including the ICR) are central to effective evaluation.
P051696 | Sao Paulo Metro Line 4 Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/692971474577575098/text/000020051-20140625200029.txt | http://documents.worldbank.org/curated/en/692971474577575098/pdf/000020051-20140625200029.pdf | The ICR has identified a number of specific lessons in relation to PPPs and the most important ones are listed below:For any PPP, regulatory commissions and strong supervision by the State or its representative is needed during construction and operation. A formal agency should be given a clear mandate or established early enough to ensure that it is properly staffed. The agency must be considered sufficiently independent and credible to conduct its duty.PPP contracts must have very stiff penalties for delays in construction as well as bonus for earlier completion. They must also have very stiff penalties for non-compliance during operations and key performance indicators must be carefully designed and enforced.When a turnkey is used, mechanisms to handle changes in the project design, either requested by the State or in view of unanticipated geological or construction reasons, must be clearly defined between the parties. This will ultimately protect public interest and facilitate the acceptance of these changes by overseeing Accounts Tribunals.
P051701 | Rural Poverty Alleviation - Maranhao | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/167621474560496993/text/000020051-20140613035046.txt | http://documents.worldbank.org/curated/en/167621474560496993/pdf/000020051-20140613035046.pdf | Based on the ICR the key lessons are: (i) Community-driven approaches can reduce bureaucratic and administrative obstacles by reducing the distance between decision-makers and beneficiaries. However not all the challenges in implementing such approaches can be visualized upfront. Hence the importance of an efficient monitoring and evaluation system to report on both quantitative and qualitative goals is essential. (ii) Though community-based organizations can provide a viable option for carrying out small scale civil works, adequate assessment of the costs and benefits of undertaking these investments to the Bank, the Borrower and the communities is essential before these investments are scaled up. (iii) Even the most sophisticated poverty targeting strategies can be difficult to implement because of political pressures, data limitations and lack of easy accessibility of communities.
P051705 | Second Fujian Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1999 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/605981475097193894/text/000020051-20140618085659.txt | http://documents.worldbank.org/curated/en/605981475097193894/pdf/000020051-20140618085659.pdf | The ICR has a useful discussion on the lessons learned. Paragraphs 2 and 3, summarized below, reach provocative conclusions and, without IEG endorsement as lessons from the project, they are proposed for investigation because of their significance in China and elsewhere (see Section 14). 1. Taking past lessons into account is essential during project preparation. Measures included related to engineering designs, bid documents, and quality control during construction were appropriate and contributed to reducing problems that had happened in past projects. In the future the scope of design oversight needs to cover also land acquisition, resettlement and geotechnical investigations. Better initial assessments and investigations would permit a more accurate budgeting of expenses for resettlement and geotechnical works to ensure that funds were available when needed.The ICR also states two other lessons learned which are controversial--but important-and are proposed for study in Section 14 without endorsing them as lessons.2. Description of project objectives is especially complex for institutional objectives. Institutional changes are long-term endeavors and it is difficult to define what can be achieved within the project time frame. Project designers need to be careful that objectives are realistic and avoid vagueness, otherwise it is implicitly suggested that nothing or little of substance could be achieved. The lesson (proposed in the ICR) is that a project should not contain an objective where strong doubts exist at the appraisal stage and the objective should be defined with measurable targets, which (in this project) could have been established. 3. Financial return on toll roads should not be stressed, as it runs counter economic efficiency. Drivers increasingly understand the advantages of using modern roads and are willing to pay for it. Yet, often they do not fully internalize the cost of driving on congested or bad roads, and therefore the willingness to pay to use a modern tolled expressway is but a fraction of the savings from diversion from a free but poor or congested road. The lesson (proposed in the ICR) is that, at least initially, the toll rate needs to be set a sufficiently low level to avoid deterring many potential users of the expressway, which could severely lower the economic return of the expressway investment.
P051736 | CN-E. China (Jiangsu) Power Transmission | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/292451475073922583/text/000020051-20140615113715.txt | http://documents.worldbank.org/curated/en/292451475073922583/pdf/000020051-20140615113715.pdf | Two of the three lessons pointed out in the ICR are appropriate: Â· The importance of long term planning to ensure sound investment decisions, while obvious, was underscored in this case by ECGCâ€™s and JEPCâ€™s initial reluctance to invest enough. Bank recommended and financed studies convinced them to schedule the investments required not only to complete the Bank project but also to meet surging power demand in the Region.Â· The need for better qualification specifications and more attention to the trade off between price and quality in the light of the problems which arose with the Yangtze River Crossing component. The fault lies with the Bank which insisted on awarding the contract to the lowest bidder despite the Borrowerâ€™s misgivings. Regarding the third lesson in the ICR -- the need to avoid rigid and Bank mandated reform programs -- it is unclear from the text why this was considered important for this particular project.
P051741 | Second Health Sector Support Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/804391474481310865/text/000020051-20140619075406.txt | http://documents.worldbank.org/curated/en/804391474481310865/pdf/000020051-20140619075406.pdf | Flexibility within a Bank-financed operation can be critical for rapidly and effectively mitigating the adverse effects of unanticipated crises. However, such flexibility needs to be reflected in a revised M&E framework. Rehabilitation/reconstruction of health facilities, rather than building new facilities, and allowing the Global Fund to assume the grant financing of priority disease programs made sense. But these were not reflected in the M&E framework, which still included indicators to increase geographic coverage and to measure outcomes of infectious disease programs.Utilization of facilities is not likely to increase as desired if the underlying reasons for low utilization are not assessed and addressed. In Madagascar, because of very difficult roads and mountainous terrain, living within 5 km of a health facility does not guarantee physical access. Furthermore, inability to pay for drugs and services is likely to continue to depress utilization if it is not addressed.
P051838 | VN-PRIMARY TEACHER DEVELOPMENT | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2002 | 2007 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/473211475098171965/text/000020051-20140619074014.txt | http://documents.worldbank.org/curated/en/473211475098171965/pdf/000020051-20140619074014.pdf | The lessons below complement the lessons mentioned in the ICR. Reforms are often controversial and there were two key lessons that can be taken from this project:- A proactive communications strategy that provides general information about the project to stakeholders and gradually introduces some of the more controversial aspects of reform to winners and loosers of reform facilitates a balanced public discourse.- A high-level steering group that functions actively and reflects the affected stakeholders in its make-up is a means of gaining acceptance of the reform agenda and securing ownership for the reforms.
P051855 | Mongolia Fiscal Accounting Technical Assistance (c 3081) | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1998 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/962661474588629986/text/000020051-20140615102957.txt | http://documents.worldbank.org/curated/en/962661474588629986/pdf/000020051-20140615102957.pdf | For an institutional development project with substantial IT elements, it is essential to have adequate IT and procurement expertise on the project team.The Bank needs to conduct a realistic assessment of agency capacity during appraisal, especially for a technically-challenging project such as this.Given Borrower capacity and the nature of the project, the Bank needs to consider very carefully the proposed timeframe within which the planned project can realistically be completed. Reference to similar projects in countries at a comparable level of development would help in this assessment.
P051856 | CN-Accounting Reform & Development | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2010 | 2011 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/368811474488514028/text/000020051-20140624160549.txt | http://documents.worldbank.org/curated/en/368811474488514028/pdf/000020051-20140624160549.pdf | Even in countries with high levels of capacity, such as China, focused objectives and simple project designs stand a better chance of success than those with complex and wide-ranging objectives. Ensuring Task Team Leaders with appropriate technical and language skills can contribute to better implementation support and increased likelihood that project objectives will be achieved. An important lesson noted in the ICR is that smaller and local training contracts were more economic and effective in that they tended to produce better quality courses tailored to local training needs and at a reasonable cost, when compared to large international contracts.
P051859 | Liao River Basin Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/213571474592656764/text/000146597-20140619163943.txt | http://documents.worldbank.org/curated/en/213571474592656764/pdf/000146597-20140619163943.pdf | The main project lessons are derived from those in the ICR.Establishing drainage companies requires greater institutional analysis, stakeholder ownership, and a longer time frame. Significant reforms are required in government policies and procedures to enable the transfer of government functions to enterprises, including existing assets, staff, decision-making, among others. The project design did not include a specific and phased strategy for achieving institutional development which is necessary in order to ensure the reforms are accomplished.There may be short-term trade-offs between meeting environmental objectives and full commercialization of utilities. Financial viability of new drainage companies in medium sized cities through full cost recovery is not a one step process. Thus government may have to subsidize utilities in the short-term until tariff increases enable financial sustainability.
P051888 | CN-Guanzhong Irrigation | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/260861474595620911/text/000020051-20140617133309.txt | http://documents.worldbank.org/curated/en/260861474595620911/pdf/000020051-20140617133309.pdf | Ensure that all project components are relevant to broader strategic objectives. In this case the objective to increase water use efficiency fully reflected Chinese and Bank policies; new irrigation and increased water consumption did not. Projects need to be able to measure progress toward institutional reform and this requires careful identification of what the reforms are and the benchmarks to measure progress towards them.
P051922 | Rural Development Support Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2001 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/388881475072129121/text/Madagascar-Rural-Development-Support-Project.txt | http://documents.worldbank.org/curated/en/388881475072129121/pdf/000020051-20140626114139.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):Innovative Community Driven Development operations in the rural sector, especially when operating in a fragile environment, require an extended horizon, a high degree of flexibility, continuous support for progressive capacity-building and repeat financing to maximize impact, learning and sustainability. The time required for such projects exceeds Bank averages, especially in fragile conditions, such as political instability and frequent natural disasters, where projects need to constantly adapt to changing external circumstances. The important elements are (i) a high degree of flexibility to respond to external shocks and adapt in terms of the type of support they provide; (ii) unique outreach and implementation arrangements for channeling support where it is needed; and (iii) experienced, multi-skilled, cross-sector Bank and Borrower project teams with continuity of leadership. Community Driven Development Projects should differentiate between target groups and sub-project objectives. The goal of ensuring food security would be suitable for the poorest segments of the rural population, who are usually characterized by very low capacity. On the other hand the goal would be to ensure financial sustainability over time for the farmers with proven farming experience and an entrepreneurial approach to production and marketing. Financing criteria and the level of subsidy provided through matching grants should be adjusted to the degree of vulnerability of the targeted group, geographical location, and the nature of the sub-project. The sourcing and quality of technical assistance needs focused attention from the earliest stages of project development. Allocating a portion of sub-project cost for technical assistance cannot resolve the fundamental problem of the scarcity and quality of such services in rural areas. Community Driven Development projects need to support an intense effort to build up such services over time, with a focus on: (i) building a sustained, long-term support for producer organizations; (ii) responding to the specific needs of potential entrepreneurs; (iii) tailoring the support to the unique technical, institutional and financial endowments of each region; (iv) ensuring adequate presence in rural areas through massive decentralization of staff and providers; (v) grouping service providers by area of specialty and introducing a black list of non-performers; and (vi) supporting "training of trainers."
P051931 | Community Reintegration and Development Project | Eastern and Southern Africa | Rwanda | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/283421474549734709/text/000020051-20140612093959.txt | http://documents.worldbank.org/curated/en/283421474549734709/pdf/000020051-20140612093959.pdf | Ensuring beneficiary participation at all stages of a project, including evaluation, promotes a sense of ownership in project achievements by the population, supporting the sustainability of the these achievements.The initial ceiling of a special account should be adjusted, if necessary, by ongoing assessments of real cash needs during implementation.Patience is needed when working at the community level, when people may lack technical knowledge and skills. Building these capacities and developing an understanding of formal Bank procedures is time consuming.When the Bank is flexible and willing to take risks, and place trust and confidence in local people at the grass roots level, communities become empowered and able to implement improvements themselves and cost-effectively.
P052021 | PA BASIC EDUCATION II | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2001 | 2009 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/560011474899506138/text/000020051-20140624160905.txt | http://documents.worldbank.org/curated/en/560011474899506138/pdf/000020051-20140624160905.pdf | A South-South dialogue may be effective to transfer television-based programs for lower secondary school students from one country to another. In this case, the Telesecundaria program developed in Mexico with the help of UNESCO was transferred to Panama, providing lower secondary education to 17,211 students located in rural areas.Systems need to be put in place for continued maintenance of schools in order to make school infrastructure sustainable. This project, in addition to the poor construction quality of schools, did not make any arrangements for infrastructure maintenance. In this respect, risks, such as storms and flooding, need to be incorporated in school designs to make buildings disaster-resistant. Institutional capacity assessments during project design are important to prevent delays during implementation. In this case, an appropriate institutional capacity assessment during project preparation could have prevented most of the delays experienced by this project in the first two years after effectiveness.Project objectives, even if similar to a preceding project, need to correspond to the specific activities to be undertaken. The projectâ€™s results framework lacked outcome indicators and attribution between inputs, outputs, and outcomes.
P052037 | Ho Chi Minh City Environmental Sanitation (Nhieu Loc-Thi Nghe Basin) Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/284591474574420885/text/000020051-20140626002616.txt | http://documents.worldbank.org/curated/en/284591474574420885/pdf/000020051-20140626002616.pdf | Lesson Learned from ICR1. Understanding governmental processes is essential for timely project implementation. Decree 209 which mandated information from the Contractor led to extensive delays. All procurement decisions, even minor ones, had to be approved by the Prime Minister's office (ICR, p. 8). 2. Financial sustainability requires looking at costs as well as revenues Establishing a tariff was useful but did not result in full cost recovery. 3.. Identification of public behavior that could undermine project achievements needs to be identified early in order to be addressed. Illegal solid waste dumping is one of the biggest challenges post-project. This should have been addressed at the appraisal phase.4. Arranging for the monitoring of all components contributing to the project's objectives is an essential part of sound project design . At project completion, it was difficult to measure how many households had been connected during project implementation and this indicator would have been useful to measure progress (ICR, p. 7).
P052080 | Sustainable Forestry Investment Project | Latin America and Caribbean | Nicaragua | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/242741474488919286/text/000020051-20140613033311.txt | http://documents.worldbank.org/curated/en/242741474488919286/pdf/000020051-20140613033311.pdf | (1) Sustainable forestry development should take a holistic approach that also addresses the issues of land security and agricultural productivity.(2) Establishing sustainable forest management institutions should involve the effective and meaningful participation of stakeholders in their design.(3) New technology transfers that are appropriate and divisible are not necessarily expensive.(4) A project that finances subprojects with matching grants and that operates in areas with disadvantaged or special groups (or with activities in which they are significantly involved) should earmark funds for these groups.
P052153 | Structural Adjustment Credit 3 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2003 | 2004 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/941401475110009202/text/000020051-20140612065604.txt | http://documents.worldbank.org/curated/en/941401475110009202/pdf/000020051-20140612065604.pdf | In countries of high political instability, widespread corruption, and poor governance, preparation and appraisal should pay particular attention to completing sound diagnostic work, past lessons and actual results achieved on the ground. This includes assessing the relevance of the objectives sought given the actual country context at the time. In addition, "safeguards" should be put in place in the form of a limited and clear-cut agenda, realistic implementation scheduling, applicability of reform measures, strict monitoring of benchmarks verified by frequent and tight supervision missions, and realistic assessment of risks. Preparation/appraisal teams should make realistic estimates of the time required to adopt/amend legislation.
P052153 | Structural Adjustment Credit 3 | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2003 | 2009 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/257411468032037102/text/468320PPAR0P051b010020090Box334133B.txt | http://documents.worldbank.org/curated/en/257411468032037102/pdf/468320PPAR0P051b010020090Box334133B.pdf | 5. Findingsand Lessons 5.1 Georgia's experience with reform shows again that Bank's support canbe effective inpromoting and supporting change ifthe authorities are committed. Providing support when the will is absent may retardrather than accelerate reform, as the authorities can muddlethrough their problems. When countries need serious reform the Bank should focus onthe fundamental problems andmake sure that its conditions leadto results, not to promises o f future reform. Ifthere is no will or commitment to tackle the difficult problems, the Bank should consider discontinuing lending. 5.2 Thejudicial reformproject deliveredmost o fits inputsbut didnot achieve the higher level objectives it sought, puttinginto question the validity o f its design. Two lessons emerge from this. First, changing institutions inthejudiciary demands interventionsbeyondthose that the project supported. Inparticular, the goal of an independentjudiciary requires continuous political will andcommitment from the highest level o f country authorities. Second, projects that support upgradinginfrastructure (court buildings, computer hardwareand software), andtrainingjudiciary staff could serve a useful purpose. Inorder to evaluate them it i s necessary to define the problem properly, to identifythe interventionsthat deal with it, and to design performance indicators tailored to evaluate ifthe interventionshave solved the problem. 5.3 Complex regulations makeit difficult to bringchange to organizations andreduce corruption. They increase the power o f discretion, encourage corruption, and strengthen the oppositionto change. Customs andtax administrations inGeorgia exemplify this problem. After the authorities simplified the tax system and customs procedures it became easier to deal with the administrative problems incustoms and taxes because inspectors had lost some o ftheir discretionary power. Before embarking on plans to improve the administration o f organizations where discretion reigns, the Bank should assess how to weaken that power by simplifyingregulations and legislations. 5.4 Banksupport fails when itusesthe wrong instrument (andtheory) to solve a problem. The fight against corruption exemplifies this lesson. The Bank demanded from the government an anti-corruption planandthe establishment o f an anti-corruption commission. The government complied but corruption thrived in 1998-2003. In 2004, a new government took effective actions to eradicate corruption (e.g., traffic police) and slashed regulations. This experience suggests that (a) creating an agency does not guarantee that the government will fight corruption and succeed; and (b) streamlining and simplifying regulations can be more powerful to fight corruption than creating organizations and commissions. 5.5 More lessons on fighting corruption are the following. First, Georgia eliminated egregious cases o f corruption with simple measures, not with an anti-corruption watchdog or an anti-corruption plan. Second, enforcement is hndamental to fight corruption. The Georgian government has done extremely well on this front. As a byproduct it has shown that it didnot need specific anti-corruption legislation to succeed.
P052154 | Structural Reform Support Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2007 | 2009 | ICRR | >=10 million & <25 million | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/240011475112302516/text/000020051-20140619073126.txt | http://documents.worldbank.org/curated/en/240011475112302516/pdf/000020051-20140619073126.pdf | a. Bunching several diverse activities in one project is a recipe for disaster. This project exemplifies well what it is achieved: disparate and unrelated components, bad results framework and indicators, poor supervision plan, and unsatisfactory results.b. Preparing projects to ensure continuity of IDA funding to countries reluctant to change misallocates IDA funds and increases the Bank's operational costs. By locking-in resources for reluctant reformers the Bank misses the chance to allocate the funds to countries more in need or more likely to use them well. Also, carrying out the actions that the credit funded demands more effort and resources from the Bank.
P052186 | MG-Microfinance | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/933341474899762755/text/000020051-20140625070634.txt | http://documents.worldbank.org/curated/en/933341474899762755/pdf/000020051-20140625070634.pdf | Long-term approach is an excellent design feature to effectively achieve success in institutional and capacity building;Smart subsidies is an important incentive in mobilizing owners' equity and commitment for developing institutions at the grassroots level and as a leverage to facilitate increased access to financial services to the low income population;Creating efficient institutional arrangements is crucial in supervising complex investment programs and for maximizing the impact along lines of continued ownership and efficient interactions between coordination agencies;Flexibility built into the design of complex investment projects enables efficient and effective adjustments during project implementation in response to the evolving operational and political environment, and to the needs of stakeholders for strong constituency support.
P052202 | SAC IV | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2002 | 2003 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/256811474649729340/text/000020051-20140612144603.txt | http://documents.worldbank.org/curated/en/256811474649729340/pdf/000020051-20140612144603.pdf | 1) It is important to ensure at preparation/appraisal that commitment exists at the technical/administrative level, and not only at the political level. Monitoring of such a commitment during implementation is crucial to avoid delays and back-tracking.2) The success of a series of one-tranche operations requires: (i) a clear vision by the Bank and the borrower of the medium-term objectives, opportunities and constraints; (ii) continuity in the Bank team; (ii) clear understanding and agreement between the Bank and the borrower of the benchmarks and triggers for further lending; and (iv) close supervision, monitoring and evaluation.3) As noted in the ICR, one-tranche operations provide for greater flexibility, especially in countries where adaptation to changing and fluid circumstances may be required.4) Fairly complex reform operations for countries with very weak institutional capacity should be accompanied by TA provided by the Bank or other donors.
P052208 | MG-Transp Sec Reform & Rehab (FY00) | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/767941475085364824/text/000020051-20140614184834.txt | http://documents.worldbank.org/curated/en/767941475085364824/pdf/000020051-20140614184834.pdf | 1. Project Development Objectives need to be aligned with project content. The different versions of the PDO are mutually inconsistent. This can be avoided if the M&E design and content is decided during preparation and modified later as in this project.2. An effective M&E system is important for both the Bank and the Borrower. For the Bank, in an APL, the M&E system is indispensable for ascertaining the trigger achievement. For the Borrower, the M&E framework should provide a useful concise road map for managing the sector entities. It may be appropriate that the M&E system is adjusted from time to time.3. Merit-based staff selection. Clear criteria for staff performance and qualifications should be the basis for staff selection and promotion. During the project there was a high turnover of managerial staff and the non-transparent, politically motivated recruitment had a negative impact on the project Executive Secretariat's (SE-PST) and implementing agency performance.4. Implementation arrangements need to be adjusted to match the implementation environment. In this project, SE-PST was set-up to coordinate the different ministries' implementation responsibilities. This arrangement became dysfunctional and should have been corrected timely (as a point of fact the correction did take place at the end of APL-1). [The Bank has a repertoire of solutions for similar cases from prior projects].5. Bank's in-country presence was useful. The Bank team's country presence enabled follow-up and interaction, which was particularly important in governance and institutional restructuring matters.
P052209 | Natural Protected Areas Project (GEF) | Latin America and Caribbean | Mexico | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1997 | 1998 | 2004 | ICRR |  | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/900961475089110299/text/000020051-20140612092841.txt | http://documents.worldbank.org/curated/en/900961475089110299/pdf/000020051-20140612092841.pdf | 1. Projects like this, which successfully take an integrated approach to protected area management plans, institutional strengthening, sustainable funding and the inclusion of local communities, are important vehicles for protecting globally valuable and threatened ecosystems.2. Project components to involve local communities in conservation and to provide alternative income opportunities are essential if biodiversity objectives are to be achieved. However, such components need to be designed, supervised and monitored with care.3. The endowment model can provide a powerful mechanism for ensuring a permanent flow of funds for operating protected areas, even in middle income countries but more so in the poorest countries. Such programs hold out the promise of sustainable management of protected areas, even if external donor funding should phase out.
P052240 | MZ-Natl Water 2 (FY99) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/764851474398016752/text/000020051-20140620071456.txt | http://documents.worldbank.org/curated/en/764851474398016752/pdf/000020051-20140620071456.pdf | Strong Government commitment can ensure success even under adverse circumstance. In this case, strong commitment on the part of GOM to sector reform and private participation ensured the satisfactory outcome of the Project, despite problems and delays when the initially chosen private operator withdrew, major floods occurred, and problems materialized subsequent to the imposition of a VAT.Bidding processes for the selection of private operators need to take into consideration uncertainties about the condition of the old network. It may well be prudent to include in the bidding process an initial â€œtransitionalâ€ operating period for network reconnaissance, followed by a negotiation process based on more precise knowledge of the networks and customers.Private operator performance depends on successful adjustment to local conditions: Experience and a good international reputation may be insufficient for easy adaptation to specific local conditions and requirements and a satisfactory transfer of knowledge. Cost recovery needs to be realistically defined. In this case, the Project supported a substantial sector reform program. Thus, it may be unrealistic to expect tariff levels to reflect the total costs of the program in the short term, as it takes many years to fully rehabilitate and expand war-ravaged networks, and to build up local operating capacity to best-practice standards.
P052247 | MA-PILOT FISHERIES DEV. | Middle East and North Africa | Morocco | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/462391474496837550/text/000020051-20140612145236.txt | http://documents.worldbank.org/curated/en/462391474496837550/pdf/000020051-20140612145236.pdf | A neutral, third party agency with appropriate expertise, such as the Bank, can play a catalytic role at a time when government and industry are trying to develop new paths of cooperation in sector management. This may not require significant lending. This catalytic type role can be particularly significant when sensitive issues such as the monitoring of commercial activities are being addressed.
P052256 | Rural Poverty Reduction Project - Minas Gerais | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2011 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/658141474561736568/text/000020051-20140624200246.txt | http://documents.worldbank.org/curated/en/658141474561736568/pdf/000020051-20140624200246.pdf | Lessons suggested by the ICR include the following: Decentralized project management can improve responsiveness to beneficiaries. In this case, the delegation of responsibilities to regional technical offices increased the accountability to beneficiaries, reduced processing times and helped to strengthen the Community Associations' management capacity. Community-driven development can help to empower women, because community associations provide opportunities for learning and for assuming leadership. Small-scale grants financing productive ventures, in contrast to community infrastructure, require a business plan, up front marketing arrangements and formal training for the operational phase.IEG adds: A complete assessment of the efficiency of CDD projects involves reviewing the evidence for cost-effectiveness, showing how this varies between subproject categories, and the extent of variation between the average for the project and the average obtained under other public programs.Intermediate outcomes need to be properly quantified with well-designed indicators, baselines and targets. In particular, social capital is hard to measure and the evidence adduced in this case was not strong enough to conclude that it had been substantially achieved.
P052263 | Pilot Social Fund Project | Western and Central Africa | Togo | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/830791474898314880/text/000020051-20140612090803.txt | http://documents.worldbank.org/curated/en/830791474898314880/pdf/000020051-20140612090803.pdf | 1. Learning and innovation are key aspects of a LIL. Monitoring and evaluation have a critical role to play in helping to maximize learning and deserve early and continuous attention. 2. The political and economic environment in the country is critical to project success. The Bank should be ready to cancel a project even if costs have been incurred on its preparation if it is evident before the project goes to the Board that the prevailing political and economic environment in the country may not support adequate project implementation.
P052293 | Infrastructure Asset Management | East Asia and Pacific | Samoa | IDA |  | Infrastructure | Transport | IDA | IPF | 1999 | 2004 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/875261474492805298/text/000020051-20140615091740.txt | http://documents.worldbank.org/curated/en/875261474492805298/pdf/000020051-20140615091740.pdf | 1. Project design. For success, projects that combine several related sectors, require (i) a multi-entity steering committee with power to decide; (ii) PMU with accountability and reporting to each participating entity; (iii) monitoring and multi-skill supervision by both Bank and the Government; and (iv) well-defined indicators relevant to both to each entity and the project.2. Public Sector Reform in Small Island State. Besides the all-applicable requirements for Government ownership, committed leaders, comprehensive consultations and well-designed plans, small island states present additional challenges in terms of: continuity and competence of staff; thin market for professional and managerial staff; and experience required to run a restructured organization. These risks require advance planning for sector reforms to succeed.3. Emergency Risk management. A successful hazard risk management model includes: (i) development or existence of a national strategy, including budget (possibly with IFI participation); (ii) community-based management plans that are based on objective risk assessment and community participation authorized by community leaders and the Government; (iii) a specific short-term program and budget for activities and works (including "fire-drills" for readiness); and (iv) for sustainability, involvement of the stakeholders and the private sector.
P052297 | TRAINING & EMPL. | Middle East and North Africa | Jordan | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/468191475079564615/text/000020051-20140612063255.txt | http://documents.worldbank.org/curated/en/468191475079564615/pdf/000020051-20140612063255.pdf | Employer-based, demand-driven training can provide an effective and efficient alternative mode to the traditional supply driven, institution based approaches. It requires that employers have the capacity to design and implement training, and where such capacity is weak, especially in small businesses, adequate support should be provided.In order to utilize an employer-based training approach as a poverty reduction mechanism, there needs to be a sufficiently large number of businesses in poor regions with the capacity to design and deliver training, and with the absorptive capacity to provide employment opportunities. Furthermore, where local committees are expected to perform promotional and implementation roles, there is need to provide funds to cover the cost of participation.Tracer studies, particularly for pilot projects, need to be comprehensive and include comparative data.
P052315 | ET-Medicinal Plant Conserv LIL (FY01) | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/250401475081850905/text/000020051-20140618085031.txt | http://documents.worldbank.org/curated/en/250401475081850905/pdf/000020051-20140618085031.pdf | 1. Preclinical and human clinical trial protocols should be in place, and the appropriate agencies responsible for their clearances should be identified, at project implementation. 2. The basic infrastructure to complete validation studies should be in place, including technical protocols and guidelines, to ensure continuity of research.3. Medicinal plants are a frequently hidden but sizable sector in the economy, one that is particularly important for poor people as suppliers/producers as well as consumers. More work is needed to understand the potential for commercialization through formal channels in parallel with providing incentives to conserve medicinal plants.4. A lesson from working with the Traditional healers in the Bale Mountain National Park, which may be applicable to other regions, is that healers are ready and willing to share their knowledge when project objectives are clearly defined and their intellectual property rights are protected. 5. Focal champions at the stakeholder and beneficiary level who understand the projectâ€™s objectives and activities help ensure successful implementation.
P052367 | Maloti-Drakensberg Transfrontier Conservation and Development Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/642281474904705382/text/000020051-20140624161952.txt | http://documents.worldbank.org/curated/en/642281474904705382/pdf/000020051-20140624161952.pdf | In order to build broadly-supported natural resource management and biodiversity conservation, a realistic assessment of assumptions and expectations underlying project readiness, the time required to achieve results, and the sequencing of activities is needed. This is especially relevant for projects with a poor populace heavily dependent upon natural resources for their survival before launching into highly technical biodiversity conservation planning and management tasks. Extensive sensitization, awareness and consensus-building actions are often needed before project implementers, stakeholders and the affected communities will be ready and motivated to implement technical activities intended to alter their access to and use of natural resources, including grazing habitats. This was recognized by project designers who acknowledged the "need for careful and detailed preparation, a long-term time horizon, and early restructuring if implementation problems occurred" based on the experience of the Lesotho Land Management and Conservation Project mentioned under "Lessons Learned" in the PAD. With institutional capacity weakness and little public awareness, a relatively simple design with clearly planned sequencing would have been more likely to be successful by permitting adequate awareness-raising and consensus-building, along with institutional capacity-building activities, as the first phase of a longer-term, sustained programmatic series of projects. This reflects what is now envisioned under the 20-year strategy agreed to between the Lesotho and South African governments.
P052368 | Maloti-Drakensberg Transfrontier Conservation and Development Project | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/630751474555834489/text/000020051-20140624170836.txt | http://documents.worldbank.org/curated/en/630751474555834489/pdf/000020051-20140624170836.pdf | Having a clear chain of causality linking a set of proposed inputs and activities to a set of expected outputs and outcomes that should logically and realistically lead to achieving the project objective is a prerequisite of sound project design. A well prepared logical or results framework combined with a M&E system that generates the information needed by project managers and partners to make decisions informed by reliable and timely feedback from monitoring data is essential to good project management. The MDTP did not do that and project implementation and development results suffered as a result.Secondly, both project objectives and the means to achieve them must be formulated with the full agreement and ownership of the borrower (i.e., the government and implementing agencies). If changing circumstances dictate that a different approach or objective should be taken, as was the case in South Africa with the secondary objective of promoting local community development and shared benefits through a payment for environmental services rather than through increased eco-tourism revenues, then it should be done consensually and adopted formally through an amendment to the project agreement and legal documents. Otherwise, time, effort, and resources will be wasted on activities not directly relevant to achieving the project's objective.Parallel implementation of projects by neighboring countries sharing a common resource, such as a river, ecosystem, watershed or airshed, but with different institutional capabilities and fiscal resources can effectively work together to achieve a common objective, such as happened with the MDTP. However, increasing the number of project participants or objectives adds to the costs and complexity of coordinating and managing the projects. It might be better to start with the smaller number of partners and objectives at first, and then, based on initial successes and experience gained, build from there to achieve more ambitious goals.
P052400 | PARTNERSHIP FOR NATURAL ECOSYSTEM MANAGEMENT PROJECT | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2008 | 2009 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/237151474940240076/text/000020051-20140619080337.txt | http://documents.worldbank.org/curated/en/237151474940240076/pdf/000020051-20140619080337.pdf | Livelihoods: Alternative natural resource-based income generating activities and other local development activities which exploit territorial assets need to accompany conservation activities to reduce pressure of local communities on natural resources and increase their incentive in engaging in sustainable management of natural resources. However, CDD operations are not necessarily the best instrument to support natural resource management activities, and therefore their complementarity with a GEF operation should be carefully assessed. When presented with CDD options, communities tend to choose activities that meet their basic needs, including health and education opportunities, as opposed to natural resource management activities. Local Involvement: Governments often do not have the capacity to manage protected area systems. Involvement of local communities in the management of protected areas and in the sharing of benefits is a critical element for protected area management. However, project preparation should include a rigorous social assessment to determine existing land access and use rights, ownership as well as analysis of the pre-existing ecosystem services that are being provided by the area prior to becoming involved in changing management structures. Care must be taken when shifting from centralized management to decentralized involvement to determine the roles and rights of local managers in relation to the national or district authorities, depending on the classification of the specific sites. Moreover, when assisting with the development of local management structures, care must be taken to determine the legitimacy and "representativeness" of an NGO chosen or the capacity of the community and its structure to manage a site in a sustainable and economically viable manner. Planning and Consultation: While wildlife resources need to be managed within a transboundary and ecosystem perspective, the creation of new protected areas should in most cases include prior consultation and/or consent from the communities, an adequately financed plan for resettlement, including attention paid to cultural heritage, social values, and economic needs. The creation of new protected areas should be accompanied by a management plan that takes into account local capacity and a long-term financing plan that works to ensure sustainability over time.
P052400 | PARTNERSHIP FOR NATURAL ECOSYSTEM MANAGEMENT PROJECT | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2008 | 2010 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/610211468231276610/text/554430PPAR0P111IC0disclosed08131101.txt | http://documents.worldbank.org/curated/en/610211468231276610/pdf/554430PPAR0P111IC0disclosed08131101.pdf | 6. Conclusion and Lessons 6.1 This PPAR was conducted as an input into IEG's Review of the World Bank's Safeguard Policies, and as such, focuses heavily on the conclusions that can be drawn and the lessons that can be learned from the implementation of the Bank's safeguards policies in GEF financed biodiversity conservation projects, in this case, in West Africa. ï¿½ Protected area projects supported by the World Bank need to ensure that other means of finance, apart from the GEF, are woven into the project design in case contingency resources are needed to ensure that negative impacts on human livelihoods are mitigated. Biodiversity conservation projects that seek to enlarge or create protected areas or conservation corridors always involve a change in access by rural residents to natural resources and sometime involve physical resettlement. Proper valuation of livelihoods and sufficient project costing for the restoration of these livelihoods are essential and should be firmly figured into project design. GEF stand-alone projects are less equipped to finance the costs of restoring livelihoods since GEF is an incremental financing instrument designed to focus on the provision of global environmental benefits. ï¿½ The Bank's Safeguard on Indigenous Peoples is not comprehensive enough to cover vulnerable groups that may be affected by a project. Biodiversity conservation projects that limit access to resources, including water and grazing rights of nomadic groups and herders, need to highlight the particular needs of these groups in the social assessment and work with the respective client governments to formulate appropriate mitigation strategies. The Bank's resettlement policies should be applied on a contextual basis so that, where appropriate, seasonal and climatic migration is taken into account in figuring the number of project affected persons. ï¿½ Projects with small grants programs typically indicate that since the activities will be chosen downstream, environmental management plans will need to be designed at the time when activities are selected, and that the management plans must be designed in consultation with the beneficiaries. The project level Environment Management Plan is often modeled as a framework process that provides guidelines on how to develop EMPs at the site or activity level. Guidelines include information concerning Bank standards on participation and inclusion, conflict resolution, monitoring and evaluation. However, for this system to be effectively implemented, adequate and upfront assessment is needed of EIA capacity at the village and inter-village level, including both capacity for assessment and capacity to mitigate harm (technical and financial capacity).
P052402 | Gourma Biodiversity Conservation Project | Western and Central Africa | Mali | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2005 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/625161474591937268/text/000020051-20140626114703.txt | http://documents.worldbank.org/curated/en/625161474591937268/pdf/000020051-20140626114703.pdf | Several key lessons are of relevance for other operations: 1. A project should not be designed in such a way that achievement of its development objectives depends on the outputs of other operations -- in this specific case the provision of essential water infrastructure in the semi-arid project region -- a risk that should be anticipated and addressed in project design. 2. Although it could have been difficult to predict exogenous risks to project outcomes such as the emerging insecurity in the project area, risks to project outcome such like lack of government institutional capacity and complications in project financial arrangements among partners -- in this specific case between the Bank/GEF and FFEM -- could have been anticipated during the design stage. The associated lesson is the need to pay much more careful attention to these critical preconditions for smooth project implementation and likelihood of achieving its development objectives during preparation, appraisal, and supervision. 3. In a situation where a project is co-financed, prior agreement regarding and formalization of the responsibilities of each donor is essential to avoid ambiguities and delays -- not to mention a total breakdown in relations, as occurred in the present project -- during implementation.
P052590 | AR NAT HWY REHAB&MAINT | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/971301474898288806/text/000020051-20140615103039.txt | http://documents.worldbank.org/curated/en/971301474898288806/pdf/000020051-20140615103039.pdf | A sound and permanent system of road financing at the national and local level through a combination of direct and indirect users fees is critical for reducing the dependency on annual budgetary allocations for road maintenance.Successful implementation of the institutional strengthening program requires clear and binding agreements between the Borrower and the Bank, strong ownership by the Borrower, and detailed programming and consistent execution over the years. Clear and consistent definition of key performance indicators at appraisal, early agreement between the executing agency and the Bank supervision team on the monitoring of these indicators, and annual reporting of such indicators would greatly contribute to a reliable monitoring of outcome and output indicators.The project experience confirmed the advantages of the CREMA performance based contract system. The CREMA system of contracting fosters the contractorsâ€™ ownership of the works by transferring the responsibilities for the service quality of the roads from the Road Authority to the contractors; thus compelling them to: (i) prepare results-oriented programming of their works and activities, (ii) exert their own quality control, (iii) implement adequate rehabilitation works the first year to ensure low maintenance costs over the remaining four years, and (iv) repair promptly any road deterioration to prevent further extension of the initial damage.
P052590 | AR NAT HWY REHAB&MAINT | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 1998 | 2006 | 2007 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/346861468002124416/text/40154.txt | http://documents.worldbank.org/curated/en/346861468002124416/pdf/40154.pdf | Lessons 7 7.1 This PPAR confirms an important lesson identified in the PPAR of the preceding project. That lesson was that contracts such as CREMAs tend to be given higher priority in budgetary allocations than maintenance works carried out under traditional contracts or by force account. Thus, reflecting that lesson, despite the deep economic crisis during the erly 2000s, the government still managed to provide some counterpart fhding for the execution of the CREMA contracts, even if such contribution was lower than originally expected. 7.2 The following new lessons emerge from the project under review\. a) Perfomzance-based contractsfor road maintenance, such as the CREUA contracts, are an efficient tool of maintenance management, and likely to be useful to other countries lookingfor ways to increase the efectiveness of their road maintenance management systems. CREMA-type contracts would be especially suitable for middle-income economies with a well developed highway agency and contracting industry. A road maintenance strategy should include a menu of management options with maintenance carried out by the private sector, thus improving eficiency and reducing the extent of maintenance carried out by government personnel. Over time, the road network should ideally be maintained largely by performance type contract. The process is likely to be gradual, as financial, economic, technical and administrative constraints need to be overcome. c) Project components which arefully locally-financed are useful parts of a project as they provide a more completeperspective of the sector assisted by a project, yet they are dzficult to monitor. The large locally-financed component in the project (a quarter of total costs) was intended to finance road maintenance works dispersed over several thousand kilometers. Thus, they were difficult to monitor. And because such works did not include Bank financing (except for a short period following a loan amendment), the usual loan recording documentation did not apply. Yet, these locally financed components are useful in that they provide a more complete perspective of the overall road maintenance effort.
P052608 | Antioquia Upper Secondary Education | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/740781468190777006/text/ICRR14773-P052608-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/740781468190777006/pdf/ICRR14773-P052608-Box393191B-PUBLIC.pdf | Lessons drawn from the ICR (pages 22-23), adapted by IEG:An effective and useful results framework requires consistency and clarity in definitions of indicators and targets. In the case of this project, lack of clarity in data sources, definitions and methodologies diminished the usefulness of data that was being routinely collected by the implementing agencies.Longer-term interventions to improve school quality may not be reflected in improved academic performance over a project period of 4-6 years. In the case of this project, the main quality interventions were improved school management and reformed curricula; however, these were likely not experienced at the classroom level until late into the project period.
P052705 | EG-SOCIAL FUND III | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/225291475110844761/text/000020051-20140615114627.txt | http://documents.worldbank.org/curated/en/225291475110844761/pdf/000020051-20140615114627.pdf | Targeting mechanisms as well as monitoring and evaluation systems need to be in place before project implementation begins. A user-friendly M&E system will facilitate subproject evaluations, provide feedback to improve targeting and efficiency, and is an essential management and planning tool.Up-front agreement between the Bank and the Borrower is also needed for procurement arrangements, standardized bidding documents, and draft contracts, in order to facilitate the procurement process and avoid implementation delays.Quality at entry can be compromised when projects are prepared on a fast-track basis. The fast track approach may not be appropriate for projects involving implementing agencies with institutional shortcomings.
P052736 | Dominican Republic: Telecom Regulatory Reform | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2007 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/792111474629963995/text/000020051-20140617140014.txt | http://documents.worldbank.org/curated/en/792111474629963995/pdf/000020051-20140617140014.pdf | Â· Building up a successful institution is time-consuming and challenging and requires close Bank supervision, especially during changes of Government administration. The creation of INDOTEL required a lot of time during project preparation because the aim was to create both the regulatory entity and the regulatory framework. Although it is best practice that the regulatory entity be independent and separated from the government entity taking policy decisions, in the case of Dominican Republic INDOTEL is both Regulator and Ministry, a fact that was not an obstacle to project development.Â· Closing an institution implies a thorough review of all its assets. At appraisal, the team failed to recognize the complicated legal procedures to dispose of DGTâ€™s physical assets (postal and telephone offices throughout the country). As a result, INDOTEL inherited most of those unwanted assets.Â· Internet community centers require a specific use. The IT Training Centers (CCIs) program has been a great success in the Dominican Republic because the CCIs have a specific purpose (education), and their administration is being done by experienced NGOs highly committed with the communities served.Â· A good Spectrum Monitoring and Administration System requires more than just the equipment. It also requires the merging and reconciliation in one data base of all records of supervision, licensing and broadcasting existing in government departments prior to the introduction of the SMAS. It took INDOTEL more than two years to transfer all the existing records to the new system, to inspect all the stations in the country and to clean the database.Â· Mobile networks are very active and expand in a timely manner. Many sites where the FDT placed public payphones (identified as towns without telecommunications services during appraisal) already had mobile phone services. Notwithstanding, all communities, especially in extremely poor areas, welcomed the payphones, because many people could not afford to buy mobile phones.
P052887 | Health Project | Eastern and Southern Africa | Comoros | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/154261475090738896/text/000020051-20140613030809.txt | http://documents.worldbank.org/curated/en/154261475090738896/pdf/000020051-20140613030809.pdf | Project restructuring should be considered in contexts of changes to technical strategies and evolutions in a country's overall political environment. Project modifications, following a long suspension period, occurred in a piecemeal fashion. A more holistic review of the project in light of technical changes to the malaria program and to the islands' powers and prerogatives, would have been more appropriate.Supervision reporting should refrain from giving satisfactory ratings to the development objectives in the absence of data/information on outcomes.Where the borrower has limited capacity for policy analysis, the project design and implementation must: be both consultative and pragmatic, collect data that will foster a learning process, and provide for capacity building in program development and policy analysis.
P053200 | Health Sector Reform Project | Eastern and Southern Africa | Lesotho | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/188161474650226817/text/000020051-20140614183419.txt | http://documents.worldbank.org/curated/en/188161474650226817/pdf/000020051-20140614183419.pdf | Sustained commitment to reforms and coordination with other ministries is important.Broad ownership of the reform process is key to the successful implementation of the reform program.Budgeting priorities must be consistent with financial planning.There is a strong need to balance improvements in health sector processes with a focus on improving health service delivery.Monitoring and evaluation must be given attention from the very start of project design.Continued success of the health sector program is reliant upon further strengthening of donor coordination in the sector.
P053200 | Health Sector Reform Project | Eastern and Southern Africa | Lesotho | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2005 | 2010 | PPAR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/589691468263701153/text/554170PPAR0P111Official0Use0Only161.txt | http://documents.worldbank.org/curated/en/589691468263701153/pdf/554170PPAR0P111Official0Use0Only161.pdf | 4. Conclusions and Lessons Health Reform 4.1 Country ownership and commitment to the reform process are key to successful implementation. The HSRP was preceded by extensive consultation among stakeholders on the vision for reform. Implementation of the project increased ownership of the reform process, but staff turnover was high. Ownership and accountability for the reform program was not sufficiently rooted within all MOHS W departments and units and the health sector in general; the HPSU was the only department well-versed with the reform program. Communication within the MOHSW remains weak. Similarly, lack of coherence on decentralization pace and scope between MOHSW, MOFDP, the Ministry of Public Service, and the Ministry of Local Government and Chieftainship led to inefficient deployment of scarce resources. The MOHS W should be encouraged to be more proactive and consistent in promoting the content and image of the reform program both within and outside the ministry. Throughout HSRP, the HPSU spearheaded the reforms, a task it managed partly due to stability in leadership and staffing. But ownership of the reforms must be more widespread across the sector to ensure accountability for results and to build up a pool of champions for the process. 4.2 Political economy analysis must be ongoing. Even issues that are seemingly resolved can re-emerge unexpectedly. For example, there are current political controversies swirling around the NAC, with continuing rumors that it is about to be dissolved. Other agencies question its usefulness and critique it as simply an additional layer of bureaucracy; certainly other Government departments, particularly MOFDP/GFCU, would like to absorb its budget along with its functions, and the MOHSW would like exclusive purview over HIV/AIDS transferred back to its HIV/AIDS Directorate. Given that the NAC's initial creation was viewed by many as simply a quick political fix, intended to placate public outcry over the increasing number of AIDS-related illnesses and deaths, it is not surprising that it remains controversial, in many cases merely a tool in ongoing power struggles. These ongoing internal political skirmishes have been tactfully mediated by the Global Fund and especially by the Bank, but neither external agency managed to stifle the feud. In retrospect, some informants suggest, perhaps less tact and a more forceful approach would have been appropriate. It should be noted, however, that competing agencies in part due to Bank persuasion have continued to function relatively well together at the technical level. 4.3 There is a strong need to balance improvements in health sector processes with a focus on improving health services delivery and it may not always be necessary to assume that there are tradeoffs between the two. Stakeholders across the sector stressed that institutional capacity is key to adequate functioning of the health system, but attention to service delivery, quality of care, and health outcomes cannot be deferred, particularly when health indicators are declining. 4.4 Health sector reform does not and cannot take place in a vacuum. In the case of the HSRP, the lack of a macroeconomic support program to push for difficult policy issues outside the purview of the MOHSW probably constrained or delayed actions, particularly in the areas of decentralization of services and upgrading the salaries and benefits of health workers (civil service salaries being a system-wide issue). A dedicated local government support program could have helped the project sort out knotty institutional issues among the ministries of finance, local government, and technical lines agencies on these issues. Lack of progress or clarity on upstream issues most importantly, setting the rules of the game for an eventual fiscal devolution to local authorities meant that downstream activities within the health sector itself had to be deferred, or redesigned to fit within the purview of only the health sector. 4.5 The use and strengthening of existing systems is preferable to the creation of new and separate fiduciary and other systems. The successful strengthening of capacity in the project accounting and procurement units underscores the value of using and building on existing systems. 4.6 Sustainable human resources retention requires long-term planning, ownership, and innovation. Like many countries in the region, shortage of skilled manpower is one of the main challenges facing the Government of Lesotho. Although Bank-financed projects have helped to build capacity in government and non-government institutions, staff that are critical to delivery of services, particularly nurses and doctors, migrate freely to neighboring South Africa. Other staff that have been empowered under the Bank project have left those positions, moving internally or to other institutions, and staff at the district level have moved to the capital. The Government, Bank, and other development partners remain faced with the challenge of formulating innovative and affordable manpower development and retention policies and strategies. It cannot be overstressed that innovation is required in this area. Levels of remuneration, while important, are not the primary issue. Staff in rural areas cite a variety of more compelling factors that make it difficult for them to attract qualified personnel\. neglect by senior management and headquarters offices, who virtually never spend time outside Maseru conferring with service providers at the health facilities themselves; housing and security; and most importantly, lack of resources, especially equipment and vehicledfuel, that would make it possible for staff to perform their main task saving lives effectively. It is also not clear that an exclusive focus on supply-side issues is appropriate in the human resources area, If all staff worked to full capacity, the situation would be improved greatly, but existing approaches have not focused on the productivity and duplication sides of the equation. 4.7 Caution must be exercised to ensure that countries do not become over-dependent on technical assistance, and that technical assistance is reasonably priced and appropriately monitored. It is important to ensure that implementation capacity remains after provision of technical assistance has ended. This can take place through support for capacity-building of existing local staff (through external training or on-the-job training) as well as specific skills transfers. Building local capacity and skills should be included in technical assistance contracts, and the Bank should work with Government to develop mediumand long-term plans to internalize key positions. In making a decision about whether to import expertise or build local capacity, the local context and ability of the country to employ or transfer skills from technical assistance to local staff should be taken into consideration. 4.8 It is also important, however, to balance training meetings, seminars, and workshops with the implementation of operational plans. In most work plans for the MOHSW, training constitutes more than 40 percent of the activities planned for the year (MOHSW 2008a). Many staff prefer training sessions to the undertaking of their regular responsibilities, because of the additional stipends and meals that are frequently made available. Consideration should be given to on-the-job training methodologies as an adjunct or alternative to traditional seminars and workshops. 4.9 Some procurement delays have been caused by lack of clarity between user departments on the functions to be performed by various technical assistance consultants. There should be a coordination mechanism within implementing agencies to lay out, from the beginning, clear responsibilities for each departmentbit. Streamlining institutional arrangements and roles of various components at the design stage is a necessity for avoiding implementation delays. Individual technical assistance provision should be evaluated for effectiveness in terms of capacity built by the client entity. 4.10 Civil society in Lesotho remains relatively neglected, and its potential to contribute to the solution of a wide array of problems in the country is underacknowledged. This is a particularly significant gap considering the magnitude of donor funds flowing to Lesotho to support the response to HIV and AIDS, and the growing proportion of those funds that now supports local, non-governmental organizations and other civil society entities. The Bank project took important initial steps to assess and close this gap, and naming the LCN as a PR for the Round 8 Global Fund grant is a landmark achievement. More effort is required, however, to strengthen logistics for communities to define and carry out their work effectively. 4.1 1 Monitoring and evaluation must be afforded appropriate attention both during project design and throughout implementation. Incentives for M&E must be structured into project activities. Care must be exercised during M&E planning exercises to take into consideration the capacity of the staff and institutions that will implement those plans. Health Systems and Communicable Diseases 4.12 There is near-universal agreement that HIV has crowded out attention to other important health challenges in Lesotho. The HCTA's focus on Global Fund resources may have exacerbated this problem, with its exclusive focus not only on HIV, but on Global Fund-financed HIV interventions; Government attention, largely because of the significant dollars involved, remains with the Global Fund grant, and opportunities to integrate both Global Fund activities and HIV-related activities with the health sector in general have been missed. Bank projects could have encouraged integration of HIV with other health services, including those for TB, reproductive health, and OVCs. Insufficient attention has been paid to the low capacity of social welfare agencies. 4.13 There have been important steps forward in this area, however. Current trends are encouraging, with more linkages between HIV and reproductive health services. For example, because of the resources devoted to PMTCT, antenatal clinics now offer HIV testing, linking HIV services to antenatal services. Very recently, MOHS W launched a new program intended to integrate child health services with HIV services, but it is premature to assess results in this area. And it is undeniable that HIV funding has had positive externalities for the rest of the health sector, most notably strengthened laboratory systems and drug supply chains. Relationship between the Bank and the Global Fund 4.14 The Bank's entrance was prescient, strategic, even pioneering, coming in at the right time and with the right forms of assistance. In other words, the Bank in an environment where there were very few donors active on HIV/AIDS in Lesotho was the first institution to act on the increasingly urgent need to assist countries in developing capacity to spend all the new funds coming from the donor community. Informants recommend the Lesotho model as strongly relevant for other countries, with a relatively small Bank investment facilitating the absorption of much larger sums from other donors. 4.15 The form of the Bank's intervention on HIV/AIDS was not without controversy, however. Bank management was initially planning a more traditional MAP project for Lesotho, but some Bank staff argued that the country would be hard-pressed to spend all the money it was about to receive from the Global Fund, let alone additional funding from the Bank. Significant non-governmental participation and implementation was envisioned for any HIV/AIDS interventions funded by the Bank from the very beginning, for example, in part because of a judgment that the government would not have the capacity to absorb the new funds. It was these arguments that led to the capacity-building project rather than the MAP approach. 4.16 Global Fund staff (the Fund Portfolio Managers), though based in Geneva, have been active partners with the government during grant implementation. In particular, Global Fund staff have intervened at critical points to discourage key personnel from leaving the Global Fund Coordinating Unit for other positions inside or outside Lesotho, primarily by persuading the Ministry of Finance (the Principal Recipient) to provide incentives to stay (the Global Fund grant pays GFCU staff salaries). The GFCU and the Ministry of Finance (where it is institutionally located) enjoy a productive working relationship, with MOFDP routinely placing GFCU matters at the top of its agenda. The Bank does not sit on the CCM, and although its impact has been crucial and the HCTA's results demonstrable, the relationship between the Bank and the GFCU has not always been smooth. Staff on the ground in Lesotho observed that until recently, it was occasionally difficult to obtain timely decisions on important matters from the Bank, and that the Bank was not as flexible as it could have been in adapting to changing implementation circumstances. It does not appear that Bank interventions have been deliberately coordinated with Global Fund staff in Geneva, although there is strong appreciation from Global Fund management for the Bank's contributions to capacity-building, particularly in the areas of procurement and institutional development at MOHSW. The Bank and Global Fund missed opportunities to work together to overcome the political tensions between the MOHSW, MOFDP, and the NAC, and therefore fully to develop the NAC into a highly-regarded agency that can effectively take the lead in the country's response to HIV/AIDS. Value Added of the Bank 4.17 The Bank is clearly regarded by both the Government and most development partners as a critical player in the health and HIV areas, mainly due to its effective catalytic and complementary role. The Bank was an essential player in fostering a sector-wide perspective, building the ownership necessary to sustain progress, and creating a demand for the information required to plan, monitor, and react effectively to sectoral needs. The Bank was also key in moving the health sector to a higher position on the MOFDP's priority list. The Bank's approach has encouraged other partners to consider how each can best coordinate support that will tap into its specific comparative advantage. 4.18 As more resources are becoming available to finance HIV programs, it is the Bank's comparative advantage to focus on system strengthening. The Bank's hands-on implementation support is still needed, given the Global Fund's status as a grant-providing agency that offers limited implementation support. Continued Bank support for strengthening of implementation systems can help remove capacity bottlenecks and speed up the pace of implementation of other partners' HIV programs. This approach is also an effective way to invest limited Bank resources, as compared to a much costlier expenditure on mainstream HIV interventions. Building capacity and filling gaps uses the Bank's comparative advantage, particularly in system and fiduciary strengthening, in a way that complements, rather than competes with, other partners' financing. In short, the Bank's approach to health and HIV/AIDS in Lesotho has accomplished a lot with relatively little money. In the current environment, with a number of global initiatives providing substantial resources toward improving health, nutrition, and population outcomes, the Bank's approach in Lesotho should serve as a valuable lesson to be extended to other priority development areas.
P053243 | Peasant Enterprise Zones Development Project | Latin America and Caribbean | Colombia | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/527851474577146740/text/000020051-20140612141339.txt | http://documents.worldbank.org/curated/en/527851474577146740/pdf/000020051-20140612141339.pdf | Learning-by-doing is an effective way to build community capacity.Substantial time is needed (in this case, two years) to lay the foundations for a participatory process.Once the process is in place, it is important to respond quickly to local priorities and community expectations in order to maintain trust.The approach taken needs to be flexible and adapted to the needs of each area.Explicit rules need to be developed at the outset and clearly signaled to the various stakeholders.Providing the appropriate information and technical assistance is critical if results are to be achieved.
P053255 | TN-ECAL II | Middle East and North Africa | Tunisia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2001 | 2005 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/231191468760755829/text/31017.txt | http://documents.worldbank.org/curated/en/231191468760755829/pdf/31017.pdf | Lessons Learned 4.6 The main lesson are\. e Tunisia's successful economic performance hasbeendue to three attributes\. ownership andbroadpolitical consensus, awell-developed humanresource . base, and a stable macroeconomic environment. e Experience inprivatization andthe financial sector shows the need for the Bankandthe development partnersto staythe course andshow flexibility intheir support, providedthere is evidenceofgenuine andsustainedreform efforts. For example, by acceptingpartialreforms insome areas, and l2 The prior authorizations of investment are numerous and ihbit startups. Inefficient operations and the lack of competition and the dockers' monopoly are amongst the issues cited inthe Bank's 2000 Private Sector Assessment Update. Since then, under E C A L 111, 60 percent o f all prior authorization for start-ups were removed. Customs documentation has been simplifiedbut the ports still constitute a major bottleneck, leading to hghcosts and delays. Goods untilrecently spent up to 18 days instorage inport because traders usedit as a substitute for inland storage. Recent reforms are reportedto have greatly reduced clearance times for goods to 4 days. buildingonpartial successesto deepenthem insubsequent operations, the support fkom the Bank andother partners was ultimately effective. Patience, perseverance and flexibility paidoff. a An important lessonfor other small emerging countries seekingto laythe foundations for sustainable growth andpoverty reduction i s the success o f Tunisia increating a competitive economy by the coordinated use o fmacro andstructuralpolicies andreforms.
P053349 | Mesoamerican Barrier Reef System (GEF) | Latin America and Caribbean | Central America |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/937121474635870611/text/000020051-20140618090100.txt | http://documents.worldbank.org/curated/en/937121474635870611/pdf/000020051-20140618090100.pdf | 1. Implementing regional projects to protect transboundary public goods is complicated by (a) processes and institutional arrangements in the Bank that are designed primarily for single-country operations, (b) differences in client country readiness and capacity, and (c) biases that favor national interests over shared regional ones.Overcoming these barriers requires flexibility in administrative processes, innovative financing to access regional financing, and educating stakeholders about the benefits of a regional approach through continuous dialogue, consultation, and outreach.2. Flexibility is needed in designing and allocating budgets to project activities to accommodate unanticipated externalities (such as climate change), to respond to new opportunities, and to meet changes in client needs during implementation.3. Regional data collection and dissemination should be demand-driven to ensure use of information and markets to pay for it.4. Alternative livelihoods must be introduced in tandem with restrictions on former resource use and closures on new entrants to the sector to reduce pressure on targeted resources. Training in alternative livelihoods must be accompanied by marketing and incubation of new lines of business.5. The private sector must be involved in setting codes of conduct for sustainable tourism and in generating investments in greener operations, but to engage the industry effectively, regulatory policies must be aligned with economic incentives.
P053357 | Rehabilitation Project | Europe and Central Asia | Albania | IBRD |  | Human Development | Social Protection & Jobs | IDA | DPF | 1998 | 1999 | 2000 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/410881474501949462/text/000020051-20140522105119.txt | http://documents.worldbank.org/curated/en/410881474501949462/pdf/000020051-20140522105119.pdf | Â· Timely support of a new, reform-minded government can yield rapid and substantial gains.
P053357 | Rehabilitation Project | Europe and Central Asia | Albania | IBRD |  | Human Development | Social Protection & Jobs | IDA | DPF | 1998 | 1999 | 2005 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/900451468768316767/text/29638.txt | http://documents.worldbank.org/curated/en/900451468768316767/pdf/29638.pdf | 5. Lessons 0 Small, focused, one-tranche policy projects with realistic objectives, supported by technical assistance, may work well intransition countries that are politically unstable and have low market economy skills (e.g., credit risk analysis for private sector banking or enforcing competitionregulations). A limited reform agendai s easier to implement, especially ifparliamentary approval i s neededfor new laws when the political landscape i s not stable. Reformcontinuity can be maintainedby similar policy or investmentfollowon projects. 0 Incrisis situations, animmediate responsecanbevaluable beyondits direct purpose. For example, the very quick preparation and disbursement o f PESC was effective inproviding development assistance and coordinating substantial humanitarianassistance. 0 PESC was disbursed against a negative list o f imports instead o f the positive list that i s usual for an emergency import credit. Disbursementagainst a negative list expedited resource transfer, which was appropriate inAlbania's circumstances. 0 As hasbeenwell documented, aid coordinationis critical to ensure appropriate, harmonizedand effective assistance where many donors are involved. Coordination should also ensure that government agencies dealing with donors are also appropriately aligned. Some institutions established for special purposes under IDAprojects such as BART, couldbe transformed into private sector commercialentities when their mandate i s complete. This transition could be an integralpart o f that organization's strategy.
P053386 | Post Conflict Reconstruction Project | Europe and Central Asia | Tajikistan | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2001 | 2001 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/442151474508972128/text/000020051-20140602105302.txt | http://documents.worldbank.org/curated/en/442151474508972128/pdf/000020051-20140602105302.pdf | Emergency projects put together in a very short time cannot be prepared with the same degree of detail as a traditional operation.Built-in flexibility to respond to unforeseen needs has to be a feature of emergency recovery projects.The usefulness of a project can be overtaken by political logic where the government considers the visibility of its interventions more important than enhancing development.In post-conflict emergency circumstances, project risks can be reduced by limiting the number of sectors addressed.
P053575 | HN- HEALTH SYSTEM REFORM PROJECT | Latin America and Caribbean | Honduras | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2002 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/211041475071292169/text/000020051-20140624191533.txt | http://documents.worldbank.org/curated/en/211041475071292169/pdf/000020051-20140624191533.pdf | Results-based disbursements can be an effective incentive for encouraging reform. Both the MOH and IHSS were dedicated to achieving the policy benchmarks so that they could receive the next disbursement. However, it is important to link disbursements not only to key policy benchmarks but also to measurable project development indicators, and to ensure that the former logically lead to the latter.When beneficiaries perceived that they have gained from a project, they can become important political allies. In this case, communities who received services through the decentralized model of health care provision rallied behind the project when it faced opposition from some labor groups. Giving beneficiaries the opportunity to be involved with decisions affecting the management of their communitiesâ€™ health care services enhanced their understanding of their rights to demand and to receive services of higher quality.Lengthy project preparation periods, although costly, can prove effective and efficient in the long run. The lengthy preparation of this project ensured buy-in from various institutions, and it provided for meticulous and well-sequenced design of the policy reform agenda.
P053578 | Social Investment Program Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2003 | 2011 | 2014 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/488371475071197817/text/000020051-20140625074459.txt | http://documents.worldbank.org/curated/en/488371475071197817/pdf/000020051-20140625074459.pdf | The following lessons are drawn from the ICR with editing and some modification.. (a) Community-Driven Development Projects need time to mature before being rapidly expanded in scope and financing. An adequate assessment of the implementing agencyâ€™s capacity for a Community-Driven Development Project is required. An agency with a weak capacity will not be able to effectively manage a rapid expansion in the scope of its activities and funding. Moreover, the addition of responsibility for addressing needs of logistically difficult areas, such as those affected by natural disasters, will add further strain on institutional capacity.(b) The fiduciary accountability of a Community-Driven Development operation is more likely to be assured when a community financing model is employed that provides (i) improved access by the hard core poor and poor, including women, to financial services; (ii) social auditing and community assessment mechanisms; (iii) a governance and accountability action plan; and (iv) an independent process monitoring system in order to ensure timely addressing impediments as well as learning.
P053578 | Social Investment Program Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2003 | 2011 | 2016 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/260981468305401859/text/106442-ppar-P053578-P157940-PUBLIC-bangladesh-2016.txt | http://documents.worldbank.org/curated/en/260981468305401859/pdf/106442-ppar-P053578-P157940-PUBLIC-bangladesh-2016.pdf | 11. Lessons Â· In rural areas, where citizens lie outside the reach of the state, facilitating the formation of strong institutions is fundamental to enabling the poor to access different sources of social and economic prosperity. The Social Investment Program transformed its approach to institution building at mid-term by ensuring that institutions were inclusive and responsive to the felt needs of the poor. This approach was reflective of the more effective design of rural livelihood programs under implementation elsewhere in the region at the time. Â· Gender inclusion, including female leadership, in village development programs is a positive but insufficient tool to ensure high quality, sustained and effective leadership over a multi-year program period. Evaluations of CDD programs have shown that for leadership to be effective, it should be (1) rotated amongst members; and that (2) leaders should have the requisite time needed and demonstrate a high level of commitment towards nurturing the less well-off group members (with regard to savings, lending, and investment behavior). Elite female members of society have the ability to extend access and information to group members, but they also may lack the time and dedication needed to ensure effective implementation of the group goals. Â· CDD projects offer a ready platform for outreach to disaster-affected populations, but additional disaster-related activities require thorough assessment of an implementing agency's capacity to adapt, to manage quick influxes of AF, and to reach disaster-affected populations outside of a project area. The Social Investment Program provided a relevant and ready platform to respond to two successive natural disasters, but the SDF required rapid retooling to be able to respond to the crises in a timely way. The needs of crisis victims also differed significantly from those of other project beneficiaries. This complexity, related to the need to manage these dual streams, requires strategic management and a reconfiguration of service delivery mechanisms, project metrics, and monitoring and reporting means.
P053615 | THAILAND-FIN.COMP.RESTR.LN. | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1998 | 2000 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/754751475088162347/text/000020051-20140522105925.txt | http://documents.worldbank.org/curated/en/754751475088162347/pdf/000020051-20140522105925.pdf | (1) The Bank should have looked for root causes of the problem from the first, rather than focusing on the outcomes of the crisis. (2) The Bank needs more flexibility in dealing with crisis situations. Staff were required to spend much of their time producing and polishing reports, rather than in activities directly aimed at solving the crisis. (3) The division of labor between the Bank and the IMF in working on this operation limited the Bank's effectiveness (the Bank was responsible for work with the finance companies, the Fund for working with the banking sector). The IMF was unduly optimistic about the health of the banking sector, and the Bank could have contributed to diagnosing and remedying the banking sector problems. (4) Institutions set up to address sector problems should have mandates of appropriate breadth. The mandate of the FRA was too narrow, and a broader mandate (to pursue loan workouts with weak but still viable finance companies) would have been more efficient.
P053615 | THAILAND-FIN.COMP.RESTR.LN. | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1998 | 2006 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/960941468173356799/text/350510REV0pdf.txt | http://documents.worldbank.org/curated/en/960941468173356799/pdf/350510REV0pdf.pdf | Lessons Learned 5.1 The significant cost o f cleaning up financial crises can offset the progress made over many years inpoverty alleviation and other social improvements, both o fwhich are central to the Bank's mandate. Giventhis, the Bank should continue to play a role in client countries inboth improving financial sector governance and soundness to reduce the probability o f crisis and inpost-crisis management and well-structured recovery. 5.2 The severity o fthe crisis was, inretrospect, initiallyunderestimatedbythe Bank and others, as was the negative impact on the economy o fthe large scale closure o fthe FCs inthe early phase o f the reforms. Thai officials interviewed by the IEGmissionnoted that these earlymis-readings o fthe severity o fthe crisis andthe impact o f the closure o f the FCs on the economy raisedconcerns about the credibility o f the IFIS'approach and, most important to Thailand's future, about the financial reform itself. This suggests that crises inother countries should be approached more comprehensively, taking into account potential negative impacts o f large scale closures. 5.3 Short-term crisis management policies can compromise essential structural reforms. The failure to factor into the design o f the reforms the inadequacies o f the Thai legal and regulatory infrastructure led to approaches that may have increasedthe cost o f cleanup. For example, traditional procedures inThailandfor corporate restructuring were notoriously slow and generally benefitedthe debtor; thus, the corporate reorganization procedures modeled after the UnitedStates (Chapter 11style) were ill-suited to the situation and may have served to worsen it (longer-delays, reducedrestructuring). A betterapproachwould havebeento simplify liquidationprocedures, involvingthe stakeholders and a bankruptcy administrator, rather thanthe court system. 5.4 The sequencing andtimingo freforms i s critical. Too little early emphasis was placed on reformingbankruptcy and foreclosure laws, developing a deposit insurance scheme, and fostering development o f capital andmoney markets. The governmentthat came to power just after the crisis emergedwas reform-minded, but the adverse macroeconomic impact o f the earlypolicy changes gave reform a badname inThailand. 5.5 The allocation ofpieces o fthe reform package among the three International Financial Institutions (IFIs) may have made sense, but only ifit hadbeen followed by better coordination. As it turnedout, the division o fresponsibilitiesresulted inan absence o f a clear guidingvision for the reform o fthe financial system. Thus, for example, commercialbank restructuringwas carried out very differently from finance company restructuring, even when they suffered from the same problems. Inaddition, the division o f labor broke down, as the Bank fairly quickly became involved inFIrestructuring and capital market development. 5.6 Succeeding loans with increasinglybroader goals and a growing list o f conditions diffusedthe focus o freform andunderminedmeaningfulmonitoring; abetter approach would have been the programmatic one now usedwidely (but not available at that time), which seeks to develop a coherent set o fpriority reforms and sequences the steps for carrying out those reforms ineach successive loan.
P053616 | TH-Fin Sector Impl. Assist. | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/190821475070122201/text/000020051-20140612132859.txt | http://documents.worldbank.org/curated/en/190821475070122201/pdf/Thailand-Financial-Sector-Implementation-Assistance.pdf | In a project initiated in an urgent situation, the Bank needs to make a strong effort to assure that adequate expertise in the areas of procurement and disbursement are available in the implementing agencyCountry Development Partnerships comprise an effective vehicle to enhance sustainability and maintain the momentum of reform
P053705 | NI TRANSPORT II | Latin America and Caribbean | Nicaragua | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Highly Satisfactory |  |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/874701474850064737/text/000020051-20140613082443.txt | http://documents.worldbank.org/curated/en/874701474850064737/pdf/000020051-20140613082443.pdf | The project indicates several lessons, the most important of which are:1. Importance of sustained IDA presence. IDA's continued presence has improved MTI performance, understanding, proactivity and effectiveness in the transport sector.2. Importance of borrower's donor coordination. Part of the project's success is due to successful donor coordination, IDA, IDB, DANIDA, which leveraged all financial aid to coordinate and ensure the effects of assistance.3. Micro enterprise is a highly successful, culture-syntonic method of routine maintenance in Nicaragua. It combines frequent surveillance of road conditions, timely and cost-efficient maintenance actions, emergency response, and an income-generating employment opportunity.
P053705 | NI TRANSPORT II | Latin America and Caribbean | Nicaragua | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2005 | 2007 | PPAR | >=25 million & <50 million | Highly Satisfactory |  |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/144311468061745009/text/398680NI.txt | http://documents.worldbank.org/curated/en/144311468061745009/pdf/398680NI.pdf | 3. Conclusion and Lessons 3.1 The project has made gradual but impressive progress in modernizing Nicaragua's road sector institutions. The organizational roles-owner, administrator, manager, supplier-have been clarified and road management methods and data support systems developed. Parallel to these organizational and technical developments, staff i s being effectively trained to apply the new techniques. 3.2 This project provides an impressive array o f accomplishments in institutional development. The transformation process from a large force account entity to a modem road administration with private sector supply o f most services i s not, however, complete. While every country must find i t s own development path, some precursors to a successful future evolution are visible. The first i s the articulation o f the relationship and division o f responsibilities between the RMF, the road administration (consolidated directorates dealing with roads and highways), and the ministry. The second, perhaps concurrent task i s the dismantling o f the government-owned Regional Highway Construction Agencies (COERCOs). There may be alternatives; the COERCOs can first be corporatized and then privatized, or they may be transformed into the road administration's regional offices. The continued reorganization o f the road sector i s a sensitive undertaking in which the consultative approach employed in the f r s t and second road projects will be o f great service. The third i s to increase the coverage o f the road data information system to all roads, whether maintainable or not and to make provision for a bridge management system. This i s necessary for the effective use o f the budget and the provision o f equitable road access. In general terms, the project experience highlights the importance o f two factors\. Government Commitment Crucial 3.3 The IDA-Government partnership improved MTI's performance and its ability to be proactive in the transport sector. An important part o f this partnership was the close and effective supervision o f the project. Through this partnership government professionals carried out a successful experiment using adoquines stabilization in long road segments in rural areas. A similar supportive approach was used in developing environmental awareness within the GoN and gaining acceptance o f the scope o f activities needed to appropriately address environmental safeguard issues. A further facet . o f GoN's commitment and high principles was the establishment o f an integrated project coordination unit, which evolved in confidence and showed solid ability in achieving donor coordination. The project's success, in part, i s due to this strong cooperationGoN with IDA, IDB, DANIDA-which ensured the effective utilization o f assistance. Participatory Approach 3.4 Both Bank and borrower had already attached great importance to community participation in the preceding road project in Nicaragua. Social inclusion was seen as a key element to develop the effectiveness o f the road administration to gain acceptance o f budget-constrained multi-year road programs and the GoN hlly supported this approach. Micro-enterprises were established, at first as an experiment under t h i s project, but these enterprises proved to be a highly successful and culturally appropriate method for routine maintenance. The use o f micro enterprises was thus substantially expanded. They combined frequent surveillance o f road conditions, timely and cost-efficient maintenance actions, an effective emergency response system, as well as an income-generating employment opportunity. For periodic maintenance, the participation o f conventional road construction and maintenance companies was initiated, and the new strategy i s gradually leading to the replacement o f the old labor construction unit service delivery. 3.5 nsummary the main lessons learned fiom this project are\. I A combination o f strong borrower commitment to attain agreed development objectives, coupled with innovation and a flexible approach, can lead to a successful project outcome despite the occurrence o f a natural disaster. 0 nhighly vulnerable countries road system planning that better accounts for I disaster eventualities needs to be promoted. 0 A participatory approach supported by capacity strengthening initiatives can be highly successful in developing a new and evolving road management organization. Transforming a country's road administration i s a gradual process and needs to be customized to the particular culture and circumstances prevailing in the country to be truly successful. The experience with the use o f the pilot adoquines (manufactured paving stones) road sections shows that this technical solution can be highly costeffective with unexpected benefits for employment and socioeconomic welfare. I t s use should be M e r promoted and replicated.
P053706 | SECOND ROADS REHAB | Latin America and Caribbean | Panama | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2000 | 2001 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/232991474512438885/text/000020051-20140529161051.txt | http://documents.worldbank.org/curated/en/232991474512438885/pdf/000020051-20140529161051.pdf | None.
P053796 | Flood Emergency Project | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/871961474595054084/text/000020051-20140615102006.txt | http://documents.worldbank.org/curated/en/871961474595054084/pdf/000020051-20140615102006.pdf | The ICR offers some useful lessons of wider applicability which this review endorses and expands upon:Emergency recovery projects should not be limited to restoration efforts only. Considerable attention should be given to causes, mitigation, and the longer term. While a timely Bank response was important in the immediate short term, the IEG study, Hazards of Nature, Risks to Development, finds that accelerated project processing is not always desirable. For some projects, rushed appraisal has led to long pauses between loan approval and first disbursement, poorly designed interventions, and diminished poverty impacts. A clear discussion upfront with the Borrower of what a Bank Emergency Recovery Loan can and cannot do is critical. Given the broad scope of many reconstruction projects, the project timeframe should be determined based on the scope and scale of restoration works, the complexities involved, the capacity of the country and implementing agencies, and the extent of risk reduction activities. Adequate time is needed to design a detailed project and clarify implementation arrangements to avoid post-effectiveness delays.
P053830 | Sustainable Forestry Pilot Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2010 | 2011 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/297391475080364078/text/000020051-20140624192153.txt | http://documents.worldbank.org/curated/en/297391475080364078/pdf/000020051-20140624192153.pdf | The ICR derives the following well-considered lessons:â€œDuring rapid changes to policy and institutions, providing just-in-time policy advice is more helpful to counterparts than large consultancy contracts, which in this case were stalled by a quality and cost-based selection method. Rapid policy and institutional changes rendered existing terms of reference redundant and revising them created even longer delaysâ€ (ICR, p.16) â€œModernizing forest harvesting and processing remains relevant for Russian forestry enterprises, but the Project demonstrated that on-lending under a Bank-funded project may not be the best instrument to achieve this objective. Much effort, possibly beyond the scope of a 5-year Bank-financed project, is needed for a commercial or state-owned bank to adapt to World Bank procurement procedures or to fully understand the focus on Development Objectives and need to follow the Bankâ€™s safeguards policies. Furthermore, if forest enterprises have affordable access to commercial credit, a Bank-funded State loan program, with complex requirements and slow procedures, is not competitiveâ€ (ICR, p.16). IEG adds a further lesson:Bank and Borrower share a responsibility to cancel or restructure loans when Project Development Objectives become less relevant.
P053832 | Egypt - Private Sector and Agriculture Development | Middle East and North Africa | Egypt, Arab Republic of | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/120731474899210150/text/000020051-20140613044441.txt | http://documents.worldbank.org/curated/en/120731474899210150/pdf/000020051-20140613044441.pdf | The main lessons, all for the Bank, are:Seek to Understand and Take Account of the Project's Social, Political and Capacity Environment: Realistic assessment is needed, both during project design and implementation. Full Project Preparation, Including Actions Needed to Start Implementation is Key to Success: Where there are gaps in preparation, the degree of impact on project implementation should be assessed, and the timing of negotiations and Board presentation adjusted as needed. Legal Covenants and Conditions for Effectiveness are Poor Substitutes for Completed Actions: Including a legal covenant to make up for an aspect of a project that is not prepared is not an effective solution, especially when this expedient is employed repeatedly for the same project. Take Decisive Remedial Actions Early, Including Project Closures as Necessary: Decisive action, based on realistic assessment, should be made as early as possible when a project is not performing.
P053834 | Implementation of Economic Reform and Development Program | Middle East and North Africa | Jordan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2003 | 2012 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/347741474892980167/text/000020051-20140625220947.txt | http://documents.worldbank.org/curated/en/347741474892980167/pdf/000020051-20140625220947.pdf | IEG agrees with the lessons highlighted in the ICR. especially the importance of strong Government commitment to the reforms for the success of the program, the need for a centralized privatization agency, and the need to focus on managing potential conflicts arising from privatization and reforms. In addition to these lessons, the experience of this project highlights the importance of gathering sufficient baseline data that would allow a comprehensive assessment of the program's effectiveness, especially in the context of technical assistance projects. In particular, baseline analysis of capacities of Government agencies responsible for reforms could have helped to understand the gaps that the project was filling, and its contribution to improved implementation of Government economic programs.
P053892 | Health System Development Project (TF023455) | Middle East and North Africa | West Bank and Gaza |  |  | Human Development | Health, Nutrition & Population | SPF | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/329151475076496488/text/000020051-20140613080204.txt | http://documents.worldbank.org/curated/en/329151475076496488/pdf/000020051-20140613080204.pdf | Successful implementation is feasible even under conflict situations and political turmoil, when the project design is uncomplicated, the borrower committed, and intensive supervision is provided (as in this case the Bank TTL was moved to the field).With complex HMIS projects it is essential first to build capacity in the client so they can truly manage the process, are knowledgeable of the products to be produced, and able to use them subsequently in analysis and planning. The technical programming and software development should then be outsourced to specialized, reputable firms.To enable the counterparts to fully understand and able to manage the project, it is helpful to produce (prior to implementation) a clear, integrated, logical action plan that pulls together the different components of the project, and demonstrating their relationship and impact on one another.
P053985 | GZ-BETHLEHEM 2000 | Middle East and North Africa | West Bank and Gaza |  |  | Infrastructure | Urban, Resilience and Land | SPF | IPF | 1999 | 2004 | 2004 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/869481474509402537/text/000020051-20140612101848.txt | http://documents.worldbank.org/curated/en/869481474509402537/pdf/000020051-20140612101848.pdf | With force majeure, such as the September 2000 intifada, that points to the difficulty of achieving the original project objectives, those objectives should be revised as soon as possible and in an explicit manner so that all parties are fully cognizant and supportive of a new direction that project has to take.Much more could probably have been achieved in the areas of marketing and sponsorship if the private sector had been more closely involved at an early stage of the project.Even during a period of crisis, close Bank supervision is possible as long as adequate local leadership exists and Bank teams are sensitive and responsive to the acute problems such leaders face. Initially, the Bethlehem 2000 Authority's leadership proved crucial to the success in launching the Celebrations.
P054051 | Solid Waste and Environmental Management Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | SPF | IPF | 2001 | 2010 | 2010 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/778631474509091258/text/000020051-20140620080359.txt | http://documents.worldbank.org/curated/en/778631474509091258/pdf/000020051-20140620080359.pdf | Among the numerous useful generic lessons indicated in the ICR, the following are particularly worth highlighting: 1. In conflict situations, it is advisable to seek out and build on the common interests (e.g., in this case, effective environmental control) that may exist beneath the conflict per se. 2. Individuals can and do make a significant difference and contribute to project success; thus seeking out and strongly supporting capable professionals is important. 3. Effective channels of public communication and feedback support sustainability and should be built into project design. 4. Investment in changing the local culture can be as important as physical investments, if not more so. 5. SWM can serve as an effective entry point for improving municipal management and service delivery more generally. 6. Early preparation, consensus building and shared learning can pay significant dividends farther down the road. 7. Consistent, thoughtful, and dedicated on-the-ground Bank supervision can make the difference between success and failure. In addition, IEG would add the need to give adequate attention during preparation and supervision to ensuring that adequate monitoring and evaluation systems are designed and put in place.
P054119 | Bahia Health System Reform Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2003 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/689701475088713730/text/000020051-20140624160014.txt | http://documents.worldbank.org/curated/en/689701475088713730/pdf/000020051-20140624160014.pdf | 1) Preparing the required operational tools should be a condition for project effectiveness listed in the legal agreement. Tools such as the operational manual are needed to implement a project and should be ready before a project becomes effective.2) Sector managers should assign task team leaders with the necessary technical and professional background to more complex projects. This is particularly important at the outset of a complex project, when the bulk of procurement activities should take place.3) Family medicine reforms should be implemented in a comprehensive way, including reforms in HR, organization, financing, equipment and construction.
P054120 | BR: AIDS & STD Control II | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2003 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/705921474649474074/text/000020051-20140612133424.txt | http://documents.worldbank.org/curated/en/705921474649474074/pdf/000020051-20140612133424.pdf | Even when Bank funding comprises a small proportion of overall program financing needs, this financing can be a catalyst for change.Lack of adequate M&E of project investments makes it difficult to assess program progress and effectiveness of interventions.While partnering with NGOs to reach many population groups not normally reached by the health system, and to give the program greater accountability, has proven to be a very effective approach, working with NGOs constitutes a significant management challenge both to ensure technical quality of projects and to develop mechanisms to ensure their sustainability.Transferring management and financing for HIV/AIDS activities to states and municipalities and focusing on outputs and outcomes rather than inputs clearly places implementers in the driver's seat and ensures accountability for their actions.Targeting resources on a priority basis to the highest-incidence areas is a successful strategy to combat the epidemic in the short-run. However, programs should combine this approach with broader, equity-based formulas to ensure that resources reach more difficult-to-reach low-income and rural populations. Providing ART free of charge is not enough to make everyone come forward for treatment. Limited physical and social access to treatment are also important impediments.
P054120 | BR: AIDS & STD Control II | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2003 | 2004 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/123571468770493272/text/ppar0288190portuguese.txt | http://documents.worldbank.org/curated/en/123571468770493272/pdf/ppar0288190portuguese.pdf | 6. Findings and Lessons 61 Failure to establish critical baseline data on HIV infection rates and on behaviors among high-risk and general population groups, and failure to undertake systematic surveillance to document trends in HIVand behaviors in both of these groups make it dif'jcult to track the evolution of the epidemic over time and to evaluate the effectiveness and impact of program interventions. While Brazil has implemented many innovative and theoretically cost-effective interventions, evidence of the actual costs, effectiveness and impact of its efforts is lacking. AIDS I and II have had limited successin strengthening Brazil's surveillance of HIV infection and of behaviors among priority populations. This has undermined Brazil's ability to evaluate the impact of its prevention efforts on behaviors and on the epidemiology of the disease. In the absenceof fully functional systems for routine monitoring of epidemiological and behavioral trends, Brazil has been forced to rely on indirect tools (ad hoc research and studies, often covering different populations, timeframes and geographical regions) to gain an appreciation of program performance and impact. 62 Inadequate data on the size and coverage of target populations for the prevention and treatment programs, respectively, especially at the state and local levels, undermine the efficiency and effectiveness of HIV/AIDS interventions. The size and coverage of high-risk groups for prevention are not adequately documented in Brazil making it difficult to establish viable targets or to estimate the'level of effort and resourcesneeded for effective intervention. While there are national estimates of the size of MSM and IDU populations, these are rudimentary at best and not meaningful at state and local levels. Baseline surveys were planned at the projects' outset, but never carried 29 out. By the same token, the effective coverage and accessof the treatment program (as a proportion of ARV-eligible persons) is not known. Baseline surveys, promotion of VCT services, improved outreach and integration of HIV/AIDS interventions with other health services are all critical in this regard. 63 Early, rigorous and sustained prevention efforts are likely to keep the pool of I&V and AIDS patients small relative to the counterfactual, and thus to reduce the burden on a country's health system and make treatment and care more feasible and affordable. It is plausible from available (albeit limited) data that prevention activities undertaken over the past 15 years in Brazil may have contributed to containing HIV infection rates and the number of new AIDS cases,thus averting a scenario of more rapid spread and the transition to a generalized epidemic. Over and above the avoidance of the devastating consequencesof HIV/AIDS on individuals, families, communities and on the country's development prospects overall, the number of HIV infections and AIDS cases averted (as reflected in declining incidence) has reduced significantly the costs and challenges of providing adequatequality and coverage of treatment and care. Simply put, the continued success and affordability of Brazil's treatment and care program depends critically on the success of its prevention efforts. 64 NGOs have a critical role to play in thefight against HIV/AIDS. In Brazil NGOs have proven highly effective in reaching stigmatized and marginalized groups making available to them both prevention and care services, for which they have a comparative advantage vis-a-vis public services. Their target populations constitute the three highest-risk groups that constitute the top priority for the prevention program\. MSM, IDUs and CSW. They have also demonstrated their effectiveness in serving as an interface between vulnerable groups, such as the poor and women, and the public services with a view to improving accessand utilization. They also continue advocacy work. 65 Even when financing a relatively modest share of the overall costs of a well- l establishedprogram, Bank support to HIV/AIDS efforts can make significant contributions to program expansion and capacity building when it is strategically . allocated. While financial support provided under AIDS I and AIDS II amounted, respectively, to only about 30 percent and 10 percent of national expenditure on STDs and HIV/AIDS during their respective implementation periods, such support was channeled to the most cost-effective components, as indicated by evidence amassedon international experience evaluated thus far (World Bank 1997). AIDS I and II devoted significant financial and technical support to the design and delivery of prevention activities, including innovative, state-of-the-art interventions aimed at changing the behavior of high-risk groups, aswell asto the expansion and promotion of counseling and testing services. Bank support to improvements and expansion of treatment and care was selective and strategic, focusing on the establishment of lower-cost alternatives, including an increasing shift to outpatient care, and on improving service quality through capacity building of service providers and of the laboratory network. These inputs combined with Brazil's achievements in significantly lowering the cost of ARVs have lowered the cost of care and treatment and improved the quality of these services. 30 66 Bank support can bring legitimacy and leverage to controversial activities and to stigmatized segments of society. The strategic orientation of Bank's assistance\.(a) has provided leverage in mobilizing additional national resources for HIV/AIDS activities at all levels of government, especially for controversial prevention interventions such as needle exchange programs; and (b) has been instrumental in securing respect and legitimacy for marginalized or stigmatized groups who were both implementers and beneficiaries of Bank support (e.g., commercial sex workers, prisoners, transgender persons and MSM, IDUs, people living with HIV/AIDS and their advocates). 67 A research program that is ad hoc and uncoordinated in its conception is likely to generate a large volume of information and data that will be difficult to interpret and usefor measuring and improving program performance and impact. While the researchprogram in Brazil has produced considerable information and data, it has not been possible to derive trends in the epidemic and in behaviors or insights on other aspects of program performance. Brazil's HIV/AIDS program would have benefited from a master plan for research, conceived to support its strategic objectives, both (a) in the choice and prioritization of topics for studies and operational research, and (b) in the standardization of methodology that would have accommodated the analysis of data across studies and of trends over time. 68 Project design and conditionality can be strategic in initiating and supporting institutional innovations which are capable of expanding and using more fully program implementation capacity, most notably\. (a) use of public monies to further stimulate and mainstream the contracting of NGOs to work on prevention and care/treatment, in line with their comparative advantages;(b) the creation of state and municipality level HIV/AIDS and STD Coordination Units, the funding of locally developed work program proposals that would be the subject of formal agreements (contracts) between respective Coordination Units and the NASCP, and the Co-financing of overhead costs and inputs by local governments; and (c) the funding of multisectoral responsesfor prevention and human rights promotion with Ministries of Education, Justice, Interior, among others. These innovations (described in paragraph 2.3-2.6)have served to solidify and expand partnerships with civil society and with other development sectors and local government and are being consolidated and institutionalized. 7. Future Directions 71 Over the past five years OED has distilled the experience of the World Bank in Biazil through a number of reviews that are relevant to the fight against HIV/AIDS.28 Taken together, these reviews point to a number of challenges for poverty alleviation and health sector development in Brazil over the coming years. They highlight the importance of\. improving M&E to measure performance and impact and thus to improve effectiveness and outcome; reaching poor marginalized groups and regions (especially the North and Northeast); and sustaining and further improving public-private 28. These reviews include most notably\. the Country Assistance Evaluation\. Brazil of May 15, 2003, The Brazil Health System\. Impact Evaluation Report of June 30, 1998, Brazil Maternal and Child Health of February 26, 2002, and NGOs in World Bank-Supported Proiects in Brazil\. A Background Paper for OED's Study of NGOs in World BankSupported Projects of July 29, 1999. 31 partnerships. The decade of experience of Bank support to HIV/AIDS in Brazil resonates with themes and recommendations raised in the previous OED reports. With the imminent launch of a third Bank-financed loan for HIV/AIDS in Brazil, whose design has incorporated many of the lessons of the past decade,the following suggestions for further improving the development effectiveness of HIV/AIDS efforts in Brazil are offered. 72* First andforemost, Brazil should take the necessary steps to improve its capacity and incentives to monitor and evaluate program performance and impact and to document the cost-effectiveness of program efforts. * First, in line with UNAIDS guidelines (UNAIDS 2000 and 2002), Brazil should continue refining and expanding its surveillance efforts to enable the routine and systematic monitoring and analysis of trends in HIV infection as well as trends in behaviors among key populations. Second generation surveillance systems are designed to permit the analysis of behaviors both to anticipate and to explain trends in HIV infections. Given the current status of the epidemic in Brazil (still concentrated among populations with high risk behaviors, with heterosexual transmission being the primary and growing mode of transmission), the surveillance of HIV infection and of behaviors should focus on high-risk groups with more than 5 percent infection rates (MSM, IDU, CSW) and should also monitor trends in the general population, paying particular attention to links between thesetwo groups, particularly through bridge populations (female partners of IDUs and bisexuals and clients of CSW), and to consequent risks of rapid spread of the virus in the general population. HIV and behavioral surveillance of high-risk groups should be carried out on a regular basis and may be most efficiently executed at the decentralized level with a view to facilitating more in-depth assessmentof local-level issues and trends and improved responses. AIDS III is supporting Brazil in its efforts to exploit fully the voluminous data currently available through ad hoc studies and surveys and through the health information system, but this will not eliminate current and future needs for systematically collected data on HIV and on behavior of key populations. NASCP's plans to carry out a national sexual and risk behavior survey in 2004 to update the 1998 baseline survey (CEBRAP 2000) is an important step in this regard. Second, the time is ripe to design a monitoring and evaluation system and strategy that is decentralized and results-based\. (a) the recently adopted fund-to-fund transfer mechanism for supporting HIV/AIDS in states and municipalities is based on the principle of results-based planning and management; (b) as noted earlier, local level public sector staff and NGOs have expresseda strong demand for good and meaningful M&E indicators, guidelines and training to enable them to track and improve their performance and impact; and (c) the new government is very committed to the design and implementation of a results-based approach to development programs. Such a system should establish baseline data on the size and current program coverage of target populations at the state and local levels to permit realistic target setting and effective monitoring and evaluation of program performance, as well as to assessthe level of effort and resources needed for a successful program. The monitoring and evaluation system should also accommodate the need for systematic evaluation of interventions implemented by NGOs against 32 program targets set at the national, state and local levels. Government comments (provided in Annex G) highlight recent achievements and ongoing efforts to redefine the M&E strategy for HIV/AIDS in favor of a more decentralized and results-based orientation, and note the continued support of CDC and the World Bank to this end. Of particular note are (i) the recent establishment of five sites of excellence in each of Brazil's five regions to foster and promote M&E activities at the decentralized level; and (ii) the development of postgraduate training in M&E of STD/HIV/AIDS designed to foster decentralization and institutionalization of M&E activities. 0 Third, the government should commission studies to document systematically the cost-effectiveness of program components and pilot interventions through (a) the design and active direction of a researchprogram that emphasizes cost-effectiveness and impact analysis; and (b) the solicitation and exploitation of considerable research capacity available in Brazil in the disciplines of economics, epidemiology (especially HIV incidence research) and sociology. Studies should prioritize the evaluation of the cost-effectiveness of current interventions aimed at MSM, IDUs and CSW. Such a program should be iterative in the sensethat it should both influence and monitor a continued fine-tuning of interventions and approachesthat will enhance costeffectiveness and improve the efficiency of resource allocation. Cost-effectiveness analysis will also be useful to other countries looking to build their HIV/AIDS programs on the experience of Brazil's long-established and innovative programs. * Finally, rigorous monitoring and evaluation of Brazil's treatment program is critical, both becauseit will allow Brazil to track and improve the effectiveness and impact of its treatment and care program, and becausethe Brazilian experience, well documented, will provide guidance and insight to many other countries seeking to establish or strengthen national treatment programs. Monitoring and evaluation of the treatment program should encompass\. behavior and compliance of those under treatment and their long-term effects on transmission, drug resistance, effective coverage, and equity in accessto services and in adherence. 73. In the meantime, in order to further consolidate and sustain Brazil's fight against HIV/AIDS and to achieve maximum impact, NASCP leadership must mobilize human andfinancial resources around the highestpriorities of the program, as evidenced by international experience to date. Government support to prevention should remain strong, ensuring that it is accorded highest priority. This will remain a challenge, especially as Brazil's treatment policy is mandated by the constitution and has a strong public constituency, whereas the many positive externalities of prevention are typically less appreciated by the public. Prevention efforts must continue to target behavior change in high-risk populations (MSM, IDUs, CSW) and expand efforts to better target emerging vulnerable groups (such as women, the poor, rural/interior populations). In addition, efforts to improve and expand surveillance, diagnosis and treatment of STDs, including enhancedoutreach and targeting, must be renewed and intensified as this package of activities constitutes a critical element of an effective prevention strategy. Sustained efforts are also neededto monitor and contain (if not reduce) the costs of care and treatment, as well as to ensure adequatefinancing of such services, all in the face of changing costs and technologies. By their very nature, public goods provision should be a priority for Government support, most particularly\. 33 surveillance, research,monitoring and evaluation, capacity building and institutional development, and sustained support/development of the laboratory network. 74. In light of the trends of the epidemic, which indicate a spread to bridge populations, many of whom include women, poor populations, and rural/interior populations, equity will become an even more important objective of the national HIV/AIDS program as it attempts to reach these groups. This being said, there is also a need to continue and intensify targeted behavior change interventions aimed at highestrisk groups (MSM, IDUs and CSW). Both prevention and care and treatment interventions were relatively easy to mount when high-risk and affected populations were concentrated for the most part in and around the South and Southeast Regions and in urban areas. Both NGOs specialized in reaching high-risk target groups (MSM, IDUs, CSW) and health services responsible for monitoring and treating those affected by HIV and AIDS were more readily available and generally capable of providing needed services. This being said, only coverage of MSM is satisfactory at 96 percent. Considerable effort needs to be made to increase the coverage of IDUs (roughly estimated at 18 percent) and of CSW, whose effective coverage by the program is not known (Ministry of Health/NASCP draft final evaluation). Equity has been an important principle of the program from the outset and will become an increasingly challenging goal in the future. The emerging vulnerable groups are considerably harder to reach by nature of their locations and their status in society; and they do not typically seek out social support and services, even where they are available. More effort needs to be made to improve coverage of HIV/AIDS interventions especially in the Northeast (seeTables F-7 and F-8, Annex F). Furthermore, women and the poor should not be addressed, respectively, ashomogeneous groups given that subgroups within each of these categories are exposed to a spectrum of risks according to the multiplicity of situations and vulnerabilities of these subgroups. Operational researchand concerted efforts to effectively reach these groups will be a major challenge of the program. 75. Given the maturity of Brazil's HIV/AIDS program and its emerging challenges, consolidation and decentralization of the institutional framework for the figkt against HIV/AIDS and STDs should bepursued with a view to strengthening the capacity of state and municipality HIV/AIDS units to assume considerably increased responsibilities for strategic program management, oversight and implementation, as well asfor managing partnerships with civil society and local level government. Such activity might be underpinned by the undertaking of an assessmentof the overall institutional and organizational framework for the fight against HIV/AIDS (at all levels of the system) in light of decentralization and other reforms and in light of its emerging priorities. Such an assessmentwould be complemented by state/municipal-level assessmentsof opportunities for improved public-private partnerships. On the basis of these assessments,fine-tuning of the organization, mandates and staffing of different levels of the program, and of mechanisms for partnerships could render program efforts more efficient and cost-effective. Local level establishment of more operationally relevant baseline data on program coverage and performance is needed to facilitate both the setting of targets and the monitoring and evaluation of program performance. Instruments and processescan be improved to evolve more fully towards performancebased management. Pedagogical supervision and accountabilities need to be strengthened considerably. 34 76 Now, more than ever, efforts should be devoted to the integration of HIV/AIDS and STD control activities into the SUS, particularly special programs within the SUS, such asfamily health and reproductive health. It will be impossible to make significant headway in reaching the emerging target groups and vulnerable populations (women, the poor, rural/interior populations) of the program unless basic health services are more accessible to them and more fully utilized. This is indeed a formidable challenge, which will require improvements to the quality, coverage, equity and outreach of priority health programs and services. Improvements to HIV/AIDS work and to health system performance, especially primary health care and public health, can and should be simultaneous and synergistic. 77 NASCP should intens@ efforts to encourage afuller utilization of CTA l services now available in the country. Most people in Brazil who are infected with HIV are not aware of their seropositive status. An important contribution to prevention efforts is for people to be aware of their status and to take necessary action both to seek treatment and care and to prevent the transmission of infection to their partners. 35
P054125 | Ozone Depleting Substances Phase-out Project (Montreal Protocolo) | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 1999 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/596111475785685563/text/000020051-20140617131724.txt | http://documents.worldbank.org/curated/en/596111475785685563/pdf/000020051-20140617131724.pdf | The main lessons are:1. The National Phase-out Plan, which takes account of the broad national picture, leads to greater and more timely success than following an individual project-by-project approach. The Plan, supported by UNDP in Colombiaâ€™s case, gives the Government both responsibility and flexibility through performance-based agreements. This allows the Authorities to adapt specific operations to the country and sector context, and to ensure a close fit between individual investments and broader policy level actions.2. The umbrella approach adopted in the subprojects is appropriate since it achieves economies of scale and accelerates the pace of conversion in a given sector.3. The phase-out achievements in individual sub-projects must be underpinned by an appropriate regulatory framework to control imports and consumption of ODS. This was accomplished in Colombiaâ€™s case.4. In most countries, there is room for only one international agency as the main policy interlocutor on Montreal Protocol issues. Despite the success of the Bank-supported subprojects and generally good rapport with the Government, it is UNDP, rather than the Bank, which is the lead MP external partner in Colombia. As implementing agency for the NPP and the principal provider of institutional support on ODS phase-out, UNDP has a higher and more productive level of policy dialogue on MP issues with the Government than does the Bank. 5. The indicative ceiling approach to MP grants is appropriate since it enables a flexible response to changing circumstances.6. Close supervision and oversight by the relevant government agency are critically important since relatively small problems can delay implementation for months.7. Documentation and reporting requirements for the MPMF are extremely rigorous and time consuming. As the Government points out in its comments, it would be beneficial to consider easing some of these requirements especially in the case of small and medium-sized beneficiary enterprises.
P054208 | INST.DEV.& PUB. ADM. | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1998 | 1999 | 2007 | PPAR |  | Highly Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/242361468764124440/text/303960RY.txt | http://documents.worldbank.org/curated/en/242361468764124440/pdf/303960RY.pdf | 7.5 The primary lessons learned from these projects are\. That in a post conflict, country unification situation such as Yemen's, to avoid fruitless expenditure and wasted resources, additional r i s k analysis i s appropriate to ensure that the Government i sfully committed to the reforms proposed and the timetable for the reform agenda. Project objectives should be framed realistically, taking into account the borrower's ability to achieve stakeholder support for proposed changes. Genuine community ownership and participation can enhance the likelihood o f project success as evidenced by Yemen's Public Works program. These Yemeni projects show that inter-ministerial, agency and stakeholder coordination are crucial to project sustainability and that the Bank could be more proactive in helping to improve the general level o f coordination.
P054217 | FINANCIAL SYSTEM INFRASTRUCTURE MODERNIZATION PROJECT | Middle East and North Africa | Algeria | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2002 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/527571475097396321/text/000020051-20140617134228.txt | http://documents.worldbank.org/curated/en/527571475097396321/pdf/000020051-20140617134228.pdf | Among the lessons learned are: (i) the financial, economic, and political environment under which a development project is to operate is a key set of considerations in the achievement of development objectives, as well as in priority-setting and sequencing of components, and considerations in technical, infrastructure, and human resource support; and (ii) the consideration and calculation of risks (e.g., risk to achievement, risk to development, etc.) in a project and its eventual success requires a comprehensive understanding of the financial, economic, and technical conditions, as well as a strong commitment from and personal involvement of key stakeholders.
P054221 | Water and Sanitation in Tourist Areas | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2018 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/225151571414859448/text/Dominican-Republic-DR-Water-Sanit-in-Tourist-Areas.txt | http://documents.worldbank.org/curated/en/225151571414859448/pdf/Dominican-Republic-DR-Water-Sanit-in-Tourist-Areas.pdf | IEG summarizes below the lessons identified by the ICR teamwith modifications: Adequatefeasibility analyses at thedesign stage need to be conducted, as they can critically affect project outcomes.When the submarine outfall was designed, the feasibility study and the geotechnical survey were not adequately conducted. It causedthe design to be re-done after the construction work has started. As a result, the Project needed to reduce its scope of activitiesdue to lack of time and resources to implement them. The realism of achieving development objectives withinthe project duration needs to be rigorously assessed, as lack of realismcan deter efficientimplementation of projectactivities. It was essential to adequately access institutional capacity and realismto designtheProjects activities, so that they could be implemented, and their outcomes measured, within the original project duration ofthree and a half years. PDO indicators should bedirectlyrelevant to measuring outcomesthat are attributable to project interventions, and need to bemonitoredaccuratelyto generateadequateand robust evidence on efficacy. The ProjectsPDO indicators, which lacked relevance or attribution to the Project, could not provide sufficient evidence to prove theProjects achievements in the outcome objectives. Failing to address capacity constraints at the earlystages of project implementation can critically affect project outcomes. This Project did not implement remedies toimprove stakeholders capacities in the beginning of the Project, which became one of the main reasons for delays in projectimplementation.
P054238 | Second Gazelle Restoration Project | East Asia and Pacific | Papua New Guinea | Blend | FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2008 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/770081474652628071/text/000020051-20140620072259.txt | http://documents.worldbank.org/curated/en/770081474652628071/pdf/000020051-20140620072259.pdf | The following lessons may be learnt from the preparation and implementation of this project:When a Borrower has a record of problems in timely and adequate provision of counterpart funding, it would behoove the Bank to take appropriate mitigating measures. Where a considerable number of different donor agencies are involved, each with its own procedures and requirements, implementation would be considerably eased if it were possible to create a mechanism whereby one of the donor's procedures were to be adopted for all procurement whether that donor is the source of funds or not.GRA's practice, following the 2005 restructuring, of using a contract administration manual together with enhanced risk management measures proved highly effective in reducing further delays and cost escalations. This practice could well be adopted in other projects both in PNG and elsewhere, provided the implementing agency is endowed with the necessary capacity.
P054384 | Recovery Program Technical Assistance | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/707141474632904807/text/000020051-20140612084809.txt | http://documents.worldbank.org/curated/en/707141474632904807/pdf/000020051-20140612084809.pdf | (a) Extensive work previously undertaken in the financial sector, along with agreement of all stakeholders, allowed the Bank and the Borrower to prepare this project on an emergency basis in less than a month. (b) Intensive supervision was critical to achievement of the project's objectives in the difficult, post-conflict environment. (c) The independence and professionalism of the PIU enabled it to resolve a number of complicated issues, as well as to implement the project satisfactorily, despite frequent changes in government.
P054384 | Recovery Program Technical Assistance | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1998 | 2003 | 2005 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/900451468768316767/text/29638.txt | http://documents.worldbank.org/curated/en/900451468768316767/pdf/29638.pdf | 5. Lessons 0 Small, focused, one-tranche policy projects with realistic objectives, supported by technical assistance, may work well intransition countries that are politically unstable and have low market economy skills (e.g., credit risk analysis for private sector banking or enforcing competitionregulations). A limited reform agendai s easier to implement, especially ifparliamentary approval i s neededfor new laws when the political landscape i s not stable. Reformcontinuity can be maintainedby similar policy or investmentfollowon projects. 0 Incrisis situations, animmediate responsecanbevaluable beyondits direct purpose. For example, the very quick preparation and disbursement o f PESC was effective inproviding development assistance and coordinating substantial humanitarianassistance. 0 PESC was disbursed against a negative list o f imports instead o f the positive list that i s usual for an emergency import credit. Disbursementagainst a negative list expedited resource transfer, which was appropriate inAlbania's circumstances. 0 As hasbeenwell documented, aid coordinationis critical to ensure appropriate, harmonizedand effective assistance where many donors are involved. Coordination should also ensure that government agencies dealing with donors are also appropriately aligned. Some institutions established for special purposes under IDAprojects such as BART, couldbe transformed into private sector commercialentities when their mandate i s complete. This transition could be an integralpart o f that organization's strategy.
P054443 | Cameroon - SAC III | Western and Central Africa | Cameroon | Blend |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/105541474497244385/text/000020051-20140613032237.txt | http://documents.worldbank.org/curated/en/105541474497244385/pdf/000020051-20140613032237.pdf | 1) Cameroon's experience with the privatization program confirms two lessons repeatedly highlighted by OED: (i) complex privatization programs should be accompanied from the start by well targeted TA operations; and (ii) they should be well sequenced within a long time-frame, possibly over several operations.2) Bank teams should be attentive to the frequent disparity in commitment between the political and administrative levels. 3) Small countries with limited resources should be encouraged to have a single multi-sector regulatory authority.4) Floating tranches are useful in allowing the country to prioritize and pace the reforms according to circumstances.
P054462 | Land Fund Project | Latin America and Caribbean | Guatemala | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/994111474587021437/text/000020051-20140615094410.txt | http://documents.worldbank.org/curated/en/994111474587021437/pdf/000020051-20140615094410.pdf | The ICR offers a number of useful lessons of wider applicability which this review endorses:The willing seller/willing buyer approach to land redistribution supported by the project needs to be complemented by other policies such as regularization of land ownership, land taxation, and other interventions to create a dynamic market for land in the country..Simply providing credit to puchase land is insufficient to increase beneficiaries' incomes. This should be complemented by technical assistance to raise productivity, especially where extension is weak, and a fixed grant assistance allowing the option to convert some funds from land purchase to productive investments.Beneficiaries should have full control of and responsibility for the use of credits and grants.Support for basic needs should be carefully assessed and provided for upon the initial settlement of families in the acquired farms in order to free up the use of funds for productive investments.Computerized financial management systems are important to avoid excessive demands on staff which increases the risk of errors.M&E needs to be in place in advance of implementation and needs to include a focus on project impacts.Land market information systems are very challenging and require a well-established and well-financed agency.
P054462 | Land Fund Project | Latin America and Caribbean | Guatemala | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2010 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/546451468040131560/text/553410PPAR0P001e0note030project0IDs.txt | http://documents.worldbank.org/curated/en/546451468040131560/pdf/553410PPAR0P001e0note030project0IDs.pdf | 7. Lessons 7.1 Assumptions about the boost to tenure security that will result from land administration initiatives (and corollary assumptions about improved access to credit and reduced conjlict) should be carefully examined and tested with empirical evidence. The assessed projects make assertions about enhanced tenure security, increased credit access and reduced conflict over land rights but provided no evidence to back these claims up. There is a literature outside the Bank challenging these assumptions and the Bank has only recently begun to take this into account. There are a number of ways to measure tenure security and the progress toward increasing it (see paragraph 2.6 above); and these measures need to be taken into account in project design and monitored during implementation. Summing up, security of land tenure is not automatically boosted by land administration initiatives; good land administration is a necessary (but not sufficient) step toward secure land tenure. 7.2 Integrating the databases of cadastre and registry is important to facilitate land use planning and tax assessments; but this integration can be attained by providing separate cadastre and registry agencies with a common technical platform-it does not presuppose creation of a single cadastre/registry agency (which may not be politically feasible). EI Salvador-with its single agency-has made more progress toward technical integration than Guatemala with its separate agencies. A unified agency is preferred, if it can be politically established. If a unified agency is not politically feasible, effective arrangements for data integration must be introduced, otherwise the unsatisfactory experience of Guatemala will be repeated in other places. There are steps that can be taken during project design and implementation to make it more likely that integration will be effective (see paragraph 3.3 above). 7.3 Land administration initiatives need to be prioritized by geographic area; other development programs may be more appropriate for remote rural areas. Regularization may be more urgent, more feasible and more sustainable in urban areas and in fertile rural areas with dynamic land markets. Urban regularization could usefully be accompanied by complementary efforts to improve municipal services, municipal financing and slum upgrading. In rural areas, there is more of a need to adopt an integrated approach to land in private property, protected areas and indigenous communities (the last two typically having been orphaned in land administration projects). While a majority of the poor often live in rural areas it does not follow that land administration efforts should give special attention to rural areas; there may be more effective ways to reduce rural poverty. 7.4 The problems associated with Guatemala's attempt at market-assisted land reform need to be avoided in subsequent projects; there is much scope for learning from previous design flaws and factors tending to undermine government support-the relevance of land reform should not be lightly dismissed. The justification for the drop off in the government and the Bank's support for land reform in Guatemala and EI Salvador merits closer examination. lEG concurs with the findings of a recent Bank policy note\. Considering the pervasive and pernicious inequality of land distribution in Central America and the fact that these inequalities were a major factor that led to civil unrest and civil wars, it is sobering to note that World Bank land projects in Central America have ended up focused on land administration ... with a secondary and discontinued effort at piloting market-based land purchase programs.51 In 7.5 During the design and preparation of land administration and land redistribution projects mechanisms need to be developedfor ensuring that the poor will have access to the land administration process and to opportunities for obtaining land; and the. effectiveness o/these mechanisms needs to be continuously monitored. The three projects assessed here each listed poverty reduction as one of their objectives and yet there was little follow up to ensure that the poor were well served. In the case of land administration, systematic adjudication in principle covers poor and non-poor alike. But coverage of the poor should not be taken for granted; and once systematic adjudication is complete there is a need for special measures to encourage poorer groups to register subsequent changes in landholding. With respect to land reform, the eligibility criteria for participation in redistributive schemes should give weight to the needs of the poor with a vocation for farming and application of those criteria should be based on a systematic survey of the socioeconomic profile of the candidates. Also, for land policy initiatives to make a big impact on rural poverty complementary measures are called to boost agricultural productivity. 7.6 The net gains from land administration and land reform initiatives should not be regarded as self-evident; much more attention must be given to measuring the impact of these initiatives and this means that when projects are prepared-rather than laterprovision must be made for conducting baseline and follow-up surveys with appropriate control groups. None of the three projects assessed here made adequate provision for impact evaluation. This shortcoming is not limited to land policy projects; but because these projects are politically so problematic the analytical foundation on which they are based probably needs to be more carefully designed and carried out than is the case for many other types of projects.
P054667 | El Nino Emergency Assistance Project | Latin America and Caribbean | Peru | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/735331475085068367/text/000020051-20140602114227.txt | http://documents.worldbank.org/curated/en/735331475085068367/pdf/000020051-20140602114227.pdf | *Prevention measures can have a substantial impact on reducing social and economic losses. Many types of contingency investments (including regular maintenance and repair work) should be incorporated in normal sector investment programs during non-emergency periods.*In designing projects in anticipation of future El Nino disaster events, detailed design standards for critical types of works (such as bridge, road and irrigation system standards based on levels of use) should be decided in advance.*When natural disasters of this proportion hit a country, the Bank should update its CAS in light of the need for long-term measures to reduce the vulnerability of the poorest segments of the population and the likely changes in the country';s overall investment priorities, especially for extensive reconstruction work.*The reconstruction and rehabilitation work that needs to be implemented often takes more than two years to complete. This should be taken into account for emergency rehabilitation projects, which, possibly, should be designed as hybrids with two stage implementation programs.
P054736 | Agriculture Services Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2001 | 2008 | 2009 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/276221474493138339/text/000020051-20140619091201.txt | http://documents.worldbank.org/curated/en/276221474493138339/pdf/000020051-20140619091201.pdf | Implementation in periods of instability in the enabling environment and unanticipated change require considerable flexibility in project format and design, both during the life of a project and afterwards when government assumes responsibility for maintaining or adapting project components. This requires a change in how the maintenance of project components should be viewed, from that of a semi-permanent "fix" to perhaps interim gap-filling in the face of a sometimes rapidly evolving ex-project or even ex-sector environment. For example, the project's Land Market and Product Market Development components are best viewed in this light. From the ICR: Â§ Successful interventions in seed development and supply require a careful balance of public and private domains, tailored to the country's situation.Â§ A legal framework governing land transactions by itself is insufficient in promoting land consolidation.Â§ Wholesale markets should probably be initiated at the lower end of their feasibility spectrum, with room to grow as demand is demonstrated.Â§ Competitive grant schemesâ€™ success can be enhanced by virtue of a strong procedural system and broad, unfocused application.Small can be (beautifully) efficient. Â§ Small grant programs allow for a more manageable, adjustable and relatively transparent implementation process.Â§ Project complexity should be evaluated in terms of implementation arrangements, not diversity of components.Â§ Develop procedures to minimize losses of institutional knowledge and experience due to staff turnover.Perhaps the most important lesson is the need for the Bank and Borrower to be adept and agile in the transition economies, and a willingness and ability to adapt quickly to changing country circumstances. As with the operation under review, application of these principles can result in ultimate project success, while a failure to dos o will likely lead to a disappointing outcome.
P054786 | RAILWAY CONCESSION PROJECT | Western and Central Africa | Cameroon | Blend | FCS | Infrastructure | Transport | IDA | IPF | 2003 | 2009 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/187591474652734289/text/000020051-20140620080754.txt | http://documents.worldbank.org/curated/en/187591474652734289/pdf/000020051-20140620080754.pdf | Concession design:There is a need to recognize the time necessary to complete the process of private participation/concessioning which entails staff retrenchment. This factor is often underestimated by transaction advisors and governments. There is also a need to strike a balance regarding the likely outcomes of a concession between what a private institution requires with respect to its profitability, and the demands of the government which are to a great extent often politically driven.Capacity building:In the context of railway concession, institutional development and capacity building are critical factors to ensure sustainability during implementation and after project completion. Specific expertise is a prerequisite for engagement into such ventures. A technical assistance component not managed by the Concessionaire should be included in the design of similar projects in order to provide appropriate assistance to the Government during both project implementation and preparation.Monitoring Indicators:Should include performance indicators that are not too ambitious and can be monitored given the data availability/collection limitations. Safeguards Implementation:The safeguards implementation should be monitored during project implementation through clear measurable indicators. Passenger services:Most passenger rail components of concessions require subsidies from the government for public service operations. These operations are not the major priority of the concessionaire and can result in a deficit and lack of assurance of financial sustainability and/or neglect of passenger services activities. An appropriate passenger services obligation, which defines clear and practical rules should be part of the concession design from the outset.
P054799 | THAILAND-ECO MGT IMPLE ASSIST | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/116111474657537618/text/000020051-20140612092026.txt | http://documents.worldbank.org/curated/en/116111474657537618/pdf/000020051-20140612092026.pdf | Relationship between technical assistance and policy-based lending. The ICR notes that the technical assistance project was useful in providing the Bank with a platform for active dialogue on structural reforms with the Government, for developing a coordinated and comprehensive approach to reforms, and for obtaining a better assurance of sustainability. However, these aspects were present in the economic recovery program loan to which the Technical Assistance Project was attached. The Project also provided diagnostics studies that were used in designing the countryâ€™s structural reform program and funding to carry out other necessary preparatory activities. Time frame required for institutional building operations: The project's closing date was extended three times (for a total period of two years) so that activities under the various components could be completed. The time needed to introduce changes in the government processes and carry out institutional building, as well as to work out consultant requirements, needs to be adequately budgeted.
P054801 | EFAL - TH | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/828971475088030860/text/000020051-20140526223615.txt | http://documents.worldbank.org/curated/en/828971475088030860/pdf/000020051-20140526223615.pdf | Bank involvement can be instrumental in a "paradigm shift"--The 4-project program of which EFAL was a part resulted in a significant shift in thinking among influential Thais (e.g., acceptance of the concept of foreclosure). A core of people came to understand and believe in the economic logic behind the reforms. The impact of this shift can be more important than that of the funds provided.Even in a project undertaken as rapidly as EFAL, it would be extremely useful to develop key indicators for project implementation to assess the degree of achievement of various objectives.
P054801 | EFAL - TH | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 1999 | 2006 | PPAR | >=100 million | Moderately Unsatisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/960941468173356799/text/350510REV0pdf.txt | http://documents.worldbank.org/curated/en/960941468173356799/pdf/350510REV0pdf.pdf | Lessons Learned 5.1 The significant cost o f cleaning up financial crises can offset the progress made over many years inpoverty alleviation and other social improvements, both o fwhich are central to the Bank's mandate. Giventhis, the Bank should continue to play a role in client countries inboth improving financial sector governance and soundness to reduce the probability o f crisis and inpost-crisis management and well-structured recovery. 5.2 The severity o fthe crisis was, inretrospect, initiallyunderestimatedbythe Bank and others, as was the negative impact on the economy o fthe large scale closure o fthe FCs inthe early phase o f the reforms. Thai officials interviewed by the IEGmissionnoted that these earlymis-readings o fthe severity o fthe crisis andthe impact o f the closure o f the FCs on the economy raisedconcerns about the credibility o f the IFIS'approach and, most important to Thailand's future, about the financial reform itself. This suggests that crises inother countries should be approached more comprehensively, taking into account potential negative impacts o f large scale closures. 5.3 Short-term crisis management policies can compromise essential structural reforms. The failure to factor into the design o f the reforms the inadequacies o f the Thai legal and regulatory infrastructure led to approaches that may have increasedthe cost o f cleanup. For example, traditional procedures inThailandfor corporate restructuring were notoriously slow and generally benefitedthe debtor; thus, the corporate reorganization procedures modeled after the UnitedStates (Chapter 11style) were ill-suited to the situation and may have served to worsen it (longer-delays, reducedrestructuring). A betterapproachwould havebeento simplify liquidationprocedures, involvingthe stakeholders and a bankruptcy administrator, rather thanthe court system. 5.4 The sequencing andtimingo freforms i s critical. Too little early emphasis was placed on reformingbankruptcy and foreclosure laws, developing a deposit insurance scheme, and fostering development o f capital andmoney markets. The governmentthat came to power just after the crisis emergedwas reform-minded, but the adverse macroeconomic impact o f the earlypolicy changes gave reform a badname inThailand. 5.5 The allocation ofpieces o fthe reform package among the three International Financial Institutions (IFIs) may have made sense, but only ifit hadbeen followed by better coordination. As it turnedout, the division o fresponsibilitiesresulted inan absence o f a clear guidingvision for the reform o fthe financial system. Thus, for example, commercialbank restructuringwas carried out very differently from finance company restructuring, even when they suffered from the same problems. Inaddition, the division o f labor broke down, as the Bank fairly quickly became involved inFIrestructuring and capital market development. 5.6 Succeeding loans with increasinglybroader goals and a growing list o f conditions diffusedthe focus o freform andunderminedmeaningfulmonitoring; abetter approach would have been the programmatic one now usedwidely (but not available at that time), which seeks to develop a coherent set o fpriority reforms and sequences the steps for carrying out those reforms ineach successive loan.
P054884 | BCEAO REGIONAL PAYMENT SYSTEMS PROJECT | Western and Central Africa | Western and Central Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2001 | 2006 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/223041474486629440/text/000020051-20140619061930.txt | http://documents.worldbank.org/curated/en/223041474486629440/pdf/000020051-20140619061930.pdf | Lessons learned are: (i) payments system projects/PSP are complex and require understanding, consensus and capacity building, and adequate timeframe and financial resources for development especially in wide regions as the WAEMU; (ii) development of PSP's need adequate flexibility to deal effectively with unexpected outcomes; (iii) continued dialogue, involvement, and strong commitment by all stakeholders can alleviate potential conflicts between divergent views; and (iv) in developing PSPs, international best practice should be advanced including leveraging past works by the Bank, IMF, and other regional development agencies.
P054886 | Electricity Market Support Project | Europe and Central Asia | Georgia | IBRD | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2001 | 2010 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/647361474484738366/text/000020051-20140624190707.txt | http://documents.worldbank.org/curated/en/647361474484738366/pdf/000020051-20140624190707.pdf | The ICR provided useful lessons, as follows:(1) Government commitment and full ownership of the reform process is essential. In Georgia, the Governmentâ€™s proactive involvement and public stance on reforms allowed the management contractors for the power sector entities to implement the necessary restructuring of their operations.(2) Management contracts can be an important tool in energy sector reforms, by bringing in competent international management to apply modern corporate management practices, as well as fight corruption and downsize entities in cooperation with trade unions. In this project, the management contractors helped to build local capacity and thus allowed the consolidation of reforms and successful transition to Georgian management. This was notably the case for the transmission company and the distribution company, which successfully made the transition from contracted management to private ownership.(3) Adequate financial resources are required to speed up reforms. Funds are required for management contractors (when applicable), billing and financial control systems, physical control systems to fight electricity theft and switch off non-paying customers, and crucial actions to retrench sector staff.(4) Investments that improve power supply reliability and cost efficiency can be strong incentives for consumers to accept reforms, such as improving payment discipline and reducing electricity theft.(5) A joint vision and sustained cooperation between Government and external partners can significantly enhance project results. In this project, Georgiaâ€™s power sector reforms benefited from coherent external partner approaches to the reform agenda and close cooperation jointly with the government. External partner coordination is also essential to ensure that their funds and interventions are complementary and well targeted to support the reform agenda.(6) Close Bank supervision and continuity of Bank project team can greatly facilitate close cooperation with the government and donor coordination, and enhance the supervision of the project's technical aspects.(7) The SCADA/Energy Management System is a key element of power sector reform, by helping ensure that blackouts and brownouts are kept to a minimum, thus opening up the possibility of more efficient and system-safe electricity trade with neighboring power systems. However, introducing modern SCADA/EMS is complex, and there can be unexpected developments during implementation, including potential delays in the implementation period.(8) Cross conditionalities that interlock technical, policy, and implementation actions should be avoided. Up-front and straightforward conditionalities that can be met prior to project approval are preferable.
P054937 | Early Childhood Education Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2003 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/635971474631245400/text/000020051-20140625155450.txt | http://documents.worldbank.org/curated/en/635971474631245400/pdf/000020051-20140625155450.pdf | The ICR (pp. 27-28) reports the following lessons:For projects containing civil works, careful consideration must be given to design, bidding documents, and selection of procurement methods. In this project, civil works were bundled and bid by amount, which resulted in the same contractor implementing more than one project and at the same time in different areas of the island, delaying the completion of the civil works. Ongoing professional development provides teachers with important time to learn new skills and opportunities for application and reflection. This project found much success with the Pedagogical Groups as a vehicle for teachers to share work strategies and reflect on pedagogical practices. The Pedagogical Groups helped strengthen teachers' understanding of the pedagogical model and curriculum.
P054937 | Early Childhood Education Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2003 | 2012 | 2013 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/732341468249029215/text/782750PPAR0P0500Box377377B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/732341468249029215/pdf/782750PPAR0P0500Box377377B00PUBLIC0.pdf | 7. Lessons 7.1 Based on the experience of this project, several lessons can be drawn\. 1. Lack of attention to country context in project design can lead to considerable delays and inefficiencies. In the case of this project, there was a long delay in project effectiveness (15 months) linked to the need for legislative approval of the loan, followed by extensive delays in implementation tied to low procurement capacity and frequent turnover of staff linked to the political cycle. There was no specific action taken to mitigate the wellknown risks from the political system with respect to delays and turnover. The solutions proposed by the Capacity Assessment conducted at appraisal were inadequate to mitigate the well known shortfall in procurement capacity, particularly in light of frequent staff turnover. 2. Greater proximity to pre-primary education is necessary but not sufficient for poor parents to enroll their children. The project built new pre-primary classrooms in areas with large numbers of poor parents and launched a communications campaign though it is unclear whether the latter targeted the poor. It also introduced quality improvements in public pre-school education. Yet, even though fewer classrooms were built than planned, there was under-enrollment of 5-year-olds in the new capacity. This suggests that there remain significant constraints to poor parents for the enrollment of their 5-year olds in preprimary education. Informants noted that the fact that public pre-school is only half a day may be a factor\. private schools provide all day programming either through a full day at school or combined with after school care, which is more convenient for working parents. This points to the importance of a good understanding of the most critical constraints affecting pre-primary enrollment. 3. In the absence of strong selection criteria and explicit mechanisms for evaluating new approaches, learning from innovation funds will be limited. As designed and implemented, the Grant Fund was not a vehicle for innovation, learning, or sustained access. Without strong monitoring and evaluation, there was no way to identify projects worthy of replication and scaling-up, as well as learn from the Fund. Providing teachers with training, the necessary classroom supplies, and ongoing support from pedagogical groups, coupled with monitoring the implementation of the pedagogical model can improve quality in pre-primary classrooms. In this project, preprimary teachers were provided with classroom supplies, a new curriculum, and peer-to-peer learning from pedagogical groups, as well as follow-up support. Some teachers observed classrooms in Model Centers. Coordinators and pedagogical leaders visited teachers' classrooms to monitor quality. This resulted in teachers using the supplies and applying what they learned from the professional development in their classrooms.
P054939 | LC- POVERTY REDUCTION FUND | Latin America and Caribbean | St. Lucia | Blend |  | Human Development | Social Protection & Jobs | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/415251474748788545/text/000020051-20140613034125.txt | http://documents.worldbank.org/curated/en/415251474748788545/pdf/000020051-20140613034125.pdf | Members of the PRF Board of Directors were appointed, de facto, as representatives of government institutions. It would have been more effective if individuals with the greatest knowledge of this area and commitment to the PRF had been selected.Communities can manage many aspects of the subproject cycle, and this can be beneficial in building local capacity. Involvement of the broader community, however, is critical to capacity building.Selection of PRF subprojects might have given too much weight to communities that had "voice" rather than those that were determined to be poor based on a more rigorous assessment.
P054958 | Egypt Pollution Abatement Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/135011474504321698/text/000020051-20140613074917.txt | http://documents.worldbank.org/curated/en/135011474504321698/pdf/000020051-20140613074917.pdf | The OED review considers the following as important lessons:To maximize the project's environmental benefits, the Bank and the Borrower should carefully assess the eligibility and potential environmental impact of subprojects in the pipeline in order to design financing mechanisms that are effective and suitable especially for targeting major polluters.The Borrower needs to establish a comprehensive and coherent framework for enforcing national environmental policies in order to promote environmental compliance through enforcement and inspections. The Borrower should also establish unified inspection guidelines to enable inspectors to effectively utilize the training they received from the project.The project's design should involve established training institutions (such as universities and institutes, industrial associations and enterprises) in capacity strengthening activities, with a view to increasing participation and disseminating knowledge more widely.
P054966 | Private Sector Development Project (APL #1) | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2002 | 2006 | 2007 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/387231474631853299/text/000020051-20140615113413.txt | http://documents.worldbank.org/curated/en/387231474631853299/pdf/000020051-20140615113413.pdf | By the time this project was formulated and approved, the private enterprise sector in Ukraine was growing rapidly and management training of the sort to have been provided by the project was not needed. Therefore, the project was not synchronized with the needs of the economy. It is important that project cycles need to be closely aligned with opportunities and needs of the economy. Borrower ownership is essential for project success. Broad-based consensus building is essential before proceeding with projects with broad objectives. The lack of support for this project, with consequent implementation delays, can be traced in part to this lack of consensus building. The fact that the Borrower had to approve the project by special procedures rather than the normal parliamentary process should have been an important sign of lack of ownership.The Bank should seek to promote the use of bilateral and other grant aid where this is available for training programs rather than seek to have clients borrow from the Bank to finance these activities.
P055003 | Nutrition, Food Security, and Social Mobilization Project | Western and Central Africa | Mauritania | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/142441474569646605/text/000020051-20140613080527.txt | http://documents.worldbank.org/curated/en/142441474569646605/pdf/000020051-20140613080527.pdf | Incentives should be more tightly linked to the desired project outcome. In this project the incentives offered through the income generation activities were poorly handled, and diverted the attention of the women's cooperatives from nutrition activities.For LIL projects and those that aim to carry out project impact evaluation, adequate provisions should be made up-front to ensure that M&E capacity/capability is available in order that good quality baseline- and subsequent- data can be collected.Growth monitoring has to be closely linked to counseling and nutrition education of mothers. Because the interpersonal and technical skills of the community nutrition workers were minimal they were not able to influence the child feeding behaviors of mothers.
P055021 | Registration & Cadastre Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/921701474852618054/text/000020051-20140620065217.txt | http://documents.worldbank.org/curated/en/921701474852618054/pdf/000020051-20140620065217.pdf | (i) Although the project has demonstrated that land administration through a â€œdual-agencyâ€ approach can be successful, a unified agency is still preferable since program implementation is easier and efficiency gains more attainable.(ii) The legal and institutional base for land administration should be established before commencing implementation, and the land administration institution(s) should have full-time staff and be dedicated only to land administration. (iii) Financial self-sufficiency for a land administration agency is desirable and feasible if fees are appropriately channeled. Fees need to be retained rather than passed to Government, and cadastral activities may need cross-subsidization from registration revenues.(iv) The efficiency of other institutions and processes are relevant to a achieving a well functioning land market. For example, in Bulgaria, the Registration Agencyâ€™s one to three day turnaround for its part of land registration is not matched by other involved institutions which add another one to two weeks. The land market is also affected by constraints outside the registration process, such as obtaining a construction permit.(v) Possible adverse impacts on weaker social groups should be investigated while preparing a land administration project and mitigating project design features included if needed. The impact on such groups should be monitored during project implementation.
P055021 | Registration & Cadastre Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2009 | 2010 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/398691468021256876/text/552060PPAR0P051IC0disclosed08131101.txt | http://documents.worldbank.org/curated/en/398691468021256876/pdf/552060PPAR0P051IC0disclosed08131101.pdf | 4. Lessons 4.1 The experience gained under the Bulgaria RCP yields the following Main lessons\. (i) While land administration through a dual-agency approach (separate institutions for cadastre and registration) can work, a uniJied agency is preferable as program implementation is easier and eflciency gains more attainable than with a single agency. 30. The degree to which institutional arrangements for registration have gone is not reflected in the ICR. Also not reflected is the time frame within which the two agencies were established and developed to their current competence. By comparison, recognizing that development of land administration systems is a long-term process, it is not uncommon for the Bank to provide support over more than one project. Bulgaria is proceeding without such further Bank engagement, and, while a second Bank project would probably add value, to date, Bulgaria has managed well without external support. 31. Thus, from the PAD (page 2) The implementation of an integrated cadastre and registration system to cover the whole country would be phased over a period of 15 years. The proposed project will cover the first five full years of this comprehensive program. 32. For instance, Thailand had three projects, Kyrgyzstan and Azerbaijan are in their second projects. Nevertheless, practical steps can be taken to reduce the disadvantages o a dual-agency f system. Bulgaria, once both the CA and RA had been established, moved fast, and the RCP's project objectives were achieved. Actions that helped the dual-agency model to work included\. establishing a PIU providing a coordination bridge between the CA and RA; and, later, the unified information technology system providing fully shared data. Nevertheless, there would be further benefits with a single agency, amongst these\. that coordination between activities would become seamless; financial self-sufficiency would be easier; registration efficiency would be faster; and there would be greater convenience for customers (paras. 3.3 to 3.33). (ii) Establish the institutional and legal base for land administration prior to a project. Government had passed a law establishing the legal basis for land administration more than a year before Board approval, and the CA was established six months before approval. But the registration coordination unit was not established until 16 months after Board approval. Registration activities only got going after the RA had been created. (paras. 3.4 to 3.49). (iii) The need for agencies, dedicated only to land administration. Having only a coordination unit within the Ministry of Justice to oversee land administration activities of the district judiciaries was inadequate. District judiciary staff were not solely answerable to the coordination unit and had many other duties besides land administration. It was not until the RA was formed -a specialized agency with trained, full-time staff and a clear command structure that land registration got off the ground (para. 3.4). (iv) Formalfinancial autonomy for land-revenue generating administration agencies is preferable as financial self-sufficiency is more easily attained and thefinancial status assuresfinancial and administrative stability. RA and CA already have combined inflows from fees that cover operating costs. However, the fees or a portion thereof need to be retained by the agencies, and cadastral activities may need cross-subsidization from the RA to the CA. (This would be simpler if the CA and RA were merged to one institution.) Financial self-reliance would better assure adequacy of funds and provide more administrative autonomy (para. 3.39). (v) Signifwant further improvements in the functioning o land markets can be gained by f improving the efficiency o land administration processes outside the purview o the f f specialist land agencies. The RA has now reduced the time taken for its part of the registration process to one day. However, another 6 to 13 days are required for other institutions (The Municipality, Tax Department, etc.) to do their work. The opportunities for future improvements in efficiency will come primarily from these institutions (paras. 3.4 1 and 3.42). (vi) Land market constraints in the broader business environment merit consideration. The RCP, by making land administration processes more efficient, has played a significant facilitating role in liberalizing the land market. But in broader terms this is not the only important influence on the land market. For instance, getting a construction permit, a frequent sequitur when a business buys a property, takes about 140 days and involves 24 procedures (para. 3.43). (vii) Possible adverse impacts on weaker social groups (such as the poor, women and illiterate) o land administration projects should be averted by speciJicproject design f features. The impact on, and utilization oJ;services, by such groups should be monitored and analyzed as implementation proceeds, Minimal information is available in Bulgaria on social influences, the typical view being that the land administration program is neutral in its treatment of all persons. However, in a number of countries, also with no difference in approach between social groups, inequalities have been found, as well as practical solutions (paras. 3.15 and 3.16). (viii) When deciding on the number and distribution o land administration offices, the f trade-off between uniform coverage and accessibility on the one hand and cost-effectiveness on the other should be considered. In the case of Bulgaria there is a logic in following the Government administrative system, with one land administration office for each of the country's court towns. This provides the same density of coverage as for other Government services. For smaller offices, however, less costly alternatives to permanent offices, such as part-time or mobile offices, could be considered (para. 3.14).
P055022 | Irrigation Development Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2009 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/679651474634850783/text/000020051-20140620073731.txt | http://documents.worldbank.org/curated/en/679651474634850783/pdf/000020051-20140620073731.pdf | A national "champion" who provides strong leadership for reform coupled with consistent and a dedicated Bank implementation support team establishes confidence and trust which will in most cases lead to successful outcomes. Relevant institutional change is enhanced by a sound understanding of the incentives that need to be provided to those who are stakeholders in the change.Sustained institutional change benefits from active participation by all stakeholders.Successful institutional change will be more easily achieved if winners and losers are clearly identified and brought into the process of change at an early stage with close attention to resolution of potential disputes.Accurate measurement of results is crucial for the understanding, monitoring and evaluation of outcomes and the GIS information generated in the context of this project proved to be valuable during implementation and will be valuable in the future.
P055061 | MX: HEALTH SYSTEM REFORM TA | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1998 | 2003 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/591771474504386776/text/000020051-20140612083609.txt | http://documents.worldbank.org/curated/en/591771474504386776/pdf/000020051-20140612083609.pdf | Political and public opposition to some of the key reforms should be countered by aggressive and well positioned public awareness campaigns. Without these, intensified Bank supervision (recommended by both ICR and Borrower) and dialogue in support of the reforms are unlikely to get the desired results. Complex reform projects require specific strategies to deal with the political aspects of reform to complement the technical packages of interventions. This also allows for technical developments to be linked to the policy arena thereby facilitating implementation of these developments.Conditionality on changes to the health care model should not focus exclusively on the economic incentives nor on theoretical policy instruments such as "free choice". They should include broader changes such as quality management issues and extension in coverage, which are more likely to galvanize the support for the policy changes by the health workforce and general public.
P055068 | Irrigation & Drainage Community Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2009 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/267361474489042629/text/000020051-20140620082105.txt | http://documents.worldbank.org/curated/en/267361474489042629/pdf/000020051-20140620082105.pdf | The ICR provided a number of relevant lessons, of which the most important were:Government support is key for successful project implementation. Without a suitable institutional framework to manage, operate and maintain irrigation and drainage infrastructure, investments in rehabilitation will only have a short term impact.The following lessons could have been added:The project's history shows that it is well worth devoting adequate time at the appraisal stage to ensuring that a project is based on sound policy. Although the Government reversed policy during implementation the project, subsequent experience clearly demonstrated merits of the original policy and influential officials agreed at the project's close that policies should not have been changed. This suggests that solid project preparation and the defense of the original strategy paid off.Weak M&E can lead to serious problems in evaluating the project results. Strenuous efforts during supervision should be made to fix M&E weaknesses.A serious assessment of appropriate cost recovery rates for irrigation systems is essential to highlight the risks of not doing the needed institutional reform. Inadequate cost recovery for irrigation water was a chronic problem for the Associations but the draconian solution by the Government of establishing the water companies and then increasing cost recovery rates 12-fold was not a solution either.
P055073 | Pilot Literacy Project | Western and Central Africa | Cote d'Ivoire | IDA |  | Human Development | Education | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/525971475074933017/text/000020051-20140613054109.txt | http://documents.worldbank.org/curated/en/525971475074933017/pdf/000020051-20140613054109.pdf | It is difficult to implement projects, particularly those involving complex institutional arrangements and partnerships, in a climate of low government commitment and political instability. The Bank should ensure clear, up-front political support and commitment before project effectiveness.- The "faire faire" approach is effective in carrying out adult literacy projects and reaching communities. However, it requires a functional institution that can coordinate NGO actions, guide them, and train them. - Merely managing NGOs does not ensure that literacy activities will be carried out. NGOs that may express willingness to teach adult literacy do not necessarily have expertise in this topic. Rather than giving weak NGOs responsibility for development of materials and training,projects should provide training and materials along with considerable help in selecting suitable teachers who may also need training by governments.
P055084 | GT COMPETITIVENESS PROJECT | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/301611474750504003/text/000020051-20140620075117.txt | http://documents.worldbank.org/curated/en/301611474750504003/pdf/000020051-20140620075117.pdf | A careful, critical assessment of the Borrowerâ€™s political and institutional capacity for implementing a project is an essential component of project preparation. The substantial delays in implementation and the number of project elements that were not implemented suggest the need for a more realistic assessment of risks, particularly the risks associated with a change in government. The experience does not suggest that public-private partnerships are necessarily less vulnerable to shifts in political priorities.A less complex project design might have produced better results. If the project had been designed as two operations, one aimed at direct support for SMEs and the other aimed at the institutional and regulatory changes needed to reduce constraints to private sector development and to attract foreign investment, it might have been easier to focus efforts on these two different aspects, including the design and implementation of an appropriate monitoring and evaluation framework. The PAD does not indicate if such an alternative was considered.The lessons identified in the ICR, are useful and highly relevant particularly on the (i) need to ensure sustainability of institutions; (ii) need for PRONACOM to focus, avoid duplication and dilution of its resources; and (iii) need for better design and implementation of M&E frameworks, particularly the logical connections between inputs, outputs, outcomes and objectives.
P055085 | SECOND RURAL AND MAIN ROADS PROJECT | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2003 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/579291475873237925/text/000012394-20150112112624.txt | http://documents.worldbank.org/curated/en/579291475873237925/pdf/000012394-20150112112624.pdf | The following lessons are taken from the ICR with some adaptation of language:For most infrastructure projects, it is prudent to trigger the Involuntary Resettlement safeguard (OP 4.12) at appraisal. Close attention to potential resettlement issues at the preparation stage, including taking into accout cultural practices and land tenure issues, is of critical importance. Elaboration of a detailed social assessment focused on the potential resettlement would have been highly useful in this case. Development objectives should be precise, clear and measurable. Alignment of the development objectives with what can realistically be achieved by the project, and attributed to it, is necessary for adequate monitoring and evaluation, as well as an aid to implementation. A thorough assessment of implementing agency staffing and capacity can help to avoid or minimize implementation problems and delays. In this case, problems encountered during both preparation and implementation could have been lessened had the implementing agencies been adequately staffed with, for example, a dedicated, full-time environmental and social management team from the outset. Ensuring adequate financing for road maintenance is nearly always a major challenge, and Bank engagement in the road sector should pay special attention to this issue. Rural roads often face still stronger financial constraints. A solid monitoring and evaluations system is of critical importance. Establishing adequate baselines for project outcome indicators should be a priority at the design stage.
P055120 | Tanzania-Transport Sector Support Project | Other | Africa |  |  | Infrastructure | Transport | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/851901527273065207/text/Africa-TZ-Transport-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/851901527273065207/pdf/Africa-TZ-Transport-Sector-Support-Project.pdf | Four lessons are taken from the ICR with some modification of the language: Establishingstandardized bidding processes and removing requirements for prequalification can create a more competitive bidding process andresult in lower costs. Earlier World Bank transport projects in Tanzania hadincreasingly high bidsfor civil works that sometimes necessitated cancellationof bidding processes by the Bank. By streamlining the biddingdocuments and standardizing relevant sections, as well ascarrying outbiddingwithout prequalification, the numberof bidders was greatly increased, with bids received from contractors from a wide range of countries. The increased competitiondrives down the costs of received bids. Well-designed airport master planshelpavoid fragmentation ofactivities andissues with safegyard implementation. Under this projects aviationcomponent, there were many issues that could have been avoided if better planned. This relates to issues in Zanzibar (poorintegration with a separate project being financed by the China Exim Bank). In Bukoba, better planning could have identified theneed to relocate the primary school. In addition, security fencing was not included in the original designs of the regionalairport, but during implementation it was determined that residents of the local areas were crossing through the airportarea. It is essential to include road safetyinto road project designtoavoid treating it as an afterthought. During the remediation activities on one project-financed roadsection, the road safety measures were removed from this part of the projects road works. As safety was not identified as akey objective of the project, and the safety of the road lengths was not monitored under the project, there was little incentivefor the contractor to retain these measures. Furthermore, identification of safety as a priority during road design and identifyingpedestrians as road users equal to those in vehicles may have encouraged road designs to incorporate footpaths or wider shouldersin areas with settlement. Assuch road safety worksare beingmore frequently included in recent World Bank roadprojects, additional attention should be given to older, legacy projects undersupervision. Consultations with those living in the area around an intervention can bevital, both during preparation and supervision. The project-financed Arusha-Minjingu road runs through anarea frequently used by nomadic Maasai herdsmen. As the road had the potential to impact their animals ability to movebetween grazing areas, the contractor did significant consultations and provided signage and earthworks in identified areas toimprove the safety and ease of herds crossing the road. In Bukoba and Tabora, the airport works blocked walking paths traditionallyused by local residents. To ease their travel, and prevent the safety risk of their incursion into the airports, the impactedresidents were involved in planning an alternate path to be constructed by the project. In both cases, users expressed appreciationfor the new routes.
P055122 | Health Sector Support Project | Western and Central Africa | Chad | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/746151474420908239/text/000020051-20140618062544.txt | http://documents.worldbank.org/curated/en/746151474420908239/pdf/000020051-20140618062544.pdf | Lack of rigor in overseeing the development and financing of a medium-term expenditure framework for health is likely to result in the under-financing of critical components of service delivery, especially in a politically volatile environment: Failure to measure trends in health outcomes during the project life and to assess the extent to which such trends are attributable to project inputs and outputs undermines the results focus of health investments as well as the Bankâ€™s and the Governmentâ€™s ability to learn and fine-tune project design and activity during implementation with a view to improving the development impact of their efforts; andThe MTR is an important opportunity to assess project progress and constraints to full implementation of components and achievement of objectives. It can be a critical juncture during which the project can be restructured and dialogue can be intensified to manage and/or to overcome bottlenecks that threaten successful outcomes. Failure to seize fully this opportunity, especially when a project is in difficulty, is likely to lead to an unsatisfactory outcome.
P055131 | Structural Adjustment Credit 2 (SAC 2) (formerly PSRAC) | Europe and Central Asia | Azerbaijan | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2002 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/278421474750308419/text/000020051-20140612152322.txt | http://documents.worldbank.org/curated/en/278421474750308419/pdf/000020051-20140612152322.pdf | 1. A thorough assessment of ownership and capacity is needed, especially for complex reforms such as those supported by the SAC II. 2. Continuous policy dialogue underpinned by sector projects and ESW is needed to successfully implement many adjustment reforms. Country office staff can, and should, play a key role in this process. 3. Adjustment operations based on full ownership and adequate capacity can provide important signals to other sources of financing.
P055133 | Post-Conflict Rehabilitation Project | Europe and Central Asia | Tajikistan | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 2000 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/954531474944895617/text/000020051-20140522104339.txt | http://documents.worldbank.org/curated/en/954531474944895617/pdf/000020051-20140522104339.pdf | Flexibility and speed are essential if the Bank is to be of real help in post-conflict cases. Balance of Payments support provided both. Equally important is the correct assessment by the Bank that a new government emerging from a conflict merits this kind of support, as in this case.
P055137 | Structural Adjustment Loan 3 | Europe and Central Asia | Russian Federation | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2001 | 2002 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/349321475092861607/text/000020051-20140602111610.txt | http://documents.worldbank.org/curated/en/349321475092861607/pdf/000020051-20140602111610.pdf | 1. As stated in the ICR, the Bank should be realistic in expectations over the pace of reforms. Especially given the implementation record in Russia and Russia's special circumstances (federal structure, large number of regions, powerful business interests), the Bank needs to evaluate carefully the likelihood of reforms, and calibrate lending conditionality closely to this. The restructuring of SAL 3 was a realistic step in this direction. 2.The Bank needs to pursue broad outreach programs in coordination with partners to build a broad base of support for essential reforms.
P055155 | Urgent Environmental Investment Project | Europe and Central Asia | Azerbaijan | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/570441474908822509/text/000020051-20140613085843.txt | http://documents.worldbank.org/curated/en/570441474908822509/pdf/000020051-20140613085843.pdf | Projects designed as pilot activities should clearly identify the desired outcomes of the demonstrations. Projects should identify whose activities or approaches are expected to change as a result of the knowledge or capacity gained. Outcome indicators should be designed to capture the catalytic effects of pilots and the projects should be designed to facilitate the necessary follow-up activities.With respect to clean-up and remediation of contaminated land, institutional aspects such as land ownership and land use planning should be identified and addressed up front. Where land is in high demand for residential and other development, it may be expected that any remediated land will be in great demand and occupied illegally unless appropriate provisions are made in advance. Particularly for the ECA region, it is important to be realistic regarding how quickly historically state-operated activities and institutions can be transformed to a model based on commercial, market based approaches. State owned companies can provide a bridging mechanism. Public Private Partnerships can also bridge the gap between purely state owned enterprises and pure commercial enterprises. Institutional structures required for sustainable project objectives should be put in place as early as possible during project implementation.
P055156 | Regional Initiatives Fund Project (RIF) | Europe and Central Asia | Bulgaria | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2001 | 2003 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/469801475097687993/text/000020051-20140604054440.txt | http://documents.worldbank.org/curated/en/469801475097687993/pdf/000020051-20140604054440.pdf | A number of lessons were reported in the ICR but, in the absence of systematic evaluative data, the robustness of these lessons is unclear. Two lessons of broad applicability based on the information in the ICR are:1. Projects such as LILs where the primary purpose is to pilot test require particularly strong and systematic monitoring and evaluation.2. When the main objective is large-scale employment generation, the experience of this project supports evidence from other sources that social funds are unlikely to be the best mechanism to achieve this.
P055157 | Health Sector Reform Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/305801474549854083/text/000146597-20140619154610.txt | http://documents.worldbank.org/curated/en/305801474549854083/pdf/000146597-20140619154610.pdf | Potential synergies between various Bank operations should be identified and capitalized upon. In this case, concurrent policy operations were critical to keeping an important hospital financing reform on the agenda. Overly complex health reforms are difficult to implement; as a rule, simplification and sequencing increase the chances for success. This project may have avoided shortcomings by adopting a more sequenced approach supported by adequate political economy analysis.Failure to assess the political economy of reform and to plan to address it reduces considerably the probability of success.. Bank-financed projects cannot always be coordinated with election cycles, and electoral outcomes cannot be predicted, but projects involving major structural reforms with political implications should be attentive to electoral considerations and stakeholder interests.
P055158 | Education Modernization Project | Europe and Central Asia | Bulgaria | IBRD |  | Human Development | Education | IBRD | IPF | 2001 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/727521474512744745/text/000020051-20140612152751.txt | http://documents.worldbank.org/curated/en/727521474512744745/pdf/000020051-20140612152751.pdf | When difficult and extensive sectoral objectives are to be achieved, an APL with a brief timeline for each phase may be insufficient. A programmatic approach may give governments more time to carry out the complex actions necessary.- A realistic assessment of a borrower's implementation capacity and ability to use procurement and financial reporting guidelines facilitates the formulation of a proper design and reduces the risk of exceedingly ambitious objectives that cannot be met.- Assigning clear responsibilities, giving authority, and making staff accountable for results would help promote implementation, increase ownership and facilitate the attainment of objectives.
P055159 | Enterprise Institution Building Project | Europe and Central Asia | Uzbekistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/133291475075552944/text/000020051-20140613085201.txt | http://documents.worldbank.org/curated/en/133291475075552944/pdf/000020051-20140613085201.pdf | The Bank should have done a more thorough stakeholder assessment to gauge the extent to which the goals of the project were shared by intended participants.When the Bank understood the extent to which the environment was inimical to privatization, cancellation of the loan should have become a more serious option, rather than the more limited restructuring done at MTR.
P055160 | Structural Adjustment Credit (SAC) | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2002 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/821421474500999051/text/000020051-20140604043836.txt | http://documents.worldbank.org/curated/en/821421474500999051/pdf/000020051-20140604043836.pdf | An interministerial Committed supported by the Prime Minister is an effective vehicle for mobilizing support for reforms supported by adjustment credits. Adjustment operations launched in a crisis can show the Bank's support for reform in a concrete way, although such operations need to be tailored to realistic capacity and implementation constraints and need to be selective.
P055160 | Structural Adjustment Credit (SAC) | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2005 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/900451468768316767/text/29638.txt | http://documents.worldbank.org/curated/en/900451468768316767/pdf/29638.pdf | 5. Lessons 0 Small, focused, one-tranche policy projects with realistic objectives, supported by technical assistance, may work well intransition countries that are politically unstable and have low market economy skills (e.g., credit risk analysis for private sector banking or enforcing competitionregulations). A limited reform agendai s easier to implement, especially ifparliamentary approval i s neededfor new laws when the political landscape i s not stable. Reformcontinuity can be maintainedby similar policy or investmentfollowon projects. 0 Incrisis situations, animmediate responsecanbevaluable beyondits direct purpose. For example, the very quick preparation and disbursement o f PESC was effective inproviding development assistance and coordinating substantial humanitarianassistance. 0 PESC was disbursed against a negative list o f imports instead o f the positive list that i s usual for an emergency import credit. Disbursementagainst a negative list expedited resource transfer, which was appropriate inAlbania's circumstances. 0 As hasbeenwell documented, aid coordinationis critical to ensure appropriate, harmonizedand effective assistance where many donors are involved. Coordination should also ensure that government agencies dealing with donors are also appropriately aligned. Some institutions established for special purposes under IDAprojects such as BART, couldbe transformed into private sector commercialentities when their mandate i s complete. This transition could be an integralpart o f that organization's strategy.
P055166 | Community Development Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/524921474659643367/text/000146597-20140619165242.txt | http://documents.worldbank.org/curated/en/524921474659643367/pdf/000146597-20140619165242.pdf | Project design needs to include measures to prevent better-off communities with stronger capacity from capturing most of the resources made available for demand-driven subprojects. The commune development component of this project was initially biased toward better-off communities because the selection process did not filter adequately for poverty criteria (see Section 3 above).The Manual of Procedures needs to be regularly revised in the light of operational experience. This is particularly the case for social fund projects with a large measure of operational autonomy and no close government or Bank oversight. The development of community associations may be an important means to build local capacity but, over the long term, these arrangements may not be sustainable; and they are no substitute for the strengthening of local government. In Madagascar the fiscal decentralization that is the key to stronger local government has yet to be fully embraced by the central authorities.
P055173 | Education System Realignment & Strengthening Program (APL #1) | Europe and Central Asia | Georgia | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2008 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/853531474549973963/text/000020051-20140619110341.txt | http://documents.worldbank.org/curated/en/853531474549973963/pdf/000020051-20140619110341.pdf | The timing and duration of activities of such an ambitious and comprehensive reform program should be carefully planned at the outset; the arguably most difficult phase of the Georgia Education APL was allocated the least timeâ€”3 years of a 12-year program.Neither stakeholder consultation in project design nor stakeholder participation in project implementation can substitute for careful analysis of the political economy of reform. Strong sector work before the project, continuous technical assistance and policy dialogue, and proactive and flexible supervision are key elements of effective supervision.Baseline data should be collected during project appraisal.
P055186 | PUBLIC FIN. REFORM | Western and Central Africa | Niger | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2000 | 2002 | ICRR | >=25 million & <50 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/537281474653110595/text/000020051-20140604043105.txt | http://documents.worldbank.org/curated/en/537281474653110595/pdf/000020051-20140604043105.pdf | 1. An unsatisfactory project can, nonetheless, generate important benefits. In this case, the groundwork has been laid for improved investment planning and expenditure management in the critical health and education sectors. Moreover, a model for suppressing new public sector arrears, and liquidating outstanding ones, has been demonstrated. Lastly, management information systems in the civil service and revenue areas of the public sector have been strengthened. 2. The Borrower's willingness to finance technical assistance supporting this credit from its own resources seems to have enhanced ownership of the results, and may represent a superior way to transfer know-how in Niger.
P055230 | ABAPO-CAMIRI HIGHWAY | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/387981474573739047/text/000020051-20140615100107.txt | http://documents.worldbank.org/curated/en/387981474573739047/pdf/000020051-20140615100107.pdf | Even when an unstable political background prevails, a successful infrastructure project can still be accomplished provided that the implementing authority has sufficient capacity internally. Initial strengthening of this capacity can result in a much better project result.Public acceptability of a project can be improved remarkably if a program to target the needs of nearby poor communities is incorporated.Specifically contracting out the Indigenous Peoples' Development Plan and a Community Relations Program to interested specialist firms is much more effective than just including the tasks as items in the civil works contract.The introduction of new maintenance contract schemes requires a gradual implementation approach according to the level of maturity experienced in the local road sector.
P055232 | Rural Education Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2003 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/551351474481382946/text/000020051-20140619081454.txt | http://documents.worldbank.org/curated/en/551351474481382946/pdf/000020051-20140619081454.pdf | Project designs that holistically deal with a sector can in principle be highly relevant to the citizens' needs. However, implementing agencies must be strong in order to carry out complex projects. It is important to assess institutional ability and government commitment before financing projects with multiple interlinked components. When there are problems during appraisal that remain unresolved, a smaller project and a simpler design may be more effective than a larger project that may not give the expected outcomes. Validating and evaluating pilot experiences prior to scaling-up is critical when these are building blocks in the initial stages of projects. Piloting allows the researcher to test procedures and assumptions that can be readjusted, if necessary. Delays in components that are expected to be implemented well early on may result in limited achievement and cancellations of components that are expected to build on them.High quality information at the start of a project is a prerequisite for designing a sound monitoring platform that allows monitoring targets throughout the process. Complexities in the measurement of baselines compromise the ability to track changes and attribute improvements to a project rather than external factors.
P055292 | Banking Sector Restructuring and Privatization Project | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/678521474560028342/text/000020051-20140613053010.txt | http://documents.worldbank.org/curated/en/678521474560028342/pdf/000020051-20140613053010.pdf | Â· The project was successful, in large measure, due to strong Borrower support.Â· The Borrower took full responsibility for program design and implementation, which worked well.Â· Flexibility on the part of the Bank in reprogramming project funds facilitated progress.Â· In some cases, it is desirable for state-owned banks to undergo cost restructuring before privatization to bring their cost/income ratios into line with private banks.Â· The recapitalization of a state-owned bank, so that it can meet the minimum capital adequacy requirement, facilitates its sale.
P055292 | Banking Sector Restructuring and Privatization Project | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2005 | 2012 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/963891468325180297/text/700300PPAR0Box0IC0disclosed08080120.txt | http://documents.worldbank.org/curated/en/963891468325180297/pdf/700300PPAR0Box0IC0disclosed08080120.pdf | 4. Conclusions and Lessons Learned 1.78 A main finding of this evaluation is that the reforms supported by the Bank's operations strengthened the financial sectors of the four focus countries and helped them resist the impact of the financial crisis of 2008-2009. 1.79 In all countries the financial systems are still banking oriented but the banking sector is much stronger and generally in a better position to respond to the financing needs of the private sector. Yet, risks remain, as credit growth is often concentrated, credit risk management systems need further strengthening, and, in some cases, credit to state-owned enterprises is not entirely based on market criteria. Moreover, in most of the focus countries, growth in private sector credit has not reached the levels anticipated or desired. 1.80 In parallel with the specific conclusions reached in the PPARs of the individual operations, a number of lessons can be drawn from findings common to the four countries. Even though the measures supported by these operations were not necessarily representative of financial sector reform efforts around the world, lessons drawn from the comparison of experiences may be useful to the governments in question, in addition to expanding the knowledge base regarding the design of these types of operations as well as the approaches they took and the results achieved. (i) The quality of analytical work is crucial for the success of policy-based operations in the financial sector. 1.81 In three of the four countries, the policy content of the operations was closely based on the findings of recently completed FSAPs and further technical analysis conducted during preparation. In Guatemala, the high quality of the technical analysis in the 2000 FSAP and the FSAL preparation was crucial to engage the government's commitment to the reform agenda. This included interactions between the Bank and the Parliament. In Morocco, the 2002 FSAP recommendations were incorporated in the design of the Bank's operation. They were fully accepted by the authorities who endorsed the need for decisive action and committed to overhaul the regulatory framework and undertake a fundamental financial and operational restructuring of state-owned financial institutions. The high quality of the technical analysis (FSAP and Accounting and Auditing ROSC) provided the basis for the policy dialogue and technical discussions during the preparation and implementation of the operation, and underpinned the extensive and effective cooperation between the government and the Bank team during implementation. 1.82 The preparation of the programmatic operations in Egypt also built on the policy dialogue that had been conducted with the authorities over a long time and particularly in the context of the 2002 FSAP, the 2007 FSAP Update, and related analytical work. In addition to valuing the Bank's experience in designing development policy loans in the financial sector, the authorities placed special weight on the Bank's role in coordinating in a concerted and effective way the offers of technical and financial assistance of bilateral and multilateral donors. The division of labor among donors aimed at maximizing the financial and technical benefits for Egypt, although this may also create a challenging task in project monitoring and supervision (see below). In Pakistan, the BSRP was not prepared on the basis of a recent FSAP. The BSDP, however, picked up some of the recommendations of the FSAP carried out in early 2004, which took stock of the banking sector reforms that had been implemented so far. 1.83 In general, the analytical work undertaken by the Bank in the four countries has reflected a significant change in policy direction. Whereas in the 1980s, a main focus was placed on moving away from direct to indirect methods of monetary and credit control, the last two decades have seen a growing emphasis on micro prudential controls that seek to strengthen the soundness and safety of banks, insurance companies and other financial institutions. The Bank's analytical work has stressed the importance of maintaining reasonable macroeconomic and financial stability, entailing moderate inflation as well as small fiscal and external deficits. Less attention has been paid until relatively recently to macro prudential issues, perhaps because the banks and other financial institutions operating in these countries have not engaged in activities that created large systemic risks. Unlike banks in many European countries, there has been little reliance on wholesale funding and limited recourse to consumer and housing loans denominated in, or indexed to, foreign currencies. The authorities have applied higher capital adequacy requirements to reflect the higher credit risks facing banks in developing countries but have not considered a more extensive use of macro prudential controls. (ii) Effectiveness of implementation support is a key condition for results because financial sector reforms are easy to design but difficult to implement. 1.84 This was most evident in Guatemala, where high quality technical analysis and advice was provided as part of implementation support of the Bank's FSAL, not only through the supervision of the operation but also through the FTAL operation of technical assistance. This continued technical and policy dialogue with the authorities and their technical teams was important to maintain the authorities' ownership and commitment to the FSAL development objectives during the course of two administrations. The Bank extended technical assistance that has greatly helped strengthen the capacity of the Bank of Guatemala and the Superintendent of Banks to implement the reform actions supported by the FSAL. The high quality of TA under the FTAL was critical in setting up the deposit insurance and bank resolution agencies and in setting up the legal authority to carry out bank resolution, a system that responded successfully to the two problem banks in 2006 and 2007. Supervision missions of the FSAL, complemented by supervision of the FTAL operation, provided timely technical assistance and advisory services to the implementing agencies, including following the failure of the fourth largest bank during the second half of 2006. 1.85 This intense level of technical assistance efforts is often crucial for the success of policy-based operations, but the needed resources are not always available to Bank teams if, contrary to the case of Guatemala, there is no parallel technical assistance loan. Although grants for TA may be available from other development partners, the coordination with Bank operations can be too slow and complex when country problems must be met quickly to achieve the best results for the country. 1.86 In Egypt, by contrast, the effectiveness of operation implementation support suffered from the division of labor among several participating donors and an apparent failure to provide for joint supervision, implementation completion reports, and evaluation missions. The Bank played a key coordinating role in the division of labor during the preparation of the loan operations but failed to act as a clearing house for implementation support. As a result, crucial comprehensive reports on key aspects of the reform program, such as the effectiveness of the capacity building program in banking supervision and the solidity of the financial and operational restructuring of state-owned commercial banks, have not been compiled. Greater attention needs to be placed on the organization of effective project supervision when several financiers participate in complex operations. Multi-donor operations, as those in Egypt, face a challenging task of effective coordination and supervision, especially when there is a division of labor in the provision of technical assistance that is crucial for the successful implementation of the reform program. 1.87 Enhancing the quality of Monitoring and Evaluation (M&E) frameworks can play a key role in strengthening program implementation and improving outcomes as suggested by evidence from several evaluations conducted by IEG. This requires adequate design of M&E, with well-specified outcome (rather than output) indicators; adequate baselines and realistic targets; strong ownership and alignment with data collection capacity of client implementing agencies. But good M&E also requires a greater transparency of the reform program, through the regular publication of comprehensive data and assessments. Enhanced transparency conveys the continuing strong commitment of the authorities and inspires greater confidence that the reform is genuine and goes beyond mere cosmetic initiatives. Lessons learned are shared with a broader audience and do indeed generate greater demand for further reforms as well as for corrective adaptations when particular measures appear to be counter-productive and overly costly. Lack of transparency veils the whole reform program in excessive secrecy and risks undermining its credibility. 1.88 Egypt offers an example where information gaps do not facilitate monitoring and evaluation of the reform program. The CBE highlights in its annual reports the objectives and broad outlines of the capacity building program but contains little detailed information on the changes that have taken place or an evaluation of the impact of the new approach on bank solvency and efficiency. There is no indication of the success of the new approach in supervising the complex operations of modern banking groups and in redressing the regulatory forbearance that had long characterized its relations with the large state-owned banks. The same also applies to the financial and operational restructuring of the state-owned commercial banks. In Morocco there is regular publication of extensive economic and financial data, including a detailed annual report on banking supervision and bank performance. These permit a comprehensive assessment of the pace and achievements of the reform program. (iii) Multi-tranched financial sector adjustment operations are effective instruments to support major financial sector reforms. 1.89 The success of the Guatemala FSAL and the Morocco FSDPL shows that a multitranched adjustment operation can be very effective in cases of major financial sector reforms that involve the enactment of new basic legislation and its regulations, and the institutional strengthening of the agencies in charge of implementing the reforms, particularly agencies that carry out bank resolution. A multi-tranched adjustment operation can support the process of reform at different stages and respond to unforeseen challenges that could derail the reform process. By contrast, the stand-alone, single-tranched Banking Sector Development Policy Credit for Pakistan did not have a material impact on privatization of state-owned banks, which was concluded prior to this operation. The focus of the operation was on institutional building issues and further strengthening the State Bank of Pakistan, but sustained progress in such areas are difficult to achieve with a stand-alone, single-tranche operation, with no follow up and no associated technical assistance. Similarly to multitranched operations, programmatic loans are also potentially effective in supporting reform programs, but may require more focused efforts to obtain the best results from major reform processes. The slippages observed in the outcomes of the DPL-2 in Egypt, compared with the DPL-1, illustrate, although the two operations were not formally part of a programmatic series. (iv) A strengthened regulatory framework and banking supervision enhance credit risk management and help withstand shocks but do not eliminate the risk of overextension of credit and deterioration of the quality of bank portfolios. 1.90 Reflecting tighter supervision and the adoption of improved risk management practices, but also other factors, such as the limited development of their financial markets, the commercial banks in all four countries that received Bank assistance did not suffer large losses from the global financial crisis because they did not hold toxic assets and did not rely on wholesale funds to support their lending. They did not suffer from either maturity or currency mismatching, while neither bank leverage nor credit expansion were excessively high. Tighter prudential rules and the adoption of improved risk management practices contributed to this favorable outcome. 1.91 Pakistan offers perhaps the best illustration of the effectiveness of these reforms, as the banking system was able to withstand the impact of the global financial crisis as well as the various bouts of domestic turbulence both political and due to the 2010 flooding. The banking sector in Pakistan has not had any major issues following the global financial crisis, partially because the banks in Pakistan did not have significant foreign exposures and also banks were not active in trading or investing in derivatives and other off balance sheet type instruments. NPLs have increased since 2007 but the banks are well provisioned against the potential loss and are actively involved in resolving these loans. In Egypt too, the banking system seems to have withstood the political turbulence in 2011 relatively unscathed so far. 1.92 But Morocco illustrates a case were the banks expanded at a very rapid pace their financing of housing, among other sectors, and faced the risk of growing NPLs in the future resulting from the abrupt fall of sales of housing units targeted to nonresident buyers. Because the banks followed conservative lending policies and insisted on relatively low leverage levels by the property developers they financed, they were not, at least initially, impacted heavily from the collapse of housing sales. However, NPLs from property developers may increase in the future if the economic recovery in Europe is overly slow or if the sovereign debt crisis were to further intensify. The central bank took steps to ensure the resiliency of the banking system by raising the minimum CAR and the commercial banks responded by slowing down the rate of credit expansion, but these actions were taken somewhat late in the process. 1.93 In Pakistan too, the rapid expansion in consumer and SME credit in the period from 2000 to 2007 affected the quality of bank loan portfolios, partly owing to poor credit assessment standards and the absence of a credit bureau during this period. A credit bureau has been established recently and could help enhance the quality of consumer lending by improving the information available to lenders regarding the credit history of borrowers. Banks are well provisioned against NPLs but the absence of a satisfactory property registration mechanism creates uncertainty as to the ownership of property and thus the value of collateral held by banks. 1.94 The evidence reviewed by the PPAR in the four focus countries does not permit to draw insights on the desired sequence of reforms in the financial sectorâ€”a perennial quest of analysts and policymakers. Experience from the reviewed operations, as well as from other countries, suggests that reformers must implement change wherever they can and push for more extensive reforms as they go along. However, the one area where some progress is needed prior to the reform is in improving the regulatory frameworkâ€”otherwise liberalization, deregulation, privatization and restructuring are likely to fail if no attempt is made to strengthen prudential regulation. Strengthening the prudential and regulatory framework is a major challenge and is bound to take time. Moreover, it cannot be done while the system continues to be state-owned, undercapitalized, under-provided, overstaffed, and generally improperly managed. Thus, as also suggested by the experience of the four focus countries of the PPAR, structural reform and regulatory strengthening can only be done in parallel and require the strong and lasting commitment of the authorities and a willingness to learn from experience and adapt as needed. (v) Restructuring of state-owned banks without privatization requires strong safeguards to prevent retrogression into unsound practices. 1.95 In Pakistan, where financial and operational restructuring of state-owned banks was actively pursued with Bank support, transfer of bank ownership to the private sector was considered a key prerequisite for improved financial intermediation. The privatized banks were pushing ahead with institutional development plans to leverage their strengths and address their weaknesses and better position themselves as private sector banks. In Morocco, the restructuring and partial privatization of formerly specialized state-owned financial institutions was also implemented in a decisive and effective way. 1.96 In Egypt the reform program did not include the privatization of the two largest commercial banks nor the large insurance companies but many measures were taken to improve the management of these institutions, which one commentator resembled to an effective â€•privatization of managementâ€– rather than â€•privatization of ownershipâ€–. The reform program has privatized the smallest of the four state-owned commercial banks and has divested public bank shares in joint-venture banks. However, state-owned institutions still control close to 50 percent of banking assets and a higher market share of insurance business. 1.97 A dogmatic approach to the ownership question would not be justified, especially after the public rescue of so many leading private banks and insurance companies in highincome countries around the world during the 2008 global financial crisis. However, as in far too many countries state-owned banks have extended loans on non-commercial criteria to borrowers with strong political connections and have suffered from large and persistent NPLs from both state-owned enterprises and large private sector borrowers, strong safeguards would be required to ensure that their operational and financial reform is viable. In Egypt, the safeguards that have been created to prevent retrogression into unsound practices do not appear to be sufficiently strong since bank lending to SOEs on a long-term basis and thin margins has been resumed. Despite the impressive scope of the overall reform program, the objective of creating a resilient and competitive financial sector appears to call for stronger safeguards. (vi) Better access to credit for the private sector requires a broader set of reforms, including a favorable macroeconomic framework. 1.98 Bank financial restructuring, privatization, and strengthening of the prudential framework and supervision of banks can lay the groundwork for an increase in credit to the private sector on a sound basis but do not necessarily entail an increase in lending volumes in the short term. If anything, as a result of cleaning up the balance sheets of banks and writing down provisioned NPLs or NPLs settled by the government, the volume of outstanding bank credit to the private sector may decline. Depending on country circumstances, a broader array of reforms, especially in the legal area, may need to complement bank sector reform to help achieve a visible improvement of access to credit. 1.99 Key legal reforms include the establishment of an efficient bankruptcy legislation and insolvency regime; the establishment of a credit bureau to share borrower information; the creation of a modern collateral regime. However, these legal reforms are more difficult to implement and take longer to become effective. For example, it takes time to start a credit bureau up, get the data and get the banks to use it. But these reforms are important and should not be overlooked. And because they take time it is important that they be initiated early in the reform process. Other factors that may delay the impact of these legal reforms is that specific institutions may need to change the way they work in order to better serve potential clients. This again takes time, even when a distortion-free regulatory framework is in placeâ€”it takes, for example, time to set up a greater branch network to reach underserviced clients or to strengthen bank appraisal capabilities by assessing projects by cash flow. Bank restructuring and privatization contribute to these outcomes but their impact may not be strong enough if the legal reforms that facilitate access to credit are neglected. 1.100 In Egypt, the provision of credit to the private sector, and more especially to SMEs, continues to fall below relative to the needs for sustainable economic growth and employment creation. Partly as a result of writing down NPLs, partly reflecting tighter bank lending standards, and partly owing to the global financial crisis, and increased government borrowing from the banks as foreign holdings of bonds declined, the credit to the private sector in proportion to GDP declined from 54 percent in 2004 to 36 percent in 2009. Two fundamental shortcomings of the Egyptian legal framework that impede the rapid and sound expansion of credit facilities to SMEs include the absence of a modern bankruptcy law and insolvency regime; and the lack of an efficient registry of collateral security on movable assets. And while a credit bureau has been established, an attempt to develop an SME rating service did not succeed. These shortcomings were not addressed by the two Bank operations reviewed. 1.101 Another example is Pakistan, where growth in private sector credit has not reached the levels anticipated or desired. The Bank's operations were designed primarily to assist the privatization of the NCBs and to shift the structure of the market from one dominated by state-owned, loss-making, and inefficient banks to private, profitable, and well-managed banks. In addition the Bank' operations supported the strengthening of the Central bank and the removal of certain legal and structural distortions in the system. The reform should have facilitated increased lending to Pakistan's private sector and, indeed, banks expanded their lending portfolios post privatization in the years up to 2007. However, as a result of still weak risk management practices and economic shocks, they suffered some losses from NPLs, thus adopting more cautious lending approach. 1.102 In addition, a number of impediments stemming from the macroeconomic and fiscal situation have been present\. (i) inflation rates have been running in excess of 20 percent, resulting in very high interest rates; (ii) state borrowing from the banking system including T-Bills amounts to about 34 percent of bank assets, in effect beginning to crowd out the private sector; (iii) banks are in a position to generate very attractive margins from investing in T-Bills, with little incentive to pursue lending to the SME sector and consumers which is much more risky and carries a much higher administrative cost. Maintaining macroeconomic stability appears a necessary complement to bank sector reform in order to achieve viable growth in private sector access to credit. Similar trends have developed in Egypt, where bank lending to the private sector is being crowded out by growing bank holdings of government securities, as the budget deficit has steadily increased and foreign investor demand for government bonds has decreased since the onset of the global financial crisis.
P055304 | Real Estate Registration Project | Europe and Central Asia | Slovenia |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/509291475085343632/text/000020051-20140613090549.txt | http://documents.worldbank.org/curated/en/509291475085343632/pdf/000020051-20140613090549.pdf | The ICR identifies several lessons from the experience of this project, including:Courts do not provide the most suitable home for registration of title. Property registration must operate as a service to participants in the land market and meet their needs - and the backlog of land registration cases that remains is in part due to the culture in the court system and a lack of business focus amongst those involved.Instilling a culture of service provision is as important as new technology. IT alone could not solve the problem of the backlogs. Once this was recognized and changes were made to the organization and management of the Land Registry Offices, progress accelerated. The property registration system needs a leader, such as a chief registrar, striving for its improvement on a daily basis. A chief registrar would provide clear management and accountability for the land registry function. It is important to have a viable business model with clearly defined performance based targets. The project significantly improved the business model being used by SMA by making it focus on identifying its key clients and potential demands. which was used to build coordination mechanisms, medium term strategies and cost recovery plans which respond to specific needs.
P055304 | Real Estate Registration Project | Europe and Central Asia | Slovenia |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2010 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/183881468100745831/text/551120PPAR0P051IC0disclosed08131101.txt | http://documents.worldbank.org/curated/en/183881468100745831/pdf/551120PPAR0P051IC0disclosed08131101.pdf | 5. Lessons 5.1 The design and implementation of the Slovenia RERMP yields the following main lessons\. (i) A multi-agency institutional structure for land administration has inherent disadvantages compared with a single agency; particularly in coordination and in prospects for attainingjnancial self-sufficiency. The division of land administration activities between SMA for cadastre and the Supreme Court for registration (other agencies involved in RERMP were for ancillary activities rather than central land administration activities), resulted in coordination difficulties between the two agencies in the first several years of the project. Also, with cadastre separate from registration, cross-subsidization from the higher revenues of registration to cadastre with lower earning possibilities is made difficult by the institutional divide (paras. 3.45 to 3.48). (ii) Where a multi-agency institutional model is accepted as unavoidable, practical steps to reduce the disadvantages of these arrangements should be integrated in project design. An existing dual structure was strongly favored by Government. In this second-best situation, two main steps were taken under RERMP which proved useful in reducing the disadvantages\. (i) a strong coordination mechanism comprising a well-staffed PCO with minimal staff turnover, and a more senior level multi-agency Program Council was created both bodies met regularly and were actively supported by Government (para. 2.5); and (ii) The digitization information technology system, established in the later years of the project, enables data to be shared between SMA and.the Supreme Court (paras. 3.15 and 3.45). (iii) A land administration agency needs to exist uniquely for that task, be operationally independent and have full-time specialist stafi (This applies whether the institution is a single agency combining cadastre and registration, or whether the agency handles cadastre or registration alone.) These features were not enjoyed by the Supreme Court and the county courts responsible for RERMP?s land registration. Court judges had many demands on their time. There was no field supervision, nor any accountability of court staff to land registration (paras. 3.8, 3.45 and 3.48). (iv) Actions beyond the core activities of land administration should be considered f they i significantly enhance project impact and are within the project's implementation capacity. RERMP's housing finance and mortgage reform component is in the banking rather than land domain, but was a significant contributor to RERMP's goal to improve the efficiency of the land market. Inclusion of this component was within Slovenia's implementation capacity. While a focused land administration project would generally be preferred, addition to a project of a high impact ancillary component may be beneficial if manageable by the institution concerned (paras. 3.9 and 3.41). (v) Legislative reforms are an essential concomitant to establishing a land administration program. Development of a legal base for land administration, which was minimal before RERMP, was, appropriately, prioritized by Government and the Bank, and laws were passed to provide a structured legislative framework. Laws were proactively amended as experience was gained, and legislation in related sectors (mortgages, taxes) was also approved (paras. 3.26 and 3.27 and Table 5). S
P055383 | Social Services Delivery Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/564971474585887299/text/000020051-20140626121522.txt | http://documents.worldbank.org/curated/en/564971474585887299/pdf/000020051-20140626121522.pdf | ICRMonitoring indicators and a system for data collection and evaluation need to be established at the beginning of the project, as does the development of adequate skills for monitoring and evaluation at all levels.Building local procurement and financial management capacity right at project start-up is crucial for smooth implementation; and designated, well trained procurement professionals should be routinely be included in the implementing team.ICRR evaluatorA rigorous results framework needs to be in place to guide implementation, especially when the project is used as a mechanism to adapt to government priorities as they arise.
P055388 | Animal & Plant Health Protection Project | Latin America and Caribbean | Brazil | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 1999 | 2002 | 2006 | ICRR | Less than 10 million | [5 empty] | http://documents.worldbank.org/curated/en/751001475078416221/text/000020051-20140613061758.txt | http://documents.worldbank.org/curated/en/751001475078416221/pdf/000020051-20140613061758.pdf | The PCN did not draw any lessons from the experience with this project, but it should have. Surely, there is something to be learned about either processes, commitments, or incentives related to the failure to sign. This failure cost the Bank a lot of preparation and appraisal resources (which are not, but should have been indicated in the PCN).
P055432 | Public Finance Structural Adjustment Credit 2 (PFSAC 2) | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2003 | 2003 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/985771475088944551/text/000020051-20140612070309.txt | http://documents.worldbank.org/curated/en/985771475088944551/pdf/000020051-20140612070309.pdf | (i) Changes in laws and regulations and in institutions are only the first step toward the final goals of growth and efficiency in public finances; the fundamental test lies in implementation. The Borrower and the Bank must be aware of possible sources of vulnerability and respond promptly to emerging problems in implementation. (ii) The presence of a core team of political and technical leadership, in the midst of elections and changing ministerial cabinets, is critical to keeping reforms on track. (iii) Inter-entity and ethnic cooperation can be facilitated by external mediation, within a slow process of consensus building. This requires, inter alia, intensive supervision.
P055432 | Public Finance Structural Adjustment Credit 2 (PFSAC 2) | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2003 | 2005 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/793831468740693918/text/31343.txt | http://documents.worldbank.org/curated/en/793831468740693918/pdf/31343.pdf | 5. Lessons When original design intentions for a quick-disbursing operationhave to be drastically reduced inscope, inthe face of practical and political difficulties, then this should give riseto areassessmentofthe whole operation, inparticular the credit amount, to ensure that there remains a relationship betweenthat amount andthepolicy adjustments being supported. 0 Providing general budget support into a situation where there i s virtually no auditing of, or accountability for, government expenditures i s unwise, inthe absenceo f a watertight, monitorableagreement with the borrower on the use o f those funds. Insofar as current IDApolicy i s not to concern itselfwith the use o f h d s inaquick-disbursing operation, then either that policyhasto change or IDA has to forego the provision o fbudget support insuch circumstances. Providingbudget support, inthe face o fmajor tax evasion and excessive government expenditures, can bepotentially counter-productive, inthe absence o f an agreed and concerted direct attack on those elements. Otherwise the presence o fbudget support reducesthe naturalpressure on governments to take urgent and meaningful action. Inasituationwherethereisnotclearborrowercommitmenttoacourseofaction, or there i s a history o fback-tracking or non-implementationo f laws and regulations, the mere passageo f legislationor promulgationo fregulations is not usually a good basis for tranche release conditionality. There also needs to be a periodo f implementationor, better, release conditionalitybasedon actual results achieved. Onany issue, includingmacro-economic andtax-related issues, IDA should maintain an independent position. Ifthere i s disagreement between IDA andthe InternationalMonetary Fund(&IF), IDA support shouldbe basedon its own assessment. 0 Inahighlychargedpoliticalatmosphere,progresscanbeachievedbybringing conflicting parties together for technical discussions, with IDA staff or TA consultants present. To be successful, however, it requires the involvement o f particularly empathetic staff, the careful choice andbriefingofTA consultants, andintensive supervision-all ofwhich happened under the two PFSAC operations andSOSAC. Inthese respects, these three operations represent good practice. When a long and complicated agenda o freforms i s needed and where future detailed actions can only be properly prescribedafter further discussions and developments on the ground, careful sequencing o f operations is required. This was done for PFSACandPFSAC2,to be followed bythe proposed Economic Management SAC; and for SOSAC,to be followed by the proposed SOSAC2. Such careful sequencing is another example o f goodpractice. By contrast, there was no immediate follow-up to TAC,compounding its poor design as a onetranche operation.
P055434 | Small-Scale Commercial Agriculture Development Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2003 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/147671474946049562/text/000020051-20140624190446.txt | http://documents.worldbank.org/curated/en/147671474946049562/pdf/000020051-20140624190446.pdf | Based on the ICR the following lessons are highlighted:Even though larger irrigation schemes offer greater economies of scale, the greater cohesiveness among WUAs operating smaller irrigation systems provide better prospects for sustainability.The development of a credit system geared to agricultural producers is difficult when a subsidized interest program is also in operation and makes it difficult to bring about modifications in operational practices of Banks and MFIs.Even if interest rates are high micro-credit can effectively meet the need of farmers provided it is managed by organizations that are trusted by farmers, understand their needs, have the expertise of working with small clients along with the ability to provide proper reporting on the resources lent.The formation and development of cooperatives and associations is a long-term undertaking requiring continuous effort. While project efforts can facilitate them, trust and cooperation take time to build.
P055446 | EMERGENCY EL NINO DROUGHT RESPONSE PROJECT | East Asia and Pacific | Papua New Guinea | Blend |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1998 | 2002 | 2003 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/991031475072668329/text/000020051-20140612061913.txt | http://documents.worldbank.org/curated/en/991031475072668329/pdf/000020051-20140612061913.pdf | An emergency loan should be the choice of instrument in the case of emergencies, not in the case of wanting to "quickly prepare a project for implementation, while the El Nino effects were still fresh in people's minds," as the ICR states. With the adequate preparation time that a sector investment and maintenance loan affords, many of the shortcomings associated with rushed project preparation that were encountered could have been avoided.To trigger more timely interventions in PIU (in this case, the PCFU) appointments and provide an incentive for appropriate selection by the Borrower agency, projects could include in the legal agreement a covenant that not only obliges appointment satisfactory to the Bank, but also has an additional clause that specifies that the appointee will have a probationary period of, say, four months, at which time the Bank would have to be satisfied with performance for it to accept the appointee as being satisfactory.Project design should take into account that the Borrower, on all levels--local and national government, as well as communities--will have even less capacity to function, due to the strains on their resources following a disaster. This realization should be coupled with a clear analysis of the Borrower institutional capabilities on all levels involved. Such an analysis should take place during project design.There is a risk in creating new project implementation entities. Where the project design called for using an existing institution (the agricultural research component) it was successful.
P055454 | Kerala Rural Water Supply and Environmental Sanitation Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/157191474652486531/text/000146597-20140619152442.txt | http://documents.worldbank.org/curated/en/157191474652486531/pdf/000146597-20140619152442.pdf | Decentralized delivery of RWSS requires the active participation of local government to ensure greater accountability and long term sustainability. Local government needs to be well integrated into the institutional design of projects to provide guidance on regulations, procedures and local conditions. Their support also provides a safety-net during the early years of beneficiary management as they are able to mobilize, as needed, external resources more efficiently. Demand-led development works well if communities make informed choices. Development of local capacity through 'leaning-by-doing' approaches, assisted by independent quality control consultants, has the potential to accelerate project implementation as happened in this project.A step-by-step approach to scaling-up decentralized service delivery works well. This approach benefits from learning-by-doing that enables refinement of approaches that lead to accelerated buy-in and implementation.
P055454 | Kerala Rural Water Supply and Environmental Sanitation Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2009 | 2013 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/274511468049801437/text/787860PPAR0P0500Box377377B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/274511468049801437/pdf/787860PPAR0P0500Box377377B00PUBLIC0.pdf | Lessons 4.9 There are five specific lessons from this assessment\. o Improving the quality of rural service delivery to increase access to water supply and sanitation improves environmental health. It is effective irrespective of the source of funding or implementation approach used, be it decentralized and community-led or centralized and government-led. o Given a supportive institutional environment, decentralized, community-led water supply and sanitation projects can be both effective and less costly at providing new rural infrastructure. Given the right training, support, and autonomy, communities are able to design, manage and operate water supply and sanitation schemes. Importantly, communities were able to manage sufficient cost recovery to cover routine operation and maintenance. However, equipment damage caused by fluctuating rural power supplies and local environmental problems (such as landslides), create repair problems beyond communities' capability, and there is a role for government-sponsored assistance with these problems. o Government line agencies that have traditionally delivered services through a centralized, government-led approach face challenges in supporting decentralized, community-led rural water supply and sanitation approaches. This is particularly so in agencies responsible for both urban and rural water supplies. The projects assessed demonstrate that creating a new and lean autonomous agency with a narrower rural focus can facilitate partnerships between local government and communities, and that this partnership empowers communities to successfully undertake small civil works and maintain them. o The limited availability of experienced NGOs capacity to facilitate community capacity-building can constrain adoption of the community-led approach for rural water and sanitation service delivery. Both projects had problems with finding experienced NGOs when they rapidly scaled-up and moved to more remote areas. o There is a role for public or private support agencies to provide much-needed expertise and technical support to trouble-shoot community-owned water schemes. Where this is missing, communities have difficulty in planning and managing major maintenance and budgeting for the schemes.
P055455 | Rajasthan Second District Primary Education Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/389461474502948272/text/000020051-20140619091255.txt | http://documents.worldbank.org/curated/en/389461474502948272/pdf/000020051-20140619091255.pdf | Expanding school access to the poorest of the poor is very challenging. It may require innovative interventions and much support from state and local supervisory agencies, such as NGOs and school management committees. Innovative means of access are needed, and implementing agencies may be cautious in setting targets for reaching such populations.- Enrollments are not enough, students must attend and obtain information in ways that their minds can process it in order to learn. Means should be sought to monitor and encourage the continued attendance of hard-to-reach students who enroll in schools. Projects increasingly concentrate expenditures at the village level, where audits are difficult to carry out. Monitoring of fiduciary processes should be based on careful review and understanding of how expenditures are incurred at the village and school level. Supervision missions could include fiduciary staff and innovative means of accounting practices that do not excessively burden beneficiaries.
P055456 | IN-TELECOMMUNICATIONS SECTOR REFORM TECHNICAL ASSISTANCE PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/583411474555700455/text/000020051-20140615113330.txt | http://documents.worldbank.org/curated/en/583411474555700455/pdf/000020051-20140615113330.pdf | Several lessons were identified by the ICR, some of which are presented here:When projects are complex and the experience in managing such projects is limited, it is essential to appoint a project management consultant early on, and to ensure there is appropriate buy-in for their recommendations. Additionally in telecommunications projects, it is better to proceed in a phased manner, and develop and test a prototype, before expansion to a fully scaled up system. When a project uses two subcontractors, it may be essential to establish a clear reporting structure, with one party reporting to the other, so that ultimate responsibility lies with one contractor. Requiring domestic production/manufacture of technical parts, may add to project complexity. In the telecommunications sector where technological advances are a key driver of change, it is necessary to build flexibility into the project. In this project, this has allowed for project realignment where necessary, and facilitated the redefinition of needs and reallocation of resources.
P055456 | IN-TELECOMMUNICATIONS SECTOR REFORM TECHNICAL ASSISTANCE PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2006 | 2009 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/232071468254358902/text/462880PPAR0P0510Box334099B01PUBLIC1.txt | http://documents.worldbank.org/curated/en/232071468254358902/pdf/462880PPAR0P0510Box334099B01PUBLIC1.pdf | 8. Lessons 8.1 A number o fimportant lessons canbe gleaned from the design andimplementationo f thisproject\. e Whenthe experience o fthe implementing agency inmanagingprojects is limited, and especially when such projects are complex, it is essential to appoint a project management consultant early-on to compensate for any gaps inexpertise. Most o fthe difficulties experienced inthe implementationo f the Telecom Sector ReformProject, involving the modernizationo fthe country's radio frequency and licensing system, were attributable to inability to take decisions and lack o f capacity to find solutions to problems; e Ina sector where technology advancement is akeydriver ofchange, itisnecessary to buildsufficient flexibility and foresight into the projects. Inthe IndiaTelecom Reform Project, flexibility allowed for project realignment duringimplementation, when required, thus facilitating a redefinition o fneeds. An example o f this was an unexpected need to gain an understanding o f televisionbroadcasting signal technology. However, with regardto the need for foresight, a better understanding o f 14Onmost missions the issues were raised at least at AdditionalSecretary level the relationship betweenrapid technological change andproject costs could have avoided a serious overestimate o f equipment costs, and this would have saved US$ 331,000 infront-end fees, while the Bank would havebetter utilizedpart o f its loan. Obsolescence also occurs more quickly inthe telecommunications field and so it i s critical to avoid delays inproject completion; e Investing incapacity buildingandinstitutional development is critical to ensuring effective project implementationandproject sustainability. This was a crucial aspect o f strengthening the regulatory anddispute settlement framework inIndia. However, itis equally important inensuring operational effectiveness, especially for equipment design, procurement and installation. Such investments need to be supported by clear leadership and a willingness to implement reforms at a senior level. Sometimes the prevailing organizational andbusiness culture can impede satisfactory progress due to competing priorities and agendas. When such a serious blockage i s encountered the issue shouldbe elevated to an appropriate level o f decision-making and, ifnecessary, pursued on a programmatic or multi agency basis.
P055459 | ELEMENTARY EDUCATION PROJECT | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2004 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/325091475068819628/text/000020051-20140619073924.txt | http://documents.worldbank.org/curated/en/325091475068819628/pdf/000020051-20140619073924.pdf | A well-managed centrally sponsored program can provide a powerful vehicle to mobilize ownership and commitment of stakeholders to a common mission. Flexibility to support differentiated needs is central to addressing the challenges in diverse local contexts.- Inputs, such as adequate physical facilities, free textbooks, and teacher training, are necessary for achieving quality education, but they need to be accompanied by sufficient attention to classroom processes. Improving instructional delivery and learning outcomes takes time, particularly when educators are unsure which methods to encourage. - A strong focus on equity in program design can help narrowing of gaps between those who receive services and those who do not, but the poorest and most marginalized populations are often very hard to reach. Special efforts are required to address access and equity concerns for the poorest, particularly in upper primary education, particularly in urban and state-aided schools.- SWAp financing and supervision can work well with a small number of donors (four in the case of this project) who are well coordinated. Data collection and analysis is crucial in monitoring progress of large projects on a regular basis.
P055461 | AR SOC&FISC NTL ID SYS | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/484481475084096500/text/000020051-20140615111028.txt | http://documents.worldbank.org/curated/en/484481475084096500/pdf/000020051-20140615111028.pdf | In many countries, there might be scope for improving service delivery by breaking the silo approach (ie not integrated across work groups) to database management. Sharing data across agencies is not easy or cheap, but the payoff may warrant the efforts.
P055467 | CAPE VERDE - PRIVATIZATION TA PROJECT | Western and Central Africa | Cabo Verde | Blend |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/950741474420182127/text/000020051-20140613054249.txt | http://documents.worldbank.org/curated/en/950741474420182127/pdf/000020051-20140613054249.pdf | While privatization is generally beneficial, the Bank should have a clear idea of the sources of benefits (e.g., better bill collection, smaller staff, easier access to capital).The decision to establish a multi-sector regulator should take into account the vested interests of line ministries.Selling shares of SOEs to public pension funds may not improve enterprise incentives. With the thin capital markets in the country, the public pension fund, INPS, purchased a significant proportion of the shares of the privatized enterprises (precise data are unavailable). The country's labor laws influenced the payments that some retrenched employees received, and thus became an element of the "gains from privatization." The project should also have addressed weaknesses in the country's labor laws.Regulation is technically complex, but the Bank should have focused more on technical aspects than on the organizational form of the regulatory agencies.
P055468 | CV-Education & Training Consolidation & Modernization | Western and Central Africa | Cabo Verde | Blend |  | Human Development | Education | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/603161474650834632/text/000020051-20140613044302.txt | http://documents.worldbank.org/curated/en/603161474650834632/pdf/000020051-20140613044302.pdf | Policy dialogue between the borrower and the Bank requires flexibility in dealing with evolving educational problems. The roles of task managers must be clear to borrower staff, particularly when countries have limited experience in dealing with the Bank.- Field testing of components that have been found effective in some countries is needed before they are established in others. This is particularly the case with small countries, where the numbers of staff are more limited and the consequences of failure may be more severe.- Carrying out large studies without a clear plan for dissemination or a government commitment to follow at least some of their recommendations may result in considerable expenditure without a measurable long-term benefit.
P055471 | TRADE REFORM AND COMPETITIVENESS | Western and Central Africa | Senegal | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2003 | 2004 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/703741475079624471/text/000020051-20140612073654.txt | http://documents.worldbank.org/curated/en/703741475079624471/pdf/000020051-20140612073654.pdf | Explicit and clear quantitative performance indicators (benchmark and outcome) are justified (and standard) in the case of trade and tax facilitation reforms and should be standardized in ex-post assessment. A monitoring system to achieve this needs to be established early on in the project. This should be complemented by systematic qualitative feedback from beneficiaries (e.g. private firms, tax payers and so on).To facilitate systematic assessment of project achievement, ICRs should take as a starting point the performance indicators matrix included in the PAF/President's Report.
P055472 | URBAN MOBILITY IMPROVEMENT PROJECT | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2009 | 2010 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/292751474513222426/text/000146597-20140619152845.txt | http://documents.worldbank.org/curated/en/292751474513222426/pdf/000146597-20140619152845.pdf | Improving urban mobility in rapidly growing urban centers in Sub-Saharan Africa may require the establishment of a special lead agency with an adequate budget to help local coordination the planning, investment and maintenance activities of multiple stakeholders, including central and local government and public and private operators.To review changes in urban mobility and point to how to achieve the effective responses needed, M&E requires performance indicators that are simple to measure and easy to interpret. The experience of this project points to the fact that innovative leasing schemes can be used to replace an aging and unsafe vehicle fleet used by informal transport operators.
P055472 | URBAN MOBILITY IMPROVEMENT PROJECT | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2009 | 2017 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/847101476984653723/text/108407-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/847101476984653723/pdf/108407-PPAR-PUBLIC.pdf | 7. Lessons The following lessons are derived from the project's implementation experience (until the 2008 closing date) as well as the 2016 assessment by the Independent Evaluation Group of the sustainability of outcomes. Thus, the lessons below all differ from those presented in the Implementation and Completion Results Report on the Urban Mobility Improvement Project (UMIP; World Bank 2009a). The establishment of an effective lead agency for urban transport planning and management requires strong and sustained support by the government and stakeholders. The assigned major roles and expectations of Conseil Executif des Transports Urbains de Dakar (Executive Council for Urban Transport in Dakar; CETUD) have not been matched by adequate financial and human resources or vested authority. In particular, it was not set up to oversee needed policy reforms. The government decided on CETUD's reorganization during its first year of implementing the complex UMIP, at a time when it had only three technical staff and no management. Moreover, despite requirements by the law that established CETUD in 1997, transport operators are not paying CETUD's fees and the government's funding is consistently inadequate, thus limiting CETUD's staff and capacity to deliver on its mandate. Land use and transport planning need to be coordinated at the metropolitan scale; spatial analysis needs to be mainstreamed into the design of urban transport projects. This lesson is especially important due to the peninsular form of Dakar. To be truly metropolitan in scope, project design needs to cover several jurisdictions. The rapid increase in the fleet of private vehicles was predictableâ€”given the lack of incentives to reduce growthâ€”and should have been incorporated in project design. Rigorous monitoring and evaluation of actual performance compared with urban mobility indicators is critical for prioritizing policy and regulatory actions. Monitoring and evaluation under UMIP and other World Bankâ€“financed transport projects has been weak. The collection and reporting of data on key performance indicators has been partial, and available data mostly focus on outputs rather than outcomes. Selected indicators are static; in UMIP, for example, the positive data on the replacement of old minibuses did not take into account the canceling effect of the rapid growth in overall vehicular traffic. Similarly, the air quality improvements attributable to the minibus replacement program are not known due to the lack of data on air quality trends for the greater Dakar area, taking into account vehicle inspection, gasoline replacement, and other parallel programs that affect air pollution. Innovative leasing mechanisms can be effective in replacing aging public transport fleets but their success depends on operator inputs at the design stage, technical assistance to professionalize operators and drivers, and restructuring of the network of informal transport operators. UMIP was successful in obtaining the commitment of informal minibus operators to join the bus replacement scheme, organize a mutual benefit association, set up a funding entity, and make regular payments. Strong and sustained technical assistance played a key role in developing new behaviors, such as timeliness, reliability, and fare stability, among operators. It was also critical to formalize bus operations and introduce franchise agreements. However, challenges that remain to be addressed include (i) the failure to guarantee exclusive rights to a specified route (which CETUD is unable to enforce); (ii) competition for bus stations, which undermines the franchise agreement; and (iii) continued rise in informal operators who do not follow the safety and operational standards of the new buses, thus compromising the latter's financial viability. Adequate road maintenance is a key underlying factor in the achievement and sustainability of targeted outcomes for improving urban transport mobility and efficiency. Most likely, the rapidly accumulating costs of road degradation due to lack of maintenance have already canceled out the (modest or negligible) outcomes of UMIP. The design of urban transport projects need to strongly factor continuous road maintenance in their results frameworks, indicators, components, and costs. These were inadequate in UMIP's design, although road construction and rehabilitation accounted for 56 percent of the costs of a project that had four other components. The lack of counterpart fundsâ€”stemming from the fierce competition for public resources, procedural delays, slow disbursement from the finance ministry, and the political and logistical difficulties of collecting road user feesâ€”has led to incomplete components at the time of project closing.
P055477 | Second Mining Development Technical Assistance Project | Latin America and Caribbean | Argentina | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 1998 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/304251474634196792/text/000020051-20140607165559.txt | http://documents.worldbank.org/curated/en/304251474634196792/pdf/000020051-20140607165559.pdf | Government commitment is essential to successful policy and institutional reform;Strong sector work ( the Argentina Mining Sector Review (1993), in this case) can greatly improve the quality of project preparation;Prior consultation, active participation and well-defined coordination between federal and provincial units are important for a project involving different tiers of governments;Sector development is better approached in an integrated manner, covering policy and regulatory reform together with institutional development and capacity-building; and In a weak macroeconomic environment, sustainability of institutional achievements is more likely for core administrative functions (e.g. administration of mining rights) than support services (e.g. mapping and informational systems). Therefore, it is preferable, wherever possible, to cluster important support services with core functions, so as to ensure that continuity of support services does not suffer.
P055480 | CL MUNIC DEVT II | Latin America and Caribbean | Chile | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/557681474497374511/text/000020051-20140613060441.txt | http://documents.worldbank.org/curated/en/557681474497374511/pdf/000020051-20140613060441.pdf | There are several lessons that can learned from this operation:Unlike the experience of many other countries, this project experience demonstrated that there is a strong interest for institutional strengthening at the local level, without having to offer 'rewards' such as infrastructure investments. (Is this because Chile's municipalities found themselves at the very early stages of decentralization, when compared with other countries). Municipal strengthening projects with solid programs of technical assistance are necessary for national decentralization strategies to succeed.Successful approaches to institutional development should be documented and disseminated through seminars and an easily accessible and regularly updated database. Easily accessible and transparent information systems on municipal performance, such as the SINIM, can help voters effectively monitor the performance of local governments and enhance accountability.Decentralization strategies through municipal development programs should regard municipal personnel as a highly valuable, yet untapped asset and resource for innovation.Field visits to municipalities by Bank missions are necessary for the effective supervision of municipal projects.
P055480 | CL MUNIC DEVT II | Latin America and Caribbean | Chile | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2005 | 2007 | PPAR | Less than 10 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/111501468236052217/text/401140CH.txt | http://documents.worldbank.org/curated/en/111501468236052217/pdf/401140CH.pdf | 8. Findings and Lessons 8.1 The findings o f this assessment endorse the following IEG lessons\. Whenever a multisector project singles out one particular sector for special attention, it needs to make the intended sectoral outcomes clear and monitorable, as well as ensuring that they are consistent with sector priorities. As for any operation, M&E o f a municipal development project should explore the use o f existing databases (SINIM in this case) to help identify measurable baselines, indicators, and targets whose achievement can be monitored easily and cheaply. The Bank should encourage borrowers and local agencies to develop and maintain customized databases o n sub national development that are in short supply in many countries. When in the public domain they also contribute to increased transparency, accountability and, through these, to democracy (in this case SINIM\. htto\.//www.sinim.cl/). The Bank needs to develop a clearer and more precisely formulated framework for improving local governance-a framework that can readily be translated into operational objectives.
P055481 | Chile: Higher Education Improvement Project | Latin America and Caribbean | Chile | IBRD |  | Human Development | Education | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/788811475076957794/text/000020051-20140613082930.txt | http://documents.worldbank.org/curated/en/788811475076957794/pdf/000020051-20140613082930.pdf | Monitoring and evaluation needs to be integrated into project preparation and implementation. Clarity is also needed on roles and responsibilities for collecting, analyzing, and utilizing performance data. - Allowing institutions to suggest and implement changes within a clear policy framework may enhance institutional autonomy while increasing accountability. - Combining quality assurance with targeted funding enhances the impact of interventions. Program and institutional accreditation allows institutions to identify weaknesses and appropriate remedies. Funding for quality improvement, in turn, provides the means by which corrective action can be taken. -The sustainability of competitive funding mechanisms in higher education is closely linked to financial management and procurement capacity at the study program level. Such capacities should be recognized as a priority within each institution and should be developed over time by university management.
P055482 | AR-Pub. Hlth. Surveillance & Disease Control Project (VIGIA) | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/468761475098895126/text/000146597-20140617121335.txt | http://documents.worldbank.org/curated/en/468761475098895126/pdf/000146597-20140617121335.pdf | The development of capacity to conduct disease surveillance and control is a critical component of efforts to strengthen public health functions and to improve the performance of the health sector in middle-income countries. Experience under this project has shown that disease surveillance and control can be instrumental in ensuring the successful mitigation of potentially grave and unanticipated health effects of social, economic and political crises.Sector structures and incentives are core elements for effective project implementation and sustainability. It is important to understand the federal structure of Argentina's health sector in order to support and facilitate capacity and dynamics both within and across the various levels of the system. The incorporation of this knowledge into project design and the identification of effective instruments to help align and secure proper participation by all relevant stakeholders are essential to project success.The incorporation of data and information into policy- and decision-making is critical in the public health field for ensuring the most strategic, highest-impact interventions. Not only does this require the availability of proper instruments and systems, it also demands a deeper change in the institutional culture of collecting and utilizing information. Achieving this cultural transformation requires time and consistency.
P055483 | Heads of Household Transition Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2006 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/382391474907871118/text/000020051-20140624184221.txt | http://documents.worldbank.org/curated/en/382391474907871118/pdf/000020051-20140624184221.pdf | In such large and complex social safety programs with links to workfare and training programs, there is need for greater focus on coordination between institutions and jurisdictions (public and private sector), and a need for greater transparency. Regular monitoring and evaluation of outcomes and impact is essential in order to ensure that such safety net programs are achieving their goals and objectives and the need for fine-tuning the systems.In designing a crisis response program, it is important to ensure plans to scale back benefits after the crisis, ensuring mechanisms to protect the most vulnerable, because otherwise countries face strong political pressure to maintain benefits.
P055490 | First Karnataka Economic Restructuring Loan/Credit | South Asia | India | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2001 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/244011475073142978/text/000020051-20140607154608.txt | http://documents.worldbank.org/curated/en/244011475073142978/pdf/000020051-20140607154608.pdf | Frequent monitoring of fiscal performance can be an effective tool in a project aimed at deficit reductionThe structural and institutional reforms facing many Indian states are so large that economic and political economy considerations require that they be introduced in a phased mannerA series of single-tranche adjustment operations, in the context of a medium-term reform framework, can be an effective instrument to support reform at the state levelMany reforms carry high short term costs and may produce benefits only in the longer term. If quick improvement can be shown in funding deferred maintenance, making available improved education and health services, and providing better governance, tangible gains may become evident that will increase the acceptability of reformIn the absence of sufficient metering of electricity and realistic prices, regulation of the supply of power supply is an important transitional measureMany reforms took longer than expected--especially those involving public enterprise reform and public sector financial reform. The Bank and the Borrower need to be realistic about the feasible pace of reform
P055495 | CHILD WELFARE REFORM | Europe and Central Asia | Romania | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/644661474510892116/text/000020051-20140612151816.txt | http://documents.worldbank.org/curated/en/644661474510892116/pdf/000020051-20140612151816.pdf | a) Community-based child welfare services can work: The sub-projects supported under the CWR project made a substantial impact on the thinking of what is feasible, which once having been proven to work, have formed the basis for subsequent scaling-up by both the EU and Governmentâ€™s own resources. Prior to the LIL, there was great skepticism as to whether the NGO activities undertaken could make any substantive contribution to dealing with institutionalized children on a large (national) scale rather than a purely local NGO scale.b) Child welfare services require addressing the whole needs of the family and form the basis in Romania for the development of modern social services: Prevention services and reintegration services need to deal with the whole issues of the family, and not just the specific issues of the particular child concerned if they are to be effective. The types of services developed under the CWR have thus formed the foundation for modern social services in Romania, almost completely lacking hitherto. c) A LIL can be an effective instrument for scaling-up local level initiatives: There have been questions in the Bank as to whether LILs are an effective instrument in scaling-up what were incipient positive instruments from a variety of NGO interventions over a number of years. The CWR was able to pick up on the best of these interventions, replicate and scale them up for a larger impact. The CWR sub-projects in turn became demonstration models for the much larger subsequent EU grant financing which continued and scaled up even further the impact of the Bankâ€™s CWR project.d) The Bank can be an important player in an area such as CWR: The Romania CWR project was the first Bank intervention in the field of CWR in ECA. Nobody had believed that the Bank had any real contribution to make in this area. The success of the CWR project demonstrates that when Bank management takes the bold step to embark in a new area, hires appropriate specialized staff, and combines this with the inherent managerial and economic management experience of the Bank, positive results and real value-added will ensue. This success includes the role of the Bank in leveraging impact with a variety of donor parties. The success of the CWR project was in large part due to the collaborative arrangements between the parties concerned. e) Lending buys a seat at the table for policy dialogue: The Bank was able to be continuously involved in issues of CWR in the High-level Policy Group, the CWR Executive Committee and make worthwhile contributions to the CWR over the life of the project going far beyond the initial project objectives as the CWR project bought the Bank a seat at the policy table.f) High profile political focus can magnify action: When the Bank first engaged in CWR in Romania, there was international media attention on the plight of institutionalized children, which gave an initial external impetus to the reforms. However, from 2000 onwards, the whole CWR received a major political boost as a result of the EU making dealing with the problem of institutionalized children Romaniaâ€™s main criterion requirement for EU entry.g) Competitive grant-making approach provides incentives for the local level to implement national policy: The CWR project embodied a social fund approach of competitive grant making, rather than choosing particular Judets based on need or political lobbying. This procedure provided incentives to bring the Judets into line with national policy.
P055571 | El Nino Emergency Recovery Project | Latin America and Caribbean | Ecuador | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/851111474566766794/text/000020051-20140604051643.txt | http://documents.worldbank.org/curated/en/851111474566766794/pdf/000020051-20140604051643.pdf | The design of an Emergency Recovery Loan (ERL) must be adjusted to local conditions. Where there is weak centralized implementation capacity, a demand-driven approach with local implementation may be more appropriate.To be effective, an ERL project needs political support at the highest level.Public participation at the local level can be a very effective tool to reduce corruption.
P055573 | CULTURAL HERITAGE | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/805861474893279089/text/000020051-20140612134539.txt | http://documents.worldbank.org/curated/en/805861474893279089/pdf/000020051-20140612134539.pdf | Money spent on the Neighborhood Fund â€œrequired substantial resources for administration and consultation that might have been better spent on renovating public streets, urban spaces, and historic buildingsâ€ (ICR 9). Similarly, the Borrower ICR notes, â€œSmall sums dispersed on many small problems do not solve essential problems." While the LIL is a fast track, "learn as you go" type of instrument, the short, quickly designed 3 year project, turned into a long, quickly designed, and much revised, 5Â½ year project. If more time had been taken to clarify some of the issues discussed in section 5 of this ICR Review, some expense and delay might have been avoided. The Borrower ICR points out: â€œIn the future it would be better to allocate more time and funds for the preparation period to avoid having to make changes in the initial programâ€ (ICR 44).One of the main objectives of this LIL was to test approaches to revive the tourism industry. Such an endeavor should logically be followed up by the funding and implementation of a larger scale project using those approaches that were most successful.
P055585 | State Revenue Service Project | Europe and Central Asia | Latvia |  |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/610981475100698148/text/000020051-20140613041515.txt | http://documents.worldbank.org/curated/en/610981475100698148/pdf/000020051-20140613041515.pdf | Key to project success was combining the technical upgrades with:--a fundamental reorganization of SRS and Customs' organizational schemes and work procedures--extensive training for all staff involvedTesting the new procedures and organization at two pilot sites contributed to project success, especially regarding institutional aspectsThe prospect of EU membership was a strong motivation toward achievement in a project whose completion would facilitate eventual membership.Projects that seek to introduce fundamental changes in institutions require greater supervision resources than other types of projects. Changing organizational behavior requires a long, iterative dialogue that is demanding in terms of the size and skill mix of the project team.
P055684 | Higher Education Technical Training Project | Western and Central Africa | Cameroon | Blend |  | Human Development | Education | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/151731474509353209/text/000020051-20140612091544.txt | http://documents.worldbank.org/curated/en/151731474509353209/pdf/000020051-20140612091544.pdf | The ICR identified 3 important lessons of broad applicability, namely: 1) It is possible to involve industry in university-level technical training programs in ways that benefit both industry and graduates: industries get more appropriately trained new technicians and part-time/inservice training opportunities for current workers; students get more on the job (real world) training and connections leading to employment; 2) Granting autonomy to institutions for use of funds they collect from students and clients is a potentially powerful reform, although this point was not fully tested at IUT Douala due to lack of de jure authority; 3) Finally, paradigm shifts (adopting new models) benefit from major policy reform at the highest (national) level. The evaluation summary (ES) also noted, on the less positive side: 1) the importance of making sure that signed covenants and other conditions are in place before moving ahead with full implementation; 2) that successful adoption of a new paradigm takes more than acceptance of innovative concepts: it requires changes in the way institutions work, including their use of and accountability for funds, their management of data and personnel, and their capacity to conduct monitoring and evaluation. Without attention to such details (and attention to them in LIL performance indicators), it is difficult to see how a model that is accepted in principle can actually be brought to scale.
P055738 | Sevastopol Heat Supply Improvement Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2006 | 2005 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/218071474854530314/text/000020051-20140612135939.txt | http://documents.worldbank.org/curated/en/218071474854530314/pdf/000020051-20140612135939.pdf | The project experience suggests that when working directly with the municipal governments on the development of infrastructure investment projects, the Bank faces a number of difficulties. The problems may relate to issues, such as intergovernmental transfers between the local and central authorities, which may not even be related to the project. The Bank, therefore, needs to explore less risky approaches for supporting improvement of essential municipal services. The Municipal Credit Market Development Project', which is currently under preparation, is helping to develop a legal and regulatory framework for subnational borrowing.
P055739 | KIEV PB ENERGY EFFIC | Europe and Central Asia | Ukraine | IBRD |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/683051474553506194/text/000020051-20140613082147.txt | http://documents.worldbank.org/curated/en/683051474553506194/pdf/000020051-20140613082147.pdf | Strong project ownership by the Borrower and commitment to results, along with highly qualified management and staff, can be critical success factors for a project as they can help keep a project on track in the face of various obstacles. Simplifying a project's design to minimize the risks can improve the chances for a successful outcome, especially in Borrower countries where the preparation and implementation of projects has been problematic.Flexibility and adaptation on the part of the Bank and Borrower to changes in the project environment can help overcome impediments, improve implementation arrangements and achieve project objectives in more effective ways.
P055755 | BANKING REFORM ASST. | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2001 | 2002 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/692231474491816312/text/000020051-20140604054917.txt | http://documents.worldbank.org/curated/en/692231474491816312/pdf/000020051-20140604054917.pdf | 1. Provision of complex crisis related technical assistance is difficult within the framework of policies and procedures that were originally created for large investment operations. In a crisis, flexibility in design and rapid and timely delivery are essential and may require a different set of policies and procedures. The interpretation of Bank rules on areas related to the level of fees, conflict of interest, confidentiality and downstream work lengthened the procurement process and delayed the timely provision of assistance. 2. The Special Financial Operations unit created to respond to the crisis contributed to the speed and quality of restructuring efforts, but this type of operation has not proven sustainable within the Bank's organizational structure.
P055755 | BANKING REFORM ASST. | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1998 | 2001 | 2004 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/917171468752402166/text/271770ID.txt | http://documents.worldbank.org/curated/en/917171468752402166/pdf/271770ID.pdf | 5. Lessons 0 Inacountry with deeplyrootedandwidespread govemance issues, wherethe authorities are not committed to deep reforms, the Bank needs to have realistic expectations about the outcome o f its interventions. InIndonesia, the ability to affect fundamental reforms with adjustment and technical assistance support has beenlimited. The effort requires a more comprehensive and long-term approach, including diagnostic work and involvement o f civil society. 0 The dilemma o f supporting a country incrisis i s highlightedby PRSL Iand, more especially, by PRSL II. The Bank needs to provide the Boardwith a frank rationale for its intervention, even where the rationale i s limitedto providing special shorterterm liquidity support for modest reforms. 0 The experience inIndonesiahighlightsthe importance of avoiding delays in banking crisis\. unless resolved quickly and decisively, the fiscal costs mount and vestedinterests further impederesolution. 0 Inamajor crisis, Bankmanagement andtop technical specialists should give priority to resolving issues that arise inthe context o f Bank assistance addressing the crisis, evenifthe vehicle for the assistance is inthe form ofa relatively modest technical assistance loan. 0 Coordination among donor agencies i s essential incountries incrisis and needs to bemade explicit. InIndonesia, coordinationwas successful only after an initial period of uncertainty, mainly becausethe IMFwas able to take the lead. 0 The Bank's'consultant fee structure and procurement rules caused delays and impededa rapid responseto Indonesia's bankingcrisis, and excludedor discouraged the few service providers with appropriate technical expertise. These rules should be reviewedwith a view to allowing exceptions to policy under certain well-definedcircumstances. 0 The Bank's central unit enabled the Bank to respond to Indonesia's needfor technical expertise, butthe unitwas not well integrated into the Bank's organization and was unfamiliar with its operational procedures, causing bureaucratic and practical problems. For future crisis response, the Bank should consider establishing a virtual crisis unit o f specialists working inthe Regions, available to respond to a specific crisis inside the relevant regional management
P055814 | TN-EXPORT DEVELOPMENT | Middle East and North Africa | Tunisia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2005 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/209911474664694967/text/000020051-20140613044936.txt | http://documents.worldbank.org/curated/en/209911474664694967/pdf/000020051-20140613044936.pdf | The project shows that a robust set of performance indicators that is adhered to provides a firm basis for assessing project achievement.Improvements in trade clearing can result when administrative/political commitment is combined with advances in information/communication technology and adoption of internationally recognized trade standards and codes.
P055815 | Third Economic Competitiveness Adjustment Loan | Middle East and North Africa | Tunisia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2002 | 2004 | 2005 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/231191468760755829/text/31017.txt | http://documents.worldbank.org/curated/en/231191468760755829/pdf/31017.pdf | Lessons Learned 4.6 The main lesson are\. e Tunisia's successful economic performance hasbeendue to three attributes\. ownership andbroadpolitical consensus, awell-developed humanresource . base, and a stable macroeconomic environment. e Experience inprivatization andthe financial sector shows the need for the Bankandthe development partnersto staythe course andshow flexibility intheir support, providedthere is evidenceofgenuine andsustainedreform efforts. For example, by acceptingpartialreforms insome areas, and l2 The prior authorizations of investment are numerous and ihbit startups. Inefficient operations and the lack of competition and the dockers' monopoly are amongst the issues cited inthe Bank's 2000 Private Sector Assessment Update. Since then, under E C A L 111, 60 percent o f all prior authorization for start-ups were removed. Customs documentation has been simplifiedbut the ports still constitute a major bottleneck, leading to hghcosts and delays. Goods untilrecently spent up to 18 days instorage inport because traders usedit as a substitute for inland storage. Recent reforms are reportedto have greatly reduced clearance times for goods to 4 days. buildingonpartial successesto deepenthem insubsequent operations, the support fkom the Bank andother partners was ultimately effective. Patience, perseverance and flexibility paidoff. a An important lessonfor other small emerging countries seekingto laythe foundations for sustainable growth andpoverty reduction i s the success o f Tunisia increating a competitive economy by the coordinated use o fmacro andstructuralpolicies andreforms.
P055821 | URBAN POVERTY PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/117771475074997064/text/000020051-20140613064720.txt | http://documents.worldbank.org/curated/en/117771475074997064/pdf/000020051-20140613064720.pdf | The project provides many lessons, including the following:Given the importance of leadership in community driven projects, identifying appropriate mechanisms and methods for selecting community leaders becomes critical. In UPP, community members identify and articulate core values they appreciate in a leader before electing community leaders through a secret ballot. This method has increased awareness and expectations, and the results have been effective overall.An open-menu system for community based infrastructure projects allows sub projects to be better representation of community identified needs. In this project, the community needs identified differed greatly from community to community, but the open-menu approach together with a negative list (limited to activities such as acquisition of weapons, harmful drugs, land, religious buildings and bank deposits), was able to respond to these community needs without being unduly prescriptive.Instead of formal evaluation after completion of each project phase, a culture of continual learning, self-evaluation and improvement is more appropriate for community driven projects. Information collected through regular audits and impact assessments have fed into the implementation process and the project showed that it is possible to practice such an implementation strategy on a large scale.Micro-credit is not an effective way to reach the poorest of the poor. Community groups have incentives to preserve their capital so they tend to be risk averse, and thus tend to lend money to existing small businesses, which are generally not run by the poorest people. The poorest also tend not to apply for micro-credit. The project was more effective in reaching the poorest of the poor when more funds were allocated by the communities for infrastructure and social programs.
P055823 | SECOND RURAL MUNICIPAL DEVELOPMENT PROJECT | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/707331474851941474/text/000020051-20140619085802.txt | http://documents.worldbank.org/curated/en/707331474851941474/pdf/000020051-20140619085802.pdf | If an organization as project implementation agency does not have basic institutional capacity and commitment at the outset, it can prove very difficult to build its capacity further. This suggests that alternative implementation arrangements need to be considered in such circumstances. Project investment can bolster policy reform when it responds to incentives of the reform itself and applies long standing technical assistance and training programs designed to provide the expertise that municipalities need to handle the new requirements of the reform.An "add-on" component, such as environmental management in this case, can be successfully incorporated into a multi-sectoral project when it is clear that the new component contributes to achieving that project's objectives, in addition to any sector-specific goal it might also serve. Municipal Associations can play an important role in the success of municipal development projects when they provide continuity in supporting key project aims at times of turnover of municipal leaders and staff.
P055844 | Public Policy Reform Technical Assistance Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2002 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/536201474570863550/text/000020051-20140624191447.txt | http://documents.worldbank.org/curated/en/536201474570863550/pdf/000020051-20140624191447.pdf | The ICR draws a number of lessons for project design (i.e., align project and political cycles, align design with implementation capacity, clear governance arrangements, careful planning and sound M&E, a good results framework) and supervision with which IEG agrees. In this instance, IEG would underscore the importance of aligning project and political cycles. This has several implications. Foremost, it implies adopting a well-defined relatively inflexible medium-term time horizon for a project (in the case of Panama, five years), focusing on the then government's highest, core, priorities, and adopting objectives and targets that are realistic given implementation capacity, and allowing reasonable time for procurement of inputs, production of outputs, and realization of results. It must be recognized however that institutional development is time consuming, and that substantive, significant changes can be achieved only over a period of time that is longer than the political cycle. This implies a high risk of non-sustainability. This risk can be limited, but not eliminated, by choosing objectives for which there is a broad political consensus. Another lesson deriving from experience under this project is the importance of realistic supervision reporting.
P055853 | Nicaragua - Telecommunication Reform | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/578661474903662663/text/000020051-20140617131852.txt | http://documents.worldbank.org/curated/en/578661474903662663/pdf/000020051-20140617131852.pdf | Government commitment is essential for the successful privatization of telecommunication services.A prior analysis of the cost of rural access requirements is appropriate in a telecommunications project designed for rural inhabitants.Frequent changes in managerial leadership and weak implementing agency capacity inhibit timely progress.
P055935 | EL NINO EMERGENCY FLOOD PROJECT | Latin America and Caribbean | Argentina | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1998 | 2005 | 2006 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/238541474420257112/text/000020051-20140613064811.txt | http://documents.worldbank.org/curated/en/238541474420257112/pdf/000020051-20140613064811.pdf | To ensure rapid response in an emergency it may be advisable to establish a dedicated coordinating unit rather than trying to work through local governments, which may be unfamiliar with Bank procedures and may lack the capacity to develop and supervise large and complex works. In projects where counterpart funding is sought from provincial governments it is important to assess, at the preparation stage, the legal and procedural restrictions that may, first, reduce the capacity of these governments to take on new debt and, second, lengthen the time needed for subsidiary loan agreements to be signed. If the definition of which provinces will participate is left open ended, and if project funds are made available to provinces on a first come, first served basis, the efficiency with which funds are targeted and the speed of disbursement may be greatly enhanced.
P055944 | Third Education and Training Project | South Asia | Maldives | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/660941474506115638/text/000020051-20140618075929.txt | http://documents.worldbank.org/curated/en/660941474506115638/pdf/000020051-20140618075929.pdf | The ICR suggests the following lessons:Small countries often have limited personnel to carry out key tasks. They can be successfully implemented when there is a strong stakeholder commitment to reform along with political and administrative commitment to set high-quality standards, monitor progress, and to make changes as needed;The Bank has the potential of making a particularly strong impact in small states. A series of projects with committed governments may successfully reform entire sectors; and The delivery of education to the populations of small islands may involve inherent inefficiencies that cannot be remedied. Student-teacher ratios will often be small when students are educated on their home islands, teacher wages may need to be adjusted accordingly, inservice training may be harder to deliver, and the educational quality may continue to lag behind larger urban centers.
P055954 | BR GOIAS STATE HIGHWAY MANAGEMENT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2007 | 2007 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/107671474487753342/text/000020051-20140615114011.txt | http://documents.worldbank.org/curated/en/107671474487753342/pdf/000020051-20140615114011.pdf | For institutional reforms to succeed, a broad consensus among major stakeholders for the reforms needs to exist. Also important is the government commitment to take the risky steps and realistic targets to monitor the progress of the reforms.An Adaptable Program Loan may be a superior option compared to investment lending, where complex sector reform to strengthen sector institutions is needed, but where there is uncertainty about the rate of progress in implementing such reforms.A framework of positive incentives for both the State and municipalities need to be developed for successful decentralization of municipal road maintenance.
P055954 | BR GOIAS STATE HIGHWAY MANAGEMENT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2007 | 2009 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/801561468226200270/text/490880PPAR0BRA162B01PUBLIC071221091.txt | http://documents.worldbank.org/curated/en/801561468226200270/pdf/490880PPAR0BRA162B01PUBLIC071221091.pdf | 7. Lessons 7.1 The ICR contains useful guidance on the importance o f satisfactory fiscal conditions to ensure successful project implementation, the needto create positive incentives ifdecentralization o f municipal road maintenance i s to succeed, andbetter understandingofthe factors that facilitate successful implementationo fAPL projects. The PPAR provides the following lessons\. Whenroad maintenance is decentralized to municipalities, special consideration needs to be given tofiscal sustainability. The Goias experience with the creation o f an inter-municipal road consortium to provide roadmaintenanceto interested municipalities shows that while such an arrangement i s technically and institutionally feasible, the weak financial condition o f municipalities can be a major hindrance to a sustainable arrangement. Outsourcing routine maintenance underperformance-based contracts ispractical and the PPAR shows it can lead to lower costs of maintenance. The model contracts to outsource routine maintenance adopted inmany Latin American Countries typically include a road section requiring rehabilitation-an expensive activityas a way to attract private contractors. The Goias experience i s important, however, since it shows that it i s possible to outsource routine maintenance only, that small private contractors are interested inbiddingfor such low-cost contracts, andthat such contracts can lower the cost o f maintenance compared to that done by the road agency personnel. Designingproject activities outside the direct area of interest and expertise of the implementing agency, such as strengthening environmental management through roadprojects, can beproblematic, particularly when they are not effectively included in a development objective and supervised accordingly. The Goias project includedunder the environment component several activities involving the incorporationof natural habitats on a prioritized basis within a science-based system of protected areas. Such activities, were outside the area o f expertise o fthe implementing agency (theroad agency AGETOP), and would require a broader partnership for implementingthe project, including natural resource and environmental protectionagencies, as well as more involvement and participation by universities, environmentalNGOs and community-basedorganizations incivil society. When such components are added, they should be clearly matched to a project objective and their achievement carefully monitored.
P055974 | BO EL NINO EMERGENCY | Latin America and Caribbean | Bolivia | IBRD |  | Infrastructure | Transport | IDA | IPF | 1998 | 2001 | 2002 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/937011475089222234/text/000020051-20140604044217.txt | http://documents.worldbank.org/curated/en/937011475089222234/pdf/000020051-20140604044217.pdf | Clear policy and a budget needed to sustain project progress. To sustain project progress in institutional capacity building in the coordination of prevention and rehabilitation works (gained at the Bolivian taxpayers expense), clear public policy for structuring and financing disaster management must be made and a budget needs to be allocated. The Government lacks this and as a result, the progress (and the investment) made will most likely be lost. Likewise, the continued existence of the national network of disaster prevention and mitigation (set up using $250,000 of project funds) is unlikely.Clearly analyze the situation to try to avoid circumstances that lead to delays that can cost the project its success. Little was done beyond the establishment of the UTOAF. Problems resulted because disaster funds were not included in the budget for that year, a management firm was not hired as agreed, and the Ministry of finance was slow in approving budgets. The delays were critical given the rapid response required.
P055988 | Wholesale Markets 2 Project | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2003 | 2001 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/102161474849633915/text/000020051-20140602104120.txt | http://documents.worldbank.org/curated/en/102161474849633915/pdf/000020051-20140602104120.pdf | (i) In projects like this where timeliness is of the essence, the bank needs to show the resolve to cancel projects when preparation delays undermine the relevance of the operation; (ii) Wholesale marketplaces combine the features of public and private goods and therefore it is not reasonable to expect private firms to be solely responsible for covering the investment cost; (iii) For projects like this, loan agreements should contain commitments by local authorities to close older wholesale marketplaces once the new facilities are ready for operation; (iv) In rapidly-developing economies, such as Poland in the 1990s, current conditions may not be a reliable guide to future developments: market niches may disappear very quickly.
P055989 | ECON.REFORM SUPP. OP | Western and Central Africa | Ghana | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1998 | 1999 | 1999 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/630541474904221010/text/000020051-20140522101739.txt | http://documents.worldbank.org/curated/en/630541474904221010/pdf/000020051-20140522101739.pdf | The Bank should move quickly to support government reform initiatives, especially in restarting adjustment programs, provided it is convinced of real ownership. However, Institutional Development needs to be carefully formulated and related measures should not be generally inclusion as components of adjustment lending.
P055991 | Land Administration Program | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2004 | 2010 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/274121475080351721/text/000020051-20140624190532.txt | http://documents.worldbank.org/curated/en/274121475080351721/pdf/000020051-20140624190532.pdf | The ICR identified a number of lessons from the project experience that are adapted below:Adding regularization functions into a single cadaster-registry agency may decrease its efficacy and efficiency. The project experience showed that land regularization programs are politically sensitive and subject to policy changes. Institutions charged with guarding cadastral and registry information need a certain degree of autonomy to protect property rights from political interference. Regularization programs also demand additional resources, which can come at the detriment of cadastral and registry functions if they are financed from the same general budget.When legal reforms are supported it is important to acknowledge the Bankâ€™s limitations in influencing the legal process and recognize inherent risks associated with the negotiation process that makes the final outcome difficult to foresee. Project design should anticipate changes to the legal framework and address questions about how to deal with potentially adverse changes. In this case there was a need for greater engagement with communities who felt threatened by some aspects of the new legislation, resulting in an inspection panel investigation. Broad community support for a project can be jeopardized by insufficient attention to the representativeness and legitimacy of consultation mechanisms.The sustainability of investments in cadastre and registry modernization depends upon adequate attention to developing municipalities into active and capable partners in the implementation of cadastral system.
P055992 | EMERGENCY ASST. LOAN | East Asia and Pacific | Korea, Republic of |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1998 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/617961474908717788/text/000020051-20140522080407.txt | http://documents.worldbank.org/curated/en/617961474908717788/pdf/000020051-20140522080407.pdf | There are three major lessons:1. The Bank should maintain access to high level expertise to deal with systemic financial corporate distress. Putting a capable team together in the case of Korea on very short notice was successful but difficult.2. It is easier to negotiate important policy reforms during periods of crisis, and this opportunity should be taken advantage of, within the time constraints available. As the Korean crisis eased, the resistance to further needed reforms by powerful vested interest groups again intensified.3. The Bank may want to deliberate further on its role as a development institution versus its role as a provider of emergency liquidity (and giving its seal of approval to a program to help restore confidence). It is possible to give expert advice while leaving the provision of funds to others.
P056018 | LAND ADMINISTRATION | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2013 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/895351467986261523/text/ICRR14639-P056018-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/895351467986261523/pdf/ICRR14639-P056018-Box393183B-PUBLIC.pdf | The following well-considered lessons are cited in the ICR:The sustainability of outcomes of land administration interventions requires building broad social and political commitment, as well as maintaining and mainstreaming key competencies across electoral cycles.The challenge of recognizing the complexity of indigenous peopleâ€™s land rights requires attention to historical and social particularities and intensive social supervision.A strong focus on local governments is critical to the sustainability of investments in cadastre and registry modernization.Alternative conflict resolution mechanisms can effectively facilitate cadastral and regularization processes.In addition, IEG proposes as a lesson that impact evaluations, like that sponsored by this project (see Section 6 above), can usefully help to establish whether changes in economic growth and poverty levels may be attributed to land administration projects.
P056074 | MUNICIPAL INNOVATIONS PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/800531474509420350/text/000020051-20140612102532.txt | http://documents.worldbank.org/curated/en/800531474509420350/pdf/000020051-20140612102532.pdf | Creating an enabling environment and some degrees of freedom are pre-conditions for inducing and empowering local institutions and officials to initiate and carry out innovations.An operational environment that is conducive to innovation is one that has flexible procedures that allow for unexpected approaches and changes called for by innovations.The personal commitment by high-level political leaders--such as ministers and city mayors--to innovation and their acceptance of the risks involved in it are crucial to successful innovation. Sustainability of innovative projects depends in part upon adequate consultation of project beneficiaries during subproject preparation and implementation. Innovations are more likely to succeed if they require organizational changes in one agency only, or in one unit only within an organizational. An innovation that depends upon the complete reform of the agency or organization is less likely to prosper.
P056074 | MUNICIPAL INNOVATIONS PROJECT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2003 | 2006 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/794301468283544395/text/35624.txt | http://documents.worldbank.org/curated/en/794301468283544395/pdf/35624.pdf | 5. Lessons Learned Localgovernments in Indonesia should continue to build upon their demonstrated capacity to successfully implement improvements in infrastructure delivery, which has also been supportedby a long line of Bankprojects. However, local governments could be more responsivestill to urban development needs expressed through local communityparticipation. Communityparticipation inurban investment planningis often viewed only a formality and investments plans are often only an expression o f technical priorities which are identified by local officials themselves. Local governments needto engage more effectively incommunity consultation to ensure that urban investment plans also reflect expressed community priorities. A cross-sectoralframework such as Integrated UrbanInfrastructure , Development Program, can work wellfor local governmentsprovided the investment resources within it are sufficiently concentrated to adequately address needs in all included sectors. When resources are spread too thinly over a large area interms o fneed, itcanunderminethe expectedbenefits ofintegratedplanningresultinginincremental, rather than substantial, improvements inurban infrastructure. e All stakeholders, including local governments themselves,need to agree and understand clearly thepurpose behind local innovations-be it to increase efficiency, to increase client-responsiveness-rather than treat innovation as a benefitper se. Local governments inIndonesia are both interested and capable o f introducing innovative service delivery improvements, but while new approaches to municipal service delivery should be encouraged, new may not necessarily mean better. Local government should always articulate andmonitor the expected benefits from the innovation. As recognized inthe 2003 CAS, theBank has experienceand a rich knowledge basefrom many years of investing in local services through government (and more recently local government) drivenprojects. Ensuringthat local governments are always included as partners, with continuous emphasis upon improvingtheir performance, should be a mainstay o f all Bank assistanceto local service provision. Monitoring and Evaluation (M&E) systems need to be designedand implemented to track outcomes related toproject objectives, as well as the inputs and outputs of project activitiesthat will help achieve these outcomes.All three projects assessed inthis report focusedmainlyon successful implementationandinsufficientefforts were made to monitor the achievement of expectedbenefits -andpoor outcomes were not always identifiedintime. M&Ei s particularly important ingeographically spread-out projects and tracking meaningful indicators (which have a plausible link to project objectives and activities) can make up for the lack o f frequent supervision missions to participatingtowns.
P056087 | Pension and Financial Market Reform Technical Assistance Credit | Latin America and Caribbean | Nicaragua | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/726231474904251811/text/000020051-20140613085300.txt | http://documents.worldbank.org/curated/en/726231474904251811/pdf/000020051-20140613085300.pdf | 1. Projects to support pension reform should be based on a very careful assessment of the fiscal impact of reform proposals before any policy discussions take place. 2. It is extremely important to garner broad-based popular and political support for reforms. Therefore, serious consultations should be pursued, and broad-based consultations mechanisms supported with technical work, before particular proposals are supported.
P056192 | Local Development Pilot Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/547341475085310076/text/000020051-20140613081541.txt | http://documents.worldbank.org/curated/en/547341475085310076/pdf/000020051-20140613081541.pdf | A municipal credit market can be established with customized training of both municipal authority staff and commercial bank personnel, within an appropriate legislative framework for municipal finance. However, a prerequisite is a thorough understanding of lenders' concerns.The market will not mature if there is a competing supply of subsidized non-market funds which needs to be addressed at the policy level and communicated to the potential loan recipients.
P056199 | Third Inland Waterways | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/474141474904455725/text/000020051-20140619082023.txt | http://documents.worldbank.org/curated/en/474141474904455725/pdf/000020051-20140619082023.pdf | 1. Challenge of achieving greater cost recovery - As in the previous inland waterway projects, cost recovery mechanisms in place for IWT are rarely sufficient to cover all costs because a stable tariff market does not (yet) exist between transport modes. Government subsidies for IWT infrastructure may be unavoidable during the transitional phase. Nevertheless, inland waterway systems are energy efficient, have a small environmental footprint, and low economic costs. As the benefit-cost analysis shows the Chinese policy to subsidize the capital costs of IWT infrastructure appears appropriate. As a corollary, an IEG study on the different perspectives provided by a benefit-cost analysis and a financial analysis would be desirable.2. In an era of uncertainty price escalation clauses are always necessary and the rule of "lowest evaluated bidder" needs to be applied judiciously. In China, contracts for the supply of equipment rarely included price escalation clauses for simplicity and ease of contract management. Unexpected increases in the cost of materials after contract award disabled contractors and suppliers in fixed price contracts to deliver the services as contracted. To avoid nonperformance or revisions for price adjustment, it is preferable that (even short) contracts have a price adjustment formula. This problem is compounded when the Bank rule for awarding contracts to the lowest qualified bidder is mandated in countries, which do not yet have a robust regulatory contracting framework nor commensurate contracting industry. In this project the Bankâ€™s procurement procedures led to awarding low price contracts to marginal bidders which resulted in change orders. 3. For cost control and timely implementation procurement and safeguards personnel need engineering experience. Bankâ€™s review of contract variations took very long. This resulted in substantial costs to the Borrower. Also the RAP costs nearly tripled from the appraisal costs. These problems can only partly be mitigated by having Bank procurement and safeguard specialists participation in the missions; country-based Bank procurement reviews would be more effective. In addition, personal experience and understanding of engineering works is necessary. Contracts with a price adjustment formula would speed up the required reviews.
P056200 | Transport Development Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/635411474630480875/text/000020051-20140619083951.txt | http://documents.worldbank.org/curated/en/635411474630480875/pdf/000020051-20140619083951.pdf | The ICR identified following lessons:The M&E system should take into account the data collection needs when defining outcome/output indicators. In countries where institutional capacity is weak or there are budget constraints, indicators requiring sophisticated data collection and processing are often difficult to measure.More rigorous project preparation in terms of planning and procurement is necessary in countries with short construction seasons since countries with long and harsh winter conditions such as Mongolia only have a few months when conditions allow for carrying out road improvement works. Use of trials and pilots of alternative road surface designs are helpful in assisting with the selection of proper technologies especially in countries where road engineering standards are relatively old/inadequate.IEG adds the following lesson: the Bank needs to take the necessary steps to ensure that the studies (such as the road safety study) aimed at strengthening borrower capacity are carried out in a timely manner.
P056213 | A Trade and Transport Facilitation Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/729331474509888195/text/000020051-20140615114851.txt | http://documents.worldbank.org/curated/en/729331474509888195/pdf/000020051-20140615114851.pdf | In a multi-agency framework, the introduction of trade facilitation measures requires continuous high level of commitment across various public and private sector stakeholders. It is also important to first develop up-front consensus among the various stakeholders and take into account the obstacles that could disrupt the project benefits during implementation.To accommodate emerging issues in a changing environment, a formal restructuring of projects under implementation is an effective mechanism for portfolio management.Better linking and sequencing of technical assistance with associated investments in physical infrastructure or services could substantially improve implementation success.Lessons learnt from other trade and transit facilitation projects would have been helpful in implementing the mitigation measures to ensure cross-agency cooperation.
P056216 | Second Loess Plateau Watershed Rehabilitation Project | East Asia and Pacific | China | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=100 million | Satisfactory |  | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/337181474588581444/text/000020051-20140614184428.txt | http://documents.worldbank.org/curated/en/337181474588581444/pdf/000020051-20140614184428.pdf | Projects that replicate successful models in a flexible manner can be highly successful at relatively low risk. Key elements of success require active Bank engagement over the long term and consistent promotion of sustainable land policy and management practices.The focus of project design on development objectives facilitates outcome-oriented project implementation. The project implementers were facing many attempts to address additional development challenges in project areas, such as marketing, farmersâ€™ organizations, agricultural extension services, and targeted poverty programs. Without neglecting the importance of these issues, the continuous discussions of the dual project objectives of increasing income and improving the environment kept the focus on how to achieve these most effectively, given the institutional and other constraints.Building a strong Bank-Borrower partnership needs consistency in task management and in the composition of the task team. The mutual trust and shared responsibility in the implementation and supervision of the project was possible through the maintenance of a consistent task team throughout the implementation of the project. The fact that the project was task-managed from the field office facilitated Bank-Borrower cooperation and partnership.
P056216 | Second Loess Plateau Watershed Rehabilitation Project | East Asia and Pacific | China | IBRD |  | Sustainable Development | Water | IBRD | IPF | 1999 | 2005 | 2008 | PPAR | >=100 million | Satisfactory |  | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/812911468218977436/text/41122.txt | http://documents.worldbank.org/curated/en/812911468218977436/pdf/41122.pdf | CONCLUSIONS AND LESSONS 3.42 Duringthe Xiaolangdi andTarimBasinProjectsthe Bankwas able to work with national-level organizations o f water policy issues giventhe cross-cutting nature o fthese enterprises. For the first and only time the Bank was inthe privilegedposition o f assisting MWR with the integrated planning ofthe Yellow RiverandTarimRiverBasins. This was importantbecausethe incremental impact o fthe projects the Bank supported on water resourcesmanagement could be modeledat the river basin scale andfully integrated with China's large portfolio o fpotentialprojects. Inboth cases, this approach indicatedthat the Bankassistedprojects were better than project alternatives that were thus rejected. And in both cases the Bank-assisted projects put a large emphasis on saving water ina river basin context. 3.43 Reviewingthe post-1990 portfolio o fagriculturalwater projects supported bythe BankinNorthandWest Chinathere hasbeena clear trendfrom buildingnewirrigation that increasesbasin-wide water demand, to projects that seek to improve water use efficiency and conservation efforts. However, there have beensome strategic mistakes that should have beenavoided -the Guanghong IrrigationProject approved in 1999 effectively doubled water use for irrigation inthe mid-reaches o fthe Yellow River near Xian. At the same time the downstream Water Conservation Project approved in2001 was extremely effective inreducing overall water consumption and i s a prime example o fwhat the Bank should support. There are three lessons\. The Bankneedsto elevateitsengagement in China's water resources policy discussions above the provinciallevelto emphasizethe perverseincentivesthat are created by extensive agricultural water subsidies. Subsidiesfor irrigation and landmanagementjeopardize water conservation effort, longer term sustainability o f irrigation and landreclamationprojects and water availability for towns, cities, industryand environmental management. Despite more than two decades o fBank partnership and several state-of-the art projects piloting new approachesthese tendto be enclave projects. While Chinese senior planners and politicians at the center acknowledge that pricing should play a role inensuring more efficient and rational allocation anduse o f water this i s still as at an early stage o f applicationand far from politically acceptable inthe provinces. Without such a change inthe near future water shortages and environmental consequences o fresource mismanagement will continue to grow to crisis proportions; 0Monitoring and Evaluation requires capacity building and reorientation to measureoutcomes and impacts.There is little virtue inimplementing development models for reclaiming degraded lands or for river basin management if impacts on welfare, incomes andthe economy cannot be accurately measured. While this is less o f a problem for physical achievements it is a major problem for measurement o f socio-economic outcomes and impacts. Muchmore attention has to be givento understandingthe appropriate counterfactual and ensuringunbiased sampling. There i s also an issue around selection o fthe most effective M&Emodel considering the outcomes expected and the cost o f the projects. Appropriate training to redressthe problems found inM&Ei s clearly indicated. Inaddition, more attention should be givento fully utilizing existing Chinese resources. The Ministry o f Finance has indicatedthat it has a national network o f monitoring that include socio-economic indicators and that consideration should be givento working with themto triangulate evaluative findings; and 0 Muchgreater care is required in dealingwith issues of attribution when estimatingex-post economic rates of return. Specifically this means clearer definition o fthe project counterfactual and a systematic accounting o fthe effects o f exogenous actors and investmenton project impact. Without such attention to these exogenous factors there i s a danger that estimated ERRSgive a false impression o f project impacts. This, inturn, may leadto incorrect lessons on development effectiveness and the efficacy o fpolicy, institutionaland engineeringmeasures utilized to achieve development objectives.
P056230 | SAL I(POLICY REFORM) | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/212561474397678203/text/000020051-20140528122256.txt | http://documents.worldbank.org/curated/en/212561474397678203/pdf/000020051-20140528122256.pdf | Â· Even in the midst of a severe political and economic crisis, the Bank can mobilize technical and financial resources that can mitigate the effects of a crisis, and establish a foundation for implementing medium-term reform policies.Â· Intensive supervision, facilitated by continuous presence of field-based staff, contributed to successful project completion.Â· A stable macroeconomic environment is necessary and fundamental to achieve structural reforms.
P056230 | SAL I(POLICY REFORM) | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2004 | PPAR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/917171468752402166/text/271770ID.txt | http://documents.worldbank.org/curated/en/917171468752402166/pdf/271770ID.pdf | 5. Lessons 0 Inacountry with deeplyrootedandwidespread govemance issues, wherethe authorities are not committed to deep reforms, the Bank needs to have realistic expectations about the outcome o f its interventions. InIndonesia, the ability to affect fundamental reforms with adjustment and technical assistance support has beenlimited. The effort requires a more comprehensive and long-term approach, including diagnostic work and involvement o f civil society. 0 The dilemma o f supporting a country incrisis i s highlightedby PRSL Iand, more especially, by PRSL II. The Bank needs to provide the Boardwith a frank rationale for its intervention, even where the rationale i s limitedto providing special shorterterm liquidity support for modest reforms. 0 The experience inIndonesiahighlightsthe importance of avoiding delays in banking crisis\. unless resolved quickly and decisively, the fiscal costs mount and vestedinterests further impederesolution. 0 Inamajor crisis, Bankmanagement andtop technical specialists should give priority to resolving issues that arise inthe context o f Bank assistance addressing the crisis, evenifthe vehicle for the assistance is inthe form ofa relatively modest technical assistance loan. 0 Coordination among donor agencies i s essential incountries incrisis and needs to bemade explicit. InIndonesia, coordinationwas successful only after an initial period of uncertainty, mainly becausethe IMFwas able to take the lead. 0 The Bank's'consultant fee structure and procurement rules caused delays and impededa rapid responseto Indonesia's bankingcrisis, and excludedor discouraged the few service providers with appropriate technical expertise. These rules should be reviewedwith a view to allowing exceptions to policy under certain well-definedcircumstances. 0 The Bank's central unit enabled the Bank to respond to Indonesia's needfor technical expertise, butthe unitwas not well integrated into the Bank's organization and was unfamiliar with its operational procedures, causing bureaucratic and practical problems. For future crisis response, the Bank should consider establishing a virtual crisis unit o f specialists working inthe Regions, available to respond to a specific crisis inside the relevant regional management
P056235 | KOREA SAL | East Asia and Pacific | Korea, Republic of |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1998 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/124691474575276701/text/000020051-20140522105248.txt | http://documents.worldbank.org/curated/en/124691474575276701/pdf/000020051-20140522105248.pdf | (1) The Bank did not adequately monitor nor assess Korea's economy. More diagnostic resources in the years prior to the crisis could have had a large payoff. The Bank should review the mechanisms and resources it is making available for this kind of work. (2) As large adjustment operations like this are pursued, the Bank should step back from the pressures of operations and carefully evaluate progress and shortfalls (see the audit recommendation in section 8). This would give the Bank a more realistic opportunity to draw lessons on the sequencing of reforms in crisis situations, the timing of real sector reforms (which may be lagging in Korea behind financial sector reforms), and how best to promote a coordinated adjustment which reducing the possibility of a future crisis. (3) The Bank and the IMF gave mixed signals at various times, despite daily contact, as noted both in the ICR and in the borrower's comments. The Bank and the IMF need to work towards even better coordination. (4) For good reasons, the Bank decided on a special pricing formula for this loan. This, however, was not adequately communicated to the Koreans in a timely fashion. Should non-standard pricing be considered in the future, the client needs to be kept fully informed.
P056236 | Higher Education Enhancement Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2002 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/698321474632559308/text/000146597-20140619170713.txt | http://documents.worldbank.org/curated/en/698321474632559308/pdf/000146597-20140619170713.pdf | When a widely adopted institutional change model is being introduced in a field like higher education for the first time in a country, it needs to be preceded by sufficient sector analytic work to create an appreciation of the complexities and the implications of the proposed changes and of the likely sources of resistance; such analysis could help determine the parts of the model that are appropriate to the context, and the pace of adoption. Higher education reforms supporting improved quality are easier to put in place than those for improved institutional efficiency and financial management, leading to decreases in cost-effectiveness. In Egypt this imbalance of reform (quality outstripping efficiency) cannot be sustained. Programs to improve the condition for higher education quality, relevance and efficiency cannot be expected to do so just because they have been made operational. Appropriate outcome indicators need to be formulated and used to determine whether to conditions have been sufficient to leverage real change.There are currently few disincentives for students enrolling in overcrowded and non-employment-conducive fields. Adding some elements of student cost recovery (which did not receive due consideration in HEEP) is a controversial topic, but some aspects of it (high subsidies for room and board) should be open to discussion, as well as fees for other non-instructional aspects of higher education.
P056236 | Higher Education Enhancement Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2002 | 2009 | 2011 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/627651468026381700/text/626510PPAR0P0700only0900BOX361497B0.txt | http://documents.worldbank.org/curated/en/627651468026381700/pdf/626510PPAR0P0700only0900BOX361497B0.pdf | 5. Conclusions and Lessons Learned Conclusions 5.1 The three MNA higher education projects were launched during the first 3 years of this century under similar circumstances\. a rapidly expanding higher education population outstripping government capacity to maintain funding levels, consequent reductions in educational quality; and a mismatch between the output of the universities and technical colleges and the needs of the countries and their labor forces. These circumstances called for increased attention to higher education relevance, quality, and efficiency, goals which all three projects attended to, either through formal objectives (Jordan), project activities (components) (Egypt), or policy strategies developed during the project (Yemen). 5.2 Each of these goals was conceptualized somewhat differently across countries, but in one way the projects all had something in common. In none of the countries and for none of the goals was there a strong elaboration of expected results or outcomes. With few exceptions project indicators were conceived of in terms of inputs, processes or outputs. For this reason it is not possible in any of them to clearly answer whether they made any substantial difference in higher education relevance, quality or efficiency. This is not to say that they accomplished nothing\. many new services and systems were delivered and changes were made in all three countries. 5.3 In fact, some parts of the Bank-supported higher education reform model flourished in the three countries. In all three competitively awarded grants motivated departments and staff members to come up with innovative programs, many connected to the labor market or addressing a national development issue. The seeds of quality assurance and accreditation have also been sown and are growing, albeit at different speeds. And ICT availability and usefulness have been accelerated, not yet for fully operational and digitized management information systems, but at least for improved internet connectivity, changes in instructional methods, and e-learning experiments. 5.4 However, some problems remain intractable\. there are still vastly more students in the arts, humanities and social sciences than in scientific and applied fields. Also, despite efforts to attract secondary school graduates into middle-level technical education (by renewing courses and forging ties with industry) students still tend to shy away from it. Moreover, even with significant attempts to improve course structure and provide in-service staff training, there appears (at least in the one study of improved pedagogy in Jordan) that not much has changed. Finally, it is not clear whether graduates are prepared for the work place\. again, a study in Jordan shows employers have not changed in their dissatisfaction with technical college graduates. Some of this might be explained by the weakness of incentive and accountability structures that was lamented in the World Bank MNA study The Road not Travelled. That is, academic or technical programs can be modernized but students must be motivated to enter them; graduates may not be able to find employment, but they won't have lost anything since tuition is free and, as in Egypt, so is room and board; and instructors can create attractive new syllabi but there will be no consequence if they don't show up to teach them. It seems that all projects, designed to provide the conditions for higher education reform, may still have missed some crucial ones. 5.5 Concerning the project goals to reform (or pilot new forms of) university governance, the efforts in all three countries were stillborn. Funding formulas were drafted but were not used; decentralization and university self-management of budgets failed to get off the ground in Egypt and Yemen. In Jordan, the efforts expected to improve the coherence of the system did not bear fruit. It seems that university governance is the most complex and change-resistant part of the accepted reform model. Some evidence from the PPAR mission suggests that this might be mostly a matter of unanticipated complexity or an underestimate of the implications of intended changes. Dealing with such complexity can be a matter of better research and analysis, or simply a matter of more time to work through it all. OR, it could be that this part the model is too biased towards Western industrialized cultures and economies (the Bank's Lessons from Experience was originally drawn up in the Anglo-American context). For this part of the world it may need governance models more consistent with Arab culture and/or more centralized governance traditions. This indeed is an area for continued analysis and dialogue. Lessons Learned 5.6 The following are some of the lessons learned from the comparative PPAR\. Â· When a widely adopted change model is being introduced to an area for the first time, it needs to be preceded by sufficient sector analytic work to create an appreciation of the complexities (implications) of the proposed changes and of the likely sources of resistance; such analysis could help determine the parts of the model that are appropriate to the context, and the pace of adoption. Â· Efforts to improve the quality of higher education need to be submitted to the same general test that is widely accepted for pre-university education\. Does it improve student learning outcomes? Standard assessment of student achievement in higher education is challenging, both in a technical and a political sense, but moves in that direction have already begun in Egypt and Jordan. Â· Restructuring higher education courses and programs and even ensuring appropriate private sector participation in decision-making are not in themselves sufficient to ensure that reforms will result in more employable graduates. Higher education systems need to systematically monitor the labor market relevance of their offerings and the success of their graduates. Â· Free university education in Yemen and Egypt (including generous room and board subsidies) creates the wrong market signals, encouraging enrollment in overloaded fields since failure to obtain employment represents little financial loss to students and their families. Â· Competitive systems for awarding grants can lead to some creative new and revised programs, but this needs to be done in conjunction with other university change efforts and on a large enough scale to have a significant effect on the quality and relevance of the university's offerings. 5.7 Graduate unemployment, which did not decline under the projects, will not change appreciably with the introduction of a few innovative program (the main approach used in the project), but requires serious gate keeping by the governments, shifting enrollments away from humanities (as in Yemen) and more serious incentive structures to steer students towards needed fields. The lack of programs for tracking and awareness-raising about graduate unemployment makes this issue less visible than it should be.
P056256 | Urban Water Project | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2005 | 2016 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/780651497542025307/text/ICRR-Disclosable-P056256-06-15-2017-1497542009855.txt | http://documents.worldbank.org/curated/en/780651497542025307/pdf/ICRR-Disclosable-P056256-06-15-2017-1497542009855.pdf | The ICR presents eight lessons and the two most relevant are given (after editing) below: Specificrequirements on safeguard matters should be included in project covenants. In the case of this project, datedcovenants on the establishment of escrow accounts for resettlement compensation was not included until project restructuring andeven then, it specified the requirement to establish the account but not to replenish the account. The Borrowersfailure to fully comply with compensation measures is amajor shortcoming of the Borrowerperformance. Stakeholder consultations on local water supply systems are critical to ensure relevant andappropriate designs. In the case of this project, the lack of proper consultation and design led to multiplevariation orders, re-working of designs, lengthy implementation delays, and significant cost escalation.Inaddition, IEG notes the following lesson: In a country with low capacity and significant governanceconcerns, there should be more assurance on the soundness of civil works design and contracts, and thorough prequalification ofcontractors. In the case of this project, the lack of due diligence on such matters led to significantimplementation shortcomings and cost overruns.
P056269 | TH-SOCIAL INVESTMENT PROJ I | East Asia and Pacific | Thailand | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Unsatisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/745771474482005240/text/000020051-20140613043541.txt | http://documents.worldbank.org/curated/en/745771474482005240/pdf/000020051-20140613043541.pdf | In crisis situations, project design should take into account the speed with which assistance can be delivered. Complex structures and processes that slow activities and disbursements should be avoided, and agencies should have a clear understanding of the requirements involved with Bank operations.During project preparation, an up-front assessment of implementing agency capacity is needed.The structure of a crisis-response project should allow sufficient flexibility to accommodate changing circumstances and mitigate risk.
P056337 | Mine Closure & Social Mitigation Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/936571475071054498/text/000020051-20140618075416.txt | http://documents.worldbank.org/curated/en/936571475071054498/pdf/000020051-20140618075416.pdf | 1. Capacity building stands a much better chance of success when it is focused on existing institutions and/or institutions which are a permanent part of the official structure, rather than on temporary entities set up to implement the project.2. Successful development of economically depressed regions affected by closure of non-viable industries requires a holistic approach, mobilizing not only technical, financial and economic expertise, but also diverse interventions such as social development schemes, funding of locally identified infrastructure, micro-credit programs, and adequate pre-layoff retraining.3. Detailed attention to environmental and social consequences of reforms (such as a mine closure program) is essential, with field visits and subsequent follow up of audits focusing on each individual unit. 4. A robust and detailed MIS is necessary to determine project outcomes, especially in the complex area of social mitigation. It is, however, important to ensure that agency staff and management have the willingness and capacity to collect the data and operate the system.5. A precondition of success in projects supporting highly socially sensitive reforms is full government commitment and active engagement, including seeking politically imaginative ways of overcoming resistance.6. Sensitivity to community and other stakeholder interests are essential throughout implementation.
P056376 | SECOND FISCAL RESTRUCTURING AND DEREGULATION TECHNICAL ASSISTANCE PROJECT | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2001 | 2001 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/352391474586483578/text/000020051-20140529162314.txt | http://documents.worldbank.org/curated/en/352391474586483578/pdf/000020051-20140529162314.pdf | (1) For reforms restructuring the government, civil service, and budget to succeed, they must have political leadership and be based on fundamental decisions about the role of the public sector.
P056376 | SECOND FISCAL RESTRUCTURING AND DEREGULATION TECHNICAL ASSISTANCE PROJECT | Eastern and Southern Africa | Malawi | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2001 | 2007 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/406021468271544252/text/37810.txt | http://documents.worldbank.org/curated/en/406021468271544252/pdf/37810.pdf | Lessons Incentives within the Bank can motivate unwise lending\. The desire to transfer resources and establishHIPC eligibility were important motivations to the initiationof FRDP III.Despite the poor macroeconomic climate andlack o f reformprogress under the previous credits, FRDP111was enlarged by US$20million (over the originally-conceived amount) andhastily structuredas a one-tranche loanmainly to facilitate establishment o fHIPC eligibility. Further, theoperationwas over-dimensioned for the scope ofitspolicypackage. 0 The region's macroeconomic assessments need to have greater realism and consistency\. The analyses o f the macroeconomic environment inthe FRDP 11 andIIIproject documents are unbalanced andlack realism andconsistency. The existence of a Fundprogram should not be a suficient conditionfor the Bank to initiate adjustment lending. Policy-based lending inan unstable macroeconomic environment is unwise\. The Malawian experience ofturbulent macroeconomic performance fiom 1994to 1998, with on-again, off-again Fundprograms shouldhave alerted the Bank that M e r adjustment lending after FRDPI\.(1) was not warranted; and (2) was unlikely to have a significant impact due to the negative effect ofmacroeconomic turbulence on the efficacy of structuralreform. Inpromoting reform, the Bank needsto take account of the incentives that a program creates\. MTEF, IFMIS,andcivil service reformwere unsuccessful in largemeasure because GOMofficials-at all levels-did not perceive that it was intheir interest to implement these reforms. While anofficialbudgetwas prepared, itwas routinely circumvented andexceededbypolitical intervention. Tenyears o feffort on MTEFandUS$2.3 milliono fexpenditure on IFMIS have produced virtually no results. 0 The Bank should structure lending to Malawiwith more earmarked, targeted aid, and tighter fiduciary controls\. To assure that funds are used in the manner intended, budgetary support should be subject to tighter fiduciary controls. Also, greater use shouldbe made o f earmarked assistance, including that which is delivered directly fiom suppliers to users, such as the successful CIDA textbook program (box 4.2).
P056390 | Ozone Depleting Substances Phase-out II Project | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2001 | 2010 | 2011 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/714351474397516459/text/000020051-20140620083307.txt | http://documents.worldbank.org/curated/en/714351474397516459/pdf/000020051-20140620083307.pdf | IEG endorses the ICR's main lessons from the project:(a) The approach of focusing on specific sectors (refrigeration and foam sectors in the case of Ecuador) allows the Government more flexibility in terms of using the technology of its choice and lowering costs.(b) The establishment and effective enforcement of an ODS Import Licensing System enables the setting of import quotas that are keyed to ODS phase-out targets. When coupled with industrial conversion and training activities, these quotas can facilitate compliance and program sustainability.(c) Prior capacity-building for local implementing agencies, particularly in the areas of the Bank's project management, procurement and financial management procedures and requirements, can significantly facilitate implementation.(d) The program's nationwide reach could be significantly enhanced by conducting the training of technicians through the national-level government service responsible for training and capacity-building.(e) As is often the case, the Government's commitment is a key ingredient in project implementation success, as is continuity of staff and the availability of counterpart financing from the Government.
P056393 | Second Social Action Fund Project (FAS II) | Eastern and Southern Africa | Angola | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2004 | 2005 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/639371474560572624/text/000020051-20140612152022.txt | http://documents.worldbank.org/curated/en/639371474560572624/pdf/000020051-20140612152022.pdf | Building capacity requires careful planning and adequate allocation of time and budget. Particular attention is also needed to systematically monitor and evaluate capacity building initiatives.In a post-conflict situation, a quick and flexible response is needed to country situations.
P056416 | Second Education Sector Development | Eastern and Southern Africa | Lesotho | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2004 | 2004 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/634811474577070456/text/000020051-20140612131507.txt | http://documents.worldbank.org/curated/en/634811474577070456/pdf/000020051-20140612131507.pdf | Free primary education is an important means to bring about education to the poorest of the poor. A phased approach may allow governments sufficient time to prepare for the large enrollment increases that follow. - Scholarships for destitute students may enable them to stay in school and pay for their daily needs. However, clear and enforceable criteria are needed to ensure that those who need the scholarships the most benefit from them.- Triggers for APLs must be carefully designed to be realistic and achievable. Flexibility in policy dialogue may prove to be more effective in bringing about agreements over subsequent tranches rather than attempt to enforce dated covenants.
P056418 | Lesotho Water Sector Improvement Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2005 | 2011 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/789491474594295257/text/000020051-20140625074804.txt | http://documents.worldbank.org/curated/en/789491474594295257/pdf/000020051-20140625074804.pdf | The following lessons are taken from the ICR with some adaptation:Ensuring sector reforms requires successful completion of three key phases: first, the adoption of appropriate sector policies and their translation into legislation and a regulatory framework; second, the creation of the necessary capacity for the application of these policies in the form of adequate institutions, trained staff and management, hardware, software, incentives and sanctions; and, third, the consistent implementation of the sector policies with strong and continuous political support.The effects of the geographic size and location of small countries such as Lesotho should be fully factored into project design with mitigation measures proposed, since they may have significant consequences for implementation. In this case, both procurement and contract management problems, and difficulties in recruiting and retaining qualified staff may be related to Lesothoâ€™s size and proximity to the Republic of South Africa.Despite less encouraging experiences elsewhere, Performance Agreements for utilities can be a successful tool if certain preconditions are in place. These include strong and public commitment to the concept and practice of the Agreement by both the Government and the utility, the immediate application of remedies when problems or shortcomings are indicated, and a direct link between donor-supported investments and other improvements and the targets in the Agreement.
P056419 | Ex-Combatants Reintegration Pilot Project | Middle East and North Africa | Djibouti | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2002 | 2004 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/277661474502652759/text/000020051-20140612091500.txt | http://documents.worldbank.org/curated/en/277661474502652759/pdf/000020051-20140612091500.pdf | A LICs or LIL can be an important instrument for small-scale Bank assistance in risky environments, but it needs to focus primarily upon learning with designs that incorporate monitoring targets of learning by the Bank itself, borrower agencies and other parties to the project. Project assistance of this kind should come sooner than five years after the end of a conflict (the moment when this credit became effective). As widely recognized (including by this project's PAD) lack of reintegration of demobilized soldiers can be most critical from economic and psycho-social perspectives in the first few post-conflict years. Economic and social reintegration of ex-combatants will only succeed when it is clearly a top priority for the borrower, and designed in partnership with local communities. Reintegration cannot be imposed by outsiders. When ex-combatants cannot be easily distinguished from the rest of society, support for reintegration may be better delivered to local communities which contain veterans, than to individuals - who are difficult to identify or to monitor. In this way, the project can have a wider impact on poverty and reach other vulnerable groups in society.When it is known that a project, a priori, cannot cover all the eligible target group, its design must incorporate selection criteria for those that will be chosen that should be as transparent and equitable as possible.
P056424 | China Tongbai Pumped Storage | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/279561474595687909/text/000020051-20140619081052.txt | http://documents.worldbank.org/curated/en/279561474595687909/pdf/000020051-20140619081052.pdf | Flexibility is of paramount importance when a large project is being implemented while a major reform program is in progress. Commitment and support at various government levels, and strong ownership by the power utility, are critical factors in successful power sector reform and associated TA. In China, Bank-assisted power sector projects have featured the piloting of new approaches, which in this project included a provincial Competitive Power Market, a comprehensive Distribution Management System, condition-based maintenance, and leasing arrangement for a peaking generation plant. Piloting, coupled with loan use flexibility and low cost, high impact, TA, could be a successful means to foster reforms and innovations.Selection of experienced implementing agencies can help minimize the impact of delays. The delays in government clearance and approval processes resulted in significant slowdowns in project implementation. The experienced implementing agencies in this project, however, were able to effectively re-schedule and re-organize construction activities, enabling them to catch up with the delays and complete construction under the original time schedule.The Bank should be proactive to reduce the Borrower's front-end fees and commitment charges. There should be an in-depth review of project design and unit prices to help reduce unnecessary financing costs. In this project, this was achieved by early and modest restructuring of the project when the unit rates in tenders came in significantly less than those estimated at appraisal. The project cost estimates proved to be too high, which resulted in excessive front-end fee and commitment charges to the Borrower.A well-experienced Panel of Experts (POEs) should be considered in large dam projects. POEs have been proven to play a key role on dam safety, and can often make suggestions resulting in significant cost savings for dam construction.
P056452 | VN-RURAL ENERGY | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/616031474634477004/text/000020051-20140618061407.txt | http://documents.worldbank.org/curated/en/616031474634477004/pdf/000020051-20140618061407.pdf | i) Long term vision. A clear roadmap aimed at achieving the final objective of the Borrower with Bank support should be developed. It should be the basis for designing specific interventions and facilitating their development. In this case, four major rural electrification projects were planned from the start to assist the Government of Vietnam to implement its Rural Electrification Program, addressing first the most urgent issues at the time, but not in the most difficult areas, and carefully preparing the institutional arrangements for the next set of interventions in more difficult areas. ii) Decentralize to the acceptable level. The decision to decentralize RE to the final implementing agencies proved to be efficient and effective in successfully implementing the project and exceeding the number of communes and households electrified.iii) Cost sharing. The development of RE is strengthened through the principle of cost sharing by the parties involved. It stimulates the mobilization of funds from several sources. Cost sharing arrangements need to be designed to ensure the ownership and dedication of related parties without surpassing their payment capacity. In this project, provincial authorities were able to provide financial support to the poorest households.iv) Stakeholders. Consulting with and obtaining strong commitments from local stakeholders are essential in projects involving a large number of parties. In this project, written commitments were obtained from rural residents, communes, districts and provinces and the layout of the electric lines were certified by those affected.v) Flexibility. Flexibility in implementation is essential -- both in term of physical scope and approval -- to allow for fast adjustment to unexpected conditions (in this case cost savings) that may contribute to an increase in the benefits of the project.vi) Project team. Projects with local implementing agencies and/or covering several local areas need a TTL and team based in the field. This allows effective coordination and interaction with the client and implementing agencies, close monitoring of project progress, and quick resolution of problems and delays arising in the project.
P056452 | VN-RURAL ENERGY | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2000 | 2007 | 2014 | PPAR | >=100 million | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/217991468329657329/text/885430PPAR0P040C0disclosed060240140.txt | http://documents.worldbank.org/curated/en/217991468329657329/pdf/885430PPAR0P040C0disclosed060240140.pdf | 5. Lessons In supporting the sector to move towards long-term financial viability and fiscal sustainability, the Bank should lay primary emphasis on broader institutional and policy measures for cost recovery. In contrast, specific target-oriented and timebound measures in the form of tariff or financial performance covenants carry excessive political implementation risks and are prone to noncompliance by the Borrower. Despite a number of financial performance measures that were included in their design, the three Bank operations were not effective in helping improve Vietnam's power sector finances, let alone place the sector on the road to sustained financial recovery. Considering this experience, the Bank should have pushed for a more systemic solution to the sector's long-simmering financial crisis through the introduction of a sound tariff methodology to ensure sustainable cost recovery and the power sector's future operational/financial sustainability, while making the sector more attractive to much-needed external private finance. A national push for universal electricity access provision will primarily depend upon the pursuit of a least cost path for grid expansion backed by appropriate sector policies, complemented by off-grid electricity in the interim or for the longterm as needed. In Vietnam, as the electricity grid expanded faster than expected, the decreasing necessity and relevance of off-grid electrification was not adequately foreseen, resulting in some off-grid facilities falling into disuse or neglect. This experience points to the need for planning ahead, and making technical provision for integrating off-grid and mini-grid facilities with the grid when it arrives, so that the expected benefits are realized from the investments. Rapid growth in electrification can be accompanied by sub-optimal use of electricity especially in a situation of relatively low or subsidized tariffs. This calls for early and serious policy attention to improving Energy Efficiency and implementation of dedicated Energy Efficiency operations on a sizable scale. The evidence shows that the Bank's program has essentially provided a supply-side support program for Vietnam's power sector, largely following demand, as the GOV has done, with less attention to demand side management. The marginal Bank-supported Energy Efficiency efforts (typically a small demand side management-style component under various power sector operations) has not been effective in to making a material difference to the Energy Efficiency landscape, let alone nationwide scale-up. The Transmission Distribution sector â€“ continues to play catch-up with increasing demand which needs to be moderated through appropriate measures including tariffs that better reflect cost-recovery levels. The extremely large reservoir of untapped Energy Efficiency opportunities calls for the creation of a solid framework for energy-saving efforts, including sizable programmatic support for Energy Efficiency, extending well beyond the piecemeal approach applied to date. The Bank should work to develop an understanding with client countries over the role of key institutions before embarking on full-fledged support for them. Otherwise, weak understanding might result in less than desirable institutional performance and sub-optimal use of technical assistance resources. In Vietnam, the Bank should have pushed for agreement on a more autonomous professional regulatory agency, before committing to a large amount of capacity building support to ERAV. In the absence of serious support from the Government in this respect, ERAV's regulatory role has weakened somewhat over the years, and some of its resources have been diverted to non-regulatory type activities (e.g., administration of the competitive generation market) instead of focusing on core regulatory activities such as tariff methodology and quality-of-service regulation, monitoring and enforcement. While ERAV's overall technical competency may have improved over the years with sustained support from the Bank, the outcomes from its efforts are weak â€“ sector finances continue to deteriorate, and the quality and reliability of electricity service for consumers has seen a downward trend in recent years. In a rapidly evolving sector environment, a de facto flexible approach should be adopted to adjust to changing priorities as well as new institutional and on-theground developments. Even if the changing situation could not be foreseen at the project design stage, such an approach would enable more smooth and successful implementation of the project. This aspect is illustrated in all three projects and particularly in the SEIER project where both the Bank and Borrower responded to changed circumstances through project restructuring to allow flexibility for investing in subprojects that took on greater priority. The project M&E framework should focus on identifying the direct causal links between project interventions and outcomes to the maximum extent possible. This is particularly important, albeit challenging, in large and rapidly evolving sector context in which Bank-supported interventions only partially influence but do not determine overall outcomes. In addition to being unnecessarily complicated with too many performance indicators, several key outcome indicators related to improved T&D reliability and efficiency were defined at the national system level, which made an accurate outcome assessment for the T&D component largely impossible or tentative at best under the TDDR and SEIER projects. While they are usually more challenging to design, in similar situations project-level indicators or appropriate proxies should be used for the relevant project areas. The community's involvement in the design, construction and operation of new rural electricity supply networks, and cost-sharing can lead to successful implementation and a sense of ownership. Ensuring local participation in all aspects of the project helped mobilize and maintain local support and commitment to rural electrification, while ensuring a rapid pace of the process, creating employment, building local capacity and thereby laying the foundation for the sustainable management and operation of the networks. Significant cost sharing by local governments and the communities was an important element of the Vietnamese financing model for rural electrification. Mobilization of local funds was essential to close the funding gap. This requires appropriate mechanisms and enabling institutional and legal frameworks, not only at national, but also at local levels.
P056487 | MINING SECTOR REFORM PROJECT | Eastern and Southern Africa | Madagascar | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1998 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/793951474750704662/text/000020051-20140612071252.txt | http://documents.worldbank.org/curated/en/793951474750704662/pdf/000020051-20140612071252.pdf | From the experience of this project and others, successful reform in the sector is associated with a coherent legal framework and effective regulation by public sector mining institutions, and mechanisms that involve communities in the management of mineral resources and sharing of benefits from mining activity;On the other hand, enforcement of new regulations can be hindered by shortcomings in governance and institutions, even if the government is otherwise committed to policy reform; andDetailed baseline information and adequate institutional capacity is crucial for improving governance in a small-scale mining area through TA.
P056491 | HEBEI EARTHQUAKE REHABILITATION PROJECT | East Asia and Pacific | China | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2001 | 2002 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/979671474565650563/text/000020051-20140604044815.txt | http://documents.worldbank.org/curated/en/979671474565650563/pdf/000020051-20140604044815.pdf | The ICR draws an excellent list of lessons on replicability, attention to preparation, procurement methods, sustainability, beneficiary participation, and income generation. To these can be added:1. The existence of recently developed building codes for earthquake-resistant structures and expertise with such structures in China permitted the project to work as quickly and effectively as it did.2. The health and education facilities built by the project were immediately turned over to the local agencies responsible for their operation. The ICR notes that "in some cases, sustainability of services may have been impaired by lack of school and hospitals materials, equipment and consumables." This suggests that some of these agencies may have been under budgetary stress, perhaps brought about by the need to shift funds to other priorities created by the post-disaster situation. Although the borrower explicitly excluded the financing of operating costs from the IDA credit, this problem might have been avoided--and might be avoided in other post-distaster situations--if some form of bridging arrangement was in place to ensure the operation of rebuilt facilities.3. The appraisal for this project was remarkably detailed, especially for an emergency loan. The appraisal included an engineering analysis of the structural failures in the region's traditional construction and analysis of the damage to the Friendship reservoir dam. The experience of this project shows that even in an urgent post-disaster situation it is possible to pay attention to detail.
P056514 | Transport Ministry Restructuring Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Transport | IDA | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/781891474897011641/text/000020051-20140612091939.txt | http://documents.worldbank.org/curated/en/781891474897011641/pdf/000020051-20140612091939.pdf | Achieving major reforms across a broad range of areas is difficult, especially in a country where building strong and broad-based supports is difficult and time-consuming. Therefore, it may be better to focus on one or two sectors. One must recognize that there are disadvantages to piecemeal restructuring, such as various parts of the government might be restructured based on different and incompatible models. The project experience shows that meaningful restructuring of a single ministry is possible. Restructuring projects must be designed with considerable flexibility in the content of the Terms of Reference, phasing and sequencing of actions and decisions, and of the time frame for implementation as getting agreements from different government agencies is difficult to schedule with any precision.
P056514 | Transport Ministry Restructuring Project | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Transport | IDA | IPF | 1999 | 2003 | 2008 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/772921468246593461/text/429040PPAR0P1070130Box327369B01public1.txt | http://documents.worldbank.org/curated/en/772921468246593461/pdf/429040PPAR0P1070130Box327369B01public1.pdf | 5. Lessons Learned from the Projects 5.1 Particular attention should be paid during preparation to the degree of commitment by government to implement reforms discussed. Stated commitments should be backed up with Letters of Intent; 5.2 During supervision the Bank should be perceptive to reasons for tardiness in the implementation of reform components of the project, so that intervention can be made earlier if need be, and at an appropriate level; 5.3 Institutional reform needs to be backed up by a professionally designed training program in which the participants can understand the strategic direction of the overall reform process, and their role within it; 5.4 Learning and Innovation Projects such as the Transport Ministry Restructuring Project should be designed to achieve a higher level of monitoring and evaluation for learning purposes than that expected of other projects, with key performance indicators and measurable outcomes to support future adjustments in direction .
P056516 | CN-Water Conservation | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2001 | 2006 | 2007 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/535281474663906727/text/000020051-20140617135613.txt | http://documents.worldbank.org/curated/en/535281474663906727/pdf/000020051-20140617135613.pdf | Technical innovations require substantial M&E systems to verify their efficacy and efficiency. This project clearly demonstrates that high tech irrigation technologies save water and, when allied with adequate agronomic support and access to markets, lead to higher incomes for farmers.Persistence at appraisal pays off in the long term despite a sceptical client. Build in small demand-driven pilots of prosed innovations and the results will speak fro themselves.
P056521 | SAL 2 | East Asia and Pacific | Korea, Republic of |  |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/557021474510810887/text/000020051-20140528125914.txt | http://documents.worldbank.org/curated/en/557021474510810887/pdf/000020051-20140528125914.pdf | (1) Strong client ownership has a clear impact on the success of the program. This is especially important in wide-ranging programs such as SALII in which the government needs to work closely with the private sector and non-government stakeholders to ensure that the program is both broadly acceptable and broadly supported. While the Government felt that the program was overspecified; given the fact that it was achieved makes a judgment difficult as to whether this was a valid point. (2) An integrated and comprehensive approach with clear linkages among the sectors is important in an economy such as Korea's, given the capacity of the government. This also facilitates effective monitoring and feedback. (3) Staffing flexibility was important to achieve results as the Bank drew on staff with previous experience on Korea to make up for the lack of recent Bank operations and ESW.
P056522 | Thailand Public Sector Reform | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2000 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/543651474396670663/text/000020051-20140607142651.txt | http://documents.worldbank.org/curated/en/543651474396670663/pdf/000020051-20140607142651.pdf | 1. High quality TA is important in building awareness, designing the reform program, and supporting implementation. 2. For successful implementation, the project design should address issues of potential conflict between newly established independent organizations and the executive branch.3. The continuity of the team and persistence of efforts over multiple years are important to build consensus for major reforms.
P056524 | BANK'G SYS REF (FSAL) | East Asia and Pacific | Philippines | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2001 | 2002 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/219221474397167541/text/000020051-20140604055132.txt | http://documents.worldbank.org/curated/en/219221474397167541/pdf/000020051-20140604055132.pdf | When a critical number of specific objectives (such as i, iv, and vi in Section 3) depends on the commitment of politicians and not simply on the leadership of the counterpart technical government agencies, the Bank should carefully identify political risk, be up front about it in the Board documents, and pro-active in addressing them.
P056595 | EL NINO EMERGENCY PROJECT | Eastern and Southern Africa | Kenya | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/688611474649239911/text/000020051-20140607154236.txt | http://documents.worldbank.org/curated/en/688611474649239911/pdf/000020051-20140607154236.pdf | Streamline the procurement and payment process. Combine the streamlined process with regular, rigorous audits performed by a private audit firm for quality control.To improve the performance of the PMU, a sometimes problematic, but necessary setup, a clear chain of command, and adequate communication channels must be delineated in advance.PMUs need sufficient technical staff to verify and check submissions/estimates in order to avoid changes in project scopes and to minimize project variations. Given the highly positive results of employing audit firms for quality control, these firms could take up a larger role in M&E.
P056596 | CN-Shijiazhuang Urban Transport | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/523421474853509794/text/000146597-20140619165149.txt | http://documents.worldbank.org/curated/en/523421474853509794/pdf/000146597-20140619165149.pdf | Complex project designs should be avoided when possible in a weak implementation environment. Urban transport projects need to achieve a balance between private cars, public transport services and other road users including cyclists and pedestrians. Traffic management measures including a appropriate parking policy need to be considered along with measures to promote the use of public transport.The implementation of the Involuntary Resettlement Safeguard requires respect for affected persons. Some of the delays were the result of the city taking a more respectful attitude towards affected persons and taking time to negotiate mutually accepted solutions.An effective M&E requires not only the definition of a good set of performance indicators during project preparation, but that it be supported by a well articulated monitoring and evaluation framework.The question remains, however, how to capture the strengthening of institutional capacity in a meaningful way and what indicators are most appropriate for evaluating public transport and the effectiveness of a vehicle inspection program.
P056796 | KR-FIN. & CORP. RES. AS | East Asia and Pacific | Korea, Republic of |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/259211474564255359/text/000020051-20140607173915.txt | http://documents.worldbank.org/curated/en/259211474564255359/pdf/000020051-20140607173915.pdf | 1. As noted in the ICR, procurement rules and procedures should be compatible with the urgency of a systemic corporate/financial sector crisis and the technical sophistication needed in a country at Korea's level of development. Tor this project, the acceleration of procurement procedures and waivers to consultant fee ceilings, under the Bank's procurement rules, took extraordinary effort by the Bank and Implementing Agency staff at a time when the focus on technical issues of corporate/financial sector crisis abatement should have had the highest priority. Complex procurement rules that delay urgently needed financial advisors may degrade the effectiveness and value of similar projects in the future if this issue is not addressed. 2. In a well-structured TA project implemented in a crisis, it is important to allow for full funding based on best estimates, even if subsequent cost savings emerge. The costs of underfunding such a project could have been extremely high. 3. It is crucial to define potential conflicts of interest for potential consultants right at the start of a project and ensure that consultants involved in the project avoid any real or perceived conflicts.
P056891 | Rural Finance Project (APL #1) | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/380131475084622031/text/000020051-20140619074546.txt | http://documents.worldbank.org/curated/en/380131475084622031/pdf/000020051-20140619074546.pdf | Two lessons can be derived from the project experience:Changes in financial sector conditions during project implementation can alter the need for liquidity in the financial system. This makes it difficult to forecast the demand for Bank-financed credit lines. In some cases (such as the RFP), it is preferable to focus on the underlying reasons for lack of access to credit -- such as the high risks and transactions costs of lending to SMEs -- rather than directly supplying credit.An agency relationship with microfinance institutions (MFIs) can reduce the likelihood of sustainability. In the RFP, no legal framework existed that would allow the Government to lend to MFIs. Instead, an agency role was developed for MFIs that required them to reimburse the Government in the short term. This forced the MFIs to quickly raise additional financing on their own.
P056891 | Rural Finance Project (APL #1) | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2001 | 2008 | 2009 | PPAR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/266871467990946481/text/48762-PPAR-P056891-Box396251B-PUBLIC.txt | http://documents.worldbank.org/curated/en/266871467990946481/pdf/48762-PPAR-P056891-Box396251B-PUBLIC.pdf | 8. Lessons Learned Four lessons may be drawn\. (1) Before a loan is negotiated it is vital to secure the implementing agency's agreement to project components and implementation procedures. If QAG's quality at entry reservations had been addressed early on this project's start-up lag may have been reduced. (2) Investment projects need to be sufficiently flexible to allow for rapid and often unanticipated changes in the economy and the external environment. In this case, the project had to be adjusted to take into account the speeding up of Romania's accession to the European Union. (3) Changes in financial sector conditions during project implementation may make it difficult to forecast the demand for Bank-financed credit lines. This project showed that it is better to address the underlying reasons for limited credit accessâ€”factors such as high risks and the heavy transaction costs entailed by lending to small enterprisesâ€”rather than directly supplying credit. (4) Before governments enter into an agency relationship with microfinance institutions (MFIs) the possible consequences for overall investment flow need to be fully understood. In the RFP, no legal framework existed that would allow the Government to lend to MFIs through their umbrella organizations, which signed the SLAs and assumed the fiduciary obligations. (The legal framework is now being developed.) Instead, an agency role was developed for MFIs that required them to reimburse the Government in the brief period stipulated in the project's operating manual. The inability of the MFIs to intermediate the funds they administered impeded a fuller flow of investment capital to rural entrepreneurs and farmers, as the MFIs could not readily recycle sub-borrower repayments under the agency arrangement.
P056978 | IRRIGATION BASED COMMUNITY DEVELOPMENT | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/412841474652536882/text/000146597-20140619161046.txt | http://documents.worldbank.org/curated/en/412841474652536882/pdf/000146597-20140619161046.pdf | The ICR offers a number of useful and well-formulated lessons, including: The model of irrigation-based community development promoted by this project is an effective mechanism for reducing rural poverty and lends itself to scaling up. "Small and medium-scale irrigation proved the optimal entry point for integrated development in mountain areas as all social and economic life in these zones is organized around the irrigation perimeter. The project also demonstrated that government agencies are both able and willing to implement this approach, and that fiscal decentralization--the Rural Development Fund under the management of the governor--aids the approach" (ICR, Section 6). Ensure that there is a continuing cross-sector dialogue with government on rural development strategy, based on a steady flow of findings and lessons from project experience. Although the decentralization and participatory strategy on which the project was based has remained pertinent to Morocco's development needs (and is embraced at the regional and local level), there has been some falling off of commitment at higher levels of government. This could have been avoided if the M&E framework of this project had provided adequate and timely empirical evidence of project performance and if this evidence had been used to help inform a continuing dialogue with the various ministries and agencies involved in rural development.Lay solid foundations for implementation at the preparation phase by assessing institutional capacity, providing the requisite training and preparing an adequate operational manual before loan effectiveness. The implementation of this project was substantially delayed by the failure to do the necessary groundwork during preparation and, in particular, the lack of detail and realism in approaching community-driven development. Procedures for participatory monitoring and evaluation need to be developed during project preparation, including provision for a baseline survey. The report concedes that, during implementation of this project, "no progress was made with participatory M&E" (ICR, Section 6).
P057007 | UG EL NINO EMERG RD REP | Eastern and Southern Africa | Uganda | IDA |  | Infrastructure | Transport | IDA | IPF | 1998 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/884871474565827948/text/000020051-20140612151555.txt | http://documents.worldbank.org/curated/en/884871474565827948/pdf/000020051-20140612151555.pdf | A project with the clear objective of alleviating the effects of natural disaster should focus only on issues related to the emergency situation. The inclusion of the Atiak - Moyo road, located in the north of the country where security condition was uncertain, was a distraction for both the Government and the Bank project implementation teams and should not have been included in this emergency project.Procurement requirements in an emergency situation should be clear. If the project needs to disburse quickly and the project is disaster-related, it should be an Emergency Reconstruction Loan. The bank should be sure the government understands the guidelines before the project begins.The Bank should as a general rule identify the risks of disaster prone developing countries and help the governments of these countries to develop institutional arrangements for coping with recurrent disasters.
P057030 | BO REG REFORM ADJ CREDI | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 1999 | 2003 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/897091474486148789/text/000020051-20140607174216.txt | http://documents.worldbank.org/curated/en/897091474486148789/pdf/000020051-20140607174216.pdf | The credibility of the regulatory system requires separation of the regulatory process from political interference. This is difficult to achieve, even when the right legal and institutional reforms are adopted. Projects with significant legislative components require careful assessment of the the political landscape during project preparation.Flexibility may be required when designing phase-in periods and limits for guarantees in Deposit Guarantee Funds.
P057167 | Technical Education Vocational & Entrepreneurship Training (TEVET) Development Program Support Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/953311474512304462/text/000146597-20140619165405.txt | http://documents.worldbank.org/curated/en/953311474512304462/pdf/000146597-20140619165405.pdf | When key actions have to be triggered by specific legislation that needs to be approved at the highest levels of Government, the implementation and sustainability of a project may be jeopardized. In order to guarantee success, new legislation should be passed prior to project approval or at a very early stage of project effectiveness. Implementation arrangements should factor in the time it takes to undertake policy changes and how potential delays in policy may impact on project outcomes.To build capacity in the implementing agency project implementation has to be mainstreamed even though weak capacity to do so may require technical support. Top down approaches using a temporary management unit will not produce sustainable systems. During preparation, a thorough capacity assessment of the implementing agency should be undertaken, including identifying areas where support would be needed. A well developed implementation plan with clear roles and responsibilities for all participants can help project execution. When roles and responsibilities are clear, even weak agencies know what they have to do and what they need to build their capacity. Experience from other countries have shown that funding TEVET by establishing a levy system that taxes the private sector to pay for public TEVET training is likely to be successful only where the country has an established, diversified private sector, typically found in advances economies.
P057167 | Technical Education Vocational & Entrepreneurship Training (TEVET) Development Program Support Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2001 | 2009 | 2011 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/909411468166492312/text/625850PPAR0P05000official0use0only0.txt | http://documents.worldbank.org/curated/en/909411468166492312/pdf/625850PPAR0P05000official0use0only0.pdf | 6. Lessons 6.1 The experience of the Zambia TDP exemplifies the challenges in shifting the TVET system from supplyto demand-driven provision of training in a country with little experience in public-private partnerships and a large informal sector. As in many African countries and in other parts of the world, Zambia's traditional TVET system comprised a network of centrally funded and managed institutions, staffed by civil servants, taking sixteen to eighteen-year olds straight from school into full-time (mostly boarding) vocational courses of one or three years. Typically, the high capital and recurrent costs of this type of training, combined with lack of incentives to innovate, led to progressive deterioration of buildings and equipment, the use of outdated machinery, materials, curricula and teaching methods, and scarcity of well-qualified instructors with industry experience. Such systems showed mixed to poor results in the employment and incomes of graduates. They were unable to respond flexibly to changing technology and labor market conditions, ill-suited to reaching the informal sector or meeting in-service training needs, and was too expensive to sustain. Policy for the TVET sector has thus shifted internationally (Box 6-1) towards institutional reforms that can help orient training to employment needs and diversify both the forms of training and the sources of funding. Box 6-1. Evolution of TVET Policy A policy review by the World Bank in 1991* was based on evidence of generally poor results from the projects that had financed training through traditional public systems. It emphasized that the dual goals of TVET policy should be to encourage private provision and financing and to improve the efficiency of publicly provided training. The proposed two-step strategy focused on (i) improving access and quality in general education and creating a supportive regulatory environment for human capital development and growth in employment; and (ii) the reform of TVET policies and institutions to orient the supply of training to local labor market needs and conditions. As a result, the emphasis in assistance for the sector from the 1990s shifted to policy and institutional reforms that could allow better responsiveness of training provision to employment needs and diversify sources of funding. The menu of measures adopted has included\. giving financial and managerial autonomy to publicly-owned TIs, subsidies and other incentives for private training provision, the establishment of national training authorities, autonomous training funds, private sector payroll levies, industrial sector councils, national labor market observatories, and graduate tracking systems. The measures have often proved difficult to implement, especially in low income countries and when economic growth is slow, and the evidence of impact in such cases is limited. Within SubSaharan Africa, Mauritius, Zimbabwe, Botswana, Namibia and Tanzania have established independent training authorities with training funds. Reforms in South Africa centered on establishment of the institutional framework for a national qualifications system and sectoral education and training authorities, financed by a training levy. * Vocational and Technical Education and Training\. A World Bank Policy Paper, 1991 6.2 In this context, the TDP represented a brave and ambitious attempt to transform the system through a particularly comprehensive package of reforms\. granting financial and managerial autonomy to publicly-owned training institutions; establishing an autonomous national training authority; and financing TVET through a competitive training fund. Where it appears to have fallen down is through taking on too much too quickly with insufficient resources or analysis of the political economy challenges. Since the planned reforms were only partially implemented (and M&E was weak), the TDP experience cannot provide much information on their impact but it does yield many lessons on the planning and implementation process. Political Economy Challenges v Design of TVET reform should be based on in-depth information and analysis of the relevant strength, perceptions, interests and incentives of different stakeholder groups. Much attention was given in TDP design to the policy and technical soundness of the vision for the new system but not enough to the implementation challenges. Change in the fundamental governance structure of TVET, which produces winners and losers, needs buy-in by multiple different stakeholders to their new roles. The design assumed that policy commitment would be sustained throughout implementation, despite indications from the outset of opposition to the plans for channeling public funds for private as well as public training provision through an autonomous training fund, and widespread doubts about the viability of a payroll levy to finance the fund. The natural concerns and the challenges facing central government staff and the staff of publicly owned TIs were seriously underestimated\. sector ministry staff were set to pass control of sector resources and management to as yet unproven non-state agencies while assuming new and different functions themselves in policy, monitoring and information management; staff of the MSTVTâ€“affiliated TIs faced losing the security of civil service status and were ill-equipped to take on their own financial management and planning in a competitive environment. Cooperation in implementing the changes would depend on all key groups being assured not only of the long term viability of the changes but also of sufficient financial and technical assistance to protect their immediate interests. Similarly, TDP neglected the incentives for private finance of training\. the doubtful assumption at appraisal was that demonstrated improvements in the general quality and relevance of training would be sufficient to inspire willingness on the part of enterprises to contribute to the TEVET Fund through a payroll levy. v Before attempting nationwide implementation of radically new governance and financing arrangements in TVET, piloting should be considered and flexibility should be built into the plans. The experience of the TDP suggests that, when understanding of the proposed reforms is not widespread and implementing capacity is constrained, it would be better to consider piloting, learning and demonstration in selected sectors and institutions. This would provide the opportunity to clarify the requirements, refine and adapt procedures, demonstrate benefits, and enlist stakeholder support before detailed plans for scaling up. The The TDP was highly unrealistic â€“ in terms of time, resources and capacity in expecting to accomplish the institutional reforms and achieve nationwide improvements in the quality of TEVET graduates within a five year time frame. Considering the difficulty in predicting the course of institutional change, when the constraints and opportunities are often influenced by individual leaders or personalities, some flexibility and contingency planning should be incorporated from the outset. v Clear definition of respective roles and responsibilities for the sector as a whole and in project implementation â€“ is crucial for successful implementation of TVET reform. Many of the problems experienced in TDP implementation might have been avoided through ensuring legislation to support the TEVET Fund before approval, clearer distinction of the responsibilities of MSTVT and TEVETA in appraisal documents, structuring project components to match the respective responsibilities, and underlining the autonomy of TEVETA through a separate implementation agreement for the activities for which it was responsible. The attempt in TDP to address the coordination challenges through a Program Coordination Office was unsuccessful and counterproductive, adding to the confusion as to who exactly was responsible or accountable for what. v Devolving managerial authority for publicly-owned training institutions from central government to local management boards is liable to be de-railed by lack of sufficient autonomy, capacity building or financial resources. The new legal status of publicly-owned TIs in Zambia was introduced abruptly, prior to TDP implementation. Their staff were stripped of civil servant status but the government undertook to finance salaries for a further three years, while the new institutions established financial viability. In other respects, the transition was not well supported and, with hindsight, should have been piloted. The TIs were already in bad shape through lack of investment while their staff lacked experience or capacity in financial planning and management. Without clear autonomy, the management boards were subject to MSTVT regulation â€“ including limits on the fees they could charge constraining their scope for initiative and for securing financial sustainability. As a result, the TIs were naturally resistant to the new competitive arrangements and the policy tended to be perceived more as a response to budget constraints than a wholehearted measure to improve their capacity to provide quality services. Their evident lack of preparedness, in turn, reinforced the temptation of the parent ministry to revert to managing and supporting them through a centralized approach. A successful transition to management boards would have required more funds, effective capacity building, and enough autonomy to allow management boards to function effectively. TVET Financing v A national training authority can provide a good base for a competitive fund channeling resources for training, so long as it is professionally managed and clearly independent from the provision of training. The training sector straddles three sets of public sector interests\. (i) education sector strategy, in terms of coherence and pathways between general secondary education, universities, and the technical and vocational options at each level; (ii) industrial strategy, promoting productivity and national competitiveness, and (iii) labor market, employment and social protection strategy, including active labor market programs. Non-government stakeholders are heterogeneous, in terms of the governance, funding sources and interests of different types of training provider and forms of training, different industrial sectors, and firms of different size. The role played by TEVETA in Zambia illustrates the benefits of a technical, non-political, umbrella authority in management and regulation of the sector. This type of agency, given sufficient autonomy, is well placed to (i) provide a forum for mediating the interests of all stakeholders â€“ several different government ministries, industry, public and private TIs and trainees â€“ to serve multiple purposes; and (ii) helping to match training to employment needs by involving employers closely through a variety of mechanisms in the design and delivery of training. The progress made in developing the capacity of TEVETA through the TDP owed much to its strong leadership. However, the neutrality of TEVETA and its independence from training provision was questioned at times, due to the role of MSTVT as the parent ministry responsible for TEVETA but also maintaining a stake in training provision, through a hands-on role and natural allegiance to the needs of its own TIs. In the short pilot phase of the TEVET Fund, questions on the its neutrality and its role beyond the public provision of training were not fully resolved. Some stakeholders perceived that MSTVT TIs were treated preferentially in Fund allocations, while others felt strongly (contrary to the official policy) that non-government providers should not be eligible for public funding. Training authorities elsewhere have often been placed under the wing of the ministry of labor, which may tend to minimize conflicts. v A competitive training fund under non-government management can be effective in addressing needs in the informal sector and the needs for in-service training (as well as formal pre-employment training) but sustainability is a major challenge. Piloting of the TEVET Fund in Zambia demonstrated the potential for such a fund to work with the range of stakeholder groups and develop new initiatives both for the informal sector and for in-service training in the formal sector. Given that formal sector TIs are naturally geared to the formal sector, Zambia's TEVET Fund illustrated some mechanisms that can be used to (i) provide means and incentives for formal TIs to focus on entrepreneurship curricula; and (ii) work through NGO and informal networks to reach the informal sector. However, the Fund depended entirely on donor resources and the reluctance of government to channel any of its own resources through the TEVET Fund rendered it unsustainable. v The use of a payroll levy for the training sector is best-suited for finance of inservice training and is difficult to apply in low-income countries or for the informal sector. The experience of payroll levies to finance training in other countries indicates that such levies are usually oriented to in-service training and that smaller firms have tended to benefit less than larger ones. In Zambia, the levy was proposed to contribute to the TEVET Fund as a whole, with financing also from the government and donor agencies. In practice, the private sector was unwilling to trust the government with training funds and the government was reluctant to attempt imposing a payroll levy for the TEVET Fund. It was not considered viable to tax the formal private sector to support training for the informal sector. The four windows of the TEVET Fund were well designed but more attention could have been given to distinguishing sources of funding for each window. More progress might have been made with the private sector through a distinct sub-fund, under their control, to finance in-service training. Similarly, organizations (including government) focusing on social and poverty objectives could be expected to participate in a sub-fund for the informal sector. For formal pre-employment training â€“ which needs coordination with public secondary and university education the TEVET Fund piloted useful approaches, including contracting of training in priority areas based on the full costs, with graduated subsidies of fees (a legitimate public cost) for the poorest students. TVET M&E v In the absence of an existing information culture, substantial time and resources are needed to develop sector capacity in M&E for results-based TVET policy. Much more attention was needed in TDP from the outset to detailed requirements of the new role of MSTVT in sector monitoring, information management and policy development. The program set out ambitious plans for a new information system, regular sector policy updates and skills development plans, but the implications for the structure and recruitment of MSTVT staff, the TA and training requirements and the time needed were not thought through. The role of TEVETA â€“ as the agency dealing directly with TIs â€“ was not clearly distinguished. As a result, the proposed information system was never fully functional and the proposed M&E and policy development activities were mostly not implemented or were not implemented well. It is likely that a less ambitious design with stronger technical support and clearer specification of respective responsibilites could have produced better results. Although some aspects of data collection and management were eventually picked up by TEVETA, the core sector policy and strategic functions were neglected. The proposed National Skills Development Plan, for example, which was intended to provide a basis for prioritization in TEVET Fund allocations, was not prepared. v The selection of outcome indicators for a TVET reform project should focus on results that can be clearly and directly attributed to the project interventions. By focusing on higher level outcome objectives, such as the employment of TEVET graduates, the TDP results framework failed to make explicit the linkages or chain between program outputs and outcomes. It would be better in many cases â€“ when higher level outcomes cannot be expected within the time frame of the project, or the specific contribution of the project interventions cannot readily be separated from other factors â€“ to focus on the intermediate outcomes for which the project or program can clearly be held accountable\. for example, an established system for regular on-going tracking of employment and incomes of TEVET graduates, with strong analysis and dissemination of the information, would have been a good outcome of the TDP. That is, it may be more useful to focus on intermediate steps â€“ such as creating the national capacity for on-going monitoring related to downstream objectives â€“ than on trying to demonstrate higher level impacts within the course of one institutional reform project. Sector-Wide Approach v For TVET institutional reform, the potential benefits of a SWAp may be difficult to realize unless country capacity is strong enough to support the use of country systems in a results-based framework. The TDP design incorporated elements of a Sector-wide Approach, in so far as the agreed financial contributions of the government and four donors were combined in the overall financial framework of the sector program which was jointly appraised. Shortcomings in country systems and capacity precluded a full sector-wide approach, pooling support to the sector budget, although the TDP benefited from strong donor coordination throughout design and implementation. Only two of the partners, including IDA, channeled resources jointly through the line ministry for the program as a whole, with expenditures to conform to agreed annual work plans and budgets. Other partners had separate arrangements for direct support to the training authority and/or individual training institutions. In the event, the activities funded through MSTVT were subject to bureaucratic delays in reaching agreement on plans and in procurement and implementation, as well as resistance to delegating authority. Efforts to build M&E capacity in the MSTVT were unsuccessful and the focus stayed on process, rather than results. The problems seem to have arisen from two sources\. country conditions were not fully conducive to a SWAp; and the implementation arrangements for the IDA credit and Netherlands funds were inappropriate for a SWAp and also out of line with the new sector institutional arrangements. Through separate arrangements, the direct support by Danida to TEVETA's capacity and operations appears to have been instrumental in the positive outcomes that the TDP did achieve. The strengths of their approach, as reported by the institutions concerned, included intensive and highly flexible technical assistance and training, which was responsive to demand and based on frequent reassessment of needs and priorities, as well as their close presence in the field.
P057182 | Legal & Judicial Reform Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/122061474577645965/text/000020051-20140615111604.txt | http://documents.worldbank.org/curated/en/122061474577645965/pdf/000020051-20140615111604.pdf | To reiterate two key lessons that the ICR notes:(i) The Bank can not support legal and judicial reform by itself. Meaningful donor collaboration (in terms of supporting various elements of a comprehensive Government strategy for legal and judicial reform) is essential in this type of complex reform.(ii) The Bank must support clients in establishing systems to monitor and evaluate progress in legal and judicial reform so as to allow for any fine-tuning or revision of the reform as may be found to be necessary.
P057187 | TZ-FIDP II | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/753581474503667010/text/000020051-20140618053334.txt | http://documents.worldbank.org/curated/en/753581474503667010/pdf/000020051-20140618053334.pdf | The ICR review identified four lessons learned, including: (i) sustained improvement of access to financial services in rural areas through the privatization of large state-owned banks; (ii) the need to build strong financial infrastructure in bank restructuring and privatization; (iii) the need for long-term investment in capacity building of regulators for successful project implementation, especially with regards to privatization; and (iv) the need for mainstreaming of project implementation which contributes significantly to the strengthening of client capacity and to signaling clear lines of authority vis-a-vis the private sector. From the Borrower's perspective lessons learned included: (i) the importance of prompt decision-making for timely completion of projects and for the avoidance of cost overruns; (ii) the need for strong stakeholders participation to facilitate the privatization process; and (iii) the value and benefit of the outcome was worth the trouble despite the cumbersome process and political sensitivities associated with state-owned bank privatization.
P057188 | PRE-SERVICE TEACHER EDUCATION | Western and Central Africa | Guinea | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2002 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/927191474512253348/text/000020051-20140612073153.txt | http://documents.worldbank.org/curated/en/927191474512253348/pdf/000020051-20140612073153.pdf | It is possible to train large numbers of student teachers through rapid means if supervisors provide strong support. However, the often low level of candidates' academic achievement may create obstacles in training.- Hiring teachers through annual contracts (and few if any benefits) is an effective means for meeting the needs of a rapidly expanding student body in many low-income countries while keeping salary costs low.- Small LIL projects enable governments to take initiative and implement efforts to improve their systems without the cumbersome procedures inherent in larger operations.
P057188 | PRE-SERVICE TEACHER EDUCATION | Western and Central Africa | Guinea | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2002 | 2003 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/847601468750019410/text/262450GUI0PPAR.txt | http://documents.worldbank.org/curated/en/847601468750019410/pdf/262450GUI0PPAR.pdf | Lessons 57. Experiencewith the projects confirms a number o f OED lessons from the education sector\. 0 Policy dialogue and project activities must stay focused on improving instructional effectiveness and providing students with basic skills. Activities aimed at strengthening management and procuring educational commodities may be necessary but they are not sufficient for the improvement o f learning and quality ineducational systems. Providing mass education under clearly inadequate instructional conditions may graduate functional illiterates andbenefit only a minority o f students. 0 Textbooks are the crucial providers o f information inschools. Ifthey are unavailable or ifstudents cannot study fi-om them sufficiently, the rest o f the educational investments lose their effectiveness. Procurement methods and plans must aim at making large numberso f textbooks available at an affordable cost and free to the poor. Textbook management must take into account the strengths o fthe private sector and the community associations. 18 Sustained investment inhuman resources can improve implementationcapacity o f specific institutions. For example, foreign fellowships for persons who returnand devote their career to the agencies they were expected to serve may result ina considerable o f trained and competent staff. 0 Inearlier decades, the Bank supported vocational training schools inmany countries, which often function with few students, highunit costs, and outdated equipment and curricula. Bank investments will bebest usedifpolicy dialogue is focused toward modernizing courses, generating income, and catering to the populations likely to be interested invocational training. 19
P057234 | Eastern Arc Forests Conservation and Management Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2004 | 2010 | 2011 | PPAR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/980011468025820126/text/6276900PPAR00P0e0only0900BOX361506B.txt | http://documents.worldbank.org/curated/en/980011468025820126/pdf/6276900PPAR00P0e0only0900BOX361506B.pdf | 5. Lessons 5.1 The experience of the TFCMP/EAFCMP suggests the following lessons\. Â· A reform agenda that depends on the buy-in of key individuals can be stalled unless there is\. (a) a contingency plan for the loss of political will and (b) sufficient flexibility in project design to enable adjustments to changes in the level of ownership. In the case of the TFCMP/EAFCMP, the right mix of people appears to have converged during preparation but the project did not prepare for the likelihood that personalities would change. Â· Late and incomplete restructuring can result in a failure to complete project activities within the project timeframe and, as a consequence, to achieve project objectives. In this case, the Bank proactively refocused credit proceeds on activities that were under control of the project implementation unit and could improve forest management within the existing institutional structure, but the objective of changing the institutional structure remained unchanged. Some of the activities added through restructuring were delayed by procurement challenges that had plagued the project since inception. Â· The use of demand-driven approaches for forestry or natural resources management activities may be constrained by insufficient demand, as communities often have other priorities. Â· Small grant monitoring that narrowly focuses on ensuring that grant monies were used for their intended purpose, is insufficient to demonstrate outcome level results and is a lost opportunity for learning. In the case of the EAMCEF, an opportunity was also lost to learn which activities generate greater returns in terms of conservation and livelihoods goals. In the case of the TASAF PRM window, an opportunity was lost to gather information that would allow for a comparison of two different modalities to deliver support for the establishment of PFM agreements. Â· The financial sustainability of endowment funds can be compromised without sufficient and early attention to developing the fund-raising skills of Endowment Fund staff. 5.2 The experience of the two pieces of sector work yields the following lessons\. Â· High quality analysis is insufficient on its own to prompt action from government decision makers. The policy note and follow up political economy analysis were both viewed as high quality documents that addressed a relevant topic but that alone was insufficient to generate results. More attention should be given to how to foster ownership of the process and objectives up front. Â· Reform of sectors in which responsibility cuts across multiple agencies may be difficult without a sustained dialogue through multiple sector units in the Bank (forestry, environment, energy). 5.3 The following lessons emerge from the experience of both the TFCMP/EAFCMP and the Sector Work\. Â· Changes in mind-set may be difficult to bring about without a strategy for generating broad-based consensus up front. In the case of the TFCMP/EAFCMP, consensus was there during preparation but was lost once core members on the borrower and bank side moved on. While consultation workshops were held during preparation, interviews with stakeholders suggest that a relatively small group of people fully bought into the reforms, understood what they were trying to accomplish, and were involved in the project's design. When key personalities changed there was an insufficient base of people who understood and bought into the proposed reforms to inform new leadership. In the case the sector work, the Bank attempted to change the way that charcoal is viewed by presenting reform of the sector as a missed opportunity. Despite producing high quality documents there has been no buy-in from decision makers. A strategy is required to engage government decision makers from the beginning and keep them engaged throughout the process. Â· One project cycle may not be long enough to bring about institutional changes. Similarly dissemination of analytic work without a program for sustained dialogue may also limit results. One project was not long enough to ensure that the new institutions had sufficient capacity to be effective and ensure a shift in the way that forests are managed. Similarly the brief period of dissemination was insufficient to ensure that the charcoal studies remain visible and are on hand for political windows of opportunity.
P057271 | GY "EL NINO" Emergency Assistance Proj | Latin America and Caribbean | Guyana | IDA |  | Sustainable Development | Water | IDA | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/438221474486004598/text/000020051-20140607163943.txt | http://documents.worldbank.org/curated/en/438221474486004598/pdf/000020051-20140607163943.pdf | In designing emergency assistance projects, adequate attention should be given to the absorptive capacity of the country. Weak administrative capacity, lack of skilled staff, and limited pool of qualified contractors and consultants can cause serious implementation delays.Emergency projects should follow-up with appropriate maintenance policies and operational and institutional support.
P057272 | GY FINANCIAL & PRIVATE SECTOR | Latin America and Caribbean | Guyana | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/163631475079611592/text/000020051-20140612072642.txt | http://documents.worldbank.org/curated/en/163631475079611592/pdf/000020051-20140612072642.pdf | 1. Complex operations need strong coordination at the agency level for each component. This was the case in the privatization component of this project, which generated much of the progress achieved by this project. Bank staff need to provide timely and targeted support to each implementing agency and department, especially those which lack capacity. Building trust and working relationships is time consuming but essential to project implementation in these circumstances. 2. The design of a privatization program in a socially sensitive manner is a key factor for its successful implementation. In this project, the Privatization Unit obtained political, labor union, and public support for privatization. While in this project, clauses to protect minority investors and employees were important in building such support, care needs to be taken to allow the new owner sufficient leeway to allow the newly privatized enterprise to be profitable.
P057272 | GY FINANCIAL & PRIVATE SECTOR | Latin America and Caribbean | Guyana | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2003 | 2004 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/671391468750034306/text/29334.txt | http://documents.worldbank.org/curated/en/671391468750034306/pdf/29334.pdf | 5. Lessons and Recommendations 5.1 Governanceproblems and distrust are the binding constraints to improving the investment climate and getting PSD going in Guyana.Unless realprogress is made on those fronts -and donors needto recognize their very limitedcapacities to help inthose areas donor-drivenprojects can expect to continue to have low rates o freturn, andmay evenbe harmful. 5.2 Every component of every donor project and everyproject process (such as consultations on project design, the hiringo fconsultants, procurement o f goods, selection o ftrainees, and choice o fregulatory options) should be assessed to seeing how theprojects andprocesses can avoid deepeningdistrust, and ifpossible, serve to build trust across the racial divide. Participatory approaches, as appliedinpreparation o f the PRSP, shouldbe applied inmonitoring andevaluation o f allprojects, bothbydonors andclients. 5.3 More diagnostic work is needed to identifi strategies and tacticsfor rationalizing incentives, building sustainable institutions, andfostering social capital. IfGuyana could build its social capital, it would have no lack o f financial capital or humancapital. New studies are not needed to undertake seriouspublic sector reforms, including civil service reforms, that have been postponedfor a decade or more. These reforms are a necessary preconditionto effective capacity buildingandthe sustainabilityof institutionsthat are currently overwhelmingly donor-dependent. 5.4 Closer donor coordination is needed to increase the eficiency and cost-effectiveness of technical assistanceprojects aimed at institutional development. Having multiple cooks (donors) inthe samekitchen(project component) preparingthe samemealsbutwithdifferent ingredients andtastes is neither efficient nor cost-effective. While inpolicy-basedoperations there maybe a case for some overlap, ininstitutional development TA projects there should be clearer division of responsibility among donors to avoid duplicationandoverlap. Agreements should be sought on lead donor andpooling arrangements reflecting donors' experiencein Guyanaand comparative/competitive advantages. 5.5 Donors and GOGalike need to strengthen ongoing and ex-post monitoring and evaluation of IDprojects to get prompt andtrue accounts not only o fprogress toward objectives but also o fthe quality, impact, andcost-effectiveness ofthe particularinstruments employed (in TA projects these include consultant advice, consultant-prepared studies, andvarious types o f training and equipment). 5.6 Donors need toface up to the labor market distortions and other downsidesfor the longer run being caused by their hiring and salary supplementationpractices. Donor policies on salary supplementation o fpublic servants (including consultants performing line positions in government) needto be rationalizedand harmonized with a view to promotingrather than postponingcivil service reform.
P057293 | Democratic Republic of Congo Economic Recovery Credit | Eastern and Southern Africa | Congo, Democratic Republic of | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2002 | 2003 | 2005 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/998871474563029560/text/000020051-20140612135706.txt | http://documents.worldbank.org/curated/en/998871474563029560/pdf/000020051-20140612135706.pdf | 1) In post conflict countries, the Bank should design modest but well focused reform programs, because borrowers have lost to a large extent the capacity to manage and coordinate a wide array of policies and measures. In addition, they remain distracted by security problems. It is probably preferable to have several smaller operations.2) In designing conditionality for adjustment operations, where legislation is to be created or amended, the focus should be on: (i) requiring the issuance of implementation decrees rather than only submission of drafts to parliament; and (ii) evidence that an effective institutional framework is in place to implement and enforce the legislation. In this regard, the Legal Department should have a much larger role and earlier input in designing conditionality. The lack of - or considerable delay in - effective implementation of revised legislation is a recurring issue in adjustment operations largely undermining their success.
P057293 | Democratic Republic of Congo Economic Recovery Credit | Eastern and Southern Africa | Congo, Democratic Republic of | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2002 | 2003 | 2012 | PPAR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/862721468235145049/text/650640PPAR0P080C0disclosed010250120.txt | http://documents.worldbank.org/curated/en/862721468235145049/pdf/650640PPAR0P080C0disclosed010250120.pdf | lessons from previous (unsuccessful) attempts to fight corruption; (iv) prioritize and sequence proposed actions and assign responsibilities; and (v) provide for adequate monitoring and evaluation arrangements. Weak strategy design was followed by an even weaker implementation. In short, the national anti-corruption strategy was not well designed, it had very little (if any) political support, and it never got implemented. 32. For a number of years, IDA and the international community avoided the issues of governance and corruption in DRC. By 2007, the concerns with deteriorating quality of governance and growing cases of corruption became so large that the international community practically imposed a Governance Compact on the Government of Antoine Gizenga as a condition for continued donor support and engagement in DRC. The Governance Compact put emphasis on transparency (publication of extended information), enhanced control mechanisms (mainly through watchdog institutions), priority processing of high-visibility cases, and implementation of Extractive Industries Transparency Initiative principles. Although the compact was intended to revive and follow-up on the 2002 national anti-corruption strategy, this was not the case since it did not have the key ingredients of a national strategy\. definition of objectives, assignment of responsibilities, and support of broad stakeholders. 33. The Anti-Corruption Commission was created with a six-month delay, but became operational after the legal basis was approved in July 2004. The commission faced many operational challenges\. it lacked experience, professional expertise and managerial skills, limited financial resources, paid low salaries irregularly, and depended on (erratic) donor support. Its deliberations were severely constrained and its low public image eroded by apparent problems of nepotism, political influence, infighting, deep mistrust, and antagonism among the ACC members. As a result, the ACC was not effective in implementing the NACS and the relevant laws, as well as launching and supervising anti-corruption initiatives. 34. The new anti-corruption law was an important step in the right direction, but its effects on fighting corruption appear limited due to design problems, significant delays in approval and effectiveness, and exceptionally weak enforcement. 35. A new code of conduct for public officials was enacted on time (October 2002) and it applied to all individuals holding public office or being paid by the state. The code was designed to fight negative values and misconduct (corruption, misappropriation of public funds, misuse of labor, favoritism, nepotism, and conflict of interest). It required all public officials to declare 27 ANNEX A assets and defined disciplinary measures for breaching the provisions of the code. In an environment where ethical behavior was no longer the norm, implementing the code was a major challenge. An independent oversight body, the Observatory of the Code of Ethics for Public Officials was created in October 2002 with full administrative and financial autonomy to effectively oversee the implementation of the Code. This did not happen, because OECP's operation was hampered by weak capacity, limited resources, and lack of political will. 36. Procurement overhaul. Public procurement reform was one of the priorities identified in the 2002 NACS as a means of reducing the scope for corruption. A public procurement reform commission, the Commission de la Reforme des Marches Publics and a national working group were jointly leading the reform of public procurement. Independent observers were appointed to the commission and a new tender system was put in place to prevent the widespread single-sourcing and the related corruption that it fueled. But the full implementation of the new procurement system was stalled by the lack of trained staff and managers, weak information systems (including the blacklisted and eligible firms), and the failure to establish tender boards in the provinces. The Bank was absent both from the design and implementation of the procurement overhaul effort in DRC and, apparently, followed a different approach in the 2004 Country Procurement Assessment Report. 37. Overall, aside from sporadic evidence on policy actions and temporary improvements in some dimension of governance during the DRC-ERC-I operation (2002-2003), there were no systematic progress indicators on the implementation of the national governance and anticorruption strategy and the priority action plan. Multiple external sources, aggregated under the Worldwide Governance Indicators, show some improvement in the quality of governance during the 2000-2008 period, but insufficient to conclude that the situation has changed in a significant way (Annex Box A1.1). 38. With low effectiveness of proposed policy actions and the Bank's early disengagement, the achievement of the DRC-ERC-I operation in improving governance and reducing corruption is rated as negligible. 39. Public Sector Financial Management. The stated objective was to improve overall public sector financial management, especially targeting improved management of public expenditures through\. (i) general public expenditure reviews; (ii) expenditure tracking and monitoring surveys in the context of HIPC; and (iii) better public expenditure oversight. The project document envisioned a single benchmark for this objective\. Parliamentary approval of the 2003 budget, including the allocation of recurrent and capital expenditures to key development ministries and agencies, acceptable to IDA. 40. A public expenditure review was conducted in 2002 as planned, but it remains unclear to what extent its findings influenced the quality of the 2003 budget. Tracking of poverty related expenditures was done jointly by IDA and IMF as a part of the 2002 PER exercise. The results obtained on the basis of standard 15 HIPC tracking benchmarks were then used to design HIPC completion point triggers.
P057294 | Rwanda - ECON. REC. CREDIT | Eastern and Southern Africa | Rwanda | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2002 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/360301475072261091/text/000020051-20140607143241.txt | http://documents.worldbank.org/curated/en/360301475072261091/pdf/000020051-20140607143241.pdf | While the ICR does not state it, it appears from comments in the supervision reports that the Government could have used technical assistance to implement this project. Given the importance of the laws needed in order to make progress toward the larger goals of macroeconomic stability, promotion of national reconciliation, and the development of a market-oriented economy, it is not viable to recommend, as the ICR does, that conditionality on legal changes should be limited to the presentation of laws to the National Assembly, and not their adoption.
P057295 | RW-Compet & Enterprise Dev (FY01) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2001 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/202731475110440897/text/000020051-20140625184247.txt | http://documents.worldbank.org/curated/en/202731475110440897/pdf/000020051-20140625184247.pdf | This Review concurs with the ICR on the following lessons:Political commitment at the highest level is needed to guide implementation of far-reaching reforms.A good M&E framework with clear causal chains linking activities to outcomes provides a critical management tool to make timely adjustment.PCU capacity needs to be sufficiently factored into project design to ensure smooth implementation.Decentralization of project supervision enhances dialogue, timely identification, and resolution of issues. In a multi-donor context, coordination among partners is critical to ensure efficiency and impact. As a top reformer of the business environment, Rwandaâ€™s experience would be of interest to many countries and should be shared widely through South-South knowledge exchange program.
P057296 | Emergency Multisector Rehabilitation and Reconstruction Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2003 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/164181474510384504/text/000020051-20140624190754.txt | http://documents.worldbank.org/curated/en/164181474510384504/pdf/000020051-20140624190754.pdf | The following lessons are adapted from the ICR:Emergency operations caused by the need to respond to post-conflict situations are very different from those related to natural disasters. In the latter cases, institutional capacity and policy may not be major issues. However, in the first case, because of the destruction caused by conflicts, it is critical to include -- as was done in this project -- institutional reforms, capacity building and sector strategy formulation in order to start laying the foundations for the future.Even in emergency situations, an effort should be made to address sustainability issues at the project or program design stage. If sustainability is not included at the design stage, such issues should be part of the dialogue throughout project implementation.Because of the uncertainties concerning cost estimates in an emergency situation, flexibility needs to be built in the financing plan so that processing of adjustments or reallocations can be simplified and the transaction costs minimized as further studies provide more reliable cost estimates.The use of NGOs can be an effective and efficient way to implement the social activities at the grass root level.
P057326 | SIERRA NEVADA SUSTAINABLE DEVELOPMENT PROJECT | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | Less than 10 million |  | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/707241475084534501/text/000146597-20140617162502.txt | http://documents.worldbank.org/curated/en/707241475084534501/pdf/000146597-20140617162502.pdf | The principal lesson from this project experience is that Government-civil society partnerships can be an effective arrangement for delivering development assistance in areas where public institutions are weak. However, the institutional framework must be carefully designed so that roles, disbursement flows and reporting requirements are well defined and mutually agreed prior to project implementation.
P057345 | BORGOU PILOT RSP | Western and Central Africa | Benin | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2002 | 2003 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/208591475094921530/text/000020051-20140607171614.txt | http://documents.worldbank.org/curated/en/208591475094921530/pdf/000020051-20140607171614.pdf | Some important lessons are identified by the ICR. One is repeated here. (i) Decentralized procurement procedures can lead to emergence of new capacities and skills in communities, can reduce the completion time for micro-projects and can generate a feeling of ownership among project beneficiaries; The Evaluation Summary adds the following lessons: (i) In a PTI intervention like the Borgou pilot development objectives should be framed at least partly in terms of poverty alleviation. This should be done in a way that is monitorable and should be backed up in design by a monitoring and evaluation system capable of measuring poverty impact. (ii) In a project whose primary objective is to build the capacity of the rural communities to better manage their socio-economic environment performance indicators need to be set up in a way that they are able to track qualitative progress on achievement of this objective.
P057345 | BORGOU PILOT RSP | Western and Central Africa | Benin | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1998 | 2002 | 2003 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/272111468768609185/text/multi0page.txt | http://documents.worldbank.org/curated/en/272111468768609185/pdf/multi0page.pdf | 5. Lessons 5.1 The experience of the Borgou Region Pilot Rural Support Project offers several important lessons for future Bank-supported CDD interventions in Benin and elsewhere.8 LESSON 1\. The LIL instrument is designed to support learning and innovation. From the Borrower's perspective, implied in the use of a LIL is future Bank support for expansion of a successful experiment. However when the Bank shifts towards favoring a different lending approach for the country, without communicating clearly and in a timely manner to the Borrower as to what this means for follow-on support, the credibility of the LIL instrument is eroded. 5.2 The government of Benin planned to use the Borgou model as an exemplar for decentralized government administration throughout the country. The project experience revealed some important lessons, precisely as is expected of a LIL, but ensuring that the lessons are fully learned is part of the preparation of a follow-on phase. The tremendous publicity surrounding the Borgou Pilot created momentum in support of the CDD approach in the country. The project closed in June 2002. The Bank has now moved towards providing Benin with budgetary support rather than project assistance. The govemment requested IDA support to help extend the Borgou model to the whole country in June 2001. IDA's response was that a follow-on operation to the Borgou Pilot would be financed through the national budget under the new procedures for IDA financing. However even as of November 2002 there was lack of clarity, in the government both at the center and the region level as to how a CDD project like the Borgou Pilot could be financed through national budget procedures and what form it would take. The Region in its comments notes that last fall (2002) a decision was taken to prepare a National Community Driven Development Project that is scheduled for Board presentation in FY04. Though a decision may finally have been taken to move forward with support, there was a considerable period of uncertainty for the Government as to whether future support would be available. This uncertainty 8. Several issues raised here support the findings of the recently completed OED desk review on CDD and the Sahel. does not bode well for local development planning. It dampened the momentum that had been generated for CDD approaches and conveyed negative and demoralizing messages to the borrower and the communities. LESSON 2\. The design of CDD projects needs to be realistic about the costs and time required to satisfactorily implement such operations. Adequate attention to building the elements of sustainability at the community level often requires much more time and resources than Bank projects normally budget for the purpose. 5.3 Section 4 of this report discussed several aspects of project design that need to be given much more attention. Balancing immediate needs and long-term development needs, accommodating the effect of social and cultural factors on capacity building, and choosing the right implementing agency are important details that require serious thought, careful attention and adequate planning. The choices made must also be compatible with local political, social, and economic conditions. Handling these issues adequately has implications for project preparation time and implementation schedules. Hence in designing and implementing CDD interventions, Bank management and staff need to be realistic about costs and disbursement schedules. LESSON 3\. In a CDD intervention the performance indicators need to be designed to monitor and track quantitative gnd qualitative progress on achievement of objectives. Though the quality of community participation in decision making is difficult to measure, if no attempt is made to do so, it is likely to receive less attention as project teams become preoccupied with meeting progress on quantitative targets. 5.4 During project implementation, more attention was given in the Borgou Pilot on completing the number of sub-projects, disbursing the credit amount and holding the identified number of training courses. All of the Borgou Pilot supervision missions cited progress in the number of micro-projects constructed, number of villages covered, number of training sessions held, and amount of money disbursed. This is particularly problematic for a LIL where process and learning should be given more prominence than physical input achievement. The mission documnents provide little information on qualitative progress on the main project development objective, improvement in the capacity of women and village communities to manage their socioeconomic environment. Where the documents note that the quantity and quality of infrastructure has improved they give little information on the basis for the quality judgment. The operational manual did identify impact indicators, but in practice outcome/impact indicators were lumped together in the supervision documents and the completion report and give more information on quantity than on improvement in quality. LESSON 4\. The Bank needs to harmonize the rules and processes in its community based interventions in a given country and coordinate effectively on these aspects with other donors supporting similar interventions in that country. 5.5 In addition to the Borgou Pilot, the Bank has supported other participatory interventions in Benin-in the Borgou region and sometimes in the same communities. The Benin country department has begun internal consultation and discussion on the need to harmonize different Bank-supported participatory approaches in the country, but so far there has been no follow-up on these discussions. In addition, other donors-among them IFAD, the French, and USAID-have been supporting construction of village-level infrastructure in the Borgou region, often using participatory approaches. The community contribution requirements for each intervention are different. For example, the Bank-supported Social Fund Project required a 10 percent contribution from communities, while the Borgou Pilot required a 20 percent contribution. As acknowledged by supervision documents, this has created confusion at the community level.9 5.6 There are also major sustainability implications of the lack of coordination and harmonization. First, when one donor project ends, the communities turn to another donor with their ready-made list of demands. Since resources do not appear to be a constraint, there is less incentive to make the best possible use of scarce money. Second, in the long run, the presence of multiple donors and multiple projects creates for villages an incentive to avoid participation in projects that put greater emphasis on community capacity building as a part of the requirement for financing a sub-project. If money for the same sub-project can come more easily from another donor, why should a community want to be tied down with a project that requires them to undertake numerous capacity building exercises? Third, differing modalities for assistance to communities and different implementation schedules can create wasteful competition among projects. Supervision documents for this project report instances of villagers withdrawing their contributions from other projects and bringing them to the Borgou Pilot because they were happier with the short implementation schedule. Fourth, no matter how efficient the project and how short the implementation schedule, communities will always prefer to contribute less rather than more, especially if they have an option to do so. The assessment field visits and conversations with villagers revealed that many would like the community contribution requirement reduced and cited their preference for the 10 percent requirement of the Social Fund project over the 20 percent requirement of the Borgou Pilot. 9. A supervision document notes that the coordinators' group had made recommendations on the harmonization of procedures among the projects. The document also suggested that the recommendations be forwarded to the relevant government ministries to facilitate the drafting of applications for amendments to the lending agreements. It noted that this was urgently needed because communities were becomning confused by the variety of community contributions required for the various projects.
P057350 | Interactive Environmental Learning & Science Promotion Project | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 1999 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/524101474663832222/text/000020051-20140615095349.txt | http://documents.worldbank.org/curated/en/524101474663832222/pdf/000020051-20140615095349.pdf | Projects involving cultural heritage may have broad public appeal and long-term sustainability, particularly if they benefit from public-private partnerships and endowments.- It is possible to turn local residents into guides of archeological sites and thus increase the incentive to preserve cultural patrimony.
P057352 | FOURTH RURAL WATER SUPPLY PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 1999 | 2007 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/480681474632145836/text/000020051-20140617134447.txt | http://documents.worldbank.org/curated/en/480681474632145836/pdf/000020051-20140617134447.pdf | Demand led projects allow for more flexibility but are also vulnerable to errors in the estimation of consumption which may increase the costs of improvements for beneficiaries. It is important to understand cultural and regional differences that may value potable water and excreta differently from westernized norms. In turn, this may lower demand for modern water supply and sanitation services.In order to substantially increase the coverage of sanitary latrines, households need to be offered a choice of sanitation options that are affordable as well as adequate information in order to make an informed decision.Increasing access to water supply creates increased wastewater due to increased water consumption, particularly in densely population areas and should be factored into water supply projects.
P057369 | JUDICIAL CONFLICT RESOLUTION IMPROVEMENT PROJECT | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2002 | 2006 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/864271474628484131/text/000020051-20140618060205.txt | http://documents.worldbank.org/curated/en/864271474628484131/pdf/000020051-20140618060205.pdf | While the judiciary is the key partner in ensuring justice reform, the Government must be a close and committed partner in this effort.Judicial reform is a long-term process, fraught with difficulties and political sensitivities. While a LIL may be an appropriate instrument to kick start a process, gain the trust of the client, and establish rapport among key stakeholders within the country, a longer-term APL may be a more suitable instrument to address such reform.Developing a long-term policy framework for judicial reform should be the first step in any judicial reform program. Without such a clear framework, the outputs generated by the LIL may not be sustainable. It is important to keep a LIL focused on realistic objectives.Even a LIL must be designed in close consultation with donor partners, particularly those donors who are addressing similar issues in the country, if the Bank is to support country-level solutions.
P057378 | STRUCTURAL ADJUSTMENT CREDIT II | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/140711474513363340/text/000020051-20140612084131.txt | http://documents.worldbank.org/curated/en/140711474513363340/pdf/000020051-20140612084131.pdf | A flexible approach to tranche release, such as the menu-based one in this operation, is a good way to respond to the specific circumstances faced by a borrower, especially in a climate of fragile political environment. Growth is not a guarantee for a reduction in poverty and explicit poverty reduction measures should be addressed at preparation/appraisal. Even though the Bank tends to respond generously with supplemental financing in times of negative external shocks, more attention should be paid to the design and supervision of these operations to ensure that the funds are used in a cost effective way and are directed to the victims of external shocks. Privatization of large PEs requires considerable preparation, notably in its legal aspects. This is a common weakness in many Bank operations, where the complexity of transactions is underestimated, leading to long delays during project execution.
P057378 | STRUCTURAL ADJUSTMENT CREDIT II | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2003 | 2006 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/556251468299697257/text/362870MG.txt | http://documents.worldbank.org/curated/en/556251468299697257/pdf/362870MG.pdf | 7. Lessons 7.1 The following lessons emerge from the assessment. 0 The recordo ffragile political stability inMadagascarpleads for designing policy development operations ina flexible mannerbasedeither on amenu-based approach to tranche release, or preferably, or on a programmatic series o f one-tranche operations withprior actions. 0 GivenMadagascar's relatively low absorptive capacity, TA operations for supporting reforms should be well focused andhave limitedobjectives initially aimed at implementationbottlenecks. 0 New institutions inMadagascar need continued assistancefrom the donor community. Establishingnew institutions does not ensure their effective operations. Continued support i s required, for example, to strengthenthe different regulatory authorities created inthe public service sectors and competition ingeneral, as well as the business fi-amework. Similarly, continuedassistancei s needed to strengthen the judiciary, which i s a long term undertaking. 0 Consideration should be given to revive the Private Sector Support Fund, which provedsuccessful, or to set up a similar schemeto promotePSD. 0 The tax effort inMadagascar i s particularly low. Muchgreater attention than in the past should be givenby the authorities andbythe Bankto revenue mobilization andreallocationo fpublic resources for povertyreduction, without which recent improvements insocial indicatorswill not be sustained.
P057394 | GATEWAY PROJECT | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2010 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/212931475083454966/text/000020051-20140624170007.txt | http://documents.worldbank.org/curated/en/212931475083454966/pdf/000020051-20140624170007.pdf | 1. Policy statements may at times be at variance with actual priorities. The discrepancy is emphatically illustrated by the divestiture program which was eventually eliminated from the project.2. A better understanding of the political economy may be helpful in the design of reforms. For example, an analysis of the winners and losers resulting from project interventions may have cast doubt on the feasibility of both the FZ and the divestiture program.3. When implementation capacity is a possible issue, mitigation measures should be implemented in advance. There is no quick fix to the acquisition of skills.4. Inadequate implementation support by the Bank often weakens results. In the case of this project, the task team underwent constant turnovers, the implementation status was not accurately reported and corrective actions were delayed. The outcome of this project would have been in doubt irrespective of the Government's ownership and local capacity.
P057394 | GATEWAY PROJECT | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2010 | 2013 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/113771468250273699/text/788000PPAR0P050t00OUO0900Box379788B.txt | http://documents.worldbank.org/curated/en/113771468250273699/pdf/788000PPAR0P050t00OUO0900Box379788B.pdf | 7. Lessons 7.1 First, tax incentives and export development services may not be enough to attract investment in export-oriented firms. The Gambia's 2001 Free Zones Act provided financial incentives for export-oriented firms located throughout the country and for support from a new Investment Promotion and Free Zones Agency. The incentives are attractive, but clearly other factors were not in place. Over the eight-year duration of the project, only one firm opted for a free zone license to benefit from the incentives, and eventually that firm could not maintain the requisite level of exports (70 percent). The project experience does not document specific reasons for the lack of a response, but it suggests that the project was launched without adequate understanding of market conditions, the effect of The Gambia's location, and other reforms. The planned quality management audit of the Customs and Excise Department, which might have pointed to areas that would create a more favorable environment for export-oriented growth, was not undertaken. 7.2 Second, while industrial enclaves have the potential to attract private investors, location is also important. The industrial enclave's benefits in terms of improved and reliable infrastructure have not been sufficient to entice private investors to locate there. Special Investment Certificates are available to firms located throughout the country and the incentives they offer have stimulated private investment; the firms do not have to locate in the enclave to receive these incentives. The enclave's location near the airport and some 15 km from the port may not be attractive to potential investors. During the project's design phase, some five sites were considered. The site closest to the port was ruled out for environmental reasons. While it is unclear whether the enclave would have fared better at the port site, it appears that site selection was not informed by a market analysis. 7.3 Third, low relevance of some components to the objectives increases the complexity of implementation and reduces the scope for achieving the desired results. In the case of the Gambia Gateway project, the core of the project was the development of the free zone/industrial park enclave and support of investment promotion activities through the Investment Promotion and Free Zones Agency. This scope was wide enough. The addition of a divestiture component with insufficient government commitment diverted attention away from the core. At restructuring, the project considered applying unused funds previously earmarked for divestiture to support a road that had no connection with the project's objectives. Eventually, the divestiture component was replaced by a narrower component preparing the groundnut sector for divestiture, which again had limited linkage to the project's objectives and did not result in divestiture, even though it ultimately produced benefits to the groundnut sector.
P057396 | REGULATORY REFORM & PRIVATIZATION TECHNICAL ASSISTANCE | Latin America and Caribbean | Bolivia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1998 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/784151475079152876/text/000020051-20140613081456.txt | http://documents.worldbank.org/curated/en/784151475079152876/pdf/000020051-20140613081456.pdf | 1. In a politically and socially unstable environment, the focus of a project should be reduced to one or two areas of reform, accompanied by broad consultation and dissemination efforts to create ownership and enhance long-term sustainability of reforms. 2. Risk assessments need to capture developments that are critical from a political and social perspective. Appropriate risk mitigation tools need to be drafted.3. A technical assistance project needs to be flexible enough to accommodate shifts in government priorities.
P057416 | Indigenous Peoples Development Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2006 | 2007 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/149841474487359252/text/000020051-20140615100018.txt | http://documents.worldbank.org/curated/en/149841474487359252/pdf/000020051-20140615100018.pdf | In such demand-driven projects which aim to target poor beneficiary groups with weak capacities, it is essential to provide technical assistance for preparing project proposals and close assistance during the implementation stage. Such assistance should be integrated into project design. Sub-project proposals should be prepared in a participatory manner ensuring community commitment and ownership of the proposed activity from the initiation. Appointment of an independent management entity is not suitable when the project is testing a new approach in a difficult and complex context that requires project managers to establish trust with the beneficiaries, have deep commitment to the approach, and be willing to closely nurture the project. "Indigenous Peoples" are not a monolithic group. In designing a project of this nature, it would be important to consider which sub-groups would work together in a collaborative manner if the project is to be effective, although this may be politically difficult.
P057449 | STATE MODERNIZATION | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/311221474595722460/text/000020051-20140619090034.txt | http://documents.worldbank.org/curated/en/311221474595722460/pdf/000020051-20140619090034.pdf | This review concurs with the lessons derived in the ICR. In addition, it provides the following: 1. State modernization reform requires commitment from all relevant stakeholders within the process. As the experience in this project indicates, reform cannot rely on a key champion that implements reform from above. Conversely, the success of e-government reform in this project was possible because of bottom-up ownership of reforms in particular of technical staff. 2. State modernization should target key areas rather than attempting a comprehensive overhaul of the system. The experience of the First and Second Amendment showed the difficulty of attempting a widespread approach to reform. 3. Clearer outcome indicators in state modernization can focus reform efforts to achieve objectives. The SINTyS component used indicators that directly measured the impact of improved information systems which focused efforts, whereas areas in which indicators were output indicators (such as procurement) were less successful.
P057459 | Sustainable Fisheries Management Project | Latin America and Caribbean | Argentina | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2002 | 2003 | ICRR | Less than 10 million | [5 empty] | http://documents.worldbank.org/curated/en/510481474509203426/text/000020051-20140612065224.txt | http://documents.worldbank.org/curated/en/510481474509203426/pdf/000020051-20140612065224.pdf | It is probable that there are lessons for project preparation and appraisal but these are not identified in the PCN. There are certainly several questions. For example, why did the Fisheries Sub-secretariat not include the proposal in their budget submission? Did the Bank really do enough to understand the ownership issue? Can everything be put down to the macro-economic crisis?
P057473 | Indigenous Community Development LIL | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/253201474635921198/text/000020051-20140618084651.txt | http://documents.worldbank.org/curated/en/253201474635921198/pdf/000020051-20140618084651.pdf | The project provides the following lessons, some of which are taken from the ICR:The design of a solid M&E system during project preparation is fundamental for a LIL. Delaying the design until implementation starts creates the risk that M&E will never receive sufficient attention.With sufficient technical support, training, participation, and procedures relevant to decentralized decision-making, indigenous communities can manage their own development -- including the management and protection of natural resources. In this project, indigenous communities showed that they could collaborate effectively with public authorities and represent their own interests within the wider institutional and political framework.LMUs with trained staff of indigenous origin can be effective in working with their communities. Training during project preparation helps to ensure that the LMUs are operationally ready when the project begins implementation.Indigenous women do not necessarily have prominent roles or easily adapt to non-indigenous concepts of empowerment and autonomous action. A targeted strategy of awareness raising, capacity building, and creation of opportunities is needed to achieve gender goals with indigenous peoples.In projects managed by indigenous communities, financial and procurement procedures may need to be adjusted to adapt to the reality of informal markets.
P057481 | Transport Infrastructure Maintenance and Rural Access | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2005 | 2012 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/330031475096639710/text/000020051-20140625111747.txt | http://documents.worldbank.org/curated/en/330031475096639710/pdf/000020051-20140625111747.pdf | Adapted from the ICR:The development objective and corresponding indicators should be commensurate to what a small scale project can realistically attain in a large-scale system. For example, a US$ 70 million Specific Investment Loan can contribute to address road maintenance issues but cannot be expected to impact sector-wide trends. This should be adequately reflected in terms of Project design, ensuring that objectives and indicators are coherent with the Projectâ€™s capacity to deliver. Fast-track preparation Projects should include significant flexibility in their design to help them become quickly operational. Although the Project was prepared rapidly, this implied that some of the preparatory work â€“ typically: engineering designs â€“ that should have been undertaken prior to Project approval were actually carried out later in the first years of implementation. This, added to the fact that the Project Appraisal Document included a very specific list of works and activities to be undertaken under the Project implied that practically no works were executed in the first two years following effectiveness. Two significant restructuring were required, with substantial delays to implementation.The ICR draws a well know lesson on promoting donor coordination. The Government of Uruguay, through the MTOP, does not think in terms of the IDB Project, the World Bank Project, or CAFâ€™s Project, but rather in terms of a comprehensive MTOP work program, which is partially financed by different sources. This partly explains why, although the Bank did not finance many of the works originally included in the project at design stage, these were completed with alternative financing sources. This programmatic approach is particularly useful for rehabilitation and maintenance works, which require regular and predictable funding, especially when such services are contracted out to the private sector.
P057530 | Rural Development in Marginal Areas Project - APL II | Latin America and Caribbean | Mexico | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | IPF | 2000 | 2005 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/674691474396890182/text/000020051-20140613033359.txt | http://documents.worldbank.org/curated/en/674691474396890182/pdf/000020051-20140613033359.pdf | Before proceeding to the second phase of an adaptable program loan the Bank needs to fully evaluate progress made under the first phase; or, at least, to have rigorous performance triggers governing the move from Phase I to Phase II. Scaling-up too quickly can complicate project management, dilute the administrative and technical capacities directed toward implementation and may reduce the potential to innovate and learn. The incentive for implementing agencies to cooperate with the Bank will be substantially reduced when they cannot perceive a direct link between the volume of project funds and the size of their operating budget. In countries such as Mexico where external loans flow directly to the Finance Ministry with no one-for-one throughput to the agencies executing the project, the Bank may have difficulty winning support from line ministries who see no growth in their budget as a consequence of the project but who have to bear the extra transaction costs associated with following Bank procedures. These circumstances reduce the Bank's influence over project implementation.
P057531 | Basic Education Development Phase II | Latin America and Caribbean | Mexico | IBRD |  | Human Development | Education | IBRD | IPF | 2002 | 2004 | 2005 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/570841475100601628/text/000020051-20140613032646.txt | http://documents.worldbank.org/curated/en/570841475100601628/pdf/000020051-20140613032646.pdf | #NAME?
P057538 | HN ROAD RECONSTRUCTION AND IMPROVEMENT | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2001 | 2008 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Modest | http://documents.worldbank.org/curated/en/554501474635902948/text/000020051-20140618083722.txt | http://documents.worldbank.org/curated/en/554501474635902948/pdf/000020051-20140618083722.pdf | Road maintenance by micro-enterprises can be an efficient management strategy and can also contribute to social development and poverty reduction. This type of program is cost-effective and has good social and economic impacts on the beneficiary zones such as development of organizational skills and diversification of productive activities (for example 44% of the micro-enterprises sold the trash picked up from roads to recycling plants).In order achieve more reliable road maintenance funding, there needs to be a sound policy and institutional framework. Ensuring up-front the basic legislative requirements for the provision of dedicated funding is a necessary but not sufficient condition to improve maintenance funding. The project experience shows the need for prioritization within a constrained resource framework. Where there is weak capacity, an externally managed Project Coordination Unit (PCU) can help increase efficiency in project implementation by bringing in new skills that might otherwise not have been available.The reconstruction of the infrastructure damaged by hurricanes is imperative but the designs of and locations for replacement infrastructure should take into account the probability of similar future events.
P057560 | Title Registration Project | Europe and Central Asia | Armenia | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2005 | 2005 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/184941475091601106/text/000020051-20140612144045.txt | http://documents.worldbank.org/curated/en/184941475091601106/pdf/000020051-20140612144045.pdf | In a project such as this, provision should be made for dealing with a potentially large number of properties that lack proper documentation (sec. 5).Improved quality of service to customers and a substantial reduction in corruption were important in creating client confidence and stimulating registered market transactions. As a result of findings during supervision missions, a project such as this evolved from a technical operation to one that focused on a strong client orientation and the elimination of corruption. A project such as this, which involves registering 830,000 properties, should budget for supplies needed in large quantities such as file covers, paper, certificates, and blank forms.The project benefited from being implemented by a single agency with strong leadership. Experience in other countries that have divided responsibility has been less successful.Automation is not necessary for providing client-friendly service, such as a one-stop window or one-day turn-around on routine services. Instead, moving aggressively toward client-oriented services is more important to increased system efficiency and user acceptance than is the transition to full automation.
P057570 | Bhutan - Urban Development Project | South Asia | Bhutan | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/312341475097361657/text/000020051-20140617140307.txt | http://documents.worldbank.org/curated/en/312341475097361657/pdf/000020051-20140617140307.pdf | To intensify project engagement with local governments, urban development projects should deploy sufficient human and financial resources and adequate reporting mechanisms to ensure that they can bring their support even to remote towns--among the poorest and the most in need--where access may be difficult.Especially when implementation is decentralized, responsibilities at each level should be made very clear and their assignment should take into account capacity constraints at the local level especially.Even when implemented by local governments, urban development projects should aim to strengthen the monitoring and evaluation capabilities of central government institutions that have to guide and oversee decentralized units.The design of urban development projects should ensure that they are coherent with the prevailing cultural norms. In Bhutan, for instance, this meant relaxing a traditional grid layout for streets in new housing areas, that was anathema to many Bhutanese, even though a such a layout may lead to a efficient land use.
P057570 | Bhutan - Urban Development Project | South Asia | Bhutan | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2006 | 2011 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/585511468201548408/text/620720PPAR0P050e0only0900BOX361491B.txt | http://documents.worldbank.org/curated/en/585511468201548408/pdf/620720PPAR0P050e0only0900BOX361491B.pdf | 6. Lessons 6.1 To provide assistance effectively to ten towns (or more), an operation requires a wholesale project design that provides Bank support through a country intermediary. The Bank cannot provide hands-on retail assistance to so many municipalities, especially with Bhutan's challenging logistics for access. With no strong country-level intermediary, the scope of a retail project should be limited to fewer towns. 6.2 The project experience clearly demonstrates the need for building greater capacity for local authorities to assess the efficiency of their investments, especially to help them avoid losses from sub-projects that, having incurred considerable costs, are left idle and thereby generating few or no benefits. 6.3 Baselines must be clearly drawn and identified at appraisal not only to make final evaluation more robust, but also to be sure that a project is focused clearly at the outset upon priority areas of need highlighted by the baseline data. 6.4 As urbanization takes root and accelerates as it is doing in Bhutan, it is important for each city and town to prepare and implement its own urban plan. The plan should assess its potential for developing efficiently within any physical constraints it might face, while respecting prevailing cultural values in land use planning and layouts. 6.5 Public health benefits may be achieved through improved urban infrastructure and services even when these services are not operating at peak efficiencyâ€”when piped water supply is interrupted, for example. But evaluations of these impacts should always consider other possible causes of the public health impacts to make convincing attribution to the operation under review. They also need count upon a decent M&E system to reliably measure the baselines and the results obtained.
P057578 | EGAT-INV PROG SUP PJ | East Asia and Pacific | Thailand | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 1999 | 2009 | 2005 | ICRR |  | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/894791474512726930/text/000020051-20140612153732.txt | http://documents.worldbank.org/curated/en/894791474512726930/pdf/000020051-20140612153732.pdf | Â· A World Bank Partial Credit Guarantee could be a useful instrument in securing favorable terms for the Borrower, provided it is applied when market conditions are appropriate and the Borrowerâ€™s own credit rating is sound.Â· Sudden economic and financial crises in a country could negatively impact power demand and void development plans. Under such circumstances, the Bank would do well to take a flexible approach to Government actions and compliance with covenants. At the same time, utilities need to exercise great financial discipline by cutting down operating expenses, dropping unnecessary investments and carrying on only indispensable investments needed to meet required service. Â· The Bank could best play the role of advisor and facilitator for countries that have already embarked on significant power sector reforms and should recognize that restructuring proposals cannot be cast in stone and could change as Government and utility thinking evolves.
P057598 | PH-RURAL FINANCE III | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/621301474630439717/text/000020051-20140619085037.txt | http://documents.worldbank.org/curated/en/621301474630439717/pdf/000020051-20140619085037.pdf | The ICR lists the following lessons:(a) Using a sound wholesale financial institution with a strong accreditation unit to appraise participating financial institutions (PFIs), rather than having the Bank review each one, can work satisfactorily in a system where there are many potential PFIs.(b) To enable more banks to participate in the project, the PFIs accreditation criteria (and particularlythe cut-off points) need to be periodically reviewed and adjusted to market conditions, andconditional accreditation procedures together with adequate action plans should be introduced at the design stage.(c) This type of wholesale finance project is a suitable mechanism for disbursing a relatively large number of loans quickly to the private sector without placing much burden on government.In addition, IEG proposes a further lesson:(d) Projects that are listed as targeted interventions and include poverty reduction among their objectives need to collect the evidence to demonstrate poverty impact; this expectation must be all the greater when--as in this case--the project has been preceded by related operations thereby affording sufficient time for impact to be assessed and for evaluation arrangements to be made.
P057598 | PH-RURAL FINANCE III | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2008 | 2009 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/518251468295232312/text/487610PPAR0Phi162B01PUBLIC071221091.txt | http://documents.worldbank.org/curated/en/518251468295232312/pdf/487610PPAR0Phi162B01PUBLIC071221091.pdf | 4. Findingsand Lessons 4.1 This was a traditional line o fcredit project channeled through a government owned wholesale bank, not the type o f finance project generally designedtoday. However, it i s a case o f an efficient publicly owned banking institution satisfactorily wholesaling credit to the rural sector. Inthe absence o f the Asian financial crisis, it would have been difficult to justify the predominant line o f credit focus. One would have expected more focus on capacity building o f intermediaryandmicrofinance institutions, onbuildingabsorptive capacity and demand, and arguably more attention to further leveling o f the playing field for competitors. However, injecting moderate amounts o f medium and longer-term capital into the rural sector was clearly very important at the time and LBP was a strong, available and proven vehicle. 4.2 Itwould havehelped strategic decisions ifthe Bank hadbetter understood several issues including\. the place o f LBP within the sector with respect to the levelness o f the playing field and the probable implicit net LBP subsidies and competitive advantages through their captive deposits and various other government programs; and, more broadly, the role o f other government and nongovernment bankingand microfinance institutions inchanneling different types o f fundingto the sector. 23 4.3 Itwould also have helped, particularly given the current circumstances andthe need for employment creation, to better understand data related to the efficiency o f employment generation from different types o f enterprise and the growth and equity impacts o f that employment. The apparent wide rangeso f costs perjob created and financial returns offer fertile ground for analysis. This i s particularly so inan only moderately targeted project design that seems to exhibit some ambivalence about whether to lendto the poor or the less poor, where to place the boundaries o f non-rural, and whether to lendfor large or small enterprises. 22 Their website is indicative oftheir reporting and information sharingcapacity. 23 The Bank Regionpoints out that the SubsidyDependencyIndex for LBP was closely monitored and improved over time and now shows anegativesubsidy. This is correct. However, IEG's concernlay more inthe possible implicit advantagesthat LBP held over the project period with its captive government services. Suchadvantages do not show up inSDIs. They also argue that the combination of wholesaleandretail lending worked well to both encourage private sector bank expansionand to reachremoteareas. IEG has concerns, as do some other players and academics, about the conflict of interest inbeing awholesaler and aretailer competitor to those receiving wholesale funds, an issue referred to inthe World Bank's operationalpolicy. 4.4 The utilization o f LBP as the wholesale bank was sound at the time. However, as the rural financial sector has beenevolving rapidly over the period o f the project, circumstances have changed. Ifthe Bank were to support a further rural finance project, the role o f LBP inthe sector would warrant re-examination although it would remain a serious contender for support because o f its exceptional capacity and ongoing attentionto enhancing efficiency and modernization. But deeper analysis may show it to have significant net benefits24over competitors conferredby its government-owned status. This may be less healthy inthe future for growth inthe rural finance sector as a whole. On the other hand, the judgment should not be one o f principle but of the effectiveness and efficiency facts, not all o f which were sufficiently understood at appraisal. 4.5 The main lessons are the following\.25 (9 A government-owned bank within a generally sound enabling environment canreach out effectively and efficiently to rural areas through wholesale operations when other private players are still reluctant to take such risks ina challenging sector and particularly at a challenging economic time. Notwithstanding government ownership, they can be independent enough to also serve as a useful counterbalance to government and political pressures towards unsustainable credit policies. (ii) Itis importantina rural finance project involving a government owned bank, to analyze explicit and implicit subsidies for both the institution inquestion andthe sector as a whole to ascertain the levelness o f the playing field for non-government entrants. Inthis case, it i s still not clear what advantages (or perhaps even net handicaps) LBP holds and what this might meanfor the optimal evolution o f a competitive sector over the coming decade. (iii)When poverty alleviation i s stated as a micro-finance objective it i s difficult to assess achievement without some form o f beneficiary impact assessment eventhough, with 24 We use the term net benefits advisedly since it i s clear that LBP's governmentownership status conferson it significant costs as well as significant benefits. Without substantial study is not clear how balancedor unbalanced these costs and benefitsmay be. 25 It is worth recalling the main lessons of the IEG assessment of Rural FinanceIand 11. Summarized, these were (inparenthesis comments ofthis current assessment are added)\. (i) focus shouldbe as narrow as possibleto Project achieve the objectivesbut broad enoughto includeelements important to long-run sustainability. The narrowing of focus that took place betweenRFI and RFII was good inthat it was more realistic about what could be accomplished.However, it was badto the extent that it avoided dealingwith policies potentially important for project success. (Still a dilemma with trade-offs, but RFIIIprobably erred somewhaton beingtoo narrow in microfinance/capacitybuilding.) (ii) Financial liberalization is more thanjust the controlling of interestrates. This refers to the lack of a level playing field with subsidizedinterest rates for certain classes of borrowersand the BSP continuedintervention inbranching decisionsby banks that satisfiedregulatory requirements.(Branching decisions now less constrainedbut this assessment still urges better analysis ofthe levelnessofthe playing field with respect to LBP role.) (iii) sustainability of credit operationsrequires ongoing access to hnding and credit projects The shouldincludeincentivesand monitor and promotethis. This refers to the needfor more attentionto rewarding depositmobilization by PFIs. (Still arguably an area for greater attentioninrural areas but electronic banking is rapidly moving inthis direction to ease deposit making.) (iv) Poverty alleviation and environmentalobjectives may exceed the reachof aproject designed to meet market based demand driven credit needs. (The evidence suggests that environmentalobjectives were quite well achievedunder RFIIIsuggestingthat such an objective did not exceed the reachofthe project. Poverty alleviation to amodest level probably also didnot exceedthe reachofthe project and probably occurred but was inadequatelymeasured.) rural finance, demonstrating causation from such assessmentsi s difficult. Such assessmentscan also contribute evidence for the designo f subsequent phases. (iv)There is a need for better coordination betweenthe Bank and IFC and resolution of disputedareas ofturfbefore preparation work on a potential project. The Guidelines may need tightening particularly with respect to mode andtiming o f coordination and respective policy roles and perhaps even some arbitration process. The Guidelinesstill seem to leave considerable discretion to staff.26 26 This lessonwas inspired by an event after RFIIIclosed(see paragraph3.48 above).
P057601 | VE PUBLIC EXPENDITURE MANAGEMENT | Latin America and Caribbean | Venezuela, Republica Bolivariana de | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1999 | 2006 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/235941474505101485/text/000020051-20140618053417.txt | http://documents.worldbank.org/curated/en/235941474505101485/pdf/000020051-20140618053417.pdf | The value of institutional improvments in one part of the public sector is diminished if the quality of institutions declines seriously in other parts of the public sector, particularly if the latter are gaining substantially increased resources.
P057602 | RY URBAN WTR SUPPLY & SANITATION APL | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2011 | 2013 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/407721474905408790/text/000020051-20140624213150.txt | http://documents.worldbank.org/curated/en/407721474905408790/pdf/000020051-20140624213150.pdf | The following lessons are taken from the ICR with some adaptation. Expanding water supply networks when the quantity of water being fed into the system is declining results in under-used infrastructure, and provides only partial benefits. In the case of this project, the issue of water scarcity was given insufficient attention, and other water resource development options, such as rainwater collection, were not given full consideration. In situations of serious water scarcity (like that in Yemen), rehabilitation of networks - through replacement of pipes and installation of water meters â€“ is likely to have limited effect as less water is flowing through the pipes.To enhance service delivery, both improvements in infrastructure and institutional development (including capacity building and enhanced governance) are necessary, especially in countries with weak capacity. Attracting international private operators to a country where they have not been present before can be difficult. The perception by the private sector of the security situation, the quality of governance, the reliability of the institutional framework, the projectâ€™s size, and expected financial benefits compared to the commercial investment, all require careful assessment.Achieving full operating cost recovery is a frequent objective in Bank funded water sector projects, but one which is rarely achieved in practice. One of the main reasons is that cost recovery depends on the tariff policy over which Bank funded activities may have little influence. Full operating cost recovery is especially difficult to attain in the short term (that is, during the life of a typical project).Declaring a project effective before all key implementation arrangements are in place is likely to exacerbate delays.
P057649 | Rural Poverty Reduction Project - Bahia | Latin America and Caribbean | Brazil | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2001 | 2005 | 2006 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/620781475092872906/text/000020051-20140613085010.txt | http://documents.worldbank.org/curated/en/620781475092872906/pdf/000020051-20140613085010.pdf | Based on the ICR the main lessons are:(1) Greater alignment of community investments with U.N. Human Development Index (HDI ) is both rational and efficient. Bahia's goal is to increase HDI from 0.688 to the median HDI for Brazil (0.766) by 2020, which serves as a unifying goal for public investment especially in poverty reduction.The Project was able to successfully target separate cohorts of municipalities defined by relative HDI with differentiated financing. The poorest municipalities received an average R$574,000 and the remaining municipalities averaged R$422,000 each. The vast majority of subprojects benefited municipalities with HDI-M of 0.417 or below. (2) Scaling up the Rural Poverty Reduction Program's impact on rural incomes through productive investments remains a major challenge. Demand from communities for employment and income-generating investments is high and there is an important challenge to scale up the productive component of this program/project to the same extent as has been achieved program-wide with infrastructure and social capital.(3) If left unresolved, government regulation and complex bureaucratic procedures, such as obtaining Environmental Permits, can distort demand for certain types of subprojects (basic rural water supply systems, small dams/reservoirs and electrification subprojects). Prior to negotiating a simplified license, the project found that communities, upon realizing the difficulties associated with obtaining environmental permits, were directing their subproject proposals to investments which did not require them.
P057653 | FUNDESCOLA IIIA (THIRD SCHOOL IMPROVEMENT PROJECT) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2002 | 2008 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/895961474503784932/text/000020051-20140619104846.txt | http://documents.worldbank.org/curated/en/895961474503784932/pdf/000020051-20140619104846.pdf | It is important to link institutional and managerial improvements to learning outcomes. If learning outcomes deteriorate while management-oriented activities are implemented, perhaps these activities do not directly help students acquire the necessary knowledge.In projects that heavily involve stakeholders, it is important to maintain a momentum and a continuous rhythm of implementation. If procurement or other difficulties result in work stoppages for extended periods of time, it may be difficult to regain trust and involvement of stakeholders. Pedagogical models developed to improve the performance of low-income students must be applied consistently and have a clear rationale for effectiveness. Otherwise there is a risk of losing the audience after a brief try to the program.
P057665 | FAMILY HEALTH EXTENSION PROGRAM | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2002 | 2007 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/499081474506276185/text/000020051-20140618085206.txt | http://documents.worldbank.org/curated/en/499081474506276185/pdf/000020051-20140618085206.pdf | The pool funding approach: (i) allows for a single procurement, financial management and disbursement system, reducing transaction costs of Bank financing and focusing on improvements to Government systems; (ii) directs Government and Bank efforts to technical and fiduciary oversight, monitoring and strengthening of national program vs. project; (iii) facilitates a division of responsibility among Bank experts (technical vs. fiduciary) and a more efficient use of their expertise; (iv) creates the vehicle to link national and Bank financing to results.Support to multiple decentralized entities with varying institutional and technical capacities can be greatly facilitated by: the establishment and utilization of indicators for assessing and monitoring their technical and fiduciary capacity; the provision of technical and fiduciary backstopping, as needed, through regular supervision and other training and pedagogical support; and special support mechanisms for lowest capacity entities. The success of a family health program, especially in a decentralized environment, depends on the capacity of family health teams to respond to patient demand. The design and implementation of a human resources action plan that fosters the stability and sustainability of family health physicians is crucial in this regard, as are quality certification systems, the linking of family health teams to technical resources, and the availability of essential pharmaceuticals for poor populations.The importance of technical backstopping of decentralized entities cannot be overstated, pointing to the need for ensuring stability of personnel at the federal level responsible for supporting and guiding states and municipalities, especially in a reform mode.
P057665 | FAMILY HEALTH EXTENSION PROGRAM | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2002 | 2007 | 2011 | PPAR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/530711468218383347/text/625710PPAR00Ar0e0only0900BOX361497B.txt | http://documents.worldbank.org/curated/en/530711468218383347/pdf/625710PPAR00Ar0e0only0900BOX361497B.pdf | 7. Conclusions and Lessons 7.1 An important finding from this three-project assessment is the comprehensive and innovative approach used by IBRD to support existing government health reform programs. Reforms included institution building, legal changes, reorganization of the care process, training of medical and administrative staff, modification of financial incentive framework, data collection and analysis, audits of performance data, and regular feed-back of results to government units and providers. These combined measures positively affected the provision of basic health care, particularly for mothers and children who seek care in public health facilities. Other factors contributed to improvements, including a budget increase for basic care and cross-sector collaboration with social protection programs to enhance health reforms. 7.2 Both countries aimed to improve health outcomes and system performance with the reforms. While the peer-reviewed literature identified various factors that have contributed to decreasing infant mortality rates â€“ in addition to improved access to family medicine; both countries made substantial progress in advancing the health reforms. In Argentina, MCHIP enrollment increased to more than 80 percent of the target population, and the Brazilian PSF program covers now 35 percent of the population in the 187 municipalities. Several studies conducted indicate that PSF improved service use among patients compared to the traditional primary care model. Findings from Argentina point to increase in service use among MCHIP members. 7.3 Modifying the incentive framework required upfront investment in data collection and analysis. In both countries IBRD disbursed earmarked health funds tied to tangible results to the government to target existing health reform programs. The central governments applied the same approach to transfer additional health funds tied to performance targets to the local governments. The local governments used the additional financing to strengthen the provision of public health care in low-income areas. This modified financing mechanism required upfront investment in the validity of data collection and analysis to define the payment. 7.4 The Bank-supported reforms improved the data flow in decentralized health systems. Decentralized health systems struggle with the information flow. Often central governments are not informed about health performance in provinces and municipalities. Both countries used their health reforms to address this data-flow issue. The central governments receive information from the local governments on progress in specific indicators (for example the MCHIP enrollment, the number of PSF units joining the Conversion Program, provincial level results for health indicators, administrative compliance in health authorities). Reliable information systems, analysis and independent audits are prerequisites for allocating resources based on population needs and service use. 7.5 Both countries improved transparency, management and accountability in the public health sectors, including\. Â· MCHIP in Argentina informed each provider about performance results such that they could improve treatment of patients, and information was made available to all stakeholders; Â· Brazilian municipalities updated their financial management including quality of the planning process, compliance with procurement regulations, timely accounting, and audit processes; Â· Both countries improved capacity-building for health staff as performance results were used for identifying training needs to improve treatment compliance. 7.6 There are lessons to be learned from Argentina and Brazil. 7.7 First, substantial upfront investments are needed in data and provider readiness if a country would like to introduce financial incentives to stimulate sector performance\. Â· The APL1 in Argentina invested upfront in IT and software at central and provincial health authorities and facilities to collect and computerize patient level data on treatment compliance. Independent auditors verified the validity and reliability of data collection. Results from data analysis are reported back to providers and local governments for actions. The consistent assessment methodology (indicators, scoring system, and audits) is credible for all stakeholders. Â· Both countries upgraded provider readiness. They invested in treatment standards against which performance compliance is assessed, training of medical staff, and additional medical staff. Health facilities received additional medical equipment, material and pharmaceuticals to implement treatment standards. Â· In Argentina purchaser capacity was built in national and provincial government purchasing units MCHIP. These units write and sign performance contracts with providers, receive data for analysis of indicator results and calculate the financial amount to be paid to providers and/or local governments. They contract and supervise work of the independent audit firm, and can also be in charge of financial management. Â· Both countries had to develop and implement communication strategies to inform patients about reforms. 7.8 Second, fiscal transfers tied to targets highlight the need for strong institutional foundations. These include budget management, accounting, monitoring, financial management, managerial capacity, independent audits of performance information, incentives that emphasize dialogue between local and central governments rather than control, and modest starts. Brazil started modestly with simple measures including process and (intermediary) outcome indicators that first aimed to set up the fiduciary framework. The MCHIP in Argentina shows that targets should be defined on the basis of room for improvement. The initial indicator payment of 4 percent for full target achieved was difficult to achieve for several provinces and caused low disbursement; thus, a gradual payment was introduced to allow paying for partial achievement of targets. The MCHIP timely adjusted targets when goals were fulfilled. In the future, when new indicators will be introduced, old indicators and targets need to be monitored to preserve results. 7.9 Third, using outcomes as a result indicator to condition disbursement is highly problematic given attribution problems related to measurement (for example the mortality rate reduction, improved health status). Argentina is using several health status indicators to define the conditioned fiscal transfer to provinces, including weight and APGAR score of newborns. The attribution of these results to MCHIP is problematic. Whether results-linked financing has an impact on health outcomes and the provision of care is unknown. There is no study that identifies the marginal effect of the results-based payment over other factors. 7.10 Fourth, pooled funding approaches of Bank and Government finances can increase transaction costs for Governments. Although Government systems are used for fiduciary tasks, Bank rules still apply. Depending on the country context, institutional and governance adjustments may be needed. The Bank still conducts fiduciary assessments and requests procurement plans to implement the program through the Government, financial and performance analysis of program execution, and program audits. Detailed total and unit cost analysis will be needed to define the disbursement criteria into the program. If municipalities are the final recipients of pooled funds, administrative staff needs to be trained on planning and budgeting to be able to access pooled funds in a timely manner. 7.11 Fifth, political changes and resulting turnovers in government administrations can lead to delays and uncertainties in implementation. Substantial reforms such as financial incentives linked to results require broad political support and country ownership that goes beyond the Minister of Health. Political will is needed to implement the consequences of poor performance (for example withhold or cut back funds) otherwise the effectiveness of the financial incentives is diluted.
P057692 | Second Magdalena Medio Regional Development Project | Latin America and Caribbean | Colombia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2002 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/582111474562955712/text/000020051-20140613030239.txt | http://documents.worldbank.org/curated/en/582111474562955712/pdf/000020051-20140613030239.pdf | Based on the ICR, this Review highlights the following lessons:1. M&E is critical, especially in LILs and second LILs. Testing cannot yield its full benefits unless impacts are systematically evaluated and implications carefully drawn. 2. Community building cannot be rushed. Process, institutional, and behavioral change take time to materialize and may need support over the long haul.3. Productive activities are likely to fail unless markets for the outputs are assured. Just supporting front-end inputs is likely to be inadequate. Sound market analysis is critical.4. Systematic attention to safeguard issues is critical in design, implementation, and M&E.5. Institutional impacts should be carefully monitored to avoid negative effects. Process, institutional, and behavioral objectives need systematic M&E (including through qualitative techniques). M&E for such objectives needs to be carefully designed and implemented to determine pros and cons of various approaches and make mid-course changes as necessary.
P057704 | PORT SECTOR REFORM | Middle East and North Africa | Egypt, Arab Republic of | IBRD |  | Infrastructure | Transport | IDA | IPF | 1998 | 2000 | 2001 | ICRR | Less than 10 million |  | Unsatisfactory |  |  |  | http://documents.worldbank.org/curated/en/713551474650946484/text/000020051-20140529065232.txt | http://documents.worldbank.org/curated/en/713551474650946484/pdf/000020051-20140529065232.pdf | If the proposed credit has a large technical assistance component, it is wise to gauge whether support for the opearation extends beyond the implementing agency.
P057731 | Metro Manila Urban Transport Integration Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/323211474854938950/text/000020051-20140625055043.txt | http://documents.worldbank.org/curated/en/323211474854938950/pdf/000020051-20140625055043.pdf | The Project Development Objective (PDO) should be well articulated and realistic and should be amenable to M but coordination mechanisms with other agencies will be necessary. This project involved several implementing agencies, each with their own strengths (e.g., DPWH for those involving complex designs, LGUs for secondary roads, MMDA for footbridges and simple works, etc.), but also requiring greater coordination among them. Restructuring of project objectives/components should be done sooner rather than later, based on a realistic assessment of feedback from the supervision process. In this project, both the Bank and the Borrower could have restructured the project components earlier than they did if they had picked up signals on implementation bottlenecks and altered several components through an effective supervision process.The need to consult/involve beneficiaries and other stakeholders in an appropriate manner to improve project design, implementation and M&E cannot be overemphasized. In this project, most of the committees or teams envisioned for project preparation and implementation were either not organized or were non-functional. These groups could have played a useful and even a crucial role in resolving issues that negatively affected implementation, particularly concerning resettlement and right-of-way issues.
P057761 | INFRASTRUCTURE SERVICES | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/576101475074178653/text/000020051-20140626113413.txt | http://documents.worldbank.org/curated/en/576101475074178653/pdf/000020051-20140626113413.pdf | The following are lessons derived from the ICR with minor modifications:- Readiness for implementation at approval is critical for achievement of implementation schedules. This Project suffered delays because feasibility studies were not completed and implementation arrangements were not fully clarified and in place at approval.- The involvement of implementing entities during project preparation and appraisal will positively contribute to quality and timeliness of implementation. This Project was prepared by the Ministry of Economic Planning and Development, and it was later devolved to the sector agencies and the regional water boards for implementation. This caused delays in recognition of problems with the feasibility studies and took time from the implementation schedule for the other agencies to become familiar with Bank requirements.- Multi-sectoral projects such as the Malawi Infrastructure Services Project are useful to deliver service improvements in under-serviced rural market areas. The Government of Malawi found the project experience useful in the delivery of comprehensive development. At the same time, such projects require additional efforts of coordination and communications among the sector agencies within the Government, and the sector departments within the Bank. - The Bank's performance during preparation and implementation is important to achieve development outcomes particularly for projects set in weaker institutional environments and for multi-sector work. The Bank's unsatisfactory performance prior to the mid-term review and the lack of effective follow up sent the wrong signal to the Government which was not able to request support or guidance from the Bank. The Bank's' recognition of the problems at mid-term and its actions to correct the situation was met likewise by the Government leading to progress in implementation and achievement of objectives. The following lesson is derived from the Borrowerâ€™s ICR:- Training implementing agencies in comprehensive project and contract management, in addition to the fiduciary and safeguards training can help build long term institutional capacity to ensure successful projects. The Government learned by doing throughout project implementation, an experience that is necessary but not sufficient for efficient project implementation.
P057767 | Technical Assistance for Institutional & Regulatory Reform for Private Sector Development Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/146351474627978649/text/000020051-20140617132900.txt | http://documents.worldbank.org/curated/en/146351474627978649/pdf/000020051-20140617132900.pdf | (i) Flexibility built into the design of complex institutional building projects enables efficient and effective adjustments during project implementation in response to a rapidly evolving operational and political environment, as well as to the needs of the stakeholder agencies;(ii) Creating efficient institutional arrangements is a critical factor in implementing a complex technical assistance program and for maximizing its impact along lines of implementation, coordination, and management;(iii) Borrower familiarization with Bank procurement rules can mitigate operational risks associated with project implementation and procurement;(iv) Technical assistance loans linked to policy loans are affected by the successes and failures in implementation of the related policy loans, which underlies the building of flexibility is such programs.
P057770 | Cultural Heritage Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2002 | 2009 | 2009 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/813331474652363456/text/000146597-20140619153626.txt | http://documents.worldbank.org/curated/en/813331474652363456/pdf/000146597-20140619153626.pdf | The ICR draws many useful findings and lessons from the experience of CHLIL. Salient among them are:The Bank should include a cultural resource specialist as a core team member to engage with technical assistance consultants and maximize project impact; The Monitoring and Evaluation framework should include indicators for cross-cutting themes as these aspects of outcomes are often omitted from indicators for specific components or objectives; and Procurement for all projects in Ethiopia is a problem, but especially for cultural heritage projects, because it is specialized and the number of suppliers is limited. The Bank's and national guidelines lack the flexibility to cater for this sector. Adapted procurement thresholds and methods should be incorporated for these projects.
P057813 | Judicial Reform Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2006 | 2008 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/757101474590684669/text/000020051-20140618075632.txt | http://documents.worldbank.org/curated/en/757101474590684669/pdf/000020051-20140618075632.pdf | 1. Outcomes of projects with overly broad objectives, not equipped with measurable performance indicators, can be difficult to relate to project outputs. 2. In cases when M&E system was not properly designed at the appraisal stage, failure to take corrective steps during implementation undermines eventual relevance of the project. 3. Failure to revise project objectives and components, due to changes in country circumstances during the course of the loan, is likely to result in inefficiencies.4. Improvements in overall governance environment due to unforeseen positive political externalities (e.g. changes in government, revolutions leading to stronger ownership of reforms and commitment to change) can be erroneously attributed to unrelated lending activities.
P057813 | Judicial Reform Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2006 | 2009 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/257411468032037102/text/468320PPAR0P051b010020090Box334133B.txt | http://documents.worldbank.org/curated/en/257411468032037102/pdf/468320PPAR0P051b010020090Box334133B.pdf | 5. Findingsand Lessons 5.1 Georgia's experience with reform shows again that Bank's support canbe effective inpromoting and supporting change ifthe authorities are committed. Providing support when the will is absent may retardrather than accelerate reform, as the authorities can muddlethrough their problems. When countries need serious reform the Bank should focus onthe fundamental problems andmake sure that its conditions leadto results, not to promises o f future reform. Ifthere is no will or commitment to tackle the difficult problems, the Bank should consider discontinuing lending. 5.2 Thejudicial reformproject deliveredmost o fits inputsbut didnot achieve the higher level objectives it sought, puttinginto question the validity o f its design. Two lessons emerge from this. First, changing institutions inthejudiciary demands interventionsbeyondthose that the project supported. Inparticular, the goal of an independentjudiciary requires continuous political will andcommitment from the highest level o f country authorities. Second, projects that support upgradinginfrastructure (court buildings, computer hardwareand software), andtrainingjudiciary staff could serve a useful purpose. Inorder to evaluate them it i s necessary to define the problem properly, to identifythe interventionsthat deal with it, and to design performance indicators tailored to evaluate ifthe interventionshave solved the problem. 5.3 Complex regulations makeit difficult to bringchange to organizations andreduce corruption. They increase the power o f discretion, encourage corruption, and strengthen the oppositionto change. Customs andtax administrations inGeorgia exemplify this problem. After the authorities simplified the tax system and customs procedures it became easier to deal with the administrative problems incustoms and taxes because inspectors had lost some o ftheir discretionary power. Before embarking on plans to improve the administration o f organizations where discretion reigns, the Bank should assess how to weaken that power by simplifyingregulations and legislations. 5.4 Banksupport fails when itusesthe wrong instrument (andtheory) to solve a problem. The fight against corruption exemplifies this lesson. The Bank demanded from the government an anti-corruption planandthe establishment o f an anti-corruption commission. The government complied but corruption thrived in 1998-2003. In 2004, a new government took effective actions to eradicate corruption (e.g., traffic police) and slashed regulations. This experience suggests that (a) creating an agency does not guarantee that the government will fight corruption and succeed; and (b) streamlining and simplifying regulations can be more powerful to fight corruption than creating organizations and commissions. 5.5 More lessons on fighting corruption are the following. First, Georgia eliminated egregious cases o f corruption with simple measures, not with an anti-corruption watchdog or an anti-corruption plan. Second, enforcement is hndamental to fight corruption. The Georgian government has done extremely well on this front. As a byproduct it has shown that it didnot need specific anti-corruption legislation to succeed.
P057814 | Reform Support Credit (former SAC4) | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2004 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/626501474490376448/text/000020051-20140613060538.txt | http://documents.worldbank.org/curated/en/626501474490376448/pdf/000020051-20140613060538.pdf | To establish impact and determine the effectiveness of Bank assistance, the Bank needs to design clear, monitorable and measurable impact indicators for those adjustment loans or credits that are single tranche loans, and where conditions must be met before Board presentation.
P057814 | Reform Support Credit (former SAC4) | Europe and Central Asia | Georgia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2004 | 2005 | 2009 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/257411468032037102/text/468320PPAR0P051b010020090Box334133B.txt | http://documents.worldbank.org/curated/en/257411468032037102/pdf/468320PPAR0P051b010020090Box334133B.pdf | 5. Findingsand Lessons 5.1 Georgia's experience with reform shows again that Bank's support canbe effective inpromoting and supporting change ifthe authorities are committed. Providing support when the will is absent may retardrather than accelerate reform, as the authorities can muddlethrough their problems. When countries need serious reform the Bank should focus onthe fundamental problems andmake sure that its conditions leadto results, not to promises o f future reform. Ifthere is no will or commitment to tackle the difficult problems, the Bank should consider discontinuing lending. 5.2 Thejudicial reformproject deliveredmost o fits inputsbut didnot achieve the higher level objectives it sought, puttinginto question the validity o f its design. Two lessons emerge from this. First, changing institutions inthejudiciary demands interventionsbeyondthose that the project supported. Inparticular, the goal of an independentjudiciary requires continuous political will andcommitment from the highest level o f country authorities. Second, projects that support upgradinginfrastructure (court buildings, computer hardwareand software), andtrainingjudiciary staff could serve a useful purpose. Inorder to evaluate them it i s necessary to define the problem properly, to identifythe interventionsthat deal with it, and to design performance indicators tailored to evaluate ifthe interventionshave solved the problem. 5.3 Complex regulations makeit difficult to bringchange to organizations andreduce corruption. They increase the power o f discretion, encourage corruption, and strengthen the oppositionto change. Customs andtax administrations inGeorgia exemplify this problem. After the authorities simplified the tax system and customs procedures it became easier to deal with the administrative problems incustoms and taxes because inspectors had lost some o ftheir discretionary power. Before embarking on plans to improve the administration o f organizations where discretion reigns, the Bank should assess how to weaken that power by simplifyingregulations and legislations. 5.4 Banksupport fails when itusesthe wrong instrument (andtheory) to solve a problem. The fight against corruption exemplifies this lesson. The Bank demanded from the government an anti-corruption planandthe establishment o f an anti-corruption commission. The government complied but corruption thrived in 1998-2003. In 2004, a new government took effective actions to eradicate corruption (e.g., traffic police) and slashed regulations. This experience suggests that (a) creating an agency does not guarantee that the government will fight corruption and succeed; and (b) streamlining and simplifying regulations can be more powerful to fight corruption than creating organizations and commissions. 5.5 More lessons on fighting corruption are the following. First, Georgia eliminated egregious cases o f corruption with simple measures, not with an anti-corruption watchdog or an anti-corruption plan. Second, enforcement is hndamental to fight corruption. The Georgian government has done extremely well on this front. As a byproduct it has shown that it didnot need specific anti-corruption legislation to succeed.
P057815 | State Tax Service Modernization Project (APL #1) | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2003 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/933841474560288240/text/000020051-20140625234327.txt | http://documents.worldbank.org/curated/en/933841474560288240/pdf/000020051-20140625234327.pdf | The ICR identified a number of relevant lessons from the project implementation, but three among them stand out: It pays off to embed the project implementation unit (PIU) into a Government departmental service: The PIU was staffed with civil servants as opposed to consultants hired with project funds. This arrangement increased project ownership and change management capacities within the Government, and improved the transfer of knowledge developed by the project to operational business units within the PIU. Since the PIU was part of the government, this has not only enhanced the sustainability of project achievements, but it will also enable government services to deepen reform efforts and provide coordination among all modernization activities independent of the source of financing. Realism and simplicity in project design: When designing a project, it is better to set realistic objectives, and identify targets and indicators which are closely linked to the intermediate outcomes and the activities supported by the project. Project supervision should be multi-purpose: Combining policy, operational and technical advice in Bank supervision support is central to operating in difficult implementing environments. Reforming the tax system of an IBRD client is a major task. The relative success achieved by this project stemmed from the combination of expertise from the Bank and other development partners such as the US Treasury in the provision of just-in-time advice on policy, operational(procurement) and technical (e-filing software) issues.
P057818 | Financial Sector Adjustment Credit (FSAC) | Europe and Central Asia | Albania | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2002 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/962131474909214787/text/000020051-20140613053427.txt | http://documents.worldbank.org/curated/en/962131474909214787/pdf/000020051-20140613053427.pdf | Technical assistance greatly enhances reform progress, especially when it is available prior to the inception of a policy-based operation--The provision of timely TA through the Financial Sector Institution Building and Technical Assistance Credit was extremely helpful in preparing the up-front conditionality of the FSAC. The availability of TA also helped get the government involved early.Clear and monitorable performance indicators facilitated achievement of the project development objectives
P057833 | Air Quality Management Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2008 | 2009 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/401161475099674074/text/000020051-20140619103645.txt | http://documents.worldbank.org/curated/en/401161475099674074/pdf/000020051-20140619103645.pdf | Among the lessons illustrated or reinforced by the experience of this project are the following: (1) Coordinated action in a number of sectors and by a range of institutions is required to achieve adequate urban air quality management; addressing only one pollution source, even if it is the most important one, will only resolve part of the problem. (2) Firm political will and adequate technical and institutional capacity are key to successful efforts to combat urban air pollution; defining fuel and vehicle standards and enhancing public awareness can help but are not sufficient in and of themselves. (3) The Bank should carefully assess both the Borrower's commitment to project objectives and its institutional capacity to implement project activities and, to the extent possible, assure or strengthen this commitment and capacity prior to approval in order to help ensure timely implementation. (4) Project instruments on the Bank's side designed to increase flexibility, such as LILs and APLs, require similarly more flexible procedures on the Borrower's side if they are to meet their generic objectives in this regard.
P057838 | Judicial Reform Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/392791475111282952/text/000020051-20140618061929.txt | http://documents.worldbank.org/curated/en/392791475111282952/pdf/000020051-20140618061929.pdf | 1. Inefficiency may arise if a clear link between the project objective and project components is not established.2. Collaboration and coordination among donor agencies are essential especially when a project component is linked to another project funded by a different donor agency. 3. The M & E framework can only be effective if it is well structured with clear time-bound targets, useful baseline information and measurable progress indicators.
P057847 | Natural Resources Management & Poverty Reduction Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2002 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/921181475070699323/text/000020051-20140620065618.txt | http://documents.worldbank.org/curated/en/921181475070699323/pdf/000020051-20140620065618.pdf | Building on useful lessons in the ICR three are emphasized (somewhat adapted):(1) Sustainable natural resource management (SNRM) requires a concerted effort at different levels. Education is an important area where SNRM should be emphasized. Local communities need to show commitment to SNRM activities and understand why it is better for them to adopt such activities. (2) Donor coordination and collaboration are essential tools to tackle complex problems. Effective collaboration and coordination of funding from multiple sources is critical for achieving a cohesive approach. The project was able to harmonize experiences and funding in order to tackle a complex problem such as illegal logging.(3) Project design should be based on achievable objectives within a reasonable time frame as well as an assessment of local implementation capacity. This project had a complex design and did not allow sufficiently for limited local capacity. It also underestimated costs. The design could have anticipated the inevitable delays due to challenging legal reform. Area management plans should be ready at an earlier stage of the project cycle to allow enough time for implementation.
P057857 | CR Equity and Efficiency of Education | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2005 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/769871475118479235/text/000180307-20141203062333.txt | http://documents.worldbank.org/curated/en/769871475118479235/pdf/000180307-20141203062333.pdf | Lessons drawn from the ICR (p. 25) are:Risk assessments are most useful when they are comprehensive and derive mitigation activities. In this case, during preparation, the political risk of a government change and mitigating measures were not adequately identified. Insufficient understanding of the government and congressional approval and budgetary process delayed project effectiveness.Participatory approaches are necessary to adapt curricula and institutions to rural and indigenous areas. In this project, a better understanding about the capabilities of local communities and regional technical units in the investment design would have been useful to strengthen the institutional context for a participatory approach. A participatory approach can help by adapting the curriculum to the needs of local populations, including indigenous groups.
P057859 | SUSTAINABLE COASTAL TOURISM PROJECT | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2002 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/257121475072040432/text/000020051-20140615102915.txt | http://documents.worldbank.org/curated/en/257121475072040432/pdf/000020051-20140615102915.pdf | Challenges to increased tourism. Honduras will need to continue to capitalize on its culture, people, environment, and cultural heritage, and address the problems that affect the quality of the tourist's visit, including poor infrastructure, public security, sanitation and environmental concerns, and social problems.Micro-enterprises can flourish when provided with high-quality technical assistance geared toward enhancing access to markets. Project technical assistance to artisans in this case helped them develop their own items and product lines that would be particularly attractive and interesting to consumers. Historic restoration projects can build enthusiasm and have a positive effect on other initiatives in the community, including strengthening municipal capacity and creating linkages with other partners and donors.It is important for municipalities to lead the effort to encourage community members to work together, as they did successfully with pilot garbage recycling in one village that involved municipal officials, school children, the private sector, and the municipal environment unit, among others.If local capacity is weak, as it initially was with the IHT, contracting out the management of a micro-enterprise fund to knowledgeable agencies with experience in micro-finance might be the better solution.Recipients of micro-finance, in places where formal education levels may be modest, require constant and close follow-up after a grant has been awarded, especially to monitor the execution of their agreed plans.
P057875 | MINING SECTOR CAPACITY BUILDING PROJECT | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Energy & Extractives | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/692221475073374598/text/Mauritania-Mining-Sector-Capacity-Building-Project.txt | http://documents.worldbank.org/curated/en/692221475073374598/pdf/Mauritania-Mining-Sector-Capacity-Building-Project.pdf | The OED review considers the following as important lessons:Institutional development often requires long gestation periods, hence ongoing institutional reform and capacity building projects should carefully identify issues that potential future projects might address in a strategic context. This may also have the beneficial effect of strengthening borrower commitment to institutional change over the long run. While capacity development efforts aimed to increase private sector investment may be relatively successful, a longer period than envisaged may be required before the the investments and benefits expected are actually generated.
P057880 | Urban Heating Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2011 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/306931474491354274/text/000020051-20140625072633.txt | http://documents.worldbank.org/curated/en/306931474491354274/pdf/000020051-20140625072633.pdf | The main lessons suggested by the preparation and implementation of this project are the following (the first two are drawn by IEG, and the other two are taken from the ICR with some adaptation of language):Thorough research and knowledge of the international market among potential suppliers can help to avoid problems during implementation. This applies, in this case, to identification during the preparation stage, of the difficulty of interesting suppliers in bidding for a large number of small value contracts spread over a wide geographical area. Consultation with stakeholders is also necessary to determine the willingness of household inhabiting multi-apartment buildings to seek collective heating solutions. In this case, the ability of communities and Home Ownersâ€™ Associations in urban Armenia for self-mobilization in dealing with heat equipment and service providers was over-estimated. Much of the technical assistance for Home Ownersâ€™ and other community Associations did not materialize or was considerably less than anticipated at appraisal. Experience with pilot projects of lending to Home Owners' Associations and condominia was mixed. The strong household preference for individual heating solutions further undermined the financial viability of the Home Ownersâ€™ Association option. Where there is lack of familiarity with OBA, as in Armenia, awareness about the workings of demand-driven subsidy schemes should be inculcated at a very early stage of project preparation. Additionally, the right mix of procurement methods should be selected for the implementation of such schemes in order to reduce the number of individual tenders and to provide flexibility in the face of changing market conditions.The success of the on-lending program in this project demonstrates the importance of clear and well-specified eligibility criteria for selecting those financial institutions which would participate in the project; transparently allocated credit lines; commercially determined terms and conditions for financing including a full requirement to collect all due interest and principal; and competition among participating financial institutions. The assumption of the full credit risk by the participating financial institutions was counterbalanced by their freedom to determine the lending terms for individual sub-loans.
P057883 | Dushanbe Water Supply Project | Europe and Central Asia | Tajikistan | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2002 | 2011 | 2013 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/541861475083603329/text/000020051-20140625081105.txt | http://documents.worldbank.org/curated/en/541861475083603329/pdf/000020051-20140625081105.pdf | The following lessons are taken from the ICR (pp. 20-21), with some adaptation of language:Innovative arrangements (for the country), particularly in a high-risk environment, need a solid back-up plan. Project design should anticipate potential disruptions or dysfunctions of planned implementation arrangements and should construct relevant contingency measures to maintain adequate technical and operational leadership and control. In this case, there was no adequate fallback when the Service Contract arrangement fell through.Prioritization is essential when a number of wide-ranging objectives are present. Project design should recognize, particularly in a low-capacity and poor-governance environment, that all things may not be possible simultaneously, and therefore pragmatic priority setting and even sequencing may be in order. Supervision resources must be tailored to implementation challenges. In this case, low client capacity, complex transactions requiring new skills and changed behaviors, and sophisticated implementation arrangements clearly required frequent missions of relatively senior experts to consolidate stakeholder understanding and ownership of project approaches.
P057910 | BR PENSION REFORM LIL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 1998 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/379291475328053252/text/000020051-20140615112707.txt | http://documents.worldbank.org/curated/en/379291475328053252/pdf/000020051-20140615112707.pdf | Keeping an eye on results and flexibility in achieving them seems to be a more effective and preferable approach than the traditional one of focusing only on a specific policy prescription. The flexible approach taken by the team played a major role in the success of the project. Indeed, the team accepted many changes--registries, software, management system, while remaining focused on helping Brazil improve a state pension system that was perceived by all as a fiscal threat.The Bank needs to have a better grip of existing conditions on the ground before embarking on a project. Projects prepared in the midst of critical periods may fail to factor in the constraints and opportunities faced by the borrower. In this particular case, the financial crisis of 1998 may have played a role in the initial lack of relevance of the design of the project. Perhaps a better designed project could have yielded the fiscal savings in a shorter period.The Bank also needs to better understand the potential and limitations of its technical instruments in projects such as this one. Better project preparation may have saved a lot of effort and aggravation on issues such as the adequacy of PROST for the task in hand, the usefulness of 15 percent samples, and how much reform was feasible within the existing constitutional and legal constraints.Institutional development may be preferable to legal reform in cases such as this one. The success of the project in terms of fiscal savings appears to have came about with the development of a pension monitoring and administration system. From the available information, it is difficult to imagine how the outcome could have been better had Brazil implemented the legal reforms that the PAD had initially deemed necessary.Understanding the true benefits of a project and their attribution requires information on the actual and potential benefits stemming from it, as well as on the total costs associated with it. In this particular case, the team could have kept track of the actual fiscal savings attributable to the project, as well as of the entire costs incurred by Brazil in implementing it. The team could have also have kept track of the institutional and regulatory changes that were happening because of the project. In the absence of such information it is difficult to know who deserves the credit for its success.
P057915 | Legal and Judicial Development Project | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/514401474491011937/text/000020051-20140612102402.txt | http://documents.worldbank.org/curated/en/514401474491011937/pdf/000020051-20140612102402.pdf | 1. Bank strategy focused on the long-term should take into account the fact that there will be slowing down of momentum and that Government ownership at the highest levels may not be maintained particularly for reforms that are exceedingly difficult. The Bank needs to more thoroughly assess commitment over a longer time frame rather than by short-term actions. 2. A M&E system should be realistic and adapted to a LIL. 3. Placing implementation responsibility in relevant ministries increased ownership of the project but led to a slowdown in the project because of change in leadership in the Ministry of Justice. 4. LILs should get adequate oversight from management.
P057915 | Legal and Judicial Development Project | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2003 | 2007 | PPAR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/187021468334802560/text/37392.txt | http://documents.worldbank.org/curated/en/187021468334802560/pdf/37392.pdf | LESSONS Restructuringwhen countrycircumstanceschange\. Whenthe project environment changes dramatically, the Bank shouldbe readyto restructure key projects inthe portfolio. When Northand South Yemen were unified, andthe new country faced the challenge o fintegrating two distinctly different civil service traditions, the Bank shouldhave moved quickly to discuss the new circumstances with the government, andhavebeenpreparedto restructure the IDPAP. Resources could have been shifted to new priorities as required. The Bank eventually did restructure the project, but only inits closing stages when the relevance o fwhat it had originally set out supportinghad diminished. An opportunitywas lost to play a more constructive role inthe fusing o f the two civil services. The consequences inthe form o fexcessnumbers andanunaffordablewage billmadetheBank's subsequent efforts to assist with public administrationreform more difficult.
P057925 | BULGARIA AGRICULTURE SECTOR ADJUSTMENT LOAN | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | DPF | 1999 | 2001 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/548241474565796118/text/000020051-20140529080242.txt | http://documents.worldbank.org/curated/en/548241474565796118/pdf/000020051-20140529080242.pdf | 1. The success of the ASAL demonstrates the value of good quality sector work. Effective use of policy notes to engage the government and other stakeholders can help build support for far reaching and difficult reforms.2. Timing of Bank interventions is equally important. As the ICR notes, constructive disengagement in a period of poor policy environment helped develop credibility with the new government which was serious about economic reforms.3. In the contribution to the debate on the "big bang" approach to reform in the transition economies, the success of ASAL shows that under the right conditions, it is possible for big bang to work. The caveat, however, is that this big bang followed a fairly long period of slow or no change.4. Finally, the project demostrates the positive impact of proactive and constructive engagement of the borrower by the Bank in ensuring progress on all elements of the reform package, and to prevent back-sliding in important reform areas.
P057925 | BULGARIA AGRICULTURE SECTOR ADJUSTMENT LOAN | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | DPF | 1999 | 2001 | 2001 | PPAR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/582601511185709566/text/multi0page.txt | http://documents.worldbank.org/curated/en/582601511185709566/pdf/multi0page.pdf | 7. Lessons Experience with this project confirms a number of OED lessons\. (1) Where there is a political consensus for reform, sector adjustment loans and their associated conditionalities, can effectively reinforce the reform agenda. While the Minister of Agriculture has ably spearheaded the reform process, the preparation and implementation of the ASAL I policy reform matrix have also played a key role in identifying an appropriate sequence of reforms and in keeping the reform process on track. Prior to 1997, before a sustained political consensus for reform existed, the Bank's policy dialogue with the Government of Bulgaria was sporadic. Afterwards, when the reform process got under way, linking the ASAL I policy conditionality to the IMF's extended financing arrangement and the FESAL II also helped expedite the reforms. (2) The process of policy and institutional reforms is just as important as the substance of the reforms in achieving sustainable outcomes. The Minister of Agriculture followed a systematic approach to policy reform, articulating a vision for the agricultural sector, building consensus each step of the way, and engaging stakeholders in both the broad outlines and the details of the reforms. While the government took longer than expected to pass certain pieces of legislation in order to satisfy these demands, there has been little backtracking. Once important decisions have been made, the government has generally stuck to these. (3) Timely and high-quality economic and sector work is extremely valuable in laying the foundation for a project. In this case, the Bank started its analytical work a full two years before the project was ultimately approved by the Board. Extensively discussing the findings with the government and other domestic stakeholders, through workshops and publications, helped build and sustain the initial consensus for reform. (4) One-tranche adjustment loans can be an effective and preferable instrument in advancing reforms under certain circumstances. In this case, it was effective because the government was committed to the reform process, and because both parties understood the ASAL I and II to be part of a package from the outset. It was preferable since it allowed for more economic and sector work, and for more time, to define the ASAL II policy conditions in the light of ongoing developments, both achievements and setbacks. 31 OED also notes that the ICR contained some minor errors. Two of the key dates on page 1 of the ICR were wrong\. the appraisal mission started on April 5, 1999, and loan effectiveness was on September 10, 1999. In three different places, the CCB was referred to as the Cooperative Central Bank, the Central Cooperative Bank, and the Commercial Credit Bank, a nonexistent entity.
P057926 | Agriculture Sector Adjustment Loan 2 (ASAL 2) | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Agriculture and Food | IBRD | DPF | 2001 | 2003 | 2003 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/831661474555213262/text/000020051-20140607162343.txt | http://documents.worldbank.org/curated/en/831661474555213262/pdf/000020051-20140607162343.pdf | (i) Single tranche adjustment can work with government commitment and broad political support (although this may be self-evident); (ii) complementary investment operations may be essential to reaping the full rewards of adjustment; and (iii) serious and increasing poverty demands direct attention in sector operations.
P057927 | Environmental & Privatization Support Adjustment Loan | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2000 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/817521474490281496/text/000020051-20140612140855.txt | http://documents.worldbank.org/curated/en/817521474490281496/pdf/000020051-20140612140855.pdf | 1. Program lending can be used successfully to promote environmental management, especially when there is strong government commitment and a series of detailed preparation studies. The main drawback may be the normal need to disburse a SAL or SECAL quickly, whereas environmental reform tends to be rather time consuming.2. This operation has been rightly described as a model for countries in transition, many of which are faced with the need to privatize highly polluting industrial enterprises and create a "culture of compliance" generally across the industrial sector. The keys to success include: careful preparation of needed legislative, procedural and institutional changes; environmental audits of enterprises prior to privatization; and full government commitment to follow-through on legal obligations.3. As pointed out in the ICR, this operation had to depend on "command and control" methods, with Stakeholder pressure playing little part and the enterprises not seeing the economic benefits of more sustainable behavior. Again, strong commitment to enforce legal agreements is essential to the "command and control" approach. The desire for early accession to the EU was a strong motivating factor for the government in this case.
P057927 | Environmental & Privatization Support Adjustment Loan | Europe and Central Asia | Bulgaria | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2000 | 2004 | 2009 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/602781468016206321/text/488100PPAR0P031C0Disclosed071301091.txt | http://documents.worldbank.org/curated/en/602781468016206321/pdf/488100PPAR0P031C0Disclosed071301091.pdf | 7. Lessons 7.1 The experience o fthe ERPP andEPSAL suggests the following lessons for future projects that attempt to address past environmental damage and improve environmental performance inthe process o fprivatization. e A development policy loan supportingprivatizationwith environmental remediation should include strong measures by the Government to monitor and rewardcompliance (or punishnon-compliance) to ensurethat remediationand compliance plans are completed on schedule. Inthe EPSAL, eventhough all o fthe policy conditions were met and the RPs and CPs were signed, the achievements in terms of implementation o fthe plans, along with their environmental results, were mixed. Over-reliance onthe goodwill o fthe enterprises themselves was a risky strategy, as changes inownership, management, and financial performance stalled progress on remediation and compliance. e Eveninwell-prepared EIAs,it is difficult to include sufficient detail inthe technical specifications o fremediation investments. Modifications indesign and re-negotiations duringimplementation should be anticipated, and possibly reflected inalongerproject implementationperiodandhigher thannormal contingency funds. e Evenwhenthe State assumes responsibility for remediatingpast environmental damages o f SOEs, setting a cap on the State's liability creates risk for potential investors and delays during re-negotiations. The possibility o f letting the State assume more o f the risk for additional remediation costs shouldbe considered. e Harmonizing country environmental legislationwith international best practice i s a necessary but not sufficient condition for improved environmental performance. In development policy lending for environmental protection, more attention needs to bepaidto improving the country's implementation practices, track record, and capacity inenvironmental regulation. This i s likely to require carefully targeted technical assistanceto buildthe capacity o f national and sub-national environmental authorities. A parallel technical assistance loan, or a wellcoordinated programof technical assistance fundedby other donors, should be considered. 7.2 Several findings o fthis PPAR are relevant to IEG's ongoing evaluation o fthe WBG's safeguard andsustainability policies. First, there were-difficultiesencountered in choosing an environmental classification for the EPSAL. Funds were not channeled through financial intermediaries, butthe fact that not all o f the participating firms had been identified at appraisal meant that the EIA requirements o f an classification could not be met. A modification o fthe classification criteria may be inorder. 7.3 Second, the PPAR was able to compare two projects with similar objectives but different financing instruments\. aninvestment loan and a DPL. Both projects supported the process o fremediating past environmental damage inthe process o fprivatization. While the DPL provided more flexibility thanthe investment loan in terms o fthe selection o fparticipating enterprises andthe preparationand implementation o f remediation and compliance plans, this flexibility came at the cost o f less control on the part o fthe Government and the Bank over the completion o fthese plans. Future DPLs inthis area needto build inbetter monitoring and enforcement mechanisms to compensate for less detailed Bank and Government control over safeguards and environmental compliance. 7.4 Finally, the EPSAL placedtoo little emphasis on the enforcement o f environmentalregulations compared to its focus on the passage o f legislation. A greater focus on institutional capacity, compliance monitoring, and sanctions for non-compliance would have improvedthe likelihood o f achieving environmental outcomes. This finding i s similar to one of the conclusions of IEG's 2008 evaluation of environmental sustainability, namelythat the achievement o f environmental outcomes i s more elusive thanthe achievement o fintermediate outcomes such as policyandinstitutionalreforms. This calls for a greater focus on environmentaloutcomes, along with a more diligent effort to develop andmonitor indicators to measure these results.
P057929 | ERITREA POWER DISTRIBUTION AND RURAL ELECTRIFICATION PROJECT | Eastern and Southern Africa | Eritrea | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2005 | 2011 | 2011 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/760841474503888047/text/000020051-20140624200059.txt | http://documents.worldbank.org/curated/en/760841474503888047/pdf/000020051-20140624200059.pdf | The following lessons can be derived from the project's experience:(1) The design of projects whose financial viability and sustainability depend critically on major policy reforms need to be based on up-front, concrete Government actions rather than covenanted future commitments, to the extent possible.(2) It is important from the very outset for the Bank and Borrower to share a common understanding of how the Bank's procurement guidelines should be applied. (3) The Bank needs to provide further guidance to task teams on the irrevocability of performance guarantees, based on the experience with the Contractor for the Asmara distribution component under this project.(4) In situations where the Bank and Borrower relationship deteriorates to the point where the overall dialogue is not constructive, the Bank needs to assess the negative spill-over effects on other projects, and whether broader country dialogue has any scope to help resolve the issues.
P057933 | TAI BASIN URBAN ENVIRONMENT PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2005 | 2010 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/375731474491369668/text/000020051-20140625060005.txt | http://documents.worldbank.org/curated/en/375731474491369668/pdf/000020051-20140625060005.pdf | The following lessons are taken from the ICR with some adaptation of language: 1. A careful examination of the evidence on sources of pollution and consideration of opportunity costs should underpin decisions on waste water treatment. Under the project, all waste water treatment plants were required reach the Class 1A discharge standard by introducing tertiary treatment to remove nitrogen and phosphorus from water in addition to the solids, organic materials, and nutrients removed in the first and second stages of treatment. But half of this type of pollution in the Lake Tai Basin comes from agricultural activities, and so the cost effectiveness of the additional stage of water treatment was uncertain. The requirement was especially burdensome for small towns with limited capacity, and resources may have been more cost-effective if they were used to reduce other sources of pollution.2. Project teams should carefully consider local circumstances when advocating an institutional model for utilities. The model proposed in the Tai Basin project went well beyond what has been implemented elsewhere in China. While full cost recovery may be a reasonable longer-term strategy to provide effective waste water collection and treatment services and ensure its sustainability, other Chinese cities have achieved this objective in the short run by making political decisions to set tariffs and subsidizing utilities to cover their costs.3. Strategies to reduce degradation of water resources should consider non-point source pollution. Roughly half of total pollution loads that enter the water systems in the Lake Tai basin come from non-point-source pollution, primarily from agricultural sources and untreated urban run-off.IEG adds an additional lesson:4. In order to provide clear guidance to counterparts and maximize development outcomes, project development objectives must be clearly drafted, and closely linked to the activities under the project. In the Tai Basin project, one of the objectives was vague, and much of the activity and attention was devoted to financial and institutional reforms which were not included in the project's objectives, causing a degree of confusion between the Bank and counterparts.
P057950 | Solid Waste Management Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2002 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/884711474571384850/text/000020051-20140624193736.txt | http://documents.worldbank.org/curated/en/884711474571384850/pdf/000020051-20140624193736.pdf | Where project activities cut across different jurisdictions and levels of government, appropriate structures and mechanisms are needed to ensure coordination. If such structures and mechanisms are non-existent or weak, they should be taken up as a first priority for assistance. Openness and clarity are key to fostering mechanisms for co-operation between administrative units. By establishing transparent and well-defined criteria, this project provided a road map for municipalities to receive much-needed and low-cost investments in the solid waste sector. Measures outlined at the design stage to mitigate risks should be given due attention during implementation. The ICR suggests that some of the problems encountered during the early part of project implementation could have been avoided if public awareness and education had been initiated earlier during implementation, and even during preparation.
P057951 | Mostar Water Supply & Sanitation Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Sustainable Development | Water | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/977271474850084841/text/000020051-20140613085357.txt | http://documents.worldbank.org/curated/en/977271474850084841/pdf/000020051-20140613085357.pdf | The likelihood of project success and sustainability of its benefits are enhanced if the Bank has a broad and sustained relationship with the counterpart in this case the city of Mostar. The Bank's continued and widespread support for the rebuilding of Mostar had generated goodwill and trust towards it, facilitating acceptance of the Bank's advice on policy dialogue and on investment projects.The project demonstrated that a public sector operator (MWSSU) can improve service quality and operational efficiency without the help of private sector operators. The project demonstrated the virtues and feasibility of limiting the use of externally contracted consultancies. The PIU was staffed entirely by MWSSU personnel with tremendous gains in institution building and cost savings. The created capacity has enabled MWSSU to provide technical assistance to other utilities and infrastructure related Ministries in Bosnia and Herzegovina that are collaborating with international financial institutions.
P057952 | Social Investment Fund 2 Project (SIF 2) | Europe and Central Asia | Armenia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/597601474420777359/text/000020051-20140617143115.txt | http://documents.worldbank.org/curated/en/597601474420777359/pdf/000020051-20140617143115.pdf | Based on the ICR the following lessons are highlighted:Even the most sophisticated poverty targeting strategies can be difficult to implement because of political pressures, data limitations and the limitation of demand driven approaches that do not ensure that the majority of the employment benefits go to the poorest. Projects aimed at capacity enhancement and community participation should explicitly and systematically monitor and evaluate the extent to which these are achieved using both quantitative and qualitative measures.Sustainability considerations must be thought through from the beginning of the project. This includes sufficient thought as to how groups/associations formed at the community level will continue to function effectively on project closure, and the in-country capacity to support operation and maintenance.
P057953 | Education Reform Project | Europe and Central Asia | Tajikistan | IDA |  | Human Development | Education | IDA | IPF | 1999 | 2004 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/307991474898621781/text/000020051-20140612102711.txt | http://documents.worldbank.org/curated/en/307991474898621781/pdf/000020051-20140612102711.pdf | Communities are often unable to pay for school construction costs. It may be more useful to request school monitoring activities from them than cash.- Learning and Innovation Loans (LILs) loans can be useful instruments to introduce significant reforms on a minor scale in difficult countries and to enable learning before scaling up good-practice outcomes. Supporting client ' s initiatives through technical assistance to scale up pilots even as they are being implemented can help to replicate good ideas. - Under post-conflict circumstances, a first time operation in a sector may be most effective if it finances only some key interventions and does not include all pressing needs in the operation. - Complex components such as Education Management Information System and student assessments typically require time to design, implement, fine-tune and evaluate. Ideally, these aspects should be implemented after a country acquires experience in implementing simpler components.
P057957 | Hard Coal Sector Adjustment Loan (SECAL) | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 1999 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/502101474585564058/text/000020051-20140602113053.txt | http://documents.worldbank.org/curated/en/502101474585564058/pdf/000020051-20140602113053.pdf | (1) The Inter-Ministerial Coal Steering Committee has proven to be a useful forum for monitoring project implementation and improving coordination and cooperation between various levels of Government, government institutions, and the mining companies.(2) Large-scale employment restructuring requires a careful analysis of regional development and potential for job creation in order that retraining programs impart the right skills and that the labor market is capable of absorbing those who have left the sector.(3) Intensive dialogue between Government, mining companies, and trade unions and the participation of trade unions in the design of the employment restructuring program have contributed significantly to the successful implementation of the employment restructuring program, free of any social unrest.(4) A SECAL is a useful instrument for carrying out comprehensive sector reforms.(5) A monthly 'scorecard' completed by industry was a very effective tool for monitoring and evaluation of project implementation. The scorecard allowed ready monitoring of all aspects of the project, helped focus discussions on key performance issues, and facilitated analysis of actual vs planned performance.
P057959 | Education Reform Project | Europe and Central Asia | Azerbaijan | IBRD |  | Human Development | Education | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/198911474486326781/text/000020051-20140612152455.txt | http://documents.worldbank.org/curated/en/198911474486326781/pdf/000020051-20140612152455.pdf | Implementing learning and innovation loans is difficult when the borrower has limited experience with Bank lending as well as with this type of instrument. It is furthermore difficult to pilot and compare alternative models to solve a given problem if experiments and evaluation methodology have not been carefully designed.- Unless staff in charge of implementation have sufficient comprehension and belief in project goals, they may neglect the project. More client-oriented and needs-based supervision may identify and allay some of these problems early on.- Innovative educational concepts must be clearly defined. Vague concepts, such as 'student-centered learning' may result in a lack of agreement on how they must be implemented, and compromise outcomes as well as quality at entry.
P057960 | Rural Development Project (APL #1) | Europe and Central Asia | Romania | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2002 | 2008 | 2009 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/582151474663944860/text/000020051-20140619082716.txt | http://documents.worldbank.org/curated/en/582151474663944860/pdf/000020051-20140619082716.pdf | Based on the ICR the key lessons are: In a top-down post-socialist environment, it takes time to build capacity/skills and engage public participation at local level. The project design should adequately factor in this additional time requirement of capacity building before the commencement of the investment activities. It is important to build into a locally implemented project some resources and mechanisms for dissemination of results and policy dialogue with the national government Otherwise, the positive effects of the project may not be fully understood at the national level, which is likely to hinder policy implications and replication; Building an adequate system of M&E at the outset with well matched (or randomized) control and treatment areas gives the Bank and others much more confidence in assessing the developmental impact of the Bankâ€™s intervention and can be a tool in itself of promoting the project-initiated approaches with clients.IEG adds the following lesson: the project's M&E design, tools (methodology, questionnaires etc.) and findings should be made publically available (on the web) in the country and disseminated within Bank.
P057995 | CAPACITY BUILDING FOR ECONOMIC MANAGEMENT PROJECT | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2002 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/646061474512323770/text/000146597-20140619170837.txt | http://documents.worldbank.org/curated/en/646061474512323770/pdf/000146597-20140619170837.pdf | IEG concurs with the lessons stated in the ICR. It is important to formulate the results framework and specify measurable output and outcome indicators, as well as specify methods for assessment. Additionally, it is important to align project objectives and design to institutional capacity in the country. Additionally, it is important to ensure a built-in flexible monitoring system that allows the client and the Bank to regularly assess progress and readjust in a timely manner as needed the activities over the project period. Appropriate and adequate project management and implementation arrangements, both at the policy and technical level, are essential for ensuring and sustaining country ownership.
P057996 | National Rural Infrastructure Project | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/859051474893023965/text/000020051-20140615105222.txt | http://documents.worldbank.org/curated/en/859051474893023965/pdf/000020051-20140615105222.pdf | The ICR identified following lessons:Decentralization is a long-term and comprehensive effort that requires political support. Moreover, the major changes expected are likely to meet resistance from some institutions. Therefore considerable effort is needed for new systems to be established and officials to be educated and convinced to accept changes.The implementation of decentralization projects requires political support that needs to be mobilized beyond technical ministries. It not practical to anchor such a project within a technical ministry. Sustainability depends on the degree to which the beneficiaries internalize the process. The ability to continue the planning, implementing and monitoring of investments using participatory processes depends on the capability to raise funds and maintain community mobilization.
P057997 | GM-Poverty All & Muni Dev (FY99) | Western and Central Africa | Gambia, The | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2007 | 2008 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/785941474665597420/text/000020051-20140618053724.txt | http://documents.worldbank.org/curated/en/785941474665597420/pdf/000020051-20140618053724.pdf | Some lessons identified in the ICR include:Building local capacity for delivery of quality works and services is key for small countries such as Gambia. However, it is also necessary to balance the need to strengthen local capacity with the need to provide quality works. Where possible the government should facilitate international contractors and consultants to help build and strengthen local capacity.Provision of relevant studies, training and technical assistance in a co-ordinated manner can provide significant results in improving local government capacity.
P057997 | GM-Poverty All & Muni Dev (FY99) | Western and Central Africa | Gambia, The | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2007 | 2009 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/507541468245977487/text/485650PPAR0P101LIC0Disclosed0718191.txt | http://documents.worldbank.org/curated/en/507541468245977487/pdf/485650PPAR0P101LIC0Disclosed0718191.pdf | 7. Findingsand Lessons Where local government lacks the experience inhandling works contracts, a specialized agency such as Gamworks can provide the contract management services needed for the local delivery o f infrastructure and urban services. Creating a single core group o f specialists within such an agency makes particular sense ina small country with high attrition rates among local government staff. Whenproject objectives focus on directly assisting the poor, the project designshould facilitate identifyingthe poor clients and their priority needs as well as sound M&Eto monitor the progress o f poverty alleviation. The Bank i s ina good position to deploy technical expertise for this purpose inthe Gambia by drawing from its extensive global experience inthis area. Whenmunicipal technical capacity and resources to maintainasphalt roads is limited, , sub-project investments should consider engineering designs such as interlockingpaving blocks, which requireminimal maintenance. Also when LGA technical capacity is weak, municipalities needmore technical assistance and training for staff at all levels. Service staff can hone basic technical skills such as those needed for maintenance and record keeping, for instance. At the leadership level, training o f LGA managers and councilors can help make them more aware o f the need for planningand budgeting o f municipal services.
P057998 | PUBL.SEC.REFORM SUPP | Western and Central Africa | Cabo Verde | Blend |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/596891474502637449/text/000020051-20140612082154.txt | http://documents.worldbank.org/curated/en/596891474502637449/pdf/000020051-20140612082154.pdf | 1. Timing project implementation to take place primarily in non-election years would mitigate the risk that changes of national leadership might undermine Borrower ownership in mid-stream.
P058015 | Agricultural Post-Privatization Assistance 2 Project (APL Phase 2) | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2005 | 2012 | 2015 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/915731475112696883/text/000012394-20150107142246.txt | http://documents.worldbank.org/curated/en/915731475112696883/pdf/000012394-20150107142246.pdf | The ICR provides five cogent, although well known, lessons from this project, namely: (i) success of one phase of a project (in this case Phase I of the project) does not necessarily lead to success in the next phase (in this case Phase II) - particularly when the second phase was not similar in content to the first phase; (ii) it is important to have clear and measurable outcome indicators for the project and they need to be systematically monitored; (iii) it is important for the success of a project to have a pro-active approach and flexibility in the Bank and government to adapt to changing circumstances; (iv) when a project is unsuccessful despite reasonable efforts to fix the situation, the Bank and Borrower should be ready to cancel the project; and (v) a properly designed and implemented M&E system is important for the projectâ€™s success.One lesson from this project is that a loosely organized team of consultants under the management of the head of a Department in the Ministry of Agriculture was not an effective arrangement for facilitating implementation, management of fiduciary responsibilities, and monitoring and evaluating of a complex project that is a concern of other government institutions such as the Ministry of Finance and the Central Bank. There was ample justification for a separate project implementation unit under the leadership of technically competent full time manager with qualified staff and with sufficient authority to advance the project's objectivesA second lesson is that if the Bank or its partner in a project realize that they have made an incorrect decision, as the Bank did with respect to its decision not to seek the cancellation of this project at mid-term, then either party should be candid about that error and be ready to correct the original decision.
P058031 | ECO & SOC SEC SUPT L | East Asia and Pacific | Malaysia | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1998 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/476891474635222358/text/000020051-20140528123240.txt | http://documents.worldbank.org/curated/en/476891474635222358/pdf/000020051-20140528123240.pdf | 1. The single-tranche operation worked well as a crisis response instrument. A QAG review (August 1999) of Bank adjustment loans made in response to the global financial crisis also confirms that in situations such this one--where the Bank is building a new relationship with Government, where the depth/breadth of Government ownership is uncertain, and the Government does not offer a strategy for building popular support for reform--a single-tranche operation based on actions already taken is appropriate. 2. In a fluid and uncertain environment, the GOM's ability to adjust monetary and fiscal policy in accordance with changing events improved outcomes. Flexibility should, however, include increased coordination between ministries. 3.In economies like Malaysia, strategies to manage the poverty impact of an economic crisis should include the urban as well as rural poor (until recently safety net/social sector programs tended to focus primarily on rural poverty).
P058038 | Agricultural and Rural Market Development Project (LIL) | Eastern and Southern Africa | Rwanda | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/458691474577166617/text/000020051-20140612143837.txt | http://documents.worldbank.org/curated/en/458691474577166617/pdf/000020051-20140612143837.pdf | The ICR details a lengthy list of very project specific lessons from the review. One that is of broader application is that it is possible, in a country like Rwanda, to develop a viable, privately operated and sustainable input supply system, under the right set of policies, incentives and institutional mechanisms.
P058050 | Community Development Support Project | Eastern and Southern Africa | Lesotho | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2004 | 2004 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/665781474939401678/text/000020051-20140612105619.txt | http://documents.worldbank.org/curated/en/665781474939401678/pdf/000020051-20140612105619.pdf | Based on the ICR the main lessons are:(i) The success of a CDD approach to a large extent depends on an adequate process being put in place and adequate capacity to implement at the grassroots level. Hence it may not be appropriate in all situations. Adequate assessment of borrower commitment and ability to undertake such interventions is critical before deciding to undertake such an approach. (ii) A multi sectoral project can be complex and challenging to implement. Design of such projects requires a thorough assessment of the institutional capacity in the country. (iii) The building of adequate community participation requires time, resources and explicit attention to incentives for the stakeholders. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured. (iv) In the case of the Bank, effective, timely and accurate reporting is critical. Bank staff and management could avert problems such as those experienced in this Project by paying close attention to disconnects in Project Status Report ratings.
P058050 | Community Development Support Project | Eastern and Southern Africa | Lesotho | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2004 | 2010 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/529741468054547515/text/543590PRSP0P00101Official0use0only1.txt | http://documents.worldbank.org/curated/en/529741468054547515/pdf/543590PRSP0P00101Official0use0only1.pdf | 6 . Lessons The varied experience of LHWP- 1B and CDSP provide seven principal lessons\. When projects are contributing to a common purpose, linkages between the projects should be exploited and reflected in a combined or mutually supporting design package. LHWP- 1B and CDSP were seen as closely related in the development strategies of both the Government and the Bank, and justified as such in the project documents poverty alleviation through revenues earned by LHWP- 1B channeled through a social fund managed under CDSP. But specific features to achieve this and to better assure the proper use of the social fund were not incorporated in either project, and each was supervised in isolation. A successful construction program does not necessarily mean a successful development program. Attention is needed to the full objectives o a project, including f on software as well as hardware. LHWP-1B's successful water infrastructure program will be a main pillar in Lesotho's development program for decades to come. But, despite the LHWP-1B and the CDSP, the royalties did not go to poverty reduction, the project's most fundamental objective. Also, while LHWP-1B was strong in all aspects related directly to construction (engineering, physical works and water delivery), it performed weakly in software aspects capacity building, training and resettlement. Vested interests can captureand severely compromise a project special project features and Bank actions are needed to counteract any such risks. The political takeover of the LFCD and the resultant collapse of community development processes illustrate that vested interests can outweigh apparently firm agreements and can compromise, or even as in the case of CDSP, nullify development intentions. Lesotho and South Africa s GoodPractice '' Water Treaty has features that may be relevant elsewhere. The following features have contributed to success\. (i) clarity and detail in the treaty document, including procedures for adjusting to changing circumstances; (ii) appropriate institutions a bridging institution has worked well in coordinating actions between the two countries; (iii) focused objectives; and (iv) independent dispute resolution mechanisms within the institutions themselves. The Bank's 20 year engagement providing technical and policy support, and as a motivator for the financial involvement of other lenders, also contributed to the treaty's success. Practical application can make resettlement work. Improving implementation is more important than perfection of resettlement policy. LHWP- 1B's resettlement program was far less complex than the construction program, was not large, and need not have been any less successful. Missing needs were\. (i) a motivated and competent institutional structure; (ii) emphasis on practical, socially responsible, flexible and participatory implementation more than perfection in policy; and (iii) particular focus on helping resettled families to become self-reliant rather than relying on compensation payments alone. Economic benefits from safeguards should be assessed as well as costs. Under LHWP-1B the costs of safeguards were considered but benefits were seldom assessed. A better approach would have been to recognize such benefits, which would have put the costs in broader perspective. For resettlement, decision makers in Lesotho might have been more readily persuaded to adequately fund and staff the resettlement program if its economic viability had been assessed as a whole. Safeguards implementation should not be frequently given second-tier priority, but should receive the same attention as the main project components. Successful implementation of a safeguard program requires the same design and supervision qualities as other project components. Compliance with a safeguard requires a range of skills and resources very familiar to Bank project operations in general\. a good action plan; readiness for implementation; good supervision including relevant specialist skills; highlighting the safeguard's importance in dialogue with Government; building implementation capacity; and monitoring. Implementation of the safeguard actions should have no lesser priority than other key project components. There is likely to be a cost, however quality actions such as the above would tend to increase staff resource needs, and would need additional Bank budget.
P058056 | Pension Reform Technical Assistance Project | Europe and Central Asia | North Macedonia | IBRD |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/606831474493470073/text/000020051-20140607165101.txt | http://documents.worldbank.org/curated/en/606831474493470073/pdf/000020051-20140607165101.pdf | 1. The PERTAP was adequately supervised thereby ensuring that the hurdles and delays that arose could be overcome. Even so, Parliamentary delays in approving the laws could not be avoided; so a more realistic timetable is necessary.2. Staff continuity, both in the Bank and in the counterpart agency, helped in its implementation.
P058067 | Second Community Water Supply and Sanitation Project | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2011 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/987621474570495227/text/000020051-20140625055657.txt | http://documents.worldbank.org/curated/en/987621474570495227/pdf/000020051-20140625055657.pdf | The following four lessons are derived from the ICR:Adequate financial analysis of provincial and local governmentsâ€™ ability to contribute should be assessed prior to implementation. In this project, these levels of government provided less than half the amount stated at appraisal and the shortfall had to be made up from additional community contributions.The Sanitation Revolving Fund model can be effective. Because of its innovative design the Fund was able to mobilize community action to improve sanitation access and leverage funds for other economic activities.Including conflict-affected areas within a national project requires flexibility in project design and implementation arrangements. Special arrangements are required to take into account the differing socio-economic and institutional challenges present in conflict-affected areas - one set of arrangements for a project will not fit all circumstances. And IEG adds this lesson: When projects are significantly affected by natural disasters attention should be given to adjusting expected outputs and outcomes as soon as possible. In this project this was not done until the very end and a consequence was that expectations became unrealistic given the reduced budget.
P058067 | Second Community Water Supply and Sanitation Project | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2011 | 2018 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/615581499954244065/text/115781-PPAR-P058067-PUBLIC.txt | http://documents.worldbank.org/curated/en/615581499954244065/pdf/115781-PPAR-P058067-PUBLIC.pdf | 7. Lessons 7.1 Lack of continuity in M&E and its utilization by an implementing agency beyond project completion undermines sustainability of development outcomes. In this project, the monitoring function for rural water schemes weakened after project completion. Currently, the Rural Water Supply Division of the NWSDB maintains a rural water schemes database. However, there is no clear evidence that this data is shared with relevant institutions or used to identify and prioritize critical support needs for CBOs managing water supply schemes. 7.2 Technical soundness of initial design and quality of construction affect performance of CBOs. In this project, poor CBO performance in sampled cases could be traced to poor technical design, resulting from several factors\. (i) insufficient time and resources spent on identifying a suitable water source; (ii) lack of local knowledge or capacity of consulting firms; and (iii) insufficient oversight by technical experts such as NWSDB staff. These factors often led to water source depletion, water quality problems and frequent repair needs. 7.3 Strong and consistent institutional and technical support is needed to achieve sustainable service delivery in CBO schemes. In this project, CBOs were expected to be fully in charge of construction and management of rural water supply schemes. However, technical aspects regarding operation and maintenance and financial supervision were often beyond the capacity of the CBO members. While units of the Rural Water Supply Division of the NWSDB and Pradeshiya Sabhas are providing support in this regard, there appears to be great variation in the capacity and interest among these units to carry out this function, depriving needy CBOs of timely support in some cases, and affecting their performance. 7.4 Proactive and adaptive project supervision in response to exogenous events can help safeguard project efficacy. In this project, there are positive and negative examples\. on the one hand, the task team responded nimbly to the tsunami by taking actions, including reallocating some of the funds to an emergency project and changing some project locations; on the other hand, the response was less nimble in taking steps to adjust the project targets to the decrease in available funds and an inflation surge, which affected project outcome.
P058070 | North-East Irrigated Agriculture Project | South Asia | Sri Lanka | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/142811474664444449/text/000020051-20140614184343.txt | http://documents.worldbank.org/curated/en/142811474664444449/pdf/000020051-20140614184343.pdf | Transparency in project design and execution is essential in recovery from post-conflict situations. This was helped by appointing the NE Provincial Council as lead implementing agency (instead of the relevant central government agencies in Colombo), actively involving CBOs and NGOs in implementation and the appointment of independent technical and financial auditors who provided impartial and transparent quality control. Early attention to build local technical capacity is essential for project sustainability. In this case it was too little and too late which adversely affected the performance of CBOs.
P058070 | North-East Irrigated Agriculture Project | South Asia | Sri Lanka | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2005 | 2015 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/118841468186563919/text/97699-PPAR-P058070-IDA-R2015-0212-Box385353B-OUO-9.txt | http://documents.worldbank.org/curated/en/118841468186563919/pdf/97699-PPAR-P058070-IDA-R2015-0212-Box385353B-OUO-9.pdf | 12. Lessons 12.1 Lending for land-based assets in a protracted conflict affected situation, characterized by massive displacement, should be sequenced within a broader social development framework that balances individual needs with equity aims. In a conflict affected situation, where war is associated with minority grievances, the distribution of assets and associated impacts can either improve or threaten fragile peace. In the case of the North Eastern Irrigated Agriculture Project, the distribution of assets (mainly repair) was highly uneven across the project area; repair was neither based on a vulnerability index nor stratified to ensure fair treatment across the project areas. 12.2 The term post-conflict should be used sparingly in the absence of a negotiated peace agreement and World Bank projects should accordingly exercise caution in project design. The North Eastern Irrigated Agriculture project in Sri Lanka was developed on the back of an optimistic country assistance strategy and a temporary cease-fire. While all signs pointed towards the need for caution, both the country assistance strategy and the project were designed to support reconstruction activities, in line with a post-conflict and reconstruction strategy. This exuberance masks the need to think more proactively about societal healing, institutional development, and good governance reforms that are needed during a country's fragile transition from war. In the case of Sri Lanka, hindsight clearly signifies that the level of attention that was awarded to reconstruction was premature. 12.3 There is a tension between responding to the immediate needs of conflict affected populations and the use of a community driven development model to respond to these needs in fluid or highly mobile environments. While the Northeast Emergency Irrigated Agriculture project in Sri Lanka was highly responsive to the urgent needs of persons living in conflicted affected areas, it financed physical works that were not utilized due to continued displacement and movement of the physical population. Humanitarian aid, in this case, may have been a better choice for the delivery of critical services, like drinking water, than a Bank project. 12.4 Participatory development is a process that should be nurtured and supported throughout all stages of a project cycle. In the case of the North Eastern Irrigated Agriculture Project, participatory needs assessments and capacity building activities were conducted to reduce the risks associated with the unequal/inequitable distribution of village assets and to ensure ownership of the assets that were being repaired. The project missed an opportunity to respond to broader human and social capacity development needs that, in the case of the North East Irrigated Agriculture Project, would have been aligned with the project aim of reintegrating the conflict affected communities, both economically and socially. This would have included attention to language, culture, and behavior and efforts to bridge societal differences through the project means.
P058128 | MA-TELECOM, POST AND IT | Middle East and North Africa | Morocco | IBRD |  | Infrastructure | Transport | IBRD | DPF | 1999 | 2001 | 2002 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/615101474907899337/text/000020051-20140604042853.txt | http://documents.worldbank.org/curated/en/615101474907899337/pdf/000020051-20140604042853.pdf | The most important lessons, well-identified in the ICR, are:(1) The integration of telecommunications, information technology, and postal components in TPI-SAL's design has encouraged the Government to consider the broader scope of information infrastructure, consistent with the global convergence among what were traditionally separate services, networks, and businesses.(2) Project design must realistically reflect the differences in institutional capacity, resources and political will for reform amongst the subsectors. In the case of TPI-SAL, expectations and achievements were higher for telecommunications, more modest for the posts, and fragmentary for IT.(3) The introduction of competition before privatization of the incumbent telecommunications operator is a powerful option for sector reform. As a result of competition, the following occurred: (a) IAM was forced to focus early on customer service, accelerate service roll-out, reduce prices, and strengthen commercial management; (b) the privatization of IAM accelerated to enable IAM to compete effectively by freeing it from public sector restrictions and facilitating access to global capital markets, technology, and management; and (c) the risk of the monopoly privileges of IAM being extended to increase its sale price was reduced.(4) The incremental costs of providing universal service, including rural areas, can be reduced through the market rather than through the imposition of obligations for potentially unprofitable services on the incumbent and new entrants. Competition has resulted in the rapid build-out of new networks and made affordable, new service modalities available to modest urban users. In this way, the cost of the gap between what operators are prepared to do on commercial terms and public service objectives of the Government can be reduced.
P058129 | Emergency Fire Prevention & Control Project | Latin America and Caribbean | Brazil | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/681321474571711332/text/000020051-20140613064905.txt | http://documents.worldbank.org/curated/en/681321474571711332/pdf/000020051-20140613064905.pdf | 1. To cope with an emergency situation, it is important to define roles and responsibilities in advance. This was revealed in both a negative and positive way by this project. On a negative note, one component was unsuccessful due to poor coordination between the IBAMA headquarters and the IBAMA local agencies, resulting in frequent staff and management changes, and frustration as local staff had little autonomy and decision-making authority. On a positive note, during the initial stages of the project, there was considerable commitment from all participating agencies, which involved several federal, state and municipal-level institutions during field actions.2. Emergency situations require flexibility. This was seen here in at least three ways. a) The involvement of the Bank allowed financing from an existing Bank project, the National Environment Project to be reallocated for emergency and preparatory work. It also shows that is important for the Bank to be involved right at the outset of an emergency project. (b) When it was clear that the immediate risk of fire was gone, the Borrower no longer had interest in providing counterpart funding, and the Bank was flexible in reallocating money between components. (c) Emergency projects are often prepared very quickly and some issues are only defined during project implementation, requiring flexibility and more intense Bank supervision4. Emergency projects must be followed by a long-term strategy to avoid future emergencies.This project combined both urgent and long-term objectives in a single two-year emergency project, which was later extended three times, for a total of six years. It might have been better to have either a short-term emergency project with very flexible arrangements, followed by a normal longer-term investment project, or a project with two phases.5. Decentralization and partnerships are needed to reach the field. In a remote and large region such as the Brazilian Amazon, it was clear from the beginning that no agency alone would be able to carry out all project activities.6. Technology is not an end in itself. The project was successful in establishing a modern risk alert and fire monitoring system that provides on-line and updated information on fire risk. Although the information was very valuable at the national level for planning, it was underutilized at the local level. Municipalities and local and state offices of extension and environmental agencies should have been trained better in the use of this tool.7.Social capital is important for long term sustainability. The project contributed greatly to understanding theimportance of communal actions and partnerships to prevent wildfires and seek alternatives. As a result, the activities and mechanisms that contributed to the projectâ€™s implementation are still in progress though financial support from the project is over.
P058202 | Rural Development Project | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/677231474908857386/text/000020051-20140614183152.txt | http://documents.worldbank.org/curated/en/677231474908857386/pdf/000020051-20140614183152.pdf | The ICR has extracted a number of useful lessons from the experience with this project. Projects like RDP should be implemented as much as possible in a decentralized way, especially where political decentralization to elected regional and local governments is already in place. While line ministries should play a substantial role in project design, they should allow regional and local governments substantial leeway in adjusting the mix of project activities during implementation. Centralized management of decentralized and autonomous implementation is counter-productive to local capacity-building. Giving regional and local governments the responsibility for implementation -- including reponsibility for examining their communitiesâ€™ specific problems, for focusing project components on addressing these problems, and for executing the related activities -- helped achieve the project objective of strengthening their capacity. Project design needs to specify clear ranking and qualification criteria for local governments to access project funds, based on socio-economic information at the local level, in order to mitigate the potential trade-off between decentralized implementation and a focus on poverty alleviation. Otherwise, regional governments are naturally under pressure to allocate access to project benefits widely across many local governments of varying need.
P058282 | ECONOMIC MGMT REFORM | Western and Central Africa | Burkina Faso | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 1999 | 2001 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/864721474481871311/text/000020051-20140529073821.txt | http://documents.worldbank.org/curated/en/864721474481871311/pdf/000020051-20140529073821.pdf | Improved donor coordination and inclusion of donor financing in the budget system would improve public budgeting and expenditure practices and outcomes.
P058284 | Cultural Heritage Project | Europe and Central Asia | Romania | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/879101474908090962/text/000020051-20140613064959.txt | http://documents.worldbank.org/curated/en/879101474908090962/pdf/000020051-20140613064959.pdf | Ensuring that funding for the PIU was adequate to attract and retain qualified personnel can improve staffing continuity, thus, likely limiting delays and facilitating greater institutional development. Correcting course along the lifetime of a project, to fully utilize resources, can result in added project benefits. The LIL instrument, true to its purpose, can provide a productive way to work with first time Bank partners (the Ministry of Culture in this case). Its small scale, experimental nature can allow for close collaboration among entities relatively new to one another (the Bank, the Ministry of Culture, and the WMF in this case).
P058308 | China Pension Reform Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/165461474631836875/text/000020051-20140615112258.txt | http://documents.worldbank.org/curated/en/165461474631836875/pdf/000020051-20140615112258.pdf | Three lessons can be learned from the objectives, design, and implementation of the Project: (i) the importance of aligning project objectives with those of the Borrower to bring a shared sense of purpose in moving the project forward, (ii) pilot trial basis prior to design and implementation at the national level brings focus and clarity to attaining project objectives, and (iii) clarity regarding the responsibilities and repayment obligations at the onset of the project launch would make project management and monitoring more effective and efficient.
P058356 | POLICY REFORM SUPPOR | Middle East and North Africa | Morocco | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2000 | 2001 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/438091474577941701/text/000020051-20140529163048.txt | http://documents.worldbank.org/curated/en/438091474577941701/pdf/000020051-20140529163048.pdf | (i) A very broad adjustment operation with an excessive number of elements, many of which have little practical value, is unlikely to achieve ambitious objectives. A more focused operation, with technical assistance in key areas (e.g. civil service reform) might have had more success. (ii) The original CAS objectives were highly relevant to Morocco's situation and the lending program should have stayed closer to that proposed in the CAS.
P058358 | Health Sector Development | East Asia and Pacific | Solomon Islands | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422811474665583997/text/000020051-20140618053935.txt | http://documents.worldbank.org/curated/en/422811474665583997/pdf/000020051-20140618053935.pdf | 1) Strong and creative Bank supervision can, with difficulty, compensate for some of the weaknesses inherent in a difficult project environment - such as, in the present case, suspension of disbursements, ethnic tensions, and macroeconomic collapse. However, civil unrest may compromise the capacity of a project for learning, even if other elements of the project continue in execution.2) A weak start on M the specificity of M&E design to the project AND its environment is critical. 3) Independent institutional capacity analysis and follow-up are critical, especially in institutionally difficult environments. 4) Public financing of advanced training overseas involves high risks that the trainees will not return or will leave the service. The benefits are largely private rather than public, and must be coupled with incentives or regulations for those trained to remain in the service, such as a pay-back requirement if the trainee leaves the service within ad certain period after completing training.5) It is easier to design multi-sectoral committees, such as in this case for reproductive health and malaria, than to make them function effectively. Benefits and costs need careful assessment before decisions are taken to create such committees, and prior consultation with participants is essential.
P058468 | Agricultural Services Innovation and Reform | South Asia | Bangladesh | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2000 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/467451474573136641/text/000020051-20140612092156.txt | http://documents.worldbank.org/curated/en/467451474573136641/pdf/000020051-20140612092156.pdf | The ICR reorts a number of lessons, but these are all specific to Bangladesh and the activities pursued by the project. One general lesson that might be drawn is that if a LIL with several components is to have an impact regardless of the outcome of the individual pilot efforts, then it needs to have a clear internal coherence and to be designed so that the capacity to innovate in the future is increased.
P058468 | Agricultural Services Innovation and Reform | South Asia | Bangladesh | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2000 | 2003 | 2007 | PPAR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/208921468205174549/text/36295010BD.txt | http://documents.worldbank.org/curated/en/208921468205174549/pdf/36295010BD.pdf | 6. Lessons and Considerations for Future Development 82. Four specificlessonsregardingthe pro-poor growth challenge, and a final lesson related to the Bank's strategyfor Bangladesh's rural sectorhave emergedfiom this review. The first four lessons are closelyinterlinked, and, together, provide two important observations. First, the projects illustratepracticalways to emphasizegrowth and social equityat the sametime, and even demonstratinghow improving equity can also improve productivity. Second,actions across the four areas canbe mutually reinforcing.Pro-poor and gender-inclusiveagriculturalgrowth canbe further stimulatedwhen more than one action area is tackled simultaneously. (1) Dedicated focus on enhancingproductivity pays off. Breakthroughsinproductivity canbe triggeredby making a quantum improvementin productivity a major goal and specifically addressing this in the project's design. Without designingthe project with this in mind, productivitybreakthroughs may not occur. 83. The SDPP and the HORTEXcomponent of the ASIRP placed their major focus on stepped up productivity, and achievedthe breakthroughsthey aimed for. The FRMF did not emphasizeproductivity enhancement, aid no major gains in the productivity of the forestry sectoroccurred. 84. The achievementsreflected the emphasisthat each project placed onproductivity. The very essence of SDPPwas to bring about a quantum leap in the silk sector's productivity to enableBangladeshto be more competitivein relation to the internationalmarket. Nearly all of the SDPP7smonitorable indicatorsmeasuredproductivity.Likewise, the major objective of the horticulturalexport component of ASIRP was to help Bangladeshiexporters to break through the barriers to entryinto the much higher-value international market, compared to the lower-value (and lower-productivity)of the domesticmarket. The FRMP was more in the mold of traditionalBank projects. Its design and impactwas on increasing the number of hectares ~mdercultivated forests, coastalprotection, environmental management and iiistitutionalimprovement. It also had a smallresearch component, as often found ill a Bank rural project. While the FRMP successfullyachievedits objectives, a major jump in productivitywas not its centralpurpose and was not achieved.33 85. The SDPP and HORTEX achieved their breakthroughsthrough a combinationof institutional as well as technologicalinnovations.The enhancement of silk sector productivitywas primarilythrough introducingtechnical improvements, but drivingthis was the new Silk Foundationand the NGO sector. The export breakthroughfor horticultural products involved substantialnew technologiesfor Bangladesh in growing, grading, packaging and transportingof produce,but it was pioneered and then catalyzedthrough an institution, HORTEX, designed and dedicated exclusivelyfor this purpose. - - 33. The reference to improve theproductivity in FRMP's developmentobjectivesreferredto the expansionof forestplantations, not to an improvementinproductivity per hectafe. 86. The SDPP and HORTEX successesmight, however, be exceptionsto the more typical situationfound in Bangladesh's agriculturalsector,where technical knowledge to enhanceproductivitymay be limited. The IEG mission was informed that research was a smallpart of government's expenditure in agriculture-only about 0.2percent of agricultural GDP.34A revolution in agriculturalproductivityis likelyto need a much strongertechnical base than Bangladesh's relatively small researchprogram can currently provide.35 (2) Sociallyinclusiverural developmentneed not constrain rapid agricultural growth. Project design featuresthat target benefits for the poor and women may even enhance agriculturalgrowth. 87. Over 80 percent of the SDPPparticipantswere poor women, and they showed greater interest and care in rearing andreeling-hence in adoptingsericulture and achieving higherproductivity-than wealthierhouseholds. Poor women were the primary target of the SDPP's NGO extensionservices.Under the FRMP's communityforestryprogram, higher productivity,sustainabilityand social inclusionwere found to be mutually complementaryto each other. Tree survivaland groundcover significantlyincreased and yields will likelybe higher, andpoor families and women were the primarybeneficiaries. The key factorleading to increased productivity and sustainabilitywas the switchto communitymanagement by the sociallydisadvantaged, who took greatercare of the plantations than governmentor villagers with higher incomes.. (3) Government-civil societypartnerships can enable large gains in development capacity, both for social inclusion andfor agricultural growth. 88. Bangladeshis known for particularly large inefficienciesin the public sector, and in governance generally.By contrast,the country is rich in its non-government sector, particularlyin its NGOs. Two of the projects reviewed, the SDPP and the ASIRP, indicate that partnerships between government and civil society canbe a major source of increased vitality and productivityin Bangladesh's rural sector. 89. Promotionof the silk sectoris based on a partnershipbetween the Silk Foundation (technical,promotionaland seed production) and the NGO sector, which does most of the extensionand field support,as well as seedproduction. The commercialprivate sectoris fast developing as an additional actor in reeling,weaving, and garment manufacture. The Silk Foundation's technical skillsare conlplementedby the NGO sector's far wider reach and greatercapacityto provide extensionservicesskilled in socialoutreach.Under the horticulturalexport component of ASIRP, horticultural exports were promoted through partner activitiesbetweenHORTEX and the private sector.36Under the DAE component of ASIRP, the partnershipsbetween DAE and NGOs at the upazila level became the centerpiece of the agriculturalextensionprogram. DAE emphasizedto the IEG mission that this 34. Source\.WB ReportNo. 34543-BD; Bangladesh\.Revitalizingthe Agricultural TechnologySystem, November 30,2005. 35 Globalevidence has indicatedthatreturns to research are higher than for any other investmentin agriculture. 36. The partnership for the first exportwas with an NGO. Sincethen, the commercialprivate sectorhas become the dominantsource of horticultural exports. approach could greatlyincrease the effectivenessof agriculturalextension-the DAE providing its technical skills, but others, especiallythe NGO sector, being better in field outreach. 90. By contrast, the FRMP projectwas implemented mostly by the Forestry Department,indicatingthat governmentimplemeiitationwithout partners can alsobe success~l,at least for forestry.However, the pilot activitiesin communityforestry all involve the FD working with small NGOs, the formermainly in technical areas and the latter in local-level social support.The initial experiencewith the FD-NGO partnerships appears promising. 37 (4) To enhancebenefiltsfor women andthe poor, project formulation needs the systematicintegrationof measuresto achieve this. Measures to achieve such social objectivesneed to be organicallyintegratedin the project\. i.e., specificallyfeaturedin the project's design, costing, institutional arrangements, staffing,management processes, the logical framework and monitoring. 91. All threeprojects took somepositive stepsto target women and the poor. These actions, which are typical of other Bank projects, arenoted immediatelybelow, but they were more in the nature of add-ons to project implementationrather than being systematically integratedinto the projects. A more systematicapproach could likely have achieved more. 92. With its labor-intensiveand cottage-based activities,the silk sector is pre-eminent in includingwomen and the poor. Silkrearing and reelingprovide regular income and can be donepart time and on marginal f m s or by the landless. The IEG mission also observed a high proportion of women employed in weaving and garmentmanufacture.Additionally, the NGO extension activities in the SDPPwere specificallytargeted to women and the poor. Based on mission discussions in the field, perhaps over 95percent of beneficiaries were poor, of which over 85percent were women. 93. Concerningthe ASIRP, DAE said that extensionworkers were asked to target women and poor liouseholds.The mission was also told that in choosing communitiesfor sub-project grants, the local (upazila) committeesfavored communitieswith a high proportion of women and the poor, but there is no datarelative to this. Assuming that the sub-projectsdid have some successin socialinclusion, this would have been importantin counteringthe natural societal tendency for minority groupsto be left behind. It is possible that the gender and poverty impact of the ASIRP would have been quitemodest without the project's efforts, sincethe mission visits found the usual tendency for men and wealthier individualsto have the primary influenceon village-level decisionmaking. 94. The FRMPprovided the most striking example of gender and poverty alleviation outcomesinfluencedby project actions. In the mission's visits to several communitymanaged plantations,the great majority of the beneficiarieswere women and the poor. As with the other two projects, the primary reason was that selectionof participants by the Forestry Departmentand local committees strongly emphasized gender and poverty criteria. 37. There is also positive global evidence where forestrydepartmentshave worked withNGOs.; for instance, in India and Nepal. This was appropriatesinceinternational experienceindicatesthat forestry development can have negative social impactsunless there are specificmeasures for social inclusion. The development of government-managedplantations commensuratelyreduces the number of hectares under traditional forests.Even when degraded, such lands provide for traditional forest-based activitiesimportant for the livelihoodsof women and the 95. However, none of the projects employed a systematicapproachto social inclusion, which would likelyhave enhanced gender and poverty alleviationoutcomes. The IEG mission noticed the followinggaps. First, the capacityto plan, implement and monitor the projects' gender and poverty aspectswas limited in both the government and Bank task teams. Themission did not encounterany social specialistsin the project agencies, and data in the ICRs indicatethat the Bank team for the FRMP onlyinvolved a social specialistin project preparation,and for the ASIRP, onlyin supervision.Second,none of the projects had a gender andpoverty alleviationplan, which should also have been integrated into the project's detailed design. Third, therewere no monitorableindicators on poverty and gender impactsin the log fiames, and project data on outcomes was limited. Hence the key features for systematicallyenhancingbenefits forwomen and alleviatingpoverty were largely absent.39 (5) The Bank's rural project portfolio in Bangladesh would merit scaling-up, prioritizing, a longer-termprogram approach, and a better strategicframework. 96. The Bank's lendingto Bangladesh's rural sectorhas declined significantly over the last 5-10 years. (See the completelistingof Bank projects to Bangladeshin Annex C.) Out of 25 ongoingprojects in the Bangladeshportfolio as of February2006, only oneproject is rural (2006 CAS, Annex B8). And only onerural project was approved during the last five years FYOl to FY0540-compared to 23 approvedprojects in the overallBangladesh lending program. None of the three projects reviewed in this PPAR had follow-onprojects. 97. This situationcontrasts sharplywith the messages expressedin Bank and Governmentpolicy documents. The government's 2005 PRSP sees agriculture as the key driver of pro-poor growth. The Bank has also emphasizedthe importanceof the rural sector and highlighted this in each of the last three CASs (1998,2001 and 2006). The 1998CAS comments that faster agriculturalgrowth and rural development are critical in a country where more than 90 percent of the poor live in rural areas. It also commentsthat several 38. Socialrisks alsoneed to be tackled in project.designand implementation. In missiondiscussionswith forestrycommunity groups,a vulnerabilityof the extremepoor to pressuresby locally influentialpersons (to sell forestrights at well below market value for instance) appearedto be a risk. Adaptationsto reduce this risk might be considered,such as strengtheningcommunity-levelinstitutions and making individualdecisions subjectto reviewby the whole community. 39. In this situation,even understanding the social impact of project activitiesis difficult, and making adjustments duringproject implementation has littlebasis on whlch to plan. In the appraisalreports and some government documents, there was also a tendencyto highlightthe expectedgender andpoverty alleviation impacts in the main text, but with limited further reference and implementationdetails in the annexes. 40. This was the Microfinanceproject (approved in FYO1)which is partly rural. Two otherprojects with impact on the rural sector in the FYOl to FY05 period were the Rural Electricity-Renewable Energy Development Project (FY02) and the Rural TransportImprovementProject (FY03). strategicprioritiesprovide the framework for our assistance, of which agriculturewas one. Sincethree of these priorities were macro or cross-cutting(macroeconomic management, private sectordevelopment, and public sectormanagement), agriculturewas one of onlytwo sectors, along with human development,that were singled out. The 2001 CAS considered rural development as one of three priorities for pro-poor growth. Whilethe 2006 CAS is less explicit in highlightingrural development,the first of the CAS's two pillars (improving the investment climate) includes agriculture-along with infrastructure,water resourcesmanagement and informationand communicationstechnology-in its listingof four sectors critical to pro-poor growth. Yet the priorityplaced on agriculture in these policy statementsdoes not appear to have been translated into the lendingprogram. This situationappears likelyto continue, sincethe 2006 CAS has only one rural development project -the proposed National Agricultural TechnologyProject -amongthe 24 projects listed in the proposed lendingprogram for 2006 to 2009 (2006 CAS, Annex B3). It should, however be noted that there are severalpast and proposed projects that supportrural developnlentmore broadly.41Whilethese projectshave potentially significantimpacts on the rural sector,none of theseprojects directlytackles the rural sector's need for a major shift in agriculturalproductivityand pro-poor growth. For this, additional direct engagement in agriculture,water and forestryis needed. 98. The IEG mission frequentlyheard the view that rural sectorlendingis more difficult and its resultsmore disappointingthan in other sectors. The threeprojects reviewed in this PPAR do not support this view. All three projectswere worthwhile, with outcomes at least moderately satisfactory. TheFRMP achieved all its physical objectives,helped improve institutional capacity, developed environmental management plans for Bangladesh's nature reserves,helped develop coastalmangrovesto improveprotection against storm surgesand started successfi~lpiloting of community-based forestry. The SDPP significantlyraised productivity in the silk sector, which had a positive impact on gender inclusion and poverty alleviation.The ASIRP pioneered and catalyzed a breakthroughin horticultural exports, and the agriculturalextensionpart of the project may alsohave had a significant impact. With sensibledesignsthat play to Bangladesh's strengths(such as the NGO sector),with the introductionof technological and institutionalinnovationsas needed, and with strong implementationsupport, ruralprojects in Bangladesh can succeed 99. In fact, the averageperformanceof the three PPAR projects is not substantially different from the aggregate situationacrossthe Bank's entireBangladesh portfolio. Excludingthe PPAR projects, nine of the 17projects completed between the beginningof 2000 and end of February 2006 had a satisfactoryoutcome, six were moderately satisfactory, onemoderatelyunsatisfactory, and one unsatisfactory. 100. The Bank should not downplay the importanceof relevance. If development of the rural sector is a strategicpriority, it does not make senseto neglect it. The question of why support for rural development has declined, is appropriateto pose across the board; not only 41. TheRural Departmentofthe Bank's SouthAsia Regionhas commentedonanearlier draftof the PPAR that it also envisages other operationsinrural livelihoods, water managenlent,fisheriesand landmanagement. The Rural Departmenthas also madereferenceto otherproposedor ongoingprojects supportingrural development suchas rural electrification,rural finance,andlocal governance. to the Bank, but also to other development agenciesand to the government.42It is better for the Bank to support a highlyrelevant development thrust, eachproject having a moderately successfL1o~~tcome,than to support areas of less relevancebecause these are easier.Not supportingrural development in Bangladesh is walking away from one of the country's highest priorities. 101. Bank lendingto the rural sectorhas also sufferedfrom a lack of continuityin recent years. Thiswas not so in the past. Both the FRMP and the ASIRP followed previous projects in their respective sectors,the Bank having supported two projects in forestryand three projects in agriculturalresearch and extensionprior to the FRMP and ASIRP. The ASIRP followedon almost immediatelyfrom the Agricultural Support ServicesProject, which had startedpioneering the new extensionapproaches and had provided initial supportto HORTEX.None of the threeprojects reviewed in this PPAR had follow-onBank support, even though two projects in particular-SDPP and ASIRP-supportedprograms which required a longertime period to become hlly established. 102. The lack of continuityin lendinghas been compoundedby uliduly shortproject durations\.The ASIRP had only a 3%year implementationperiod, and the SDPP 5%years, which included the establishmentof a new agency, the SF, to implementthe project. The 9% years implementationperiod for FRMP was more realistic and about right for the large program that the FRMP supported (thoughthis unusually long implementationperiod could have been broken down into two shorter projects). Thismore realistic time fiamehas probably contributed to the higher outcome and sustainabilityratings for the FRMP relative to the other two projects. 103. The IEG missionnoted the particular vulnerability of the ASIRP's agricultural extension component. In field discussions,it was encouraging to find, four years afterproject closure, enthusiasm still present amongDAE staff for the new extension approachintroduced under the ASIRP. However, as one district officer expressed it, we stillhave the partnerships,but, sincethere is no money, nothing for the partners to do. The ASIRP began a new extensionprogram, followingthe initial stepsthat were taken in the later years of the ASSP, but, inevitably, the program was far from fully establishedwhen the 3%year project ended. StoppingBank lendingat that stagewas unfortunate, since a strongresearch aid extensionprogram is a paramount need for acceleratedagriculturalgrowth in Bangladesh. The FRMP, SDPP and HORTEX programs, although lessurgently in need of continued nurturing,would also have benefited from continuedtechnical and financialsupport. 104. The sparse rural sectorwork in the last decademay have contributed to the Bank's limited attentionto Bangladesh's rural sector.The situationis better now; papers on the rural non-farm sectorand on agriculturaltechnology were issuedrespectively in 2004 and 2005, water management has alsobeen reviewed, and there arethree ongoing studies-on agribusiness, rural finance, and a public sector expenditurereview. Work on an agricultural masterplan has also been done, in partnership with the Government. However, this impressivearray of activityappearsto be pieces of a pie rather than a comprehensiverural 42. ResidentBank stafftoldthe IEG missionthat they hadobserveda decline inrural lendingby most of the donorcommunity.And the Governmentdoes not always apply sufficient funds to the areas it has prioritized;for instance, the muchreduced funding of the agriculturalextensionprogramafterASIRP closed. strategy.What still appears missing is a thorough sector analysiswith sufficient depth and breadth to prepare an overallrural sector strategy. This could also be used to engage the Government and the donor community in a strategic and broad-ranging dialogue on sector policy and lending.
P058476 | LIEPAJA REGION SOLID WASTE MANAGEMENT PROJECT | Europe and Central Asia | Latvia |  | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/350691474488450835/text/000020051-20140618090240.txt | http://documents.worldbank.org/curated/en/350691474488450835/pdf/000020051-20140618090240.pdf | An external stimulus, such as EU accession and related harmonization of local legislation to EU standards, requires extra effort by a project (beyond the achievement of its formal objectives) and may impact project results.A project implementation unit (PIU) should be integrated into the management structure of the ongoing project rather than operate as a separate unit. In this way its competence will be retained within the project and not lost at the end of the contract period.A complex business plan with long term company strategies should only be applied to well established companies. It can prove too complicated for a new start-up operator like L-RAS to take on.Getting project ideas across requires good communications and knowledge of the languages used by project stakeholders. Intensive language training, in English for local managers and in the local language for Bank staff can help.
P058503 | Amazon Region Protected Areas (GEF) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2003 | 2009 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/362181474592585380/text/000146597-20140619164524.txt | http://documents.worldbank.org/curated/en/362181474592585380/pdf/000146597-20140619164524.pdf | Remote, sparsely populated areas pose special procurement and logistical challenges that need to be taken account of in estimating implementation and outcome targets. In the Amazon there are few service providers and it is difficult to launch any effort that requires extensive public participation, preparation of management plans, purchase of equipment, construction of infrastructure and public awareness campaigns. The capitalization of endowment funds for protected areas needs to grow in line with the expansion of these areas and the estimates of requirements need to be regularly updated. In this case, only now, after six years of implementation, is there sufficient financial data to project expenditure needs for the protected areas. Arrangements for consolidating the management of protected areas need to be made when these areas are first designated. Care needs to be taken to avoid creating perverse incentives for protected areas not to graduate from new to 'mature' status. This project provided a level of support to new areas which was much higher than that available to areas on the threshold of graduation: this provided a disincentive for areas to graduate and rewarded the less efficient areas (ICR, p. 29).
P058512 | Education Development Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Human Development | Education | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/498961474420165322/text/000020051-20140613052527.txt | http://documents.worldbank.org/curated/en/498961474420165322/pdf/000020051-20140613052527.pdf | In post-conflict environments where beneficiaries cannot agree on a single course of action, funds to promote educational quality according to the goals of each group may help bring about school-level improvements and local beneficiary involvement.- Engaging groups of beneficiaries in a dialogue on project needs and decentralizing procurement may be an effective way to bring about implementation in an environment of fragmented political structures. A project implementation unit is also very effective under such circumstances.
P058520 | Health Project | Europe and Central Asia | Latvia |  |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/774781474650789717/text/000020051-20140612151340.txt | http://documents.worldbank.org/curated/en/774781474650789717/pdf/000020051-20140612151340.pdf | In undertaking a health reform program, much work has to be done to support the interventions, in explicitly targeting measures to ensure accessibility to health services, and in better explaining the health reforms to both health care personnel and the general public.In a transition economy, the relevance and significance of the Bank's procurement rules may need additional clarification.Management matrices are very useful for ensuring that responsibilities are well understood.
P058521 | Electric Power Reconstruction 3 Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2001 | 2008 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/335901474492159138/text/000146597-20140619155904.txt | http://documents.worldbank.org/curated/en/335901474492159138/pdf/000146597-20140619155904.pdf | High-quality feasibility studies and reconfirmed agreement by the stakeholders are needed to prepare tranche investments within an overall long-term plan for sector reconstruction and reformThe criteria for selection and prioritization of investments need to be based on transparent criteria (a challenge in a post-conflict country with strong ethnic divisions)The success of sector reforms and restructuring depend on high-quality analytical work, meaningful consultation and participation of stakeholders, and political backing and sustained commitment. The design of sector restructuring and the pace of its implementation should be owned and endorsed by the major stakeholders. To successfully introduce Financial Management Information Systems, it is important to first implement pilots activities to demonstrate system benefits. Adequate familiarization of the staff with new technologies should be carried out before introducing a major change in business processes and sophisticated information technology tools.
P058526 | Integrated Drug Prevention Pilot Project | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/806581474635052639/text/000020051-20140607151526.txt | http://documents.worldbank.org/curated/en/806581474635052639/pdf/000020051-20140607151526.pdf | Given that the nature and degree of illicit drug abuse in Argentina did not appear to be as serious as in other countries, the Bank team should have been aware that this would be a low-priority loan, and therefore to proceed without a supporting legal framework at election time would a risky strategy. Eventually it proved a waste of resources for both the Bank and the Borrower.
P058536 | THAILAND - EFAL II | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2000 | 2001 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/886481474850621900/text/000020051-20140529160142.txt | http://documents.worldbank.org/curated/en/886481474850621900/pdf/000020051-20140529160142.pdf | a. During a crisis, a reform program has to be designed with the purpose of handling the crisis. Excessive conditions stretch the Government's implementing capacity to its limit, and force the Borrower to follow equally on conditions that have different degrees of importance for the success of the program.b. When an institution has limited capacity for poverty targeting and limited time to start up the program, the simplest decentralized program may be the most effective. Untargeted programs that require community participation may be more effective in protecting the poor than programs which aim at a better targeting but which are more difficult to manage
P058536 | THAILAND - EFAL II | East Asia and Pacific | Thailand | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2000 | 2006 | PPAR | >=100 million | Moderately Unsatisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/960941468173356799/text/350510REV0pdf.txt | http://documents.worldbank.org/curated/en/960941468173356799/pdf/350510REV0pdf.pdf | Lessons Learned 5.1 The significant cost o f cleaning up financial crises can offset the progress made over many years inpoverty alleviation and other social improvements, both o fwhich are central to the Bank's mandate. Giventhis, the Bank should continue to play a role in client countries inboth improving financial sector governance and soundness to reduce the probability o f crisis and inpost-crisis management and well-structured recovery. 5.2 The severity o fthe crisis was, inretrospect, initiallyunderestimatedbythe Bank and others, as was the negative impact on the economy o fthe large scale closure o fthe FCs inthe early phase o f the reforms. Thai officials interviewed by the IEGmissionnoted that these earlymis-readings o fthe severity o fthe crisis andthe impact o f the closure o f the FCs on the economy raisedconcerns about the credibility o f the IFIS'approach and, most important to Thailand's future, about the financial reform itself. This suggests that crises inother countries should be approached more comprehensively, taking into account potential negative impacts o f large scale closures. 5.3 Short-term crisis management policies can compromise essential structural reforms. The failure to factor into the design o f the reforms the inadequacies o f the Thai legal and regulatory infrastructure led to approaches that may have increasedthe cost o f cleanup. For example, traditional procedures inThailandfor corporate restructuring were notoriously slow and generally benefitedthe debtor; thus, the corporate reorganization procedures modeled after the UnitedStates (Chapter 11style) were ill-suited to the situation and may have served to worsen it (longer-delays, reducedrestructuring). A betterapproachwould havebeento simplify liquidationprocedures, involvingthe stakeholders and a bankruptcy administrator, rather thanthe court system. 5.4 The sequencing andtimingo freforms i s critical. Too little early emphasis was placed on reformingbankruptcy and foreclosure laws, developing a deposit insurance scheme, and fostering development o f capital andmoney markets. The governmentthat came to power just after the crisis emergedwas reform-minded, but the adverse macroeconomic impact o f the earlypolicy changes gave reform a badname inThailand. 5.5 The allocation ofpieces o fthe reform package among the three International Financial Institutions (IFIs) may have made sense, but only ifit hadbeen followed by better coordination. As it turnedout, the division o fresponsibilitiesresulted inan absence o f a clear guidingvision for the reform o fthe financial system. Thus, for example, commercialbank restructuringwas carried out very differently from finance company restructuring, even when they suffered from the same problems. Inaddition, the division o f labor broke down, as the Bank fairly quickly became involved inFIrestructuring and capital market development. 5.6 Succeeding loans with increasinglybroader goals and a growing list o f conditions diffusedthe focus o freform andunderminedmeaningfulmonitoring; abetter approach would have been the programmatic one now usedwidely (but not available at that time), which seeks to develop a coherent set o fpriority reforms and sequences the steps for carrying out those reforms ineach successive loan.
P058544 | KH - Cambodia SAC | East Asia and Pacific | Cambodia | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2000 | 2004 | 2005 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/505731474851774967/text/000020051-20140612150449.txt | http://documents.worldbank.org/curated/en/505731474851774967/pdf/000020051-20140612150449.pdf | One-tranche operations are better suited to borrowers with very low institutional and administrative capacity as they allow more flexibility during preparation and supervision and avoid the embarrassment of multiple extensions of the closing date.
P058587 | Regional Fiscal Technical Assistance Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2000 | 2011 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/383181474665067918/text/000020051-20140625082615.txt | http://documents.worldbank.org/curated/en/383181474665067918/pdf/000020051-20140625082615.pdf | All lessons cited in the ICR are supported. A crucial lesson is the importance of a mutually reinforcing package of properly sequenced analytical work, technical assistance, policy lending, and parallel assistance from other donors. As part of such a mutually reinforcing package, technical assistance can be vital to build up technical capacities so that subnational units can benefit from the financial incentives available in quick disbursing operations. By focusing on technical rules and frameworks, such support packages can provide a measure of stability and predictability to help maintain technical standards despite the uncertainties of politics.
P058627 | Health Sector Development Program | Eastern and Southern Africa | Tanzania | IDA |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/670631475100505305/text/000020051-20140612150700.txt | http://documents.worldbank.org/curated/en/670631475100505305/pdf/000020051-20140612150700.pdf | When there is a general move by IDA and other donors towards general budgetary support, as with a Poverty Reduction Strategy Credit (PRSC), certain sectors (health in this case) may become at risk of being "neglected" by the government, ie the Ministry of Finance. It is important that Ministry and Health and donors (including IDA) continue to take action to ensure the required funding for health is not diminished. This tendency by MOF to neglect the health sector is already evident in this project where, with donor financing increasing in the sector, government spending (as a percentage of total sector spending) has decreased - (applies only to 2004)Human resources issues in the health sector pertaining to incentives and improvement of service delivery, cannot be fully resolved without corresponding reform/action taken within the civil service as a whole.As reforms require new and diversified skills, investments in staff training have to be wholly integrated with the reform program with the appropriate resource allocation.
P058681 | Education Sector Support Project | East Asia and Pacific | Malaysia | IBRD |  | Human Development | Education | IBRD | IPF | 1999 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/494541474501029702/text/000020051-20140613052835.txt | http://documents.worldbank.org/curated/en/494541474501029702/pdf/000020051-20140613052835.pdf | Lack of familiarity with various Bank guidelines and documentation requirements is a frequent reason for slow implementation and delays. Borrower staff need training early on to anticipate and resolve potential conflicts between Bank guidelines and local procurement procedures.In large-scale staff development programs, international training may be found to be too costly to implement on a large scale, and some inappropriate staff may be selected. Care should be taken to ensure that specificselection criteria are well established, and that the subsequent selection process closely follows theestablished criteria.
P058683 | SECOND MUNICIPAL INFRASTRUCTURE DEVELOPMENT PROJECT | Middle East and North Africa | West Bank and Gaza |  |  | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/699661474508944038/text/000020051-20140613080002.txt | http://documents.worldbank.org/curated/en/699661474508944038/pdf/000020051-20140613080002.pdf | Significant progress can be made even in a very difficult environment if adequate local leadership exists, and if the Bank team is sensitive and responsive to the problems and takes quick and decisive action. This can occur most effectively when there is close on-ground Bank supervision and communication with clients.Capacity building can be achieved even during crisis if the participating institutions are accountable and have a strong incentive to perform. MPWH's capacity was built on-the-job, based on strong leadership and a determination to establish itself as an organization. It is not enough to just develop performance indicators to monitor project outcomes and impacts. Building good monitoring and evaluation system also requires establishment of base-line data to appropriately measure the project impact during implementation and after completion.The project experience demonstrates that it is important to obtain firm commitment from local partners prior to implementing components that (partly) depend on their inputs.
P058684 | GZ-COMMUNITY DEV. II | Middle East and North Africa | West Bank and Gaza |  |  | Human Development | Social Protection & Jobs | SPF | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/604971474490959993/text/000020051-20140612071914.txt | http://documents.worldbank.org/curated/en/604971474490959993/pdf/000020051-20140612071914.pdf | The project was intended to be a Community Driven Development (CDD) operation. The Evaluation Summary identifies one project specific and two CDD relevant lessons.Project specific lessons: In conflict and post conflict situations, where the ongoing security and political situation creates a high degree of uncertainty, a Bank operation has to be realistic right from the design stage about sustainability expectations. A follow-on operation called the Integrated Community Development Project (ICDP) is being supported in West Bank and Gaza. Given the current political situation in the region, sustainability could be an issue even in that intervention and this risk should be factored in the approval process of other follow-on projects.CDD relevant lessons:(i) It is important to clearly recognize that the CDD approach cannot work effectively in all situations.Given the uncertain and politically volatile environment in which it was being implemented, the project in West Bank and Gaza consulted with communities about their preferences but could give them little actual control over decisions and resources. Community preference for sub-projects could not also be realistically met for a variety of reasons, some of which are noted here: other agencies were already active in supporting interventions in the health and educations sectors and the Bank was to supplement rather than replace their work, road rehabilitation had been neglected in the past and required urgent attention, the uprising made village access roads even more critical (para 4.2, ICR). Ultimately, there was a significant disconnect between local community priority and actual sub-project execution by sector (graph page 4). (ii) Even in demand driven interventions calculations of rates of return should be emphasized at least at the project completion stage. In the Second Community Development Project no ERR was undertaken ex-ante on the ground that the sub-projects were to be demand driven. However an ex-post ERR can be calculated and should be attempted to get a reliable indicator of efficiency.
P058706 | Forest Conservation and Management Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2010 | 2011 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/239371475069787934/text/000020051-20140624162125.txt | http://documents.worldbank.org/curated/en/239371475069787934/pdf/000020051-20140624162125.pdf | The ICR provides a number of valuable lessons from the project experience. The most pertinent are adapted here.Forest sector projects should avoid overly ambitious designs that aim to address multiple challenges in a single operation. Recipient implementation capacity is often insufficient to address such complexities within the given time frame and limited resources can be spread too thinly. Design should be more focused to ensure sustainable project outcomes.Forest sector reforms require strong political and technical leadership and need to be in line with government priorities. A transparent consultative process should be carried out continually so that staff at all levels feel ownership and consider change as an opportunity rather than as a threat.Constant engagement and supervision is critical for projects implemented during times of significant policy change. This includes utilizing outside expertise with strong in-country experience, mobilizing senior Bank management, and ensuring flexibility in the design to respond to changes in priorities while retaining the overall goals.Community involvement in forest management involves complex social, institutional and regulatory issues. Sufficient time and expertise to build capacity and raise awareness must be built into the project. Developing cost-sharing mechanisms between government and communities cannot be decided within the sector alone. It needs to be based on established and transparent criteria that are acceptable to all parties. Inter alia, this requires collaboration from the outset with the Ministry of Finance. Fund-raising efforts for the endowment of conservation funds must be varied, and commence ina timely fashion if targets for capitalization are to be achieved. There are often restrictions on bi-lateralfunds being invested directly into endowment funds and therefore alternative, creative ways to attract and contribute to the overall fund must be developed, targeting all potential sources of monies including foundations and the private sector.
P058706 | Forest Conservation and Management Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2010 | 2011 | PPAR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/980011468025820126/text/6276900PPAR00P0e0only0900BOX361506B.txt | http://documents.worldbank.org/curated/en/980011468025820126/pdf/6276900PPAR00P0e0only0900BOX361506B.pdf | 5. Lessons 5.1 The experience of the TFCMP/EAFCMP suggests the following lessons\. Â· A reform agenda that depends on the buy-in of key individuals can be stalled unless there is\. (a) a contingency plan for the loss of political will and (b) sufficient flexibility in project design to enable adjustments to changes in the level of ownership. In the case of the TFCMP/EAFCMP, the right mix of people appears to have converged during preparation but the project did not prepare for the likelihood that personalities would change. Â· Late and incomplete restructuring can result in a failure to complete project activities within the project timeframe and, as a consequence, to achieve project objectives. In this case, the Bank proactively refocused credit proceeds on activities that were under control of the project implementation unit and could improve forest management within the existing institutional structure, but the objective of changing the institutional structure remained unchanged. Some of the activities added through restructuring were delayed by procurement challenges that had plagued the project since inception. Â· The use of demand-driven approaches for forestry or natural resources management activities may be constrained by insufficient demand, as communities often have other priorities. Â· Small grant monitoring that narrowly focuses on ensuring that grant monies were used for their intended purpose, is insufficient to demonstrate outcome level results and is a lost opportunity for learning. In the case of the EAMCEF, an opportunity was also lost to learn which activities generate greater returns in terms of conservation and livelihoods goals. In the case of the TASAF PRM window, an opportunity was lost to gather information that would allow for a comparison of two different modalities to deliver support for the establishment of PFM agreements. Â· The financial sustainability of endowment funds can be compromised without sufficient and early attention to developing the fund-raising skills of Endowment Fund staff. 5.2 The experience of the two pieces of sector work yields the following lessons\. Â· High quality analysis is insufficient on its own to prompt action from government decision makers. The policy note and follow up political economy analysis were both viewed as high quality documents that addressed a relevant topic but that alone was insufficient to generate results. More attention should be given to how to foster ownership of the process and objectives up front. Â· Reform of sectors in which responsibility cuts across multiple agencies may be difficult without a sustained dialogue through multiple sector units in the Bank (forestry, environment, energy). 5.3 The following lessons emerge from the experience of both the TFCMP/EAFCMP and the Sector Work\. Â· Changes in mind-set may be difficult to bring about without a strategy for generating broad-based consensus up front. In the case of the TFCMP/EAFCMP, consensus was there during preparation but was lost once core members on the borrower and bank side moved on. While consultation workshops were held during preparation, interviews with stakeholders suggest that a relatively small group of people fully bought into the reforms, understood what they were trying to accomplish, and were involved in the project's design. When key personalities changed there was an insufficient base of people who understood and bought into the proposed reforms to inform new leadership. In the case the sector work, the Bank attempted to change the way that charcoal is viewed by presenting reform of the sector as a missed opportunity. Despite producing high quality documents there has been no buy-in from decision makers. A strategy is required to engage government decision makers from the beginning and keep them engaged throughout the process. Â· One project cycle may not be long enough to bring about institutional changes. Similarly dissemination of analytic work without a program for sustained dialogue may also limit results. One project was not long enough to ensure that the new institutions had sufficient capacity to be effective and ensure a shift in the way that forests are managed. Similarly the brief period of dissemination was insufficient to ensure that the charcoal studies remain visible and are on hand for political windows of opportunity.
P058724 | Cultural Assets Rehabilitation Project | Eastern and Southern Africa | Eritrea | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2008 | 2008 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/655851474505479025/text/000020051-20140618091031.txt | http://documents.worldbank.org/curated/en/655851474505479025/pdf/000020051-20140618091031.pdf | A number of lessons were identified from this project experience, including:Culture cannot be managed by different bodies under different institutional set-ups, and it is important to have a common institutional umbrella for management of the culture sector.The project demonstrated that cultural activities, such as school competitions, public discussions at archaeological sites and dissemination of oral history and traditions, can be used as a unifying force in post conflict societies to promote national identity and tolerance.LILs should have a simple design, as a few activities are adequate to test an objective. As experimental projects, the design and supervision of LILs should be flexible as the project purpose is to learn. It should be open to changing arrangements and adapting activities within the project in order to meet the objectives in the most feasible manner. Bank management should provide sustained engagement, even when projects are small. The perception that this project was marginal to the Bank's portfolio in Eritrea may have led to a missed opportunity to promote cultural heritage for national-building and unification of a post-conflict situation.
P058730 | Niger Agro-Pastoral Export Promotion Project | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/354791474509060039/text/000020051-20140615105312.txt | http://documents.worldbank.org/curated/en/354791474509060039/pdf/000020051-20140615105312.pdf | Based partly on the completion report, the following three lessons are emphasized: Adequate funding and importance has to be given to developing an effective monitoring and evaluation system with appropriate indicators to ensure not only that the project is on track but also to assess how far the various components contribute to achievement of project objectives.Project experience points to the need for adequate management oversight in ensuring that findings of QAG reviews are given adequate attention. Several weaknesses in project design could have been overcome if the findings of the Quality Enhancement Review had been taken seriously. Close attention to ensuring good quality at entry can help avoid implementation problems down the road.Sustainability considerations must be thought through from the beginning of the project. This includes sufficient care in the process of formation of groups/associations, capacity building efforts and in-country capacity to undertake implementation.
P058730 | Niger Agro-Pastoral Export Promotion Project | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2000 | 2006 | 2008 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/898421468290735785/text/443660PPAR0P061sclosed0July03002008.txt | http://documents.worldbank.org/curated/en/898421468290735785/pdf/443660PPAR0P061sclosed0July03002008.pdf | 6. Lessons and Considerations for Future Development 6.1 Several lessons -bothpositive and negative -relating to project design have emerged from this review\. (1) Empoweringcommunitiesto take controlof the implementationof their own developmentplansimprovescommunityownershipandmotivationto engage in sustainabledevelopmentpractices. 6.2 As demonstratedbythe example o fboththe PPIP andthe NRMP, eliciting demand for low-cost small-scale irrigationtechnologies by farmers inthe PPIP, and putting communities incharge o f designing, recruiting and paying for the implementationo f their collectively developed community development plans inthe NRMP, resulted inthe successhl achievement o f project objectives. Inboth cases, intensive sensitization and awareness campaigns as well as regular direct contact with the targeted beneficiaries were at the base o fprojects' activities. 6.3 Inthe caseofPPIP, welltargeted andinnovativepublicity towards farmersincluding radio and TV broadcasts, road-side demonstrations, and seasonal leasing o f equipment with no obligation to buy-played a decisive role intechnology promotion and a steady increase intheir adoption despite the population's low literacy rate. Farmersmade investments inthe purchase and installation o f small-scale irrigation equipment almost totally from their own funds and through the community saving andcredit unions (SCUs) which they formed. Funds for these SCUs were mobilized almost totally by farmers themselves, with the exception o ffive out o fthe 27 SCUs established, which benefitedfrom small donor trust hnds. 6.4 Inthe caseofNRMP,theintroductionofCBPPputgrassrootsbeneficiariesatthe center o f the action, and significantly improved community ownership and motivation to engage insustainable natural resource management practices, as demonstrated bythe fact that 77 percent o f the requests for financing from project funds were presented after the CBPPwas put into effect. An unintendedbeneficial effect was the unique opportunity to depart from the common practice o f relyingupon cumbersome government procurement procedures and large businesses and contractors based inthe capital. The selection o f local enterprises instead had a positive impact on the local economy. (2) Fast-trackinvestmentoperationsmay easily miss achievingtheir development objectives. 6.5 APEP took only about six months for its preparation anddesign. As a result, the project design ideas didnot mature enough. The preparationprocess failed to define the broad lines o f an export strategy for ago-pastoral products, and the poor design didnot match country capacities and business conditions. Nor didthe preparation team anticipate the seriousness o fthe implementation risksit identified, almost all o f which came to pass while the proposedmitigation measureswere not effective, which contributed heavily to an unsatisfactory project outcome, despite the strategically relevant objectives. Inaddition, one riskrelatingto the capacity ofthe PMUto screensubproject proposals was not identified. This contributed to a significant cost overrun o fproject management costsby about US$2 million, equal to twice the original allocation. 6.6 A project such as APEP shouldhavebeen apilot operation, or a first time-slice ofa longer APL investment operation, giventhe difficult environment it hadto navigate through. This includedthe first attempt to take acommodity chain approach to marketingand exports, a nonexistent export strategy, a highlyinformal export sector, inadequate availability of local technical andmanagerial expertise, a highly individualistic culture among stakeholders, an insufficient entrepreneurial spirit, a low literacy rate, and an insufficient exposure to foreign market standards. A pilot could have preparedthe ground, determining the best commodities to concentrate on, and focusing on linking exporters to producers. Subsequentinvestments could have then assisted stakeholdersover a longer haul to maximizerevenues from exports. (3) Export developmentneedsto follow a well-definedstrategy, and a commodity chain approachneedsto emphasizeproducer-exporterlinkages. 6.7 Theprevailingeconomic situation inNiger hadestablished an enabling environment for export development. The GONhadengagedina comprehensive tax reform, reducing and simplifyingexternal trade restrictions inpreparation for regionalintegration underthe West African Economic and MonetaryUnioninthe 1 9 9 0 ~ ~ the devaluation o f the CFAF in and 1994hadboostedthe competitiveness o f exports on regionalmarkets. However, APEP was not able to positionNiger to take advantageo fthese favorable conditions for two main reasons\. the absenceo f a coherent export strategy, andmissinglinks betweenproducers and exporters. 6.8 APEP didnot help define an export development strategy early on. Thus, it allocated its matching funds on subprojects on an ad hoc basis, spreading its resourcestoo thinly and not focusing on commodities that hadthe best export potential, such as onions and the livestock sector. A misplaced add-on focus onpoverty alleviation, not includedinthe originalproject design, exacerbatedthis situation, leading to the approval o f subprojects, even ifthey had a weak dossier,just becausethey were submittedby groups whose members were said to bepoor. As aresult, enterprises that were somewhat skilled, hada certain business acumen, were already active inthe commodity subsectors, and hadthe highest potentialo fbringinginincreasedexport revenues representedless than 25 percent o f total beneficiaries financed through APEP. 6.9 Although APEP was praised for its institutional buildingo fproducer andexporter associations, it neglectedthe importance oflinkingthem together to develop sustainablesupply chains with free-flowing informationon opportunities andmarket standards, so that exports o f highqualityincrementalproductionwouldresult. These linkagesdidnot form spontaneously either, as traders still triedto sell what they could get from farmers, not what the market asked for, and little or no feedback was givento farmers on marketneeds andstandards. Here, the project didnot take into consideration, for example, the traditional informalapproachto marketing, or the levelo findividualism, illiteracy, andpovertywhich were not conducive to a speedyandefficient interaction andcooperationbetween stakeholders. (4) Similar agriculturaldevelopmentprojectsinneighboringcountriescan have oppositeoutcomesdue to the qualityof projectpreparatioddesign,the levelof engagementof the implementingagencies,andthe prevailinglandtenure securitysituation. 6.10 Itis interesting to notethat similar projects with similar development objectives small-scale irrigationpromotion and agricultural products export promotion -implemented intwo neighboring countrieswith similar socio-economic conditions-Niger andMalihad opposite outcomes.57 6.11 Niger's PPIP, which was approved inFY95, had a highly satisfactory outcome while Mali's PPIP, which was approvedtwo years later inFY97 had a highlyunsatisfactory outcome. The major differences betweenthe two projects which resulted intheir opposite outcome ratings concern the level o f engagement o fthe implementing agency and the degree o f landtenure security. 6.12 Niger's PPIP implementing agency, ANPIP, was fully engaged inproject activities and worked very closely with the farmers. The successhl testing o f simple low-cost and high-return small-scale irrigationtechnologies, the encompassing andeffective demonstration and dissemination o f tests results, and the creation o f advisory services groups helpedmotivate farmers and generate highinterest in, anddemand for, the small-scale irrigation technologies to the extent that Nigerien farmers investedinthese technologies from their own meager resources. Although these activities were built into the design o f Mali's PPIP, the project's implementing agency -the Agricultural Supply Chain Promotion Agency-was not fully engaged. It was implementing another Bank project, the Agricultural Trading and Processing Promotion Pilot Project and didnot devote sufficient time to PPIP, work closely with the farmers, or activate project activities on time to generate demand for small-scale irrigation from farmers. It showed little interest inPPIP which resulted inits highlyunsatisfactory outcome. 6.13 Another factor that played a decisive role inthe respective outcome ratings o fboth projects was landtenure security. Niger, aided by the international community, had decided to put land tenure security at the heart o fnational development, andwas fully committed to provide farmers andpastoralists with the incentive o f land tenure security -whether land ownership or land-use rights -to motivate them to invest intheir lands and livestock herds. Niger's government simplified the process bydecentralizing it to the community level through the establishment o f Village LandTenure Commissions, and subsidized its costs. Since the GONis fully committed to this process, it has also built inlegal measures to protect the rights o f land ownership seekers. Suchwas not the case inMali which decidednot to tackle this thorny subject yet. As a result, Malian farmers hesitated to invest inlands that they didnot officially owninfear o fhavingtheir land-use rrrights'rrevoked when these lands gained invalue due to the investments inirrigation. This was demonstrated bythe fact that Mali's PPIP generated initial highinterest and demand by farmers to participate inproject activities -which included a small land tenure component to encourage farmers to start the process o f formalizing their landtenure situation. Once farmers understoodthat this 57. IEGassessed the outcomes of the two Maliprojects in 2007 ina previous PPAR o f three agricultural development projects inMaliReport No. 40206, dated June 25, 2007 -which has beenpublicly disclosed. The same consultant, Jumana Farah, preparedbothPPARs. component was not going to finance all the costly and centralized process, which outcome would not benecessarily respectedbythe village chiefs, farmers lost interest inthe project anddidnotparticipate inPPIP. Mali's PPIP resultedinonly 10hao frehabilitated irrigated landandno new investments insmall-scale irrigationschemes, comparedwith the expectation at appraisal o f 400 ha o frehabilitated irrigatedland andthe establishment o f 600 ha o fnewlyirrigated land.By contrast inNiger, it is estimated that an additional 1,100 ha were put into use through the promotiono f small-scale irrigationtechnologies. 6.14 As to the agricultural export promotionprojects inMali andNiger, Mali's Agricultural Trading andProcessingPromotionPilot Project which was approved inFY95 hadamoderately satisfactory outcome, whileNiger's Agro-Pastoral Export PromotionProject which was approved inFYOl had an unsatisfactory outcome. This was despitethe fact that bothprojects faced the same challenging environment to their implementation, i.e., a highly informal sector, limitedaccess to information, technical and marketing know-how, weak professional associations, inadequate access to credit, lack o f export infrastructure, andineffective quality control o f exports. The opposite outcomes can be attributed to shortcomings imbeddedinproject preparation anddesign. 6.15 To start with, Mali's ATPPP took four years from inceptionto Board approval which made it possible to holdparticipatoryworkshops with potentialprivate sector beneficiaries, to establish an export promotionstrategy and action plan, to test private initiatives inagroprocessing, to test internal and export markets and transport modes, and to conduct specific studies. This in-depth preparation processhelpedthe design ideasto mature, and to realistically assess the country's capacities andother implementation risks which allowedthe elaboration ofmitigationmeasuresthat provedeffective. Most importantly, ATPPP was designed as apilot operation due to the challenging environment it hadto navigate through. Despite the testing o fproject ideas, the conduct o f studies, and the elaboration o f an export strategy, the design team still felt necessaryto widenthe testingthrough ATPPP rather than engageina fill-fledged operation. Incomparison, Niger's APEP took only six months from inceptionto Boardapproval. The hastyprocessresultedina shallow analysis o fthe implementation risks andineffectivemitigationmeasures. A key factor o f success such as the elaboration of a solid andintegrated export strategy which should have guided the funding of subprojects didnot get proper attention. 6.16 Inaddition, Mali's ATPPP financed therehabilitation or establishment ofcollective export infrastructure such as handling/processing and storage facilities, while APEP included a matching grant facility that dispensedhighly subsidized finds to individual associations of producers or exporters. This probably influenced the divergingoutcomes o f the two projects. Itmighthave causedMalianexporters to work harder to maximizetheir profits from the use o fthe collective assets which were accessibleto the differentgroups at predetermined and set times, while the Nigerienexporters were secure inhavingthe assets on their own lands whether they made use o fthem or not. Finally, staffing o f the regionalbranches o f the projects' implementingagencies seems also to have influenced project outcomes. Mali's ATPPP regionalbrancheswere each staffed with 3 high-level staffinaddition to 4 support staff, while Niger's APEP regionalbrancheswere only composedo f one project representativewith 2 support staff. APEP's regional staffwere not able to get aproper handle onproject activities, nor to follow beneficiaries closely.
P058770 | Improving Learning in Primary Schools (LIL) | Western and Central Africa | Mali | IDA |  | Human Development | Education | IDA | IPF | 2000 | 2003 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/816351475097000494/text/000020051-20140612104227.txt | http://documents.worldbank.org/curated/en/816351475097000494/pdf/000020051-20140612104227.pdf | Government ownership of the concept of transitional bilingual education and commitment to this cause, despite poor funding and some resistance in government and the community, is slowly transforming an education system in which most children had been doomed to failure due to their lack of French language ability;Learning in one's native language reduces levels of student drop-out and repetition, and thus improves the internal efficiency of education; however, since unit costs are initially higher, governments must be able to act strategically, paying more in the short run for added savings and benefits a few years later; In a multilingual environment where there are relatively few dominant native languages, large coverage can be gained by focusing on them (in Mali the use of 4 national languages covers about 80 percent of primary school students); this could be an example for other countries in the region; The impact of transitional bilingual programs on learning gains should be documented with firm evidence in which well defined treatment and control groups are tested and results compared to baseline performance. A well funded and trained M Teachers who have been trained and supported in implementing transitional bilingual education and active learning can become champions for this approach to basic education and catalysts for change among their colleagues; however, short one-off training sessions are not sufficient to allow a new educational approach to take root; Learning and Innovations Loans can deepen a reform process and effectively lay the ground work for the technical features of larger sector investment programs.
P058841 | KH-NORTHEAST VILLAGE | East Asia and Pacific | Cambodia | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/640961475092616890/text/000020051-20140613070109.txt | http://documents.worldbank.org/curated/en/640961475092616890/pdf/000020051-20140613070109.pdf | Based on the ICR, the following lessons are noted :The building of adequate community participation requires time and resources. Setting up grass root organizations is just the first step. More time and resources are needed to strengthen and consolidate gains so that their sustainability over the long run is assured. The Bank should systematically and realistically assess the costs and benefits of undertaking participatory projects. The expereince of the NVDP project shows that there are several key constraints to sustained participation which do not appear to have been taken into account. These include: (a) the high opportunity cost of participation; (b) the low likelihood of significant return on participation in the form of further investment in the village; and (c) literacy and low base-level capacity. Project experience shows that there are substantial variations in capacity between VDCs of different villages. Poorer and more isolated villagers lacked basic skills and capabilities among VDC members. Therefore, VDC formulation and training in poorer and/or isolated villages requires more intensive facilitation to achieve results. Local contribution (in form of cash or material/labor) also varied by villages. Therefore, project design should allow for greater flexibility by varying amounts required according to individual households ability to pay, allowing for substitution of labor for cash contribution and including incentives for contributing cash, such as a matching fund formula rather than a fixed percentage of a predetermined amount or project size.
P058841 | KH-NORTHEAST VILLAGE | East Asia and Pacific | Cambodia | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2007 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/364411468239356558/text/40125.txt | http://documents.worldbank.org/curated/en/364411468239356558/pdf/40125.pdf | 7. Looking Forward and Lessons Learned 7.1 Project design and implementation ina low-income post-conflict country continue to present a unique set o f issues for the Bank or any development agency. These projects are highlyvisible as animportant shareo fthe total capital flow into a sector; they tax the limited capacity o f the Borrower's institutions and infrastructure, there i s often very little local experience on which to build, and they challenge the emergingregulatoryand administrative framework within which they are to be established. Experience with the four projects reviewed inthis report point to the importance o f particular aspects o f design and implementationthat could strengthen the Bank's effectiveness inthis type o f environment. (1) Use of the Learning Instrument Loan. Two o f the four projectsreviewedinthis PPARwere LILs\. the NortheastVillage Development Project and the Forest Concession Management and Control Pilot Project. While the case was made for usingthis instrument inboth appraisal documents, it was a contributing factor inthe problemsencounteredbythe forestryproject. Usingthe LILpermitted the deferralo f the social impact assessment. Itwas logical to defer social impact assessmentsto the context o fthe individual concession management plans that wouldbe producedunder the project, rather than to conduct a hypotheticalassessment ex ante based on average or exceptional conditions among all 14concessions to be treated under the project. Nevertheless, this deferral left the project vulnerable to criticism on safeguard issues and, inpractice, as the InspectionPanelReport noted, a safeguardpostponed i s a safeguard denied.34The Bank has since introduced the use o f framework assessmentsto be conducted beforeproject approval to addressbroad issues that will be more specifically attended to duringthe course o f implementation and this would almost certainly have flagged the muchvaunted issue o fresin trees as well as other competing claims inconcession areas. Infbture, the useofLILs or anyinstrumentthat circumventsany oftheusual safeguard investigation duringpreparationshouldbe subject not only to the normal tests o f eligibility, but also the test o f downside risks, be these technical or the likelihood o f adverse public opinion. (2) The Importance of Continuous Contact for Effective Implementation. A problem which arose due to o f the Bank's small portfolio inCambodiawas that a resident office was not established until2003, so that most project development, appraisal and supervision prior to that time was conducted through visiting missions. When coupled with the fragile institutional framework inpost-conflict Cambodiaandthe limited counterpart pool, this periodic mission approach to relationships and task development was very inefficient. Credibility, knowledge transfer, consensus buildingand decision-makingwere all seriouslyhampered, evenwhen teams came frequently from Bangkok. Where the client is not familiar with Bank operations and procedures or i s confronting serious impediments to its ability to act on that knowledge, continuous presence o f competent Bank representatives i s a critical factor inmovingdialogue andoperations forward. Theresults o fthe FEW,which didhave the benefit o f a resident sector staffmember, confirm this benefit. (3) Sector and Country Strategies as a Management Tool for Operations. Sector or country strategies are often seen as the leading edge for policy dialogue and the identification o f investment opportunities, but their usefulness duringproject implementationmaynot be as widely recognized. As long as operations are set initially ina sound strategic context andtheir implementationproceeds smoothly, nothing is lost by temporarily setting strategy aside. Butwhen ambiguity or disagreements arise inimplementation, particularly with the evolving focus or 34. InvestigationReport, The InspectionPanel, March 30,2006, Report No. 35556, pagexxii. importanceof an activity, an agreed strategy canbecome an effective management tool. Inthe case o f the two projects whose overall outcomes were unsatisfactory, usingthe strategies inthis way duringthe course o fimplementationmighthave given staff and counterparts the basis for reorientingtheir efforts and increasingthe efficacy o fthe operation. Revisitingthe country strategy might have ledthose working on APIP to look more closely at how the Ministrywas going to use its enhanced capacity.35And it mighthave kept those working on the FCMCPP from losing focus on their tasks amid the barrage o fpublic criticism.36 Mid-termreviewshave beenan important innovationinBankwork, basically intendedto reflect on objectives and strategy inlight o f implementationexperience. Usingcountry and sector strategy as part ofimplementation support takes this a step krther by keepingthe collective eye o f stakeholders o n where the tasks at hand are intendedto take the Borrower. (4) A GradualApproach to Change. Institutions generally respondmore favorably to moderate or gradual change than to radical innovation, particularly when power or stature are being threatened. The FCMCPP was designed to take a step-by-step approach to reforming the industrial exploitation of the country's timber resources, and this review concurs with the Region's contention that this was the correct approach. Deeply rooted rights and practices were at issue andthe challenge to achieving a resource management focus inthis lucrative industrywas going to take time andpersuasion. A firm and resolute explanationo f the gradual approach might have appealed to calmer heads andmitigatedthe groundswell o f support for the unrealistic alternative. (5) Dealingwith InformalTransaction Costs as a Development Issue. To an outsider, informal transaction costs may be seen as corruption, butto a participant they may be an accepted form o f sharing or a means o freaffirming one's role ina group. While fiduciary accountability requires correct procedures and oversight, the development impact o fthe Bank's approach to the issue i s very much linkedto the sensitivity with which it introduces the qualities o f transparency and cost-effectiveness as desirable qualities inprocurement transactions. This is a time-consumingprocess that depends on mutual trust that i s very difficult to buildeither longdistance or inthe context o f public criticism or embarrassment. The collaborative approach betweenthe Region, the Bank's Department o fInstitutional Integrity, and the Borrowerprior to May 2005 hadresulted inthe introduction o f guidelines andprocedures that were steadily increasingthe degree o ftransparency inproject-relatedprocurement, in contrast to the acrimonious stand-off that prevailed for over a year following the release o f INT's findings o fwrong-doing to the public.
P058842 | MINDANAO RURAL DEVELOPMENT PROJECT | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2006 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/208071475075768696/text/000020051-20140613065045.txt | http://documents.worldbank.org/curated/en/208071475075768696/pdf/000020051-20140613065045.pdf | Where complex institutional change across many distributed entities is attempted, project design must provide for sufficient time for the changes to set in. This will improve the chances for realizing the expected benefits from decentralization.A learning-by-doing approach is an effective way to operationalize and facilitate devolution of responsibilities, especially where a large number of units are involved.Strengthening grass roots organizations, local governments and communities is vital to meaningful participatory and integrated development, and improves chances for better governance and accountability.M&E activities are almost always given lesser priority compared with other more concrete project activities. It is not enough that attention is given to the design of the M&E system in project design and preparation. Full operationalization and usefulness of the M&E system and the MIS are directly linked with the level of priority, financial resources and good quality staff associated with the exercises.
P058843 | CN-Guangxi Highway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/969231474586268344/text/000020051-20140618085248.txt | http://documents.worldbank.org/curated/en/969231474586268344/pdf/000020051-20140618085248.pdf | An up-front cash deposit by the contractors strengthens the likelihood that environmental safeguard measures contained in civil works contracts will be carefully executed.
P058844 | Third Henan Provincial Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/134721474595660135/text/000020051-20140618062727.txt | http://documents.worldbank.org/curated/en/134721474595660135/pdf/000020051-20140618062727.pdf | The ICR offers a number of useful lessons of which three are presented below:Traffic safety should be addressed in an integrated approach involving all stakeholders (police, health, education, and transport departments).Overloading of trucks can cause significant damage to pavement structure and can also contribute to the number and severity of traffic accidents. To prevent overloading damage, proper enforcement of load limits is crucial.Local roads in poor rural areas are effective in enhancing economic opportunities in poor areas. Therefore, highways projects should not just focus on investments in expressways but should also consider connecting rural road components.
P058845 | Second Jiangxi Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2007 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/721401474630114054/text/000020051-20140618055540.txt | http://documents.worldbank.org/curated/en/721401474630114054/pdf/000020051-20140618055540.pdf | The ICR identified well known/documented lessons which include: Design changes and technical specifications during construction need to be checked more rigorously to make sure they reflect the same standards as were applied to the original design.Bank supervision missions should regularly visit the construction sites to identify problems early on and to provide timely advice.The foreign consultants need to be carefully selected and their activities supervised. Also, they should be penalized for the performance of unsatisfactory work.
P058846 | CN-Natl Railway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/957081475084659323/text/000020051-20140619082439.txt | http://documents.worldbank.org/curated/en/957081475084659323/pdf/000020051-20140619082439.pdf | The project supports several lessons of general interest and use.1. The prescription for efficient implementation of a physical project : thorough project planning and design, including the safeguards; well-designed incentives for the contractors such as completion targets; use of an environmental supervision engineer (for the EMP) to back up the supervision engineer of the civil works.2. Environmental Management Plan must be part of the contract documents. The use of an environmental supervision engineer (ESE) ensures its successful implementation. Because of its success as a pilot under this operation, ESE is now being used in other projects to supervise --and with authority to require-- the implementation of the EMP . As a result more attention is being paid to environmental safeguards, freeing up more time of the supervising engineer of the project's civil works to concentrate on technical issues.3. Input-based targets for institutional components are of limited use in measuring results; an outcome-based approach discussing institutional and policy options in workshops and seminars is more productive. The result of not meeting the prescribed reform indicators within this project placed an undue strain on the relationship between the Bank and the Ministry of Railways which at one time threatened to discontinue both borrowing and the Bankâ€™s support to railway policy development. After an assessment of the mutual benefits of the relationship, the Bank reacted proactively, reflecting an understanding that changes in the country and within the Bank, and internationally about railway reforms, necessitated a new approach.
P058847 | CN-3rd Xinjiang Hwy Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2003 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/358821474943210498/text/000020051-20140624162312.txt | http://documents.worldbank.org/curated/en/358821474943210498/pdf/000020051-20140624162312.pdf | The less developed western provinces of China can close the knowledge gap rapidly by sharing experiences from other provinces and elsewhere. This was exemplified in the Third Xinjiang Project, especially in the areas of road maintenance management and transport facilitation.Diligent geological survey and proper design for low volume roads should not be neglected in areas of known geological instability.Improving road safety, especially on four-lane highway sections requires blending a combination of design and operational knowledge. When moving from a controlled expressway to a road featuring at-grade intersections, engineering design and appropriate signage play a critical role. Similarly, wider roads are not necessarily safer roads without appropriate complementary measures.Target indicators should be carefully chosen to avoid ambiguous or non-attributable results. In this regard, experience from past projects elsewhere should be carefully considered before a final selection is made.
P058877 | Emergency Flood & Earthquake Recovery Project | Europe and Central Asia | Turkiye | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2004 | 2004 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/662761474649430475/text/000020051-20140612131030.txt | http://documents.worldbank.org/curated/en/662761474649430475/pdf/000020051-20140612131030.pdf | 1. Methodologies are needed for addressing the problem of reconciling post-disaster damage and needs assessments, and tailoring project implementation to the refining of the needs estimate, such as by phasing construction and instituting checkpoints for incremental stages during implementation of construction components. 2. A strong, experienced, and independent PIU familiar with Bank procedures is especially critical to effective implementation of fast-track emergency projects; staffing should be balanced to include experience and skills in both technical aspects as well as in institutional strengthening.3. Construction supervision by international consultants can lend credibility to reconstruction activitiesâ€”necessary in an environment of distrust of local code enforcement and construction quality. Beneficiaries were comfortable with the quality of construction for this reason. 4. Activities that do not perform well in the early stages of an emergency project may perform very well later on; patience, along with careful monitoring and support, is called for. 5. In order to guarantee the sustainability of apartment blocks and their environment/landscaping arrangements, site and block management organizations should be established.6. Ensuring stakeholder understanding of overall project goals requires that they be engaged to some degree in project implementation. 7. The maximum momentum in an emergency project is normally in the first few months after the disaster. In view of this, any substantive changes that need to be introduced into the project design should be incorporated during this period. 8. The design of residential sites under emergency construction should recognize that the sites will become permanent settlements and allow for the long-term needs of beneficiaries in the broadest sense, and allow for the higher costs of such an approach. This includes the provision or enabling of commercial development and social facilities, as well as complete environmental services such as adequate drainage and durable site amenities and finishes. 9. The Bank needs to develop appropriate, operationally-oriented protocols, procedures and design criteria for responding to situations demanding large emergency construction programs, that can be applied soon after a disaster to ensure that design meets the needs of long-term urban development, as well as the short-term emergency needs; this would include methodologies for reviewing Borrowerâ€™s estimation of needed construction volumes, a design check list covering both technical and social/environmental criteria to ensure comprehensiveness; governments in hazardous areas could consider developing building and site plan prototypes that are designed and engineered and kept for use when needed.
P058877 | Emergency Flood & Earthquake Recovery Project | Europe and Central Asia | Turkiye | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2004 | 2005 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/406751468311433007/text/326760TR.txt | http://documents.worldbank.org/curated/en/406751468311433007/pdf/326760TR.pdf | 10. Lessons 10.1 The following lessons arise from both the experience o f individual projects responding to natural disasters in Turkey and from the collective experience o f the four projects over time. Bank involvement during the emergency phase can be highly beneficial. Expeditious cash support proved valuable to disaster victims o n an individual financial and psychological level as w e l l as o n a macroeconomic level. A cash transfer project, while r i s k y if continued for the long term because o f the potential to create dependency, can be a u s e h l means to providing stability and safety to victims. The Cash Transfer project provided support to victims in a time o f intense need. The promptly provided support enabled people to survive, put funds into the economy, and was reported as highly preferable to in-kind support by beneficiaries. The Bank needs to develop a clearer understanding o f which aspects of emergency response can be rushed, and which cannot. Analysis o f the projects reveals a need to get on the ground quickly, but then take the necessary time to prepare. The prompt fielding o f Bank teams enabled more effective donor coordination, which proved useful to the Government o f Turkey in organizing funding for the recovery effort. However, quickly prepared plans for reconstruction met with huge delays. More time spent in the design phase could be afforded and might be time w e l l spent. An emergency creates pressure to opt for speed at the expense o f detail, yet it i s the details that determine the outcome o f a project. Taking the time to develop a finer textured design could have lessened a number o f problems. Greater accuracy of damage assessments is still needed to avoid unnecessary construction. Although there has been progress, and the Marmara response had the most comprehensive damage assessment o f any o f the projects, more precise estimates o f public and private infrastructure requirements would lead to significant (financial and social) cost savings and a faster retum to normality. Addressing the social and economic recovey aspects o f emergency projects, although difJicult, is criticalfor the sustainability of the reconstruction investments. The Bank has a long and positive experience in terms o f the execution o f physical components o f projects the physical design o f the housing in Erzincan, TEFER, and MEER i s appropriate and o f good quality. The failure to create legally required social organization necessary for upkeep and decision-making in the housing areas caused problems, however. Although considerable learning took place from one project to the next, incorporating lessons learned from a number o f studies, and involving social scientists in the project process, creating the necessary sustainable users organizations to manage infrastructure remains an unsolved challenge. Creating a capacity for maintenance i s often as critical to long-term vulnerability reduction as the quality o f the initial construction. Reducing vulnerability to earthquakes requires different approachesfor rural and urban areas. For rural areas, project approaches that were notably successful and worthy o f replication in future projects include\. 0 Incorporating seismic-resistant building training into the rural housing component 0 Linking payments to easily definable construction progress 0 Rebuildingin situ For urban areas, successful strategies include\. 0 Preserving pre-disaster social networks, proximity to jobs. 0 Promoting policies that favor the creation o f markets, shops, and related commercial development and services. 0 Fostering stable urban communities by creating a safe space for parents and children (playgrounds, parks, sports fields). Likewise, basic site amenities such as landscaping, parking, erosion control/adequate drainage, contribute to a positive environment. For both rural and urban areas\. 0 Providing a reasonable range o f design options to cover differences in family size and occupations. 0 The creation o f a sense community and o f trust contributes to infrastructure maintenance, and even community survival. CASs in disaster prone countries should thoroughly address disaster risk. Given that each project notes that a disaster o f that magnitude was not anticipated in the CAS, there appears to be room for increased anticipation o f disasters in the CAS, and better overall preparedness on the part o f the Bank. With the frequency o f disasters in Turkey, they should not be treated as an unexpected interruption o f business as usual. Bank task managers need guidance o n recovery strategies, expedited contracting procedures, and disaster-resistant design criteria when responding to large emergencies. The scale o f urgently needed construction in the immediate post-disaster context can be expected to exceed governmental management capacity at the outset. Creating New Disaster Management Institutions takes more time than is available under one project. Although i t was anticipated that Bank involvement in Erzincan would help to prevent the recurrence o f similar damage in the hture by increasing capacity for hazard mitigation, such a goal proved impossible to obtain in one project cycle. As it turns out, in Turkey institutional development took place slowly across many years and several projects. During the period when emergency reconstruction needs are high, institutional development issues can be neglected. Focus i s on getting people housed. Nevertheless, through the implementation o f several projects, the idea o f preparedness has taken root, and become a topic o f discussion. Turkey's focus i s moving from crisis management to disaster preparedness. Cash Transfer projects can make an extremely important contribution to recovery. Lessons from the one experience are\. 0 I t was possible to effectively and accurately administer emergency cash transfers o n a large scale. 0 Using institutions with cash transfer experience, and that already have the necessary human resources and management systems in place, was critical to smooth delivery o f the assistance program. 0 Getting cash support to victims quickly, positively affected the economy and perhaps even affected people's sense o f safety and security. I t was a prominent f i r s t sign o f the government's support in a time o f acute need. 0 The process was streamlined by SSF staff, volunteers, other government agencies, and NGOs worked together. I none project site, application processing, bank account creation (for allowances), and result notification were combined into one procedure. 0 Because cash transfer runs the risk o f creating dependency, public awareness campaigns are required that make clear up front the number o f months that payments will be made. When beneficiaries know this, they can make informed resource allocation decisions. Otherwise, going month to month without clear information o n the duration o f payments can lead to dependency beyond the short-term. Beneficiary knowledge was not adequately valued or used. The barns, though w e l l built, are not being used to house animals because the engineers who designed them did not realize how cold the winters were in Erzincan. In Sutqiiler the waste water treatment plant was not wanted by the municipality, which refused to cover its operating costs or to staff it. W h i l e it may have been the lowest cost technology to build, maintenance costs could not be covered by local funding. Overestimating infrastructure needs can lead to major social problems. Each post-disaster assessment process was significantly flawed. All the projects that built new infrastructure significantly surpassed the existing demand. There i s an incentive for agencies to overestimate because allocating surplus u n i t s provides rent and other benefits. Before that can happen, however, overestimation o f beneficiary needs led t o empty units, smashed glass, broken doors, looting, and a succession o f social problems associated with crime and insecurity. The shops and businesses need a low-crime environment and a critical mass o f functioning u n i t s to become successful as a mall. With too many units built, the concentrations o f businesses were low, thus taking away from the success o f the whole.
P058898 | Rural Infrastructure Rehabilitation Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/486871474490104458/text/000020051-20140619110708.txt | http://documents.worldbank.org/curated/en/486871474490104458/pdf/000020051-20140619110708.pdf | The report does not outline any general lessons but two might be drawn:Where the Bank has little previous experience with a Borrower, it is advisable to ensure that the project provides for adequate professional input to support project management and the Bank should monitor this input carefully to ensure that progress is on track; andIn particular, where the traditional institutional style in the borrowing country is authoritarian and the project calls for development of local community groups, adequate provision should be made for continuous professional oversight in this area.
P058969 | Cultural Heritage Preservation Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2007 | 2009 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/511831474576749987/text/000020051-20140619073258.txt | http://documents.worldbank.org/curated/en/511831474576749987/pdf/000020051-20140619073258.pdf | The restoration, conservation and touristic promotion of cultural heritage sites can be a valuable asset to economic growth and development. This project was originally not focused on a return on the restoration investments, or on generating a stream of income to cover the costs for maintenance of the sites or as a contribution to local and regional economic growth. The project did manage to add this type of intervention going beyond civil works during implementation. However, adding such activities at the beginning of the project would have led to broader and more sustainable results.Engaging communities in economic and social activities around cultural sites is key to a successful cultural heritage site project. No other activities have been as successful in building widespread understanding, stewardship and real commitment to conservation.The importance and reliability of data and its collection should be agreed upon in detail and up-front with implementing agencies. The domino effect of this initial lack reaches far into the future.For instance, in this project, poor or no control over ticket sales at sites was a major obstacle to analyze the financial sustainability of the sites. Very stringent procurement rules can prevent corruption, add to project savings, and show the importance of adapting procurement rules to country circumstances. It also strengthens the Bankâ€™s fiduciary role in monitoring of contracts in the context of poor governance. Institutional strategies and longer-term Bank engagement are needed to build comprehensive and effective capacity in this sector.
P059055 | Emergency Flood Assistance Project | Europe and Central Asia | Tajikistan | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2002 | 2003 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/988451474553430405/text/000020051-20140607151232.txt | http://documents.worldbank.org/curated/en/988451474553430405/pdf/000020051-20140607151232.pdf | Respond to the emergency phase with timely advice, not a slap-dash project. In a post-disaster context, responding too quickly can lead to projects that ultimately contribute little that is useful from a social and economic point of view. Floods and landslides occur in all areas of Tajikistan with regularity. Speedily replacing and repairing damaged infrastructure over and over again is hard to see as useful. What would be needed is to help the GOT to learn to deal with the fundamentals of disaster management, and support the preparation and implementation of comprehensive, affordable and sustainable natural disaster prevention and mitigation strategy. Heed clear warning signs. IDA should not entrust the implementation of challenging emergency projects to newly created PIUs that have no staff with even minimal expertise, particularly when the government refuses technical assistance support. Short-sightedness in this regard can create project implementation conditions whose deficiencies cannot be overcome by supervision.Build in flexibility. Although the Bank often demonstrated flexibility, the situation on the ground required more. Disaster responses often have to address totally unforeseeable needs. Faced with extremely weak government institutions lacking the necessary resources both human and material, (given timely problem identification) selected emergency components could instead be carried out, on behalf of the Government, by branches of international organizations or NGOs having the necessary managerial expertise. It can be anticipated, however, that emergency reconstruction will be dynamic, and supervision of emergency projects necessarily resource intensive. Staff on the ground helps: supervision arrangements for ERLs often benefit by providing for a substantial involvement of Country Office staff in day-to-day follow up.Learn from past mistakes. The project adopted the same procurement arrangements identified in the ICR for the Tajikistan Post-Conflict Rehabilitation Credit (IDA 30370) as being of debatable effectiveness--separating the procurement of construction materials from the procurement of works. As could have been anticipated, the arrangements proved to be too complex and cumbersome and, rather than preventing mismanagement, opened the door to it.
P059055 | Emergency Flood Assistance Project | Europe and Central Asia | Tajikistan | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2002 | 2008 | PPAR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/813231468133797066/text/438380PPAR0P051lcosed0July022020080.txt | http://documents.worldbank.org/curated/en/813231468133797066/pdf/438380PPAR0P051lcosed0July022020080.pdf | 6. Lessons 0 It is importantfor the Bank to be at a disaster site early, but afalse sense of urgency may compromisethe quality of what is being constructed.Infrastructure design, implementation, and supervision take time. Rapid reopening o f transport linkswas important for Tajikistan inthe short term, but given that floods and landslides damage the same roadsrepeatedly, scarceresources may have beenbetter usedto find longterm solutions, such as reinforcing hillsides or relocating roads away from hazardprone areas. Although detailedplanning would have been more time-consuming, it would more likely have preventedrepeated repairs inthe future. This experience i s reflected inthe Bank's revisedpolicy on emergency lending (OPPB 8.00) o f March 2007, which ensuresthat reconstructionprojects are no longer pressed into a threeyear time limit. Involve local specialists in the identijkation and designofjlood reconstruction projects. Tajikistan inherited a highly centralized institutional structure from Soviet times. This is why, duringproject preparation, subprojectswere identifiedand designedinthe capital Dushanbewithout consulting highly skilledtechnical people in far-flung valleys o f rural Tajikistan where the floods occurred. Inhindsight,project identification and design would likely have been improvedhad local staff been consulted. 0 A water strategy that integratesjlood management with the county's irrigationand hydropower needs couldpreventfuture jlooding rather thanproviding only temporary relie$ Floods and landslides regularly occur throughout Tajikistan. It would have been useful to helpthe government learn to deal with the fundamentals o f disaster management and to support the preparation and implementation o f a comprehensive, affordable, and sustainable natural disaster prevention and mitigation strategy that also took other water management aspects into account. 0 Donor coordination is important not only with respect to damage and needs assessment but also in the transitionfiom the relief to the recoveryphase of a disaster.More coordination betweenthe World Bank and the ADB would have been beneficial, especially since both organizations shared the same RPCU. 7. BroaderIssuesArising from the Evaluation Integrated Water Resource Management in Tajikistan 7.1 Tajikistan i s rich inwater. Annual flow volumes consist o f 64 cubic kilometers per year o f water from some 25,000 watercourses, 1,300 lakes, and 24,000 glaciers with a volume o f 845 cubic kilometers. Much o f the water runs through riparian countries o f Afghanistan, Turkmenistan, Uzbekistan, and Kazakhstanto the Aral Sea. Water has obvious benefits, but also the potential for destruction. For example, there are 142 settlements inTajikistan that flood constantly and 490 settlements that flood seasonally.12 Flooding is not the only risk. Environmental degradation, contamination o f water sources, earthquakes, pests and drought also create setbacks for the rural population and have a particularly debilitating effect on the poor. Severe energy shortages inthe winter lead people to cut down trees on fragile hillsides. Goats and sheep graze the hills and destroy grass cover. When water pours down inwinter and snowmelt from glaciers sets on in spring, water carries with itmudfrom the hills, destroying infrastructure and settlements. 7.2 World Bank strategy papers such as Country Assistance Strategies (CASs) and the country's ownPoverty Reduction Strategy Papers (PRSPs) have addressed different aspects o f water at different times (see Table 1). While the first CASs focused on more efficient use o f water supply for irrigation, the 2003 CAS more fully considered the root causes o f flooding, such as environmental aspects o f soil degradation and deforestation. The most recent 2007 CAS progress report explored the watedenergy nexus and highlightedthe great potential for hydropower development. Tajikistan could be generating 317 billion kilowatt hours per year, but currently produces only 5 percent o f its p0tentia1.l~While every CAS has given some attentionto flooding and other natural disasters, the link betweenbetter water management and the potential for hydropower has not been explicit. Thus, future CASs could take a broader view o f water management by integrating the different aspects o f water management into one strategy. Table 1. Potentialfor an IntegratedApproach to Water Management CAS Irrigation WSS WRM Hydropower . . Flooding/ ND Environmental Degradation 1996 CAS X X X X 1998 CAS X X X X 2003 CAS X X X X 2005 CAS X X 2007 CAS Prog. Rep. X X X X Source\.IEG 12. The Ministry ofIrrigationandWater Managementof the Republic of Tajikistan, UNDP, theExecutive Committeeof the International Fund for Saving the Aral Sea. 2006. Water Sector Development Strategy in Tajikistan. Dushanbe. 13. Ministry o fIrrigationand Water Managementofthe Republic of Tajikistan, et al. 2006, p. 15. DisasterManagement 7.3 Project design focused on simplicity and flexibility, but did not take account o f the medium-and long-term issues o f disaster management. Medium-.and long-term flood management was left to the ADB, which approved a parallel project inthe amount o f $6.25 million inDecember 1999.14Inaddition, the ADB, usingJapanese trust funds, completed a Strategy for ImprovedFlood Management's inFebruary 2002. That strategy describedthe institutional arrangements for disaster management inTajikistan, cooperation among international donors, and forecasting and preparedness mechanisms for institutions and local communities. Among the 10 recommendations offered by the strategy (see Annex F), little progress can be recorded for six (implemented mostly by international donors and NGOs). Two recommendations have been fully implemented\. one on changes to Tajikistan's legal and policy framework, the other on the Lake Sarez riskmanagement program, which was fundedby the World Bank and other donors. One recommendation that has not been acted upon concerned institutional reform. Tajikistan has four agencies that deal with flood warning, evacuation, and rehabilitation.16Nothing has changed so far with respect to developing an institutionally integrated approach to flood management, as recommendedby the strategy. The ADB's evaluation department criticized the flood strategy for not havingbeenput into operation and assessedthe overall outcome o f the consultancy as uns~ccessfU1.'~Notwithstandingthe ADB's evaluation, the IEGmission was informedby the Tajikistan CES that an emergency flood plan would be ready for implementation by January 2008. 7.4 After the floods o f 2005, which damagedone World Bank-funded embankment, the ADB began implementation ofa follow-up operationthat involves developing a 14. The World Bank 1999\.MOP for SupplementalCredit. This document states the during discussions with thejoint IDA-ADB appraisalmissioninAugust 1999, the Governmenthas recognizedthat borrowing finds for recurringnaturaldisasters, thoughextraordinaryinthis case, is not sustainablewithout aflood management strategy. Followingthese discussions,the Governmenthas requestedthe assistance ofIDA and ADB for astudy that would develop acomprehensive flood managementplan.The study would most likely include(a) areviewofthe current situation; (b) recommendationsfor short -,mediumand long-term mitigation measures; (c) improvements inhydrologicalcriteriafor works; (d) improvementsindesignsand techniques for roadandbridgeconstructionas well as embankmentremediationmeasures; (e) designof a flood forecasting andwarning system; and (0an actionplanthat helpsthe Government coordinate agencies and organizations when a flood occurs. 15.Inaddition, a grant amountingto $205,000 was providedby Japan (TA 3319-TAJ). This grant was to finance adisaster specialist for sevenmonthsto develop aflood managementplanandto provide TA to the implementationunitjointly usedby the ADB and the World Bank. 16. Key agencies responsiblefor flood relief andmitigation are the following\. The CES, the Ministry of Water Resources and LandReclamation andthe Agency for Hydrometeorology. As a more recentADB-funded study on flood management inTajikistanfound, the institutions' specific roles and responsibilitieswith respectto flood management are not completelyspecifiedinthe underlying legislationand are not integratedor well coordinatedwithin a coherent system. ADB TA 4811-TAJ,2007\. KhatlonFloodManagementProject.DraftFinalReport.Mott MacDonald. 17. Accordingto the ADB's evaluationreport, The TA hadlimited impacton capacity building, and the draft ofthe disaster management planpreparedunderthe TA has yet to be convertedinto an operationally usefuldocument. The TA is rated relevant, less effective, and inefficient, and its sustainability is unlikely. Overall, the TA is ratedunsuccessful. detailedflood management plan for Tajikistan's southern regionKhatlon. This time the ADB is working inparallelwith JICA, which also developeda flood managementplan and is implementing an operation inthe same region, though at somewhat different locations. Cooperation betweenthe more than 70 international organizations and NGOs with in-country representationis facilitated by a donor coordination group called REACT (Emergency Assessment and Coordination Team). REACT, which was founded in2000 by ECHO, meets every monthwith the CES. Minutes from these meetings as well as disaster statistics are posted on the UNDP's local website, a novelty for a country that usedto keep its statistics and information highly aggregated and secret. 7.5 The EFAP did not include any component on institutional strengthening. However, at the time o f project negotiations, the government decided to place the newly created RPCU underthe Executive Office o f the President o f the Republic. Itwas to coordinate international assistance and oversee the implementationo fprojects to rehabilitate and reconstruct infrastructure after disasters. As the IEGstudy Hazards of Nature, Risks to Development found, involvement o f the highestlevels o f government is important for successful project implementation. Inthe EFAP, however, government officials would have deemed it more appropriate to have the PCU report to the Ministry o f Water Resources and LandReclamation, which specializes in structural aspects o f water management. Inaddition, local engineers experienced inreconstruction after flooding wanted to be consulted on subproject selection. Such consultation would have been easier hadthe RPCU been set up under a line agency rather than the President's office. Thus, while inmany disaster situations a direct link to the highest levels o f power i s important, line agencies in Tajikistan may be better equipped, given their technical know-how, to provide for medium-and long-term rehabilitation needs. 7.6 The Bank may be well advisedto plan carefully for the transition from the emergency to the recovery and reconstructionphase o f a disaster. Under the new OP/BP 8.00, no time limit will hurry a project to completion. Therefore, more time can be taken to carefully planprojects, taking mediumand long-term mitigation measures into account. 18. ADB Loan4811-TAJKhatlonFlood ManagementProject. 19. DisasterManagement in Tajikistan\. www.untj.org/react.
P059073 | Dar es Salaam Water Supply and Sanitation Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2011 | 2012 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/512971474504993607/text/000020051-20140624203944.txt | http://documents.worldbank.org/curated/en/512971474504993607/pdf/000020051-20140624203944.pdf | The ICR draws a number of useful lessons from the experience of this project, from which the following are summarized with some adaptation:Proper attention must be paid to creating the necessary conditions to attract qualified bidders for WSS lease contracts in a difficult operating environment. When qualified and experienced operators warn of risks, and indicate their unwillingness to participate unless these are addressed, they should be heeded.The Bank should be willing to withdraw from or suspend preparation of operations supporting lease contracts when the selection process is not fully transparent, where the preconditions for contractual failure are clearly present, and where the Authorities do not heed the Bankâ€™s advice for addressing them.The Bank should always prepare, or cause to be prepared, a full contingency plan which can be put into effect should the proposed PSP arrangement not materialize or collapse. This is especially important in a politically sensitive sector such as WSS and has already been done in a number of cases. It was not, however, done for this project.The establishment of a robust and well coordinated system for developing, collecting, updating and using operational and commercial data for monitoring operator performance and progress in PDO achievement is a central requirement of any operation supporting performance-based contracting. The monitoring system should be reinforced by carefully designed and supervised surveys of beneficiaries and households.Consistency between the terms of the lease contract on the one hand and the regulatory framework on the other should be ensured.The legal and other aspects of requiring a parent company of a lease contract operator to post the performance bond should be thoroughly examined.
P059127 | AGRIC.RES & TRNG. II | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2009 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/528381474903472685/text/000020051-20140620085229.txt | http://documents.worldbank.org/curated/en/528381474903472685/pdf/000020051-20140620085229.pdf | Based on the lessons in the ICR the following are emphasized:Project design should include a formalized incentive structure to ensure effective coordination between complimentary institutions. The experience of ARTP II demonstrated that despite best intentions, formal structures for inter-agency collaboration need to be strengthened at all levels and responsibilities need to be clear for key players to enhance efficiency and effectiveness of implementation.Government funding is needed for the sustainability of research institutions. It is important to explore different avenues to generate higher funding for research, for example through tax on commodities, as in the case of coffee, and at the same time reduce dependency on development partners. The government funding for NARO's salaries increased from 50 to 90% over the project time and is expected to reach 100% by FY10. However, it is not enough to only fully fund salaries as it is also necessary to fund other recurring research costs.A sound M&E system requires a formal incentive structure to adequately monitor the project impact. Although the project envisaged the establishment of a functional and sound M&E system that would adequately report against development objectives, the absence of an incentive system hindered M&E activities. The lack of accurate data limited NARO's ability to reflect on its achievements.
P059143 | Second Poverty Alleviation Microfinance Project (Microfinance II) | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/881391474650410573/text/000020051-20140620082019.txt | http://documents.worldbank.org/curated/en/881391474650410573/pdf/000020051-20140620082019.pdf | Three are three important lessons: (i) It is a mistake to attach a new component to a project which is essentially otherwise completed. In this case, this did not detract substantially from the overall project, but it did raise processing issues while short-changing the rickshaw pullers who did not benefit as fully as they might have if assistance had been prepared more carefully; (ii) Credit by itself is not enough and needs to be accompanied by training and other facilities, especially in pursuit of changes in profession, as in the case of rickshaw pullers under this project; and (iii) Support for and by a key Apex institution, PKSF in this case, is essential to reach a broad range of the population through a number of POs.
P059149 | KARNATAKA STRUCTURAL ADJUSTMENT LOAN II | South Asia | India | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2002 | 2003 | 2004 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/176331475088995096/text/000020051-20140612070818.txt | http://documents.worldbank.org/curated/en/176331475088995096/pdf/000020051-20140612070818.pdf | The fiscal target utilized in the project was the consolidated fiscal balance, which includes the power sector financing requirement. This was an appropriate and meaningful indicator of the state's fiscal situationThe project included a very large number of conditions and components, which makes supervision and monitoring of project achievement more difficult
P059161 | Introduction of Climate Friendly measures in Transport | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2003 | 2009 | 2010 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/876991474634865835/text/000020051-20140620070333.txt | http://documents.worldbank.org/curated/en/876991474634865835/pdf/000020051-20140620070333.pdf | Bank knowledge and previous experience in a sector or country should be leveraged to produce a strong design. The involvement of many stakeholders adds to project complexity but also ensures greater adoption and buy-in. Political opposition can be mitigated by vesting implementing agencies with the authority to work at a technical level across the boundaries of state and other jurisdictions where opposing political parties may be involved. For example, in this case, while political opposition between the parties in power in Mexico State and Mexico City respectively threatened to hamper the project, one commission was given technical level jurisdiction in both zones, a factor which assisted the achievement of the projectâ€™s objectives. A well-designed and implemented M&E system is a valuable aid to policy makers.The success of a project can be greatly enhanced by an implementing agency with high capacity The creation of an enabling environment for public transport â€“ including appropriate regulatory, institutional and technical frameworks, is an essential precondition for realizing substantial gains in environmental management and performance.Among the major benefits of environment-enhancing transport projects are improved public health and reductions in health care expenditures. These benefits should be identified and quantified wherever possible.
P059223 | UG-Nakivubo Channel Rehab SIl (FY99) | Eastern and Southern Africa | Uganda | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/200471475088638799/text/000020051-20140613032425.txt | http://documents.worldbank.org/curated/en/200471475088638799/pdf/000020051-20140613032425.pdf | Institutional reform takes time and overambitous targets in too short a time period will jeopardize achievement of reform objectivesBuilding a communications strategy to enhance stakeholder buy-in to changing business-as-usual should be considered early in a project - probably during appraisal - where involved institutions are well defined (e.g. urban and city management). The Dhaka air pollution reduction operation was a notable good example of what can be achieved.
P059242 | Madhya Pradesh District Poverty Initiatives Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/890851474493153890/text/000020051-20140619105915.txt | http://documents.worldbank.org/curated/en/890851474493153890/pdf/000020051-20140619105915.pdf | A design strength of this project was that the project management unit (PMU) was operationally autonomous without being isolated from government or constituting a parallel administrative channel: the heads of the main line agencies were represented in the leadership structure of the PMU.The key to sustainable enhancement of rural livelihoods is to focus on market linkages that provide income opportunities for beneficiaries. This entails: (i) identifying the partners and the products they need to buy; (ii) developing agreements with the partners; (iii) addressing beneficiary skill gaps; and (iv) helping beneficiaries to supply partners. Transparent targeting of the poorest individuals in a community can be achieved through a participatory wealth ranking process that allows villagers in a general assembly (Gram Sabha) to decide who are the poorest among them. If control over environmental management is not handled directly by the project management unit but is outsourced to an external agency there may be a lack of follow-up on agreed actions; on the other hand, the external agency may add value by bringing skills to bear that are beyond the remit of the PMU.
P059305 | District Upland Development and Conservation Project | East Asia and Pacific | Lao People's Democratic Republic | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/448731475088522613/text/000020051-20140612150016.txt | http://documents.worldbank.org/curated/en/448731475088522613/pdf/000020051-20140612150016.pdf | The success of pilot projects (and of operations supported by Learning and Innovation Loans) hinges on the quality of learning that takes place and the testing of the project process, rather than the physical results that are obtained. To be successful, pilots need to be preceded by some analysis of institutional constraints and the prospect that lessons learned will feed into the design of government programs. Modest investments in health and education facilities can be more powerful ways to win the support of communities than agriculture and conservation initiatives, which take longer to establish and may produce less palpable results; but whether better health and education equip communities to manage their natural environment better is unclear.
P059323 | CLOSED(T) STRUCTURAL ADJUSTMENT LOAN | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/712041474419860905/text/000020051-20140528121521.txt | http://documents.worldbank.org/curated/en/712041474419860905/pdf/000020051-20140528121521.pdf | For countries with endemic corruption, the challenge for external assistance is to induce recipients to focus on institutional reforms to create responsive and accountable governance. The balance of payments and fiscal crises offer windows of opportunity to build Bank-country partnership to face this challenge.
P059323 | CLOSED(T) STRUCTURAL ADJUSTMENT LOAN | South Asia | Pakistan | Blend |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 1999 | 2006 | PPAR | >=100 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/313441468065937476/text/34101.txt | http://documents.worldbank.org/curated/en/313441468065937476/pdf/34101.pdf | Lessons 0 A series o f one-tranche loans in a programmatic framework can be an effective instrument for support reforms o f a country with a poor track record. However, effectiveness o f a series o f one-tranche loans depends on a willingness to withhold lending until a critical mass o f previously-agreed prior actions have been undertaken. The delay between the SAL and the first SAC was particularly effective in this respect. 0 Complex or politically-difficult sector reforms are best supported through dedicated sector operations. A multi-sector operation can play only a secondary or facilitating role when dealing with institutional development (as in tax reform or civil service reform), deep-rooted reluctance to reform (as in power), need for specific funding to offset costs o f adjustment (as in banking), or weak service delivery (as in health and education). O f course, even a dedicated sector operation can succeed only if there i s commitment to reform.
P059477 | Second Water & Sanitation for Low Income Communities Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2000 | 2011 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/185281474594143095/text/000020051-20140625061712.txt | http://documents.worldbank.org/curated/en/185281474594143095/pdf/000020051-20140625061712.pdf | Projects with decentralized decision-making and implementation arrangements can still benefit from a centralized management and accountability structure for some overall functions. In this case, attributing all implementation responsibility to the Ministry of Health at the national level, and district-based health offices at the local level, maintained strong community participation while also ensuring focus on the objective of improving public health.Flexibility matters, particularly when implementation experience and international evidence indicate new approaches. Beginning in the mid-2000s, there was increasing evidence of the success of the Community-Led Total Sanitation (CLTS) approach in other large Asian countries, an approach that focuses on community-led behavior change related to sanitation and hygiene rather than building toilets. This projectâ€™s initial approach of financing access to sanitation facilities through a revolving fund showed only limited results. The projectâ€™s decision to pilot CLTS in some project villages, and subsequent decision to assist the national government in adopting an extended version of the approach (STBM) nation-wide, was considered to be instrumental in making progress toward the development objectives (ICR, p. 23).Trust fund resources can be a crucial complement to project resources. In this case, the AusAID trust fund was used to strengthen capacity in technical and management areas at all levels. This strengthened capacity facilitated the introduction of innovative approaches such as CLTS/STBM.Impact evaluations can play a vital role in understanding the contribution of a project. It is critically important, however, to establish credible baseline data, and to define control areas carefully.
P059481 | RURAL ACCESS PROJECT | South Asia | Bhutan | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/766501474944767030/text/000146597-20140617120748.txt | http://documents.worldbank.org/curated/en/766501474944767030/pdf/000146597-20140617120748.pdf | The development of rural roads network in a country with scattered population and mountainous terrain is very expensive and yet critical for boosting rural economy and improving the welfare of rural populations.The Bank and other development partners can play an important role in promoting environmentally sustainable approaches for road construction.Geological surveys should be carried out prior to road construction especially in mountainous terrain to avoid implementation delays and costly remedial mitigation measures.If a number of stakeholders are involved (e.g. head office, field office, PMU, site engineers), the responsibilities and roles of the stakeholders need to be clearly defined and reporting linkages established for smooth project implementation. The combination of long-term and short-term Technical Assistance can be an effective means of strengthening borrower capacity.
P059501 | Technical Assistance for Economic Reform Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/852471475111412679/text/000020051-20140619084901.txt | http://documents.worldbank.org/curated/en/852471475111412679/pdf/000020051-20140619084901.pdf | While a "process" TA operation provides flexibility and allows the Bank to be more responsive to its client, it is extremely important to develop, record, and monitor a clear implementation and financial management strategy for sub-project execution.Even in process projects, the results framework and the links between inputs, outputs, outcomes, and impact need to be discussed in the Project Design Summary and in participation agreements. This is necessary to rate the project outcomes. Additionally, in such process projects, sub-project participation agreements must include a clear results framework linking sub-project outputs and outcomes to project objectives.Bank management needs to monitor whether its recommendations in the ISRs are being implemented.
P059510 | WASTEWATER DISPOSAL IN TOURISM CENTERS PROJECT | Latin America and Caribbean | Dominican Republic | IBRD |  | Sustainable Development | Water | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/650441474908788001/text/000020051-20140613082840.txt | http://documents.worldbank.org/curated/en/650441474908788001/pdf/000020051-20140613082840.pdf | 1) The LIL was adequate for piloting the ocean outfall technology. However, the preparation and implementation of a private concession contract were unsuitable for a LIL. The LIL should have been restricted to the design stage of the PSP intervention, which eventually happened.2) There should always be an institutional contingency plan for reform projects. It is not possible to anticipate the political shifts that will occur over a period and to design projects accordingly. However, a degree of political astuteness needs to be foremost in the design of projects as sensitive as this one. The risks were identified by Bank staff yet it does not appear that there was a fallback plan in relation to PSP.3) Although the project was thoroughly prepared, more flexibility would have been necessary to adjust the design to changing circumstances, particularly to the creation of the new local operating entity Puerto Plata Water and Sewerage Corporation (CORAAPPLATA) with an autonomous corporate structure established by the government.4) More care would have been needed to ensure collection of fees in order to enable CORAAPPLATA to maintain the new installations.
P059565 | BR- BA BASIC EDU PROJECT (PHASE I) | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Education | IBRD | IPF | 2001 | 2003 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/567311474657815709/text/000020051-20140612093701.txt | http://documents.worldbank.org/curated/en/567311474657815709/pdf/000020051-20140612093701.pdf | The use of two APLs for a total program of less than five years -- the same length as a typical single Specific Investment Loan -- may add flexibility but at the cost of additional work in project preparation and processing.Expanding basic school enrollment to reach the last decile of the school-age population is liable to be accompanied by a short term drop in student assessment results and increase in repetition rates. As highlighted in the Borrower's Contribution, specific actions need to be implemented to address the educational needs of specific groups, such as indigenous people and those living in recent land settlements.Capacity and procedures for procurement of civil works need to be established prior to project effectiveness.
P059566 | BR- CEARA BASIC EDUCATION | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/933851474664181424/text/000020051-20140619104208.txt | http://documents.worldbank.org/curated/en/933851474664181424/pdf/000020051-20140619104208.pdf | Inadequate appraisal of borrowers' implementation capacity poses high risks to project success. During appraisal, borrower implementation capacity should be carefully assessed, in fiduciary terms as well as in the ability to provide counterpart funds and carry out procurement procedures. Projects should be appropriately dimensioned, taking into account the number of activities, the number of implementing agencies and their implementing, and especially coordinating, capacity. Project preparation should ensure that implementation details are in place, such as implementation manuals, inter-agency agreements, and terms of reference for important activities.-Carefully link institutional development activities with the drive for improved learning outcomes. Management models and institutional development activities are very important to achieve equitable access for poor students in low-income areas. However, it is important to link these to learning outcomes. If learning outcomes stagnate or deteriorate while management-oriented activities are implemented, perhaps these activities should become better linked to help students acquire the necessary knowledge.- Program and sector investment loans have complementary roles. Program loans can effectively complement the implementation provided under sector investment loans by ensuring the passage of relevant laws or the allocation of budgets to priority programs. Thus program and sector investment projects covering the same sector require tight coordination in appraisal as well as in supervision.
P059663 | Road Network Improvement Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2004 | 2012 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/237201474556374099/text/000020051-20140625232300.txt | http://documents.worldbank.org/curated/en/237201474556374099/pdf/000020051-20140625232300.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation of language:A well functioning road management system needs to incorporate both the technical capacity and financial resources to ensure regular and reliable data collection for monitoring and evaluating performance. Continued emphasis on the development of robust data management systems is critical for establishing a functioning road management system. Baseline measurements are also of paramount importance to the overall success of monitoring PBCs, therefore initial and periodic measurements of key data is necessary and must be fully funded.Active implementation support can facilitate creative solutions to compensating affected persons. Various innovative measures to meet the overarching objective of ensuring restoration of livelihoods could include: (i) tax breaks (ranging from three to six months) to compensate for income loss during construction; (ii) use of reporting by neighbors as a means to verify eligibility; and (iii) active communication campaigns to clearly and visually illustrate the borderline of the public Right of Way and the categories of affected land.Replacement cost survey should always be conducted, and price contingency clause may be introduced to address price increase. As land acquisition often lasts for a long time, it may be prudent to introduce price contingencies to account for the increase in value of land that are likely to occur between the time of the RAP preparation and its implementation, in particular in a country with high inflation.
P059755 | Institution Building Technical Assistance 2 Project (IBTA 2) | Europe and Central Asia | Tajikistan | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2005 | 2007 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/745161475075667842/text/000020051-20140615095514.txt | http://documents.worldbank.org/curated/en/745161475075667842/pdf/000020051-20140615095514.pdf | 1) Careful sequencing and alignment should be ensured in the case of TA projects in support of - or closely related to - adjustment operations. In those cases, TA activities should be defined and designed to match the reform agenda. 2) The mid-term review is the opportunity to assess the need to restructure/refocus a project. In this particular case (a mid-term review was planned after December 31, 2002), the Bank missed the opportunity to redesign the project to correct the failings and shortcomings that had become quite apparent by then, in particular under the public administration reform component.
P059763 | Cultural Heritage Pilot Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/718501474490461727/text/000020051-20140613065134.txt | http://documents.worldbank.org/curated/en/718501474490461727/pdf/000020051-20140613065134.pdf | If the Bank is to contribute successfully to cultural heritage projects it needs to form partnerships with agencies strong in the skills that it lacks. Renovating community spaces in historic cities is as important as restoring large, world-famous monuments. When several donors are involved in funding, delays in project startup should be anticipated in the implementation schedule.
P059803 | Nura River Clean-Up Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2003 | 2011 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/343881474586729082/text/000020051-20140626115153.txt | http://documents.worldbank.org/curated/en/343881474586729082/pdf/000020051-20140626115153.pdf | The ICR reports the following lessons:In pollution clean-up projects, adaptation to local conditions and inherent uncertainties regarding the extent of pollution is largely a process of â€œlearning by doing.â€ Pollution remediation is a complex and risky business, involving a high level of uncertainty, even with the most advanced knowledge and sophisticated technologies. Often when environmental contamination occurs, the physic-chemical processes involved tend to be governed by complex conditions that can lead to extremely irregular pollution distributions and create a high probability for unforeseen situations, which can only be uncovered during remediation works. This has profound implications on timing and costs. No amount of up-front information gathering by drilling, sampling and analysis will lead to 100 percent certainty and thus there is a need to adapt to these circumstances during implementation.Implementation delays resulting from institutional changes and state approval processes are more difficult to manage if they are not factored as risks into project design. The project team should be cognizant of the country systems in place and assess whether they pose any apparent risks. Then appropriate mitigation measures should be in place to minimize the impacts of potential delays.Post-closure management of project assets, including operation and maintenance of the landfill, is better managed by up-front agreements with respect to project assets with project counterparts. Post-completion arrangements of all assets created, especially the landfill, should be discussed and agreed with the Borrower before project completion or loan closing.IEG also finds that:It is difficult to assess the welfare impact of environmental clean-up projects if no assessment of beneficiary views/impacts is conducted. The project did not have plans for the assessment of impacts of the clean-up activities on project beneficiaries. Ideally, this should be done at the design stage or during implementation, to better understand the projectâ€™s impact on beneficiaries but also on other qualitative aspects related to welfare, poverty reduction, etc. In the absence of longer-term health and epidemiological studies of the beneficiary population, a beneficiary assessment can be a valuable tool in understanding the social/health gains made under the project.
P059864 | Second Rural Transport Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2000 | 2006 | 2008 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/367371475099434907/text/000020051-20140618061107.txt | http://documents.worldbank.org/curated/en/367371475099434907/pdf/000020051-20140618061107.pdf | 1. A country's road administration must have technical standards and specifications for its roads, which are uniform throughout the country. These standards should cover all kinds of roads and have a protocol for granting exceptions. Otherwise much time and effort is spent on agreeing on standards and specifications in each project, and there is a danger that each donor and consultant will develop their own standards and specifications.2. Projects should rely on local consultants to the extent possible and develop local consultants' skills. Foreign consultants normally lack language skills and understanding of local culture and institutional economics.3. There should be a network not a project approach to maintenance financing. For an initial period, project-specific financing may keep a road segment well-maintained, but the network as a whole, serving the area's population and economic activity deteriorates. For longer term a network approach to road management is needed with an institutional mandate. This can only come from the government entities responsible for (rural) roads.
P059872 | Basic Education 2 Project (APL #2) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2003 | 2008 | 2009 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/235191474664590385/text/000020051-20140618194342.txt | http://documents.worldbank.org/curated/en/235191474664590385/pdf/000020051-20140618194342.pdf | Some lessons are offered below and several coincide with lessons identified in the ICR, as well as the BEP1 ICR Review that remain pertinent:A project restructuring provides an opportunity to reassess the feasibility of the KPI targets and to revise if necessary. If this is not done and the objectives are overly ambitious, the project's rating against the project's original KPI targets will likely suffer;In instances where the first phase of an APL has been unsatisfactory, the second phase will likely replicate weaknesses in design and implementation arrangements unless there is a detailed re-assessment (even when the triggers have been met);Triggers for APL transition to subsequent phases that are focused exclusively on the achievement of outputs or procurement actions can miss the opportunity to encourage a stronger results focus; and Without an institutional assessment during project preparation the institutional capacity requirements for implementation may be underestimated, and not be matched with the available institutional capacity.
P059930 | ID-DECNT. AGRICULTURAL/FORESTRY EXT | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/518441474590016000/text/000020051-20140613081815.txt | http://documents.worldbank.org/curated/en/518441474590016000/pdf/000020051-20140613081815.pdf | Based on the ICR the key lessons are: (i) Continuous monitoring and evaluation of project processes and impact with the active participation of beneficiaries and key stakeholders are essential for influencing policy and institutional change;(ii) Timely budget flows from central and local governments to the project implementing agencies down to the field level should be ensured;(iii) To ensure high adoption rates among farmers, extension activities should focus on introducing and/or improving low-cost, highly profitable, market-led production and processing activities;(iv) Management structures such as the district extension committees, which are set up to coordinate extension activities at the district level, need both political and financial backing to survive beyond the life of the project.
P059931 | Water Resources & Irrigation Sector Management Program | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2003 | 2011 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/177181475112766174/text/000012394-20150107110007.txt | http://documents.worldbank.org/curated/en/177181475112766174/pdf/000012394-20150107110007.pdf | The ICR lists the lessons as Institutional development and reform oriented investments in the water sector need a long-term program approach synchronized with government policyA participatory approach in basin water resources and irrigation management improves decision-making effectiveness, and enhances ownership of the solutions by different stakeholders.Inter-agency collaboration and coordination proved essential not only for project implementation but also for ensuring project impact and sustainability.Role-sharing, in a decentralization policy environment, between national, provincial and district agencies for basin water resources and irrigation management for national basins/schemes is more effective if it is structured through legal arrangements, instead of being addressed through ad hoc agreements.It is critical to retain a stable team of government staff during the implementation. M&E indicator design should be specific and easy to measure, and be able to reflect PDO achievement. This Review would add (a) the importance of serious and regular attention to M&E during Bank supervision and (b) the need for effective decentralized financial management arrangements to be in place to ensure a smooth flow of funds to the project entities (an issue best tackled before Board approval).
P059936 | Northern Mountains Poverty Reduction Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2008 | 2009 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/870551474635383489/text/000020051-20140619081758.txt | http://documents.worldbank.org/curated/en/870551474635383489/pdf/000020051-20140619081758.pdf | Operations and maintenance. The biggest challenge for projects of this nature is to ensure funding for operation and maintenance (O complementary intervention through budget support operations (development policy loans) is needed to ensure that government's recurrent budget includes funds specifically earmarked for maintenance of roads and other public goods. Information flow. In order to give the strongest possible voice to the poor, public information campaigns are essential. If information flow is limited the poor will not participate in the selection and implementation of investments and will not hold local authorities to account. Procurement. Transparent and efficient procurement is an essential part of community development projects. In this project, local authorities were initially skeptical about the open, competitive approach to procurement but were won over once they saw that these procedures helped to defuse criticism and pressure from their constituents. For very small, labor intensive works at the village level, community participation in procurement helps build local capacity, creates employment and reduces costs.
P059971 | KH-EDUCATION QUALITY IMPROVEMENT | East Asia and Pacific | Cambodia | IDA |  | Human Development | Education | IDA | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/336521474895638465/text/000020051-20140612152834.txt | http://documents.worldbank.org/curated/en/336521474895638465/pdf/000020051-20140612152834.pdf | Key lessons learned from this LIL are:One viable model for improving school quality is to gradually build the concept of effective schools from the ground up including school or cluster-level choices about learning materials, teacher training, and innovative practices, yielding grounded experiences and results which can be translated into policies at higher levels; Even at the grassroots level, but also at higher administrative levels, technical assistance is important to catalyze local creativity, introduce fresh ideas, and build capacity;Allowing schools or clusters of schools to articulate their own teacher training needs can be a more effective way of organizing inservice teacher training than creating teacher training programs at the center (central Ministry or teacher training college);For Projects aiming to improve school effectiveness through substantial changes in educator attitudes and practices, it would be good to include some observable, intermediate outcomes (such time on task, student activity level, or child-centered teaching) in addition to the kind of performance indicators set for the Project (student enrollment, attendance, promotion/drop-out, and achievement, and policy improvement), since the latter often change quite gradually or are affected by system-wide improvements. Classroom observations by qualitative researchers (reported in an ICR supporting document) revealed positive changes in classrooms which were not reflected in the formal project performance indicators. It is a good idea to draw Project catalysts at the school/cluster level (in EQIP called "animators") from among the district officers so that once the Project is completed these officers will be in a position to support the continuation of innovation; however, since the Project provided financial incentives to animators, the country will need to find ways to motivate local managers to keep up the extra school support efforts;Good information and effective communication covering innovative practices and their impacts are important, requiring both adequately-resourced monitoring and evaluation systems, and timely, readable reports in the national language in order to reach target audiences and influence the overall policy dialogue.
P060003 | Forest Concession Management and Control Pilot Project | East Asia and Pacific | Cambodia | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2000 | 2006 | 2008 | ICRR | Less than 10 million | Unsatisfactory |  |  | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/654471475110977463/text/000020051-20140617142856.txt | http://documents.worldbank.org/curated/en/654471475110977463/pdf/000020051-20140617142856.pdf | (1) When engaging technically in concession system reform in countries with weak regulatory and enforcement capacity, the ability of technical assistance to rapidly build needed capacity amongst forest managers in the field should not be overestimated. A technical assistance package supported by grant funding and implemented by an international technical agency with a strong track record of working in the sector in difficult countries with weak institutions would be a preferred formula. (2) The use of Independent Third Party Monitors to witness and report on illegal forest activities is an effective tool that has proven valuable in the Congo basin, for example. To enhance the effectiveness of this instrument, the Bank should develop clear terms of strategic and contractual engagement with entities engaged in third party monitoring and ensure that there is "buy-in" on the part of the borrower ultimately responsible for enforcement. (3) The design of a robust Monitoring and Evaluation Framework, including clear project management roles concerning implementation and utilization, should be considered a primary tool when implementing a Learning and Innovation Loan. A properly designed and functioning M&E system should provide the basis for a clear dialogue between the Bank and the Borrower. (4) Forest sector projects that contribute to a reduction of concession-held forest lands as part of a pro-reform sector reform initiative should have a clearly developed vision, designed in consultation with community members, of how subsequent land use can contribute to rural poverty alleviation, with a focus on equity, traditional rights, and biodiversity protection. The Bank can contribute economic and sector work which analyzes alternative options for non-concession land use.(5) As iterated in IEG's Review of the Implementation of the World Bank's 1991 Forest Strategy, forest-rich countries often feature poor governance, corruption, and political alliances between various segments of the private sector and elites, combined with minimal local and regional enforcement capacity. The situation can improve only if countries develop broad-based participatory institutions that offer equal voice to local constituencies, especially the vulnerable, and only if they can find the resources to forgo the short term over-exploitation of forests.
P060003 | Forest Concession Management and Control Pilot Project | East Asia and Pacific | Cambodia | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2000 | 2006 | 2007 | PPAR | Less than 10 million | Unsatisfactory |  |  | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/364411468239356558/text/40125.txt | http://documents.worldbank.org/curated/en/364411468239356558/pdf/40125.pdf | 7. Looking Forward and Lessons Learned 7.1 Project design and implementation ina low-income post-conflict country continue to present a unique set o f issues for the Bank or any development agency. These projects are highlyvisible as animportant shareo fthe total capital flow into a sector; they tax the limited capacity o f the Borrower's institutions and infrastructure, there i s often very little local experience on which to build, and they challenge the emergingregulatoryand administrative framework within which they are to be established. Experience with the four projects reviewed inthis report point to the importance o f particular aspects o f design and implementationthat could strengthen the Bank's effectiveness inthis type o f environment. (1) Use of the Learning Instrument Loan. Two o f the four projectsreviewedinthis PPARwere LILs\. the NortheastVillage Development Project and the Forest Concession Management and Control Pilot Project. While the case was made for usingthis instrument inboth appraisal documents, it was a contributing factor inthe problemsencounteredbythe forestryproject. Usingthe LILpermitted the deferralo f the social impact assessment. Itwas logical to defer social impact assessmentsto the context o fthe individual concession management plans that wouldbe producedunder the project, rather than to conduct a hypotheticalassessment ex ante based on average or exceptional conditions among all 14concessions to be treated under the project. Nevertheless, this deferral left the project vulnerable to criticism on safeguard issues and, inpractice, as the InspectionPanelReport noted, a safeguardpostponed i s a safeguard denied.34The Bank has since introduced the use o f framework assessmentsto be conducted beforeproject approval to addressbroad issues that will be more specifically attended to duringthe course o f implementation and this would almost certainly have flagged the muchvaunted issue o fresin trees as well as other competing claims inconcession areas. Infbture, the useofLILs or anyinstrumentthat circumventsany oftheusual safeguard investigation duringpreparationshouldbe subject not only to the normal tests o f eligibility, but also the test o f downside risks, be these technical or the likelihood o f adverse public opinion. (2) The Importance of Continuous Contact for Effective Implementation. A problem which arose due to o f the Bank's small portfolio inCambodiawas that a resident office was not established until2003, so that most project development, appraisal and supervision prior to that time was conducted through visiting missions. When coupled with the fragile institutional framework inpost-conflict Cambodiaandthe limited counterpart pool, this periodic mission approach to relationships and task development was very inefficient. Credibility, knowledge transfer, consensus buildingand decision-makingwere all seriouslyhampered, evenwhen teams came frequently from Bangkok. Where the client is not familiar with Bank operations and procedures or i s confronting serious impediments to its ability to act on that knowledge, continuous presence o f competent Bank representatives i s a critical factor inmovingdialogue andoperations forward. Theresults o fthe FEW,which didhave the benefit o f a resident sector staffmember, confirm this benefit. (3) Sector and Country Strategies as a Management Tool for Operations. Sector or country strategies are often seen as the leading edge for policy dialogue and the identification o f investment opportunities, but their usefulness duringproject implementationmaynot be as widely recognized. As long as operations are set initially ina sound strategic context andtheir implementationproceeds smoothly, nothing is lost by temporarily setting strategy aside. Butwhen ambiguity or disagreements arise inimplementation, particularly with the evolving focus or 34. InvestigationReport, The InspectionPanel, March 30,2006, Report No. 35556, pagexxii. importanceof an activity, an agreed strategy canbecome an effective management tool. Inthe case o f the two projects whose overall outcomes were unsatisfactory, usingthe strategies inthis way duringthe course o fimplementationmighthave given staff and counterparts the basis for reorientingtheir efforts and increasingthe efficacy o fthe operation. Revisitingthe country strategy might have ledthose working on APIP to look more closely at how the Ministrywas going to use its enhanced capacity.35And it mighthave kept those working on the FCMCPP from losing focus on their tasks amid the barrage o fpublic criticism.36 Mid-termreviewshave beenan important innovationinBankwork, basically intendedto reflect on objectives and strategy inlight o f implementationexperience. Usingcountry and sector strategy as part ofimplementation support takes this a step krther by keepingthe collective eye o f stakeholders o n where the tasks at hand are intendedto take the Borrower. (4) A GradualApproach to Change. Institutions generally respondmore favorably to moderate or gradual change than to radical innovation, particularly when power or stature are being threatened. The FCMCPP was designed to take a step-by-step approach to reforming the industrial exploitation of the country's timber resources, and this review concurs with the Region's contention that this was the correct approach. Deeply rooted rights and practices were at issue andthe challenge to achieving a resource management focus inthis lucrative industrywas going to take time andpersuasion. A firm and resolute explanationo f the gradual approach might have appealed to calmer heads andmitigatedthe groundswell o f support for the unrealistic alternative. (5) Dealingwith InformalTransaction Costs as a Development Issue. To an outsider, informal transaction costs may be seen as corruption, butto a participant they may be an accepted form o f sharing or a means o freaffirming one's role ina group. While fiduciary accountability requires correct procedures and oversight, the development impact o fthe Bank's approach to the issue i s very much linkedto the sensitivity with which it introduces the qualities o f transparency and cost-effectiveness as desirable qualities inprocurement transactions. This is a time-consumingprocess that depends on mutual trust that i s very difficult to buildeither longdistance or inthe context o f public criticism or embarrassment. The collaborative approach betweenthe Region, the Bank's Department o fInstitutional Integrity, and the Borrowerprior to May 2005 hadresulted inthe introduction o f guidelines andprocedures that were steadily increasingthe degree o ftransparency inproject-relatedprocurement, in contrast to the acrimonious stand-off that prevailed for over a year following the release o f INT's findings o fwrong-doing to the public.
P060005 | Urban Infrastructure and City Management Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2010 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/139971474491276637/text/000020051-20140624162036.txt | http://documents.worldbank.org/curated/en/139971474491276637/pdf/000020051-20140624162036.pdf | The ICR identified following lessons:The project confirmed findings from other urban development projects in the Africa Region that the "City Contract Approach" its tools (priority investment program, priority maintenance program, municipal support program, and financial ratios) can be used to effectively to facilitate improvements in service delivery and municipal and urban management.Bank safeguard policies can be used as a basis for a constructive dialogue on the management of social and environmental impacts, thus bringing about changes that reach beyond the project context.
P060005 | Urban Infrastructure and City Management Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2010 | 2019 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/939641549554073372/text/133113-PPAR-P060005-P165746-PUBLIC.txt | http://documents.worldbank.org/curated/en/939641549554073372/pdf/133113-PPAR-P060005-P165746-PUBLIC.pdf | 7. Lessons 7.1 The main lessons from this operation are as follows\. â€¢ The World Bank's absence in a sector creates knowledge and implementation gaps for both World Bank and client, requiring significant catch-up transaction costs. In the case of postconflict Rwanda, the World Bank took four years to prepare the project, to undertake analytical and preparatory work and extensive consultation with key stakeholders. Combined with strong implementation support, the World Bank was able to successfully implement and complete the first urban project in Rwanda. The World Bank's withdrawal from the sector in 2009 and reengagement in 2014 entailed rebuilding its knowledge base and implementation capacity at central and project levels and relearning some of the lessons from the UICMP albeit in a much different urban environment. In both cases, the lack of World Bank activity in the urban sector for several years translated into significant catch-up transaction costs for the World Bank and the client in terms of knowledge base and implementation capacity when re-engagement took place. â€¢ Using a delegated management agency to address the weak implementation capacity of local governments requires a focus on building such capacity and a clear exit strategy to ensure long-term sustainability. The use of a contract management agency approach in postconflict Rwanda through ASSETIP ensured that the civil works were generally of good quality and were completed on time. However, the use of this type of implementation modality needs to have a clear exit strategy to ensure sustainability of results by focusing on building the capacity of local governments. In the case of Rwanda, the World Bank had a clear exit strategy by facilitating the mainstreaming of ASSETIP in coordination with government through a framework agreement that would allow ASSETIP to work on behalf of decentralized entities and public institutions to execute their investment programs. Under this arrangement, local governments would decide when and how to use the services of ASSETIP to complement their capacity needs. â€¢ To maximize learning from pilot project components, their lessons should be documented and disseminated to inform the future work of the World Bank and government. In the case of Rwanda, the pilots on urban upgrading and land development were envisaged to demonstrate what works and does not work in addressing the issue of informal settlements. The urban upgrading pilot demonstrated how upgrading an informal settlement could improve the lives of the beneficiaries. Although the lessons from the two pilots were documented at project close, the lessons were not disseminated, largely because the second phase of the UICMP was dropped and the World Bank did not have any further engagement in the urban sector until 2014. Absent the dissemination of lessons learned from the pilots, the World Bank and the government had to relearn the lessons from previous interventions (for example, urban upgrading is currently being piloted under the ongoing RUDP). 7.2 During the preparation of the Country Partnership Strategy (FY14â€“18), the government approached the World Bank to lead the urban sector and to support the government's priority interventions. 30 The government's EDPRS 2 and Vision 2020 placed urbanization as one of the central pillars of its economic transformation objective. In line with the government's priorities under EDRPS 2, the current Country Partnership Strategy (FY14â€“18) includes the urban sector as one of the subpillars of accelerating economic growth. The first urban sector operation, the RUDP, was approved in FY16, 10 years after UICMP was approved. The RUDP builds on the design elements of UICMP with regard to the project objective (access to urban infrastructure), geographic focus (six secondary cities), and components (urban upgrading). Except to mention UICMP's outcome rating of highly satisfactory, none of the project documents, including the PAD, referred to lessons from the UICMP. 7.3 In parallel with the preparation of the RUDP, the World Bank had undertaken several analytical pieces on the role of urbanization in economic development, which provided the basis for a synthesis note on urbanization. Urbanization and economic transformation was also part the World Bank's recently completed flagship report on Rwanda on Future Drivers of Growth. The World Bank's Advisory Services and Analytics were completed between 2015 and 2017, a bit late to influence the government's policy and strategy which were issued between 2015 and 2016. Nonetheless, the work provides the building blocks for the World Bank's policy dialogue with the government on urban development and could potentially influence the government's policy and strategy on urban development in Rwanda over time (World Bank 2019).
P060029 | Sustainable Forestry Development Project (Natural Forest Protection) | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2002 | 2011 | 2012 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/103301468242639821/text/678820PPAR0P100C0disclosed070160120.txt | http://documents.worldbank.org/curated/en/103301468242639821/pdf/678820PPAR0P100C0disclosed070160120.pdf | 5. Lessons 5.1 This assessment of forest projects and AAA has highlighted the steps the Bank has taken to move beyond its (highly successful) engagement with plantation development in China. Renegotiating its support for forest interventions involves supporting new activities, and finding new interlocutors. The Bank has been more successful in the first of these switches than it has in the second. As the FY2010 Shandong Ecological Afforestation Project and the FY2010 Integrated Forestry Development Project have shown, the Bank is now seeking to involve local forest authorities, village leaders and farmers in the design of forest management plans that would ultimately take the place of the logging quota system, which lacks transparency and is unevenly enforced. This is the latest phase in the evolution of a more participatory approach to forestry that dates back to the FY98 Forestry Development in Poor Areas, assessed in this report. In addition, recent analytic work builds on the 2010 Forest AAA that was evaluated here. The FY2012 North East State Forest Reform Study aims to develop a roadmap for the State Forestry Administration, to support policy and institutional reforms in the management of state-owned forests in Northeast China, with a view to enhancing management efficiency, economic viability resource sustainability, and local livelihoods. Progress in the dialogue on policy reform will depend in no small measure on the Bank's ability to engage with new government agencies in China\. the State Forestry Administration's Project Management Center has proved to be a highly effective partner for plantation establishmentâ€”with a first-rate performance record, probably unparalleled in the worldâ€”but if the Bank is to broaden its engagement on forest interventions it needs to develop a dialogue with other interlocutors in addition to PMC. Since the sector work evaluated in this report was completed there is some evidence that the Bank's forestry team in China has diversified the scope of its engagement\. although continuing to work with the Project Management Center (specifically, on plantation establishment), the Bank is working with other departments in the State Forestry Administration and directly with provincial governments. 5.2 Based on the assessment of the projects and AAA in this report, IEG draws three lessons. 5.3 Even if poverty reduction is not an objective of the project, there is a sound case for monitoring and evaluation to measure project-driven changes in the incomes of beneficiaries because these are likely to influence the incentives for beneficiaries to consolidate project achievements. The Forestry Development in Poor Areas Project made provision for three household surveysâ€”baseline, midterm and final. These surveys were included in order to assess attainment of the outcome target of increasing incomes by 60 percent; and, more broadly, because poverty reduction was an explicit objective of the project. The Sustainable Forestry Development Project did not include poverty reduction or income enhancement in its objectives, and made no provision for household surveys. There was close monitoring of plantation establishment and, given the tight quality controls, there was good reason to infer that the incomes generated from this component would be substantial, creating an incentive for farmers to pursue the recommended tending and harvesting guidelines in order to maximize returns. However, unlike in the earlier project, there is no indication whether poorer households invested in plantations. More importantly, in the case of the protected area and natural forest management components, it was less certain that incentives were sufficient for communities to commit to conservation and sustainable forest management. These components included modest efforts to improve livelihoods and to boost incomes but in the absence of evidence from household surveys it is impossible to know whether the impact was big enough to generate the incentive needed to consolidate project gains in natural resource management. Given the steep rise in wages in China, labor devoted to (poorly remunerated) conservation activities carries a high opportunity cost, making it all the more important that projects have the monitoring and evaluation apparatus needed to measure livelihood changes and assess the level of incentives. 5.4 Until recently, the scope for the Bank to broaden its operational engagement with forest issues in China was limited by governments' insistence that, where IBRD funds are on-lent, producers and local governments must repay them with interest; central and provincial governments now recognize the public good nature of forests and are more willing to assume direct responsibility for repaying Bank loans that provide forest environmental services. Making loan recipients responsible for repayment 53 rewards solid performance but is hard to justify where there is no revenue stream to amortize debt obligationsâ€”that is, where loans are used to finance delivery of public goods. The â€•responsibility systemâ€– lends itself to the financing of commercial wood plantations but is harder to apply to conservation-oriented forestry and environmental protection. The experience from the projects assessed here shows that poorer counties and poorer farmers have difficulties meeting loan repayment obligations, partly because the government's enforcement of the logging ban and protection of natural forest and nature reserves reduces their sources of income. Excluding the poor from IBRD-funded projects is not desirable. Neither is it realistic to expect that grants will fully substitute for IBRD loans. (The Sustainable Forestry Development Project pushed in this direction, seeking to graft on a European Union grant to a World Bank project, with unsatisfactory consequences.) Had central and provincial governments not been willing to assume a larger share of the responsibility for paying back loans, it would have been difficult for agencies like the Bank to move away from financing commercial plantations. In recent years, government policy has evolved to emphasize the contribution of forest environmental services to China's development. The central government, and some provincial governments, are now willing to use Bank loans to support the provision of forest public goods through direct government budget expendituresâ€”rather than solely for on-lending to planting entities for forestry production activities. This trend is evident in the Bank-supported Shandong Afforestation Project and the proposed Hunan Forest Restoration and Development Project. 5.5 Parallel-financing by another donor is difficult to supervise if it is applied to a single component of a Bank-supported project, and may be best dealt with as a separate operation. The Bank used its convening power to elicit grant funds from the European Union for the natural forest management component of the Sustainable Forestry Development Project. This was a valid attempt to diversify the range of Bank engagement toward public good forestry, which the Chinese government was unwilling to finance on IBRD terms. The component was parallel-financed, not Co-financed, meaning that the European Union was in charge of supervising the component. At appraisal, the Bank stated that the two partners would cooperate closely, participating in each other's supervision missions. In practice, this failed to happen. Cooperation was limited, in part, because the Bank-supervised components were implemented by PMC while the EU component was implemented by a separate department of the State Forestry Administration. Moreover, the practice of the Chinese government has been to deal with each donor separately with no encouragement to collaboration between them. The poor performance of the consultant team fielded by the EU slowed down implementation of the component and, incidentally, delayed the closing of the overall project and pulled down the outcome rating. The potential for shared learning between the Bank and the EU was not realized.
P060092 | CF-Fisc Consolidation Credit SAD (FY00) | Western and Central Africa | Central African Republic | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2000 | 2003 | 2004 | ICRR | >=10 million & <25 million | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/213741474549797336/text/000020051-20140612100924.txt | http://documents.worldbank.org/curated/en/213741474549797336/pdf/000020051-20140612100924.pdf | In very fragile post-conflict situations, Bank interventions should be limited to the bare minimum, focusing on the social services, in support of actions undertaken by other UN agencies responsible for assistance to demobilization, refugees, etc. For instance, issues as complex as privatization and sector reorganization should be addressed much later when all the pre-requisites are in place (in the case of CAR, even in the absence of conflict, such issues would be a major challenge).The recourse to floating tranches is useful when, under stable political conditions, it is not possible to determine at preparation/appraisal the time required to take a given action (e.g., approval of a law by Parliament); they are of little use in an unstable political and economic situation.
P060132 | RY Public Works II | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2003 | 2004 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/267821475072755992/text/000020051-20140612100248.txt | http://documents.worldbank.org/curated/en/267821475072755992/pdf/000020051-20140612100248.pdf | For effective M&E, baseline data should be gathered for each key performance indicator that can demonstrate whether project objectives are achieved or otherwise. Once in place, to remain effective M&E systems and procedures need continuous expansion and strengthening.Both Bank and the borrower were able to capitalize on the experience and momentum gained through the successful first Public Works project in Yemen (Cr.2878), retaining the services of the agency responsible for its execution.Sustainability of project benefits needs to be considered at the outset, especially through ensuring that adequate resources will be made available to ensure the operation and maintenance of completed facilities.Transparent procurement procedures for selecting contractors and consultants, in the end, can satisfy all parties concerned and reduce otherwise considerable pressures upon and unqualified claims to local project authorities.Close coordination with Local Councils early on in the project cycle helps avoid duplication of services provided by different implementing agencies and supported by different donors, as well as enhancing the institutional development of local authorities and decentralization in general.
P060132 | RY Public Works II | Middle East and North Africa | Yemen, Republic of | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2003 | 2005 | PPAR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/242361468764124440/text/303960RY.txt | http://documents.worldbank.org/curated/en/242361468764124440/pdf/303960RY.pdf | 7.5 The primary lessons learned from these projects are\. That in a post conflict, country unification situation such as Yemen's, to avoid fruitless expenditure and wasted resources, additional r i s k analysis i s appropriate to ensure that the Government i sfully committed to the reforms proposed and the timetable for the reform agenda. Project objectives should be framed realistically, taking into account the borrower's ability to achieve stakeholder support for proposed changes. Genuine community ownership and participation can enhance the likelihood o f project success as evidenced by Yemen's Public Works program. These Yemeni projects show that inter-ministerial, agency and stakeholder coordination are crucial to project sustainability and that the Bank could be more proactive in helping to improve the general level o f coordination.
P060221 | FORTALEZA METROPOLITAN TRANSPORT PROJECT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2002 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/864251475328158670/text/000020051-20140624201908.txt | http://documents.worldbank.org/curated/en/864251475328158670/pdf/000020051-20140624201908.pdf | Objectives should be formally restructured if they become unrealistic: The new Government did not provide fiscal space for the project in its budget due to macroeconomic difficulties. The corresponding government decision to reduce project scope undermined the achievement of the original project objectives which were not restructured. It is hard to accomplish ambitious objectives in a limited project time frame: This project supported the West line of the metrorail in Fortaleza, complementing the South line which was financed by JBIC. The key institutional reforms including decentralization and private sector participation were applicable to the entire metro system, but the project suffered inter alia from non-achievement of some project objectives because of the deteriorating macroeconomic environment and delays in the rehabilitation of the South line both of which were outside the project's control. The importance of ensuring coordination of the two projects was identified but did not ultimately accomplish full integration of the physical and tariff systems needed to achieve the intended objectives. There remains a possibility that the privatization process will continue in the future but at a slower pace than that of a typical Bank-financed sector investment loan.
P060258 | PRSL II | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1999 | 2000 | 2001 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/238781475081037014/text/000020051-20140529155743.txt | http://documents.worldbank.org/curated/en/238781475081037014/pdf/000020051-20140529155743.pdf | (i) Satisfactory progress can be made in a difficult political environment by focusing on few key actions, pursuing an active dialogue and consultations with civil society, donors and the Government, monitoring closely the program in conjunction with partners, and stationing key Bank team members in the field office. (ii) The focus should be on implementation of laws and not only on their passage by the Parliament.
P060258 | PRSL II | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 1999 | 2000 | 2004 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/917171468752402166/text/271770ID.txt | http://documents.worldbank.org/curated/en/917171468752402166/pdf/271770ID.pdf | 5. Lessons 0 Inacountry with deeplyrootedandwidespread govemance issues, wherethe authorities are not committed to deep reforms, the Bank needs to have realistic expectations about the outcome o f its interventions. InIndonesia, the ability to affect fundamental reforms with adjustment and technical assistance support has beenlimited. The effort requires a more comprehensive and long-term approach, including diagnostic work and involvement o f civil society. 0 The dilemma o f supporting a country incrisis i s highlightedby PRSL Iand, more especially, by PRSL II. The Bank needs to provide the Boardwith a frank rationale for its intervention, even where the rationale i s limitedto providing special shorterterm liquidity support for modest reforms. 0 The experience inIndonesiahighlightsthe importance of avoiding delays in banking crisis\. unless resolved quickly and decisively, the fiscal costs mount and vestedinterests further impederesolution. 0 Inamajor crisis, Bankmanagement andtop technical specialists should give priority to resolving issues that arise inthe context o f Bank assistance addressing the crisis, evenifthe vehicle for the assistance is inthe form ofa relatively modest technical assistance loan. 0 Coordination among donor agencies i s essential incountries incrisis and needs to bemade explicit. InIndonesia, coordinationwas successful only after an initial period of uncertainty, mainly becausethe IMFwas able to take the lead. 0 The Bank's'consultant fee structure and procurement rules caused delays and impededa rapid responseto Indonesia's bankingcrisis, and excludedor discouraged the few service providers with appropriate technical expertise. These rules should be reviewedwith a view to allowing exceptions to policy under certain well-definedcircumstances. 0 The Bank's central unit enabled the Bank to respond to Indonesia's needfor technical expertise, butthe unitwas not well integrated into the Bank's organization and was unfamiliar with its operational procedures, causing bureaucratic and practical problems. For future crisis response, the Bank should consider establishing a virtual crisis unit o f specialists working inthe Regions, available to respond to a specific crisis inside the relevant regional management
P060270 | ENTERPRISE REFORM PROJECT | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2006 | 2007 | ICRR | Less than 10 million | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory |  | http://documents.worldbank.org/curated/en/282691475097059840/text/000020051-20140615110138.txt | http://documents.worldbank.org/curated/en/282691475097059840/pdf/000020051-20140615110138.pdf | When the Bank doesn't do its "homework," it risks damage to its reputation: The ERP reflected inadequate knowledge of local capacity and conditions in the pilot sites. This lack contributed to delays, the exit of 2 pilot localities, and the failure to achieve PDOs.*The Bank did not exercise pro-active management and identify problems in a timely manner. Even when it became clear that project achievement was falling far short of what was envisioned, the PSRs do not reflect a pro-active determination to diagnose problems and take action to remedy them. In some cases, reporting indicates that the Bank knew there were problems but did not know the source.Haste makes waste: The project was prepared hastily so it could be approved in FY99, the last year during which China could borrow on IDA terms (ICR para 3.5.5). It is likely that in the rush to prepare the project before the deadline, critical aspects of quality at entry were not given adequate attention, which contributed to the poor design and ultimate highly unsatisfactory outcome.*"Damage to the relationship with two ...participating cities....has resulted in two cities pulling out of the program." (PSR, 6/22/01)
P060329 | HIV/AIDS Rapid Response Project | Western and Central Africa | Gambia, The | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/925961474853629717/text/000020051-20140618062112.txt | http://documents.worldbank.org/curated/en/925961474853629717/pdf/000020051-20140618062112.pdf | Agreed-upon actions for improving implementation may not take place in the absence of an accountability mechanism. Bank staff made important recommendations to increase the effectiveness of activities, but these were not followed. For a project relying on a â€œlearning-by-doingâ€ approach, indicators related to effectiveness of activities must be monitored and must be discernible in a short time frame in order to be useful. The only indicator used for the CCSI component in this project was â€œdisbursement levelâ€.Sustained government commitment is necessary from project preparation through project closing to ensure a supportive environment.The lack of baseline data can result in setting inappropriate targets and emphasizing the wrong activities. Most project resources were spent on raising awareness, which was already high, rather than on changing behavior. Resources were also aimed at the general population rather than on prevention among high-risk groups whose behavior is the main driver in a concentrated epidemic.The Bank, the Borrower and civil society are more inclined to promote interventions for the general population rather than prevention activities for high-risk groups. This was a lost opportunity for the Bank to help the Borrower invest in more effective and cost-effective HIV/AIDS programs.The failure to conduct sound assessments of institutional needs, capacities and alternatives can result in institutions that are ineffective in achieving project objectives.
P060330 | PG-Mining Sector Inst. Strengthening TA | East Asia and Pacific | Papua New Guinea | Blend | FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2000 | 2006 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/965791475094402830/text/000020051-20140618054426.txt | http://documents.worldbank.org/curated/en/965791475094402830/pdf/000020051-20140618054426.pdf | 1. Sector restructuring and capacity building are long-term undertakings. Special attention should be given to the time required to amend existing legislation and/or adopt new one and their effective implementation. 2. Greater attention to the social dimensions of a project or program (in this case, the Women in Mining Program) helps identify measures aimed at mitigating the possible negative impacts of an investment. 3. At preparation/appraisal, the Bank should ensure that ownership and commitment are shared by all ministries/agencies concerned not only at the political level but also at the technical/administrative level.
P060392 | BO- HEALTH REFORM-APL I | Latin America and Caribbean | Bolivia | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/887161474563457958/text/000020051-20140612134056.txt | http://documents.worldbank.org/curated/en/887161474563457958/pdf/000020051-20140612134056.pdf | The use of well-defined indicators linked to expected outcomes and agreed ex-ante with the Borrower: (i) helps improve design and implementation by ensuring focus and aligning interventions around a set of clear benchmarks; and (ii) facilitates an orientation of policy dialogue around high-impact actions that will achieve negotiated results.Performance agreements are an instrument that can help regions align their health priorities with the MoH and can be most effective when indicators are: (i) few in number to ensure proper focus; (ii) monitored using a consistent methodology; and (iii) available on a periodic basis to allow for implementation of corrective actions.Performance agreements are most effective when they are accompanied by sufficient incentives at national and regional levels to ensure compliance with the set targets and to sustain the level of effort and interest. Making the achievement of benchmarks legally binding under the DCA was effective in this regard at the national level. The absence of such an incentive at the regional level might explain, at least in part, the observed weak compliance with the targets set in some specific regions.Efforts to bridge the cultural barrier created by ethnic diversity are critical both to improving the quality of services and to increasing the utilization of these services.
P060392 | BO- HEALTH REFORM-APL I | Latin America and Caribbean | Bolivia | IBRD |  | Human Development | Health, Nutrition & Population | IDA | IPF | 1999 | 2004 | 2018 | PPAR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/748801532017664145/text/126362-PPAR-P060392-P074212-P101206-PUBLIC.txt | http://documents.worldbank.org/curated/en/748801532017664145/pdf/126362-PPAR-P060392-P074212-P101206-PUBLIC.pdf | Lessons 5.10 The experience of the APL program indicates the following lessons\. 5.11 The definition of a common results framework is useful to align the efforts of different government levels. The M&E design of APL I was innovative in that it strategically defined a common set of indicators as APL phase triggers, the local management and accountability tool (that is, performance agreements), and KPIs. Although some of the indicators were initially ambiguous and later modified, this focus on common results helped different stakeholders (central government, local governments, World Bank staff) to concentrate efforts on the achievement of these selected areas. There is a risk though of not tracking lower-level indicators measuring progress in activities and outputs. 5.12 A robust results-based approach needs to define a clear mechanism of rewards/sanctions to function well. Otherwise it risks turning into a mere monitoring tool that could lead to perverse incentives. Performance agreements did not have a standard methodology for setting targets at the local level, altering the judgment of performance based on the stringency of targets set. In addition, the approach did not have a clear mechanism for rewards to ensure compliance of local governments with the targets and to sustain the level of effort and interest. Rather, it seemed to be used to monitor results sporadically and improve the capacities of local governments lagging behind through investment subprojects. While a traditional results-based approach (financially) rewards the achievement of results, these performance agreements seemed to act as a tool to flag allocation of funds to those local governments struggling to achieve targets. 5.13 Project design coordinating efforts with parallel programs that have similar goals has a great potential for efficiency, but it raises methodological concerns about the attribution of outcomes. In APL III demand components were sought to be articulated through the Zero Malnutrition and Bono Juana Azurduy programs, aimed at reducing malnutrition and increasing demand for health care services. While coordination with other government programs that have similar goals can enhance efficiency by exploiting synergies and minimizing duplication of effort, it creates challenges for the attribution of results to the activities of either program. Initial piloting and evaluation intentions were not possible because the conditional cash transfer program was directly launched at the national level, which limited the development of specific M&E arrangements to disentangle program effects. 5.14 While continued focus on quality objectives is certainly commendable, it needs to be accompanied by more robust outcome measures to prove quality enhancements. The prevalence of structural aspects of quality reflects the low baseline of health facilities' infrastructure conditions as well as the high costs of collecting process quality indicators. It is also consistent with the type of first-generation reforms APL I and II aimed to address (such as expansion of service coverage by ensuring financing for vaccines and public health insurance and infrastructure). APL III aimed at reducing the occurrence of risk factors affecting maternal and child health, but it did not identify appropriate measures, especially on process quality, and instead used complete prenatal coverage and user satisfaction surveys, and other narrow aspect of structural quality. 5.15 Programmatic approaches are suitable where sector knowledge is strong, program objectives are long-term and clear, and country ownership is established. The choice of an APL instrument for the overall program was appropriate because the government's goals to reduce infant and child mortality were well articulated and would take an extended time, requiring consistency and deepening of reforms over several phases. Strong government ownership of these goals, and a vision for how to pursue them over time, further strengthened the case for an APL. Sufficiently robust triggers, moreover, ensured they did not become inappropriate over time, thus securing continuation of the APL phases. These are useful lessons for the new Multiphase Programmatic Approach. 5.16 Ambitious projects partially relying on a government promise to pass a reform law are likely to need a restructuring. Reallocation of project funds in response to ad hoc government requests may lessen the logic of the results chain and risk the M&E framework from providing sufficient evidence of project achievements. Building on the success of the previous phases, APL III designed activities based on the government's expectations to transform the health insurance system, which did not occur. The cancellation of related activities and the inclusion of less-aligned activities affected the M&E framework, which was ultimately insufficient to provide evidence of the project's achievements. Additional data outside the M&E frameworks had to be used by the end of the project. This example highlights the value of evidence-based policy and reform versus less-aligned changes. A reform process could benefit from articulating a learning agenda and process for fine tuning reforms based on evidence and lessons.
P060434 | Rural Investment & Services Project (APL #1) | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2007 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/703881474490360562/text/000020051-20140613050524.txt | http://documents.worldbank.org/curated/en/703881474490360562/pdf/000020051-20140613050524.pdf | A number of useful lessons were drawn in the ICR. Somewhat adapted these are:(i) Policy conditionality, particularly in the form of broad letters of sector development policy, should match the project scale and scope or be supported by the lending program outside the project. (ii) Grant elements in credit lines often create problems, the poverty objectives of a grant element should be clearly articulated and its impact on that objective monitored.(iii) Business and technical advice in rural finance and small business enterprises are as important as funds availability.
P060434 | Rural Investment & Services Project (APL #1) | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2002 | 2007 | 2009 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/600341468274229437/text/487600PPAR0p061C0Disclosed071231091.txt | http://documents.worldbank.org/curated/en/600341468274229437/pdf/487600PPAR0p061C0Disclosed071231091.pdf | 8. Lessons Learned Five lessons may be drawn\. (1) Conditionsattachedto projects,particularlythose bearingon sector developmentpolicy,should be proportionateto projectscale; otherwise, they should be consignedto other operations.Government sent a policy letter to the Bank and signeda memorandum o funderstanding, inthe hope that broader policy reforms would be supported by a 3rdStructural Adjustment Credit. But SAC111was dropped from the Moldova lending program after an unsuccessfwl 2ndTranche Review, burdeningRISP1with the added responsibility o f addressing the broader reform agenda. (2) Credit agreements and projectbudgetsshould be sufficientlyflexibleto allow for changes inproject financialintermediariesduring implementation. RISP1allowed any pre-qualified financial intermediary to apply to borrowproject funds under subsidiaryloan agreements (SLAs) with the Borrower. Eligibility criteria were established inthe preparationphase and a number of PFIswere evaluated. However, the demand for project resources was greater than the available funds so that resources had to be rationedbetweenthe competing intermediaries. The rules neededto allow new intermediaries to take part inthe competition; and to include the option o f assigning funds by auction. (3) Grant elements in credit linesmay not havethe intendedeffect. A grant element was included inthe credit line for enterprise start-ups inorder to accommodate businesses with weaker collateral. But, inpractice, the same collateral requirements were applied, whether or not a grant was attached to the loan. (4) Credit linesinvolvingmultiplesubloans require a considerable delegationof fiduciary responsibility.InRISP1, delegation worked because\. (i) thestart,banksandborrowersreceivedclearadviceabouttheavailable from credit lines; (ii)the project management unit built up the expertise to conduct a major part of the screening process, leaving the Bank to prior-review larger loans and post-review smaller ones; and (iii) thanks to the technical assistance received from partners, banks were able to improve their subloan applications so that, when needed, prior review, could be conducted expeditiously. (5) Providing consulting services to help small entrepreneurs prepare and implementbusinessplansis as criticalfor the success ofruralfinanceprogramsas providinglong-termcredit. Combining financing with technical assistancehelpedto make RISPl a success. Providing long-term funding to rural businesses was vital. But withouttheBusinessDevelopmentServicescomponent,itis unlikelythatthecreditline would havedisbursed.
P060474 | Sustainability of the National System of Protected Areas Project | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2006 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/983681475110949049/text/000020051-20140617132032.txt | http://documents.worldbank.org/curated/en/983681475110949049/pdf/000020051-20140617132032.pdf | Protected area management requires particular emphasis on self-sufficient generation of revenues. Project features to achieve this need to be a dominant or at least a major part of project design and implementation arrangements: In Bolivia's financial straights, financial self-sufficiency is particularly important. Appropriately, the project emphasized this: one of the 3 objectives was on financing mechanisms, a key project component was to establish and capitalize a trust fund for financing protected areas, and monitorable indicators included financial performance. About 1/3rd of park operating costs are being financed by the trust fund, and envisaged next steps are to develop better mechanisms for collecting user fees and for contributions by local governments.Local management of protected areas can improve administration and financing: Local governments are still insufficiently involved in Bolivia's park management. Substantially increased and even full management responsibility of the local governments might be more effective in ownership, handling local issues and raising finances.Biodiversity conservation benefits from a long-term perspective and program design: Conceiving the project as the first phase of a longer (15 year) program has enabled sustained attention to issues and capacity building that cant be expected to be dealt with in a shorter period, and the confidence to proceed with initiatives based on assured continuity of the program.
P060484 | AR Basic Municipal Services Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/366441467296141090/text/ICRR-Disclosable-P060484-06-30-2016-1467296114472.txt | http://documents.worldbank.org/curated/en/366441467296141090/pdf/ICRR-Disclosable-P060484-06-30-2016-1467296114472.pdf | The ICR provided a series of lessons. The most importanttwo are as follows with some modification oflanguage: Key technicalassistance activities require different approaches and attractive financial terms for demand-driven projects. Theproject experience showed that key technical assistance activities which are critical in improving the Projects executionand the sustainability of sectoral policies was not implemented due to the Provinces and Municipalities lack of willingnessto fund technical assistance through loan proceeds. Providing technical assistance and opportunities for peer learning from otherMunicipalities, as well as more attractive financial terms could be central elements to increase that capacity. In addition,efforts could be made to maximize the use of systemic improvements through the implementation of specific measures to improveexisting systems at the Provincial and Municipal level, instead of focusing on subproject levelcompliance. Demand driven investment projects flexibly respond toa variety of local demands, however they may not be ideal to support sectoral reforms, therefore a better strategy to address thesetwo issues could be limiting the project to fewer sub-sectors. Although subproject eligibility criteria requires detailedeconomic and technical evaluation of individual investments, it is important to note that individual subprojects in a multi-sectorproject do not receive the same level of attention as in operations with a more limited scope. Focusing on fewer sub-sectors seemsto be a more effective strategy to mitigate this risk and, at the same time, to fully capitalize on economies-of-scale and theknow-how generated by the project. This applies for both physical investments and institutional development.
P060499 | Indigenous and Afro-Peruvian Peoples Development Project | Latin America and Caribbean | Peru | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/993471474904105442/text/000020051-20140613030909.txt | http://documents.worldbank.org/curated/en/993471474904105442/pdf/000020051-20140613030909.pdf | (i) The LIL is an instrument for piloting and testing new and innovative ideas, and should be kept simple and uncomplicated.In cases of such weak institutional capacity, perhaps the LIL should have focused first only on capacity building of key stakeholders.(ii) As the ICR states, 'learning by doing' does not mean that the project designers are exempt from ensuring that there is a well defined implementation plan and an operational manual.
P060573 | TOCANTINS SUSTAINABLE REGIONAL DEVELOPMENT PROJECT | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2004 | 2012 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/338521474750581610/text/000020051-20140625191959.txt | http://documents.worldbank.org/curated/en/338521474750581610/pdf/000020051-20140625191959.pdf | The following lessons are taken from the ICR with some adaptation of language:In multi-sector operations conducted in a politically unstable environment, limiting the number of entities involved and recognizing and allowing for political risk can mitigate the impact of changes in administration on implementation. For multi-sector operations, clear and functional implementation arrangements, including a central coordination mechanism (such as a project implementation unit), are critical for efficiency in project management. In this case, no such central coordination existed.Effective monitoring and evaluation requires that outcome indicators should be simple, measurable and with a direct link to both the project financed activities and to the objectives. Opportunities such as mid-term reviews or restructuring can be used to improve and update the results framework. Although participatory mechanisms can help to foster local ownership, they can also create unfulfilled expectations that could be avoided or mitigated through sufficient outreach and clearer communication.
P060575 | Programatic Fiscal Reform I | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2001 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/782751474895940452/text/000020051-20140607171912.txt | http://documents.worldbank.org/curated/en/782751474895940452/pdf/000020051-20140607171912.pdf | The Law of Fiscal Responsibility offers a useful instrument worthy of emulation, particularly by countries having a federal system, to impose fiscal discipline at all levels of government through a single legislative device.
P060577 | Southeast Regional Development Learning and Innovation Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2002 | 2006 | 2005 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/147831474512861332/text/000020051-20140613045217.txt | http://documents.worldbank.org/curated/en/147831474512861332/pdf/000020051-20140613045217.pdf | The additionality and currency repayment terms of Bank loans may make them uncompetitive for second-tier banks. A fee-based contract for technical assistance or trust-funded grants may make more sense in these cases.Technical assistance can help guide a subsidized state credit program into a viable atomonous MFI, but this evolution takes time. Local political support is imperative.Sector-specific infocenters and portals are more likely to succeed than those with a more general business clientele.Start-up infocenters are labor intensive, facing challenges in product development, marketing, and technology. Building on existing cybercafes is more promising because they already have products, infrastructure, a commercial orientation, and often a good location.
P060686 | Municipal Development in Rural Areas | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2003 | 2007 | 2005 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/888721474653098102/text/000020051-20140613042741.txt | http://documents.worldbank.org/curated/en/888721474653098102/pdf/000020051-20140613042741.pdf | Based on the PCN, the main lesson is that institutional mechanisms and project implementation arrangements need careful and early design â€“ the key implementation actors should have the incentives and capacity to implement the project - and the degree of borrower commitment needs to be systematically and realistically assessed upfront. The need for management oversight in this process is critical in order to ensure the efficient use of Bank resources.
P060718 | Renewable Energy for Agriculture Project (GEF) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/714181474489592647/text/000020051-20140617132408.txt | http://documents.worldbank.org/curated/en/714181474489592647/pdf/000020051-20140617132408.pdf | The main lessons are:1. The choice of an agricultural sector institution (FIRCO) as the implementing agency, rather than an energy sector entity, was highly beneficial since it ensured that renewable energy provision remained demand-driven and could be tailored to the needs of farmers.2. The impact of the PV systems is considerably enhanced if farmers are simultaneously helped to diversify cultivation and to market their crops.3. The establishment of vendor financing systems in new sectors and remote geographic areas requires careful design, and must take full account of already operating replication systems.4. An effective financing scheme for renewable energy use for productive purposes in rural areas will likely require continued subsidized financing.5. In future renewable energy projects, it would be useful to include indicators which measure changes in beneficiary income and in category of beneficiary.6. The project shows the benefits of flexibility during implementation, especially in an innovative operation of this kind.
P060785 | HN ECONOMIC & FIN.MANAGEMENT PROJECT | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2001 | 2007 | 2007 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/759071474489623163/text/000020051-20140617135253.txt | http://documents.worldbank.org/curated/en/759071474489623163/pdf/000020051-20140617135253.pdf | The main lesson, as stated in the ICR, is that in a difficult environment such as Honduras, with limited implementation capacity and tense political relations between different branches of government, projects in support of inherently long-term public sector modernization efforts must be realistic and modest.
P060786 | Public Sector Modernization Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2004 | 2011 | 2012 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/343421474566229736/text/000020051-20140625071111.txt | http://documents.worldbank.org/curated/en/343421474566229736/pdf/000020051-20140625071111.pdf | IEG mainly supports lessons discussed in the ICR. In particular, IEG supports the ICR position that more narrowly focused operations limit implementation complexity for the borrower and supervision challenges for the Bank. However, there are also considerations that make complex operations desirable for borrowers judged to have the capacity to implement them. Clients may request a wide range of components because they want to take advantage of an opening for wide-ranging reform (e.g. a crisis response, or the coming to power of a new government). There may also be reason for such an operation when the political context for reforms is uncertain, and a venture capital approach makes sense, assuming that some components that have no traction will be dropped during implementation and restructuring. IEG also supports the thrust of the ICR lesson that information and communication technology (ICT) operations need enhanced preparation. An e-readiness assessment is crucial, along with consideration of business process changes that can take full advantage of new ICT opportunities.
P060833 | PUBLIC SERV. REF PROG | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/191521475084648225/text/000020051-20140619081006.txt | http://documents.worldbank.org/curated/en/191521475084648225/pdf/000020051-20140619081006.pdf | Lessons include:Supply-driven reform cannot work and if it does, it is unlikely to be sustainable. The reform agenda should have been centered around key MDAs and should have involved providing them with right incentives for reform. Civil society and non-governmental partners constitute important stakeholders in public sector reform and their involvement in monitoring progress is a key factor in creating and sustaining demand.A shift from the focus on the ultimate outcomes to a sole focus on outputs (and at best some intermediate outcomes) is not advisable in an APL. There should be clear links between desired outcomes and expected outputs, and the links should be closely monitored from the outset.
P060833 | PUBLIC SERV. REF PROG | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2008 | 2014 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/467601468309235088/text/787790PPAR0Tan000OUOU0900Box379827B.txt | http://documents.worldbank.org/curated/en/467601468309235088/pdf/787790PPAR0Tan000OUOU0900Box379827B.pdf | 7. Lessons 7.1 An excessive focus on form rather than function in public service reform is counterproductive, particularly when based on models borrowed from other countries and implemented without sufficient consideration of local conditions. The best illustrations are represented by the proliferation of Executive Agencies with limited managerial autonomy and hence limited impact on service delivery. Using the number of new executive agencies as an indicator of success, as the projectâ€Ÿs result matrix did, is misleading. 7.2 Political windows of opportunity may span years but rarely decades, and that reform programs that aim at improving service delivery need to show some short term results to citizens to build support in public opinion. This could help ensure that they cannot be easily reversed after a change in government. This lesson points to the importance of understanding each countryâ€Ÿs political landscape, the dynamic nature of the external environment for reform, the need for sustained dialogue, and the long term nature of public sector reform. Insistence on considering capacity building outputs as outcomes shows a rather technocratic view of public service reform, as such changes are certainly visible to experts but invisible to citizens unless they see improved service delivery. 7.3 Capacity building cannot be seen as an effort that can show results in terms of improved services only in the medium term. Capacity is built also by interventions that lead to incremental improvements in service delivery (for example, faster processing of certificates, titles or passports) that provide feedback to the capacity building efforts in a virtuous circle. Capacity building is incremental and must be translated into incremental improvements in performance with short term and medium term results. 7.4 Performance incentives work only where management has enough autonomy in deciding how to combine resources to achieve results. The Executive Agencies that were most successful in Tanzania had own revenues and some control on how to spend them. 7.5 The consequences of failing to address policy reversals early can be serious. While policy reversals are always possible in democracies, such changes should have immediate effects on projects and programs that are being implemented either to support the policies being reversed or are assuming the continuation of such policies in their results frameworks. Identification of risks and mitigating measures at project design, and sanctions during implementation, including suspension or cancellation of credits and grants, are important tools to be considered in such cases. 7.6 The risks of unfocused public service reform projects in low capacity environments are high, even when political commitment is strong. Projects should be shorter and smaller, aligning ambitions to capacity and political realities, building the next project on the achievements of the previous one, in fast cycles that require short preparation times, and a strong ability to listen and adjust quickly to the needs of reformers in government.
P060908 | Mexico Mesoamerican Biological Corridor Project (GEF) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/788081474503854077/text/000020051-20140624184051.txt | http://documents.worldbank.org/curated/en/788081474503854077/pdf/000020051-20140624184051.pdf | The desired function(s) of a corridor must be determined prior to its design so that it can be managed in a way that yields optimal outcomes based on the functions it is expected to perform. The roles corridors play derive from six ecological functions: habitat, conduit, filter, barrier, source, and sink (Hess G.R.; Fischer R.A. 2001). Project support may contribute to one or more of these goals, but it is essential that projects designed to support corridor consolidation are explicit about what they are trying to achieve and that specific indicators are put in place to measure the contribution of the project to these aims. All stakeholders involved in corridor design and management should have a clear unified understanding of the agreed-upon functions of the proposed corridor and the implications thereof for land administration and management, natural resource extraction, and their role in relation to biological monitoring and reporting.While more research is needed, there is evidence that conservation corridors and the conservation friendly activities that have been promoted therein, may reduce vulnerability associated with natural disaster and aid communities in their climate adaptation efforts. Corridor conservation practices such as conversion to sylvopastoral systems, hillside management, increased crop varieties and landscape management approaches that incorporate conservation and production spaces can reduce vulnerability to extreme climatic events. When dealing with challenges that require intersectoral collaboration, such as support for a conservation corridor system, project design should involve public institutions which have an intersectoral mandate in order to facilitate the cross sector efforts required by environment, climate change, and social issues.
P060943 | MY-SOCIAL SEC SUPPORT | East Asia and Pacific | Malaysia | IBRD |  | Human Development | Social Protection & Jobs | IBRD | IPF | 1999 | 2003 | 2004 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/444381474657858121/text/000020051-20140612103947.txt | http://documents.worldbank.org/curated/en/444381474657858121/pdf/000020051-20140612103947.pdf | Bank procurement rules may appear too cumbersome to countries that are able to set and follow their own procurement rules and that can finance their own operations. - Successful implementation of projects prepared to respond to crises depends upon widespread support among key stakeholders inside and outside governments. This is especially important in an environment where macroeconomic events provide the main impetus for project dialogue and design.- Strong government ownership is crucial from initial design throughout implementation for project components that probe or research areas of increased sensitivity, especially those carried out by technical assistance.
P061209 | Basic Education Project | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2004 | 2009 | 2011 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/289311475091415555/text/000020051-20140620081328.txt | http://documents.worldbank.org/curated/en/289311475091415555/pdf/000020051-20140620081328.pdf | Provision of school places needs to be complemented by targeted interventions to address specific constraints of some groups. For example, alternative schools and tutoring programs for girls were used effectively in this project.Standardized measures of education quality that will allow results to be comparable across time and place are required. Assessment of efficacy can be constrained by lack of comparable learning outcome indicators. Further, as access to basic education is extended to children with lower economic status, even if the quality of instruction remains the same or improves, average learning outcomes of children enrolled can fall despite the fact that many poor children are learning more. The need to ensure that learning outcomes are monitored, not just on average, but among the poor cannot be over emphasized.Decentralization of education management, especially to local/school levels, should be accompanied by a clearly worked out fiduciary management system that would ensure proper use and accountability of funds to minimize the risk of leakage and suspension of the reform (ICR, p. 33).When large-scale recruitment of contract teachers is planned at lower salary levels, clear and effective management systems must be in place to ensure that the new teachers are used effectively and to minimize opportunities for conflict with unions that may not be fully supportive of the new terms of employment (ICR, p. 33).
P061214 | SB-SAC | East Asia and Pacific | Solomon Islands | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2001 | 2002 | ICRR | Less than 10 million | Highly Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/356381474510131839/text/000020051-20140602113707.txt | http://documents.worldbank.org/curated/en/356381474510131839/pdf/000020051-20140602113707.pdf | In an ethnically diverse country with significant regional variation in income, the Bank should consider efforts to mitigate inequalitiesBased on initial progress under the project, even where government capacity is thin, a patient and painstaking dialogue can yield substantial benefits in reform progress
P061314 | GEF CR-ECOMARKETS | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2000 | 2007 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/778571474504635524/text/000020051-20140617134315.txt | http://documents.worldbank.org/curated/en/778571474504635524/pdf/000020051-20140617134315.pdf | (1) Implementing a successful environmental services program takes a concerted effort over time with political support and an efficient national institutional arrangement and equally efficient local institutions when the program is decentralized.(2) Developing sustainable financing sources for biodiversity conservation is particularly challenging. Efforts to induce the private sector to enter into voluntary agreements to pay for environmental services may be a useful way of strengthening the private sectorâ€™s awareness and understanding of the system of payments for ecosystem services, but are unlikely to generate significant amounts of funding to support a national-level PSA program.(3) While a fixed national price might make political and administrative implementation of a payments for environmental services program easier, it is probably not the most efficient. Differentiated payments would make for a more efficient use of scarce resources and would allow for an increase in the area covered. The use of undifferentiated payments may result in over-payment in some areas (e,g., paying for conservation in cases where conservation may well have happened anyway), while offering insufficient payments to induce conservation in other priority areas. (4) The design of PSA programs should target efforts (including extending adequate support to appropriate and capable CBOs and NGOs) to ensure that small and medium-sized landholders, many of whom are poor, have access to and can participate in the program.
P061496 | SAC | Europe and Central Asia | Moldova | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 1999 | 2002 | 2003 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/643651474496592104/text/000020051-20140607162132.txt | http://documents.worldbank.org/curated/en/643651474496592104/pdf/000020051-20140607162132.pdf | Improved public expenditure management requires focused efforts at capacity building--Efforts to rationalize and control budgetary spending using only administrative tools have limited impact.Beyond land privatization and farm restructuring, post-privatization support is necessary to evoke a "supply response"--Assistance with management, marketing, and finance are required in order to create a more efficient agricultural sector
P061558 | WATER SECTOR PROJECT | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2001 | 2011 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/428091474483375702/text/000020051-20140624183833.txt | http://documents.worldbank.org/curated/en/428091474483375702/pdf/000020051-20140624183833.pdf | Depending on country conditions, some cost recovery may be possible even in difficult circumstances. By providing greater access to water services and reducing operational costs through new infrastructure and efficiency improvements using PPP, the cost of water to households can be significantly reduced below that of alternative providers such as commercialized standpipes and water vendors. Under these circumstances poor people may be able to reduce their water coping costs and show willingness to pay.Private sector participation may be a feasible delivery option even in poor countries. Niger was able to attract international competition for urban water services and at the same time was able to promote local private operators for rural facilities.Improving in a sustainable manner water service provision often requires both supporting sectoral reform and financing key investments. Tackling water sector institutional reform without the funding of major investments can be risky as the latter usually provide a counterbalance to the political cost of the reform.Rehabilitation investments, which are critical to the improvement of the services in the context of a PPP, can be delegated to the lease contractor. This would ensure timely execution and avoid conflicts with the asset-holding companies, which tend to favor large-scale investments.
P061577 | PERAC | Western and Central Africa | Benin | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2001 | 2003 | 2004 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/697451474397615201/text/000020051-20140612105255.txt | http://documents.worldbank.org/curated/en/697451474397615201/pdf/000020051-20140612105255.pdf | 1) The transition to performance budgeting is a slow and gradual process, especially in countries with limited administrative and institutional capacity. 2) In promoting/extending performance budgeting, the Bank and the borrower should choose very carefully the candidate ministries.3) As the ICR points out, not only does performance budgeting require a considerable input from the Bank and donors to supervise and assist in the transition at the level of the central ministries, but also at the sectoral levels, where specialized TA and training are needed for strategy formulation, methodology, links between budget requests and results, monitoring, performance indicators, etc. 4) In the absence of tranche conditionality in budget reform, it is critically important for the preparation/appraisal team and the borrower to set clearly agreed and realistic targets, benchmarks, and triggers before moving to the next operation. It requires also close supervision and monitoring by the Bank.
P062619 | BR INSS REF LIL | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/798901475073402141/text/000020051-20140613060240.txt | http://documents.worldbank.org/curated/en/798901475073402141/pdf/000020051-20140613060240.pdf | 1. It takes two sides to implement a program -- there was excellent cooperation between the Bank and the Ministry of Social Security. The Government points to strong commitment by the top echelons of the Administration which ensured that in the case of modifications to the direction of the project or changes in government, procedures were rapidly adapted to the new circumstances.2. Loan size is not necessarily a determinant of a Government's interest in a project. Attention in this case was mobilized on a small loan that formed part of a larger program of social protection operations. The change of culture associated with the execution of activities planned under the aegis of this LIL required adherence to a strict timetable and a certain dynamism that was not evident in the social security public service - where bureaucracy and budgetary problems had been at the root of constant delays. The project helped to change behavior and later operations were able to draw on the experience. 3. Having a clear purpose of the LIL. The ICR is written around the technical assistance aspects of this operation, but it did have a hypothesis-testing aspect as well, even though this may not have been recognized at the time: the LIL in fact tested whether the Brazilian system of social protection using cash transfers to poor people could be made more efficient and equitable. It thereby enabled a much larger loan (the Brazil Bolsa Familia APL of $500 million) to be approved by the Board in June 2004.
P062628 | Public-Private Partnership and Information Management for Regional Development Project | Eastern and Southern Africa | Madagascar | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2003 | 2004 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/630691474633015316/text/000020051-20140612093346.txt | http://documents.worldbank.org/curated/en/630691474633015316/pdf/000020051-20140612093346.pdf | Before proceeding with a project, the Bank should gain assurances of strong commitment from all involved levels of governmentBefore proceeding with a project, the Bank should carefully assess the capacity of Borrower institutions to implement the project. The Bank should also assure that all key administrative and contractual arrangements are in place or well-advancedExcessive turnover in Bank task management makes the achievement of project objectives more difficult
P062668 | Emergency Recovery & Disaster Management Project | Latin America and Caribbean | St. Kitts and Nevis | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2004 | 2004 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/414381475070057328/text/St-Kitts-Nevis-Oecs-Emergency-Recovery-Disaster-Management-Program.txt | http://documents.worldbank.org/curated/en/414381475070057328/pdf/000020051-20140612105844.pdf | 1. Reconstruction components often require careful assessment and a longer-term effort that generally extends the implementation period beyond the normal three years stipulated for Bank-assisted emergency operations (ERLs). 2. If major works are included in an emergency project, there should be an explicit provision at the design stage for a review of project scope after designs have been prepared. In this particular case, it would have been more practical to separate the actual emergency operation, which would have included quick- disbursing components and technical assistance, and have the actual reconstruction works financed by a standard investment loan in a later phase. 3. Processing loans and/or credits for different (in this case, OECS) countries as separate projects, even if they are part of a broader program, may be preferable to integrating them into one horizontal APL. The Bank system does not allow for a segregation of reporting and accounting on individual sub-projects (because APL phases each correspond to one project with one P0 number). 4. The implementation capacity of post-disaster Project Coordinating Units is slow to develop in most cases. 5. In projects lacking a critical mass of work it is difficult for governments to allocate enough of their scarce qualified manpower to Project Coordinating units. 6. TORs for consulting engineers need to specify government budget constraints to avoid over-designed infrastructure that will be unaffordable and therefore impossible to implement. 7. In emergency projects with short implementation periods (and where delays can compromise timely completion), the Bank needs to consider requiring performance guarantees of consultants and applying penalties for late submissions.
P062682 | Flood Emergency Project | Europe and Central Asia | Kyrgyz Republic | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 1999 | 2004 | 2005 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/113421474750526646/text/000020051-20140612152405.txt | http://documents.worldbank.org/curated/en/113421474750526646/pdf/000020051-20140612152405.pdf | Simple technologies and design approaches which are new for the borrowing country can be successfully introduced, and adopted by relatively inexperienced contractors if the necessary support of international experts, along with effective local support, is provided. Import of new products can demonstrate the effectiveness of new technologies and provide the key to their acceptance on a wider scale, as well as a guide and comparative gauge for local manufacture.A generally cooperative approach to resolving contractorsâ€™ difficulties, especially lenience with extension of contracts without imposing penalties, eased project implementation.In this case, flexibility of project design, accompanied by good resource planning, sound engineering design, and effective management for implementation, produced very good results. What was planned as an emergency recovery project hasenhanced not only the nationâ€™s long-term infrastructural assets, but also its stock of engineering and contracting expertise and has provided significant short-term employment.Good communication with all levels made for effective problem solving by Bank staff.A very high proportion of project funds in infrastructure projects are channelled to contractors. The impact of these projects on the contracting industry could be substantial, especially in transition economies.Timely project implementation depends on good project planning. In this case, the time-frames of both sub-project contracts and the project itself had to be extended because no proper account was taken of the need to halt works during the flood season.On-the-job training and regular supervision by experienced engineers is critical for satisfactory results and to provide a relatively homogeneous quality level.
P062714 | IRRIGATION IMPROVEMENT PROJECT | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/554171474483354769/text/000146597-20140619162924.txt | http://documents.worldbank.org/curated/en/554171474483354769/pdf/000146597-20140619162924.pdf | Several important lessons may be drawn from this project, including the following:A clear understanding of the opportunities and technical and social constraints for improved water use efficiency is needed in the design and management of spate irrigation systems. While each system and season is different, these opportunities may lie in increasing available water capture, designing, managing and creating incentives to optimize water spread and yield, and developing support services to move towards higher value commodities to the extent that markets permit. Government needs to provide the recurrent budget that sustainable operation of improved irrigation works calls for: both to cover the upkeep of headworks (which will remain government's responsibility) and for further consolidation of user associations so that they may fully discharge their responsibilities for maintaining secondary and tertiary canals once hand-over has taken place. The design and promotion of participatory irrigation management schemes needs to take full account of inequalities in the distribution of land and water rights because these influence farmers' incentive to participate and help to define the scope for poverty reduction; social assessments conducted as part of project appraisal need to map these inequalities and to propose ways to mitigate their adverse effects.
P062748 | VN - COMMUNITY BASED RURAL INFRA. | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/425261475070748794/text/Vietnam-Community-Based-Rural-Infrastructure.txt | http://documents.worldbank.org/curated/en/425261475070748794/pdf/Vietnam-Community-Based-Rural-Infrastructure.pdf | Of the lessons derived by the ICR, the following are considered by IEG to be especially noteworthy:Â· The design and implementation of a robust M&E framework, underpinned by a well-functioning, automated MIS, should be an integral part of a project involving a large number of performance indicators and implementing agencies. Its design should take account of the specific needs of a decentralized community-based operation.Â· Centralized control of financial management, while reducing somewhat the risk of irregularities, is inappropriate for such a decentralized operation as this one. Although the project was successful in building capacity at the commune level, the opportunity was missed to develop financial and project management abilities at the provincial and district levels.Â· The project demonstrates that a careful, gradual, country-oriented approach to community participation, built upwards from the â€œgrass roots,â€ can be more fruitful than a standardized methodology based on experience elsewhere. This would be particularly likely to be the case in countries where the traditions of democracy and freedom of choice at the community level are in their infancy.Â· If, as in this case, it is the intention to mainstream the project's approach within the country, then a â€œroad mapâ€ for achieving this should be incorporated into the project's design. In this case, its absence inhibited the counterpart agency from integrating the project's achievements into the government's system.
P062790 | BO INST REF (OLD CIV S) | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 1999 | 2007 | 2009 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/469961475092820807/text/000020051-20140619074855.txt | http://documents.worldbank.org/curated/en/469961475092820807/pdf/000020051-20140619074855.pdf | The ICR contains an unusually thoughtful, analytical retrospective on implementation of the project and possible implications for future support of institutional reform in Bolivia and elsewhere. In addition to lessons drawn, the analysis presents both findings of analysis and raises a number of issues for further consideration. The key lessons for possible Bank support of public sector institutional reform in Bolivia from IEGâ€™s perspective and with which IEG concurs are stated in the ICR (paragraph 82 d). These set forth the following criteria â€“ based on the Bankâ€™s experience under IRP â€“ for future Bank support. Of these, 5 stand out for their resonance with the lessons of IEG evaluations of instances of effective support in other countries in political or social turmoil: (i) Reforms should be narrowly defined, in order to avoid the dissipation of efforts; (ii) Champions for each area or agency under reforms should be identified and take the leadership of reform;(iii) Selected areas or agencies of reform should provide quick gains, visible results in the short term;(iv) Preferably these gains should be linked to services delivered to the public;(v) Areas or agencies selected for reform should be isolated (e.g., by selection of â€œconsensusâ€ targets â€“ although such may be nonexistent if all parties pursue a â€œgridlockâ€ strategy) so that external political events do not affect their objectives or achievements.
P062837 | PSMAC | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2000 | 2002 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/386451474907796376/text/000020051-20140602110121.txt | http://documents.worldbank.org/curated/en/386451474907796376/pdf/000020051-20140602110121.pdf | Government commitment is essential for this kind of reform. The uneven pace of implementation for this modest program is a reminder that reform efforts need widespread support, and the Bank should assist governments to build such support with the population.
P062837 | PSMAC | Middle East and North Africa | Yemen, Republic of | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 1999 | 2000 | 2007 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/187021468334802560/text/37392.txt | http://documents.worldbank.org/curated/en/187021468334802560/pdf/37392.pdf | LESSONS Restructuringwhen countrycircumstanceschange\. Whenthe project environment changes dramatically, the Bank shouldbe readyto restructure key projects inthe portfolio. When Northand South Yemen were unified, andthe new country faced the challenge o fintegrating two distinctly different civil service traditions, the Bank shouldhave moved quickly to discuss the new circumstances with the government, andhavebeenpreparedto restructure the IDPAP. Resources could have been shifted to new priorities as required. The Bank eventually did restructure the project, but only inits closing stages when the relevance o fwhat it had originally set out supportinghad diminished. An opportunitywas lost to play a more constructive role inthe fusing o f the two civil services. The consequences inthe form o fexcessnumbers andanunaffordablewage billmadetheBank's subsequent efforts to assist with public administrationreform more difficult.
P062840 | TD-Petroleum Economy Mgmt | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2005 | 2007 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/295651474944656014/text/000020051-20140617131144.txt | http://documents.worldbank.org/curated/en/295651474944656014/pdf/000020051-20140617131144.pdf | Ownership, commitment, and leadership at both the political and technical levels are essential on a long term basis to sustain public sector reforms and strengthen institutional capacity. In the case of the GEEP, support for the project wavered and declined as implementation progressed and as GOC's policies on the management of oil revenue changed.- In countries endowed with mineral resources expected to generate revenues for a long period, it is essential that Bank support be directed at the public/private structures directly responsible for managing the resources. If temporary structures are necessary, these should be as simple as possible with well defined mandates and with the necessary authority to guarantee coordination. -Institutional capacity building requires the prerequisite of a well defined and concrete strategy jointly developed by the Bank and the Borrower and with full ownership by the latter. -Consistency and continuity in Bank supervision are essential (in this case, there were six TTLs).
P062840 | TD-Petroleum Economy Mgmt | Western and Central Africa | Chad | IDA |  | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2000 | 2005 | 2010 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/565481468224677215/text/503150PPAR0P05101Official0use0only1.txt | http://documents.worldbank.org/curated/en/565481468224677215/pdf/503150PPAR0P05101Official0use0only1.pdf | 4. Lessons and Future Implications 4.1 The well-known lesson that government ownership and commitment are the major influence o n the effectiveness of projects and programs i s underlined by the experience o f the Chad-Cameroon program. Other lessons learned from the program are identified belowmany o f them also well known but brought in sharp relief by this experience. Because the findings and conclusions are discussed in the earlier sections, the lessons and implications are listed below with a minimum o f elaboration. (Project-specific lessons are included in the corresponding annex.) RELEVANCE, R I S K S , AND TIMING 4.2 International experience has shown that adequate expenditure management mechanisms should be in place, and tested, before a large revenue increase i s likely to accrue. In this case, the time available for capacity-building after Board approval and before the flow o f o i l revenue was much shorter than expected and the revenue much larger-adding to the difficulty o f building capacity contemporaneously with program implementation. A secondary lesson is therefore to build expenditure management capacity as robust as necessary to fit a high scenario o f revenue increase. (The capacity created will be useful to the country even if the high scenario does not materialize.) 4.3 Setting up institutional enclaves and special mechanisms to protect resources and accomplish quick results can damage local capacity in the long term. Such enclaves are generally not successful beyond the short term and, even when successful in the short term, they tend to undermine the already weak local systems and thus long-term development. In this case, although the rationale for the establishment o f the revenue escrow account and the earmarking arrangements was strong in the specific country context in 2000, when tested by reality these mechanisms failed to achieve their objectives and meanwhile stood in the way o f sustainable improvements in fiscal and expenditure management capacity. 4.4 While protecting inputs must remain a paramount consideration, development objectives should be formulated in terms o f outcomes (ifpossible), meaningful outputs, or concrete process improvements-rather than in terms o f inputs-and performance indicators should be limited to thefew key indicators that are critical to achieving the PDOs and are monitorable. Even when the immediate aim o f the project i s to increase resource availability, reduce the cost o f input acquisition, or channel resources toward priority uses, a failure to define clearly the expected results in terms o f key outputs, outcomes, or major process improvements risks distorting the actual design o f the project away from those results. In this case, defining the main project objective for Chad in terms o f budgeted expenditure to be achieved diverted attention away from the efficiency o f expenditure and budget execution. And to l i s t dozens o f key performance indicators o f diverse importance and questionable monitorability makes monitoring impossible. AND DESIGN APPROACH 4.5 If the WBG decides to risk involvement in ambiguous and fluid situations, it pays not to do so in overly detailed and rigid ways. Utmost clarity is needed o n the objectives, principles, and parameters, but the design and implementation modalities should be as fluid as the situation itself, rather than rely on binary choices and numerical rules. This approach, however, may in practice foster a propensity to make successive small compromises, cumulating in the risk that continued Bank engagement may result in acquiescence to inefficient use o f resources. Thus, in addition to clarity o f purpose, an adaptable engagement grounded on flexible but robust dialogue requires a strong fabric o f reciprocal trust between staff and management and continuity o f both. 4.6 Revenue transparency i s necessary-specially for revenues from extractive industries-but i s not sufficient. Transparency on the expenditure side i s critical as well. In this case, setting as the main target a global minimum percentage spending on several sectors implied that the global target could be met even if the intersectoral allocation o f the resources was very different from what had been agreed, and without regard to the efficiency o f their use. 4.7 Project design must be based on recognition o f institutional and administrative capacity. I t i s important in countries with weak capacity to focus on addressing the basic problems rather than attempting to introduce sophisticated practices. In this case, paradoxically, major components o f the program in effect assumed the prior existence o f the very capacity they aimed to build. 4.8 An innovative design, even if it proves unsuccessful, may contain novel elements worthy o f consideration and possible replication. In this case, there are three such elements\. The formation o f the Collige de ContrGle was an excellent and exciting idea, even if it did not enjoy the necessary government support-and such joint publidprivate/ NGO entities have the potential to foster expenditure efficiency as well as social accountability in countries with a government reasonably interested in a prodevelopment, pro-poor expenditure policy. The Provisional Committee to allocate the 5 percent o f the direct o i l revenue to the oil-producing region can be an illustration for similar arrangements in other countries with valuable mineral resources, despite flaws in i t s operation in this case. Finally, the cover and voice given to local NGOs through the dialogue on the preparation o f the program and during i t s implementation should be a regular feature o f all such WBG interventions. WBG PERFORMANCE 4.9 Although in complex and high-profile cases strategic guidance and major decisions must come from the top leadership o f the WBG, it i s not clear in this case that the top-down direct intervention by the Bank President's Office in 2006 was helpful to formulate a new agreement with a better chance o f enforcement. 4.10 In large, complex WBG projects with multiple stakeholders, good WB-IFC cooperation i s important to improve the chances for positive results. In this case there was good WB-IFC cooperation on the main pipeline project, but it also extended to Advisory Services operations. In late-2004, when the IDA-funded capacity-building projects were found to be progressing slower than expected, IFC was able to provide new funding for sustaining the capacity-building initiatives. 4.1 1 IFC's Advisory Services have a signijkantpotential role to help the local private sector. They can enable local companies to participate in the economic activity created by the project; help the sponsors-typically large multinational corporations-meet national content 47 requirements; and promote local economic development. In this case, the Enterprise Center-the focal point o f IFC's Chad SME program-became the cornerstone o f Exxon's procurement platform that was the sole source for all o f i t s purchases in Chad, starting in 2005. 4.12 Whether the World Bank or the I F C i s involved, the concern with development effectiveness goes beyond the gates o f individual projects-however well they may be technically done-to the results o f the overall program. There i s no contradiction between viewing favorably the technical and financial success o f the pipeline project even though the weight o f other unfavorable outcomes leads to a negative conclusion o n the development outcome o f the program o f which it was a component, as in this evaluation. However, the evaluation illustrates the basic point that a part o f a program, however well carried out, cannot be separated from the overall program and the broader setting within which its impact i s being assessed\. a project or a subproject cannot be ring-fenced in the assessment. 4.13 Continuity is critical to manage a project that i s central to a program, and a minimum o f in-house technical competence is necessary to supervise consultants. In this case, the revenue management project had six task team leaders in its seven years, and the Chad capacity-building project relied almost entirely on consultants for the first years, without any in-house expertise in the technical dimensions o f o i l exploration and production. 4.14 Good communications and transparency are particularly important in the context o f a difficult decision. Senior management would want to appropriately consider the views o f key operational managers and staff and ensure the fullest possible measure o f advance consultation with key development partners. IMPLICATIONS FOR THE FUTURE MAJOR 4.15 With substantial o i l revenue expected to continue for many years, it i s s t i l l possible for Chad to escape the resource curse. The difficulties are known. Institutional and organizational capacity remain weak. Macroeconomic sustainability i s injeopardy. Fiduciary risk i s likely to increase in the short t e r m with the unexpected fall in o i l price and revenue in 2009 and 2010-producing pressures to preserve security and regime maintenance expenditures, and hence a downward pressure on pro-development, pro-poor expenditure. Budgeting systems and skills remain quite insufficient for efficient resource allocation, and motivation and integrity have been weakened by the lack o f consequences for the spreading non-compliance with fundamental rules. However, there are scenarios under which a good development outcome in the long run is s t i l l conceivable. The Bank could cooperate with the IMF in monitoring overall fiscal and expenditure outcomes and make a useful contribution by providing good and flexible advice in public sector management-focused o n the basics, recognizing capacity realities, and supported by assertive cooperation o f certain major bilateral partners. But the most important factor would be a new and genuine determination by Chad's government to use the o i l resources for development and poverty reduction, and do so responsively and efficiently. 4.16 The Chad-Cameroon o i l development and pipeline construction program exemplifies the inherent tension between the limits o f the WBG as an international organization and i t s mandate to foster development and poverty reduction. The WBG went very far in 1999 toward the development side, by setting up complicated and prescriptive arrangements to maximize the probability that the Chad government would use the o i l revenue windfall mainly for development and poverty reduction. For various reasons, the revenue windfall turned out to be used in large part for military expenditure and other regime maintenance and for wasteful construction. The governance climate in Chad did not improve-rather the reverse. 4.17 However, it should not be concluded from this experience that the WBG should not intervene in supporting extractive industries because doing so carries reputational risks and success i s unlikely. Indeed, despite the disappointing overall outcomes o n the development and governance side, WBG involvement contributed to a notable increase in expenditures in social sectors and environmental and social protection within the confines o f the project better than they would have been otherwise. The analysis o f this report suggests that realistic and constructive WBG involvement in extractive industries could rest o n combining an insistence on high standards o f environmental and social protection with flexible conditionality o n the composition o f all expenditure and its efficiency-complemented by assistance to strengthen a unified budget system, ensure transparency in both revenue and expenditure, and build capacity in accountability institutions. T o be effective, WBG involvement must be buttressed by an agreement with all other major donors that violation o f the environmental and social standards or backsliding o n fiscal transparency or accountability would trigger consequences for the overall f l o w o f aid t o the government concerned.
P062916 | Bangladesh Central Bank Strengthening Project | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2003 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/701041475787383140/text/000180307-20150108104352.txt | http://documents.worldbank.org/curated/en/701041475787383140/pdf/000180307-20150108104352.pdf | IEG concurs with the lessons noted in the ICR and two of the lessons stand out.The first lesson is the critical importance of committed and reform-minded leadership and senior management and a capable project team for implementing and sustaining complex institutional reforms in a traditional and hierarchical institution. The second lesson is the importance of defining the project development objective and to link it closely with a results framework that allows the project team to accurately measure progress towards the objective.
P062932 | HEALTH REFORM PROGRAM (First Phase: Mother and Child Insuranceand Decentralization of Health Services) | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/370121474664846792/text/000020051-20140617140752.txt | http://documents.worldbank.org/curated/en/370121474664846792/pdf/000020051-20140617140752.pdf | Political volatility can have a detrimental effect on project implementation and impact. Frequent changes of political appointees often result in changes in priorities that lead to confusion in project teams and delay in project implementation.Use of a variety of lending and non-lending instruments can enhance dialogue and the implementation of critical sector reform.The use of a clear evidence-based causality model can strongly enhance the achievement of project development objectives.Strategies to document and address cultural barriers to health services access are vital for improving overall access to care when beneficiaries belong to diverse indigenous groups.
P062932 | HEALTH REFORM PROGRAM (First Phase: Mother and Child Insuranceand Decentralization of Health Services) | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2006 | 2009 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/459241468070134508/text/491110PPAR0PER162B01PUBLIC071221091.txt | http://documents.worldbank.org/curated/en/459241468070134508/pdf/491110PPAR0PER162B01PUBLIC071221091.pdf | 4. LESSONS AND VALUE-ADDED OF THE BANK 4.1 This chapter provides a 10-year perspective on the Bank's objectives and continued value added in HNP in Peru, as well as lessons on some o f the key themes o f the broader IEG evaluation o f Bank support for HNP. The period o f analysis spanned four CASs (1 994, 1997,2002, and 2006). The first three included health as a key strategy to improve human capital, while the l a d 5 prioritized new sectors, such as water and sanitation, electricity, housing and property rights, but continued to emphasize efforts to reform the health system and to improve service quality through a new social contract based on better information and accountability in the social sectors. 4.2 During this period, Peru's economy improved remarkably due to fiscal discipline and economic reforms, yet poverty and inequality persisted and public administration was weak and centralized. The country moved from a period o f collapsing infrastructure that affected the health sector, to achieving important improvements both in terms o f health facilities and coverage. However, the quality o f social services was poor and marked by inequality in access. There were improvements in access and health outcomes among the poor and the gap between the poor and non-poor has narrowed, but in absolute terms the gap remains large HEALTH OUTCOMES AMONG THE POOR 4.3 The Bank's experience in Peru demonstrates how an emphasis on pro-poor health policies can be sustained through multiple instruments in a constantly changing political environment. In addition to the two health investment projects assessed here, the Bank invoked policy dialogue, policy notes, analytical work, and policy lending. Respondents reported that analytical studies such as Peru\. Improving Health Care for the Poor (World Bank 1999b) and An Opportunity for a Different Peru (Giugale and others 2007) were highly influential in helping to assess the options. The PSRL series was complementary to health investment lending, including as one o f i t s main objectives to protect critical anti-poverty expenditures from budgetary cuts and to improve access o f the poor to health programs such as SIS and CLAS. All o f these actions were consistent with the poverty reduction objectives o f the four CASs. Even as 65 The fourth CAS was also referred to as a Country Partnership Strategy. the health investment projects' activities were adapted over time, the poverty focus did not change. 4.4 Geographical targeting can achieve a general pro-poor focus, but in a country with large inequalities in both urban and rural areas such as Peru, more precise targeting mechanisms are needed to ensure that resources disproportionately reach the poor. While both BHNP and PARSALUD had a pro-poor focus, the targeting mechanisms for the poor were relatively crude. B H N P took place in 13 provinces classified at the time as the most deprived and in two classified as deprived. PARSALUD' s initial targeting focused on rural and Andean populations. While SIS was applied nationwide, it lacked precise targeting mechanisms for beneficiaries. Respondents for this evaluation suggested that the Bank prioritized the expansion o f coverage first, while quality and targeting were seen as steps to be taken once the program had sufficient strength and coverage. After the reorganization o f components in 2003, efforts were made to support actions directed towards improving the targeting o f SIS. Although in rural areas SIS registered and provided services to all beneficiaries, in urban areas, a socioeconomic assessment was carried out to determine whether the beneficiary qualified for the SIS subsidy. This socioeconomic assessment was then used for the implementation o f the SISFOH (the Household Targeting System in Peru), which i s used to improve targeting o f various social programs in the 30 largest cities in the country. 4.5 The failure of monitoring and evaluation design and implementationto focus explicitly on the poor weakens the ability of programs to assess impacts and to learn from and perfect pro-poor targeting. The two investment projects explicitly addressed H N P outcomes among people in poor regions and the poorest groups in the population, but evidence was collected in most cases on average health outcomes. Neither project set targets for outcomes or impacts specifically for the poor, nor were outcomes or access for the poor to be monitored. While access and outcomes can be tracked through the national DHS surveys for those in urban and rural areas and by wealth quintile, and to some extent in project regions compared to the rest o f Peru, there was no mechanism or evaluation design for assessing the marginal effect o f the specific interventions supported by the projects on the outcomes o f the poor. During the implementation o f PARSALUD, the SIS component included specific intermediate outcomes for the first two quintiles o f the population. However, there i s still scope for better specified outcome goals for specific groups that are living in poverty. HEALTH REFORM 4.6 Health system reforms that proceed in a iecemealway can nevertheless result in improvementsin access and efficiency! Although not comprehensive, incremental reforms in Peru have resulted in\. (a) creation o f a targeted insurance scheme that has improved access and improved efficiency in the allocation o f resources; (b) introduction o f some market competition for ESSALUD in the provision o f services; (c) development o f community-managed services such as CLAS,with greater local accountability; (d) the beginning o f a decentralization process; (e) the introduction o f Ewig (2004) individual targeting mechanisms; and ( f ) reorganization o f the M O H . These piecemeal reforms have been supported by small groups within the M O H , supported by the Bank, and by economic officials interested in rationalizing public expenditure and in a broader effort to support modernization efforts. However these teams have been dismantled several times and there has not been continuous support from high-level health officials or other sectors o f society to broaden the reform.67 Thus, elements included in the vision for health reform for 20 10 have been implemented only partially; the establishment o f universal health insurance funded with subsidies for the poor and contributions from the non-poor and enlistment o f private and public institutions both as insurers and in service provision remain part o f the unfinished agenda. 4.7 Creating new institutions can be less difficult than reforming existing ones. The transformation o f ESSALUD and the health care units o f the Armed Forces and the National Police have proved to be more difficult than the creation o f new organizations such as SIS. Resistance to change within ESSALUD and the health sector bureaucracy and the complexity o f comprehensive health reforms have been significant obstacles for the reform. 4.8 The Bank can contribute to sustaining health reform efforts through the use of multiple instruments and analytic work. The strategy o f using multiple lending instruments and analytic work to maintaining a focus on the poor was equally important in Peru in maintaining a focus on health reform. The PSRLs, which disbursed US$450 million, were effective means to maintain the reform agenda despite the political cycle. The conditions included in each PRSL were to be met prior to loan approval and involved no borrower counterpart funds. They provided incentives for both the M O H and the MEF to work toward the same goals. The most recent policy note on Peru (World Bank, 2006b) keeps the reform on the agenda. It proposes the creation o f a means-tested universal health insurance expansion o f SIS; to subcontract all public health clinics to CLAS , and to force all publicly founded health systems to coordinate. Decentralization and accountability are also part o f the Agenda. The Bank has the flexibility needed during those transitions and it's able to adapt the projects while retaining the objectives. 4.9 Health reform projects need a realistic ex ante assessment of political and institutional risks including analysis of the interests of specific key stakeholders in the health system and mitigation strategies. Decisive support from the government and political support from stakeholders are key to the potential success o f innovations. While the SIS model (with political dividends for the government) i s now a part o f the health system in Peru, the CLAS model, which has support at the local level and from Peruvian health analysts, it i s s t i l l at risk o f being undermined. Opposition from the ESSALUD bureaucracy has stalled progress on reform o f health insurance for the formal sector. Although the A P L instrument was adopted for PARSALUD and provided flexibility for the long-term support o f reforms, the implementation o f i t s first phase was difficult and the health reform initiative was refocused on health service delivery. In the 67 Respondents for this evaluation characterized this progress as transformation o f the health sector Peruvian style. One respondent said, it's the only way to make change in Peru\. incremental and slow. It helps to sustain changes. However, other respondents argued that this slow change i s inefficient and has a high cost for the country. recently approved PARSALUD I1 project, political issues with labor contracts in the C L A S and the reforms o f ESSALUD have led again to a project primarily concerned with health service delivery and incremental reforms. 4.10 Confrontinghuman resource issues i s fundamental to sustain progress in the health sector and the focus on the poor. After the economic collapse o f the eighties, Peru was forced to reduce real wages for all civil servants. Health workers developed coping strategies based o n second jobs, parallel businesses, misappropriation and corruption. The situation resulted in l o w productivity, l o w quality and a bias against the poor. The CLAS model made an effort to avoid these conflicts, by providing different kinds o f contracts to i t s health workers. However, this innovation was effectively reversed in the case o f the physicians. DONOR COORDINATION 4.1 1 Donor coordination and elimination o f parallel structures can be enhanced by joint management units. At the time o f the BHNP, there was little coordination by the government or between the donors o f large projects funded by USAID and the IDB. This resulted in the projects creating, and the M o H supporting, parallel structures for project implementation. Following a government request, PARSALUD combined financing from the World Bank and IDB and worked through a joint PCU, helping to eliminate parallel project structures and improve inter-agency coordination in support o f the government's agenda. VALUE ADDED OF THE WORLD BANK 4.12 The World Bank's evolving value added and contributions to Peru's health sector between 1994 and 2006 can be divided into three phases. In the early nineties, the Bank supported the GOP to alleviate the impact o f a severe macroeconomic stabilization package with emergency programs to protect the poor. In the health sector, Bank efforts were concentrated on reconstruction o f services and infrastructure, mainly through the BHNP, and focused on maternal and child health among the poor. This was also the focus o f the government Programa de Salud Basicapara Todos, and other international donors and development agencies working on health issues at the time such as USAID and IDB. By the mid-nineties, indicators were improving and the country's economic situation stabilized. There was a shift towards supporting the GOP in defining a medium-term strategy to develop social sector policy and institutions, including support for health sector reform, primarily in the way the sector was funded. The main instrument was the insurance program, intended to reduce economic barriers to access. More recently, the Bank renewed i t s emphasis on support for health service delivery focused primarily on maternal and child health and mortality, especially among the poor. The multilateral donors have become more o f a complementary source to government financing, as exemplified by PARSALUD where the government funded almost three times what was estimated at appraisal and the contributions o f the Bank and IDB were scaled back by two-thirds. Nevertheless, the Bank's HNP investment loans have served as instruments to maintain policy dialogue on health reform and health services, which has positively impacted health outputs and outcomes in Peru. In recent years, the Bank's knowledge, technical assistance, ability to convene various development actors, and ability to foster innovative interventions have gained relevance over lending interventions. 4.13 The two main areas o f substantive impact of the Bank in terms of improving access to health services for the poor have been its support for the design and better targeting o f the SIS and for improved quality and coverage o f maternal health care in Peru. Although SIS has been an important innovation, further efforts are needed to reduce direct and opportunity costs for health care for the poor. SIS could also reduce resource allocation to tertiary care and focus on the primary and secondary levels where the poor make higher use o f services. 4.14 Government officials consider the Bank's ability to mobilize financial and human resources and to connect technical assistance with financial services to be an added value that few other donors can match. In addition, the Bank i s valued for its wide experience and ability to share lessons from similar programs in other countries;68 i t s poverty focus, underscored by highly effective analytic work providing an outsider's perspective; i t s long-term relationship that has helped to maintain a medium-term agenda and dialogue on health in the face o f high turnover in the sector;69 and its institutional culture that has emphasized outcome-oriented projects, efficiency, and transparency in the allocation o f resources. The Bank i s seen by both the Government and other members o f the assistance community as an intellectual leader and a major source o f advice on development policies and structural change in the health sector. The Policy Notes, in particular, are valued by policymakers as a considerable intellectual effort to understand local conditions and address a wide range o f health topics in Peru.70 The active role o f the Resident Mission on health issues in Peru i s seen as positive. Respondents also perceived a greater willingness o f the Bank to take into account country p r i o r i t i e ~However, .~~ development partners and members o f civil society interviewed by the IEG mission also offered a critique (Box 4-1). Respondents particularly valued the transfer o f knowledge through the Bank, regarding health reform experiences o f Argentina, Bolivia, and Colombia. Respondents indicated that the dialogue has been pursued mainly with government and to a lesser extent with other development and assistance agencies, research centers, universities and NGOs. 70 One o f the most valued i s World Bank (1999b), Improving Health Care for the Poor, which i s widely used and cited both by academics and health officials. This piece was used as one o f the main sources to design the PARSALUD project and the PSRL series. However, respondents suggested that dissemination o f the Policy Notes i s too restricted to small circles and that technical analysis can rely more on local knowledge. '' Two examples cited by respondents were the inclusion o f hospitals as part o f PARSALUD interventions (taking into account the role o f regional hospitals as part o f a referral system for reducing maternal mortality), and the focus o f PARSALUD interventions on the time o f delivery and post-partum period instead o f the prenatal period. In both cases, the initially proposed design by the Bank was adapted to local suggestions. 4.15 The World Bank support should reinforce country priorities; however it also needs act to ensure that key HNP priorities remain on the national agenda. Although nutrition interventions were introduced late in the project cycle o f BHNP, PARSALUD did little to address nutrition and nutrition indicators stagnated (Annex D, Table D-2).72 Additionally, the World Bank has been absent on population issues in Peru; the use o f modern contraceptives has actually declined since 2000, overall and in both urban and rural areas (Annex D, Table D-2). Box 4-1\. Partner, civil society and NGO views of the World Bank's role in HNP There seems to be a general agreement on the main issues. However, some o f the main points where the opinions vary are the following\. Some former government staff, academics and NGO staff, think the Bank could have been more decisive on maintaining a comprehensive health reform agenda. The Bank's analytic products seem to be more valued by government officials, who find them u s e h l to support technical dialogue and policy initiatives, than by university professors and researchers. Some respondents were critical o f what they see as a predominantly economic focus of the Bank on health issues. The reforms promoted by the Bank are seen as efficiency-oriented, while some respondents would like to see a more comprehensive reform to improve health as a basic human right. Staff from NGOs and civil society organizations critiqued the Bank for declining to get involved in difficult political issues, particularly family planning. NGO staff think the Bank could play a stronger role in terms of strengthening civil society, improving accountability and helping to promote anti-corruption efforts Some staff from donor agencies and international organizations expressed concern about a lack o f coordination with other actors who have technical know-how and experience that could benefit project design. As with civil society, they view the Bank's dialogue as mainly with the government. l2 The neglect of nutrition has been acknowledged and new economic and sector work has been launched.
P062936 | ENT EXP FACIL (BEEF) | Europe and Central Asia | Bosnia and Herzegovina | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/381041474420199871/text/000020051-20140613055056.txt | http://documents.worldbank.org/curated/en/381041474420199871/pdf/000020051-20140613055056.pdf | Commitment to macroeconomic stability and structural reform can help reduce economic risks and improve the performance of the financial sector. As a result, the economic rationale for setting up specialized organizations to grant export credit or ensure risks should be thought out carefully and framed in a broader economic picture than that done in these line-of-credit type operations.
P062991 | AR SPECIAL SAL (SSAL) | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2003 | 2003 | ICRR | >=100 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/459961475084271307/text/000020051-20140607165017.txt | http://documents.worldbank.org/curated/en/459961475084271307/pdf/000020051-20140607165017.pdf | (A) Detailed ESW done during years of little lending allowed the Bank to lend quickly to support structural reforms that were identified earlier.(B) It is appropriate for crisis loans to support those structural reforms that directly and immediately help in dealing with the crisis (e.g. improving tax collections or inter-governmental fiscal transfers) or social programs protecting the economically vulnerable. It is less clear whether other needed structural reforms (e.g. improving the insurance industry) should be included (see section 8 below). The SSAL supported reforms of both types and the ICR mentions the conflicts between disbursing for liquidity support and the time-consuming process of getting the reforms underway.(B) A short term crisis calls for a short term loan, and the SSAL is more appropriate than conventional Bank instruments. It is less clear, however, if the Bank should be a "residual lender" in Fund supported financial rescue packages. The loan amounts are unrelated to the benefits of structural reforms, and these benefits do not follow if stabilization fails.
P062992 | AR SPEC REPURCHASE | Latin America and Caribbean | Argentina | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 1999 | 2004 | 2004 | ICRR | >=100 million | Highly Unsatisfactory | Satisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/280991474896038102/text/000020051-20140612064039.txt | http://documents.worldbank.org/curated/en/280991474896038102/pdf/000020051-20140612064039.pdf | If the government does not maintain a macroeconomic framework conducive to the achievement of project objectives, the Bank should consider taking prompt remedial action, including project termination and cancellation of undisbursed balancesWhen macroeconomic policies create large economic imbalances, a repo facility has little chance of calming the fears of depositors and investors because by itself it cannot restore economic stability
P063081 | Public Sector Financial Management Reform Support | Europe and Central Asia | Georgia | IBRD | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/721951475085622686/text/000020051-20140625233048.txt | http://documents.worldbank.org/curated/en/721951475085622686/pdf/000020051-20140625233048.pdf | Key lessons in the ICR are supported, inter alia as follows:1. Complex reforms should be approached by creating a decision-making environment that encourages experimentation and feedback loops in learning, where there is continual results monitoring and redesign based on experience. Such redesign may be needed due to changes in Government priorities, as well as actual results which may be unexpected. Project designs should be adaptable enough to allow for such changes, while ensuring that the revised targets are as significant and meaningful as the original ones.2. Design complexity should be managed to be within the capacity of implementing organizations. When many reforms are needed, it is worth considering to carry them out sequentially to avoid overly complex arrangements. 3. Major interventions should be preceded by consultations where key stakeholders come up with a prioritized set of locally defined problems, and recommended solutions. Politically acceptable solutions come from a gradual process of step-by-step experimentation, and engagement with many stakeholders playing many different roles. This engagement comes from long conversations with people, both individually and in workshops. PFMIS development and other key initiatives should move ahead as part of such processes, so that key stakeholders holding different roles agree that the initiatives are the proper response to identified problems. While Georgia was not categorized as a fragile and conflict affected state (FCS), the period after the Rose Revolution was characterized by the same diversity of views, capacity gaps, and uncertainty often found in FCS contexts. The deep, consultative approach used in Georgia may be particularly relevant in such situations.One other, crucial lesson is important. To ensure effective coordination of support to complex, institutional reforms, it is very useful to have a TTL trusted by senior government and political leaders, leading the consultative process from the Bank side. There are also important benefits if such a TTL stays with the project from design to completion.
P063081 | Public Sector Financial Management Reform Support | Europe and Central Asia | Georgia | IBRD | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2012 | 2018 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/768271532459328570/text/126842-PPAR-P063081-P165243-PUBLIC.txt | http://documents.worldbank.org/curated/en/768271532459328570/pdf/126842-PPAR-P063081-P165243-PUBLIC.pdf | 7. Lessons 7.1 Creating a decision-making environment with continuous results monitoring and course correction based on experience would be a more promising approach to complex reforms. Such course correction may be needed due to changes in government priorities, as well as actual results that may be unexpected. This was demonstrated by the project's failure to assess the government's capacity for in-house PFMIS development and the possibility to change course to achieve this subobjective. Institutional development project designs should be adaptable enough to allow for constructive changes while ensuring that the revised targets are as significant and meaningful as the original ones. 7.2 The costs of building and upgrading a PFMIS when a country's needs are evolving should be carefully assessed. When a PFMIS has to be built from a very low level of institutional capacity and the country's future needs are difficult to project, the cost of upgrading and customizing an off-the-shelf PFMIS may grow, possibly placing an excessive burden on the budget. If the local capabilities are adequate, as in the case of Georgia, an alternative would be in-house development of the PFMIS, which may allow for more flexibility in future upgrades and tailoring of the system to the government's evolving needs. Assessing local IT capabilities and, if needed, providing training, are prerequisites for choosing the right option. 7.3 An alternative design option for technical assistance projects related to PFM modernization would be a two-stage approach. The first stage could consist of a much smaller effort, focusing on the strategically most important areas of PFM reform, with substantial technical assistance for assessing in-house capacity for integrated PFMIS development. In the case of the PSFMR project, such a two-stage design might have prevented the unsuccessful international competitive bidding for the PFMIS, strengthening instead the in-house capacity for system development through targeted training. Depending on the outcomes of the first stage, the second stage of the project could involve either the purchase and implementation of an off-the-shelf PFMIS or the provision of training and further capacity building for in-house PFMIS development. 7.4 Project implementation may be hindered by uneven institutional capacity across government agencies. When such is case, the involvement of multiple implementing agencies may cause lines of accountability to become unclear, and uncoordinated initiatives at individual agency level may become counterproductive and impede reforms. That was the implementation experience with this project. Simplicity in project design and activity coordination is in these cases an important requirement for project success.
P063089 | Emergency Flood Recovery Project | South Asia | Bangladesh | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 1999 | 2000 | 2001 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/734931475075197595/text/000020051-20140529164105.txt | http://documents.worldbank.org/curated/en/734931475075197595/pdf/000020051-20140529164105.pdf | Establishing clear emergency recovery objectives, unencumbered by conditionality related to longer-term institutional and macroeconomic reform, enables rapid implementation that, inter alia, benefits the poorest.With proper and transparent fiduciary and procurement controls, the Bank's procurement and disbursement procedures can be successfully streamlined and simplified giving greater ownership to the borrower thus enhancing the Bank's country partnership. This, in turn, provides a platform to discuss and resolve systemic differences on development issues. In countries prone to natural disasters, appraisal of emergency credits should seek to mainstream disaster mitigation and recovery into longer-term country institutional development activities.
P063095 | Privatization and Utility Reform Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/141131474664960363/text/000020051-20140619080920.txt | http://documents.worldbank.org/curated/en/141131474664960363/pdf/000020051-20140619080920.pdf | The ICR has several good lessons, but two stand out. First, there is a need for consensus on privatization issues especially at the policy makers level. Without this consensus, there are always delays in program implementation. Second, a robust and well targeted public awareness program is critical to sustain public support, especially for the larger, and politically difficult transactions. After the restructuring, these lessons were absorbed leading to speedier implementation.
P063096 | Land Reform Support Project | Eastern and Southern Africa | Zimbabwe | Blend |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2002 | 2005 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/801481474481705090/text/000020051-20140612150617.txt | http://documents.worldbank.org/curated/en/801481474481705090/pdf/000020051-20140612150617.pdf | Attempts to pilot market-assisted approaches to land reform are unlikely to work when the government is unable or unwilling to protect property rights, and there is escalating rural violence. The feasibility of supporting land reform will be much greater when donors are able to finance the total investment package--land plus infrastructure and technical assistance; until recently the Bank was proscribed from lending for land purchase, seriously reducing its ability to support land reform.
P063123 | YANGTZE FLOOD EMERGENCY REHABILITATION | East Asia and Pacific | China | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/687411474555656527/text/000020051-20140607165515.txt | http://documents.worldbank.org/curated/en/687411474555656527/pdf/000020051-20140607165515.pdf | The project confirmed lessons learned from Bank emergency earthquake relief interventions in China: (a) sub-projects should be simple and suitable for rapid implementation; (b) local government must support and participate in project implementation; and (c) there are substantial benefits to the use of Bank "fast track" processing.Under its highly decentralized and efficient system of administration, China has been able to rapidly disseminate to county-level, the skills and capacities acquired by provincial PMOs on other Bank-supported projects, Retroactive financing to a trusted client, streamlined procedures and negotiation of the loan in Beijing, all helped ensure quick appraisal and implementation. Management by the World Bank Office in Beijing also had a positive impact by quickly solving implementation problems. Within the constraints of the Bank and China's policies, equity and repayment performance would be best served by targeting limited concessionary IDA funds (50% of the Bank loan in this case) and any grants, to non-revenue-generating sub-projects, and/or poorer counties.
P063201 | DO Hurricane Georges Emergency Recovery | Latin America and Caribbean | Dominican Republic | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2003 | 2004 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/178731475080410828/text/000020051-20140612095754.txt | http://documents.worldbank.org/curated/en/178731475080410828/pdf/000020051-20140612095754.pdf | 1. More time than the OP 8.50-stipulated 3 years is needed to successfully implement an emergency project. This is especially true for institutional capacity building in disaster mitigation and preparedness.2. Reducing disaster vulnerability should not be confined to reconstruction projects. Building to hazard-resistant standards should be integral to operations in all relevant sectors. Similarly, opportunities to raise consciousness levels regarding the relationship between disaster and development need to be identified in all ongoing Bank-financed operations in disaster-prone countries.3. After every emergency, the appraisal team should first assess possibility of implementing the ERL by relying on existing government staff and agencies. If government institutions are unable to implement a project, however, experienced staff need to be identified, and placed in project implementation units (PIUs) that have real decision-making power so that they can respond effectively to the rapidly changing post-disaster context.4. Excessive conditionality in the post-disaster context may delay project start-up and strain institutional capacities when efforts are made to meet deadlines that have become unrealistic.5. Extending a project for insufficiently long periods demoralizes conscientious implementers (when they are required to deliver what is beyond their capacity).6. Provision for adequate O&M should be a major concern from the beginning of project implementation.
P063317 | Conservation & Sustainable Use of Biodiversity in High Andes Region (GEF) | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/115211474628567295/text/000020051-20140619075914.txt | http://documents.worldbank.org/curated/en/115211474628567295/pdf/000020051-20140619075914.pdf | In addition to displaying technical competency, implementing agencies need to have influence with government. In this case, the IAvH had credibility as a scientific institution and had strong financial management skills but it showed limited capacity to engage with the various levels of government, so that at project closing it was unclear if the project's achievements would be scaled up.The outcomes expected from a project need to be clearly defined at the outset and reflected in the M&E system. This project never developed a compelling results chain showing how the diverse outputs would build up to a set of sustainable outcomes. Projects that seek to strengthen national protected area systems need to pay close attention to arrangements for recovering recurrent costs. With respect to this project, government's budgetary commitment is uncertain (partly because responsibility is divided between central and regional environment agencies) and IAvH had little capacity or incentive to compensate for this uncertainty. Some attempt was made to mobilize funds from users of environmental services (e.g. downstream farmers) but, unlike in other GEF-supported Andean projects, no attention was given to building a capital fund, interest on which could be used to cover recurrent costs.
P063340 | BR SOC SECURITY REF I | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=100 million | Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/113991474396543676/text/000020051-20140526231226.txt | http://documents.worldbank.org/curated/en/113991474396543676/pdf/000020051-20140526231226.pdf | Effective political communication is necessary to catalyze support for difficult reforms. The ICR notes (as opposed to the SAR) that ineffective use of information and poor political communication turned out to be the main weaknesses of the Administrationâ€™s reform strategy. Applying analytical tools can help de-politicize reforms and promote change. State Civil servants at the state level have used simulation models to explore reform options, and trade information among Governors, whose support for future amendments of the constitution is essential.Sensitivity to the politics of reform. The Bankâ€™s willingness to support a less ambitious program of improvements to the reformed pension system has allowed it to have greater influence on the formulation of future reforms of the system.
P063341 | BR ADMIN & FISC REF | Latin America and Caribbean | Brazil | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2000 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/373221475072199044/text/000020051-20140607140718.txt | http://documents.worldbank.org/curated/en/373221475072199044/pdf/000020051-20140607140718.pdf | The operation shows the complexity in implementing/enforcing fiscal reforms that need to involve Sub-National Governments in a substantive way. It has applications for other medium and large countries experiencing similar problems.
P063351 | BR SOCIAL PROTECTION | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1999 | 1999 | 2000 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/355991474650863086/text/000020051-20140526231140.txt | http://documents.worldbank.org/curated/en/355991474650863086/pdf/000020051-20140526231140.pdf | Financial crises provide an opportunity to leverage difficult reforms, but ownership by the Borrower is still critical to implement them and disburse funds rapidly. The objectives and conditions of the loan were largely designed as an extension of efforts already underway to consolidate social safety net programs.Governments that reform social sector policies, and their partners, must develop a comprehensive and accessible public information campaign that explains the rationale of the reforms in order to help consolidate a clear social agenda.Brazil and other countries in Latin America have a wide variety of social protection spending programs scattered across ministries, often with high expenditures and poor targeting. Although the programs are politically sensitive, the Bank should insist that the whole range of programs be evaluated. Without such evaluation it is difficult to use the opportunities that financial crises provide for leveraging reforms in a direction that could make social protection programs more effective for the poor.
P063383 | OSE Modernization and Systems Rehabilitation | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2000 | 2007 | 2008 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/369171474560273578/text/000020051-20140618080942.txt | http://documents.worldbank.org/curated/en/369171474560273578/pdf/000020051-20140618080942.pdf | PSP is not the only solution: Various incentives can promote efficiency gains and enhance competition. By unbundling the sector, the project created an opportunity for other agencies to hold OSE to account. By progressively decentralizing regional departments, OSE stimulated internal competition between regional units. By putting in place a system of internal benchmarking, 21 cities across the country started to produce some significant changes. In addition, properly disseminated internal and external benchmarking results are critical in raising consumersâ€™ awareness of the levels of service they are entitled to, and helping consumers, with the support of the media and civil society, hold OSE to account. UFW cannot simply be addressed by focusing only on operational solutions, and efforts to support the operational and commercial cross-over are critical. Addressing unaccounted for water requires a deepening institutional integration between commercial and engineering silos, and rolling-out innovative approaches. Since UFW is intimately linked to the overall efficiency and effectiveness of a water utility, institutional reforms to improve the performance of a utility need to be designed with reducing UFW in mind â€“ from the integration of commercial and operational systems, to the creation of a social unit focusing on instilling a paying culture amongst different clients (informal settlements, large consumers, etc.).Provide a space for learning by doing and innovation. This tactic not only strengthened the overall M&E framework of this project, but also increased OSEâ€™s commitment to, and ownership of, the process. Benchmarking turned into something not just about the project, but of real use and benefit to the utility as a whole, its external stakeholders and consumers.
P063386 | CL-MILLENNIUM SCIENCE INITIATIVE (LIL) | Latin America and Caribbean | Chile | IBRD |  | Human Development | Education | IBRD | IPF | 1999 | 2003 | 2003 | ICRR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/187371474636135095/text/000020051-20140607171016.txt | http://documents.worldbank.org/curated/en/187371474636135095/pdf/000020051-20140607171016.pdf | 1. The model of (i) transparent, merit-based allocation of research funds, (ii) investigator autonomy, and (iii) specific focus on training opportunities and on collaborations and networking has quickly increased the efficiency of R & D, the quantity and quality of advanced training, and the volume of collaborations and networking. When more time has elapsed, it seems likely that it will also have increased the quantity and quality of R & D.2. Nevertheless, capitalizing on the LIL -- by scaling up the successful pilot reforms to change whole sectors/systems -- will require considerable further thought and effort and remains challenging. In particular, decisions are needed on whether to continue or change the special institutional arrangements at MinPlan used for the pilot, and on incentives to get other public S & T agencies to change to the new approach.
P063388 | AR-Health Insurance for the Uninsured | Latin America and Caribbean | Argentina | IBRD |  | Human Development | Health, Nutrition & Population | IBRD | IPF | 2000 | 2002 | 2004 | ICRR | Less than 10 million |  | Satisfactory |  |  |  | http://documents.worldbank.org/curated/en/228731474566915988/text/000020051-20140612062632.txt | http://documents.worldbank.org/curated/en/228731474566915988/pdf/000020051-20140612062632.pdf | The PCN offers no lessons of broader applicability to other countries or to Argentina. It is silent on the issue of whether the change in government might have been anticipated, and negotiations delayed to obtain support from the new government.
P063390 | FIN SCTR REFORM | Latin America and Caribbean | Uruguay | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2000 | 2000 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory |  | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/524041474573993105/text/000020051-20140529161922.txt | http://documents.worldbank.org/curated/en/524041474573993105/pdf/000020051-20140529161922.pdf | In slow reforming countries, the Bank can be more effective by adopting modest goals for reform in the short-term while keeping them within a medium-term reform frameworkIn slow reforming countries, the Bank should use several single-tranche adjustment operations to support a medium term reform program
P063398 | Municipal Water and Wastewater Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2004 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/843671475096883518/text/000020051-20140625223829.txt | http://documents.worldbank.org/curated/en/843671475096883518/pdf/000020051-20140625223829.pdf | Lesson from the ICRSound baseline information is needed for project evaluation, including its economic justification. Time savings (time spent fetching water), reduction of coping costs (related to booster pumps, individual storage tanks, household disinfection equipment, water boiling or purchase of bottled water), health improvements, and environmental improvements were difficult to measure in this case, due to uncertainty about baselines. Lesson from IEG In order to evaluate results more fully, a water supply and wastewater sector project needs data on total water production and consumption as well as total wastewater collection, treatment and disposal. It should also include data on unaccounted for water.
P063463 | Methane Gas Capture and Use at a Landfill - Demonstration Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2001 | 2006 | 2007 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/426001474627865844/text/000020051-20140617132722.txt | http://documents.worldbank.org/curated/en/426001474627865844/pdf/000020051-20140617132722.pdf | (1). Foreign technology and simulation models need to be adapted to local conditions, particularly in the ex-ante evaluation of a project. In the case of the LFG Victoria Salinas plant, the high ambient temperature and rainfall in the Monterey area and the composition of the solid waste were parameters having significant impact on the mathematical model used to estimate the volume of methane available in the landfill and the performance of the plant. As a result, the application of a non-adapted model in the ex-ante evaluation gave an optimistic estimate of methane, and lower than actual operation and maintenance costs of the plant. (2). Lack of appropriate legislation applicable to the capture and use of LFG causes significant delays in the processing of permits and contracts needed to implement a LFG plant. Since the UMS Law does not yet recognize LFG as a form of renewable energy, the implementation process of the Victoria Salinas plant was cumbersome and, moreover, it did not allow negotiation of better prices for the sale of the energy generated. This may discourage private sector participation in future LFG projects.(3). Capacity building and dissemination of LFG capture and use must be standing programs of the State Government particularly when the administration periods of municipal authorities are relatively short. In the UMS the municipal authorities have a turnover of 3 years. This makes the learning process of LFG management difficult at times. However, incentives such as participation as shareholders in a LFG co-generation plant, discounts on electricity prices and potential improvement of the local environmental and social conditions have proven to be helpful in keeping alive the interest of municipalities in LFG projects.
P063472 | YEAR 2000 EMERGENCY ASSISTANCE PROJECT | South Asia | Sri Lanka | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2001 | 2002 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/197051474489137530/text/000020051-20140604055719.txt | http://documents.worldbank.org/curated/en/197051474489137530/pdf/000020051-20140604055719.pdf | Among the reasons critical for this project's success were its well-defined and focused objectives, strong client demand and commitment, flexible design, and a good and effective Apex system that leaves the main implementation responsibilities to the beneficiary organizations. Another lesson is that the Bank should seize the opportunity to accomplish quickly during periods of crisis or perceived crisis what would be difficult and slow under normal circumstances. Cumbersome procurement procedures in the public sector (including tender committees that meet infrequently) need to be addressed frontally, either with general institutional reforms or with ad-hoc solutions, such as by requiring that the government set up a specialized tender committee for the project that can attend timely to procurement matters as they arise.
P063472 | YEAR 2000 EMERGENCY ASSISTANCE PROJECT | South Asia | Sri Lanka | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2001 | 2003 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/572281468763781674/text/261380LK0PPAR.txt | http://documents.worldbank.org/curated/en/572281468763781674/pdf/261380LK0PPAR.pdf | LESSONS 0 The performance o f a wide range o f projects-not only those inconflict zones-is vulnerable to the impact o f war, especially through unexpected conflict events duringproject implementation. Projects will not do so well duringconflict as inapeaceful situation. Spatial separation o fa project from active conflict zones does not guarantee that an operation will be free o f conflict constraints. 0 Project design should not be blindto conflict, and must cautiously but explicitly address the constraints imposed. War-weary governments are unlikely to have strong ownership o f reform unrelatedto the causes o fthe conflict. Decentralization may go against centralized conduct o f war. Conflict generates a poor business climate that private firms themselves are unwilling to invest in. 0 Itis importantto focus upona clear vision o fthe intendeddevelopment results of a project, and to remain focused on them through systematic monitoring and evaluation. Inother words, the baseline shouldbe measured, the counterfactual clearly understood, and M&E supported and implemented.
P063501 | Y2K READINESS PROJ. | East Asia and Pacific | Malaysia | IBRD |  | Infrastructure | Transport | IBRD | IPF | 1999 | 2002 | 2003 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/171001475087906084/text/000020051-20140607162936.txt | http://documents.worldbank.org/curated/en/171001475087906084/pdf/000020051-20140607162936.pdf | Project appraisal should verify that there is a real demand by the borrower for the assistance proferred by a project. The experience shows the difficulty of launching time-sensitive Technical Assistance operations. The main lesson is that the Bank should understand at the project preparation stage the special case of projects that require precise timing for implementation and deal with it in a manner that would address its urgency.
P063546 | Pension System Investment Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2003 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/429971474501544120/text/000146597-20140619165800.txt | http://documents.worldbank.org/curated/en/429971474501544120/pdf/000146597-20140619165800.pdf | Ensure full commitment and buy-in from key institutions involved in and affected by project implementation. The resistance from powerful institutions (i.e. Tax Department) may prevent the achievement of important project objectives (unified reporting and registry system). Realistically assess the capacity of participating institutions (PI) to design and implement reforms identified in the project.Agree on a well defined and measurable set of outcome and intermediate outcome indicators and dedicate enough resources for M&E through the entire project implementation period.
P063577 | Community Development & Culture Project (LIL) | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2006 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/454551474506718151/text/000020051-20140618060018.txt | http://documents.worldbank.org/curated/en/454551474506718151/pdf/000020051-20140618060018.pdf | Consistent with the intent of a LIL, this project generated a large number of broadly applicable lessons: Cultural assets can mobilize the communities that surround them. The CDCP has shown local history and heritage can be catalysts that promote employment and income generation as well as improved asset management. The Bank is in a unique position to assist developing countries to effectively manage their heritage. UNESCO is a non-lending institution, and the private sector in developing countries is often not yet ready for private-public partnerships. Conservation and restoration of built heritage is complex, costly and requires very specific expertise that the Bank should mobilize, even in operations where conservation is peripheral. All proposed conservation/restoration works should be assessed by a peer review panel, preferably international in the case of significant works, lest a reputational risk be incurred. Clarification of title prior to interventions on historic structures diminishes risks of contention and ensures effectiveness of investments. Project experience indicates that the use and/or management of public assets by private entities and the provision of subsidies/grants to public assets linked to private utilization should be carefully monitored. Even more importantly, subsidies for improving privately owned property without a clearly defined rationale can undermine a projectâ€™s success. Comprehensive approaches to heritage assets management should include long-term financial planning lest sustainability be put at risk. Signage components are more complex than they appear and are more likely to be well implemented by roads and transportation agencies. The benefits of having additional funding should be carefully weighed against the opportunity cost and the time and efforts to obtain such funding. While seeking additional funds and obtaining them often enlarges the scope of a project and legitimizes it in the eyes of institutional stakeholders, the use of trust funds can sometimes be distracting as they often take human resources away from main objectives without necessarily adding value to the project. Disbursement schedules should correspond closely to the nature of the investments concerned. Task Teams often come under pressure to prepare unrealistic disbursement schedules that correspond to Country Unitsâ€™ priorities, leading to acceptable implementation results reflecting negatively on both lenders and borrowers. Task Teams should spend more time on preparing credible disbursement projections, which should better reflect the nature of the proposed activities and country experience. Computerized Project Management scheduling can help. Changing standards â€œmid-streamâ€ can have detrimental results, especially when they result in downgrading the project when performance was actually improving. Even when new standards are more realistic, the detrimental impact on counterpart morale impacts the progress of work on the ground.
P063584 | Social Investment Fund (ZAMSIF) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2006 | 2009 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/534721475111312314/text/000020051-20140619072940.txt | http://documents.worldbank.org/curated/en/534721475111312314/pdf/000020051-20140619072940.pdf | Drawing on the lessons in the ICR, the project shows that:In social fund projects where a decentralized structure is necessary to achieve project objectives, and where decentralization reforms are outside the scope of the project, the Bank needs to take into account the risk that decentralization may not occur. This risk need to be carefully assessed during project preparation, and mitigating measures proposed. When they happen, governance problems need to be flagged early so that project implementation arrangements can be adapted.Implementation of the M&E system needs to start early in the project with the collection of baseline data. If outside agencies (such as the Central Statistical Office) are responsible for data collection, the project's implementing agency needs to take an active role to ensure that the necessary information is collected.Methods for allocating project resources to the poor and other vulnerable groups need to be monitored to ensure that resources flow to intended target groups.
P063622 | Second National Fadama Development Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2004 | 2010 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/237401475076408318/text/000020051-20140624165531.txt | http://documents.worldbank.org/curated/en/237401475076408318/pdf/000020051-20140624165531.pdf | The project experience yielded the following lessons that are adapted from the ICR:The LDP concept was successful because it was owned by the communities, was socially inclusive and participatory.CDD projects can have a greater impact, synergy and complementary when tools and approaches are harmonized.Standardization of subproject documents, technical designs, and unit costs simplifies the preparation and evaluation of subprojects, improves quality at entry, facilitates the procurement of goods and works, prevents over-design, and enables participation by community groups.A socially-inclusive approach to local development planning can be an effective tool for avoiding and managing conflicts arising from competition to access scarce land and water resources for local enterprise.
P063622 | Second National Fadama Development Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2004 | 2010 | 2014 | PPAR | >=50 million & <100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/199951468292896593/text/889580PPAR0P060IC0disclosed07070140.txt | http://documents.worldbank.org/curated/en/199951468292896593/pdf/889580PPAR0P060IC0disclosed07070140.pdf | 7. Lessons Ã˜ Technical interventions that transform land related assets require a socially and culturally sensitive project design that to the extent possible provides inclusive development opportunities to all affected parties. The Fadama program is illustrative of the risks that are attendant in neglecting social analysis in technical work streams. The project's first phase contributed to conflict between natural resource users groups by financing activities that expanded livelihood benefits to one user group at the expense of others. Ã˜ Community based approaches to local development require sustained and phased commitment. None of the Fadama villages visited by IEG demonstrated a present day capacity to participate in local development planning in a socially inclusive and accountable manner, in despite of the project's efforts to instill this. Fadama II villages were only supported by one project cycle. Villagers interviewed for this review expressed a significant level of disappointment about the lack of continued access to facilitated negotiation for the provisions of local goods and services. The conflict training and mediation module piloted by the project was appreciated by stakeholders but ultimately found to be unsustainable in the absence of the project architecture. Maintenance of public infrastructure has also expectedly emerged as a key challenge. Ã˜ The sustainability of community-based initiatives depends crucially on an enabling institutional environment, which requires government commitment, and on accountability of leaders to their community to avoid supply-driven demand-driven development (Mansuri and Rao, 2004). This overarching lesson on community driven development put forth by the World Bank's Development Economics Groups is very applicable to the Nigerian context. Ã˜ Programs designed to change behavior need to be grounded in a deep understanding of context; they need to be willing to engage in a study of what motivates people. Programs implemented at scale should include a sensitive design that takes into account the different cultural, linguistic and ethnic characteristics of the targeted population. Programs designed to change behavior also require observational and qualitative indicators, that in turn, require capacity building and implementation support to tweak project assumptions and project adjust design in real time.
P063643 | Financial Sector Adjustment Loan | Latin America and Caribbean | Colombia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2000 | 2002 | 2003 | ICRR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/847451474634332372/text/000020051-20140607172723.txt | http://documents.worldbank.org/curated/en/847451474634332372/pdf/000020051-20140607172723.pdf | 1. Macroeconomic stability (and hence sound fiscal policy) is necessary for a healthy financial system. Banking rescues add to the fiscal burden.2. International capital market inefficiencies can sometimes be exploited to a country's advantage (e.g., World Bank interest swaps) and Bank guarantees could allow this to happen, but the terms must be carefully scrutinized because, as in this case, the inefficiencies were not in Colombia's favor.
P063643 | Financial Sector Adjustment Loan | Latin America and Caribbean | Colombia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2000 | 2002 | 2008 | PPAR | >=100 million | Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/329281468262790327/text/Colombia-Financial-Markets-Development-Technical-Assistance-Project-Financial-Sector-Adjustment-Loan-and-First-and-Second-Programmatic-Financial-Sector-Adjustment-Loan-Projects.txt | http://documents.worldbank.org/curated/en/329281468262790327/pdf/Colombia-Financial-Markets-Development-Technical-Assistance-Project-Financial-Sector-Adjustment-Loan-and-First-and-Second-Programmatic-Financial-Sector-Adjustment-Loan-Projects.pdf | 6. Lessons 6.1 The experience with the four operations reviewed in this PPAR shows a remarkable turnaround in both the government's approach, policy response, and regulatory and institutional framework in the financial sector, and in the Bank's analytical knowledge of the sector. Mainly thanks to the early and effective government response, a systemic financial crisis was avoided and the financial sector today, although still smaller in number of institutions and total assets than before the crisis, is much stronger and well regulated. In addition, the Colombian economy has recovered and the economic policies of the government have managed to put an end to the persistent double-digit inflation that was a characteristic of the Colombian economy for three decades. The success in lowering inflation has eliminated an important vulnerability of the financial sector. Unfortunately, however, the other major macroeconomic source of vulnerability, i.e., the fiscal deficit, remains a problem that needs to be addressed. 6.2 On the Bank's side, the progress in its analytical understanding of the sector, and in its contribution to addressing its problems has also been substantial. Both analytical understanding and support to addressing the problems were low at the onset and during the first year of the crisis but improved considerably after mid-1999. In the most recent years, however, the narrow definition of the programmatic approach adopted in 2002 has reduced the opportunities for continuing support to the sector (as well as reducing the relevance of PFSAL 11). In addition to the many specific lessons derived from the operations, and from the analytical work during the period (including under the FSAP), five more general lessons emerge from this review\. Accurate, up-to-date sector information and analytical knowledge is critical for an adequate support to theJinancial sector\. an outdated assessment of the sector by 1997 made the FMDTA irrelevant and blindsided the Bank to the vulnerabilities of the financial sector. It also slowed down the Bank's response after the onset of the crisis. Agility and quick reaction to crises requires adequate technical resources and streamlined decision-making\. the Bank compounded its inadequate prior knowledge of the sector in 1998 by allocating insufficient technical/human resources until the joint FSAP was launched, and by slow and bureaucratic decision-making in the face of urgent client demands. Agility, flexibility, and openness to change are also crucial during implementation of a project orprogram\. during implementation of FMDTA, the inadequate starting point could have been partly remedied by earlier, and deeper restructuring to face the new conditions on the ground; during implementation of the FSALs, improved economic conditions and slow progress in some areas (housing finance, capital markets) could have been better addressed (even in the absence of a TA project) through a change in the second phase of the program (e.g. by splitting PFSAL I1 into two smaller, more spaced operations implemented over a longer period of time). Exploiting the synergies among different Bank instruments is crucial\. technical assistance operations and adjustment lending can reinforce each other when they are part of a coordinated sector intervention (and based on adequate analytical work). In Colombia, an outdated TA project was only belatedly and marginally linked to the FSAL; during the short period of the PFSALs (and after them) there was no TA vehicle on the ground to continue the support. A programmatic approach tojinancial sector reforms i s likely to require a time horizon of several years to allowfor policy and institutional reforms to be translated into outcomes and results\. the two-phase single year approach of the PFSALs was too short to address the complex secondand third-generation issues facing Colombia's financial sector.
P063644 | Power and Communications Sectors Modernization and Rural Services Project (PROMEC) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2002 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/508391474632433407/text/000020051-20140619110431.txt | http://documents.worldbank.org/curated/en/508391474632433407/pdf/000020051-20140619110431.pdf | 1. Contrary to what is suggested in the ICR, over-complex project design with a wide range of components and objectives, and several pilot sub-projects and implementing agencies, should be avoided. It may be true, as the ICR contends, that the involvement of so many agencies helped to ensure support for the project during a time of political turbulence. This would only apply, however, in the particular circumstances prevailing in Ecuador during the preparation and implementation of this project, and does not justify the making of a general rule.2. It is important to ensure that proper logistical and administrative arrangements for procurement, contracting etc. are in place before the project becomes effective. The fact that this was not done in this case increased delays and the risk of failure.3. Pilot projects are, almost by definition, likely to be difficult, even if small. This was certainly true for this project, where the problems of getting four of them off the ground were underestimated. The complete failure of one, and the late implementation of the other three, reduced their usefulness both as learning exercises and as promotion vehicles. 4. Where possible, it is preferable to use strong existing community organizations for operating sub-projects rather than attempting to establish new ones. Similarly, great caution should be exercised before setting up small, special purpose companies. Such companies are, by their nature, vulnerable to failure and can be expected to make losses for several years.
P063656 | Vilnius District Heating Project | Europe and Central Asia | Lithuania |  |  | Infrastructure | Energy & Extractives | IBRD | IPF | 2002 | 2003 | 2004 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/342751474659879830/text/000020051-20140612133118.txt | http://documents.worldbank.org/curated/en/342751474659879830/pdf/000020051-20140612133118.pdf | While a strong regulatory agency is usually needed for concession agreements to succeed, Lithuania's effective regulatory agency had little role to play in this project, which is based on "regulation by contract".
P063683 | Regional Trade Facilitation Project I | Other | Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2001 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/209341475113473762/text/000020051-20150312115736.txt | http://documents.worldbank.org/curated/en/209341475113473762/pdf/000020051-20150312115736.pdf | The ICR notes that one lesson concerns the importance of a correct diagnostic. Here, an innovative and well conceived project was marred by misperceptions about client needs and the nature of structural constraints in the financial sector. Furthermore, the ATI's design did not conform to international best practices in a well established global industry. There are indications that the Bank lacked adequate resources and the full range of expertise necessary for the preparation and supervision of such a specialized project.A second lesson concerns the uncomfortable balance between the project's commercial and development objectives, beginning with confusing (multiple) objectives and a lack of precision in the results framework. The inherent conflict between profitability and developmental outcomes such trade and regional integration which incur costs was reflected not only in the M&E framework, but in ATI Board governance. To some extent the problem may stem from different sets of stakeholders with different interests and may be especially acute regional operations. The regional setting also raised some issues of regulatory jurisdiction. The Bank may have slipped into the role of de facto regional financial regulator, for which it lacked both expertise and authority.
P063717 | Regional Project for the Implmentation of the Strategic Action Program for the Red Sea and Gulf of Aden | Middle East and North Africa | Red Sea and Gulf of Aden |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 1999 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/286271474570137735/text/000020051-20140614183331.txt | http://documents.worldbank.org/curated/en/286271474570137735/pdf/000020051-20140614183331.pdf | 1. Regional programs and projects are particularly challenging for the Bank, especially when the countries concerned are at widely differing economic and social levels and where commitment to the regional implementing organization is more rhetorical than real. Building the capacity of such organizations is a slow and painful process. Nevertheless, determined efforts from the Bank can make a difference both in strengthening cooperation and in showing results on the ground (in the sea, in this case). However, regional approaches are best reserved for those problems which are truly regional (such as navigation and oil spill contingency planning); other issues (like ICZM) might best be dealt with through a series of country projects.2. ICZM remains a nebulous concept for most planners in the region (and perhaps also in the donor community). This may change once one or two strong pilot projects have been actually implemented.
P063732 | ID-CORPORATE RESTRUCTRG | East Asia and Pacific | Indonesia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/289901474893244252/text/000020051-20140612132530.txt | http://documents.worldbank.org/curated/en/289901474893244252/pdf/000020051-20140612132530.pdf | The Bank should not undertake a project without sufficient knowledge of the intended beneficiaries, in this case, the firms intended to be restructured, and their operational soundnessEven in a situation perceived as urgent, the Bank needs to ensure that conditions critical to successful project launch and implementation are in place: institutional arrangements, Borrower commitment, design appropriate to achieve stated objectivesField-based supervision was critical to improving project performance, as the political and economic circumstances changed rapidly
P063791 | Mauritania: Telecommunication and Postal Sector Reform | Western and Central Africa | Mauritania | IDA |  | Infrastructure | Transport | IDA | IPF | 1999 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/371371474893311967/text/000020051-20140612141030.txt | http://documents.worldbank.org/curated/en/371371474893311967/pdf/000020051-20140612141030.pdf | A highly professional analysis of the opportunities and risks for the private sector paved the way for successful telecommunication privatization. The details of this process are highly relevant to other countries considering a similar privatization strategy.Political commitment and ownership is essential for the successful implementation of a sector reform program and especially one involving privatization. At an early stage a definition of a sector strategy, outlining the Government's vision should be agreed.A good communications campaign and media relationship in readiness for privatization are essential ingredients to enhance private sector confidence, mitigate country risk and build consensus on the reform agenda.For the monitoring of project implementation progress and the assessment of the project's impact, it is important at an early stage to include indicators that closely reflect the development objective and the objectives of each component. An entity in charge of coordinating and collecting data on a regular basis should also be designated.To maximize the impact of competition, the Mauritanian experience demonstrated the importance of establishing a level playing field between operators, enacting clear rules of the game, and making sound policy choices.
P063913 | Java-Bali Power Sector Restructuring and Strengthening Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2003 | 2014 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/961711467996704798/text/ICRR14788-P063913-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/961711467996704798/pdf/ICRR14788-P063913-Box393191B-PUBLIC.pdf | The following lessons are selected from the ICR:i. Ensuring quality at entry is far more important than speedy commitment, because inadequate preparation ultimately delays project benefits. When a project is processed at great speed for approval (for whatever reason, such as lack of Bank lending for several years), this may lead to technical choices (such as â€œupratingâ€ of cables in a power transmission project), which eventually turn out to be not feasible, thus delaying the project by years. ii. The safeguards issues for power transmission projects need close attention during preparation. This is particularly true for land acquisition. If this issue is not addressed during preparation, significant delays are likely at a later stage.iii. The success of the Enterprise Resource Planning (ERP) system, as implemented in the Java-Bali Power Sector Restructuring Project in Indonesia, led to significant cost savings and offers important lessons for sector practitioners. The factors that contributed to installation of the ERP system within the deadline and cost envisaged at the outset, are worth replicating. These include transparency of financial and management information systems, particularly significant in countries where public sector governance is an issue.
P063918 | LEGAL AND JUDICIAL DEVELOPMENT | Middle East and North Africa | Morocco | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/403531474481985811/text/000020051-20140613035537.txt | http://documents.worldbank.org/curated/en/403531474481985811/pdf/000020051-20140613035537.pdf | (i) Focused and sharp goals and objectives, clearly-linked activities, and strong country ownership and commitment are the underpinnings of a successful project in legal reform. (ii) Champions may be sort lived and therefore it is essential to generate broader consensus and a wider range stakeholder support when the context is supportive. (iii) While legislative reform is necessary, there is perhaps need to phase activities and first ensure consensus building among key stakeholders, and to work on strengthening political will.
P063939 | SOCIAL SAFETY NET ADJUSTMENT | East Asia and Pacific | Indonesia | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 1999 | 2001 | 2003 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/795101474510940188/text/000020051-20140607152929.txt | http://documents.worldbank.org/curated/en/795101474510940188/pdf/000020051-20140607152929.pdf | The Bank should avoid adjustment loans with process conditions. Process outcomes are very difficult to verify or use as conditionalities - the Bank cannot contract on a "sincerity" basis to ensure government abides.Adjustment loans have serious limitations for addressing institutional issues.It is better for the Bank and its client to take the risk of doing something badly (attempting to assist a weak government introduce new governance processes) than do nothing at all. The public nature of the exercise and close monitoring undoubtedly reduced corruption and inefficiency from what it might have been, given the Bank's politically determined commitments to transfer resources.)
P064008 | SMALL TOWNS WATER | Western and Central Africa | Nigeria | Blend |  | Sustainable Development | Water | IDA | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/364061475088617151/text/000020051-20140613032141.txt | http://documents.worldbank.org/curated/en/364061475088617151/pdf/000020051-20140613032141.pdf | Do not provide investment funding when sound governance is either in doubt or likely to be a serious issue.If a borrowers continually refuses to take into account the Bank's concerns on implementation and governance issues then management should cancel the project.Never underestimate communities' willingness to pay for basic service provision - but be very careful while appraising institutional arrangements and responsibilities that there are sufficient safeguards to protect communities' investments.Pilot operations under LILs should be appropriately scaled so that they can be well managed and monitored.
P064008 | SMALL TOWNS WATER | Western and Central Africa | Nigeria | Blend |  | Sustainable Development | Water | IDA | IPF | 2000 | 2004 | 2006 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/491941468065930403/text/36443010UNI.txt | http://documents.worldbank.org/curated/en/491941468065930403/pdf/36443010UNI.pdf | 1. Findings and Lessons COUNTRY AND SECTORBACKGROUND 1. Nigeria is the most populous state in Africa with an estimated population of 140 million in 2004 occupying an area of 926,000 square kilometers. The aimual population growth rate is thought to have declined from 2.9 percent over the 1980-2001 period and is projected to be 1.9percent over the 2001-15 period. About 45 percent of the population is considered urban and about 55 percent rural. The rural population includes communities with populations below 5,000; larger communities are considered urban. Per capita GNP reached close to US$1,300 in 1980but has since dropped sharply and was estimated at US$290 in 2001. After independence in 1960the Nigeria was mostly ruled by the military but since 1999the country has been led by a democratically elected president. The northern half of the country is primarily Muslim and the southern half primarily Christians. Disputes over political power, access to the benefits from oil resources and inter-denominational strife flare up periodically. 2. It has long been thought that about half of the urban population is connected to potable water but current data now indicate that the urban coverage might be at most half that, or 25 percent. Rural coverage is lower. In both urban and rural areas water service is intermittent or absent and water is unsafe. With the exception of the capital Abuja, the country has no operative sanitary sewerage. Infant mortality, which was estimated at 117per thousand live births in 1980, has declined to 101 per thousand live births by the year 2004. Over the same period, under-five child mortality declined marginally from 230 to 197per thousand live births.' Poor water service and no sanitary excreta disposal can explain much of the high mortality. 3. Water supply is a state responsibility in Nigeria and each of the 36 states and the Federal Capital Territory has created a State Water Board to exercise its authority. The State Water Boards are vested with the duty to provide service in both urban and some semi-urban areas. State ministries of water are responsible for service delivery in small towns and rural areas. The Federal Ministry of Water Resources is responsible for national and international aspects of water resource allocation and for approving large water resource development projects. FMWR oversees the activities of 11 River Basin Development Authorities. The FMWR has a Department of Water Supply and Quality Control, but without any formal regulatory authority. In practice, the country lacks reliable consolidated assessments of access and quality of water supply and sanitation services. To remedy this gap the Department of Water Supply and Quality Control is planning a study to establish a country-wide baseline to track Nigeria's progress towards meeting the water access targets under the Millennium Developnlent Goals. It is already clear that Nigeria is unlikely to meet the MDG target^.^ 1.UNICEF. 2005. Globally the average infant mortality rate in 2004 was 54 per 1,000;ranging from 5 for industrialized countries to 59 for developing countries and 98 for the least developed countries. Source\. http\./lchildinfo.org/areas/childmortality/infantdata.php. 2. In its comments (see Annex B) the FMWR notes that the Federal Government, through the FMWR, continued to invest over US100 million dollars, every year on water supply infrastructural development. 4. IEG rates the outcome of the National Water Rehabilitation Project as highly unsatisfactory3,the outcome of the First Multi-State Water SupplyProject as moderately unsatisfactory. In contrast, the outcome of the Small Town Water Supply and Sanitation Project is rated as satisfactory. 5 . The improving trend in project outcomes can in large part be explained by a shift in responsibility for project implementation away from the Federal Ministry of Water Resources under the National Project, to only two State Water Boards (Kaduna and Katsina) under the Multi-State project, and finally a clear focus on a limited number of towns under the Small Towns project. This shift enabled an alignment of the incentives of the beneficiaries with the objective of designing and building simple systems that can be sustainably operated. 6. The three projects also mark a rebalancing of the needs for maintenance of existing assets versus simply investing in new capacity. The National and Multi-State projects show that increasing system coverage and capacity is of little use if the rest of the existing system is dysfunctional due to inadequate maintenance. Conversely, the Small Towns project obliged the participating towns to contribute financially to the investments and organize sustainable operation and maintenance of systems they now owned. Indeed, about half have employed small private entrepreneurs to operate the systems. And the likely sustainability of the Small Towns project (with 13 out of 16towns operational) attest to the merits of the principle of demand-driven investments where the communities have the final decision on the type and cost of the system that will be built. Lesson One\. The tracking of the targets under the Millennium Development Goals must improve to account for the water supply service deficiencies of Nigeria. 7 . It is highly unlikely that the MDG water supply and sanitation targets will be met in Nigeria. The reasons are twofold. First, the present PPAR has demonstrated that the present weighted access to water supply of 42 percent does not paint a true picture of access. The PPAR has estimated urban connection rates in Kaduna state at the most as 25 percent and this after the state has benefited from three previous Bank loans and is benefiting from a fourth, the National Urban Water Sector Reform Project, approved in 2004. It stands to reason that Kaduna state is likely to have one of the highest, if not the highest, rates of access to water supply in Nigeria which makes it likely that the present actual access in Nigeria is at the most about half that conventionally assumed. 8. Second, the PPAR reports on the abysmal quality of water service in Nigeria with intermittent service being the rule and bacteriological quality of service unsafe. Therefore what the MDG define as access to water supply service cannot be taken as safe or as 3. In its comments (see Annex B) on the draft PPAR the FMWR notes that Besides, only three out of the 188 rehabilitated schemes were visited and thereby wondered how the PRAR came to the conclusion that the project was highly unsatisfactory. representing a modicum of satisfactory service. In some cases such as for the system in Zonkwa built under the First Multi-State Water Supply project in Kaduna state water has not been available for four months. In Kaduna's capital city only 28 percent of water samples test negative for pathogens; and in the mega-city of Lagos the actual average consumption of the population has been estimated at 12 liters per capita per day.4 9. Such glaring deficiencies in the quality of service demand that the simplistic MDG definitions of what constitutes access to water supply service must evolve to incorporate some form of quality considerations. These might comprise the continuity of service that is fundamental to safeguard the bacteriological safety of supplies. To track such an amended definitions of access, Nigeria must equip itself with a sound monitoring and evaluation system. Such a system will not require much external financing, but simply having the Federal Ministry of Water Resources, through its Directorate of Water Supply, annually monitor a dozen or so of the most central performance indicators of the water supply operations of the State Water Boards. Lesson Two\. Effective coordination between central, state and local governments requires demand-driven approaches where the consumers have the initiative. 10. The three assessed projects show a clear evolution from a supply-driven strategy where the Federal Ministry of Water Resources controlled the National Water Rehabilitation Project tightly, via the First Multi-State Water Supply project where two State Water Boards were responsible for project implementation, to the Small Towns Water Supply project where the local communities were the driving and deciding force for all major decisions. The results clearly show the relative benefits of the three approaches\. the Small Towns project has been rated as satisfactory, the First Multi-State Water Supply as moderately unsatisfactory and the National Water Rehabilitation Project as unsatisfactory. Lesson Three\. Maintenance merits priority over new works. 11. The results of the National Water Rehabilitation Project are proof that new works in the absence of reliable maintenance will not increase supply. Effectively no attention was paid to ensuring a reliable system of maintenance of the power supply, or the effective and reliable production of replacement power through standby generators. Maintenance was mentioned as an objective but for maintenance to happen there must be policy declarations, policy instrumentation and policy implementation. None of this happened. The political powers at state levels were not asked to support maintenance through policy declarations or the adoptions of suitable legislation and regulation, nor were they asked to guarantee the financing to undertake maintenance and operate the systems reliably. In the absence of financial self-sufficiency the first victim of financial stress was preventive maintenance with serious long-term consequences. 4. Agenda 21, the Rio Declaration on Environment and Development. established a target of access to at least 40 litres per capita per day of safe water in urban areas by the year 2000. The full implementation of Agenda 21,the Programme for Further Implementation of Agenda 21 and the Commitments to the Rio principles, were strongly reaffirmed at the World Summit on Sustainable Development held in Johannesburg, South Africa in 2002. Lesson Four\. Demand-driven projects demand adequate community development. 12. The success of the demand-driven Small Towns Water Supply and Sanitation Project could not have happened without substantial resources expended on activating the small towns and stimulating them to setting up Water Consumer Associations. These WCAs quickly appreciated the fact that they were in the driver's seat and arranged for the collection of funds to pay the required 10percent contribution of the project investments.' Subsequently, they took on the responsibility of operating the works .themselvesor employing private operators for the purpose. The support from the Federal and State Project Coordination Units was mainly positive. However, in the case of the selection of the technical alternative there should have been better guidance under the Kuta sub-project to weed out the very expensive option that will if it will ever be operational be very costly and complicated to operate. Demand-driven approaches must therefore be combined with some kind of project selection criteria based on a cost-effective analysis of different options. Such criteria might simply be a ceiling for the capitalized value of the projected capital and current costs of a given sub-project over the useful life of the investment. Lesson Five\.Water Projects cannot succeed without the political will to reform 13. The failure of the National Water Rehabilitation and First Multi-State Water Supply projects show there was not effective attention paid to tracking meaningful operational performance indicators, and to creating viable commercial systems with appropriate tariffs and systems to bill and collect sufficient revenue to enable the State Water Board to become financially sufficient. The ultimate responsibility for this failure must be shared between the political and technical authorities in Nigeria and the Bank preparation and supervision teams. 14. A more reasonable lending strategy would have been to apply a step-wise analysis and acceptance of the investment programs of individual state water boards where the political will in each state would be tested at each successive step in project preparation and implementation. Accordingly and first, for a state to be considered for financing under the Bank loan it would have to agree to supply the minimum of performance indicators to allow the preparation teams to judge what mixture of reform and investment would be required. Second, the state would receive access to funding conditioned on implementing the reforms that would have been agreed on as a result of the initial diagnostic. Third, there must be a 5. The Bank's Africa Region staff note\. . ..it is important to recognize the tension that may arise with politicians who are often more interested in short-term impacts rather than this time-consuming approach associated with community participation. If community participation is considered to be critical for sustainability, then the question policy makers and project fmanciers should be struggling with is what is the appropriate level of contribution that will ensure that communities have a enough ownership in facilities to make them sustainable over time?? In fact, in Nigeria, different projects have used different rules. Under the IDA STWSSP, the contribution from communities was 10% but under the EU Small Towns Project it was reduced to 5%. The common view that the higher the contribution, the higher the likelihood that facilities will be maintained and sustained does not take into account the transaction costs of convincing local governments and communities; too high a contribution may paralyze investments and also might appear unfair in comparison of what is required from urban customers, i.e. almost nothing up-front. There are examples elsewhere that have been positive without contributions being provided by the communities but other rules have been set up by the communities with regard to the management of the facilities and services. There is no magic number and each project should define the rules of the game based on the exact situation of the communities and their willingness to invest in facilities and services that will provide benefits that they are looking for. willingness on the part of the financing agencies, including the Bank, to exclude those states from financing where the political will to reform, and therefore chances of a positive project outcome, are not at hand.
P064045 | EC Fin Sectr TA Ln | Latin America and Caribbean | Ecuador | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/915381474631132065/text/000020051-20140613040419.txt | http://documents.worldbank.org/curated/en/915381474631132065/pdf/000020051-20140613040419.pdf | The ICR draws the lesson that the Bank should have flagged risks more realistically and sought to mitigate them (particularly in the governance of AGD). In addition, the project's failure illustrates the importance of focusing on deep rooted causes of bank failure (e.g. fiscal problems that also led to the failure of earlier SALs and policy and regulatory distortions that led to offshore bank deposits). Finally, introducing new laws that attempt to correct or sidestep inadequate laws can be risky both because they are subject to modifications in the process of being ratified that can alter their impact, as well as to court challenges that slow down crisis resolution. A technical assistance project is unlikely to succeed when the accompanying SAL that it sought to support failed.
P064064 | Mine Township Services Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/843711474893001995/text/000020051-20140615102307.txt | http://documents.worldbank.org/curated/en/843711474893001995/pdf/000020051-20140615102307.pdf | The project's main lessons relate to the vision, planning and preparation for institutional development subsequent to the project period - i.e. the "Exit Strategy" (Lessons 2 and 3 are derived from the ICR lessons):1. Project design should be within an overall longer-term perspective for a sector's development. The project was seen as a "transitional" project and the water supply and sanitation improvements had strategic importance as necessary in order to attract private interests to Zambia's copper mining sector, for which privatization was a strategic priority. In this situation, preparing the project without a clear exit strategy for after the project was probably justified, but involved risks. The exit strategy was to be prepared during the project, but, in the event, a clear path forward with stakeholder consensus only partially emerged. If time had been less pressing, a better approach would have been to devise and agree on the longer term objectives and institutional structures before or during project preparation. 2. (if the exit strategy had to be prepared during project implementation) the process/roadmap for determining the exit strategy should be clearly defined, key stakeholders should be involved throughout the process, the implementing agency should be given an appropriately strong mandate, and the Bank should be closely associated with the process and development of the strategy. This process for preparing the exit strategy should be agreed and the mechanisms to take the process forward should be detailed out as part of project preparation and design. 3. Clearly defined tariff setting mechanisms and regulatory approvals are a key part of a utility commercialization program. Tariff adjustment mechanisms and rules for regulatory interventions and approvals should be as clearly determined and as predictable as possible for the utilities and their customers. A long-term tariff adjustment formula should be considered, using clear and autometic adjustment criteria which could be reviewed on a three to five year cycle. The features of the mechanisms should be designed to maximally protect from political interventions.
P064082 | TN-Transport Sector Project II | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2001 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/557041475091650153/text/000020051-20140620085512.txt | http://documents.worldbank.org/curated/en/557041475091650153/pdf/000020051-20140620085512.pdf | It is critical to set up a realistic and measurable objective in accordance with a practical and agreed time frame.Setting up new structures and institutional arrangements for transport at the regional level is complex and sensitive, touching on decentralization issues going well beyond urban transport. Success depends on full discussion and a thorough review of alternatives to reach consensus before implementation commences.Reforming public enterprises needs sustained commitment from the relevant ministries, benchmarking performance regularly with strongly performing enterprises in other countries, and a clear understanding by all stakeholders of the dynamics of the tariffs in relation to productivity and the financial stability of the enterprise.Transport arrangements for mining companies often work more successfully when the companies or joint venture companies themselves driven by the profit motive take responsibility for the transportation of the minerals.When there are major bottlenecks because of conflicts between national regulations and Bank procurement guidelines, this may be better addressed at program level rather than through individual projects.In countries governed by the Napoleonic Code and its legal and juridical administration, legislation on its own means very little. It is important to take prior action to ensure that the detailed application decrees are put into effect within a reasonable time frame.
P064083 | HO HURRICANE EMERGENCY | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2006 | 2001 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/930351474907116855/text/000020051-20140529162101.txt | http://documents.worldbank.org/curated/en/930351474907116855/pdf/000020051-20140529162101.pdf | From the Bank ICR (identical to those of Nicaragua Hurricane Emergency Project C3158)Very early Bank involvement is needed to develop an overall emergency assistance.As part of the process of defining an emergency assistance strategy, the Bank should quickly assess the country's macroeconomic situation, risks and requirements, and identify any need for quick disbursing support, through balance of payments support operations, for instance.Longer-term concerns about disaster management preparedness and mitigation need to be addressed, but it is not effective to combine this with emergency support objectives.The Bank's timely response in preparing emergency operations is critical. In this sense, the Bank should continue to respond flexibly to reducing periods for distribution of key documents and for adherence to routine, internal procedures.The existence of experienced operational staff in a Bank field office is fundamental for assisting Governments deal initially with early damage assessment, and definition of assistance priorities, financing options, and implementation arrangements.From the borrower ICR:Simplicity of project design for an emergency permits the definition of clear and precise targets, which can be framed under a program of balance of payments support.Designing a project without complex conditionality can give it the flexibility that is most needed in situations of emergency.From OED:We learn little about how best to provide post-disaster emergency assistance from this kind of project. Being streamlined in implementation, balance of payments support for emergency recovery can be a good idea, but it should also report--across broad categories of eligible items at least--how Bank funds were spent and also the recovery purposes to which the imported items were put. Such reporting can provide valuable inputs into the design of future emergency recovery projects.
P064084 | NI HURRICANE EMERGENCY | Latin America and Caribbean | Nicaragua | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 1999 | 2000 | 2001 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/480381474907403099/text/000020051-20140529162016.txt | http://documents.worldbank.org/curated/en/480381474907403099/pdf/000020051-20140529162016.pdf | From the Bank ICR: (identical to those of Honduras Hurricane Emergency Project C3159)Very early Bank involvement is needed to develop an overall emergency assistance.As part of the process of defining an emergency assistance strategy, the Bank should quickly assess the country's macroeconomic situation, risks and requirements, and identify any need for quick disbursing support, through balance of payments support operations, for instance.Longer-term concerns about disaster management preparedness and mitigation need to be addressed, but it is not effective to combine this with emergency support objectives.The Bank's timely response in preparing emergency operations is critical. In this sense, the Bank should continue to respond flexibly to reducing periods for distribution of key documents and for adherence to routine, internal procedures.The existence of experienced operational staff in a Bank field office is fundamental for assisting Governments deal initially with early damage assessment, and definition of assistance priorities, financing options, and implementation arrangements.From OED: We learn little about how best to provide post-disaster emergency assistance from this kind of project. Being streamlined in implementation, balance of payments support for emergency recovery can be a good idea, but it should also report--across broad categories of eligible items at least--how Bank funds were spent and also the recovery purposes to which the imported items were put. Such reporting can provide valuable inputs into the design of future emergency recovery projects.
P064094 | ENERGY SECAC | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Energy & Extractives | IDA | DPF | 1999 | 2002 | 2003 | ICRR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/708701475073233215/text/000020051-20140607164243.txt | http://documents.worldbank.org/curated/en/708701475073233215/pdf/Georgia-Energy-SECAC.pdf | The key energy sector issue in many transition economies is how to manage and eventually eliminate the quasi-fiscal deficitEnergy privatization may be possible even under adverse circumstances (e.g., poor financial performance, high corruption, weak state capacity), although the outcome may include low privatization proceeds, higher tariffs, and worse performance of state-owned companies before and during privatizationGovernment support to private investors after privatization is critical, especially in helping to fight vested interests and corruption; this is a key element affecting the sustainability of privatizationWhere government capacity is sufficient, it is desirable to improve energy company financial performance prior to privatizationIf government capacity is low, a high level of coordination between ILIs is necessary to assure sufficient temporary financial support for energy firms to make them viable candidates for privatization
P064094 | ENERGY SECAC | Europe and Central Asia | Georgia | IBRD |  | Infrastructure | Energy & Extractives | IDA | DPF | 1999 | 2002 | 2004 | PPAR | >=25 million & <50 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory |  | http://documents.worldbank.org/curated/en/746081468751804137/text/26439.txt | http://documents.worldbank.org/curated/en/746081468751804137/pdf/26439.pdf | 8. Lessons Learned 8.1 Georgia's weak governance severely limitsthe country's ability to create conditions conducive to economic development and the effective use of development assistance-The problems that limit growth inGeorgia transcend economic policy. The political and geographic fragmentation o f the country poses severe challenges to the executive. The inability o f the executive to overcome obstacles posed by the parliament and regional officials, establish a minimumlevel o f the rule o f law, and overcome a pervasive culture o f corruption severely limits the country's ability to establish sustained, broad-based growth with significant job creation. 8.2 For a country such as Georgia, which experienced economic collapse, it is incumbent that the Bank give high priority to prompt measures that can directly mitigate conditions for the poorest. 53This section is based on interviews with energy sector firms, govemment officials, and Bank staff. 8.3 Turnover on the country team limited program effectiveness-From 1994to 1998,there was one Country Economist for Georgia. Officials interviewed cited the benefits that they believe this continuitybrought. However, since 1998, there have been3 Country Economists, and an interval o f around6 months duringwhich the position was unfilled. While there werejust two Country Directors duringthe periodcoveredby this PPAR, and good continuity on the rest o fthe Country Team, the tumover diminished the continuity o f the program, andprobablyconstrained the ESW that was performed. 8.4 A more robust and timely ESW programwould have been beneficial to the design o f the reformprogram-The Country's first poverty studywas completed in 1999; the design o f the reform program would have benefited from earlier work inthis area. A study o fthe sources o fgrowth might also have beenbeneficialbyidentifyingsectors from which growth might be expected to flow, and then considering means by which to facilitate such growth. A Public Expenditure Review-a veryuseful analytical tool for a country with Georgia's perennially weak fiscal situation-was completed in 1996, and then not again until 2002. Fiduciary reports (CFAAs and CPARs) were completed infrequently. The rapid tumover inCountry Economists was probably part o fthe reason for the weak ESW. 8.5 Turnover among policy officials hinderedreform progress-During the seven years coveredby this PPAR, there were seven Prime Ministers and four Ministers of Finance. There was also substantial tumover among other officials concerned with implementingthe reform program. For an official contemplating a brieftenure, it i s more difficult to appreciate the benefits o f reform, and so this tumover made reform progress considerably more difficult.
P064118 | Water Resources Sector Adjusment Loan | East Asia and Pacific | Indonesia | IBRD |  | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 1999 | 2005 | 2006 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/147531474575029511/text/000020051-20140613065219.txt | http://documents.worldbank.org/curated/en/147531474575029511/pdf/000020051-20140613065219.pdf | A strong enabling environment significantly contributes to successful reforms: Indonesia had several factors that helped its reform program: (i) a trigger for reform (Indonesia needed urgent budgetary support to finance food imports in the wake of the East Asian economic crisis and the El Nino drought); (ii) a coinciding national reform drive that included a decentralization objective; (iii) a reform champion in a highly reformist Minister; and (iv) a popular reaction to several prior decades of limited reform and transparency. Ownership of moderately ambitious reforms may have greater impact than more extensive reforms with less ownership. Ownership may have design implications: Indonesia's reform program was largely devised by government and other stakeholders over nearly a year of intensive and highly participatory discussions. The reform components prepared during project implementation (such as the national water policy, legal provisions, etc.) were also the product of extensive home-grown interaction. The Bank successfully played an advisory but unobtrusive role. A participatory approach does, however, have implications. First, consensus takes time; the original 18 month project period was far too short for this, and the extensions were inevitable. Second, homegrown reform may need to be less than perfect in design. The ICR expresses the implications well: "Prioritize achieving sustainability and local ownership over the perfection of what is delivered, and over the adherence to time schedules imposed by non-essential interests." And "better a 70% product that sticks than a 100% product that doesnt." Project design and the implementation period need assessment for realism. Indonesia's comprehensive water sector reform program was professionally sound, but was too demanding to expect full implementation. The project, in addition to its complex policy, legislative and institutional reforms, contained field implementation actions such as establishing a water quality network, forming fully functional basin management units in 8 provinces, establishing 4 river basin corporations, and implementing water pollution control in six river basins. The initial project period of 18 months (accepted by the Bank under pressure from Government) was patently unrealistic. In such a situation, the 4 years of extension could even be regarded less as an implementation weakness but as a sensible correction. Assessment of an appropriate project period could use standard analytical tools. OED has commented before that reform action including drafting of regulations can be projected and scheduled in the same way that large construction projects can be, and using similar tools: e.g. computerized project management techniques.
P064149 | CAR - POLICY SUPPORT PROJECT | Western and Central Africa | Central African Republic | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2000 | 2005 | 2005 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/472721475100588213/text/000020051-20140613032513.txt | http://documents.worldbank.org/curated/en/472721475100588213/pdf/000020051-20140613032513.pdf | Especially in risky circumstances, projects should contain minimal conditions of effectiveness, and such conditions as establishment of satisfactory accounting and financial management systems should be formulated as conditions of Board presentation. In this case, this mispecification of conditionality led to a one year delay in effectiveness. The Bank should use a LICUS approach (coordinating financing and policy reforms very closely with other donors) with realistic expectations when facing risky conditions as in the CAR.
P064237 | Tuberculosis & AIDS Control Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2003 | 2009 | 2011 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/873141474897860483/text/000020051-20140620075545.txt | http://documents.worldbank.org/curated/en/873141474897860483/pdf/000020051-20140620075545.pdf | Effective political economy analysis, and continued attention and sensitivity to contextual political and cultural factors, is essential. In this case, adaptation of evidence-based practice on TB to the Russian context was critical for moving the project forward.The Bank can produce significant impact through relatively inexpensive capacity building, policy dialog, analytical work, and project preparation activities. In this case, such activities dramatically improved Government commitment to fighting HIV/AIDS and TB, and improved the efficiency and technical quality of the response.Comprehensive needs assessments from the outset of project implementation can play an important role in ensuring effective use of resources and encouraging collaboration across a wide array of institutional actors.Comprehensive coverage plays a crucial role in HIV/AIDS and TB programs, working across regions and integrating efforts of the civilian and prison sector.The involvement of core research institutes in project preparation and implementation, including their collaboration with international agencies, can enhance the quality of the response and produce side benefits of enhanced institutional collaboration across the health sector.Through deliberate effort, communicable disease projects and health system reform projects can effectively reinforce one another. The TTL provided information that 80% of the equipment purchased through this project has been intended for primary care facilities, consciously reinforcing the aims of the parallel Health Reform Improvement Project by strengthening non-specialized, decentralized care.
P064238 | Northern Restructuring Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2001 | 2010 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/190251475098672694/text/000020051-20140624161420.txt | http://documents.worldbank.org/curated/en/190251475098672694/pdf/000020051-20140624161420.pdf | The following lessons are selected from those presented in the ICR with some adaptation of language:When an operation supports the formulation and implementation of socially sensitive policies, then efforts should be made during preparation to extend and deepen consensus for such policies as much as possible among all concerned stakeholders, especially within government. Relying on a single "champion," as in this case, leaves the project vulnerable to changes in staff and in institutional oversight responsibility.Project design should ensure coherence between development objectives and the activities and inputs financed by the operation.Where demand is unknown, flexibility in design is important to enable the project to react smoothly to unforeseen changes in the volume and pattern of demand.Monitoring and evaluation should not be left to project implementation units or other structures outside the mainstream, permanent government institutions. Despite the reportedly high quality of the data bases developed under this project, relevant ministries felt no ownership of them, and did not use them.
P064305 | Third Social Fund Project | Eastern and Southern Africa | Madagascar | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 1999 | 2003 | 2004 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/534051475110161913/text/000020051-20140612094529.txt | http://documents.worldbank.org/curated/en/534051475110161913/pdf/000020051-20140612094529.pdf | Drawing on the ICR, some lessons are:1. To be a useful management tool, and identify areas of weakness/strength for remedial action/replication, the M&E system has to be based on a sound methodology.2. Creating maintenance committees is not sufficient to ensure sustainability of community subprojects. Measures to ensure that these committees continue to function after subproject completion should be taken.3. Cross-sector coordination is critical among Bank sectoral staff, among country sectoral staff, and between Bank and country sectoral staff in multisector operations. 4. Coordination is also needed among the various donors working at the local level with respect to harmonizing their project requirements (e.g., for beneficiary contributions, subproject cycles etc).
P064438 | THE GREATER ADDO ELEPHANT NATIONAL PARK PROJECT | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2004 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/180961474572046688/text/000020051-20140624203112.txt | http://documents.worldbank.org/curated/en/180961474572046688/pdf/000020051-20140624203112.pdf | The following lessons are emphasized:Implementing a participatory approach to achieve biodiversity conservation with government programs, private sector and local communities can be effective both for improving biodiversity conservation and for promoting economic development. The project provided a good example on how stakeholders could play a positive role to support biodiversity conservation without compromising development.Income generated through nature based tourism can compete successfully with that generated through agricultural activities, especially considering that agriculture income is limited by the poor soil conditions and water availability. The project experience demonstrated how the linkage between pro-poor job creation, investment from private sector and biodiversity could be an engine for regional economic growth. Sound science remains essential to conservation planning and responding to stakeholder demands. The project showed how scientific evidence can be used to raise community awareness and build commitment to protecting natural resources.
P064508 | Treasury Development Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2002 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/889441475073113077/text/000020051-20140625235907.txt | http://documents.worldbank.org/curated/en/889441475073113077/pdf/000020051-20140625235907.pdf | The lessons from both the Bank's and borrower's ICR are supported, inter alia: Strong borrower ownership and leadership are keys to success, and it is worth extra time to help formulate a strategic vision during project preparation.Specialized expertise in information technology should be provided as part of the Bank team.Continuity of Bank, borrower and contractor teams is critical to ensure consistency and in depth follow-up of emerging issues with Government counterparts.A flexible and constructive approach is needed from all sides in recognition to changes in country legislation, while ensuring that the core regulatory framework remains stable during the implementation of complex, ICT systems.
P064510 | Second Social Action Project | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2000 | 2006 | 2007 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/765021474487206409/text/000020051-20140617132815.txt | http://documents.worldbank.org/curated/en/765021474487206409/pdf/000020051-20140617132815.pdf | The following lessons were included in the ICR:Community participation can ensure ownership by the communities of the whole approach and process, including community mobilization and the selection of sub-projects, the monitoring of construction and the subsequent operation and maintenance of infrastructure.In an emergency and civil conflict situation, project design should be simple in order to deliver urgently needed support quickly.A social fund can mobilize communities to work with the formal health and education structures to supply social services, rather than being limited to traditional infrastructure investments.
P064536 | Child Welfare Reform Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2001 | 2006 | 2007 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/388311474898779102/text/000020051-20140617135432.txt | http://documents.worldbank.org/curated/en/388311474898779102/pdf/000020051-20140617135432.pdf | This ICR Review supports three of the four lessons drawn in the ICR, viz. that:NGO capacity may be uneven and that a proper assessment of the capacities should precede the delegation of responsibilities to them;Creating new institutions requires that the division of labor and relationship between the new institution and existing ones is clearly defined; and Sustained commitment of local authorities has to be built-up and secured before their selection as partners.This ICR Review adds to the ICR's second lesson and modifies the fourth one as below:Creating new institutions requires up-front consideration of the end game (exit strategy etc) and a deliberate movement towards it;While the project implementation timeframe has to be realistic vis a vis objectives (as noted in the ICR), project objectives and design also need to be realistic vis a vis the country's institutional capacity.
P064542 | Enterprise and Financial Sector Adjustment Loan (EFSAL) | Europe and Central Asia | Slovak Republic |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2002 | 2004 | 2005 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/136291474508847194/text/000020051-20140613040700.txt | http://documents.worldbank.org/curated/en/136291474508847194/pdf/000020051-20140613040700.pdf | Extensive technical assistance and Bank analytical work (rated highly satisfactory by QAG) proved extremely useful in facilitating achievement under the loan (TA was provided by the Fund, DFID, USAID, and the EU).Slovakia's status as a candidate for EU accession (it became a member in May, 2004) acted as a powerful incentive to move forward on EFSAL reforms.The conditionality for tranche release was very extensive, and it might have been more efficient to designate core conditions for that purpose.
P064556 | BI Emergency Economic Recovery Credit | Eastern and Southern Africa | Burundi | IDA |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2000 | 2003 | 2004 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/809841475078506382/text/000020051-20140612131122.txt | http://documents.worldbank.org/curated/en/809841475078506382/pdf/000020051-20140612131122.pdf | In post-crisis situations where government is restarting basic programs, projects need to be designed flexibly. While governments need to be given intensive supervision and support, responsibilities should be devolved to the extent possible given the quality of governance. Poverty-alleviation activities in post-conflict situations need to be supported to the maximum extent feasible.
P064557 | Education Sector Reconstruction Project | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Education | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/963511475094109454/text/000020051-20140626000948.txt | http://documents.worldbank.org/curated/en/963511475094109454/pdf/000020051-20140626000948.pdf | The ICR (pp. 26-27) notes four lessons learned, on: a) the need to avoid complex organizational structures; b) the need to have appropriate indicators; c) the usefulness of delegating responsibility to sound implementing agencies; and d) the need for continuity of project management. Additional comments from IEG are as follows:1. Measuring Learning Achievement. This project demonstrates the difficulty of measuring the impact of program inputs on learning outcomes over a relatively short period of time. Although the intent was excellent in including a reading assessment, the project inputs were not such that, even had the intended activities taken place in a timely fashion, they could have been shown to demonstrate student achievement in reading. It is also not clear whether the teacher training emphasized this aspect of learning, and obviously it would have been important that this be the case in order to assess impact.2. Project indicators should be matched to project activities. The ICR notes correctly that the project indicators were at too high a level to be able to demonstrate the progress made under actual project components and activities. The project concentrated activities in nine poor regions where good progress was made, whereas indicators used in the project for country-level progress show different results. This mismatch seems to occur when the Bank, governments, and donors wish to move to sector wide approaches but are constrained by fiscal and implementation weaknesses in country circumstances. This tension should be managed by Bank and Government teams in discussion with other donors in order for the success of project stand-alone activities to be correctly gauged.3. Progress can be made in post-conflict environments, but it can be slower than anticipated. With good donor collaboration, willingness on the part of the government, and strategic financing for key inputs, it is possible to make a positive impact on service delivery in post-conflict settings. This project's design took into account structural weaknesses in some implementing agencies and successfully designed some activities accordingly. However, in spite of simplifying the components at project entry, it still experienced some delays due to the nature of emerging government institutions. It is therefore extremely important to ensure that project objectives and design are realistic in these contexts..
P064558 | BI-Agriculture Rehabilitation & Sustainable Land Management | Eastern and Southern Africa | Burundi | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2005 | 2011 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/137451474594030640/text/000180307-20141118112848.txt | http://documents.worldbank.org/curated/en/137451474594030640/pdf/000180307-20141118112848.pdf | The ICR identifies three main lessons: Do not sacrifice depth of training and capacity building in favor of greater coverage. This project provided over 275,000 person days of training, many of these agrotechnical in nature. Even so, more sustained monitoring to detect training effectiveness could have led to targeted mentoring that may have improved the efficiency of outcomes.Performance based contracts can lead to better performance. Incentive to both public and private implementing agencies need to be performance based. Outcome orientated contracts (in the case of private) or enforced performance agreements (in the case of public) could strengthen their accountability and performance towards beneficiaries.Sustaining sustainable land management requires economic and financial incentives. Where the economic incentives were lower in the project, there was greater deterioration of project financed sustainable land infrastructure, and vice versa. The Government ICR notes, for example, that beneficiaries that also have livestock (to whom to feed the soil-fixing grasses that reinforce terraces) tend to better sustain their investments. Similarly, landowners appear to take better care of infrastructure than renters.
P064570 | Cultural Heritage Project | Western and Central Africa | Mauritania | IDA |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2000 | 2005 | 2006 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/386351474491912240/text/000020051-20140613080302.txt | http://documents.worldbank.org/curated/en/386351474491912240/pdf/000020051-20140613080302.pdf | For some topics (like cultural heritage) where the Bank a shortage of specialized expertise, even flexible, innovative, and relatively small projects like LILs need to be sure to include knowledgeable specialists, especially during preparation. Without such preparation, projects stand to suffer delays, and a create a dangerous lack of confidence, presenting a reputational risk not only to the project, but to the Bank as well. Close involvement of external partners can play a critical role in the success of specialized projects, such as this cultural heritage loan, through the provision of technical expertise, capacity building, and continued funding. In this case, these elements contributed substantially to the sustainability of the cultural heritage gains made during project implementation. In a multi-ethnic country like Mauritania, support to the living arts can play an important role in social cohesion. Relatively small investments in events targeting specific segments of the population brought the participants a sense of recognition at the national level, as well as an important expression of membership of the same culture
P064573 | Senegal River Basin Water and Environmental Management Project | Other | Africa |  |  | Sustainable Development | Water | GEF | IPF | 2004 | 2009 | 2010 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/112301474853106635/text/000020051-20140619111111.txt | http://documents.worldbank.org/curated/en/112301474853106635/pdf/000020051-20140619111111.pdf | GEF grant funding can play a critical role in building effective regional institutions. In this project GEF's support to build the capacity of OMVS to facilitate multi-country dialogue on policy, planning and development enabled a consensus among the Senegal River Basin riparian states on how to managed the river basin more effectively and increase environmental benefits.Trans-boundary Diagnostic Analysis highlights the need for a multi-sector approach to managing river basins shared among several riparians. In this project TDA facilitated inclusion of environmental and land management consideration into the water planning framework and establishment of multi-sector planning institutions.Carefully examine the transaction costs of partnerships and their management arrangements before committing to them. In this project the pressure to leverage the GEF grant led to the inclusion of activities at the local level managed by other donors. While the Bank partnered with UNDP (that managed the micro-projects) the apparent synergy of this partnership was undermined by coordination problems and their differing operational practices and procedures. It was also burdensome for the OMVS.
P064585 | Rural Finance 2 Project | Europe and Central Asia | Kyrgyz Republic | IDA |  | Sustainable Development | Agriculture and Food | IDA | IPF | 1999 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/281541474627452819/text/000020051-20140613085756.txt | http://documents.worldbank.org/curated/en/281541474627452819/pdf/000020051-20140613085756.pdf | The ICR has extracted a number of useful lessons from the experience with this project. The creation of a "greenfield" financial intermediary, such as the KAFC, from scratch, takes a long time. Stakeholders, including the Bank, must be prepared to invest sufficient time and attention -- in this case, two Bank-supported projects over almost 10 years -- in getting the new institution firmly established on a profitable and financially sustainable basis. Achieving financial sustainability required not only a capital base and loanable funds, but also extensive technical assistance for institutional development. This included not only training, hands-on support, and effective motivation to improve the capacity of KAFC staff , but also technical assistance to improve the knowledge and capacity of borrowers, in this case through the development of rural advisory services.It is important to have regular and effective dialogue with the government to ensure that the government does not make politically-based decisions that undermine the day-to-day operations of state-owned financial institutions. The Bank was very effective in responding to the April 2002 decree on interest rate subsidies, but less effective in relation to the privatization of KAFC.
P064614 | Second Secondary Education Project - Province of Buenos Aires | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/542491474486787013/text/000146597-20140619152241.txt | http://documents.worldbank.org/curated/en/542491474486787013/pdf/000146597-20140619152241.pdf | Education projects often focus on inputs and outcomes, leaving instructional processes as a â€œblack boxâ€ about which little is known. However, adding inputs into the black box without knowing how the variables operate inside it can be ineffective. In particular, when schools receive resources to provide extra time for their students, it is important to monitor how instructional time is used in order to make decisions regarding the cost effectiveness of the extra expenditures.Changes at the federal level, which are beyond the control of a sub-national borrower, can have a major impact on the outcome of sub-national projects. Staff working at the sub-national level must monitor closely the higher-level decisions and policies that affect sub-national projects, and adjust project implementation early on in order to conform to national trends.There are trade-offs between expediency and institutionalization: A project implementation unit may be able to carry out project activities quickly, but it may also risk isolation be prevented from participating in decisions that affect a project. It is important for project implementation units to be closely linked to policy-makers.The focus on school autonomy and social services may mean that school directors spend a disproportionate amount of their time and efforts tackling challenges unrelated to education, such as social services, fundraising, and procuring items that can be procured centrally (e.g. bake sales to buy photocopier toner and paper). Time spent on activities of secondary importance may interfere with attention to instructional activities. Local education offices may procure equipment and funds more effectively and enable staff to focus on learning acquisition.
P064634 | TRNSPRT REHB (SUPPL) | Latin America and Caribbean | Honduras | IDA |  | Infrastructure | Transport | IDA | IPF | 1999 | 2003 | 2004 | PPAR |  | Satisfactory |  |  | Satisfactory |  | http://documents.worldbank.org/curated/en/449651468752083062/text/291170HN.txt | http://documents.worldbank.org/curated/en/449651468752083062/pdf/291170HN.pdf | 5. Conclusions and Lessons Learned 5.1 It has already been indicated that the project objectives were and continue to be relevant. They were consistent with the views of both the old and new governments and enjoyed support from the worldwide professional community. The same applies for the general conceptual model that was promoted\. greater private sector participation or outright privatization. However, in spite of this agreement, the measures for rail, ports, and urban transport are still evolving. For the road sector, a good institutional model emerged. It would appear then that the objective and the (mental) model, and even the process for achieving the objectives were spelled out in too great detail during preparation when a less specific definition would have been more pertinent.2This detail was both time-consuming and costly and, in the end, was only partially followed. This leads to the following Lessons Learned\. Good preparation is important, but must allow for a realistic time frame. For policy/institutional restructuring projects, it should set out the broad study direction and assist the borrower to take full ownersh@ of the process, which should be jne-tuned as the project proceeds, with full input from the key sector players. Theproject preparationplan should include an assessment ofpossible risks. In the event that theproject experiences internal and/or external shocks, necessitating institutional restructuring, such restructuring can best be expedited through aflexible approach and good supervision. Key elements of aproject's policy and institutional development agenda may still be completed after aproject's closing date if theproject staff and consultants have nurtured an appropriate relationshipfor that agenda and remain engaged, if possible, beyond project closing. 2. Again, this is observed in several other audited projects (Pakistan, PPAR No. 20123 Fourth Highway Project, Loan 2814-PAK; Transport Sector Project, Loan 3241-PAK; Karachi Port Modernization Project, Loan 3335-PAK; and Peru, PPAR No. 22474 Rural Roads Rehabilitation and Maintenance Project, Loan 3963-PE; even the results of a Bolivia project can be viewed in the same way, Bolivia PPAR No.19515\. Export Corridors Project, Credit 2012-BO).
P064728 | Land Management and Policy Development Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2010 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/533291475076761980/text/000020051-20140625054910.txt | http://documents.worldbank.org/curated/en/533291475076761980/pdf/000020051-20140625054910.pdf | The following lessons are based on those presented in the ICR:Inadequate forward planning for high-level oversight of implementing agencies may hamper project implementation. The failure to set up the high-level steering committee envisaged during preparation sapped coordination between the three implementing agencies and impeded discussion of policy reform. If the Project Implementation Plan is not aligned with government's budget cycle, implementation may be delayed. There was little progress in the first year of implementation because the project became effective after the government deadline for submitting the procurement and disbursement schedule for the respective budget year. The project results framework may not be credible if M&E is not in place before project startup, and if measurable outcome indicators are not specified. M&E design was not sufficiently thought through during preparation and the indicators selected did not adequately capture the tenure security and service quality objectives of the project. Governments may not be willing to borrow for the technical assistance components of Bank-supported projects, in which case grant funding by other donors may have a vital role to play. Earlier East Asia land administration projects had comprehensive programs of technical assistance that were grant funded by donor partners. In this operation, the absence of such an arrangement made it difficult to manage the complexity of the project's design. Prior actions by government may be preferable to a long list of dated covenants that the Borrower is expected to comply with during implementation. The presence of such a long list of covenants in this case suggested the need to "lock in" a government that was not fully committed to project objectives.
P064728 | Land Management and Policy Development Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2010 | 2014 | PPAR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/407951468278683358/text/858090PPAR0P0647280Box382166B00OUO090.txt | http://documents.worldbank.org/curated/en/407951468278683358/pdf/858090PPAR0P0647280Box382166B00OUO090.pdf | 7. Lessons In a country like Indonesia where the institutions bearing on land rights are poorly defined and not transparently administered, the priority needs to be championing legal and policy reform; in these circumstances, a project that pays less attention to reform than to land titling is unlikely to lead to a sustained increase in tenure security. This project approached institutional reform incidentally and made no headway because there was little support for it\. there was little or no high-level commitment by government and the three implementing agencies showed little or no inclination to work together on policy reform. 7.1 The gains from a program of systematic land titling may not be sustained if the cost of registering subsequent land transactions is high (partly because there is a culture of making side payments to officials); and if the state often does not respect the private interest in land that has been formally registered. Worldwide experience shows that the (sporadic) registration of subsequent land transactionsâ€”for which there is an urgent need as parcels are divided among heirs, or as they change ownersâ€”will always be more expensive for the landowner compared to the cost of receiving title under a systematic program (partly as a result of economies of scale). The cost gap is particularly high in Indonesia and the project did not reduce it. At around 10 percent of the property value, the cost of sporadic registration is more than double the regional average, making it likely that subsequent transactions will not be registered. Registered land rights are not strongly guaranteed\. even people in possession of a land title for many years can still lose their land if the court rules in favor of a third party that successfully challenges the original claim to the land. 7.2 The decentralization of land management presupposes that there is adequate coordination between the sub-provincial agencies responsible for surveying, mapping and zoning; because not all aspects of land management can be self-financing, land management may be compromised if transfers from central government are erratic and insufficient. Despite the project's investment in local government capacity building, the National Land Agency was not sufficiently decentralized to facilitate collaboration with local institutions, and survey and mapping initiatives by these agencies were not harmonized, reducing the efficiency of spatial planning. This problem is aggravated by the underfunding of provincial and local levels of government.
P064729 | Sustainable Forestry Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2002 | 2011 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/383471474568991774/text/000020051-20140625060142.txt | http://documents.worldbank.org/curated/en/383471474568991774/pdf/000020051-20140625060142.pdf | The ICR includes the following lessons:Preparing and implementing projects with the close involvement of local governments increases the likelihood of attaining a sound and sustainable project outcome;If local governments (in this case, counties) are expected to provide counterpart funds, their capacity to do so needs to be carefully assessed during project preparation; andIEG adds the following lesson:It is probably not feasible to treat parallel-financed components as part of the same project as components financed by the Bank; parallel financiers invariably have different priorities and follow different procedures so that, if there are delays with this component, implementation of the project as a whole may be held up.
P064729 | Sustainable Forestry Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2002 | 2011 | 2012 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/103301468242639821/text/678820PPAR0P100C0disclosed070160120.txt | http://documents.worldbank.org/curated/en/103301468242639821/pdf/678820PPAR0P100C0disclosed070160120.pdf | 5. Lessons 5.1 This assessment of forest projects and AAA has highlighted the steps the Bank has taken to move beyond its (highly successful) engagement with plantation development in China. Renegotiating its support for forest interventions involves supporting new activities, and finding new interlocutors. The Bank has been more successful in the first of these switches than it has in the second. As the FY2010 Shandong Ecological Afforestation Project and the FY2010 Integrated Forestry Development Project have shown, the Bank is now seeking to involve local forest authorities, village leaders and farmers in the design of forest management plans that would ultimately take the place of the logging quota system, which lacks transparency and is unevenly enforced. This is the latest phase in the evolution of a more participatory approach to forestry that dates back to the FY98 Forestry Development in Poor Areas, assessed in this report. In addition, recent analytic work builds on the 2010 Forest AAA that was evaluated here. The FY2012 North East State Forest Reform Study aims to develop a roadmap for the State Forestry Administration, to support policy and institutional reforms in the management of state-owned forests in Northeast China, with a view to enhancing management efficiency, economic viability resource sustainability, and local livelihoods. Progress in the dialogue on policy reform will depend in no small measure on the Bank's ability to engage with new government agencies in China\. the State Forestry Administration's Project Management Center has proved to be a highly effective partner for plantation establishmentâ€”with a first-rate performance record, probably unparalleled in the worldâ€”but if the Bank is to broaden its engagement on forest interventions it needs to develop a dialogue with other interlocutors in addition to PMC. Since the sector work evaluated in this report was completed there is some evidence that the Bank's forestry team in China has diversified the scope of its engagement\. although continuing to work with the Project Management Center (specifically, on plantation establishment), the Bank is working with other departments in the State Forestry Administration and directly with provincial governments. 5.2 Based on the assessment of the projects and AAA in this report, IEG draws three lessons. 5.3 Even if poverty reduction is not an objective of the project, there is a sound case for monitoring and evaluation to measure project-driven changes in the incomes of beneficiaries because these are likely to influence the incentives for beneficiaries to consolidate project achievements. The Forestry Development in Poor Areas Project made provision for three household surveysâ€”baseline, midterm and final. These surveys were included in order to assess attainment of the outcome target of increasing incomes by 60 percent; and, more broadly, because poverty reduction was an explicit objective of the project. The Sustainable Forestry Development Project did not include poverty reduction or income enhancement in its objectives, and made no provision for household surveys. There was close monitoring of plantation establishment and, given the tight quality controls, there was good reason to infer that the incomes generated from this component would be substantial, creating an incentive for farmers to pursue the recommended tending and harvesting guidelines in order to maximize returns. However, unlike in the earlier project, there is no indication whether poorer households invested in plantations. More importantly, in the case of the protected area and natural forest management components, it was less certain that incentives were sufficient for communities to commit to conservation and sustainable forest management. These components included modest efforts to improve livelihoods and to boost incomes but in the absence of evidence from household surveys it is impossible to know whether the impact was big enough to generate the incentive needed to consolidate project gains in natural resource management. Given the steep rise in wages in China, labor devoted to (poorly remunerated) conservation activities carries a high opportunity cost, making it all the more important that projects have the monitoring and evaluation apparatus needed to measure livelihood changes and assess the level of incentives. 5.4 Until recently, the scope for the Bank to broaden its operational engagement with forest issues in China was limited by governments' insistence that, where IBRD funds are on-lent, producers and local governments must repay them with interest; central and provincial governments now recognize the public good nature of forests and are more willing to assume direct responsibility for repaying Bank loans that provide forest environmental services. Making loan recipients responsible for repayment 53 rewards solid performance but is hard to justify where there is no revenue stream to amortize debt obligationsâ€”that is, where loans are used to finance delivery of public goods. The â€•responsibility systemâ€– lends itself to the financing of commercial wood plantations but is harder to apply to conservation-oriented forestry and environmental protection. The experience from the projects assessed here shows that poorer counties and poorer farmers have difficulties meeting loan repayment obligations, partly because the government's enforcement of the logging ban and protection of natural forest and nature reserves reduces their sources of income. Excluding the poor from IBRD-funded projects is not desirable. Neither is it realistic to expect that grants will fully substitute for IBRD loans. (The Sustainable Forestry Development Project pushed in this direction, seeking to graft on a European Union grant to a World Bank project, with unsatisfactory consequences.) Had central and provincial governments not been willing to assume a larger share of the responsibility for paying back loans, it would have been difficult for agencies like the Bank to move away from financing commercial plantations. In recent years, government policy has evolved to emphasize the contribution of forest environmental services to China's development. The central government, and some provincial governments, are now willing to use Bank loans to support the provision of forest public goods through direct government budget expendituresâ€”rather than solely for on-lending to planting entities for forestry production activities. This trend is evident in the Bank-supported Shandong Afforestation Project and the proposed Hunan Forest Restoration and Development Project. 5.5 Parallel-financing by another donor is difficult to supervise if it is applied to a single component of a Bank-supported project, and may be best dealt with as a separate operation. The Bank used its convening power to elicit grant funds from the European Union for the natural forest management component of the Sustainable Forestry Development Project. This was a valid attempt to diversify the range of Bank engagement toward public good forestry, which the Chinese government was unwilling to finance on IBRD terms. The component was parallel-financed, not Co-financed, meaning that the European Union was in charge of supervising the component. At appraisal, the Bank stated that the two partners would cooperate closely, participating in each other's supervision missions. In practice, this failed to happen. Cooperation was limited, in part, because the Bank-supervised components were implemented by PMC while the EU component was implemented by a separate department of the State Forestry Administration. Moreover, the practice of the Chinese government has been to deal with each donor separately with no encouragement to collaboration between them. The poor performance of the consultant team fielded by the EU slowed down implementation of the component and, incidentally, delayed the closing of the overall project and pulled down the outcome rating. The potential for shared learning between the Bank and the EU was not realized.
P064730 | CN-Yangtze Dike Strengthening | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2000 | 2009 | 2010 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/339741474852063098/text/000146597-20140619164313.txt | http://documents.worldbank.org/curated/en/339741474852063098/pdf/000146597-20140619164313.pdf | The following are the main lessons from the project derived from the ICR lessons:Where applicable, Bank projects should be fully integrated into a country's larger program for a given sector. This way, unexpected changes (for example, cost savings) can be quickly and efficiently taken advantage of to improve overall sector performance. A programmatic approach allows improvements in areas that, even if originally outside the project design, nevertheless contribute to the achievement of the project objective(s).In situations where a project is likely to trigger potentially significant safeguard policies, incorporating them as full components can help ensure they are satisfactorily completed. In this instance, environmental and resettlement safeguards were included as distinct components, fully costed and financed, providing them a similar status as the other components.Robust cost estimates at appraisal can save time during implementation by recognizing early on where cost savings are possible, thus allowing the funds to be incorporated into project design prior to implementation. Significant cost savings were only recognized after appraisal and the components had to be revised.
P064821 | ROAD MAINTENANCE PROJECT | East Asia and Pacific | Lao People's Democratic Republic | IDA |  | Infrastructure | Transport | IDA | IPF | 2001 | 2005 | 2006 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/623571474566295427/text/000020051-20140613061028.txt | http://documents.worldbank.org/curated/en/623571474566295427/pdf/000020051-20140613061028.pdf | To make maintenance of road assets a priority, a paradigm shift in Government policy is required where the preservation of the existing network receives priority over its expansion. A passive approach to funding maintenance is less effective than a development of coherent framework/plan for maintenance financing.To discourage overloading and subsequent damage to road network, appropriate axle load legislation needs to be passed but the key to effective control of overloading is very good traffic law enforcement.The effectiveness of capacity building is greatly enhanced by strong internal leadership which encourages ownership and responsibility - this can sometimes be more effective than technical assistance.
P064836 | Tunisia Urban Water Supply | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2006 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/565031550845200310/text/Tunisia-TN-Urban-Water-Supply.txt | http://documents.worldbank.org/curated/en/565031550845200310/pdf/Tunisia-TN-Urban-Water-Supply.pdf | The ICR (pages 22-23) draws four lessons from the experience of implementing this project. Of these, the threemost important are, with some adaptation of language.(1)Outsourcingnon-core tasks forinfrastructure and designcan help in devising better cost-effective options. A lessonderived frompriorwater supply projects in Tunisia was the notion that outsourcingof SONEDEs noncore infrastructuretaskswouldaid in exposingSONEDEto new and better cost-effective technologyfor water treatment plants. Althoughthis lesson was identified at appraisal,the lesson was not heeded during implementation. Several of the delays, whicheventually led to cancellation of the tenders associated with rehabilitation of thetreatment plants planned under the AF,could be attributed to thelack of in-house expertise for keeping up with changes in technologies for water treatmentplants.(2) New technology and mobile payments can help in improving collection efficiency.In this project, SONEDE installed 93,000 classical water meters that could be read/monitored remotely, in the households that didnot have functioning meters. An independent technical audit in November 2017 showed a sharp increase in collection and therebycontributed to SONEDEs financial position.(3) Conducting customer satisfaction survey andbeneficiary assessmentscan help in improving service delivery. Although an indicator aimed at customer satisfactionsurveys was selected at appraisal, the surveys were not carried out during the project. Regular beneficiary assessment could helpthe national public utility improveits service deliveryby better understanding thecustomers needs andrespondto the needs of different categories of customers.
P064844 | Rural Electrification and Transmission Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2004 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/662641475079857227/text/000020051-20140625231137.txt | http://documents.worldbank.org/curated/en/662641475079857227/pdf/000020051-20140625231137.pdf | Adapted from the ICR:To bring private sector investments in renewable energy in rural areas, the basic policy and regulatory enabling environment needs to be complemented with carefully designed and well targeted financing support, technical assistance and capacity building.In designing solar home system programs for rural areas, the choice of appropriate system sizes based on robust up-front analysis, suitable delivery approaches, and post-installation operation and maintenance arrangements is likely to have a positive effect on the cost effectiveness and sustainability of solar home system programs.Support for developing, scaling up and sustaining productive use of electricity is highly likely to make a significant impact on the feasibility and viability of rural electrification investments.
P064853 | Private Sector Adjustment Loan (PSAL) | Europe and Central Asia | Romania | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 1999 | 2000 | 2004 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/210631468776360104/text/266870RO.txt | http://documents.worldbank.org/curated/en/210631468776360104/pdf/266870RO.pdf | 4. Lessons Learned IndustrialDevelopmentProject 4.1 Financialsector operationsshouldbeundertakenonly in a conducive macroeconomicenvironment-The unstable macroeconomic environment hinderedthe ability o fthe project to achieve its goals. The highand variable inflationgave economic actors an incentive to focus on protecting the value o f their assets andpay less attention to identifyingproductive investments. 4.2 For a projectwhose goal is to advancestructuraltransformationof the enterprisesector,a moresuitableinstrumentmighthavebeen an adjustment operation-The policy-related measures undertakenduringpreparation o fthe IDPwere a useful first step, but fell well short o f what would have beenneeded to achieve significant progress. An adjustment operation, with the transfer o fresources focused on 36. Also, as a matter of sequencing, increased energy prices were part of Fundconditionality, and it was logical to raise prices first, and subsequently tackle the privatization of electricity distribution companies. policy change, might have been a better choice. Ifmacroeconomic instability precluded an adjustmentoperation, a Technical Assistance loan mighthave beenutilized. 4.3 A financial sector operation must bebased on a realistic assessment of sectoral capacity and a judicious use o f appropriate and meaningful eligibility criteria for participating financial institutions-In utilizing PFIs as intermediaries, the IDP depended on them beingwell managed, with adequate financial strength, and with requisite loan appraisal and management skills. At the time o fproject inception (and until 1999), the Romanianfinancial sector was dominatedby state-owned banks that often channeled resources to loss-making SOEs and suffered from frequent Government intervention and a lack o fbasic bankingskills. Ina high-riskenvironment, the Bank clearly needs to go beyondminimally-recognized international levels for accreditation criteria and establish standards that assure that the banks selected have a solid track record of making good loans. 4.4 The size o f the line o f credit was too large given the risks and uncertainties of the macro and business environment-During project identification, manybanks and enterprises reported a need for term lending. However, the Bank paid insufficient attention to the turbulent economic conditions prevailing, and the lack o f motivation o f many enterprise managers to restructure their firms even after privatization. Onthe bankingside, the Bank didnot appreciate the disincentives to lendcausedbythe lack o f legal protection-including the absence of effective collateral (addressed by PSAL), weak capital bases, and the attractiveness o f short-term, high-yield instruments such as government debt. Private Sector Adjustment Loan 4.5 Timing and government commitment are critical to the success of an ambitious reform program-Several earlier efforts inthe area o f PSAL reforms hadnot succeeded. Macroeconomic and financial turmoil brought the government to understand that quick action was necessary ifa debacle, potentially including default, was to be avoided. This, along with the prospect o f EUaccession, provided much o f the political impetusfor PSAL success. 4.6 Ready access to technical assistance was key to project achievement-The PIBLprovidedresources by which PSAL staff could readily access international-level expertise inthe restructuring, privatization, and liquidation o fbothbanks and enterprises. Outside expertise was also mobilized to support the creation o f an asset resolution agency. And finally, expert advisors provided a great deal of input into the Action Plan to improvethe investmentclimate. 4.7 Collaboration among donors contributed to project success-The Bank worked closely with other donors, which resulted inthe transmission o f a consistent messageto the GOR. While there were occasionally differences inapproach or timing, these were generally minor, and effective collaboration with the Fund, EU, EBRD, bilateral donors, and FIAS played a role inproject success.
P064876 | Burundi Road Sector Development | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2004 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/123181468226746998/text/ICRR-Disclosable-P064876-06-21-2016-1466540605349.txt | http://documents.worldbank.org/curated/en/123181468226746998/pdf/ICRR-Disclosable-P064876-06-21-2016-1466540605349.pdf | IEG selected a number oflessons from the ICR, with some adaptation: For post-conflict affectedcountries, project objectives, designs, implementation arrangements, and ME should be simple and implementable. Inpost-conflict situations, helping the government to generate employment and rebuild infrastructure is generally among the keypriorities. Asthe governments capacity to rebuild the nation is usually low, the design and scope should focus onquick and easy implementation, with rapid and visible outputs. In post-conflict situations,substantive contingency funds should be included together with conservative cost assumptions. Under this project, costswere underestimated, which together with delaysled to significant cost overruns. An adequatetime frame should be given to implementinstitutional strengtheningagenda in post-conflict countries.Institutional reforms should be modest and realistic. This project duration doubled from five to more than ten years, however,without much accomplishedin improving thesector management andinstitutional capacity, as envisaged atappraisal.
P064879 | Irrigation Dam Safety | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 1999 | 2010 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/414131474630608025/text/000020051-20140626103643.txt | http://documents.worldbank.org/curated/en/414131474630608025/pdf/000020051-20140626103643.pdf | IEG offers the following lessons:Dam safety design requires both local knowledge and international experience. Objective assessment of dam safety is complicated and it needs a deep level of experience which most often can be provided by international experts. The complementary lesson from this project is that local knowledge and experience is also crucial. The ICR mentions the local knowledge that the low drawdown capacity of Armenian dams is a hazard. This was not mentioned in the PAD, nor reflected in the rehabilitation design for six dams in the 20 riskiest dams which were the core of this project. The potential value of a panel of independent dam safety experts should not be overlooked. A panel of independent dam safety experts would have been consistent with Bank Guidelines and might have identified the fundamental design problems that led to the near failure of the dam at Vardakar dam. This may have led to more urgent action to rectify the systematic drawdown problems in the other five dams.
P064883 | WESTERN ALTIPLANO NATURAL RESOURCES MANAGEMENT PROJECT | Latin America and Caribbean | Guatemala | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2003 | 2005 | 2006 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/421271474571659366/text/000020051-20140613061707.txt | http://documents.worldbank.org/curated/en/421271474571659366/pdf/000020051-20140613061707.pdf | The Bank should be cautious in approving projects within six months of a general election in countries experiencing political instability.
P064886 | SUSTAINABLE FORESTRY FOR RURAL DEVELOPMENT PROJECT | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2003 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/218111475115402580/text/ICRR14456-P064886.txt | http://documents.worldbank.org/curated/en/218111475115402580/pdf/ICRR14456-P064886.pdf | Lessons on Inclusion from the ICR. Projects that adopt an inclusive approach towards integrating ethnic groups, vulnerable persons, and women in project design require an understanding of pre-existing conceptions and attitudes around equity issues and associated investments in training and capacity building to achieve equity related goals. The SUFORD project adopted an inclusive approach and prioritized the participation of ethnic group communities, but translating these principles into practice was a challenge. Equity goals also need to be built into M&E design and monitored throughout the life cycle of the project. Gender related participation aims can be more effectively achieved if barriers to entry are diagnosed at appraisal and women's perceptions and ideas of how to overcome these barriers are incorporated into project design. In forest projects, women will have separate and unique perceptions about the design of sustainable forest management plans, in line with their household related income and food security needs. Gender related participation aims in forest and rural development programs can also have a greater chance of being achieved by prioritizing the recruitment of dedicated female staff and female advisors with extension skills and experience in working with women. Gender related impacts can be better understood by introducing gender-dissagregated tools such as gender budgeting and social auditing. The same applies for ethnic minorities and vulnerable groups.
P064886 | SUSTAINABLE FORESTRY FOR RURAL DEVELOPMENT PROJECT | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2003 | 2014 | 2018 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/239161528225963013/text/125929-PPAR-P163409-P064886-PUBLIC.txt | http://documents.worldbank.org/curated/en/239161528225963013/pdf/125929-PPAR-P163409-P064886-PUBLIC.pdf | Lessons 6.1 A pattern of weak government commitment to increasing citizen's natural resource rights exists in Lao PDR. This is the third IEG assessment in 15 years to highlight project failures associated with the Lao government's lack of commitment and limited transparency in administering land and natural resources. Borrower performance on the FOMACOP was rated unsatisfactory because The government was not consistently committed to policy reform or to supporting the innovative village forestry model (World Bank 2002, 26). An assessment of the Second Land Titling Project also rated government performance as unsatisfactory. It found that The government did not fully implement Decree 192, which called for adequate compensation to titleholders whose land was compulsorily purchased by the government. In this respect, government has not demonstrated its full commitment toward honoring the half million or so land titles issued under the two projects supported by the World Bank (IEG 2013, 35). In the case of SUFORD, various social assessments conducted by the project team found that attempts to include ethnic minorities in participatory planning and the sharing of benefits were less effective than the project design envisaged, an impression that was borne out by IEG's visits to seven project villages. 6.2 Villagers who are denied secure community tenure and rights to forest resources are unlikely to commit to sustainable forest management. Experience in other countries has shown that villages will have a genuine stake in sustainably managing forestland only when they own it (Segura Warnholtz et al. 2017). In Lao PDR, the law indicates that is the state that has sole ownership over the production forest. Villages whose boundaries extend into the production forest are given a right to be involved with management and to receive a share of the benefits, but the forest is not allocated to them. In the absence of a secure claim to production forest resources (including non-timber forest products) and without a steady stream of revenue from sustainable harvesting of timber, it will be hard to motivate villagers to engage in a participatory management schemeâ€”and even harder when the various levels of government inconsistently apply the principles of participatory management. 6.3 The zoning of natural forest may fail to reflect variations in the richness of the resource, so the area earmarked for sustainable management may be unrealistically large, stretching administrative resources too thin. In Lao PDR, the production forest area is a legal entity that overlaps with other forest entities and encompasses only part of the richest forest stock. The overlaps aggravate uncertainties about tenure. The large extent of the production forest area (all of which is to be covered by SUFORD-led management plans) creates an apparatus that provincial and district offices will not have the recurrent budget to administer effectively. In the absence of comprehensive data about the extent of the forest resourceâ€”including data on growth rates collected through the periodic inspection of permanent sample plotsâ€”it is difficult to develop a rational zoning strategy, or to make projections about the scope for sustainable harvesting. In response to political pressures, compared to FOMACOP, SUFORD offered a larger number of villages a potential claim to forest resources, which was problematic given the thinness of the resource. 6.4 Zoning and the preparation of management plans for specific forest tracts are important first steps but they are not, in themselves, sufficient evidence that sustainable forest management is being implemented. The completion of forest management plans for 1.3 million hectares that SUFORD sponsored was a significant step forward for a country with a weak record of forest governance. But the foundation that this provided has not been consolidated by follow-up monitoring of forest inventory. Unless they are complemented by ground truthing, involving the systematic resurvey of sample plots, the remote sensing data are insufficient proof of natural forest regeneration, because they don't capture what is going on under the canopy. Moreover, SUFORD acknowledges that the remote sensing data for 2005-2010 and 2005-2010 are unreliable. The OP and AF phases of SUFORD that this report assesses ended in 2012. Therefore, it is impossible to determine how much of the modest extension of the canopy that (more reliable) satellite data show occurred between 2010 and 2015 can be attributed to the first two phases. Now that the final phase (SUFORDâ€”Scale Up) is nearing completion the onus is on the government of Lao PDR to set up a system of monitoring of the forest resource based on the regular inspection of representative sample plots. Only then will the rate of forest regenerationâ€”and progress toward the national target of covering 70 percent of the territory with forestâ€”be reliably tracked.
P064887 | Natural Disaster Management Project | Latin America and Caribbean | Mexico | IBRD |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2001 | 2005 | 2006 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Satisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/808001474893404479/text/000020051-20140613065306.txt | http://documents.worldbank.org/curated/en/808001474893404479/pdf/000020051-20140613065306.pdf | Since very little occurred during the project's implementation phase, the lessons are derived primarily from what happened during the preparation phase, when most of the work was carried out.The Bank and Borrower need to improve their communications with each other and enhance their coordination efforts at the earliest phases of the project cycle. Establishing clear project objectives and identifying means to achieve those goals through project components are essential to project success, and both parties must agree and support them fully. When obstacles arise that threaten the implementation of those objectives and components, both parties must work together to find alternative solutions that they both find acceptable. Strong political support is key to the successful outcome of the project. Without strong ownership of the project at all levels of the government, it is unlikely that the project would be efficiently and effectively implemented.Changes in personnel often affect the project in a negative way. From the Borrower's perspective, the appointment of different individuals to take charge of the project may cause changes in government management of the project and lead to inter-unit rivalries. Such personnel changes may ultimately affect the degree of commitment to and ownership of the project, which in turn have a negative impact on project performance. From the Bank's perspective, cycling through four task managers negatively affected its relations with the Borrower, and consequently, weakened the Bank's leverage with the client.
P064895 | HN FIFTH SOCIAL INVESTMENT FUND PROJECT | Latin America and Caribbean | Honduras | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2006 | 2008 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/269891475094778646/text/000020051-20140615113244.txt | http://documents.worldbank.org/curated/en/269891475094778646/pdf/000020051-20140615113244.pdf | Two important lessons follow from the experience of the social fund:The recent IEG PPAR for the Third and Fourth Social Investment Fund projects pointed to the need to give serious attention to the maintenance of sub-projects constructed. The report noted that the maintenance issue goes beyond social funds and needs to be seriously addressed as a part of the overall policy dialogue of the Bank within the country. The experience of the Fifth project shows that while the project encouraged stronger coordination between municipalities, more needs to be done in clarifying and setting institutional rules to ensure that adequate funds are available and clear responsibilities are agreed among various actors. Going forward, there is a need for Bank management to ensure that adequate attention is given to this issue in the country dialogue so that the resources spent in subprojects under the social funds are able to meet the social and economic infrastructure needs of the country in the long term.There is a need for the Bank to ensure that much more attention is given to strengthening of financial management arrangements in social funds. IEG's recent evaluation of community based and driven development approaches noted the importance of finding ways to ensure fiduciary compliance in cases where small subprojects are implemented by hundreds of remote communities in scattered locations.
P064901 | Second Social Security Special Sector Adjustment Loan | Latin America and Caribbean | Brazil | IBRD |  | Human Development | Social Protection & Jobs | IBRD | DPF | 2000 | 2001 | 2002 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/751821474666294378/text/000020051-20140602113528.txt | http://documents.worldbank.org/curated/en/751821474666294378/pdf/000020051-20140602113528.pdf | (a) Successful pension reform required substantial dialogue, discussion and debate with local counterpart, policy makers and experts. (b) Successful pension reform should be seen as a long term process during which not all branches of Government will agree on actions proposed by the executive branch of government. Different legislative methods may be needed to final objectives.
P064906 | Poverty Reduction and Local Development Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2007 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/295151475071079740/text/Nicaragua-Poverty-Reduction-And-Local-Development-Project.txt | http://documents.worldbank.org/curated/en/295151475071079740/pdf/000020051-20140618081900.pdf | 1. Small Scale Social Investments should be complemented by Sectoral Strategies. In short, while constructing or repairing schools and health posts can increase access to social services, these activities alone are not sufficient to improving learning outcomes, or reducing child/maternal mortality and morbidity indicators. Complementary sectoral measures are required. 2. Bottom-up and demand driven initiatives can improve the quality and relevance of social and economic investments. However, Community Driven Development (CDD) activities must be integrated with local government programs rather than by-pass them in order to ensure long-term sustainability of the small scale social and economic investments carried out at the community level, provide enabling conditions for scaling up and prevent erosion of local capacity. 3. Decentralized program implementation is likely to work better when there is clarity among implementing actors on the design and the objectives, and with a clearly defined system with accountability mechanisms for each operational level. They should be implemented following the municipal, political and administrative calendars rather than central agencies and/or Ministries. 4. Building tools for impact evaluation into project design enables the testing of alternative mechanisms prior to scaling up.
P064913 | NATURAL DISASTER MITIGATION | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/892411474483739791/text/000020051-20140624213009.txt | http://documents.worldbank.org/curated/en/892411474483739791/pdf/000020051-20140624213009.pdf | The ICR provides several lessons, of which four are adapted and highlighted here.The subject matter of a disaster risk management project can span several sectors, and the project's impact can be enhanced by coordination with other relevant Bank projects or national programs. This project introduced organizational changes that promoted coordination and integration with other national initiatives in land administration, land-use planning, and sustainable natural resource management. By implementing processes for consulting with local organizations, a disaster risk management project can improve its relevance and effectiveness, particularly in social development aspects. This project's experience showed that local organizations generally have a better knowledge of the geography of the area, understanding of the populationâ€™s mindset, contacts with the local authorities, and a good grasp of the needs of the population. In most cases, the local organizations showed a remarkable sense of commitment toward the most vulnerable and poor.Crises provide opportunities to promote change, even if the environment for coordination and implementation is challenging. In this project, the post-Mitch situation - though an unfortunate event - focused the attention and improved the commitment of the the government and population to address organization changes and facilitate the improvement of the countryâ€™s disaster vulnerability and and disaster risk management capacity.
P064914 | Forests and Rural Productivity | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2004 | 2013 | 2013 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/485211475101323581/text/000020051-20140624192921.txt | http://documents.worldbank.org/curated/en/485211475101323581/pdf/000020051-20140624192921.pdf | The following lessons are adapted from those presented in the ICR:â€¢ Addressing poverty reduction and rural development through sustainable use of natural resources in a decentralized environment requires project design and implementation arrangements that are flexible enough to allow for learning and making adjustments to adapt to this learning. Sustaining project outcomes also requires attention to offsetting the fiscal impacts of the decentralized processes by ensuring a sustained source of income. In this case the projects support for modernization of the municipal cadastre system improved the financial capacity of the municipalities to invest in rural development and NRM initiatives. â€¢ Developing a decentralized and privatized extension system requires a combination of private and producer organization-based technical service providers. The former are needed where innovation and/or specialized services are required. The latter have the benefit of being decentralized already, and working with and through them builds local level capacity and creates the potential for more efficient expansion of the system locally, and across other crops and activities. â€¢ Consolidation of community enterprises and agro-forestry groups is a long-term commitment that requires continuity in strengthening social and human capital.â€¢ Land tenure regularization in national forest lands is a complex process that requires a strategy that includes inter-agency coordination, clarity of the methodological and legal framework as well as experienced and committed staff.
P064915 | Agricultural Technology & Rural Technical Education Project | Latin America and Caribbean | Nicaragua | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2005 | 2006 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/426191474650174681/text/000020051-20140613085105.txt | http://documents.worldbank.org/curated/en/426191474650174681/pdf/000020051-20140613085105.pdf | 1. There is a need to think strategically about the institutional arrangements for managing competitive funds. If an independent organization is to be established to manage the competitive process and the funds, there needs to be a reasonable assurance that future funds will be available after the initial injection (providing the use of the competitive grants is judged successful) in order to justify the initial costs of establishing the separate entity. 2. If a fund is part of an effort that is to give specific attention to disadvantaged groups (such as indigenous populations), then some special earmarking within the fund will be necessary to ensure that these groups gain access to some of the funds, given their lack of experience in preparing grant applications etc.. 3. Especially if the program is to focus particularly on disadvantaged groups or regions steps should be taken to ensure that adequate resources are provided to provide support to these groups in project preparation and review.
P064915 | Agricultural Technology & Rural Technical Education Project | Latin America and Caribbean | Nicaragua | IDA |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2000 | 2005 | 2009 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/277821468057286448/text/491490PPAR0p061fficial0Use0Only1pdf.txt | http://documents.worldbank.org/curated/en/277821468057286448/pdf/491490PPAR0p061fficial0Use0Only1pdf.pdf | 6. Conclusions and Lessons 6.1 An importantfinding o this four-project assessment is the lack o hard f f evidence about the results o competitivefund investments in research and extension. f In each o f these countries, agricultural productivity has risen since the mid 1990s, with growth increasingly based on intensification rather than area expansion. Potentially, the assessed projects contributed to this expansion. But, with the exception o f Peru, there i s no robust survey evidence linking productivity and income changes to the project interventions. Even in the case o f Peru there are doubts about which o f the steps in the results chain were most critical for achieving the increase in farm incomes. For example, extension services potentially have a role to play in the technology transfer chain but it i s unclear just how a critical a role. In each o f these four countries extension has withered on the vine; but from the evidence generated by these projects it i s impossible to conclude if this attrition i s truly significant-or whether, for example, tighter linkage o f farmers to producer associations i s an effective substitute. 6.2 With respect to the viability o f the competitive fund model, more study i s needed to compare the efficiency o f the model with the alternative-a single (public) supplier with fiinds directly assigned by government. There is a perception-stronger in Brazil and Colombia than in Peru and Nicaragua-that the competitive process has been managed in a way that i s both fair and transparent and has tended to raise the quality o f the research proposals that are approved for funding. But there i s no indication o f how costs per unit o f technology adopted vary between the competitive and the direct assignment approach. 6.3 Thefourprojects included in this assessment, and thefollow-on projects that have succeeded them, have generated substantial learning, both by the Bank and by the countries concerned. InNicaragua, there i s now greater realism about what can be achieved in a context o f weak institutions and high donor dependence. In Peru, the importance o f integrating the competitive fund approach with the broader public sector apparatus o f research and extension has been acknowledged; and the government's commitment to maintainingthe regional network o f INCAGRO bodes well for increased decentralization. In Colombia, the progress under the follow-on project in linking subprojects to commodity chains and increasing engagement with producer associations i s resulting ina more strategic allocation o f competitive fund resources that will help to enhance the country's agricultural competitiveness under the terms o f the new free trade agreement with the USA. In Brazil, the returns to increasing EMBRAPA'S connectedness with diverse research institutions, both within the country and beyond, have become f i l l y apparent. 6.4 The findings from this assessment suggest lessons o f broad relevance that are likely to apply beyond the four countries studied. A principal lesson concerns the importance o strengthening the capacity o research organizations, not just financing f f research. Competitive funds can be an important vehicle for research financing and have a strategic role to play in piloting new ways o f working, or focusing research on new topics; but they are most likely to make a sound and lasting contribution when they complement a relatively strong public-sector framework for research (in this respect, prospects were brighter to begin with in Brazil and Colombia than they were in Nicaragua and Peru). Public funding i s essential for agricultural innovation systems and private funding complements rather than substitutes for higher levels o f public funding 6.5 Second, to be able to compete, research institutions must have a minimum budget and a critical mass o staff-all f institutions need a portion o the budget that is f f f corefunded to cover costs o maintenance and upgrading o physical and human resource infrastructure. Competitive grants usually only fund operating costs; and the subprojects they finance have only 2-3 years' duration.' The sustainability o f the public sector research apparatus in general and the competitive funding model in particular depends on a continuing commitment o f government funds. The new model is unlikely to flourish in a climate o f fiscal austerity because there i s only limited scope for private funds to substitute for public money. 6.6 Third, the competitive fund model i s more likely to strengthenthe strongest agencies providing research and extension services than it is to reduce the disparities between the strong and the weak. Thus, in Brazil, the model strengthenedan agency that was pre-eminentto begin with. At the other extreme, in Nicaragua, the model was underfundedfrom the outset, i t s transformative capacity was limited by the weakness o f all the actors in the competitive arena, and the government provided little support to it. The principle o f competition between alternative service providers breaks down where the range o f providers i s limited (a problem at the municipal level and for small countries) and many o f the potential providers lack the skills needed to prepare viable sub-project proposals. 6.7 Fourth, the competitive model has not itselfled to a large growth in the role o f f the private GforprofiQ sector as a provider o agricultural research and extension; but it has contributed to the broaderprocess o private sector development. Compared to high- f income countries, in Brazil, Colombia, Nicaragua and Peru, commercial f i r m s have played a smaller role as providers relative to public and private nonprofit agencies. To the extent that commercial f i r m s have played a role, they have largely done so outside the framework o f competitive grant schemes; this i s the case, for example, for the partnership between EMBRAPA and the private multinational Monsanto for producing herbicide-tolerant soybeans2O n the other hand, under the competitive schemes, through the medium o f subproject Co-payments, producers have provided private funds as a complement to public sector grants; they have received training in the preparation o f business plans; and they have become more market-oriented owing to partnerships with producer associations that have been facilitated by competitive funding agreements. In this sense, the competitive fund model has contributed to the broader goal o f private sector development without entailing a major role for commercial f i r m s as service providers.
P064916 | Natural Disaster Vulnerability Reduction | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/216531474592967021/text/000020051-20140620065311.txt | http://documents.worldbank.org/curated/en/216531474592967021/pdf/000020051-20140620065311.pdf | 1. Disaster risk management is an important part of development strategy, particularly in highly disaster prone countries with high poverty rates.2. Economic measurement of benefits from avoiding the damages from natural disasters should be a regular part of the economic accounting of disaster-prone countries.3. A monitoring and evaluation framework that includes outcome indicators and specific targets is necessary to measure results.4. Low ownership and awareness in the community leads to poor maintenance, as the presence of trash and debris on the works sites showed in this case.Frequently, the community was not introduced to the works, nor invited to any process of public consultation.5. Establishing a culture of prevention takes time, and requires dedication and resources over multipleyears and activities. The project shows that a combination of analytical work (risk mapping)followed by a concrete action (mitigation works) is a good way to keep actors involved through afull project cycle.6. Clear roles and responsibilities should be assigned to the coordinating agency staff (in this case SE-SINAPRED) both in regular times and in times of crisis, to ensure there is enough capacity at headquarters at all times for prevention and mitigation purposes. 7.The Country Management Unit (CMU) at the Bank should monitor standards for PCU salaries according to the national levels and based on other institutions across Bank projects. This will diminish tensions that can emerge from internal and external equity problems among institutionsfunded by the Bank.
P064918 | Rural Productivity Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2007 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/807541473932629220/text/ICRR14943-P064918-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/807541473932629220/pdf/ICRR14943-P064918-Box396299B-PUBLIC.pdf | The ICR offers a number of lessons of which three are given here with some adjustment of language.1. Whether a Bank loan is blended with a GEF grant aimed at similar objectives is less important than ensuring synergies between the two projects. In this case, it would probably have been easier and less costly in terms of management to have blended the two but the two projects were still able to complement each other in strategy and in implementation.2. Follow-on operations should build on previous success and, where needed, consolidate that success. This also allows monitoring performance over a sustained period. In this case, selecting entirely new organizations increased the challenge and ignored the need for consolidation of the achievements of the earlier groups while making longer term sustainability monitoring more difficult..3. To be used efficiently and sustainably, revolving funds for producer associations need a minimum level of organizational strength and cohesiveness at association level. In this case, there was variability and it was clear that some producer organizations had reached a minimum threshold and some had not and will continue to face sustainability problems. Defining a minimum set of standards or milestones to achieve organizational thresholds may aid producer organization support decisions and ensure better sustainability.
P064919 | Judicial Modernization Project | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2003 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/674901474570479770/text/000020051-20140624213100.txt | http://documents.worldbank.org/curated/en/674901474570479770/pdf/000020051-20140624213100.pdf | The Review agrees with the ICR Lessons in general. It adds the following:A clear and prioritized action plan that supports achievement of strategic objectives is helpful. A project can then be designed as part of this action plan with realistic and phased objectives, and with implementing arrangements that are consistent with existing capacity. Pilot activities, such as establishing one or two integrated court models, which can then be used to demonstrate results of judicial reform can be effective in complex and low-capacity contexts.The selection of clear, relevant, economic, adequate, and monitorable indicators is important to understand project effectiveness. When initially-selected indicators are found to be inadequate or uneconomic, they should be revised in a timely manner.
P064921 | DZ-BUDGET SYST. MODERN. | Middle East and North Africa | Algeria | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/556101474483920218/text/000020051-20140620075210.txt | http://documents.worldbank.org/curated/en/556101474483920218/pdf/000020051-20140620075210.pdf | The project experience confirms the finding of IEGâ€™s Evaluation of Bank Support for Decentralization that a clear strategy, owned by the client, is essential before providing support for such complex and ambitious reform.A political economy analysis of who wins and who loses is important when there is wide resistance to reform and change.
P064925 | Support for Strategic Local Development and Investment Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/552851498140337429/text/ICRR-Disclosable-P064925-06-22-2017-1498140320850.txt | http://documents.worldbank.org/curated/en/552851498140337429/pdf/ICRR-Disclosable-P064925-06-22-2017-1498140320850.pdf | Three lessons were selected by IEG from a longer list provided in the ICR, with some adaptation of thelanguage: A highly volatile local political environmentmay have far reaching anddisruptive effects during project implementation that should be fully understood and factoredin design in order to mitigatethe impact. In the Philippines, local electionstake placeevery three years and usually result in changesin local administration as well as in composition of the local council. In turn, these changes often result in a) lack of supportto LGU loan proposals formally submitted by the previous leaders; b) another review by the new council of the proposal; c)inadequate supportof OM of completed subprojects. Possible measures include considering fully the 3-year political cyclein project design; providing incentives for LGUs to sustain support for the subprojects already in the pipeline of an LGU financeprogram, and streamlining and simplifying national government requirements on LGUborrowing. Pricing of sub-loans is critical to timely implementation of financialintermediary operations supported by the Bank. It should be transparent, flexible, andmarket driven. Special care is necessary during the design stage particularly in assessing competitiveness of pass--on ratesvis--vis other credit financing available toLGUs. In an environment where LGUs have more competitiveoptions,direct lending might not be suitable for financial intermediation toLGUs. Municipal ordinancesentail politicalprocesses (as they involve local councils with elected members) and can therefore be time consuming,however they are invaluable to improving sustainability and ensuring adequate OMof local services. Design can includetechnical assistanceinformulation of such ordinances, in facilitating the dialogue necessary to reach broad support to the proposed ordinance, and inimplementation of the ordinance.
P064926 | Health Sector Management | East Asia and Pacific | Samoa | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2001 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/723981475099845165/text/000020051-20140618063025.txt | http://documents.worldbank.org/curated/en/723981475099845165/pdf/000020051-20140618063025.pdf | Clearly stated, specific development objectives logically linked to readily measured outcome indicators with baselines are critical not only for project evaluation but also for effective project implementation; Particular attention should be given to interdependence and timing of project components, and appropriate measures should be taken to ensure that a delay in one component does not derail the entire project. In this case, substantial delays in completion of some components resulted in sequencing and component linkage problems; andPolitical and institutional analysis might have improved the prospects for timely policy change and legal reforms, particularly in a country and sector where the Bank has no experience.
P064961 | PUBLIC WORKS AND EMPLOYMENT CREATION PROJECT | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/176191474663958807/text/000020051-20140619082854.txt | http://documents.worldbank.org/curated/en/176191474663958807/pdf/000020051-20140619082854.pdf | The Bank ICR cites three lessons, all of which are related to the post-conflict situation that Burundi faced as it implemented this project. The delegated contract management arrangement for project implementation--initially through AGETIP and later through ABUTIP in this case--can be well suited to mitigating capacity constraints in a post-conflict environment. It can help obtain peace dividends through the swift implementation of programs while ensuring that basic fiduciary requirements are met. [IEG notes from the experience of this project that careful oversight and regulation of such agencies is necessary if they are to succeed in these functions.]Demand driven selection of subprojects through participatory arrangements with beneficiaries helps foster social cohesion in a country emerging from conflict. The rapid creation of short-term employment is valuable in a post conflict situation, where unemployment and poverty are especially high and quick adjustments, even if temporary, can help those most affected--war widows, ex-combatants, returnees and refugees--quickly adapt and reintegrate as country development resumes. The Borrower ICR brings two important additional lessons:The institutional framework of the project (and its M (ii) improving financial and accounts management; (iii) strengthening urban planning and maintenance of infrastructure; and (iv) better environmental management.Works contracts through externally financed project attract more bidder interest than contracts for similar works that are directly financed by the Government. Contractors surveyed at completion gave three reasons for this: (i) more confidence in the procurement process; (ii) payments are made more reliably; and (iii) better contract management, particularly through frequent monitoring and prompt management of conflict as they arise.
P064965 | RURAL SECTOR SUPPORT PROJECT | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2001 | 2008 | 2009 | ICRR | >=25 million & <50 million | Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/390391475096581511/text/000020051-20140619104620.txt | http://documents.worldbank.org/curated/en/390391475096581511/pdf/000020051-20140619104620.pdf | The ICR drew some useful lessons including the following (adapted):1. It is important to maintain a focus in project design on a manageable agenda within the capacity constraints of the borrower in the project.2. There is a need to build capacity related to safeguards in the project unit to ensure effective implementation of safeguards and a need for strong Bank support to assist the borrower in this area.3. It is important to have a consistent, coherent and straightforward M&E system articulated in the PAD with indicators clearly connected to the project objectives.4. More attention needs to be paid to the development of sustainable access to rural finance including capacity building with participating financial institutions and innovative product development to replace initial grants when depleted.
P064981 | Sana'a Basin Water Management Project | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2003 | 2010 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/568711474484799914/text/000020051-20140624193603.txt | http://documents.worldbank.org/curated/en/568711474484799914/pdf/000020051-20140624193603.pdf | The main lessons that can be drawn from the experience of this project are:Care should be taken to ensure that there is political commitment, not just to the physical investment dimensions of a project, but also to the more difficult legal and regulatory reforms needed to halt, and then to reverse, the depletion of a scarce, highly valuable, and diminishing natural resource.For a project in a politically and socially sensitive area, such as the water sector in Yemen, it is important to limit preparation time to the minimum necessary to assure good quality at entry, so as to reduce the risk of loss of political momentum for necessary reforms.Country dialogue, including IDA management intervention when appropriate, should be used at an early stage to resolve complex institutional issues with Government.Implementation of effective ground water governance requires strong commitment and support, not just of Government and its institutions, but of local stakeholders, especially water users. An approach involving greater reliance on community-based governance, backed by technical assistance and an adequate legal framework, may have been more successful than the top-down regulatory one adopted, but was not considered.Sufficient time and resources need to be invested to develop local understanding of the projectâ€™s objectives, as well as the willingness and the capacity of stakeholders to participate in its implementation.
P064983 | MORTGAGE FINANCE TECHNICAL ASSISTANCE PROJECT | Middle East and North Africa | Algeria | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2002 | 2007 | 2008 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/821771474586210766/text/000020051-20140618080102.txt | http://documents.worldbank.org/curated/en/821771474586210766/pdf/000020051-20140618080102.pdf | Teams designing and implementing a project should not rely only on the commitment of the main implementation agencies and make sure that all ministries involved in the project are committed and actively participate in the implementation through a steering committee set-up at an appropriate policy decision-making level and sufficiently inclusive. This was not the case for the steering committee envisaged in the PAD. In any case, this steering committee was not put in place as envisaged. Instead an inter-ministerial committee was set-up, at the end of the project, to ensure participation and cooperation between different ministries but it was too late to have the intended catalyzing effect.
P064983 | MORTGAGE FINANCE TECHNICAL ASSISTANCE PROJECT | Middle East and North Africa | Algeria | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2002 | 2007 | 2010 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/713801468052844398/text/554270PPAR0Box1ficial0Use0Only01061.txt | http://documents.worldbank.org/curated/en/713801468052844398/pdf/554270PPAR0Box1ficial0Use0Only01061.pdf | 4. Conclusions and Lessons 4.1 Both Algeria and Morocco are committed to housing sector reforms, although each country finds itself at a different stage of reform; Algeria seeding it and Morocco sustaining it. The 2003-2008 period under review was a good time for housing sector reform. Economic growth of both countries was buoyant. Reform was needed because of the inadequacies of the existing housing stocks, particularly overcrowded dwellings and poorly constructed units especially in the bidonvilles. Good quality formal houses are in short supply, making them very expensive and inaccessible to the poor especially. Key reform themes that arise from this context include housing finance, slum upgrading and institutional consolidation. All three of the Bank-supported operations addressed one or more of these themes. Thus the Algeria Mortgage TA Project planted some seeds of housing finance reform by helping the banks manage mortgage lending and bringing greater confidence to property titles and their registration. But these were not enough for the mortgage market to function well and at scale as intended, simply because supply-side constraints meant that there were few houses to finance. The connection of Morocco's Housing DPL and the Slum Upgrading PSIA to GOM's Villes sans Bidonvilles Program was a sure way of harnessing these operations to ongoing housing sector reform in the country. It was a two-way interaction with reasonably good results. The operations supporting the reforms underway, and the reforms themselves, particularly the large scale VSB and Al Ornrane consolidation, conferred an importance upon the operations that they otherwise would not have enjoyed in the country. 4.2 Bank support came in the form of three different instruments, a SIL, a DPL and a PSIA. Although the performance across them varied, a variance that had more to do with the housing sector reform context in which they were implemented than the type of instrument used. The experience of these operations demonstrates that reform can be supported by many different types of instruments. The chances of success will depend more upon the local commitment to reform and the diagnosis of it, than the choice of instrument itself. 4.3 The PPAR draws key lessons from the performance of these operations around the three key issues highlighted in the main text of this report, as well as others deriving from the broader assessment of performance summarized in the Annexes. As the operational experience in Algeria and Morocco were so different, the lessons are grouped separately for each country. ALGERIA o Seeding housing reform by focusing upon a selected bottlenecks-such as in bank processing of mortgage loans and in the registration of property titles---cannot guarantee that the reform will take root. Even if they constitute necessary conditions for reform, they must be calibrated with other actions-to ease the supply of new housing, for example-to achieve the well-functioning markets promised by the housing sector reform. o When sector reform is embryonic, support at the early stages needs to concentrate on the most basic and urgent changes and improvements. In the case of the Algeria, this means focusing first upon strengthening the primary mortgage market. This has to be well established before reform can move on to consider more sophisticated instruments of housing finance, such as mortgage insurance and securitization. The latter did not take root in the Algerian case. o Housing sector reforms need to be calibrated and synchronized in order to succeed. In Algeria, improving the origination and processing of mortgage loans went ahead even though demand for such loans was weak. In such cases, reform measures might need to be scaled back or delayed. o The success (or failure) of housing sector reform requires readily available data and information to demonstrate the results of reported changes and to measure the baselines prior to these changes. The lending and other operations that support the reform can themselves support and include actions to encourage greater dissemination of data and information upon their sector. MOROCCO o Policies and programs aimed at achieving cities without slums need to treat slums as a dynamic feature of urban development. Without appropriate urban planning and land use controls, the formation of new slums can overwhelm the achievements of upgrading and redeveloping existing ones. o For housing reform to be sustained, it is important to modernize and consolidate the institutional framework for taking the reform forward through a powerful and financially sound agency such as A Z Omrane that enjoys hi1 government support. o A sector policy loan can perform well and help achieve reforms if it has realistic objectives that focus upon pursuing a few well-chosen prior actions and triggers, as was the case of the Morocco Housing DPL. o Sector reform is more likely to succeed if harnessed to a flagship program that is well understood by all stakeholders and beneficiaries, such as the VSB Program in Morocco.
P065035 | Gansu and Xinjiang Pastoral Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2004 | 2010 | 2012 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/270621474488693161/text/000020051-20140625053938.txt | http://documents.worldbank.org/curated/en/270621474488693161/pdf/000020051-20140625053938.pdf | The ICR offers a number of lessons of which the following are the most important ( with some adjustment of language):1. A project with wide coverage exacerbated by complex design overlaid with multiple productivity, income and environmental objectives, while useful in principle for a holistic approach, in practice presents a heavy burden for project management and supervision and runs the risk that, in implementation, some subcomponents will be given priority by the borrower and others neglected. 2. There are risks in project design and implementation in the inflexible application of production models and associated prescriptions specified in advance due to changing prices and market demand and crowding out by alternative financing. Project design needs to be flexible and nimble to accommodate such changes.3. Investments in public good supporting services such as livestock breeding improvement, veterinary services and artificial insemination services can be very effective in enhancing livestock productivity and in benefiting large numbers of poor farmers/herders.4. For effective M& E, indicators, baseline data and responsibility for data collection and analysis should be clearly defined at project appraisal.
P065041 | Trade & Transport Facilitation in Southeast Europe Project (TTFSE) | Europe and Central Asia | Romania | IBRD |  | Infrastructure | Transport | IBRD | IPF | 2000 | 2004 | 2006 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/428561474909018849/text/000020051-20140613065350.txt | http://documents.worldbank.org/curated/en/428561474909018849/pdf/000020051-20140613065350.pdf | In a multi-sectoral and multi-agency activity, active participation and cooperation among the sectors and agencies is essential for successful implementation and achievement of project objectives.Effort put into developing measurable indicators and the means to collect data, can pay off in keeping the focus on results, and improving the chances for the success of a project.The borrower should ensure that new policies and legislation do not inadvertently result in adverse institutional changes for projects under implementation.
P065059 | Krakow Energy Efficiency Project | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2001 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/688691474549871966/text/000146597-20140619161805.txt | http://documents.worldbank.org/curated/en/688691474549871966/pdf/000146597-20140619161805.pdf | When lending to reform energy utilities, the Bank should focus on the capacity of the borrower to be flexible and entrepreneurial when appraising a project whose success depends on business skills and the ability to tap new markets. The Bank should appraise carefully if the right type of people will be available to spearhead this new business model and if not, how such skills and commercial attitudes can be brought into the project.When lending to a borrower that will enter an unfamiliar market, loan planning should focus on defining risks, mitigation strategies, and provision of adequate liquidity to cover likely contingencies. Since the opening of new Energy Service Company markets requires changes in the thinking of many stakeholders, the Bank should provide direct technical assistance to diverse project participants beyond just the borrower. For example, support is needed to establish an association of energy efficiency contractors to facilitate the transactions between governments, clients and the industry. At the early stages of establishing Energy Service Companies, effective marketing, public relations strategies, and promotion campaigns need to be formulated and implemented.
P065111 | Port Cities Development Program | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2003 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/251451474484819088/text/000020051-20140624195038.txt | http://documents.worldbank.org/curated/en/251451474484819088/pdf/000020051-20140624195038.pdf | The ICR draws a number of relevant lessons, namely:(a) The importance of understanding and taking account of the political economy of a country when designing a project or program (b) National level and local level reforms are difficult to combine over a short period of time and hence sequencing starting with the national level is indicated. This lesson is related to the risk associated with strengthening institutions "from the bottom up".(c) Strategies and investment plans need to be informed by appropriate and analytically rigorous consultations with stakeholders.Two other lessons could have been drawn from this project::(d) The frequently cited importance of keeping projects simple. In this case, the numerous studies, strategies and plans were difficult to procure and implement on time. As a result, their impact can as yet not be assessed. Ensuring agreement on terms of reference for studies at appraisal would probably have reduced the procurement time considerably.(e) The absence of a beneficiary assessment (as in this project) makes it very difficult to assess project benefits from the beneficiaries' viewpoint.
P065113 | PH-SOCIAL EXPENDITURE MGMT | East Asia and Pacific | Philippines | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2000 | 2004 | 2005 | ICRR | >=50 million & <100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/274071474506063519/text/000020051-20140612144432.txt | http://documents.worldbank.org/curated/en/274071474506063519/pdf/000020051-20140612144432.pdf | (i) The importance of shared vision of institutional reforms and high level commitment and strong ownership of reforms among key policy makers: there was strong commitment from management of the implementation agencies and ownership for the reforms within the departments. This commitment permeated to the lower levels of the department.(iii) The advantage of aligning of objectives of the project with the goals of the agencies involved: In 1999, DBM which is responsible for managing the budget, public sector compensation policy and organizational management was initiating a government-wide public expenditure management improvement program at the time the project design was developed. At the same time, Commission on Audit (COA) which issues accounting rules and regulation in addition to conducting financial audit was beginning to conduct value for money audits and working with civil society groups on participatory audits. The focus of these two agencies were improvements in financial management and reporting, increased accountability and efficiency in budget execution, and improved public sector performance in all government agencies and departments were clearly aligned with the objective of the project.(iv) The role of civil society and community involvement: civil society and community involvement through the joint monitoring of the school building program, the increased role of Parent Teacher's Community Associations (PTCAs) in the rehabilitation of schools, the civil society monitoring of the delivery of textbooks was crucial in improving civil society opinions about the government processes. Prior to the project, allegations of graft and corruption in procurement in the social sectors had created a sense of distrust among civil society.(v) The role of reform at the center to support change at local level: many of the reforms initiated under the project were done at the central level except for the principal-led management of construction and repairs and maintenance. Sequencing of reforms is however crucial to its success. Strengthening central departments was the first step in these reforms. Subsequent steps need to be taken to ensure that regional and division offices of the agencies benefit from these reforms. Under the project, much of the procurement was centralized. While large gains in cost savings were realized, there are potential gains in efficiency that could be achieved through regional procurement of school furniture, for example. The subsequent stages of procurement reform would need to test the efficiency gains of decentralizing some of the procurement.
P065126 | Health Sector Support Project | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2005 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/331471475116164599/text/000012394-20150312070826.txt | http://documents.worldbank.org/curated/en/331471475116164599/pdf/000012394-20150312070826.pdf | Lessons drawn from the ICR (pp. 37-38):Risk assessment has to be internalized in project design. While overall risk was rated as high, the components of this rating were underestimated and the mitigation measures were insufficient. A more rigorous assessment might have concluded that: (i) significant risks (political, socio-cultural, technical, and financial) existed; and (ii) the feasibility of completing the project as designed was questionable. There is a need to temper expectations that a single health project can impact the entire health sector. Political leadership and financial commitment by the Government are needed for sectoral change. Inadequate sector financing, as well as shortage and poor distribution of health personnel, remain issues in Guinea that can only be tackled with increased Government spending for the sector. This is all the more important in the context of the introduction of a results based financing approach to strengthen the sectorâ€™s focus on results towards improved availability and quality of health services.Monitoring and evaluation can be improved throughout the project. Projects can recover from inadequate M&E design. While the timing of the DHS (in 2005 and 2012) was fortuitous for evaluating the project, the projectâ€™s sustained efforts to establish the annual HMIS reports (2007-2013) and reconstruct project data for the entire period were essential in providing an evidentiary trail for the project.
P065127 | National Rural Infrastructure Project | Western and Central Africa | Guinea | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2005 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/962951475112462593/text/000012394-20150108150811.txt | http://documents.worldbank.org/curated/en/962951475112462593/pdf/000012394-20150108150811.pdf | The IEG review endorses a number of lessons identified in the ICR and summarized below: (i) Choice and readiness of the implementing agency: A well-functioning implementing agency for the project is a critical factor to ensure success. In the case of the project, this risk should have been mitigated as part of the preparation process, even if it would have resulted in a delay in project approval. In particular, earlier training program should have been put in place for project key staff.(ii) Importance of ownership of project activities: The labor intensive maintenance components had strong ownership by project beneficiaries and the targeted length was entirely executed. This is because the beneficiaries of this particular component and local contractors worked together to ensure the implementation of labor intensive maintenance works.(iii) Existence of Contractorsâ€™ capacities is a key element of project success: The project scope and type (rural roads) required works to be executed by small contractors over a large geographic area. For this to happen in better conditions, the capacities of the local SME contracting industry should have been assessed and the works planned accordingly. In addition, the geographical location of works should have been a parameter for the package of contracts to facilitate implementation by small contractors and follow up by administration and supervision firms.(iv) Proper costing of project components/activities is a requirement to achieve PDOs: The project included an indicator on road maintenance while the project did not support this activity directly since it did not provide funding to the Road Maintenance Fund. This means that there is need for a careful selection of indicators and a need to ensure that sufficient leverage exists at the project level for some indicators and reforms.
P065128 | SAC IV | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2002 | 2002 | 2003 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/350191474595578778/text/000020051-20140607172639.txt | http://documents.worldbank.org/curated/en/350191474595578778/pdf/000020051-20140607172639.pdf | 1. A strategy in SAC IV to strengthen the entire governance system of public resources, i.e., budgetary oversight and accountability was important to ensure effective management of resources; it was more effective than a strategy narrowly targeted to civil service reforms would have been. 2. A strategy to promote broad consultation and good communication builds consensus for budgetary reforms. Such a strategy is also essential for public enterprise reform. 3. When an adjustment operation is fourth in a series of loans, the task of justification is more demanding, especially if it targets areas where the Bank has been active for 15 years. The documents (President's Report, ICR) should explain what earlier projects tried to achieve, what they did achieve and failed to achieve, and what could be expected from the new operation. 4. The adjustment operation should provide concrete performance indicators and a monitoring plan to assess whether its core objective of improving service delivery was achieved.
P065128 | SAC IV | Western and Central Africa | Guinea | IDA |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2002 | 2002 | 2004 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/729991468751529556/text/27166.txt | http://documents.worldbank.org/curated/en/729991468751529556/pdf/27166.pdf | 7. Key Lessons Learned\n7.1 Undertake a Solid Economic and Sector Work Program. A well-conceived\nand carefully executedprogram of economic work is essential to underpin policy lending\noperations. During the period under review the only economic report issued was the 1990\nCEM. Both the financial sector and the public expenditure reviews remained in draft\nstage and are not generally accessible.\n\n7.2 Focus Policy Reform on a Few Key Areas with Monitorable Performance\nIndicators. While numerous aspects of economic management need improvement,\ncapacity limitations require a focus on the most important areas where there is\ndemonstrated commitment from the authorities and a capacity to deliver. Rather than\nciting assertions of good intentions, tranche release conditions should focus on actual\nperformance outcomes, as assessed by readily available, time-bound, monitorable, and\nobjectively verifiable performance indicators.\n\n7.3 In the Presence of Persistent Fiscal Deficits, Address both Fiscal Revenue\nMobilization as well as Expenditure Procedure Issues.\n\n7.4 Underpin Civil Service Reform Efforts with Upstream Work. It would have been\nuseful to have had the civil service reforms underpinned by analytical work and a clearer\nagreement with and commitment from the highest level of the government on the goals,\nand the likely outcomes of civil service reform.\n\n7.5 Reserve Single Tranche Credits Onlyfor Governments with an Established Track\nRecord of Good Policy Reform Performance. Given the experience with one-tranche\noperations, the region should carefully assess how a series of one-tranche PRSCs can be\nstructured to ensure that key objectives are achieved and to manage the risk, given the\nexisting governance situation in Guinea.\n\n7.6 Ensure Proper Identification o f Resource Gap. Resource gaps can be exaggerated\nto get the attention of external donors and to serve to mobilize additional external\nresources. IDA should carefully ascertain that the resource gaps are based on a realistic\nassessment of ownership and effective implementation capacity.\n\n7.7 Ensure Continuity of IDA Stafl Management should plan for and manage rotation\nand turnover in a manner which is not disruptive to IDA\'s operations and client relations.\n\n7.8 Forewarn of Unsustainable IDA Risk Exposure. In the period encompassed by\nthis Review, IDA substantially increased its portfolio exposure in Guinea, shifting from\nbeing one of the smaller external creditors to the principal official external creditor. The\nconsequence was a major increase in IDA\'s risk exposure, a phenomenon which was not\nadequately assessed and communicated to IDA Management and the Board in a timely\nmanner. Despite its rising exposure as an official external creditor, IDA did not give\nsufficient consideration to the likely sustainable external debt burden for the country. It\nalso did not discuss the implications of sending to the Board relatively large lending\noperations that were increasing the debt burden. IDA did not identify or formulate the\n\x0c 27\n\ntrigger for an exit or the orderly reduction in its risk exposure. This culminated in the\ncountry requiring access to HIPC debt relief. Procedures for orderly reduction of IDA\nrisk exposure deserve more carehl attention. An adequate assessment of\ncreditworthiness of the country in the face of a rising and likely unsustainable debt\nburden could have provided the analytical underpinning for properly providing loan loss\nreserves for IDA'Sexpanding Guinean portfolio.
P065129 | GN-Village Comm Supp Program - Phase 2 | Western and Central Africa | Guinea | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/707531467989511177/text/ICRR14913-ICRR-PUBLIC-P065129-Box396265B.txt | http://documents.worldbank.org/curated/en/707531467989511177/pdf/ICRR14913-ICRR-PUBLIC-P065129-Box396265B.pdf | The following most important lessons from this project suggested by the ICR are summarized below - with some editorial adjustments.Participatory budgeting, monitoring and evaluation mechanisms at community level ensure real ownership of community development and empower communities. When communities are given the requisite tools and empowered through subsidiarity to participate in budgeting and monitoring and evaluating progress at the community level, they can address many of their own development issues.Decentralized institutions for planning and implementing community activities do not necessarily mean that a decentralization policy will be adopted in the various sectors of the economy. Hence good practice is to define, develop, and implement - in a progressive and participatory manner - a sector-by-sector decentralized action plan that results in an integrated and coherent strategy for transferring skills and competencies from the center to the decentralized institutions. Increasing the tax revenues available to the municipal level institutions is not simply the result of establishing market infrastructure or implementing income-generating activities; it also depends on the development of civil society and good governance at the local level. Good governance of tax returns will result in citizens becoming more involved in and committed to local tax and non-tax resource mobilization.This Review suggests the following additional lessonsGood governance is crucial for successful project implementation and can overcome periodic political instability. This project showed that even under the stress of political instability a government can make important decisions that are within its powers.Well planned and intensive training programs can have significant positive impacts on the competence of governments. However, training programs need to be systematically evaluated to ensure their relevance and the sustainability of benefits.
P065163 | Structural Adjustment Credit 3 | Europe and Central Asia | Moldova | IBRD |  | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2002 | 2004 | 2004 | ICRR | Less than 10 million | Unsatisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/802901475083635660/text/000020051-20140612105346.txt | http://documents.worldbank.org/curated/en/802901475083635660/pdf/000020051-20140612105346.pdf | 1. The need for adequate appreciation of political economy of proposed reforms is essential. Adjustment loans in risky situations should be multi-tranched and not frontloaded. The three tranche formulation of this loan was an appropriate risk mitigation strategy. 2. With unsatisfactory performance, terminating an operation rather than giving extensions sends a clear message to the government, which sets a firm basis for the future country assistance strategy.
P065188 | Export Finance Intermediation Loan (EFIL) | Europe and Central Asia | Turkiye | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2000 | 2004 | 2004 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/691631474649318397/text/000020051-20140612104039.txt | http://documents.worldbank.org/curated/en/691631474649318397/pdf/000020051-20140612104039.pdf | 1. Excessively controlled procurement requirements unsuitable for private sector borrowers, and the World Bankâ€™s previous currency pool loan features proved to be a hindrance to expeditious project implementation in other credit lines, so in this case commercial practices for procurement and a single currency loan (SCL) feature were used, which helped to smooth subloan implementation and disbursement arrangements. 2. It makes sense to combine the Borrower and Implementing Agency functions into one and the same entity -- Eximbank in this case and to lend directly to it, once the due diligence tests were met. There was no need to lend to the Treasury and have it on-lend the funds. The project design was straightforward and efficient
P065189 | Structural Adjustment Credit 4 (SAC 4) | Europe and Central Asia | Armenia | IBRD |  | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2001 | 2003 | 2004 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/294081474898353937/text/000020051-20140612092711.txt | http://documents.worldbank.org/curated/en/294081474898353937/pdf/000020051-20140612092711.pdf | Adjustment credits that specify minimum budgetary allocations to the social sectors have the effect of increasing their share of scarce budget resourcesTechnical Assistance--from the SATAC 2 project as well as from other donors--was critical to the achievement of reforms
P065200 | Indigenous Management of Protected Areas in the Peruvian Amazon (GEF) Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2001 | 2007 | 2008 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/816261475079774856/text/000020051-20140618082638.txt | http://documents.worldbank.org/curated/en/816261475079774856/pdf/000020051-20140618082638.pdf | Participatory Conservation Models that combine conventional conservation with an indigenous conception of protected areas require intensive up-front organizational planning and close supervision, but co-management schemes have a vast potential to bring about fair, negotiated agreements on management roles, rights and responsibilities that support sound decentralized governance and long-term conservation efforts. Organizational arrangements that may be considered include representative steering committees to help guide area categorization and advisory bodies with both indigenous and local population representation. Participation in categorization and management planning are key facets to setting up a successful negotiated scheme. Lessons still need to be learned however about the outcomes of issuing communal land titles in and around communal reserve systems, in terms of rights over resource extraction and the generation and distribution of incomes and benefits that are able to be derived from the communal reserve system. Co-management schemes arranged between different stakeholder groups in and around protected areas can promote intercultural dialogue and may even serve to stave off future land and resource conflicts. The World Bank can assume the role of a neutral mediator between indigenous groups, other stakeholders, and the local and national government.
P065256 | PE NATIONAL RURAL WATER SUPPLY AND SANITATION PROJECT | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2003 | 2013 | 2015 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/836991475115970411/text/000020051-20150113011221.txt | http://documents.worldbank.org/curated/en/836991475115970411/pdf/000020051-20150113011221.pdf | IEG summary of broad ICR lessons for the sector in Peru:Accelerating water and sanitation services in Peru requires a common strategy and the simplification of the countryâ€™s complex administrative processes. The emergence of Peru's National Growth Strategy, for instance, required extending the project area with a consequent increase in costs as subprojects became more dispersed. Cumbersome administrative procedures and supply of other state programs without cofinancing, were serious obstacles to the project implementation of this project.Scaling up the provision of rural water supply and sanitation services in Peru requires a more decentralized approach to planning, executing and monitoring projects with the continued support by a strong center. Building capacity at the Municipal District level to implement project activities and works would probably be efficient, although may not be applicable in all regions because of local capacity constraints. These need to be assessed in all cases to determine how much decentralization is possible. The Technical Management Units in this project's participating municipalities are one way of improving the model.Constraints to possible counterpart funding by municipalities and contributions by communities require careful attention at appraisal and be fed realistically into project design. Optimistic expectations raised during project preparation may not always be realized during implementation. In the case of this project, many municipalities had insufficient budgetary resources to be eligible to participate, and the Bank did not accept alternative sources (from regional governments, for example). Rising incomes in general, as was the case with this project's beneficiaries, can raise their opportunity costs of providing unskilled labor at no charge to the project. Without a careful assessment up front project inputs from these sources may have to be curtailed, as the scope of a project itself.- IEG summary of ICR lesson at the project level:Improving public health benefits requires a project that involves several sectors. The health benefits of this project were negligible, as demonstrated by data at completion showing no reduction in the incidence of diarrhea with under-fives and no improvement in hand washing practices among mothers. This experience shows that it is important to sustain hygiene education with continuous training of frontline workers throughout project implementation and beyond through the health and education sectors, local governments, and the private sector- other lessons drawn by IEG:Project preparation and appraisal of investment operations should ensure that a project is compatible with country conditions and can work successfully in those conditions. Among other things, this requires a thorough appraisal of the financial and institutional resources available to the project as well as the commitment and ability of in-country stakeholders to achieving the agreed objectives. A major shortcoming in the case of this project was that the appraisal estimated unit costs that were only 20-25 percent of the actual costs incurred. Subsequent cost re-estimates required project restructuring, caused considerable implementation delays, and confirmed the considerable reduction in the project scope from what had been originally intended, truncating the total beneficiaries to 250,000 from the appraisal's 615,000.Project appraisal documents should routinely report the basic parameters used to estimate project costs. If PAD cost tables provide summary details--such as the cost elements included, the number of beneficiaries, unit costs and their benchmarks--any errors can be more easily picked up by internal reviews during appraisal. If not by then, they can be picked up early in implementation so that necessary and appropriate corrections can be made quickly to avoid some of the protracted delays and loss of efficiency suffered by this operation. .Project identification and preparation by the Bank should always include careful assessments of Borrower capacity and commitments. In the case of this project, neither were accurately assessed, with the result that a mixture of inability and unwillingness of the part of some Borrower agencies undermined the implementation and achievements of the operation. Project design by the Bank should not consciously create hurdles for even a strongly able and committed Borrower to overcome, as occurred in this project.Additional financing should not routinely be used to cover cost overruns. If used indiscriminately in this way, AF can, like taxation amnesties, provide a perverse incentive for the Bank and Borrower to underestimate costs at appraisal and throughout implementation if they know that shortfalls of funding will be covered by AF. The AF Project Paper's argument in the case of this project, that the AF is "mainly justified by increases in the cost of the interventions" (AF-PP p. 18) might be misunderstood as being a casual approach by the Bank to errors occurring during project preparation. Rigorous project preparation should leave no space for ambiguity, as was the case in this project, where it remains unclear whether the costs actually increased during the eleven years of implementation or were simply understated at appraisal.
P065256 | PE NATIONAL RURAL WATER SUPPLY AND SANITATION PROJECT | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2003 | 2013 | 2016 | PPAR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/738531469435204573/text/106723-ppar-P008051-P065256-PUBLIC-peru-0716.txt | http://documents.worldbank.org/curated/en/738531469435204573/pdf/106723-ppar-P008051-P065256-PUBLIC-peru-0716.pdf | 4. Lessons Learned Lessons A strong focus on project outcomes and adequate accountability mechanisms are key factors to the achievement of significant improvements in service provision. The project's design focused on performance and outcomes, and provided for a management contract between SEDAPAL and the line ministry with annual performance targets, with arrangements for institutional capacity development, performance-linked financial incentives, accompanied by effective monitoring. Efforts to replicate successful experiences from other contexts must carefully take into account the receptivity of the implementing institutions and beneficiaries. The pilot effort to bring low-cost condominial networks to low-income peri-urban areas yielded limited results and was eventually discontinued due to insufficient social acceptance, the preference of beneficiaries for conventional networks, and the reluctance of SEDAPAL and contractors to depart from conventional network norms and methods. In retrospect, the receptivity of both beneficiaries as well as SEDAPAL and the contractors was not adequately gauged. Resource conservation techniques can yield quick benefits to liberate water resources for new clients. The project provides a successful example of the comprehensive and synchronized application of demand and supply management techniques to liberate water resources. These made it possible to simultaneously achieve improved coverage and continuity of service in what had been, before the project, a heavily constrained resource that was widely rationed. It also provides a powerful illustration of the potential magnitude of customer response by sending economic signals through the pricing of water. Project design needs to address gaps and weaknesses in sector institutions and governance identified during project preparation, failing which the risk to achieving project outcomes and timely implementation is much increased. In this project, the World Bank made an adequate diagnosis of the sector institutions, but failed to make significant provisions to deal with them, thus affecting project implementation. The modalities of cost-sharing and community participation need to be adapted to the local context and supplementary resources made available as needed. Many municipalities did not have significant budgetary resources to participate in the project. In addition, over time, rural communities became less inclined to contribute free labor or local materials as other economic opportunities opened up. This affected contractor interest and affected overall project progress. In such situations, alternative means should be sought to fill the resource gap. Community participation in planning and operations underpins sustainability, but adequate training support, financial incentives, and contractual arrangements are necessary for continued and effective participation. The community water and sanitation services associations are seen as key to the operations and maintenance of rural water and sanitation facilities. In practice they have generally not been effective and there is a lot of turnover, due to insufficient capacity and financial resources. It appears that well-organized and trained people may assume the management, operation and maintenance of rural facilities, but to ensure sustainability there needs to be provision for training, a contractual arrangement of accountability, and compensation. Behavioral change for improved water and sanitation-related hygiene requires ongoing engagement with the community, and collaboration with health and education sectors. The effort to change and sustain hygiene-related behavior needs to go much beyond sporadic visits to communities by extension staff during the project. It is important to reinforce the messages after the project; doing this requires a multi-sectoral approach that includes not only the health and education sectors but also the private sector, to the extent possible. Continuous training of frontline workers and delivery of such training through local governments appears to be key to this effort.
P065263 | Colombia Earthquake Recovery Project | Latin America and Caribbean | Colombia | IBRD |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2000 | 2004 | 2003 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/419341475079063441/text/000020051-20140607174134.txt | http://documents.worldbank.org/curated/en/419341475079063441/pdf/000020051-20140607174134.pdf | A decentralized structure for disaster management can be effective if the project implementation unit works directly with local implementing entities, such as popular NGOs, which help the project connect with the community. It created strong local ownership which contributes to sustainability, and helped the project to proceed quickly .The PIU's direct connection to the President and other high level decision-makers contributed to effective implementation by avoiding delays. The technical requirements for NGOs should be clearly specified in TORs, and NGOs' ability to meet those standards should be assessed as part of the selection process.Having a single implementing agency, such as FOREC, mediate between home buyers and builders was a cost effective way of providing housing.Including renters in the housing subsidy program was an effective way of preventing a homeless/squatting problem and helped to integrate poorer families into the fabric of society.Training on procurement and related guidelines should be conducted as soon as possible in the project cycle.
P065270 | Post-Accession Rural Support Project | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2012 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/909771475093171918/text/000012394-20150409075949.txt | http://documents.worldbank.org/curated/en/909771475093171918/pdf/000012394-20150409075949.pdf | The ICR offers five lessons and the most relevant are summarized below:Bundling unrelated objectives into a single project presents severe implementation challenges. The most significant challenge under such an arrangement is ensuring that project management staff in the PIU have an adequate range of experience and skills. In this project, the lack of such integration led to a fragmentation of project management and the loss of focus on outcomes for one of the objectives. Poverty and unemployment are often at the root of social exclusion. An operation to tackle social inclusion in a comprehensive way, depending on country circumstances, should also include a component specifically targeting employment creation.Consider using independent interlocutors to ensure CDD implementation complements and fosters partnership with, rather than by-pass, local and regional government. This project utilized regional consultants that were embedded in local government offices and able to work effectively with local authorities and regional social policy personnel.
P065301 | ECONOMIC MANAGEMENT CAPACITY BUILDING PROJECT | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2000 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/764031474853802197/text/000020051-20140619085716.txt | http://documents.worldbank.org/curated/en/764031474853802197/pdf/000020051-20140619085716.pdf | These lessons are in broad alignment with those mentioned in the ICR:1. The absence of a robust results-based framework with measurable (and quantified) indicators linked to project objectives and components will impair M&E and complicate findings on the achievement of outcomes. 2. Lack of harmonization of donor procedures regarding disbursement requirements will cause delays and unduly burden the implementing agency. The latter will be able to deliver only when it is sufficiently staffed and equipped. An effective steering committee is needed to complement the project unit.3. The effects of training can only be observed when measured against indicators of success. In the absence of these, the measurement of increased capacity is problematic.
P065351 | Hard Coal Sector Adjustment Loan (SECAL) 2 | Europe and Central Asia | Poland | IBRD |  | Infrastructure | Energy & Extractives | IBRD | DPF | 2002 | 2002 | 2003 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/273351474506736020/text/000020051-20140607161658.txt | http://documents.worldbank.org/curated/en/273351474506736020/pdf/000020051-20140607161658.pdf | An extensive dialogue between the government and the trade unions is an important factor in employment restructuring and mine closure efforts;The Bank can play an important role in bringing together key stakeholders to focus on important and contentious issues such as privatization; andA Sectoral Adjustment Loan is an appropriate instrument for supporting comprehensive sector reform.
P065372 | Social Action Fund Project | Eastern and Southern Africa | Tanzania | IDA |  | Human Development | Social Protection & Jobs | IDA | IPF | 2001 | 2005 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/564501475077016118/text/000020051-20140615094836.txt | http://documents.worldbank.org/curated/en/564501475077016118/pdf/000020051-20140615094836.pdf | A strong information, education, and communication component helps to improve accountability and contributes to improved governance, a key to community empowerment.Community-driven development projects, which involve many actors in implementation, are facilitated by having norms and standards for community-level investments.Sustainability can be enhanced by avoiding supply-driven targets, instead giving local governments the responsibility to work with communities to identify priorities.